- Exhibit Reference: Prepared Direct Testimony of Joel Mumford and Todd Van De Putte dated September 18, 2012

QUESTION 1:

In addition to providing detailed reasons (referencing Q 4 of DRA-OCE-2) why SoCalGas released the 1st contractor, could you please provide detailed reasons why the 2nd contractor Ensign was hired?

RESPONSE 1:

The 2nd Directional Drilling Contractor was not Ensign, it was Baker Hughes-INTEQ.  Baker Hughes-INTEQ was hired because the directional drilling tool proprietary design was different than that of the Sperry rotary steerable tool. SoCalGas felt that after initial experience with the Sperry-Halliburton GEOPilot rotary steerable tools and discovering the difficult drilling conditions in the WEZU C2C well, although initially the GEOPilot rotary steerable tools performed well, it became apparent that the GEOPilot tool didn’t have sufficient capability to build angle at a higher rate when difficult well course correction scenarios occurred at the Honor Rancho Field.  After comparing the rotary steerable tools specifications for both contractors, it was determined that the Baker Hughes-INTEQ Autotrak tools were projected to have the capability of a higher build rate, should it be needed.  That additional capability was an important adjustment in tool selection in the event that SoCalGas encountered continued difficult drilling conditions in the other wells during the project like what was encountered during the drilling of WEZU C2C.

QUESTION 2:

Was the second contractor Ensign among the first people who made a bid for the job originally?

RESPONSE 2:

Ensign is not a directional drilling contractor.  Baker Hughes-INTEQ did originally bid for the work.

QUESTION 3:

Why wasn’t the 2nd contractor Ensign selected first?

RESPONSE 3:

Ensign is not a directional drilling contractor.  Baker Hughes-INTEQ was not selected initially due to their limited availability, pricing, and their original lack of commitment to providing locally experienced personnel for the project.  SoCalGas felt that Halliburton’s initial commitment to providing a highly experienced Senior Directional Driller who had 20+yrs of directional drilling experience and had drilled wells previously at the Honor Rancho Field was an important selection criteria.  Baker Hughes-INTEQ did not initially commit to providing that level of experienced personnel due to their high workload and manpower shortage at that time.

QUESTION 4:

Whose decision was it to fire the 1st contractor, Halliburton?

RESPONSE 4:

It was a SoCalGas Storage Engineering management team decision.

QUESTION 5:

Who hired the new contractor?

RESPONSE 5:

The SoCalGas Storage Engineering management team.

QUESTION 6:

Please provide a copy of the Declaration of Jim Strader, dated April 6, 2010 provided in A09-07-014, giving the methodology used to arrive at the cost estimates for the wells.

RESPONSE 6:

Please see Attachment 1 to the attached April 6, 2010 SoCalGas motion.

QUESTION 7:

Please explain why tools either failed or got lost in the drilling of Liquid Production Wells Nos.1 & 2?

RESPONSE 7:

The drilling difficulties experienced during the drilling of WEZU C2C were primarily related to the ability of the directional drilling tools to steer the bit along the planned directional well path in the lower section of the wellbore.  The encountered geologic formations in the well made it difficult for the directional drilling tools to maintain the planned course and the stresses placed on the directional tools while attempting to steer and maintain the well course caused the drilling tool mechanical failures.   In the case of WEZU C7, there were no difficulties in maintaining the planned directional well course with the directional drilling tools. However, in the WEZU C7 well, the lower section of the wellbore and the geologic formation in that section of the wellbore became mechanically unstable over time, thus causing wellbore sloughing and the hole began to cave in.  In this instance, bottomhole assemblies became stuck in the wellbore during the wellbore cleanout operations because of the wellbore sloughing, and the drilling tools were lost in the wellbore.

QUESTION 8:

It appears the problems encountered by the 1st contractor in Liquid Production Well #1: WEZU C2C is similar to those encountered by the 2nd Contractor in Liquid Production Well #2: WEZU C7. Is this right?

RESPONSE 8:

That is not correct.  The problems encountered during the drilling of WEZU C7 were related to formation sloughing and instability.

QUESTION 9:

How much were the cost of the three various drilling assemblies lost in Liquid Production Well #2: WEZU C7?

RESPONSE 9:

- Total Baker Hughes-INTEQ Lost-In-Hole Deductible Paid Charges: $295,761

- Total Lost-In-Hole Other Vendor Replacement Charges

- (Reamer, Collars, drill pipe, etc.):						 $50,757

- Three drilling assemblies Total Lost In Hole Total Charges: 		 $346,518

The balance of the remaining tool charges for the WEZU C7 well were related to rotary steerable tool repairs, drill pipe re-hardbanding, etc. which are billed by the vendors after the well drilling operations are completed and these charges would not appear in the daily cost estimate reports.

QUESTION 10:

How was the cost handled?

RESPONSE 10:

Lost-In-Hole Limited Liability Insurance was taken out by SoCalGas and a deductible paid based on the value of the lost tools. This is an optional insurance provided by most directional drilling contractors in the oil and gas industry.  The referenced $50,757 in additional costs was charged to the project.

QUESTION 11:

Was an insurance claim filed by any party (SoCal Gas, Halliburton and Ensign) for the lost and failed tools?

RESPONSE 11:

Ensign is not a directional drilling contractor, Baker Hughes-INTEQ was the second directional drilling contractor.  As discussed in Response 10 above, SoCalGas procured Lost-In–Hole insurance which covered their mud motors, rotary steerable tools and their miscellaneous bottomhole assembly components. SoCalGas does not know if Halliburton or Baker Hughes-INTEQ had their own insurance covering these tools.

QUESTION 12:

Since SoCalGas, Halliburton and Ensign have liability insurance, why are the costs of lost tools not covered by insurance?

RESPONSE 12:

Please see Responses 10 and 11 above.

QUESTION 13:

Furthermore, in reference to Section 15.0 (a) of the contract agreement between SoCalGas and the contractors, should there still be cost sharing for failed and lost tools between SoCalGas and the contractors?

RESPONSE 13:

The indemnification provisions of Section 15 do not apply to failed/lost tools and equipment.  Please see Section 16.7 of the agreement (“Downhole Tools/Equipment”) that specifically supersedes Section 15 with respect to these items.

QUESTION 14:

Were any of the lost tools retrieved?

RESPONSE 14:

Despite diligent efforts to recover the lost tools, which is a condition of the Lost in Hole Insurance, the tools could not be retrieved.

QUESTION 15:

What process was used to select the bad tools used by both contractors?

RESPONSE 15:

The directional drilling tools used by both directional drilling contractors were not “bad” tools.  It is relatively common to lose drilling tools in wells as part of the normal drilling process, which is one reason drilling is expensive and Lost-In-Hole insurance is a standard (and relatively expensive) offering in the drilling industry.  The directional tools used were selected based on the recommendation of the contractors and their numerous years of drilling experience and local knowledge of drilling 100s of wells throughout California, in addition to their worldwide directional drilling expertise.  SoCalGas agreed with these contractor recommendations based on our local knowledge as well as the directional drilling contractors knowledge of the drilling conditions in the Honor Rancho Storage Field.

QUESTION 16:

What process was used to select the good tools used by both contractors?

RESPONSE 16:

Again, there were no “good tools” or “bad tools.”  Please see our response to Question 15 for an explanation of the process we used to select all of the tools we used.

QUESTION 17:

What kind of incentives did you give the contractors to complete the project within scheduled time?

RESPONSE 17:

As is typical in the industry, the contract was on a time-and-material basis. The incentive for the contractors to perform well is the potential to get future work from SoCalGas, in addition to the effect on their reputation within the relatively small California oil and gas drilling industry and its effect on their ability to get future work from other operators.

QUESTION 18:

How much control did you exact over this and describe how you exercised this control?

RESPONSE 18:

SoCalGas managed the contractors via a 24/7 on-site wellsite supervisor, in addition to SoCalGas personnel being available 24/7 during all drilling operations.

QUESTION 19:

Did you have intermediate milestones or was your contract focused on the end of the job goals?

RESPONSE 19:

We did not have contractual “intermediate milestones.”  Drilling wells are not typically managed like a surface facilities or a pipeline construction contract.  However, there were project phases with expected completion durations planned for each well drilled for the project.

QUESTION 20:

In A09-07-014, Appendix A, there were alternative well sites in the event a chosen drill site is no longer viable possibly due to discovery of poor formation thickness, rock type or permeability, did SoCal Gas and the contractors explore this alternatives, given the difficulties encountered during the well drilling?

RESPONSE 20:

The alternative well sites were not needed to achieve the geologic target objectives.  All four of the wells drilled 2 brine disposal and 2 liquid production wells reached their expected geologic objectives via the planned well locations and directional well plans. If other alternative well sites had been selected it would have changed the surface facility plan/design at a significant increase in cost to the project, including surface facility construction delays and it would not have ensured an improved result given the geologic target objective.

QUESTION 21:

Was a geological survey done before the commencement of drilling?

RESPONSE 21:

Geologic studies of the Honor Rancho field were first performed by the oil company that discovered the field, and these studies were updated by SoCalGas when we took over the field.  SoCalGas has a working geologic model of the Honor Rancho field which is based on historical and current geologic data, and is updated whenever new data is available - such as from new wells. The most recent update of the Honor Rancho geologic model was performed by Dr. Thom Davis, in which he built a 3 dimensional computer based geologic model. Dr. Davis is well known for his work in petroleum geology as well as having worked for the USGS and the Southern California Earthquake Center in furthering understanding of fault systems in California and how earthquakes are generated. See his website http://www.thomasldavisgeologist.com.  This model has been successfully utilized in the past to select/target and drill wells in the field.  This geologic model for the Honor Rancho Storage Field proved to be accurate and successful in targeting and drilling all 4 of the required wells for this project, as all the wells reached their objectives and at the anticipated targeted depths.

QUESTION 22:

Did the geological survey anticipate the problems the 1st and 2nd contractors experienced during the drilling of these wells?

RESPONSE 22:

See response to OCE-03-21.  In addition, the geology of the Honor Rancho Field is complex and as such can be difficult to predict drilling problems.  Well drilling is an uncertain activity that can involve no problems at all, problems like the ones we encountered that are surmountable but increase costs, or even insurmountable problems that result in unusable/unproductive wells that must be abandoned or redrilled.  Even with advanced technologies and a mature, proved field/formation it is impossible to predict drilling problems at depth.  This situation is exacerbated in the Honor Rancho Field because the formation is not consistent across the field. Two horizontal wells had previously been drilled in different parts of the Honor Rancho field with relatively little drilling difficulty, and so it was our initial hope that the new wells would not pose any unusual difficulty.

QUESTION 23:

At what point were you aware of the over-runs and what steps did you take to mitigate it?

RESPONSE 23:

The cost overruns occurred on a well-by-well basis.  The estimated well costs were recorded for each well on a daily basis by our drilling project management software.  SoCalGas monitored those estimated costs on a daily basis and made daily decisions in order to mitigate those costs.  SoCalGas monitored the cost of each phase of a given well and the time taken to complete each phase.  During a well drilling operation drilling difficulties are not uncommon, but unless you drill the well to the objective target depth that well has no value and would simply be a sunk cost.  A well drilling operation is at the mercy of the drilled formations and there are only limited opportunities to mitigate costs during a drilling operation.  As the drilling operation is a time-and-material operation, the main driver to reduce the cost is by reducing the amount of time required to drill the well.  For example, if the drilling rate slows down due to an unexpected formation change, the drill bit would be changed to a different design in order to increase the drill rate through that given formation and as such reduce the time to complete the well.  The Rotary Steerable directional drilling systems are another example of a cost mitigation measure which is designed to drill directional wells faster and more accurately, thus requiring less total rig time on a given well, thus reducing the overall time and cost to drill the well.  SoCalGas closely monitored the well drilling operation and made every reasonable attempt to improve the efficiency of the drilling process.

QUESTION 24:

In instances where projects were not completed within scheduled time, did the contractors in each case do a written request for an extension of time, in compliance with your contract?

RESPONSE 24:

The contracts were based on a time and dollar value, not on a well-by-well basis.  As the project progressed, if the project was going to exceed the original time and/or dollar value estimates the contracts were extended as required.