SDGE Residential Therm Kits

Prepared for

The Management of San Diego Gas and Electric

Prepared by

ASW Engineering Management

Date:

November 12, 2008

Abbreviations and Acronyms

| SDGE | San Diego Gas and Electric |
| --- | --- |
| SH | Showerhead |
| DCW | Domestic Cold Water – The city water temperature entering a residence is normally between 50°F to 56°F |
| DHW | Domestic Hot Water |
| WH | Water heating is a thermodynamic process using an energy source to heat water above its initial temperature. Typical domestic uses of hot water are for cooking, cleaning, bathing, and space heating. |
| DWH | Domestic Water Heater - Usually cylindrical tank type ranging from 20 to 100 U.S. gallons of storage |
| EEK | Energy Efficiency Kit – normally contains a low-flow showerhead and three faucet aerators for bathroom lavatories and kitchen sinks |
| GPM | Gallons per Minute |
| Psi | Pounds per square each |

Table of Contents

Introduction 	  1

Objective 	 1

Instrumentation 	  1

Methodology 	  2

Data Submittal 	  3

Proposed Work Schedule 	  4

Project Implementation Budget 	  5

Consulting Fee 	 6

Appendix “A” Filed Data Collection Form 	  7

Introduction

The management of SDGE requested that ASW Engineering Management collect domestic hot water usage data on showerheads, lavatories and kitchen sinks for 200 residences in their service territory.

Towards the stated goal, this document describes the proposed water measuring protocols and associated budget.

Objective

The main objective of ASW is to gather sufficient data of showerheads and aerators at each residence and submit the findings to SDGE for future analysis and reporting.

Instrumentation

Figure-1 shows the Hedland flow meter that will be used to measure the DCW and DHW flow of the showerheads and associated water pressures.

Figure-1

To measure the GPM of lavatories and kitchen sinks, ASW’s auditors will use a flow meter bag from Niagara Conservation.

Methodology

To accomplish the objective, ASW proposes to perform the following major tasks:

- SDGE will provide ASW with names, addresses and phone numbers of SDGE customers sorted by county and zip code

- SDGE will mail customers letters of introduction to inform customers they will be receiving a call from ASW regarding installation of the kits

- ASW schedules appointments at the customers’ convenience

- Upon arrival for the installation, ASW will interview the customer to attain the following information:

  - Number of people in household

  - Number of showers, kitchen sinks and bath sinks

  - Number of showers per day per shower

- Data will be collected on the primary shower:

  - Showers per week

  - Rated flow (GPM) identified on existing showerhead

  - Length of shower (min)

- Showerhead measurements will be taken with the Hedland flow/pressure gauge before the installation of the new shower head to establish a baseline and after the installation of the low flow showerhead

  - Install the gauge with the existing showerhead and obtain the following       measurements at full on hot, full on cold, full on mixed

    - Water temperature

    - GPM

    - Flowing pressure

    - Static pressure - full on both

  - Adjust mixed temperature to achieve 105 degrees and record same data as above

    - If full on mixed temp is above 105, reduce the hot water

    - If full on temp is below 105, reduce the cold water

- Install the low flow showerhead

  - Install the gauge with the new showerhead and obtain the following measurements at full on hot, full on cold, full on mixed

    - Water temperature

    - GPM

    - Flowing pressure

    - Static pressure - full on both

  - Adjust mix temperature to achieve 105 degrees and record same data as with existing showerhead

    - If full on mixed temp is above 105, reduce the hot water

    - If full on temp is below 105, reduce the cold water

- Bathroom sink - data will be collected on one bathroom sink, however, aerators will be installed on two bathroom sinks

    - Identify rated flow (GPM) from existing aerator

  - Measure flow w/bag - before and after installation of aerator

  - Measure GPM using bag - full on hot, full on cold, full on both

  - Temperature - measure at mixed temperature then adjust to 105 degrees

    - Record how long the water runs each day (min/day)

- Data will be collected on the kitchen sink - Same procedures as bathroom sinks

- Surveyor will record data from DHW heater, if accessible:

  - Manufacturer

  - Model

  - Age

  - Type (storage/instantaneous)

  - Storage - Gallons

  - Temperature setting of water heater

  - Temperature at tap closest to WH

  - Efficiency, if available

  - Source fuel

  - Burner capacity - BTUH if gas, kW if electric

- Surveyor will enter the collected data into the Project Excel database

- The Excel database will be reviewed for consistency

Comment –

The management of SDGE requested that ASW perform the audits in two phases: Phase-1 will include 25 sites; Phase-2 will include 175 sites.  The main reason for Phase-1 is that management will have the opportunity to review the data being collected and make revisions if deemed necessary.

Data Submittal

ASW will summarize all the collected data in an Excel workbook and email it to SDGE for their analysis and final report.  See Appendix “A” (page-7) for a preliminary Field Data Collection Form.

Proposed Work Schedule

Figure-2 shows the proposed work schedule.

Figure-2 Proposed Work Schedule

| TASKS# Week Ending  | 11/15 | 11/22 | 11/29 | 12/6 | 12/13 | 12/20 | 12/27 | 1/3/09 | 1/10 | 1/17 | 1/24 | 1/31/09 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Lead Time – |  |  |  |  |  |  |  |  |  |  |  |  |
| Planning Phase |  |  |  |  |  |  |  |  |  |  |  |  |
| SDGE Provides Site Address to ASW |  |  |  |  |  |  |  |  |  |  |  |  |
| SDGE Sends Letters to its Customers |  |  |  |  |  |  |  |  |  |  |  |  |
| ASW Develops Data Collection Form |  |  |  |  |  |  |  |  |  |  |  |  |
| ASW Develops Project Database |  |  |  |  |  |  |  |  |  |  |  |  |
| Audit Scheduling |  |  |  |  |  |  |  |  |  |  |  |  |
| Pilot Audit – 25 Sites |  |  |  |  |  |  |  |  |  |  |  |  |
| SDGE Feedback |  |  |  |  |  |  |  |  |  |  |  |  |
| Audits – 175 Sites |  |  |  |  |  |  |  |  |  |  |  |  |
| ASW Delivers Data to SDGE |  |  |  |  |  |  |  |  |  |  |  |  |

Project Implementation Budget

Figure-3 shows the estimated budget breakdown to collect the previously stated data.

Figure-3 Project Implementation Budget

Consulting Fee

ASW will be compensated on a time-and-materials basis within the established consulting budget of $ 74,927 (Seventy Four Thousand Nine Hundred and Twenty Seven Dollars).  ASW can not exceed this budget without advance written authorization from the management of SDGE.

The compensation for labor will be made at the following rates throughout the duration of this agreement.

| CLASSIFICATION | HOURLY RATE |
| --- | --- |
| Principal | $ 170 |
| Senior Engineer | $ 150 |
| Staff Engineer | $ 125 |
| Auditor | $ 75 |
| Administration Support | $ 45 |

Considerations

- The above rates do not include the direct costs; such as mileage, parking fees, etc.  Direct costs will be passed through without a markup.

- ASW will invoice on a monthly basis for work completed during the previous month.

Appendix A - Field Data Collection Form