## Q1
b) Circuit Number | a) c) GHID/ID number Undergrounded | e) Circuit Voltage | f) Project Start Date | g) Energization Date (See Note 1) | g) Project Completion Date (See Note 1) | h)Number of months to complete the project planning | i) Number of Months to complete the design | j) Number of months to complete the permitting | k) Number of months to complete the construction | m) UG Circuit Miles | n) Trench Miles | o) Total Cost - attributed to SDG&E's electric facilities (See Note 2) | p) Total Cost - attributed to non-electric utilities | q) Rule 20? | r) WMP? | s) Post-Wildfire Rebuilding? | t) Joint Trench with Comm? | u) Shared Trench with Gas? | v) Expected Useful Life (See Note 3)
C1001 | C1001 HFTD PSPS | 12kV | No Record | 2020-08-20 | TBD | No Record | No Record | No Record | No Record | 0.34 | 0.34 | No Record | Not Applicable | N | Y | N | N | N | 40 Years
C1021 | C1021 Quick Win | 12kV | 2019-12-02 | 2020-10-24 | TBD | 1 | 5 | 2 | 4.8 | 0.31 | 0.17 | 1312974.12 | Not Applicable | N | Y | N | N | N | 40 Years
C1030 | C1030 Ph.1 | 12kV | 2019-09-03 | 2021-02-25 | TBD | 1 | 9.8 | 3 | 7.2 | 6.63 | 5.49 | 9269697.23 | Not Applicable | N | Y | N | N | N | 40 Years
C1030 | C1030 Ph.2A | 12kV | 2019-09-21 | 2021-09-01 | TBD | 1 | 11.5 | 4 | 11.2 | 7.5 | 6.31 | 12331069.42 | Not Applicable | N | Y | N | N | N | 40 Years
C1030 | C1030 Ph.2B | 12kV | 2019-09-21 | 2021-06-23 | TBD | 1 | 11.5 | Not Applicable | 8.9 | 5.07 | 4.79 | 5502257.5 | Not Applicable | N | Y | N | N | N | 40 Years
C1030 | C1030 DUG Ph.1 | 12kV | 2019-09-03 | 2021-07-21 | TBD | 1 | 12.6 | 6 | 9.3 | 3.88 | 2.89 | 9440685.19 | Not Applicable | N | Y | N | N | N | 40 Years
C1030 | C1030 DUG Ph.2 | 12kV | 2020-12-17 | 2021-10-09 | TBD | 0.5 | 4.8 | 2 | 4.6 | 2.596 | 2.35 | 5534595.43 | Not Applicable | N | Y | N | N | N | 40 Years
C221 | C221 Ph.1 | 12kV | No Record | 2020-09-20 | 2021-04-27 | No Record | No Record | No Record | No Record | 0.53 | 0.34 | 1335406.98 | Not Applicable | N | Y | N | N | N | 40 Years
C221 | C221 Ph.2 | 12kV | 2019-08-19 | 2020-09-03 | 2021-04-27 | 1 | 8 | 3 | 4 | 0.91 | 0.83 | 1552300.01 | Not Applicable | N | Y | N | N | N | 40 Years
C221 | C221 DUG Ph.2 | 12kV | 2020-01-15 | 2021-12-07 | TBD | 3 | 15.7 | 11 | 4 | 0.41 | 0.41 | 2200199.95 | Not Applicable | N | Y | N | N | N | 40 Years
C357 | C357 Quick Win Job1 and 2 | 12kV | 2020-02-01 | 2020-09-04 | TBD | 0.5 | 3 | No Record | 3.5 | 0.83 | 0.83 | 3501069.11 | 107227.68 | N | Y | N | Y | N | 40 Years
C445 | C445 DUG | 12kV | 2020-03-05 | 2022-03-20 | TBD | 1.5 | 17.9 | 13.5 | 5 | 3.08 | 2.35 | 6034572.02 | Not Applicable | N | Y | N | N | N | 40 Years
C448 | C448 DUG | 12kV | 2020-03-05 | 2021-08-13 | TBD | 2 | 10 | 3 | 5.4 | 1.25 | 1.13 | 3344982 | Not Applicable | N | Y | N | N | N | 40 Years
C448 | C448 Microgrid Partnership | 12kV | 2020-06-22 | 2021-09-30 | TBD | 2 | 10.3 | No Record | 3.2 | 0.5 | 0.5 | No Record | Not Applicable | N | Y | N | N | N | 40 Years
C448 | C448 Microgid Only | 12kV | 2020-06-22 | 2021-09-30 | TBD | 2 | 9.5 | No Record | 4 | 0.92 | 0.92 | 566819 | Not Applicable | N | Y | N | N | N | 40 Years
C75 | C75 DUG Ph.1 | 12kV | 2020-04-01 | 2020-12-15 | TBD | 1 | 4.5 | 4 | 3 | 6.83 | 0.15 | 3228122.36 | Not Applicable | N | Y | N | N | N | 40 Years
C754 | C754 Quick Win | 12kV | No Record | 2020-05-05 | 2020-07-15 | No Record | No Record | No Record | No Record | 0.3 | 0.3 | 402786.43 | Not Applicable | N | Y | N | N | N | 40 Years
C79 | C79 DUG | 12kV | 2019-11-11 | 2021-09-10 | TBD | 1 | 13 | 6 | 8.2 | 3.38 | 3.38 | 9715718.23 | Not Applicable | N | Y | N | N | N | 40 Years
Note 1. Project listed are not completed due to pending final as-built digitization and accounting closeout, with the exception of C221 Ph.1, C221 Ph.2, and C754 Quick Win. Project energization dates are provided as reference.
Note 2. The total cost is subject to change until final as-built digitization and accounting closeout is completed, with the exception of C221 Ph.1, C221 Ph.2, and C754 Quick Win.
Note 3. In general, underground cable has a useful life of 40 years. However, many variables such as conduit, connections, field conditions, surrounding environment, and etc. will affect useful life of Underground Distribution System.

## Q6d
Strategic Undergrounding Unit Cost
*Based on current actuals to date + remaining forecast
|  | Cost/Mile | Notes
| Civil | 1600000 | Based on 2020 and 2021 projects.
| Electrical | 200000 | Based on 2020 and 2021 projects.
| Material | 120000 | Based on 2020 and 2021 projects.
| Construction | 1920000
| Engineering & Design | 350000
| Project Support | 122600 | Based on 2021 Forecasted Spend
| Internal Labor | 26000 | Based on 2021 Forecasted Spend
| Total Directs | 2418600