## 2020 Actuals Q4-Q5
ESH Overhead System Hardening Programs
2020 Actuals by Program
(Capital Expenditures, Direct Costs $ Only)
CAPEX ($M)
Category | Bare Conductor Hardening | Covered Conductor Hardening | Total ESH OH System Hardening
Engineering/Design | 55.356 | 0.67853 | 56.0345
Project Management | 28.3577 | 0.33777 | 28.6955
Construction | 43.97 | 0.73779 | 44.7078
Material | 10.6943 | 0.043601 | 10.7379
Total Direct CAPEX $ | 138.378 | 1.7977 | 140.1757
Check WMP Filing:
WMP Filing | 138.378 | 1.7977
Difference | 0 | 0

## CalPA DR4-Q4 CC
ESH OH Covered Conductor 2021 - Budget by Category
|  |  | Line Energized Goal | Miles
| Miles |  | 2020 | 1
Engineering/Design/Project Management | 80 |  | 2021 | 20
Construction | 20 |  | 2022 | 60
Engineering/Design/Project Management | 430695.45 | 29.54%
Construction | 927218.2 | 63.6%
Material | 100000 | 6.859%
Direct Cost | 1457913.65 | 100%
| Miles | Direct - $'s
Engineering/Design/Project Management | 80 | 34455636
Construction | 20 | 18544364
Material | 20 | 2000000
Total Direct Cost |  | 55000000
| Check WMP Filing | 55000000
| Difference | 0
ESH OH Covered Conductor 2022 - Budget by Category
Miles
Engineering/Design/Project Management | 80
Construction | 60
Engineering/Design/Project Management | 430297.7485 | 29.54%
Construction | 933119.6687 | 64.06%
Material | 93150 | 6.395%
Direct Cost | 1456567.4172 | 100%
| Miles | Direct - $'s
Engineering/Design/Project Management | 80 | 34423819.8761
Construction | 60 | 55987180.1239
Material | 60 | 5589000
Total Direct Cost |  | 96000000
| Check WMP Filing | 96000000
| Difference | 0

## CalPA DR4-Q5 Bare
ESH OH Bare Conductor Hardening 2021 - Budget by Category
|  |  | Line Energized Goal | Miles
| Miles |  | 2020 | 102
Engineering/Design/Project Management | 7 |  | 2021 | 100
Construction | 100 |  | 2022 | 5
Engineering/Design/Project Management | 385991.6089 | 30.18%
Construction | 812980.5874 | 63.57%
Material | 80000 | 6.255%
Direct Cost | 1278972.1963 | 100%
| Miles | Direct - $'s
Engineering/Design/Project Management | 7 | 2701941.2621
Construction | 100 | 81298058.74
Material | 100 | 8000000
Total Direct Cost |  | 92000000.0021
| Check WMP Filing | 92000000
| Difference | 0
ESH OH Bare Conductor Hardening 2022 - Budget by Category
Miles
Engineering/Design/Project Management | 1
Construction | 5
Engineering/Design/Project Management | 397856.1121 | 30.18%
Construction | 839428.7776 | 63.68%
Material | 81000 | 6.144%
Direct Cost | 1318284.8897 | 100%
| Miles | Direct - $'s
Engineering/Design/Project Management | 1 | 397856.1121
Construction | 5 | 4197143.8879
Material | 5 | 405000
Total Direct Cost |  | 5000000
| Check WMP Filing | 5000000
| Difference | 0