151612667037 | 151697337037 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2022-07-27 | 2022-07-27 | 2022-07-27 |  | 2022-08-19 | Underground | R15/16- Reloc | 2022-08-01 | 1 |  | 4 | 15 | 18 | 2022 | 2022 | R15/16
151653092565 | 151642772565 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-21 |  | 2022-11-21 | 2023-02-22 | 2023-03-17 | Underground | R15/16- Reloc | 2023-02-22 |  |  | 68 | 18 | 85 | 2022 | 2023 | R15/16
151629577350 | 151604567350 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-09-09 | 2022-09-14 | 2022-10-17 |  | 2023-04-03 | Underground | R15/16- Reloc | 2023-01-18 | 4 | 24 | 68 | 54 | 147 | 2022 | 2023 | R15/16
151674254552 | 151625044552 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-20 | 2022-09-22 | 2023-03-03 |  | 2022-12-22 | Overhead | R15/16 | 2023-03-08 | 3 | 117 | 4 |  | 68 | 2022 | 2022 | R15/16
151644971443 | 151613511443 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-31 | 2023-08-31 | 2023-08-31 | 2023-10-08 | 2023-10-11 | Underground | R15/16- Reloc | 2023-10-08 | 1 |  | 27 | 3 | 30 | 2023 | 2023 | R15/16
151682291509 | 151609191509 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-30 | 2023-09-01 | 2023-09-01 | 2023-09-21 | 2023-11-01 | Overhead | R15/16 | 2023-09-21 | 3 |  | 15 | 30 | 46 | 2023 | 2023 | R15/16
151693523459 | 151612093459 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-13 | 2022-09-13 | 2022-09-13 | 2022-11-22 | 2022-11-30 | Overhead | R15/16 | 2022-11-22 | 1 |  | 51 | 7 | 57 | 2022 | 2022 | R15/16
151698537833 | 151614997833 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-04 | 2022-08-04 | 2022-08-04 | 2022-10-18 | 2023-01-05 | Overhead | R15/16 | 2022-10-18 | 1 |  | 54 | 58 | 111 | 2022 | 2023 | R15/16
151652136143 | 151656906143 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Commercial | 2022-10-05 | 2022-10-05 | 2022-10-05 |  | 2022-10-23 | Underground | R15/16- Reloc | 2022-10-07 | 1 |  | 3 | 11 | 13 | 2022 | 2022 | R15/16
151639976036 | 151648336036 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-01 |  | 2022-10-05 | 2022-12-20 | 2022-12-06 | Overhead | R15/16 | 2022-12-20 |  |  | 55 |  | 47 | 2022 | 2022 | R15/16
151607005326 | 151613105326 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-07-16 | 2023-07-16 | 2023-07-16 | 2023-08-25 | 2023-09-11 | Underground | R15/16- Reloc | 2023-08-25 | 0 |  | 30 | 12 | 41 | 2023 | 2023 | R15/16
151658506536 | 151653116536 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-29 | 2022-11-29 | 2023-01-30 | 2023-01-19 | 2023-02-14 | Underground | R15/16- Reloc | 2023-01-19 | 1 | 45 |  | 19 | 56 | 2022 | 2023 | R15/16
151623924082 | 151624844082 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2023-09-08 | 2023-09-08 | 2023-09-29 | 2023-10-12 | 2023-11-07 | Underground | R15/16- Reloc | 2023-10-12 | 1 | 16 | 10 | 19 | 43 | 2023 | 2023 | R15/16
151616415335 | 151671775335 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-10-04 | 2023-10-04 | 2023-10-12 | 2023-10-17 | 2023-11-10 | Underground | R15/16- Reloc | 2023-10-17 | 1 | 7 | 4 | 19 | 28 | 2023 | 2023 | R15/16
151639026387 | 151658856387 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-07 | 2022-10-07 | 2022-10-07 |  | 2022-11-01 | Overhead | R15/16 | 2022-10-31 | 1 |  | 17 | 2 | 18 | 2022 | 2022 | R15/16
151676111237 | 151650081237 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-04 | 2023-08-04 | 2023-08-30 | 2023-09-28 | 2023-10-09 | Underground | R15/16- Reloc | 2023-09-28 | 1 | 19 | 22 | 8 | 47 | 2023 | 2023 | R15/16
151692775302 | 151648805302 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-27 | 2022-12-06 | 2023-01-30 | 2023-01-09 | 2023-06-09 | Underground | R15/16- Reloc | 2023-01-09 | 7 | 40 |  | 110 | 140 | 2022 | 2023 | R15/16
151626392340 | 151629972340 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-09-11 | 2023-09-11 | 2023-09-11 |  | 2023-12-26 | Underground | R15/16- Reloc |  | 1 |  |  |  | 77 | 2023 | 2023 | R15/16
151619773235 | 151648663235 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-09-21 | 2023-09-21 | 2023-09-21 | 2023-09-25 | 2023-10-24 | Overhead | R15/16 | 2023-09-25 | 1 |  | 3 | 22 | 24 | 2023 | 2023 | R15/16
151659878377 | 151689548377 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-24 | 2022-10-24 | 2022-10-27 | 2023-04-24 | 2023-06-12 | Underground | R15/16- Reloc | 2023-04-24 | 1 | 4 | 128 | 36 | 166 | 2022 | 2023 | R15/16
151684859076 | 151697069076 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-06 |  | 2022-11-02 | 2023-01-11 | 2023-04-11 | Overhead | R15/16 | 2023-01-11 |  |  | 51 | 65 | 156 | 2022 | 2023 | R15/16
151632549760 | 151615949760 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-07 | 2022-11-07 | 2022-11-07 | 2023-02-15 | 2023-02-25 | Overhead | R15/16 | 2023-02-15 | 1 |  | 73 | 8 | 80 | 2022 | 2023 | R15/16
151644080855 | 151675090855 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-31 | 2022-08-31 | 2022-08-31 | 2022-11-11 | 2023-01-23 | Underground | R15/16- Reloc | 2022-11-11 | 1 |  | 53 | 52 | 104 | 2022 | 2023 | R15/16
151617500997 | 151672870997 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-16 | 2023-08-28 | 2023-08-28 | 2023-09-18 | 2023-10-11 | Underground | R15/16- Reloc | 2023-09-18 | 9 |  | 16 | 18 | 41 | 2023 | 2023 | R15/16
151650012949 | 151627662949 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-10 | 2022-08-10 | 2022-09-07 | 2023-01-05 | 2023-01-05 | Underground | R15/16- Reloc | 2023-01-05 | 1 | 21 | 87 |  | 107 | 2022 | 2023 | R15/16
151665192627 | 151697202627 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-06 | 2022-09-06 | 2022-09-06 |  | 2023-08-14 | Overhead | R15/16 | 2023-05-03 | 1 |  | 172 | 74 | 245 | 2022 | 2023 | R15/16
151605405513 | 151618475513 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-07-19 | 2023-07-19 | 2023-07-19 | 2023-09-20 | 2023-10-17 | Overhead | R15/16 | 2023-09-20 | 1 |  | 46 | 20 | 65 | 2023 | 2023 | R15/16
151607738587 | 151629548587 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-10 | 2022-08-10 | 2022-08-10 | 2022-08-22 | 2022-09-27 | Overhead | R15/16 | 2022-08-22 | 1 |  | 9 | 27 | 35 | 2022 | 2022 | R15/16
151693108147 | 151619488147 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-06 | 2022-08-06 | 2022-08-06 | 2022-09-30 | 2022-10-03 | Underground | R15/16- Reloc | 2022-09-30 | 0 |  | 40 | 2 | 41 | 2022 | 2022 | R15/16
151630869201 | 151641029201 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-16 | 2022-08-16 | 2022-08-16 | 2022-12-20 | 2023-01-04 | Overhead | R15/16 | 2022-12-20 | 1 |  | 91 | 12 | 102 | 2022 | 2023 | R15/16
151697456103 | 151652316103 | SDG&E | UG NON RES NB BUDG 218 | Residential | 2022-10-04 | 2022-10-04 | 2022-10-05 | 2022-12-21 | 2023-10-31 | Underground | R15/16- Reloc | 2022-12-21 | 1 | 2 | 56 | 225 | 281 | 2022 | 2023 | R15/16
151601193861 | 151615343861 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-09-15 | 2022-09-15 | 2022-09-15 |  | 2022-10-23 | Underground | R15/16- Reloc | 2022-10-04 | 1 |  | 14 | 14 | 27 | 2022 | 2022 | R15/16
151695613941 | 151612663941 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-09-14 | 2022-09-16 | 2022-09-16 |  | 2023-01-10 | Underground | R15/16- Reloc | 2022-11-01 | 3 |  | 33 | 51 | 85 | 2022 | 2023 | R15/16
151625496878 | 151628516878 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-07-25 | 2023-08-01 | 2023-08-01 | 2023-10-26 | 2023-11-10 | Underground | R15/16- Reloc | 2023-10-26 | 6 |  | 63 | 12 | 79 | 2023 | 2023 | R15/16
151600145005 | 151633095005 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-23 | 2022-09-26 | 2022-09-26 | 2022-12-26 | 2022-12-29 | Overhead | R15/16 | 2022-12-26 | 2 |  | 66 | 4 | 70 | 2022 | 2022 | R15/16
151623166393 | 151628786393 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-07-26 | 2023-07-26 | 2023-07-26 | 2023-08-09 | 2023-09-14 | Overhead | R15/16 | 2023-08-09 | 1 |  | 11 | 27 | 37 | 2023 | 2023 | R15/16
151634515881 | 151665485881 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-09-29 | 2023-10-16 | 2023-10-16 | 2023-10-18 | 2023-11-10 | Overhead | R15/16 | 2023-10-18 | 12 |  | 3 | 18 | 31 | 2023 | 2023 | R15/16
151671270693 | 151671250693 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Commercial | 2022-08-30 | 2022-08-30 | 2022-08-30 | 2023-01-05 | 2023-01-05 | Underground | R15/16- Reloc | 2023-01-05 | 1 |  | 93 |  | 93 | 2022 | 2023 | R15/16
151673069992 | 151600019992 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-27 | 2022-11-09 | 2022-11-09 |  | 2023-09-27 | Overhead | R15/16 | 2023-06-20 | 10 |  | 160 | 72 | 240 | 2022 | 2023 | R15/16
151659695487 | 151658215487 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2022-08-24 | 2022-08-24 | 2022-09-30 |  | 2023-05-10 | Underground | R15/16- Reloc | 2023-02-15 | 1 | 28 | 99 | 61 | 186 | 2022 | 2023 | R15/16
151670068076 | 151691538076 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-24 | 2022-10-25 | 2022-10-25 | 2023-03-07 | 2023-03-24 | Overhead | R15/16 | 2023-03-07 | 2 |  | 96 | 14 | 110 | 2022 | 2023 | R15/16
151623326695 | 151626606695 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2022-09-20 | 2022-09-20 | 2022-10-11 | 2023-04-10 | 2023-04-11 | Underground | R15/16- Reloc | 2023-04-10 | 1 | 16 | 130 | 2 | 146 | 2022 | 2023 | R15/16
151653022560 | 151662832560 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-12-05 | 2022-12-06 | 2022-12-06 | 2023-02-15 | 2023-02-25 | Overhead | R15/16 | 2023-02-15 | 2 |  | 52 | 8 | 60 | 2022 | 2023 | R15/16
151637271809 | 151652441809 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-29 | 2022-11-29 | 2022-11-29 | 2023-03-07 | 2023-03-24 | Overhead | R15/16 | 2023-03-07 | 1 |  | 71 | 14 | 84 | 2022 | 2023 | R15/16
151604921258 | 151645181258 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-22 | 2022-11-22 | 2022-11-22 | 2023-01-08 | 2023-01-11 | Underground | R15/16- Reloc | 2023-01-08 | 1 |  | 34 | 3 | 37 | 2022 | 2023 | R15/16
151691662414 | 151635112414 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-09-25 | 2022-09-25 | 2022-12-05 |  | 2022-12-22 | Underground | R15/16- Reloc | 2022-12-20 | 0 | 51 | 12 | 3 | 64 | 2022 | 2022 | R15/16
151695024734 | 151673434734 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-10-04 | 2023-10-05 | 2023-10-05 | 2023-10-23 | 2023-11-29 | Overhead | R15/16 | 2023-10-23 | 2 |  | 13 | 28 | 41 | 2023 | 2023 | R15/16
151669189359 | 151642379359 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-17 | 2022-08-17 | 2022-08-17 |  | 2022-10-21 | Overhead | R15/16 | 2022-08-31 | 1 |  | 11 | 38 | 48 | 2022 | 2022 | R15/16
151607446369 | 151660646369 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-07 | 2022-10-07 | 2022-10-07 |  | 2023-03-16 | Overhead | R15/16 | 2023-02-03 | 1 |  | 86 | 30 | 115 | 2022 | 2023 | R15/16
151660074599 | 151659844599 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-09-27 | 2023-10-04 | 2023-10-04 | 2023-11-28 | 2023-12-08 | Overhead | R15/16 | 2023-11-28 | 6 |  | 40 | 9 | 53 | 2023 | 2023 | R15/16
151643991593 | 151632481593 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-15 | 2022-11-15 | 2022-11-29 | 2023-02-08 | 2023-09-12 | Underground | R15/16- Reloc | 2023-02-08 | 1 | 11 | 52 | 155 | 216 | 2022 | 2023 | R15/16
151672462800 | 151656772800 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-23 | 2022-09-06 | 2022-09-06 | 2023-01-05 | 2023-01-05 | Underground | R15/16- Reloc | 2023-01-05 | 11 |  | 88 |  | 98 | 2022 | 2023 | R15/16
151615016163 | 151657306163 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-06 | 2022-10-06 | 2022-10-06 | 2022-12-31 | 2023-01-06 | Overhead | R15/16 | 2022-12-31 | 1 |  | 62 | 5 | 67 | 2022 | 2023 | R15/16
151629904792 | 151634064792 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-09-23 |  | 2022-09-23 |  | 2022-12-13 | Underground | R15/16- Reloc | 2022-12-09 |  |  | 56 | 3 | 58 | 2022 | 2022 | R15/16
151659442828 | 151641572828 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-09-16 | 2023-09-16 | 2023-09-16 | 2023-11-01 | 2023-11-07 | Overhead | R15/16 | 2023-11-01 | 0 |  | 33 | 5 | 37 | 2023 | 2023 | R15/16
151675706560 | 151662726560 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-10 | 2022-10-10 | 2022-10-10 | 2022-12-01 | 2022-12-01 | Overhead | R15/16 | 2022-12-01 | 1 |  | 39 |  | 39 | 2022 | 2022 | R15/16
151657981566 | 151640351566 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-18 | 2022-11-28 | 2022-11-28 |  | 2023-03-01 | Overhead | R15/16 | 2023-02-10 | 7 |  | 55 | 14 | 74 | 2022 | 2023 | R15/16
151677952207 | 151600572207 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-24 | 2023-08-24 | 2023-09-11 | 2023-09-12 | 2023-12-11 | Overhead | R15/16 | 2023-09-12 | 1 | 13 | 2 | 65 | 78 | 2023 | 2023 | R15/16
151630804199 | 151669334199 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-12-08 | 2022-12-08 | 2023-01-30 | 2022-12-29 | 2023-08-09 | Underground | R15/16- Reloc | 2022-12-29 | 1 | 38 |  | 160 | 175 | 2022 | 2023 | R15/16
151656147507 | 151677507507 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-17 | 2022-10-18 | 2022-10-18 | 2023-01-30 | 2023-01-31 | Overhead | R15/16 | 2023-01-30 | 2 |  | 75 | 2 | 77 | 2022 | 2023 | R15/16
151699817922 | 151638657922 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-07-31 | 2023-08-09 | 2023-08-09 | 2023-08-22 | 2023-09-26 | Overhead | R15/16 | 2023-08-22 | 8 |  | 10 | 26 | 42 | 2023 | 2023 | R15/16
151619624593 | 151625544593 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-20 | 2022-09-22 | 2022-09-22 | 2023-01-18 | 2023-02-08 | Overhead | R15/16 | 2023-01-18 | 3 |  | 85 | 16 | 102 | 2022 | 2023 | R15/16
151609802335 | 151619302335 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-05 | 2022-08-05 | 2022-09-02 | 2023-08-07 | 2023-08-09 | Underground | R15/16- Reloc | 2023-08-07 | 1 | 21 | 242 | 3 | 264 | 2022 | 2023 | R15/16
151674458366 | 151697718366 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-26 | 2022-10-26 | 2022-10-26 | 2023-01-11 | 2023-01-28 | Overhead | R15/16 | 2023-01-11 | 1 |  | 56 | 13 | 68 | 2022 | 2023 | R15/16
151626616876 | 151628526876 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-07-25 | 2023-07-31 | 2023-08-01 | 2023-09-11 | 2023-09-20 | Underground | R15/16- Reloc | 2023-09-11 | 5 | 2 | 30 | 8 | 42 | 2023 | 2023 | R15/16
151619644157 | 151624944157 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-20 | 2022-09-20 | 2022-09-20 |  | 2023-01-10 | Overhead | R15/16 | 2022-11-17 | 1 |  | 43 | 39 | 81 | 2022 | 2023 | R15/16
151663549228 | 151697139228 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-10-17 | 2023-10-17 | 2023-11-09 | 2023-11-09 | 2023-12-28 | Underground | R15/16- Reloc | 2023-11-09 | 1 | 18 |  | 36 | 53 | 2023 | 2023 | R15/16
151671566414 | 151617046414 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Commercial | 2023-07-18 | 2023-07-19 | 2023-07-26 | 2023-08-03 | 2023-08-24 | Overhead | R15/16 | 2023-08-03 | 2 | 6 | 7 | 16 | 28 | 2023 | 2023 | R15/16
151649216025 | 151688286025 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-10-13 | 2023-10-13 | 2023-10-18 | 2023-11-06 | 2023-11-29 | Underground | R15/16- Reloc | 2023-11-06 | 1 | 4 | 14 | 18 | 34 | 2023 | 2023 | R15/16
151693463199 | 151623503199 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-09-07 | 2023-09-07 | 2023-09-21 | 2023-11-22 | 2023-11-29 | Overhead | R15/16 | 2023-11-22 | 1 | 11 | 45 | 6 | 60 | 2023 | 2023 | R15/16
151697424277 | 151658484277 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-24 | 2022-08-24 | 2022-09-20 | 2023-01-05 | 2023-01-05 | Underground | R15/16- Reloc | 2023-01-05 | 1 | 20 | 78 |  | 97 | 2022 | 2023 | R15/16
151621892899 | 151639802899 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-09-14 | 2023-09-14 | 2023-09-18 | 2023-11-22 | 2023-12-14 | Overhead | R15/16 | 2023-11-22 | 1 | 3 | 48 | 17 | 66 | 2023 | 2023 | R15/16
151630461140 | 151641991140 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-18 |  | 2022-11-18 | 2023-01-23 | 2023-01-24 | Overhead | R15/16 | 2023-01-23 |  |  | 47 | 2 | 48 | 2022 | 2023 | R15/16
151680858367 | 151698018367 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-26 | 2022-10-26 | 2022-10-26 | 2023-01-09 | 2023-01-13 | Overhead | R15/16 | 2023-01-09 | 1 |  | 54 | 5 | 58 | 2022 | 2023 | R15/16
151607696577 | 151625106577 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-07-22 | 2023-07-28 | 2023-07-28 | 2023-08-19 | 2023-08-22 | Underground | R15/16- Reloc | 2023-08-19 | 5 |  | 16 | 2 | 22 | 2023 | 2023 | R15/16
151677946803 | 151637056803 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-07-29 |  | 2023-07-29 | 2023-07-31 | 2023-10-20 | Overhead | R15/16 | 2023-07-31 |  |  | 1 | 60 | 60 | 2023 | 2023 | R15/16
151625399432 | 151645199432 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-18 | 2022-08-18 | 2022-08-18 | 2022-10-12 | 2023-01-05 | Overhead | R15/16 | 2022-10-12 | 1 |  | 40 | 62 | 101 | 2022 | 2023 | R15/16
151613905255 | 151641095255 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-28 | 2022-09-28 | 2022-09-28 | 2022-12-15 | 2022-12-20 | Overhead | R15/16 | 2022-12-15 | 1 |  | 57 | 4 | 60 | 2022 | 2022 | R15/16
151600298216 | 151670518216 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-15 | 2023-08-15 | 2023-08-15 | 2023-11-09 | 2023-12-15 | Overhead | R15/16 | 2023-11-09 | 1 |  | 63 | 27 | 89 | 2023 | 2023 | R15/16
151671756207 | 151626116207 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-07-24 |  | 2023-07-24 | 2023-08-28 | 2023-10-05 | Overhead | R15/16 | 2023-08-28 |  |  | 26 | 29 | 54 | 2023 | 2023 | R15/16
151609613638 | 151652103638 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-21 | 2022-08-31 | 2022-09-14 |  | 2023-02-14 | Underground | R15/16- Reloc | 2023-02-14 | 8 | 11 | 110 |  | 127 | 2022 | 2023 | R15/16
151653387064 | 151673287064 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-14 | 2022-10-14 | 2022-10-14 |  | 2022-12-15 | Underground | R15/16- Reloc | 2022-12-13 | 1 |  | 43 | 3 | 45 | 2022 | 2022 | R15/16
151635637668 | 151621657668 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Commercial | 2022-08-08 | 2022-08-08 | 2022-10-20 | 2022-12-08 | 2023-02-22 | Underground | R15/16- Reloc | 2022-12-08 | 1 | 54 | 36 | 55 | 143 | 2022 | 2023 | R15/16
151616004197 | 151625354197 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-20 | 2022-09-20 | 2022-09-20 | 2023-01-11 | 2023-01-28 | Overhead | R15/16 | 2023-01-11 | 1 |  | 82 | 13 | 94 | 2022 | 2023 | R15/16
151668741852 | 151655111852 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-30 | 2022-11-30 | 2022-11-30 | 2023-03-01 | 2023-03-17 | Overhead | R15/16 | 2023-03-01 | 1 |  | 66 | 13 | 78 | 2022 | 2023 | R15/16
151600128920 | 151646958920 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-03 | 2023-08-03 | 2023-08-18 | 2023-09-25 | 2023-11-17 | Underground | R15/16- Reloc | 2023-09-25 | 1 | 12 | 27 | 40 | 77 | 2023 | 2023 | R15/16
151675797533 | 151651797533 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-04 | 2022-10-04 | 2022-10-19 |  | 2023-06-01 | Underground | R15/16- Reloc | 2023-05-24 | 1 | 12 | 156 | 7 | 173 | 2022 | 2023 | R15/16
151642469542 | 151625089542 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-09-20 | 2022-09-20 | 2022-11-04 |  | 2023-03-02 | Underground | R15/16- Reloc | 2022-12-22 | 1 | 34 | 35 | 51 | 118 | 2022 | 2023 | R15/16
151620169992 | 151653419992 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-22 | 2022-08-23 | 2022-08-23 | 2022-09-26 | 2023-01-05 | Overhead | R15/16 | 2022-09-26 | 2 |  | 25 | 74 | 99 | 2022 | 2023 | R15/16
151609073163 | 151632153163 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH DIST RELOC REARR CUST REQ | Commercial | 2022-08-11 | 2023-02-06 | 2023-03-20 | 2023-03-30 | 2023-06-12 | Overhead | R15/16 | 2023-03-30 | 128 | 31 | 9 | 53 | 218 | 2022 | 2023 | R15/16
151618559943 | 151644379943 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-17 | 2022-08-18 | 2022-08-22 | 2022-09-24 | 2022-09-27 | Underground | R15/16- Reloc | 2022-09-24 | 2 | 3 | 25 | 2 | 30 | 2022 | 2022 | R15/16
151631422449 | 151644712449 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-17 | 2022-09-02 | 2022-09-02 |  | 2023-08-09 | Overhead | R15/16 | 2023-03-30 | 13 |  | 150 | 95 | 256 | 2022 | 2023 | R15/16
151676990196 | 151653030196 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-07 | 2023-08-07 | 2023-08-21 | 2023-08-23 | 2023-09-13 | Underground | R15/16- Reloc | 2023-08-23 | 1 | 11 | 3 | 16 | 28 | 2023 | 2023 | R15/16
151692916103 | 151648406103 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-27 | 2022-12-06 | 2023-01-25 | 2023-01-17 | 2023-07-24 | Underground | R15/16- Reloc | 2023-01-17 | 7 | 37 |  | 135 | 171 | 2022 | 2023 | R15/16
151694894122 | 151630564122 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-09-11 | 2023-09-11 | 2023-09-29 | 2023-10-27 | 2023-11-21 | Underground | R15/16- Reloc | 2023-10-27 | 1 | 15 | 21 | 18 | 52 | 2023 | 2023 | R15/16
151697677752 | 151613377752 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-04 | 2022-08-04 | 2022-08-04 | 2022-10-20 | 2023-01-05 | Overhead | R15/16 | 2022-10-20 | 1 |  | 56 | 56 | 111 | 2022 | 2023 | R15/16
151681242868 | 151652112868 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-22 | 2022-09-07 | 2022-09-07 | 2023-01-05 | 2023-01-05 | Underground | R15/16- Reloc | 2023-01-05 | 13 |  | 87 |  | 99 | 2022 | 2023 | R15/16
151626647709 | 151655687709 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-30 | 2022-11-30 | 2023-01-30 | 2023-03-03 | 2023-03-06 | Underground | R15/16- Reloc | 2023-03-03 | 1 | 44 | 25 | 2 | 69 | 2022 | 2023 | R15/16
151630207194 | 151641727194 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-01 | 2023-08-03 | 2023-08-03 | 2023-08-10 | 2023-09-15 | Underground | R15/16- Reloc | 2023-08-10 | 3 |  | 6 | 27 | 34 | 2023 | 2023 | R15/16
151637172840 | 151649392840 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-28 | 2022-12-05 | 2022-12-09 |  | 2023-07-10 | Overhead | R15/16 | 2023-07-10 | 6 | 5 | 152 |  | 161 | 2022 | 2023 | R15/16
151630538293 | 151663618293 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-10 | 2023-08-14 | 2023-08-14 | 2023-09-28 | 2023-10-12 | Overhead | R15/16 | 2023-09-28 | 3 |  | 34 | 11 | 46 | 2023 | 2023 | R15/16
151620632919 | 151620332919 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2023-09-06 | 2023-09-06 | 2023-09-18 |  | 2023-12-11 | Underground | R15/16- Reloc |  | 1 | 9 |  |  | 69 | 2023 | 2023 | R15/16
151645416567 | 151663956567 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-10 | 2022-10-10 | 2022-10-10 | 2023-01-17 | 2023-02-26 | Overhead | R15/16 | 2023-01-17 | 1 |  | 72 | 29 | 100 | 2022 | 2023 | R15/16
151637597131 | 151675037131 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-17 | 2023-08-17 | 2023-10-27 | 2023-10-27 | 2023-12-08 | Underground | R15/16- Reloc | 2023-10-27 | 1 | 52 |  | 31 | 82 | 2023 | 2023 | R15/16
151696546512 | 151626326512 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-07-24 | 2023-07-27 | 2023-07-27 | 2023-09-07 | 2023-09-13 | Overhead | R15/16 | 2023-09-07 | 4 |  | 31 | 5 | 38 | 2023 | 2023 | R15/16
151657414330 | 151619834330 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Commercial | 2023-09-06 | 2023-09-06 | 2023-10-02 | 2023-11-14 | 2023-11-17 | Underground | R15/16- Reloc | 2023-11-14 | 1 | 19 | 32 | 4 | 53 | 2023 | 2023 | R15/16
151686026554 | 151694596554 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-22 | 2023-10-24 | 2023-10-24 | 2023-11-03 | 2023-11-20 | Overhead | R15/16 | 2023-11-03 | 46 |  | 9 | 12 | 65 | 2023 | 2023 | R15/16
151692789721 | 151650669721 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-19 | 2022-08-19 | 2022-08-19 | 2022-10-04 | 2022-10-05 | Overhead | R15/16 | 2022-10-04 | 1 |  | 33 | 2 | 34 | 2022 | 2022 | R15/16
151655172287 | 151621312287 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-09-06 | 2023-09-11 | 2023-09-11 | 2023-11-09 | 2023-12-29 | Overhead | R15/16 | 2023-11-09 | 4 |  | 44 | 37 | 83 | 2023 | 2023 | R15/16
151675038761 | 151690408761 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-24 | 2022-10-31 | 2022-10-31 |  | 2023-04-13 | Overhead | R15/16 | 2022-12-15 | 6 |  | 34 | 86 | 124 | 2022 | 2023 | R15/16
151621449416 | 151692069416 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-24 | 2022-10-26 | 2022-11-04 | 2023-03-11 | 2023-03-15 | Underground | R15/16- Reloc | 2023-03-11 | 3 | 8 | 91 | 3 | 103 | 2022 | 2023 | R15/16
151672953402 | 151611313402 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-30 | 2023-09-21 | 2023-09-22 | 2023-09-26 | 2023-10-20 | Overhead | R15/16 | 2023-09-26 | 17 | 2 | 3 | 19 | 38 | 2023 | 2023 | R15/16
151601568182 | 151618728182 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-09-15 |  | 2022-09-15 | 2023-01-06 | 2023-01-09 | Underground | R15/16- Reloc | 2023-01-06 |  |  | 82 | 2 | 83 | 2022 | 2023 | R15/16
151659611155 | 151646511155 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-03 | 2023-08-03 | 2023-08-30 | 2023-09-01 | 2023-09-26 | Underground | R15/16- Reloc | 2023-09-01 | 1 | 20 | 3 | 18 | 39 | 2023 | 2023 | R15/16
151693348630 | 151676118630 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-17 | 2023-08-17 | 2023-08-17 | 2023-08-23 | 2023-10-02 | Overhead | R15/16 | 2023-08-23 | 1 |  | 5 | 29 | 33 | 2023 | 2023 | R15/16
151663699058 | 151679119058 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-18 | 2023-08-18 | 2023-08-18 | 2023-09-18 | 2023-10-06 | Overhead | R15/16 | 2023-09-18 | 1 |  | 22 | 15 | 36 | 2023 | 2023 | R15/16
151677123424 | 151607713424 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-12 | 2022-09-12 | 2022-09-12 |  | 2023-02-22 | Overhead | R15/16 | 2023-02-10 | 1 |  | 110 | 9 | 118 | 2022 | 2023 | R15/16
151670186562 | 151668256562 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2023-10-02 | 2023-10-02 | 2023-10-23 | 2023-10-25 | 2023-11-06 | Underground | R15/16- Reloc | 2023-10-25 | 1 | 16 | 3 | 9 | 26 | 2023 | 2023 | R15/16
151647840149 | 151660690149 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-25 | 2022-08-25 | 2022-08-25 |  | 2022-11-30 | Overhead | R15/16 | 2022-11-22 | 1 |  | 64 | 7 | 70 | 2022 | 2022 | R15/16
151638717362 | 151699567362 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-07-28 | 2022-07-29 | 2022-07-29 | 2022-10-06 | 2022-10-11 | Overhead | R15/16 | 2022-10-06 | 2 |  | 50 | 4 | 54 | 2022 | 2022 | R15/16
151673480606 | 151662520606 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-25 | 2022-08-29 | 2022-08-29 |  | 2023-07-28 | Overhead | R15/16 | 2023-02-28 | 3 |  | 132 | 109 | 242 | 2022 | 2023 | R15/16
151627638624 | 151631338624 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-07-26 | 2023-07-27 | 2023-08-17 | 2023-10-10 | 2023-10-18 | Underground | R15/16- Reloc | 2023-10-10 | 2 | 16 | 39 | 7 | 61 | 2023 | 2023 | R15/16
151664372702 | 151668702702 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-12-07 | 2022-12-07 | 2022-12-07 | 2023-09-17 | 2023-09-20 | Overhead | R15/16 | 2023-09-17 | 1 |  | 203 | 3 | 206 | 2022 | 2023 | R15/16
151684577033 | 151697277033 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2022-07-27 | 2022-07-27 | 2022-07-27 |  | 2022-08-19 | Underground | R15/16- Reloc | 2022-08-01 | 1 |  | 4 | 15 | 18 | 2022 | 2022 | R15/16
151651701283 | 151610751283 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-30 | 2023-08-30 | 2023-08-30 | 2023-09-14 | 2023-10-11 | Overhead | R15/16 | 2023-09-14 | 1 |  | 12 | 20 | 31 | 2023 | 2023 | R15/16
151608157982 | 151632627982 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-07-26 | 2023-07-26 | 2023-08-10 | 2023-08-21 | 2023-08-23 | Underground | R15/16- Reloc | 2023-08-21 | 1 | 12 | 8 | 3 | 21 | 2023 | 2023 | R15/16
151677440902 | 151651700902 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-21 | 2022-08-21 | 2022-08-31 |  | 2023-03-02 | Underground | R15/16- Reloc | 2022-12-22 | 0 | 8 | 82 | 51 | 139 | 2022 | 2023 | R15/16
151682344297 | 151650614297 | RETOFIT OF EXISTING DISTRIBUTION SYSTEM | OH NB SUPPORT BUDG 219 | Residential | 2022-10-03 | 2022-10-04 | 2023-10-03 | 2023-10-13 | 2023-11-14 | Overhead | R15/16 | 2023-10-13 | 2 | 261 | 9 | 23 | 292 | 2022 | 2023 | R15/16
151664297121 | 151613217121 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-10-27 | 2023-11-14 | Underground | R15/16- Reloc | 2023-10-27 | 1 |  | 2 | 13 | 14 | 2023 | 2023 | R15/16
151697382842 | 151641542842 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-09-16 | 2023-09-16 | 2023-09-16 | 2023-10-07 | 2023-10-11 | Underground | R15/16- Reloc | 2023-10-07 | 0 |  | 15 | 3 | 18 | 2023 | 2023 | R15/16
151694305730 | 151617455730 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-07-19 | 2023-07-20 | 2023-07-20 | 2023-07-25 | 2023-10-02 | Overhead | R15/16 | 2023-07-25 | 2 |  | 4 | 50 | 54 | 2023 | 2023 | R15/16
151632399145 | 151695969145 | MODIFICATION OF EXISTING DISTRIB SYSTEM | OH NB SUPPORT BUDG 219 | Residential | 2022-10-26 | 2022-10-26 | 2022-11-02 | 2022-11-22 | 2022-12-09 | Overhead | R15/16 | 2022-11-22 | 1 | 6 | 15 | 14 | 33 | 2022 | 2022 | R15/16
151652238472 | 151627548472 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-10 |  | 2022-08-10 | 2022-09-29 | 2023-01-05 | Overhead | R15/16 | 2022-09-29 |  |  | 37 | 71 | 107 | 2022 | 2023 | R15/16
151697373304 | 151629853304 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-09-11 | 2023-09-11 | 2023-09-21 | 2023-09-21 | 2023-11-01 | Underground | R15/16- Reloc | 2023-09-21 | 1 | 9 |  | 30 | 38 | 2023 | 2023 | R15/16
151626039203 | 151640559203 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-16 | 2022-08-16 | 2022-08-16 | 2022-10-05 | 2023-01-05 | Overhead | R15/16 | 2022-10-05 | 1 |  | 37 | 67 | 103 | 2022 | 2023 | R15/16
151625431393 | 151646331393 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-23 | 2022-11-23 | 2022-11-23 | 2023-03-01 | 2023-05-26 | Underground | R15/16- Reloc | 2023-03-01 | 1 |  | 71 | 63 | 133 | 2022 | 2023 | R15/16
151684834474 | 151669094474 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-29 | 2022-08-31 | 2022-09-21 |  | 2023-02-03 | Underground | R15/16- Reloc | 2022-11-21 | 3 | 16 | 44 | 55 | 115 | 2022 | 2023 | R15/16
151612581010 | 151634241010 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-15 | 2022-11-17 | 2022-11-18 |  | 2023-02-03 | Underground | R15/16- Reloc | 2022-12-01 | 3 | 2 | 10 | 47 | 59 | 2022 | 2023 | R15/16
151625162583 | 151640352583 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH DIST RELOC REARR CUST REQ | Commercial | 2022-09-27 | 2022-09-27 | 2023-03-15 | 2023-03-16 | 2023-05-26 | Overhead | R15/16 | 2023-03-16 | 1 | 122 | 2 | 52 | 174 | 2022 | 2023 | R15/16
151647230142 | 151649900142 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Commercial | 2022-08-19 | 2022-08-19 | 2022-08-24 | 2022-09-12 | 2022-10-03 | Underground | R15/16- Reloc | 2022-09-12 | 1 | 4 | 14 | 16 | 32 | 2022 | 2022 | R15/16
151619800594 | 151631250594 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-15 | 2022-11-15 | 2022-11-15 | 2023-04-24 | 2023-06-12 | Overhead | R15/16 | 2023-04-24 | 1 |  | 115 | 36 | 150 | 2022 | 2023 | R15/16
151644446070 | 151688836070 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-10-13 | 2023-10-13 | 2023-10-17 | 2023-10-20 | 2023-12-14 | Underground | R15/16- Reloc | 2023-10-20 | 1 | 3 | 4 | 40 | 45 | 2023 | 2023 | R15/16
151675530364 | 151697520364 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Commercial | 2022-07-27 | 2022-08-25 | 2022-08-25 | 2022-09-26 | 2023-01-05 | Underground | R15/16- Reloc | 2022-09-26 | 22 |  | 23 | 74 | 117 | 2022 | 2023 | R15/16
151607357190 | 151651907190 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS UD | Commercial | 2022-10-04 | 2022-10-14 | 2022-10-17 | 2023-01-05 | 2023-01-05 | Underground | R15/16- Reloc | 2023-01-05 | 9 | 2 | 59 |  | 68 | 2022 | 2023 | R15/16
151665671875 | 151640071875 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-01 | 2023-08-01 | 2023-12-07 | 2023-12-07 | 2023-12-28 | Underground | R15/16- Reloc | 2023-12-07 | 1 | 93 |  | 16 | 108 | 2023 | 2023 | R15/16
151629033362 | 151604673362 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Commercial | 2022-07-30 | 2022-09-11 | 2022-09-12 | 2022-09-24 | 2022-09-28 | Underground | R15/16- Reloc | 2022-09-24 | 30 | 1 | 10 | 3 | 43 | 2022 | 2022 | R15/16
151636781599 | 151649921599 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-28 | 2022-11-30 | 2022-11-30 |  | 2023-05-30 | Overhead | R15/16 | 2023-01-27 | 3 |  | 43 | 88 | 132 | 2022 | 2023 | R15/16
151660048379 | 151699538379 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-10-18 | 2023-11-02 | 2023-11-02 | 2023-11-03 | 2023-11-16 | Overhead | R15/16 | 2023-11-03 | 12 |  | 2 | 10 | 22 | 2023 | 2023 | R15/16
151600759157 | 151611699157 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-03 | 2022-08-03 | 2022-08-16 | 2022-10-09 | 2022-10-12 | Underground | R15/16- Reloc | 2022-10-09 | 1 | 10 | 39 | 3 | 51 | 2022 | 2022 | R15/16
151614337232 | 151625917232 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-09-20 | 2022-09-20 | 2023-01-26 | 2023-03-27 | 2023-03-29 | Underground | R15/16- Reloc | 2023-03-27 | 1 | 93 | 43 | 3 | 137 | 2022 | 2023 | R15/16
151676224952 | 151664064952 | MODIFICATION OF EXISTING DISTRIB SYSTEM | OH NB SUPPORT BUDG 219 | Residential | 2022-10-10 | 2022-10-10 | 2023-01-06 | 2023-04-07 | 2023-07-10 | Overhead | R15/16 | 2023-04-07 | 1 | 65 | 66 | 67 | 196 | 2022 | 2023 | R15/16
151669446213 | 151625556213 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-07-24 |  | 2023-07-24 | 2023-08-08 | 2023-08-18 | Overhead | R15/16 | 2023-08-08 |  |  | 12 | 9 | 20 | 2023 | 2023 | R15/16
151697645803 | 151622075803 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-07-20 | 2023-07-20 | 2023-07-20 | 2023-12-01 | 2023-12-07 | Overhead | R15/16 | 2023-12-01 | 1 |  | 97 | 5 | 101 | 2023 | 2023 | R15/16
151663910380 | 151679160380 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-18 | 2022-10-18 | 2022-11-13 |  | 2023-03-01 | Underground | R15/16- Reloc | 2023-02-28 | 1 | 19 | 77 | 2 | 97 | 2022 | 2023 | R15/16
151636950890 | 151673860890 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-31 | 2022-09-01 | 2022-09-01 |  | 2023-06-26 | Underground | R15/16- Reloc | 2023-03-13 | 2 |  | 138 | 76 | 214 | 2022 | 2023 | R15/16
151638222953 | 151601622953 |  | UG MISC STREET LIGHTING SL |  | 2022-09-08 | 2022-09-08 | 2022-09-08 | 2022-09-09 | 2022-09-14 | Underground | R15/16- Reloc | 2022-09-09 | 1 |  | 2 | 4 | 5 | 2022 | 2022 | R15/16
151672564174 | 151623504174 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-09-19 | 2022-09-19 | 2022-09-19 |  | 2022-10-23 | Underground | R15/16- Reloc | 2022-10-12 | 1 |  | 18 | 8 | 25 | 2022 | 2022 | R15/16
151602627078 | 151601387078 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-07-29 | 2022-07-29 | 2022-07-29 | 2022-08-10 | 2022-08-11 | Underground | R15/16- Reloc | 2022-08-10 | 1 |  | 9 | 2 | 10 | 2022 | 2022 | R15/16
151620981204 | 151699191204 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-24 | 2023-08-29 | 2023-08-29 | 2023-08-30 | 2023-11-16 | Overhead | R15/16 | 2023-08-30 | 4 |  | 2 | 57 | 61 | 2023 | 2023 | R15/16
151638402456 | 151699852456 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-09-07 | 2022-09-07 | 2023-03-15 |  | 2023-07-31 | Underground | R15/16- Reloc | 2023-03-15 | 1 | 136 |  | 99 | 234 | 2022 | 2023 | R15/16
151685942259 | 151629492259 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-09-11 | 2023-09-12 | 2023-09-12 | 2023-10-03 | 2023-11-09 | Overhead | R15/16 | 2023-10-03 | 2 |  | 16 | 28 | 44 | 2023 | 2023 | R15/16
151695437282 | 151617967282 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-07-19 | 2023-07-19 | 2023-08-03 | 2023-10-19 | 2023-10-25 | Underground | R15/16- Reloc | 2023-10-19 | 1 | 12 | 56 | 5 | 71 | 2023 | 2023 | R15/16
151693673744 | 151613643744 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-14 | 2022-09-14 | 2022-09-14 | 2023-04-13 | 2023-04-22 | Overhead | R15/16 | 2023-04-13 | 1 |  | 152 | 7 | 158 | 2022 | 2023 | R15/16
151671641672 | 151651521672 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2022-11-29 | 2022-11-29 | 2022-11-29 |  | 2022-12-07 | Underground | R15/16- Reloc |  | 1 |  |  |  | 7 | 2022 | 2022 | R15/16
151604247970 | 151663017970 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-10 | 2022-10-10 | 2022-10-24 |  | 2023-06-26 | Underground | R15/16- Reloc | 2023-03-09 | 1 | 11 | 99 | 78 | 186 | 2022 | 2023 | R15/16
151609465394 | 151667855394 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-10-02 | 2023-10-11 | 2023-10-11 | 2023-10-17 | 2023-11-06 | Overhead | R15/16 | 2023-10-17 | 8 |  | 5 | 15 | 26 | 2023 | 2023 | R15/16
151619068688 | 151633908688 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-12 | 2022-08-12 | 2022-08-12 | 2023-01-11 | 2023-06-12 | Overhead | R15/16 | 2023-01-11 | 1 |  | 109 | 109 | 217 | 2022 | 2023 | R15/16
151645127137 | 151646827137 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-03 | 2023-08-03 | 2023-08-03 | 2023-08-04 | 2023-08-09 | Overhead | R15/16 | 2023-08-04 | 1 |  | 2 | 4 | 5 | 2023 | 2023 | R15/16
151647391174 | 151695571174 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-25 | 2022-11-21 | 2022-11-21 |  | 2023-08-11 | Underground | R15/16- Reloc | 2023-04-04 | 20 |  | 97 | 94 | 209 | 2022 | 2023 | R15/16
151635677741 | 151654327741 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-07 | 2023-08-08 | 2023-08-08 | 2023-08-10 | 2023-08-25 | Overhead | R15/16 | 2023-08-10 | 2 |  | 3 | 12 | 15 | 2023 | 2023 | R15/16
151694706781 | 151682646781 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-10-10 | 2023-10-24 | 2023-10-24 | 2023-11-01 | 2023-11-14 | Underground | R15/16- Reloc | 2023-11-01 | 11 |  | 7 | 10 | 26 | 2023 | 2023 | R15/16
151617539166 | 151640269166 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-16 | 2022-08-16 | 2022-08-16 | 2022-10-04 | 2023-01-05 | Overhead | R15/16 | 2022-10-04 | 1 |  | 36 | 68 | 103 | 2022 | 2023 | R15/16
151618489919 | 151624589919 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-10 | 2022-11-10 | 2022-11-10 | 2023-05-25 | 2023-06-13 | Overhead | R15/16 | 2023-05-25 | 1 |  | 141 | 14 | 154 | 2022 | 2023 | R15/16
151623275953 | 151632305953 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-09-23 |  | 2022-09-23 | 2022-12-28 | 2023-01-25 | Underground | R15/16- Reloc | 2022-12-28 |  |  | 69 | 21 | 89 | 2022 | 2023 | R15/16
151676434717 | 151649144717 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-09-20 | 2023-10-05 | 2023-10-05 | 2023-11-03 | 2023-11-15 | Underground | R15/16- Reloc | 2023-11-03 | 12 |  | 22 | 9 | 41 | 2023 | 2023 | R15/16
151640450138 | 151656160138 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-23 | 2022-08-23 | 2022-08-24 | 2022-11-13 | 2022-11-16 | Underground | R15/16- Reloc | 2022-11-13 | 1 | 2 | 58 | 3 | 62 | 2022 | 2022 | R15/16
151677393445 | 151608443445 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-12 | 2022-09-12 | 2022-09-12 |  | 2022-10-13 | Overhead | R15/16 | 2022-10-12 | 1 |  | 23 | 2 | 24 | 2022 | 2022 | R15/16
151693369832 | 151624909832 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Commercial | 2022-09-20 | 2022-10-10 | 2022-11-08 |  | 2023-03-02 | Overhead | R15/16 |  | 15 | 22 |  |  | 118 | 2022 | 2023 | R15/16
151673049435 | 151690019435 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-24 | 2022-11-04 | 2022-11-04 |  | 2023-04-27 | Underground | R15/16- Reloc | 2023-01-10 | 10 |  | 48 | 78 | 134 | 2022 | 2023 | R15/16
151648362072 | 151608622072 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-29 | 2023-09-08 | 2023-09-08 | 2023-09-28 | 2023-11-13 | Overhead | R15/16 | 2023-09-28 | 9 |  | 15 | 33 | 55 | 2023 | 2023 | R15/16
151638716405 | 151660716405 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-07 | 2022-10-07 | 2022-10-07 | 2022-11-10 | 2022-11-14 | Overhead | R15/16 | 2022-11-10 | 1 |  | 25 | 3 | 27 | 2022 | 2022 | R15/16
151600489861 | 151665869861 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Commercial | 2022-10-11 | 2022-11-01 | 2022-11-08 |  | 2023-02-03 | Underground | R15/16- Reloc |  | 16 | 6 |  |  | 84 | 2022 | 2023 | R15/16
151623387233 | 151639807233 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-07-31 | 2023-07-31 | 2023-08-03 | 2023-08-18 | 2023-09-22 | Underground | R15/16- Reloc | 2023-08-18 | 1 | 4 | 12 | 26 | 40 | 2023 | 2023 | R15/16
151678224925 | 151677874925 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-10-06 | 2023-10-06 | 2023-10-06 | 2023-10-09 | 2023-10-09 | Overhead | R15/16 | 2023-10-09 | 1 |  | 2 |  | 2 | 2023 | 2023 | R15/16
151664405117 | 151612295117 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-07-14 | 2023-07-14 | 2023-07-14 | 2023-08-01 | 2023-08-11 | Underground | R15/16- Reloc | 2023-08-01 | 1 |  | 13 | 9 | 21 | 2023 | 2023 | R15/16
151621182632 | 151699292632 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-24 | 2023-08-24 | 2023-09-14 | 2023-09-19 | 2023-11-02 | Underground | R15/16- Reloc | 2023-09-19 | 1 | 16 | 4 | 33 | 51 | 2023 | 2023 | R15/16
151656741242 | 151609341242 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-30 | 2023-08-30 | 2023-08-30 | 2023-09-26 | 2023-11-14 | Underground | R15/16- Reloc | 2023-09-26 | 1 |  | 20 | 36 | 55 | 2023 | 2023 | R15/16
151605913302 | 151612963302 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH DIST RELOC REARR CUST REQ | Residential | 2022-08-03 | 2023-05-23 | 2022-12-19 | 2023-05-23 | 2023-12-20 | Overhead | R15/16 | 2023-05-23 | 210 |  | 112 | 152 | 361 | 2022 | 2023 | R15/16
151638321805 | 151652641805 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-29 | 2022-11-29 | 2022-11-29 | 2023-02-08 | 2023-02-28 | Overhead | R15/16 | 2023-02-08 | 1 |  | 52 | 15 | 66 | 2022 | 2023 | R15/16
151617954010 | 151631964010 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-14 | 2022-11-14 | 2022-12-27 | 2023-03-20 | 2023-06-13 | Underground | R15/16- Reloc | 2023-03-20 | 1 | 32 | 60 | 62 | 152 | 2022 | 2023 | R15/16
151612869170 | 151641259170 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-16 | 2022-08-16 | 2022-08-16 | 2022-08-25 | 2022-10-20 | Overhead | R15/16 | 2022-08-25 | 1 |  | 8 | 41 | 48 | 2022 | 2022 | R15/16
151617088619 | 151632228619 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-11 | 2022-08-11 | 2022-08-11 | 2022-11-22 | 2022-12-06 | Overhead | R15/16 | 2022-11-22 | 1 |  | 74 | 11 | 84 | 2022 | 2022 | R15/16
151637240786 | 151672690786 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-30 | 2022-08-30 | 2022-08-30 | 2022-09-23 | 2022-09-26 | Overhead | R15/16 | 2022-09-23 | 1 |  | 19 | 2 | 20 | 2022 | 2022 | R15/16
151630666013 | 151656016013 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2022-10-05 | 2022-10-05 | 2022-10-05 | 2023-07-20 | 2023-08-16 | Underground | R15/16- Reloc | 2023-07-20 | 1 |  | 207 | 20 | 226 | 2022 | 2023 | R15/16
151685653099 | 151605683099 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-10 | 2022-09-10 | 2022-09-10 |  | 2023-03-31 | Overhead | R15/16 | 2023-03-01 | 0 |  | 123 | 23 | 145 | 2022 | 2023 | R15/16
151601123374 | 151615503374 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2023-09-01 | 2023-09-01 | 2023-09-22 | 2023-10-02 | 2023-10-03 | Underground | R15/16- Reloc | 2023-10-02 | 1 | 16 | 7 | 2 | 23 | 2023 | 2023 | R15/16
151698809021 | 151605789021 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2023-03-21 | 2023-06-12 | Underground | R15/16- Reloc | 2023-03-21 | 1 |  | 101 | 60 | 160 | 2022 | 2023 | R15/16
151671052430 | 151645672430 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-03 | 2023-08-03 | 2023-09-12 | 2023-09-26 | 2023-11-14 | Underground | R15/16- Reloc | 2023-09-26 | 1 | 29 | 11 | 36 | 74 | 2023 | 2023 | R15/16
151655705714 | 151640785714 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-16 | 2022-10-04 | 2022-10-04 |  | 2023-06-16 | Underground | R15/16- Reloc | 2023-03-07 | 36 |  | 111 | 74 | 219 | 2022 | 2023 | R15/16
151631787343 | 151664577343 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-11 | 2022-10-17 | 2022-10-17 | 2023-01-05 | 2023-01-05 | Underground | R15/16- Reloc | 2023-01-05 | 5 |  | 59 |  | 63 | 2022 | 2023 | R15/16
151694149388 | 151628399388 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-11-01 | 2023-11-10 | 2023-11-10 | 2023-11-14 | 2023-12-14 | Overhead | R15/16 | 2023-11-14 | 8 |  | 3 | 23 | 32 | 2023 | 2023 | R15/16
151634318594 | 151672518594 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-13 | 2022-10-28 | 2022-10-28 | 2023-04-03 | 2023-04-04 | Overhead | R15/16 | 2023-04-03 | 12 |  | 112 | 2 | 124 | 2022 | 2023 | R15/16
151628253518 | 151612463518 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-14 | 2022-09-14 | 2022-09-14 |  | 2023-01-25 | Overhead | R15/16 | 2023-01-18 | 1 |  | 91 | 6 | 96 | 2022 | 2023 | R15/16
151612985832 | 151645035832 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-29 | 2022-10-04 | 2022-10-04 |  | 2023-08-14 | Overhead | R15/16 | 2023-04-26 | 4 |  | 147 | 79 | 228 | 2022 | 2023 | R15/16
151691914470 | 151629034470 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-21 | 2022-09-21 | 2022-09-21 | 2022-09-27 | 2022-09-28 | Overhead | R15/16 | 2022-09-27 | 1 |  | 5 | 2 | 6 | 2022 | 2022 | R15/16
151692401629 | 151618441629 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-08 | 2022-11-09 | 2022-11-28 |  | 2023-07-11 | Underground | R15/16- Reloc | 2023-05-22 | 2 | 14 | 126 | 37 | 176 | 2022 | 2023 | R15/16
151611627923 | 151615757923 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-04 | 2022-08-04 | 2022-08-04 |  | 2022-10-21 | Overhead | R15/16 | 2022-08-24 | 1 |  | 15 | 43 | 57 | 2022 | 2022 | R15/16
151628153382 | 151607923382 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-09-12 | 2022-09-12 | 2022-09-12 | 2023-01-05 | 2023-01-05 | Underground | R15/16- Reloc | 2023-01-05 | 1 |  | 84 |  | 84 | 2022 | 2023 | R15/16
151632673921 | 151639253921 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2022-11-17 | 2023-05-03 | 2023-09-27 |  | 2023-11-30 | Underground | R15/16- Reloc |  | 120 | 106 |  |  | 271 | 2022 | 2023 | R15/16
151623021900 | 151619561900 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-09-06 | 2023-09-06 | 2023-09-06 | 2023-09-21 | 2023-11-03 | Overhead | R15/16 | 2023-09-21 | 1 |  | 12 | 32 | 43 | 2023 | 2023 | R15/16
151625725270 | 151644255270 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-29 | 2022-09-29 | 2022-09-29 | 2022-11-21 | 2022-12-06 | Overhead | R15/16 | 2022-11-21 | 1 |  | 38 | 12 | 49 | 2022 | 2022 | R15/16
151664678034 | 151665498034 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-11 | 2023-08-11 | 2023-08-11 | 2023-08-14 | 2023-08-17 | Overhead | R15/16 | 2023-08-14 | 1 |  | 2 | 4 | 5 | 2023 | 2023 | R15/16
151645247591 | 151607157591 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-02 | 2022-08-02 | 2022-08-02 |  | 2022-10-23 | Overhead | R15/16 | 2022-10-06 | 1 |  | 48 | 12 | 59 | 2022 | 2022 | R15/16
151688106233 | 151617906233 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-07-18 | 2023-07-18 | 2023-07-25 | 2023-08-08 | 2023-11-15 | Overhead | R15/16 | 2023-08-08 | 1 | 6 | 11 | 72 | 87 | 2023 | 2023 | R15/16
151676813185 | 151600693185 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-08 | 2022-09-09 | 2022-09-09 | 2022-11-22 | 2022-12-13 | Overhead | R15/16 | 2022-11-22 | 2 |  | 53 | 16 | 69 | 2022 | 2022 | R15/16
151642571729 | 151651051729 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-29 | 2022-11-29 | 2022-11-29 |  | 2023-03-02 | Underground | R15/16- Reloc | 2022-12-22 | 1 |  | 18 | 51 | 68 | 2022 | 2023 | R15/16
151607291367 | 151644401367 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-21 | 2022-11-22 | 2022-11-22 | 2023-02-04 | 2023-02-07 | Overhead | R15/16 | 2023-02-04 | 2 |  | 54 | 2 | 57 | 2022 | 2023 | R15/16
151640664203 | 151609834203 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-30 | 2023-08-30 | 2023-09-29 | 2023-10-10 | 2023-10-19 | Underground | R15/16- Reloc | 2023-10-10 | 1 | 23 | 8 | 8 | 37 | 2023 | 2023 | R15/16
151641021524 | 151605041524 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-28 | 2023-08-28 | 2023-09-01 | 2023-10-17 | 2023-10-31 | Underground | R15/16- Reloc | 2023-10-17 | 1 | 5 | 33 | 11 | 47 | 2023 | 2023 | R15/16
151693212289 | 151695022289 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-25 |  | 2022-11-18 | 2023-03-02 | 2023-03-17 | Underground | R15/16- Reloc | 2023-03-02 |  |  | 75 | 12 | 104 | 2022 | 2023 | R15/16
151610410910 | 151613830910 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-07-17 |  | 2023-07-17 | 2023-08-31 | 2023-10-11 | Underground | R15/16- Reloc | 2023-08-31 |  |  | 34 | 30 | 63 | 2023 | 2023 | R15/16
151638721387 | 151692781387 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-21 | 2023-08-21 | 2023-08-31 | 2023-09-11 | 2023-11-09 | Underground | R15/16- Reloc | 2023-09-11 | 1 | 9 | 8 | 44 | 59 | 2023 | 2023 | R15/16
151640497292 | 151617337292 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH PRE ARR CUST WORK | Commercial | 2023-07-18 | 2023-07-18 | 2023-08-03 |  | 2023-09-13 | Overhead | R15/16 | 2023-09-13 | 1 | 13 | 30 |  | 42 | 2023 | 2023 | R15/16
151681338468 | 151600168468 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-27 | 2022-10-27 | 2022-10-27 | 2023-02-22 | 2023-03-17 | Overhead | R15/16 | 2023-02-22 | 1 |  | 85 | 18 | 102 | 2022 | 2023 | R15/16
151633374159 | 151613824159 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2022-09-14 | 2022-09-15 | 2022-09-20 |  | 2023-08-30 | Underground | R15/16- Reloc |  | 2 | 4 |  |  | 251 | 2022 | 2023 | R15/16
151609009426 | 151645459426 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-17 | 2022-08-17 | 2022-08-17 | 2023-09-28 | 2023-10-06 | Overhead | R15/16 | 2023-09-28 | 1 |  | 292 | 7 | 298 | 2022 | 2023 | R15/16
151619436321 | 151627166321 | SDG&E | UG NON RES NB BUDG 218 | Commercial | 2023-07-25 | 2023-07-25 | 2023-07-25 | 2023-09-25 | 2023-12-21 | Underground | R15/16- Reloc | 2023-09-25 | 1 |  | 45 | 64 | 108 | 2023 | 2023 | R15/16
151625080680 | 151632660680 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-15 | 2022-11-15 | 2022-11-15 | 2023-01-31 | 2023-03-31 | Overhead | R15/16 | 2023-01-31 | 1 |  | 56 | 44 | 99 | 2022 | 2023 | R15/16
151652389306 | 151629089306 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-10 |  | 2022-08-17 | 2023-01-26 | 2023-02-18 | Overhead | R15/16 | 2023-01-26 |  |  | 117 | 17 | 138 | 2022 | 2023 | R15/16
151625161243 | 151604751243 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Commercial | 2022-10-31 | 2022-10-31 | 2023-03-02 | 2023-08-28 | 2023-08-30 | Overhead | R15/16 | 2023-08-28 | 1 | 89 | 128 | 3 | 218 | 2022 | 2023 | R15/16
151684047583 | 151600907583 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-07-28 | 2022-08-01 | 2022-08-01 |  | 2023-08-17 | Overhead | R15/16 | 2023-08-16 | 3 |  | 273 | 2 | 276 | 2022 | 2023 | R15/16
151643223267 | 151610163267 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-30 | 2023-09-20 | 2023-09-20 | 2023-09-28 | 2023-11-15 | Overhead | R15/16 | 2023-09-28 | 16 |  | 7 | 35 | 56 | 2023 | 2023 | R15/16
151642190605 | 151666920605 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-26 | 2022-08-29 | 2022-08-29 | 2022-09-15 | 2022-09-16 | Overhead | R15/16 | 2022-09-15 | 2 |  | 14 | 2 | 16 | 2022 | 2022 | R15/16
151624310928 | 151638490928 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-18 | 2022-11-18 | 2022-11-18 | 2023-09-29 | 2023-10-19 | Overhead | R15/16 | 2023-09-29 | 1 |  | 226 | 15 | 240 | 2022 | 2023 | R15/16
151656290792 | 151623500792 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-08 | 2022-08-09 | 2022-08-31 | 2023-01-05 | 2023-01-05 | Overhead | R15/16 | 2023-01-05 | 2 | 17 | 92 |  | 109 | 2022 | 2023 | R15/16
151626958651 | 151608468651 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-10-24 | 2023-10-24 | 2023-11-06 | 2023-11-15 | 2023-12-05 | Overhead | R15/16 | 2023-11-15 | 1 | 10 | 8 | 15 | 31 | 2023 | 2023 | R15/16
151614525929 | 151688585929 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-10-13 | 2023-10-17 | 2023-10-17 | 2023-11-20 | 2023-12-07 | Overhead | R15/16 | 2023-11-20 | 3 |  | 25 | 14 | 40 | 2023 | 2023 | R15/16
151659358100 | 151618738100 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-05 | 2022-08-05 | 2022-08-05 | 2023-01-05 | 2023-01-05 | Underground | R15/16- Reloc | 2023-01-05 | 1 |  | 110 |  | 110 | 2022 | 2023 | R15/16
151625116383 | 151615946383 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-07-18 | 2023-07-25 | 2023-07-25 | 2023-08-25 | 2023-09-21 | Underground | R15/16- Reloc | 2023-08-25 | 6 |  | 24 | 20 | 48 | 2023 | 2023 | R15/16
151605335941 | 151623725941 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-07-21 | 2023-07-21 | 2023-07-21 | 2023-10-24 | 2023-11-02 | Overhead | R15/16 | 2023-10-24 | 1 |  | 68 | 8 | 75 | 2023 | 2023 | R15/16
151634032185 | 151625182185 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-09-09 | 2023-09-09 | 2023-09-09 | 2023-10-28 | 2023-10-31 | Underground | R15/16- Reloc | 2023-10-28 | 0 |  | 35 | 2 | 37 | 2023 | 2023 | R15/16
151668446089 | 151682406089 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-10-10 | 2023-10-10 | 2023-10-17 | 2023-10-19 | 2023-11-10 | Underground | R15/16- Reloc | 2023-10-19 | 1 | 6 | 3 | 17 | 24 | 2023 | 2023 | R15/16
151637061203 | 151676621203 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-17 | 2023-08-29 | 2023-08-29 |  | 2023-11-06 | Overhead | R15/16 | 2023-09-20 | 9 |  | 17 | 34 | 58 | 2023 | 2023 | R15/16
151636626219 | 151657656219 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-06 | 2022-10-06 | 2022-10-06 | 2022-12-08 | 2023-01-14 | Overhead | R15/16 | 2022-12-08 | 1 |  | 46 | 27 | 72 | 2022 | 2023 | R15/16
151694325599 | 151619505599 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-07-19 | 2023-07-19 | 2023-07-19 | 2023-08-30 | 2023-11-06 | Overhead | R15/16 | 2023-08-30 | 1 |  | 31 | 49 | 79 | 2023 | 2023 | R15/16
151698706141 | 151633186141 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-09-23 | 2022-10-05 | 2022-10-05 |  | 2023-01-10 | Underground | R15/16- Reloc | 2022-11-15 | 9 |  | 30 | 41 | 78 | 2022 | 2023 | R15/16
151637642894 | 151610622894 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-30 | 2023-08-31 | 2023-09-18 | 2023-10-26 | 2023-11-10 | Underground | R15/16- Reloc | 2023-10-26 | 2 | 13 | 29 | 12 | 53 | 2023 | 2023 | R15/16
151633116490 | 151633126490 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Commercial | 2023-07-27 | 2023-07-27 | 2023-07-27 | 2023-07-27 | 2023-08-01 | Overhead | R15/16 | 2023-07-27 | 1 |  |  | 4 | 4 | 2023 | 2023 | R15/16
151689857607 | 151654237607 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-07 | 2023-08-07 | 2023-08-07 | 2023-08-10 | 2023-09-15 | Underground | R15/16- Reloc | 2023-08-10 | 1 |  | 4 | 27 | 30 | 2023 | 2023 | R15/16
151687606252 | 151601106252 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-10-19 | 2023-10-19 | 2023-10-19 | 2023-11-21 | 2023-12-05 | Overhead | R15/16 | 2023-11-21 | 1 |  | 24 | 11 | 34 | 2023 | 2023 | R15/16
151633937986 | 151678337986 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-01 | 2022-09-02 | 2022-10-24 |  | 2023-01-10 | Overhead | R15/16 |  | 2 | 37 |  |  | 94 | 2022 | 2023 | R15/16
151632137045 | 151673197045 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2022-10-14 | 2022-10-14 | 2022-10-14 |  | 2023-02-08 | Underground | R15/16- Reloc |  | 1 |  |  |  | 84 | 2022 | 2023 | R15/16
151602745640 | 151682505640 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-10-10 | 2023-10-13 | 2023-10-13 | 2023-11-29 | 2023-12-04 | Underground | R15/16- Reloc | 2023-11-29 | 4 |  | 34 | 4 | 40 | 2023 | 2023 | R15/16
151602763727 | 151617133727 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-04 |  | 2022-09-14 | 2023-03-07 | 2023-03-24 | Underground | R15/16- Reloc | 2023-03-07 |  |  | 125 | 14 | 167 | 2022 | 2023 | R15/16
151601478417 | 151605438417 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG DIST RELOC REARR CUST REQ | Commercial | 2022-08-01 | 2022-08-01 | 2022-10-28 | 2022-11-21 | 2023-11-17 | Underground | R15/16- Reloc | 2022-11-21 | 1 | 65 | 17 | 260 | 340 | 2022 | 2023 | R15/16
151667052707 | 151668582707 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Commercial | 2022-12-08 | 2022-12-08 | 2022-12-08 |  | 2023-03-01 | Underground | R15/16- Reloc | 2022-12-16 | 1 |  | 7 | 54 | 60 | 2022 | 2023 | R15/16
151689889148 | 151696409148 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-26 | 2022-10-26 | 2022-11-02 |  | 2023-09-05 | Underground | R15/16- Reloc | 2023-05-08 | 1 | 6 | 134 | 87 | 225 | 2022 | 2023 | R15/16
151649481065 | 151668761065 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-29 | 2022-08-31 | 2022-09-01 | 2023-06-16 | 2023-07-12 | Underground | R15/16- Reloc | 2023-06-16 | 3 | 2 | 207 | 19 | 228 | 2022 | 2023 | R15/16
151678107898 | 151662217898 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-10 | 2023-08-10 | 2023-08-10 | 2023-10-09 | 2023-11-15 | Overhead | R15/16 | 2023-10-09 | 1 |  | 43 | 28 | 70 | 2023 | 2023 | R15/16
151673199176 | 151628419176 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS UD | Commercial | 2022-08-10 | 2022-08-10 | 2022-08-16 |  | 2022-10-21 | Underground | R15/16- Reloc |  | 1 | 5 |  |  | 53 | 2022 | 2022 | R15/16
151647675006 | 151642195006 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2023-09-18 | 2023-09-18 | 2023-10-09 | 2023-10-15 | 2023-10-18 | Underground | R15/16- Reloc | 2023-10-15 | 1 | 16 | 5 | 3 | 23 | 2023 | 2023 | R15/16
151612520885 | 151637400885 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-17 | 2022-11-17 | 2022-11-17 | 2023-03-22 | 2023-04-18 | Overhead | R15/16 | 2023-03-22 | 1 |  | 90 | 20 | 109 | 2022 | 2023 | R15/16
151648832172 | 151627552172 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-09-10 | 2023-09-10 | 2023-09-10 | 2023-09-12 | 2023-10-26 | Overhead | R15/16 | 2023-09-12 | 0 |  | 2 | 33 | 34 | 2023 | 2023 | R15/16
151626306245 | 151657126245 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-12-01 | 2022-12-01 | 2023-07-24 | 2023-11-20 | 2023-11-21 | Underground | R15/16- Reloc | 2023-11-20 | 1 | 168 | 86 | 2 | 254 | 2022 | 2023 | R15/16
151611273026 | 151653363026 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-07 | 2023-08-07 | 2023-09-19 | 2023-10-20 | 2023-12-14 | Underground | R15/16- Reloc | 2023-10-20 | 1 | 32 | 24 | 40 | 94 | 2023 | 2023 | R15/16
151641363572 | 151633143572 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-09-12 | 2023-09-25 | 2023-09-25 | 2023-12-06 | 2023-12-12 | Overhead | R15/16 | 2023-12-06 | 10 |  | 53 | 5 | 66 | 2023 | 2023 | R15/16
151673531601 | 151698871601 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-27 | 2022-11-14 | 2022-11-28 | 2023-10-04 | 2023-10-06 | Overhead | R15/16 | 2023-10-04 | 13 | 11 | 223 | 3 | 247 | 2022 | 2023 | R15/16
151673762624 | 151623742624 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2022-08-08 | 2022-08-17 | 2022-09-06 | 2022-09-14 | 2023-09-05 | Underground | R15/16- Reloc | 2022-09-14 | 8 | 15 | 7 | 255 | 282 | 2022 | 2023 | R15/16
151624560476 | 151634120476 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-15 | 2022-11-15 | 2022-11-15 | 2023-01-26 | 2023-02-16 | Overhead | R15/16 | 2023-01-26 | 1 |  | 53 | 16 | 68 | 2022 | 2023 | R15/16
151682075021 | 151636015021 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-09-13 | 2023-09-13 | 2023-10-08 | 2023-11-01 | 2023-11-08 | Underground | R15/16- Reloc | 2023-11-01 | 1 | 18 | 18 | 6 | 41 | 2023 | 2023 | R15/16
151656379231 | 151632289231 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-11 | 2022-08-16 | 2022-08-16 |  | 2023-04-03 | Underground | R15/16- Reloc | 2023-01-18 | 4 |  | 112 | 54 | 168 | 2022 | 2023 | R15/16
151610409840 | 151632299840 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-11 |  | 2022-11-07 | 2023-02-08 | 2023-03-04 | Overhead | R15/16 | 2023-02-08 |  |  | 68 | 18 | 147 | 2022 | 2023 | R15/16
151652317835 | 151696487835 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-07-27 | 2022-07-27 | 2022-08-04 | 2022-09-16 | 2023-01-05 | Underground | R15/16- Reloc | 2022-09-16 | 1 | 7 | 32 | 80 | 117 | 2022 | 2023 | R15/16
151650699011 | 151640089011 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-09-27 | 2022-09-27 | 2022-11-01 | 2022-12-19 | 2022-12-20 | Underground | R15/16- Reloc | 2022-12-19 | 1 | 26 | 35 | 2 | 61 | 2022 | 2022 | R15/16
151653680485 | 151699710485 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-24 | 2023-08-24 | 2023-08-24 | 2023-09-07 | 2023-10-17 | Overhead | R15/16 | 2023-09-07 | 1 |  | 11 | 29 | 39 | 2023 | 2023 | R15/16
151668529544 | 151609739544 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-02 | 2022-11-02 | 2022-11-04 | 2023-01-15 | 2023-02-06 | Underground | R15/16- Reloc | 2023-01-15 | 1 | 3 | 51 | 16 | 69 | 2022 | 2023 | R15/16
151665220639 | 151671760639 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-30 | 2022-08-30 | 2022-08-30 |  | 2022-11-30 | Overhead | R15/16 | 2022-11-18 | 1 |  | 59 | 9 | 67 | 2022 | 2022 | R15/16
151628270006 | 151654040006 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-23 | 2022-08-23 | 2022-08-23 |  | 2022-12-11 | Overhead | R15/16 | 2022-12-05 | 1 |  | 75 | 5 | 79 | 2022 | 2022 | R15/16
151650173045 | 151671233045 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-12-08 |  | 2023-01-30 | 2023-01-23 | 2023-08-14 | Overhead | R15/16 | 2023-01-23 |  |  |  | 146 | 178 | 2022 | 2023 | R15/16
151631860471 | 151666540471 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-27 | 2022-08-27 | 2022-08-27 |  | 2023-06-19 | Overhead | R15/16 | 2023-03-08 | 0 |  | 138 | 74 | 211 | 2022 | 2023 | R15/16
151686615662 | 151648805662 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2022-10-02 | 2022-10-02 | 2022-10-02 |  | 2023-02-03 | Underground | R15/16- Reloc | 2022-12-01 | 0 |  | 44 | 47 | 90 | 2022 | 2023 | R15/16
151632197660 | 151653847660 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-07 | 2023-08-07 | 2023-08-07 | 2023-09-21 | 2023-09-27 | Overhead | R15/16 | 2023-09-21 | 1 |  | 34 | 5 | 38 | 2023 | 2023 | R15/16
151628174375 | 151648384375 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-19 |  | 2022-09-21 | 2023-02-22 | 2023-04-08 | Overhead | R15/16 | 2023-02-22 |  |  | 111 | 33 | 166 | 2022 | 2023 | R15/16
151621008645 | 151608238645 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2023-10-24 | 2023-10-24 | 2023-11-06 | 2023-11-27 | 2023-11-28 | Underground | R15/16- Reloc | 2023-11-27 | 1 | 10 | 16 | 2 | 26 | 2023 | 2023 | R15/16
151653671119 | 151697761119 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2023-08-23 | 2023-08-30 | 2023-08-30 | 2023-09-04 | 2023-09-07 | Underground | R15/16- Reloc | 2023-09-04 | 6 |  | 4 | 4 | 12 | 2023 | 2023 | R15/16
151631315039 | 151639845039 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-27 | 2022-09-27 | 2022-09-27 | 2022-12-15 | 2022-12-20 | Overhead | R15/16 | 2022-12-15 | 1 |  | 58 | 4 | 61 | 2022 | 2022 | R15/16
151693455266 | 151605245266 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-31 | 2022-11-02 | 2023-04-10 |  | 2023-08-18 | Underground | R15/16- Reloc | 2023-04-26 | 3 | 114 | 13 | 83 | 210 | 2022 | 2023 | R15/16
151678589881 | 151699999881 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-09-07 | 2022-09-07 | 2022-11-08 | 2023-01-06 | 2023-01-09 | Underground | R15/16- Reloc | 2023-01-06 | 1 | 45 | 44 | 2 | 89 | 2022 | 2023 | R15/16
151639879576 | 151649689576 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-19 | 2022-08-19 | 2022-08-19 | 2022-10-19 | 2023-01-05 | Overhead | R15/16 | 2022-10-19 | 1 |  | 44 | 57 | 100 | 2022 | 2023 | R15/16
151696752631 | 151697502631 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-09-06 | 2022-09-06 | 2022-09-06 | 2022-09-12 | 2022-09-15 | Underground | R15/16- Reloc | 2022-09-12 | 1 |  | 5 | 4 | 8 | 2022 | 2022 | R15/16
151697267791 | 151685777791 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-21 | 2022-10-21 | 2022-10-21 |  | 2023-02-03 | Underground | R15/16- Reloc | 2022-12-01 | 1 |  | 30 | 47 | 76 | 2022 | 2023 | R15/16
151684154921 | 151628864921 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-21 | 2022-09-21 | 2022-09-26 |  | 2023-01-10 | Overhead | R15/16 |  | 1 | 4 |  |  | 80 | 2022 | 2023 | R15/16
151669612764 | 151644032764 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-17 | 2022-09-06 | 2022-09-06 |  | 2023-01-10 | Overhead | R15/16 | 2022-11-17 | 15 |  | 53 | 39 | 105 | 2022 | 2023 | R15/16
151689297982 | 151610187982 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-02 | 2022-08-03 | 2022-08-05 | 2022-10-09 | 2023-01-24 | Underground | R15/16- Reloc | 2022-10-09 | 2 | 3 | 46 | 77 | 126 | 2022 | 2023 | R15/16
151645688716 | 151632998716 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-12 | 2022-08-12 | 2022-08-12 | 2022-10-31 | 2022-11-03 | Overhead | R15/16 | 2022-10-31 | 1 |  | 57 | 4 | 60 | 2022 | 2022 | R15/16
151638220577 | 151635210577 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-15 |  | 2022-11-15 | 2023-02-08 | 2023-02-28 | Overhead | R15/16 | 2023-02-08 |  |  | 62 | 15 | 76 | 2022 | 2023 | R15/16
151668578150 | 151693478150 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-25 | 2022-10-25 | 2022-10-25 | 2023-01-26 | 2023-02-16 | Overhead | R15/16 | 2023-01-26 | 1 |  | 68 | 16 | 83 | 2022 | 2023 | R15/16
151664467578 | 151653447578 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-07 | 2023-08-07 | 2023-08-08 | 2023-08-23 | 2023-09-19 | Underground | R15/16- Reloc | 2023-08-23 | 1 | 2 | 12 | 20 | 32 | 2023 | 2023 | R15/16
151639202255 | 151689102255 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-10-13 | 2023-10-13 | 2023-12-12 | 2023-12-13 | 2023-12-28 | Underground | R15/16- Reloc | 2023-12-13 | 1 | 43 | 2 | 12 | 55 | 2023 | 2023 | R15/16
151645277573 | 151608957573 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-02 |  | 2022-08-02 | 2022-12-21 | 2023-01-04 | Overhead | R15/16 | 2022-12-21 |  |  | 102 | 11 | 112 | 2022 | 2023 | R15/16
151621200960 | 151675130960 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-31 | 2022-08-31 | 2022-08-31 |  | 2022-10-17 | Underground | R15/16- Reloc | 2022-10-04 | 1 |  | 25 | 10 | 34 | 2022 | 2022 | R15/16
151633930790 | 151632060790 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-11 | 2022-08-11 | 2022-08-31 |  | 2023-06-01 | Overhead | R15/16 |  | 1 | 15 |  |  | 211 | 2022 | 2023 | R15/16
151608879500 | 151627869500 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-10 | 2022-08-10 | 2022-08-18 | 2022-10-10 | 2022-10-21 | Overhead | R15/16 | 2022-10-10 | 1 | 7 | 38 | 10 | 53 | 2022 | 2022 | R15/16
151601797594 | 151608367594 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-02 | 2022-08-02 | 2022-08-02 | 2022-09-21 | 2023-01-05 | Overhead | R15/16 | 2022-09-21 | 1 |  | 37 | 77 | 113 | 2022 | 2023 | R15/16
151646216093 | 151654186093 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-05 | 2022-10-05 | 2022-10-05 | 2023-04-05 | 2023-04-18 | Underground | R15/16- Reloc | 2023-04-05 | 1 |  | 131 | 10 | 140 | 2022 | 2023 | R15/16
151697789908 | 151638939908 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-15 | 2022-08-15 | 2022-08-22 | 2023-03-07 | 2023-03-24 | Overhead | R15/16 | 2023-03-07 | 1 | 6 | 142 | 14 | 160 | 2022 | 2023 | R15/16
151668997700 | 151654947700 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-07 | 2023-08-08 | 2023-08-08 | 2023-08-21 | 2023-09-01 | Underground | R15/16- Reloc | 2023-08-21 | 2 |  | 10 | 10 | 20 | 2023 | 2023 | R15/16
151655840920 | 151670420920 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-15 | 2023-08-15 | 2023-08-27 | 2023-10-27 | 2023-10-30 | Overhead | R15/16 | 2023-10-27 | 1 | 9 | 45 | 2 | 55 | 2023 | 2023 | R15/16
151670727288 | 151602827288 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-07-29 | 2022-07-29 | 2022-07-29 |  | 2022-11-30 | Overhead | R15/16 | 2022-11-18 | 1 |  | 81 | 9 | 89 | 2022 | 2022 | R15/16
151636603159 | 151653723159 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-30 | 2022-11-30 | 2022-12-21 | 2023-02-15 | 2023-02-25 | Underground | R15/16- Reloc | 2023-02-15 | 1 | 16 | 41 | 8 | 63 | 2022 | 2023 | R15/16
151619837232 | 151638497232 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-07-31 | 2023-07-31 | 2023-08-03 | 2023-09-18 | 2023-10-25 | Underground | R15/16- Reloc | 2023-09-18 | 1 | 4 | 33 | 28 | 63 | 2023 | 2023 | R15/16
151677306944 | 151602236944 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-28 | 2022-10-28 | 2023-04-25 | 2023-04-27 | 2023-06-13 | Underground | R15/16- Reloc | 2023-04-27 | 1 | 128 | 3 | 34 | 163 | 2022 | 2023 | R15/16
151677093087 | 151603323087 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-09 | 2022-09-09 | 2022-09-09 | 2022-11-22 | 2022-12-01 | Overhead | R15/16 | 2022-11-22 | 1 |  | 53 | 8 | 60 | 2022 | 2022 | R15/16
151613436224 | 151659916224 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-07 | 2022-10-07 | 2022-10-07 | 2022-12-14 | 2022-12-14 | Overhead | R15/16 | 2022-12-14 | 1 |  | 49 |  | 49 | 2022 | 2022 | R15/16
151695665308 | 151620185308 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-09-16 | 2022-09-16 | 2023-01-30 | 2023-06-27 | 2023-06-29 | Underground | R15/16- Reloc | 2023-06-27 | 1 | 97 | 107 | 3 | 205 | 2022 | 2023 | R15/16
151652541091 | 151607221091 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-29 | 2023-08-29 | 2023-08-29 | 2023-10-23 | 2023-11-01 | Overhead | R15/16 | 2023-10-23 | 1 |  | 40 | 8 | 47 | 2023 | 2023 | R15/16
151632679224 | 151639179224 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2022-11-17 | 2023-01-27 | 2023-11-09 | 2023-11-28 | 2023-12-18 | Underground | R15/16- Reloc | 2023-11-28 | 52 | 205 | 14 | 15 | 283 | 2022 | 2023 | R15/16
151692671306 | 151607491306 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-29 | 2023-08-29 | 2023-08-30 | 2023-08-31 | 2023-10-13 | Overhead | R15/16 | 2023-08-31 | 1 | 2 | 2 | 32 | 34 | 2023 | 2023 | R15/16
151662752297 | 151625132297 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-10 | 2022-12-06 | 2022-12-06 |  | 2023-02-01 | Overhead | R15/16 | 2023-01-17 | 19 |  | 31 | 12 | 60 | 2022 | 2023 | R15/16
151628897983 | 151661417983 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-10 | 2023-08-10 | 2023-08-10 | 2023-09-23 | 2023-09-26 | Underground | R15/16- Reloc | 2023-09-23 | 1 |  | 32 | 2 | 34 | 2023 | 2023 | R15/16
151655212972 | 151626782972 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-09-08 | 2023-09-18 | 2023-09-18 | 2023-10-24 | 2023-11-02 | Overhead | R15/16 | 2023-10-24 | 7 |  | 27 | 8 | 40 | 2023 | 2023 | R15/16
151666800115 | 151676080115 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-17 | 2023-08-21 | 2023-08-21 | 2023-09-19 | 2023-10-26 | Overhead | R15/16 | 2023-09-19 | 3 |  | 22 | 28 | 51 | 2023 | 2023 | R15/16
151650642713 | 151661222713 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2023-08-10 | 2023-08-17 | 2023-09-15 | 2023-10-21 | 2023-11-07 | Underground | R15/16- Reloc | 2023-10-21 | 6 | 22 | 26 | 12 | 64 | 2023 | 2023 | R15/16
151677980697 | 151635720697 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-07-28 | 2023-07-28 | 2023-08-26 | 2023-10-18 | 2023-10-24 | Underground | R15/16- Reloc | 2023-10-18 | 1 | 21 | 38 | 5 | 63 | 2023 | 2023 | R15/16
151654968454 | 151615928454 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-10-27 | 2023-11-03 | 2023-11-03 | 2023-11-03 | 2023-12-19 | Overhead | R15/16 | 2023-11-03 | 6 |  |  | 33 | 38 | 2023 | 2023 | R15/16
151613705249 | 151614105249 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-07-17 | 2023-07-17 | 2023-07-17 | 2023-07-24 | 2023-07-31 | Underground | R15/16- Reloc | 2023-07-24 | 1 |  | 6 | 6 | 11 | 2023 | 2023 | R15/16
151645972056 | 151639172056 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-07-31 | 2023-07-31 | 2023-09-08 | 2023-09-11 | 2023-10-11 | Underground | R15/16- Reloc | 2023-09-11 | 1 | 30 | 2 | 23 | 53 | 2023 | 2023 | R15/16
151644665822 | 151645235822 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-09-29 | 2022-09-29 | 2022-10-03 | 2022-11-07 | 2022-11-10 | Underground | R15/16- Reloc | 2022-11-07 | 1 | 3 | 26 | 4 | 31 | 2022 | 2022 | R15/16
151632676084 | 151639146084 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2022-11-17 | 2023-01-13 | 2023-10-17 | 2023-11-27 | 2023-12-18 | Underground | R15/16- Reloc | 2023-11-27 | 42 | 198 | 30 | 16 | 283 | 2022 | 2023 | R15/16
151643917787 | 151676977787 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-18 | 2022-10-21 | 2022-10-21 | 2023-03-05 | 2023-03-08 | Underground | R15/16- Reloc | 2023-03-05 | 4 |  | 96 | 3 | 102 | 2022 | 2023 | R15/16
151608544742 | 151632604742 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-23 | 2022-09-23 | 2022-09-23 |  | 2022-11-30 | Overhead | R15/16 | 2022-11-21 | 1 |  | 42 | 8 | 49 | 2022 | 2022 | R15/16
151658302325 | 151697342325 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-23 | 2023-08-28 | 2023-09-11 | 2023-10-01 | 2023-10-04 | Underground | R15/16- Reloc | 2023-10-01 | 4 | 11 | 15 | 3 | 31 | 2023 | 2023 | R15/16
151641867590 | 151672097590 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2022-10-13 | 2022-10-13 | 2022-10-20 | 2023-01-30 | 2023-04-24 | Underground | R15/16- Reloc | 2023-01-30 | 1 | 6 | 73 | 61 | 138 | 2022 | 2023 | R15/16
151671246410 | 151671406410 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2023-10-03 | 2023-10-03 | 2023-10-20 |  | 2023-12-11 | Underground | R15/16- Reloc |  | 1 | 14 |  |  | 50 | 2023 | 2023 | R15/16
151626544483 | 151649124483 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-19 |  | 2022-09-21 |  | 2022-11-30 | Overhead | R15/16 | 2022-11-22 |  |  | 45 | 7 | 74 | 2022 | 2022 | R15/16
151649018020 | 151607528020 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-01 | 2022-08-05 | 2022-08-05 |  | 2023-01-10 | Underground | R15/16- Reloc | 2022-11-16 | 5 |  | 74 | 40 | 117 | 2022 | 2023 | R15/16
151612633134 | 151620533134 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-09-06 | 2023-09-06 | 2023-09-20 | 2023-09-29 | 2023-10-19 | Underground | R15/16- Reloc | 2023-09-29 | 1 | 11 | 8 | 15 | 32 | 2023 | 2023 | R15/16
151629100564 | 151669020564 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-29 | 2022-08-29 | 2022-08-29 |  | 2023-08-14 | Underground | R15/16- Reloc | 2023-04-21 | 1 |  | 170 | 82 | 251 | 2022 | 2023 | R15/16
151649797587 | 151607617587 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-01 | 2022-08-01 | 2022-08-01 |  | 2022-08-19 | Underground | R15/16- Reloc | 2022-08-18 | 1 |  | 14 | 2 | 15 | 2022 | 2022 | R15/16
151625166254 | 151685896254 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH PRE ARR CUST WORK | Commercial | 2022-10-21 | 2022-10-21 | 2023-07-25 | 2023-07-27 | 2023-08-03 | Overhead | R15/16 | 2023-07-27 | 1 | 198 | 3 | 6 | 205 | 2022 | 2023 | R15/16
151675134135 | 151635864135 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-09-14 | 2023-09-14 | 2023-09-29 | 2023-09-29 | 2023-10-19 | Overhead | R15/16 | 2023-09-29 | 1 | 12 |  | 15 | 26 | 2023 | 2023 | R15/16
151636507211 | 151699537211 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-07-28 | 2022-07-28 | 2022-07-28 |  | 2022-11-17 | Overhead | R15/16 | 2022-11-15 | 1 |  | 79 | 3 | 81 | 2022 | 2022 | R15/16
151657716132 | 151667556132 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2023-10-02 | 2023-10-05 | 2023-10-18 | 2023-11-01 | 2023-11-21 | Underground | R15/16- Reloc | 2023-11-01 | 4 | 10 | 11 | 15 | 37 | 2023 | 2023 | R15/16
151644527998 | 151660117998 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-07 | 2022-10-07 | 2023-02-02 |  | 2023-08-11 | Underground | R15/16- Reloc | 2023-04-11 | 1 | 85 | 49 | 89 | 221 | 2022 | 2023 | R15/16
151677037442 | 151664467442 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-10 | 2022-10-10 | 2022-10-18 |  | 2023-03-24 | Underground | R15/16- Reloc | 2023-01-12 | 1 | 7 | 63 | 52 | 120 | 2022 | 2023 | R15/16
151666049686 | 151633779686 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Commercial | 2022-08-12 | 2022-08-12 | 2022-08-19 | 2023-01-05 | 2023-01-05 | Underground | R15/16- Reloc | 2023-01-05 | 1 | 6 | 100 |  | 105 | 2022 | 2023 | R15/16
151674484918 | 151622334918 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-09 | 2022-11-09 | 2023-01-30 | 2023-03-13 | 2023-03-16 | Underground | R15/16- Reloc | 2023-03-13 | 1 | 59 | 31 | 4 | 92 | 2022 | 2023 | R15/16
151698484963 | 151664094963 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-09-29 | 2023-09-29 | 2023-10-06 | 2023-10-31 | 2023-11-01 | Underground | R15/16- Reloc | 2023-10-31 | 1 | 6 | 18 | 2 | 24 | 2023 | 2023 | R15/16
151638564160 | 151664624160 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-09-29 | 2023-09-29 | 2023-09-29 | 2023-10-10 | 2023-10-11 | Underground | R15/16- Reloc | 2023-10-10 | 1 |  | 8 | 2 | 9 | 2023 | 2023 | R15/16
151646624161 | 151621824161 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-19 | 2022-09-19 | 2022-09-19 | 2023-04-14 | 2023-04-17 | Overhead | R15/16 | 2023-04-14 | 1 |  | 150 | 2 | 151 | 2022 | 2023 | R15/16
151659593808 | 151612603808 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-10-11 | 2022-10-14 | Overhead | R15/16 | 2022-10-11 | 2 | 2 | 19 | 4 | 24 | 2022 | 2022 | R15/16
151635234588 | 151655454588 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-30 | 2022-11-30 | 2023-01-30 | 2023-01-03 | 2023-04-13 | Underground | R15/16- Reloc | 2023-01-03 | 1 | 44 |  | 73 | 97 | 2022 | 2023 | R15/16
151619258083 | 151621978083 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-09-19 | 2022-09-19 | 2022-12-22 |  | 2023-01-25 | Underground | R15/16- Reloc | 2023-01-18 | 1 | 69 | 20 | 6 | 93 | 2022 | 2023 | R15/16
151666759845 | 151647979845 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-18 | 2022-08-22 | 2022-08-22 |  | 2023-03-02 | Underground | R15/16- Reloc | 2022-12-19 | 3 |  | 86 | 54 | 141 | 2022 | 2023 | R15/16
151644714921 | 151677214921 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-10-06 | 2023-10-06 | 2023-10-06 | 2023-11-07 | 2023-12-14 | Underground | R15/16- Reloc | 2023-11-07 | 1 |  | 23 | 28 | 50 | 2023 | 2023 | R15/16
151670479649 | 151607059649 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2022-08-01 | 2022-08-09 | 2022-08-19 |  | 2023-01-05 | Underground | R15/16- Reloc |  | 7 | 9 |  |  | 114 | 2022 | 2023 | R15/16
151648779141 | 151629149141 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-10 | 2022-08-15 | 2022-08-15 |  | 2023-06-26 | Overhead | R15/16 | 2023-03-17 | 4 |  | 155 | 72 | 229 | 2022 | 2023 | R15/16
151615872887 | 151658722887 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-24 | 2022-08-24 | 2022-09-07 |  | 2022-10-23 | Underground | R15/16- Reloc | 2022-10-06 | 1 | 11 | 22 | 12 | 43 | 2022 | 2022 | R15/16
151691576326 | 151692026326 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2023-10-16 | 2023-10-16 | 2023-10-19 |  | 2023-12-11 | Underground | R15/16- Reloc |  | 1 | 4 |  |  | 41 | 2023 | 2023 | R15/16
151659053705 | 151630493705 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-09-12 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-10-30 | Overhead | R15/16 | 2023-09-26 | 10 |  | 2 | 25 | 35 | 2023 | 2023 | R15/16
151610033204 | 151602963204 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-09-08 | 2022-09-08 | 2022-12-22 | 2023-01-30 | 2023-01-31 | Underground | R15/16- Reloc | 2023-01-30 | 1 | 76 | 28 | 2 | 104 | 2022 | 2023 | R15/16
151627551415 | 151645851415 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-02 | 2023-08-03 | 2023-09-01 | 2023-09-06 | 2023-10-10 | Underground | R15/16- Reloc | 2023-09-06 | 2 | 22 | 4 | 25 | 50 | 2023 | 2023 | R15/16
151601083762 | 151652023762 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-21 | 2022-08-30 | 2022-09-14 | 2023-01-05 | 2023-01-05 | Underground | R15/16- Reloc | 2023-01-05 | 7 | 12 | 82 |  | 99 | 2022 | 2023 | R15/16
151657999132 | 151607589132 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-01 |  | 2022-11-01 | 2022-11-03 | 2023-03-27 | Underground | R15/16- Reloc | 2022-11-03 |  |  | 3 | 103 | 105 | 2022 | 2023 | R15/16
151656312191 | 151696042191 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-23 | 2023-09-08 | 2023-09-11 | 2023-09-12 | 2023-10-12 | Overhead | R15/16 | 2023-09-12 | 13 | 2 | 2 | 23 | 37 | 2023 | 2023 | R15/16
151617002633 | 151676492633 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-17 | 2023-08-17 | 2023-09-14 | 2023-09-22 | 2023-11-08 | Underground | R15/16- Reloc | 2023-09-22 | 1 | 21 | 7 | 34 | 60 | 2023 | 2023 | R15/16
151677167165 | 151637047165 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-07-29 |  | 2023-08-02 | 2023-08-02 | 2023-08-30 | Overhead | R15/16 | 2023-08-02 |  |  |  | 21 | 23 | 2023 | 2023 | R15/16
151681407144 | 151696987144 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-07-27 | 2022-07-27 | 2022-07-27 | 2023-01-18 | 2023-02-08 | Overhead | R15/16 | 2023-01-18 | 1 |  | 126 | 16 | 141 | 2022 | 2023 | R15/16
151633370762 | 151670750762 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-15 | 2023-08-15 | 2023-08-25 | 2023-08-29 | 2023-09-28 | Underground | R15/16- Reloc | 2023-08-29 | 1 | 9 | 3 | 23 | 33 | 2023 | 2023 | R15/16
151689678148 | 151621028148 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-06 | 2022-08-06 | 2022-08-06 |  | 2023-03-02 | Underground | R15/16- Reloc | 2022-12-22 | 0 |  | 99 | 51 | 149 | 2022 | 2023 | R15/16
151669912302 | 151604612302 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-31 | 2022-10-31 | 2022-12-04 | 2023-02-01 | 2023-02-02 | Underground | R15/16- Reloc | 2023-02-01 | 1 | 25 | 43 | 2 | 69 | 2022 | 2023 | R15/16
151622257329 | 151621917329 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-07-20 | 2023-07-21 | 2023-08-04 | 2023-08-10 | 2023-09-15 | Underground | R15/16- Reloc | 2023-08-10 | 2 | 11 | 5 | 27 | 42 | 2023 | 2023 | R15/16
151682177402 | 151651517402 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-04 | 2023-08-04 | 2023-08-04 | 2023-09-15 | 2023-09-20 | Overhead | R15/16 | 2023-09-15 | 1 |  | 31 | 4 | 34 | 2023 | 2023 | R15/16
151615447796 | 151610637796 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-02 | 2022-08-03 | 2022-08-03 |  | 2022-09-08 | Overhead | R15/16 | 2022-09-06 | 2 |  | 25 | 3 | 28 | 2022 | 2022 | R15/16
151610908418 | 151632428418 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-07-26 | 2023-07-26 | 2023-08-15 | 2023-10-08 | 2023-10-11 | Underground | R15/16- Reloc | 2023-10-08 | 1 | 15 | 39 | 3 | 56 | 2023 | 2023 | R15/16
151681577536 | 151657197536 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-08 |  | 2023-08-08 | 2023-09-29 | 2023-12-05 | Overhead | R15/16 | 2023-09-29 |  |  | 39 | 48 | 86 | 2023 | 2023 | R15/16
151692402798 | 151648762798 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-03 | 2023-08-03 | 2023-09-18 | 2023-11-20 | 2023-11-22 | Underground | R15/16- Reloc | 2023-11-20 | 1 | 33 | 46 | 3 | 80 | 2023 | 2023 | R15/16
151633112349 | 151649172349 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-28 | 2022-12-05 | 2022-12-05 | 2023-02-12 | 2023-08-01 | Underground | R15/16- Reloc | 2023-02-12 | 6 |  | 50 | 122 | 177 | 2022 | 2023 | R15/16
151619692978 | 151631222978 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-14 | 2022-11-14 | 2022-12-21 | 2023-02-21 | 2023-03-03 | Underground | R15/16- Reloc | 2023-02-21 | 1 | 28 | 45 | 9 | 80 | 2022 | 2023 | R15/16
151655795913 | 151642185913 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-16 | 2022-10-04 | 2022-10-04 |  | 2023-01-10 | Underground | R15/16- Reloc | 2022-11-09 | 36 |  | 27 | 45 | 106 | 2022 | 2023 | R15/16
151686830706 | 151602250706 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-25 | 2023-08-25 | 2023-08-25 | 2023-09-18 | 2023-09-19 | Underground | R15/16- Reloc | 2023-09-18 | 1 |  | 17 | 2 | 18 | 2023 | 2023 | R15/16
151666129583 | 151682309583 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-19 | 2022-10-19 | 2022-11-04 |  | 2023-01-25 | Underground | R15/16- Reloc | 2023-01-18 | 1 | 13 | 54 | 6 | 71 | 2022 | 2023 | R15/16
151691818031 | 151625838031 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-07-24 | 2023-07-24 | 2023-08-11 | 2023-11-06 | 2023-11-09 | Underground | R15/16- Reloc | 2023-11-06 | 1 | 15 | 62 | 4 | 79 | 2023 | 2023 | R15/16
151614797902 | 151625637902 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2023-07-24 | 2023-07-24 | 2023-08-09 | 2023-08-17 | 2023-12-11 | Underground | R15/16- Reloc | 2023-08-17 | 1 | 13 | 7 | 83 | 101 | 2023 | 2023 | R15/16
151607420562 | 151651050562 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-04 | 2023-08-04 | 2023-08-24 | 2023-10-18 | 2023-10-25 | Underground | R15/16- Reloc | 2023-10-18 | 1 | 15 | 40 | 6 | 59 | 2023 | 2023 | R15/16
151617275291 | 151614935291 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-07-17 | 2023-07-17 | 2023-07-17 | 2023-08-14 | 2023-09-19 | Overhead | R15/16 | 2023-08-14 | 1 |  | 21 | 27 | 47 | 2023 | 2023 | R15/16
151611033613 | 151624343613 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2023-09-08 | 2023-09-08 | 2023-09-26 | 2023-10-03 | 2023-10-05 | Underground | R15/16- Reloc | 2023-10-03 | 1 | 13 | 6 | 3 | 20 | 2023 | 2023 | R15/16
151651463304 | 151654873304 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-30 | 2022-11-30 | 2022-12-14 | 2022-12-21 | 2023-03-24 | Underground | R15/16- Reloc | 2022-12-21 | 1 | 11 | 6 | 68 | 83 | 2022 | 2023 | R15/16
151647670037 | 151626380037 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-07-24 | 2023-07-24 | 2023-08-21 | 2023-10-11 | 2023-10-16 | Underground | R15/16- Reloc | 2023-10-11 | 1 | 21 | 38 | 4 | 61 | 2023 | 2023 | R15/16
151689977989 | 151610517989 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-02 | 2022-08-03 | 2022-08-05 | 2022-10-04 | 2022-10-06 | Underground | R15/16- Reloc | 2022-10-04 | 2 | 3 | 43 | 3 | 48 | 2022 | 2022 | R15/16
151664573606 | 151635633606 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-09-13 | 2023-09-25 | 2023-09-25 | 2023-09-29 | 2023-11-28 | Overhead | R15/16 | 2023-09-29 | 9 |  | 5 | 43 | 55 | 2023 | 2023 | R15/16
151649337535 | 151657407535 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS UD | Commercial | 2023-08-08 |  | 2023-08-08 | 2023-08-22 | 2023-08-25 | Underground | R15/16- Reloc | 2023-08-22 |  |  | 11 | 4 | 14 | 2023 | 2023 | R15/16
151699843344 | 151650953344 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2022-08-19 | 2022-08-30 | 2022-09-12 |  | 2023-10-27 | Underground | R15/16- Reloc | 2023-10-27 | 8 | 10 | 295 |  | 311 | 2022 | 2023 | R15/16
151602675848 | 151651605848 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-04 |  | 2022-10-04 | 2022-12-11 | 2022-12-11 | Underground | R15/16- Reloc | 2022-12-11 |  |  | 49 |  | 49 | 2022 | 2022 | R15/16
151655640489 | 151631320489 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-14 | 2022-11-14 | 2022-11-14 | 2023-05-15 | 2023-06-13 | Overhead | R15/16 | 2023-05-15 | 1 |  | 131 | 22 | 152 | 2022 | 2023 | R15/16
151660351636 | 151669271636 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2022-10-12 | 2022-11-21 | 2022-11-29 |  | 2023-05-17 | Underground | R15/16- Reloc |  | 29 | 7 |  |  | 156 | 2022 | 2023 | R15/16
151699596222 | 151601716222 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2022-09-08 | 2022-09-08 | 2022-10-07 |  | 2023-12-11 | Underground | R15/16- Reloc |  | 1 | 22 |  |  | 328 | 2022 | 2023 | R15/16
151627433519 | 151613063519 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-14 | 2022-09-14 | 2022-09-14 |  | 2022-12-15 | Overhead | R15/16 | 2022-12-14 | 1 |  | 66 | 2 | 67 | 2022 | 2022 | R15/16
151635170961 | 151669840961 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-15 | 2023-08-28 | 2023-08-28 | 2023-10-10 | 2023-10-18 | Underground | R15/16- Reloc | 2023-10-10 | 10 |  | 32 | 7 | 47 | 2023 | 2023 | R15/16
151641760036 | 151626350036 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-07-24 | 2023-07-24 | 2023-08-21 | 2023-10-24 | 2023-10-31 | Underground | R15/16- Reloc | 2023-10-24 | 1 | 21 | 47 | 6 | 72 | 2023 | 2023 | R15/16
151619434434 | 151630184434 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-22 | 2022-09-22 | 2022-09-22 |  | 2023-01-11 | Overhead | R15/16 | 2023-01-09 | 1 |  | 78 | 3 | 80 | 2022 | 2023 | R15/16
151662470370 | 151666000370 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-26 | 2022-08-26 | 2022-08-26 |  | 2022-09-23 | Overhead | R15/16 | 2022-09-14 | 1 |  | 14 | 8 | 21 | 2022 | 2022 | R15/16
151635960766 | 151602710766 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-25 | 2023-08-25 | 2023-08-25 | 2023-10-16 | 2023-11-14 | Overhead | R15/16 | 2023-10-16 | 1 |  | 37 | 22 | 58 | 2023 | 2023 | R15/16
151659859208 | 151641789208 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-16 | 2022-08-16 | 2022-08-16 |  | 2023-01-10 | Underground | R15/16- Reloc | 2022-11-10 | 1 |  | 63 | 44 | 106 | 2022 | 2023 | R15/16
151628242720 | 151663662720 | MODIFICATION OF EXISTING DISTRIB SYSTEM | UG NB SUPPORT BUDG 219 | Commercial | 2022-10-10 | 2022-12-22 | 2023-03-16 | 2023-03-29 | 2023-05-26 | Underground | R15/16- Reloc | 2023-03-29 | 54 | 61 | 10 | 43 | 165 | 2022 | 2023 | R15/16
151660351737 | 151669301737 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2022-10-12 | 2022-11-21 | 2022-11-29 |  | 2023-05-17 | Underground | R15/16- Reloc |  | 29 | 7 |  |  | 156 | 2022 | 2023 | R15/16
151636431930 | 151600731930 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-27 | 2022-10-27 | 2022-11-30 |  | 2023-02-26 | Underground | R15/16- Reloc | 2023-01-06 | 1 | 25 | 28 | 36 | 87 | 2022 | 2023 | R15/16
151639352068 | 151641012068 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2022-11-18 | 2022-11-18 | 2022-12-01 | 2022-12-01 | 2022-12-03 | Underground | R15/16- Reloc | 2022-12-01 | 1 | 10 |  | 2 | 11 | 2022 | 2022 | R15/16
151691172970 | 151609682970 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-02 | 2022-11-02 | 2022-12-21 | 2023-03-06 | 2023-03-09 | Overhead | R15/16 | 2023-03-06 | 1 | 36 | 54 | 4 | 92 | 2022 | 2023 | R15/16
151634061052 | 151604911052 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-31 | 2022-10-31 | 2022-11-17 |  | 2023-04-17 | Underground | R15/16- Reloc | 2023-01-26 | 1 | 14 | 51 | 58 | 121 | 2022 | 2023 | R15/16
151692014728 | 151663664728 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-25 | 2022-08-25 | 2022-09-24 |  | 2023-03-02 | Underground | R15/16- Reloc | 2022-12-19 | 1 | 22 | 61 | 54 | 136 | 2022 | 2023 | R15/16
151680657075 | 151698297075 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-07-28 | 2022-07-28 | 2022-07-28 | 2022-09-15 | 2023-01-05 | Overhead | R15/16 | 2022-09-15 | 1 |  | 36 | 81 | 116 | 2022 | 2023 | R15/16
151629036586 | 151606816586 | MODIFICATION OF EXISTING DISTRIB SYSTEM | OH NB SUPPORT BUDG 219 | Commercial | 2022-09-11 | 2022-09-28 | 2023-07-27 | 2023-08-14 | 2023-10-31 | Overhead | R15/16 | 2023-08-14 | 13 | 217 | 13 | 57 | 297 | 2022 | 2023 | R15/16
151608089510 | 151612839510 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-03 | 2022-11-03 | 2022-11-04 |  | 2023-06-27 | Overhead | R15/16 | 2023-03-01 | 1 | 2 | 84 | 85 | 169 | 2022 | 2023 | R15/16
151605306441 | 151689916441 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-10-13 | 2023-10-21 | 2023-10-21 | 2023-12-13 | 2023-12-26 | Underground | R15/16- Reloc | 2023-12-13 | 6 |  | 38 | 10 | 53 | 2023 | 2023 | R15/16
151666568595 | 151613128595 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-07-17 | 2023-07-17 | 2023-08-16 | 2023-09-26 | 2023-11-10 | Underground | R15/16- Reloc | 2023-09-26 | 1 | 23 | 30 | 34 | 85 | 2023 | 2023 | R15/16
151687738692 | 151677268692 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-18 | 2023-08-18 | 2023-08-18 | 2023-09-12 | 2023-10-23 | Overhead | R15/16 | 2023-09-12 | 1 |  | 18 | 30 | 47 | 2023 | 2023 | R15/16
151643713950 | 151649043950 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-28 | 2022-12-01 | 2022-12-22 |  | 2023-05-30 | Underground | R15/16- Reloc | 2023-02-07 | 4 | 16 | 34 | 81 | 132 | 2022 | 2023 | R15/16
151651548162 | 151695628162 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-10-17 | 2023-10-17 | 2023-10-31 | 2023-11-15 | 2023-12-12 | Underground | R15/16- Reloc | 2023-11-15 | 1 | 11 | 12 | 20 | 41 | 2023 | 2023 | R15/16
151685323405 | 151670953405 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-30 | 2022-09-12 | 2022-09-12 |  | 2023-01-10 | Overhead | R15/16 | 2022-11-03 | 10 |  | 39 | 49 | 96 | 2022 | 2023 | R15/16
151631598723 | 151670138723 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-15 | 2023-08-17 | 2023-08-17 | 2023-09-27 | 2023-10-10 | Underground | R15/16- Reloc | 2023-09-27 | 3 |  | 30 | 10 | 41 | 2023 | 2023 | R15/16
151634968077 | 151625468077 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-07 | 2023-12-11 | Overhead | R15/16 | 2023-11-07 | 1 |  | 6 | 25 | 30 | 2023 | 2023 | R15/16
151690243334 | 151602303334 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH DIST RELOC REARR CUST REQ | Residential | 2022-07-28 | 2022-10-28 | 2023-06-27 | 2023-07-06 | 2023-08-23 | Overhead | R15/16 | 2023-07-06 | 67 | 173 | 8 | 35 | 280 | 2022 | 2023 | R15/16
151632679227 | 151639189227 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS UD | Residential | 2022-11-17 | 2023-05-05 | 2023-11-09 | 2023-11-28 | 2023-12-18 | Underground | R15/16- Reloc | 2023-11-28 | 122 | 135 | 14 | 15 | 283 | 2022 | 2023 | R15/16
151698482577 | 151638532577 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-09-14 | 2023-09-14 | 2023-09-14 | 2023-09-20 | 2023-11-08 | Overhead | R15/16 | 2023-09-20 | 1 |  | 5 | 36 | 40 | 2023 | 2023 | R15/16
151661572897 | 151650502897 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-19 | 2022-08-19 | 2022-09-07 | 2022-10-12 | 2022-10-13 | Underground | R15/16- Reloc | 2022-10-12 | 1 | 14 | 26 | 2 | 40 | 2022 | 2022 | R15/16
151600075134 | 151604085134 | MODIFICATION OF EXISTING DISTRIB SYSTEM | OH NB SUPPORT BUDG 219 | Residential | 2022-10-31 | 2022-10-31 | 2023-04-07 | 2023-04-19 | 2023-05-26 | Overhead | R15/16 | 2023-04-19 | 1 | 115 | 9 | 28 | 150 | 2022 | 2023 | R15/16
151699728967 | 151657748967 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-11-02 | 2023-11-07 | 2023-11-07 | 2023-11-13 | 2023-11-21 | Overhead | R15/16 | 2023-11-13 | 4 |  | 5 | 7 | 14 | 2023 | 2023 | R15/16
151661270138 | 151659930138 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-09 | 2023-08-09 | 2023-08-21 | 2023-09-13 | 2023-11-01 | Underground | R15/16- Reloc | 2023-09-13 | 1 | 9 | 18 | 36 | 61 | 2023 | 2023 | R15/16
151657081570 | 151689581570 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-24 | 2022-11-28 | 2022-11-28 |  | 2023-04-03 | Overhead | R15/16 | 2023-01-17 | 26 |  | 37 | 55 | 116 | 2022 | 2023 | R15/16
151632514242 | 151651584242 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-22 | 2022-08-22 | 2023-01-30 | 2023-02-11 | 2023-02-14 | Underground | R15/16- Reloc | 2023-02-11 | 1 | 116 | 10 | 2 | 127 | 2022 | 2023 | R15/16
151642430424 | 151630200424 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-13 | 2022-11-13 | 2022-11-13 |  | 2023-04-27 | Underground | R15/16- Reloc | 2023-02-01 | 0 |  | 58 | 62 | 119 | 2022 | 2023 | R15/16
151641182920 | 151655212920 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-30 | 2022-12-09 | 2022-12-09 |  | 2023-10-06 | Overhead | R15/16 | 2023-06-30 | 8 |  | 146 | 71 | 223 | 2022 | 2023 | R15/16
151675232907 | 151624122907 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-09-19 | 2022-09-19 | 2022-12-09 |  | 2023-03-17 | Underground | R15/16- Reloc | 2023-01-04 | 1 | 60 | 19 | 53 | 130 | 2022 | 2023 | R15/16
151630285144 | 151642185144 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-28 |  | 2022-09-28 | 2023-01-18 | 2023-06-13 | Overhead | R15/16 | 2023-01-18 |  |  | 81 | 105 | 185 | 2022 | 2023 | R15/16
151607341773 | 151654681773 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Commercial | 2022-11-30 | 2022-11-30 | 2022-11-30 | 2023-01-22 | 2023-01-25 | Overhead | R15/16 | 2023-01-22 | 1 |  | 38 | 3 | 41 | 2022 | 2023 | R15/16
151634327431 | 151680007431 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-18 | 2022-10-18 | 2022-10-18 |  | 2023-03-27 | Overhead | R15/16 | 2023-01-13 | 1 |  | 64 | 52 | 115 | 2022 | 2023 | R15/16
151615730020 | 151623000020 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-09 | 2022-11-09 | 2022-11-09 | 2023-05-04 | 2023-06-12 | Overhead | R15/16 | 2023-05-04 | 1 |  | 127 | 28 | 154 | 2022 | 2023 | R15/16
151620232984 | 151602622984 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-25 | 2023-09-18 | 2023-09-18 | 2023-11-01 | 2023-11-28 | Overhead | R15/16 | 2023-11-01 | 17 |  | 33 | 20 | 68 | 2023 | 2023 | R15/16
151626092493 | 151604832493 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-07-30 | 2022-07-30 | 2022-09-03 | 2022-10-02 | 2022-10-05 | Underground | R15/16- Reloc | 2022-10-02 | 0 | 25 | 20 | 3 | 48 | 2022 | 2022 | R15/16
151652590312 | 151670030312 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-15 | 2023-08-15 | 2023-08-22 | 2023-11-08 | 2023-11-15 | Overhead | R15/16 | 2023-11-08 | 1 | 6 | 57 | 6 | 67 | 2023 | 2023 | R15/16
151625912143 | 151626002143 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-09-08 |  | 2023-09-08 | 2023-09-08 | 2023-09-27 | Underground | R15/16- Reloc | 2023-09-08 |  |  |  | 14 | 14 | 2023 | 2023 | R15/16
151629732697 | 151641202697 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-09-15 | 2023-09-15 | 2023-09-15 | 2023-09-21 | 2023-10-04 | Overhead | R15/16 | 2023-09-21 | 1 |  | 5 | 10 | 14 | 2023 | 2023 | R15/16
151665486806 | 151689056806 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-10-13 | 2023-10-13 | 2023-10-24 | 2023-11-10 | 2023-12-01 | Underground | R15/16- Reloc | 2023-11-10 | 1 | 8 | 14 | 16 | 36 | 2023 | 2023 | R15/16
151666330808 | 151606940808 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-01 | 2022-11-01 | 2022-11-16 |  | 2023-01-12 | Overhead | R15/16 | 2023-01-09 | 1 | 12 | 39 | 4 | 53 | 2022 | 2023 | R15/16
151626732789 | 151675642789 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-17 | 2022-10-17 | 2022-12-08 | 2023-03-01 | 2023-03-17 | Underground | R15/16- Reloc | 2023-03-01 | 1 | 39 | 60 | 13 | 110 | 2022 | 2023 | R15/16
151633136091 | 151653296091 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-05 | 2022-10-05 | 2022-10-05 | 2023-01-20 | 2023-01-28 | Underground | R15/16- Reloc | 2023-01-20 | 1 |  | 78 | 6 | 83 | 2022 | 2023 | R15/16
151628576400 | 151658266400 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-06 | 2022-10-07 | 2022-10-07 | 2022-12-18 | 2022-12-21 | Underground | R15/16- Reloc | 2022-12-18 | 2 |  | 51 | 3 | 55 | 2022 | 2022 | R15/16
151691098881 | 151632978881 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-12 | 2022-08-12 | 2022-08-12 |  | 2022-11-30 | Overhead | R15/16 | 2022-11-22 | 1 |  | 73 | 7 | 79 | 2022 | 2022 | R15/16
151643812214 | 151670062214 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-15 | 2023-08-15 | 2023-09-11 | 2023-11-07 | 2023-11-13 | Overhead | R15/16 | 2023-11-07 | 1 | 20 | 42 | 5 | 65 | 2023 | 2023 | R15/16
151602824946 | 151636014946 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-26 | 2022-09-26 | 2022-09-26 | 2023-06-22 | 2023-08-08 | Overhead | R15/16 | 2023-06-22 | 1 |  | 194 | 34 | 227 | 2022 | 2023 | R15/16
151600802924 | 151673602924 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-12-09 |  | 2022-12-09 | 2023-02-03 | 2023-02-06 | Overhead | R15/16 | 2023-02-03 |  |  | 41 | 2 | 42 | 2022 | 2023 | R15/16
151616947716 | 151666737716 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-11 | 2022-10-13 | 2022-10-21 |  | 2023-01-10 | Underground | R15/16- Reloc | 2022-11-09 | 3 | 7 | 14 | 45 | 66 | 2022 | 2023 | R15/16
151695767931 | 151691917931 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-24 | 2022-10-24 | 2022-10-24 | 2022-12-12 | 2022-12-15 | Underground | R15/16- Reloc | 2022-12-12 | 1 |  | 36 | 4 | 39 | 2022 | 2022 | R15/16
151678707312 | 151666137312 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Commercial | 2022-08-26 | 2022-10-12 | 2023-01-27 | 2023-06-02 | 2023-08-17 | Underground | R15/16- Reloc | 2023-06-02 | 34 | 78 | 91 | 55 | 255 | 2022 | 2023 | R15/16
151620916335 | 151659046335 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-09-27 | 2023-10-06 | 2023-10-20 | 2023-10-20 | 2023-11-06 | Underground | R15/16- Reloc | 2023-10-20 | 8 | 11 |  | 12 | 29 | 2023 | 2023 | R15/16
151646815068 | 151662965068 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-12-05 | 2022-12-05 | 2023-01-30 | 2023-01-05 | 2023-06-16 | Underground | R15/16- Reloc | 2023-01-05 | 1 | 41 |  | 117 | 140 | 2022 | 2023 | R15/16
151619852634 | 151600592634 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-24 | 2023-09-14 | 2023-09-14 | 2023-09-15 | 2023-11-02 | Overhead | R15/16 | 2023-09-15 | 16 |  | 2 | 35 | 51 | 2023 | 2023 | R15/16
151679350029 | 151654050029 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-23 | 2022-08-23 | 2022-08-23 |  | 2022-09-26 | Overhead | R15/16 | 2022-09-20 | 1 |  | 21 | 5 | 25 | 2022 | 2022 | R15/16
151608693160 | 151640163160 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-09-15 | 2023-09-19 | 2023-09-19 | 2023-10-30 | 2023-11-02 | Underground | R15/16- Reloc | 2023-10-30 | 3 |  | 30 | 4 | 35 | 2023 | 2023 | R15/16
151631198323 | 151654768323 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-08 | 2023-08-14 | 2023-08-14 | 2023-10-16 | 2023-10-23 | Underground | R15/16- Reloc | 2023-10-16 | 5 |  | 46 | 6 | 55 | 2023 | 2023 | R15/16
151609155719 | 151616995719 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2023-07-18 | 2023-07-21 | 2023-07-21 | 2023-07-27 | 2023-07-28 | Underground | R15/16- Reloc | 2023-07-27 | 4 |  | 5 | 2 | 9 | 2023 | 2023 | R15/16
151657446134 | 151667806134 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2023-10-02 | 2023-10-03 | 2023-10-18 | 2023-10-31 | 2023-11-21 | Underground | R15/16- Reloc | 2023-10-31 | 2 | 12 | 10 | 16 | 37 | 2023 | 2023 | R15/16
151611653709 | 151614403709 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Commercial | 2022-09-14 | 2022-09-14 | 2022-09-14 | 2023-01-05 | 2023-01-05 | Underground | R15/16- Reloc | 2023-01-05 | 1 |  | 82 |  | 82 | 2022 | 2023 | R15/16
151695620519 | 151610480519 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-02 | 2022-11-15 | 2022-11-15 | 2022-12-07 | 2023-03-02 | Overhead | R15/16 | 2022-12-07 | 10 |  | 17 | 62 | 87 | 2022 | 2023 | R15/16
151685098729 | 151677438729 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-18 | 2023-08-18 | 2023-08-18 | 2023-10-13 | 2023-10-24 | Underground | R15/16- Reloc | 2023-10-13 | 1 |  | 41 | 8 | 48 | 2023 | 2023 | R15/16
151677222971 | 151637612971 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-09-14 | 2023-09-18 | 2023-09-18 | 2023-11-15 | 2023-11-21 | Overhead | R15/16 | 2023-11-15 | 3 |  | 43 | 5 | 49 | 2023 | 2023 | R15/16
151608829123 | 151672809123 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-13 | 2022-11-01 | 2022-11-01 | 2023-01-19 | 2023-04-13 | Overhead | R15/16 | 2023-01-19 | 14 |  | 58 | 61 | 131 | 2022 | 2023 | R15/16
151698060912 | 151605680912 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-28 |  | 2023-08-28 | 2023-09-14 | 2023-12-08 | Overhead | R15/16 | 2023-09-14 |  |  | 14 | 62 | 75 | 2023 | 2023 | R15/16
151688176647 | 151658896647 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-07 | 2022-10-10 | 2022-10-10 |  | 2023-01-10 | Overhead | R15/16 | 2022-11-10 | 2 |  | 24 | 44 | 68 | 2022 | 2023 | R15/16
151697434198 | 151606524198 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-09-12 | 2022-09-12 | 2022-09-20 | 2023-02-07 | 2023-03-24 | Underground | R15/16- Reloc | 2023-02-07 | 1 | 7 | 101 | 34 | 140 | 2022 | 2023 | R15/16
151601148969 | 151605798969 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2023-02-05 | 2023-02-08 | Overhead | R15/16 | 2023-02-05 | 1 |  | 69 | 3 | 72 | 2022 | 2023 | R15/16
151617288264 | 151667078264 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-14 | 2023-08-14 | 2023-08-14 | 2023-09-18 | 2023-09-18 | Underground | R15/16- Reloc | 2023-09-18 | 1 |  | 26 |  | 26 | 2023 | 2023 | R15/16
151682294524 | 151663044524 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-25 | 2022-08-25 | 2022-09-21 |  | 2022-12-05 | Underground | R15/16- Reloc | 2022-12-01 | 1 | 20 | 52 | 3 | 73 | 2022 | 2022 | R15/16
151688815569 | 151644445569 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-22 | 2022-11-22 | 2023-01-30 | 2023-03-21 | 2023-03-22 | Underground | R15/16- Reloc | 2023-03-21 | 1 | 50 | 37 | 2 | 87 | 2022 | 2023 | R15/16
151634628662 | 151679128662 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-18 | 2022-10-28 | 2022-10-28 |  | 2023-06-27 | Overhead | R15/16 | 2023-05-25 | 9 |  | 150 | 24 | 181 | 2022 | 2023 | R15/16
151617582334 | 151633012334 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-09-12 | 2023-09-12 | 2023-09-12 | 2023-11-15 | 2023-12-08 | Overhead | R15/16 | 2023-11-15 | 1 |  | 47 | 18 | 64 | 2023 | 2023 | R15/16
151673220245 | 151613830245 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-09-14 | 2022-09-14 | 2023-02-23 |  | 2023-07-28 | Underground | R15/16- Reloc | 2023-04-04 | 1 | 117 | 29 | 84 | 228 | 2022 | 2023 | R15/16
151622600071 | 151656150071 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-23 | 2022-08-23 | 2022-08-23 |  | 2023-02-09 | Overhead | R15/16 | 2023-02-07 | 1 |  | 121 | 3 | 123 | 2022 | 2023 | R15/16
151602916995 | 151647466995 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Commercial | 2022-11-23 | 2022-11-29 | 2023-04-26 |  | 2023-08-18 | Underground | R15/16- Reloc |  | 5 | 107 |  |  | 193 | 2022 | 2023 | R15/16
151666040306 | 151634370306 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2022-08-12 | 2022-08-12 | 2022-08-25 | 2023-01-05 | 2023-01-05 | Underground | R15/16- Reloc | 2023-01-05 | 1 | 10 | 96 |  | 105 | 2022 | 2023 | R15/16
151645870982 | 151602870982 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-25 | 2023-08-28 | 2023-08-28 | 2023-10-13 | 2023-10-27 | Underground | R15/16- Reloc | 2023-10-13 | 2 |  | 35 | 11 | 46 | 2023 | 2023 | R15/16
151695544132 | 151608684132 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-12 | 2022-09-19 | 2022-09-19 | 2022-12-06 | 2022-12-09 | Overhead | R15/16 | 2022-12-06 | 6 |  | 57 | 4 | 65 | 2022 | 2022 | R15/16
151694254447 | 151617374447 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-09-15 | 2022-09-21 | 2022-09-21 | 2023-01-05 | 2023-01-05 | Underground | R15/16- Reloc | 2023-01-05 | 5 |  | 77 |  | 81 | 2022 | 2023 | R15/16
151614984722 | 151616824722 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2022-09-15 | 2022-09-15 | 2022-09-23 | 2022-09-27 | 2022-09-27 | Underground | R15/16- Reloc | 2022-09-27 | 1 | 7 | 3 |  | 9 | 2022 | 2022 | R15/16
151645736622 | 151663036622 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-10 | 2022-10-10 | 2022-10-10 |  | 2023-07-28 | Overhead | R15/16 | 2023-03-22 | 1 |  | 118 | 93 | 210 | 2022 | 2023 | R15/16
151649136853 | 151671536853 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-13 | 2022-10-13 | 2022-10-13 |  | 2022-11-11 | Overhead | R15/16 | 2022-11-09 | 1 |  | 20 | 3 | 22 | 2022 | 2022 | R15/16
151659637794 | 151678057794 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-18 | 2022-10-21 | 2022-10-21 | 2022-11-29 | 2022-11-29 | Underground | R15/16- Reloc | 2022-11-29 | 4 |  | 28 |  | 31 | 2022 | 2022 | R15/16
151627967627 | 151648637627 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-03 | 2023-08-07 | 2023-08-07 | 2023-10-30 | 2023-11-07 | Overhead | R15/16 | 2023-10-30 | 3 |  | 61 | 7 | 69 | 2023 | 2023 | R15/16
151696069353 | 151612879353 | STREET AND HIGHWAY RELOCATION | UG ELEC SVC RFS US | Commercial | 2022-11-03 | 2022-11-03 | 2022-11-03 |  | 2022-12-04 | Underground | R15/16- Reloc | 2022-11-15 | 1 |  | 9 | 14 | 22 | 2022 | 2022 | R15/16
151607917646 | 151648877646 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2022-10-03 | 2022-10-10 | 2022-10-20 |  | 2023-01-10 | Underground | R15/16- Reloc |  | 6 | 9 |  |  | 72 | 2022 | 2023 | R15/16
151639098788 | 151682158788 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-19 | 2022-10-31 | 2022-10-31 | 2023-03-05 | 2023-03-08 | Underground | R15/16- Reloc | 2023-03-05 | 9 |  | 90 | 3 | 101 | 2022 | 2023 | R15/16
151683949216 | 151673799216 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Commercial | 2022-08-31 | 2022-08-31 | 2023-02-13 |  | 2023-06-23 | Underground | R15/16- Reloc |  | 1 | 119 |  |  | 213 | 2022 | 2023 | R15/16
151656152163 | 151655382163 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2022-11-30 | 2022-11-30 | 2022-12-02 |  | 2023-05-17 | Underground | R15/16- Reloc |  | 1 | 3 |  |  | 121 | 2022 | 2023 | R15/16
151655590578 | 151670670578 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-30 | 2022-08-30 | 2022-08-30 | 2023-02-22 | 2023-03-17 | Overhead | R15/16 | 2023-02-22 | 1 |  | 127 | 18 | 144 | 2022 | 2023 | R15/16
151618529392 | 151668689392 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-10-03 | 2023-10-03 | 2023-11-10 | 2023-11-16 | 2023-11-29 | Underground | R15/16- Reloc | 2023-11-16 | 1 | 29 | 5 | 10 | 42 | 2023 | 2023 | R15/16
151643854183 | 151658664183 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-24 | 2022-08-24 | 2022-09-19 | 2022-10-03 | 2022-10-18 | Underground | R15/16- Reloc | 2022-10-03 | 1 | 19 | 11 | 12 | 40 | 2022 | 2022 | R15/16
151605419534 | 151679619534 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Commercial | 2022-10-18 | 2022-10-18 | 2022-11-04 |  | 2023-08-02 | Underground | R15/16- Reloc |  | 1 | 14 |  |  | 207 | 2022 | 2023 | R15/16
151693229584 | 151607519584 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-01 | 2022-11-04 | 2022-11-04 |  | 2023-06-01 | Underground | R15/16- Reloc | 2023-02-27 | 4 |  | 82 | 69 | 153 | 2022 | 2023 | R15/16
151655413722 | 151654683722 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-26 | 2023-10-17 | Underground | R15/16- Reloc | 2023-09-26 | 1 | 2 |  | 16 | 17 | 2023 | 2023 | R15/16
151657258559 | 151676158559 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-10-17 | 2022-10-17 | 2022-10-28 | 2023-01-23 | 2023-01-26 | Underground | R15/16- Reloc | 2023-01-23 | 1 | 10 | 62 | 4 | 74 | 2022 | 2023 | R15/16
151608022846 | 151623972846 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-07-22 | 2023-07-22 | 2023-09-16 | 2023-11-26 | 2023-11-29 | Underground | R15/16- Reloc | 2023-11-26 | 0 | 40 | 50 | 3 | 93 | 2023 | 2023 | R15/16
151636522008 | 151611712008 | MOBILE HOMES PARK AB622 | OH DIST RELOC REARR CUST REQ | Residential | 2022-08-03 | 2022-08-03 | 2023-06-12 | 2023-07-24 | 2023-08-23 | Overhead | R15/16 | 2023-07-24 | 1 | 224 | 31 | 23 | 276 | 2022 | 2023 | R15/16
151665961508 | 151613421508 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-31 | 2023-09-01 | 2023-09-01 | 2023-09-22 | 2023-09-28 | Underground | R15/16- Reloc | 2023-09-22 | 2 |  | 16 | 5 | 21 | 2023 | 2023 | R15/16
151653130014 | 151656230014 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-23 | 2022-08-23 | 2022-08-23 | 2023-06-25 | 2023-06-29 | Underground | R15/16- Reloc | 2023-06-25 | 1 |  | 219 | 4 | 223 | 2022 | 2023 | R15/16
151670170721 | 151671300721 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-30 | 2022-08-30 | 2022-08-30 | 2023-01-05 | 2023-01-23 | Overhead | R15/16 | 2023-01-05 | 1 |  | 93 | 13 | 105 | 2022 | 2023 | R15/16
151636782966 | 151648992966 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-28 | 2022-12-12 | 2022-12-16 |  | 2023-04-17 | Underground | R15/16- Reloc | 2023-01-26 | 11 | 5 | 30 | 58 | 101 | 2022 | 2023 | R15/16
151676131604 | 151612771604 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-08-31 | 2023-08-31 | 2023-09-04 | 2023-09-11 | 2023-09-28 | Underground | R15/16- Reloc | 2023-09-11 | 1 | 3 | 6 | 14 | 21 | 2023 | 2023 | R15/16
151698089640 | 151606939640 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-01 | 2022-08-01 | 2022-08-19 | 2022-10-06 | 2023-01-05 | Underground | R15/16- Reloc | 2022-10-06 | 1 | 15 | 35 | 66 | 114 | 2022 | 2023 | R15/16
151631347758 | 151659257758 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-09 | 2023-08-09 | 2023-08-09 | 2023-08-31 | 2023-10-10 | Overhead | R15/16 | 2023-08-31 | 1 |  | 17 | 29 | 45 | 2023 | 2023 | R15/16
151612198594 | 151610658594 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-02 | 2022-08-02 | 2022-08-10 |  | 2022-10-23 | Underground | R15/16- Reloc | 2022-10-04 | 1 | 7 | 40 | 14 | 59 | 2022 | 2022 | R15/16
151683216220 | 151623166220 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH DIST RELOC REARR CUST REQ | Residential | 2022-08-08 | 2022-08-08 | 2022-10-06 | 2022-10-17 | 2022-11-03 | Overhead | R15/16 | 2022-10-17 | 1 | 44 | 8 | 14 | 64 | 2022 | 2022 | R15/16
151639044466 | 151602194466 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-09-08 | 2022-09-08 | 2022-09-21 | 2023-01-05 | 2023-01-05 | Underground | R15/16- Reloc | 2023-01-05 | 1 | 10 | 77 |  | 86 | 2022 | 2023 | R15/16
151618839468 | 151647649468 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-18 | 2022-08-18 | 2022-08-18 | 2022-09-29 | 2023-01-05 | Overhead | R15/16 | 2022-09-29 | 1 |  | 31 | 71 | 101 | 2022 | 2023 | R15/16
151684112750 | 151648652750 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-28 | 2022-11-28 | 2022-12-08 | 2023-03-01 | 2023-03-17 | Underground | R15/16- Reloc | 2023-03-01 | 1 | 9 | 60 | 13 | 80 | 2022 | 2023 | R15/16
151681239488 | 151613299488 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-04 | 2022-11-04 | 2022-11-04 | 2023-01-18 | 2023-02-10 | Overhead | R15/16 | 2023-01-18 | 1 |  | 54 | 18 | 71 | 2022 | 2023 | R15/16
151688664212 | 151625264212 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-20 | 2022-09-20 | 2022-09-20 | 2022-10-05 | 2023-01-05 | Overhead | R15/16 | 2022-10-05 | 1 |  | 12 | 67 | 78 | 2022 | 2023 | R15/16
151629012249 | 151641712249 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-11-18 |  | 2022-11-18 | 2023-02-15 | 2023-03-08 | Underground | R15/16- Reloc | 2023-02-15 |  |  | 64 | 16 | 79 | 2022 | 2023 | R15/16
151648618474 | 151627588474 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-08-10 |  | 2022-08-10 | 2022-10-13 | 2023-02-17 | Overhead | R15/16 | 2022-10-13 |  |  | 47 | 92 | 138 | 2022 | 2023 | R15/16
151665722706 | 151639972706 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-09-15 | 2023-09-15 | 2023-09-15 | 2023-09-21 | 2023-11-15 | Overhead | R15/16 | 2023-09-21 | 1 |  | 5 | 40 | 44 | 2023 | 2023 | R15/16
151668571817 | 151621861817 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-09-07 | 2023-09-07 | 2023-09-07 | 2023-12-12 | 2023-12-14 | Overhead | R15/16 | 2023-12-12 | 1 |  | 69 | 3 | 71 | 2023 | 2023 | R15/16
151671493422 | 151606843422 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-12 | 2022-09-12 | 2022-09-12 |  | 2022-12-11 | Overhead | R15/16 | 2022-12-05 | 1 |  | 61 | 5 | 65 | 2022 | 2022 | R15/16
151651044683 | 151610864683 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2022-09-13 | 2022-12-30 | 2023-01-30 | 2023-01-03 | 2023-07-28 | Underground | R15/16- Reloc | 2023-01-03 | 79 | 22 |  | 149 | 229 | 2022 | 2023 | R15/16
151618787443 | 151679337443 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-10-18 | 2022-10-18 | 2022-10-18 | 2023-01-05 | 2023-01-05 | Overhead | R15/16 | 2023-01-05 | 1 |  | 58 |  | 58 | 2022 | 2023 | R15/16
151679313642 | 151611853642 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-13 | 2022-09-13 | 2022-09-13 |  | 2022-11-30 | Overhead | R15/16 | 2022-11-22 | 1 |  | 51 | 7 | 57 | 2022 | 2022 | R15/16
151699855941 | 151637875941 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Commercial | 2022-08-15 | 2022-08-16 | 2022-10-04 |  | 2023-06-16 | Underground | R15/16- Reloc |  | 2 | 36 |  |  | 220 | 2022 | 2023 | R15/16
151660351730 | 151669281730 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2022-10-12 | 2022-11-21 | 2022-11-29 | 2023-06-16 | 2023-07-07 | Underground | R15/16- Reloc | 2023-06-16 | 29 | 7 | 144 | 16 | 193 | 2022 | 2023 | R15/16
151628903824 | 151629753824 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-09-11 | 2023-09-11 | 2023-09-27 | 2023-10-09 | 2023-10-24 | Underground | R15/16- Reloc | 2023-10-09 | 1 | 13 | 9 | 12 | 32 | 2023 | 2023 | R15/16
151697305877 | 151619715877 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-16 | 2023-07-21 | 2023-07-21 | 2023-08-04 | 2023-08-21 | Overhead | R15/16 | 2023-08-04 | 221 |  | 11 | 12 | 242 | 2022 | 2023 | R15/16
151619746842 | 151632926842 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Commercial | 2022-09-23 | 2022-09-23 | 2023-01-30 | 2023-01-23 | 2023-08-14 | Underground | R15/16- Reloc | 2023-01-23 | 1 | 92 |  | 146 | 232 | 2022 | 2023 | R15/16
151637821834 | 151655531834 |  | UG MISC STREET LIGHTING SL |  | 2022-11-30 | 2022-11-30 | 2022-11-30 | 2023-03-30 | 2023-02-21 | Underground | R15/16- Reloc | 2023-03-30 | 1 |  | 87 |  | 60 | 2022 | 2023 | R15/16
151626316846 | 151637816846 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-07-30 | 2023-07-30 | 2023-07-30 | 2023-10-05 | 2023-11-08 | Overhead | R15/16 | 2023-10-05 | 0 |  | 49 | 25 | 73 | 2023 | 2023 | R15/16
151621053543 | 151640023543 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-09-15 | 2023-09-15 | 2023-09-22 | 2023-09-27 | 2023-10-10 | Underground | R15/16- Reloc | 2023-09-27 | 1 | 6 | 4 | 10 | 18 | 2023 | 2023 | R15/16
151631180524 | 151630660524 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-14 |  | 2022-11-14 |  | 2023-03-31 | Overhead | R15/16 | 2023-03-24 |  |  | 95 | 6 | 100 | 2022 | 2023 | R15/16
151690959647 | 151616549647 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-11-07 | 2022-11-07 | 2022-11-07 | 2023-01-26 | 2023-02-18 | Overhead | R15/16 | 2023-01-26 | 1 |  | 59 | 17 | 75 | 2022 | 2023 | R15/16
151628715056 | 151638445056 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-09-27 | 2022-09-27 | 2022-09-27 | 2022-12-21 | 2023-02-17 | Overhead | R15/16 | 2022-12-21 | 1 |  | 62 | 43 | 104 | 2022 | 2023 | R15/16
151656228451 | 151614628451 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-10-27 | 2023-11-03 | 2023-11-03 | 2023-11-20 | 2023-12-19 | Overhead | R15/16 | 2023-11-20 | 6 |  | 12 | 22 | 38 | 2023 | 2023 | R15/16
151645467346 | 151665687346 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2022-10-11 | 2022-10-11 | 2022-10-17 | 2022-10-17 | 2023-01-05 | Underground | R15/16- Reloc | 2022-10-17 | 1 | 5 |  | 59 | 63 | 2022 | 2023 | R15/16
151688124477 | 151669304477 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-29 | 2022-08-31 | 2022-09-21 |  | 2023-03-16 | Underground | R15/16- Reloc | 2022-12-05 | 3 | 16 | 54 | 74 | 144 | 2022 | 2023 | R15/16
151630082124 | 151675352124 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-08-17 | 2023-09-08 | 2023-09-08 | 2023-09-25 | 2023-11-28 | Overhead | R15/16 | 2023-09-25 | 17 |  | 12 | 47 | 74 | 2023 | 2023 | R15/16
151695529148 | 151623879148 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-08-09 | 2022-08-16 | 2022-08-16 | 2022-09-02 | 2022-09-06 | Underground | R15/16- Reloc | 2022-09-02 | 6 |  | 14 | 3 | 21 | 2022 | 2022 | R15/16
151669355545 | 151620635545 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH DIST RELOC REARR CUST REQ | Commercial | 2021-06-04 | 2021-06-04 | 2021-06-18 | 2021-06-25 | 2021-07-20 | Overhead | R15/16 | 2021-06-25 | 1 | 11 | 6 | 18 | 33 | 2021 | 2021 | R15/16
151662929127 | 151680899127 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Commercial | 2021-06-30 | 2021-07-01 | 2021-07-15 |  | 2021-08-23 | Underground | R15/16- Reloc |  | 2 | 11 |  |  | 39 | 2021 | 2021 | R15/16
151673795803 | 151613345803 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2021-07-15 | 2021-07-19 | 2021-08-30 |  | 2023-05-22 | Underground | R15/16- Reloc |  | 3 | 31 |  |  | 483 | 2021 | 2023 | R15/16
151697246033 | 151633356033 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2021-06-09 | 2021-06-21 | 2021-06-21 |  | 2021-08-23 | Overhead | R15/16 | 2021-07-13 | 9 |  | 17 | 30 | 54 | 2021 | 2021 | R15/16
151662044227 | 151630524227 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2021-07-22 | 2021-08-18 | 2021-08-18 |  | 2021-12-16 | Underground | R15/16- Reloc | 2021-11-15 | 20 |  | 64 | 24 | 106 | 2021 | 2021 | R15/16
151640460381 | 151630350381 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2021-07-22 | 2021-07-22 | 2021-07-23 |  | 2021-10-25 | Underground | R15/16- Reloc | 2021-09-21 | 1 | 2 | 43 | 25 | 68 | 2021 | 2021 | R15/16
151662058361 | 151679278361 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2021-06-30 | 2021-07-01 | 2021-07-09 |  | 2023-05-21 | Underground | R15/16- Reloc | 2021-09-13 | 2 | 7 | 47 | 440 | 493 | 2021 | 2023 | R15/16
151649089132 | 151677919132 |  | UG MISC STREET LIGHTING SL |  | 2021-06-29 | 2021-07-15 | 2021-07-15 |  | 2021-11-16 | Underground | R15/16- Reloc |  | 13 |  |  |  | 101 | 2021 | 2021 | R15/16
151699576896 | 151621966896 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2021-06-04 | 2021-06-11 | 2021-06-29 | 2021-07-10 | 2021-07-13 | Underground | R15/16- Reloc | 2021-07-10 | 6 | 13 | 9 | 2 | 28 | 2021 | 2021 | R15/16
151669596703 | 151683056703 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2021-07-01 | 2021-07-01 | 2021-09-07 |  | 2021-11-09 | Underground | R15/16- Reloc | 2021-10-29 | 1 | 49 | 39 | 8 | 94 | 2021 | 2021 | R15/16
151671101095 | 151630331095 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Residential | 2021-07-22 | 2021-07-22 | 2021-07-29 | 2021-08-11 | 2021-09-10 | Underground | R15/16- Reloc | 2021-08-11 | 1 | 6 | 10 | 23 | 37 | 2021 | 2021 | R15/16
151648120675 | 151626150675 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Commercial | 2021-06-07 | 2021-06-07 | 2021-07-26 |  | 2021-10-25 | Underground | R15/16- Reloc | 2021-08-24 | 1 | 36 | 22 | 45 | 101 | 2021 | 2021 | R15/16
151622048567 | 151653218567 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2021-06-17 | 2021-06-17 | 2021-07-12 | 2021-07-15 | 2021-07-20 | Underground | R15/16- Reloc | 2021-07-15 | 1 | 18 | 4 | 4 | 24 | 2021 | 2021 | R15/16
151649959039 | 151679519039 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2021-06-29 | 2021-06-29 | 2021-07-15 | 2021-09-15 | 2021-09-16 | Underground | R15/16- Reloc | 2021-09-15 | 1 | 13 | 45 | 2 | 58 | 2021 | 2021 | R15/16
151662011728 | 151627811728 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2021-07-22 | 2021-08-02 | 2021-08-02 |  | 2021-12-03 | Underground | R15/16- Reloc | 2021-11-09 | 8 |  | 72 | 19 | 97 | 2021 | 2021 | R15/16
151649723202 | 151601893202 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Commercial | 2021-07-13 | 2021-07-13 | 2022-06-20 | 2022-12-08 | 2022-12-21 | Underground | R15/16- Reloc | 2022-12-08 | 1 | 245 | 124 | 10 | 377 | 2021 | 2022 | R15/16
151688452469 | 151685342469 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2021-07-02 | 2021-08-06 | 2021-08-06 |  | 2021-09-14 | Overhead | R15/16 | 2021-08-19 | 26 |  | 10 | 19 | 53 | 2021 | 2021 | R15/16
151621446734 | 151673086734 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2021-06-26 | 2021-06-26 | 2021-06-26 |  | 2022-05-19 | Overhead | R15/16 | 2022-04-27 | 0 |  | 218 | 17 | 234 | 2021 | 2022 | R15/16
151683706333 | 151628056333 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2021-06-08 | 2021-06-23 | 2021-06-23 |  | 2021-10-25 | Overhead | R15/16 | 2021-09-02 | 12 |  | 52 | 38 | 100 | 2021 | 2021 | R15/16
151696057419 | 151618787419 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2021-06-03 | 2021-06-03 | 2021-06-30 | 2021-07-26 | 2021-07-29 | Underground | R15/16- Reloc | 2021-07-26 | 1 | 20 | 19 | 4 | 41 | 2021 | 2021 | R15/16
151694296284 | 151634446284 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2021-06-09 | 2021-06-22 | 2021-06-22 |  | 2021-11-08 | Underground | R15/16- Reloc | 2021-09-20 | 10 |  | 65 | 36 | 109 | 2021 | 2021 | R15/16
151630902066 | 151640172066 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Commercial | 2021-06-11 | 2021-07-22 | 2022-12-01 | 2023-04-18 | 2023-08-14 | Underground | R15/16- Reloc | 2023-04-18 | 30 | 356 | 99 | 85 | 567 | 2021 | 2023 | R15/16
151694304883 | 151620234883 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2021-06-03 | 2021-06-03 | 2021-06-13 | 2022-04-20 | 2022-04-20 | Underground | R15/16- Reloc | 2022-04-20 | 1 | 7 | 223 |  | 230 | 2021 | 2022 | R15/16
151693715153 | 151695525153 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2020-05-28 | 2020-06-09 | 2020-06-24 | 2020-07-01 | 2021-09-09 | Underground | R15/16- Reloc | 2020-07-01 | 9 | 12 | 6 | 312 | 336 | 2020 | 2021 | R15/16
151627968083 | 151653028083 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-01-22 | 2020-01-22 | 2020-01-25 |  | 2020-06-09 | Overhead | R15/16 | 2020-04-07 | 1 | 3 | 52 | 46 | 100 | 2020 | 2020 | R15/16
151632991007 | 151647811007 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-04-30 | 2020-05-14 | 2020-05-14 |  | 2020-07-09 | Underground | R15/16- Reloc | 2020-05-28 | 11 |  | 11 | 31 | 51 | 2020 | 2020 | R15/16
151665530116 | 151629800116 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-01-13 | 2020-01-24 | 2020-02-12 |  | 2020-06-09 | Overhead | R15/16 |  | 10 | 14 |  |  | 107 | 2020 | 2020 | R15/16
151660411727 | 151648631727 | SPECIFIC BUDGET PROJECTS | OH DIST SPECIFIC BUDG PROJ | Commercial | 2020-04-30 | 2020-10-28 | 2020-11-23 |  | 2021-10-19 | Overhead | R15/16 | 2021-10-25 | 130 | 19 | 241 |  | 384 | 2020 | 2021 | R15/16
151671254795 | 151633164795 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Commercial | 2020-01-14 | 2020-01-14 | 2020-06-19 | 2020-06-19 | 2020-11-19 | Underground | R15/16- Reloc | 2020-06-19 | 1 | 114 |  | 110 | 223 | 2020 | 2020 | R15/16
151638210706 | 151605400706 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG DIST RELOC REARR CUST REQ | Commercial | 2020-06-04 | 2020-09-25 | 2021-02-17 | 2021-05-14 | 2021-07-30 | Underground | R15/16- Reloc | 2021-05-14 | 82 | 104 | 63 | 56 | 302 | 2020 | 2021 | R15/16
151694741080 | 151652411080 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG DIST RELOC REARR CUST REQ | Commercial | 2020-01-22 | 2020-01-24 | 2020-05-14 | 2020-07-31 | 2020-09-22 | Underground | R15/16- Reloc | 2020-07-31 | 3 | 80 | 57 | 38 | 175 | 2020 | 2020 | R15/16
151636996720 | 151684986720 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH DIST RELOC REARR CUST REQ | Commercial | 2020-03-27 | 2020-06-04 | 2021-01-08 | 2021-02-23 | 2022-08-08 | Overhead | R15/16 | 2021-02-23 | 50 | 157 | 33 | 380 | 617 | 2020 | 2022 | R15/16
151604837134 | 151641977134 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-06-24 | 2020-06-24 | 2020-07-13 |  | 2020-11-11 | Underground | R15/16- Reloc | 2020-07-24 | 1 | 14 | 10 | 79 | 101 | 2020 | 2020 | R15/16
151684665645 | 151608745645 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-01-02 | 2020-01-02 | 2020-01-02 |  | 2020-06-09 | Underground | R15/16- Reloc | 2020-02-18 | 1 |  | 34 | 81 | 114 | 2020 | 2020 | R15/16
151642732429 | 151678502429 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-05-19 | 2020-05-19 | 2020-05-28 |  | 2020-07-09 | Underground | R15/16- Reloc | 2020-06-03 | 1 | 8 | 5 | 27 | 38 | 2020 | 2020 | R15/16
151654844757 | 151685334757 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-03-27 | 2020-03-27 | 2020-06-19 |  | 2020-10-06 | Underground | R15/16- Reloc | 2020-07-30 | 1 | 61 | 30 | 49 | 138 | 2020 | 2020 | R15/16
151648810022 | 151685350022 | SDG&E | UG NON RES NB BUDG 218 | Commercial | 2020-02-07 | 2020-02-07 | 2020-02-10 | 2020-02-12 | 2020-12-21 | Underground | R15/16- Reloc | 2020-02-12 | 1 | 2 | 3 | 224 | 227 | 2020 | 2020 | R15/16
151627928838 | 151671608838 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-01-31 | 2020-01-31 | 2020-01-31 |  | 2021-11-10 | Overhead | R15/16 | 2020-03-10 | 1 |  | 28 | 437 | 464 | 2020 | 2021 | R15/16
151658697882 | 151652697882 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2020-01-23 | 2020-01-23 | 2020-01-23 |  | 2020-06-09 | Underground | R15/16- Reloc | 2020-02-05 | 1 |  | 10 | 90 | 99 | 2020 | 2020 | R15/16
151676787142 | 151675737142 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-07-13 | 2020-07-13 | 2020-07-13 |  | 2020-11-02 | Overhead | R15/16 | 2020-09-02 | 1 |  | 38 | 44 | 81 | 2020 | 2020 | R15/16
151652665553 | 151606475553 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-01-02 | 2020-01-02 | 2020-01-02 | 2020-02-12 | 2020-02-13 | Overhead | R15/16 | 2020-02-12 | 1 |  | 30 | 2 | 31 | 2020 | 2020 | R15/16
151660977563 | 151617587563 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-04-14 | 2020-04-14 | 2020-04-14 | 2021-04-14 | 2020-06-29 | Overhead | R15/16 | 2021-04-14 | 1 |  | 262 |  | 55 | 2020 | 2020 | R15/16
151673608748 | 151606328748 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Commercial | 2020-02-18 | 2020-02-18 | 2020-04-22 |  | 2021-11-10 | Overhead | R15/16 |  | 1 | 47 |  |  | 452 | 2020 | 2021 | R15/16
151637818315 | 151662548315 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-01-28 | 2020-01-28 | 2020-01-28 |  | 2020-06-09 | Overhead | R15/16 | 2020-02-24 | 1 |  | 20 | 77 | 96 | 2020 | 2020 | R15/16
151600585619 | 151623695619 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-06-16 | 2020-06-16 | 2020-06-29 |  | 2020-12-15 | Underground | R15/16- Reloc | 2020-09-11 | 1 | 10 | 55 | 68 | 131 | 2020 | 2020 | R15/16
151674193116 | 151601713116 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-06-02 | 2020-06-02 | 2020-06-04 | 2020-06-15 | 2020-06-17 | Underground | R15/16- Reloc | 2020-06-15 | 1 | 3 | 8 | 3 | 12 | 2020 | 2020 | R15/16
151697828779 | 151699238779 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-06-01 | 2020-06-01 | 2020-07-28 |  | 2021-04-14 | Underground | R15/16- Reloc | 2020-12-14 | 1 | 42 | 100 | 88 | 228 | 2020 | 2021 | R15/16
151672846680 | 151602266680 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Commercial | 2020-06-02 | 2020-07-01 | 2020-07-07 | 2020-07-08 | 2020-12-21 | Underground | R15/16- Reloc | 2020-07-08 | 22 | 5 | 2 | 119 | 145 | 2020 | 2020 | R15/16
151679336276 | 151600606276 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-04-03 | 2020-04-03 | 2020-04-03 |  | 2020-07-14 | Overhead | R15/16 | 2020-06-17 | 1 |  | 54 | 20 | 73 | 2020 | 2020 | R15/16
151685276273 | 151699456273 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-04-03 | 2020-04-03 | 2020-04-03 | 2020-05-11 | 2020-05-12 | Overhead | R15/16 | 2020-05-11 | 1 |  | 27 | 2 | 28 | 2020 | 2020 | R15/16
151605563136 | 151605653136 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-06-04 | 2020-06-04 | 2020-06-04 |  | 2020-07-14 | Overhead | R15/16 | 2020-06-17 | 1 |  | 10 | 20 | 29 | 2020 | 2020 | R15/16
151655744446 | 151669514446 | RETOFIT OF EXISTING DISTRIBUTION SYSTEM | UG NB SUPPORT BUDG 219 | Commercial | 2020-07-09 | 2020-07-09 | 2020-09-21 | 2020-11-12 | 2021-02-03 | Underground | R15/16- Reloc | 2020-11-12 | 1 | 53 | 39 | 60 | 150 | 2020 | 2021 | R15/16
151671330119 | 151694350119 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-02-12 | 2020-02-12 | 2020-02-12 |  | 2020-07-14 | Underground | R15/16- Reloc | 2020-06-16 | 1 |  | 90 | 21 | 110 | 2020 | 2020 | R15/16
151628965405 | 151603525405 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2019-12-30 | 2019-12-30 | 2019-12-30 |  | 2021-11-10 | Overhead | R15/16 | 2020-01-27 | 1 |  | 21 | 468 | 488 | 2019 | 2021 | R15/16
151613580356 | 151666310356 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-03-17 | 2020-03-17 | 2020-08-12 |  | 2020-12-15 | Underground | R15/16- Reloc | 2020-09-10 | 1 | 107 | 22 | 69 | 196 | 2020 | 2020 | R15/16
151633929204 | 151673549204 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-02-03 | 2020-02-03 | 2020-02-03 | 2020-03-03 | 2020-06-09 | Overhead | R15/16 | 2020-03-03 | 1 |  | 22 | 71 | 92 | 2020 | 2020 | R15/16
151642432476 | 151672922476 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Commercial | 2020-05-14 | 2020-05-14 | 2020-05-28 |  | 2021-04-13 | Underground | R15/16- Reloc | 2020-12-07 | 1 | 11 | 138 | 92 | 239 | 2020 | 2021 | R15/16
151626742914 | 151659162914 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-01-27 | 2020-01-27 | 2020-03-04 |  | 2020-06-09 | Underground | R15/16- Reloc | 2020-03-26 | 1 | 28 | 17 | 54 | 97 | 2020 | 2020 | R15/16
151617376507 | 151600746507 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-04-03 | 2020-04-03 | 2020-04-06 |  | 2020-07-09 | Overhead | R15/16 | 2020-05-28 | 1 | 2 | 39 | 31 | 70 | 2020 | 2020 | R15/16
151606810713 | 151649140713 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-04-30 | 2020-04-30 | 2020-05-13 | 2020-06-30 | 2020-07-01 | Underground | R15/16- Reloc | 2020-06-30 | 1 | 10 | 35 | 2 | 45 | 2020 | 2020 | R15/16
151611135408 | 151644965408 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-06-26 | 2020-06-26 | 2020-06-26 | 2020-11-12 | 2020-12-15 | Overhead | R15/16 | 2020-11-12 | 1 |  | 100 | 24 | 123 | 2020 | 2020 | R15/16
151648216515 | 151661036515 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2020-07-06 | 2020-07-06 | 2020-07-07 | 2020-10-08 | 2020-11-06 | Underground | R15/16- Reloc | 2020-10-08 | 1 | 2 | 68 | 22 | 90 | 2020 | 2020 | R15/16
151686986778 | 151686996778 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2020-03-27 | 2020-03-27 | 2020-04-08 |  | 2021-08-06 | Underground | R15/16- Reloc |  | 1 | 9 |  |  | 356 | 2020 | 2021 | R15/16
151627849007 | 151672389007 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-02-01 | 2020-02-01 | 2020-02-01 | 2020-07-09 | 2020-10-06 | Overhead | R15/16 | 2020-07-09 | 0 |  | 114 | 64 | 177 | 2020 | 2020 | R15/16
151607953973 | 151668063973 |  | OH LS 1A STREET LIGHTS SL | Commercial | 2020-01-30 | 2020-02-11 | 2020-06-11 |  | 2020-07-14 | Overhead | R15/16 |  | 9 | 88 |  |  | 119 | 2020 | 2020 | R15/16
151664249485 | 151675429485 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-03-23 | 2020-03-23 | 2020-04-30 |  | 2020-07-09 | Underground | R15/16- Reloc | 2020-05-28 | 1 | 29 | 21 | 31 | 79 | 2020 | 2020 | R15/16
151688722302 | 151630172302 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2020-02-27 | 2020-02-27 | 2020-02-27 | 2020-06-08 | 2020-06-09 | Underground | R15/16- Reloc | 2020-06-08 | 1 |  | 73 | 2 | 74 | 2020 | 2020 | R15/16
151682086281 | 151604256281 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2019-12-30 | 2019-12-30 | 2020-01-07 |  | 2021-11-10 | Underground | R15/16- Reloc | 2020-09-25 | 1 | 7 | 189 | 294 | 488 | 2019 | 2021 | R15/16
151613205056 | 151638975056 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-06-24 | 2020-06-24 | 2020-06-24 |  | 2020-10-06 | Overhead | R15/16 | 2020-08-13 | 1 |  | 37 | 39 | 75 | 2020 | 2020 | R15/16
151636663108 | 151611593108 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-02-20 | 2020-02-20 | 2020-03-06 |  | 2020-11-02 | Underground | R15/16- Reloc | 2020-09-03 | 1 | 12 | 130 | 43 | 183 | 2020 | 2020 | R15/16
151648354124 | 151696954124 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-02-12 | 2020-02-12 | 2020-09-16 |  | 2021-04-14 | Underground | R15/16- Reloc | 2020-12-10 | 1 | 156 | 62 | 90 | 306 | 2020 | 2021 | R15/16
151658304495 | 151670524495 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-03-19 | 2020-03-19 | 2020-03-19 |  | 2020-07-01 | Overhead | R15/16 | 2020-04-30 | 1 |  | 31 | 45 | 75 | 2020 | 2020 | R15/16
151678683993 | 151619003993 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-06-11 | 2020-06-11 | 2020-06-11 |  | 2020-08-28 | Underground | R15/16- Reloc | 2020-07-01 | 1 |  | 15 | 43 | 57 | 2020 | 2020 | R15/16
151622100514 | 151657650514 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-07-01 | 2020-07-01 | 2020-08-14 | 2020-09-15 | 2020-12-18 | Underground | R15/16- Reloc | 2020-09-15 | 1 | 33 | 23 | 69 | 123 | 2020 | 2020 | R15/16
151648846420 | 151660096420 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-07-02 | 2020-07-02 | 2020-07-02 |  | 2021-11-03 | Overhead | R15/16 | 2021-06-22 | 1 |  | 254 | 97 | 350 | 2020 | 2021 | R15/16
151638450080 | 151667330080 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-07-08 | 2020-08-04 | 2020-08-07 |  | 2021-01-21 | Overhead | R15/16 |  | 20 | 4 |  |  | 142 | 2020 | 2021 | R15/16
151696067381 | 151641597381 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-01-16 | 2020-01-16 | 2020-01-17 |  | 2020-06-09 | Overhead | R15/16 | 2020-03-20 | 1 | 2 | 46 | 58 | 104 | 2020 | 2020 | R15/16
151673986419 | 151694896419 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-05-28 | 2020-05-28 | 2020-07-06 |  | 2020-10-06 | Underground | R15/16- Reloc | 2020-07-30 | 1 | 28 | 19 | 49 | 94 | 2020 | 2020 | R15/16
151606188703 | 151667928703 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-01-30 | 2020-01-30 | 2020-01-30 | 2020-06-01 | 2020-06-03 | Overhead | R15/16 | 2020-06-01 | 1 |  | 88 | 3 | 90 | 2020 | 2020 | R15/16
151639984989 | 151675064989 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-03-23 | 2020-03-23 | 2020-03-23 |  | 2020-07-08 | Underground | R15/16- Reloc |  | 1 |  |  |  | 78 | 2020 | 2020 | R15/16
151630016902 | 151633806902 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH DIST RELOC REARR CUST REQ | Commercial | 2020-01-14 | 2020-01-14 | 2020-04-08 | 2020-04-14 | 2020-08-25 | Overhead | R15/16 | 2020-04-14 | 1 | 62 | 5 | 96 | 161 | 2020 | 2020 | R15/16
151640555806 | 151687365806 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-03-27 | 2020-03-27 | 2020-03-30 |  | 2020-06-29 | Overhead | R15/16 | 2020-04-22 | 1 | 2 | 18 | 49 | 67 | 2020 | 2020 | R15/16
151627078500 | 151608078500 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-01-02 | 2020-01-09 | 2020-01-28 |  | 2021-07-23 | Overhead | R15/16 |  | 6 | 14 |  |  | 407 | 2020 | 2021 | R15/16
151690296562 | 151653386562 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-03-10 | 2020-03-10 | 2020-04-06 |  | 2020-07-08 | Underground | R15/16- Reloc | 2020-05-14 | 1 | 20 | 29 | 40 | 87 | 2020 | 2020 | R15/16
151628714987 | 151664844987 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-03-16 | 2020-03-16 | 2020-03-23 | 2020-05-18 | 2020-05-19 | Underground | R15/16- Reloc | 2020-05-18 | 1 | 6 | 41 | 2 | 47 | 2020 | 2020 | R15/16
151638229540 | 151647909540 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-04-30 | 2020-04-30 | 2020-04-30 | 2020-08-19 | 2020-10-29 | Overhead | R15/16 | 2020-08-19 | 1 |  | 80 | 52 | 131 | 2020 | 2020 | R15/16
151638253834 | 151634923834 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Commercial | 2020-03-02 | 2020-03-02 | 2020-03-12 |  | 2020-07-08 | Underground | R15/16- Reloc |  | 1 | 9 |  |  | 93 | 2020 | 2020 | R15/16
151604197380 | 151624357380 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-01-09 | 2020-01-09 | 2020-01-17 |  | 2020-06-09 | Underground | R15/16- Reloc | 2020-02-06 | 1 | 7 | 15 | 89 | 109 | 2020 | 2020 | R15/16
151696693776 | 151615773776 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-06-10 | 2020-06-10 | 2020-06-10 |  | 2020-10-06 | Overhead | R15/16 | 2020-08-10 | 1 |  | 44 | 42 | 85 | 2020 | 2020 | R15/16
151637718634 | 151617698634 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Commercial | 2020-04-14 | 2020-04-21 | 2020-04-21 |  | 2020-10-06 | Overhead | R15/16 |  | 6 |  |  |  | 126 | 2020 | 2020 | R15/16
151617341084 | 151672141084 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-05-14 | 2020-05-14 | 2020-05-14 |  | 2021-11-10 | Overhead | R15/16 | 2020-11-12 | 1 |  | 131 | 260 | 390 | 2020 | 2021 | R15/16
151684566275 | 151600016275 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-04-03 | 2020-04-03 | 2020-04-03 |  | 2020-07-08 | Overhead | R15/16 | 2020-05-21 | 1 |  | 35 | 35 | 69 | 2020 | 2020 | R15/16
151667672290 | 151690232290 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Commercial | 2020-05-26 | 2020-05-26 | 2020-05-26 |  | 2020-07-10 | Overhead | R15/16 | 2020-06-11 | 1 |  | 13 | 22 | 34 | 2020 | 2020 | R15/16
151636035970 | 151681945970 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Commercial | 2020-03-25 | 2020-03-25 | 2020-04-01 | 2020-04-16 | 2020-06-11 | Underground | R15/16- Reloc | 2020-04-16 | 1 | 6 | 12 | 41 | 57 | 2020 | 2020 | R15/16
151681208989 | 151606608989 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2020-02-18 | 2020-03-31 | 2020-04-24 | 2020-04-29 | 2023-04-16 | Underground | R15/16- Reloc | 2020-04-29 | 31 | 19 | 4 | 773 | 824 | 2020 | 2023 | R15/16
151627432247 | 151605522247 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-02-14 | 2020-02-14 | 2020-05-26 |  | 2020-08-20 | Underground | R15/16- Reloc | 2020-06-24 | 1 | 73 | 22 | 42 | 135 | 2020 | 2020 | R15/16
151688915234 | 151602895234 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-06-03 | 2020-06-03 | 2020-06-25 |  | 2020-08-28 | Underground | R15/16- Reloc | 2020-07-07 | 1 | 17 | 9 | 39 | 63 | 2020 | 2020 | R15/16
151622600022 | 151653140022 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-05-04 | 2020-05-04 | 2020-05-04 |  | 2020-07-09 | Overhead | R15/16 | 2020-06-02 | 1 |  | 22 | 28 | 49 | 2020 | 2020 | R15/16
151603078081 | 151623498081 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-04-17 | 2020-04-17 | 2020-04-17 | 2020-08-19 | 2020-08-20 | Overhead | R15/16 | 2020-08-19 | 1 |  | 89 | 2 | 90 | 2020 | 2020 | R15/16
151665953292 | 151605763292 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-06-04 | 2020-06-04 | 2020-06-04 | 2020-07-29 | 2021-01-08 | Overhead | R15/16 | 2020-07-29 | 1 |  | 40 | 118 | 157 | 2020 | 2021 | R15/16
151615037124 | 151674907124 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-07-13 | 2020-07-13 | 2020-07-13 |  | 2020-10-06 | Overhead | R15/16 | 2020-07-24 | 1 |  | 10 | 53 | 62 | 2020 | 2020 | R15/16
151608150009 | 151688600009 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-02-10 | 2020-02-10 | 2020-02-10 | 2020-02-18 | 2021-11-13 | Underground | R15/16- Reloc | 2020-02-18 | 1 |  | 7 | 454 | 460 | 2020 | 2021 | R15/16
151624540516 | 151657670516 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-07-01 | 2020-07-01 | 2020-08-14 | 2020-08-25 | 2020-12-29 | Underground | R15/16- Reloc | 2020-08-25 | 1 | 33 | 8 | 91 | 130 | 2020 | 2020 | R15/16
151680476209 | 151618266209 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-01-08 | 2020-01-08 | 2020-01-08 |  | 2020-06-09 | Underground | R15/16- Reloc | 2020-06-08 | 1 |  | 109 | 2 | 110 | 2020 | 2020 | R15/16
151685933924 | 151658923924 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-03-12 | 2020-03-12 | 2020-03-12 | 2020-04-13 | 2020-06-29 | Underground | R15/16- Reloc | 2020-04-13 | 1 |  | 23 | 56 | 78 | 2020 | 2020 | R15/16
151607892769 | 151697292769 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-02-13 | 2020-02-13 | 2020-03-02 |  | 2020-06-29 | Underground | R15/16- Reloc | 2020-04-23 | 1 | 13 | 39 | 48 | 98 | 2020 | 2020 | R15/16
151651789668 | 151685079668 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-02-07 | 2020-02-07 | 2020-02-07 |  | 2020-07-02 | Overhead | R15/16 | 2020-05-06 | 1 |  | 64 | 42 | 105 | 2020 | 2020 | R15/16
151602467794 | 151622537794 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-04-16 | 2020-04-16 | 2020-04-16 |  | 2020-07-07 | Underground | R15/16- Reloc | 2020-05-13 | 1 |  | 20 | 40 | 59 | 2020 | 2020 | R15/16
151656323558 | 151611593558 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-06-09 | 2020-06-09 | 2020-06-09 |  | 2020-10-06 | Underground | R15/16- Reloc | 2020-07-14 | 1 |  | 26 | 61 | 86 | 2020 | 2020 | R15/16
151691506965 | 151662306965 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-07-06 | 2020-07-06 | 2020-07-09 |  | 2021-02-17 | Underground | R15/16- Reloc | 2020-10-19 | 1 | 4 | 73 | 88 | 163 | 2020 | 2021 | R15/16
151625227849 | 151698857849 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2019-12-23 | 2020-01-06 | 2020-01-23 |  | 2023-05-22 | Underground | R15/16- Reloc |  | 11 | 14 |  |  | 891 | 2019 | 2023 | R15/16
151633699280 | 151672969280 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-02-03 | 2020-02-03 | 2020-02-03 |  | 2020-07-07 | Overhead | R15/16 | 2020-05-13 | 1 |  | 73 | 40 | 112 | 2020 | 2020 | R15/16
151693036346 | 151693046346 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH DIST RELOC REARR CUST REQ | Commercial | 2020-03-31 | 2022-05-10 | 2022-10-07 | 2022-10-17 | 2022-11-01 | Overhead | R15/16 | 2022-10-17 | 551 | 109 | 7 | 12 | 676 | 2020 | 2022 | R15/16
151677310094 | 151620680094 | NON-RESIDENTIAL - MISCELLANEOUS | UG NON RES NB BUDG 218 | Commercial | 2020-01-08 | 2020-01-08 | 2020-05-05 | 2021-01-29 | 2021-04-14 | Underground | R15/16- Reloc | 2021-01-29 | 1 | 85 | 194 | 54 | 331 | 2020 | 2021 | R15/16
151695712074 | 151695642074 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG DIST RELOC REARR CUST REQ | Commercial | 2020-05-28 | 2020-06-26 | 2020-08-28 | 2020-09-15 | 2020-10-21 | Underground | R15/16- Reloc | 2020-09-15 | 22 | 46 | 13 | 27 | 105 | 2020 | 2020 | R15/16
151663217171 | 151637917171 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-01-16 | 2020-01-16 | 2020-01-16 | 2020-04-27 | 2020-07-07 | Overhead | R15/16 | 2020-04-27 | 1 |  | 73 | 52 | 124 | 2020 | 2020 | R15/16
151612411819 | 151699991819 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-02-13 | 2020-02-13 | 2020-02-27 |  | 2020-07-01 | Underground | R15/16- Reloc | 2020-04-30 | 1 | 11 | 46 | 45 | 100 | 2020 | 2020 | R15/16
151608287476 | 151650707476 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-01-21 | 2020-01-22 | 2020-01-22 | 2020-03-02 | 2020-06-09 | Overhead | R15/16 | 2020-03-02 | 2 |  | 29 | 72 | 101 | 2020 | 2020 | R15/16
151636707826 | 151676717826 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-07-13 | 2020-07-13 | 2020-07-20 |  | 2022-02-07 | Underground | R15/16- Reloc | 2022-01-10 | 1 | 6 | 386 | 21 | 411 | 2020 | 2022 | R15/16
151615245052 | 151640345052 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-06-24 | 2020-06-24 | 2020-06-24 |  | 2021-07-01 | Overhead | R15/16 | 2020-09-24 | 1 |  | 67 | 201 | 267 | 2020 | 2021 | R15/16
151685395438 | 151666325438 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-03-17 | 2020-03-17 | 2020-03-26 |  | 2020-07-02 | Underground | R15/16- Reloc | 2020-05-05 | 1 | 8 | 29 | 43 | 78 | 2020 | 2020 | R15/16
151648332531 | 151684462531 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2020-02-06 | 2020-02-13 | 2020-03-04 |  | 2023-05-22 | Underground | R15/16- Reloc |  | 6 | 15 |  |  | 858 | 2020 | 2023 | R15/16
151638266059 | 151689906059 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH DIST RELOC REARR CUST REQ | Residential | 2020-05-26 | 2021-02-10 | 2021-04-08 | 2021-04-09 | 2021-05-12 | Overhead | R15/16 | 2021-04-09 | 187 | 42 | 2 | 24 | 252 | 2020 | 2021 | R15/16
151649047304 | 151688887304 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2019-12-17 | 2020-03-25 | 2020-04-13 | 2020-04-13 | 2020-04-14 | Underground | R15/16- Reloc | 2020-04-13 | 72 | 14 |  | 2 | 86 | 2019 | 2020 | R15/16
151632819335 | 151645419335 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-04-29 | 2020-04-29 | 2020-04-29 |  | 2020-07-07 | Underground | R15/16- Reloc | 2020-05-11 | 1 |  | 9 | 42 | 50 | 2020 | 2020 | R15/16
151649315236 | 151648895236 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG DIST RELOC REARR CUST REQ | Commercial | 2020-04-30 | 2020-05-01 | 2021-06-17 | 2021-11-19 | 2022-01-19 | Underground | R15/16- Reloc | 2021-11-19 | 2 | 295 | 112 | 44 | 450 | 2020 | 2022 | R15/16
151682582622 | 151632462622 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-02-28 | 2020-02-28 | 2020-09-02 |  | 2021-01-08 | Overhead | R15/16 | 2020-10-05 | 1 | 134 | 24 | 70 | 226 | 2020 | 2021 | R15/16
151690525327 | 151602885327 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2019-12-30 | 2019-12-30 | 2019-12-30 |  | 2021-11-10 | Overhead | R15/16 | 2020-01-23 | 1 |  | 19 | 470 | 488 | 2019 | 2021 | R15/16
151653250137 | 151693610137 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-02-11 | 2020-02-11 | 2020-02-11 |  | 2020-07-09 | Overhead | R15/16 | 2020-05-27 | 1 |  | 77 | 32 | 108 | 2020 | 2020 | R15/16
151607696599 | 151645936599 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Commercial | 2020-06-25 | 2020-06-29 | 2020-07-07 |  | 2021-07-01 | Underground | R15/16- Reloc |  | 3 | 7 |  |  | 266 | 2020 | 2021 | R15/16
151627662101 | 151603842101 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-02-14 | 2020-02-14 | 2020-02-27 |  | 2020-06-09 | Underground | R15/16- Reloc | 2020-04-02 | 1 | 10 | 26 | 49 | 83 | 2020 | 2020 | R15/16
151678644125 | 151658534125 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2020-03-12 | 2020-03-16 | 2020-03-16 |  | 2020-08-28 | Underground | R15/16- Reloc | 2020-06-26 | 3 |  | 75 | 46 | 122 | 2020 | 2020 | R15/16
151689324719 | 151633064719 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-06-19 | 2020-06-19 | 2020-06-19 |  | 2020-10-06 | Overhead | R15/16 | 2020-08-27 | 1 |  | 50 | 29 | 78 | 2020 | 2020 | R15/16
151646965583 | 151659815583 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2020-07-02 | 2020-07-02 | 2020-09-28 |  | 2023-05-22 | Underground | R15/16- Reloc |  | 1 | 63 |  |  | 753 | 2020 | 2023 | R15/16
151665241877 | 151681891877 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-05-21 | 2020-05-21 | 2020-05-21 |  | 2020-10-06 | Underground | R15/16- Reloc | 2020-08-27 | 1 |  | 71 | 29 | 99 | 2020 | 2020 | R15/16
151617154691 | 151670754691 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-03-19 | 2020-03-19 | 2020-03-19 | 2020-04-05 | 2020-04-08 | Underground | R15/16- Reloc | 2020-04-05 | 1 |  | 12 | 3 | 15 | 2020 | 2020 | R15/16
151601798187 | 151662728187 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-07-06 | 2020-07-06 | 2020-07-23 |  | 2020-11-02 | Underground | R15/16- Reloc | 2020-09-02 | 1 | 14 | 30 | 44 | 86 | 2020 | 2020 | R15/16
151612933322 | 151680703322 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS UD | Residential | 2020-05-20 | 2020-06-04 | 2020-06-04 |  | 2020-07-14 | Underground | R15/16- Reloc |  | 12 |  |  |  | 40 | 2020 | 2020 | R15/16
151655016514 | 151696116514 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Commercial | 2019-12-20 | 2020-01-08 | 2020-01-10 | 2020-01-14 | 2020-10-13 | Underground | R15/16- Reloc | 2020-01-14 | 14 | 3 | 3 | 196 | 213 | 2019 | 2020 | R15/16
151613343291 | 151602643291 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-06-03 | 2020-06-04 | 2020-06-04 |  | 2022-08-03 | Overhead | R15/16 |  | 2 |  |  |  | 566 | 2020 | 2022 | R15/16
151630267310 | 151630197310 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2020-01-13 | 2020-01-13 | 2020-01-17 |  | 2021-08-06 | Underground | R15/16- Reloc |  | 1 | 5 |  |  | 410 | 2020 | 2021 | R15/16
151683491771 | 151600971771 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-06-03 | 2020-06-03 | 2020-08-26 |  | 2021-02-17 | Underground | R15/16- Reloc | 2020-10-20 | 1 | 61 | 40 | 87 | 186 | 2020 | 2021 | R15/16
151607077320 | 151613107320 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS UD | Residential | 2020-04-10 | 2020-04-10 | 2020-04-13 |  | 2020-06-24 | Underground | R15/16- Reloc |  | 1 | 2 |  |  | 54 | 2020 | 2020 | R15/16
151600796385 | 151611706385 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH PRE ARR CUST WORK | Commercial | 2020-06-08 | 2020-06-11 | 2020-07-02 |  | 2022-08-01 | Overhead | R15/16 |  | 4 | 16 |  |  | 561 | 2020 | 2022 | R15/16
151669478449 | 151626428449 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2020-01-10 | 2020-01-10 | 2020-01-28 | 2020-02-25 | 2020-02-27 | Underground | R15/16- Reloc | 2020-02-25 | 1 | 13 | 21 | 3 | 35 | 2020 | 2020 | R15/16
151686392823 | 151699192823 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2020-07-13 | 2020-07-14 | Underground | R15/16- Reloc | 2020-07-13 | 1 |  | 31 | 2 | 32 | 2020 | 2020 | R15/16
151619979593 | 151624009593 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG PRE ARRANGED CUST WORK | Commercial | 2020-01-09 | 2020-01-16 | 2020-02-07 | 2020-02-12 | 2020-03-12 | Underground | R15/16- Reloc | 2020-02-12 | 6 | 17 | 4 | 22 | 46 | 2020 | 2020 | R15/16
151645965218 | 151679355218 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Commercial | 2020-03-24 | 2020-03-24 | 2020-03-25 |  | 2020-06-24 | Overhead | R15/16 | 2020-04-21 | 1 | 2 | 20 | 47 | 67 | 2020 | 2020 | R15/16
151655557095 | 151624417095 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-01-09 | 2020-01-09 | 2020-01-16 |  | 2020-12-18 | Underground | R15/16- Reloc | 2020-09-17 | 1 | 6 | 176 | 67 | 247 | 2020 | 2020 | R15/16
151696884759 | 151633724759 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-06-19 | 2020-06-19 | 2020-06-19 |  | 2020-10-06 | Overhead | R15/16 | 2020-10-06 | 1 |  | 78 |  | 78 | 2020 | 2020 | R15/16
151654546111 | 151657876111 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Commercial | 2020-07-01 | 2020-07-01 | 2020-07-01 | 2020-07-23 | 2020-07-24 | Overhead | R15/16 | 2020-07-23 | 1 |  | 17 | 2 | 18 | 2020 | 2020 | R15/16
151661959124 | 151674669124 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-02-03 | 2020-02-03 | 2020-02-03 |  | 2021-08-16 | Underground | R15/16- Reloc | 2021-03-25 | 1 |  | 299 | 103 | 401 | 2020 | 2021 | R15/16
151659742598 | 151684712598 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH PRE ARR CUST WORK | Commercial | 2020-02-06 | 2020-02-11 | 2020-03-03 |  | 2023-05-23 | Overhead | R15/16 |  | 4 | 16 |  |  | 859 | 2020 | 2023 | R15/16
151666471881 | 151681941881 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-05-21 | 2020-05-21 | 2020-05-21 |  | 2020-07-09 | Underground | R15/16- Reloc | 2020-06-09 | 1 |  | 14 | 23 | 36 | 2020 | 2020 | R15/16
151695216434 | 151612136434 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2020-01-03 | 2020-01-03 | 2020-01-10 |  | 2020-06-09 | Underground | R15/16- Reloc | 2020-02-11 | 1 | 6 | 23 | 86 | 113 | 2020 | 2020 | R15/16
151674192617 | 151695672617 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2020-05-29 | 2020-05-29 | 2020-05-29 |  | 2020-07-14 | Overhead | R15/16 | 2020-06-17 | 1 |  | 14 | 20 | 33 | 2020 | 2020 | R15/16
151691307775 | 151641807775 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH DIST RELOC REARR CUST REQ | Residential | 2020-06-24 | 2020-06-24 | 2020-07-20 | 2020-07-21 | 2020-09-18 | Overhead | R15/16 | 2020-07-21 | 1 | 19 | 2 | 44 | 63 | 2020 | 2020 | R15/16
151645334820 | 151690464820 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2019-12-17 | 2019-12-17 | 2019-12-18 | 2020-03-02 | 2020-03-05 | Overhead | R15/16 | 2020-03-02 | 1 | 2 | 54 | 4 | 58 | 2019 | 2020 | R15/16
151687036592 | 151631186592 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-01-11 | 2023-01-20 | 2023-01-30 | 2023-01-20 | 2023-07-31 | Overhead | R15/16 | 2023-01-20 | 8 | 7 |  | 137 | 144 | 2023 | 2023 | R15/16
151653322828 | 151664872828 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-06-20 | 2023-06-20 | 2023-06-20 | 2023-07-16 | 2023-07-19 | Underground | R15/16- Reloc | 2023-07-16 | 1 |  | 19 | 3 | 22 | 2023 | 2023 | R15/16
151682501813 | 151653141813 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS UD | Residential | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-03-09 | 2023-05-14 | Underground | R15/16- Reloc | 2023-03-09 | 1 |  | 2 | 47 | 48 | 2023 | 2023 | R15/16
151686162166 | 151622792166 | MODIFICATION OF EXISTING DISTRIB SYSTEM | OH NB SUPPORT BUDG 219 | Commercial | 2023-02-23 | 2023-02-24 | 2023-06-14 | 2023-08-11 | 2023-09-13 | Overhead | R15/16 | 2023-08-11 | 2 | 79 | 43 | 24 | 145 | 2023 | 2023 | R15/16
151678913511 | 151685343511 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-12-16 | 2022-12-16 | 2023-08-08 | 2023-08-30 | 2023-03-20 | Overhead | R15/16 | 2023-08-30 | 1 | 168 | 17 |  | 67 | 2022 | 2023 | R15/16
151668263209 | 151672123209 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-06-24 | 2023-06-24 | 2023-06-24 | 2023-07-15 | 2023-07-18 | Underground | R15/16- Reloc | 2023-07-15 | 0 |  | 15 | 2 | 17 | 2023 | 2023 | R15/16
151659234322 | 151697564322 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-12-27 | 2022-12-27 | 2022-12-27 | 2023-03-15 | 2023-05-14 | Overhead | R15/16 | 2023-03-15 | 1 |  | 57 | 43 | 99 | 2022 | 2023 | R15/16
151644795483 | 151640485483 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-03-02 | 2023-03-02 | 2023-04-11 | 2023-06-20 | 2023-06-21 | Underground | R15/16- Reloc | 2023-06-20 | 1 | 29 | 51 | 2 | 80 | 2023 | 2023 | R15/16
151665088122 | 151676838122 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-05-03 | 2023-05-04 | 2023-05-05 | 2023-07-14 | 2023-07-17 | Overhead | R15/16 | 2023-07-14 | 2 | 2 | 51 | 2 | 54 | 2023 | 2023 | R15/16
151670376457 | 151650146457 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-01-19 | 2023-01-19 | 2023-01-30 | 2023-03-15 | 2023-03-25 | Underground | R15/16- Reloc | 2023-03-15 | 1 | 8 | 33 | 8 | 47 | 2023 | 2023 | R15/16
151643564998 | 151608934998 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2021-08-24 | 2021-08-24 | 2021-08-24 |  | 2021-12-28 | Overhead | R15/16 | 2021-12-15 | 1 |  | 82 | 10 | 91 | 2021 | 2021 | R15/16
151636435423 | 151612385423 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2021-08-25 | 2021-08-26 | 2021-08-26 | 2021-10-25 | 2022-10-17 | Overhead | R15/16 | 2021-10-25 | 2 |  | 43 | 256 | 299 | 2021 | 2022 | R15/16
151669085660 | 151677195660 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-12-13 |  | 2023-01-25 | 2023-03-02 | 2023-03-17 | Overhead | R15/16 | 2023-03-02 |  |  | 27 | 12 | 69 | 2022 | 2023 | R15/16
151608822283 | 151655902283 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-06-15 | 2023-06-15 | 2023-06-15 | 2023-07-11 | 2023-07-14 | Overhead | R15/16 | 2023-07-11 | 1 |  | 19 | 4 | 22 | 2023 | 2023 | R15/16
151630117301 | 151615537301 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-04-05 | 2023-04-05 | 2023-04-28 | 2023-10-14 | 2023-11-06 | Underground | R15/16- Reloc | 2023-10-14 | 1 | 18 | 121 | 16 | 154 | 2023 | 2023 | R15/16
151624421601 | 151624091601 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-05-31 | 2023-06-08 | 2023-06-08 | 2023-08-16 | 2023-09-21 | Overhead | R15/16 | 2023-08-16 | 7 |  | 50 | 27 | 82 | 2023 | 2023 | R15/16
151630522240 | 151630372240 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-06-02 | 2023-06-14 | 2023-06-14 |  | 2023-06-29 | Overhead | R15/16 | 2023-06-26 | 9 |  | 9 | 4 | 20 | 2023 | 2023 | R15/16
151659454816 | 151605734816 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2021-08-23 | 2021-08-23 | 2021-08-23 | 2021-10-06 | 2021-10-06 | Overhead | R15/16 | 2021-10-06 | 1 |  | 33 |  | 33 | 2021 | 2021 | R15/16
151618587363 | 151689347363 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-03-24 | 2023-03-24 | 2023-04-29 |  | 2023-07-12 | Underground | R15/16- Reloc | 2023-05-19 | 1 | 26 | 15 | 39 | 79 | 2023 | 2023 | R15/16
151649676903 | 151682566903 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-12-15 | 2022-12-21 | 2023-01-30 | 2023-01-23 | 2023-06-16 | Underground | R15/16- Reloc | 2023-01-23 | 5 | 29 |  | 105 | 132 | 2022 | 2023 | R15/16
151648520245 | 151615560245 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-05-25 |  | 2023-07-18 | 2023-07-24 | 2023-07-12 | Underground | R15/16- Reloc | 2023-07-24 |  |  | 5 |  | 35 | 2023 | 2023 | R15/16
151675377090 | 151661707090 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-04-26 | 2023-04-27 | 2023-04-27 | 2023-05-23 | 2023-06-13 | Underground | R15/16- Reloc | 2023-05-23 | 2 |  | 19 | 16 | 35 | 2023 | 2023 | R15/16
151690163198 | 151682243198 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-03-22 | 2023-03-22 | 2023-03-22 |  | 2023-07-31 | Underground | R15/16- Reloc | 2023-03-22 | 1 |  |  | 94 | 94 | 2023 | 2023 | R15/16
151604032210 | 151661802210 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-03-13 | 2023-03-13 | 2023-06-14 | 2023-06-26 | 2023-06-30 | Underground | R15/16- Reloc | 2023-06-26 | 1 | 68 | 9 | 5 | 80 | 2023 | 2023 | R15/16
151668176069 | 151639256069 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-01-17 | 2023-01-17 | 2023-01-25 | 2023-03-06 | 2023-03-27 | Underground | R15/16- Reloc | 2023-03-06 | 1 | 7 | 29 | 16 | 50 | 2023 | 2023 | R15/16
151652595619 | 151605615619 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2021-08-22 | 2021-08-22 | 2021-08-27 |  | 2021-10-25 | Underground | R15/16- Reloc | 2021-09-15 | 0 | 5 | 14 | 29 | 46 | 2021 | 2021 | R15/16
151631642603 | 151657032603 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-06-16 | 2023-06-16 | 2023-06-19 | 2023-06-26 | 2023-08-02 | Overhead | R15/16 | 2023-06-26 | 1 | 2 | 6 | 28 | 34 | 2023 | 2023 | R15/16
151633975731 | 151676215731 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG DIST RELOC REARR CUST REQ | Commercial | 2023-05-03 | 2023-05-15 | 2023-07-20 | 2023-10-10 | 2023-10-26 | Underground | R15/16- Reloc | 2023-10-10 | 9 | 49 | 59 | 13 | 127 | 2023 | 2023 | R15/16
151699500111 | 151662640111 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-04-27 | 2023-04-27 | 2023-05-23 | 2023-07-07 | 2023-07-10 | Underground | R15/16- Reloc | 2023-07-07 | 1 | 19 | 34 | 2 | 53 | 2023 | 2023 | R15/16
151628083854 | 151659913854 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2021-08-04 | 2021-08-04 | 2021-08-16 | 2021-11-26 | 2021-11-29 | Underground | R15/16- Reloc | 2021-11-26 | 1 | 9 | 75 | 2 | 84 | 2021 | 2021 | R15/16
151698423422 | 151656123422 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-03-09 | 2023-03-09 | 2023-06-27 | 2023-08-28 | 2023-09-14 | Underground | R15/16- Reloc | 2023-08-28 | 1 | 79 | 45 | 14 | 136 | 2023 | 2023 | R15/16
151631163850 | 151691013850 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2022-12-20 | 2022-12-20 | 2022-12-22 | 2023-01-15 | 2023-01-18 | Underground | R15/16- Reloc | 2023-01-15 | 1 | 3 | 17 | 3 | 22 | 2022 | 2023 | R15/16
151608530107 | 151662660107 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-04-27 | 2023-05-23 | 2023-05-23 | 2023-07-07 | 2023-07-10 | Underground | R15/16- Reloc | 2023-07-07 | 19 |  | 34 | 2 | 53 | 2023 | 2023 | R15/16
151657371938 | 151647431938 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-06-12 |  | 2023-06-12 | 2023-06-23 | 2023-09-12 | Overhead | R15/16 | 2023-06-23 |  |  | 10 | 58 | 67 | 2023 | 2023 | R15/16
151602362902 | 151613302902 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH DIST RELOC REARR CUST REQ | Commercial | 2023-05-23 | 2023-05-23 | 2023-06-21 | 2023-10-02 | 2023-10-25 | Overhead | R15/16 | 2023-10-02 | 1 | 22 | 74 | 18 | 112 | 2023 | 2023 | R15/16
151642388787 | 151688918787 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-05-09 | 2023-05-10 | 2023-05-10 |  | 2023-06-06 | Overhead | R15/16 | 2023-05-16 | 2 |  | 5 | 16 | 21 | 2023 | 2023 | R15/16
151685087645 | 151696477645 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-02-09 | 2023-02-24 | 2023-05-01 | 2023-08-07 | 2023-08-07 | Underground | R15/16- Reloc | 2023-08-07 | 12 | 47 | 71 |  | 128 | 2023 | 2023 | R15/16
151636024713 | 151647454713 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-06-12 | 2023-10-03 | 2023-10-05 | 2023-11-06 | 2023-12-18 | Underground | R15/16- Reloc | 2023-11-06 | 82 | 3 | 23 | 31 | 136 | 2023 | 2023 | R15/16
151673817326 | 151646657326 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-09-23 | 2021-09-24 | Underground | R15/16- Reloc | 2021-09-23 | 1 |  | 10 | 2 | 11 | 2021 | 2021 | R15/16
151650726066 | 151607636066 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-01-03 | 2023-01-03 | 2023-01-25 | 2023-01-17 | 2023-04-27 | Underground | R15/16- Reloc | 2023-01-17 | 1 | 17 |  | 73 | 83 | 2023 | 2023 | R15/16
151696636097 | 151626856097 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-11-10 | 2021-12-17 | Overhead | R15/16 | 2021-11-10 | 1 |  | 51 | 28 | 78 | 2021 | 2021 | R15/16
151690602671 | 151661232671 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-06-19 | 2023-06-19 | 2023-06-19 | 2023-06-22 | 2023-06-26 | Overhead | R15/16 | 2023-06-22 | 1 |  | 4 | 3 | 6 | 2023 | 2023 | R15/16
151621478658 | 151600378658 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-07-10 | 2023-07-10 | 2023-08-17 | 2023-08-21 | 2023-10-05 | Underground | R15/16- Reloc | 2023-08-21 | 1 | 29 | 3 | 34 | 64 | 2023 | 2023 | R15/16
151668455511 | 151688625511 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2023-07-01 | 2023-07-05 | 2023-07-19 | 2023-08-03 | 2023-08-18 | Underground | R15/16- Reloc | 2023-08-03 | 3 | 11 | 12 | 12 | 35 | 2023 | 2023 | R15/16
151633206546 | 151698016546 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Commercial | 2023-03-28 | 2023-03-28 | 2023-04-21 |  | 2023-08-10 | Underground | R15/16- Reloc |  | 1 | 19 |  |  | 98 | 2023 | 2023 | R15/16
151607668871 | 151655078871 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-01-23 | 2023-02-08 | 2023-02-08 | 2023-03-27 | 2023-07-28 | Underground | R15/16- Reloc | 2023-03-27 | 13 |  | 34 | 90 | 135 | 2023 | 2023 | R15/16
151626706548 | 151626806548 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH PRE ARR CUST WORK | Commercial | 2021-08-31 | 2021-08-31 | 2021-09-02 |  | 2022-03-31 | Overhead | R15/16 |  | 1 | 3 |  |  | 153 | 2021 | 2022 | R15/16
151696238600 | 151613498600 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH PRE ARR CUST WORK | Commercial | 2021-08-26 | 2021-08-30 | 2021-09-20 | 2021-09-26 | 2021-09-29 | Overhead | R15/16 | 2021-09-26 | 3 | 16 | 5 | 3 | 25 | 2021 | 2021 | R15/16
151648022307 | 151660912307 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-03-13 | 2023-03-13 | 2023-03-13 | 2023-05-04 | 2023-05-09 | Overhead | R15/16 | 2023-05-04 | 1 |  | 39 | 4 | 42 | 2023 | 2023 | R15/16
151655778054 | 151677958054 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-02-02 | 2023-02-02 | 2023-02-02 |  | 2023-06-26 | Underground | R15/16- Reloc | 2023-02-15 | 1 |  | 10 | 94 | 103 | 2023 | 2023 | R15/16
151626387171 | 151662427171 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Residential | 2023-01-25 | 2023-01-25 | 2023-01-25 |  | 2023-05-30 | Underground | R15/16- Reloc | 2023-02-01 | 1 |  | 6 | 85 | 90 | 2023 | 2023 | R15/16
151692624486 | 151698974486 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Commercial | 2021-08-19 | 2021-08-19 | 2021-08-19 | 2022-02-06 | 2022-02-09 | Underground | R15/16- Reloc | 2022-02-06 | 1 |  | 122 | 3 | 125 | 2021 | 2022 | R15/16
151654195244 | 151612045244 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-11-03 | 2021-11-04 | Overhead | R15/16 | 2021-11-03 | 1 |  | 51 | 2 | 52 | 2021 | 2021 | R15/16
151672903435 | 151682443435 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-06-29 | 2023-06-29 | 2023-06-29 | 2023-07-25 | 2023-08-25 | Overhead | R15/16 | 2023-07-25 | 1 |  | 19 | 24 | 42 | 2023 | 2023 | R15/16
151670647488 | 151672427488 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-03-17 | 2023-05-02 | 2023-05-02 |  | 2023-09-08 | Overhead | R15/16 | 2023-05-08 | 33 |  | 5 | 90 | 126 | 2023 | 2023 | R15/16
151657316102 | 151643886102 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-04-18 | 2023-04-18 | 2023-10-17 | 2023-12-05 | 2023-12-11 | Underground | R15/16- Reloc | 2023-12-05 | 1 | 131 | 36 | 5 | 170 | 2023 | 2023 | R15/16
151648728663 | 151651998663 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-04-21 | 2023-05-09 | 2023-05-09 |  | 2023-06-27 | Overhead | R15/16 | 2023-05-22 | 13 |  | 10 | 27 | 48 | 2023 | 2023 | R15/16
151638248308 | 151661978308 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-01-25 | 2023-02-03 | 2023-02-03 | 2023-02-22 | 2023-08-14 | Overhead | R15/16 | 2023-02-22 | 8 |  | 14 | 124 | 144 | 2023 | 2023 | R15/16
151684942128 | 151653612128 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-03-08 | 2023-03-08 | 2023-06-13 | 2023-07-20 | 2023-07-21 | Underground | R15/16- Reloc | 2023-07-20 | 1 | 70 | 28 | 2 | 98 | 2023 | 2023 | R15/16
151625087274 | 151640467274 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2021-09-08 |  | 2021-09-10 | 2021-11-19 | 2022-04-21 | Overhead | R15/16 | 2021-11-19 |  |  | 51 | 110 | 162 | 2021 | 2022 | R15/16
151658737290 | 151661237290 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-04-26 | 2023-04-28 | 2023-04-28 | 2023-08-15 | 2023-09-18 | Overhead | R15/16 | 2023-08-15 | 3 |  | 78 | 25 | 104 | 2023 | 2023 | R15/16
151664455101 | 151608475101 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2021-08-24 | 2021-08-24 | 2021-08-24 | 2021-10-13 | 2021-10-13 | Overhead | R15/16 | 2021-10-13 | 1 |  | 37 |  | 37 | 2021 | 2021 | R15/16
151646878441 | 151684518441 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-02-05 | 2023-02-05 | 2023-02-05 | 2023-04-23 | 2023-05-30 | Overhead | R15/16 | 2023-04-23 | 0 |  | 55 | 27 | 82 | 2023 | 2023 | R15/16
151678387682 | 151610547682 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-01-04 | 2023-01-30 | 2023-01-30 |  | 2023-06-01 | Overhead | R15/16 | 2023-02-07 | 19 |  | 7 | 83 | 107 | 2023 | 2023 | R15/16
151674313683 | 151679813683 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-06-28 | 2023-06-28 | 2023-06-28 |  | 2023-10-04 | Overhead | R15/16 | 2023-07-06 | 1 |  | 7 | 65 | 71 | 2023 | 2023 | R15/16
151678534614 | 151609894614 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-04-03 | 2023-04-03 | 2023-04-03 |  | 2023-12-01 | Underground | R15/16- Reloc | 2023-11-09 | 1 |  | 159 | 17 | 175 | 2023 | 2023 | R15/16
151670237107 | 151658997107 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-04-25 | 2023-04-27 | 2023-04-27 |  | 2023-06-29 | Underground | R15/16- Reloc | 2023-05-19 | 3 |  | 17 | 30 | 48 | 2023 | 2023 | R15/16
151646279933 | 151618319933 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-02-21 | 2023-02-21 | 2023-02-21 | 2023-05-05 | 2023-05-08 | Overhead | R15/16 | 2023-05-05 | 1 |  | 54 | 2 | 55 | 2023 | 2023 | R15/16
151668761664 | 151642951664 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-06-09 | 2023-06-09 | 2023-06-09 | 2023-09-08 | 2023-09-14 | Overhead | R15/16 | 2023-09-08 | 1 |  | 66 | 5 | 70 | 2023 | 2023 | R15/16
151646145308 | 151614905308 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-11-10 | 2022-06-27 | Overhead | R15/16 | 2021-11-10 | 1 |  | 55 | 164 | 218 | 2021 | 2022 | R15/16
151629379722 | 151612339722 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-02-17 | 2023-02-17 | 2023-02-17 | 2023-03-21 | 2023-06-12 | Overhead | R15/16 | 2023-03-21 | 1 |  | 23 | 60 | 82 | 2023 | 2023 | R15/16
151645374526 | 151671514526 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-03-17 | 2023-04-03 | 2023-04-03 | 2023-08-29 | 2023-08-31 | Underground | R15/16- Reloc | 2023-08-29 | 12 |  | 107 | 3 | 120 | 2023 | 2023 | R15/16
151642816577 | 151646986577 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-04-19 | 2023-04-21 | 2023-04-21 |  | 2023-08-18 | Underground | R15/16- Reloc | 2023-04-24 | 3 |  | 2 | 85 | 88 | 2023 | 2023 | R15/16
151604693049 | 151675263049 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2022-12-12 |  | 2022-12-21 |  | 2023-02-26 | Overhead | R15/16 | 2023-01-03 |  |  | 10 | 39 | 55 | 2022 | 2023 | R15/16
151690008678 | 151674108678 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-01-31 | 2023-01-31 | 2023-02-07 | 2023-04-18 | 2023-06-13 | Underground | R15/16- Reloc | 2023-04-18 | 1 | 6 | 51 | 41 | 96 | 2023 | 2023 | R15/16
151611508815 | 151601158815 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-07-10 | 2023-07-10 | 2023-08-18 | 2023-12-04 | 2023-12-07 | Underground | R15/16- Reloc | 2023-12-04 | 1 | 30 | 77 | 4 | 109 | 2023 | 2023 | R15/16
151686874594 | 151687544594 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC RFS US | Commercial | 2023-06-30 | 2023-06-30 | 2023-07-10 | 2023-07-25 | 2023-08-24 | Underground | R15/16- Reloc | 2023-07-25 | 1 | 7 | 12 | 23 | 40 | 2023 | 2023 | R15/16
151656140991 | 151636200991 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-02-28 | 2023-02-28 | 2023-02-28 |  | 2023-06-26 | Overhead | R15/16 | 2023-03-16 | 1 |  | 13 | 73 | 85 | 2023 | 2023 | R15/16
151674859244 | 151689079244 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG ELEC SVC DISCON RECON | Residential | 2023-02-07 | 2023-02-13 | 2023-02-13 | 2023-03-24 | 2023-03-27 | Underground | R15/16- Reloc | 2023-03-24 | 5 |  | 30 | 2 | 35 | 2023 | 2023 | R15/16
151638785961 | 151632635961 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-04-12 | 2023-04-14 | 2023-04-14 |  | 2023-08-15 | Overhead | R15/16 | 2023-04-17 | 3 |  | 2 | 87 | 90 | 2023 | 2023 | R15/16
151612544833 | 151684164833 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC DISCON RECON | Residential | 2023-06-29 | 2023-07-12 | 2023-07-12 | 2023-08-29 | 2023-09-06 | Overhead | R15/16 | 2023-08-29 | 10 |  | 35 | 7 | 50 | 2023 | 2023 | R15/16

## Response to Question 2
Table SDGE Q2 - SDG&E Energization Timelines
by Step in Energization Process (Rule 15 timeline)
Standard | Average | Median | Standard | *Estimated | *Estimated | Notes
Steps in the | in business days11 | in business days | Deviation in business days | Reasonable | Maximum
Energization |  |  |  | Average (business day) | (business day)
Process
Customer Initiation | 41 | 4 | 69
Engineering &Design | 184 | 141 | 152
Dependencies | *included in Engineering & Design | *included in Engineering & Design | *included in Engineering & Design
Site Readiness | 151 | 120 | 128
Construction | 80 | 31 | 120
*Only provide these fields if there is no data available on the energization process step.
1. SDG&E uses an excel spreadsheet function to estimate the number of business days. It may not fully reflect the actual business days as it only excludes weekends, but may include non-working holidays.

## Response to Question 3
Table SDGE Q3 - Energization Timelines by Upstream Distribution Capacity Upgrade Type
Upstream Distribution Capacity Upgrade Type | Average (business days1) | Median (business days) | Standard Deviation (business days) | Percentage of Instances Upgrade Type is Triggered by an Energization Request | Notes
New and upgrade circuits | 646 | 626 | 181 | N/A
1. SDG&E uses an excel spreadsheet function to estimate the number of business days. It may not fully reflect the actual business days as it only excludes weekends, but may include non-working holidays.

## Response to Question 4
Table SDGE Q4 - Energization Timelines by Tariff Type (in business days)
Tariff | Average | Median (day) | Standard | Notes
| (day) |  | Deviation (day)
Rule 15 | 450 | 417 | 230 | Job initiation (not AFS) to energize date; includes all stakeholders activities and generally occurring delays
Rule 16 | 188 | 121 | 188 | Job initiation (not AFS) to energize date; includes all stakeholders activities and generally occurring delays
Rule 15 and 16 | 149 | 93 | 168 | Job initiation (not AFS) to energize date; includes all stakeholders activities and generally occurring delays
Rule 45 | n/a | n/a | n/a | n/a, only one site energized in 2023
Rule 15 and | n/a | n/a | n/a | n/a
45
1. SDG&E uses an excel spreadsheet function to estimate the number of business days. It may not fully reflect the actual business days as it only excludes weekends, but may include non-working holidays.