## Rule15SourceDataQuestions2&4
PROJECT_NBR | JOB_NBR | CONSTR_ORD_TYPE_CODE_DESC | JOB_WORK_TYPE_CODE_DESC | RES_COM_IND | JOB_ORIG_DATE | CA_PLANING_DATE | PRE_CONSTR_PHASE_START_DATE | CONSTR_PHASE_START_DATE | Energize_Complete | OH/UG | Rule | Construction_Start_Date | IN to IP | IP to PC | PC to CO | CO to EN | IN to EN | Job Orig Year | Energ/Complete Year | Tariff
150101287911 | 159934911101 | NON-RESIDENTIAL - LARGE OFFICE | UG EXT NON RES | Commercial | 2021-07-09 | 2021-07-09 | 2022-08-04 | 2023-02-21 | 2023-09-05 | Underground | R15 | 2023-02-21 | 1 | 280 | 144 | 141 | 563 | 2021 | 2023 | R15
157576248540 | 153494540576 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2021-06-10 | 2021-08-22 | 2021-09-19 | 2022-03-04 | 2022-06-07 | Overhead | R15 | 2022-03-04 | 52 | 20 | 120 | 68 | 259 | 2021 | 2022 | R15
158823250701 | 150161701823 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Residential | 2021-07-11 | 2021-07-11 | 2021-10-05 | 2022-02-08 | 2022-02-23 | Overhead | R15 | 2022-02-08 | 0 | 62 | 91 | 12 | 163 | 2021 | 2022 | R15
158426278239 | 151917239426 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-07-19 | 2021-11-11 | 2022-05-06 | 2023-08-15 | 2023-09-18 | Overhead | R15 | 2023-08-15 | 84 | 127 | 333 | 25 | 566 | 2021 | 2023 | R15
152676279848 | 152532848676 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-07-21 | 2021-10-26 | 2022-05-19 | 2023-03-09 | 2023-12-26 | Underground | R15 | 2023-03-09 | 70 | 148 | 211 | 209 | 635 | 2021 | 2023 | R15
152629325750 | 152319750629 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Residential | 2021-07-21 | 2021-07-21 | 2023-07-21 | 2023-09-29 | 2023-10-23 | Overhead | R15 | 2023-09-29 | 1 | 523 | 51 | 17 | 589 | 2021 | 2023 | R15
153798246569 | 153883569798 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-01-16 | 2020-05-08 | 2021-09-03 |  | 2022-10-24 | Underground | R15 |  | 82 | 346 |  |  | 723 | 2020 | 2022 | R15
156687255897 | 152585897687 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential Subdivision | 2020-06-17 | 2021-04-21 | 2021-11-10 | 2022-07-01 | 2022-07-18 | Underground | R15 | 2022-07-01 | 221 | 146 | 168 | 12 | 544 | 2020 | 2022 | R15
159356223510 | 156923510356 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-07-09 | 2021-01-06 | 2021-03-15 | 2021-09-10 | 2021-10-20 | Underground | R15 | 2021-09-10 | 130 | 49 | 130 | 29 | 335 | 2020 | 2021 | R15
157142224336 | 157171336142 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-05-14 | 2020-05-14 | 2021-03-22 | 2021-11-04 | 2021-11-23 | Underground | R15 | 2021-11-04 | 1 | 223 | 164 | 14 | 399 | 2020 | 2021 | R15
157879261302 | 157920302879 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-02-04 | 2021-01-08 | 2021-12-14 | 2023-02-09 | 2022-11-04 | Underground | R15 | 2023-02-09 | 244 | 243 | 303 |  | 719 | 2020 | 2022 | R15
157916226800 | 157917800916 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-02-04 | 2021-01-29 | 2021-04-13 | 2021-08-21 | 2021-10-11 | Underground | R15 | 2021-08-21 | 259 | 53 | 94 | 36 | 440 | 2020 | 2021 | R15
158608202644 | 151847644608 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-06-12 | 2020-06-17 | 2020-09-02 | 2020-10-19 | 2020-11-10 | Overhead | R15 | 2020-10-19 | 4 | 56 | 34 | 17 | 108 | 2020 | 2020 | R15
157242240766 | 157243766242 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Residential | 2020-05-14 | 2021-02-08 | 2021-07-26 | 2022-04-21 | 2022-05-04 | Underground | R15 | 2022-04-21 | 193 | 121 | 194 | 10 | 515 | 2020 | 2022 | R15
155444191586 | 155031586444 | CUSTOMER UPGRADE IN SERVICE | UG RES INDIVIDUAL | Residential | 2020-05-01 | 2020-05-01 | 2020-05-19 | 2020-05-19 | 2020-12-21 | Underground | R15 | 2020-05-19 | 1 | 13 |  | 155 | 167 | 2020 | 2020 | R15
157018207107 | 154978107018 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-06-29 | 2020-06-30 | 2020-10-13 | 2021-08-23 | 2021-12-09 | Underground | R15 | 2021-08-23 | 2 | 76 | 225 | 79 | 379 | 2020 | 2021 | R15
157020197284 | 158578284020 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-05-22 | 2020-05-26 | 2020-07-14 | 2020-07-20 | 2020-09-23 | Underground | R15 | 2020-07-20 | 3 | 36 | 5 | 48 | 89 | 2020 | 2020 | R15
153429199213 | 157469213429 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential Subdivision | 2020-02-03 | 2020-04-06 | 2020-08-03 | 2020-12-10 | 2023-09-17 | Underground | R15 | 2020-12-10 | 46 | 86 | 94 | 722 | 945 | 2020 | 2023 | R15
159724208126 | 150351126724 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Commercial | 2020-04-06 | 2020-09-04 | 2020-10-23 |  | 2021-11-04 | Overhead | R15 |  | 110 | 36 |  |  | 414 | 2020 | 2021 | R15
158220247722 | 158216722220 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-02-05 | 2021-06-24 | 2021-09-13 | 2022-07-27 | 2022-09-08 | Underground | R15 | 2022-07-27 | 362 | 58 | 228 | 32 | 677 | 2020 | 2022 | R15
151271202278 | 151173278271 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-06-09 | 2020-06-09 | 2020-09-02 | 2021-02-17 | 2021-03-10 | Overhead | R15 | 2021-02-17 | 1 | 62 | 121 | 16 | 197 | 2020 | 2021 | R15
151430231281 | 154219281430 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2020-06-24 | 2020-06-24 | 2021-05-18 | 2021-06-14 | 2021-10-19 | Overhead | R15 | 2021-06-14 | 1 | 235 | 20 | 92 | 345 | 2020 | 2021 | R15
156949196591 | 156781591949 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-01-30 | 2020-02-03 | 2020-07-07 | 2020-11-09 | 2020-12-16 | Underground | R15 | 2020-11-09 | 3 | 112 | 90 | 28 | 230 | 2020 | 2020 | R15
156476217683 | 158611683476 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2020-05-22 | 2020-05-27 | 2021-01-19 |  | 2022-08-01 | Overhead | R15 |  | 4 | 170 |  |  | 572 | 2020 | 2022 | R15
158005153226 | 153829226005 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-04-17 | 2019-04-19 | 2019-05-23 |  | 2019-12-19 | Underground | R15 |  | 3 | 25 |  |  | 177 | 2019 | 2019 | R15
159356250838 | 159203838356 | FOREIGN UTILITY | UG EXT NON RES | Commercial | 2020-02-11 | 2020-02-21 | 2021-10-06 | 2021-11-15 | 2021-12-14 | Underground | R15 | 2021-11-15 | 9 | 424 | 29 | 22 | 481 | 2020 | 2021 | R15
154695220963 | 154633963695 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-03-06 | 2020-09-23 | 2021-02-18 | 2021-10-06 | 2021-10-21 | Underground | R15 | 2021-10-06 | 144 | 107 | 165 | 12 | 425 | 2020 | 2021 | R15
152468228942 | 152552942468 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-04-17 | 2020-04-28 | 2021-04-30 | 2021-12-17 | 2022-01-11 | Underground | R15 | 2021-12-17 | 8 | 264 | 166 | 18 | 453 | 2020 | 2022 | R15
150147199299 | 157448299147 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG EXT NON RES | Commercial | 2020-05-15 | 2020-05-15 | 2020-07-31 | 2020-09-24 | 2021-01-21 | Underground | R15 | 2020-09-24 | 1 | 56 | 40 | 86 | 180 | 2020 | 2021 | R15
152941215365 | 152959365941 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Commercial | 2020-01-13 | 2020-01-13 | 2020-12-22 | 2021-06-16 | 2021-08-10 | Underground | R15 | 2021-06-16 | 1 | 247 | 127 | 40 | 412 | 2020 | 2021 | R15
158236264810 | 157038810236 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-07-10 | 2020-12-01 | 2022-01-14 | 2023-11-06 | 2023-11-28 | Underground | R15 | 2023-11-06 | 103 | 294 | 472 | 17 | 883 | 2020 | 2023 | R15
152109258598 | 159830598109 | NON-RESIDENTIAL - LODGING | UG EXT NON RES | Commercial | 2020-02-13 | 2020-04-27 | 2021-11-24 | 2023-06-30 | 2023-07-25 | Underground | R15 | 2023-06-30 | 53 | 413 | 418 | 18 | 899 | 2020 | 2023 | R15
153785193716 | 155391716785 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-03-10 | 2020-03-11 | 2020-06-09 | 2020-06-09 | 2020-09-01 | Overhead | R15 | 2020-06-09 | 2 | 65 |  | 61 | 126 | 2020 | 2020 | R15
155020210119 | 155876119020 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2020-07-02 | 2020-08-23 | 2020-11-10 | 2021-10-21 | 2022-10-29 | Overhead | R15 | 2021-10-21 | 37 | 57 | 248 | 267 | 607 | 2020 | 2022 | R15
151364252773 | 151401773364 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-02-20 | 2020-02-20 | 2021-10-19 | 2022-09-07 | 2022-10-03 | Underground | R15 | 2022-09-07 | 1 | 434 | 232 | 19 | 683 | 2020 | 2022 | R15
155171219859 | 156806859171 | NON-RESIDENTIAL - LOT DEVELOPMENT | UG DEV NON RES | Commercial | 2020-05-12 | 2020-05-15 | 2021-02-08 | 2021-10-29 | 2022-01-31 | Underground | R15 | 2021-10-29 | 4 | 192 | 190 | 67 | 450 | 2020 | 2022 | R15
153067211362 | 158108362067 | RESIDENTIAL - MULTI-FAMILY | OH DEVELOPMENT RESD OD | Residential | 2020-02-05 | 2020-05-06 | 2020-11-19 | 2021-05-23 | 2021-06-18 | Overhead | R15 | 2021-05-23 | 66 | 142 | 132 | 20 | 358 | 2020 | 2021 | R15
151980211207 | 152950207980 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-06-17 | 2020-09-02 | 2020-11-18 | 2020-12-02 | 2021-04-16 | Overhead | R15 | 2020-12-02 | 56 | 56 | 11 | 98 | 218 | 2020 | 2021 | R15
152196219555 | 154737555196 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2020-01-21 | 2020-07-16 | 2021-02-05 | 2021-03-08 | 2021-03-25 | Overhead | R15 | 2021-03-08 | 128 | 147 | 22 | 14 | 308 | 2020 | 2021 | R15
152831323774 | 150286774831 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-12-30 | 2019-12-30 | 2023-06-30 | 2023-08-21 | 2023-11-21 | Overhead | R15 | 2023-08-21 | 1 | 915 | 37 | 67 | 1017 | 2019 | 2023 | R15
150756230021 | 153269021756 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Commercial | 2020-06-19 | 2020-12-28 | 2021-05-08 | 2022-07-05 | 2022-07-25 | Overhead | R15 | 2022-07-05 | 137 | 95 | 302 | 15 | 547 | 2020 | 2022 | R15
153094214336 | 153135336094 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Commercial | 2020-01-13 | 2020-01-13 | 2020-12-18 | 2021-07-28 | 2021-08-25 | Underground | R15 | 2021-07-28 | 1 | 245 | 159 | 21 | 423 | 2020 | 2021 | R15
159878188770 | 153148770878 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2020-01-13 | 2020-01-24 | 2020-04-22 | 2020-08-20 | 2020-12-23 | Overhead | R15 | 2020-08-20 | 10 | 64 | 87 | 90 | 248 | 2020 | 2020 | R15
159314248749 | 159276749314 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Commercial | 2020-03-31 | 2020-03-31 | 2021-09-20 | 2023-02-08 | 2023-03-01 | Underground | R15 | 2023-02-08 | 1 | 385 | 363 | 16 | 762 | 2020 | 2023 | R15
154299210541 | 159739541299 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2020-04-02 | 2020-07-13 | 2020-11-12 | 2021-01-11 | 2022-08-25 | Underground | R15 | 2021-01-11 | 73 | 89 | 43 | 424 | 626 | 2020 | 2022 | R15
159581234819 | 159583819581 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-02-12 | 2020-02-12 | 2021-06-15 | 2021-08-19 | 2023-10-02 | Underground | R15 | 2021-08-19 | 1 | 350 | 48 | 553 | 949 | 2020 | 2023 | R15
158462218507 | 154043507462 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2020-04-27 | 2020-04-27 | 2021-01-26 | 2021-03-12 | 2021-04-26 | Overhead | R15 | 2021-03-12 | 1 | 197 | 34 | 32 | 261 | 2020 | 2021 | R15
151919223702 | 152010702919 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential | 2020-01-08 | 2020-03-25 | 2021-03-15 | 2022-01-06 | 2022-02-04 | Underground | R15 | 2022-01-06 | 56 | 254 | 214 | 22 | 543 | 2020 | 2022 | R15
151399227765 | 152080765399 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2020-06-12 | 2020-12-17 | 2021-04-20 | 2021-06-14 | 2021-07-28 | Overhead | R15 | 2021-06-14 | 135 | 89 | 40 | 33 | 294 | 2020 | 2021 | R15
159261237462 | 155472462261 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Commercial | 2020-03-10 | 2020-10-28 | 2021-07-01 | 2022-10-11 | 2022-11-04 | Underground | R15 | 2022-10-11 | 167 | 177 | 334 | 19 | 694 | 2020 | 2022 | R15
156691233354 | 155969354691 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Residential | 2020-03-12 | 2020-03-17 | 2021-06-03 | 2021-06-17 | 2021-11-15 | Overhead | R15 | 2021-06-17 | 4 | 318 | 11 | 108 | 438 | 2020 | 2021 | R15
150048288995 | 158205995048 | Affordable Housing | UG DEV RES | Residential | 2020-03-25 | 2020-03-25 | 2022-08-16 | 2023-05-25 | 2023-08-11 | Underground | R15 | 2023-05-25 | 1 | 625 | 203 | 57 | 883 | 2020 | 2023 | R15
158700193719 | 156018719700 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-05-08 | 2020-05-08 | 2020-06-09 | 2020-10-28 | 2021-02-16 | Underground | R15 | 2020-10-28 | 1 | 23 | 102 | 80 | 203 | 2020 | 2021 | R15
159628189071 | 150203071628 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-04-06 | 2020-04-06 | 2020-04-28 | 2020-05-20 | 2020-05-21 | Overhead | R15 | 2020-05-20 | 1 | 17 | 17 | 2 | 34 | 2020 | 2020 | R15
155683217374 | 152434374683 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-06-16 | 2020-11-05 | 2021-01-15 | 2021-04-23 | 2021-06-02 | Underground | R15 | 2021-04-23 | 103 | 52 | 71 | 29 | 252 | 2020 | 2021 | R15
151353213495 | 153118495353 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-01-13 | 2020-01-13 | 2020-12-10 | 2022-06-30 | 2022-08-02 | Underground | R15 | 2022-06-30 | 1 | 239 | 406 | 24 | 667 | 2020 | 2022 | R15
157696304958 | 150228958696 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-04-06 | 2020-04-10 | 2023-01-30 | 2023-02-14 | 2023-02-06 | Overhead | R15 | 2023-02-14 | 5 | 732 | 12 |  | 741 | 2020 | 2023 | R15
154450243438 | 154387438450 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-06-25 | 2020-06-25 | 2021-08-13 | 2022-06-07 | 2022-07-19 | Overhead | R15 | 2022-06-07 | 1 | 297 | 213 | 31 | 539 | 2020 | 2022 | R15
157806274754 | 155252754806 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-03-10 | 2020-07-07 | 2022-04-05 | 2022-05-24 | 2022-06-13 | Underground | R15 | 2022-05-24 | 86 | 456 | 36 | 15 | 590 | 2020 | 2022 | R15
154343276824 | 155292824343 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Residential | 2021-08-02 | 2021-11-03 | 2022-04-22 | 2022-05-12 | 2022-06-13 | Overhead | R15 | 2022-05-12 | 68 | 123 | 15 | 23 | 226 | 2021 | 2022 | R15
151156313437 | 158733437156 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-08-16 | 2021-08-16 | 2023-03-24 | 2023-05-24 | 2023-07-07 | Overhead | R15 | 2023-05-24 | 1 | 420 | 44 | 33 | 495 | 2021 | 2023 | R15
150829275933 | 155449933829 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2021-09-14 | 2021-09-15 | 2022-04-14 | 2022-05-13 | 2022-06-20 | Overhead | R15 | 2022-05-13 | 2 | 152 | 22 | 27 | 200 | 2021 | 2022 | R15
150307298527 | 154458527307 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential | 2021-09-10 | 2021-09-10 | 2022-10-27 | 2023-03-02 | 2023-03-09 | Underground | R15 | 2023-03-02 | 1 | 295 | 91 | 6 | 390 | 2021 | 2023 | R15
154906282327 | 155275327906 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential Subdivision | 2021-08-02 | 2021-09-28 | 2022-06-10 | 2022-11-09 | 2022-12-06 | Underground | R15 | 2022-11-09 | 42 | 184 | 109 | 20 | 352 | 2021 | 2022 | R15
157509296384 | 159687384509 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-08-18 | 2021-08-18 | 2022-10-07 |  | 2023-03-09 | Underground | R15 | 2023-02-03 | 1 | 298 | 86 | 25 | 407 | 2021 | 2023 | R15
154906282324 | 155274324906 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential Subdivision | 2021-08-02 | 2021-09-28 | 2022-06-10 |  | 2022-09-13 | Overhead | R15 | 2022-08-08 | 42 | 184 | 42 | 27 | 292 | 2021 | 2022 | R15
154906282324 | 155274324906 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential Subdivision | 2021-08-02 | 2021-09-28 | 2022-06-10 |  | 2022-09-13 | Overhead | R15 | 2022-08-08 | 42 | 184 | 42 | 27 | 292 | 2021 | 2022 | R15
151945335781 | 158887781945 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2023-07-03 | 2023-10-03 | 2023-10-16 | 2023-12-15 | 2023-12-28 | Overhead | R15 | 2023-12-15 | 67 | 10 | 45 | 10 | 129 | 2023 | 2023 | R15
156638336825 | 158256825638 | AGRICULTURAL | OH EXTENSION NON RESD OD | Commercial | 2021-08-12 | 2022-01-07 | 2023-10-25 | 2023-11-27 | 2023-12-21 | Overhead | R15 | 2023-11-27 | 107 | 469 | 24 | 19 | 616 | 2021 | 2023 | R15
155095192400 | 156987400095 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-12-10 | 2019-12-10 | 2020-05-27 | 2020-09-09 | 2021-03-19 | Underground | R15 | 2020-09-09 | 1 | 122 | 76 | 138 | 334 | 2019 | 2021 | R15
154498202394 | 154507394498 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2019-10-03 | 2019-10-03 | 2020-09-01 | 2021-03-12 | 2021-04-30 | Underground | R15 | 2021-03-12 | 1 | 239 | 139 | 36 | 412 | 2019 | 2021 | R15
155709198631 | 155933631709 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential Subdivision | 2019-06-25 | 2019-06-25 | 2020-07-27 | 2022-05-16 | 2022-05-27 | Underground | R15 | 2022-05-16 | 1 | 285 | 471 | 10 | 764 | 2019 | 2022 | R15
152986225247 | 154345247986 | Electric Vehicle | UG EXT NON RES | Commercial | 2019-11-20 | 2020-01-29 | 2021-03-30 | 2021-07-19 | 2021-10-19 | Underground | R15 | 2021-07-19 | 51 | 305 | 80 | 67 | 500 | 2019 | 2021 | R15
156331178511 | 156172511331 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-06-25 | 2019-07-18 | 2020-01-29 | 2020-10-23 | 2021-11-12 | Underground | R15 | 2020-10-23 | 18 | 140 | 193 | 276 | 624 | 2019 | 2021 | R15
159208210244 | 159296244208 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-09-05 | 2019-09-05 | 2020-11-10 | 2021-03-29 | 2021-06-21 | Underground | R15 | 2021-03-29 | 1 | 309 | 100 | 61 | 468 | 2019 | 2021 | R15
150077184068 | 159520068077 | NON-RESIDENTIAL - HEALTH CARE | OH EXTENSION NON RESD OD | Commercial | 2019-10-28 | 2019-11-15 | 2020-03-13 | 2020-04-03 | 2020-08-17 | Overhead | R15 | 2020-04-03 | 15 | 86 | 16 | 97 | 211 | 2019 | 2020 | R15
159437251681 | 153636681437 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2019-09-30 | 2019-09-30 | 2021-10-11 | 2022-04-21 | 2022-05-10 | Underground | R15 | 2022-04-21 | 1 | 531 | 139 | 14 | 682 | 2019 | 2022 | R15
154424222362 | 154337362424 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential Subdivision | 2019-08-08 | 2019-08-08 | 2021-03-03 | 2021-12-08 | 2022-01-04 | Underground | R15 | 2021-12-08 | 1 | 410 | 201 | 20 | 629 | 2019 | 2022 | R15
158680204383 | 158691383680 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-10-23 | 2019-10-23 | 2020-09-18 | 2021-02-04 | 2021-04-15 | Underground | R15 | 2021-02-04 | 1 | 238 | 100 | 51 | 387 | 2019 | 2021 | R15
155224172547 | 156093547224 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2019-01-08 | 2019-01-08 | 2019-11-21 |  | 2021-11-08 | Underground | R15 |  | 1 | 228 |  |  | 740 | 2019 | 2021 | R15
155221164920 | 152451920221 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-07-29 | 2019-08-14 | 2019-09-17 | 2020-02-20 | 2020-07-07 | Overhead | R15 | 2020-02-20 | 13 | 25 | 113 | 99 | 247 | 2019 | 2020 | R15
159437248407 | 153633407437 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2019-09-30 | 2019-09-30 | 2021-09-17 |  | 2022-06-21 | Underground | R15 | 2022-05-31 | 1 | 515 | 183 | 16 | 712 | 2019 | 2022 | R15
155685246317 | 155686317685 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-12-02 | 2020-10-14 | 2021-09-02 | 2022-11-01 | 2023-02-06 | Underground | R15 | 2022-11-01 | 228 | 232 | 304 | 70 | 831 | 2019 | 2023 | R15
157018272195 | 155273195018 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2019-06-20 | 2020-03-13 | 2022-03-11 | 2022-03-31 | 2022-08-02 | Overhead | R15 | 2022-03-31 | 192 | 521 | 15 | 89 | 814 | 2019 | 2022 | R15
151970213221 | 151885221970 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-07-25 | 2019-07-25 | 2020-12-08 | 2021-07-27 | 2022-01-07 | Underground | R15 | 2021-07-27 | 1 | 359 | 166 | 119 | 642 | 2019 | 2022 | R15
155672249602 | 155673602672 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2021-05-14 | 2021-05-14 | 2021-09-27 | 2021-10-20 | 2021-11-30 | Underground | R15 | 2021-10-20 | 1 | 97 | 18 | 30 | 143 | 2021 | 2021 | R15
157501254154 | 157356154501 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-08-28 | 2020-08-28 | 2021-10-28 | 2023-08-17 | 2023-09-25 | Underground | R15 | 2023-08-17 | 1 | 305 | 471 | 28 | 802 | 2020 | 2023 | R15
157325282165 | 159886165325 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2020-10-22 | 2021-08-30 | 2022-06-09 | 2022-06-21 | 2023-12-26 | Underground | R15 | 2022-06-21 | 223 | 204 | 9 | 396 | 829 | 2020 | 2023 | R15
154141243263 | 155948263141 | Electric Vehicle | UG EXT NON RES | Commercial | 2021-02-23 | 2021-03-31 | 2021-08-12 | 2022-08-10 | 2022-10-03 | Underground | R15 | 2022-08-10 | 27 | 97 | 260 | 39 | 420 | 2021 | 2022 | R15
159893251107 | 154923107893 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-05-13 | 2021-06-07 | 2021-10-07 | 2022-03-23 | 2022-04-25 | Underground | R15 | 2022-03-23 | 18 | 89 | 120 | 24 | 248 | 2021 | 2022 | R15
151532263950 | 159622950532 | CUSTOMER UPGRADE IN SERVICE | UG R15 RES NON RES BUDG 225 | Commercial | 2021-04-21 | 2021-06-24 | 2022-01-07 | 2023-06-15 | 2023-07-28 | Underground | R15 | 2023-06-15 | 47 | 142 | 375 | 32 | 593 | 2021 | 2023 | R15
151194269939 | 158237939194 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-04-15 | 2021-04-20 | 2022-02-22 | 2022-06-16 | 2022-07-01 | Underground | R15 | 2022-06-16 | 4 | 221 | 83 | 12 | 317 | 2021 | 2022 | R15
150520295109 | 151681109520 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential Subdivision | 2020-10-30 | 2020-10-30 | 2022-09-27 | 2023-07-03 | 2023-07-21 | Underground | R15 | 2023-07-03 | 1 | 498 | 200 | 15 | 711 | 2020 | 2023 | R15
156250236019 | 152924019250 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-02-12 | 2019-02-15 | 2021-06-22 | 2022-01-04 | 2022-01-24 | Underground | R15 | 2022-01-04 | 4 | 613 | 141 | 15 | 770 | 2019 | 2022 | R15
157254236069 | 152833069254 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2020-09-23 | 2021-01-27 | 2021-06-21 | 2021-10-12 | 2021-10-28 | Overhead | R15 | 2021-10-12 | 91 | 104 | 82 | 13 | 287 | 2020 | 2021 | R15
157397232995 | 157534995397 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2020-11-30 | 2020-12-03 | 2021-06-02 | 2021-06-25 | 2022-03-02 | Overhead | R15 | 2021-06-25 | 4 | 130 | 18 | 179 | 328 | 2020 | 2022 | R15
157916241904 | 159289904916 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2021-05-24 | 2021-05-24 | 2021-08-03 | 2021-08-21 | 2022-02-03 | Underground | R15 | 2021-08-21 | 1 | 52 | 14 | 119 | 184 | 2021 | 2022 | R15
159528297082 | 159479082528 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-12-09 | 2020-12-09 | 2022-10-14 | 2023-08-25 | 2023-09-20 | Underground | R15 | 2023-08-25 | 1 | 483 | 226 | 19 | 726 | 2020 | 2023 | R15
152503196736 | 158657736503 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-03-18 | 2019-03-18 | 2020-07-08 | 2020-11-04 | 2021-02-27 | Underground | R15 | 2020-11-04 | 1 | 343 | 86 | 83 | 510 | 2019 | 2021 | R15
152084167434 | 152186434084 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-02-08 | 2019-02-08 | 2019-10-08 | 2021-06-14 | 2021-07-13 | Underground | R15 | 2021-06-14 | 1 | 173 | 440 | 22 | 633 | 2019 | 2021 | R15
159506177173 | 151017173506 | CUSTOMER UPGRADE IN SERVICE | UG R15 RES NON RES BUDG 225 | Commercial | 2019-05-28 | 2019-05-31 | 2020-01-16 | 2020-04-15 | 2020-05-27 | Underground | R15 | 2020-04-15 | 4 | 165 | 65 | 31 | 262 | 2019 | 2020 | R15
154939216431 | 154970431939 | Electric Vehicle | UG EXT NON RES | Commercial | 2019-04-22 | 2020-09-17 | 2021-01-07 | 2021-10-13 | 2021-11-03 | Underground | R15 | 2021-10-13 | 369 | 81 | 200 | 16 | 663 | 2019 | 2021 | R15
151794226703 | 155621703794 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2020-10-02 | 2021-02-10 | 2021-04-13 | 2021-05-24 | 2021-09-24 | Underground | R15 | 2021-05-24 | 94 | 45 | 30 | 90 | 256 | 2020 | 2021 | R15
155884236522 | 155756522884 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-11-19 | 2020-11-19 | 2021-06-24 | 2023-03-07 | 2023-04-05 | Underground | R15 | 2023-03-07 | 1 | 156 | 444 | 22 | 620 | 2020 | 2023 | R15
155670263750 | 155671750670 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2021-05-14 | 2021-06-09 | 2022-01-06 | 2022-07-12 | 2022-08-01 | Underground | R15 | 2022-07-12 | 19 | 152 | 134 | 15 | 317 | 2021 | 2022 | R15
152852232352 | 153443352852 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2020-08-12 | 2020-08-13 | 2021-05-26 |  | 2022-03-10 | Underground | R15 |  | 2 | 205 |  |  | 412 | 2020 | 2022 | R15
158943247186 | 156412186943 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-04-07 | 2021-04-07 | 2021-09-09 | 2022-01-04 | 2023-12-26 | Underground | R15 | 2022-01-04 | 1 | 112 | 84 | 516 | 710 | 2021 | 2023 | R15
158943246994 | 158906994943 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-10-19 | 2020-10-19 | 2021-09-09 | 2021-11-12 | 2022-02-08 | Underground | R15 | 2021-11-12 | 1 | 234 | 47 | 63 | 342 | 2020 | 2022 | R15
152717173379 | 152636379717 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2019-04-10 | 2019-04-10 | 2019-12-02 | 2020-03-05 | 2021-02-25 | Underground | R15 | 2020-03-05 | 1 | 169 | 69 | 256 | 492 | 2019 | 2021 | R15
155782226030 | 156391030782 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-10-07 | 2021-01-27 | 2021-04-07 | 2021-09-23 | 2021-10-27 | Underground | R15 | 2021-09-23 | 81 | 51 | 122 | 25 | 276 | 2020 | 2021 | R15
154031173033 | 154425033031 | CUSTOMER UPGRADE IN SERVICE | UG RES INDIVIDUAL | Residential | 2019-02-20 | 2019-02-20 | 2019-11-26 | 2021-08-25 | 2021-09-30 | Underground | R15 | 2021-08-25 | 1 | 200 | 457 | 27 | 682 | 2019 | 2021 | R15
155221259194 | 155234194221 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Commercial | 2020-10-01 | 2021-02-01 | 2021-11-30 | 2023-03-29 | 2023-04-21 | Underground | R15 | 2023-03-29 | 88 | 217 | 347 | 18 | 667 | 2020 | 2023 | R15
152051153195 | 152490195051 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-02-08 | 2019-04-14 | 2019-05-23 | 2019-07-23 | 2020-01-08 | Overhead | R15 | 2019-07-23 | 46 | 29 | 44 | 122 | 239 | 2019 | 2020 | R15
150638236592 | 158205592638 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-03-04 | 2021-03-04 | 2021-06-25 | 2021-09-06 | 2023-09-15 | Overhead | R15 | 2021-09-06 | 1 | 82 | 52 | 530 | 662 | 2021 | 2023 | R15
157736221406 | 150366406736 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-05-22 | 2019-06-14 | 2021-02-23 | 2021-04-20 | 2021-05-24 | Underground | R15 | 2021-04-20 | 18 | 443 | 41 | 25 | 524 | 2019 | 2021 | R15
151085272556 | 151234556085 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-02-01 | 2021-02-01 | 2022-03-14 | 2022-08-10 | 2022-08-19 | Underground | R15 | 2022-08-10 | 1 | 291 | 108 | 8 | 405 | 2021 | 2022 | R15
151776242735 | 151859735776 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-04-30 | 2021-04-30 | 2021-08-10 |  | 2021-12-09 | Underground | R15 | 2022-08-16 | 1 | 73 | 266 |  | 160 | 2021 | 2021 | R15
156479157913 | 150906913479 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-04-01 | 2019-06-06 | 2019-07-16 | 2019-08-26 | 2019-11-12 | Underground | R15 | 2019-08-26 | 49 | 29 | 30 | 57 | 162 | 2019 | 2019 | R15
152803234083 | 150182083803 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-07-27 | 2020-12-17 | 2021-06-08 | 2021-08-19 | 2021-10-18 | Underground | R15 | 2021-08-19 | 104 | 124 | 53 | 43 | 321 | 2020 | 2021 | R15
155577245971 | 155578971577 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential | 2021-05-14 | 2021-05-14 | 2021-08-30 | 2021-09-07 | 2021-10-26 | Underground | R15 | 2021-09-07 | 1 | 77 | 7 | 36 | 118 | 2021 | 2021 | R15
157664271269 | 157045269664 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2021-04-09 | 2021-04-29 | 2022-03-03 | 2022-06-14 | 2022-10-04 | Overhead | R15 | 2022-06-14 | 15 | 221 | 74 | 81 | 388 | 2021 | 2022 | R15
151392242736 | 155908736392 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential Subdivision | 2021-05-17 | 2021-05-17 | 2021-08-10 | 2021-09-01 | 2021-10-06 | Underground | R15 | 2021-09-01 | 1 | 62 | 17 | 26 | 103 | 2021 | 2021 | R15
159753296081 | 159698081753 | NON-RESIDENTIAL - WAREHOUSE | UG EXT NON RES | Commercial | 2021-05-25 | 2021-05-25 | 2022-10-05 | 2023-06-23 | 2023-10-03 | Underground | R15 | 2023-06-23 | 1 | 357 | 188 | 73 | 616 | 2021 | 2023 | R15
155483256838 | 154082838483 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-12-30 | 2021-04-28 | 2021-11-17 | 2023-09-27 | 2023-10-20 | Underground | R15 | 2023-09-27 | 86 | 146 | 486 | 18 | 733 | 2020 | 2023 | R15
156489206385 | 156496385489 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-05-01 | 2019-05-01 | 2020-10-06 | 2020-11-12 | 2021-04-06 | Underground | R15 | 2020-11-12 | 1 | 375 | 28 | 104 | 505 | 2019 | 2021 | R15
158527251757 | 155304757527 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2021-02-18 | 2021-03-02 | 2021-10-12 | 2021-10-25 | 2021-11-12 | Overhead | R15 | 2021-10-25 | 9 | 161 | 10 | 15 | 192 | 2021 | 2021 | R15
159691165092 | 150887092691 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-02-01 | 2019-05-23 | 2019-09-19 | 2020-02-05 | 2020-10-21 | Underground | R15 | 2020-02-05 | 80 | 86 | 100 | 186 | 449 | 2019 | 2020 | R15
156687221014 | 156747014687 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential Subdivision | 2019-01-11 | 2019-01-11 | 2021-02-22 |  | 2022-06-23 | Underground | R15 | 2022-01-06 | 1 | 552 | 229 | 121 | 900 | 2019 | 2022 | R15
158977221695 | 150364695977 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-07-27 | 2020-09-09 | 2021-02-26 | 2021-09-14 | 2021-09-24 | Underground | R15 | 2021-09-14 | 33 | 123 | 143 | 9 | 305 | 2020 | 2021 | R15
159735178689 | 156088689735 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential Subdivision | 2019-03-04 | 2019-04-11 | 2020-01-30 | 2020-12-18 | 2021-01-21 | Underground | R15 | 2020-12-18 | 29 | 211 | 232 | 25 | 494 | 2019 | 2021 | R15
154182288755 | 156391755182 | Affordable Housing | UG DEV RES | Residential | 2020-11-21 | 2022-03-16 | 2022-08-12 | 2022-11-09 | 2022-12-13 | Underground | R15 | 2022-11-09 | 343 | 108 | 64 | 25 | 537 | 2020 | 2022 | R15
150924192428 | 150856428924 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2019-02-01 | 2019-02-01 | 2020-05-28 | 2021-06-24 | 2021-07-13 | Overhead | R15 | 2021-06-24 | 1 | 345 | 281 | 14 | 638 | 2019 | 2021 | R15
156489274923 | 156497923489 | NON-RESIDENTIAL - LODGING | UG EXT NON RES | Commercial | 2019-05-01 | 2019-05-01 | 2022-04-05 | 2022-12-01 | 2022-12-22 | Underground | R15 | 2022-12-01 | 1 | 765 | 173 | 16 | 952 | 2019 | 2022 | R15
155847282779 | 156696779847 | NON-RESIDENTIAL - HEALTH CARE | UG EXT NON RES | Commercial | 2021-02-25 | 2021-02-25 | 2022-06-16 | 2022-12-28 | 2023-01-13 | Underground | R15 | 2022-12-28 | 1 | 341 | 140 | 13 | 492 | 2021 | 2023 | R15
154510213506 | 150346506510 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2019-05-22 | 2019-05-22 | 2020-12-10 | 2021-10-12 | 2021-11-03 | Overhead | R15 | 2021-10-12 | 1 | 407 | 219 | 17 | 641 | 2019 | 2021 | R15
155059257742 | 157722742059 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2020-10-13 | 2020-12-17 | 2021-11-22 | 2022-07-28 | 2022-09-07 | Underground | R15 | 2022-07-28 | 48 | 243 | 179 | 30 | 497 | 2020 | 2022 | R15
155699264714 | 155704714699 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-04-26 | 2019-04-26 | 2022-01-13 | 2022-02-03 | 2023-11-09 | Underground | R15 | 2022-02-03 | 1 | 710 | 16 | 461 | 1185 | 2019 | 2023 | R15
156493254043 | 150436043493 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-10-26 | 2021-01-14 | 2021-10-27 | 2022-11-28 | 2023-08-15 | Overhead | R15 | 2022-11-28 | 59 | 205 | 284 | 187 | 732 | 2020 | 2023 | R15
158659150585 | 152122585659 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-02-07 | 2019-02-12 | 2019-04-29 | 2020-03-23 | 2020-12-21 | Underground | R15 | 2020-03-23 | 4 | 55 | 236 | 196 | 488 | 2019 | 2020 | R15
155749242461 | 156112461749 | NON-RESIDENTIAL - LOT DEVELOPMENT | UG DEV NON RES | Commercial | 2021-05-17 | 2021-05-17 | 2021-08-05 | 2021-08-18 | 2022-08-29 | Underground | R15 | 2021-08-18 | 1 | 59 | 10 | 269 | 336 | 2021 | 2022 | R15
150706181854 | 151927854706 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2019-06-03 | 2019-06-13 | 2020-02-25 | 2020-04-21 | 2020-07-28 | Overhead | R15 | 2020-04-21 | 9 | 184 | 41 | 71 | 302 | 2019 | 2020 | R15
150282231181 | 153096181282 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-12-23 | 2021-04-11 | 2021-05-17 | 2021-11-30 | 2022-01-06 | Overhead | R15 | 2021-11-30 | 78 | 26 | 142 | 28 | 272 | 2020 | 2022 | R15
157326286528 | 159878528326 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2020-10-22 | 2021-08-30 | 2022-07-22 | 2022-09-22 | 2022-10-03 | Underground | R15 | 2022-09-22 | 223 | 235 | 45 | 8 | 508 | 2020 | 2022 | R15
151714251098 | 158954098714 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-03-08 | 2021-03-08 | 2021-10-08 | 2022-09-22 | 2022-10-18 | Underground | R15 | 2022-09-22 | 1 | 155 | 250 | 19 | 422 | 2021 | 2022 | R15
151961255769 | 153830769961 | NON-RESIDENTIAL - WAREHOUSE | UG EXT NON RES | Commercial | 2021-02-11 | 2021-04-19 | 2021-11-09 | 2022-05-06 | 2022-07-06 | Underground | R15 | 2022-05-06 | 48 | 147 | 129 | 44 | 365 | 2021 | 2022 | R15
157500251819 | 157526819500 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-08-28 | 2020-08-28 | 2021-10-13 | 2022-11-09 | 2022-11-21 | Underground | R15 | 2022-11-09 | 1 | 294 | 281 | 9 | 582 | 2020 | 2022 | R15
152325240199 | 155695199325 | NON-RESIDENTIAL - WAREHOUSE | UG EXT NON RES | Commercial | 2021-02-22 | 2021-02-22 | 2021-07-23 | 2021-09-20 | 2021-10-12 | Underground | R15 | 2021-09-20 | 1 | 110 | 42 | 17 | 167 | 2021 | 2021 | R15
152604170549 | 156734549604 | FOREIGN UTILITY | UG EXT NON RES | Commercial | 2019-05-02 | 2019-08-29 | 2019-11-04 | 2020-10-26 | 2022-08-25 | Underground | R15 | 2020-10-26 | 86 | 48 | 256 | 479 | 866 | 2019 | 2022 | R15
156557315427 | 158655427557 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-01-21 | 2021-01-21 | 2023-04-11 | 2023-05-24 | 2023-07-07 | Underground | R15 | 2023-05-24 | 1 | 579 | 32 | 33 | 642 | 2021 | 2023 | R15
154114178802 | 151587802114 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-04-04 | 2019-04-04 | 2020-01-30 | 2020-07-07 | 2020-09-22 | Underground | R15 | 2020-07-07 | 1 | 216 | 114 | 56 | 384 | 2019 | 2020 | R15
155506239697 | 156767697506 | GENERAL/OTHER | UG EXT NON RES | Residential | 2020-11-24 | 2020-11-24 | 2021-07-20 |  | 2022-07-06 | Underground | R15 | 2022-08-15 | 1 | 171 | 280 |  | 422 | 2020 | 2022 | R15
151523213623 | 158741623523 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-07-17 | 2020-08-20 | 2020-12-10 | 2021-01-26 | 2021-04-20 | Underground | R15 | 2021-01-26 | 25 | 81 | 34 | 61 | 198 | 2020 | 2021 | R15
154424222720 | 156302720424 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2020-08-24 | 2020-09-14 | 2021-03-05 | 2023-05-25 | 2023-08-17 | Underground | R15 | 2023-05-25 | 16 | 125 | 580 | 61 | 779 | 2020 | 2023 | R15
156514270003 | 157040003514 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential Subdivision | 2020-08-27 | 2021-05-24 | 2022-02-22 |  | 2022-05-19 | Underground | R15 |  | 193 | 197 |  |  | 451 | 2020 | 2022 | R15
150853264669 | 150802669853 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2020-09-14 | 2020-09-14 | 2022-01-13 | 2022-10-19 | 2022-11-14 | Underground | R15 | 2022-10-19 | 1 | 349 | 200 | 19 | 566 | 2020 | 2022 | R15
150853264669 | 150802669853 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Residential | 2020-09-14 | 2020-09-14 | 2022-01-13 | 2022-10-19 | 2022-11-14 | Overhead | R15 | 2022-10-19 | 1 | 349 | 200 | 19 | 566 | 2020 | 2022 | R15
155899245609 | 154194609899 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-09-28 | 2020-09-28 | 2021-08-27 | 2021-12-14 | 2022-01-11 | Underground | R15 | 2021-12-14 | 1 | 240 | 78 | 21 | 337 | 2020 | 2022 | R15
154734221141 | 156947141734 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Residential | 2020-10-09 | 2020-11-02 | 2021-02-19 | 2021-03-03 | 2021-04-06 | Overhead | R15 | 2021-03-03 | 17 | 80 | 9 | 25 | 128 | 2020 | 2021 | R15
155676242196 | 155677196676 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2021-05-14 | 2021-06-09 | 2021-08-05 | 2021-08-09 | 2023-06-13 | Underground | R15 | 2021-08-09 | 19 | 42 | 3 | 482 | 543 | 2021 | 2023 | R15
156882172760 | 154021760882 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-02-19 | 2019-05-08 | 2019-11-22 | 2020-01-07 | 2020-11-11 | Overhead | R15 | 2020-01-07 | 57 | 143 | 33 | 222 | 452 | 2019 | 2020 | R15
158358238998 | 158460998358 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-04-15 | 2021-04-15 | 2021-07-15 | 2021-09-21 | 2021-09-24 | Overhead | R15 | 2021-09-21 | 1 | 66 | 49 | 4 | 117 | 2021 | 2021 | R15
158085182683 | 151115683085 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-05-28 | 2019-05-28 | 2020-03-02 | 2020-12-07 | 2021-02-27 | Overhead | R15 | 2020-12-07 | 1 | 200 | 201 | 60 | 459 | 2019 | 2021 | R15
151180152903 | 153392903180 | NON-RESIDENTIAL - LOT DEVELOPMENT | UG DEV NON RES | Commercial | 2019-04-15 | 2019-04-25 | 2019-05-20 | 2020-05-07 | 2021-11-23 | Underground | R15 | 2020-05-07 | 9 | 18 | 254 | 404 | 682 | 2019 | 2021 | R15
156399279024 | 156430024399 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Residential | 2019-03-05 | 2019-04-30 | 2022-05-11 | 2023-03-20 | 2023-05-22 | Overhead | R15 | 2023-03-20 | 41 | 792 | 224 | 46 | 1100 | 2019 | 2023 | R15
150875215341 | 151649341875 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-12-20 | 2020-12-20 | 2020-12-22 | 2021-01-13 | 2023-10-02 | Overhead | R15 | 2021-01-13 | 0 | 2 | 17 | 709 | 726 | 2020 | 2023 | R15
150537249820 | 150538820537 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential | 2020-07-28 | 2020-07-28 | 2021-09-28 | 2021-11-09 | 2022-01-06 | Underground | R15 | 2021-11-09 | 1 | 306 | 31 | 43 | 378 | 2020 | 2022 | R15
150461159418 | 158037418461 | CUSTOMER UPGRADE IN SERVICE | UG RES INDIVIDUAL | Residential | 2019-05-09 | 2019-05-09 | 2019-07-30 | 2020-02-20 | 2022-03-09 | Underground | R15 | 2020-02-20 | 1 | 59 | 148 | 535 | 740 | 2019 | 2022 | R15
154510213505 | 154368505510 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2019-04-19 | 2019-04-19 | 2020-12-10 | 2021-10-12 | 2021-11-03 | Underground | R15 | 2021-10-12 | 1 | 430 | 219 | 17 | 664 | 2019 | 2021 | R15
158668242245 | 156184245668 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-11-20 | 2021-03-25 | 2021-08-05 | 2022-05-20 | 2022-06-08 | Underground | R15 | 2022-05-20 | 90 | 96 | 207 | 14 | 404 | 2020 | 2022 | R15
157991246336 | 158575336991 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2021-03-07 | 2021-03-07 | 2021-09-02 | 2021-09-23 | 2021-10-01 | Overhead | R15 | 2021-09-23 | 0 | 129 | 16 | 7 | 150 | 2021 | 2021 | R15
150309215944 | 158849944309 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential | 2020-07-20 | 2020-10-14 | 2020-12-30 | 2021-07-15 | 2021-12-21 | Underground | R15 | 2021-07-15 | 63 | 56 | 142 | 114 | 372 | 2020 | 2021 | R15
150537172272 | 150654272537 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-01-31 | 2019-04-15 | 2019-11-19 | 2020-03-02 | 2020-05-05 | Underground | R15 | 2020-03-02 | 53 | 157 | 75 | 47 | 329 | 2019 | 2020 | R15
153438247942 | 153274942438 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-02-10 | 2021-04-26 | 2021-09-14 | 2021-09-20 | 2022-07-20 | Underground | R15 | 2021-09-20 | 54 | 102 | 5 | 218 | 376 | 2021 | 2022 | R15
159437222122 | 157438122437 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential | 2019-01-16 | 2019-09-24 | 2021-03-01 | 2022-01-05 | 2023-09-05 | Underground | R15 | 2022-01-05 | 180 | 375 | 223 | 435 | 1210 | 2019 | 2023 | R15
154545172457 | 159461457545 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2019-05-16 | 2019-07-29 | 2019-11-22 | 2021-08-31 | 2021-09-29 | Underground | R15 | 2021-08-31 | 53 | 85 | 463 | 22 | 620 | 2019 | 2021 | R15
159267243456 | 155180456267 | NON-RESIDENTIAL - SMALL RETAIL | OH EXTENSION NON RESD OD | Residential | 2021-02-18 | 2021-02-18 | 2021-08-13 | 2021-12-09 | 2022-01-05 | Overhead | R15 | 2021-12-09 | 1 | 127 | 85 | 20 | 230 | 2021 | 2022 | R15
154614240110 | 154884110614 | RESIDENTIAL - MULTI-FAMILY | OH RESD INDIVIDUAL OD | Residential | 2020-09-30 | 2020-10-02 | 2021-07-22 | 2021-10-12 | 2021-11-01 | Overhead | R15 | 2021-10-12 | 3 | 210 | 59 | 15 | 284 | 2020 | 2021 | R15
150452158660 | 159099660452 | FOREIGN UTILITY | OH EXTENSION NON RESD OD | Residential | 2019-03-21 | 2019-04-25 | 2019-07-22 | 2019-08-26 | 2020-01-09 | Overhead | R15 | 2019-08-26 | 26 | 63 | 26 | 99 | 211 | 2019 | 2020 | R15
154311219992 | 156319992311 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential Subdivision | 2020-11-21 | 2021-01-06 | 2021-02-09 |  | 2022-10-29 | Underground | R15 |  | 33 | 25 |  |  | 505 | 2020 | 2022 | R15
155662238069 | 155663069662 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-05-14 | 2021-05-14 | 2021-07-08 | 2021-11-16 | 2021-11-30 | Underground | R15 | 2021-11-16 | 1 | 40 | 94 | 11 | 143 | 2021 | 2021 | R15
155982188333 | 155977333982 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-04-29 | 2019-09-12 | 2020-04-20 | 2021-03-02 | 2021-05-06 | Underground | R15 | 2021-03-02 | 99 | 158 | 227 | 48 | 529 | 2019 | 2021 | R15
158068237022 | 154166022068 | AGRICULTURAL | OH EXTENSION NON RESD OD | Commercial | 2021-03-29 | 2021-04-28 | 2021-06-28 | 2021-08-12 | 2021-09-23 | Overhead | R15 | 2021-08-12 | 23 | 44 | 34 | 31 | 129 | 2021 | 2021 | R15
155812175344 | 159371344812 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-03-21 | 2019-03-21 | 2019-12-30 | 2020-02-25 | 2020-07-07 | Underground | R15 | 2020-02-25 | 1 | 203 | 42 | 96 | 339 | 2019 | 2020 | R15
151194249659 | 158326659194 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-04-15 | 2021-04-20 | 2021-09-28 | 2022-03-15 | 2022-03-29 | Underground | R15 | 2022-03-15 | 4 | 116 | 121 | 11 | 249 | 2021 | 2022 | R15
151576242355 | 151517355576 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-10-30 | 2020-10-30 | 2021-08-06 | 2022-04-19 | 2022-05-04 | Underground | R15 | 2022-04-19 | 1 | 201 | 183 | 12 | 394 | 2020 | 2022 | R15
150210235034 | 150144034210 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2020-12-10 | 2021-01-19 | 2021-06-15 | 2022-06-15 | 2022-06-30 | Underground | R15 | 2022-06-15 | 29 | 106 | 262 | 12 | 406 | 2020 | 2022 | R15
157195237376 | 158442376195 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-09-03 | 2020-09-03 | 2021-07-01 | 2022-05-04 | 2022-05-24 | Underground | R15 | 2022-05-04 | 1 | 216 | 220 | 15 | 449 | 2020 | 2022 | R15
153010292315 | 153053315010 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-03-24 | 2021-03-24 | 2022-09-02 | 2023-09-20 | 2023-09-25 | Underground | R15 | 2023-09-20 | 1 | 378 | 274 | 4 | 654 | 2021 | 2023 | R15
153010272975 | 153051975010 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-03-24 | 2021-03-24 | 2022-03-18 | 2022-11-11 | 2023-04-05 | Underground | R15 | 2022-11-11 | 1 | 258 | 171 | 104 | 531 | 2021 | 2023 | R15
150015180086 | 152438086015 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-06-05 | 2019-11-21 | 2020-02-11 |  | 2021-04-29 | Underground | R15 |  | 122 | 59 |  |  | 497 | 2019 | 2021 | R15
151177162712 | 151373712177 | INDUSTRIAL | UG EXT NON RES | Commercial | 2019-02-05 | 2019-02-05 | 2019-08-29 | 2020-05-26 | 2021-11-23 | Underground | R15 | 2020-05-26 | 1 | 148 | 194 | 391 | 731 | 2019 | 2021 | R15
156621223457 | 156623457621 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-02-25 | 2021-03-12 | 2021-03-12 |  | 2021-03-12 | Underground | R15 | 2021-02-25 | 12 |  |  | 12 | 12 | 2021 | 2021 | R15
155984161881 | 155877881984 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential Subdivision | 2019-04-29 | 2019-05-31 | 2019-08-20 | 2020-04-02 | 2021-03-05 | Overhead | R15 | 2020-04-02 | 25 | 58 | 163 | 242 | 485 | 2019 | 2021 | R15
152114158799 | 151788799114 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-04-05 | 2019-05-08 | 2019-07-24 | 2019-08-22 | 2020-02-06 | Overhead | R15 | 2019-08-22 | 24 | 56 | 22 | 121 | 220 | 2019 | 2020 | R15
156454232083 | 157585083454 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-08-29 | 2020-11-18 | 2021-05-24 | 2021-11-30 | 2022-01-11 | Underground | R15 | 2021-11-30 | 58 | 134 | 137 | 31 | 357 | 2020 | 2022 | R15
150410150398 | 150268398410 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-01-30 | 2019-01-30 | 2019-04-26 | 2019-07-02 | 2019-11-12 | Underground | R15 | 2019-07-02 | 1 | 63 | 48 | 96 | 205 | 2019 | 2019 | R15
157102207008 | 157079008102 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-08-27 | 2020-08-27 | 2020-10-12 |  | 2021-01-27 | Overhead | R15 |  | 1 | 33 |  |  | 110 | 2020 | 2021 | R15
159672302362 | 154305362672 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | OH EXTENSION NON RESD OD | Commercial | 2021-05-11 | 2021-12-14 | 2022-12-05 | 2023-05-12 | 2023-08-28 | Overhead | R15 | 2023-05-12 | 156 | 255 | 115 | 77 | 600 | 2021 | 2023 | R15
150189253756 | 159495756189 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-01-26 | 2021-09-08 | 2021-10-26 | 2022-08-10 | 2022-10-29 | Underground | R15 | 2022-08-10 | 162 | 35 | 207 | 58 | 459 | 2021 | 2022 | R15
157125171414 | 157215414125 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-03-08 | 2019-03-08 | 2019-11-12 | 2020-04-27 | 2020-04-30 | Underground | R15 | 2020-04-27 | 1 | 178 | 120 | 4 | 300 | 2019 | 2020 | R15
157567268436 | 151680436567 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential | 2020-10-30 | 2020-10-30 | 2022-02-10 | 2022-04-12 | 2023-10-15 | Underground | R15 | 2022-04-12 | 1 | 335 | 44 | 394 | 771 | 2020 | 2023 | R15
159980252563 | 159150563980 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-10-20 | 2021-07-20 | 2021-10-18 | 2021-12-30 | 2022-02-11 | Overhead | R15 | 2021-12-30 | 196 | 65 | 54 | 32 | 344 | 2020 | 2022 | R15
158356152124 | 157433124356 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-01-15 | 2019-04-02 | 2019-05-13 | 2019-07-15 | 2019-12-31 | Underground | R15 | 2019-07-15 | 56 | 30 | 46 | 122 | 251 | 2019 | 2019 | R15
152430221001 | 152821001430 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-08-10 | 2020-09-14 | 2021-02-18 | 2021-08-10 | 2022-02-09 | Overhead | R15 | 2021-08-10 | 26 | 114 | 124 | 132 | 393 | 2020 | 2022 | R15
154036202166 | 152556166036 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-06-06 | 2020-02-25 | 2020-08-28 | 2021-09-15 | 2021-09-30 | Underground | R15 | 2021-09-15 | 189 | 134 | 274 | 12 | 606 | 2019 | 2021 | R15
150147301895 | 159701895147 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Commercial | 2021-04-21 | 2021-04-21 | 2022-11-30 | 2023-07-24 | 2023-08-24 | Underground | R15 | 2023-07-24 | 1 | 421 | 169 | 24 | 612 | 2021 | 2023 | R15
153417247677 | 159593677417 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-07-22 | 2020-07-22 | 2021-09-14 | 2022-05-13 | 2022-06-03 | Underground | R15 | 2022-05-13 | 1 | 300 | 174 | 16 | 488 | 2020 | 2022 | R15
151702154219 | 151623219702 | AGRICULTURAL | OH EXTENSION NON RESD OD | Commercial | 2019-02-05 | 2019-02-05 | 2019-06-04 | 2020-07-19 | 2020-11-05 | Overhead | R15 | 2020-07-19 | 1 | 86 | 294 | 79 | 458 | 2019 | 2020 | R15
157920247196 | 157269196920 | FOREIGN UTILITY | OH EXTENSION NON RESD OD | Commercial | 2021-03-01 | 2021-04-01 | 2021-09-10 |  | 2023-01-10 | Overhead | R15 |  | 24 | 117 |  |  | 487 | 2021 | 2023 | R15
157001270004 | 159833004001 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2020-10-22 | 2021-06-22 | 2022-02-22 | 2022-04-18 | 2023-10-15 | Underground | R15 | 2022-04-18 | 174 | 176 | 40 | 390 | 777 | 2020 | 2023 | R15
157581278275 | 156206275581 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Commercial | 2021-01-12 | 2021-11-22 | 2022-05-05 | 2022-10-18 | 2022-10-24 | Underground | R15 | 2022-10-18 | 225 | 119 | 119 | 5 | 465 | 2021 | 2022 | R15
154163197440 | 154181440163 | NON-RESIDENTIAL - LODGING | UG EXT NON RES | Commercial | 2019-04-18 | 2019-04-18 | 2020-07-15 | 2022-03-18 | 2022-04-12 | Underground | R15 | 2022-03-18 | 1 | 325 | 438 | 18 | 779 | 2019 | 2022 | R15
157148150924 | 152199924148 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-04-08 | 2019-04-17 | 2019-04-30 | 2019-05-08 | 2019-10-24 | Overhead | R15 | 2019-05-08 | 8 | 10 | 7 | 122 | 144 | 2019 | 2019 | R15
156191262744 | 156450744191 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-08-25 | 2020-08-25 | 2021-12-28 | 2022-04-06 | 2022-05-02 | Overhead | R15 | 2022-04-06 | 1 | 351 | 72 | 19 | 440 | 2020 | 2022 | R15
153612241287 | 157844287612 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2020-08-31 | 2020-08-31 | 2021-07-29 | 2022-05-18 | 2022-05-27 | Underground | R15 | 2022-05-18 | 1 | 239 | 210 | 8 | 455 | 2020 | 2022 | R15
151920244135 | 155361135920 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-01-06 | 2021-02-24 | 2021-08-19 | 2021-09-20 | 2021-10-06 | Overhead | R15 | 2021-09-20 | 36 | 127 | 23 | 13 | 196 | 2021 | 2021 | R15
152218269073 | 158240073218 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2021-01-19 | 2021-07-06 | 2022-02-15 | 2022-05-11 | 2022-05-27 | Overhead | R15 | 2022-05-11 | 121 | 161 | 62 | 13 | 354 | 2021 | 2022 | R15
153902241409 | 154381409902 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-11-11 | 2020-11-11 | 2021-07-30 | 2022-10-03 | 2022-10-11 | Overhead | R15 | 2022-10-03 | 1 | 188 | 307 | 7 | 500 | 2020 | 2022 | R15
154614247704 | 157528704614 | CUSTOMER UPGRADE IN SERVICE | UG RES INDIVIDUAL | Residential | 2020-08-28 | 2020-10-02 | 2021-09-13 | 2021-11-10 | 2021-11-30 | Underground | R15 | 2021-11-10 | 26 | 247 | 43 | 15 | 328 | 2020 | 2021 | R15
152394216390 | 158825390394 | NON-RESIDENTIAL - SMALL RETAIL | UG EXT NON RES | Commercial | 2020-09-08 | 2020-09-28 | 2021-01-07 | 2021-05-13 | 2021-06-21 | Underground | R15 | 2021-05-13 | 15 | 74 | 91 | 28 | 205 | 2020 | 2021 | R15
154163263396 | 158938396163 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-01-22 | 2021-03-29 | 2022-01-04 | 2022-04-19 | 2022-05-16 | Overhead | R15 | 2022-04-19 | 47 | 202 | 76 | 20 | 342 | 2021 | 2022 | R15
156152224970 | 157342970152 | NON-RESIDENTIAL - WAREHOUSE | UG EXT NON RES | Commercial | 2021-01-15 | 2021-02-06 | 2021-03-26 | 2021-08-30 | 2021-10-25 | Underground | R15 | 2021-08-30 | 16 | 35 | 112 | 41 | 202 | 2021 | 2021 | R15
159858194087 | 151036087858 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-05-28 | 2019-10-05 | 2020-06-11 | 2021-04-06 | 2021-06-30 | Underground | R15 | 2021-04-06 | 94 | 179 | 214 | 62 | 547 | 2019 | 2021 | R15
155333233470 | 159115470333 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-03-09 | 2021-04-07 | 2021-06-04 | 2021-07-02 | 2022-08-22 | Underground | R15 | 2021-07-02 | 22 | 43 | 21 | 297 | 380 | 2021 | 2022 | R15
153863220664 | 153516664863 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-09-25 | 2020-10-08 | 2021-02-16 | 2021-09-01 | 2021-10-19 | Underground | R15 | 2021-09-01 | 10 | 94 | 142 | 35 | 278 | 2020 | 2021 | R15
152468234980 | 153828980468 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential | 2020-08-14 | 2020-08-14 | 2021-06-14 | 2021-12-01 | 2021-12-21 | Underground | R15 | 2021-12-01 | 1 | 217 | 123 | 15 | 353 | 2020 | 2021 | R15
158333238350 | 158360350333 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-03-04 | 2021-03-04 | 2021-07-09 | 2022-06-23 | 2022-08-26 | Underground | R15 | 2022-06-23 | 1 | 92 | 250 | 47 | 387 | 2021 | 2022 | R15
150896205492 | 154604492896 | NON-RESIDENTIAL - LODGING | OH EXTENSION NON RESD OD | Commercial | 2020-08-19 | 2020-08-19 | 2020-09-28 | 2021-07-15 | 2022-08-25 | Overhead | R15 | 2021-07-15 | 1 | 29 | 209 | 291 | 527 | 2020 | 2022 | R15
157767294426 | 157011426767 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential Subdivision | 2021-04-09 | 2021-04-21 | 2022-09-21 | 2023-10-17 | 2023-11-14 | Underground | R15 | 2023-10-17 | 9 | 371 | 280 | 21 | 678 | 2021 | 2023 | R15
150308248936 | 151828936308 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2021-04-30 | 2021-08-02 | 2021-09-22 | 2023-02-06 | 2023-02-08 | Underground | R15 | 2023-02-06 | 67 | 38 | 359 | 3 | 464 | 2021 | 2023 | R15
153397252145 | 155745145397 | NON-RESIDENTIAL - LARGE OFFICE | UG EXT NON RES | Commercial | 2021-02-22 | 2021-07-07 | 2021-10-14 | 2022-09-21 | 2022-10-24 | Underground | R15 | 2022-09-21 | 98 | 72 | 245 | 24 | 436 | 2021 | 2022 | R15
152066243820 | 152186820066 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-02-04 | 2021-03-15 | 2021-08-15 | 2022-01-19 | 2022-02-07 | Underground | R15 | 2022-01-19 | 28 | 110 | 113 | 14 | 263 | 2021 | 2022 | R15
156736241668 | 151744668736 | NON-RESIDENTIAL - SMALL RETAIL | UG EXT NON RES | Commercial | 2020-09-18 | 2020-10-02 | 2021-08-02 | 2022-07-12 | 2023-11-20 | Underground | R15 | 2022-07-12 | 11 | 217 | 247 | 355 | 827 | 2020 | 2023 | R15
159009254256 | 155976256009 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-01-11 | 2021-03-10 | 2021-10-29 | 2021-11-15 | 2021-11-30 | Overhead | R15 | 2021-11-15 | 43 | 168 | 12 | 12 | 232 | 2021 | 2021 | R15
153010273090 | 153052090010 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-03-24 | 2021-03-24 | 2022-03-17 | 2023-04-18 | 2023-07-12 | Underground | R15 | 2023-04-18 | 1 | 257 | 284 | 62 | 601 | 2021 | 2023 | R15
159828156178 | 159861178828 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2019-03-25 | 2019-04-02 | 2019-06-24 | 2020-02-25 | 2020-07-07 | Underground | R15 | 2020-02-25 | 7 | 60 | 177 | 96 | 337 | 2019 | 2020 | R15
150627236930 | 157475930627 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2020-08-28 | 2020-08-28 | 2021-06-28 | 2022-06-23 | 2022-07-25 | Underground | R15 | 2022-06-23 | 1 | 217 | 259 | 23 | 497 | 2020 | 2022 | R15
151194243108 | 158234108194 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Commercial | 2021-04-15 | 2021-04-20 | 2021-08-11 | 2021-11-16 | 2021-11-30 | Underground | R15 | 2021-11-16 | 4 | 82 | 70 | 11 | 164 | 2021 | 2021 | R15
156125242464 | 156586464125 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential Subdivision | 2021-05-18 | 2021-05-18 | 2021-08-05 | 2021-10-22 | 2022-01-04 | Underground | R15 | 2021-10-22 | 1 | 58 | 57 | 53 | 166 | 2021 | 2022 | R15
156856217896 | 158896896856 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2020-07-20 | 2020-08-31 | 2021-01-22 | 2021-03-24 | 2021-04-26 | Overhead | R15 | 2021-03-24 | 31 | 105 | 44 | 24 | 201 | 2020 | 2021 | R15
159371287951 | 159372951371 | Affordable Housing | UG DEV RES | Residential | 2020-10-21 | 2020-10-21 | 2022-08-04 | 2023-02-17 | 2023-03-13 | Underground | R15 | 2023-02-17 | 1 | 467 | 142 | 17 | 624 | 2020 | 2023 | R15
159437220285 | 157439285437 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential | 2019-01-16 | 2019-09-24 | 2021-02-11 | 2021-10-12 | 2023-02-06 | Underground | R15 | 2021-10-12 | 180 | 363 | 174 | 345 | 1059 | 2019 | 2023 | R15
153670242356 | 153672356670 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-11-09 | 2020-11-09 | 2021-08-06 | 2021-12-29 | 2022-01-21 | Underground | R15 | 2021-12-29 | 1 | 195 | 104 | 18 | 315 | 2020 | 2022 | R15
153754224931 | 153746931754 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential Subdivision | 2019-04-16 | 2019-04-16 | 2021-03-26 | 2022-11-01 | 2022-11-22 | Underground | R15 | 2022-11-01 | 1 | 509 | 418 | 16 | 941 | 2019 | 2022 | R15
150445162710 | 150470710445 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-01-30 | 2019-05-06 | 2019-08-29 | 2020-06-25 | 2020-09-30 | Underground | R15 | 2020-06-25 | 69 | 84 | 216 | 70 | 436 | 2019 | 2020 | R15
159502173956 | 151612956502 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential | 2019-05-30 | 2019-07-30 | 2019-12-11 | 2020-04-28 | 2020-07-29 | Underground | R15 | 2020-04-28 | 44 | 97 | 100 | 67 | 305 | 2019 | 2020 | R15
158755239380 | 154304380755 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2021-02-16 | 2021-02-16 | 2021-07-16 | 2021-12-10 | 2022-01-05 | Overhead | R15 | 2021-12-10 | 1 | 109 | 106 | 19 | 232 | 2021 | 2022 | R15
151177164193 | 151374193177 | INDUSTRIAL | UG EXT NON RES | Commercial | 2019-02-05 | 2019-02-05 | 2019-09-12 | 2020-05-11 | 2020-09-30 | Underground | R15 | 2020-05-11 | 1 | 158 | 173 | 103 | 432 | 2019 | 2020 | R15
153474222067 | 157370067474 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-01-15 | 2021-01-21 | 2021-03-01 | 2021-04-30 | 2021-06-02 | Underground | R15 | 2021-04-30 | 5 | 28 | 45 | 24 | 99 | 2021 | 2021 | R15
157513156701 | 158738701513 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential Subdivision | 2019-01-24 | 2019-02-05 | 2019-06-28 | 2020-01-29 | 2020-04-11 | Underground | R15 | 2020-01-29 | 9 | 104 | 154 | 53 | 317 | 2019 | 2020 | R15
158471233106 | 158303106471 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-04-15 | 2021-04-15 | 2021-06-01 | 2022-04-08 | 2022-04-11 | Overhead | R15 | 2022-04-08 | 1 | 34 | 224 | 2 | 258 | 2021 | 2022 | R15
157002286504 | 159891504002 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2020-10-22 | 2021-06-24 | 2022-07-21 | 2022-08-22 | 2022-09-14 | Underground | R15 | 2022-08-22 | 176 | 281 | 23 | 18 | 495 | 2020 | 2022 | R15
155462198045 | 157505045462 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2019-05-06 | 2020-02-23 | 2020-07-22 | 2023-06-08 | 2023-08-16 | Underground | R15 | 2023-06-08 | 210 | 108 | 752 | 50 | 1118 | 2019 | 2023 | R15
157328286466 | 159894466328 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2020-10-23 | 2021-09-01 | 2022-07-21 | 2023-11-24 | 2023-11-24 | Underground | R15 | 2023-11-24 | 224 | 232 | 352 |  | 806 | 2020 | 2023 | R15
150318237540 | 150081540318 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-03-11 | 2021-06-08 | 2021-07-01 | 2021-09-27 | 2021-10-11 | Overhead | R15 | 2021-09-27 | 64 | 18 | 63 | 11 | 153 | 2021 | 2021 | R15
151063282172 | 150341172063 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-10-06 | 2021-12-01 | 2022-06-09 | 2022-09-15 | 2022-10-24 | Underground | R15 | 2022-09-15 | 41 | 137 | 71 | 28 | 274 | 2021 | 2022 | R15
150668304071 | 154829071668 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2022-01-27 | 2022-03-28 | 2022-12-27 | 2023-10-19 | 2023-11-03 | Underground | R15 | 2023-10-19 | 43 | 197 | 213 | 12 | 462 | 2022 | 2023 | R15
153162286902 | 155857902162 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential Subdivision | 2022-05-23 | 2022-06-13 | 2022-07-25 | 2022-10-13 | 2022-10-31 | Underground | R15 | 2022-10-13 | 16 | 31 | 59 | 13 | 116 | 2022 | 2022 | R15
157148254704 | 151342704148 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-10-11 | 2021-10-12 | 2021-11-02 | 2022-02-15 | 2022-03-11 | Underground | R15 | 2022-02-15 | 2 | 16 | 76 | 19 | 110 | 2021 | 2022 | R15
156163318113 | 156221113163 | NON-RESIDENTIAL - HEALTH CARE | UG DEV NON RES | Commercial | 2022-05-24 | 2022-05-24 | 2023-05-05 | 2023-10-06 | 2023-10-23 | Underground | R15 | 2023-10-06 | 1 | 249 | 111 | 12 | 370 | 2022 | 2023 | R15
152645295279 | 152948279645 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential | 2022-03-02 | 2022-06-28 | 2022-09-29 | 2023-08-08 | 2023-08-28 | Underground | R15 | 2023-08-08 | 85 | 68 | 224 | 15 | 389 | 2022 | 2023 | R15
154769272801 | 154801801769 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-10-25 | 2021-10-25 | 2022-03-15 | 2022-04-27 | 2022-05-19 | Underground | R15 | 2022-04-27 | 1 | 102 | 32 | 17 | 149 | 2021 | 2022 | R15
154147287901 | 150787901147 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2022-04-07 | 2022-06-09 | 2022-08-03 | 2023-07-24 | 2023-09-05 | Overhead | R15 | 2023-07-24 | 46 | 40 | 254 | 32 | 369 | 2022 | 2023 | R15
150306308923 | 156857923306 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2022-03-18 | 2022-06-01 | 2023-02-09 | 2023-02-27 | 2023-03-16 | Overhead | R15 | 2023-02-27 | 54 | 182 | 13 | 14 | 260 | 2022 | 2023 | R15
157509296388 | 155536388509 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2022-01-31 | 2022-01-31 | 2022-10-07 | 2022-10-31 | 2022-12-01 | Overhead | R15 | 2022-10-31 | 1 | 180 | 17 | 24 | 219 | 2022 | 2022 | R15
150210290465 | 157575465210 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2022-02-08 | 2022-02-09 | 2022-08-26 | 2023-09-07 | 2023-10-25 | Underground | R15 | 2023-09-07 | 2 | 143 | 270 | 35 | 447 | 2022 | 2023 | R15
153941319968 | 155956968941 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2022-03-16 | 2022-10-04 | 2023-05-22 | 2023-07-14 | 2023-08-17 | Overhead | R15 | 2023-07-14 | 145 | 165 | 40 | 25 | 372 | 2022 | 2023 | R15
157905277275 | 157397275905 | INDUSTRIAL | UG EXT NON RES | Commercial | 2021-09-23 | 2021-09-24 | 2022-04-27 | 2022-08-12 | 2022-09-07 | Underground | R15 | 2022-08-12 | 2 | 154 | 78 | 19 | 250 | 2021 | 2022 | R15
157295275591 | 153031591295 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-12-01 | 2021-12-28 | 2022-04-12 | 2022-08-01 | 2022-08-12 | Underground | R15 | 2022-08-01 | 20 | 76 | 80 | 10 | 183 | 2021 | 2022 | R15
157272294216 | 159163216272 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2022-07-26 | 2022-07-26 | 2022-09-20 | 2023-03-22 | 2023-05-05 | Underground | R15 | 2023-03-22 | 1 | 41 | 132 | 33 | 204 | 2022 | 2023 | R15
152349298279 | 158560279349 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential Subdivision | 2021-09-28 | 2021-09-28 | 2022-10-26 |  | 2023-11-30 | Underground | R15 |  | 1 | 282 |  |  | 568 | 2021 | 2023 | R15
157010303435 | 155580435010 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Residential | 2021-12-13 | 2022-02-04 | 2022-12-19 | 2023-03-01 | 2023-05-05 | Overhead | R15 | 2023-03-01 | 40 | 227 | 53 | 48 | 365 | 2021 | 2023 | R15
154433310913 | 154403913433 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2022-04-27 | 2022-04-27 | 2023-02-27 | 2023-09-12 | 2023-10-09 | Underground | R15 | 2023-09-12 | 1 | 219 | 142 | 20 | 379 | 2022 | 2023 | R15
154628292972 | 155117972628 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-10-27 | 2022-05-03 | 2022-09-08 |  | 2023-05-22 | Underground | R15 |  | 135 | 93 |  |  | 409 | 2021 | 2023 | R15
151145287219 | 157408219145 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-09-22 | 2021-09-22 | 2022-07-28 | 2023-06-26 | 2023-08-16 | Underground | R15 | 2023-06-26 | 1 | 222 | 238 | 38 | 496 | 2021 | 2023 | R15
157864280614 | 155128614864 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2022-03-10 | 2022-03-10 | 2022-05-25 | 2022-07-14 | 2022-07-25 | Overhead | R15 | 2022-07-14 | 1 | 55 | 37 | 8 | 98 | 2022 | 2022 | R15
159437284215 | 157194215437 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2022-03-21 | 2022-03-22 | 2022-06-30 | 2022-12-07 | 2023-01-06 | Underground | R15 | 2022-12-07 | 2 | 73 | 115 | 23 | 210 | 2022 | 2023 | R15
158883323265 | 154548265883 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential Subdivision | 2022-04-27 | 2022-04-27 | 2023-06-26 | 2023-10-09 | 2023-10-20 | Underground | R15 | 2023-10-09 | 1 | 304 | 76 | 10 | 388 | 2022 | 2023 | R15
154694307461 | 155988461694 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Commercial | 2021-12-15 | 2021-12-15 | 2023-01-27 | 2023-07-17 | 2023-06-28 | Underground | R15 | 2023-07-17 | 1 | 293 | 122 |  | 401 | 2021 | 2023 | R15
151766290359 | 155983359766 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2022-02-01 | 2022-02-03 | 2022-08-26 |  | 2023-09-29 | Underground | R15 |  | 3 | 147 |  |  | 434 | 2022 | 2023 | R15
154426301774 | 155705774426 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2022-10-05 | 2022-10-05 | 2022-11-30 | 2023-07-24 | 2023-08-16 | Underground | R15 | 2023-07-24 | 1 | 41 | 169 | 18 | 226 | 2022 | 2023 | R15
150013264348 | 157407348013 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2021-06-29 | 2021-06-29 | 2022-01-11 | 2022-05-18 | 2022-07-18 | Underground | R15 | 2022-05-18 | 1 | 141 | 92 | 44 | 275 | 2021 | 2022 | R15
152645294500 | 151343500645 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential | 2021-07-15 | 2022-01-18 | 2022-09-21 | 2023-06-19 | 2023-07-28 | Underground | R15 | 2023-06-19 | 134 | 177 | 194 | 30 | 532 | 2021 | 2023 | R15
151055283433 | 153609433055 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Residential | 2021-06-10 | 2021-12-28 | 2022-06-22 |  | 2022-08-18 | Overhead | R15 |  | 144 | 127 |  |  | 311 | 2021 | 2022 | R15
156058297577 | 151929577058 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-07-19 | 2021-07-19 | 2022-12-22 | 2023-06-23 | 2023-09-05 | Underground | R15 | 2023-06-23 | 1 | 374 | 132 | 53 | 557 | 2021 | 2023 | R15
152368282207 | 154728207368 | Affordable Housing | UG DEV RES | Residential | 2021-06-15 | 2022-01-19 | 2022-06-10 | 2023-06-20 | 2023-07-25 | Underground | R15 | 2023-06-20 | 157 | 103 | 268 | 26 | 551 | 2021 | 2023 | R15
150068296009 | 151335009068 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-07-15 | 2022-01-18 | 2022-10-05 | 2023-08-14 | 2023-09-20 | Underground | R15 | 2023-08-14 | 134 | 187 | 224 | 28 | 570 | 2021 | 2023 | R15
158798288720 | 150917720798 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential | 2021-07-14 | 2022-01-19 | 2022-08-11 | 2023-06-20 | 2023-07-25 | Underground | R15 | 2023-06-20 | 136 | 147 | 224 | 26 | 530 | 2021 | 2023 | R15
153203265158 | 153473158203 | CUSTOMER UPGRADE IN SERVICE | UG RES INDIVIDUAL | Residential | 2021-06-09 | 2021-09-07 | 2022-01-19 | 2022-04-21 | 2022-05-25 | Underground | R15 | 2022-04-21 | 65 | 97 | 67 | 25 | 251 | 2021 | 2022 | R15
154440293093 | 157133093440 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-06-25 | 2021-06-28 | 2022-09-09 | 2023-03-29 | 2023-07-14 | Underground | R15 | 2023-03-29 | 2 | 315 | 144 | 78 | 536 | 2021 | 2023 | R15
159166289337 | 152673337166 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-07-21 | 2021-08-21 | 2022-08-17 | 2022-10-04 | 2023-11-30 | Underground | R15 | 2022-10-04 | 23 | 258 | 35 | 303 | 617 | 2021 | 2023 | R15
151157246208 | 153665208157 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential | 2021-06-10 | 2021-06-12 | 2021-09-01 | 2022-10-05 | 2022-10-24 | Underground | R15 | 2022-10-05 | 2 | 58 | 286 | 14 | 358 | 2021 | 2022 | R15
153141259639 | 153339639141 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2021-06-09 | 2021-09-07 | 2021-12-03 | 2022-03-08 | 2022-05-17 | Overhead | R15 | 2022-03-08 | 65 | 64 | 68 | 51 | 245 | 2021 | 2022 | R15
155128199041 | 155009041128 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-01-22 | 2020-01-22 | 2020-07-30 | 2021-01-20 | 2021-02-27 | Underground | R15 | 2021-01-20 | 1 | 137 | 125 | 28 | 288 | 2020 | 2021 | R15
156811256254 | 159007254811 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2020-05-26 | 2020-09-08 | 2021-11-12 | 2023-06-26 | 2023-10-03 | Underground | R15 | 2023-06-26 | 76 | 309 | 422 | 72 | 876 | 2020 | 2023 | R15
158588194599 | 158976599588 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-02-10 | 2020-02-10 | 2020-06-18 | 2020-09-24 | 2023-10-06 | Underground | R15 | 2020-09-24 | 1 | 94 | 71 | 792 | 955 | 2020 | 2023 | R15
159185197336 | 152870336185 | CUSTOMER UPGRADE IN SERVICE | UG R15 RES NON RES BUDG 225 | Commercial | 2020-02-27 | 2020-03-30 | 2020-07-16 | 2020-12-27 | 2021-10-18 | Underground | R15 | 2020-12-27 | 23 | 79 | 117 | 211 | 428 | 2020 | 2021 | R15
152430221004 | 155460004430 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-05-04 | 2020-08-13 | 2021-02-18 | 2021-06-03 | 2022-02-09 | Underground | R15 | 2021-06-03 | 74 | 136 | 76 | 180 | 463 | 2020 | 2022 | R15
157687206765 | 150969765687 | NON-RESIDENTIAL - LARGE OFFICE | UG EXT NON RES | Commercial | 2020-04-10 | 2020-04-10 | 2020-10-10 | 2023-01-30 | 2023-02-10 | Underground | R15 | 2023-01-30 | 1 | 131 | 601 | 10 | 741 | 2020 | 2023 | R15
156729228086 | 150984086729 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2020-06-08 | 2020-10-26 | 2021-04-23 | 2021-10-22 | 2022-05-25 | Overhead | R15 | 2021-10-22 | 101 | 130 | 131 | 154 | 513 | 2020 | 2022 | R15
157911250489 | 157912489911 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-02-04 | 2020-06-25 | 2021-10-04 | 2022-02-28 | 2022-10-04 | Underground | R15 | 2022-02-28 | 103 | 333 | 106 | 157 | 696 | 2020 | 2022 | R15
150694192828 | 152517828694 | FOREIGN UTILITY | OH EXTENSION NON RESD OD | Commercial | 2020-02-26 | 2020-05-07 | 2020-06-02 | 2022-03-26 | 2022-03-29 | Overhead | R15 | 2022-03-26 | 52 | 19 | 474 | 2 | 545 | 2020 | 2022 | R15
155501209362 | 154869362501 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential Subdivision | 2020-05-01 | 2020-05-01 | 2020-11-02 | 2021-06-02 | 2022-06-21 | Underground | R15 | 2021-06-02 | 1 | 132 | 153 | 275 | 558 | 2020 | 2022 | R15
156407219205 | 153774205407 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-01-16 | 2020-01-16 | 2021-02-01 | 2021-12-27 | 2021-11-12 | Underground | R15 | 2021-12-27 | 1 | 273 | 236 |  | 477 | 2020 | 2021 | R15
151628234700 | 151979700628 | FOREIGN UTILITY | OH EXTENSION NON RESD OD | Commercial | 2020-06-12 | 2020-08-07 | 2021-06-11 | 2022-03-22 | 2022-04-07 | Overhead | R15 | 2022-03-22 | 41 | 221 | 203 | 13 | 475 | 2020 | 2022 | R15
152225214524 | 152305524225 | Electric Vehicle | UG EXT NON RES | Commercial | 2020-02-25 | 2020-03-03 | 2020-12-18 | 2022-04-12 | 2022-06-03 | Underground | R15 | 2022-04-12 | 6 | 209 | 343 | 39 | 594 | 2020 | 2022 | R15
153161208102 | 158112102161 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Residential | 2020-03-25 | 2020-03-25 | 2020-10-23 | 2020-11-06 | 2022-03-22 | Overhead | R15 | 2020-11-06 | 1 | 153 | 11 | 358 | 520 | 2020 | 2022 | R15
152679237434 | 157769434679 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-05-19 | 2020-08-05 | 2021-07-02 |  | 2022-02-16 | Underground | R15 |  | 57 | 238 |  |  | 457 | 2020 | 2022 | R15
158057221166 | 152400166057 | CUSTOMER UPGRADE IN SERVICE | UG R15 RES NON RES BUDG 225 | Residential | 2020-04-17 | 2020-10-05 | 2021-02-19 | 2021-06-24 | 2022-08-22 | Underground | R15 | 2021-06-24 | 122 | 100 | 90 | 303 | 612 | 2020 | 2022 | R15
151562187520 | 156225520562 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-01-28 | 2020-03-04 | 2020-04-14 | 2020-06-24 | 2020-09-30 | Overhead | R15 | 2020-06-24 | 27 | 30 | 52 | 71 | 177 | 2020 | 2020 | R15
154316215504 | 151066504316 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Commercial | 2020-02-19 | 2020-10-05 | 2020-12-23 | 2021-11-18 | 2022-01-11 | Underground | R15 | 2021-11-18 | 164 | 58 | 237 | 39 | 495 | 2020 | 2022 | R15
150093203324 | 150081324093 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-04-03 | 2020-05-19 | 2020-09-09 | 2021-09-14 | 2022-03-01 | Underground | R15 | 2021-09-14 | 33 | 82 | 265 | 121 | 498 | 2020 | 2022 | R15
156116185442 | 150634442116 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-01-02 | 2020-01-02 | 2020-03-25 | 2020-05-15 | 2020-09-18 | Overhead | R15 | 2020-05-15 | 1 | 60 | 38 | 91 | 187 | 2020 | 2020 | R15
152812320998 | 157862998812 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2023-03-21 | 2023-03-21 | 2023-06-02 | 2023-06-03 | 2023-07-19 | Overhead | R15 | 2023-06-03 | 1 | 54 | 1 | 33 | 87 | 2023 | 2023 | R15
159171259600 | 158464600171 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-08-13 | 2021-08-13 | 2021-12-02 |  | 2022-02-18 | Underground | R15 |  | 1 | 80 |  |  | 136 | 2021 | 2022 | R15
150311313951 | 153185951311 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2023-02-28 | 2023-02-28 | 2023-03-28 | 2023-04-03 | 2023-07-12 | Overhead | R15 | 2023-04-03 | 1 | 21 | 5 | 73 | 97 | 2023 | 2023 | R15
156709247270 | 156770270709 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2021-08-06 | 2021-08-13 | 2021-09-09 |  | 2021-10-19 | Overhead | R15 | 2021-09-08 | 6 | 20 |  | 30 | 53 | 2021 | 2021 | R15
157509289888 | 159686888509 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-08-18 | 2021-08-18 | 2022-08-22 | 2023-08-30 | 2023-09-25 | Underground | R15 | 2023-08-30 | 1 | 264 | 268 | 19 | 549 | 2021 | 2023 | R15
155326253987 | 155381987326 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-08-02 | 2021-08-02 | 2021-10-27 | 2022-04-08 | 2022-04-11 | Underground | R15 | 2022-04-08 | 1 | 63 | 118 | 2 | 181 | 2021 | 2022 | R15
150307298526 | 154634526307 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-09-10 | 2021-09-10 | 2022-10-27 | 2023-05-03 | 2023-06-27 | Underground | R15 | 2023-05-03 | 1 | 295 | 135 | 40 | 468 | 2021 | 2023 | R15
158974282100 | 153597100974 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-09-07 | 2022-04-05 | 2022-06-08 | 2022-07-20 | 2022-07-22 | Underground | R15 | 2022-07-20 | 151 | 47 | 31 | 3 | 229 | 2021 | 2022 | R15
158969322798 | 151197798969 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2023-05-23 | 2023-05-23 | 2023-06-21 | 2023-08-02 | 2023-12-29 | Overhead | R15 | 2023-08-02 | 1 | 22 | 31 | 108 | 159 | 2023 | 2023 | R15
155016326248 | 159696248016 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2023-02-10 | 2023-02-13 | 2023-07-24 | 2023-10-25 | 2023-11-29 | Underground | R15 | 2023-10-25 | 2 | 116 | 68 | 26 | 209 | 2023 | 2023 | R15
155418326491 | 159352491418 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2023-03-27 | 2023-05-26 | 2023-07-27 | 2023-08-01 | 2023-08-21 | Overhead | R15 | 2023-08-01 | 45 | 45 | 4 | 15 | 106 | 2023 | 2023 | R15
154063242091 | 154009091063 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-07-28 | 2021-07-28 | 2021-08-04 |  | 2023-10-04 | Underground | R15 |  | 1 | 6 |  |  | 571 | 2021 | 2023 | R15
158441320635 | 157411635441 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2023-01-31 | 2023-01-31 | 2023-05-31 | 2023-11-15 | 2023-12-12 | Overhead | R15 | 2023-11-15 | 1 | 87 | 121 | 20 | 226 | 2023 | 2023 | R15
156469313339 | 159004339469 | CUSTOMER UPGRADE IN SERVICE | OH RESD INDIVIDUAL OD | Residential | 2023-02-07 | 2023-02-07 | 2023-03-23 | 2023-03-28 | 2023-09-13 | Overhead | R15 | 2023-03-28 | 1 | 33 | 4 | 122 | 157 | 2023 | 2023 | R15
158065211160 | 158240160065 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2019-10-22 | 2019-10-22 | 2020-11-18 | 2021-03-09 | 2021-07-26 | Underground | R15 | 2021-03-09 | 1 | 282 | 80 | 100 | 460 | 2019 | 2021 | R15
158837164569 | 156535569837 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-08-20 | 2019-08-20 | 2019-09-16 | 2019-11-06 | 2020-04-30 | Overhead | R15 | 2019-11-06 | 1 | 20 | 38 | 127 | 183 | 2019 | 2020 | R15
156315218372 | 156316372315 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2019-12-04 | 2020-05-06 | 2021-01-25 | 2021-05-24 | 2021-09-17 | Underground | R15 | 2021-05-24 | 111 | 189 | 86 | 85 | 468 | 2019 | 2021 | R15
159529198022 | 159649022529 | CUSTOMER UPGRADE IN SERVICE | UG R15 RES NON RES BUDG 225 | Residential | 2019-07-12 | 2019-07-12 | 2020-07-21 | 2021-10-13 | 2021-10-28 | Underground | R15 | 2021-10-13 | 1 | 268 | 322 | 12 | 600 | 2019 | 2021 | R15
156199205455 | 156231455199 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2019-08-19 | 2020-07-07 | 2020-09-28 | 2022-06-16 | 2022-07-05 | Overhead | R15 | 2022-06-16 | 232 | 60 | 449 | 14 | 752 | 2019 | 2022 | R15
155986207827 | 155897827986 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential Subdivision | 2019-06-25 | 2019-06-25 | 2020-10-21 | 2022-05-10 | 2022-05-27 | Underground | R15 | 2022-05-10 | 1 | 347 | 405 | 14 | 764 | 2019 | 2022 | R15
159329182040 | 157224040329 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-10-16 | 2019-10-30 | 2020-02-26 | 2021-05-01 | 2022-08-25 | Underground | R15 | 2021-05-01 | 11 | 86 | 308 | 344 | 747 | 2019 | 2022 | R15
156548204486 | 159269486548 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-09-05 | 2019-09-05 | 2020-09-21 | 2021-03-15 | 2021-05-12 | Underground | R15 | 2021-03-15 | 1 | 273 | 126 | 43 | 440 | 2019 | 2021 | R15
155796178582 | 155809582796 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Commercial | 2019-10-09 | 2019-10-19 | 2020-01-29 | 2020-11-25 | 2021-02-27 | Underground | R15 | 2020-11-25 | 8 | 73 | 216 | 68 | 363 | 2019 | 2021 | R15
158680201986 | 158499986680 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-10-23 | 2019-10-23 | 2020-08-27 | 2020-12-03 | 2021-09-23 | Underground | R15 | 2020-12-03 | 1 | 222 | 71 | 211 | 502 | 2019 | 2021 | R15
151160175183 | 154988183160 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2019-06-18 | 2019-07-12 | 2019-12-26 | 2019-12-30 | 2021-04-05 | Overhead | R15 | 2019-12-30 | 19 | 120 | 3 | 331 | 470 | 2019 | 2021 | R15
156668189502 | 157876502668 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2019-12-12 | 2020-02-10 | 2020-04-30 | 2020-05-01 | 2020-07-28 | Overhead | R15 | 2020-05-01 | 43 | 59 | 2 | 63 | 164 | 2019 | 2020 | R15
157317175386 | 152088386317 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2019-11-08 | 2019-11-18 | 2019-12-30 |  | 2020-04-27 | Overhead | R15 | 2020-02-06 | 7 | 31 | 29 | 58 | 122 | 2019 | 2020 | R15
158215226704 | 158216704215 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-12-13 | 2019-12-13 | 2021-04-13 | 2021-10-26 | 2021-11-12 | Underground | R15 | 2021-10-26 | 1 | 348 | 141 | 14 | 501 | 2019 | 2021 | R15
155841221705 | 155843705841 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-08-16 | 2019-08-16 | 2021-02-25 |  | 2022-06-22 | Underground | R15 |  | 1 | 400 |  |  | 744 | 2019 | 2022 | R15
154251194462 | 154079462251 | CUSTOMER UPGRADE IN SERVICE | UG EXT NON RES | Commercial | 2019-11-20 | 2019-12-18 | 2020-06-15 |  | 2021-02-04 | Underground | R15 |  | 21 | 129 |  |  | 317 | 2019 | 2021 | R15
150771163319 | 150588319771 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2019-07-18 | 2019-07-29 | 2019-09-04 | 2019-10-31 | 2020-04-29 | Overhead | R15 | 2019-10-31 | 8 | 28 | 42 | 130 | 205 | 2019 | 2020 | R15
158680204005 | 158690005680 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-10-23 | 2019-10-23 | 2020-09-16 | 2021-02-03 | 2021-04-15 | Underground | R15 | 2021-02-03 | 1 | 236 | 101 | 52 | 387 | 2019 | 2021 | R15
150816224909 | 156350909816 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-12-04 | 2020-10-19 | 2021-03-26 | 2021-05-26 | 2021-06-29 | Overhead | R15 | 2021-05-26 | 229 | 115 | 44 | 25 | 410 | 2019 | 2021 | R15
155829181699 | 150232699829 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Residential | 2019-09-10 | 2019-09-26 | 2020-02-24 | 2020-05-01 | 2020-12-21 | Underground | R15 | 2020-05-01 | 13 | 108 | 50 | 167 | 335 | 2019 | 2020 | R15
154280196771 | 152515771280 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-11-11 | 2019-11-27 | 2020-07-09 | 2020-12-17 | 2021-01-21 | Underground | R15 | 2020-12-17 | 13 | 162 | 116 | 26 | 314 | 2019 | 2021 | R15
159437243431 | 153634431437 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2019-09-30 | 2019-09-30 | 2021-08-13 | 2022-08-25 | 2022-10-04 | Underground | R15 | 2022-08-25 | 1 | 490 | 270 | 29 | 787 | 2019 | 2022 | R15
158006197221 | 158572221006 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-08-30 | 2020-02-13 | 2020-07-13 | 2022-04-20 | 2022-05-17 | Underground | R15 | 2022-04-20 | 120 | 108 | 463 | 20 | 708 | 2019 | 2022 | R15
158599314097 | 158672097599 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-09-28 | 2021-09-28 | 2023-03-30 | 2023-06-30 | 2023-12-03 | Underground | R15 | 2023-06-30 | 1 | 393 | 67 | 111 | 569 | 2021 | 2023 | R15
158325187509 | 159432509325 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-10-26 | 2020-01-28 | 2020-04-14 | 2020-12-11 | 2021-04-01 | Underground | R15 | 2020-12-11 | 67 | 56 | 174 | 80 | 374 | 2019 | 2021 | R15
159437260592 | 153150592437 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2019-09-26 | 2019-09-26 | 2021-12-10 | 2022-06-28 | 2022-07-05 | Underground | R15 | 2022-06-28 | 1 | 577 | 143 | 6 | 724 | 2019 | 2022 | R15
153367196787 | 158106787367 | RESIDENTIAL - SINGLE FAMILY ATTACHED | OH RESD INDIVIDUAL OD | Residential | 2019-07-03 | 2019-12-02 | 2020-07-09 | 2021-03-17 | 2021-05-04 | Overhead | R15 | 2021-03-17 | 109 | 159 | 180 | 35 | 480 | 2019 | 2021 | R15
159941191450 | 159848450941 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2019-07-15 | 2019-07-15 | 2020-05-18 | 2020-12-08 | 2021-11-22 | Underground | R15 | 2020-12-08 | 1 | 221 | 147 | 250 | 616 | 2019 | 2021 | R15
151904163103 | 158827103904 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-09-03 | 2019-09-03 | 2019-09-03 | 2021-07-15 | 2022-03-22 | Underground | R15 | 2021-07-15 | 1 |  | 488 | 179 | 666 | 2019 | 2022 | R15
153608188569 | 158796569608 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-09-02 | 2020-01-24 | 2020-04-21 | 2021-03-18 | 2021-05-03 | Underground | R15 | 2021-03-18 | 105 | 63 | 238 | 33 | 436 | 2019 | 2021 | R15
159428182046 | 157257046428 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-10-16 | 2019-10-30 | 2020-02-26 | 2022-03-25 | 2022-04-26 | Underground | R15 | 2022-03-25 | 11 | 86 | 543 | 23 | 660 | 2019 | 2022 | R15
151396183170 | 156267170396 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2019-06-27 | 2019-06-27 | 2020-03-06 | 2020-08-05 | 2021-03-11 | Underground | R15 | 2020-08-05 | 1 | 182 | 109 | 157 | 446 | 2019 | 2021 | R15
150171167637 | 156587637171 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-06-28 | 2019-08-14 | 2019-10-10 | 2020-05-04 | 2020-12-21 | Underground | R15 | 2020-05-04 | 34 | 42 | 148 | 166 | 387 | 2019 | 2020 | R15
155707198628 | 155907628707 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential Subdivision | 2019-06-25 | 2019-06-25 | 2020-07-27 | 2021-12-08 | 2022-12-28 | Underground | R15 | 2021-12-08 | 1 | 285 | 358 | 276 | 917 | 2019 | 2022 | R15
156537204456 | 156702456537 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-10-13 | 2020-07-09 | 2020-09-22 | 2021-05-01 | 2021-06-21 | Underground | R15 | 2021-05-01 | 194 | 54 | 159 | 36 | 441 | 2019 | 2021 | R15
157116162505 | 150543505116 | CUSTOMER UPGRADE IN SERVICE | OH R15 ELEC VEHICLE RES OF | Residential | 2019-07-17 | 2019-07-17 | 2019-08-27 | 2020-02-03 | 2020-07-07 | Overhead | R15 | 2020-02-03 | 1 | 30 | 115 | 112 | 255 | 2019 | 2020 | R15
155850177624 | 158995624850 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2019-10-24 | 2019-11-08 | 2020-01-21 | 2020-01-23 | 2020-07-09 | Overhead | R15 | 2020-01-23 | 12 | 53 | 3 | 121 | 186 | 2019 | 2020 | R15
157551157170 | 158686170551 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential Subdivision | 2019-07-08 | 2019-07-08 | 2019-07-08 |  | 2019-07-08 | Overhead | R15 | 2019-07-07 | 1 |  |  | 1 | 1 | 2019 | 2019 | R15
155980211257 | 155991257980 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential Subdivision | 2019-06-25 | 2019-06-25 | 2020-11-20 | 2022-05-16 | 2022-05-27 | Underground | R15 | 2022-05-16 | 1 | 369 | 387 | 10 | 764 | 2019 | 2022 | R15
155981209568 | 155968568981 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential Subdivision | 2019-06-25 | 2019-06-25 | 2020-11-04 | 2022-01-26 | 2022-03-08 | Underground | R15 | 2022-01-26 | 1 | 357 | 321 | 30 | 706 | 2019 | 2022 | R15
159986281219 | 156106219986 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2022-02-02 | 2022-03-18 | 2022-06-01 | 2023-03-17 | 2023-05-26 | Overhead | R15 | 2023-03-17 | 33 | 54 | 208 | 51 | 343 | 2022 | 2023 | R15
154971299377 | 150740377971 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG EXT NON RES | Commercial | 2021-11-19 | 2022-03-14 | 2022-11-04 | 2023-07-14 | 2023-10-26 | Underground | R15 | 2023-07-14 | 82 | 170 | 181 | 75 | 505 | 2021 | 2023 | R15
153963289299 | 154609299963 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2022-07-06 | 2022-07-06 | 2023-01-27 | 2023-08-04 | 2023-08-16 | Underground | R15 | 2023-08-04 | 1 | 148 | 136 | 9 | 291 | 2022 | 2023 | R15
159437273478 | 159767478437 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2021-11-15 | 2021-11-15 | 2022-03-22 | 2022-07-08 | 2022-07-22 | Underground | R15 | 2022-07-08 | 1 | 92 | 79 | 11 | 180 | 2021 | 2022 | R15
158497305625 | 158581625497 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2022-06-06 | 2022-07-21 | 2023-01-25 | 2023-10-05 | 2023-10-23 | Underground | R15 | 2023-10-05 | 34 | 135 | 182 | 13 | 361 | 2022 | 2023 | R15
150994287527 | 151405527994 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2022-01-12 | 2022-01-29 | 2022-08-01 | 2022-12-07 | 2023-07-14 | Overhead | R15 | 2022-12-07 | 13 | 131 | 93 | 158 | 393 | 2022 | 2023 | R15
155038280619 | 153277619038 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-10-18 | 2022-01-25 | 2022-05-25 |  | 2022-10-05 | Underground | R15 |  | 72 | 87 |  |  | 253 | 2021 | 2022 | R15
154250303025 | 154260025250 | NON-RESIDENTIAL - WAREHOUSE | UG EXT NON RES | Commercial | 2022-04-26 | 2022-04-26 | 2023-01-30 | 2023-05-16 | 2023-07-07 | Underground | R15 | 2023-05-16 | 1 | 200 | 77 | 39 | 314 | 2022 | 2023 | R15
153109317554 | 154128554109 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2022-01-25 | 2022-01-25 | 2023-05-02 | 2023-08-18 | 2023-08-30 | Underground | R15 | 2023-08-18 | 1 | 331 | 79 | 9 | 417 | 2022 | 2023 | R15
153419284026 | 159748026419 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential Subdivision | 2022-02-17 | 2022-04-01 | 2022-06-27 | 2023-01-05 | 2023-01-23 | Underground | R15 | 2023-01-05 | 32 | 62 | 139 | 13 | 243 | 2022 | 2023 | R15
155404287053 | 154763053404 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Residential | 2021-10-25 | 2022-02-07 | 2022-07-27 | 2022-08-22 | 2022-10-03 | Overhead | R15 | 2022-08-22 | 76 | 123 | 19 | 31 | 246 | 2021 | 2022 | R15
151044285479 | 158558479044 | NON-RESIDENTIAL - WAREHOUSE | UG EXT NON RES | Commercial | 2022-02-11 | 2022-02-11 | 2022-07-14 | 2023-05-31 | 2023-08-16 | Underground | R15 | 2023-05-31 | 1 | 110 | 230 | 56 | 394 | 2022 | 2023 | R15
154695275851 | 153821851695 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2022-01-24 | 2022-01-27 | 2022-04-14 | 2022-05-12 | 2022-06-02 | Overhead | R15 | 2022-05-12 | 4 | 56 | 21 | 16 | 94 | 2022 | 2022 | R15
158919281928 | 159353928919 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2021-10-01 | 2022-01-27 | 2022-06-07 | 2023-09-11 | 2023-10-10 | Overhead | R15 | 2023-09-11 | 85 | 94 | 330 | 22 | 528 | 2021 | 2023 | R15
159456300382 | 159481382456 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2022-02-15 | 2022-02-15 | 2022-11-14 | 2023-07-07 | 2023-08-16 | Underground | R15 | 2023-07-07 | 1 | 195 | 170 | 29 | 392 | 2022 | 2023 | R15
154695307462 | 156065462695 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Commercial | 2021-12-15 | 2021-12-15 | 2023-01-27 | 2023-07-11 | 2023-07-07 | Underground | R15 | 2023-07-11 | 1 | 293 | 118 |  | 408 | 2021 | 2023 | R15
154185282633 | 154231633185 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2022-04-26 | 2022-04-26 | 2022-06-15 | 2023-06-07 | 2023-06-09 | Overhead | R15 | 2023-06-07 | 1 | 37 | 256 | 3 | 294 | 2022 | 2023 | R15
150803297261 | 153306261803 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2022-04-21 | 2022-05-05 | 2022-10-17 | 2023-06-16 | 2023-09-05 | Underground | R15 | 2023-06-16 | 11 | 118 | 175 | 58 | 359 | 2022 | 2023 | R15
159283273202 | 159606202283 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2022-02-16 | 2022-02-16 | 2022-03-18 | 2022-04-08 | 2022-05-10 | Overhead | R15 | 2022-04-08 | 1 | 23 | 16 | 23 | 60 | 2022 | 2022 | R15
155076306818 | 155077818076 | Affordable Housing | OH RESD INDIVIDUAL OD | Residential | 2022-01-28 | 2022-01-28 | 2023-01-30 | 2023-02-24 | 2023-05-23 | Overhead | R15 | 2023-02-24 | 1 | 262 | 20 | 63 | 343 | 2022 | 2023 | R15
157372287659 | 157155659372 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG RES INDIVIDUAL | Residential | 2022-03-21 | 2022-03-21 | 2022-08-03 | 2023-08-01 | 2023-10-19 | Underground | R15 | 2023-08-01 | 1 | 98 | 260 | 58 | 414 | 2022 | 2023 | R15
154575324864 | 159330864575 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2022-03-31 | 2022-11-04 | 2023-07-12 | 2023-08-15 | 2023-09-20 | Overhead | R15 | 2023-08-15 | 157 | 179 | 25 | 27 | 385 | 2022 | 2023 | R15
154575324864 | 159330864575 | RESIDENTIAL - MULTI-FAMILY | OH RESD INDIVIDUAL OD | Residential | 2022-03-31 | 2022-11-04 | 2023-07-12 | 2023-08-15 | 2023-09-20 | Overhead | R15 | 2023-08-15 | 157 | 179 | 25 | 27 | 385 | 2022 | 2023 | R15
153059298281 | 154182281059 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2022-01-25 | 2022-01-25 | 2022-10-26 | 2022-12-16 | 2023-11-30 | Underground | R15 | 2022-12-16 | 1 | 197 | 38 | 250 | 483 | 2022 | 2023 | R15
156729319226 | 156771226729 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-09-20 | 2021-09-20 | 2023-05-15 | 2023-08-23 | 2023-11-07 | Underground | R15 | 2023-08-23 | 1 | 431 | 73 | 55 | 557 | 2021 | 2023 | R15
155344323128 | 154266128344 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential Subdivision | 2022-04-26 | 2022-04-26 | 2023-06-23 | 2023-10-09 | 2023-10-20 | Underground | R15 | 2023-10-09 | 1 | 304 | 77 | 10 | 389 | 2022 | 2023 | R15
158205309857 | 152343857205 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2022-09-19 | 2022-12-14 | 2023-02-22 | 2023-10-16 | 2023-11-15 | Underground | R15 | 2023-10-16 | 63 | 51 | 169 | 23 | 303 | 2022 | 2023 | R15
157970221614 | 158913614970 | Electric Vehicle | UG EXT NON RES | Commercial | 2020-05-26 | 2020-10-28 | 2021-02-26 | 2022-09-26 | 2022-09-30 | Underground | R15 | 2022-09-26 | 112 | 88 | 412 | 5 | 614 | 2020 | 2022 | R15
155501208446 | 154710446501 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Commercial | 2020-06-26 | 2020-06-26 | 2020-10-26 | 2021-05-25 | 2021-08-24 | Underground | R15 | 2021-05-25 | 1 | 87 | 152 | 66 | 303 | 2020 | 2021 | R15
154200225470 | 151783470200 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-06-11 | 2020-06-11 | 2021-04-01 | 2022-06-28 | 2022-07-15 | Underground | R15 | 2022-06-28 | 1 | 211 | 324 | 14 | 547 | 2020 | 2022 | R15
157295266996 | 153653996295 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Commercial | 2020-03-02 | 2020-11-19 | 2022-02-01 | 2022-06-03 | 2022-06-22 | Underground | R15 | 2022-06-03 | 189 | 314 | 89 | 14 | 603 | 2020 | 2022 | R15
156099197685 | 150459685099 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-04-07 | 2020-04-07 | 2020-07-17 | 2020-08-12 | 2020-11-05 | Overhead | R15 | 2020-08-12 | 1 | 74 | 19 | 62 | 153 | 2020 | 2020 | R15
156446273403 | 156387403446 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-03-16 | 2020-03-24 | 2022-03-21 | 2022-12-01 | 2023-01-06 | Underground | R15 | 2022-12-01 | 7 | 520 | 184 | 27 | 735 | 2020 | 2023 | R15
155171231139 | 156900139171 | NON-RESIDENTIAL - WAREHOUSE | UG EXT NON RES | Commercial | 2020-05-13 | 2020-09-24 | 2021-05-18 | 2021-12-06 | 2022-02-09 | Underground | R15 | 2021-12-06 | 97 | 169 | 145 | 48 | 456 | 2020 | 2022 | R15
155687207052 | 155689052687 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-01-24 | 2020-01-24 | 2020-10-13 | 2020-12-16 | 2021-01-21 | Underground | R15 | 2020-12-16 | 1 | 188 | 47 | 27 | 260 | 2020 | 2021 | R15
153951250154 | 156589154951 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-05-12 | 2020-07-08 | 2021-09-30 | 2021-11-06 | 2022-04-21 | Underground | R15 | 2021-11-06 | 42 | 322 | 27 | 119 | 508 | 2020 | 2022 | R15
150733189214 | 151840214733 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2020-01-07 | 2020-01-07 | 2020-04-28 | 2020-10-01 | 2022-10-29 | Overhead | R15 | 2020-10-01 | 1 | 81 | 113 | 542 | 734 | 2020 | 2022 | R15
151440188703 | 152702703440 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-04-20 | 2020-04-20 | 2020-04-22 | 2021-02-17 | 2021-04-16 | Underground | R15 | 2021-02-17 | 1 | 3 | 216 | 43 | 260 | 2020 | 2021 | R15
150048277316 | 158206316048 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential | 2020-03-25 | 2020-03-25 | 2022-04-27 | 2022-11-23 | 2023-03-06 | Underground | R15 | 2022-11-23 | 1 | 546 | 151 | 74 | 769 | 2020 | 2023 | R15
153522193713 | 153366713522 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-03-02 | 2020-03-02 | 2020-06-09 | 2020-06-18 | 2021-05-05 | Overhead | R15 | 2020-06-18 | 1 | 72 | 8 | 230 | 308 | 2020 | 2021 | R15
151460216348 | 156013348460 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-05-07 | 2020-09-04 | 2021-01-06 | 2021-08-06 | 2022-07-28 | Underground | R15 | 2021-08-06 | 87 | 89 | 153 | 255 | 581 | 2020 | 2022 | R15
154931247689 | 154888689931 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-04-30 | 2020-05-01 | 2021-09-13 | 2022-07-18 | 2022-08-02 | Underground | R15 | 2022-07-18 | 2 | 357 | 221 | 12 | 589 | 2020 | 2022 | R15
151246249026 | 151248026246 | Affordable Housing | UG DEV RES | Residential | 2020-04-10 | 2020-09-03 | 2021-09-22 | 2022-04-08 | 2022-04-27 | Underground | R15 | 2022-04-08 | 105 | 275 | 143 | 14 | 534 | 2020 | 2022 | R15
158102203834 | 154339834102 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-03-05 | 2020-08-14 | 2020-09-15 | 2020-10-15 | 2020-11-10 | Overhead | R15 | 2020-10-15 | 117 | 23 | 23 | 19 | 179 | 2020 | 2020 | R15
157321223898 | 151123898321 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-06-08 | 2020-10-31 | 2021-03-17 | 2022-06-06 | 2023-07-03 | Underground | R15 | 2022-06-06 | 105 | 98 | 319 | 281 | 801 | 2020 | 2023 | R15
155624228699 | 157333699624 | NON-RESIDENTIAL - WAREHOUSE | UG EXT NON RES | Commercial | 2020-03-20 | 2020-11-14 | 2021-04-30 | 2022-05-26 | 2022-10-29 | Underground | R15 | 2022-05-26 | 171 | 120 | 280 | 112 | 681 | 2020 | 2022 | R15
157518292734 | 159461734518 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2020-02-12 | 2020-02-12 | 2022-09-06 | 2023-08-21 | 2023-09-06 | Overhead | R15 | 2023-08-21 | 1 | 670 | 250 | 13 | 931 | 2020 | 2023 | R15
157919240860 | 157950860919 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-02-04 | 2021-02-10 | 2021-07-26 | 2022-07-11 | 2022-08-01 | Underground | R15 | 2022-07-11 | 267 | 119 | 251 | 16 | 650 | 2020 | 2022 | R15
156046222212 | 154356212046 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-06-25 | 2020-12-17 | 2021-03-02 | 2022-04-19 | 2022-04-28 | Overhead | R15 | 2022-04-19 | 126 | 54 | 296 | 8 | 481 | 2020 | 2022 | R15
156346214523 | 156348523346 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-01-28 | 2020-01-28 | 2020-12-18 | 2021-05-21 | 2021-08-02 | Underground | R15 | 2021-05-21 | 1 | 234 | 111 | 52 | 395 | 2020 | 2021 | R15
152786196427 | 158922427786 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG EXT NON RES | Commercial | 2020-02-10 | 2020-06-19 | 2020-07-02 | 2020-07-31 | 2021-03-11 | Underground | R15 | 2020-07-31 | 95 | 10 | 22 | 160 | 284 | 2020 | 2021 | R15
151246223624 | 151341624246 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-06-09 | 2020-06-09 | 2021-03-15 | 2021-10-31 | 2021-11-09 | Overhead | R15 | 2021-10-31 | 1 | 200 | 165 | 7 | 371 | 2020 | 2021 | R15
156488246984 | 153286984488 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Residential | 2020-06-19 | 2021-03-11 | 2021-09-08 | 2022-09-20 | 2023-02-03 | Overhead | R15 | 2022-09-20 | 190 | 130 | 270 | 99 | 686 | 2020 | 2023 | R15
155762205055 | 156249055762 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-05-08 | 2020-05-28 | 2020-09-25 | 2020-10-08 | 2020-11-16 | Overhead | R15 | 2020-10-08 | 15 | 87 | 10 | 28 | 137 | 2020 | 2020 | R15
152051213363 | 152291363051 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2020-01-08 | 2020-01-10 | 2020-12-09 | 2021-11-03 | 2021-11-22 | Underground | R15 | 2021-11-03 | 3 | 239 | 236 | 14 | 489 | 2020 | 2021 | R15
157062222063 | 156914063062 | NON-RESIDENTIAL - MISCELLANEOUS | UG DEV NON RES | Commercial | 2020-05-13 | 2020-05-14 | 2021-03-01 | 2021-09-30 | 2021-10-15 | Underground | R15 | 2021-09-30 | 2 | 208 | 154 | 12 | 373 | 2020 | 2021 | R15
153853230377 | 153975377853 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-01-16 | 2020-05-08 | 2021-05-12 | 2022-04-19 | 2023-09-17 | Underground | R15 | 2022-04-19 | 82 | 264 | 245 | 369 | 957 | 2020 | 2023 | R15
151918223697 | 151819697918 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential | 2020-01-08 | 2020-03-25 | 2021-03-16 | 2021-08-12 | 2022-02-07 | Underground | R15 | 2021-08-12 | 56 | 255 | 108 | 128 | 544 | 2020 | 2022 | R15
157871226017 | 157881017871 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-02-04 | 2020-06-25 | 2021-04-08 | 2021-08-18 | 2021-10-11 | Underground | R15 | 2021-08-18 | 103 | 206 | 95 | 39 | 440 | 2020 | 2021 | R15
156729227819 | 150985819729 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2020-06-08 | 2020-10-26 | 2021-04-22 | 2022-04-07 | 2022-05-25 | Underground | R15 | 2022-04-07 | 101 | 129 | 251 | 35 | 513 | 2020 | 2022 | R15
153840260380 | 154350380840 | NON-RESIDENTIAL - SMALL RETAIL | UG EXT NON RES | Commercial | 2020-06-25 | 2020-08-15 | 2021-12-08 | 2022-03-11 | 2022-04-01 | Underground | R15 | 2022-03-11 | 37 | 343 | 68 | 16 | 462 | 2020 | 2022 | R15
157782186506 | 159660506782 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-02-12 | 2020-02-12 | 2020-04-06 | 2020-08-06 | 2021-03-11 | Underground | R15 | 2020-08-06 | 1 | 39 | 89 | 156 | 282 | 2020 | 2021 | R15
157413220265 | 151929265413 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-04-15 | 2021-01-21 | 2021-02-10 | 2021-07-12 | 2022-01-07 | Overhead | R15 | 2021-07-12 | 202 | 15 | 109 | 130 | 453 | 2020 | 2022 | R15
159635214087 | 154104087635 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-03-04 | 2020-03-30 | 2020-12-15 | 2021-03-19 | 2021-05-06 | Underground | R15 | 2021-03-19 | 19 | 187 | 69 | 35 | 307 | 2020 | 2021 | R15
151985223498 | 152003498985 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential | 2020-01-08 | 2020-03-25 | 2021-03-15 | 2021-08-12 | 2022-02-04 | Underground | R15 | 2021-08-12 | 56 | 254 | 109 | 127 | 543 | 2020 | 2022 | R15
159170200646 | 154507646170 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-11-21 | 2019-11-21 | 2020-08-14 | 2020-08-26 | 2021-02-16 | Overhead | R15 | 2020-08-26 | 1 | 192 | 9 | 125 | 324 | 2019 | 2021 | R15
153510174026 | 153521026510 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential Subdivision | 2019-06-12 | 2019-06-12 | 2019-12-10 | 2020-08-07 | 2020-11-06 | Underground | R15 | 2020-08-07 | 1 | 130 | 174 | 66 | 368 | 2019 | 2020 | R15
150733191914 | 154540914733 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-10-03 | 2019-10-03 | 2020-05-22 | 2020-10-01 | 2021-01-14 | Underground | R15 | 2020-10-01 | 1 | 167 | 95 | 76 | 336 | 2019 | 2021 | R15
154861189631 | 158102631861 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-08-28 | 2020-01-22 | 2020-05-01 | 2020-08-31 | 2020-11-12 | Underground | R15 | 2020-08-31 | 106 | 73 | 87 | 54 | 317 | 2019 | 2020 | R15
154945230460 | 155053460945 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-11-25 | 2019-11-25 | 2021-05-12 | 2022-10-20 | 2023-04-17 | Underground | R15 | 2022-10-20 | 1 | 383 | 377 | 128 | 886 | 2019 | 2023 | R15
156257202621 | 151909621257 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-11-07 | 2019-11-21 | 2020-09-02 | 2021-06-22 | 2022-08-03 | Underground | R15 | 2021-06-22 | 11 | 205 | 210 | 292 | 715 | 2019 | 2022 | R15
155765186664 | 157075664765 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-10-15 | 2019-10-21 | 2020-04-06 | 2021-11-08 | 2021-11-29 | Underground | R15 | 2021-11-08 | 5 | 121 | 416 | 16 | 555 | 2019 | 2021 | R15
154280281970 | 154291970280 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-06-16 | 2020-04-03 | 2022-06-08 | 2023-06-12 | 2023-07-21 | Underground | R15 | 2023-06-12 | 210 | 569 | 264 | 30 | 1070 | 2019 | 2023 | R15
159437259604 | 153637604437 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2019-09-30 | 2019-09-30 | 2021-12-02 | 2022-06-28 | 2022-07-05 | Underground | R15 | 2022-06-28 | 1 | 569 | 149 | 6 | 722 | 2019 | 2022 | R15
157317174989 | 157127989317 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-08-23 | 2019-10-26 | 2019-12-23 | 2020-03-02 | 2020-06-18 | Underground | R15 | 2020-03-02 | 46 | 41 | 51 | 79 | 215 | 2019 | 2020 | R15
152728176219 | 155674219728 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-08-15 | 2019-09-05 | 2020-01-09 | 2020-01-13 | 2020-03-09 | Overhead | R15 | 2020-01-13 | 16 | 91 | 3 | 41 | 148 | 2019 | 2020 | R15
155602190132 | 159535132602 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-07-12 | 2020-01-22 | 2020-05-06 | 2020-08-20 | 2022-08-25 | Underground | R15 | 2020-08-20 | 139 | 76 | 77 | 526 | 815 | 2019 | 2022 | R15
150161196016 | 150154016161 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2019-10-30 | 2020-02-21 | 2020-06-30 | 2022-05-23 | 2023-01-18 | Underground | R15 | 2022-05-23 | 83 | 93 | 495 | 173 | 841 | 2019 | 2023 | R15
159681286900 | 154809900681 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-10-04 | 2019-10-04 | 2022-07-25 | 2022-12-08 | 2023-01-11 | Underground | R15 | 2022-12-08 | 1 | 732 | 99 | 25 | 854 | 2019 | 2023 | R15
151855184658 | 152666658855 | CUSTOMER UPGRADE IN SERVICE | UG R15 RES NON RES BUDG 225 | Residential | 2019-09-24 | 2019-09-24 | 2020-03-19 |  | 2021-10-29 | Underground | R15 |  | 1 | 128 |  |  | 549 | 2019 | 2021 | R15
153608188582 | 158795582608 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2019-09-02 | 2020-01-29 | 2020-04-21 | 2020-04-23 | 2020-09-01 | Overhead | R15 | 2020-04-23 | 108 | 60 | 3 | 94 | 262 | 2019 | 2020 | R15
159437259881 | 153641881437 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-09-30 | 2019-09-30 | 2021-12-03 | 2023-05-22 | 2023-06-16 | Underground | R15 | 2023-05-22 | 1 | 570 | 382 | 20 | 970 | 2019 | 2023 | R15
159437224942 | 153157942437 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-09-26 | 2019-09-26 | 2021-03-26 | 2022-01-14 | 2022-02-25 | Underground | R15 | 2022-01-14 | 1 | 392 | 211 | 31 | 632 | 2019 | 2022 | R15
157018272214 | 155274214018 | NON-RESIDENTIAL - HEALTH CARE | UG EXT NON RES | Commercial | 2019-06-20 | 2020-03-13 | 2022-03-10 | 2022-07-06 | 2022-07-27 | Underground | R15 | 2022-07-06 | 192 | 520 | 85 | 16 | 810 | 2019 | 2022 | R15
153301210372 | 153116372301 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG EXT NON RES | Commercial | 2019-06-11 | 2019-06-11 | 2020-11-12 | 2021-03-09 | 2021-04-26 | Underground | R15 | 2021-03-09 | 1 | 373 | 84 | 35 | 490 | 2019 | 2021 | R15
150147252270 | 152629270147 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Commercial | 2019-07-30 | 2019-07-30 | 2021-10-15 |  | 2023-09-05 | Underground | R15 |  | 1 | 579 |  |  | 1071 | 2019 | 2023 | R15
155560173692 | 158362692560 | CUSTOMER UPGRADE IN SERVICE | UG R15 RES NON RES BUDG 225 | Residential | 2019-07-05 | 2019-07-05 | 2019-12-06 | 2021-04-02 | 2021-06-02 | Underground | R15 | 2021-04-02 | 1 | 111 | 346 | 44 | 499 | 2019 | 2021 | R15
151843159635 | 153211635843 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2019-06-10 | 2019-06-10 | 2019-08-01 | 2019-08-01 | 2020-09-23 | Overhead | R15 | 2019-08-01 | 1 | 39 |  | 300 | 338 | 2019 | 2020 | R15
153485165126 | 153449126485 | FOREIGN UTILITY | OH EXTENSION NON RESD OD | Commercial | 2019-06-12 | 2019-07-01 | 2019-09-19 | 2020-02-17 | 2020-04-24 | Overhead | R15 | 2020-02-17 | 14 | 59 | 108 | 50 | 228 | 2019 | 2020 | R15
153702178833 | 151143833702 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2019-09-16 | 2019-10-14 | 2020-01-31 | 2020-05-20 | 2020-09-18 | Overhead | R15 | 2020-05-20 | 21 | 80 | 79 | 88 | 265 | 2019 | 2020 | R15
156221187302 | 159980302221 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-07-15 | 2019-08-07 | 2020-04-13 | 2020-07-01 | 2020-11-04 | Underground | R15 | 2020-07-01 | 18 | 179 | 58 | 91 | 343 | 2019 | 2020 | R15
152789192957 | 152901957789 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2019-09-25 | 2019-09-25 | 2020-06-01 | 2020-11-18 | 2023-11-20 | Underground | R15 | 2020-11-18 | 1 | 179 | 123 | 784 | 1084 | 2019 | 2023 | R15
158239227764 | 158799764239 | RESIDENTIAL - MOBILE HOME | UG DEV RES | Residential | 2019-12-17 | 2019-12-20 | 2021-04-20 | 2021-08-19 | 2021-10-01 | Underground | R15 | 2021-08-19 | 4 | 348 | 88 | 32 | 469 | 2019 | 2021 | R15
159104177801 | 154970801104 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential Subdivision | 2019-08-12 | 2019-08-12 | 2020-01-22 | 2021-06-21 | 2021-12-30 | Underground | R15 | 2021-06-21 | 1 | 118 | 369 | 139 | 624 | 2019 | 2021 | R15
156817184144 | 159031144817 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-09-03 | 2019-09-05 | 2020-03-16 | 2020-03-29 | 2020-09-02 | Overhead | R15 | 2020-03-29 | 3 | 138 | 10 | 113 | 262 | 2019 | 2020 | R15
150786217772 | 150110772786 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2019-07-15 | 2019-08-31 | 2021-01-21 | 2021-09-28 | 2021-10-21 | Underground | R15 | 2021-09-28 | 35 | 364 | 179 | 18 | 594 | 2019 | 2021 | R15
159544181055 | 155556055544 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-08-14 | 2019-10-07 | 2020-02-19 | 2020-10-29 | 2022-09-28 | Underground | R15 | 2020-10-29 | 39 | 98 | 182 | 500 | 816 | 2019 | 2022 | R15
155152182063 | 153495063152 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-09-28 | 2019-10-05 | 2020-02-26 | 2021-04-19 | 2021-05-20 | Underground | R15 | 2021-04-19 | 5 | 103 | 299 | 24 | 429 | 2019 | 2021 | R15
154498204107 | 154509107498 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2019-10-03 | 2019-10-03 | 2020-09-17 | 2021-06-11 | 2022-10-29 | Underground | R15 | 2021-06-11 | 1 | 251 | 192 | 361 | 802 | 2019 | 2022 | R15
151501195630 | 158302630501 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-10-22 | 2019-10-22 | 2020-06-29 | 2020-07-20 | 2020-11-04 | Underground | R15 | 2020-07-20 | 1 | 180 | 16 | 78 | 272 | 2019 | 2020 | R15
153351228207 | 154347207351 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-11-20 | 2020-03-13 | 2021-04-23 | 2022-12-14 | 2023-07-03 | Underground | R15 | 2022-12-14 | 83 | 291 | 429 | 144 | 944 | 2019 | 2023 | R15
151209214310 | 151532310209 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-11-06 | 2019-11-12 | 2020-12-18 | 2021-11-22 | 2021-12-21 | Underground | R15 | 2021-11-22 | 5 | 289 | 242 | 22 | 555 | 2019 | 2021 | R15
154861187923 | 158101923861 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-08-28 | 2020-01-09 | 2020-04-16 | 2020-08-31 | 2020-11-20 | Underground | R15 | 2020-08-31 | 97 | 71 | 98 | 60 | 323 | 2019 | 2020 | R15
155708216540 | 155050540708 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-10-05 | 2019-10-05 | 2021-01-07 | 2021-03-31 | 2021-06-02 | Underground | R15 | 2021-03-31 | 0 | 329 | 60 | 46 | 433 | 2019 | 2021 | R15
150669203113 | 150782113669 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential Subdivision | 2019-11-01 | 2019-11-01 | 2020-09-08 | 2023-05-17 | 2023-09-06 | Underground | R15 | 2023-05-17 | 1 | 223 | 702 | 81 | 1004 | 2019 | 2023 | R15
150635169067 | 155692067635 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-06-24 | 2019-06-24 | 2019-10-21 | 2021-02-24 | 2021-03-31 | Underground | R15 | 2021-02-24 | 1 | 86 | 353 | 26 | 463 | 2019 | 2021 | R15
151274216439 | 158302439274 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-12-13 | 2019-12-13 | 2021-09-14 | 2021-09-30 | 2021-12-07 | Underground | R15 | 2021-09-30 | 1 | 458 | 13 | 49 | 518 | 2019 | 2021 | R15
157765179372 | 159462372765 | FOREIGN UTILITY | OH EXTENSION NON RESD OD | Commercial | 2019-10-26 | 2019-10-30 | 2020-02-05 | 2020-04-21 | 2020-11-11 | Overhead | R15 | 2020-04-21 | 3 | 71 | 55 | 147 | 273 | 2019 | 2020 | R15
150668202952 | 150518952668 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential Subdivision | 2019-11-01 | 2019-11-01 | 2020-09-04 | 2022-06-09 | 2022-06-20 | Underground | R15 | 2022-06-09 | 1 | 221 | 460 | 8 | 687 | 2019 | 2022 | R15
153631189313 | 159557313631 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2019-07-12 | 2019-12-06 | 2020-04-29 | 2020-07-14 | 2021-03-18 | Overhead | R15 | 2020-07-14 | 106 | 104 | 55 | 178 | 440 | 2019 | 2021 | R15
151548210984 | 151731984548 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2019-07-24 | 2019-07-24 | 2020-11-17 |  | 2022-05-02 | Underground | R15 |  | 1 | 345 |  |  | 724 | 2019 | 2022 | R15
150375240797 | 156603797375 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-12-06 | 2020-09-24 | 2021-07-27 | 2023-06-26 | 2023-07-21 | Underground | R15 | 2023-06-26 | 210 | 219 | 500 | 20 | 946 | 2019 | 2023 | R15
151579178502 | 158693502579 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2019-10-23 | 2019-10-23 | 2020-01-28 | 2020-03-23 | 2023-02-10 | Overhead | R15 | 2020-03-23 | 1 | 70 | 40 | 755 | 863 | 2019 | 2023 | R15
152201201013 | 155790013201 | NON-RESIDENTIAL - HEALTH CARE | UG EXT NON RES | Commercial | 2019-06-24 | 2019-06-24 | 2020-08-19 | 2021-12-02 | 2022-01-06 | Underground | R15 | 2021-12-02 | 1 | 303 | 337 | 26 | 664 | 2019 | 2022 | R15
152935199025 | 153006025935 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2019-09-25 | 2019-09-25 | 2020-07-30 | 2020-11-17 | 2021-03-12 | Underground | R15 | 2020-11-17 | 1 | 222 | 79 | 84 | 383 | 2019 | 2021 | R15
150994287529 | 151093529994 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-10-28 | 2022-01-29 | 2022-08-01 | 2023-02-25 | 2023-05-18 | Underground | R15 | 2023-02-25 | 328 | 131 | 150 | 59 | 667 | 2020 | 2023 | R15
158943149593 | 151519593943 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-02-05 | 2019-03-15 | 2019-04-19 | 2019-07-02 | 2019-12-04 | Overhead | R15 | 2019-07-02 | 29 | 26 | 53 | 112 | 217 | 2019 | 2019 | R15
159188246585 | 159343585188 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-04-21 | 2021-05-14 | 2021-09-02 | 2022-05-31 | 2022-06-03 | Underground | R15 | 2022-05-31 | 18 | 80 | 194 | 4 | 293 | 2021 | 2022 | R15
152404239017 | 154775017404 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2021-03-31 | 2021-06-07 | 2021-07-15 | 2021-08-21 | 2021-09-21 | Overhead | R15 | 2021-08-21 | 49 | 29 | 27 | 22 | 125 | 2021 | 2021 | R15
157580282969 | 152990969580 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2020-12-22 | 2021-05-11 | 2022-06-16 | 2022-08-28 | 2023-11-30 | Underground | R15 | 2022-08-28 | 101 | 288 | 52 | 329 | 768 | 2020 | 2023 | R15
150294205399 | 150314399294 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Residential | 2019-03-28 | 2020-05-25 | 2020-09-28 | 2021-08-23 | 2022-02-09 | Overhead | R15 | 2021-08-23 | 303 | 91 | 236 | 123 | 750 | 2019 | 2022 | R15
153849219661 | 152071661849 | RESIDENTIAL - SINGLE FAMILY ATTACHED | OH RESD INDIVIDUAL OD | Residential | 2020-08-05 | 2020-09-06 | 2021-02-04 | 2021-02-19 | 2021-04-08 | Overhead | R15 | 2021-02-19 | 23 | 109 | 12 | 35 | 177 | 2020 | 2021 | R15
151980220239 | 150928239980 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-12-15 | 2020-12-15 | 2021-02-12 | 2021-05-05 | 2021-06-28 | Underground | R15 | 2021-05-05 | 1 | 44 | 59 | 39 | 140 | 2020 | 2021 | R15
150386292357 | 150163357386 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Commercial | 2021-05-27 | 2021-05-27 | 2022-09-02 | 2022-09-21 | 2022-10-18 | Underground | R15 | 2022-09-21 | 1 | 332 | 14 | 20 | 364 | 2021 | 2022 | R15
154007263173 | 157851173007 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-12-01 | 2021-07-21 | 2022-01-03 | 2022-04-13 | 2022-10-29 | Underground | R15 | 2022-04-13 | 167 | 119 | 73 | 143 | 499 | 2020 | 2022 | R15
153927257483 | 150006483927 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2021-01-27 | 2021-02-16 | 2021-11-19 | 2022-03-15 | 2022-03-28 | Overhead | R15 | 2022-03-15 | 15 | 199 | 83 | 10 | 304 | 2021 | 2022 | R15
154146146348 | 150541348146 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-01-31 | 2019-01-31 | 2019-03-18 | 2019-05-21 | 2019-05-24 | Overhead | R15 | 2019-05-21 | 1 | 33 | 47 | 4 | 82 | 2019 | 2019 | R15
159760249874 | 154485874760 | CUSTOMER UPGRADE IN SERVICE | OH RESD INDIVIDUAL OD | Residential | 2020-08-18 | 2020-11-10 | 2021-09-29 | 2022-04-22 | 2022-06-02 | Overhead | R15 | 2022-04-22 | 61 | 232 | 148 | 30 | 468 | 2020 | 2022 | R15
156753229850 | 153010850753 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-11-05 | 2021-01-26 | 2021-05-07 | 2021-06-17 | 2021-12-30 | Underground | R15 | 2021-06-17 | 59 | 74 | 30 | 141 | 301 | 2020 | 2021 | R15
156107282232 | 156108232107 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-05-17 | 2021-06-03 | 2022-06-10 | 2023-08-03 | 2023-08-30 | Underground | R15 | 2023-08-03 | 14 | 267 | 300 | 20 | 598 | 2021 | 2023 | R15
158420279920 | 154431920420 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-03-30 | 2021-11-05 | 2022-05-18 | 2023-07-17 | 2023-08-16 | Underground | R15 | 2023-07-17 | 159 | 139 | 304 | 23 | 622 | 2021 | 2023 | R15
154511174358 | 154532358511 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2019-04-19 | 2019-08-12 | 2019-12-13 | 2020-10-05 | 2021-01-20 | Underground | R15 | 2020-10-05 | 82 | 90 | 212 | 78 | 459 | 2019 | 2021 | R15
154675219987 | 154492987675 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-09-29 | 2020-11-30 | 2021-02-09 | 2021-11-24 | 2022-01-06 | Underground | R15 | 2021-11-24 | 45 | 52 | 207 | 32 | 333 | 2020 | 2022 | R15
150390159911 | 155354911390 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential Subdivision | 2019-04-25 | 2019-04-25 | 2019-08-02 |  | 2021-03-30 | Underground | R15 |  | 1 | 72 |  |  | 504 | 2019 | 2021 | R15
157095237021 | 158071021095 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2020-10-14 | 2021-01-04 | 2021-06-28 | 2022-01-27 | 2022-02-11 | Overhead | R15 | 2022-01-27 | 59 | 126 | 154 | 12 | 348 | 2020 | 2022 | R15
150566279952 | 150962952566 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-12-15 | 2020-12-15 | 2022-05-20 | 2023-06-08 | 2023-07-03 | Underground | R15 | 2023-06-08 | 1 | 374 | 275 | 18 | 665 | 2020 | 2023 | R15
158412248651 | 159723651412 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-04-22 | 2021-06-25 | 2021-09-21 | 2022-01-04 | 2022-01-11 | Underground | R15 | 2022-01-04 | 47 | 63 | 76 | 6 | 189 | 2021 | 2022 | R15
152958309172 | 155769172958 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2021-04-05 | 2021-10-14 | 2023-02-14 | 2023-10-06 | 2023-10-30 | Underground | R15 | 2023-10-06 | 139 | 349 | 169 | 17 | 671 | 2021 | 2023 | R15
152483172772 | 152477772483 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential Subdivision | 2019-02-08 | 2019-02-08 | 2019-11-25 | 2020-03-04 | 2020-11-19 | Overhead | R15 | 2020-03-04 | 1 | 207 | 73 | 187 | 465 | 2019 | 2020 | R15
155984161886 | 155878886984 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG RES INDIVIDUAL | Residential Subdivision | 2019-04-29 | 2019-05-31 | 2019-08-20 | 2020-04-02 | 2021-03-05 | Underground | R15 | 2020-04-02 | 25 | 58 | 163 | 242 | 485 | 2019 | 2021 | R15
158357157429 | 152417429357 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-06-05 | 2019-06-05 | 2019-07-09 | 2019-12-20 | 2020-06-11 | Overhead | R15 | 2019-12-20 | 1 | 25 | 119 | 125 | 267 | 2019 | 2020 | R15
153010297012 | 153054012010 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-03-24 | 2021-03-24 | 2022-10-14 | 2023-10-17 | 2023-09-25 | Underground | R15 | 2023-10-17 | 1 | 408 | 263 |  | 654 | 2021 | 2023 | R15
157972149780 | 158051780972 | NON-RESIDENTIAL - SMALL RETAIL | UG EXT NON RES | Commercial | 2019-03-13 | 2019-03-19 | 2019-04-19 | 2020-12-08 | 2021-02-27 | Underground | R15 | 2020-12-08 | 5 | 24 | 428 | 59 | 513 | 2019 | 2021 | R15
153943238006 | 155937006943 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Commercial | 2021-05-17 | 2021-05-17 | 2021-07-07 |  | 2021-10-01 | Underground | R15 | 2021-07-07 | 1 | 38 |  | 63 | 100 | 2021 | 2021 | R15
152730157947 | 157766947730 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2019-03-12 | 2019-03-27 | 2019-07-16 | 2019-08-21 | 2021-11-30 | Overhead | R15 | 2019-08-21 | 12 | 80 | 27 | 595 | 711 | 2019 | 2021 | R15
156250292895 | 152925895250 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-02-12 | 2020-10-23 | 2023-01-30 | 2023-02-08 | 2023-03-01 | Underground | R15 | 2023-02-08 | 444 | 592 | 8 | 16 | 1057 | 2019 | 2023 | R15
151251253834 | 154881834251 | FOREIGN UTILITY | UG EXT NON RES | Commercial | 2021-05-12 | 2021-08-27 | 2021-10-26 | 2022-06-28 | 2022-07-18 | Underground | R15 | 2022-06-28 | 78 | 43 | 176 | 15 | 309 | 2021 | 2022 | R15
158264259946 | 158268946264 | Affordable Housing | UG DEV RES | Residential | 2020-10-15 | 2020-10-15 | 2021-12-06 | 2023-06-22 | 2023-07-03 | Underground | R15 | 2023-06-22 | 1 | 298 | 404 | 8 | 708 | 2020 | 2023 | R15
158032243087 | 159693087032 | Electric Vehicle | UG EXT NON RES | Commercial | 2021-03-10 | 2021-05-27 | 2021-08-11 | 2022-03-21 | 2022-11-01 | Underground | R15 | 2022-03-21 | 57 | 55 | 159 | 162 | 430 | 2021 | 2022 | R15
153481150911 | 151567911481 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-02-05 | 2019-02-08 | 2019-05-01 | 2019-07-02 | 2019-12-04 | Overhead | R15 | 2019-07-02 | 4 | 59 | 45 | 112 | 217 | 2019 | 2019 | R15
155843266357 | 154438357843 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-09-29 | 2020-09-29 | 2022-01-27 | 2023-03-23 | 2023-06-11 | Underground | R15 | 2023-03-23 | 1 | 348 | 301 | 57 | 704 | 2020 | 2023 | R15
152778299641 | 155024641778 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2021-02-18 | 2021-04-30 | 2022-11-07 | 2023-06-19 | 2023-07-25 | Overhead | R15 | 2023-06-19 | 52 | 397 | 161 | 27 | 634 | 2021 | 2023 | R15
153168271785 | 153181785168 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2021-02-09 | 2021-02-09 | 2022-03-07 | 2022-04-05 | 2022-04-26 | Overhead | R15 | 2022-04-05 | 1 | 280 | 22 | 16 | 316 | 2021 | 2022 | R15
151980211220 | 158220220980 | AGRICULTURAL | OH EXTENSION NON RESD OD | Residential | 2020-09-02 | 2020-09-02 | 2020-11-18 | 2022-02-08 | 2022-02-24 | Overhead | R15 | 2022-02-08 | 1 | 56 | 320 | 13 | 387 | 2020 | 2022 | R15
154229259788 | 154291788229 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-03-29 | 2021-03-29 | 2021-12-03 | 2022-06-06 | 2022-06-22 | Underground | R15 | 2022-06-06 | 1 | 180 | 132 | 13 | 323 | 2021 | 2022 | R15
151274275061 | 150487061274 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2021-05-28 | 2021-07-21 | 2022-04-06 | 2022-06-20 | 2022-06-30 | Overhead | R15 | 2022-06-20 | 39 | 186 | 54 | 9 | 285 | 2021 | 2022 | R15
158394161296 | 158756296394 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | OH EXTENSION NON RESD OD | Commercial | 2019-03-19 | 2019-06-04 | 2019-08-16 | 2019-10-14 | 2020-02-06 | Overhead | R15 | 2019-10-14 | 56 | 54 | 42 | 84 | 233 | 2019 | 2020 | R15
155962223574 | 157625574962 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2020-08-29 | 2020-08-29 | 2021-03-15 | 2021-09-09 | 2021-09-30 | Overhead | R15 | 2021-09-09 | 0 | 141 | 129 | 16 | 284 | 2020 | 2021 | R15
153449266215 | 157689215449 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2020-10-14 | 2021-05-20 | 2022-01-26 | 2022-08-04 | 2022-08-19 | Underground | R15 | 2022-08-04 | 157 | 180 | 137 | 12 | 483 | 2020 | 2022 | R15
151302269036 | 151375036302 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2019-04-03 | 2019-04-03 | 2022-02-15 |  | 2023-01-17 | Underground | R15 |  | 1 | 750 |  |  | 990 | 2019 | 2023 | R15
156063231782 | 157619782063 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2020-08-31 | 2020-08-31 | 2021-05-20 | 2021-11-01 | 2021-11-22 | Overhead | R15 | 2021-11-01 | 1 | 189 | 118 | 16 | 321 | 2020 | 2021 | R15
159716243806 | 153340806716 | FOREIGN UTILITY | UG EXT NON RES | Commercial | 2020-11-06 | 2020-11-06 | 2021-08-16 | 2021-10-26 | 2021-11-10 | Underground | R15 | 2021-10-26 | 1 | 202 | 52 | 12 | 264 | 2020 | 2021 | R15
159544285144 | 155170144544 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2021-01-06 | 2021-01-20 | 2022-07-11 |  | 2022-08-29 | Overhead | R15 |  | 11 | 384 |  |  | 429 | 2021 | 2022 | R15
157738215585 | 152070585738 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2020-09-21 | 2020-09-30 | 2020-12-28 | 2021-02-18 | 2021-03-19 | Overhead | R15 | 2021-02-18 | 8 | 64 | 39 | 22 | 130 | 2020 | 2021 | R15
159486176924 | 159494924486 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Residential | 2019-05-16 | 2019-08-27 | 2020-01-14 | 2020-01-15 | 2020-09-18 | Overhead | R15 | 2020-01-15 | 74 | 101 | 2 | 178 | 352 | 2019 | 2020 | R15
150062267105 | 150989105062 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2021-03-16 | 2021-03-23 | 2022-02-01 | 2022-02-15 | 2022-03-08 | Overhead | R15 | 2022-02-15 | 6 | 226 | 11 | 16 | 256 | 2021 | 2022 | R15
150558152189 | 151384189558 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-04-03 | 2019-04-03 | 2019-05-13 | 2019-06-12 | 2019-11-12 | Underground | R15 | 2019-06-12 | 1 | 29 | 23 | 110 | 160 | 2019 | 2019 | R15
154157234464 | 154124464157 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-05-10 | 2021-05-10 | 2021-06-10 | 2021-08-03 | 2021-08-06 | Overhead | R15 | 2021-08-03 | 1 | 24 | 39 | 4 | 65 | 2021 | 2021 | R15
159589257056 | 158842056589 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-05-21 | 2021-08-17 | 2021-11-17 | 2022-04-27 | 2022-05-17 | Underground | R15 | 2022-04-27 | 63 | 67 | 116 | 15 | 258 | 2021 | 2022 | R15
153886278646 | 155431646886 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-09-14 | 2022-02-11 | 2022-05-09 | 2023-03-15 | 2023-04-17 | Underground | R15 | 2023-03-15 | 109 | 62 | 223 | 24 | 415 | 2021 | 2023 | R15
157509289890 | 159685890509 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-08-18 | 2021-08-18 | 2022-08-22 | 2023-02-08 | 2023-03-09 | Underground | R15 | 2023-02-08 | 1 | 264 | 123 | 22 | 407 | 2021 | 2023 | R15
150307281898 | 154630898307 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2021-09-10 | 2021-09-10 | 2022-06-08 | 2023-02-08 | 2023-02-22 | Underground | R15 | 2023-02-08 | 1 | 194 | 176 | 11 | 379 | 2021 | 2023 | R15
157203283294 | 156112294203 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-08-04 | 2022-05-02 | 2022-06-21 | 2022-12-30 | 2023-02-03 | Underground | R15 | 2022-12-30 | 194 | 37 | 139 | 26 | 393 | 2021 | 2023 | R15
152091246198 | 152044198091 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-08-30 | 2021-08-31 | 2021-09-02 | 2021-09-30 | 2021-12-15 | Underground | R15 | 2021-09-30 | 2 | 3 | 21 | 55 | 78 | 2021 | 2021 | R15
150307298525 | 154632525307 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-09-10 | 2021-09-10 | 2022-10-27 | 2023-03-02 | 2023-03-09 | Underground | R15 | 2023-03-02 | 1 | 295 | 91 | 6 | 390 | 2021 | 2023 | R15
157884260087 | 150186087884 | NON-RESIDENTIAL - WAREHOUSE | UG EXT NON RES | Commercial | 2021-08-20 | 2021-08-20 | 2021-12-06 | 2022-03-28 | 2022-04-21 | Underground | R15 | 2022-03-28 | 1 | 77 | 81 | 19 | 175 | 2021 | 2022 | R15
159467193823 | 154896823467 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2019-10-05 | 2019-10-12 | 2020-06-10 | 2021-10-22 | 2022-01-25 | Overhead | R15 | 2021-10-22 | 5 | 173 | 358 | 68 | 602 | 2019 | 2022 | R15
157464227954 | 154344954464 | Electric Vehicle | UG EXT NON RES | Commercial | 2019-11-20 | 2019-12-19 | 2021-04-22 | 2022-05-23 | 2022-06-13 | Underground | R15 | 2022-05-23 | 22 | 351 | 283 | 16 | 669 | 2019 | 2022 | R15
152450184443 | 159494443450 | FOREIGN UTILITY | OH EXTENSION NON RESD OD | Residential | 2019-07-11 | 2019-09-26 | 2020-03-17 | 2020-04-07 | 2020-09-22 | Overhead | R15 | 2020-04-07 | 56 | 124 | 16 | 121 | 314 | 2019 | 2020 | R15
155678212900 | 157366900678 | NON-RESIDENTIAL - HEALTH CARE | UG EXT NON RES | Commercial | 2019-08-26 | 2020-08-11 | 2020-12-04 | 2023-03-13 | 2023-06-11 | Underground | R15 | 2023-03-13 | 252 | 84 | 592 | 65 | 990 | 2019 | 2023 | R15
151224223628 | 151146628224 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2019-09-16 | 2020-08-19 | 2021-03-15 | 2022-07-04 | 2022-07-07 | Overhead | R15 | 2022-07-04 | 243 | 149 | 341 | 4 | 734 | 2019 | 2022 | R15
150147232808 | 152627808147 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Commercial | 2019-07-30 | 2019-07-30 | 2021-05-28 | 2021-10-28 | 2023-08-30 | Underground | R15 | 2021-10-28 | 1 | 479 | 110 | 480 | 1067 | 2019 | 2023 | R15
152230200014 | 152334014230 | INDUSTRIAL | OH EXTENSION NON RESD OD | Commercial | 2019-09-23 | 2020-04-14 | 2020-08-07 | 2021-01-29 | 2022-04-01 | Overhead | R15 | 2021-01-29 | 147 | 84 | 126 | 306 | 660 | 2019 | 2022 | R15
152975174789 | 152984789975 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-11-13 | 2019-11-13 | 2019-12-18 | 2020-01-12 | 2020-11-18 | Overhead | R15 | 2020-01-12 | 1 | 26 | 18 | 223 | 266 | 2019 | 2020 | R15
158977232214 | 152974214977 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2019-11-13 | 2021-02-09 | 2021-05-25 | 2022-03-17 | 2022-05-02 | Underground | R15 | 2022-03-17 | 325 | 76 | 213 | 33 | 644 | 2019 | 2022 | R15
156397196810 | 156527810397 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2019-06-27 | 2019-06-27 | 2020-07-09 | 2021-03-10 | 2022-05-04 | Underground | R15 | 2021-03-10 | 1 | 271 | 175 | 301 | 745 | 2019 | 2022 | R15
153346197975 | 153278975346 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2019-11-15 | 2020-06-20 | 2020-07-22 | 2022-02-08 | 2022-03-01 | Overhead | R15 | 2022-02-08 | 156 | 23 | 405 | 16 | 598 | 2019 | 2022 | R15
159988190330 | 159927330988 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-10-29 | 2019-10-29 | 2020-05-08 | 2021-03-01 | 2021-04-01 | Underground | R15 | 2021-03-01 | 1 | 139 | 212 | 24 | 373 | 2019 | 2021 | R15
155948204880 | 158808880948 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-09-03 | 2019-10-04 | 2020-09-23 | 2021-05-03 | 2021-06-28 | Underground | R15 | 2021-05-03 | 24 | 254 | 159 | 41 | 475 | 2019 | 2021 | R15
159137173476 | 153348476137 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-08-02 | 2019-08-21 | 2019-12-04 | 2020-03-10 | 2020-09-15 | Underground | R15 | 2020-03-10 | 14 | 76 | 70 | 136 | 293 | 2019 | 2020 | R15
150655243326 | 150644326655 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential Subdivision | 2019-11-01 | 2019-11-01 | 2021-08-12 |  | 2022-06-20 | Underground | R15 | 2022-06-10 | 1 | 465 | 217 | 7 | 687 | 2019 | 2022 | R15
151718319108 | 155817108718 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-12-03 | 2019-12-03 | 2023-05-15 | 2023-06-19 | 2023-07-25 | Overhead | R15 | 2023-06-19 | 1 | 900 | 26 | 27 | 951 | 2019 | 2023 | R15
153085219908 | 156549908085 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2019-12-06 | 2020-02-27 | 2021-02-08 | 2021-03-18 | 2021-10-14 | Overhead | R15 | 2021-03-18 | 60 | 248 | 29 | 151 | 485 | 2019 | 2021 | R15
150537301579 | 152380579537 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | OH EXTENSION NON RESD OD | Commercial | 2022-01-18 | 2022-03-15 | 2022-11-29 | 2023-11-21 | 2023-12-20 | Overhead | R15 | 2023-11-21 | 41 | 186 | 256 | 22 | 502 | 2022 | 2023 | R15
153287191380 | 153407380287 | NON-RESIDENTIAL - LARGE RETAIL | UG EXT NON RES | Residential Subdivision | 2019-06-11 | 2019-06-12 | 2020-05-18 | 2020-08-19 | 2021-12-09 | Underground | R15 | 2020-08-19 | 2 | 244 | 68 | 342 | 653 | 2019 | 2021 | R15
154561216938 | 154579938561 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2019-10-03 | 2019-10-03 | 2021-01-13 | 2021-09-28 | 2021-10-18 | Underground | R15 | 2021-09-28 | 1 | 335 | 185 | 15 | 533 | 2019 | 2021 | R15
155961172970 | 158098970961 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-08-29 | 2019-08-30 | 2019-11-26 | 2020-02-14 | 2020-06-18 | Underground | R15 | 2020-02-14 | 2 | 63 | 59 | 90 | 211 | 2019 | 2020 | R15
159346192580 | 157301580346 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-10-16 | 2019-12-19 | 2020-05-28 | 2020-07-23 | 2020-09-23 | Overhead | R15 | 2020-07-23 | 47 | 116 | 41 | 45 | 246 | 2019 | 2020 | R15
159948208796 | 156413796948 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-10-11 | 2019-10-11 | 2020-10-29 | 2020-12-17 | 2021-02-04 | Underground | R15 | 2020-12-17 | 1 | 275 | 36 | 36 | 345 | 2019 | 2021 | R15
152871194646 | 158775646871 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-07-08 | 2019-07-08 | 2020-06-17 | 2020-11-20 | 2020-12-17 | Underground | R15 | 2020-11-20 | 1 | 248 | 113 | 20 | 379 | 2019 | 2020 | R15
155762187301 | 157106301762 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-10-15 | 2019-10-21 | 2020-04-13 | 2020-07-02 | 2020-11-04 | Underground | R15 | 2020-07-02 | 5 | 126 | 59 | 90 | 277 | 2019 | 2020 | R15
154121174072 | 151662072121 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2019-07-23 | 2019-07-23 | 2019-12-11 | 2020-01-25 | 2020-05-27 | Overhead | R15 | 2020-01-25 | 1 | 102 | 33 | 88 | 222 | 2019 | 2020 | R15
150573167403 | 151735403573 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2019-07-24 | 2019-07-24 | 2019-10-08 | 2019-12-03 | 2020-04-21 | Overhead | R15 | 2019-12-03 | 1 | 55 | 41 | 101 | 195 | 2019 | 2020 | R15
159681246226 | 159720226681 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-07-12 | 2019-07-12 | 2021-09-01 | 2022-10-31 | 2022-12-02 | Underground | R15 | 2022-10-31 | 1 | 559 | 304 | 25 | 886 | 2019 | 2022 | R15
151548262809 | 157394809548 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2019-08-26 | 2019-08-26 | 2021-12-29 | 2023-01-12 | 2023-03-06 | Underground | R15 | 2023-01-12 | 1 | 613 | 272 | 38 | 921 | 2019 | 2023 | R15
159056197327 | 157477327056 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Residential | 2019-08-26 | 2020-03-11 | 2020-07-14 | 2022-04-08 | 2023-01-31 | Underground | R15 | 2022-04-08 | 143 | 90 | 454 | 213 | 897 | 2019 | 2023 | R15
154498203916 | 154508916498 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2019-10-03 | 2019-10-03 | 2020-09-16 | 2021-05-28 | 2021-12-29 | Underground | R15 | 2021-05-28 | 1 | 250 | 183 | 154 | 585 | 2019 | 2021 | R15
157765182697 | 150362697765 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-10-30 | 2019-10-30 | 2020-03-02 | 2020-04-21 | 2020-11-11 | Underground | R15 | 2020-04-21 | 1 | 89 | 37 | 147 | 271 | 2019 | 2020 | R15
150147242117 | 152628117147 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Commercial | 2019-07-30 | 2019-07-30 | 2021-08-04 | 2022-05-02 | 2023-09-17 | Underground | R15 | 2022-05-02 | 1 | 527 | 194 | 360 | 1079 | 2019 | 2023 | R15
154424222500 | 154338500424 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential Subdivision | 2019-08-08 | 2020-05-18 | 2021-03-04 | 2022-08-25 | 2022-10-04 | Underground | R15 | 2022-08-25 | 203 | 209 | 386 | 29 | 824 | 2019 | 2022 | R15
158463180999 | 158746999463 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-07-08 | 2019-07-08 | 2020-02-19 | 2021-06-16 | 2021-07-13 | Underground | R15 | 2021-06-16 | 1 | 163 | 346 | 20 | 527 | 2019 | 2021 | R15
158188226780 | 158214780188 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-12-13 | 2019-12-13 | 2021-04-13 | 2021-10-26 | 2021-11-12 | Underground | R15 | 2021-10-26 | 1 | 348 | 141 | 14 | 501 | 2019 | 2021 | R15
158462218357 | 157845357462 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-12-11 | 2019-12-11 | 2021-01-26 | 2021-03-04 | 2021-11-29 | Underground | R15 | 2021-03-04 | 1 | 295 | 28 | 193 | 514 | 2019 | 2021 | R15
155891177877 | 150053877891 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-07-15 | 2019-08-07 | 2020-01-24 | 2020-08-24 | 2020-09-22 | Underground | R15 | 2020-08-24 | 18 | 123 | 152 | 22 | 312 | 2019 | 2020 | R15
155445221840 | 155439840445 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-06-21 | 2019-06-21 | 2021-02-26 | 2023-01-18 | 2022-07-25 | Underground | R15 | 2023-01-18 | 1 | 441 | 494 |  | 807 | 2019 | 2022 | R15
156933189687 | 159045687933 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-09-03 | 2019-10-21 | 2020-05-01 | 2020-07-15 | 2020-11-04 | Underground | R15 | 2020-07-15 | 35 | 140 | 54 | 81 | 307 | 2019 | 2020 | R15
153697173687 | 152793687697 | NON-RESIDENTIAL - SMALL RETAIL | UG EXT NON RES | Commercial | 2019-07-30 | 2019-07-30 | 2019-12-06 | 2020-06-19 | 2020-08-31 | Underground | R15 | 2020-06-19 | 1 | 94 | 141 | 52 | 285 | 2019 | 2020 | R15
158325187506 | 159417506325 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2019-10-26 | 2020-01-28 | 2020-04-14 | 2020-08-13 | 2020-11-04 | Overhead | R15 | 2020-08-13 | 67 | 56 | 88 | 60 | 268 | 2019 | 2020 | R15
156532196571 | 158754571532 | RESIDENTIAL - MULTI-FAMILY | OH RESD INDIVIDUAL OD | Residential | 2019-07-08 | 2019-12-10 | 2020-07-07 | 2020-07-07 | 2020-11-04 | Overhead | R15 | 2020-07-07 | 112 | 151 |  | 87 | 348 | 2019 | 2020 | R15
155449199493 | 153218493449 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2019-11-14 | 2020-05-22 | 2020-08-04 | 2021-02-10 | 2021-04-20 | Overhead | R15 | 2021-02-10 | 137 | 53 | 137 | 50 | 374 | 2019 | 2021 | R15
156481189925 | 156414925481 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2019-06-27 | 2019-06-27 | 2020-05-04 | 2020-11-13 | 2021-04-20 | Underground | R15 | 2020-11-13 | 1 | 223 | 140 | 113 | 474 | 2019 | 2021 | R15
158584215977 | 152204977584 | CUSTOMER UPGRADE IN SERVICE | UG R15 RES NON RES BUDG 225 | Residential | 2019-11-08 | 2020-12-21 | 2021-01-04 | 2021-04-14 | 2021-05-05 | Underground | R15 | 2021-04-14 | 292 | 11 | 73 | 16 | 389 | 2019 | 2021 | R15
157540239222 | 158577222540 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-07-17 | 2021-01-12 | 2021-07-15 | 2021-07-18 | 2021-07-21 | Overhead | R15 | 2021-07-18 | 128 | 133 | 2 | 3 | 264 | 2020 | 2021 | R15
153403166974 | 153404974403 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-04-15 | 2019-04-15 | 2019-10-05 | 2020-05-05 | 2020-05-08 | Overhead | R15 | 2020-05-05 | 1 | 125 | 152 | 4 | 280 | 2019 | 2020 | R15
150294204937 | 150315937294 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2019-03-28 | 2020-05-05 | 2020-09-25 | 2021-08-23 | 2022-02-09 | Underground | R15 | 2021-08-23 | 289 | 104 | 237 | 123 | 750 | 2019 | 2022 | R15
153162233178 | 157045178162 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2020-08-27 | 2020-08-27 | 2021-06-02 | 2022-03-01 | 2022-03-09 | Underground | R15 | 2022-03-01 | 1 | 200 | 195 | 7 | 400 | 2020 | 2022 | R15
153620307947 | 158048947620 | AGRICULTURAL | OH EXTENSION NON RESD OD | Commercial | 2021-01-19 | 2021-05-07 | 2023-02-01 | 2023-02-16 | 2023-03-06 | Overhead | R15 | 2023-02-16 | 79 | 454 | 12 | 13 | 555 | 2021 | 2023 | R15
156757263248 | 158894248757 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2021-01-22 | 2021-06-29 | 2022-01-03 | 2022-04-12 | 2022-08-27 | Underground | R15 | 2022-04-12 | 113 | 135 | 72 | 99 | 416 | 2021 | 2022 | R15
158751152636 | 159347636751 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-01-28 | 2019-03-21 | 2019-05-17 | 2019-08-28 | 2020-01-10 | Underground | R15 | 2019-08-28 | 39 | 42 | 74 | 98 | 250 | 2019 | 2020 | R15
158242212363 | 157205363242 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2020-08-28 | 2020-08-31 | 2020-12-01 | 2021-01-11 | 2022-03-28 | Overhead | R15 | 2021-01-11 | 2 | 67 | 30 | 316 | 412 | 2020 | 2022 | R15
155843239507 | 154437507843 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-09-29 | 2020-09-29 | 2021-07-20 | 2023-08-10 | 2023-08-21 | Underground | R15 | 2023-08-10 | 1 | 211 | 538 | 8 | 755 | 2020 | 2023 | R15
156563170929 | 157755929563 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-01-17 | 2019-01-17 | 2019-11-06 | 2020-07-30 | 2020-11-19 | Underground | R15 | 2020-07-30 | 1 | 210 | 192 | 81 | 481 | 2019 | 2020 | R15
155550220484 | 158722484550 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2020-07-17 | 2020-09-28 | 2021-02-12 |  | 2022-02-04 | Underground | R15 |  | 52 | 100 |  |  | 406 | 2020 | 2022 | R15
152888177904 | 156737904888 | CUSTOMER UPGRADE IN SERVICE | UG R15 RES NON RES BUDG 225 | Commercial | 2019-01-11 | 2019-01-11 | 2020-01-23 | 2020-10-21 | 2021-10-27 | Underground | R15 | 2020-10-21 | 1 | 270 | 195 | 266 | 729 | 2019 | 2021 | R15
151157246225 | 153666225157 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential | 2021-06-10 | 2021-06-12 | 2021-09-01 | 2022-10-05 | 2022-10-24 | Underground | R15 | 2022-10-05 | 2 | 58 | 286 | 14 | 358 | 2021 | 2022 | R15
151033273287 | 151115287033 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-07-14 | 2021-07-14 | 2022-03-21 | 2023-01-11 | 2023-01-25 | Underground | R15 | 2023-01-11 | 1 | 179 | 213 | 11 | 401 | 2021 | 2023 | R15
152813255770 | 158458770813 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-07-01 | 2021-07-21 | 2021-11-09 | 2021-11-24 | 2021-12-08 | Overhead | R15 | 2021-11-24 | 15 | 80 | 12 | 11 | 115 | 2021 | 2021 | R15
156041242205 | 158055205041 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-06-30 | 2021-06-30 | 2021-08-05 | 2021-08-11 | 2021-09-13 | Underground | R15 | 2021-08-11 | 1 | 27 | 5 | 24 | 54 | 2021 | 2021 | R15
159212288453 | 152633453212 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-07-21 | 2021-08-23 | 2022-08-10 | 2023-05-04 | 2023-11-30 | Underground | R15 | 2023-05-04 | 24 | 253 | 192 | 151 | 617 | 2021 | 2023 | R15
153714248772 | 155228772714 | AGRICULTURAL | OH EXTENSION NON RESD OD | Commercial | 2021-06-17 | 2021-06-17 | 2021-09-21 | 2021-09-28 | 2021-10-11 | Overhead | R15 | 2021-09-28 | 1 | 69 | 6 | 10 | 83 | 2021 | 2021 | R15
151194247681 | 158063681194 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Commercial | 2021-06-30 | 2021-06-30 | 2021-09-13 | 2022-05-09 | 2022-05-27 | Underground | R15 | 2022-05-09 | 1 | 54 | 171 | 15 | 238 | 2021 | 2022 | R15
158266219397 | 158287397266 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2020-03-26 | 2020-10-05 | 2021-02-04 | 2023-01-30 | 2023-02-27 | Underground | R15 | 2023-01-30 | 138 | 89 | 518 | 21 | 763 | 2020 | 2023 | R15
151362212375 | 152719375362 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-04-20 | 2020-04-20 | 2020-12-02 | 2020-12-16 | 2020-12-22 | Overhead | R15 | 2020-12-16 | 1 | 163 | 11 | 5 | 177 | 2020 | 2020 | R15
153958282867 | 158879867958 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Residential | 2020-03-30 | 2020-03-30 | 2022-06-16 | 2022-07-11 | 2023-02-10 | Overhead | R15 | 2022-07-11 | 1 | 579 | 18 | 155 | 750 | 2020 | 2023 | R15
152207219102 | 151382102207 | NON-RESIDENTIAL - SMALL RETAIL | UG EXT NON RES | Commercial | 2020-02-20 | 2020-02-25 | 2021-01-29 | 2021-05-12 | 2021-06-21 | Underground | R15 | 2021-05-12 | 4 | 244 | 74 | 29 | 348 | 2020 | 2021 | R15
157518195049 | 151053049518 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-04-10 | 2020-04-21 | 2020-06-23 | 2020-08-04 | 2020-11-04 | Underground | R15 | 2020-08-04 | 8 | 46 | 31 | 67 | 149 | 2020 | 2020 | R15
151353205568 | 159840568353 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2020-04-02 | 2020-04-07 | 2020-09-28 | 2022-07-19 | 2022-08-02 | Overhead | R15 | 2022-07-19 | 4 | 125 | 472 | 11 | 609 | 2020 | 2022 | R15
152244268238 | 153794238244 | FOREIGN UTILITY | OH EXTENSION NON RESD OD | Commercial | 2020-03-03 | 2020-10-26 | 2022-02-09 | 2022-09-01 | 2022-10-04 | Overhead | R15 | 2022-09-01 | 170 | 338 | 147 | 24 | 676 | 2020 | 2022 | R15
154703221130 | 155569130703 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Residential | 2020-03-11 | 2020-08-12 | 2021-02-19 | 2022-04-07 | 2022-05-02 | Underground | R15 | 2022-04-07 | 111 | 138 | 295 | 18 | 559 | 2020 | 2022 | R15
153695207199 | 157009199695 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2020-05-14 | 2020-06-01 | 2020-10-14 | 2020-11-23 | 2021-02-12 | Overhead | R15 | 2020-11-23 | 13 | 98 | 29 | 60 | 197 | 2020 | 2021 | R15
152900214468 | 155447468900 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2020-01-24 | 2020-04-21 | 2020-12-18 | 2021-11-24 | 2021-12-13 | Overhead | R15 | 2021-11-24 | 63 | 174 | 244 | 14 | 492 | 2020 | 2021 | R15
159188230027 | 150541027188 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2020-02-14 | 2020-11-06 | 2021-05-08 | 2023-10-10 | 2023-10-10 | Overhead | R15 | 2023-10-10 | 191 | 131 | 632 |  | 953 | 2020 | 2023 | R15
150012193876 | 157628876012 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-05-18 | 2020-05-18 | 2020-06-10 | 2020-09-10 | 2020-11-12 | Underground | R15 | 2020-09-10 | 1 | 18 | 67 | 46 | 129 | 2020 | 2020 | R15
152484251213 | 157250213484 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2020-07-10 | 2020-09-06 | 2021-10-08 | 2022-07-06 | 2022-07-19 | Overhead | R15 | 2022-07-06 | 41 | 285 | 194 | 10 | 528 | 2020 | 2022 | R15
150957262158 | 157063158957 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2020-03-19 | 2020-12-16 | 2021-12-21 | 2023-10-05 | 2023-11-07 | Underground | R15 | 2023-10-05 | 195 | 265 | 468 | 24 | 949 | 2020 | 2023 | R15
155280208180 | 159239180280 | FOREIGN UTILITY | UG EXT NON RES | Commercial | 2020-03-31 | 2020-04-17 | 2020-10-23 | 2021-08-20 | 2021-11-02 | Underground | R15 | 2021-08-20 | 14 | 136 | 216 | 53 | 416 | 2020 | 2021 | R15
150549210892 | 158148892549 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2020-03-25 | 2020-06-23 | 2020-11-17 | 2021-06-08 | 2021-12-29 | Overhead | R15 | 2021-06-08 | 65 | 106 | 146 | 147 | 461 | 2020 | 2021 | R15
155480198796 | 159155796480 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-02-11 | 2020-06-10 | 2020-07-29 | 2022-02-22 | 2022-03-23 | Overhead | R15 | 2022-02-22 | 87 | 36 | 410 | 22 | 552 | 2020 | 2022 | R15
157944254498 | 157945498944 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-02-04 | 2021-02-10 | 2021-11-02 | 2023-06-26 | 2023-07-21 | Underground | R15 | 2023-06-26 | 267 | 190 | 430 | 20 | 904 | 2020 | 2023 | R15
151503217605 | 159700605503 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-05-29 | 2020-06-23 | 2021-01-19 | 2021-08-30 | 2021-09-30 | Underground | R15 | 2021-08-30 | 18 | 151 | 160 | 24 | 350 | 2020 | 2021 | R15
158102203832 | 154460832102 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-03-05 | 2020-08-14 | 2020-09-15 | 2020-10-15 | 2020-11-10 | Underground | R15 | 2020-10-15 | 117 | 23 | 23 | 19 | 179 | 2020 | 2020 | R15
150357206422 | 154916422357 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-06-29 | 2020-08-17 | 2020-10-06 | 2020-11-04 | 2021-01-28 | Overhead | R15 | 2020-11-04 | 36 | 37 | 22 | 62 | 154 | 2020 | 2021 | R15
153045230776 | 151395776045 | NON-RESIDENTIAL - SMALL OFFICE | UG EXT NON RES | Commercial | 2020-04-13 | 2020-10-21 | 2021-05-14 | 2021-08-03 | 2023-11-17 | Underground | R15 | 2021-08-03 | 138 | 148 | 58 | 599 | 940 | 2020 | 2023 | R15
158051195048 | 158008048051 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-02-05 | 2020-02-05 | 2020-06-23 | 2020-07-08 | 2020-07-08 | Overhead | R15 | 2020-07-08 | 1 | 100 | 12 |  | 111 | 2020 | 2020 | R15
153438238492 | 156137492438 | NON-RESIDENTIAL - LODGING | UG EXT NON RES | Commercial | 2020-05-08 | 2021-02-25 | 2021-07-12 | 2022-06-23 | 2022-07-25 | Underground | R15 | 2022-06-23 | 210 | 98 | 249 | 23 | 577 | 2020 | 2022 | R15
155242226420 | 155243420242 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-01-22 | 2020-01-22 | 2021-04-09 | 2021-10-02 | 2021-10-05 | Overhead | R15 | 2021-10-02 | 1 | 318 | 126 | 2 | 445 | 2020 | 2021 | R15
155501208448 | 154868448501 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential Subdivision | 2020-05-01 | 2020-05-01 | 2020-10-26 | 2022-10-12 | 2022-11-01 | Underground | R15 | 2022-10-12 | 1 | 127 | 513 | 15 | 653 | 2020 | 2022 | R15
157284200024 | 159104024284 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-03-30 | 2020-06-15 | 2020-08-07 | 2020-10-01 | 2020-11-10 | Underground | R15 | 2020-10-01 | 56 | 40 | 40 | 29 | 162 | 2020 | 2020 | R15
155969199335 | 152286335969 | AGRICULTURAL | OH EXTENSION NON RESD OD | Commercial | 2020-06-15 | 2020-06-30 | 2020-08-03 | 2020-08-20 | 2021-01-04 | Overhead | R15 | 2020-08-20 | 12 | 25 | 14 | 98 | 146 | 2020 | 2021 | R15
153700208136 | 151220136700 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Commercial | 2020-06-08 | 2020-08-29 | 2020-10-23 | 2020-11-06 | 2021-03-13 | Underground | R15 | 2020-11-06 | 60 | 40 | 11 | 91 | 200 | 2020 | 2021 | R15
153370225468 | 154894468370 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-06-29 | 2020-08-14 | 2021-04-01 | 2021-04-22 | 2021-06-14 | Overhead | R15 | 2021-04-22 | 35 | 165 | 16 | 38 | 251 | 2020 | 2021 | R15
157254235333 | 153240333254 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-06-18 | 2020-09-23 | 2021-06-18 | 2021-11-17 | 2021-12-02 | Underground | R15 | 2021-11-17 | 70 | 193 | 109 | 12 | 381 | 2020 | 2021 | R15
151722209306 | 158042306722 | NON-RESIDENTIAL - SMALL RETAIL | UG EXT NON RES | Commercial | 2020-03-24 | 2020-07-08 | 2020-11-02 | 2021-07-14 | 2021-12-01 | Underground | R15 | 2021-07-14 | 77 | 84 | 183 | 101 | 442 | 2020 | 2021 | R15
157628221605 | 157837605628 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-02-04 | 2020-06-25 | 2021-02-24 | 2021-06-03 | 2021-09-21 | Underground | R15 | 2021-06-03 | 103 | 175 | 72 | 79 | 426 | 2020 | 2021 | R15
153464195272 | 156981272464 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-05-13 | 2020-05-13 | 2020-06-24 | 2021-02-14 | 2021-02-17 | Overhead | R15 | 2021-02-14 | 1 | 31 | 168 | 3 | 201 | 2020 | 2021 | R15
154315202602 | 152306602315 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-01-09 | 2020-03-12 | 2020-09-02 | 2020-11-09 | 2021-02-23 | Underground | R15 | 2020-11-09 | 46 | 125 | 49 | 77 | 294 | 2020 | 2021 | R15
157588209611 | 150696611588 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-06-05 | 2020-07-06 | 2020-11-04 | 2021-08-11 | 2021-09-13 | Underground | R15 | 2021-08-11 | 22 | 88 | 201 | 24 | 332 | 2020 | 2021 | R15
151845261690 | 153176690845 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-02-28 | 2020-12-01 | 2021-12-17 | 2022-06-17 | 2022-07-08 | Underground | R15 | 2022-06-17 | 198 | 274 | 131 | 16 | 616 | 2020 | 2022 | R15
156949196584 | 156780584949 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2020-01-30 | 2020-02-03 | 2020-07-06 | 2020-11-09 | 2020-12-09 | Overhead | R15 | 2020-11-09 | 3 | 111 | 91 | 23 | 225 | 2020 | 2020 | R15
158863211672 | 157456672863 | RESIDENTIAL - MULTI-FAMILY | OH RESD INDIVIDUAL OD | Residential | 2020-07-13 | 2020-07-19 | 2020-11-24 | 2020-12-21 | 2021-02-18 | Overhead | R15 | 2020-12-21 | 5 | 92 | 20 | 44 | 159 | 2020 | 2021 | R15
150636253955 | 152297955636 | SPECIAL FACILITIES / ALTERNATE SERVICE | UG R15 SPECIAL FAC | Commercial | 2020-06-15 | 2020-12-10 | 2021-10-27 | 2022-05-12 | 2022-06-13 | Underground | R15 | 2022-05-12 | 129 | 230 | 142 | 23 | 521 | 2020 | 2022 | R15
158229274024 | 158234024229 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2020-02-05 | 2021-07-13 | 2022-03-28 | 2024-01-12 | 2022-12-01 | Underground | R15 | 2024-01-12 | 375 | 185 | 470 |  | 737 | 2020 | 2022 | R15
152504189344 | 152600344504 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-02-26 | 2020-03-02 | 2020-04-29 | 2021-02-02 | 2021-04-20 | Underground | R15 | 2021-02-02 | 4 | 43 | 200 | 56 | 300 | 2020 | 2021 | R15
158700194953 | 156008953700 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2020-05-07 | 2020-05-07 | 2020-06-22 | 2020-09-29 | 2020-11-09 | Overhead | R15 | 2020-09-29 | 1 | 33 | 72 | 30 | 133 | 2020 | 2020 | R15
152914189230 | 150944230914 | NON-RESIDENTIAL - MISCELLANEOUS | UG DEV NON RES | Commercial | 2020-01-03 | 2020-01-03 | 2020-04-27 | 2020-11-24 | 2021-01-12 | Underground | R15 | 2020-11-24 | 1 | 82 | 152 | 36 | 268 | 2020 | 2021 | R15
158105214470 | 159839470105 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-12-23 | 2019-12-23 | 2020-12-18 | 2021-10-28 | 2022-01-04 | Underground | R15 | 2021-10-28 | 1 | 260 | 225 | 49 | 532 | 2019 | 2022 | R15
156111252844 | 156023844111 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-07-06 | 2020-07-06 | 2021-10-19 | 2022-01-24 | 2022-03-23 | Underground | R15 | 2022-01-24 | 1 | 337 | 70 | 43 | 448 | 2020 | 2022 | R15
150307300653 | 154633653307 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-09-10 | 2021-09-10 | 2022-11-15 | 2023-03-29 | 2023-05-05 | Underground | R15 | 2023-03-29 | 1 | 308 | 97 | 28 | 431 | 2021 | 2023 | R15
150731323273 | 159944273731 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG RES INDIVIDUAL | Residential | 2022-12-28 | 2023-02-14 | 2023-06-27 | 2023-09-27 | 2023-10-24 | Underground | R15 | 2023-09-27 | 35 | 96 | 67 | 20 | 215 | 2022 | 2023 | R15
151153276433 | 154594433153 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2021-09-10 | 2021-09-10 | 2022-04-20 | 2022-07-30 | 2022-10-25 | Overhead | R15 | 2022-07-30 | 1 | 159 | 73 | 62 | 293 | 2021 | 2022 | R15
151153276433 | 154594433153 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-09-10 | 2021-09-10 | 2022-04-20 | 2022-07-30 | 2022-10-25 | Underground | R15 | 2022-07-30 | 1 | 159 | 73 | 62 | 293 | 2021 | 2022 | R15
159625299424 | 159657424625 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Commercial | 2021-08-18 | 2021-08-18 | 2022-11-03 | 2023-06-15 | 2023-09-11 | Underground | R15 | 2023-06-15 | 1 | 317 | 161 | 63 | 539 | 2021 | 2023 | R15
152256327829 | 150251829256 | NON-RESIDENTIAL - SMALL RETAIL | UG EXT NON RES | Commercial | 2023-07-11 | 2023-07-11 | 2023-08-09 |  | 2023-09-20 | Underground | R15 |  | 1 | 22 |  |  | 52 | 2023 | 2023 | R15
152216311313 | 154422313216 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2023-01-18 | 2023-01-18 | 2023-03-03 | 2023-05-17 | 2023-08-23 | Underground | R15 | 2023-05-17 | 1 | 33 | 54 | 71 | 156 | 2023 | 2023 | R15
156804314881 | 150377881804 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2023-02-14 | 2023-03-22 | 2023-04-05 | 2023-05-30 | 2023-07-03 | Overhead | R15 | 2023-05-30 | 27 | 11 | 40 | 25 | 100 | 2023 | 2023 | R15
158665295960 | 154709960665 | CUSTOMER UPGRADE IN SERVICE | UG EXT NON RES | Commercial | 2021-07-29 | 2022-05-17 | 2022-10-04 | 2023-10-17 | 2023-12-12 | Underground | R15 | 2023-10-17 | 209 | 101 | 271 | 41 | 619 | 2021 | 2023 | R15
150007315441 | 157937441007 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2023-02-02 | 2023-02-02 | 2023-04-11 |  | 2023-09-29 | Overhead | R15 |  | 1 | 49 |  |  | 172 | 2023 | 2023 | R15
153381268996 | 156614996381 | SPECIAL FACILITIES / ALTERNATE SERVICE | UG R15 SPECIAL FAC | Commercial | 2021-08-06 | 2021-08-06 | 2022-02-15 | 2022-04-21 | 2022-05-13 | Underground | R15 | 2022-04-21 | 1 | 138 | 48 | 17 | 201 | 2021 | 2022 | R15
152894325702 | 157532702894 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG RES INDIVIDUAL | Residential | 2022-12-12 | 2022-12-12 | 2023-07-20 | 2023-08-25 | 2023-11-28 | Underground | R15 | 2023-08-25 | 1 | 159 | 27 | 68 | 252 | 2022 | 2023 | R15
150307281897 | 154631897307 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2021-09-10 | 2021-09-10 | 2022-06-08 | 2022-11-21 | 2022-12-06 | Underground | R15 | 2022-11-21 | 1 | 194 | 119 | 12 | 323 | 2021 | 2022 | R15
150307281896 | 154459896307 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2021-09-10 | 2021-09-10 | 2022-06-08 | 2022-11-17 | 2022-11-22 | Underground | R15 | 2022-11-17 | 1 | 194 | 117 | 4 | 313 | 2021 | 2022 | R15
154826290531 | 155320531826 | Affordable Housing | UG DEV RES | Residential | 2021-08-02 | 2022-04-21 | 2023-01-30 | 2023-10-20 | 2023-09-30 | Underground | R15 | 2023-10-20 | 189 | 203 | 190 |  | 565 | 2021 | 2023 | R15
156726280491 | 154344491726 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-09-09 | 2021-09-09 | 2022-05-24 | 2022-07-05 | 2022-07-25 | Overhead | R15 | 2022-07-05 | 1 | 184 | 31 | 15 | 228 | 2021 | 2022 | R15
153162280541 | 154849541162 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential | 2022-03-09 | 2022-03-21 | 2022-05-23 | 2022-08-03 | 2022-08-12 | Underground | R15 | 2022-08-03 | 9 | 46 | 53 | 8 | 113 | 2022 | 2022 | R15
158244284330 | 155186330244 | Affordable Housing | OH RESD INDIVIDUAL OD | Residential | 2022-01-28 | 2022-01-28 | 2022-07-01 | 2022-10-14 | 2022-12-12 | Overhead | R15 | 2022-10-14 | 1 | 111 | 76 | 42 | 227 | 2022 | 2022 | R15
150189298293 | 152971293189 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2022-05-10 | 2022-05-13 | 2022-10-26 | 2023-06-15 | 2023-07-25 | Overhead | R15 | 2023-06-15 | 4 | 119 | 167 | 29 | 316 | 2022 | 2023 | R15
151701300626 | 151618626701 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2022-02-24 | 2022-02-24 | 2022-11-15 | 2023-08-24 | 2023-09-13 | Underground | R15 | 2023-08-24 | 1 | 189 | 203 | 15 | 405 | 2022 | 2023 | R15
158321313148 | 158504148321 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential Subdivision | 2021-09-28 | 2021-09-28 | 2023-03-20 | 2023-06-29 | 2023-07-21 | Underground | R15 | 2023-06-29 | 1 | 385 | 74 | 17 | 474 | 2021 | 2023 | R15
152525288367 | 151878367525 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2022-04-13 | 2022-04-13 | 2022-08-09 | 2023-06-26 | 2023-07-21 | Underground | R15 | 2023-06-26 | 1 | 85 | 230 | 20 | 333 | 2022 | 2023 | R15
153975277421 | 158221421975 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-11-08 | 2022-03-01 | 2022-04-27 | 2022-05-06 | 2023-02-03 | Underground | R15 | 2022-05-06 | 82 | 42 | 8 | 196 | 325 | 2021 | 2023 | R15
152150298282 | 154357282150 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential Subdivision | 2022-01-26 | 2022-02-24 | 2022-10-26 | 2022-12-24 | 2023-11-30 | Underground | R15 | 2022-12-24 | 22 | 175 | 43 | 244 | 482 | 2022 | 2023 | R15
151282308877 | 157600877282 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Residential | 2022-06-01 | 2022-06-01 | 2023-02-09 | 2023-07-24 | 2023-08-16 | Overhead | R15 | 2023-07-24 | 1 | 182 | 118 | 18 | 316 | 2022 | 2023 | R15
152698281934 | 154760934698 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-10-24 | 2021-10-25 | 2022-06-08 | 2022-11-02 | 2022-11-22 | Underground | R15 | 2022-11-02 | 1 | 163 | 106 | 15 | 282 | 2021 | 2022 | R15
150147308935 | 154772935147 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Commercial | 2022-01-27 | 2022-01-27 | 2023-02-09 | 2023-08-07 | 2023-08-24 | Underground | R15 | 2023-08-07 | 1 | 271 | 128 | 14 | 411 | 2022 | 2023 | R15
153678304829 | 153702829678 | Affordable Housing | OH RESD INDIVIDUAL OD | Residential | 2022-04-23 | 2022-04-23 | 2023-01-05 | 2023-01-05 | 2023-03-21 | Overhead | R15 | 2023-01-05 | 0 | 184 |  | 54 | 237 | 2022 | 2023 | R15
156821278641 | 150828641821 | RESIDENTIAL - MULTI-FAMILY | OH DEVELOPMENT RESD OD | Residential | 2021-10-08 | 2022-01-28 | 2022-05-09 | 2022-05-31 | 2022-07-01 | Overhead | R15 | 2022-05-31 | 81 | 72 | 17 | 24 | 191 | 2021 | 2022 | R15
151633308459 | 151427459633 | Affordable Housing | UG DEV RES | Residential | 2022-06-20 | 2022-07-06 | 2023-02-06 |  | 2023-12-22 | Underground | R15 |  | 13 | 154 |  |  | 395 | 2022 | 2023 | R15
154355269008 | 153478008355 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2022-01-22 | 2022-01-22 | 2022-02-15 | 2022-03-07 | 2023-10-04 | Overhead | R15 | 2022-03-07 | 0 | 17 | 15 | 413 | 443 | 2022 | 2023 | R15
158858290877 | 156017877858 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Residential | 2021-12-15 | 2022-01-07 | 2022-09-01 | 2022-10-27 | 2022-11-23 | Overhead | R15 | 2022-10-27 | 18 | 170 | 41 | 20 | 246 | 2021 | 2022 | R15
158188281958 | 159577958188 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2022-03-31 | 2022-04-26 | 2022-06-08 | 2023-06-29 | 2023-10-26 | Underground | R15 | 2023-06-29 | 19 | 32 | 277 | 86 | 411 | 2022 | 2023 | R15
152450313385 | 154116385450 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential Subdivision | 2022-01-25 | 2022-01-25 | 2023-03-22 | 2023-06-23 | 2023-11-30 | Underground | R15 | 2023-06-23 | 1 | 302 | 68 | 115 | 483 | 2022 | 2023 | R15
153770289857 | 153724857770 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2021-10-20 | 2022-02-09 | 2022-08-22 | 2022-12-16 | 2023-01-13 | Overhead | R15 | 2022-12-16 | 81 | 139 | 85 | 21 | 323 | 2021 | 2023 | R15
158918281102 | 156513102918 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-11-02 | 2021-11-18 | 2022-05-31 | 2022-12-19 | 2023-01-18 | Underground | R15 | 2022-12-19 | 13 | 139 | 145 | 23 | 317 | 2021 | 2023 | R15
151311301547 | 154600547311 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-10-22 | 2021-12-03 | 2022-11-28 | 2022-12-16 | 2023-01-06 | Underground | R15 | 2022-12-16 | 31 | 257 | 15 | 16 | 316 | 2021 | 2023 | R15
156647286494 | 157405494647 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2022-02-07 | 2022-03-03 | 2022-07-22 | 2023-01-26 | 2023-03-20 | Overhead | R15 | 2023-01-26 | 19 | 102 | 135 | 38 | 291 | 2022 | 2023 | R15
158580297225 | 158474225580 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential Subdivision | 2022-07-22 | 2022-07-22 | 2022-10-17 | 2023-06-07 | 2023-07-03 | Underground | R15 | 2023-06-07 | 1 | 62 | 168 | 19 | 247 | 2022 | 2023 | R15
154872287302 | 154892302872 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2021-12-09 | 2021-12-09 | 2022-07-28 | 2023-05-30 | 2023-06-28 | Underground | R15 | 2023-05-30 | 1 | 166 | 219 | 22 | 405 | 2021 | 2023 | R15
158621271075 | 152980075621 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Commercial | 2022-03-02 | 2022-03-02 | 2022-03-02 | 2022-03-03 | 2022-03-23 | Underground | R15 | 2022-03-03 | 1 |  | 2 | 15 | 16 | 2022 | 2022 | R15
158370280813 | 158334813370 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2022-02-10 | 2022-02-10 | 2022-05-26 | 2022-10-07 | 2022-10-11 | Overhead | R15 | 2022-10-07 | 1 | 76 | 97 | 3 | 174 | 2022 | 2022 | R15
158592299910 | 158664910592 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-09-28 | 2021-09-28 | 2022-11-09 |  | 2023-11-30 | Underground | R15 |  | 1 | 292 |  |  | 568 | 2021 | 2023 | R15
150236297308 | 159040308236 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2022-05-03 | 2022-08-17 | 2022-10-17 | 2023-03-01 | 2023-03-30 | Overhead | R15 | 2023-03-01 | 77 | 44 | 98 | 22 | 238 | 2022 | 2023 | R15
155402323783 | 154332783402 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential Subdivision | 2022-04-26 | 2022-04-26 | 2023-06-29 | 2023-10-05 | 2023-10-23 | Underground | R15 | 2023-10-05 | 1 | 308 | 71 | 13 | 390 | 2022 | 2023 | R15
153108313382 | 154035382108 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2022-01-25 | 2022-01-25 | 2023-03-22 | 2023-07-12 | 2023-08-23 | Underground | R15 | 2023-07-12 | 1 | 302 | 81 | 31 | 412 | 2022 | 2023 | R15
152350275911 | 159471911350 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2022-02-15 | 2022-03-01 | 2022-04-15 | 2022-06-29 | 2022-07-22 | Underground | R15 | 2022-06-29 | 11 | 34 | 54 | 18 | 114 | 2022 | 2022 | R15
155295276977 | 153824977295 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2021-12-06 | 2022-01-24 | 2022-04-25 | 2022-05-24 | 2022-06-13 | Overhead | R15 | 2022-05-24 | 36 | 66 | 22 | 15 | 136 | 2021 | 2022 | R15
150147279832 | 154706832147 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Commercial | 2022-03-09 | 2022-03-09 | 2022-05-18 | 2022-07-13 | 2022-07-25 | Underground | R15 | 2022-07-13 | 1 | 51 | 41 | 9 | 99 | 2022 | 2022 | R15
158186290335 | 154241335186 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2022-05-16 | 2022-05-16 | 2022-08-26 | 2022-09-12 | 2022-10-05 | Overhead | R15 | 2022-09-12 | 1 | 75 | 12 | 18 | 103 | 2022 | 2022 | R15
159926289414 | 155108414926 | NON-RESIDENTIAL - LARGE RETAIL | UG EXT NON RES | Commercial | 2021-10-26 | 2021-10-26 | 2022-08-17 | 2022-11-16 | 2022-11-22 | Underground | R15 | 2022-11-16 | 1 | 212 | 66 | 5 | 281 | 2021 | 2022 | R15
157509290348 | 154311348509 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2022-01-26 | 2022-08-03 | 2022-08-26 | 2022-10-10 | 2022-10-13 | Overhead | R15 | 2022-10-10 | 136 | 18 | 32 | 4 | 187 | 2022 | 2022 | R15
159970263428 | 152722428970 | GENERAL/OTHER | OH EXTENSION NON RESD OD | Residential | 2021-11-30 | 2021-11-30 | 2022-01-04 | 2022-01-06 | 2022-01-17 | Overhead | R15 | 2022-01-06 | 1 | 26 | 3 | 8 | 35 | 2021 | 2022 | R15
153164295068 | 152571068164 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2022-01-19 | 2022-02-16 | 2022-09-27 | 2022-12-20 | 2023-01-18 | Overhead | R15 | 2022-12-20 | 21 | 160 | 61 | 22 | 261 | 2022 | 2023 | R15
152345290386 | 152688386345 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2022-01-19 | 2022-02-11 | 2022-08-26 | 2023-05-17 | 2023-06-01 | Underground | R15 | 2023-05-17 | 18 | 141 | 189 | 12 | 357 | 2022 | 2023 | R15
151237314497 | 155007497237 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2022-08-19 | 2022-10-24 | 2023-04-03 | 2023-05-22 | 2023-07-28 | Overhead | R15 | 2023-05-22 | 47 | 116 | 36 | 50 | 246 | 2022 | 2023 | R15
154013319311 | 150140311013 | Affordable Housing | OH RESD INDIVIDUAL OD | Residential | 2022-07-28 | 2022-10-25 | 2023-05-16 | 2023-06-14 | 2023-08-16 | Overhead | R15 | 2023-06-14 | 64 | 146 | 22 | 46 | 275 | 2022 | 2023 | R15
151532318015 | 158470015532 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG RES INDIVIDUAL | Commercial | 2022-10-20 | 2023-02-10 | 2023-05-05 | 2023-07-27 | 2023-08-24 | Underground | R15 | 2023-07-27 | 82 | 61 | 60 | 21 | 221 | 2022 | 2023 | R15
150154316748 | 152758748154 | CUSTOMER UPGRADE IN SERVICE | UG R15 RES NON RES BUDG 225 | Commercial | 2022-11-11 | 2022-11-11 | 2023-04-24 | 2023-06-12 | 2023-07-21 | Underground | R15 | 2023-06-12 | 1 | 117 | 36 | 30 | 181 | 2022 | 2023 | R15
159053161441 | 159054441053 | CUSTOMER UPGRADE IN SERVICE | UG R15 RES NON RES BUDG 225 | Commercial | 2019-01-25 | 2019-01-30 | 2019-08-16 | 2020-09-01 | 2020-11-16 | Underground | R15 | 2020-09-01 | 4 | 143 | 273 | 55 | 472 | 2019 | 2020 | R15
156041239231 | 154334231041 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-05-10 | 2021-06-08 | 2021-07-16 | 2021-10-22 | 2021-11-16 | Underground | R15 | 2021-10-22 | 22 | 29 | 71 | 18 | 137 | 2021 | 2021 | R15
157469251022 | 157477022469 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-08-28 | 2020-08-28 | 2021-10-06 | 2023-06-08 | 2023-07-03 | Underground | R15 | 2023-06-08 | 1 | 289 | 437 | 18 | 742 | 2020 | 2023 | R15
158882224649 | 158722649882 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential Subdivision | 2019-05-14 | 2019-05-14 | 2021-03-24 | 2022-09-06 | 2022-09-23 | Underground | R15 | 2022-09-06 | 1 | 487 | 380 | 14 | 879 | 2019 | 2022 | R15
152350228893 | 152372893350 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-02-05 | 2021-04-06 | 2021-04-30 | 2021-05-19 | 2021-06-21 | Underground | R15 | 2021-05-19 | 43 | 19 | 14 | 24 | 97 | 2021 | 2021 | R15
150147266250 | 159659250147 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-04-21 | 2021-04-21 | 2023-01-10 | 2023-01-12 | 2022-10-03 | Underground | R15 | 2023-01-12 | 1 | 450 | 3 |  | 379 | 2021 | 2022 | R15
151246249025 | 152280025246 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2020-09-21 | 2020-09-21 | 2021-09-22 | 2021-12-28 | 2022-02-04 | Overhead | R15 | 2021-12-28 | 1 | 263 | 70 | 29 | 360 | 2020 | 2022 | R15
150189267055 | 150192055189 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2020-12-10 | 2021-07-26 | 2022-02-01 |  | 2022-08-26 | Underground | R15 |  | 163 | 137 |  |  | 447 | 2020 | 2022 | R15
159978213562 | 159979562978 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-07-24 | 2020-07-24 | 2020-12-10 | 2021-01-10 | 2021-07-26 | Underground | R15 | 2021-01-10 | 1 | 100 | 22 | 141 | 262 | 2020 | 2021 | R15
153461254836 | 159587836461 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-07-22 | 2020-07-22 | 2021-11-03 | 2022-09-15 | 2023-02-21 | Underground | R15 | 2022-09-15 | 1 | 336 | 227 | 114 | 675 | 2020 | 2023 | R15
153010304101 | 153057101010 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-03-24 | 2021-03-24 | 2022-12-27 | 2023-08-16 | 2023-08-24 | Underground | R15 | 2023-08-16 | 1 | 460 | 167 | 7 | 632 | 2021 | 2023 | R15
156331302113 | 150066113331 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Residential | 2021-04-23 | 2021-07-29 | 2022-12-02 | 2023-06-20 | 2023-07-25 | Underground | R15 | 2023-06-20 | 70 | 352 | 143 | 26 | 588 | 2021 | 2023 | R15
156151243930 | 156855930151 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-01-14 | 2021-01-14 | 2021-08-16 | 2023-01-25 | 2023-02-22 | Underground | R15 | 2023-01-25 | 1 | 153 | 378 | 21 | 550 | 2021 | 2023 | R15
158272149782 | 153468782272 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-02-14 | 2019-03-06 | 2019-04-19 | 2019-08-22 | 2020-01-10 | Overhead | R15 | 2019-08-22 | 15 | 33 | 90 | 102 | 237 | 2019 | 2020 | R15
155629245624 | 157771624629 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential | 2021-03-02 | 2021-05-26 | 2021-08-27 | 2022-06-10 | 2022-06-23 | Underground | R15 | 2022-06-10 | 62 | 68 | 206 | 10 | 343 | 2021 | 2022 | R15
151880245884 | 151863884880 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-04-30 | 2021-04-30 | 2021-08-30 | 2022-04-28 | 2022-05-23 | Underground | R15 | 2022-04-28 | 1 | 87 | 174 | 18 | 277 | 2021 | 2022 | R15
154210221016 | 155920016210 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2020-10-05 | 2020-12-14 | 2021-02-22 | 2021-06-25 | 2022-08-08 | Overhead | R15 | 2021-06-25 | 51 | 51 | 90 | 292 | 481 | 2020 | 2022 | R15
154498278176 | 154408176498 | Electric Vehicle | UG EXT NON RES | Commercial | 2021-05-11 | 2021-05-11 | 2022-05-04 | 2022-11-10 | 2022-12-09 | Underground | R15 | 2022-11-10 | 1 | 257 | 137 | 22 | 414 | 2021 | 2022 | R15
153045230880 | 159316880045 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2020-10-21 | 2021-01-24 | 2021-05-14 | 2021-08-03 | 2021-08-25 | Overhead | R15 | 2021-08-03 | 68 | 80 | 58 | 17 | 221 | 2020 | 2021 | R15
152945168302 | 155319302945 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-04-25 | 2019-08-22 | 2019-10-15 | 2020-04-16 | 2020-06-11 | Underground | R15 | 2020-04-16 | 86 | 39 | 133 | 41 | 296 | 2019 | 2020 | R15
151430231282 | 157221282430 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2020-11-25 | 2020-11-25 | 2021-05-18 | 2021-06-02 | 2021-07-21 | Overhead | R15 | 2021-06-02 | 1 | 125 | 12 | 36 | 171 | 2020 | 2021 | R15
156015250093 | 156418093015 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-01-12 | 2021-01-12 | 2021-09-30 |  | 2022-03-23 | Underground | R15 |  | 1 | 188 |  |  | 312 | 2021 | 2022 | R15
154651252034 | 154723034651 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2021-01-05 | 2021-03-04 | 2021-10-14 | 2021-10-27 | 2021-11-16 | Overhead | R15 | 2021-10-27 | 43 | 161 | 10 | 15 | 226 | 2021 | 2021 | R15
159528297083 | 159515083528 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-12-09 | 2020-12-09 | 2022-10-14 | 2023-08-25 | 2023-09-20 | Underground | R15 | 2023-08-25 | 1 | 483 | 226 | 19 | 726 | 2020 | 2023 | R15
152860232232 | 153570232860 | FOREIGN UTILITY | OH EXTENSION NON RESD OD | Commercial | 2020-09-25 | 2020-11-16 | 2021-05-25 | 2021-06-02 | 2021-09-28 | Overhead | R15 | 2021-06-02 | 37 | 137 | 7 | 85 | 263 | 2020 | 2021 | R15
151194236247 | 158221247194 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2021-04-15 | 2021-04-20 | 2021-06-22 | 2022-01-21 | 2022-02-03 | Underground | R15 | 2022-01-21 | 4 | 46 | 154 | 10 | 211 | 2021 | 2022 | R15
152489267157 | 154722157489 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG RES INDIVIDUAL | Residential | 2021-02-17 | 2021-07-12 | 2022-02-02 | 2023-02-14 | 2023-09-05 | Underground | R15 | 2023-02-14 | 104 | 148 | 270 | 146 | 665 | 2021 | 2023 | R15
158432279831 | 150817831432 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-03-16 | 2021-03-17 | 2022-05-18 | 2023-05-02 | 2023-06-09 | Underground | R15 | 2023-05-02 | 2 | 306 | 250 | 29 | 584 | 2021 | 2023 | R15
159852264323 | 152331323852 | CUSTOMER UPGRADE IN SERVICE | UG EXT NON RES | Commercial | 2021-03-22 | 2021-03-22 | 2022-01-11 | 2022-02-10 | 2022-04-01 | Underground | R15 | 2022-02-10 | 1 | 212 | 23 | 37 | 270 | 2021 | 2022 | R15
155788278043 | 153404043788 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-05-06 | 2021-05-06 | 2022-05-03 | 2022-05-13 | 2022-06-22 | Overhead | R15 | 2022-05-13 | 1 | 259 | 9 | 29 | 295 | 2021 | 2022 | R15
153924157370 | 150820370924 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-05-24 | 2019-06-11 | 2019-07-10 | 2020-06-08 | 2021-11-12 | Underground | R15 | 2020-06-08 | 13 | 22 | 239 | 375 | 646 | 2019 | 2021 | R15
150189254619 | 150190619189 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2020-12-10 | 2021-07-21 | 2021-11-02 | 2022-02-08 | 2022-03-08 | Underground | R15 | 2022-02-08 | 160 | 75 | 71 | 21 | 324 | 2020 | 2022 | R15
150189266309 | 150191309189 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential Subdivision | 2020-12-10 | 2021-10-05 | 2022-01-27 | 2022-07-18 | 2022-08-02 | Underground | R15 | 2022-07-18 | 214 | 83 | 123 | 12 | 429 | 2020 | 2022 | R15
159982171650 | 150723650982 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-03-30 | 2019-03-30 | 2019-11-13 | 2020-09-25 | 2020-12-23 | Underground | R15 | 2020-09-25 | 0 | 163 | 228 | 64 | 453 | 2019 | 2020 | R15
157581278394 | 159325394581 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2021-03-09 | 2021-09-16 | 2022-05-05 |  | 2022-09-07 | Overhead | R15 | 2022-09-12 | 138 | 166 | 93 |  | 392 | 2021 | 2022 | R15
157351252678 | 152981678351 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2020-12-22 | 2021-05-10 | 2021-10-19 | 2022-04-16 | 2023-09-20 | Underground | R15 | 2022-04-16 | 100 | 117 | 129 | 373 | 717 | 2020 | 2023 | R15
157796285444 | 157739444796 | Electric Vehicle | UG EXT NON RES | Commercial | 2021-03-02 | 2021-03-02 | 2022-07-12 | 2023-05-24 | 2023-07-17 | Underground | R15 | 2023-05-24 | 1 | 356 | 227 | 39 | 620 | 2021 | 2023 | R15
158095188828 | 150278828095 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-05-22 | 2020-01-21 | 2020-04-24 | 2020-08-17 | 2020-12-22 | Underground | R15 | 2020-08-17 | 175 | 69 | 82 | 92 | 415 | 2019 | 2020 | R15
156449172985 | 158282985449 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2019-05-10 | 2019-05-10 | 2019-11-26 | 2019-12-20 | 2020-04-24 | Overhead | R15 | 2019-12-20 | 1 | 143 | 19 | 91 | 251 | 2019 | 2020 | R15
154462267195 | 157963195462 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2021-03-03 | 2021-06-07 | 2022-02-02 | 2023-05-30 | 2023-07-03 | Overhead | R15 | 2023-05-30 | 69 | 173 | 345 | 25 | 609 | 2021 | 2023 | R15
158045237842 | 156881842045 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-11-24 | 2021-01-28 | 2021-07-06 | 2021-07-15 | 2021-12-17 | Overhead | R15 | 2021-07-15 | 48 | 114 | 8 | 112 | 279 | 2020 | 2021 | R15
155345225665 | 159394665345 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-01-25 | 2021-01-25 | 2021-04-02 | 2023-01-13 | 2023-02-06 | Underground | R15 | 2023-01-13 | 1 | 50 | 466 | 17 | 531 | 2021 | 2023 | R15
152816284542 | 152746542816 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Commercial | 2021-02-08 | 2021-02-08 | 2022-07-05 | 2023-01-11 | 2023-02-10 | Underground | R15 | 2023-01-11 | 1 | 367 | 137 | 23 | 525 | 2021 | 2023 | R15
150932240989 | 158393989932 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-03-04 | 2021-03-04 | 2021-07-27 | 2021-08-26 | 2021-08-30 | Overhead | R15 | 2021-08-26 | 1 | 104 | 23 | 3 | 128 | 2021 | 2021 | R15
157350270001 | 152626001350 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2020-12-22 | 2021-04-09 | 2022-02-22 |  | 2023-09-30 | Underground | R15 |  | 79 | 228 |  |  | 724 | 2020 | 2023 | R15
151157229981 | 158067981157 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential Subdivision | 2020-12-02 | 2021-01-21 | 2021-05-07 | 2021-10-05 | 2022-08-22 | Underground | R15 | 2021-10-05 | 37 | 77 | 108 | 230 | 449 | 2020 | 2022 | R15
157102316984 | 157124984102 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Commercial | 2019-03-08 | 2019-03-08 | 2023-04-25 | 2023-06-02 | 2023-07-03 | Underground | R15 | 2023-06-02 | 1 | 1078 | 29 | 22 | 1127 | 2019 | 2023 | R15
157870224346 | 154594346870 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2021-02-17 | 2021-02-17 | 2021-03-22 |  | 2022-08-01 | Overhead | R15 | 2021-03-30 | 1 | 24 | 7 | 350 | 379 | 2021 | 2022 | R15
154034233101 | 154035101034 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2020-11-10 | 2020-11-10 | 2021-06-01 | 2021-10-22 | 2022-04-24 | Underground | R15 | 2021-10-22 | 1 | 146 | 104 | 131 | 379 | 2020 | 2022 | R15
157978186868 | 155662868978 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-02-28 | 2019-03-19 | 2020-04-09 | 2020-12-16 | 2021-10-26 | Underground | R15 | 2020-12-16 | 14 | 278 | 180 | 225 | 694 | 2019 | 2021 | R15
155388209870 | 155526870388 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-08-21 | 2020-08-21 | 2020-11-06 | 2023-05-27 | 2023-05-30 | Overhead | R15 | 2023-05-27 | 1 | 56 | 666 | 2 | 723 | 2020 | 2023 | R15
156943309444 | 157053444943 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-08-27 | 2020-08-27 | 2023-02-14 | 2023-06-21 | 2023-10-03 | Underground | R15 | 2023-06-21 | 1 | 644 | 92 | 75 | 809 | 2020 | 2023 | R15
157872271475 | 157897475872 | NON-RESIDENTIAL - SMALL RETAIL | OH EXTENSION NON RESD OD | Commercial | 2019-01-17 | 2019-01-17 | 2022-03-04 | 2022-04-20 | 2023-04-17 | Overhead | R15 | 2022-04-20 | 1 | 817 | 34 | 259 | 1108 | 2019 | 2023 | R15
152483172771 | 152478771483 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2019-02-08 | 2019-02-08 | 2019-11-25 | 2020-06-29 | 2020-11-18 | Underground | R15 | 2020-06-29 | 1 | 207 | 156 | 103 | 464 | 2019 | 2020 | R15
153219182422 | 158218422219 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-01-23 | 2019-01-23 | 2020-02-28 | 2021-06-05 | 2022-08-25 | Underground | R15 | 2021-06-05 | 1 | 288 | 331 | 319 | 937 | 2019 | 2022 | R15
153612255122 | 157846122612 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential Subdivision | 2020-08-31 | 2020-08-31 | 2021-11-04 | 2022-07-28 | 2022-08-08 | Underground | R15 | 2022-07-28 | 1 | 309 | 191 | 8 | 506 | 2020 | 2022 | R15
155763188924 | 151148924763 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-04-02 | 2019-10-14 | 2020-04-23 | 2020-07-01 | 2020-10-21 | Underground | R15 | 2020-07-01 | 140 | 139 | 50 | 81 | 407 | 2019 | 2020 | R15
155800232612 | 159304612800 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-10-21 | 2021-03-25 | 2021-05-27 | 2021-10-13 | 2021-10-21 | Underground | R15 | 2021-10-13 | 112 | 46 | 100 | 7 | 262 | 2020 | 2021 | R15
159207241176 | 155678176207 | NON-RESIDENTIAL - WAREHOUSE | UG EXT NON RES | Commercial | 2020-11-18 | 2020-11-18 | 2021-07-29 | 2022-01-12 | 2022-01-31 | Underground | R15 | 2022-01-12 | 1 | 182 | 120 | 14 | 314 | 2020 | 2022 | R15
155460212819 | 158475819460 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-12-03 | 2020-12-03 | 2020-12-07 | 2020-12-17 | 2021-02-27 | Overhead | R15 | 2020-12-17 | 1 | 3 | 9 | 52 | 62 | 2020 | 2021 | R15
156939266081 | 159729081939 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2020-10-22 | 2021-06-04 | 2022-01-25 | 2022-04-08 | 2022-10-29 | Underground | R15 | 2022-04-08 | 162 | 168 | 54 | 146 | 527 | 2020 | 2022 | R15
151331240113 | 151034113331 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-03-16 | 2021-04-28 | 2021-07-22 | 2021-12-17 | 2022-01-11 | Overhead | R15 | 2021-12-17 | 32 | 62 | 107 | 18 | 216 | 2021 | 2022 | R15
157872271477 | 157918477872 | NON-RESIDENTIAL - SMALL RETAIL | UG EXT NON RES | Commercial | 2019-01-17 | 2021-05-17 | 2022-03-04 | 2022-11-03 | 2023-04-17 | Underground | R15 | 2022-11-03 | 608 | 210 | 175 | 118 | 1108 | 2019 | 2023 | R15
157593241293 | 159235293593 | Electric Vehicle | UG EXT NON RES | Commercial | 2020-10-20 | 2020-10-20 | 2021-07-30 | 2021-11-09 | 2021-11-22 | Underground | R15 | 2021-11-09 | 1 | 204 | 73 | 10 | 285 | 2020 | 2021 | R15
159105252679 | 152975679105 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2020-12-22 | 2021-05-11 | 2021-10-19 | 2022-09-04 | 2023-10-15 | Underground | R15 | 2022-09-04 | 101 | 116 | 229 | 290 | 734 | 2020 | 2023 | R15
151565236997 | 155037997565 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2021-02-18 | 2021-02-24 | 2021-06-28 | 2022-05-18 | 2022-05-24 | Overhead | R15 | 2022-05-18 | 5 | 89 | 233 | 5 | 329 | 2021 | 2022 | R15
150189247091 | 150136091189 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2020-12-10 | 2021-07-06 | 2021-09-09 | 2022-01-24 | 2022-02-18 | Underground | R15 | 2022-01-24 | 149 | 48 | 98 | 20 | 312 | 2020 | 2022 | R15
150177157652 | 153686652177 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Commercial | 2019-02-14 | 2019-02-14 | 2019-07-12 | 2020-01-28 | 2021-11-12 | Underground | R15 | 2020-01-28 | 1 | 107 | 143 | 469 | 717 | 2019 | 2021 | R15
153141259635 | 158315635141 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-10-15 | 2020-10-15 | 2021-12-03 | 2022-03-07 | 2023-09-01 | Underground | R15 | 2022-03-07 | 1 | 297 | 67 | 390 | 752 | 2020 | 2023 | R15
151391271544 | 153640544391 | NON-RESIDENTIAL - LARGE RETAIL | UG EXT NON RES | Commercial | 2021-03-26 | 2022-01-18 | 2022-03-04 | 2023-09-22 | 2023-10-09 | Underground | R15 | 2023-09-22 | 213 | 34 | 406 | 12 | 662 | 2021 | 2023 | R15
150221149450 | 158968450221 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-01-25 | 2019-01-25 | 2019-04-17 | 2020-01-10 | 2020-04-23 | Underground | R15 | 2020-01-10 | 1 | 59 | 193 | 75 | 325 | 2019 | 2020 | R15
153010307698 | 153058698010 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-03-24 | 2021-03-24 | 2023-01-31 | 2023-10-17 | 2023-09-25 | Underground | R15 | 2023-10-17 | 1 | 485 | 186 |  | 654 | 2021 | 2023 | R15
153927257567 | 153755567927 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-11-10 | 2021-07-07 | 2021-11-19 | 2022-03-01 | 2022-04-01 | Underground | R15 | 2022-03-01 | 172 | 98 | 73 | 24 | 364 | 2020 | 2022 | R15
152278223508 | 155629508278 | NON-RESIDENTIAL - WAREHOUSE | UG EXT NON RES | Commercial | 2020-11-18 | 2020-11-30 | 2021-03-15 | 2022-04-06 | 2022-04-26 | Underground | R15 | 2022-04-06 | 9 | 76 | 278 | 15 | 375 | 2020 | 2022 | R15
152621281122 | 152612122621 | Electric Vehicle | UG EXT NON RES | Commercial | 2020-11-04 | 2020-11-04 | 2022-05-31 | 2022-12-01 | 2022-12-12 | Underground | R15 | 2022-12-01 | 1 | 410 | 133 | 8 | 549 | 2020 | 2022 | R15
152647288603 | 155785603647 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-05-17 | 2022-02-04 | 2022-08-10 | 2022-09-19 | 2022-10-11 | Overhead | R15 | 2022-09-19 | 190 | 134 | 29 | 17 | 367 | 2021 | 2022 | R15
158932259296 | 158819296932 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-03-08 | 2021-03-08 | 2021-12-01 | 2023-08-07 | 2023-09-12 | Overhead | R15 | 2023-08-07 | 1 | 193 | 439 | 27 | 657 | 2021 | 2023 | R15
153389213285 | 153491285389 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-08-12 | 2020-08-20 | 2020-12-09 | 2021-06-22 | 2022-08-22 | Underground | R15 | 2021-06-22 | 7 | 80 | 140 | 305 | 529 | 2020 | 2022 | R15
153330152191 | 153285191330 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-02-13 | 2019-02-13 | 2019-05-13 | 2019-10-05 | 2020-02-20 | Underground | R15 | 2019-10-05 | 1 | 64 | 105 | 99 | 267 | 2019 | 2020 | R15
159095314363 | 154300363095 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2021-02-13 | 2021-04-01 | 2023-03-31 | 2023-07-20 | 2023-06-27 | Overhead | R15 | 2023-07-20 | 34 | 522 | 80 |  | 617 | 2021 | 2023 | R15
159095314363 | 154300363095 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-02-13 | 2021-04-01 | 2023-03-31 | 2023-07-20 | 2023-06-27 | Underground | R15 | 2023-07-20 | 34 | 522 | 80 |  | 617 | 2021 | 2023 | R15
157727295081 | 158393081727 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-04-15 | 2021-04-15 | 2022-09-27 | 2023-11-21 | 2023-12-19 | Underground | R15 | 2023-11-21 | 1 | 379 | 301 | 21 | 699 | 2021 | 2023 | R15
155668243178 | 155669178668 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-05-14 | 2021-05-14 | 2021-08-12 | 2022-03-25 | 2022-04-13 | Underground | R15 | 2022-03-25 | 1 | 65 | 162 | 14 | 239 | 2021 | 2022 | R15
159988280677 | 155749677988 | NON-RESIDENTIAL - HEALTH CARE | UG EXT NON RES | Commercial | 2021-01-08 | 2021-01-08 | 2022-05-25 | 2022-11-09 | 2023-08-29 | Underground | R15 | 2022-11-09 | 1 | 359 | 121 | 210 | 688 | 2021 | 2023 | R15
150958315293 | 152353293958 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential Subdivision | 2020-11-03 | 2020-11-10 | 2023-04-10 | 2023-04-19 | 2023-05-26 | Overhead | R15 | 2023-04-19 | 6 | 630 | 8 | 28 | 669 | 2020 | 2023 | R15
156040168736 | 155983736040 | NON-RESIDENTIAL - LARGE OFFICE | UG EXT NON RES | Commercial | 2019-03-04 | 2019-03-04 | 2019-10-18 |  | 2020-11-19 | Underground | R15 | 2020-03-26 | 1 | 165 | 115 | 171 | 449 | 2019 | 2020 | R15
159673278645 | 159543645673 | Affordable Housing | UG DEV RES | Residential | 2020-10-22 | 2020-10-22 | 2022-05-09 | 2022-05-19 | 2023-01-18 | Underground | R15 | 2022-05-19 | 1 | 403 | 9 | 175 | 585 | 2020 | 2023 | R15
150736290419 | 150821419736 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-11-19 | 2021-11-19 | 2022-08-26 | 2023-04-06 | 2023-07-03 | Underground | R15 | 2023-04-06 | 1 | 201 | 160 | 63 | 422 | 2021 | 2023 | R15
151102290595 | 152316595102 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2022-05-06 | 2022-05-26 | 2022-08-30 | 2022-11-03 | 2022-11-21 | Underground | R15 | 2022-11-03 | 15 | 69 | 48 | 13 | 142 | 2022 | 2022 | R15
154228313384 | 154479384228 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential Subdivision | 2022-01-26 | 2022-03-03 | 2023-03-22 |  | 2023-06-13 | Underground | R15 |  | 27 | 275 |  |  | 360 | 2022 | 2023 | R15
159437283975 | 157193975437 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2022-03-21 | 2022-03-22 | 2022-06-28 | 2022-11-02 | 2022-12-09 | Underground | R15 | 2022-11-02 | 2 | 71 | 92 | 28 | 190 | 2022 | 2022 | R15
151633308458 | 151426458633 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2022-06-20 | 2022-07-06 | 2023-02-06 | 2023-11-09 | 2023-12-14 | Underground | R15 | 2023-11-09 | 13 | 154 | 199 | 26 | 389 | 2022 | 2023 | R15
156502293863 | 153686863502 | Affordable Housing | UG DEV RES | Residential | 2022-01-24 | 2022-03-21 | 2022-09-15 |  | 2023-10-24 | Underground | R15 |  | 41 | 129 |  |  | 457 | 2022 | 2023 | R15
151071302479 | 153293479071 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2022-06-28 | 2022-07-20 | 2022-12-07 | 2023-07-24 | 2023-08-16 | Underground | R15 | 2023-07-24 | 17 | 101 | 164 | 18 | 297 | 2022 | 2023 | R15
154872301590 | 154893590872 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2021-12-09 | 2021-12-09 | 2022-11-29 | 2023-07-13 | 2023-08-16 | Underground | R15 | 2023-07-13 | 1 | 254 | 163 | 25 | 440 | 2021 | 2023 | R15
152350275913 | 152648913350 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2022-03-01 | 2022-03-01 | 2022-04-15 | 2022-06-29 | 2022-08-22 | Overhead | R15 | 2022-06-29 | 1 | 34 | 54 | 39 | 125 | 2022 | 2022 | R15
154082272998 | 156863998082 | CUSTOMER UPGRADE IN SERVICE | UG R15 RES NON RES BUDG 225 | Commercial | 2021-08-09 | 2021-08-17 | 2022-03-18 | 2022-08-31 | 2022-12-12 | Underground | R15 | 2022-08-31 | 7 | 154 | 119 | 74 | 351 | 2021 | 2022 | R15
153230286457 | 150994457230 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-08-24 | 2021-08-24 | 2022-07-22 | 2023-01-04 | 2023-01-24 | Underground | R15 | 2023-01-04 | 1 | 239 | 119 | 15 | 371 | 2021 | 2023 | R15
158895272141 | 150025141895 | FOREIGN UTILITY | OH EXTENSION NON RESD OD | Commercial | 2021-08-19 | 2021-10-07 | 2022-03-09 | 2022-04-26 | 2022-05-19 | Overhead | R15 | 2022-04-26 | 36 | 110 | 35 | 18 | 196 | 2021 | 2022 | R15
157662299105 | 159965105662 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2022-09-07 | 2022-09-07 | 2022-11-01 | 2022-11-16 | 2023-01-25 | Overhead | R15 | 2022-11-16 | 1 | 40 | 12 | 51 | 101 | 2022 | 2023 | R15
157349327654 | 151925654349 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG EXT NON RES | Commercial | 2022-09-16 | 2022-09-16 | 2023-08-07 |  | 2023-10-20 | Underground | R15 | 2023-10-11 | 1 | 232 | 48 | 8 | 286 | 2022 | 2023 | R15
153941319972 | 152736972941 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG RES INDIVIDUAL | Residential | 2022-09-21 | 2023-01-25 | 2023-05-22 | 2023-07-14 | 2023-08-17 | Underground | R15 | 2023-07-14 | 91 | 84 | 40 | 25 | 237 | 2022 | 2023 | R15
158264296345 | 155993345264 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2022-08-24 | 2022-08-25 | 2022-10-07 | 2022-10-25 | 2022-11-04 | Overhead | R15 | 2022-10-25 | 2 | 32 | 13 | 9 | 53 | 2022 | 2022 | R15
153150319596 | 156571596150 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2022-12-07 | 2022-12-07 | 2023-05-18 | 2023-05-24 | 2023-07-07 | Overhead | R15 | 2023-05-24 | 1 | 117 | 5 | 33 | 153 | 2022 | 2023 | R15
155517324874 | 155528874517 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2022-11-30 | 2023-01-18 | 2023-07-13 | 2023-09-19 | 2023-09-29 | Underground | R15 | 2023-09-19 | 36 | 127 | 49 | 9 | 218 | 2022 | 2023 | R15
156874303334 | 155503334874 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2022-08-23 | 2022-11-10 | 2022-12-21 | 2023-01-10 | 2023-02-23 | Overhead | R15 | 2023-01-10 | 58 | 30 | 15 | 33 | 133 | 2022 | 2023 | R15
153498319397 | 156324397498 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2022-08-25 | 2022-08-25 | 2023-05-18 | 2023-07-27 | 2023-09-27 | Overhead | R15 | 2023-07-27 | 1 | 191 | 51 | 45 | 285 | 2022 | 2023 | R15
152230287091 | 152260091230 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2021-07-20 | 2021-07-20 | 2022-07-27 | 2023-09-15 | 2023-11-14 | Underground | R15 | 2023-09-15 | 1 | 267 | 298 | 43 | 606 | 2021 | 2023 | R15
157130271719 | 152120719130 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-06-04 | 2021-11-18 | 2022-03-08 | 2022-07-20 | 2023-02-21 | Underground | R15 | 2022-07-20 | 120 | 79 | 97 | 155 | 448 | 2021 | 2023 | R15
159754251026 | 155313026754 | CUSTOMER UPGRADE IN SERVICE | OH RESD INDIVIDUAL OD | Residential | 2021-06-17 | 2021-06-17 | 2021-10-06 | 2022-09-26 | 2022-09-29 | Overhead | R15 | 2022-09-26 | 1 | 80 | 254 | 4 | 336 | 2021 | 2022 | R15
151033273322 | 151114322033 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-07-14 | 2021-07-14 | 2022-03-21 | 2022-11-28 | 2022-12-07 | Underground | R15 | 2022-11-28 | 1 | 179 | 181 | 8 | 366 | 2021 | 2022 | R15
158201279027 | 151139027201 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-07-16 | 2021-09-09 | 2022-05-11 | 2022-07-14 | 2022-07-27 | Underground | R15 | 2022-07-14 | 40 | 175 | 47 | 10 | 269 | 2021 | 2022 | R15
155702239611 | 152088611702 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-06-04 | 2021-06-08 | 2021-07-20 | 2022-05-13 | 2022-06-07 | Underground | R15 | 2022-05-13 | 3 | 31 | 214 | 18 | 263 | 2021 | 2022 | R15
152613256842 | 154866842613 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-06-16 | 2021-07-26 | 2021-11-16 | 2022-07-12 | 2022-08-01 | Underground | R15 | 2022-07-12 | 29 | 82 | 171 | 15 | 294 | 2021 | 2022 | R15
153045250490 | 158590490045 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-07-02 | 2021-07-02 | 2021-10-04 |  | 2021-11-10 | Underground | R15 |  | 1 | 67 |  |  | 94 | 2021 | 2021 | R15
154347295849 | 152934849347 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2021-07-22 | 2022-02-22 | 2022-10-04 | 2023-04-26 | 2023-06-28 | Overhead | R15 | 2023-04-26 | 154 | 161 | 147 | 46 | 505 | 2021 | 2023 | R15
151823299124 | 158255124823 | CUSTOMER UPGRADE IN SERVICE | OH EXTENSION NON RESD OD | Commercial | 2020-02-05 | 2020-03-16 | 2022-11-01 | 2023-03-30 | 2023-07-07 | Overhead | R15 | 2023-03-30 | 29 | 687 | 108 | 72 | 893 | 2020 | 2023 | R15
153680195369 | 154225369680 | GENERAL/OTHER | UG EXT NON RES | Commercial | 2020-01-17 | 2020-01-17 | 2020-06-25 | 2020-07-29 | 2020-11-04 | Underground | R15 | 2020-07-29 | 1 | 115 | 25 | 71 | 209 | 2020 | 2020 | R15
156650279139 | 150675139650 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-04-08 | 2020-08-26 | 2022-05-12 | 2023-08-15 | 2023-09-27 | Underground | R15 | 2023-08-15 | 101 | 447 | 329 | 32 | 906 | 2020 | 2023 | R15
153495189446 | 157232446495 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-02-01 | 2020-03-26 | 2020-04-29 | 2020-08-19 | 2021-01-04 | Overhead | R15 | 2020-08-19 | 39 | 25 | 81 | 99 | 241 | 2020 | 2021 | R15
159188224294 | 159148294188 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential Subdivision | 2020-03-31 | 2020-04-16 | 2021-03-22 | 2021-10-15 | 2021-11-02 | Underground | R15 | 2021-10-15 | 13 | 243 | 150 | 13 | 416 | 2020 | 2021 | R15
156650272785 | 156660785650 | CUSTOMER UPGRADE IN SERVICE | UG R15 RES NON RES BUDG 225 | Residential | 2020-05-12 | 2020-05-12 | 2022-03-15 | 2022-07-06 | 2022-08-25 | Underground | R15 | 2022-07-06 | 1 | 481 | 82 | 37 | 598 | 2020 | 2022 | R15
156650272785 | 156660785650 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2020-05-12 | 2020-05-12 | 2022-03-15 | 2022-07-06 | 2022-08-25 | Underground | R15 | 2022-07-06 | 1 | 481 | 82 | 37 | 598 | 2020 | 2022 | R15
156354225409 | 150987409354 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2020-06-08 | 2021-02-09 | 2021-03-31 | 2021-04-26 | 2021-10-15 | Overhead | R15 | 2021-04-26 | 177 | 37 | 19 | 125 | 355 | 2020 | 2021 | R15
151082234379 | 159494379082 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2020-05-28 | 2020-12-27 | 2021-06-11 | 2021-07-15 | 2021-11-16 | Overhead | R15 | 2021-07-15 | 152 | 120 | 25 | 89 | 384 | 2020 | 2021 | R15
151750228989 | 152270989750 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-01-08 | 2021-03-09 | 2021-05-01 | 2021-10-11 | 2021-12-08 | Underground | R15 | 2021-10-11 | 305 | 39 | 116 | 43 | 501 | 2020 | 2021 | R15
153429205582 | 150306582429 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential Subdivision | 2020-04-06 | 2020-04-06 | 2020-09-28 | 2020-12-10 | 2022-09-26 | Underground | R15 | 2020-12-10 | 1 | 126 | 54 | 468 | 646 | 2020 | 2022 | R15
153522188786 | 157736786522 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-02-04 | 2020-02-04 | 2020-04-22 | 2020-11-04 | 2020-11-09 | Overhead | R15 | 2020-11-04 | 1 | 57 | 141 | 4 | 200 | 2020 | 2020 | R15
152821203785 | 155611785821 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2020-05-05 | 2020-06-18 | 2020-09-12 |  | 2022-03-29 | Overhead | R15 |  | 33 | 62 |  |  | 496 | 2020 | 2022 | R15
152271183012 | 152070012271 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-02-24 | 2020-03-03 | 2020-03-05 | 2020-04-09 | 2020-10-27 | Overhead | R15 | 2020-04-09 | 7 | 3 | 26 | 144 | 177 | 2020 | 2020 | R15
158601213339 | 157734339601 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Commercial | 2020-05-18 | 2020-08-03 | 2020-12-09 | 2022-06-15 | 2022-07-14 | Underground | R15 | 2022-06-15 | 56 | 93 | 396 | 22 | 564 | 2020 | 2022 | R15
159674220735 | 159675735674 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-02-12 | 2020-04-22 | 2021-02-17 | 2021-05-25 | 2021-09-28 | Underground | R15 | 2021-05-25 | 51 | 216 | 70 | 91 | 425 | 2020 | 2021 | R15
159022239939 | 153521939022 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2020-03-02 | 2021-04-15 | 2021-07-22 | 2022-10-13 | 2022-11-11 | Underground | R15 | 2022-10-13 | 294 | 71 | 321 | 22 | 705 | 2020 | 2022 | R15
156716208631 | 158210631716 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2020-05-20 | 2020-05-21 | 2020-10-27 | 2020-11-05 | 2021-01-14 | Overhead | R15 | 2020-11-05 | 2 | 114 | 8 | 51 | 172 | 2020 | 2021 | R15
157518292728 | 159463728518 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Commercial | 2020-02-12 | 2020-02-12 | 2022-09-06 |  | 2023-07-24 | Underground | R15 |  | 1 | 670 |  |  | 899 | 2020 | 2023 | R15
154907192592 | 158863592907 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-02-10 | 2020-03-02 | 2020-05-29 | 2020-06-26 | 2021-09-23 | Overhead | R15 | 2020-06-26 | 16 | 65 | 21 | 325 | 424 | 2020 | 2021 | R15
154678222714 | 154095714678 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-06-24 | 2020-09-21 | 2021-03-08 | 2022-03-18 | 2022-04-21 | Underground | R15 | 2022-03-18 | 64 | 121 | 270 | 25 | 477 | 2020 | 2022 | R15
157031223280 | 156974280031 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2020-01-31 | 2020-01-31 | 2021-03-11 | 2022-01-19 | 2022-02-15 | Underground | R15 | 2022-01-19 | 1 | 290 | 225 | 20 | 533 | 2020 | 2022 | R15
151105244281 | 150949281105 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Commercial | 2020-06-08 | 2020-06-08 | 2021-08-18 | 2022-05-17 | 2022-06-13 | Underground | R15 | 2022-05-17 | 1 | 313 | 195 | 20 | 526 | 2020 | 2022 | R15
158206246318 | 158215318206 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-02-05 | 2021-06-24 | 2021-09-02 | 2022-07-01 | 2022-07-26 | Underground | R15 | 2022-07-01 | 362 | 51 | 217 | 18 | 645 | 2020 | 2022 | R15
159100198095 | 159102095100 | NON-RESIDENTIAL - HEALTH CARE | UG EXT NON RES | Commercial | 2019-12-17 | 2019-12-23 | 2020-07-23 |  | 2021-02-18 | Underground | R15 | 2020-12-04 | 5 | 154 | 97 | 55 | 308 | 2019 | 2021 | R15
158221212704 | 152801704221 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-04-20 | 2020-06-04 | 2020-12-03 | 2021-02-23 | 2021-04-08 | Underground | R15 | 2021-02-23 | 34 | 131 | 59 | 33 | 254 | 2020 | 2021 | R15
157263274407 | 155734407263 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2020-05-06 | 2021-06-24 | 2022-03-31 | 2023-03-29 | 2023-05-10 | Underground | R15 | 2023-03-29 | 297 | 201 | 260 | 31 | 786 | 2020 | 2023 | R15
151105259606 | 151130606105 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Commercial | 2020-06-08 | 2020-06-08 | 2021-12-02 | 2022-10-14 | 2022-10-31 | Underground | R15 | 2022-10-14 | 1 | 389 | 227 | 12 | 626 | 2020 | 2022 | R15
155280208039 | 152773039280 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2020-04-20 | 2020-05-20 | 2020-10-23 | 2021-08-20 | 2021-11-08 | Overhead | R15 | 2021-08-20 | 23 | 113 | 216 | 57 | 406 | 2020 | 2021 | R15
151332208114 | 151333114332 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2020-02-20 | 2020-04-06 | 2020-10-23 | 2021-09-22 | 2021-10-15 | Underground | R15 | 2021-09-22 | 33 | 145 | 239 | 18 | 432 | 2020 | 2021 | R15
153083199537 | 154136537083 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-01-17 | 2020-01-17 | 2020-08-04 |  | 2023-05-12 | Underground | R15 |  | 1 | 143 |  |  | 866 | 2020 | 2023 | R15
150731289867 | 150771867731 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Commercial | 2020-04-08 | 2020-04-08 | 2022-08-22 | 2023-07-03 | 2023-09-05 | Underground | R15 | 2023-07-03 | 1 | 619 | 226 | 47 | 890 | 2020 | 2023 | R15
150731289867 | 150771867731 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2020-04-08 | 2020-04-08 | 2022-08-22 | 2023-07-03 | 2023-09-05 | Overhead | R15 | 2023-07-03 | 1 | 619 | 226 | 47 | 890 | 2020 | 2023 | R15
152936215907 | 156380907936 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-01-28 | 2020-11-04 | 2020-12-31 |  | 2021-12-15 | Underground | R15 |  | 202 | 42 |  |  | 492 | 2020 | 2021 | R15
152786196426 | 158921426786 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2020-02-10 | 2020-06-23 | 2020-07-02 | 2020-07-31 | 2021-03-11 | Overhead | R15 | 2020-07-31 | 97 | 8 | 22 | 160 | 284 | 2020 | 2021 | R15
151293222443 | 150626443293 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Residential | 2020-06-04 | 2020-10-30 | 2021-03-03 | 2022-07-01 | 2022-08-04 | Underground | R15 | 2022-07-01 | 107 | 89 | 348 | 25 | 566 | 2020 | 2022 | R15
155483233082 | 155479082483 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Commercial | 2020-05-05 | 2020-09-17 | 2021-06-01 | 2021-12-16 | 2022-01-11 | Underground | R15 | 2021-12-16 | 98 | 184 | 143 | 19 | 441 | 2020 | 2022 | R15
155483233082 | 155479082483 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2020-05-05 | 2020-09-17 | 2021-06-01 | 2021-12-16 | 2022-01-11 | Overhead | R15 | 2021-12-16 | 98 | 184 | 143 | 19 | 441 | 2020 | 2022 | R15
156518298522 | 156713522518 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-04-08 | 2021-04-08 | 2022-10-27 | 2023-07-03 | 2023-07-21 | Underground | R15 | 2023-07-03 | 1 | 406 | 178 | 15 | 597 | 2021 | 2023 | R15
152196219554 | 151393554196 | Affordable Housing | UG RES INDIVIDUAL | Residential | 2020-10-29 | 2020-10-29 | 2021-02-05 | 2021-07-22 | 2022-08-25 | Underground | R15 | 2021-07-22 | 1 | 72 | 120 | 286 | 476 | 2020 | 2022 | R15
159398243827 | 156904827398 | NON-RESIDENTIAL - SMALL OFFICE | UG EXT NON RES | Commercial | 2021-04-09 | 2021-07-01 | 2021-08-15 | 2022-02-08 | 2022-03-29 | Underground | R15 | 2022-02-08 | 60 | 32 | 127 | 36 | 253 | 2021 | 2022 | R15
155473258982 | 154308982473 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-10-22 | 2021-10-26 | 2021-11-29 | 2022-06-15 | 2022-07-05 | Underground | R15 | 2022-06-15 | 3 | 25 | 143 | 15 | 183 | 2021 | 2022 | R15
157349237038 | 157506038349 | Electric Vehicle | UG EXT NON RES | Commercial | 2020-02-03 | 2020-02-03 | 2021-06-30 | 2022-09-11 | 2022-04-21 | Underground | R15 | 2022-09-11 | 1 | 368 | 313 |  | 579 | 2020 | 2022 | R15
153615250073 | 155952073615 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2020-10-05 | 2020-10-05 | 2021-09-30 | 2022-07-19 | 2022-08-02 | Underground | R15 | 2022-07-19 | 1 | 259 | 209 | 11 | 477 | 2020 | 2022 | R15
156757263250 | 151931250757 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Residential | 2021-07-19 | 2021-07-19 | 2022-01-03 | 2022-04-07 | 2022-04-13 | Overhead | R15 | 2022-04-07 | 1 | 121 | 69 | 5 | 193 | 2021 | 2022 | R15
157714294873 | 153385873714 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-09-03 | 2021-09-03 | 2022-09-26 | 2023-06-21 | 2023-08-24 | Underground | R15 | 2023-06-21 | 1 | 277 | 193 | 47 | 515 | 2021 | 2023 | R15
154492205626 | 151993626492 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Commercial | 2019-11-07 | 2020-03-06 | 2020-09-29 | 2021-11-30 | 2021-12-27 | Underground | R15 | 2021-11-30 | 87 | 148 | 306 | 20 | 558 | 2019 | 2021 | R15
157237183060 | 155034060237 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-11-25 | 2019-12-06 | 2020-03-05 | 2020-05-18 | 2020-09-30 | Overhead | R15 | 2020-05-18 | 10 | 65 | 53 | 98 | 223 | 2019 | 2020 | R15
159010170356 | 154209356010 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-06-15 | 2019-06-15 | 2019-11-01 | 2021-09-07 | 2021-10-19 | Underground | R15 | 2021-09-07 | 0 | 100 | 483 | 31 | 612 | 2019 | 2021 | R15
150524295106 | 151873106524 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2020-11-02 | 2020-11-02 | 2022-09-27 | 2022-10-13 | 2023-11-30 | Underground | R15 | 2022-10-13 | 1 | 497 | 13 | 296 | 804 | 2020 | 2023 | R15
155897176737 | 154870737897 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-01-03 | 2019-03-07 | 2020-01-14 | 2020-05-13 | 2020-08-31 | Underground | R15 | 2020-05-13 | 46 | 224 | 87 | 79 | 433 | 2019 | 2020 | R15
156130282234 | 156131234130 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-05-17 | 2021-06-02 | 2023-07-12 | 2023-08-03 | 2023-08-24 | Underground | R15 | 2023-08-03 | 13 | 551 | 17 | 16 | 594 | 2021 | 2023 | R15
159028205962 | 150396962028 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Residential | 2019-01-30 | 2020-05-07 | 2020-09-30 | 2021-05-07 | 2021-07-09 | Underground | R15 | 2021-05-07 | 332 | 105 | 158 | 46 | 638 | 2019 | 2021 | R15
156021278084 | 159421084021 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG EXT NON RES | Commercial | 2020-10-21 | 2020-10-21 | 2022-05-03 | 2023-03-01 | 2023-03-30 | Underground | R15 | 2023-03-01 | 1 | 400 | 217 | 22 | 637 | 2020 | 2023 | R15
155129222678 | 155064678129 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-10-01 | 2021-02-06 | 2021-03-08 | 2021-04-22 | 2022-08-29 | Underground | R15 | 2021-04-22 | 92 | 21 | 34 | 353 | 498 | 2020 | 2022 | R15
150119251610 | 150234610119 | Affordable Housing | UG DEV RES | Residential | 2021-04-23 | 2021-07-01 | 2021-10-11 | 2022-08-12 | 2022-08-30 | Underground | R15 | 2022-08-12 | 50 | 73 | 220 | 13 | 353 | 2021 | 2022 | R15
154762161993 | 154735993762 | NON-RESIDENTIAL - MISCELLANEOUS | UG DEV NON RES | Commercial | 2019-01-02 | 2019-02-01 | 2019-08-23 | 2019-12-20 | 2021-11-12 | Underground | R15 | 2019-12-20 | 23 | 146 | 86 | 496 | 748 | 2019 | 2021 | R15
157718181659 | 157853659718 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2019-05-07 | 2019-05-07 | 2020-02-25 | 2020-09-17 | 2020-12-09 | Underground | R15 | 2020-09-17 | 1 | 211 | 148 | 60 | 417 | 2019 | 2020 | R15
153612244211 | 157845211612 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential Subdivision | 2020-08-31 | 2020-08-31 | 2021-08-19 | 2022-05-18 | 2022-05-27 | Underground | R15 | 2022-05-18 | 1 | 254 | 195 | 8 | 455 | 2020 | 2022 | R15
150270165553 | 150281553270 | FOREIGN UTILITY | OH EXTENSION NON RESD OD | Commercial | 2019-05-21 | 2019-06-07 | 2019-09-24 | 2019-10-03 | 2020-04-27 | Overhead | R15 | 2019-10-03 | 14 | 78 | 8 | 148 | 245 | 2019 | 2020 | R15
150518295108 | 151679108518 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential Subdivision | 2020-10-30 | 2020-10-30 | 2022-09-27 | 2022-10-28 | 2023-11-30 | Underground | R15 | 2022-10-28 | 1 | 498 | 24 | 285 | 805 | 2020 | 2023 | R15
156449172983 | 158283983449 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-05-10 | 2019-05-10 | 2019-11-26 |  | 2020-09-15 | Underground | R15 | 2020-03-04 | 1 | 143 | 72 | 140 | 353 | 2019 | 2020 | R15
154311219991 | 156318991311 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential Subdivision | 2020-11-21 | 2020-11-21 | 2021-02-09 | 2021-06-28 | 2021-10-06 | Overhead | R15 | 2021-06-28 | 0 | 57 | 100 | 73 | 228 | 2020 | 2021 | R15
159502158767 | 150277767502 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2019-01-30 | 2019-06-13 | 2019-07-24 | 2020-03-06 | 2021-11-29 | Underground | R15 | 2020-03-06 | 97 | 30 | 163 | 452 | 739 | 2019 | 2021 | R15
157377217455 | 153412455377 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-11-06 | 2020-11-06 | 2021-01-15 |  | 2022-08-29 | Underground | R15 |  | 1 | 51 |  |  | 472 | 2020 | 2022 | R15
153371296211 | 153342211371 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2020-08-12 | 2020-08-12 | 2022-10-06 | 2023-06-01 | 2023-07-25 | Underground | R15 | 2023-06-01 | 1 | 562 | 171 | 39 | 770 | 2020 | 2023 | R15
152852254227 | 155165227852 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2020-08-19 | 2020-08-27 | 2021-10-28 | 2022-05-31 | 2022-07-01 | Underground | R15 | 2022-05-31 | 7 | 306 | 154 | 24 | 488 | 2020 | 2022 | R15
153330152190 | 153284190330 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2019-02-13 | 2019-02-13 | 2019-05-13 | 2019-10-05 | 2020-02-20 | Overhead | R15 | 2019-10-05 | 1 | 64 | 105 | 99 | 267 | 2019 | 2020 | R15
156449248200 | 156949200449 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG EXT NON RES | Commercial | 2020-10-09 | 2021-07-08 | 2021-09-16 | 2022-10-18 | 2022-11-01 | Underground | R15 | 2022-10-18 | 195 | 51 | 284 | 11 | 538 | 2020 | 2022 | R15
153770288259 | 159516259770 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG EXT NON RES | Commercial | 2021-03-09 | 2022-02-08 | 2022-08-09 | 2023-10-31 | 2023-11-29 | Underground | R15 | 2023-10-31 | 241 | 131 | 321 | 22 | 712 | 2021 | 2023 | R15
153383266354 | 157647354383 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2021-04-13 | 2021-07-24 | 2022-01-27 | 2022-02-14 | 2022-03-07 | Overhead | R15 | 2022-02-14 | 74 | 134 | 13 | 16 | 235 | 2021 | 2022 | R15
158614290163 | 158767163614 | AGRICULTURAL | OH EXTENSION NON RESD OD | Commercial | 2021-05-20 | 2022-04-15 | 2022-08-24 | 2022-12-20 | 2023-07-14 | Overhead | R15 | 2022-12-20 | 237 | 94 | 85 | 149 | 562 | 2021 | 2023 | R15
157680287115 | 156356115680 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-11-20 | 2020-11-20 | 2022-07-27 | 2022-12-01 | 2023-01-11 | Underground | R15 | 2022-12-01 | 1 | 439 | 92 | 30 | 559 | 2020 | 2023 | R15
155665252969 | 155666969665 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2021-05-14 | 2021-06-09 | 2021-10-19 | 2022-03-31 | 2022-04-25 | Underground | R15 | 2022-03-31 | 19 | 95 | 118 | 18 | 247 | 2021 | 2022 | R15
159997276400 | 159998400997 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2019-03-26 | 2019-10-03 | 2022-04-19 | 2023-08-22 | 2023-09-06 | Underground | R15 | 2023-08-22 | 138 | 664 | 351 | 12 | 1162 | 2019 | 2023 | R15
154338204015 | 157394015338 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2019-01-15 | 2019-03-11 | 2020-09-17 | 2021-09-02 | 2021-09-30 | Underground | R15 | 2021-09-02 | 40 | 399 | 251 | 21 | 708 | 2019 | 2021 | R15
158567263162 | 151246162567 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2021-04-28 | 2021-07-12 | 2022-01-03 | 2023-06-01 | 2023-07-14 | Overhead | R15 | 2023-06-01 | 54 | 126 | 369 | 32 | 578 | 2021 | 2023 | R15
159245236379 | 151757379245 | NON-RESIDENTIAL - LODGING | UG EXT NON RES | Commercial | 2020-10-31 | 2020-12-30 | 2021-06-23 | 2021-11-10 | 2021-12-02 | Underground | R15 | 2021-11-10 | 43 | 126 | 101 | 17 | 284 | 2020 | 2021 | R15
151215150188 | 151346188215 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Commercial | 2019-02-05 | 2019-02-05 | 2019-04-25 | 2019-09-24 | 2019-10-14 | Underground | R15 | 2019-09-24 | 1 | 58 | 109 | 15 | 180 | 2019 | 2019 | R15
156856159385 | 156353385856 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-01-09 | 2019-01-09 | 2019-07-30 | 2019-11-22 | 2020-03-31 | Underground | R15 | 2019-11-22 | 1 | 145 | 84 | 93 | 320 | 2019 | 2020 | R15
157991229818 | 158576818991 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-03-07 | 2021-03-07 | 2021-05-07 | 2021-09-23 | 2021-10-01 | Underground | R15 | 2021-09-23 | 0 | 45 | 100 | 7 | 150 | 2021 | 2021 | R15
151157239925 | 152752925157 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential | 2021-02-08 | 2021-05-21 | 2021-07-21 | 2022-06-22 | 2022-08-16 | Underground | R15 | 2022-06-22 | 75 | 44 | 241 | 40 | 397 | 2021 | 2022 | R15
158596214036 | 157422036596 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-08-28 | 2020-09-07 | 2020-12-15 | 2021-05-26 | 2021-06-29 | Underground | R15 | 2021-05-26 | 7 | 72 | 117 | 25 | 218 | 2020 | 2021 | R15
150965220155 | 158724155965 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2020-09-04 | 2020-11-30 | 2021-02-10 | 2021-06-03 | 2021-12-29 | Underground | R15 | 2021-06-03 | 62 | 53 | 82 | 150 | 344 | 2020 | 2021 | R15
155224172337 | 156092337224 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2019-01-08 | 2019-01-08 | 2019-11-21 | 2020-02-27 | 2020-07-21 | Overhead | R15 | 2020-02-27 | 1 | 228 | 71 | 104 | 401 | 2019 | 2020 | R15
157920216408 | 159694408920 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-05-17 | 2019-06-27 | 2021-01-06 | 2021-09-13 | 2021-12-13 | Underground | R15 | 2021-09-13 | 30 | 400 | 179 | 66 | 672 | 2019 | 2021 | R15
157329270000 | 152948000329 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2020-12-22 | 2021-04-09 | 2022-02-22 | 2022-06-17 | 2023-10-15 | Underground | R15 | 2022-06-17 | 79 | 228 | 84 | 346 | 734 | 2020 | 2023 | R15
152585181050 | 152656050585 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-04-10 | 2019-04-19 | 2020-02-19 | 2021-02-26 | 2021-05-26 | Underground | R15 | 2021-02-26 | 8 | 219 | 268 | 64 | 556 | 2019 | 2021 | R15
156862232996 | 151676996862 | FOREIGN UTILITY | OH EXTENSION NON RESD OD | Commercial | 2020-09-17 | 2020-09-23 | 2021-06-02 | 2021-07-14 | 2021-08-25 | Overhead | R15 | 2021-07-14 | 5 | 181 | 31 | 31 | 245 | 2020 | 2021 | R15
159608264140 | 159539140608 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-05-25 | 2021-09-08 | 2022-01-09 | 2022-04-07 | 2022-04-18 | Underground | R15 | 2022-04-07 | 77 | 88 | 64 | 8 | 235 | 2021 | 2022 | R15
153306268734 | 157510734306 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential Subdivision | 2020-08-28 | 2020-08-28 | 2022-02-11 | 2022-10-05 | 2022-10-11 | Underground | R15 | 2022-10-05 | 1 | 381 | 169 | 5 | 553 | 2020 | 2022 | R15
158943246998 | 156791998943 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2021-02-25 | 2021-02-25 | 2021-09-09 | 2022-01-04 | 2022-01-25 | Overhead | R15 | 2022-01-04 | 1 | 141 | 84 | 16 | 239 | 2021 | 2022 | R15
151396170330 | 151359330396 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential Subdivision | 2019-02-05 | 2019-02-05 | 2019-11-01 | 2020-07-07 | 2022-10-04 | Overhead | R15 | 2020-07-07 | 1 | 194 | 178 | 586 | 956 | 2019 | 2022 | R15
159043282963 | 153000963043 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-12-22 | 2021-06-21 | 2022-06-16 | 2022-07-13 | 2023-09-17 | Underground | R15 | 2022-07-13 | 130 | 259 | 20 | 308 | 714 | 2020 | 2023 | R15
153089267849 | 155319849089 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-04-02 | 2021-10-20 | 2022-02-07 | 2022-04-08 | 2022-04-28 | Underground | R15 | 2022-04-08 | 144 | 79 | 45 | 15 | 280 | 2021 | 2022 | R15
152615202768 | 152616768615 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-04-09 | 2019-11-20 | 2020-09-04 | 2020-10-21 | 2023-09-15 | Underground | R15 | 2020-10-21 | 162 | 208 | 34 | 758 | 1159 | 2019 | 2023 | R15
152561229961 | 156342961561 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-08-24 | 2020-08-24 | 2021-05-07 | 2023-06-12 | 2023-09-29 | Underground | R15 | 2023-06-12 | 1 | 185 | 547 | 80 | 810 | 2020 | 2023 | R15
151565237343 | 155181343565 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-02-18 | 2021-02-24 | 2021-06-30 | 2022-05-18 | 2023-05-01 | Underground | R15 | 2022-05-18 | 5 | 91 | 231 | 249 | 573 | 2021 | 2023 | R15
153929198885 | 159902885929 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG EXT NON RES | Commercial | 2019-05-20 | 2019-05-20 | 2020-07-29 | 2022-05-06 | 2022-06-03 | Underground | R15 | 2022-05-06 | 1 | 313 | 463 | 21 | 795 | 2019 | 2022 | R15
156053158902 | 155847902053 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential | 2019-01-08 | 2019-02-07 | 2019-07-24 | 2020-07-28 | 2020-09-22 | Underground | R15 | 2020-07-28 | 23 | 120 | 265 | 41 | 446 | 2019 | 2020 | R15
158690159907 | 158537907690 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-05-13 | 2019-05-13 | 2019-08-02 | 2020-06-08 | 2020-09-18 | Underground | R15 | 2020-06-08 | 1 | 60 | 222 | 75 | 355 | 2019 | 2020 | R15
152120211013 | 150898013120 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-09-15 | 2020-09-15 | 2020-11-17 | 2021-03-02 | 2022-01-21 | Overhead | R15 | 2021-03-02 | 1 | 46 | 76 | 234 | 354 | 2020 | 2022 | R15
150517282968 | 151549968517 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential Subdivision | 2020-10-30 | 2020-10-30 | 2022-06-16 | 2022-08-24 | 2023-11-30 | Underground | R15 | 2022-08-24 | 1 | 425 | 50 | 332 | 805 | 2020 | 2023 | R15
159417265887 | 150231887417 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential Subdivision | 2021-04-23 | 2021-08-23 | 2022-01-24 | 2023-11-09 | 2023-10-04 | Underground | R15 | 2023-11-09 | 87 | 111 | 469 |  | 639 | 2021 | 2023 | R15
159515239612 | 150536612515 | NON-RESIDENTIAL - WAREHOUSE | UG EXT NON RES | Commercial | 2020-10-26 | 2021-01-06 | 2021-07-20 | 2022-12-15 | 2023-01-18 | Underground | R15 | 2022-12-15 | 53 | 140 | 368 | 25 | 583 | 2020 | 2023 | R15
151302252972 | 152954972302 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-11-05 | 2021-09-27 | 2021-10-20 | 2021-12-20 | 2022-01-11 | Underground | R15 | 2021-12-20 | 233 | 18 | 44 | 17 | 309 | 2020 | 2022 | R15
152856267120 | 152843120856 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2021-05-04 | 2021-05-04 | 2022-02-01 | 2024-01-10 | 2023-11-21 | Underground | R15 | 2024-01-10 | 1 | 196 | 507 |  | 666 | 2021 | 2023 | R15
153063247702 | 159249702063 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2020-10-21 | 2021-01-06 | 2021-09-13 | 2022-12-15 | 2023-01-06 | Underground | R15 | 2022-12-15 | 56 | 179 | 329 | 17 | 578 | 2020 | 2023 | R15
158139295219 | 158388219139 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-12-29 | 2022-02-11 | 2022-09-29 |  | 2023-02-23 | Underground | R15 | 2023-02-02 | 33 | 165 | 91 | 16 | 302 | 2021 | 2023 | R15
157713289117 | 157681117713 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2022-03-23 | 2022-03-23 | 2022-08-15 | 2023-09-29 | 2023-10-12 | Underground | R15 | 2023-09-29 | 1 | 104 | 295 | 10 | 407 | 2022 | 2023 | R15
150681299911 | 158584911681 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-09-28 | 2021-09-28 | 2022-11-09 | 2022-12-07 | 2023-11-30 | Underground | R15 | 2022-12-07 | 1 | 292 | 21 | 257 | 568 | 2021 | 2023 | R15
156022293475 | 155999475022 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2022-02-01 | 2022-02-01 | 2022-09-13 | 2023-08-11 | 2023-09-30 | Underground | R15 | 2023-08-11 | 1 | 161 | 239 | 36 | 434 | 2022 | 2023 | R15
155947288301 | 155533301947 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2022-01-31 | 2022-02-01 | 2022-08-08 | 2023-03-03 | 2023-09-05 | Overhead | R15 | 2023-03-03 | 2 | 135 | 150 | 133 | 417 | 2022 | 2023 | R15
153795307215 | 150387215795 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2022-05-04 | 2022-07-06 | 2023-01-26 | 2023-06-25 | 2023-06-29 | Overhead | R15 | 2023-06-25 | 46 | 147 | 107 | 4 | 302 | 2022 | 2023 | R15
159625305185 | 155456185625 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Commercial | 2021-12-13 | 2021-12-13 | 2023-01-30 | 2023-06-15 | 2023-08-16 | Underground | R15 | 2023-06-15 | 1 | 296 | 99 | 45 | 438 | 2021 | 2023 | R15
158704322892 | 156522892704 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2022-05-25 | 2023-01-28 | 2023-06-22 | 2023-10-16 | 2023-12-12 | Overhead | R15 | 2023-10-16 | 178 | 104 | 83 | 42 | 405 | 2022 | 2023 | R15
152531269188 | 159600188531 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-11-15 | 2022-01-04 | 2022-02-16 | 2022-03-21 | 2022-04-07 | Overhead | R15 | 2022-03-21 | 37 | 32 | 24 | 14 | 104 | 2021 | 2022 | R15
158007301922 | 152325922007 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG EXT NON RES | Residential | 2022-05-06 | 2022-09-09 | 2022-11-30 | 2023-05-11 | 2023-09-01 | Underground | R15 | 2023-05-11 | 91 | 59 | 117 | 82 | 346 | 2022 | 2023 | R15
153582301346 | 153446346582 | Affordable Housing | OH SUBDIVISION RESD OD | Residential | 2022-04-22 | 2022-04-22 | 2022-11-22 | 2023-06-08 | 2023-07-14 | Overhead | R15 | 2023-06-08 | 1 | 153 | 143 | 27 | 321 | 2022 | 2023 | R15
152748301818 | 151586818748 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2022-06-21 | 2022-06-21 | 2022-11-30 | 2023-05-08 | 2023-06-16 | Underground | R15 | 2023-05-08 | 1 | 117 | 114 | 30 | 259 | 2022 | 2023 | R15
154250303027 | 154261027250 | NON-RESIDENTIAL - WAREHOUSE | UG EXT NON RES | Commercial | 2022-04-26 | 2022-04-26 | 2023-01-30 | 2023-07-12 | 2023-08-25 | Underground | R15 | 2023-07-12 | 1 | 200 | 118 | 33 | 349 | 2022 | 2023 | R15
154872297784 | 154894784872 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2021-12-09 | 2021-12-09 | 2022-10-21 | 2023-07-20 | 2023-08-24 | Underground | R15 | 2023-07-20 | 1 | 227 | 195 | 26 | 446 | 2021 | 2023 | R15
152209280014 | 154642014209 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2022-03-09 | 2022-04-26 | 2022-05-19 | 2023-01-09 | 2023-01-19 | Overhead | R15 | 2023-01-09 | 35 | 18 | 168 | 9 | 227 | 2022 | 2023 | R15
150668283910 | 156493910668 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential Subdivision | 2022-05-25 | 2022-06-03 | 2022-06-27 | 2023-03-30 | 2023-07-06 | Underground | R15 | 2023-03-30 | 8 | 17 | 199 | 71 | 292 | 2022 | 2023 | R15
152698285698 | 154761698698 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2021-10-24 | 2021-10-25 | 2022-07-15 | 2022-10-31 | 2022-11-22 | Overhead | R15 | 2022-10-31 | 1 | 190 | 77 | 17 | 282 | 2021 | 2022 | R15
150811308017 | 150813017811 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2022-04-07 | 2022-04-07 | 2023-02-02 | 2023-09-11 | 2023-10-03 | Underground | R15 | 2023-09-11 | 1 | 216 | 158 | 17 | 389 | 2022 | 2023 | R15
153679295096 | 153766096679 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | OH EXTENSION NON RESD OD | Commercial | 2022-04-23 | 2022-04-23 | 2022-09-28 | 2022-10-29 | 2022-11-09 | Overhead | R15 | 2022-10-29 | 0 | 113 | 23 | 8 | 143 | 2022 | 2022 | R15
154371285998 | 152906998371 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2022-01-20 | 2022-03-16 | 2022-07-19 | 2022-10-15 | 2022-12-09 | Underground | R15 | 2022-10-15 | 40 | 90 | 64 | 40 | 232 | 2022 | 2022 | R15
157976274666 | 154407666976 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2022-03-08 | 2022-03-16 | 2022-04-01 | 2022-05-25 | 2022-06-20 | Underground | R15 | 2022-05-25 | 7 | 13 | 39 | 19 | 75 | 2022 | 2022 | R15
156981282164 | 159885164981 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2020-10-22 | 2021-07-09 | 2022-06-09 | 2022-06-21 | 2023-09-17 | Underground | R15 | 2022-06-21 | 187 | 240 | 9 | 324 | 757 | 2020 | 2023 | R15
157412240147 | 150518147412 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-09-14 | 2021-02-08 | 2021-07-22 |  | 2023-06-02 | Underground | R15 |  | 106 | 119 |  |  | 710 | 2020 | 2023 | R15
156442231336 | 152454336442 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2021-05-03 | 2021-05-03 | 2021-05-19 | 2021-07-31 | 2021-08-03 | Overhead | R15 | 2021-07-31 | 1 | 13 | 53 | 2 | 67 | 2021 | 2021 | R15
152634144411 | 156625411634 | AGRICULTURAL | OH EXTENSION NON RESD OD | Commercial | 2019-01-10 | 2019-01-28 | 2019-02-27 | 2019-03-07 | 2019-09-11 | Overhead | R15 | 2019-03-07 | 13 | 23 | 7 | 135 | 175 | 2019 | 2019 | R15
157335159906 | 155661906335 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2019-02-28 | 2019-02-28 | 2019-08-02 | 2019-08-09 | 2019-11-18 | Overhead | R15 | 2019-08-09 | 1 | 112 | 6 | 72 | 188 | 2019 | 2019 | R15
155778236150 | 158993150778 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-01-22 | 2021-03-04 | 2021-06-21 | 2021-11-11 | 2021-12-06 | Underground | R15 | 2021-11-11 | 30 | 78 | 104 | 18 | 227 | 2021 | 2021 | R15
151105260560 | 158466560105 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Commercial | 2021-01-21 | 2021-01-21 | 2021-12-09 | 2023-09-14 | 2023-10-13 | Underground | R15 | 2023-09-14 | 1 | 231 | 461 | 22 | 712 | 2021 | 2023 | R15
151085269931 | 151236931085 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-02-01 | 2021-02-01 | 2022-02-22 | 2022-11-29 | 2022-12-13 | Underground | R15 | 2022-11-29 | 1 | 277 | 201 | 11 | 487 | 2021 | 2022 | R15
153419235274 | 159256274419 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-07-22 | 2020-07-22 | 2021-06-17 | 2022-06-03 | 2022-06-22 | Underground | R15 | 2022-06-03 | 1 | 237 | 252 | 14 | 501 | 2020 | 2022 | R15
157630204628 | 157629628630 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-05-07 | 2019-05-07 | 2020-09-21 | 2022-08-25 | 2022-09-09 | Underground | R15 | 2022-08-25 | 1 | 360 | 504 | 12 | 874 | 2019 | 2022 | R15
159807278785 | 159843785807 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-03-10 | 2021-03-15 | 2022-05-10 | 2023-07-14 | 2023-09-13 | Underground | R15 | 2023-07-14 | 4 | 302 | 309 | 44 | 656 | 2021 | 2023 | R15
156798211291 | 152536291798 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-08-07 | 2020-08-07 | 2020-11-19 | 2021-01-06 | 2021-10-07 | Underground | R15 | 2021-01-06 | 1 | 75 | 35 | 197 | 305 | 2020 | 2021 | R15
155641242208 | 155642208641 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2021-05-14 | 2021-06-09 | 2021-08-05 | 2021-10-22 | 2021-11-12 | Underground | R15 | 2021-10-22 | 19 | 42 | 57 | 16 | 131 | 2021 | 2021 | R15
151430231283 | 152660283430 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-11-04 | 2020-11-04 | 2021-05-18 | 2022-07-08 | 2022-07-26 | Underground | R15 | 2022-07-08 | 1 | 140 | 299 | 13 | 450 | 2020 | 2022 | R15
154237189142 | 150110142237 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-05-21 | 2019-05-21 | 2020-04-27 | 2020-09-24 | 2020-11-16 | Underground | R15 | 2020-09-24 | 1 | 245 | 109 | 38 | 390 | 2019 | 2020 | R15
153293210612 | 152794612293 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2020-09-23 | 2020-10-27 | 2020-11-16 | 2021-01-11 | 2021-02-04 | Overhead | R15 | 2021-01-11 | 25 | 15 | 41 | 19 | 97 | 2020 | 2021 | R15
156806299855 | 153943855806 | RESIDENTIAL - MULTI-FAMILY | OH RESD INDIVIDUAL OD | Residential | 2019-02-19 | 2019-02-19 | 2022-11-08 | 2023-02-22 | 2023-05-05 | Overhead | R15 | 2023-02-22 | 1 | 971 | 77 | 53 | 1099 | 2019 | 2023 | R15
157352230025 | 152980025352 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-03-24 | 2021-04-19 | 2021-05-08 | 2022-09-27 | 2023-04-17 | Underground | R15 | 2022-09-27 | 19 | 15 | 362 | 145 | 539 | 2021 | 2023 | R15
153202161211 | 155354211202 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-02-27 | 2019-03-06 | 2019-08-15 | 2020-06-19 | 2020-10-13 | Underground | R15 | 2020-06-19 | 6 | 117 | 222 | 83 | 425 | 2019 | 2020 | R15
158680238888 | 157396888680 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Residential | 2020-11-30 | 2020-11-30 | 2021-07-13 | 2021-11-16 | 2021-12-02 | Underground | R15 | 2021-11-16 | 1 | 162 | 91 | 13 | 264 | 2020 | 2021 | R15
151133165080 | 157993080133 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-05-08 | 2019-05-08 | 2019-09-18 |  | 2021-09-13 | Underground | R15 |  | 1 | 96 |  |  | 614 | 2019 | 2021 | R15
150531295117 | 151806117531 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2020-11-02 | 2020-11-02 | 2022-09-28 | 2023-02-04 | 2023-11-30 | Underground | R15 | 2023-02-04 | 1 | 498 | 93 | 214 | 804 | 2020 | 2023 | R15
154751237212 | 154679212751 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Commercial | 2019-02-22 | 2019-02-22 | 2021-06-30 | 2023-01-25 | 2023-05-17 | Underground | R15 | 2023-01-25 | 1 | 614 | 411 | 81 | 1104 | 2019 | 2023 | R15
151085271028 | 151237028085 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-02-01 | 2021-02-01 | 2022-03-01 | 2023-02-23 | 2023-03-06 | Underground | R15 | 2023-02-23 | 1 | 282 | 258 | 8 | 546 | 2021 | 2023 | R15
153874281201 | 158397201874 | NON-RESIDENTIAL - SMALL RETAIL | UG EXT NON RES | Commercial | 2021-04-15 | 2021-04-15 | 2022-05-31 | 2023-11-16 | 2023-12-28 | Underground | R15 | 2023-11-16 | 1 | 294 | 383 | 31 | 706 | 2021 | 2023 | R15
151743186032 | 151160032743 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2019-02-04 | 2019-03-06 | 2020-04-01 | 2020-10-12 | 2021-02-24 | Underground | R15 | 2020-10-12 | 23 | 281 | 139 | 98 | 538 | 2019 | 2021 | R15
155096156751 | 158972751096 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG EXT NON RES | Commercial | 2019-01-25 | 2019-01-25 | 2019-07-01 | 2019-09-10 | 2022-08-29 | Underground | R15 | 2019-09-10 | 1 | 112 | 52 | 775 | 937 | 2019 | 2022 | R15
156687221072 | 156745072687 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential Subdivision | 2019-01-11 | 2019-01-11 | 2021-02-22 | 2022-03-04 | 2022-03-23 | Underground | R15 | 2022-03-04 | 1 | 552 | 270 | 14 | 834 | 2019 | 2022 | R15
158395154458 | 157036458395 | INDUSTRIAL | UG EXT NON RES | Commercial | 2019-03-07 | 2019-03-07 | 2019-06-06 | 2019-09-25 | 2019-07-16 | Underground | R15 | 2019-09-25 | 1 | 66 | 80 |  | 94 | 2019 | 2019 | R15
154826326218 | 151104218826 | Affordable Housing | UG DEV RES | Residential | 2022-02-23 | 2022-09-27 | 2023-07-24 | 2023-10-17 | 2023-10-31 | Underground | R15 | 2023-10-17 | 155 | 215 | 62 | 11 | 440 | 2022 | 2023 | R15
156536301651 | 156486651536 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-09-17 | 2021-09-17 | 2022-11-29 | 2023-09-15 | 2023-10-30 | Underground | R15 | 2023-09-15 | 1 | 313 | 209 | 32 | 552 | 2021 | 2023 | R15
157277269324 | 153468324277 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2022-01-21 | 2022-02-01 | 2022-02-16 | 2022-06-15 | 2022-06-29 | Underground | R15 | 2022-06-15 | 8 | 12 | 86 | 11 | 114 | 2022 | 2022 | R15
154610279613 | 156256613610 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG RES INDIVIDUAL | Residential Subdivision | 2021-11-01 | 2022-04-13 | 2022-05-17 | 2023-09-20 | 2023-10-10 | Underground | R15 | 2023-09-20 | 118 | 25 | 352 | 15 | 507 | 2021 | 2023 | R15
152991315868 | 154151868991 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential Subdivision | 2022-01-25 | 2022-01-25 | 2023-04-14 | 2023-06-23 | 2023-07-21 | Underground | R15 | 2023-06-23 | 1 | 319 | 51 | 21 | 389 | 2022 | 2023 | R15
158149300144 | 158571144149 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential Subdivision | 2021-09-28 | 2021-09-28 | 2022-11-10 | 2022-12-11 | 2023-11-30 | Underground | R15 | 2022-12-11 | 1 | 293 | 22 | 254 | 568 | 2021 | 2023 | R15
154048307872 | 154710872048 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2022-05-17 | 2022-05-17 | 2023-02-01 | 2023-02-08 | 2023-07-25 | Overhead | R15 | 2023-02-08 | 1 | 187 | 6 | 120 | 311 | 2022 | 2023 | R15
150068297123 | 153000123068 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2022-03-02 | 2022-05-16 | 2022-10-14 | 2023-11-27 | 2023-12-26 | Underground | R15 | 2023-11-27 | 54 | 110 | 292 | 22 | 475 | 2022 | 2023 | R15
158235274022 | 158179022235 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG EXT NON RES | Commercial | 2021-09-27 | 2021-09-27 | 2022-03-28 | 2023-03-23 | 2023-06-12 | Underground | R15 | 2023-03-23 | 1 | 131 | 259 | 58 | 446 | 2021 | 2023 | R15
152777292731 | 152847731777 | Electric Vehicle | UG EXT NON RES | Commercial | 2021-12-01 | 2021-12-01 | 2022-09-06 | 2023-05-11 | 2023-08-24 | Underground | R15 | 2023-05-11 | 1 | 200 | 178 | 76 | 452 | 2021 | 2023 | R15
154478296363 | 153322363478 | CUSTOMER UPGRADE IN SERVICE | UG R15 RES NON RES BUDG 225 | Commercial | 2022-01-21 | 2022-05-10 | 2022-10-07 | 2023-04-24 | 2023-06-09 | Underground | R15 | 2023-04-24 | 78 | 109 | 142 | 35 | 361 | 2022 | 2023 | R15
158989260563 | 154591563989 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-12-08 | 2021-12-08 | 2021-12-09 |  | 2022-01-06 | Overhead | R15 | 2021-12-08 | 1 | 2 |  | 22 | 22 | 2021 | 2022 | R15
154695275852 | 153169852695 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2021-10-18 | 2021-12-28 | 2022-04-14 | 2022-07-06 | 2022-07-19 | Underground | R15 | 2022-07-06 | 52 | 78 | 60 | 10 | 197 | 2021 | 2022 | R15
150307299012 | 159080012307 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2022-06-08 | 2022-06-08 | 2022-11-01 | 2023-06-29 | 2023-07-25 | Underground | R15 | 2023-06-29 | 1 | 105 | 173 | 19 | 295 | 2022 | 2023 | R15
156829317324 | 151626324829 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2022-04-12 | 2022-04-13 | 2023-04-28 | 2023-06-08 | 2023-07-21 | Underground | R15 | 2023-06-08 | 2 | 273 | 30 | 32 | 334 | 2022 | 2023 | R15
151055283436 | 154353436055 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-10-21 | 2021-12-28 | 2022-06-22 | 2023-07-20 | 2023-08-16 | Underground | R15 | 2023-07-20 | 49 | 127 | 282 | 20 | 475 | 2021 | 2023 | R15
158320312046 | 158554046320 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential Subdivision | 2021-09-28 | 2021-09-28 | 2023-03-10 | 2023-03-14 | 2023-07-03 | Underground | R15 | 2023-03-14 | 1 | 379 | 3 | 80 | 460 | 2021 | 2023 | R15
159606290550 | 152758550606 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2022-06-24 | 2022-06-24 | 2022-08-29 | 2023-01-05 | 2023-01-20 | Underground | R15 | 2023-01-05 | 1 | 47 | 94 | 12 | 151 | 2022 | 2023 | R15
154479300921 | 157535921479 | AGRICULTURAL | OH EXTENSION NON RESD OD | Commercial | 2022-07-19 | 2022-07-20 | 2022-11-17 | 2022-12-08 | 2023-01-31 | Overhead | R15 | 2022-12-08 | 2 | 87 | 16 | 39 | 141 | 2022 | 2023 | R15
154693316985 | 156045985693 | NON-RESIDENTIAL - SMALL RETAIL | UG EXT NON RES | Commercial | 2021-12-15 | 2021-12-15 | 2023-04-25 | 2023-09-05 | 2023-09-26 | Underground | R15 | 2023-09-05 | 1 | 355 | 96 | 16 | 465 | 2021 | 2023 | R15
155052289876 | 153780876052 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2022-05-13 | 2022-05-13 | 2022-08-22 | 2022-11-18 | 2022-12-09 | Overhead | R15 | 2022-11-18 | 1 | 72 | 65 | 16 | 151 | 2022 | 2022 | R15
150307298575 | 159049575307 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2022-06-08 | 2022-06-08 | 2022-10-28 | 2023-05-25 | 2023-07-07 | Underground | R15 | 2023-05-25 | 1 | 103 | 150 | 32 | 283 | 2022 | 2023 | R15
157011299486 | 156849486011 | NON-RESIDENTIAL - SMALL RETAIL | UG EXT NON RES | Commercial | 2022-07-15 | 2022-09-27 | 2022-11-04 | 2023-04-06 | 2023-12-26 | Underground | R15 | 2023-04-06 | 53 | 29 | 110 | 189 | 378 | 2022 | 2023 | R15
159885282823 | 156209823885 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-11-01 | 2022-02-04 | 2022-06-16 | 2022-06-29 | 2022-09-06 | Overhead | R15 | 2022-06-29 | 70 | 95 | 10 | 50 | 222 | 2021 | 2022 | R15
154826303706 | 151086706826 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2022-02-23 | 2022-08-17 | 2022-12-20 | 2023-10-12 | 2023-11-20 | Underground | R15 | 2023-10-12 | 126 | 90 | 213 | 28 | 454 | 2022 | 2023 | R15
150730285441 | 155548441730 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2022-05-20 | 2022-05-20 | 2022-07-12 | 2022-12-27 | 2023-01-18 | Overhead | R15 | 2022-12-27 | 1 | 38 | 121 | 17 | 174 | 2022 | 2023 | R15
154826300886 | 151068886826 | Affordable Housing | UG DEV RES | Residential | 2022-02-23 | 2022-07-07 | 2022-11-17 | 2023-07-25 | 2023-08-16 | Underground | R15 | 2023-07-25 | 97 | 96 | 179 | 17 | 386 | 2022 | 2023 | R15
151906235973 | 151888973906 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-09-18 | 2020-11-10 | 2021-06-22 | 2021-12-29 | 2022-01-21 | Underground | R15 | 2021-12-29 | 38 | 161 | 137 | 18 | 351 | 2020 | 2022 | R15
155187236020 | 150044020187 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-01-27 | 2021-01-28 | 2021-06-20 | 2022-08-10 | 2022-10-03 | Underground | R15 | 2022-08-10 | 2 | 102 | 298 | 39 | 439 | 2021 | 2022 | R15
153449265343 | 157729343449 | RESIDENTIAL - MULTI-FAMILY | OH DEVELOPMENT RESD OD | Residential | 2020-10-14 | 2021-05-14 | 2022-01-19 | 2022-03-17 | 2022-08-31 | Overhead | R15 | 2022-03-17 | 153 | 179 | 42 | 120 | 491 | 2020 | 2022 | R15
157125171418 | 157214418125 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-03-08 | 2019-03-08 | 2019-11-12 | 2020-01-12 | 2020-04-30 | Overhead | R15 | 2020-01-12 | 1 | 178 | 44 | 79 | 300 | 2019 | 2020 | R15
151701234552 | 151755552701 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2019-05-31 | 2019-05-31 | 2021-06-11 | 2021-11-08 | 2021-11-30 | Underground | R15 | 2021-11-08 | 1 | 531 | 107 | 17 | 653 | 2019 | 2021 | R15
155858160233 | 152032233858 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2019-02-07 | 2019-05-13 | 2019-08-05 |  | 2019-12-04 | Underground | R15 | 2020-01-21 | 68 | 61 | 122 |  | 215 | 2019 | 2019 | R15
157467251023 | 157515023467 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-08-28 | 2020-08-28 | 2021-10-06 | 2022-10-17 | 2023-04-17 | Underground | R15 | 2022-10-17 | 1 | 289 | 269 | 131 | 687 | 2020 | 2023 | R15
151157229983 | 154405983157 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential | 2021-02-16 | 2021-03-14 | 2021-05-07 | 2021-10-19 | 2022-10-19 | Underground | R15 | 2021-10-19 | 19 | 40 | 118 | 262 | 437 | 2021 | 2022 | R15
157925242462 | 157926462925 | NON-RESIDENTIAL - MISCELLANEOUS | UG DEV NON RES | Commercial | 2021-05-18 | 2021-05-18 | 2021-08-05 | 2022-07-19 | 2022-08-08 | Underground | R15 | 2022-07-19 | 1 | 58 | 249 | 15 | 320 | 2021 | 2022 | R15
158954239763 | 151685763954 | CUSTOMER UPGRADE IN SERVICE | UG R15 RES NON RES BUDG 225 | Residential | 2020-12-21 | 2021-02-02 | 2021-07-20 | 2022-03-02 | 2022-03-09 | Underground | R15 | 2022-03-02 | 32 | 121 | 162 | 6 | 318 | 2020 | 2022 | R15
155931243825 | 150402825931 | FOREIGN UTILITY | UG EXT NON RES | Commercial | 2020-10-24 | 2020-10-24 | 2021-08-15 | 2022-06-01 | 2022-06-16 | Underground | R15 | 2022-06-01 | 0 | 210 | 208 | 12 | 429 | 2020 | 2022 | R15
153162240160 | 157046160162 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2020-08-27 | 2020-08-27 | 2021-07-22 | 2022-02-28 | 2022-03-23 | Underground | R15 | 2022-02-28 | 1 | 236 | 158 | 18 | 410 | 2020 | 2022 | R15
150478244544 | 150511544478 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2020-09-11 | 2020-09-11 | 2021-08-20 | 2022-07-21 | 2022-08-08 | Overhead | R15 | 2022-07-21 | 1 | 246 | 240 | 13 | 497 | 2020 | 2022 | R15
158095188827 | 150277827095 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-05-22 | 2020-01-17 | 2020-04-24 | 2020-08-17 | 2020-12-22 | Overhead | R15 | 2020-08-17 | 173 | 71 | 82 | 92 | 415 | 2019 | 2020 | R15
153010311781 | 153055781010 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-03-24 | 2021-03-24 | 2023-03-07 | 2023-10-25 | 2023-11-03 | Underground | R15 | 2023-10-25 | 1 | 510 | 167 | 8 | 683 | 2021 | 2023 | R15
157060214342 | 158240342060 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-03-14 | 2019-05-01 | 2020-12-17 | 2022-10-27 | 2022-11-01 | Overhead | R15 | 2022-10-27 | 35 | 427 | 486 | 4 | 949 | 2019 | 2022 | R15
151908246567 | 156196567908 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-01-12 | 2021-01-12 | 2021-09-03 |  | 2022-03-28 | Underground | R15 | 2021-11-23 | 1 | 169 | 58 | 90 | 315 | 2021 | 2022 | R15
158068234463 | 158340463068 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-04-15 | 2021-04-15 | 2021-06-10 | 2022-01-29 | 2022-02-03 | Overhead | R15 | 2022-01-29 | 1 | 41 | 167 | 4 | 211 | 2021 | 2022 | R15
153306248745 | 157368745306 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2020-08-28 | 2020-08-28 | 2021-09-20 | 2022-08-17 | 2022-08-31 | Underground | R15 | 2022-08-17 | 1 | 277 | 238 | 11 | 524 | 2020 | 2022 | R15
155588242224 | 153661224588 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2021-02-11 | 2021-04-06 | 2021-08-05 | 2021-09-03 | 2022-01-16 | Overhead | R15 | 2021-09-03 | 39 | 88 | 22 | 96 | 242 | 2021 | 2022 | R15
159355159863 | 158217863355 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-05-09 | 2019-05-09 | 2019-08-02 | 2020-02-03 | 2020-04-11 | Underground | R15 | 2020-02-03 | 1 | 62 | 132 | 50 | 242 | 2019 | 2020 | R15
151786260583 | 151833583786 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential | 2020-09-18 | 2020-09-18 | 2021-12-09 | 2023-05-30 | 2023-07-17 | Underground | R15 | 2023-05-30 | 1 | 320 | 384 | 35 | 737 | 2020 | 2023 | R15
156935278399 | 152303399935 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-02-04 | 2021-11-05 | 2022-05-06 | 2023-07-24 | 2023-10-03 | Underground | R15 | 2023-07-24 | 197 | 131 | 317 | 52 | 694 | 2021 | 2023 | R15
154931272994 | 151901994931 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-09-18 | 2020-09-18 | 2022-03-18 |  | 2022-09-27 | Underground | R15 |  | 1 | 391 |  |  | 528 | 2020 | 2022 | R15
150147248771 | 153774771147 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Commercial | 2021-03-26 | 2021-03-26 | 2021-09-21 | 2022-12-15 | 2022-12-16 | Underground | R15 | 2022-12-15 | 1 | 128 | 323 | 2 | 451 | 2021 | 2022 | R15
151085269938 | 151235938085 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-02-01 | 2021-02-01 | 2022-02-22 | 2022-10-06 | 2022-10-24 | Underground | R15 | 2022-10-06 | 1 | 277 | 163 | 13 | 451 | 2021 | 2022 | R15
152991251255 | 153098255991 | NON-RESIDENTIAL - MISCELLANEOUS | UG DEV NON RES | Commercial | 2020-11-05 | 2021-01-27 | 2021-10-08 | 2021-11-17 | 2021-12-15 | Underground | R15 | 2021-11-17 | 60 | 183 | 29 | 21 | 290 | 2020 | 2021 | R15
151085256216 | 151239216085 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-02-01 | 2021-02-01 | 2021-11-12 | 2022-02-17 | 2022-02-18 | Underground | R15 | 2022-02-17 | 1 | 205 | 70 | 2 | 275 | 2021 | 2022 | R15
158756231601 | 152522601756 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2020-08-07 | 2021-02-26 | 2021-05-20 | 2022-05-09 | 2022-05-23 | Underground | R15 | 2022-05-09 | 146 | 60 | 253 | 11 | 467 | 2020 | 2022 | R15
157782241962 | 157783962782 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-03-02 | 2021-06-08 | 2021-08-03 | 2021-12-20 | 2022-01-17 | Overhead | R15 | 2021-12-20 | 71 | 41 | 100 | 21 | 230 | 2021 | 2022 | R15
151085251762 | 151232762085 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2021-02-01 | 2021-02-01 | 2021-10-12 | 2022-05-02 | 2022-05-16 | Underground | R15 | 2022-05-02 | 1 | 182 | 145 | 11 | 336 | 2021 | 2022 | R15
152852265059 | 155166059852 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2020-08-19 | 2020-08-27 | 2022-01-19 | 2022-07-21 | 2022-08-11 | Underground | R15 | 2022-07-21 | 7 | 365 | 132 | 16 | 517 | 2020 | 2022 | R15
152856265970 | 152842970856 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-05-04 | 2021-05-04 | 2022-01-24 | 2023-11-07 | 2023-11-14 | Underground | R15 | 2023-11-07 | 1 | 190 | 467 | 6 | 661 | 2021 | 2023 | R15
151642216176 | 154266176642 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-11-12 | 2020-11-12 | 2021-01-05 | 2021-08-12 | 2022-02-02 | Underground | R15 | 2021-08-12 | 1 | 39 | 158 | 125 | 320 | 2020 | 2022 | R15
152114239828 | 154725828114 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2020-11-14 | 2021-01-11 | 2021-07-20 | 2022-02-18 | 2022-03-29 | Overhead | R15 | 2022-02-18 | 41 | 137 | 154 | 28 | 357 | 2020 | 2022 | R15
158744238483 | 158745483744 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential | 2020-07-17 | 2020-07-17 | 2021-07-12 | 2021-07-28 | 2023-09-17 | Underground | R15 | 2021-07-28 | 1 | 257 | 13 | 558 | 826 | 2020 | 2023 | R15
153306254567 | 157369567306 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2020-08-28 | 2020-08-28 | 2021-11-01 | 2022-08-17 | 2022-12-08 | Underground | R15 | 2022-08-17 | 1 | 307 | 208 | 82 | 595 | 2020 | 2022 | R15
153498150566 | 156040566498 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-04-29 | 2019-04-29 | 2019-04-29 | 2020-06-25 | 2022-10-03 | Underground | R15 | 2020-06-25 | 1 |  | 304 | 593 | 896 | 2019 | 2022 | R15
153657233787 | 156984787657 | CUSTOMER UPGRADE IN SERVICE | UG R15 RES NON RES BUDG 225 | Residential | 2019-03-07 | 2019-03-07 | 2021-06-07 | 2022-12-22 | 2023-01-06 | Underground | R15 | 2022-12-22 | 1 | 588 | 404 | 12 | 1002 | 2019 | 2023 | R15
157533266055 | 151875055533 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential | 2020-11-02 | 2020-11-02 | 2022-01-25 | 2022-05-17 | 2023-09-17 | Underground | R15 | 2022-05-17 | 1 | 322 | 81 | 349 | 750 | 2020 | 2023 | R15
159331233349 | 159345349331 | NON-RESIDENTIAL - LODGING | UG EXT NON RES | Commercial | 2020-07-21 | 2020-09-24 | 2021-06-03 | 2022-06-15 | 2022-07-07 | Underground | R15 | 2022-06-15 | 48 | 181 | 270 | 17 | 513 | 2020 | 2022 | R15
157102285252 | 157950252102 | NON-RESIDENTIAL - MISCELLANEOUS | UG DEV NON RES | Commercial | 2019-05-08 | 2019-05-08 | 2022-07-11 | 2023-06-22 | 2023-06-22 | Underground | R15 | 2023-06-22 | 1 | 829 | 249 |  | 1077 | 2019 | 2023 | R15
158807255233 | 158900233807 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2019-03-19 | 2019-04-29 | 2021-11-05 | 2023-06-12 | 2023-07-25 | Underground | R15 | 2023-06-12 | 30 | 660 | 417 | 32 | 1136 | 2019 | 2023 | R15
154746204477 | 150907477746 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential | 2019-05-24 | 2019-05-24 | 2020-09-22 | 2020-11-30 | 2020-12-28 | Underground | R15 | 2020-11-30 | 1 | 348 | 50 | 21 | 417 | 2019 | 2020 | R15
150815157178 | 154172178815 | CUSTOMER UPGRADE IN SERVICE | UG R15 RES NON RES BUDG 225 | Commercial | 2019-02-20 | 2019-02-20 | 2019-07-08 | 2020-04-03 | 2020-05-27 | Underground | R15 | 2020-04-03 | 1 | 99 | 195 | 39 | 331 | 2019 | 2020 | R15
154073160428 | 159535428073 | CUSTOMER UPGRADE IN SERVICE | UG RES INDIVIDUAL | Commercial | 2019-05-17 | 2019-05-17 | 2019-08-07 | 2020-07-27 | 2021-03-24 | Underground | R15 | 2020-07-27 | 1 | 59 | 254 | 173 | 484 | 2019 | 2021 | R15
155285216160 | 157555160285 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Residential | 2020-08-29 | 2020-08-29 | 2021-01-04 | 2021-07-20 | 2023-02-10 | Overhead | R15 | 2021-07-20 | 0 | 91 | 142 | 409 | 640 | 2020 | 2023 | R15
151157245876 | 159746876157 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential | 2021-05-25 | 2021-06-12 | 2021-08-31 | 2022-04-21 | 2022-05-12 | Underground | R15 | 2022-04-21 | 14 | 57 | 168 | 16 | 253 | 2021 | 2022 | R15
152195224650 | 150102650195 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-09-10 | 2021-01-23 | 2021-03-24 | 2023-08-09 | 2023-09-08 | Underground | R15 | 2023-08-09 | 97 | 43 | 621 | 23 | 782 | 2020 | 2023 | R15
153042282817 | 153782817042 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2021-05-07 | 2021-08-05 | 2022-06-16 | 2022-09-03 | 2022-09-06 | Overhead | R15 | 2022-09-03 | 65 | 226 | 57 | 2 | 348 | 2021 | 2022 | R15
153362221098 | 155423098362 | CUSTOMER UPGRADE IN SERVICE | UG R15 RES NON RES BUDG 225 | Commercial | 2020-10-02 | 2020-10-10 | 2021-02-23 | 2021-06-17 | 2022-02-01 | Underground | R15 | 2021-06-17 | 6 | 97 | 83 | 164 | 348 | 2020 | 2022 | R15
153010284159 | 153059159010 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-03-24 | 2021-03-24 | 2022-06-30 | 2023-04-18 | 2023-05-23 | Underground | R15 | 2023-04-18 | 1 | 332 | 209 | 26 | 565 | 2021 | 2023 | R15
154430145914 | 157088914430 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-01-14 | 2019-01-23 | 2019-03-12 | 2019-05-02 | 2019-10-24 | Overhead | R15 | 2019-05-02 | 8 | 35 | 38 | 126 | 204 | 2019 | 2019 | R15
156714242734 | 159242734714 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential Subdivision | 2021-04-20 | 2021-05-13 | 2021-08-10 | 2022-01-06 | 2022-01-17 | Underground | R15 | 2022-01-06 | 18 | 64 | 108 | 8 | 195 | 2021 | 2022 | R15
159204245434 | 155649434204 | NON-RESIDENTIAL - WAREHOUSE | UG EXT NON RES | Commercial | 2020-11-18 | 2020-11-18 | 2021-08-26 | 2022-09-19 | 2022-08-29 | Underground | R15 | 2022-09-19 | 1 | 202 | 278 |  | 464 | 2020 | 2022 | R15
154433252363 | 155479363433 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-10-02 | 2020-10-02 | 2021-10-15 | 2022-03-16 | 2022-05-09 | Underground | R15 | 2022-03-16 | 1 | 271 | 109 | 39 | 417 | 2020 | 2022 | R15
154270261363 | 158436363270 | FOREIGN UTILITY | UG EXT NON RES | Commercial | 2021-05-19 | 2021-09-05 | 2021-12-15 | 2022-05-15 | 2022-09-08 | Underground | R15 | 2022-05-15 | 78 | 73 | 108 | 84 | 342 | 2021 | 2022 | R15
157970227860 | 151195860970 | NON-RESIDENTIAL - SMALL RETAIL | OH EXTENSION NON RESD OD | Commercial | 2019-05-29 | 2019-05-29 | 2021-04-20 | 2021-12-10 | 2022-01-26 | Overhead | R15 | 2021-12-10 | 1 | 495 | 169 | 34 | 696 | 2019 | 2022 | R15
150552244831 | 150553831552 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential | 2020-07-28 | 2020-07-28 | 2021-08-23 |  | 2022-10-29 | Underground | R15 | 2021-09-01 | 1 | 280 | 8 | 303 | 589 | 2020 | 2022 | R15
157723277238 | 156910238723 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Residential Subdivision | 2021-04-09 | 2021-04-14 | 2022-04-27 | 2023-05-01 | 2023-06-16 | Overhead | R15 | 2023-05-01 | 4 | 271 | 264 | 35 | 571 | 2021 | 2023 | R15
156865153229 | 157695229865 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2019-01-16 | 2019-02-21 | 2019-05-23 | 2019-06-18 | 2019-08-21 | Overhead | R15 | 2019-06-18 | 27 | 66 | 19 | 47 | 156 | 2019 | 2019 | R15
153424263044 | 151453044424 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2021-02-01 | 2021-04-22 | 2021-12-30 | 2022-01-14 | 2022-01-31 | Overhead | R15 | 2022-01-14 | 59 | 181 | 12 | 12 | 261 | 2021 | 2022 | R15
155843239489 | 156710489843 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-08-26 | 2020-09-29 | 2021-07-19 | 2022-10-07 | 2023-02-21 | Underground | R15 | 2022-10-07 | 25 | 210 | 320 | 98 | 650 | 2020 | 2023 | R15
155357277271 | 155460271357 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-02-19 | 2021-09-03 | 2022-04-27 | 2022-06-17 | 2022-06-30 | Underground | R15 | 2022-06-17 | 141 | 169 | 38 | 10 | 355 | 2021 | 2022 | R15
155068170939 | 154937939068 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-02-25 | 2019-02-25 | 2019-11-07 | 2019-12-24 | 2020-02-12 | Overhead | R15 | 2019-12-24 | 1 | 184 | 34 | 37 | 253 | 2019 | 2020 | R15
159954199193 | 152839193954 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2019-04-11 | 2019-08-14 | 2020-08-03 | 2021-02-24 | 2021-04-16 | Underground | R15 | 2021-02-24 | 90 | 254 | 148 | 38 | 527 | 2019 | 2021 | R15
152114239830 | 154726830114 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-11-14 | 2021-01-11 | 2021-07-20 | 2022-02-18 | 2022-03-29 | Underground | R15 | 2022-02-18 | 41 | 137 | 154 | 28 | 357 | 2020 | 2022 | R15
152945168131 | 155302131945 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2019-04-25 | 2019-08-22 | 2019-10-15 | 2020-05-04 | 2020-06-11 | Overhead | R15 | 2020-05-04 | 86 | 39 | 145 | 29 | 296 | 2019 | 2020 | R15
153847194010 | 155380010847 | Electric Vehicle | UG EXT NON RES | Commercial | 2019-01-04 | 2019-05-09 | 2020-06-11 | 2021-05-21 | 2021-08-31 | Underground | R15 | 2021-05-21 | 90 | 286 | 247 | 73 | 693 | 2019 | 2021 | R15
158567263163 | 151245163567 | RESIDENTIAL - MULTI-FAMILY | OH RESD INDIVIDUAL OD | Residential | 2021-04-28 | 2021-04-28 | 2022-01-03 | 2023-07-31 | 2023-09-20 | Overhead | R15 | 2023-07-31 | 1 | 179 | 411 | 38 | 626 | 2021 | 2023 | R15
153144279049 | 156054049144 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG RES INDIVIDUAL | Residential | 2021-01-11 | 2021-01-11 | 2022-05-12 | 2022-10-05 | 2022-10-31 | Underground | R15 | 2022-10-05 | 1 | 349 | 105 | 19 | 471 | 2021 | 2022 | R15
156015250144 | 151352144015 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG RES INDIVIDUAL | Residential | 2020-09-16 | 2021-01-12 | 2021-09-30 | 2023-05-04 | 2023-08-14 | Underground | R15 | 2023-05-04 | 85 | 188 | 416 | 73 | 759 | 2020 | 2023 | R15
159485226717 | 155894717485 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2020-11-19 | 2021-02-24 | 2021-04-14 | 2022-02-17 | 2022-03-08 | Overhead | R15 | 2022-02-17 | 70 | 36 | 222 | 14 | 339 | 2020 | 2022 | R15
159485226717 | 155894717485 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Commercial | 2020-11-19 | 2021-02-24 | 2021-04-14 | 2022-02-17 | 2022-03-08 | Underground | R15 | 2022-02-17 | 70 | 36 | 222 | 14 | 339 | 2020 | 2022 | R15
153227221410 | 159052410227 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential Subdivision | 2020-12-07 | 2020-12-07 | 2021-02-23 | 2021-06-02 | 2021-07-01 | Underground | R15 | 2021-06-02 | 1 | 57 | 72 | 22 | 149 | 2020 | 2021 | R15
158625182334 | 150829334625 | CUSTOMER UPGRADE IN SERVICE | UG R15 RES NON RES BUDG 225 | Residential | 2019-02-01 | 2019-03-19 | 2020-02-28 |  | 2022-06-06 | Underground | R15 |  | 33 | 249 |  |  | 872 | 2019 | 2022 | R15
157793243104 | 157810104793 | Electric Vehicle | UG EXT NON RES | Commercial | 2021-03-02 | 2021-03-02 | 2021-08-11 | 2023-01-04 | 2023-02-08 | Underground | R15 | 2023-01-04 | 1 | 117 | 366 | 26 | 507 | 2021 | 2023 | R15
151085272682 | 151233682085 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-02-01 | 2021-02-01 | 2022-03-15 | 2022-06-27 | 2022-07-08 | Underground | R15 | 2022-06-27 | 1 | 292 | 75 | 10 | 375 | 2021 | 2022 | R15
153424263047 | 151454047424 | NON-RESIDENTIAL - WAREHOUSE | UG EXT NON RES | Commercial | 2021-02-01 | 2021-04-22 | 2021-12-30 | 2022-06-29 | 2022-07-25 | Underground | R15 | 2022-06-29 | 59 | 181 | 130 | 19 | 386 | 2021 | 2022 | R15
155843266359 | 154439359843 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-09-29 | 2020-09-29 | 2022-01-27 | 2023-08-24 | 2023-11-24 | Underground | R15 | 2023-08-24 | 1 | 348 | 411 | 67 | 824 | 2020 | 2023 | R15
153162250833 | 157047833162 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2020-08-27 | 2020-08-27 | 2021-10-06 | 2022-04-18 | 2022-05-27 | Underground | R15 | 2022-04-18 | 1 | 290 | 139 | 30 | 457 | 2020 | 2022 | R15
157534268429 | 151796429534 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2020-11-02 | 2020-11-02 | 2022-02-10 | 2022-06-09 | 2023-10-12 | Underground | R15 | 2022-06-09 | 1 | 334 | 86 | 351 | 769 | 2020 | 2023 | R15
159189239046 | 159373046189 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2020-10-21 | 2020-11-30 | 2021-07-14 | 2021-08-20 | 2022-02-16 | Overhead | R15 | 2021-08-20 | 29 | 163 | 28 | 129 | 346 | 2020 | 2022 | R15
151320270590 | 154711590320 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2021-02-16 | 2021-02-16 | 2022-02-25 | 2022-03-25 | 2023-01-05 | Overhead | R15 | 2022-03-25 | 1 | 269 | 21 | 205 | 493 | 2021 | 2023 | R15
157238217407 | 159097407238 | INDUSTRIAL | UG EXT NON RES | Commercial | 2020-07-21 | 2020-11-09 | 2021-01-14 | 2021-06-17 | 2021-10-14 | Underground | R15 | 2021-06-17 | 80 | 49 | 111 | 86 | 323 | 2020 | 2021 | R15
154564159728 | 150879728564 | INDUSTRIAL | UG EXT NON RES | Commercial | 2019-02-01 | 2019-02-01 | 2019-08-01 | 2020-05-11 | 2020-08-25 | Underground | R15 | 2020-05-11 | 1 | 130 | 203 | 77 | 408 | 2019 | 2020 | R15
158009239480 | 158030480009 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-05-18 | 2021-05-18 | 2021-07-18 | 2021-08-16 | 2021-08-20 | Underground | R15 | 2021-08-16 | 1 | 44 | 21 | 5 | 69 | 2021 | 2021 | R15
158164275777 | 158592777164 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Commercial | 2020-07-16 | 2020-07-16 | 2022-04-15 | 2022-09-21 | 2023-02-13 | Underground | R15 | 2022-09-21 | 1 | 457 | 114 | 104 | 673 | 2020 | 2023 | R15
151707260445 | 150251445707 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-05-27 | 2021-05-31 | 2021-12-08 | 2022-08-23 | 2022-09-06 | Underground | R15 | 2022-08-23 | 3 | 138 | 185 | 11 | 334 | 2021 | 2022 | R15
155800232619 | 150923619800 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-03-16 | 2021-04-08 | 2021-05-27 |  | 2021-10-03 | Overhead | R15 | 2021-06-15 | 18 | 36 | 14 | 79 | 144 | 2021 | 2021 | R15
156894195378 | 153119378894 | NON-RESIDENTIAL - SMALL RETAIL | UG EXT NON RES | Commercial | 2019-04-12 | 2019-04-12 | 2020-06-26 | 2020-10-01 | 2021-11-22 | Underground | R15 | 2020-10-01 | 1 | 316 | 70 | 298 | 682 | 2019 | 2021 | R15
151743184466 | 150822466743 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2019-02-01 | 2019-03-06 | 2020-03-18 | 2020-09-01 | 2021-11-23 | Underground | R15 | 2020-09-01 | 24 | 271 | 120 | 321 | 733 | 2019 | 2021 | R15
157493243878 | 157495878493 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2020-08-28 | 2020-09-23 | 2021-08-17 | 2021-09-11 | 2023-09-17 | Underground | R15 | 2021-09-11 | 19 | 235 | 19 | 525 | 796 | 2020 | 2023 | R15
157723277138 | 151355138723 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential Subdivision | 2020-07-31 | 2021-05-27 | 2022-04-27 | 2023-04-26 | 2023-06-28 | Underground | R15 | 2023-04-26 | 215 | 240 | 261 | 46 | 759 | 2020 | 2023 | R15
154122227186 | 158808186122 | CUSTOMER UPGRADE IN SERVICE | UG EXT NON RES | Commercial | 2021-01-22 | 2021-01-22 | 2021-04-16 | 2021-05-13 | 2021-07-26 | Underground | R15 | 2021-05-13 | 1 | 61 | 20 | 53 | 132 | 2021 | 2021 | R15
152867210527 | 150626527867 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-10-26 | 2020-10-29 | 2020-11-12 | 2021-09-02 | 2021-10-19 | Underground | R15 | 2021-09-02 | 4 | 11 | 211 | 34 | 257 | 2020 | 2021 | R15
151085271027 | 151238027085 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-02-01 | 2021-02-01 | 2022-03-01 | 2023-04-25 | 2023-08-03 | Underground | R15 | 2023-04-25 | 1 | 282 | 301 | 73 | 654 | 2021 | 2023 | R15
151028256953 | 150709953028 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2020-10-27 | 2021-02-17 | 2021-11-16 | 2022-05-03 | 2022-05-18 | Overhead | R15 | 2022-05-03 | 82 | 195 | 121 | 12 | 407 | 2020 | 2022 | R15
156555170070 | 153980070555 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-04-17 | 2019-04-17 | 2019-10-30 | 2020-12-07 | 2021-11-12 | Underground | R15 | 2020-12-07 | 1 | 141 | 289 | 245 | 673 | 2019 | 2021 | R15
157352230024 | 152769024352 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2021-03-24 | 2021-04-20 | 2021-05-08 | 2022-09-27 | 2022-09-30 | Overhead | R15 | 2022-09-27 | 20 | 14 | 362 | 4 | 398 | 2021 | 2022 | R15
158376288265 | 158952265376 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG RES INDIVIDUAL | Residential | 2021-04-19 | 2021-10-24 | 2022-08-08 | 2022-12-22 | 2023-01-11 | Underground | R15 | 2022-12-22 | 135 | 206 | 99 | 15 | 453 | 2021 | 2023 | R15
150941253986 | 152757986941 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-08-11 | 2020-09-30 | 2021-10-27 | 2021-12-15 | 2022-01-05 | Underground | R15 | 2021-12-15 | 37 | 281 | 36 | 16 | 367 | 2020 | 2022 | R15
150530295110 | 151818110530 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-11-02 | 2020-11-02 | 2022-09-27 | 2023-03-05 | 2023-11-30 | Underground | R15 | 2023-03-05 | 1 | 497 | 114 | 194 | 804 | 2020 | 2023 | R15
157579240976 | 159063976579 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2020-07-20 | 2020-07-28 | 2021-07-28 | 2023-03-10 | 2023-06-28 | Overhead | R15 | 2023-03-10 | 7 | 262 | 423 | 79 | 768 | 2020 | 2023 | R15
155000176352 | 154923352000 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-04-23 | 2019-04-23 | 2020-01-10 | 2021-01-06 | 2021-11-12 | Underground | R15 | 2021-01-06 | 1 | 189 | 259 | 223 | 669 | 2019 | 2021 | R15
150567236704 | 153608704567 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-03-26 | 2021-03-26 | 2021-06-25 | 2021-09-15 | 2021-10-01 | Underground | R15 | 2021-09-15 | 1 | 66 | 59 | 13 | 136 | 2021 | 2021 | R15
159508174909 | 151222909508 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-05-28 | 2019-05-31 | 2019-12-19 | 2020-06-23 | 2020-09-01 | Underground | R15 | 2020-06-23 | 4 | 145 | 134 | 51 | 331 | 2019 | 2020 | R15
158882224652 | 158723652882 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential Subdivision | 2019-05-14 | 2019-05-14 | 2021-03-24 | 2022-12-15 | 2023-02-02 | Underground | R15 | 2022-12-15 | 1 | 487 | 452 | 36 | 973 | 2019 | 2023 | R15
156664222700 | 152695700664 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-11-04 | 2020-11-07 | 2021-03-05 | 2021-05-03 | 2021-06-18 | Underground | R15 | 2021-05-03 | 3 | 85 | 42 | 35 | 163 | 2020 | 2021 | R15
156687232676 | 156746676687 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential Subdivision | 2019-01-11 | 2019-01-11 | 2021-05-28 | 2022-01-19 | 2022-03-08 | Underground | R15 | 2022-01-19 | 1 | 621 | 169 | 35 | 823 | 2019 | 2022 | R15
150315314766 | 150213766315 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Residential | 2021-04-23 | 2021-10-26 | 2023-04-04 | 2023-08-01 | 2023-08-23 | Overhead | R15 | 2023-08-01 | 133 | 376 | 86 | 17 | 609 | 2021 | 2023 | R15
158477183047 | 150470047477 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-05-22 | 2019-10-01 | 2020-03-05 | 2020-08-18 | 2020-11-19 | Underground | R15 | 2020-08-18 | 95 | 113 | 119 | 68 | 392 | 2019 | 2020 | R15
155469204482 | 157901482469 | CUSTOMER UPGRADE IN SERVICE | UG R15 RES NON RES BUDG 225 | Commercial | 2019-01-17 | 2020-08-22 | 2020-09-21 | 2021-01-12 | 2021-03-22 | Underground | R15 | 2021-01-12 | 417 | 21 | 82 | 50 | 568 | 2019 | 2021 | R15
159336303019 | 153645019336 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-05-06 | 2021-09-22 | 2022-12-20 | 2023-10-13 | 2023-11-14 | Underground | R15 | 2023-10-13 | 100 | 325 | 214 | 23 | 659 | 2021 | 2023 | R15
159372163447 | 154137447372 | AGRICULTURAL | OH EXTENSION NON RESD OD | Commercial | 2019-04-18 | 2019-04-18 | 2019-09-05 | 2020-05-27 | 2020-11-06 | Overhead | R15 | 2020-05-27 | 1 | 101 | 190 | 118 | 407 | 2019 | 2020 | R15
151653236188 | 159735188653 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-03-10 | 2021-06-04 | 2021-06-22 | 2022-08-01 | 2022-08-09 | Overhead | R15 | 2022-08-01 | 63 | 13 | 290 | 7 | 370 | 2021 | 2022 | R15
151605171617 | 151686617605 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-05-31 | 2019-05-31 | 2019-11-13 | 2022-12-07 | 2022-12-22 | Underground | R15 | 2022-12-07 | 1 | 119 | 801 | 12 | 930 | 2019 | 2022 | R15
157718181850 | 157854850718 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2019-05-07 | 2019-05-07 | 2020-02-25 | 2020-10-30 | 2021-01-28 | Underground | R15 | 2020-10-30 | 1 | 211 | 179 | 65 | 453 | 2019 | 2021 | R15
150523282970 | 151649970523 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2020-11-02 | 2020-11-02 | 2022-06-16 | 2022-07-18 | 2023-10-15 | Underground | R15 | 2022-07-18 | 1 | 424 | 23 | 325 | 770 | 2020 | 2023 | R15
152406241288 | 156726288406 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2020-10-08 | 2021-01-05 | 2021-07-29 | 2021-08-18 | 2021-10-25 | Overhead | R15 | 2021-08-18 | 64 | 148 | 15 | 49 | 273 | 2020 | 2021 | R15
155893228582 | 159962582893 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG RES INDIVIDUAL | Residential | 2020-10-23 | 2020-12-08 | 2021-04-27 | 2021-08-02 | 2021-10-18 | Underground | R15 | 2021-08-02 | 33 | 101 | 70 | 56 | 257 | 2020 | 2021 | R15
159528280810 | 159485810528 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-12-09 | 2020-12-09 | 2022-05-26 | 2022-11-10 | 2022-12-09 | Underground | R15 | 2022-11-10 | 1 | 382 | 121 | 22 | 523 | 2020 | 2022 | R15
151743192796 | 156553796743 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2019-03-06 | 2019-03-06 | 2020-06-02 | 2020-10-21 | 2021-04-13 | Underground | R15 | 2020-10-21 | 1 | 325 | 102 | 125 | 550 | 2019 | 2021 | R15
151157229985 | 152790985157 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential Subdivision | 2021-02-08 | 2021-02-27 | 2021-05-07 | 2022-01-12 | 2022-02-04 | Underground | R15 | 2022-01-12 | 15 | 50 | 179 | 18 | 260 | 2021 | 2022 | R15
154034238575 | 156156575034 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2020-11-20 | 2020-11-20 | 2021-07-12 | 2022-06-02 | 2022-06-16 | Underground | R15 | 2022-06-02 | 1 | 167 | 234 | 11 | 410 | 2020 | 2022 | R15
159028276474 | 151828474028 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential Subdivision | 2020-11-02 | 2020-11-02 | 2022-04-20 | 2022-08-06 | 2023-11-30 | Underground | R15 | 2022-08-06 | 1 | 383 | 78 | 344 | 804 | 2020 | 2023 | R15
150464241417 | 150465417464 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential | 2020-07-28 | 2020-07-28 | 2021-07-30 | 2021-08-19 | 2023-09-05 | Underground | R15 | 2021-08-19 | 1 | 264 | 15 | 534 | 811 | 2020 | 2023 | R15
150361163522 | 157264522361 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential Subdivision | 2019-01-15 | 2019-01-15 | 2019-09-05 | 2020-12-07 | 2021-09-23 | Underground | R15 | 2020-12-07 | 1 | 168 | 328 | 209 | 703 | 2019 | 2021 | R15
159486177626 | 159488626486 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Residential | 2019-05-16 | 2019-08-27 | 2020-01-21 | 2020-01-29 | 2020-09-18 | Underground | R15 | 2020-01-29 | 74 | 106 | 7 | 168 | 352 | 2019 | 2020 | R15
153049170248 | 155722248049 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-03-01 | 2019-06-13 | 2019-10-30 | 2020-06-02 | 2020-09-18 | Underground | R15 | 2020-06-02 | 75 | 100 | 155 | 79 | 406 | 2019 | 2020 | R15
157304286443 | 159893443304 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2020-10-23 | 2021-09-01 | 2022-07-21 | 2022-08-11 | 2023-09-17 | Underground | R15 | 2022-08-11 | 224 | 232 | 16 | 287 | 756 | 2020 | 2023 | R15
155579263575 | 155660575579 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2021-05-14 | 2021-05-14 | 2022-01-05 | 2022-03-31 | 2022-04-18 | Underground | R15 | 2022-03-31 | 1 | 169 | 62 | 13 | 242 | 2021 | 2022 | R15
150147248770 | 156079770147 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Commercial | 2021-02-24 | 2021-02-24 | 2021-09-21 | 2022-06-21 | 2021-11-12 | Underground | R15 | 2022-06-21 | 1 | 150 | 196 |  | 188 | 2021 | 2021 | R15
150816160407 | 158521407816 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2019-01-23 | 2019-01-23 | 2019-08-07 | 2020-01-30 | 2022-10-29 | Underground | R15 | 2020-01-30 | 1 | 141 | 127 | 717 | 983 | 2019 | 2022 | R15
150832260760 | 159909760832 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-04-22 | 2021-08-16 | 2021-12-10 | 2021-12-22 | 2022-06-20 | Overhead | R15 | 2021-12-22 | 83 | 85 | 9 | 129 | 303 | 2021 | 2022 | R15
150060273711 | 152978711060 | Affordable Housing | UG DEV RES | Commercial | 2020-12-22 | 2022-02-17 | 2022-03-24 | 2022-11-09 | 2022-12-19 | Underground | R15 | 2022-11-09 | 303 | 26 | 165 | 29 | 520 | 2020 | 2022 | R15
155483256839 | 151028839483 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2021-04-28 | 2021-04-28 | 2021-11-17 | 2023-10-16 | 2023-10-23 | Overhead | R15 | 2023-10-16 | 1 | 146 | 499 | 6 | 649 | 2021 | 2023 | R15
155319271951 | 156414951319 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2020-11-21 | 2021-09-28 | 2022-03-08 | 2022-03-18 | 2022-04-13 | Overhead | R15 | 2022-03-18 | 222 | 116 | 9 | 19 | 363 | 2020 | 2022 | R15
156079237203 | 150034203079 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-01-27 | 2021-02-09 | 2021-06-29 | 2022-07-18 | 2022-08-02 | Underground | R15 | 2022-07-18 | 10 | 101 | 275 | 12 | 395 | 2021 | 2022 | R15
157466238337 | 157523337466 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2020-08-28 | 2020-08-28 | 2021-07-09 | 2022-07-11 | 2022-10-29 | Underground | R15 | 2022-07-11 | 1 | 226 | 262 | 80 | 566 | 2020 | 2022 | R15
153977208345 | 152351345977 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2020-09-22 | 2020-10-12 | 2020-10-26 | 2021-04-19 | 2022-07-29 | Underground | R15 | 2021-04-19 | 15 | 11 | 126 | 335 | 484 | 2020 | 2022 | R15
153977208345 | 152351345977 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential Subdivision | 2020-09-22 | 2020-10-12 | 2020-10-26 | 2021-04-19 | 2022-07-29 | Overhead | R15 | 2021-04-19 | 15 | 11 | 126 | 335 | 484 | 2020 | 2022 | R15
153396255558 | 150339558396 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2021-03-14 | 2021-06-04 | 2021-11-09 | 2022-03-04 | 2022-06-07 | Underground | R15 | 2022-03-04 | 60 | 113 | 84 | 68 | 322 | 2021 | 2022 | R15
156999222544 | 157580544999 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Residential | 2020-08-28 | 2020-10-27 | 2021-03-04 | 2023-08-28 | 2023-09-27 | Overhead | R15 | 2023-08-28 | 43 | 93 | 648 | 23 | 804 | 2020 | 2023 | R15
151969315586 | 158745586969 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2023-02-06 | 2023-02-09 | 2023-04-12 | 2023-06-16 | 2023-07-25 | Underground | R15 | 2023-06-16 | 4 | 45 | 48 | 28 | 122 | 2023 | 2023 | R15
156857286454 | 156322454857 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential Subdivision | 2021-08-05 | 2021-08-05 | 2022-07-22 | 2022-08-17 | 2022-10-03 | Underground | R15 | 2022-08-17 | 1 | 252 | 19 | 34 | 303 | 2021 | 2022 | R15
157619314245 | 157575245619 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2023-03-20 | 2023-03-20 | 2023-03-30 | 2023-04-24 | 2023-05-17 | Underground | R15 | 2023-04-24 | 1 | 9 | 18 | 18 | 43 | 2023 | 2023 | R15
156016330252 | 158946252016 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2023-07-03 | 2023-07-19 | 2023-08-22 | 2023-09-11 | 2023-09-27 | Overhead | R15 | 2023-09-11 | 13 | 25 | 15 | 13 | 63 | 2023 | 2023 | R15
154812272199 | 153935199812 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2021-07-28 | 2021-10-13 | 2022-03-11 | 2022-10-05 | 2022-10-25 | Underground | R15 | 2022-10-05 | 56 | 108 | 149 | 15 | 325 | 2021 | 2022 | R15
150958315355 | 157486355958 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential Subdivision | 2022-12-12 | 2023-01-27 | 2023-04-10 | 2023-10-31 | 2023-11-14 | Underground | R15 | 2023-10-31 | 35 | 52 | 147 | 11 | 242 | 2022 | 2023 | R15
159216314928 | 159079928216 | RESIDENTIAL - MULTI-FAMILY | UG RES INDIVIDUAL | Residential | 2021-08-17 | 2021-08-17 | 2023-04-06 | 2023-10-12 | 2023-11-15 | Underground | R15 | 2023-10-12 | 1 | 428 | 136 | 25 | 587 | 2021 | 2023 | R15
150307298524 | 154457524307 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential | 2021-09-10 | 2021-09-10 | 2022-10-27 | 2023-03-02 | 2023-03-09 | Underground | R15 | 2023-03-02 | 1 | 295 | 91 | 6 | 390 | 2021 | 2023 | R15
155319301483 | 155393483319 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2021-09-14 | 2022-04-19 | 2022-11-23 | 2023-05-05 | 2023-06-09 | Underground | R15 | 2023-05-05 | 156 | 157 | 118 | 26 | 454 | 2021 | 2023 | R15
157714298227 | 153383227714 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential Subdivision | 2021-09-03 | 2021-09-03 | 2022-10-25 | 2023-05-26 | 2023-08-24 | Underground | R15 | 2023-05-26 | 1 | 298 | 154 | 65 | 515 | 2021 | 2023 | R15
159927279875 | 150012875927 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2021-08-19 | 2021-12-16 | 2022-05-19 | 2022-05-31 | 2022-06-27 | Overhead | R15 | 2022-05-31 | 86 | 111 | 9 | 20 | 223 | 2021 | 2022 | R15
153387325259 | 159987259387 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2023-07-10 | 2023-07-10 | 2023-07-18 | 2023-08-02 | 2023-08-16 | Overhead | R15 | 2023-08-02 | 1 | 7 | 12 | 11 | 28 | 2023 | 2023 | R15
152696263333 | 158357333696 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Residential | 2021-08-13 | 2021-08-26 | 2022-01-04 | 2022-11-10 | 2022-12-06 | Overhead | R15 | 2022-11-10 | 10 | 94 | 223 | 19 | 343 | 2021 | 2022 | R15
156961286315 | 156294315961 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential Subdivision | 2021-08-05 | 2021-08-05 | 2022-07-21 | 2022-08-19 | 2022-10-03 | Underground | R15 | 2022-08-19 | 1 | 251 | 22 | 32 | 303 | 2021 | 2022 | R15
156041191125 | 152011125041 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-07-25 | 2020-01-30 | 2020-05-15 | 2020-10-02 | 2022-10-29 | Underground | R15 | 2020-10-02 | 136 | 77 | 101 | 541 | 852 | 2019 | 2022 | R15
154583175841 | 150566841583 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Residential | 2019-07-17 | 2019-10-14 | 2020-01-06 | 2020-04-14 | 2020-07-29 | Overhead | R15 | 2020-04-14 | 64 | 61 | 72 | 77 | 271 | 2019 | 2020 | R15
154003238146 | 154019146003 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Residential | 2019-08-06 | 2019-09-04 | 2021-07-08 | 2022-06-05 | 2022-08-29 | Underground | R15 | 2022-06-05 | 22 | 482 | 237 | 61 | 800 | 2019 | 2022 | R15
152975175544 | 157024544975 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-10-15 | 2019-10-29 | 2019-12-31 | 2020-02-10 | 2020-11-10 | Underground | R15 | 2020-02-10 | 11 | 46 | 30 | 197 | 281 | 2019 | 2020 | R15
156315218363 | 156208363315 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2019-12-04 | 2020-05-06 | 2021-01-25 | 2021-10-11 | 2021-11-03 | Underground | R15 | 2021-10-11 | 111 | 189 | 186 | 18 | 501 | 2019 | 2021 | R15
158211226597 | 158184597211 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-12-13 | 2019-12-13 | 2021-04-13 | 2021-08-31 | 2021-10-19 | Underground | R15 | 2021-08-31 | 1 | 348 | 101 | 36 | 483 | 2019 | 2021 | R15
159010170355 | 151424355010 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2019-09-17 | 2019-09-17 | 2019-11-01 | 2020-12-21 | 2021-04-01 | Overhead | R15 | 2020-12-21 | 1 | 34 | 297 | 74 | 403 | 2019 | 2021 | R15
159941189906 | 159849906941 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2019-07-15 | 2019-07-15 | 2020-05-04 | 2021-05-17 | 2021-06-25 | Underground | R15 | 2021-05-17 | 1 | 211 | 271 | 30 | 510 | 2019 | 2021 | R15
155983270024 | 155943024983 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential Subdivision | 2019-06-25 | 2019-06-25 | 2022-02-22 | 2023-03-09 | 2023-04-17 | Underground | R15 | 2023-03-09 | 1 | 696 | 273 | 28 | 995 | 2019 | 2023 | R15
159551177876 | 159996876551 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-07-15 | 2019-08-07 | 2020-01-24 | 2020-11-03 | 2020-12-16 | Underground | R15 | 2020-11-03 | 18 | 123 | 203 | 32 | 373 | 2019 | 2020 | R15
159437242936 | 153640936437 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-09-30 | 2019-09-30 | 2021-08-11 | 2022-09-16 | 2022-10-05 | Underground | R15 | 2022-09-16 | 1 | 488 | 288 | 14 | 788 | 2019 | 2022 | R15
152938199028 | 153021028938 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2019-09-25 | 2019-09-25 | 2020-07-30 | 2021-05-17 | 2021-05-21 | Underground | R15 | 2021-05-17 | 1 | 222 | 208 | 5 | 433 | 2019 | 2021 | R15
158620175591 | 151865591620 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-09-19 | 2019-11-21 | 2020-01-02 | 2020-04-16 | 2020-12-21 | Underground | R15 | 2020-04-16 | 46 | 31 | 76 | 178 | 328 | 2019 | 2020 | R15
150958185938 | 152747938958 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-09-24 | 2019-09-24 | 2020-04-01 | 2022-01-03 | 2022-01-19 | Underground | R15 | 2022-01-03 | 1 | 137 | 459 | 13 | 607 | 2019 | 2022 | R15
151328180175 | 156147175328 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-10-10 | 2019-10-10 | 2020-02-12 | 2020-06-05 | 2020-08-25 | Underground | R15 | 2020-06-05 | 1 | 90 | 83 | 58 | 229 | 2019 | 2020 | R15
152529224069 | 153636069529 | NON-RESIDENTIAL - LARGE OFFICE | OH EXTENSION NON RESD OD | Commercial | 2019-11-19 | 2020-12-16 | 2021-03-18 | 2021-04-05 | 2021-06-08 | Overhead | R15 | 2021-04-05 | 282 | 67 | 13 | 47 | 406 | 2019 | 2021 | R15
151406251195 | 151315195406 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential Subdivision | 2019-09-17 | 2019-09-17 | 2021-10-08 | 2022-07-12 | 2022-08-01 | Underground | R15 | 2022-07-12 | 1 | 539 | 198 | 15 | 750 | 2019 | 2022 | R15
153668176978 | 153719978668 | AGRICULTURAL | OH EXTENSION NON RESD OD | Commercial | 2019-08-05 | 2019-09-05 | 2020-01-15 | 2020-02-06 | 2020-07-21 | Overhead | R15 | 2020-02-06 | 24 | 95 | 17 | 119 | 252 | 2019 | 2020 | R15
152798174201 | 152399201798 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-07-30 | 2019-09-09 | 2019-12-11 | 2020-01-31 | 2021-11-12 | Underground | R15 | 2020-01-31 | 30 | 68 | 38 | 466 | 599 | 2019 | 2021 | R15
159818184805 | 157948805818 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-07-03 | 2019-08-28 | 2020-03-20 | 2020-09-17 | 2022-10-29 | Underground | R15 | 2020-09-17 | 41 | 148 | 130 | 552 | 868 | 2019 | 2022 | R15
158592170342 | 158660342592 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-10-23 | 2019-10-23 | 2019-10-31 | 2021-09-30 | 2022-05-25 | Underground | R15 | 2021-09-30 | 1 | 7 | 501 | 170 | 676 | 2019 | 2022 | R15
155250171474 | 155104474250 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-06-19 | 2019-07-22 | 2019-11-12 | 2021-06-02 | 2022-03-03 | Underground | R15 | 2021-06-02 | 24 | 82 | 407 | 197 | 707 | 2019 | 2022 | R15
154561222368 | 154580368561 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2019-10-03 | 2019-10-03 | 2021-03-03 | 2022-02-10 | 2022-02-24 | Underground | R15 | 2022-02-10 | 1 | 370 | 247 | 11 | 626 | 2019 | 2022 | R15
152787193081 | 152862081787 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2019-09-25 | 2019-09-25 | 2020-06-02 | 2020-11-17 | 2021-03-12 | Underground | R15 | 2020-11-17 | 1 | 180 | 121 | 84 | 383 | 2019 | 2021 | R15
150519158003 | 153807003519 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2019-06-13 | 2019-07-08 | 2019-07-15 | 2019-08-14 | 2019-08-20 | Overhead | R15 | 2019-08-14 | 18 | 6 | 23 | 5 | 49 | 2019 | 2019 | R15
151406220933 | 150974933406 | RESIDENTIAL - SINGLE FAMILY ATTACHED | OH SUBDIVISION RESD OD | Residential Subdivision | 2019-11-04 | 2019-11-04 | 2021-02-19 | 2021-03-29 | 2021-05-05 | Overhead | R15 | 2021-03-29 | 1 | 340 | 27 | 28 | 393 | 2019 | 2021 | R15
155449199334 | 153300334449 | FOREIGN UTILITY | UG EXT NON RES | Commercial | 2019-11-14 | 2020-04-30 | 2020-08-03 | 2021-02-10 | 2021-04-20 | Underground | R15 | 2021-02-10 | 121 | 68 | 138 | 50 | 374 | 2019 | 2021 | R15
156817188963 | 158358963817 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-12-16 | 2020-02-21 | 2020-04-24 | 2020-05-19 | 2020-08-25 | Overhead | R15 | 2020-05-19 | 50 | 46 | 18 | 71 | 182 | 2019 | 2020 | R15
159437240896 | 153631896437 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-09-30 | 2019-09-30 | 2021-07-29 | 2022-02-01 | 2022-06-21 | Underground | R15 | 2022-02-01 | 1 | 479 | 134 | 101 | 712 | 2019 | 2022 | R15
153070176970 | 154011970070 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Commercial | 2019-10-01 | 2019-10-10 | 2020-01-15 | 2020-08-07 | 2020-10-05 | Underground | R15 | 2020-08-07 | 8 | 70 | 148 | 42 | 265 | 2019 | 2020 | R15
151721189584 | 153790584721 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2019-08-05 | 2019-08-06 | 2020-04-30 | 2020-12-16 | 2021-02-26 | Underground | R15 | 2020-12-16 | 2 | 193 | 165 | 53 | 410 | 2019 | 2021 | R15
153307172036 | 156307036307 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2019-10-10 | 2019-11-01 | 2019-11-19 | 2019-12-09 | 2020-04-13 | Overhead | R15 | 2019-12-09 | 17 | 13 | 15 | 91 | 133 | 2019 | 2020 | R15
151194223654 | 151205654194 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Commercial | 2019-07-22 | 2019-07-22 | 2021-03-15 | 2021-09-22 | 2021-10-26 | Overhead | R15 | 2021-09-22 | 1 | 431 | 138 | 25 | 592 | 2019 | 2021 | R15
151194223654 | 151205654194 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH SUBDIVISION RESD OD | Commercial | 2019-07-22 | 2019-07-22 | 2021-03-15 | 2021-09-22 | 2021-10-26 | Overhead | R15 | 2021-09-22 | 1 | 431 | 138 | 25 | 592 | 2019 | 2021 | R15
156041196802 | 152013802041 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-07-25 | 2020-03-10 | 2020-07-08 | 2020-10-02 | 2021-04-06 | Underground | R15 | 2020-10-02 | 164 | 87 | 63 | 133 | 444 | 2019 | 2021 | R15
158793201248 | 156844248793 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Residential | 2019-10-14 | 2020-01-26 | 2020-08-20 | 2021-10-13 | 2021-10-25 | Overhead | R15 | 2021-10-13 | 75 | 149 | 300 | 9 | 531 | 2019 | 2021 | R15
150786217774 | 150069774786 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2019-07-15 | 2020-10-28 | 2021-01-21 | 2021-01-29 | 2021-03-18 | Overhead | R15 | 2021-01-29 | 338 | 62 | 7 | 35 | 439 | 2019 | 2021 | R15
159840169218 | 156346218840 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential Subdivision | 2019-06-26 | 2019-06-28 | 2019-10-25 | 2020-01-29 | 2021-02-25 | Underground | R15 | 2020-01-29 | 3 | 86 | 69 | 282 | 437 | 2019 | 2021 | R15
156857255067 | 156864067857 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-10-14 | 2019-10-14 | 2021-11-04 | 2022-12-01 | 2022-12-13 | Underground | R15 | 2022-12-01 | 1 | 539 | 281 | 9 | 827 | 2019 | 2022 | R15
155827168286 | 151291286827 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2019-07-22 | 2019-09-13 | 2019-10-15 | 2019-11-01 | 2022-03-28 | Overhead | R15 | 2019-11-01 | 40 | 23 | 14 | 627 | 701 | 2019 | 2022 | R15
155988207750 | 156020750988 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential Subdivision | 2019-06-25 | 2019-06-25 | 2020-10-21 | 2022-08-18 | 2022-08-31 | Underground | R15 | 2022-08-18 | 1 | 347 | 477 | 10 | 832 | 2019 | 2022 | R15
159171189660 | 153391660171 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG RES INDIVIDUAL | Commercial | 2019-08-01 | 2019-08-14 | 2020-05-01 | 2020-12-28 | 2021-03-03 | Underground | R15 | 2020-12-28 | 10 | 188 | 172 | 48 | 415 | 2019 | 2021 | R15
156624190246 | 156568246624 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-08-21 | 2019-08-21 | 2020-05-06 | 2021-03-17 | 2021-04-20 | Underground | R15 | 2021-03-17 | 1 | 186 | 226 | 25 | 435 | 2019 | 2021 | R15
156624183607 | 156567607624 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-08-21 | 2019-08-21 | 2020-03-10 | 2021-02-02 | 2022-03-28 | Underground | R15 | 2021-02-02 | 1 | 145 | 236 | 300 | 679 | 2019 | 2022 | R15
155974270565 | 155727565974 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential Subdivision | 2019-06-25 | 2019-06-25 | 2022-02-25 | 2023-03-08 | 2023-03-30 | Underground | R15 | 2023-03-08 | 1 | 699 | 269 | 17 | 983 | 2019 | 2023 | R15
151406251194 | 151314194406 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential Subdivision | 2019-09-17 | 2019-09-17 | 2021-10-08 | 2022-04-04 | 2022-05-11 | Underground | R15 | 2022-04-04 | 1 | 539 | 127 | 28 | 692 | 2019 | 2022 | R15
159618182669 | 151704669618 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2019-07-24 | 2019-08-14 | 2020-03-02 | 2020-05-11 | 2021-11-12 | Underground | R15 | 2020-05-11 | 16 | 144 | 51 | 395 | 603 | 2019 | 2021 | R15
157289197567 | 150628567289 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2019-10-31 | 2019-10-31 | 2020-07-16 | 2022-05-24 | 2022-07-08 | Underground | R15 | 2022-05-24 | 1 | 186 | 484 | 34 | 702 | 2019 | 2022 | R15
152976184626 | 150953626976 | NON-RESIDENTIAL - SMALL RETAIL | UG EXT NON RES | Commercial | 2019-09-13 | 2019-09-13 | 2020-03-19 | 2021-02-11 | 2021-04-20 | Underground | R15 | 2021-02-11 | 1 | 135 | 236 | 49 | 418 | 2019 | 2021 | R15
152677214439 | 152712439677 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-11-12 | 2019-11-12 | 2020-12-22 | 2022-01-26 | 2022-02-14 | Underground | R15 | 2022-01-26 | 1 | 291 | 287 | 14 | 590 | 2019 | 2022 | R15
154561220287 | 154578287561 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2019-10-03 | 2019-10-10 | 2021-02-11 | 2022-01-26 | 2022-02-11 | Underground | R15 | 2022-01-26 | 6 | 351 | 250 | 13 | 617 | 2019 | 2022 | R15
159437257264 | 153147264437 | RESIDENTIAL - MULTI-FAMILY | UG DEV RES | Residential | 2019-09-26 | 2019-09-26 | 2021-11-18 | 2022-10-19 | 2022-11-01 | Underground | R15 | 2022-10-19 | 1 | 561 | 240 | 10 | 809 | 2019 | 2022 | R15
156569200564 | 157472564569 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2019-01-15 | 2019-02-19 | 2020-08-13 | 2021-03-01 | 2021-04-01 | Underground | R15 | 2021-03-01 | 26 | 388 | 143 | 24 | 578 | 2019 | 2021 | R15
155118302489 | 155133489118 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Residential | 2022-03-10 | 2022-03-10 | 2022-12-06 | 2023-05-30 | 2023-11-03 | Underground | R15 | 2023-05-30 | 1 | 194 | 126 | 114 | 432 | 2022 | 2023 | R15
151619302294 | 159449294619 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Residential | 2022-01-05 | 2022-01-05 | 2022-12-05 | 2023-04-24 | 2023-05-26 | Overhead | R15 | 2023-04-24 | 1 | 239 | 101 | 25 | 363 | 2022 | 2023 | R15
159608266251 | 155972251608 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-10-29 | 2021-12-03 | 2022-01-26 | 2022-04-20 | 2022-04-25 | Overhead | R15 | 2022-04-20 | 26 | 39 | 61 | 4 | 127 | 2021 | 2022 | R15
158519298235 | 158508235519 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2022-03-28 | 2022-03-28 | 2022-10-26 | 2023-11-06 | 2023-11-14 | Underground | R15 | 2023-11-06 | 1 | 153 | 269 | 7 | 427 | 2022 | 2023 | R15
154693320253 | 156048253693 | RESIDENTIAL DEV OF LAND-NEW STREETS | UG MISC RES | Commercial | 2021-12-15 | 2021-12-15 | 2023-05-25 | 2023-06-16 | 2023-07-25 | Underground | R15 | 2023-06-16 | 1 | 377 | 17 | 28 | 420 | 2021 | 2023 | R15
155411279121 | 153581121411 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2022-01-22 | 2022-01-22 | 2022-05-12 | 2022-05-29 | 2023-01-25 | Overhead | R15 | 2022-05-29 | 0 | 79 | 12 | 173 | 263 | 2022 | 2023 | R15
157953320886 | 157954886953 | Electric Vehicle | UG EXT NON RES | Commercial | 2022-02-09 | 2022-02-09 | 2023-06-01 | 2023-09-28 | 2023-11-21 | Underground | R15 | 2023-09-28 | 1 | 342 | 86 | 39 | 465 | 2022 | 2023 | R15
157944294311 | 154077311944 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2022-04-26 | 2022-04-26 | 2022-09-20 | 2023-07-10 | 2023-07-25 | Underground | R15 | 2023-07-10 | 1 | 106 | 210 | 12 | 326 | 2022 | 2023 | R15
158755285513 | 155663513755 | AGRICULTURAL | UG EXT NON RES | Residential | 2022-05-21 | 2022-05-21 | 2022-07-13 | 2022-11-16 | 2022-12-06 | Underground | R15 | 2022-11-16 | 0 | 38 | 91 | 15 | 142 | 2022 | 2022 | R15
158755285513 | 155663513755 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2022-05-21 | 2022-05-21 | 2022-07-13 | 2022-11-16 | 2022-12-06 | Overhead | R15 | 2022-11-16 | 0 | 38 | 91 | 15 | 142 | 2022 | 2022 | R15
152645299319 | 152947319645 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential | 2022-03-02 | 2022-06-28 | 2022-11-03 | 2023-08-25 | 2023-11-03 | Underground | R15 | 2023-08-25 | 85 | 93 | 212 | 51 | 438 | 2022 | 2023 | R15
152209280012 | 154508012209 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2022-03-08 | 2022-03-21 | 2022-05-19 | 2023-01-09 | 2023-01-30 | Underground | R15 | 2023-01-09 | 10 | 44 | 168 | 16 | 235 | 2022 | 2023 | R15
151194279641 | 158179641194 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential Subdivision | 2022-02-10 | 2022-02-14 | 2022-05-16 | 2022-07-01 | 2022-07-26 | Underground | R15 | 2022-07-01 | 3 | 66 | 35 | 18 | 119 | 2022 | 2022 | R15
151265283137 | 153743137265 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-12-06 | 2021-12-20 | 2022-06-21 | 2022-06-27 | 2022-10-06 | Overhead | R15 | 2022-06-27 | 11 | 132 | 5 | 74 | 219 | 2021 | 2022 | R15
152201273459 | 154670459201 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2021-10-22 | 2021-10-22 | 2022-03-22 | 2022-03-29 | 2022-04-07 | Overhead | R15 | 2022-03-29 | 1 | 108 | 6 | 8 | 120 | 2021 | 2022 | R15
154110315419 | 154052419110 | NON-RESIDENTIAL - LARGE OFFICE | UG EXT NON RES | Commercial | 2022-09-28 | 2022-09-28 | 2023-04-12 | 2023-08-01 | 2023-08-18 | Underground | R15 | 2023-08-01 | 1 | 141 | 80 | 14 | 233 | 2022 | 2023 | R15
158234334297 | 155061297234 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2022-10-03 | 2022-10-04 | 2023-10-03 | 2023-10-13 | 2023-11-14 | Overhead | R15 | 2023-10-13 | 2 | 261 | 9 | 23 | 292 | 2022 | 2023 | R15
152808320889 | 152830889808 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG EXT NON RES | Commercial | 2022-08-10 | 2022-08-10 | 2023-06-01 | 2023-09-15 | 2023-11-21 | Underground | R15 | 2023-09-15 | 1 | 212 | 77 | 48 | 335 | 2022 | 2023 | R15
150509332990 | 154600990509 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential Subdivision | 2022-11-22 | 2023-05-16 | 2023-09-18 | 2023-10-03 | 2023-10-11 | Underground | R15 | 2023-10-03 | 126 | 90 | 12 | 7 | 232 | 2022 | 2023 | R15
154428318342 | 156240342428 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2022-12-05 | 2022-12-05 | 2023-05-08 | 2023-11-15 | 2023-12-29 | Underground | R15 | 2023-11-15 | 1 | 111 | 138 | 33 | 280 | 2022 | 2023 | R15
156815331492 | 155180492815 | RESIDENTIAL - MULTI-FAMILY | OH DEVELOPMENT RESD OD | Residential | 2022-11-29 | 2022-12-06 | 2023-09-01 | 2023-10-19 | 2023-11-15 | Overhead | R15 | 2023-10-19 | 6 | 194 | 35 | 20 | 252 | 2022 | 2023 | R15
158569312586 | 157663586569 | NON-RESIDENTIAL - MISCELLANEOUS | OH EXTENSION NON RESD OD | Commercial | 2022-09-01 | 2022-12-05 | 2023-03-15 | 2023-03-21 | 2023-04-17 | Overhead | R15 | 2023-03-21 | 68 | 73 | 5 | 20 | 163 | 2022 | 2023 | R15
150869328456 | 155268456869 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential Subdivision | 2022-11-29 | 2022-12-19 | 2023-08-16 | 2023-09-19 | 2023-10-02 | Underground | R15 | 2023-09-19 | 15 | 173 | 25 | 10 | 220 | 2022 | 2023 | R15
151546323277 | 155522277546 | CUSTOMER UPGRADE IN SERVICE | OH R15 VEHC NON RESD OD | Commercial | 2022-10-05 | 2022-10-25 | 2023-06-27 | 2023-10-09 | 2023-11-29 | Overhead | R15 | 2023-10-09 | 15 | 176 | 75 | 38 | 301 | 2022 | 2023 | R15
152544309401 | 156436401544 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH RESD INDIVIDUAL OD | Residential | 2022-08-25 | 2022-08-25 | 2023-02-14 | 2023-05-01 | 2023-08-14 | Overhead | R15 | 2023-05-01 | 1 | 124 | 55 | 76 | 253 | 2022 | 2023 | R15
158919272923 | 152206923919 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG SUB RES | Residential | 2021-06-04 | 2022-01-26 | 2022-03-16 | 2023-09-11 | 2023-10-10 | Underground | R15 | 2023-09-11 | 169 | 36 | 389 | 22 | 613 | 2021 | 2023 | R15
159927279877 | 151554877927 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2021-06-02 | 2021-12-16 | 2022-05-19 | 2022-10-22 | 2022-10-25 | Underground | R15 | 2022-10-22 | 142 | 111 | 112 | 2 | 365 | 2021 | 2022 | R15
151273267824 | 152489824273 | AGRICULTURAL | OH EXTENSION NON RESD OD | Commercial | 2021-06-07 | 2021-06-07 | 2022-02-07 | 2022-03-04 | 2022-08-29 | Overhead | R15 | 2022-03-04 | 1 | 176 | 20 | 127 | 321 | 2021 | 2022 | R15
153335295691 | 152685691335 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH WORK RELATED TO UG | Residential | 2021-06-07 | 2021-06-10 | 2022-10-03 | 2022-10-13 | 2022-11-01 | Overhead | R15 | 2022-10-13 | 4 | 343 | 9 | 14 | 367 | 2021 | 2022 | R15
153821220706 | 150540706821 | CUSTOMER UPGRADE IN SERVICE | UG EXT NON RES | Commercial | 2020-06-04 | 2020-09-25 | 2021-02-17 | 2021-05-14 | 2021-07-30 | Underground | R15 | 2021-05-14 | 82 | 104 | 63 | 56 | 302 | 2020 | 2021 | R15
155574204446 | 156951446574 | FOREIGN UTILITY | UG EXT NON RES | Commercial | 2020-07-09 | 2020-07-09 | 2020-09-21 | 2020-11-12 | 2021-02-03 | Underground | R15 | 2020-11-12 | 1 | 53 | 39 | 60 | 150 | 2020 | 2021 | R15
150428218904 | 153144904428 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Residential | 2020-02-28 | 2020-02-28 | 2021-01-28 | 2021-06-17 | 2021-07-20 | Overhead | R15 | 2021-06-17 | 1 | 240 | 101 | 24 | 363 | 2020 | 2021 | R15
159042210971 | 157087971042 | INDUSTRIAL | OH EXTENSION NON RESD OD | Residential | 2020-05-14 | 2020-05-14 | 2020-11-17 |  | 2021-04-16 | Overhead | R15 | 2020-12-18 | 1 | 134 | 24 | 86 | 242 | 2020 | 2021 | R15
155638213005 | 153121005638 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-06-18 | 2020-10-21 | 2020-12-07 | 2022-04-26 | 2022-08-22 | Underground | R15 | 2022-04-26 | 90 | 34 | 362 | 85 | 568 | 2020 | 2022 | R15
152180234814 | 156364814180 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG RES INDIVIDUAL | Residential | 2020-03-16 | 2021-05-18 | 2021-06-15 | 2021-08-30 | 2021-09-29 | Underground | R15 | 2021-08-30 | 307 | 21 | 55 | 23 | 403 | 2020 | 2021 | R15
154931235236 | 154889236931 | NON-RESIDENTIAL - MISCELLANEOUS | UG EXT NON RES | Commercial | 2020-04-30 | 2020-05-01 | 2021-06-17 | 2021-11-19 | 2022-01-19 | Underground | R15 | 2021-11-19 | 2 | 295 | 112 | 44 | 450 | 2020 | 2022 | R15
159299199850 | 159484850299 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Commercial | 2020-04-01 | 2020-05-28 | 2020-08-06 | 2020-08-21 | 2020-10-05 | Overhead | R15 | 2020-08-21 | 42 | 51 | 12 | 32 | 134 | 2020 | 2020 | R15
152032205456 | 159378456032 | OH Work for UG Extension (Non-CP) | OH WORK NON CP REL TO UG EXT | Residential Subdivision | 2020-04-01 | 2020-04-01 | 2020-09-28 |  | 2021-03-17 | Overhead | R15 | 2021-01-28 | 1 | 129 | 89 | 35 | 251 | 2020 | 2021 | R15
158230261730 | 158231730230 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG SUB RES | Residential | 2020-02-05 | 2021-07-13 | 2021-12-17 | 2023-11-16 | 2023-11-28 | Underground | R15 | 2023-11-16 | 375 | 114 | 500 | 9 | 995 | 2020 | 2023 | R15

## Rule16SourceDataQuestion4
PROJECT_NBR | JOB_NBR | CONSTR_ORD_TYPE_CODE_DESC | JOB_WORK_TYPE_CODE_DESC | RES_COM_IND | JOB_ORIG_DATE | CA_PLANING_DATE | PRE_CONSTR_PHASE_START_DATE | CONSTR_PHASE_START_DATE | Energize_Complete | OH/UG | Rule | Construction_Start_Date | IN to IP | IP to PC | PC to CO | CO to EN | IN to EN | Job Orig Year | Energ/Complete Year | Tariff
163827246824 | 160891246824 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-14 | 2022-10-04 | 2021-09-07 | 2022-10-05 | 2021-11-11 | Underground | R16 | 2022-10-05 | 320 |  | 282 |  | 87 | 2021 | 2021 | R16
162126240909 | 167958240909 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-30 | 2021-06-30 | 2021-07-27 | 2021-09-22 | 2021-11-09 | Underground | R16 | 2021-09-22 | 1 | 20 | 42 | 35 | 95 | 2021 | 2021 | R16
161811238372 | 162835238372 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-08 | 2021-06-08 | 2021-07-09 |  | 2021-10-14 | Underground | R16 | 2021-09-07 | 1 | 24 | 43 | 28 | 93 | 2021 | 2021 | R16
166554248617 | 167784248617 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-29 | 2021-06-29 | 2021-09-21 |  | 2021-12-14 | Underground | R16 | 2021-12-02 | 1 | 61 | 53 | 9 | 121 | 2021 | 2021 | R16
165990251113 | 166085251113 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-06-22 | 2021-06-22 | 2021-10-07 | 2021-11-08 | 2022-01-12 | Underground | R16 | 2021-11-08 | 1 | 78 | 23 | 48 | 147 | 2021 | 2022 | R16
165249236365 | 161877236365 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-03 | 2021-06-03 | 2021-06-23 |  | 2021-10-25 | Underground | R16 | 2021-07-29 | 1 | 15 | 27 | 63 | 103 | 2021 | 2021 | R16
169928240902 | 162628240902 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-08 | 2021-06-08 | 2021-07-27 |  | 2021-12-14 | Underground | R16 | 2021-11-16 | 1 | 36 | 81 | 21 | 136 | 2021 | 2021 | R16
168771245885 | 162783245885 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-08 | 2021-06-08 | 2021-08-30 | 2023-03-13 | 2023-03-31 | Underground | R16 | 2023-03-13 | 1 | 60 | 401 | 15 | 474 | 2021 | 2023 | R16
166820238226 | 169197238226 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-07 | 2021-07-07 | 2021-07-09 |  | 2021-09-13 | Underground | R16 | 2021-08-18 | 1 | 3 | 29 | 19 | 49 | 2021 | 2021 | R16
165365241437 | 167741241437 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-28 | 2021-07-13 | 2021-07-30 | 2022-03-06 | 2022-03-08 | Underground | R16 | 2022-03-06 | 12 | 14 | 156 | 2 | 182 | 2021 | 2022 | R16
169999241968 | 165230241968 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-17 | 2021-06-17 | 2021-08-04 | 2021-10-01 | 2021-10-04 | Underground | R16 | 2021-10-01 | 1 | 35 | 43 | 2 | 78 | 2021 | 2021 | R16
163622236882 | 166196236882 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-22 | 2021-06-22 | 2021-06-28 | 2021-08-13 | 2022-10-17 | Underground | R16 | 2021-08-13 | 1 | 5 | 35 | 307 | 345 | 2021 | 2022 | R16
166684242052 | 169013242052 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-06 | 2021-07-07 | 2021-08-04 |  | 2021-11-08 | Underground | R16 | 2021-09-22 | 2 | 21 | 36 | 34 | 90 | 2021 | 2021 | R16
166551245476 | 161132245476 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-14 | 2021-08-20 | 2021-08-27 |  | 2021-10-25 | Underground | R16 |  | 28 | 6 |  |  | 74 | 2021 | 2021 | R16
169649287610 | 162659287610 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-21 | 2021-07-21 | 2022-08-02 | 2023-03-23 | 2023-04-08 | Underground | R16 | 2023-03-23 | 1 | 270 | 168 | 12 | 448 | 2021 | 2023 | R16
161739241180 | 165912241180 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-21 | 2021-06-24 | 2021-07-28 | 2021-11-05 | 2021-12-08 | Underground | R16 | 2021-11-05 | 4 | 25 | 73 | 24 | 123 | 2021 | 2021 | R16
165372239820 | 162224239820 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2021-08-30 | 2021-10-11 | Underground | R16 | 2021-08-30 | 1 |  | 30 | 31 | 60 | 2021 | 2021 | R16
164479241377 | 161013241377 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-14 | 2021-07-14 | 2021-07-30 | 2022-01-27 | 2022-03-02 | Underground | R16 | 2022-01-27 | 1 | 13 | 130 | 25 | 166 | 2021 | 2022 | R16
164849237896 | 169170237896 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-07 | 2021-07-07 | 2021-07-07 | 2021-09-21 | 2021-11-01 | Underground | R16 | 2021-09-21 | 1 |  | 55 | 30 | 84 | 2021 | 2021 | R16
163991249087 | 161397249087 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-15 | 2021-07-15 | 2021-09-23 | 2021-12-13 | 2022-01-19 | Underground | R16 | 2021-12-13 | 1 | 51 | 58 | 28 | 135 | 2021 | 2022 | R16
169030269922 | 162444269922 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-21 | 2021-07-21 | 2022-02-22 | 2022-05-09 | 2022-06-09 | Underground | R16 | 2022-05-09 | 1 | 155 | 55 | 24 | 232 | 2021 | 2022 | R16
162179242959 | 167499242959 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-28 | 2021-07-23 | 2021-08-11 | 2022-07-20 | 2022-09-20 | Underground | R16 | 2022-07-20 | 20 | 14 | 246 | 45 | 322 | 2021 | 2022 | R16
162820246313 | 169901246313 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-09 | 2021-08-24 | 2021-09-02 | 2022-05-16 | 2022-06-20 | Underground | R16 | 2022-05-16 | 33 | 8 | 183 | 26 | 247 | 2021 | 2022 | R16
163629242058 | 162988242058 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-22 | 2021-07-22 | 2021-08-04 | 2021-11-01 | 2021-12-02 | Underground | R16 | 2021-11-01 | 1 | 10 | 64 | 24 | 96 | 2021 | 2021 | R16
166260235260 | 161482235260 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-02 | 2021-06-02 | 2021-06-16 |  | 2021-08-23 | Underground | R16 | 2021-08-06 | 1 | 11 | 38 | 12 | 59 | 2021 | 2021 | R16
161939245661 | 162306245661 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-20 | 2021-07-20 | 2021-08-27 |  | 2021-11-13 | Underground | R16 | 2021-10-21 | 1 | 29 | 40 | 17 | 84 | 2021 | 2021 | R16
168353243440 | 168239243440 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-01 | 2021-07-01 | 2021-08-12 |  | 2021-11-15 | Underground | R16 | 2021-10-22 | 1 | 31 | 52 | 17 | 98 | 2021 | 2021 | R16
164190236185 | 163350236185 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-09 | 2021-06-09 | 2021-06-22 |  | 2021-08-23 | Underground | R16 | 2021-08-03 | 1 | 10 | 31 | 15 | 54 | 2021 | 2021 | R16
164270242032 | 161737242032 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-03 | 2021-06-03 | 2021-08-04 |  | 2021-11-16 | Underground | R16 | 2021-10-19 | 1 | 45 | 55 | 21 | 119 | 2021 | 2021 | R16
160557246007 | 168410246007 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-01 | 2021-07-01 | 2021-08-31 |  | 2023-08-16 | Underground | R16 | 2023-05-02 | 1 | 44 | 436 | 77 | 555 | 2021 | 2023 | R16
161223243352 | 168454243352 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-01 | 2021-07-01 | 2021-08-12 |  | 2021-10-25 | Underground | R16 | 2021-09-15 | 1 | 31 | 25 | 29 | 83 | 2021 | 2021 | R16
164959247067 | 160736247067 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-13 | 2021-07-13 | 2021-09-08 | 2021-12-08 | 2021-12-10 | Underground | R16 | 2021-12-08 | 1 | 42 | 66 | 3 | 109 | 2021 | 2021 | R16
169807244427 | 162687244427 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-07 | 2021-06-08 | 2021-08-19 | 2021-10-28 | 2021-10-28 | Underground | R16 | 2021-10-28 | 2 | 53 | 51 |  | 104 | 2021 | 2021 | R16
161782250491 | 168890250491 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-05 | 2021-07-05 | 2021-10-04 | 2021-11-08 | 2021-11-09 | Underground | R16 | 2021-11-08 | 1 | 66 | 26 | 2 | 92 | 2021 | 2021 | R16
165073240005 | 169497240005 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-08 | 2021-07-08 | 2021-07-21 | 2021-08-20 | 2021-08-25 | Underground | R16 | 2021-08-20 | 1 | 10 | 23 | 4 | 35 | 2021 | 2021 | R16
167509241259 | 162528241259 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-21 | 2021-07-30 | 2021-07-30 | 2022-01-06 | 2022-01-06 | Underground | R16 | 2022-01-06 | 8 |  | 115 |  | 122 | 2021 | 2022 | R16
165247238222 | 167868238222 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-06-29 | 2021-07-08 | 2021-07-08 |  | 2022-02-07 | Underground | R16 |  | 8 |  |  |  | 160 | 2021 | 2022 | R16
165300249185 | 161951249185 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-19 | 2021-09-22 | 2021-09-22 |  | 2021-12-17 | Underground | R16 | 2021-11-18 | 48 |  | 42 | 22 | 110 | 2021 | 2021 | R16
168114242223 | 168380242223 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-01 | 2021-07-01 | 2021-08-05 |  | 2021-11-18 | Underground | R16 |  | 1 | 26 |  |  | 101 | 2021 | 2021 | R16
166193240262 | 160978240262 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-14 | 2021-07-14 | 2021-07-22 | 2021-09-09 | 2021-09-09 | Underground | R16 | 2021-09-09 | 1 | 7 | 36 |  | 42 | 2021 | 2021 | R16
166913238915 | 160723238915 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-07-14 | 2021-07-14 | 2021-07-14 | 2021-10-22 | 2021-10-28 | Underground | R16 | 2021-10-22 | 1 |  | 73 | 5 | 77 | 2021 | 2021 | R16
164728278022 | 166769278022 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-06-24 | 2021-06-24 | 2022-05-03 |  | 2023-06-06 | Underground | R16 | 2023-02-01 | 1 | 224 | 197 | 90 | 509 | 2021 | 2023 | R16
165083235982 | 166051235982 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-06-21 | 2021-06-21 | 2021-06-21 | 2021-12-16 | 2023-03-09 | Underground | R16 | 2021-12-16 | 1 |  | 129 | 321 | 449 | 2021 | 2023 | R16
166493254041 | 168212254041 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-06-30 | 2021-06-30 | 2021-10-27 | 2022-11-28 | 2023-08-10 | Underground | R16 | 2022-11-28 | 1 | 86 | 284 | 184 | 552 | 2021 | 2023 | R16
169574242698 | 167575242698 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-06-28 | 2021-06-28 | 2021-08-10 | 2022-08-04 | 2022-08-08 | Underground | R16 | 2022-08-04 | 1 | 32 | 258 | 3 | 291 | 2021 | 2022 | R16
165709282213 | 163056282213 | AGRICULTURAL | R16 RESD AND NON RESD US | Residential Subdivision | 2021-07-23 | 2021-08-17 | 2022-06-10 |  | 2023-01-05 | Underground | R16 |  | 18 | 214 |  |  | 380 | 2021 | 2023 | R16
160522236439 | 163054236439 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-06-09 | 2021-06-09 | 2021-06-24 |  | 2021-10-28 | Underground | R16 |  | 1 | 12 |  |  | 102 | 2021 | 2021 | R16
165988263442 | 163202263442 | AGRICULTURAL | R16 RESD AND NON RESD US | Residential Subdivision | 2021-07-23 | 2021-12-06 | 2022-01-04 |  | 2023-01-10 | Underground | R16 |  | 97 | 22 |  |  | 383 | 2021 | 2023 | R16
169656239696 | 165861239696 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-06-21 | 2021-07-07 | 2021-07-20 | 2022-05-02 | 2022-05-16 | Underground | R16 | 2022-05-02 | 13 | 10 | 205 | 11 | 236 | 2021 | 2022 | R16
160690243561 | 165958243561 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-06-21 | 2021-07-26 | 2021-08-13 |  | 2022-01-04 | Underground | R16 | 2021-11-23 | 26 | 15 | 73 | 31 | 142 | 2021 | 2022 | R16
168918294352 | 161771294352 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2021-07-19 | 2021-11-08 | 2022-09-21 | 2022-12-19 | 2023-01-23 | Underground | R16 | 2022-12-19 | 81 | 228 | 64 | 26 | 396 | 2021 | 2023 | R16
165707282017 | 163197282017 | AGRICULTURAL | R16 RESD AND NON RESD US | Residential Subdivision | 2021-07-23 | 2021-08-09 | 2022-06-09 |  | 2023-01-05 | Underground | R16 |  | 12 | 219 |  |  | 380 | 2021 | 2023 | R16
161282245407 | 165941245407 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-06-21 | 2021-07-29 | 2021-08-26 |  | 2022-04-20 | Underground | R16 | 2022-03-04 | 29 | 21 | 137 | 34 | 218 | 2021 | 2022 | R16
164626250835 | 165029250835 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-06-16 | 2021-10-06 | 2021-10-06 |  | 2023-07-25 | Underground | R16 | 2023-07-19 | 81 |  | 466 | 5 | 550 | 2021 | 2023 | R16
164892235479 | 165251235479 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-06-17 | 2021-06-17 | 2021-06-18 |  | 2023-06-07 | Underground | R16 |  | 1 | 2 |  |  | 515 | 2021 | 2023 | R16
165739235262 | 162677235262 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-06-07 | 2021-06-16 | 2021-06-16 |  | 2021-10-13 | Underground | R16 | 2021-09-23 | 8 |  | 72 | 15 | 93 | 2021 | 2021 | R16
169459238599 | 160365238599 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-12 | 2021-07-13 | 2021-07-13 |  | 2021-10-27 | Overhead | R16 | 2021-08-12 | 2 |  | 23 | 55 | 78 | 2021 | 2021 | R16
165692237825 | 168398237825 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-01 | 2021-07-01 | 2021-07-06 | 2021-11-16 | 2021-11-17 | Overhead | R16 | 2021-11-16 | 1 | 4 | 96 | 2 | 100 | 2021 | 2021 | R16
161119238144 | 164189238144 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-14 | 2021-06-22 | 2021-07-08 |  | 2021-08-23 | Overhead | R16 | 2021-07-27 | 7 | 13 | 14 | 20 | 51 | 2021 | 2021 | R16
165208234021 | 162676234021 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-07 | 2021-06-07 | 2021-06-07 |  | 2021-08-23 | Overhead | R16 | 2021-07-13 | 1 |  | 27 | 30 | 56 | 2021 | 2021 | R16
165143247207 | 163497247207 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-10 | 2021-09-09 | 2021-09-09 | 2022-01-27 | 2022-03-02 | Overhead | R16 | 2022-01-27 | 66 |  | 101 | 25 | 190 | 2021 | 2022 | R16
167076233488 | 161950233488 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-03 | 2021-06-04 | 2021-06-04 |  | 2021-10-25 | Overhead | R16 | 2021-08-23 | 2 |  | 57 | 46 | 103 | 2021 | 2021 | R16
165342235081 | 163654235081 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-10 | 2021-06-10 | 2021-06-15 |  | 2021-11-03 | Overhead | R16 | 2021-06-17 | 1 | 4 | 3 | 100 | 105 | 2021 | 2021 | R16
165668237186 | 167677237186 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-28 | 2021-06-30 | 2021-06-30 | 2022-07-12 | 2022-07-13 | Overhead | R16 | 2022-07-12 | 3 |  | 270 | 2 | 273 | 2021 | 2022 | R16
163179236368 | 166438236368 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-23 | 2021-06-23 | 2021-06-23 | 2022-02-23 | 2022-03-23 | Overhead | R16 | 2022-02-23 | 1 |  | 176 | 21 | 196 | 2021 | 2022 | R16
164072240056 | 162784240056 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-22 | 2021-07-22 | 2021-07-22 | 2021-09-22 | 2021-09-22 | Overhead | R16 | 2021-09-22 | 1 |  | 45 |  | 45 | 2021 | 2021 | R16
161435234959 | 164401234959 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-14 | 2021-06-15 | 2021-06-15 | 2021-12-07 | 2021-12-08 | Overhead | R16 | 2021-12-07 | 2 |  | 126 | 2 | 128 | 2021 | 2021 | R16
165937240087 | 162359240087 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-21 | 2021-07-21 | 2021-07-22 |  | 2021-11-02 | Overhead | R16 | 2021-10-18 | 1 | 2 | 63 | 12 | 75 | 2021 | 2021 | R16
162588243057 | 167527243057 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-28 | 2021-07-14 | 2021-08-12 | 2021-08-12 | 2021-09-14 | Overhead | R16 | 2021-08-12 | 13 | 22 |  | 24 | 57 | 2021 | 2021 | R16
161931235302 | 165045235302 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2021-06-18 | 2021-11-04 | Overhead | R16 | 2021-06-18 | 1 |  | 3 | 100 | 102 | 2021 | 2021 | R16
166717233391 | 161941233391 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-03 | 2021-06-03 | 2021-06-03 |  | 2021-09-10 | Overhead | R16 | 2021-08-16 | 1 |  | 53 | 20 | 72 | 2021 | 2021 | R16
167653238267 | 169033238267 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-06 | 2021-07-09 | 2021-07-09 | 2021-08-30 | 2021-08-31 | Overhead | R16 | 2021-08-30 | 4 |  | 37 | 2 | 41 | 2021 | 2021 | R16
169404235002 | 164307235002 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-12-02 | 2021-12-20 | Overhead | R16 | 2021-12-02 | 1 |  | 124 | 13 | 136 | 2021 | 2021 | R16
169023251633 | 162355251633 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-20 | 2021-10-11 | 2021-10-11 | 2021-12-09 | 2023-03-31 | Overhead | R16 | 2021-12-09 | 60 |  | 44 | 342 | 444 | 2021 | 2023 | R16
166924250790 | 162365250790 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-20 | 2021-10-05 | 2021-10-06 | 2021-12-09 | 2022-02-17 | Overhead | R16 | 2021-12-09 | 56 | 2 | 47 | 51 | 153 | 2021 | 2022 | R16
166808234642 | 161563234642 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-02 | 2021-06-02 | 2021-06-11 |  | 2021-08-12 | Overhead | R16 | 2021-07-09 | 1 | 8 | 21 | 25 | 52 | 2021 | 2021 | R16
164600235147 | 165091235147 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2021-09-01 | 2021-10-26 | Overhead | R16 | 2021-09-01 | 1 |  | 56 | 40 | 95 | 2021 | 2021 | R16
169049237703 | 168712237703 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-02 | 2021-07-02 | 2021-07-02 | 2022-06-23 | 2022-08-03 | Overhead | R16 | 2022-06-23 | 1 |  | 255 | 30 | 284 | 2021 | 2022 | R16
166922239288 | 161447239288 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-16 | 2021-07-16 | 2021-07-16 | 2021-09-01 | 2021-10-27 | Overhead | R16 | 2021-09-01 | 1 |  | 34 | 41 | 74 | 2021 | 2021 | R16
168180239056 | 169988239056 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-09 | 2021-07-15 | 2021-07-15 | 2021-09-28 | 2021-09-29 | Overhead | R16 | 2021-09-28 | 5 |  | 54 | 2 | 59 | 2021 | 2021 | R16
162813256344 | 160305256344 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-12 | 2021-11-12 | 2021-11-12 | 2022-04-27 | 2022-06-01 | Overhead | R16 | 2022-04-27 | 90 |  | 119 | 26 | 233 | 2021 | 2022 | R16
164793236187 | 166171236187 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-22 | 2021-06-22 | 2021-06-22 |  | 2021-10-25 | Overhead | R16 | 2021-08-26 | 1 |  | 48 | 43 | 90 | 2021 | 2021 | R16
168780238161 | 169334238161 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-07 | 2021-07-07 | 2021-07-07 | 2021-09-01 | 2021-10-25 | Overhead | R16 | 2021-09-01 | 1 |  | 41 | 39 | 79 | 2021 | 2021 | R16
169382236400 | 166605236400 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-23 | 2021-06-23 | 2021-06-23 | 2021-06-30 | 2021-09-13 | Overhead | R16 | 2021-06-30 | 1 |  | 6 | 54 | 59 | 2021 | 2021 | R16
161149235100 | 164632235100 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-15 | 2021-06-15 | 2021-06-15 |  | 2021-09-13 | Overhead | R16 | 2021-08-18 | 1 |  | 47 | 19 | 65 | 2021 | 2021 | R16
160056237183 | 167149237183 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-25 | 2021-06-29 | 2021-06-29 | 2021-08-16 | 2021-10-25 | Overhead | R16 | 2021-08-16 | 3 |  | 35 | 51 | 87 | 2021 | 2021 | R16
160574237065 | 167621237065 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-28 | 2021-06-28 | 2021-06-28 | 2021-09-28 | 2021-11-09 | Overhead | R16 | 2021-09-28 | 1 |  | 67 | 31 | 97 | 2021 | 2021 | R16
161869239528 | 161887239528 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-19 | 2021-07-19 | 2021-07-19 | 2021-08-13 | 2021-11-09 | Overhead | R16 | 2021-08-13 | 1 |  | 20 | 63 | 82 | 2021 | 2021 | R16
162877242366 | 166943242366 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-25 | 2021-06-25 | 2021-08-06 | 2021-12-07 | 2021-12-20 | Overhead | R16 | 2021-12-07 | 1 | 31 | 88 | 10 | 127 | 2021 | 2021 | R16
164642240343 | 166938240343 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-24 | 2021-07-23 | 2021-07-23 | 2021-07-30 | 2021-12-09 | Overhead | R16 | 2021-07-30 | 22 |  | 6 | 95 | 121 | 2021 | 2021 | R16
162468235121 | 164397235121 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-14 | 2021-06-15 | 2021-06-15 |  | 2021-10-25 | Overhead | R16 | 2021-09-08 | 2 |  | 62 | 34 | 96 | 2021 | 2021 | R16
168992236416 | 166880236416 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-24 | 2021-06-24 | 2021-06-24 |  | 2022-02-28 | Overhead | R16 | 2021-07-12 | 1 |  | 13 | 166 | 178 | 2021 | 2022 | R16
164870234034 | 162094234034 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-04 | 2021-06-04 | 2021-06-08 | 2022-05-05 | 2023-10-04 | Overhead | R16 | 2022-05-05 | 1 | 3 | 238 | 370 | 609 | 2021 | 2023 | R16
167462238118 | 169477238118 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-08 | 2021-07-08 | 2021-07-08 |  | 2021-09-01 | Overhead | R16 | 2021-08-09 | 1 |  | 23 | 18 | 40 | 2021 | 2021 | R16
163527240095 | 162840240095 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-22 | 2021-07-22 | 2021-07-22 |  | 2021-10-25 | Overhead | R16 | 2021-08-30 | 1 |  | 28 | 41 | 68 | 2021 | 2021 | R16
168731189514 | 169117189514 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-02-11 | 2020-02-11 | 2020-05-01 |  | 2023-10-10 | Underground | R16 | 2023-11-15 | 1 | 59 | 924 |  | 956 | 2020 | 2023 | R16
166968235409 | 164769235409 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-15 | 2021-06-18 | 2021-06-18 |  | 2021-08-23 | Overhead | R16 | 2021-08-05 | 4 |  | 35 | 13 | 50 | 2021 | 2021 | R16
160979233344 | 161664233344 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-02 | 2021-06-02 | 2021-06-02 | 2021-07-07 | 2021-08-23 | Overhead | R16 | 2021-07-07 | 1 |  | 26 | 34 | 59 | 2021 | 2021 | R16
165890235146 | 164757235146 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2021-06-21 | 2021-08-23 | Overhead | R16 | 2021-06-21 | 1 |  | 4 | 46 | 49 | 2021 | 2021 | R16
167505238565 | 169344238565 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-07 | 2021-07-07 | 2021-07-12 | 2022-03-25 | 2022-03-28 | Overhead | R16 | 2022-03-25 | 1 | 4 | 185 | 2 | 189 | 2021 | 2022 | R16
161450233910 | 161451233910 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-02 | 2021-06-02 | 2021-06-07 |  | 2021-12-16 | Overhead | R16 | 2021-11-15 | 1 | 4 | 116 | 24 | 142 | 2021 | 2021 | R16
169883254014 | 161626254014 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-16 | 2021-07-20 | 2021-10-29 |  | 2021-12-17 | Overhead | R16 | 2021-11-17 | 3 | 74 | 14 | 23 | 111 | 2021 | 2021 | R16
163541235300 | 165061235300 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2021-07-27 | 2021-08-23 | Overhead | R16 | 2021-07-27 | 1 |  | 30 | 20 | 49 | 2021 | 2021 | R16
160563236606 | 166915236606 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-24 | 2021-06-24 | 2021-06-24 | 2021-10-04 | 2021-11-09 | Overhead | R16 | 2021-10-04 | 1 |  | 73 | 27 | 99 | 2021 | 2021 | R16
161914240045 | 162596240045 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-21 | 2021-07-21 | 2021-07-21 |  | 2021-10-26 | Overhead | R16 | 2021-09-01 | 1 |  | 31 | 40 | 70 | 2021 | 2021 | R16
167337233622 | 161901233622 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-03 | 2021-06-04 | 2021-06-04 |  | 2021-10-25 | Overhead | R16 | 2021-08-26 | 2 |  | 60 | 43 | 103 | 2021 | 2021 | R16
169750236226 | 166441236226 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-22 | 2021-06-22 | 2021-06-22 | 2021-07-09 | 2021-08-23 | Overhead | R16 | 2021-07-09 | 1 |  | 14 | 32 | 45 | 2021 | 2021 | R16
160602235064 | 164385235064 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-14 | 2021-06-15 | 2021-06-15 |  | 2021-12-02 | Overhead | R16 | 2021-11-04 | 2 |  | 103 | 21 | 124 | 2021 | 2021 | R16
162772338472 | 167900338472 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-11-03 | 2023-11-03 | 2023-11-03 | 2023-11-03 | 2023-11-21 | Overhead | R16 | 2023-11-03 | 1 |  |  | 13 | 13 | 2023 | 2023 | R16
160387236614 | 167030236614 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-24 | 2021-06-24 | 2021-06-24 | 2022-03-21 | 2022-04-21 | Overhead | R16 | 2022-03-21 | 1 |  | 193 | 24 | 216 | 2021 | 2022 | R16
168913239748 | 161616239748 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-16 | 2021-07-20 | 2021-07-20 | 2021-09-14 | 2021-09-15 | Overhead | R16 | 2021-09-14 | 3 |  | 41 | 2 | 44 | 2021 | 2021 | R16
169633234550 | 163648234550 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-10 | 2021-06-10 | 2021-06-11 |  | 2021-08-13 | Overhead | R16 | 2021-07-20 | 1 | 2 | 28 | 19 | 47 | 2021 | 2021 | R16
165858237264 | 164550237264 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-15 | 2021-06-30 | 2021-06-30 | 2021-08-13 | 2021-10-25 | Overhead | R16 | 2021-08-13 | 12 |  | 33 | 52 | 95 | 2021 | 2021 | R16
166654249833 | 165541249833 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-18 | 2021-09-28 | 2021-09-28 | 2022-01-20 | 2022-03-04 | Overhead | R16 | 2022-01-20 | 73 |  | 83 | 32 | 186 | 2021 | 2022 | R16
167336235083 | 161674235083 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-03 | 2021-06-15 | 2021-06-15 |  | 2021-12-28 | Overhead | R16 | 2021-11-16 | 9 |  | 111 | 31 | 149 | 2021 | 2021 | R16
162554239203 | 161340239203 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-15 | 2021-07-15 | 2021-07-15 |  | 2021-10-25 | Overhead | R16 | 2021-08-31 | 1 |  | 34 | 40 | 73 | 2021 | 2021 | R16
163241237549 | 164584237549 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-15 | 2021-07-01 | 2021-07-01 |  | 2021-08-13 | Overhead | R16 | 2021-07-19 | 13 |  | 13 | 20 | 44 | 2021 | 2021 | R16
161571236639 | 167168236639 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-25 | 2021-06-25 | 2021-06-25 |  | 2021-09-01 | Overhead | R16 | 2021-08-09 | 1 |  | 32 | 18 | 49 | 2021 | 2021 | R16
164123239548 | 161825239548 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-19 | 2021-07-19 | 2021-07-19 |  | 2021-10-27 | Overhead | R16 | 2021-08-11 | 1 |  | 18 | 56 | 73 | 2021 | 2021 | R16
161509237968 | 169012237968 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-06 | 2021-07-06 | 2021-07-07 | 2022-04-17 | 2022-04-20 | Overhead | R16 | 2022-04-17 | 1 | 2 | 203 | 3 | 207 | 2021 | 2022 | R16
160529235238 | 165319235238 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-17 | 2021-06-17 | 2021-06-17 | 2021-09-05 | 2021-09-08 | Overhead | R16 | 2021-09-05 | 1 |  | 57 | 3 | 60 | 2021 | 2021 | R16
163340234309 | 163399234309 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-10 | 2021-06-10 | 2021-06-10 |  | 2021-08-12 | Overhead | R16 | 2021-07-08 | 1 |  | 21 | 26 | 46 | 2021 | 2021 | R16
162830239524 | 161844239524 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-19 | 2021-07-19 | 2021-07-19 | 2021-09-21 | 2021-11-09 | Overhead | R16 | 2021-09-21 | 1 |  | 47 | 36 | 82 | 2021 | 2021 | R16
168862233721 | 162218233721 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-05 | 2021-06-05 | 2021-06-05 |  | 2021-10-25 | Overhead | R16 | 2021-08-30 | 0 |  | 61 | 41 | 101 | 2021 | 2021 | R16
164643238914 | 167919238914 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-06-29 | 2021-06-29 | 2021-07-14 | 2021-09-15 | 2021-09-16 | Underground | R16 | 2021-09-15 | 1 | 12 | 46 | 2 | 58 | 2021 | 2021 | R16
166746146361 | 165077146361 | AGRICULTURAL | R16 RESD AND NON RESD US | Residential | 2019-01-04 | 2019-01-11 | 2019-03-18 |  | 2022-08-29 | Underground | R16 |  | 6 | 47 |  |  | 952 | 2019 | 2022 | R16
166746146362 | 165079146362 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2019-01-04 | 2019-01-17 | 2019-03-18 |  | 2019-10-28 | Underground | R16 |  | 10 | 43 |  |  | 212 | 2019 | 2019 | R16
168112264379 | 161884264379 | CUSTOMER UPGRADE IN SERVICE | UG SVC CONVERSION | Residential | 2021-07-19 | 2021-07-19 | 2022-01-12 | 2022-04-06 | 2022-05-16 | Underground | R16 | 2022-04-06 | 1 | 128 | 61 | 29 | 216 | 2021 | 2022 | R16
166702281757 | 166676281757 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2021-06-23 | 2021-06-23 | 2022-06-07 | 2023-09-21 | 2023-12-05 | Underground | R16 | 2023-09-21 | 1 | 250 | 338 | 54 | 640 | 2021 | 2023 | R16
163067256115 | 166796256115 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2021-06-24 | 2021-08-27 | 2021-11-11 | 2023-01-26 | 2023-02-21 | Underground | R16 | 2023-01-26 | 47 | 55 | 316 | 19 | 434 | 2021 | 2023 | R16
163770288403 | 169735288403 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG R16 RESD AND NON RESD UD | Commercial | 2021-07-08 | 2022-05-10 | 2022-08-09 | 2023-11-13 | 2023-12-26 | Underground | R16 | 2023-11-13 | 219 | 66 | 330 | 32 | 644 | 2021 | 2023 | R16
163329285291 | 163471285291 | Electric Vehicle | UG R16 RESD AND NON RESD UD | Commercial | 2021-06-09 | 2021-06-09 | 2022-07-11 | 2022-12-01 | 2023-01-23 | Underground | R16 | 2022-12-01 | 1 | 284 | 104 | 38 | 424 | 2021 | 2023 | R16
168188237787 | 166601237787 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2021-06-23 | 2021-07-01 | 2021-07-06 | 2023-09-05 | 2022-09-20 | Underground | R16 | 2023-09-05 | 7 | 4 | 566 |  | 325 | 2021 | 2022 | R16
168215240653 | 167151240653 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2021-06-25 | 2021-07-20 | 2021-07-27 |  | 2023-09-17 | Underground | R16 |  | 18 | 6 |  |  | 581 | 2021 | 2023 | R16
165986281999 | 163111281999 | AGRICULTURAL | R16 RESD AND NON RESD US | Residential Subdivision | 2021-07-23 | 2021-11-18 | 2022-06-08 |  | 2023-01-10 | Underground | R16 |  | 85 | 145 |  |  | 383 | 2021 | 2023 | R16
166202239533 | 161862239533 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-07-19 | 2021-07-19 | 2021-07-19 |  | 2021-09-14 | Overhead | R16 | 2021-08-19 | 1 |  | 24 | 19 | 42 | 2021 | 2021 | R16
163141234528 | 162976234528 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-06-09 | 2021-06-09 | 2021-06-10 | 2021-07-07 | 2021-08-12 | Overhead | R16 | 2021-07-07 | 1 | 2 | 20 | 27 | 47 | 2021 | 2021 | R16
167078241158 | 162907241158 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-07-22 | 2021-07-29 | 2021-07-29 | 2021-08-05 | 2021-10-27 | Overhead | R16 | 2021-08-05 | 6 |  | 6 | 60 | 70 | 2021 | 2021 | R16
167579233872 | 162787233872 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Commercial | 2021-06-08 | 2021-06-08 | 2021-06-08 |  | 2023-06-07 | Underground | R16 |  | 1 |  |  |  | 522 | 2021 | 2023 | R16
169478248017 | 167673248017 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-06-28 | 2021-06-28 | 2021-09-16 |  | 2022-02-28 | Overhead | R16 | 2022-01-24 | 1 | 59 | 93 | 26 | 176 | 2021 | 2022 | R16
161933241885 | 162592241885 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2021-06-07 | 2021-07-08 | 2021-08-02 | 2022-12-07 | 2023-02-21 | Overhead | R16 | 2022-12-07 | 24 | 18 | 353 | 55 | 447 | 2021 | 2023 | R16
167736250629 | 162127250629 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2021-06-04 | 2021-09-27 | 2021-10-05 |  | 2023-02-03 | Overhead | R16 |  | 82 | 7 |  |  | 436 | 2021 | 2023 | R16
160896239131 | 160196239131 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2021-07-12 | 2021-07-12 | 2021-07-15 | 2022-02-25 | 2022-03-11 | Overhead | R16 | 2022-02-25 | 1 | 4 | 162 | 11 | 175 | 2021 | 2022 | R16
165105236410 | 166675236410 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-06-23 | 2021-06-24 | 2021-06-24 |  | 2022-04-08 | Overhead | R16 | 2022-05-04 | 2 |  | 225 |  | 208 | 2021 | 2022 | R16
162938233398 | 162119233398 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2021-06-04 | 2021-06-04 | 2021-06-04 | 2022-02-07 | 2021-10-25 | Underground | R16 | 2022-02-07 | 1 |  | 177 |  | 102 | 2021 | 2021 | R16
162852255837 | 166711255837 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2021-06-23 | 2021-08-13 | 2021-11-09 |  | 2022-08-11 | Underground | R16 |  | 38 | 63 |  |  | 297 | 2021 | 2022 | R16
168823250701 | 160161250701 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH CP R16 WORK RELO TO UG | Residential | 2021-07-11 | 2021-07-11 | 2021-10-05 | 2022-02-08 | 2022-02-23 | Overhead | R16 | 2022-02-08 | 0 | 62 | 91 | 12 | 163 | 2021 | 2022 | R16
160188242326 | 165973242326 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-21 | 2021-08-05 | 2021-08-05 | 2021-11-10 | 2021-12-17 | Overhead | R16 | 2021-11-10 | 34 |  | 70 | 28 | 130 | 2021 | 2021 | R16
164203243363 | 169911243363 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-09 | 2021-08-12 | 2021-08-12 | 2021-11-01 | 2022-02-07 | Overhead | R16 | 2021-11-01 | 25 |  | 58 | 71 | 152 | 2021 | 2022 | R16
160905244389 | 162538244389 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-21 | 2021-08-19 | 2021-08-19 | 2022-04-26 | 2022-05-19 | Overhead | R16 | 2022-04-26 | 22 |  | 179 | 18 | 217 | 2021 | 2022 | R16
162801155113 | 163114155113 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-11 | 2019-06-11 | 2019-06-13 |  | 2019-08-26 | Underground | R16 |  | 1 | 3 |  |  | 55 | 2019 | 2019 | R16
168387235029 | 164622235029 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-15 | 2021-06-15 | 2021-06-15 | 2022-03-08 | 2022-03-31 | Overhead | R16 | 2022-03-08 | 1 |  | 191 | 18 | 208 | 2021 | 2022 | R16
164556283638 | 167881283638 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG R16 RESD AND NON RESD UD | Commercial | 2021-06-29 | 2022-04-07 | 2022-06-24 | 2022-10-31 | 2022-11-22 | Underground | R16 | 2022-10-31 | 203 | 57 | 92 | 17 | 366 | 2021 | 2022 | R16
162680251153 | 167536251153 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-28 | 2021-07-15 | 2021-10-07 | 2021-12-01 | 2022-02-01 | Underground | R16 | 2021-12-01 | 14 | 61 | 40 | 45 | 157 | 2021 | 2022 | R16
161982239516 | 162320239516 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-20 | 2021-07-20 | 2021-07-20 |  | 2021-11-09 | Overhead | R16 | 2021-10-13 | 1 |  | 62 | 20 | 81 | 2021 | 2021 | R16
165665239752 | 162142239752 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-20 | 2021-07-20 | 2021-07-20 |  | 2021-10-25 | Overhead | R16 | 2021-09-02 | 1 |  | 33 | 38 | 70 | 2021 | 2021 | R16
169031244353 | 161304244353 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-15 | 2021-07-15 | 2021-08-19 | 2021-09-21 | 2021-11-01 | Underground | R16 | 2021-09-21 | 1 | 26 | 24 | 30 | 78 | 2021 | 2021 | R16
167352239270 | 165913239270 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-21 | 2021-06-21 | 2021-07-15 |  | 2021-11-13 | Underground | R16 | 2021-10-21 | 1 | 19 | 71 | 17 | 105 | 2021 | 2021 | R16
168954239487 | 160964239487 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2021-07-14 | 2021-07-15 | 2021-07-19 | 2021-08-25 | 2022-01-31 | Overhead | R16 | 2021-08-25 | 2 | 3 | 28 | 114 | 144 | 2021 | 2022 | R16
162629325750 | 162319325750 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH CP R16 WORK RELO TO UG | Residential | 2021-07-21 | 2021-07-21 | 2023-07-21 | 2023-09-29 | 2023-10-23 | Overhead | R16 | 2023-09-29 | 1 | 523 | 51 | 17 | 589 | 2021 | 2023 | R16
162874237170 | 167874237170 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-08-03 | 2022-04-26 | Overhead | R16 | 2021-08-03 | 1 |  | 26 | 191 | 216 | 2021 | 2022 | R16
165507239241 | 165908239241 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-06-21 | 2021-07-15 | 2021-07-15 | 2022-03-30 | 2022-04-04 | Overhead | R16 | 2022-03-30 | 19 |  | 185 | 4 | 206 | 2021 | 2022 | R16
165096308002 | 165008308002 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Commercial | 2021-06-16 | 2021-06-16 | 2023-02-01 | 2023-06-12 | 2023-08-16 | Underground | R16 | 2023-06-12 | 1 | 426 | 94 | 48 | 566 | 2021 | 2023 | R16
164094237399 | 167031237399 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-24 | 2021-06-24 | 2021-07-02 | 2021-11-10 | 2021-12-16 | Underground | R16 | 2021-11-10 | 1 | 7 | 94 | 27 | 126 | 2021 | 2021 | R16
164934235120 | 164760235120 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-15 | 2021-06-15 | 2021-06-15 |  | 2021-09-14 | Overhead | R16 | 2021-08-19 | 1 |  | 48 | 19 | 66 | 2021 | 2021 | R16
160552234956 | 164386234956 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-14 | 2021-06-15 | 2021-06-15 | 2021-10-05 | 2021-10-06 | Overhead | R16 | 2021-10-05 | 2 |  | 81 | 2 | 83 | 2021 | 2021 | R16
164980241058 | 160372241058 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-12 | 2021-07-28 | 2021-07-28 |  | 2021-12-02 | Underground | R16 | 2021-11-04 | 13 |  | 72 | 21 | 104 | 2021 | 2021 | R16
165081234516 | 163639234516 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-10 | 2021-06-10 | 2021-06-10 | 2021-06-30 | 2021-10-28 | Overhead | R16 | 2021-06-30 | 1 |  | 15 | 87 | 101 | 2021 | 2021 | R16
165988263441 | 163201263441 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2021-07-23 | 2021-12-03 | 2022-01-04 |  | 2023-09-05 | Underground | R16 |  | 96 | 23 |  |  | 553 | 2021 | 2023 | R16
163018182182 | 162960182182 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2020-01-13 | 2020-01-27 | 2020-02-27 |  | 2021-01-12 | Underground | R16 |  | 11 | 24 |  |  | 262 | 2020 | 2021 | R16
163018215336 | 160936215336 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-15 | 2020-12-15 | 2020-12-22 |  | 2021-11-08 | Overhead | R16 |  | 1 | 6 |  |  | 235 | 2020 | 2021 | R16
163018259807 | 162397259807 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-11-29 | 2021-11-29 | 2021-12-03 |  | 2022-03-07 | Overhead | R16 |  | 1 | 5 |  |  | 71 | 2021 | 2022 | R16
163019207763 | 165266207763 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-01 | 2020-10-06 | 2020-10-20 |  | 2021-04-15 | Overhead | R16 |  | 4 | 11 |  |  | 141 | 2020 | 2021 | R16
163160143714 | 169574143714 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-29 | 2019-02-04 | 2019-02-20 |  | 2019-04-26 | Overhead | R16 |  | 5 | 13 |  |  | 64 | 2019 | 2019 | R16
163162143097 | 166379143097 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-09 | 2019-02-04 | 2019-02-13 |  | 2019-04-15 | Overhead | R16 |  | 19 | 8 |  |  | 69 | 2019 | 2019 | R16
165556152993 | 168919152993 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Commercial | 2019-05-14 | 2019-05-14 | 2019-05-21 |  | 2019-07-23 | Underground | R16 |  | 1 | 6 |  |  | 51 | 2019 | 2019 | R16
165623159380 | 160579159380 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-17 | 2019-07-22 | 2019-07-29 |  | 2019-09-24 | Overhead | R16 |  | 4 | 6 |  |  | 50 | 2019 | 2019 | R16
165628149216 | 162738149216 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-10 | 2019-04-12 | 2019-04-16 |  | 2019-06-03 | Overhead | R16 |  | 3 | 3 |  |  | 39 | 2019 | 2019 | R16
165628157637 | 162580157637 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-06 | 2019-07-05 | 2019-07-12 |  | 2019-12-06 | Overhead | R16 |  | 22 | 6 |  |  | 132 | 2019 | 2019 | R16
165629140703 | 166381140703 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-09 | 2019-01-16 | 2019-01-17 |  | 2019-02-21 | Overhead | R16 |  | 6 | 2 |  |  | 32 | 2019 | 2019 | R16
165629145774 | 169591145774 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-29 | 2019-02-01 | 2019-03-11 |  | 2019-04-25 | Overhead | R16 |  | 4 | 27 |  |  | 63 | 2019 | 2019 | R16
165629144304 | 164023144304 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-19 | 2019-02-20 | 2019-02-25 |  | 2020-07-14 | Overhead | R16 |  | 2 | 4 |  |  | 366 | 2019 | 2020 | R16
165629161956 | 167913161956 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-02 | 2019-08-20 | 2019-08-23 |  | 2019-09-27 | Overhead | R16 |  | 36 | 4 |  |  | 64 | 2019 | 2019 | R16
165629162763 | 161609162763 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-23 | 2019-08-28 | 2019-08-29 |  | 2019-10-30 | Overhead | R16 |  | 27 | 2 |  |  | 72 | 2019 | 2019 | R16
165629261368 | 165066261368 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-10 | 2021-12-14 | 2021-12-15 |  | 2022-03-14 | Overhead | R16 |  | 3 | 2 |  |  | 67 | 2021 | 2022 | R16
165629302577 | 165676302577 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-01 | 2022-12-01 | 2022-12-07 |  | 2023-04-17 | Overhead | R16 |  | 1 | 5 |  |  | 98 | 2022 | 2023 | R16
165640147307 | 166513147307 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-05 | 2019-03-19 | 2019-03-26 |  | 2019-05-20 | Overhead | R16 |  | 11 | 6 |  |  | 55 | 2019 | 2019 | R16
165640295248 | 160577295248 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-23 | 2022-09-14 | 2022-09-28 |  | 2023-09-22 | Overhead | R16 |  | 278 | 11 |  |  | 545 | 2021 | 2023 | R16
166077158900 | 163712158900 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-13 | 2019-07-17 | 2019-07-24 |  | 2019-09-10 | Overhead | R16 |  | 25 | 6 |  |  | 64 | 2019 | 2019 | R16
166077170111 | 167119170111 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-16 | 2019-10-25 | 2019-10-30 |  | 2019-11-26 | Overhead | R16 |  | 8 | 4 |  |  | 30 | 2019 | 2019 | R16
166077175049 | 166870175049 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-09 | 2019-12-12 | 2019-12-23 |  | 2020-06-09 | Overhead | R16 |  | 4 | 8 |  |  | 132 | 2019 | 2020 | R16
166077192953 | 165981192953 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-12 | 2020-05-06 | 2020-06-01 |  | 2021-04-15 | Underground | R16 |  | 40 | 19 |  |  | 286 | 2020 | 2021 | R16
166077220036 | 162996220036 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2020-12-22 | 2021-01-30 | 2021-02-10 |  | 2022-05-12 | Underground | R16 |  | 29 | 8 |  |  | 363 | 2020 | 2022 | R16
166077283310 | 163370283310 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-03 | 2022-03-04 | 2022-06-21 |  | 2022-08-23 | Underground | R16 |  | 2 | 78 |  |  | 124 | 2022 | 2022 | R16
166077284983 | 164137284983 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-26 | 2022-04-29 | 2022-07-08 |  | 2022-10-21 | Underground | R16 |  | 4 | 51 |  |  | 129 | 2022 | 2022 | R16
166077289995 | 164128289995 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-16 | 2022-08-17 | 2022-08-23 |  | 2022-08-23 | Underground | R16 |  | 2 | 5 |  |  | 6 | 2022 | 2022 | R16
166319140425 | 166095140425 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-09 | 2019-01-09 | 2019-01-15 |  | 2019-01-31 | Overhead | R16 |  | 1 | 5 |  |  | 17 | 2019 | 2019 | R16
166319174245 | 163671174245 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-11-18 | 2019-12-04 | 2019-12-12 |  | 2020-10-29 | Overhead | R16 |  | 13 | 7 |  |  | 249 | 2019 | 2020 | R16
166551155236 | 169594155236 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-17 | 2019-06-11 | 2019-06-14 |  | 2020-08-05 | Overhead | R16 |  | 18 | 4 |  |  | 319 | 2019 | 2020 | R16
166551174196 | 161643174196 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-18 | 2019-09-18 | 2019-12-13 |  | 2020-06-09 | Overhead | R16 |  | 1 | 63 |  |  | 190 | 2019 | 2020 | R16
166551317041 | 163902317041 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2021-07-27 | 2022-02-17 | 2023-04-26 |  | 2023-09-27 | Underground | R16 |  | 148 | 310 |  |  | 567 | 2021 | 2023 | R16
166553150423 | 168882150423 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-19 | 2019-03-19 | 2019-04-26 |  | 2019-08-12 | Overhead | R16 |  | 1 | 29 |  |  | 105 | 2019 | 2019 | R16
166553170105 | 164399170105 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-03 | 2019-10-24 | 2019-10-30 |  | 2019-11-27 | Overhead | R16 |  | 16 | 5 |  |  | 40 | 2019 | 2019 | R16
166553219173 | 163003219173 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-22 | 2021-01-15 | 2021-02-01 |  | 2022-05-19 | Underground | R16 |  | 19 | 12 |  |  | 368 | 2020 | 2022 | R16
166356186024 | 169233186024 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-31 | 2020-03-31 | 2020-03-31 | 2020-10-09 | 2021-07-02 | Overhead | R16 | 2020-10-09 | 1 |  | 139 | 191 | 329 | 2020 | 2021 | R16
163512185500 | 161968185500 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-02-24 | 2020-02-24 | 2020-03-26 |  | 2021-07-07 | Underground | R16 |  | 1 | 24 |  |  | 358 | 2020 | 2021 | R16
166554153946 | 160225153946 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-22 | 2019-05-22 | 2019-05-31 |  | 2019-08-12 | Overhead | R16 |  | 1 | 8 |  |  | 59 | 2019 | 2019 | R16
168361195231 | 169049195231 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-26 | 2020-05-26 | 2020-06-25 |  | 2020-11-02 | Underground | R16 | 2020-09-04 | 1 | 23 | 52 | 42 | 115 | 2020 | 2020 | R16
167331203905 | 167169203905 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-31 | 2020-02-03 | 2020-09-14 | 2021-02-02 | 2021-02-02 | Underground | R16 | 2021-02-02 | 2 | 161 | 102 |  | 263 | 2020 | 2021 | R16
165630174599 | 169029174599 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-17 | 2019-12-17 | 2019-12-17 | 2020-04-08 | 2020-04-15 | Overhead | R16 | 2020-04-08 | 1 |  | 82 | 6 | 87 | 2019 | 2020 | R16
166599163783 | 160660163783 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-17 | 2019-09-06 | 2019-09-09 |  | 2021-11-10 | Overhead | R16 |  | 38 | 2 |  |  | 606 | 2019 | 2021 | R16
169208183616 | 168998183616 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-11 | 2020-02-11 | 2020-03-10 |  | 2020-07-09 | Underground | R16 | 2020-05-29 | 1 | 21 | 59 | 30 | 108 | 2020 | 2020 | R16
166599159393 | 161613159393 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-23 | 2019-07-26 | 2019-07-30 |  | 2020-06-09 | Overhead | R16 |  | 4 | 3 |  |  | 231 | 2019 | 2020 | R16
169328181645 | 161960181645 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-24 | 2020-02-24 | 2020-02-24 |  | 2020-07-09 | Underground | R16 | 2020-05-27 | 1 |  | 68 | 32 | 99 | 2020 | 2020 | R16
167124194028 | 161798194028 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-06-12 | 2020-06-12 | 2020-06-12 |  | 2020-08-27 | Overhead | R16 | 2020-06-25 | 1 |  | 10 | 46 | 55 | 2020 | 2020 | R16
166599166620 | 163274166620 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-26 | 2019-10-01 | 2019-10-02 |  | 2019-10-16 | Overhead | R16 |  | 4 | 2 |  |  | 15 | 2019 | 2019 | R16
161982177336 | 162563177336 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-10 | 2020-01-10 | 2020-01-18 |  | 2020-07-01 | Underground | R16 | 2020-04-30 | 1 | 6 | 74 | 45 | 124 | 2020 | 2020 | R16
160611195514 | 164763195514 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-26 | 2020-06-26 | 2020-06-26 | 2020-09-15 | 2020-12-18 | Overhead | R16 | 2020-09-15 | 1 |  | 58 | 69 | 126 | 2020 | 2020 | R16
163924177665 | 161028177665 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-03 | 2020-01-07 | 2020-01-21 | 2020-01-22 | 2020-06-23 | Overhead | R16 | 2020-01-22 | 3 | 11 | 2 | 110 | 123 | 2020 | 2020 | R16
167601182680 | 163440182680 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-02 | 2020-03-02 | 2020-03-02 |  | 2020-06-09 | Overhead | R16 | 2020-04-02 | 1 |  | 24 | 49 | 72 | 2020 | 2020 | R16
169478194987 | 163664194987 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-22 | 2020-06-22 | 2020-06-22 | 2020-08-12 | 2020-10-06 | Overhead | R16 | 2020-08-12 | 1 |  | 38 | 40 | 77 | 2020 | 2020 | R16
166640168585 | 163275168585 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-26 | 2019-10-01 | 2019-10-17 |  | 2021-08-23 | Overhead | R16 |  | 4 | 13 |  |  | 498 | 2019 | 2021 | R16
166972234704 | 160863234704 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2020-02-18 | 2021-03-30 | 2021-06-11 |  | 2022-08-03 | Underground | R16 |  | 291 | 54 |  |  | 642 | 2020 | 2022 | R16
169490186711 | 160549186711 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-07 | 2020-04-07 | 2020-04-07 | 2020-11-11 | 2021-11-13 | Overhead | R16 | 2020-11-11 | 1 |  | 157 | 263 | 419 | 2020 | 2021 | R16
169356223510 | 166923223510 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE FOR UPGRADE UD | Commercial | 2020-07-09 | 2021-01-06 | 2021-03-15 | 2021-09-10 | 2021-10-20 | Underground | R16 | 2021-09-10 | 130 | 49 | 130 | 29 | 335 | 2020 | 2021 | R16
167975199937 | 160494199937 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-07 | 2020-04-07 | 2020-08-07 | 2020-09-10 | 2020-12-17 | Overhead | R16 | 2020-09-10 | 1 | 89 | 25 | 71 | 183 | 2020 | 2020 | R16
162954189467 | 164645189467 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-30 | 2020-04-30 | 2020-04-30 |  | 2020-07-14 | Overhead | R16 | 2020-06-17 | 1 |  | 35 | 20 | 54 | 2020 | 2020 | R16
168397230089 | 169923230089 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-13 | 2020-02-13 | 2021-05-10 |  | 2022-06-20 | Underground | R16 | 2022-05-25 | 1 | 323 | 273 | 19 | 613 | 2020 | 2022 | R16
166641155345 | 165108155345 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-25 | 2019-03-05 | 2019-06-14 |  | 2021-07-09 | Overhead | R16 |  | 7 | 74 |  |  | 620 | 2019 | 2021 | R16
161006181257 | 161025181257 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-19 | 2020-02-19 | 2020-02-21 |  | 2020-06-09 | Underground | R16 |  | 1 | 3 |  |  | 80 | 2020 | 2020 | R16
166641220172 | 165902220172 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-01 | 2019-03-25 | 2021-02-10 |  | 2021-11-05 | Overhead | R16 |  | 17 | 493 |  |  | 701 | 2019 | 2021 | R16
163644189438 | 162681189438 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2020-04-20 | 2020-04-30 | 2020-04-30 | 2020-07-08 | 2020-11-05 | Overhead | R16 | 2020-07-08 | 9 |  | 50 | 87 | 144 | 2020 | 2020 | R16
160753196798 | 162247196798 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-16 | 2020-07-09 | 2020-07-09 | 2020-07-31 | 2020-10-06 | Overhead | R16 | 2020-07-31 | 18 |  | 17 | 48 | 81 | 2020 | 2020 | R16
166641149603 | 166166149603 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-04 | 2019-04-10 | 2019-04-18 |  | 2019-08-12 | Overhead | R16 |  | 28 | 7 |  |  | 116 | 2019 | 2019 | R16
160543189199 | 164744189199 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-21 | 2020-01-21 | 2020-04-29 |  | 2020-07-13 | Underground | R16 | 2020-06-15 | 1 | 72 | 34 | 21 | 125 | 2020 | 2020 | R16
166641147510 | 160233147510 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-27 | 2019-03-27 | 2019-03-28 |  | 2019-07-23 | Overhead | R16 |  | 1 | 2 |  |  | 85 | 2019 | 2019 | R16
166641166721 | 161268166721 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-29 | 2019-06-21 | 2019-10-02 |  | 2021-11-10 | Overhead | R16 |  | 18 | 74 |  |  | 641 | 2019 | 2021 | R16
163748176945 | 163237176945 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-14 | 2020-01-14 | 2020-01-14 |  | 2021-11-13 | Overhead | R16 | 2021-10-19 | 1 |  | 461 | 19 | 479 | 2020 | 2021 | R16
166641161885 | 164381161885 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-07 | 2019-08-16 | 2019-08-20 |  | 2020-10-06 | Overhead | R16 |  | 8 | 3 |  |  | 305 | 2019 | 2020 | R16
169246190865 | 164203190865 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Commercial | 2020-03-04 | 2020-04-09 | 2020-05-13 |  | 2020-07-09 | Underground | R16 |  | 27 | 25 |  |  | 92 | 2020 | 2020 | R16
163882197086 | 167648197086 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-13 | 2020-07-13 | 2020-07-13 |  | 2020-10-06 | Underground | R16 | 2020-08-03 | 1 |  | 16 | 47 | 62 | 2020 | 2020 | R16
166641182766 | 161656182766 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-21 | 2020-02-25 | 2020-03-02 |  | 2020-06-23 | Overhead | R16 |  | 3 | 5 |  |  | 88 | 2020 | 2020 | R16
160594184222 | 166353184222 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2020-03-16 | 2020-03-16 | 2020-03-16 |  | 2020-06-09 | Overhead | R16 | 2020-04-09 | 1 |  | 19 | 44 | 62 | 2020 | 2020 | R16
163698197331 | 168225197331 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-15 | 2020-07-15 | 2020-07-15 | 2020-07-20 | 2020-10-06 | Overhead | R16 | 2020-07-20 | 1 |  | 4 | 57 | 60 | 2020 | 2020 | R16
164430185454 | 166948185454 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-18 | 2020-03-20 | 2020-03-27 | 2020-03-27 | 2020-07-07 | Overhead | R16 | 2020-03-27 | 3 | 6 |  | 73 | 80 | 2020 | 2020 | R16
166568194700 | 162932194700 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-17 | 2020-06-17 | 2020-06-17 |  | 2021-07-01 | Overhead | R16 | 2020-07-14 | 1 |  | 20 | 253 | 272 | 2020 | 2021 | R16
166652152029 | 162691152029 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-10 | 2019-05-08 | 2019-05-10 |  | 2019-09-19 | Overhead | R16 |  | 21 | 3 |  |  | 117 | 2019 | 2019 | R16
162330199078 | 168090199078 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-14 | 2020-07-14 | 2020-07-31 | 2020-10-14 | 2021-07-16 | Underground | R16 | 2020-10-14 | 1 | 14 | 54 | 198 | 264 | 2020 | 2021 | R16
164205175476 | 161201175476 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-01-03 | 2020-01-03 | 2020-01-03 |  | 2020-07-08 | Overhead | R16 | 2020-04-20 | 1 |  | 77 | 58 | 134 | 2020 | 2020 | R16
164583192578 | 169830192578 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-29 | 2020-05-29 | 2020-05-29 | 2020-07-20 | 2020-10-06 | Overhead | R16 | 2020-07-20 | 1 |  | 37 | 57 | 93 | 2020 | 2020 | R16
161094187002 | 161011187002 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-04-09 | 2020-04-09 | 2020-04-09 |  | 2021-09-13 | Underground | R16 | 2021-08-18 | 1 |  | 355 | 19 | 373 | 2020 | 2021 | R16
166652158420 | 168162158420 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-03 | 2019-07-12 | 2019-07-18 |  | 2020-10-06 | Overhead | R16 |  | 8 | 5 |  |  | 330 | 2019 | 2020 | R16
165489191379 | 168154191379 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-05-20 | 2020-05-20 | 2020-05-20 |  | 2020-08-28 | Underground | R16 | 2020-06-26 | 1 |  | 28 | 46 | 73 | 2020 | 2020 | R16
166776199902 | 162327199902 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-06-15 | 2020-06-15 | 2020-08-06 | 2020-10-06 | 2021-01-21 | Overhead | R16 | 2020-10-06 | 1 | 39 | 44 | 78 | 159 | 2020 | 2021 | R16
168462182777 | 163022182777 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-28 | 2020-03-03 | 2020-03-03 |  | 2020-06-09 | Overhead | R16 | 2020-03-30 | 3 |  | 20 | 52 | 73 | 2020 | 2020 | R16
165857178064 | 161350178064 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-06 | 2020-01-06 | 2020-01-24 |  | 2020-06-09 | Underground | R16 | 2020-03-27 | 1 | 15 | 46 | 53 | 112 | 2020 | 2020 | R16
166652252805 | 167767252805 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-24 | 2021-09-30 | 2021-10-19 |  | 2022-10-21 | Overhead | R16 |  | 5 | 14 |  |  | 281 | 2021 | 2022 | R16
166652293706 | 162619293706 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-09 | 2022-09-07 | 2022-09-14 |  | 2023-09-06 | Overhead | R16 |  | 22 | 6 |  |  | 282 | 2022 | 2023 | R16
169130176926 | 160653176926 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2020-01-02 | 2020-01-02 | 2020-01-14 |  | 2020-06-09 | Underground | R16 |  | 1 | 9 |  |  | 114 | 2020 | 2020 | R16
166652315511 | 169349315511 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-27 | 2023-03-27 | 2023-04-11 |  | 2023-10-04 | Overhead | R16 |  | 1 | 12 |  |  | 138 | 2023 | 2023 | R16
164492224434 | 160318224434 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Commercial | 2020-06-03 | 2021-03-17 | 2021-03-23 |  | 2022-08-29 | Underground | R16 |  | 206 | 5 |  |  | 584 | 2020 | 2022 | R16
160144186908 | 166274186908 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-28 | 2020-01-28 | 2020-04-08 | 2020-05-13 | 2020-05-15 | Underground | R16 | 2020-05-13 | 1 | 52 | 26 | 3 | 79 | 2020 | 2020 | R16
160452176283 | 161783176283 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-07 | 2020-01-07 | 2020-01-07 |  | 2020-06-09 | Underground | R16 | 2020-03-05 | 1 |  | 43 | 69 | 111 | 2020 | 2020 | R16
160400183729 | 162492183729 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-26 | 2020-03-10 | 2020-03-10 | 2020-11-05 | 2021-07-24 | Overhead | R16 | 2020-11-05 | 10 |  | 173 | 187 | 368 | 2020 | 2021 | R16
165560182712 | 163746182712 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-03-03 | 2020-03-03 | 2020-03-03 | 2020-08-14 | 2020-10-06 | Overhead | R16 | 2020-08-14 | 1 |  | 119 | 38 | 156 | 2020 | 2020 | R16
160600187504 | 161801187504 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-14 | 2020-04-14 | 2020-04-14 |  | 2020-10-06 | Underground | R16 | 2020-07-30 | 1 |  | 78 | 49 | 126 | 2020 | 2020 | R16
165021184756 | 166734184756 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2020-03-17 | 2020-03-20 | 2020-03-20 |  | 2020-07-08 | Overhead | R16 | 2020-05-14 | 4 |  | 40 | 40 | 82 | 2020 | 2020 | R16
165257197761 | 161695197761 | NON-RESIDENTIAL - WAREHOUSE | UG R16 RESD AND NON RESD UD | Commercial | 2020-01-07 | 2020-04-08 | 2020-07-17 | 2020-11-11 | 2020-12-16 | Underground | R16 | 2020-11-11 | 67 | 73 | 84 | 26 | 247 | 2020 | 2020 | R16
162763191590 | 167822191590 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-19 | 2020-05-19 | 2020-05-19 |  | 2020-07-13 | Overhead | R16 | 2020-06-15 | 1 |  | 20 | 21 | 40 | 2020 | 2020 | R16
167242185231 | 167712185231 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-23 | 2020-03-24 | 2020-03-24 | 2020-03-25 | 2020-07-02 | Overhead | R16 | 2020-03-25 | 2 |  | 2 | 72 | 74 | 2020 | 2020 | R16
167073179213 | 167483179213 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-02-03 | 2020-02-03 | 2020-02-03 |  | 2020-06-09 | Underground | R16 | 2020-02-19 | 1 |  | 13 | 80 | 92 | 2020 | 2020 | R16
166621188632 | 166250188632 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-03-14 | 2020-03-14 | 2020-04-21 |  | 2020-07-10 | Overhead | R16 |  | 0 | 27 |  |  | 85 | 2020 | 2020 | R16
169727206932 | 160360206932 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-04-06 | 2020-04-07 | 2020-10-13 |  | 2021-10-25 | Underground | R16 |  | 2 | 136 |  |  | 406 | 2020 | 2021 | R16
169922178893 | 169931178893 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-12-23 | 2019-12-23 | 2020-01-31 | 2022-11-24 | 2022-11-28 | Underground | R16 | 2022-11-24 | 1 | 30 | 735 | 3 | 766 | 2019 | 2022 | R16
167159148181 | 169949148181 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-26 | 2019-04-02 | 2019-04-04 |  | 2020-06-09 | Overhead | R16 |  | 6 | 3 |  |  | 316 | 2019 | 2020 | R16
165814202715 | 165974202715 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-02 | 2020-07-02 | 2020-09-03 |  | 2021-04-21 | Underground | R16 | 2021-01-26 | 1 | 46 | 104 | 62 | 210 | 2020 | 2021 | R16
167273191896 | 168607191896 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-22 | 2020-05-22 | 2020-05-22 | 2021-06-09 | 2021-08-16 | Overhead | R16 | 2021-06-09 | 1 |  | 274 | 49 | 322 | 2020 | 2021 | R16
167162172777 | 167314172777 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-16 | 2019-10-29 | 2019-11-25 |  | 2020-07-09 | Underground | R16 |  | 10 | 20 |  |  | 192 | 2019 | 2020 | R16
167162172833 | 167330172833 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-16 | 2019-10-28 | 2019-11-25 |  | 2021-11-10 | Underground | R16 |  | 9 | 21 |  |  | 541 | 2019 | 2021 | R16
168961216412 | 169684216412 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2020-05-29 | 2020-06-02 | 2021-01-06 |  | 2021-05-07 | Underground | R16 |  | 3 | 157 |  |  | 246 | 2020 | 2021 | R16
167162228718 | 165963228718 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-06 | 2021-04-09 | 2021-04-29 |  | 2021-10-25 | Underground | R16 |  | 4 | 15 |  |  | 145 | 2021 | 2021 | R16
167162252035 | 166122252035 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-09-16 | 2021-09-17 | 2021-10-14 |  | 2022-04-26 | Underground | R16 |  | 2 | 20 |  |  | 159 | 2021 | 2022 | R16
168472195647 | 165051195647 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2020-08-21 | 2020-08-24 | Overhead | R16 | 2020-08-21 | 1 |  | 40 | 2 | 41 | 2020 | 2020 | R16
166904190351 | 165619190351 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-07 | 2020-05-07 | 2020-05-07 |  | 2020-07-09 | Overhead | R16 | 2020-05-28 | 1 |  | 16 | 31 | 46 | 2020 | 2020 | R16
161430230653 | 161415230653 | NON-RESIDENTIAL - LODGING | UG R16 RESD AND NON RESD UD | Commercial | 2020-04-13 | 2020-04-13 | 2021-05-14 | 2021-07-30 | 2022-03-23 | Underground | R16 | 2021-07-30 | 1 | 285 | 56 | 169 | 508 | 2020 | 2022 | R16
165039189126 | 163967189126 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-27 | 2020-04-27 | 2020-04-27 |  | 2020-07-09 | Overhead | R16 | 2020-06-08 | 1 |  | 31 | 24 | 54 | 2020 | 2020 | R16
167164151918 | 166497151918 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2019-01-10 | 2019-04-22 | 2019-05-10 |  | 2019-08-12 | Underground | R16 |  | 73 | 15 |  |  | 153 | 2019 | 2019 | R16
165465178467 | 166436178467 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-29 | 2020-01-29 | 2020-01-29 | 2020-02-21 | 2020-02-24 | Overhead | R16 | 2020-02-21 | 1 |  | 18 | 2 | 19 | 2020 | 2020 | R16
167998185327 | 167959185327 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2020-03-24 | 2020-03-24 | 2020-03-25 |  | 2021-12-02 | Underground | R16 |  | 1 | 2 |  |  | 443 | 2020 | 2021 | R16
160835177403 | 164523177403 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-18 | 2020-01-18 | 2020-01-18 |  | 2020-06-09 | Overhead | R16 | 2020-03-17 | 0 |  | 42 | 61 | 102 | 2020 | 2020 | R16
167165154597 | 161409154597 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-30 | 2019-06-06 | 2019-06-07 |  | 2019-08-12 | Overhead | R16 |  | 6 | 2 |  |  | 53 | 2019 | 2019 | R16
162487191694 | 168206191694 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Residential | 2020-05-20 | 2020-05-21 | 2020-05-21 |  | 2020-07-09 | Overhead | R16 |  | 2 |  |  |  | 37 | 2020 | 2020 | R16
167165156021 | 162678156021 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-07 | 2019-06-18 | 2019-06-21 |  | 2019-10-04 | Overhead | R16 |  | 8 | 4 |  |  | 86 | 2019 | 2019 | R16
165435183777 | 165791183777 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-11 | 2020-03-11 | 2020-03-11 | 2021-06-29 | 2021-12-29 | Overhead | R16 | 2021-06-29 | 1 |  | 340 | 132 | 471 | 2020 | 2021 | R16
167165163823 | 167729163823 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-08-27 | 2019-09-03 | 2019-09-09 |  | 2019-09-26 | Overhead | R16 |  | 6 | 5 |  |  | 23 | 2019 | 2019 | R16
165109182057 | 160513182057 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-30 | 2020-01-06 | 2020-02-26 | 2020-03-17 | 2020-03-18 | Underground | R16 | 2020-03-17 | 6 | 38 | 15 | 2 | 58 | 2019 | 2020 | R16
160525193743 | 168389193743 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-21 | 2020-05-21 | 2020-06-08 | 2020-11-09 | 2020-11-10 | Underground | R16 | 2020-11-09 | 1 | 13 | 111 | 2 | 124 | 2020 | 2020 | R16
167165176510 | 169239176510 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-18 | 2020-01-02 | 2020-01-10 |  | 2020-12-14 | Overhead | R16 |  | 12 | 7 |  |  | 259 | 2019 | 2020 | R16
162614184347 | 166623184347 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-17 | 2020-03-17 | 2020-03-17 | 2020-05-07 | 2020-05-07 | Overhead | R16 | 2020-05-07 | 1 |  | 38 |  | 38 | 2020 | 2020 | R16
161817225165 | 164527225165 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-25 | 2020-06-25 | 2021-03-30 | 2021-07-02 | 2021-08-12 | Underground | R16 | 2021-07-02 | 1 | 199 | 69 | 30 | 296 | 2020 | 2021 | R16
166591222163 | 169230222163 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2020-05-27 | 2020-10-03 | 2021-03-02 |  | 2021-10-25 | Overhead | R16 |  | 93 | 107 |  |  | 369 | 2020 | 2021 | R16
169050176889 | 168939176889 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-18 | 2019-12-18 | 2020-01-14 |  | 2020-07-14 | Underground | R16 | 2020-06-18 | 1 | 20 | 113 | 19 | 150 | 2019 | 2020 | R16
167165215334 | 161405215334 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-12-17 | 2020-12-18 | 2020-12-22 |  | 2021-04-29 | Overhead | R16 |  | 2 | 3 |  |  | 96 | 2020 | 2021 | R16
161050182979 | 164385182979 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-05 | 2020-03-05 | 2020-03-05 |  | 2020-07-01 | Overhead | R16 | 2020-05-01 | 1 |  | 42 | 44 | 85 | 2020 | 2020 | R16
162070197291 | 168057197291 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-14 | 2020-07-14 | 2020-07-14 | 2020-11-23 | 2021-04-07 | Overhead | R16 | 2020-11-23 | 1 |  | 95 | 98 | 192 | 2020 | 2021 | R16
164200196478 | 166568196478 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-07-08 | 2020-07-08 | 2020-07-08 | 2020-08-27 | 2020-11-02 | Overhead | R16 | 2020-08-27 | 1 |  | 37 | 48 | 84 | 2020 | 2020 | R16
161524193371 | 162797193371 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-02-26 | 2020-02-26 | 2020-06-05 |  | 2023-08-14 | Underground | R16 | 2023-07-18 | 1 | 73 | 813 | 20 | 904 | 2020 | 2023 | R16
168959183552 | 164945183552 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-09 | 2020-03-09 | 2020-03-09 | 2020-05-12 | 2020-05-13 | Overhead | R16 | 2020-05-12 | 1 |  | 47 | 2 | 48 | 2020 | 2020 | R16
160407211784 | 162039211784 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-24 | 2020-11-18 | 2020-11-23 |  | 2021-05-07 | Overhead | R16 | 2021-02-25 | 193 | 4 | 69 | 52 | 315 | 2020 | 2021 | R16
164498190299 | 165967190299 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-07 | 2020-05-07 | 2020-05-07 | 2020-06-18 | 2020-06-18 | Underground | R16 | 2020-06-18 | 1 |  | 31 |  | 31 | 2020 | 2020 | R16
162240196027 | 160388196027 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-06-04 | 2020-06-04 | 2020-06-30 |  | 2023-11-17 | Underground | R16 |  | 1 | 19 |  |  | 902 | 2020 | 2023 | R16
167943192390 | 169355192390 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-28 | 2020-05-28 | 2020-05-28 | 2020-09-23 | 2020-12-29 | Overhead | R16 | 2020-09-23 | 1 |  | 85 | 70 | 154 | 2020 | 2020 | R16
166357191494 | 167808191494 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-19 | 2020-05-19 | 2020-05-19 |  | 2022-10-20 | Overhead | R16 |  | 1 |  |  |  | 633 | 2020 | 2022 | R16
161064195055 | 164186195055 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2020-06-24 | 2020-06-24 | 2020-06-24 |  | 2021-04-14 | Overhead | R16 | 2020-12-11 | 1 |  | 123 | 89 | 211 | 2020 | 2021 | R16
167022194544 | 162517194544 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-16 | 2020-06-16 | 2020-06-16 | 2020-07-22 | 2020-10-06 | Overhead | R16 | 2020-07-22 | 1 |  | 27 | 55 | 81 | 2020 | 2020 | R16
167412203255 | 167422203255 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-15 | 2020-05-15 | 2020-09-09 |  | 2021-02-17 | Underground | R16 | 2020-10-19 | 1 | 84 | 29 | 88 | 199 | 2020 | 2021 | R16
166558182986 | 164317182986 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-05 | 2020-03-05 | 2020-03-05 | 2020-04-24 | 2020-07-01 | Overhead | R16 | 2020-04-24 | 1 |  | 37 | 49 | 85 | 2020 | 2020 | R16
164907175073 | 169864175073 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-12-23 | 2019-12-23 | 2019-12-23 |  | 2020-07-08 | Underground | R16 | 2020-04-16 | 1 |  | 84 | 60 | 143 | 2019 | 2020 | R16
169130176928 | 160722176928 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2020-01-02 | 2020-01-02 | 2020-01-14 |  | 2022-08-29 | Underground | R16 |  | 1 | 9 |  |  | 693 | 2020 | 2022 | R16
161533186943 | 160797186943 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-04-09 | 2020-04-09 | 2020-04-09 |  | 2020-07-02 | Underground | R16 |  | 1 |  |  |  | 61 | 2020 | 2020 | R16
168083194442 | 168158194442 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-20 | 2020-05-20 | 2020-06-15 |  | 2020-10-06 | Underground | R16 | 2020-08-17 | 1 | 19 | 46 | 37 | 100 | 2020 | 2020 | R16
166451192231 | 169043192231 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-26 | 2020-05-26 | 2020-05-26 |  | 2020-07-13 | Overhead | R16 | 2020-06-15 | 1 |  | 15 | 21 | 35 | 2020 | 2020 | R16
166046222474 | 164357222474 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-06-25 | 2020-12-17 | 2021-03-05 | 2022-06-29 | 2022-07-01 | Underground | R16 | 2022-06-29 | 126 | 57 | 344 | 3 | 527 | 2020 | 2022 | R16
166194186785 | 160510186785 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-07 | 2020-04-07 | 2020-04-08 |  | 2021-04-16 | Overhead | R16 |  | 1 | 2 |  |  | 269 | 2020 | 2021 | R16
165530187519 | 169511187519 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-02-12 | 2020-02-12 | 2020-04-15 | 2021-10-06 | 2021-11-10 | Underground | R16 | 2021-10-06 | 1 | 46 | 386 | 26 | 456 | 2020 | 2021 | R16
169686182965 | 164119182965 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-04 | 2020-03-04 | 2020-03-04 | 2020-04-03 | 2020-04-22 | Overhead | R16 | 2020-04-03 | 1 |  | 23 | 14 | 36 | 2020 | 2020 | R16
169804181695 | 161576181695 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2020-01-06 | 2020-02-19 | 2020-02-24 |  | 2021-01-07 | Underground | R16 | 2020-10-02 | 33 | 4 | 160 | 70 | 264 | 2020 | 2021 | R16
162954274979 | 162606274979 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-06-17 | 2020-10-23 | 2022-04-06 |  | 2023-06-05 | Underground | R16 |  | 93 | 379 |  |  | 774 | 2020 | 2023 | R16
168457176075 | 161639176075 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-07 | 2020-01-07 | 2020-01-08 |  | 2020-06-09 | Overhead | R16 | 2020-03-09 | 1 | 2 | 44 | 67 | 111 | 2020 | 2020 | R16
163931198118 | 167784198118 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-13 | 2020-07-22 | 2020-07-22 | 2020-07-23 | 2020-10-06 | Overhead | R16 | 2020-07-23 | 8 |  | 2 | 54 | 62 | 2020 | 2020 | R16
168922186912 | 160807186912 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-04-09 | 2020-04-09 | 2020-04-09 | 2021-12-13 | 2023-06-07 | Underground | R16 | 2021-12-13 | 1 |  | 438 | 388 | 825 | 2020 | 2023 | R16
163464195079 | 166932195079 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-05-13 | 2020-05-13 | 2020-06-23 | 2021-02-14 | 2021-02-17 | Overhead | R16 | 2021-02-14 | 1 | 30 | 169 | 3 | 201 | 2020 | 2021 | R16
161370195624 | 164492195624 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-06-26 | 2020-06-26 | 2020-06-29 |  | 2021-07-19 | Overhead | R16 | 2020-12-07 | 1 | 2 | 116 | 161 | 277 | 2020 | 2021 | R16
168438183208 | 164707183208 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-06 | 2020-03-06 | 2020-03-06 | 2020-04-22 | 2020-07-08 | Overhead | R16 | 2020-04-22 | 1 |  | 34 | 56 | 89 | 2020 | 2020 | R16
165020210173 | 165877210173 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-07-02 | 2020-08-03 | 2020-11-10 | 2021-10-21 | 2021-12-08 | Underground | R16 | 2021-10-21 | 23 | 72 | 248 | 35 | 375 | 2020 | 2021 | R16
167152183725 | 167671183725 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-02-04 | 2020-03-10 | 2020-03-10 |  | 2021-11-08 | Overhead | R16 | 2021-05-21 | 26 |  | 314 | 122 | 460 | 2020 | 2021 | R16
165809183875 | 165986183875 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-27 | 2020-01-27 | 2020-03-12 |  | 2020-07-10 | Underground | R16 | 2020-06-10 | 1 | 34 | 65 | 23 | 120 | 2020 | 2020 | R16
160619141133 | 168519141133 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-23 | 2019-01-23 | 2019-01-24 |  | 2019-08-26 | Overhead | R16 |  | 1 | 2 |  |  | 154 | 2019 | 2019 | R16
163159190199 | 163851190199 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-27 | 2020-05-06 | 2020-05-06 | 2020-06-03 | 2020-06-16 | Underground | R16 | 2020-06-03 | 8 |  | 21 | 10 | 37 | 2020 | 2020 | R16
169250189965 | 165246189965 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2020-05-04 | 2020-05-04 | 2020-05-04 | 2020-07-24 | 2020-07-28 | Overhead | R16 | 2020-07-24 | 1 |  | 60 | 3 | 62 | 2020 | 2020 | R16
169848187648 | 162034187648 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-15 | 2020-04-15 | 2020-04-15 |  | 2020-07-07 | Overhead | R16 | 2020-05-11 | 1 |  | 19 | 42 | 60 | 2020 | 2020 | R16
162525177808 | 162658177808 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-01-10 | 2020-01-10 | 2020-01-23 |  | 2022-06-28 | Underground | R16 |  | 1 | 10 |  |  | 643 | 2020 | 2022 | R16
168933182996 | 164547182996 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-03-06 | 2020-03-06 | 2020-03-06 | 2020-04-08 | 2020-06-23 | Overhead | R16 | 2020-04-08 | 1 |  | 24 | 55 | 78 | 2020 | 2020 | R16
160951183794 | 165801183794 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-12 | 2020-03-12 | 2020-03-12 |  | 2020-10-06 | Overhead | R16 | 2020-07-13 | 1 |  | 88 | 62 | 149 | 2020 | 2020 | R16
163353197080 | 164789197080 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-06-29 | 2020-07-07 | 2020-07-13 |  | 2020-10-06 | Overhead | R16 |  | 7 | 5 |  |  | 72 | 2020 | 2020 | R16
164059176972 | 163549176972 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-15 | 2020-01-15 | 2020-01-15 |  | 2022-10-17 | Overhead | R16 |  | 1 |  |  |  | 719 | 2020 | 2022 | R16
166222201171 | 161703201171 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-06-11 | 2020-06-11 | 2020-08-20 |  | 2021-11-08 | Overhead | R16 | 2021-05-07 | 1 | 51 | 187 | 132 | 368 | 2020 | 2021 | R16
166649197847 | 166908197847 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-13 | 2020-05-13 | 2020-07-20 |  | 2020-12-15 | Underground | R16 | 2020-09-10 | 1 | 49 | 39 | 69 | 155 | 2020 | 2020 | R16
167864195759 | 165011195759 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-29 | 2020-06-29 | 2020-06-29 |  | 2021-01-08 | Underground | R16 | 2020-10-06 | 1 |  | 72 | 69 | 140 | 2020 | 2021 | R16
163513152041 | 166937152041 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-03 | 2019-05-08 | 2019-05-10 |  | 2019-08-12 | Overhead | R16 |  | 4 | 3 |  |  | 72 | 2019 | 2019 | R16
163669187567 | 164541187567 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-18 | 2020-01-18 | 2020-04-15 |  | 2020-10-06 | Underground | R16 | 2020-08-12 | 0 | 63 | 86 | 40 | 187 | 2020 | 2020 | R16
163513172046 | 161480172046 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-06 | 2019-11-08 | 2019-11-15 |  | 2021-11-10 | Overhead | R16 |  | 3 | 6 |  |  | 526 | 2019 | 2021 | R16
160919190774 | 161579190774 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-21 | 2020-02-21 | 2020-05-12 |  | 2020-08-28 | Underground | R16 | 2020-07-06 | 1 | 58 | 40 | 40 | 136 | 2020 | 2020 | R16
162610175669 | 160907175669 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-03 | 2020-01-03 | 2020-01-03 |  | 2020-04-29 | Overhead | R16 |  | 1 |  |  |  | 84 | 2020 | 2020 | R16
168367194961 | 168338194961 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-21 | 2020-05-21 | 2020-06-22 |  | 2020-10-06 | Underground | R16 | 2020-07-27 | 1 | 23 | 26 | 52 | 99 | 2020 | 2020 | R16
166520194960 | 163369194960 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-06-22 | 2020-06-22 | 2020-06-22 | 2021-04-14 | 2021-04-16 | Underground | R16 | 2021-04-14 | 1 |  | 213 | 3 | 215 | 2020 | 2021 | R16
165257197760 | 161694197760 | NON-RESIDENTIAL - WAREHOUSE | UG R16 RESD AND NON RESD UD | Commercial | 2020-01-07 | 2020-04-13 | 2020-07-17 | 2020-11-11 | 2020-12-09 | Underground | R16 | 2020-11-11 | 70 | 70 | 84 | 21 | 242 | 2020 | 2020 | R16
166291180911 | 160645180911 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-02-18 | 2020-02-18 | 2020-02-18 | 2020-05-11 | 2020-05-12 | Overhead | R16 | 2020-05-11 | 1 |  | 60 | 2 | 61 | 2020 | 2020 | R16
169213184399 | 166735184399 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-03-18 | 2020-03-18 | 2020-03-18 | 2021-03-18 | 2021-03-19 | Overhead | R16 | 2021-03-18 | 1 |  | 262 | 2 | 263 | 2020 | 2021 | R16
169326178161 | 165950178161 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-01-27 | 2020-01-27 | 2020-01-27 | 2020-03-18 | 2020-03-19 | Overhead | R16 | 2020-03-18 | 1 |  | 38 | 2 | 39 | 2020 | 2020 | R16
164742177718 | 169357177718 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-12-19 | 2019-12-19 | 2020-01-22 |  | 2020-10-06 | Underground | R16 | 2020-07-17 | 1 | 25 | 128 | 58 | 209 | 2019 | 2020 | R16
167939200739 | 168012200739 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-20 | 2020-05-20 | 2020-08-18 |  | 2022-10-17 | Underground | R16 |  | 1 | 65 |  |  | 629 | 2020 | 2022 | R16
167332183978 | 166083183978 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-13 | 2020-03-13 | 2020-03-13 | 2020-04-21 | 2020-04-22 | Overhead | R16 | 2020-04-21 | 1 |  | 28 | 2 | 29 | 2020 | 2020 | R16
161014189305 | 168634189305 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-07 | 2020-02-07 | 2020-04-29 |  | 2023-02-06 | Underground | R16 | 2020-06-12 | 1 | 59 | 33 | 692 | 782 | 2020 | 2023 | R16
169514183240 | 164660183240 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-06 | 2020-03-06 | 2020-03-06 |  | 2020-07-02 | Overhead | R16 | 2020-05-04 | 1 |  | 42 | 44 | 85 | 2020 | 2020 | R16
169532181670 | 162082181670 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-24 | 2020-02-24 | 2020-02-24 |  | 2021-11-13 | Overhead | R16 | 2021-10-20 | 1 |  | 433 | 18 | 450 | 2020 | 2021 | R16
160900179538 | 168006179538 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-05 | 2020-02-06 | 2020-02-06 | 2020-03-11 | 2020-03-17 | Overhead | R16 | 2020-03-11 | 2 |  | 25 | 5 | 30 | 2020 | 2020 | R16
163871197081 | 167501197081 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-07-13 | 2020-07-13 | 2020-07-13 |  | 2021-07-02 | Underground | R16 | 2020-10-22 | 1 |  | 74 | 182 | 255 | 2020 | 2021 | R16
166175185805 | 168673185805 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-27 | 2020-03-27 | 2020-03-30 |  | 2020-07-01 | Overhead | R16 | 2020-04-30 | 1 | 2 | 24 | 45 | 69 | 2020 | 2020 | R16
167986199920 | 166296199920 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-07 | 2020-07-27 | 2020-08-06 |  | 2020-12-29 | Overhead | R16 |  | 15 | 9 |  |  | 126 | 2020 | 2020 | R16
166714257712 | 166875257712 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-11-02 | 2021-11-22 | 2021-11-22 |  | 2022-02-07 | Underground | R16 | 2022-01-13 | 15 |  | 39 | 18 | 70 | 2021 | 2022 | R16
165891188701 | 165729188701 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-03-12 | 2020-03-12 | 2020-04-22 |  | 2021-04-14 | Underground | R16 | 2020-12-17 | 1 | 30 | 172 | 85 | 285 | 2020 | 2021 | R16
160701185811 | 169064185811 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-30 | 2020-03-30 | 2020-03-30 | 2020-09-28 | 2020-09-29 | Overhead | R16 | 2020-09-28 | 1 |  | 131 | 2 | 132 | 2020 | 2020 | R16
167018207107 | 164978207107 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-06-29 | 2020-06-30 | 2020-10-13 | 2021-08-23 | 2021-12-09 | Underground | R16 | 2021-08-23 | 2 | 76 | 225 | 79 | 379 | 2020 | 2021 | R16
163828189517 | 163489189517 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-01-15 | 2020-01-15 | 2020-05-01 | 2020-09-25 | 2020-12-29 | Overhead | R16 | 2020-09-25 | 1 | 78 | 106 | 68 | 250 | 2020 | 2020 | R16
169953190864 | 166926190864 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-03-18 | 2020-03-18 | 2020-05-13 | 2022-10-07 | 2022-10-10 | Underground | R16 | 2022-10-07 | 1 | 41 | 628 | 2 | 669 | 2020 | 2022 | R16
165702181963 | 162049181963 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-25 | 2020-02-25 | 2020-02-25 | 2020-03-13 | 2020-06-09 | Overhead | R16 | 2020-03-13 | 1 |  | 14 | 63 | 76 | 2020 | 2020 | R16
167128200017 | 167097200017 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-14 | 2020-05-14 | 2020-08-07 |  | 2021-07-01 | Underground | R16 | 2020-10-12 | 1 | 62 | 47 | 189 | 296 | 2020 | 2021 | R16
165238197040 | 166801197040 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-17 | 2020-07-10 | 2020-07-10 | 2020-09-16 | 2020-11-13 | Overhead | R16 | 2020-09-16 | 84 |  | 49 | 43 | 174 | 2020 | 2020 | R16
162599183958 | 164817183958 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-09 | 2020-03-13 | 2020-03-13 | 2020-03-27 | 2020-07-08 | Overhead | R16 | 2020-03-27 | 5 |  | 11 | 74 | 88 | 2020 | 2020 | R16
168540182006 | 169972182006 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-14 | 2020-02-14 | 2020-02-26 | 2020-03-10 | 2020-07-07 | Underground | R16 | 2020-03-10 | 1 | 9 | 10 | 86 | 103 | 2020 | 2020 | R16
162161183966 | 165962183966 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-12 | 2020-03-12 | 2020-03-12 | 2020-03-25 | 2020-06-09 | Overhead | R16 | 2020-03-25 | 1 |  | 10 | 55 | 64 | 2020 | 2020 | R16
164209180104 | 164498180104 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-18 | 2020-01-18 | 2020-02-10 | 2020-03-16 | 2020-08-28 | Underground | R16 | 2020-03-16 | 0 | 16 | 26 | 120 | 160 | 2020 | 2020 | R16
164730184617 | 161877184617 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-08 | 2020-01-08 | 2020-03-19 | 2020-05-20 | 2022-08-03 | Underground | R16 | 2020-05-20 | 1 | 52 | 45 | 576 | 671 | 2020 | 2022 | R16
162209192405 | 167966192405 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-19 | 2020-05-19 | 2020-05-27 | 2020-06-11 | 2020-06-12 | Underground | R16 | 2020-06-11 | 1 | 7 | 12 | 2 | 19 | 2020 | 2020 | R16
160875177819 | 165610177819 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-23 | 2020-01-23 | 2020-01-23 |  | 2020-07-01 | Overhead | R16 | 2020-03-02 | 1 |  | 28 | 88 | 115 | 2020 | 2020 | R16
168110178845 | 169358178845 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-12-19 | 2019-12-19 | 2020-01-31 | 2022-11-01 | 2022-11-02 | Underground | R16 | 2022-11-01 | 1 | 32 | 718 | 2 | 750 | 2019 | 2022 | R16
164926177530 | 164927177530 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-01-21 | 2020-01-21 | 2020-01-21 |  | 2020-10-08 | Underground | R16 | 2020-08-14 | 1 |  | 149 | 40 | 188 | 2020 | 2020 | R16
160228186846 | 160678186846 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-08 | 2020-04-08 | 2020-04-08 |  | 2023-06-08 | Overhead | R16 |  | 1 |  |  |  | 827 | 2020 | 2023 | R16
161501196071 | 160024196071 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-12-26 | 2019-12-26 | 2020-06-30 |  | 2021-07-26 | Underground | R16 |  | 1 | 134 |  |  | 413 | 2019 | 2021 | R16
163524247845 | 167596247845 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-02-04 | 2020-02-04 | 2021-09-14 |  | 2022-02-24 | Overhead | R16 | 2022-02-23 | 1 | 421 | 117 | 2 | 538 | 2020 | 2022 | R16
161238170329 | 160820170329 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-01 | 2019-11-01 | 2019-11-01 |  | 2020-10-06 | Overhead | R16 | 2020-09-18 | 1 |  | 231 | 13 | 243 | 2019 | 2020 | R16
169469181300 | 161165181300 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-20 | 2020-02-20 | 2020-02-20 |  | 2022-10-21 | Overhead | R16 | 2022-08-10 | 1 |  | 645 | 53 | 697 | 2020 | 2022 | R16
162152184785 | 167233184785 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-20 | 2020-03-20 | 2020-03-20 |  | 2020-07-01 | Overhead | R16 | 2020-04-27 | 1 |  | 27 | 48 | 74 | 2020 | 2020 | R16
168467211002 | 168982211002 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-02-10 | 2020-09-18 | 2020-11-17 |  | 2021-04-07 | Overhead | R16 |  | 160 | 43 |  |  | 303 | 2020 | 2021 | R16
167093186098 | 169713186098 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-04-02 | 2020-04-02 | 2020-04-02 | 2020-06-10 | 2020-08-28 | Overhead | R16 | 2020-06-10 | 1 |  | 50 | 58 | 107 | 2020 | 2020 | R16
169925179510 | 165141179510 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-22 | 2020-01-22 | 2020-02-05 | 2020-02-18 | 2020-02-19 | Overhead | R16 | 2020-02-18 | 1 | 11 | 10 | 2 | 21 | 2020 | 2020 | R16
160275198127 | 169270198127 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Commercial | 2020-03-31 | 2020-06-02 | 2020-07-22 | 2021-04-27 | 2021-05-20 | Overhead | R16 | 2021-04-27 | 46 | 37 | 200 | 18 | 298 | 2020 | 2021 | R16
163032179876 | 161965179876 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2020-01-08 | 2020-01-08 | 2020-02-11 |  | 2020-06-09 | Underground | R16 |  | 1 | 25 |  |  | 110 | 2020 | 2020 | R16
169213184420 | 166659184420 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-03-17 | 2020-03-17 | 2020-03-17 | 2022-11-21 | 2022-11-22 | Overhead | R16 | 2022-11-21 | 1 |  | 700 | 2 | 701 | 2020 | 2022 | R16
161058190447 | 166057190447 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-03-12 | 2020-03-13 | 2020-05-09 | 2020-09-22 | 2021-02-12 | Underground | R16 | 2020-09-22 | 2 | 41 | 97 | 104 | 242 | 2020 | 2021 | R16
166039192873 | 160310192873 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2020-06-03 | 2020-06-03 | 2020-06-03 |  | 2021-07-14 | Overhead | R16 | 2020-11-20 | 1 |  | 123 | 169 | 291 | 2020 | 2021 | R16
163567178210 | 163568178210 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-15 | 2020-01-15 | 2020-01-27 | 2020-03-25 | 2020-03-25 | Underground | R16 | 2020-03-25 | 1 | 9 | 43 |  | 51 | 2020 | 2020 | R16
160860187763 | 167221187763 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-31 | 2020-02-03 | 2020-04-16 | 2020-07-07 | 2020-07-10 | Underground | R16 | 2020-07-07 | 2 | 54 | 59 | 4 | 116 | 2020 | 2020 | R16
169171213511 | 161347213511 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-02-20 | 2020-02-20 | 2020-12-10 |  | 2021-08-23 | Underground | R16 |  | 1 | 211 |  |  | 393 | 2020 | 2021 | R16
169139194553 | 162570194553 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-16 | 2020-06-16 | 2020-06-17 |  | 2020-08-28 | Overhead | R16 | 2020-07-02 | 1 | 2 | 12 | 42 | 54 | 2020 | 2020 | R16
166199186320 | 169161186320 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-03-31 | 2020-04-03 | 2020-04-03 |  | 2020-07-08 | Overhead | R16 | 2020-05-22 | 4 |  | 36 | 34 | 72 | 2020 | 2020 | R16
164745191974 | 166928191974 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-05-13 | 2020-05-13 | 2020-05-22 | 2021-04-20 | 2021-11-08 | Underground | R16 | 2021-04-20 | 1 | 8 | 238 | 145 | 389 | 2020 | 2021 | R16
169665194190 | 162060194190 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-12 | 2020-06-12 | 2020-06-12 |  | 2021-11-11 | Overhead | R16 | 2021-07-20 | 1 |  | 288 | 83 | 370 | 2020 | 2021 | R16
160168176103 | 161700176103 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-01-07 | 2020-01-07 | 2020-01-07 |  | 2020-06-09 | Overhead | R16 | 2020-01-13 | 1 |  | 5 | 107 | 111 | 2020 | 2020 | R16
168470175316 | 160434175316 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-12-31 | 2019-12-31 | 2019-12-31 | 2020-03-02 | 2020-03-05 | Underground | R16 | 2020-03-02 | 1 |  | 45 | 4 | 48 | 2019 | 2020 | R16
166658193126 | 160299193126 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-06-03 | 2020-06-03 | 2020-06-03 | 2020-06-18 | 2020-08-20 | Overhead | R16 | 2020-06-18 | 1 |  | 12 | 46 | 57 | 2020 | 2020 | R16
168062192393 | 169432192393 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-28 | 2020-05-28 | 2020-05-28 | 2020-07-13 | 2020-10-06 | Overhead | R16 | 2020-07-13 | 1 |  | 33 | 62 | 94 | 2020 | 2020 | R16
163358183443 | 164881183443 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-09 | 2020-03-09 | 2020-03-09 |  | 2020-10-06 | Overhead | R16 | 2020-07-14 | 1 |  | 92 | 61 | 152 | 2020 | 2020 | R16
161015196226 | 163984196226 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-23 | 2020-06-30 | 2020-07-01 | 2020-07-30 | 2020-10-06 | Overhead | R16 | 2020-07-30 | 6 | 2 | 22 | 49 | 76 | 2020 | 2020 | R16
165581191551 | 167902191551 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-19 | 2020-05-19 | 2020-05-19 |  | 2020-08-20 | Overhead | R16 | 2020-06-24 | 1 |  | 27 | 42 | 68 | 2020 | 2020 | R16
160033198029 | 166811198029 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-07-09 | 2020-07-09 | 2020-07-21 |  | 2021-11-09 | Underground | R16 |  | 1 | 9 |  |  | 349 | 2020 | 2021 | R16
164410184472 | 166910184472 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-18 | 2020-03-18 | 2020-03-18 | 2020-06-15 | 2020-06-16 | Overhead | R16 | 2020-06-15 | 1 |  | 64 | 2 | 65 | 2020 | 2020 | R16
166302233594 | 163624233594 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2020-01-15 | 2021-06-05 | 2021-06-05 | 2023-07-18 | 2023-07-19 | Overhead | R16 | 2023-07-18 | 363 |  | 552 | 2 | 916 | 2020 | 2023 | R16
160958275385 | 167487275385 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-03-23 | 2020-03-23 | 2022-04-08 |  | 2023-10-05 | Underground | R16 |  | 1 | 535 |  |  | 924 | 2020 | 2023 | R16
162431179347 | 167827179347 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-04 | 2020-02-04 | 2020-02-04 | 2020-03-24 | 2020-06-09 | Overhead | R16 | 2020-03-24 | 1 |  | 36 | 56 | 91 | 2020 | 2020 | R16
161226187581 | 161685187581 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-21 | 2020-02-21 | 2020-04-14 |  | 2020-08-28 | Underground | R16 | 2020-07-07 | 1 | 38 | 61 | 39 | 136 | 2020 | 2020 | R16
160718206174 | 165840206174 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-05 | 2020-10-05 | 2020-10-05 |  | 2021-04-14 | Overhead | R16 | 2020-12-17 | 1 |  | 54 | 85 | 138 | 2020 | 2021 | R16
160029195016 | 160904195016 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-08 | 2020-06-23 | 2020-06-23 | 2020-07-06 | 2020-07-14 | Overhead | R16 | 2020-07-06 | 12 |  | 10 | 7 | 27 | 2020 | 2020 | R16
168617242904 | 169042242904 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-30 | 2020-03-30 | 2021-08-10 | 2021-08-11 | 2021-08-11 | Underground | R16 | 2021-08-11 | 1 | 357 | 2 |  | 358 | 2020 | 2021 | R16
169025175520 | 169973175520 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-12-23 | 2019-12-31 | 2019-12-31 | 2020-02-14 | 2021-11-13 | Overhead | R16 | 2020-02-14 | 7 |  | 34 | 456 | 495 | 2019 | 2021 | R16
162852190189 | 164253190189 | MOBILE HOMES PARK AB622 | ELEC SVC FOR MOBILE HOMES | Residential | 2020-04-28 | 2020-04-28 | 2020-05-06 |  | 2022-04-07 | Underground | R16 |  | 1 | 7 |  |  | 508 | 2020 | 2022 | R16
169221191205 | 169297191205 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-03-31 | 2020-03-31 | 2020-05-15 |  | 2022-12-20 | Underground | R16 | 2022-12-16 | 1 | 34 | 676 | 3 | 711 | 2020 | 2022 | R16
164091194764 | 163157194764 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-18 | 2020-06-18 | 2020-06-18 |  | 2021-11-10 | Overhead | R16 | 2020-07-17 | 1 |  | 22 | 344 | 365 | 2020 | 2021 | R16
160233178832 | 167022178832 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-01-31 | 2020-01-31 | 2020-01-31 |  | 2020-06-09 | Overhead | R16 | 2020-04-20 | 1 |  | 57 | 37 | 93 | 2020 | 2020 | R16
168078181443 | 161606181443 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-21 | 2020-02-21 | 2020-02-21 |  | 2020-06-09 | Underground | R16 | 2020-03-11 | 1 |  | 14 | 65 | 78 | 2020 | 2020 | R16
164579185987 | 166106185987 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-13 | 2020-03-13 | 2020-03-31 |  | 2021-05-06 | Underground | R16 | 2021-02-22 | 1 | 13 | 235 | 54 | 300 | 2020 | 2021 | R16
163097185896 | 168919185896 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-31 | 2020-03-31 | 2020-03-31 |  | 2020-10-06 | Overhead | R16 | 2020-07-15 | 1 |  | 77 | 60 | 136 | 2020 | 2020 | R16
166402175094 | 160013175094 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-26 | 2019-12-26 | 2019-12-26 | 2020-01-31 | 2020-07-07 | Overhead | R16 | 2020-01-31 | 1 |  | 27 | 113 | 139 | 2019 | 2020 | R16
167194194583 | 162600194583 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-06-16 | 2020-06-16 | 2020-06-16 |  | 2020-10-06 | Overhead | R16 | 2020-07-14 | 1 |  | 21 | 61 | 81 | 2020 | 2020 | R16
163744188899 | 166082188899 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-13 | 2020-04-24 | 2020-04-24 | 2020-06-10 | 2020-06-11 | Overhead | R16 | 2020-06-10 | 31 |  | 34 | 2 | 65 | 2020 | 2020 | R16
167328183772 | 167075183772 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-31 | 2020-01-31 | 2020-03-11 | 2020-04-14 | 2020-04-15 | Underground | R16 | 2020-04-14 | 1 | 29 | 25 | 2 | 54 | 2020 | 2020 | R16
169684190131 | 167212190131 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-19 | 2020-03-19 | 2020-05-06 | 2020-10-05 | 2020-10-06 | Underground | R16 | 2020-10-05 | 1 | 35 | 109 | 2 | 144 | 2020 | 2020 | R16
169995236649 | 169997236649 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2020-02-13 | 2021-01-11 | 2021-06-25 | 2022-06-16 | 2022-06-29 | Underground | R16 | 2022-06-16 | 238 | 120 | 255 | 10 | 620 | 2020 | 2022 | R16
163695166806 | 169830166806 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-07-14 | 2019-07-14 | 2019-10-04 |  | 2019-11-21 | Overhead | R16 |  | 0 | 60 |  |  | 94 | 2019 | 2019 | R16
163398197136 | 167712197136 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-13 | 2020-07-13 | 2020-07-13 |  | 2021-04-13 | Underground | R16 | 2020-12-08 | 1 |  | 107 | 91 | 197 | 2020 | 2021 | R16
160577194576 | 162646194576 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-17 | 2020-06-17 | 2020-06-17 | 2020-10-22 | 2023-04-12 | Overhead | R16 | 2020-10-22 | 1 |  | 92 | 645 | 736 | 2020 | 2023 | R16
163096188934 | 161284188934 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-10 | 2020-04-11 | 2020-04-24 | 2020-06-05 | 2021-01-14 | Overhead | R16 | 2020-06-05 | 1 | 10 | 31 | 160 | 200 | 2020 | 2021 | R16
161157188545 | 167521188545 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-03 | 2020-02-03 | 2020-04-21 |  | 2020-06-29 | Underground | R16 | 2020-04-22 | 1 | 57 | 2 | 49 | 106 | 2020 | 2020 | R16
164367180556 | 164542180556 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-01-18 | 2020-01-18 | 2020-02-14 | 2021-09-08 | 2021-10-25 | Underground | R16 | 2021-09-08 | 0 | 20 | 409 | 34 | 461 | 2020 | 2021 | R16
169724208126 | 160351208126 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-04-06 | 2020-09-04 | 2020-10-23 |  | 2021-11-04 | Underground | R16 |  | 110 | 36 |  |  | 414 | 2020 | 2021 | R16
165571177052 | 161704177052 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-01-07 | 2020-01-07 | 2020-01-16 |  | 2020-07-08 | Underground | R16 | 2020-05-21 | 1 | 8 | 91 | 35 | 132 | 2020 | 2020 | R16
164286179602 | 165937179602 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-27 | 2020-01-27 | 2020-02-06 |  | 2021-07-24 | Underground | R16 | 2020-11-09 | 1 | 9 | 198 | 185 | 390 | 2020 | 2021 | R16
164326185855 | 168561185855 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-03-27 | 2020-03-31 | 2020-03-31 | 2020-06-26 | 2020-09-01 | Overhead | R16 | 2020-06-26 | 3 |  | 64 | 48 | 113 | 2020 | 2020 | R16
168959181829 | 169840181829 | NON-RESIDENTIAL - SMALL RETAIL | OH R16 RES NON RES OS | Commercial | 2020-02-13 | 2020-02-13 | 2020-02-25 |  | 2020-06-29 | Overhead | R16 |  | 1 | 9 |  |  | 98 | 2020 | 2020 | R16
163201183281 | 164664183281 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-06 | 2020-03-06 | 2020-03-06 |  | 2020-06-24 | Overhead | R16 | 2020-04-21 | 1 |  | 33 | 47 | 79 | 2020 | 2020 | R16
167610254101 | 160692254101 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Commercial | 2020-04-08 | 2021-02-22 | 2021-10-27 | 2022-01-03 | 2022-01-26 | Underground | R16 | 2022-01-03 | 229 | 178 | 49 | 18 | 471 | 2020 | 2022 | R16
164536177713 | 164378177713 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-18 | 2020-01-18 | 2020-01-22 | 2020-07-09 | 2022-08-29 | Overhead | R16 | 2020-07-09 | 0 | 3 | 122 | 558 | 681 | 2020 | 2022 | R16
167888182320 | 163142182320 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-28 | 2020-02-28 | 2020-02-28 |  | 2020-07-02 | Overhead | R16 | 2020-05-06 | 1 |  | 49 | 42 | 90 | 2020 | 2020 | R16
164701209505 | 168188209505 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-15 | 2020-07-15 | 2020-11-03 | 2020-11-06 | 2021-04-07 | Underground | R16 | 2020-11-06 | 1 | 80 | 4 | 109 | 191 | 2020 | 2021 | R16
166373151065 | 166815151065 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-05-02 | 2019-05-02 | 2019-05-02 |  | 2019-08-26 | Underground | R16 | 2019-06-25 | 1 |  | 39 | 45 | 83 | 2019 | 2019 | R16
162902196278 | 165996196278 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-02 | 2020-07-02 | 2020-07-02 |  | 2021-07-01 | Overhead | R16 | 2020-08-05 | 1 |  | 25 | 237 | 261 | 2020 | 2021 | R16
166394151087 | 166737151087 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-05-02 | 2019-05-02 | 2019-05-02 |  | 2019-08-26 | Underground | R16 | 2019-06-25 | 1 |  | 39 | 45 | 83 | 2019 | 2019 | R16
166500179505 | 168152179505 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-05 | 2020-02-05 | 2020-02-05 | 2020-04-17 | 2021-06-30 | Overhead | R16 | 2020-04-17 | 1 |  | 53 | 314 | 366 | 2020 | 2021 | R16
166395150974 | 166859150974 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-05-02 | 2019-05-02 | 2019-05-02 |  | 2019-08-26 | Underground | R16 | 2019-06-25 | 1 |  | 39 | 45 | 83 | 2019 | 2019 | R16
166197182934 | 164237182934 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-05 | 2020-03-05 | 2020-03-05 | 2020-05-04 | 2020-05-06 | Overhead | R16 | 2020-05-04 | 1 |  | 43 | 3 | 45 | 2020 | 2020 | R16
161274176459 | 161832176459 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-01-07 | 2020-01-07 | 2020-01-10 |  | 2020-06-09 | Overhead | R16 |  | 1 | 4 |  |  | 111 | 2020 | 2020 | R16
167316188482 | 163052188482 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-21 | 2020-04-21 | 2020-04-21 |  | 2021-11-10 | Overhead | R16 | 2020-05-12 | 1 |  | 16 | 392 | 407 | 2020 | 2021 | R16
163556186247 | 169801186247 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-04-02 | 2020-04-02 | 2020-04-02 |  | 2020-07-08 | Overhead | R16 | 2020-05-22 | 1 |  | 37 | 34 | 70 | 2020 | 2020 | R16
169309229812 | 169339229812 | SPECIFIC BUDGET PROJECTS | UG R16 RESD AND NON RESD UD | Commercial | 2019-12-19 | 2019-12-19 | 2021-05-06 |  | 2022-01-18 | Underground | R16 |  | 1 | 361 |  |  | 544 | 2019 | 2022 | R16
162821186482 | 160260186482 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-06 | 2020-04-06 | 2020-04-06 |  | 2020-06-23 | Overhead | R16 | 2020-04-15 | 1 |  | 8 | 50 | 57 | 2020 | 2020 | R16
162829196852 | 167291196852 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-10 | 2020-07-10 | 2020-07-10 |  | 2020-10-06 | Overhead | R16 | 2020-08-20 | 1 |  | 30 | 34 | 63 | 2020 | 2020 | R16
166638190795 | 163477190795 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-04-24 | 2020-05-12 | 2020-05-12 |  | 2020-12-29 | Overhead | R16 |  | 13 |  |  |  | 178 | 2020 | 2020 | R16
169482197951 | 169701197951 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-29 | 2020-05-29 | 2020-07-21 | 2020-08-10 | 2020-10-06 | Underground | R16 | 2020-08-10 | 1 | 38 | 15 | 42 | 93 | 2020 | 2020 | R16
167647186250 | 169728186250 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-02 | 2020-04-02 | 2020-04-02 | 2022-03-08 | 2022-03-31 | Overhead | R16 | 2022-03-08 | 1 |  | 504 | 18 | 521 | 2020 | 2022 | R16
162448182158 | 162554182158 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-01-10 | 2020-01-10 | 2020-02-28 | 2023-01-20 | 2023-01-23 | Underground | R16 | 2023-01-20 | 1 | 36 | 756 | 2 | 792 | 2020 | 2023 | R16
162106196382 | 166815196382 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-05-12 | 2020-05-12 | 2020-07-02 |  | 2021-05-06 | Overhead | R16 | 2021-02-24 | 1 | 38 | 170 | 52 | 258 | 2020 | 2021 | R16
160908190660 | 163632190660 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-01-15 | 2020-01-24 | 2020-05-11 | 2021-07-30 | 2021-08-02 | Underground | R16 | 2021-07-30 | 8 | 77 | 320 | 2 | 404 | 2020 | 2021 | R16
169130191592 | 167682191592 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-18 | 2020-05-18 | 2020-05-19 |  | 2022-10-19 | Overhead | R16 |  | 1 | 2 |  |  | 633 | 2020 | 2022 | R16
169716183602 | 165022183602 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-09 | 2020-03-09 | 2020-03-09 |  | 2020-10-06 | Overhead | R16 | 2020-07-23 | 1 |  | 99 | 54 | 152 | 2020 | 2020 | R16
166399185217 | 167807185217 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-24 | 2020-03-25 | 2020-03-25 | 2023-01-05 | 2023-01-05 | Underground | R16 | 2023-01-05 | 2 |  | 727 |  | 728 | 2020 | 2023 | R16
166608179089 | 167541179089 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-03 | 2020-02-03 | 2020-02-03 | 2020-03-10 | 2020-03-11 | Overhead | R16 | 2020-03-10 | 1 |  | 27 | 2 | 28 | 2020 | 2020 | R16
160555195275 | 164249195275 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-24 | 2020-06-24 | 2020-06-24 | 2020-07-07 | 2020-10-06 | Overhead | R16 | 2020-07-07 | 1 |  | 10 | 66 | 75 | 2020 | 2020 | R16
160904165606 | 166526165606 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-20 | 2019-09-19 | 2019-09-24 |  | 2020-06-09 | Overhead | R16 |  | 23 | 4 |  |  | 211 | 2019 | 2020 | R16
162664177079 | 164364177079 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-17 | 2020-01-17 | 2020-01-17 |  | 2020-08-28 | Overhead | R16 | 2020-07-01 | 1 |  | 119 | 43 | 161 | 2020 | 2020 | R16
162212205822 | 167409205822 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-13 | 2020-07-13 | 2020-09-30 |  | 2021-01-22 | Overhead | R16 | 2020-10-15 | 1 | 58 | 12 | 72 | 140 | 2020 | 2021 | R16
161127174937 | 162320174937 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-09-22 | 2019-09-22 | 2019-12-20 |  | 2023-03-16 | Underground | R16 |  | 0 | 65 |  |  | 909 | 2019 | 2023 | R16
166441177262 | 163659177262 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-15 | 2020-01-15 | 2020-01-16 |  | 2020-07-09 | Overhead | R16 | 2020-05-28 | 1 | 2 | 96 | 31 | 127 | 2020 | 2020 | R16
166848189345 | 161817189345 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-15 | 2020-04-15 | 2020-04-29 |  | 2020-07-09 | Underground | R16 | 2020-06-08 | 1 | 11 | 29 | 24 | 62 | 2020 | 2020 | R16
164037194031 | 169252194031 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-05-27 | 2020-06-03 | 2020-06-12 |  | 2020-11-11 | Underground | R16 |  | 6 | 8 |  |  | 121 | 2020 | 2020 | R16
167311197397 | 168371197397 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-03-26 | 2020-03-26 | 2020-07-15 |  | 2021-05-07 | Underground | R16 | 2021-02-26 | 1 | 80 | 163 | 51 | 292 | 2020 | 2021 | R16
165446187257 | 160839187257 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-04-09 | 2020-04-09 | 2020-04-15 |  | 2021-11-04 | Underground | R16 | 2021-06-02 | 1 | 5 | 296 | 112 | 411 | 2020 | 2021 | R16
166112187123 | 161095187123 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-10 | 2020-04-10 | 2020-04-10 |  | 2020-07-09 | Overhead | R16 | 2020-06-04 | 1 |  | 40 | 26 | 65 | 2020 | 2020 | R16
165748188422 | 162774188422 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-20 | 2020-04-20 | 2020-04-20 |  | 2020-07-09 | Overhead | R16 | 2020-06-01 | 1 |  | 31 | 29 | 59 | 2020 | 2020 | R16
160361187559 | 161798187559 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-15 | 2020-04-15 | 2020-04-15 |  | 2020-07-02 | Overhead | R16 | 2020-05-06 | 1 |  | 16 | 42 | 57 | 2020 | 2020 | R16
163131178748 | 166819178748 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-30 | 2020-01-30 | 2020-01-30 | 2020-04-07 | 2020-04-09 | Overhead | R16 | 2020-04-07 | 1 |  | 49 | 3 | 51 | 2020 | 2020 | R16
163130139214 | 165407139214 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-05 | 2019-01-05 | 2019-01-05 |  | 2020-10-06 | Overhead | R16 | 2020-07-14 | 0 |  | 397 | 61 | 457 | 2019 | 2020 | R16
164085186683 | 160480186683 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-04-07 | 2020-04-07 | 2020-04-07 |  | 2020-06-09 | Overhead | R16 | 2020-04-08 | 1 |  | 2 | 45 | 46 | 2020 | 2020 | R16
168078198004 | 168159198004 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-07-14 | 2020-07-14 | 2020-07-21 | 2020-09-29 | 2020-10-02 | Overhead | R16 | 2020-09-29 | 1 | 6 | 51 | 4 | 59 | 2020 | 2020 | R16
166293187310 | 161509187310 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-13 | 2020-04-13 | 2020-04-13 |  | 2020-08-14 | Overhead | R16 | 2020-06-22 | 1 |  | 51 | 40 | 90 | 2020 | 2020 | R16
164113188772 | 163220188772 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-22 | 2020-04-22 | 2020-04-22 |  | 2020-08-28 | Overhead | R16 | 2020-07-02 | 1 |  | 52 | 42 | 93 | 2020 | 2020 | R16
160775196368 | 161617196368 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-11 | 2020-06-11 | 2020-07-02 | 2020-10-09 | 2021-01-20 | Underground | R16 | 2020-10-09 | 1 | 16 | 72 | 74 | 160 | 2020 | 2021 | R16
160337192432 | 165289192432 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-05-04 | 2020-05-04 | 2020-05-28 | 2020-07-06 | 2020-12-09 | Overhead | R16 | 2020-07-06 | 1 | 19 | 28 | 113 | 158 | 2020 | 2020 | R16
163731156062 | 161084156062 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-05-28 | 2019-05-28 | 2019-06-21 |  | 2019-08-26 | Overhead | R16 |  | 1 | 19 |  |  | 65 | 2019 | 2019 | R16
161344192183 | 168850192183 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-26 | 2020-05-26 | 2020-05-26 |  | 2021-07-01 | Overhead | R16 | 2020-06-18 | 1 |  | 18 | 271 | 288 | 2020 | 2021 | R16
163340194516 | 162448194516 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-16 | 2020-06-16 | 2020-06-16 |  | 2020-10-06 | Overhead | R16 | 2020-07-09 | 1 |  | 18 | 64 | 81 | 2020 | 2020 | R16
161430231281 | 164219231281 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH CP R16 WORK RELO TO UG | Commercial | 2020-06-24 | 2020-06-24 | 2021-05-18 | 2021-06-14 | 2021-10-19 | Overhead | R16 | 2021-06-14 | 1 | 235 | 20 | 92 | 345 | 2020 | 2021 | R16
163649182579 | 163803182579 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-03-03 | 2020-03-03 | 2020-03-03 | 2020-03-11 | 2020-03-12 | Overhead | R16 | 2020-03-11 | 1 |  | 7 | 2 | 8 | 2020 | 2020 | R16
169502180891 | 160479180891 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2020-02-14 | 2020-02-14 | 2020-02-18 |  | 2020-07-08 | Underground | R16 |  | 1 | 3 |  |  | 104 | 2020 | 2020 | R16
160791197233 | 161392197233 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-09 | 2020-06-19 | 2020-07-14 | 2020-09-02 | 2020-09-04 | Underground | R16 | 2020-09-02 | 9 | 18 | 37 | 3 | 64 | 2020 | 2020 | R16
166949196591 | 166781196591 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-01-30 | 2020-02-03 | 2020-07-07 | 2020-11-09 | 2020-12-16 | Underground | R16 | 2020-11-09 | 3 | 112 | 90 | 28 | 230 | 2020 | 2020 | R16
166476217683 | 168611217683 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH CP R16 WORK RELO TO UG | Commercial | 2020-05-22 | 2020-05-27 | 2021-01-19 |  | 2022-08-01 | Overhead | R16 |  | 4 | 170 |  |  | 572 | 2020 | 2022 | R16
166476217683 | 168611217683 | INDUSTRIAL | UG R16 RESD AND NON RESD UD | Commercial | 2020-05-22 | 2020-05-27 | 2021-01-19 |  | 2022-08-01 | Underground | R16 |  | 4 | 170 |  |  | 572 | 2020 | 2022 | R16
165091200700 | 164566200700 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-03-06 | 2020-07-23 | 2020-08-14 |  | 2022-08-29 | Underground | R16 |  | 100 | 17 |  |  | 647 | 2020 | 2022 | R16
164511179409 | 163471179409 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2020-01-14 | 2020-01-28 | 2020-02-05 |  | 2022-07-19 | Underground | R16 |  | 11 | 7 |  |  | 656 | 2020 | 2022 | R16
167148194517 | 167125194517 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-20 | 2020-03-20 | 2020-06-16 | 2020-07-07 | 2020-07-08 | Underground | R16 | 2020-07-07 | 1 | 63 | 16 | 2 | 79 | 2020 | 2020 | R16
166480181016 | 160852181016 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-19 | 2020-02-19 | 2020-02-19 |  | 2020-06-23 | Overhead | R16 | 2020-04-15 | 1 |  | 41 | 50 | 90 | 2020 | 2020 | R16
168089190963 | 167708190963 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-03-24 | 2020-03-24 | 2020-05-13 |  | 2020-10-06 | Underground | R16 | 2020-07-09 | 1 | 37 | 42 | 64 | 141 | 2020 | 2020 | R16
163239298459 | 168075298459 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-07-14 | 2022-04-28 | 2022-10-28 | 2022-12-12 | 2023-02-03 | Overhead | R16 | 2022-12-12 | 468 | 132 | 32 | 40 | 669 | 2020 | 2023 | R16
163258195223 | 160876195223 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-02-19 | 2020-05-18 | 2020-06-24 | 2020-10-08 | 2020-12-07 | Underground | R16 | 2020-10-08 | 64 | 28 | 77 | 43 | 209 | 2020 | 2020 | R16
166080200210 | 162359200210 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-06-15 | 2020-08-05 | 2020-08-11 | 2020-08-11 | 2020-11-04 | Overhead | R16 | 2020-08-11 | 38 | 5 |  | 62 | 103 | 2020 | 2020 | R16
166018177268 | 163682177268 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-01-15 | 2020-01-16 | 2020-01-16 |  | 2022-10-18 | Overhead | R16 |  | 2 |  |  |  | 720 | 2020 | 2022 | R16
169208179548 | 166663179548 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Commercial | 2020-01-29 | 2020-01-30 | 2020-02-06 |  | 2020-06-09 | Underground | R16 |  | 2 | 6 |  |  | 95 | 2020 | 2020 | R16
161710183720 | 163994183720 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-03-04 | 2020-03-10 | 2020-03-10 | 2021-01-19 | 2021-04-23 | Overhead | R16 | 2021-01-19 | 5 |  | 226 | 69 | 298 | 2020 | 2021 | R16
167913177778 | 165575177778 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-23 | 2020-01-23 | 2020-01-24 |  | 2020-07-07 | Overhead | R16 | 2020-05-06 | 1 | 2 | 74 | 45 | 119 | 2020 | 2020 | R16
162320177853 | 165480177853 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-23 | 2020-01-23 | 2020-01-23 |  | 2020-06-09 | Overhead | R16 | 2020-03-02 | 1 |  | 28 | 72 | 99 | 2020 | 2020 | R16
168339147981 | 161200147981 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-04-02 | 2019-04-02 | 2019-04-02 |  | 2019-04-26 | Underground | R16 | 2019-04-03 | 1 |  | 2 | 18 | 19 | 2019 | 2019 | R16
167060178480 | 166086178480 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2020-01-28 | 2020-01-28 | 2020-01-28 | 2020-06-23 | 2021-07-01 | Overhead | R16 | 2020-06-23 | 1 |  | 106 | 268 | 373 | 2020 | 2021 | R16
168371144958 | 166737144958 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-06 | 2019-03-06 | 2019-03-06 |  | 2019-08-26 | Underground | R16 | 2019-06-24 | 1 |  | 79 | 46 | 124 | 2019 | 2019 | R16
169356250838 | 169203250838 | FOREIGN UTILITY | UG R16 RESD AND NON RESD UD | Commercial | 2020-02-11 | 2020-02-21 | 2021-10-06 | 2021-11-15 | 2021-12-14 | Underground | R16 | 2021-11-15 | 9 | 424 | 29 | 22 | 481 | 2020 | 2021 | R16
164131197202 | 167629197202 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-13 | 2020-07-13 | 2020-07-13 |  | 2020-10-06 | Overhead | R16 | 2020-08-10 | 1 |  | 21 | 42 | 62 | 2020 | 2020 | R16
160327178580 | 166162178580 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-01-27 | 2020-01-27 | 2020-01-29 |  | 2020-07-14 | Overhead | R16 |  | 1 | 3 |  |  | 122 | 2020 | 2020 | R16
169138200326 | 169237200326 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-03-31 | 2020-03-31 | 2020-08-11 | 2021-10-21 | 2021-10-22 | Underground | R16 | 2021-10-21 | 1 | 96 | 313 | 2 | 409 | 2020 | 2021 | R16
166120202214 | 164493202214 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-06-26 | 2020-08-07 | 2020-08-28 | 2020-12-10 | 2021-02-04 | Underground | R16 | 2020-12-10 | 31 | 16 | 75 | 41 | 160 | 2020 | 2021 | R16
169818184750 | 167083184750 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-12-10 | 2019-12-10 | 2020-03-20 |  | 2021-07-07 | Underground | R16 |  | 1 | 74 |  |  | 412 | 2019 | 2021 | R16
166053192874 | 168072192874 | STREET AND HIGHWAY RELOCATION | R16 ELECTRIC RELOCATION US | Commercial | 2020-02-05 | 2020-03-25 | 2020-06-03 |  | 2020-10-06 | Underground | R16 |  | 36 | 51 |  |  | 175 | 2020 | 2020 | R16
166447189555 | 162201189555 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-02-24 | 2020-04-28 | 2020-05-01 |  | 2020-11-02 | Underground | R16 | 2020-08-31 | 47 | 4 | 87 | 46 | 181 | 2020 | 2020 | R16
167988205958 | 162384205958 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-06-15 | 2020-07-29 | 2020-10-02 |  | 2021-04-20 | Underground | R16 |  | 33 | 48 |  |  | 222 | 2020 | 2021 | R16
163620191677 | 166586191677 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-17 | 2020-05-21 | 2020-05-21 |  | 2020-07-09 | Underground | R16 | 2020-06-03 | 48 |  | 10 | 27 | 83 | 2020 | 2020 | R16
169586177178 | 163854177178 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-01-16 | 2020-01-16 | 2020-01-16 | 2021-05-13 | 2021-11-08 | Overhead | R16 | 2021-05-13 | 1 |  | 346 | 128 | 473 | 2020 | 2021 | R16
169280200902 | 169275200902 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-27 | 2020-05-27 | 2020-08-18 |  | 2021-11-13 | Underground | R16 | 2021-10-20 | 1 | 60 | 307 | 18 | 383 | 2020 | 2021 | R16
167906192945 | 169933192945 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-01 | 2020-06-01 | 2020-06-01 |  | 2020-10-06 | Underground | R16 | 2020-07-08 | 1 |  | 28 | 65 | 92 | 2020 | 2020 | R16
160833166903 | 169700166903 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-12 | 2019-08-21 | 2019-10-04 |  | 2019-11-26 | Overhead | R16 |  | 29 | 33 |  |  | 98 | 2019 | 2019 | R16
168734187396 | 161696187396 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-14 | 2020-04-14 | 2020-04-14 | 2020-08-14 | 2020-10-06 | Overhead | R16 | 2020-08-14 | 1 |  | 89 | 38 | 126 | 2020 | 2020 | R16
163118197307 | 168351197307 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-02-06 | 2020-02-06 | 2020-07-14 |  | 2020-10-06 | Overhead | R16 |  | 1 | 114 |  |  | 174 | 2020 | 2020 | R16
163114181958 | 162912181958 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-27 | 2020-02-27 | 2020-02-27 | 2020-03-05 | 2020-10-06 | Overhead | R16 | 2020-03-05 | 1 |  | 6 | 154 | 159 | 2020 | 2020 | R16
168360193296 | 160603193296 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-04 | 2020-06-04 | 2020-06-04 | 2020-12-23 | 2021-05-05 | Overhead | R16 | 2020-12-23 | 1 |  | 145 | 96 | 240 | 2020 | 2021 | R16
163715183915 | 166131183915 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-13 | 2020-03-13 | 2020-03-13 | 2020-04-27 | 2020-07-02 | Overhead | R16 | 2020-04-27 | 1 |  | 32 | 49 | 80 | 2020 | 2020 | R16
160833240747 | 161015240747 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-14 | 2021-07-16 | 2021-07-26 |  | 2021-10-25 | Overhead | R16 |  | 3 | 7 |  |  | 74 | 2021 | 2021 | R16
164063274164 | 167367274164 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-20 | 2020-03-20 | 2022-03-29 |  | 2022-05-03 | Overhead | R16 | 2022-04-26 | 1 | 528 | 21 | 6 | 553 | 2020 | 2022 | R16
160458197125 | 160476197125 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-04 | 2020-06-04 | 2020-07-13 |  | 2021-08-10 | Underground | R16 | 2021-03-18 | 1 | 28 | 179 | 104 | 309 | 2020 | 2021 | R16
160833290154 | 163743290154 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-04 | 2022-03-18 | 2022-08-25 |  | 2023-03-02 | Overhead | R16 |  | 11 | 115 |  |  | 260 | 2022 | 2023 | R16
162242188861 | 163460188861 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-23 | 2020-04-23 | 2020-04-23 | 2020-04-27 | 2020-05-07 | Overhead | R16 | 2020-04-27 | 1 |  | 3 | 9 | 11 | 2020 | 2020 | R16
164684201392 | 164665201392 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-26 | 2020-06-26 | 2020-08-21 |  | 2020-11-06 | Underground | R16 | 2020-09-03 | 1 | 41 | 10 | 47 | 96 | 2020 | 2020 | R16
167658188544 | 162759188544 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-20 | 2020-04-21 | 2020-04-21 |  | 2020-10-06 | Underground | R16 | 2020-08-28 | 2 |  | 94 | 28 | 122 | 2020 | 2020 | R16
163113189406 | 164447189406 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-29 | 2020-04-29 | 2020-04-29 |  | 2020-10-06 | Overhead | R16 | 2020-07-27 | 1 |  | 64 | 52 | 115 | 2020 | 2020 | R16
164532177711 | 164499177711 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-18 | 2020-01-18 | 2020-01-22 | 2020-01-30 | 2020-02-03 | Overhead | R16 | 2020-01-30 | 0 | 3 | 7 | 3 | 11 | 2020 | 2020 | R16
160327181629 | 164751181629 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-01-20 | 2020-01-20 | 2020-02-24 |  | 2021-01-12 | Overhead | R16 |  | 1 | 26 |  |  | 257 | 2020 | 2021 | R16
168779175366 | 160392175366 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-30 | 2019-12-30 | 2019-12-30 | 2020-08-11 | 2020-10-06 | Overhead | R16 | 2020-08-11 | 1 |  | 162 | 41 | 202 | 2019 | 2020 | R16
166700225199 | 161943225199 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-04-15 | 2020-04-15 | 2021-03-30 | 2021-05-03 | 2021-08-30 | Underground | R16 | 2021-05-03 | 1 | 250 | 25 | 86 | 359 | 2020 | 2021 | R16
160768190663 | 161394190663 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-13 | 2020-04-13 | 2020-05-11 |  | 2021-11-08 | Underground | R16 | 2021-03-18 | 1 | 21 | 224 | 168 | 411 | 2020 | 2021 | R16
163382180744 | 164850180744 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-21 | 2020-01-21 | 2020-02-14 | 2020-04-24 | 2020-04-27 | Underground | R16 | 2020-04-24 | 1 | 19 | 51 | 2 | 70 | 2020 | 2020 | R16
165720186075 | 165692186075 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-01-24 | 2020-01-24 | 2020-04-01 | 2022-05-26 | 2022-05-27 | Underground | R16 | 2022-05-26 | 1 | 49 | 562 | 2 | 611 | 2020 | 2022 | R16
162242185681 | 168742185681 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-27 | 2020-03-27 | 2020-03-27 |  | 2020-07-02 | Overhead | R16 | 2020-05-04 | 1 |  | 27 | 44 | 70 | 2020 | 2020 | R16
160018196078 | 160406196078 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-04 | 2020-06-04 | 2020-07-01 |  | 2020-10-06 | Underground | R16 | 2020-08-06 | 1 | 20 | 27 | 44 | 89 | 2020 | 2020 | R16
164249176164 | 161708176164 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-07 | 2020-01-07 | 2020-01-07 | 2020-02-07 | 2020-02-12 | Overhead | R16 | 2020-02-07 | 1 |  | 24 | 4 | 27 | 2020 | 2020 | R16
162599183094 | 164458183094 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-06 | 2020-03-06 | 2020-03-06 | 2020-07-16 | 2020-07-17 | Overhead | R16 | 2020-07-16 | 1 |  | 95 | 2 | 96 | 2020 | 2020 | R16
166590202428 | 164500202428 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-06-25 | 2020-08-29 | 2020-09-01 |  | 2021-07-02 | Overhead | R16 |  | 47 | 2 |  |  | 267 | 2020 | 2021 | R16
162509196339 | 166120196339 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-06 | 2020-07-06 | 2020-07-06 |  | 2020-12-29 | Overhead | R16 | 2020-09-25 | 1 |  | 60 | 68 | 127 | 2020 | 2020 | R16
163236198144 | 163322198144 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-01-14 | 2020-01-14 | 2020-07-23 |  | 2020-10-06 | Underground | R16 |  | 1 | 138 |  |  | 191 | 2020 | 2020 | R16
169517193994 | 168131193994 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-02-05 | 2020-02-05 | 2020-06-11 |  | 2020-11-06 | Overhead | R16 | 2020-07-10 | 1 | 92 | 22 | 86 | 198 | 2020 | 2020 | R16
169581234822 | 169584234822 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-02-12 | 2020-02-12 | 2021-06-14 |  | 2023-10-04 | Underground | R16 |  | 1 | 349 |  |  | 951 | 2020 | 2023 | R16
161772176773 | 160628176773 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-31 | 2019-12-31 | 2020-01-13 |  | 2020-06-09 | Underground | R16 | 2020-03-30 | 1 | 10 | 56 | 52 | 116 | 2019 | 2020 | R16
165148196056 | 165483196056 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2020-01-23 | 2020-06-05 | 2020-07-01 | 2022-03-09 | 2022-03-11 | Underground | R16 | 2022-03-09 | 97 | 19 | 441 | 3 | 557 | 2020 | 2022 | R16
163361167526 | 165691167526 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-09 | 2019-10-09 | 2019-10-09 |  | 2019-11-21 | Overhead | R16 | 2019-11-12 | 1 |  | 25 | 8 | 32 | 2019 | 2019 | R16
169777186861 | 160245186861 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-06 | 2020-04-08 | 2020-04-08 |  | 2021-07-24 | Overhead | R16 | 2020-10-30 | 3 |  | 148 | 191 | 340 | 2020 | 2021 | R16
161055194418 | 163224194418 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-22 | 2020-04-22 | 2020-06-16 |  | 2020-08-28 | Underground | R16 | 2020-06-30 | 1 | 40 | 11 | 44 | 93 | 2020 | 2020 | R16
169444182343 | 163137182343 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-28 | 2020-02-28 | 2020-02-28 |  | 2020-10-06 | Overhead | R16 | 2020-07-22 | 1 |  | 104 | 55 | 158 | 2020 | 2020 | R16
162689187337 | 165147187337 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-10 | 2020-03-10 | 2020-04-14 | 2020-07-20 | 2020-07-23 | Underground | R16 | 2020-07-20 | 1 | 26 | 70 | 4 | 98 | 2020 | 2020 | R16
166054197102 | 167563197102 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-13 | 2020-07-13 | 2020-07-13 |  | 2020-10-06 | Overhead | R16 | 2020-08-07 | 1 |  | 20 | 43 | 62 | 2020 | 2020 | R16
163351183263 | 163609183263 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-03-03 | 2020-03-03 | 2020-03-07 |  | 2020-07-09 | Overhead | R16 | 2020-06-01 | 1 | 4 | 61 | 29 | 93 | 2020 | 2020 | R16
169358184238 | 166476184238 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-16 | 2020-03-16 | 2020-03-16 | 2020-03-17 | 2020-06-24 | Overhead | R16 | 2020-03-17 | 1 |  | 2 | 72 | 73 | 2020 | 2020 | R16
163990190287 | 165696190287 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-06 | 2020-05-06 | 2020-05-07 |  | 2022-10-20 | Overhead | R16 |  | 1 | 2 |  |  | 642 | 2020 | 2022 | R16
165242226453 | 165244226453 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-01-22 | 2020-01-22 | 2021-04-12 | 2021-10-02 | 2021-10-05 | Overhead | R16 | 2021-10-02 | 1 | 319 | 125 | 2 | 445 | 2020 | 2021 | R16
169787195394 | 161171195394 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-08 | 2020-06-15 | 2020-06-26 | 2020-07-10 | 2020-07-29 | Underground | R16 | 2020-07-10 | 6 | 10 | 11 | 14 | 38 | 2020 | 2020 | R16
164215190036 | 165608190036 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-05 | 2020-05-05 | 2020-05-05 |  | 2020-07-08 | Overhead | R16 | 2020-05-26 | 1 |  | 16 | 32 | 47 | 2020 | 2020 | R16
161983185233 | 164801185233 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-09 | 2020-03-09 | 2020-03-24 |  | 2020-07-01 | Underground | R16 | 2020-04-29 | 1 | 12 | 27 | 46 | 83 | 2020 | 2020 | R16
164276181297 | 161239181297 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-20 | 2020-02-20 | 2020-02-20 | 2020-02-26 | 2020-06-09 | Overhead | R16 | 2020-02-26 | 1 |  | 5 | 75 | 79 | 2020 | 2020 | R16
163107179405 | 167757179405 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-05 | 2020-02-05 | 2020-02-05 | 2020-03-18 | 2020-07-10 | Overhead | R16 | 2020-03-18 | 1 |  | 31 | 83 | 113 | 2020 | 2020 | R16
161072188302 | 160908188302 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-04-10 | 2020-04-10 | 2020-04-20 | 2020-04-30 | 2022-08-29 | Underground | R16 | 2020-04-30 | 1 | 7 | 9 | 608 | 622 | 2020 | 2022 | R16
169403178190 | 165949178190 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-27 | 2020-01-27 | 2020-01-27 |  | 2020-06-09 | Overhead | R16 | 2020-03-13 | 1 |  | 35 | 63 | 97 | 2020 | 2020 | R16
161256196370 | 161456196370 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-10 | 2020-06-10 | 2020-07-02 |  | 2020-10-06 | Underground | R16 | 2020-08-19 | 1 | 17 | 35 | 35 | 85 | 2020 | 2020 | R16
163443177888 | 165356177888 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-23 | 2020-01-23 | 2020-01-23 |  | 2020-06-09 | Overhead | R16 | 2020-02-13 | 1 |  | 16 | 84 | 99 | 2020 | 2020 | R16
166970193287 | 161885193287 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-15 | 2020-06-04 | 2020-06-04 | 2020-06-24 | 2020-06-25 | Overhead | R16 | 2020-06-24 | 37 |  | 15 | 2 | 52 | 2020 | 2020 | R16
169057181376 | 166827181376 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-30 | 2020-02-06 | 2020-02-21 |  | 2022-08-29 | Underground | R16 |  | 6 | 12 |  |  | 673 | 2020 | 2022 | R16
167090185703 | 161107185703 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-19 | 2020-02-19 | 2020-03-27 | 2020-09-09 | 2020-09-15 | Underground | R16 | 2020-09-09 | 1 | 28 | 119 | 5 | 150 | 2020 | 2020 | R16
169401183913 | 169269183913 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-02-11 | 2020-03-12 | 2020-03-13 |  | 2022-03-10 | Underground | R16 |  | 23 | 2 |  |  | 543 | 2020 | 2022 | R16
164092190176 | 165915190176 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-07 | 2020-05-07 | 2020-05-07 |  | 2020-08-28 | Underground | R16 | 2020-07-01 | 1 |  | 40 | 43 | 82 | 2020 | 2020 | R16
164792184155 | 166694184155 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-17 | 2020-03-17 | 2020-03-17 | 2020-03-31 | 2020-04-02 | Overhead | R16 | 2020-03-31 | 1 |  | 11 | 3 | 13 | 2020 | 2020 | R16
168362189947 | 165346189947 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-05-04 | 2020-05-04 | 2020-05-04 | 2020-07-09 | 2020-07-10 | Overhead | R16 | 2020-07-09 | 1 |  | 49 | 2 | 50 | 2020 | 2020 | R16
169648158627 | 166507158627 | NON-RESIDENTIAL - SMALL RETAIL | R16 RESD AND NON RESD US | Commercial | 2019-01-10 | 2019-07-22 | 2019-07-22 |  | 2019-10-30 | Underground | R16 |  | 138 |  |  |  | 210 | 2019 | 2019 | R16
162976195426 | 163581195426 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-01-15 | 2020-04-14 | 2020-06-26 | 2021-02-11 | 2021-03-26 | Underground | R16 | 2021-02-11 | 65 | 54 | 165 | 32 | 313 | 2020 | 2021 | R16
167793183965 | 165888183965 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-12 | 2020-03-12 | 2020-03-12 | 2020-04-30 | 2020-04-30 | Overhead | R16 | 2020-04-30 | 1 |  | 36 |  | 36 | 2020 | 2020 | R16
163631189316 | 165378189316 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-01-23 | 2020-01-23 | 2020-04-29 | 2020-07-28 | 2021-01-04 | Overhead | R16 | 2020-07-28 | 1 | 70 | 65 | 115 | 248 | 2020 | 2021 | R16
169920178683 | 166670178683 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-29 | 2020-01-29 | 2020-01-29 | 2020-05-14 | 2020-05-15 | Overhead | R16 | 2020-05-14 | 1 |  | 77 | 2 | 78 | 2020 | 2020 | R16
162500186182 | 162610186182 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-01-10 | 2020-01-10 | 2020-04-02 | 2022-11-17 | 2022-12-05 | Underground | R16 | 2022-11-17 | 1 | 60 | 686 | 13 | 757 | 2020 | 2022 | R16
162941215365 | 162959215365 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-01-13 | 2020-01-13 | 2020-12-22 | 2021-06-16 | 2021-08-10 | Underground | R16 | 2021-06-16 | 1 | 247 | 127 | 40 | 412 | 2020 | 2021 | R16
161183191480 | 167558191480 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2020-05-18 | 2020-05-18 | 2020-05-18 |  | 2021-04-14 | Overhead | R16 | 2020-12-11 | 1 |  | 150 | 89 | 238 | 2020 | 2021 | R16
161554186873 | 168910186873 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-10 | 2020-02-10 | 2020-04-09 | 2020-07-20 | 2020-07-21 | Underground | R16 | 2020-07-20 | 1 | 44 | 73 | 2 | 117 | 2020 | 2020 | R16
164225194143 | 166481194143 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-11 | 2020-05-11 | 2020-06-12 | 2020-09-05 | 2020-09-09 | Underground | R16 | 2020-09-05 | 1 | 25 | 61 | 3 | 88 | 2020 | 2020 | R16
165151179846 | 168916179846 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-10 | 2020-02-10 | 2020-02-10 | 2020-04-23 | 2020-04-24 | Overhead | R16 | 2020-04-23 | 1 |  | 54 | 2 | 55 | 2020 | 2020 | R16
160577274880 | 169933274880 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-04-04 | 2022-04-04 | 2022-04-04 |  | 2022-06-30 | Underground | R16 |  | 1 |  |  |  | 64 | 2022 | 2022 | R16
165392192448 | 168824192448 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-27 | 2020-05-27 | 2020-05-27 |  | 2021-11-09 | Overhead | R16 | 2021-10-11 | 1 |  | 359 | 22 | 380 | 2020 | 2021 | R16
160579178364 | 165969178364 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-27 | 2020-01-27 | 2020-01-27 | 2020-03-10 | 2020-03-11 | Overhead | R16 | 2020-03-10 | 1 |  | 32 | 2 | 33 | 2020 | 2020 | R16
161054157502 | 165998157502 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2019-06-26 | 2019-06-26 | 2019-07-09 |  | 2020-05-27 | Underground | R16 |  | 1 | 10 |  |  | 241 | 2019 | 2020 | R16
163142182790 | 163779182790 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-03 | 2020-03-03 | 2020-03-03 |  | 2020-07-10 | Overhead | R16 | 2020-06-11 | 1 |  | 73 | 22 | 94 | 2020 | 2020 | R16
164937180050 | 169071180050 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-10 | 2020-02-10 | 2020-02-10 | 2020-03-13 | 2020-03-17 | Overhead | R16 | 2020-03-13 | 1 |  | 25 | 3 | 27 | 2020 | 2020 | R16
161116144481 | 165384144481 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential Subdivision | 2019-02-27 | 2019-02-27 | 2019-02-27 |  | 2020-06-09 | Underground | R16 |  | 1 |  |  |  | 335 | 2019 | 2020 | R16
166250197558 | 165847197558 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-03-12 | 2020-03-12 | 2020-07-20 |  | 2020-12-18 | Underground | R16 |  | 1 | 93 |  |  | 202 | 2020 | 2020 | R16
162890196275 | 165976196275 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-02 | 2020-07-02 | 2020-07-02 | 2020-10-14 | 2021-07-02 | Overhead | R16 | 2020-10-14 | 1 |  | 75 | 188 | 262 | 2020 | 2021 | R16
162335200637 | 162206200637 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-15 | 2020-06-15 | 2020-08-17 |  | 2021-02-17 | Underground | R16 | 2020-10-19 | 1 | 46 | 46 | 88 | 178 | 2020 | 2021 | R16
168681196179 | 165975196179 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-02 | 2020-07-02 | 2020-07-02 | 2020-09-15 | 2020-09-29 | Overhead | R16 | 2020-09-15 | 1 |  | 54 | 11 | 64 | 2020 | 2020 | R16
160505194921 | 163409194921 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-19 | 2020-06-22 | 2020-06-22 |  | 2021-07-19 | Overhead | R16 | 2020-11-10 | 2 |  | 102 | 180 | 282 | 2020 | 2021 | R16
169120194058 | 160221194058 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-02 | 2020-06-02 | 2020-06-12 | 2020-08-05 | 2020-08-07 | Underground | R16 | 2020-08-05 | 1 | 9 | 39 | 3 | 49 | 2020 | 2020 | R16
167136186583 | 160233186583 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-06 | 2020-04-06 | 2020-04-06 |  | 2020-07-01 | Overhead | R16 | 2020-04-27 | 1 |  | 16 | 48 | 63 | 2020 | 2020 | R16
160524176174 | 162014176174 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-01-08 | 2020-01-08 | 2020-01-08 | 2021-02-17 | 2021-05-07 | Overhead | R16 | 2021-02-17 | 1 |  | 291 | 58 | 348 | 2020 | 2021 | R16
168404186274 | 169488186274 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-01 | 2020-04-01 | 2020-04-03 |  | 2020-07-10 | Underground | R16 | 2020-05-27 | 1 | 3 | 39 | 33 | 73 | 2020 | 2020 | R16
169172174898 | 169182174898 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-18 | 2019-12-18 | 2019-12-20 | 2020-01-13 | 2020-01-16 | Overhead | R16 | 2020-01-13 | 1 | 3 | 17 | 4 | 22 | 2019 | 2020 | R16
165831195404 | 166953195404 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-13 | 2020-05-13 | 2020-06-25 | 2020-09-03 | 2020-09-15 | Underground | R16 | 2020-09-03 | 1 | 32 | 51 | 9 | 90 | 2020 | 2020 | R16
167382192158 | 168209192158 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-05-20 | 2020-05-26 | 2020-05-26 | 2020-06-08 | 2020-06-09 | Underground | R16 | 2020-06-08 | 5 |  | 10 | 2 | 15 | 2020 | 2020 | R16
168447189139 | 164143189139 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-28 | 2020-04-28 | 2020-04-28 | 2020-07-07 | 2020-07-08 | Overhead | R16 | 2020-07-07 | 1 |  | 51 | 2 | 52 | 2020 | 2020 | R16
164306191790 | 168392191790 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2020-05-21 | 2020-05-21 | 2020-05-21 |  | 2020-07-10 | Overhead | R16 | 2020-06-10 | 1 |  | 15 | 23 | 37 | 2020 | 2020 | R16
164178195628 | 164767195628 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2021-04-23 | 2021-04-29 | Overhead | R16 | 2021-04-23 | 1 |  | 215 | 5 | 219 | 2020 | 2021 | R16
161079193172 | 161232193172 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-02-20 | 2020-02-20 | 2020-06-05 |  | 2023-08-04 | Underground | R16 | 2023-07-18 | 1 | 77 | 813 | 14 | 902 | 2020 | 2023 | R16
161721193548 | 164265193548 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-04-28 | 2020-05-20 | 2020-06-08 |  | 2021-09-13 | Underground | R16 |  | 17 | 14 |  |  | 360 | 2020 | 2021 | R16
166529192160 | 168800192160 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-25 | 2020-05-25 | 2020-05-25 |  | 2020-07-09 | Underground | R16 | 2020-06-04 | 1 |  | 9 | 26 | 34 | 2020 | 2020 | R16
164831188595 | 169408188595 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-04-01 | 2020-04-01 | 2020-04-22 | 2020-08-14 | 2020-10-05 | Underground | R16 | 2020-08-14 | 1 | 16 | 83 | 37 | 134 | 2020 | 2020 | R16
160631212565 | 166139212565 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-06 | 2020-11-17 | 2020-12-02 |  | 2021-11-04 | Overhead | R16 |  | 97 | 12 |  |  | 349 | 2020 | 2021 | R16
162765197003 | 167382197003 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-12 | 2020-07-12 | 2020-07-13 | 2021-02-26 | 2021-03-01 | Overhead | R16 | 2021-02-26 | 0 | 1 | 165 | 2 | 166 | 2020 | 2021 | R16
169669225481 | 161769225481 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-06-11 | 2020-10-27 | 2021-03-31 | 2022-12-07 | 2022-10-28 | Underground | R16 | 2022-12-07 | 99 | 112 | 441 |  | 622 | 2020 | 2022 | R16
163026301735 | 168968301735 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-24 | 2022-11-04 | 2022-11-29 |  | 2023-03-17 | Underground | R16 |  | 10 | 18 |  |  | 105 | 2022 | 2023 | R16
160199189688 | 163306189688 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-22 | 2020-05-01 | 2020-05-01 |  | 2020-08-28 | Overhead | R16 | 2020-07-02 | 8 |  | 45 | 42 | 93 | 2020 | 2020 | R16
167554198696 | 168148198696 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-07-14 | 2020-07-14 | 2020-07-28 |  | 2021-11-08 | Overhead | R16 | 2021-05-24 | 1 | 11 | 215 | 121 | 345 | 2020 | 2021 | R16
160934185668 | 168872185668 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-30 | 2020-03-30 | 2020-03-30 | 2020-04-14 | 2020-08-20 | Overhead | R16 | 2020-04-14 | 1 |  | 12 | 93 | 104 | 2020 | 2020 | R16
168285202368 | 168197202368 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-21 | 2020-05-21 | 2020-08-31 | 2021-09-07 | 2021-09-08 | Underground | R16 | 2021-09-07 | 1 | 73 | 267 | 2 | 340 | 2020 | 2021 | R16
160609193619 | 164024193619 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-03-04 | 2020-03-04 | 2020-06-09 | 2020-11-05 | 2020-11-10 | Underground | R16 | 2020-11-05 | 1 | 70 | 108 | 4 | 180 | 2020 | 2020 | R16
163840260401 | 164352260401 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-06-25 | 2020-10-23 | 2021-12-08 |  | 2022-06-20 | Underground | R16 |  | 87 | 294 |  |  | 518 | 2020 | 2022 | R16
160293194844 | 163371194844 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-19 | 2020-06-19 | 2020-06-19 | 2020-07-07 | 2020-10-06 | Overhead | R16 | 2020-07-07 | 1 |  | 13 | 66 | 78 | 2020 | 2020 | R16
169400185985 | 169234185985 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-31 | 2020-03-31 | 2020-03-31 |  | 2020-07-07 | Overhead | R16 | 2020-05-06 | 1 |  | 27 | 45 | 71 | 2020 | 2020 | R16
163576209973 | 164996209973 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-22 | 2020-01-22 | 2020-11-09 |  | 2022-08-03 | Overhead | R16 |  | 1 | 209 |  |  | 661 | 2020 | 2022 | R16
161941189966 | 161942189966 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-04-15 | 2020-05-04 | 2020-05-04 |  | 2020-08-20 | Underground | R16 |  | 14 |  |  |  | 92 | 2020 | 2020 | R16
162363190440 | 166126190440 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-05-07 | 2020-05-07 | 2020-05-07 | 2020-05-18 | 2021-01-04 | Underground | R16 | 2020-05-18 | 1 |  | 8 | 166 | 173 | 2020 | 2021 | R16
161548262697 | 162084262697 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Residential Subdivision | 2020-06-13 | 2020-06-13 | 2021-12-28 | 2022-04-12 | 2022-05-02 | Underground | R16 | 2022-04-12 | 0 | 402 | 76 | 15 | 491 | 2020 | 2022 | R16
167163184648 | 166889184648 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-18 | 2020-03-18 | 2020-03-18 |  | 2020-06-23 | Overhead | R16 | 2020-04-16 | 1 |  | 22 | 49 | 70 | 2020 | 2020 | R16
169848191645 | 167387191645 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-03-20 | 2020-03-20 | 2020-05-20 | 2020-11-25 | 2021-04-07 | Overhead | R16 | 2020-11-25 | 1 | 44 | 136 | 96 | 274 | 2020 | 2021 | R16
162766189340 | 164304189340 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-04-28 | 2020-04-28 | 2020-04-28 |  | 2020-10-06 | Overhead | R16 | 2020-07-28 | 1 |  | 66 | 51 | 116 | 2020 | 2020 | R16
169059190627 | 166489190627 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-11 | 2020-05-11 | 2020-05-11 |  | 2022-10-20 | Overhead | R16 |  | 1 |  |  |  | 639 | 2020 | 2022 | R16
164808194372 | 162528194372 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-06-17 | 2020-06-17 | 2020-06-17 |  | 2021-10-28 | Overhead | R16 | 2021-07-30 | 1 |  | 293 | 65 | 357 | 2020 | 2021 | R16
167170184698 | 167112184698 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-31 | 2020-01-31 | 2020-03-19 |  | 2020-07-01 | Underground | R16 | 2020-04-28 | 1 | 35 | 29 | 47 | 109 | 2020 | 2020 | R16
168608202389 | 168929202389 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-02-10 | 2020-08-07 | 2020-09-01 | 2020-09-23 | 2020-11-10 | Overhead | R16 | 2020-09-23 | 130 | 18 | 17 | 35 | 197 | 2020 | 2020 | R16
168697193368 | 160574193368 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-04-07 | 2020-04-22 | 2020-06-05 |  | 2020-08-14 | Underground | R16 |  | 12 | 33 |  |  | 94 | 2020 | 2020 | R16
165235185373 | 163034185373 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-02-28 | 2020-02-28 | 2020-03-26 | 2020-10-21 | 2021-07-07 | Underground | R16 | 2020-10-21 | 1 | 20 | 150 | 186 | 354 | 2020 | 2021 | R16
160327181630 | 164752181630 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-01-20 | 2020-01-20 | 2020-02-24 |  | 2021-01-12 | Overhead | R16 |  | 1 | 26 |  |  | 257 | 2020 | 2021 | R16
164231189043 | 164520189043 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-17 | 2020-01-17 | 2020-04-24 |  | 2021-11-10 | Underground | R16 | 2020-05-12 | 1 | 71 | 13 | 392 | 474 | 2020 | 2021 | R16
167105181246 | 163253181246 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-01-14 | 2020-01-16 | 2020-02-20 |  | 2021-11-13 | Underground | R16 |  | 3 | 26 |  |  | 479 | 2020 | 2021 | R16
169278228630 | 165030228630 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-06-29 | 2021-04-19 | 2021-04-28 | 2022-09-19 | 2022-12-08 | Underground | R16 | 2022-09-19 | 211 | 8 | 364 | 59 | 639 | 2020 | 2022 | R16
167680180083 | 168857180083 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-10 | 2020-02-10 | 2020-02-11 |  | 2020-06-24 | Underground | R16 | 2020-06-04 | 1 | 2 | 83 | 15 | 98 | 2020 | 2020 | R16
162230193650 | 167844193650 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-05-19 | 2020-05-28 | 2020-06-08 |  | 2021-08-13 | Underground | R16 |  | 8 | 8 |  |  | 324 | 2020 | 2021 | R16
165942191768 | 168460191768 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-21 | 2020-05-21 | 2020-05-21 | 2021-04-19 | 2021-11-05 | Overhead | R16 | 2021-04-19 | 1 |  | 238 | 145 | 382 | 2020 | 2021 | R16
166262192164 | 166612192164 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-17 | 2020-03-17 | 2020-05-26 |  | 2020-12-14 | Underground | R16 | 2020-09-08 | 1 | 51 | 76 | 70 | 195 | 2020 | 2020 | R16
160653222725 | 169534222725 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2020-04-01 | 2020-04-01 | 2021-03-05 |  | 2021-11-08 | Underground | R16 | 2021-04-21 | 1 | 243 | 34 | 144 | 419 | 2020 | 2021 | R16
163032189392 | 163882189392 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-27 | 2020-04-29 | 2020-04-29 | 2020-05-19 | 2020-07-14 | Overhead | R16 | 2020-05-19 | 3 |  | 15 | 41 | 57 | 2020 | 2020 | R16
165941174923 | 169443174923 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-19 | 2019-12-19 | 2019-12-19 |  | 2021-08-23 | Overhead | R16 | 2021-07-12 | 1 |  | 408 | 31 | 438 | 2019 | 2021 | R16
164485176994 | 160141176994 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-27 | 2019-12-27 | 2020-01-14 | 2020-02-07 | 2020-02-10 | Underground | R16 | 2020-02-07 | 1 | 13 | 19 | 2 | 32 | 2019 | 2020 | R16
161687190615 | 160277190615 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-06 | 2020-04-07 | 2020-05-12 |  | 2021-11-10 | Overhead | R16 |  | 2 | 26 |  |  | 418 | 2020 | 2021 | R16
160941192197 | 160948192197 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-04-09 | 2020-04-09 | 2020-05-29 |  | 2021-07-26 | Underground | R16 | 2020-10-23 | 1 | 37 | 106 | 197 | 338 | 2020 | 2021 | R16
160232186426 | 160390186426 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-06 | 2020-04-06 | 2020-04-06 |  | 2020-07-07 | Overhead | R16 | 2020-05-13 | 1 |  | 28 | 40 | 67 | 2020 | 2020 | R16
165390192298 | 169076192298 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-27 | 2020-05-27 | 2020-05-27 |  | 2020-08-28 | Overhead | R16 | 2020-06-30 | 1 |  | 25 | 44 | 68 | 2020 | 2020 | R16
165742188704 | 165734188704 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-03-11 | 2020-03-11 | 2020-04-22 |  | 2021-07-19 | Underground | R16 | 2020-11-25 | 1 | 31 | 156 | 169 | 354 | 2020 | 2021 | R16
161059186070 | 169492186070 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-01 | 2020-04-01 | 2020-04-01 | 2020-04-03 | 2020-06-09 | Overhead | R16 | 2020-04-03 | 1 |  | 3 | 48 | 50 | 2020 | 2020 | R16
164087175036 | 169677175036 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-20 | 2019-12-23 | 2019-12-23 | 2020-01-08 | 2020-01-09 | Overhead | R16 | 2020-01-08 | 2 |  | 13 | 2 | 15 | 2019 | 2020 | R16
167108191730 | 168262191730 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-21 | 2020-05-21 | 2020-05-21 |  | 2020-08-28 | Overhead | R16 | 2020-06-30 | 1 |  | 29 | 44 | 72 | 2020 | 2020 | R16
165841194021 | 169287194021 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2020-05-28 | 2020-05-28 | 2020-06-10 |  | 2022-10-28 | Underground | R16 |  | 1 | 10 |  |  | 632 | 2020 | 2022 | R16
160493190026 | 162960190026 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-21 | 2020-04-21 | 2020-05-04 |  | 2020-08-28 | Underground | R16 | 2020-06-29 | 1 | 10 | 41 | 45 | 94 | 2020 | 2020 | R16
165314175842 | 161490175842 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-06 | 2020-01-06 | 2020-01-06 | 2020-01-08 | 2020-01-09 | Overhead | R16 | 2020-01-08 | 1 |  | 3 | 2 | 4 | 2020 | 2020 | R16
163400206129 | 161547206129 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-06 | 2020-01-06 | 2020-10-02 |  | 2021-01-20 | Underground | R16 | 2020-10-12 | 1 | 195 | 7 | 73 | 273 | 2020 | 2021 | R16
160545192489 | 169285192489 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-27 | 2020-05-28 | 2020-05-28 |  | 2021-04-16 | Overhead | R16 | 2020-03-16 | 2 |  |  | 285 | 233 | 2020 | 2021 | R16
168951187146 | 161197187146 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-10 | 2020-04-10 | 2020-04-10 | 2020-05-18 | 2020-05-19 | Overhead | R16 | 2020-05-18 | 1 |  | 27 | 2 | 28 | 2020 | 2020 | R16
166320190632 | 164078190632 | NON-RESIDENTIAL - LODGING | R16 RESD AND NON RESD US | Commercial | 2020-03-05 | 2020-03-05 | 2020-05-12 |  | 2020-11-04 | Underground | R16 |  | 1 | 49 |  |  | 175 | 2020 | 2020 | R16
162930189620 | 166805189620 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-17 | 2020-04-24 | 2020-04-30 | 2020-06-05 | 2020-06-08 | Underground | R16 | 2020-06-05 | 29 | 5 | 27 | 2 | 60 | 2020 | 2020 | R16
167660200799 | 163626200799 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2020-08-14 | 2020-08-14 | 2020-08-18 |  | 2021-04-20 | Underground | R16 |  | 1 | 3 |  |  | 178 | 2020 | 2021 | R16
163227189063 | 166813189063 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-03-17 | 2020-04-23 | 2020-04-27 |  | 2020-07-08 | Overhead | R16 |  | 28 | 3 |  |  | 82 | 2020 | 2020 | R16
168001183377 | 164475183377 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-03-06 | 2020-03-06 | 2020-03-09 |  | 2021-01-21 | Underground | R16 |  | 1 | 2 |  |  | 230 | 2020 | 2021 | R16
161185196057 | 165687196057 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-01 | 2020-07-01 | 2020-07-01 |  | 2020-10-06 | Overhead | R16 | 2020-08-10 | 1 |  | 29 | 42 | 70 | 2020 | 2020 | R16
160520187289 | 160522187289 | NON-RESIDENTIAL - SUBSEQUENT WORK | R16 ELEC DEVELOPMENT | Commercial | 2020-04-07 | 2020-04-11 | 2020-04-13 | 2020-12-15 | 2021-01-04 | Underground | R16 | 2020-12-15 | 4 | 1 | 177 | 15 | 195 | 2020 | 2021 | R16
166392179769 | 168669179769 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-07 | 2020-02-07 | 2020-02-07 | 2020-03-16 | 2020-07-14 | Overhead | R16 | 2020-03-16 | 1 |  | 27 | 87 | 113 | 2020 | 2020 | R16
165279174887 | 169441174887 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-19 | 2019-12-19 | 2019-12-19 |  | 2020-07-09 | Overhead | R16 | 2020-05-29 | 1 |  | 117 | 30 | 146 | 2019 | 2020 | R16
164046189358 | 162738189358 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE FOR UPGRADE UD | Commercial | 2020-04-20 | 2020-04-20 | 2020-04-30 | 2021-02-08 | 2022-06-21 | Underground | R16 | 2021-02-08 | 1 | 9 | 203 | 357 | 567 | 2020 | 2022 | R16
162283196279 | 165944196279 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-02 | 2020-07-02 | 2020-07-02 |  | 2020-12-15 | Underground | R16 | 2020-09-10 | 1 |  | 51 | 69 | 119 | 2020 | 2020 | R16
165767194343 | 167365194343 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-15 | 2020-05-15 | 2020-06-14 | 2020-07-07 | 2020-07-10 | Underground | R16 | 2020-07-07 | 1 | 21 | 17 | 4 | 41 | 2020 | 2020 | R16
168432183925 | 165903183925 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-12 | 2020-03-12 | 2020-03-12 | 2020-04-07 | 2020-06-23 | Overhead | R16 | 2020-04-07 | 1 |  | 19 | 56 | 74 | 2020 | 2020 | R16
162761184405 | 164580184405 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-06 | 2020-03-06 | 2020-03-17 |  | 2023-10-04 | Overhead | R16 |  | 1 | 8 |  |  | 934 | 2020 | 2023 | R16
165120191523 | 167680191523 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-18 | 2020-05-18 | 2020-05-18 |  | 2020-07-13 | Overhead | R16 | 2020-06-15 | 1 |  | 21 | 21 | 41 | 2020 | 2020 | R16
162109258598 | 169830258598 | NON-RESIDENTIAL - LODGING | UG R16 RESD AND NON RESD UD | Commercial | 2020-02-13 | 2020-04-27 | 2021-11-24 | 2023-06-30 | 2023-07-25 | Underground | R16 | 2023-06-30 | 53 | 413 | 418 | 18 | 899 | 2020 | 2023 | R16
162272179721 | 168498179721 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-02-06 | 2020-02-07 | 2020-02-07 | 2020-02-27 | 2020-02-28 | Overhead | R16 | 2020-02-27 | 2 |  | 15 | 2 | 17 | 2020 | 2020 | R16
161325195414 | 164817195414 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2020-07-27 | 2023-09-12 | Overhead | R16 | 2020-07-27 | 1 |  | 21 | 817 | 837 | 2020 | 2023 | R16
161312201868 | 161350201868 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-09 | 2020-06-09 | 2020-08-26 |  | 2021-07-02 | Underground | R16 | 2020-10-26 | 1 | 57 | 44 | 180 | 279 | 2020 | 2021 | R16
162504197317 | 166805197317 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-08 | 2020-07-08 | 2020-07-15 | 2020-07-31 | 2020-10-06 | Overhead | R16 | 2020-07-31 | 1 | 6 | 13 | 48 | 65 | 2020 | 2020 | R16
168137183756 | 169605183756 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-12 | 2020-02-12 | 2020-03-10 |  | 2020-10-06 | Underground | R16 | 2020-08-05 | 1 | 20 | 107 | 45 | 170 | 2020 | 2020 | R16
168150189963 | 165288189963 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-04 | 2020-05-04 | 2020-05-04 |  | 2020-08-28 | Overhead | R16 | 2020-07-02 | 1 |  | 44 | 42 | 85 | 2020 | 2020 | R16
160409252992 | 168836252992 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Residential | 2021-09-29 | 2021-09-29 | 2021-10-20 |  | 2022-01-20 | Overhead | R16 |  | 1 | 16 |  |  | 82 | 2021 | 2022 | R16
166711185430 | 167033185430 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-31 | 2020-01-31 | 2020-03-26 |  | 2022-10-20 | Underground | R16 |  | 1 | 40 |  |  | 710 | 2020 | 2022 | R16
163353177644 | 164725177644 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-21 | 2020-01-21 | 2020-01-21 | 2020-02-21 | 2020-02-28 | Overhead | R16 | 2020-02-21 | 1 |  | 24 | 6 | 29 | 2020 | 2020 | R16
165059243246 | 161698243246 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2020-06-11 | 2021-07-23 | 2021-08-12 | 2023-01-05 | 2023-01-05 | Underground | R16 | 2023-01-05 | 292 | 15 | 366 |  | 671 | 2020 | 2023 | R16
160031221617 | 162016221617 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-01-08 | 2021-01-08 | 2021-02-26 | 2021-06-17 | 2022-08-25 | Underground | R16 | 2021-06-17 | 263 | 36 | 80 | 311 | 687 | 2020 | 2022 | R16
168877187585 | 163833187585 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-16 | 2020-01-17 | 2020-04-14 | 2020-07-29 | 2020-09-09 | Underground | R16 | 2020-07-29 | 2 | 63 | 77 | 31 | 170 | 2020 | 2020 | R16
167216192060 | 167774192060 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-18 | 2020-05-22 | 2020-05-22 | 2020-11-23 | 2021-04-07 | Overhead | R16 | 2020-11-23 | 5 |  | 132 | 98 | 233 | 2020 | 2021 | R16
162347184470 | 166736184470 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-18 | 2020-03-18 | 2020-03-18 | 2020-06-04 | 2020-07-09 | Overhead | R16 | 2020-06-04 | 1 |  | 57 | 26 | 82 | 2020 | 2020 | R16
164054190502 | 167621190502 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-23 | 2020-03-23 | 2020-05-08 |  | 2020-10-06 | Underground | R16 | 2020-07-10 | 1 | 35 | 46 | 63 | 142 | 2020 | 2020 | R16
160282198925 | 160868198925 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-09 | 2020-04-09 | 2020-07-29 | 2020-10-14 | 2021-10-05 | Underground | R16 | 2020-10-14 | 1 | 80 | 56 | 255 | 389 | 2020 | 2021 | R16
166393180363 | 169665180363 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-12 | 2020-02-12 | 2020-02-12 | 2020-05-20 | 2020-09-01 | Overhead | R16 | 2020-05-20 | 1 |  | 71 | 75 | 145 | 2020 | 2020 | R16
169959183747 | 165174183747 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-10 | 2020-03-10 | 2020-03-10 | 2020-04-07 | 2020-07-02 | Overhead | R16 | 2020-04-07 | 1 |  | 21 | 63 | 83 | 2020 | 2020 | R16
161499179849 | 162639179849 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2020-01-10 | 2020-01-10 | 2020-02-11 |  | 2022-08-29 | Underground | R16 |  | 1 | 23 |  |  | 687 | 2020 | 2022 | R16
161563181219 | 161581181219 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-01-06 | 2020-01-06 | 2020-02-20 |  | 2020-12-29 | Underground | R16 | 2020-09-30 | 1 | 34 | 160 | 65 | 257 | 2020 | 2020 | R16
165091200701 | 164567200701 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-03-06 | 2020-07-23 | 2020-08-14 |  | 2021-10-25 | Underground | R16 |  | 100 | 17 |  |  | 427 | 2020 | 2021 | R16
169173178530 | 166465178530 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-29 | 2020-01-29 | 2020-01-29 |  | 2020-07-02 | Overhead | R16 | 2020-05-04 | 1 |  | 69 | 44 | 112 | 2020 | 2020 | R16
161786143253 | 163579143253 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-02-14 | 2019-02-14 | 2019-02-14 |  | 2021-11-13 | Overhead | R16 |  | 1 |  |  |  | 717 | 2019 | 2021 | R16
165888189396 | 164535189396 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-30 | 2020-04-30 | 2020-04-30 |  | 2021-04-15 | Overhead | R16 | 2020-12-18 | 1 |  | 167 | 85 | 251 | 2020 | 2021 | R16
169935198830 | 160241198830 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-06 | 2020-04-06 | 2020-07-29 |  | 2021-07-24 | Underground | R16 | 2020-11-17 | 1 | 83 | 80 | 179 | 340 | 2020 | 2021 | R16
168066189027 | 162088189027 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-24 | 2020-02-25 | 2020-04-24 | 2020-06-29 | 2020-07-01 | Underground | R16 | 2020-06-29 | 2 | 44 | 47 | 3 | 93 | 2020 | 2020 | R16
163766200203 | 166410200203 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-07 | 2020-07-07 | 2020-08-10 | 2021-01-13 | 2021-01-13 | Underground | R16 | 2021-01-13 | 1 | 25 | 113 |  | 137 | 2020 | 2021 | R16
163221154699 | 169440154699 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-05-16 | 2019-05-16 | 2019-06-07 |  | 2021-12-16 | Underground | R16 |  | 1 | 17 |  |  | 676 | 2019 | 2021 | R16
160578180152 | 169345180152 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-11 | 2020-02-11 | 2020-02-11 |  | 2020-07-01 | Overhead | R16 | 2020-04-30 | 1 |  | 58 | 45 | 102 | 2020 | 2020 | R16
167639186946 | 161001186946 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-09 | 2020-04-09 | 2020-04-09 | 2020-05-05 | 2020-05-06 | Overhead | R16 | 2020-05-05 | 1 |  | 19 | 2 | 20 | 2020 | 2020 | R16
165127176252 | 161945176252 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-08 | 2020-01-08 | 2020-01-08 | 2020-02-26 | 2020-02-27 | Overhead | R16 | 2020-02-26 | 1 |  | 36 | 2 | 37 | 2020 | 2020 | R16
163157188025 | 162430188025 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-17 | 2020-04-17 | 2020-04-17 |  | 2020-08-28 | Underground | R16 | 2020-07-02 | 1 |  | 55 | 42 | 96 | 2020 | 2020 | R16
166962180983 | 169810180983 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-13 | 2020-02-18 | 2020-02-18 |  | 2020-07-14 | Overhead | R16 | 2020-06-18 | 4 |  | 88 | 19 | 109 | 2020 | 2020 | R16
161841185050 | 163462185050 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-14 | 2020-01-14 | 2020-03-24 |  | 2020-07-09 | Overhead | R16 | 2020-05-29 | 1 | 51 | 49 | 30 | 128 | 2020 | 2020 | R16
166270204201 | 165926204201 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-05-07 | 2020-05-07 | 2020-09-17 |  | 2021-08-23 | Overhead | R16 | 2021-07-12 | 1 | 96 | 213 | 31 | 338 | 2020 | 2021 | R16
164067146745 | 169146146745 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-03-21 | 2019-03-21 | 2019-03-21 |  | 2020-12-15 | Underground | R16 | 2020-09-14 | 1 |  | 388 | 67 | 454 | 2019 | 2020 | R16
169193233126 | 160661233126 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-04-08 | 2020-04-16 | 2021-06-01 | 2022-09-27 | 2022-09-28 | Underground | R16 | 2022-09-27 | 7 | 294 | 346 | 2 | 646 | 2020 | 2022 | R16
169349178458 | 166303178458 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-28 | 2020-01-28 | 2020-01-28 | 2020-07-17 | 2020-08-07 | Overhead | R16 | 2020-07-17 | 1 |  | 124 | 16 | 139 | 2020 | 2020 | R16
164076145035 | 166705145035 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-03-06 | 2019-03-06 | 2019-03-06 |  | 2020-12-15 | Underground | R16 | 2020-09-14 | 1 |  | 399 | 67 | 465 | 2019 | 2020 | R16
164078146648 | 169068146648 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-03-20 | 2019-03-20 | 2019-03-20 |  | 2020-12-29 | Underground | R16 | 2020-09-30 | 1 |  | 401 | 65 | 465 | 2019 | 2020 | R16
162947185013 | 167836185013 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-24 | 2020-03-24 | 2020-03-24 | 2020-04-28 | 2020-07-01 | Overhead | R16 | 2020-04-28 | 1 |  | 26 | 47 | 72 | 2020 | 2020 | R16
164081151582 | 167417151582 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-05-06 | 2019-05-06 | 2019-05-06 |  | 2020-12-18 | Underground | R16 | 2020-09-17 | 1 |  | 359 | 67 | 425 | 2019 | 2020 | R16
164085151415 | 167503151415 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-05-06 | 2019-05-06 | 2019-05-06 |  | 2020-12-18 | Underground | R16 | 2020-09-17 | 1 |  | 359 | 67 | 425 | 2019 | 2020 | R16
168856187475 | 167146187475 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2020-03-19 | 2020-03-20 | 2020-04-15 |  | 2021-01-08 | Underground | R16 |  | 2 | 19 |  |  | 212 | 2020 | 2021 | R16
164088149174 | 163423149174 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-04-15 | 2019-04-15 | 2019-04-15 |  | 2020-12-15 | Underground | R16 | 2020-09-14 | 1 |  | 371 | 67 | 437 | 2019 | 2020 | R16
166906215368 | 163067215368 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-18 | 2020-06-18 | 2020-12-23 |  | 2021-11-02 | Overhead | R16 | 2021-06-15 | 1 | 135 | 125 | 101 | 359 | 2020 | 2021 | R16
165834174804 | 169186174804 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-18 | 2019-12-18 | 2019-12-18 |  | 2021-11-10 | Overhead | R16 | 2020-01-22 | 1 |  | 26 | 471 | 496 | 2019 | 2021 | R16
163059194180 | 164461194180 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-28 | 2020-04-29 | 2020-06-12 | 2020-07-20 | 2020-07-20 | Underground | R16 | 2020-07-20 | 2 | 33 | 27 |  | 60 | 2020 | 2020 | R16
167245179644 | 168445179644 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-06 | 2020-02-06 | 2020-02-06 | 2020-03-18 | 2020-03-19 | Overhead | R16 | 2020-03-18 | 1 |  | 30 | 2 | 31 | 2020 | 2020 | R16
161549184719 | 164637184719 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-06 | 2020-03-06 | 2020-03-19 | 2020-05-05 | 2020-05-05 | Overhead | R16 | 2020-05-05 | 1 | 10 | 34 |  | 43 | 2020 | 2020 | R16
169971184116 | 166583184116 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-17 | 2020-03-17 | 2020-03-17 | 2020-04-30 | 2020-05-01 | Overhead | R16 | 2020-04-30 | 1 |  | 33 | 2 | 34 | 2020 | 2020 | R16
160604196069 | 165513196069 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-30 | 2020-06-30 | 2020-06-30 | 2020-08-06 | 2021-11-10 | Overhead | R16 | 2020-08-06 | 1 |  | 28 | 330 | 357 | 2020 | 2021 | R16
166664185244 | 168129185244 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-05 | 2020-02-05 | 2020-03-24 | 2020-07-06 | 2020-07-07 | Underground | R16 | 2020-07-06 | 1 | 35 | 75 | 2 | 110 | 2020 | 2020 | R16
165325201174 | 160868201174 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-02-18 | 2020-05-12 | 2020-08-20 |  | 2021-01-07 | Overhead | R16 |  | 61 | 73 |  |  | 233 | 2020 | 2021 | R16
160630195245 | 162555195245 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-17 | 2020-06-17 | 2020-06-24 |  | 2022-06-28 | Underground | R16 |  | 1 | 6 |  |  | 530 | 2020 | 2022 | R16
169518185475 | 168610185475 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-27 | 2020-03-27 | 2020-03-27 | 2020-08-12 | 2020-10-06 | Overhead | R16 | 2020-08-12 | 1 |  | 99 | 40 | 138 | 2020 | 2020 | R16
163010190924 | 169263190924 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-11 | 2020-02-11 | 2020-05-13 | 2020-05-18 | 2021-07-11 | Overhead | R16 | 2020-05-18 | 1 | 67 | 4 | 300 | 369 | 2020 | 2021 | R16
164503191102 | 167240191102 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-14 | 2020-05-14 | 2020-05-14 |  | 2020-07-09 | Overhead | R16 | 2020-06-08 | 1 |  | 18 | 24 | 41 | 2020 | 2020 | R16
166250186490 | 166089186490 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Commercial | 2019-10-10 | 2019-10-12 | 2020-04-06 |  | 2021-07-09 | Underground | R16 |  | 2 | 126 |  |  | 457 | 2019 | 2021 | R16
167841205683 | 167776205683 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-02-04 | 2020-02-04 | 2020-09-29 |  | 2023-05-04 | Underground | R16 |  | 1 | 171 |  |  | 848 | 2020 | 2023 | R16
166250187242 | 166440187242 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Commercial | 2019-10-10 | 2019-10-12 | 2020-04-13 |  | 2021-09-09 | Underground | R16 |  | 2 | 131 |  |  | 501 | 2019 | 2021 | R16
166250187348 | 166441187348 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Commercial | 2019-10-10 | 2019-10-12 | 2020-04-13 |  | 2021-06-30 | Underground | R16 |  | 2 | 131 |  |  | 450 | 2019 | 2021 | R16
168770179523 | 168083179523 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-05 | 2020-02-05 | 2020-02-05 |  | 2020-06-09 | Overhead | R16 | 2020-03-13 | 1 |  | 28 | 63 | 90 | 2020 | 2020 | R16
161490190867 | 166839190867 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-13 | 2020-05-13 | 2020-05-13 | 2020-07-17 | 2020-07-20 | Overhead | R16 | 2020-07-17 | 1 |  | 48 | 2 | 49 | 2020 | 2020 | R16
163993184515 | 166818184515 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-03-18 | 2020-03-18 | 2020-03-18 |  | 2021-08-16 | Underground | R16 | 2021-03-19 | 1 |  | 263 | 107 | 369 | 2020 | 2021 | R16
167045207595 | 167609207595 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-18 | 2020-06-03 | 2020-10-20 | 2021-09-01 | 2021-10-25 | Overhead | R16 | 2021-09-01 | 13 | 100 | 227 | 39 | 376 | 2020 | 2021 | R16
166250197880 | 165934197880 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-03-12 | 2020-03-13 | 2020-07-20 |  | 2021-01-08 | Underground | R16 |  | 2 | 92 |  |  | 217 | 2020 | 2021 | R16
163236198923 | 164255198923 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-01-17 | 2020-02-05 | 2020-07-29 |  | 2021-01-20 | Underground | R16 |  | 14 | 126 |  |  | 264 | 2020 | 2021 | R16
166250198932 | 166007198932 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Commercial | 2020-03-13 | 2020-03-13 | 2020-07-30 |  | 2020-12-17 | Underground | R16 |  | 1 | 100 |  |  | 200 | 2020 | 2020 | R16
165540182835 | 164123182835 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-04 | 2020-03-04 | 2020-03-04 |  | 2020-06-16 | Overhead | R16 | 2020-04-13 | 1 |  | 29 | 47 | 75 | 2020 | 2020 | R16
167881177511 | 164970177511 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-21 | 2020-01-21 | 2020-01-21 |  | 2022-10-20 | Overhead | R16 |  | 1 |  |  |  | 718 | 2020 | 2022 | R16
162464182637 | 163421182637 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-03-02 | 2020-03-02 | 2020-03-02 |  | 2020-07-08 | Underground | R16 | 2020-04-17 | 1 |  | 35 | 59 | 93 | 2020 | 2020 | R16
169204228635 | 164899228635 | NON-RESIDENTIAL - WAREHOUSE | R16 RESD AND NON RESD US | Commercial | 2020-06-29 | 2021-04-19 | 2021-04-28 | 2022-09-19 | 2022-10-03 | Underground | R16 | 2022-09-19 | 211 | 8 | 364 | 11 | 591 | 2020 | 2022 | R16
165593190280 | 168320190280 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-02-05 | 2020-02-05 | 2020-05-06 |  | 2023-08-14 | Underground | R16 | 2023-08-04 | 1 | 66 | 848 | 7 | 919 | 2020 | 2023 | R16
167193188706 | 163190188706 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-22 | 2020-04-22 | 2020-04-22 | 2020-05-21 | 2020-05-21 | Overhead | R16 | 2020-05-21 | 1 |  | 22 |  | 22 | 2020 | 2020 | R16
166824160506 | 161798160506 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-07-25 | 2019-08-07 | 2019-08-07 |  | 2019-08-28 | Underground | R16 | 2019-08-20 | 10 |  | 10 | 7 | 25 | 2019 | 2019 | R16
167136194841 | 169108194841 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-02-11 | 2020-02-11 | 2020-06-19 |  | 2021-05-06 | Underground | R16 | 2021-02-22 | 1 | 94 | 177 | 54 | 323 | 2020 | 2021 | R16
166913174910 | 169399174910 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-19 | 2019-12-19 | 2019-12-19 |  | 2020-06-09 | Overhead | R16 | 2020-02-26 | 1 |  | 50 | 75 | 124 | 2019 | 2020 | R16
169988226811 | 165877226811 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential Subdivision | 2020-03-12 | 2020-03-12 | 2021-04-14 |  | 2021-11-09 | Underground | R16 |  | 1 | 285 |  |  | 434 | 2020 | 2021 | R16
163693194401 | 162200194401 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2020-06-15 | 2020-06-15 | 2020-06-15 |  | 2020-10-29 | Overhead | R16 | 2020-09-01 | 1 |  | 57 | 43 | 99 | 2020 | 2020 | R16
164673192629 | 169517192629 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-29 | 2020-05-29 | 2020-05-29 |  | 2020-08-28 | Overhead | R16 | 2020-07-07 | 1 |  | 28 | 39 | 66 | 2020 | 2020 | R16
161800185933 | 164804185933 | RESIDENTIAL - MOBILE HOME | R16 RESD AND NON RESD US | Residential | 2020-03-09 | 2020-03-09 | 2020-03-31 |  | 2020-07-01 | Underground | R16 |  | 1 | 17 |  |  | 83 | 2020 | 2020 | R16
166033194054 | 166954194054 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-13 | 2020-05-13 | 2020-06-12 | 2020-07-31 | 2020-08-04 | Underground | R16 | 2020-07-31 | 1 | 23 | 36 | 3 | 60 | 2020 | 2020 | R16
168616191966 | 169084191966 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-30 | 2020-03-30 | 2020-05-22 | 2020-05-22 | 2020-10-26 | Underground | R16 | 2020-05-22 | 1 | 40 |  | 112 | 151 | 2020 | 2020 | R16
168576151585 | 167557151585 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-05-07 | 2019-05-07 | 2019-05-07 |  | 2020-11-02 | Underground | R16 | 2020-09-04 | 1 |  | 349 | 42 | 390 | 2019 | 2020 | R16
168578151572 | 167743151572 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-05-07 | 2019-05-07 | 2019-05-07 |  | 2020-11-02 | Underground | R16 | 2020-09-04 | 1 |  | 349 | 42 | 390 | 2019 | 2020 | R16
168607149067 | 162847149067 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-04-10 | 2019-04-12 | 2019-04-12 |  | 2020-10-06 | Underground | R16 | 2020-08-07 | 3 |  | 346 | 43 | 390 | 2019 | 2020 | R16
168643151650 | 167717151650 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-05-07 | 2019-05-07 | 2019-05-07 |  | 2020-10-06 | Underground | R16 | 2020-08-14 | 1 |  | 334 | 38 | 371 | 2019 | 2020 | R16
163904175025 | 169498175025 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-20 | 2019-12-20 | 2019-12-20 | 2020-02-11 | 2020-12-15 | Overhead | R16 | 2020-02-11 | 1 |  | 38 | 221 | 258 | 2019 | 2020 | R16
164257186156 | 169743186156 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2020-04-02 | 2020-04-02 | 2020-04-02 | 2020-04-17 | 2020-05-04 | Overhead | R16 | 2020-04-17 | 1 |  | 12 | 12 | 23 | 2020 | 2020 | R16
167557192216 | 169261192216 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-27 | 2020-05-27 | 2020-05-27 | 2020-06-15 | 2020-06-17 | Overhead | R16 | 2020-06-15 | 1 |  | 14 | 3 | 16 | 2020 | 2020 | R16
168707151592 | 167704151592 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-05-07 | 2019-05-07 | 2019-05-07 |  | 2020-10-06 | Underground | R16 | 2020-07-10 | 1 |  | 309 | 63 | 371 | 2019 | 2020 | R16
168732147641 | 160717147641 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-03-29 | 2019-03-29 | 2019-03-29 |  | 2020-07-09 | Underground | R16 | 2020-06-05 | 1 |  | 311 | 25 | 335 | 2019 | 2020 | R16
168734147499 | 160730147499 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-03-29 | 2019-03-29 | 2019-03-29 |  | 2020-07-09 | Underground | R16 | 2020-06-05 | 1 |  | 311 | 25 | 335 | 2019 | 2020 | R16
169459191792 | 169787191792 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-04-02 | 2020-04-02 | 2020-05-21 |  | 2021-02-17 | Underground | R16 | 2020-10-16 | 1 | 36 | 107 | 89 | 230 | 2020 | 2021 | R16
161085190311 | 165988190311 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-07 | 2020-05-07 | 2020-05-07 |  | 2020-07-08 | Overhead | R16 | 2020-05-21 | 1 |  | 11 | 35 | 45 | 2020 | 2020 | R16
165981190975 | 167166190975 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-14 | 2020-05-14 | 2020-05-14 |  | 2020-07-14 | Overhead | R16 | 2020-06-17 | 1 |  | 25 | 20 | 44 | 2020 | 2020 | R16
169795204040 | 166410204040 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-05-11 | 2020-05-11 | 2020-09-15 |  | 2021-07-26 | Underground | R16 |  | 1 | 92 |  |  | 316 | 2020 | 2021 | R16
169054150953 | 168917150953 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-24 | 2019-01-24 | 2019-05-02 |  | 2020-07-13 | Underground | R16 |  | 1 | 71 |  |  | 383 | 2019 | 2020 | R16
169054150955 | 168950150955 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-24 | 2019-01-24 | 2019-05-02 |  | 2019-11-14 | Underground | R16 |  | 1 | 71 |  |  | 211 | 2019 | 2019 | R16
162842196333 | 165969196333 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-02 | 2020-07-02 | 2020-07-02 | 2020-08-11 | 2020-08-20 | Overhead | R16 | 2020-08-11 | 1 |  | 29 | 8 | 36 | 2020 | 2020 | R16
163606191822 | 168190191822 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-20 | 2020-05-20 | 2020-05-20 |  | 2020-08-28 | Overhead | R16 | 2020-06-29 | 1 |  | 29 | 45 | 73 | 2020 | 2020 | R16
169335177879 | 165617177879 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-24 | 2020-01-24 | 2020-01-24 |  | 2020-06-09 | Overhead | R16 | 2020-03-24 | 1 |  | 43 | 56 | 98 | 2020 | 2020 | R16
167729189450 | 163980189450 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-01-16 | 2020-01-17 | 2020-04-29 | 2020-10-21 | 2021-01-25 | Overhead | R16 | 2020-10-21 | 2 | 74 | 126 | 69 | 268 | 2020 | 2021 | R16
165037199608 | 166257199608 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-09 | 2020-05-09 | 2020-08-04 |  | 2020-12-18 | Underground | R16 | 2020-09-21 | 0 | 62 | 35 | 65 | 160 | 2020 | 2020 | R16
161396194800 | 166504194800 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential Subdivision | 2020-05-12 | 2020-05-12 | 2020-06-18 |  | 2021-10-25 | Underground | R16 |  | 1 | 28 |  |  | 380 | 2020 | 2021 | R16
161396194800 | 166504194800 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential Subdivision | 2020-05-12 | 2020-05-12 | 2020-06-18 |  | 2021-10-25 | Underground | R16 |  | 1 | 28 |  |  | 380 | 2020 | 2021 | R16
164882184473 | 166923184473 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-18 | 2020-03-18 | 2020-03-18 | 2020-07-20 | 2020-10-06 | Overhead | R16 | 2020-07-20 | 1 |  | 89 | 57 | 145 | 2020 | 2020 | R16
167645186949 | 160985186949 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-09 | 2020-04-09 | 2020-04-09 |  | 2020-07-09 | Overhead | R16 | 2020-06-04 | 1 |  | 41 | 26 | 66 | 2020 | 2020 | R16
163802191506 | 166126191506 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2020-01-28 | 2020-05-14 | 2020-05-19 |  | 2021-04-14 | Overhead | R16 |  | 78 | 4 |  |  | 317 | 2020 | 2021 | R16
163083193613 | 167248193613 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-03-19 | 2020-05-28 | 2020-06-09 | 2021-09-17 | 2021-11-01 | Underground | R16 | 2021-09-17 | 51 | 9 | 334 | 32 | 423 | 2020 | 2021 | R16
164788196476 | 164980196476 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-01 | 2020-05-01 | 2020-07-08 |  | 2020-10-06 | Underground | R16 | 2020-07-29 | 1 | 49 | 16 | 50 | 113 | 2020 | 2020 | R16
163532176055 | 161348176055 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-06 | 2020-01-08 | 2020-01-08 | 2020-01-22 | 2021-11-10 | Overhead | R16 | 2020-01-22 | 3 |  | 11 | 471 | 483 | 2020 | 2021 | R16
161842184851 | 161291184851 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-20 | 2020-03-20 | 2020-03-20 |  | 2020-07-08 | Overhead | R16 | 2020-05-21 | 22 |  | 45 | 35 | 100 | 2020 | 2020 | R16
164287190117 | 160342190117 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-04-06 | 2020-04-06 | 2020-05-06 | 2021-08-30 | 2023-09-19 | Overhead | R16 | 2021-08-30 | 1 | 23 | 344 | 537 | 902 | 2020 | 2023 | R16
160975139752 | 164874139752 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-01-03 | 2019-01-03 | 2019-01-10 |  | 2019-01-31 | Overhead | R16 |  | 1 | 6 |  |  | 21 | 2019 | 2019 | R16
163085222138 | 162893222138 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-02-27 | 2020-02-27 | 2021-03-02 |  | 2021-11-09 | Overhead | R16 |  | 1 | 264 |  |  | 444 | 2020 | 2021 | R16
169975184440 | 166614184440 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-17 | 2020-03-17 | 2020-03-17 | 2020-03-26 | 2020-06-29 | Overhead | R16 | 2020-03-26 | 1 |  | 8 | 68 | 75 | 2020 | 2020 | R16
169704287084 | 160800287084 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-04-08 | 2020-05-08 | 2022-07-26 |  | 2023-09-06 | Underground | R16 |  | 23 | 578 |  |  | 891 | 2020 | 2023 | R16
164907192593 | 164846192593 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-03-09 | 2020-04-23 | 2020-05-29 | 2020-06-26 | 2020-11-06 | Overhead | R16 | 2020-06-26 | 34 | 27 | 21 | 96 | 175 | 2020 | 2020 | R16
165229182372 | 163264182372 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-02-29 | 2020-02-29 | 2020-02-29 | 2020-03-10 | 2020-06-09 | Overhead | R16 | 2020-03-10 | 0 |  | 7 | 66 | 72 | 2020 | 2020 | R16
161577141221 | 165768141221 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-08 | 2019-01-08 | 2019-01-24 |  | 2019-04-08 | Underground | R16 | 2019-03-05 | 1 | 13 | 29 | 25 | 65 | 2019 | 2019 | R16
163498182773 | 163499182773 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-03-03 | 2020-03-03 | 2020-03-03 |  | 2020-06-09 | Overhead | R16 | 2020-03-04 | 1 |  | 2 | 70 | 71 | 2020 | 2020 | R16
160428218900 | 163861218900 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-03-03 | 2020-03-03 | 2021-01-28 | 2022-11-22 | 2022-12-01 | Underground | R16 | 2022-11-22 | 1 | 238 | 474 | 8 | 718 | 2020 | 2022 | R16
169465181903 | 161653181903 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-02-21 | 2020-02-25 | 2020-02-25 |  | 2020-12-15 | Overhead | R16 | 2020-09-14 | 3 |  | 145 | 67 | 213 | 2020 | 2020 | R16
165703185493 | 165615185493 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-01-24 | 2020-01-24 | 2020-03-27 | 2021-07-16 | 2021-10-25 | Underground | R16 | 2021-07-16 | 1 | 46 | 341 | 72 | 457 | 2020 | 2021 | R16
163405196751 | 166813196751 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-09 | 2020-07-09 | 2020-07-09 |  | 2020-10-06 | Overhead | R16 | 2020-08-10 | 1 |  | 23 | 42 | 64 | 2020 | 2020 | R16
163884174693 | 169256174693 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-19 | 2019-12-19 | 2019-12-19 |  | 2020-06-09 | Overhead | R16 | 2020-03-05 | 1 |  | 56 | 69 | 124 | 2019 | 2020 | R16
165068187809 | 165913187809 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-01-27 | 2020-01-27 | 2020-04-16 |  | 2023-01-10 | Underground | R16 | 2022-10-31 | 1 | 59 | 663 | 52 | 772 | 2020 | 2023 | R16
164574177025 | 163523177025 | AGRICULTURAL | R16 RESD AND NON RESD US | Residential Subdivision | 2020-01-15 | 2020-01-15 | 2020-01-15 |  | 2021-11-09 | Underground | R16 |  | 1 |  |  |  | 475 | 2020 | 2021 | R16
166500179508 | 168171179508 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-05 | 2020-02-05 | 2020-02-05 | 2020-04-17 | 2021-06-30 | Overhead | R16 | 2020-04-17 | 1 |  | 53 | 314 | 366 | 2020 | 2021 | R16
169763248859 | 169844248859 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-02-13 | 2020-02-13 | 2021-09-22 | 2022-01-30 | 2022-02-02 | Underground | R16 | 2022-01-30 | 1 | 420 | 93 | 3 | 515 | 2020 | 2022 | R16
164962178576 | 166568178576 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-29 | 2020-01-29 | 2020-01-29 | 2020-03-12 | 2020-03-16 | Overhead | R16 | 2020-03-12 | 1 |  | 32 | 3 | 34 | 2020 | 2020 | R16
160586203317 | 160723203317 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-05 | 2020-06-05 | 2020-09-10 |  | 2021-11-08 | Underground | R16 | 2021-05-14 | 1 | 70 | 177 | 127 | 372 | 2020 | 2021 | R16
162914180821 | 160538180821 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-14 | 2020-02-14 | 2020-02-14 |  | 2023-06-08 | Overhead | R16 |  | 1 |  |  |  | 865 | 2020 | 2023 | R16
160497179920 | 167476179920 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-03 | 2020-02-03 | 2020-02-09 |  | 2021-10-25 | Underground | R16 | 2021-10-25 | 1 | 5 | 446 |  | 451 | 2020 | 2021 | R16
161360195704 | 164918195704 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-29 | 2020-06-29 | 2020-06-29 |  | 2020-10-06 | Underground | R16 | 2020-08-04 | 1 |  | 27 | 46 | 72 | 2020 | 2020 | R16
168080194441 | 168156194441 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-20 | 2020-05-20 | 2020-06-15 |  | 2020-10-06 | Underground | R16 | 2020-08-17 | 1 | 19 | 46 | 37 | 100 | 2020 | 2020 | R16
169746187800 | 162087187800 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-16 | 2020-04-16 | 2020-04-16 | 2020-04-22 | 2020-07-08 | Overhead | R16 | 2020-04-22 | 1 |  | 5 | 56 | 60 | 2020 | 2020 | R16
160914186975 | 161017186975 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-04-10 | 2020-04-10 | 2020-04-10 |  | 2021-12-06 | Overhead | R16 | 2020-05-08 | 1 |  | 21 | 412 | 432 | 2020 | 2021 | R16
164418174716 | 169171174716 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-12-17 | 2019-12-17 | 2019-12-17 |  | 2020-06-09 | Overhead | R16 | 2020-03-04 | 1 |  | 57 | 70 | 126 | 2019 | 2020 | R16
169288187645 | 169685187645 | CUSTOMER UPGRADE IN SERVICE | UG SVC CONVERSION | Commercial | 2020-02-12 | 2020-03-02 | 2020-04-15 | 2020-07-31 | 2022-05-02 | Underground | R16 | 2020-07-31 | 14 | 33 | 78 | 457 | 579 | 2020 | 2022 | R16
163784197438 | 166646197438 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-08 | 2020-07-08 | 2020-07-16 | 2020-08-12 | 2020-10-06 | Underground | R16 | 2020-08-12 | 1 | 7 | 20 | 40 | 65 | 2020 | 2020 | R16
164950200563 | 167759200563 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-13 | 2020-08-11 | 2020-08-13 | 2020-08-28 | 2020-12-15 | Overhead | R16 | 2020-08-28 | 22 | 3 | 12 | 78 | 112 | 2020 | 2020 | R16
164487190446 | 166324190446 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-09 | 2020-05-09 | 2020-05-09 |  | 2020-07-13 | Overhead | R16 | 2020-06-15 | 0 |  | 26 | 21 | 46 | 2020 | 2020 | R16
162308181851 | 162249181851 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-25 | 2020-02-25 | 2020-02-25 | 2020-06-04 | 2020-06-19 | Overhead | R16 | 2020-06-04 | 1 |  | 73 | 12 | 84 | 2020 | 2020 | R16
163454177132 | 164180177132 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-17 | 2020-01-17 | 2020-01-17 | 2020-02-04 | 2020-02-05 | Overhead | R16 | 2020-02-04 | 1 |  | 13 | 2 | 14 | 2020 | 2020 | R16
169952184115 | 166601184115 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-03-17 | 2020-03-17 | 2020-03-17 | 2020-08-27 | 2020-10-29 | Overhead | R16 | 2020-08-27 | 1 |  | 118 | 46 | 163 | 2020 | 2020 | R16
166536176883 | 163175176883 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-01-14 | 2020-01-14 | 2020-01-14 | 2020-02-27 | 2020-02-28 | Overhead | R16 | 2020-02-27 | 1 |  | 33 | 2 | 34 | 2020 | 2020 | R16
165226178297 | 165965178297 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-27 | 2020-01-27 | 2020-01-27 |  | 2020-06-09 | Underground | R16 | 2020-02-19 | 1 |  | 18 | 80 | 97 | 2020 | 2020 | R16
167418199202 | 167433199202 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-15 | 2020-05-15 | 2020-07-31 | 2020-08-26 | 2020-08-28 | Underground | R16 | 2020-08-26 | 1 | 56 | 19 | 3 | 76 | 2020 | 2020 | R16
164119197402 | 168167197402 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-15 | 2020-07-15 | 2020-07-15 |  | 2020-10-06 | Underground | R16 | 2020-08-05 | 1 |  | 16 | 45 | 60 | 2020 | 2020 | R16
161492196776 | 166826196776 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-09 | 2020-07-09 | 2020-07-09 | 2020-08-27 | 2020-11-02 | Overhead | R16 | 2020-08-27 | 1 |  | 36 | 48 | 83 | 2020 | 2020 | R16
163855177729 | 165136177729 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-22 | 2020-01-22 | 2020-01-22 |  | 2020-06-09 | Overhead | R16 | 2020-03-26 | 1 |  | 47 | 54 | 100 | 2020 | 2020 | R16
162913194676 | 163219194676 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-19 | 2020-06-19 | 2020-06-19 | 2020-12-31 | 2021-04-20 | Underground | R16 | 2020-12-31 | 1 |  | 140 | 79 | 218 | 2020 | 2021 | R16
164343276653 | 167262276653 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2020-05-14 | 2021-11-03 | 2022-04-21 | 2022-07-12 | 2022-08-18 | Underground | R16 | 2022-07-12 | 385 | 122 | 59 | 28 | 591 | 2020 | 2022 | R16
161274217053 | 163503217053 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-04-23 | 2020-07-26 | 2021-01-13 |  | 2022-06-22 | Underground | R16 |  | 67 | 123 |  |  | 565 | 2020 | 2022 | R16
169088190668 | 166570190668 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-11 | 2020-05-11 | 2020-05-11 | 2020-07-13 | 2020-10-06 | Overhead | R16 | 2020-07-13 | 1 |  | 46 | 62 | 107 | 2020 | 2020 | R16
168267181742 | 169202181742 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-11 | 2020-02-11 | 2020-02-24 |  | 2020-06-09 | Underground | R16 | 2020-03-26 | 1 | 10 | 24 | 54 | 86 | 2020 | 2020 | R16
160968199435 | 162809199435 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-18 | 2020-06-19 | 2020-08-03 | 2020-09-22 | 2020-09-25 | Underground | R16 | 2020-09-22 | 2 | 32 | 37 | 4 | 72 | 2020 | 2020 | R16
161395196831 | 166914196831 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-09 | 2020-07-09 | 2020-07-09 | 2020-08-06 | 2020-10-06 | Overhead | R16 | 2020-08-06 | 1 |  | 21 | 44 | 64 | 2020 | 2020 | R16
169515187359 | 161737187359 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-01-07 | 2020-01-07 | 2020-04-14 | 2020-09-23 | 2020-12-29 | Underground | R16 | 2020-09-23 | 1 | 71 | 117 | 70 | 256 | 2020 | 2020 | R16
160346185004 | 160507185004 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-31 | 2019-12-31 | 2020-03-23 |  | 2021-04-15 | Underground | R16 | 2020-12-18 | 1 | 60 | 195 | 85 | 338 | 2019 | 2021 | R16
164942200179 | 166323200179 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-09 | 2020-05-09 | 2020-08-11 |  | 2021-01-08 | Underground | R16 | 2020-10-05 | 0 | 67 | 40 | 70 | 175 | 2020 | 2021 | R16
169950201673 | 168450201673 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-03-26 | 2020-03-26 | 2020-08-25 | 2021-03-12 | 2021-08-11 | Underground | R16 | 2021-03-12 | 1 | 109 | 144 | 109 | 360 | 2020 | 2021 | R16
163227189064 | 166814189064 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-03-17 | 2020-04-23 | 2020-04-27 |  | 2020-07-08 | Overhead | R16 |  | 28 | 3 |  |  | 82 | 2020 | 2020 | R16
168510194612 | 162806194612 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-06-17 | 2020-06-17 | 2020-06-18 |  | 2020-10-06 | Overhead | R16 |  | 1 | 2 |  |  | 80 | 2020 | 2020 | R16
162346177524 | 164797177524 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-21 | 2020-01-21 | 2020-01-21 | 2020-01-28 | 2020-06-09 | Overhead | R16 | 2020-01-28 | 1 |  | 6 | 96 | 101 | 2020 | 2020 | R16
162752184211 | 164150184211 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-01-16 | 2020-01-16 | 2020-03-16 |  | 2021-07-26 | Underground | R16 | 2020-11-13 | 1 | 43 | 175 | 182 | 398 | 2020 | 2021 | R16
168029190186 | 164263190186 | MOBILE HOMES PARK AB622 | ELEC SVC FOR MOBILE HOMES | Residential | 2020-04-28 | 2020-04-28 | 2020-05-06 |  | 2022-04-07 | Underground | R16 |  | 1 | 7 |  |  | 508 | 2020 | 2022 | R16
162975184152 | 167822184152 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-04 | 2020-02-04 | 2020-03-17 | 2020-06-16 | 2020-06-17 | Overhead | R16 | 2020-06-16 | 1 | 31 | 66 | 2 | 97 | 2020 | 2020 | R16
163904189634 | 165163189634 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-01 | 2020-05-01 | 2020-05-01 |  | 2020-07-09 | Overhead | R16 | 2020-05-28 | 1 |  | 20 | 31 | 50 | 2020 | 2020 | R16
168961218390 | 169683218390 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-05-29 | 2020-06-09 | 2021-01-25 |  | 2021-08-26 | Underground | R16 |  | 8 | 165 |  |  | 325 | 2020 | 2021 | R16
163445197695 | 166771197695 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-08 | 2020-07-17 | 2020-07-17 | 2020-08-13 | 2020-11-02 | Overhead | R16 | 2020-08-13 | 8 |  | 20 | 58 | 84 | 2020 | 2020 | R16
163424202309 | 163900202309 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-16 | 2020-09-01 | 2020-09-01 |  | 2020-12-29 | Overhead | R16 | 2020-09-30 | 164 |  | 22 | 65 | 249 | 2020 | 2020 | R16
164346185426 | 166420185426 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-16 | 2020-03-19 | 2020-03-26 | 2020-04-02 | 2020-05-13 | Underground | R16 | 2020-04-02 | 4 | 6 | 6 | 30 | 43 | 2020 | 2020 | R16
163094214336 | 163135214336 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-01-13 | 2020-01-13 | 2020-12-18 | 2021-07-28 | 2021-08-25 | Underground | R16 | 2021-07-28 | 1 | 245 | 159 | 21 | 423 | 2020 | 2021 | R16
169905193278 | 160851193278 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-08 | 2020-04-10 | 2020-06-05 | 2020-09-14 | 2020-09-15 | Underground | R16 | 2020-09-14 | 3 | 41 | 72 | 2 | 115 | 2020 | 2020 | R16
161045190266 | 165818190266 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-06 | 2020-05-06 | 2020-05-06 |  | 2020-07-09 | Overhead | R16 | 2020-05-28 | 1 |  | 17 | 31 | 47 | 2020 | 2020 | R16
168028185784 | 168480185784 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-03-26 | 2020-03-26 | 2020-03-30 |  | 2020-10-06 | Overhead | R16 | 2020-08-03 | 1 | 3 | 91 | 47 | 139 | 2020 | 2020 | R16
169878188770 | 163148188770 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH CP R16 WORK RELO TO UG | Commercial | 2020-01-13 | 2020-01-24 | 2020-04-22 | 2020-08-20 | 2020-12-23 | Overhead | R16 | 2020-08-20 | 10 | 64 | 87 | 90 | 248 | 2020 | 2020 | R16
162287197182 | 167458197182 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-13 | 2020-07-13 | 2020-07-13 | 2021-08-09 | 2021-10-25 | Overhead | R16 | 2021-08-09 | 1 |  | 281 | 56 | 336 | 2020 | 2021 | R16
168016224721 | 160516224721 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-12-30 | 2021-03-24 | 2021-03-24 | 2022-02-09 | 2022-03-29 | Underground | R16 | 2022-02-09 | 323 |  | 231 | 35 | 587 | 2019 | 2022 | R16
169862188247 | 161388188247 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-21 | 2020-02-21 | 2020-04-20 |  | 2020-07-01 | Underground | R16 | 2020-04-27 | 1 | 42 | 6 | 48 | 94 | 2020 | 2020 | R16
164944197720 | 165508197720 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-06-30 | 2020-06-30 | 2020-07-17 |  | 2021-07-12 | Underground | R16 | 2020-11-25 | 1 | 14 | 94 | 164 | 270 | 2020 | 2021 | R16
166519191433 | 167540191433 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-17 | 2020-05-19 | 2020-05-19 |  | 2020-10-06 | Overhead | R16 | 2020-07-14 | 2 |  | 41 | 61 | 102 | 2020 | 2020 | R16
160810250220 | 164323250220 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Commercial | 2020-01-17 | 2020-01-25 | 2021-09-30 |  | 2023-01-05 | Overhead | R16 |  | 6 | 439 |  |  | 775 | 2020 | 2023 | R16
167978195401 | 163528195401 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-06-22 | 2020-06-22 | 2020-06-25 | 2020-07-20 | 2020-07-21 | Overhead | R16 | 2020-07-20 | 1 | 4 | 18 | 2 | 22 | 2020 | 2020 | R16
167674193207 | 160656193207 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-05 | 2020-06-05 | 2020-06-05 | 2020-06-10 | 2020-10-06 | Overhead | R16 | 2020-06-10 | 1 |  | 4 | 85 | 88 | 2020 | 2020 | R16
160000197768 | 161261197768 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-06-09 | 2020-06-09 | 2020-07-20 | 2020-07-28 | 2020-07-28 | Overhead | R16 | 2020-07-28 | 1 | 30 | 7 |  | 36 | 2020 | 2020 | R16
160877176871 | 161795176871 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-07 | 2020-01-14 | 2020-01-14 | 2020-02-17 | 2020-02-19 | Underground | R16 | 2020-02-17 | 6 |  | 25 | 3 | 32 | 2020 | 2020 | R16
163249198907 | 163975198907 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-23 | 2020-06-24 | 2020-07-29 | 2020-09-09 | 2020-09-15 | Underground | R16 | 2020-09-09 | 2 | 26 | 31 | 5 | 61 | 2020 | 2020 | R16
161617192020 | 168672192020 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-22 | 2020-05-22 | 2020-05-22 | 2020-09-15 | 2020-09-16 | Overhead | R16 | 2020-09-15 | 1 |  | 83 | 2 | 84 | 2020 | 2020 | R16
163840181142 | 161003181142 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-19 | 2020-02-19 | 2020-02-19 |  | 2020-07-01 | Overhead | R16 | 2020-04-29 | 1 |  | 51 | 46 | 96 | 2020 | 2020 | R16
165431184534 | 166835184534 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-18 | 2020-03-18 | 2020-03-18 |  | 2020-07-01 | Overhead | R16 | 2020-04-29 | 1 |  | 31 | 46 | 76 | 2020 | 2020 | R16
161116196681 | 166510196681 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-07 | 2020-07-07 | 2020-07-07 | 2020-08-05 | 2021-07-01 | Overhead | R16 | 2020-08-05 | 1 |  | 22 | 237 | 258 | 2020 | 2021 | R16
163439191670 | 167776191670 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-19 | 2020-05-19 | 2020-05-20 |  | 2020-07-10 | Overhead | R16 | 2020-06-02 | 1 | 2 | 10 | 29 | 39 | 2020 | 2020 | R16
163720184807 | 167177184807 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-20 | 2020-03-20 | 2020-03-20 | 2020-05-11 | 2020-05-12 | Overhead | R16 | 2020-05-11 | 1 |  | 37 | 2 | 38 | 2020 | 2020 | R16
160566194778 | 163621194778 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-22 | 2020-06-22 | 2020-06-22 |  | 2020-10-06 | Overhead | R16 | 2020-07-10 | 1 |  | 15 | 63 | 77 | 2020 | 2020 | R16
168763193173 | 165895193173 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-05-07 | 2020-05-07 | 2020-06-05 |  | 2021-11-10 | Underground | R16 | 2020-12-31 | 1 | 22 | 150 | 225 | 395 | 2020 | 2021 | R16
165257197762 | 161696197762 | NON-RESIDENTIAL - WAREHOUSE | UG R16 RESD AND NON RESD UD | Commercial | 2020-01-07 | 2020-04-22 | 2020-07-17 | 2020-12-11 | 2021-01-13 | Underground | R16 | 2020-12-11 | 77 | 63 | 106 | 24 | 267 | 2020 | 2021 | R16
163298175377 | 160333175377 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-31 | 2019-12-31 | 2019-12-31 |  | 2020-06-09 | Overhead | R16 | 2020-02-07 | 1 |  | 29 | 88 | 116 | 2019 | 2020 | R16
163922191600 | 167842191600 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-19 | 2020-05-19 | 2020-05-19 |  | 2022-04-05 | Overhead | R16 | 2022-01-06 | 1 |  | 428 | 64 | 491 | 2020 | 2022 | R16
165624228856 | 167334228856 | NON-RESIDENTIAL - SUBSEQUENT WORK | R16 ELEC DEVELOPMENT | Commercial | 2020-03-20 | 2021-03-30 | 2021-04-30 | 2022-06-14 | 2022-06-14 | Underground | R16 | 2022-06-14 | 268 | 24 | 293 |  | 583 | 2020 | 2022 | R16
168675186881 | 160750186881 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-08 | 2020-04-08 | 2020-04-08 | 2020-08-18 | 2020-10-06 | Overhead | R16 | 2020-08-18 | 1 |  | 95 | 36 | 130 | 2020 | 2020 | R16
161348185600 | 165885185600 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-12 | 2020-03-12 | 2020-03-26 |  | 2020-07-08 | Overhead | R16 | 2020-04-16 | 1 | 11 | 16 | 60 | 85 | 2020 | 2020 | R16
167718194467 | 162229194467 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2020-06-15 | 2020-06-15 | 2020-06-15 |  | 2022-08-01 | Underground | R16 |  | 1 |  |  |  | 556 | 2020 | 2022 | R16
165261179550 | 168367179550 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-06 | 2020-02-06 | 2020-02-06 |  | 2021-06-30 | Overhead | R16 | 2020-04-20 | 1 |  | 53 | 313 | 365 | 2020 | 2021 | R16
165335180253 | 166200180253 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-01-28 | 2020-01-28 | 2020-02-13 |  | 2022-10-21 | Underground | R16 | 2022-08-24 | 1 | 13 | 660 | 43 | 714 | 2020 | 2022 | R16
169869183796 | 165832183796 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-12 | 2020-03-12 | 2020-03-12 | 2020-03-13 | 2020-04-29 | Overhead | R16 | 2020-03-13 | 1 |  | 2 | 34 | 35 | 2020 | 2020 | R16
164704187467 | 161607187467 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-14 | 2020-04-14 | 2020-04-14 |  | 2021-11-10 | Overhead | R16 | 2020-05-11 | 1 |  | 20 | 393 | 412 | 2020 | 2021 | R16
165179189464 | 166770189464 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-17 | 2020-03-17 | 2020-04-29 | 2020-10-02 | 2022-08-03 | Underground | R16 | 2020-10-02 | 1 | 32 | 113 | 479 | 622 | 2020 | 2022 | R16
163199197203 | 166891197203 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-09 | 2020-07-13 | 2020-07-13 |  | 2020-12-29 | Overhead | R16 | 2020-09-30 | 3 |  | 58 | 65 | 124 | 2020 | 2020 | R16
160011190102 | 165881190102 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-03-12 | 2020-03-12 | 2020-05-05 |  | 2021-11-11 | Underground | R16 | 2020-12-31 | 1 | 39 | 173 | 226 | 436 | 2020 | 2021 | R16
164589174752 | 169200174752 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-12-18 | 2019-12-18 | 2019-12-19 | 2022-03-23 | 2021-05-06 | Underground | R16 | 2022-03-23 | 1 | 2 | 590 |  | 362 | 2019 | 2021 | R16
169958186020 | 168440186020 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-26 | 2020-03-27 | 2020-03-31 |  | 2020-06-09 | Underground | R16 |  | 2 | 3 |  |  | 54 | 2020 | 2020 | R16
169931182783 | 163565182783 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-03 | 2020-03-03 | 2020-03-03 |  | 2020-06-09 | Overhead | R16 | 2020-04-01 | 1 |  | 22 | 50 | 71 | 2020 | 2020 | R16
163937186687 | 168233186687 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-03-25 | 2020-03-25 | 2020-04-07 | 2021-11-16 | 2021-12-28 | Underground | R16 | 2021-11-16 | 1 | 10 | 421 | 31 | 460 | 2020 | 2021 | R16
167846185471 | 168368185471 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-26 | 2020-03-27 | 2020-03-27 | 2020-04-24 | 2020-07-08 | Overhead | R16 | 2020-04-24 | 2 |  | 21 | 54 | 75 | 2020 | 2020 | R16
163121178916 | 167105178916 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-01 | 2020-02-01 | 2020-02-01 |  | 2020-06-09 | Overhead | R16 | 2020-03-10 | 0 |  | 27 | 66 | 92 | 2020 | 2020 | R16
167111186851 | 160684186851 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-08 | 2020-04-08 | 2020-04-09 |  | 2020-06-23 | Overhead | R16 | 2020-04-16 | 1 | 2 | 6 | 49 | 55 | 2020 | 2020 | R16
162076184531 | 166870184531 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-18 | 2020-03-18 | 2020-03-18 |  | 2020-06-29 | Overhead | R16 | 2020-04-23 | 1 |  | 27 | 48 | 74 | 2020 | 2020 | R16
160803194743 | 162975194743 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-17 | 2020-06-18 | 2020-06-18 |  | 2020-11-06 | Overhead | R16 | 2020-09-10 | 2 |  | 61 | 42 | 103 | 2020 | 2020 | R16
166640196918 | 167120196918 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-10 | 2020-07-10 | 2020-07-10 | 2020-07-23 | 2020-07-24 | Overhead | R16 | 2020-07-23 | 1 |  | 10 | 2 | 11 | 2020 | 2020 | R16
163004195208 | 164250195208 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-24 | 2020-06-24 | 2020-06-24 | 2020-07-03 | 2020-09-17 | Overhead | R16 | 2020-07-03 | 1 |  | 8 | 55 | 62 | 2020 | 2020 | R16
165328182706 | 166164182706 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-01-28 | 2020-01-28 | 2020-03-02 | 2021-12-14 | 2022-01-24 | Underground | R16 | 2021-12-14 | 1 | 25 | 467 | 30 | 520 | 2020 | 2022 | R16
169936275749 | 169938275749 | SPECIFIC BUDGET PROJECTS | OH R16 RES NON RES OD | Commercial | 2020-06-01 | 2021-07-26 | 2022-04-13 |  | 2023-06-14 | Overhead | R16 |  | 301 | 188 |  |  | 793 | 2020 | 2023 | R16
163770193894 | 163800193894 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-04-24 | 2020-04-28 | 2020-06-10 |  | 2020-10-06 | Overhead | R16 |  | 3 | 32 |  |  | 118 | 2020 | 2020 | R16
162051213364 | 166857213364 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Residential | 2020-05-12 | 2020-05-12 | 2020-12-09 | 2022-06-15 | 2022-07-11 | Underground | R16 | 2022-06-15 | 1 | 152 | 396 | 19 | 565 | 2020 | 2022 | R16
163068147501 | 165494147501 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-02-28 | 2019-02-28 | 2019-03-28 |  | 2020-06-09 | Underground | R16 |  | 1 | 21 |  |  | 334 | 2019 | 2020 | R16
162561182621 | 164511182621 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-17 | 2020-01-17 | 2020-03-02 | 2021-01-13 | 2021-01-14 | Underground | R16 | 2021-01-13 | 1 | 32 | 228 | 2 | 260 | 2020 | 2021 | R16
169365193679 | 161394193679 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-09 | 2020-06-09 | 2020-06-09 | 2020-06-24 | 2020-06-25 | Overhead | R16 | 2020-06-24 | 1 |  | 12 | 2 | 13 | 2020 | 2020 | R16
169284192944 | 169943192944 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-01 | 2020-06-01 | 2020-06-01 |  | 2020-08-27 | Underground | R16 | 2020-06-25 | 1 |  | 19 | 46 | 64 | 2020 | 2020 | R16
166470191584 | 167731191584 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-18 | 2020-05-19 | 2020-05-19 |  | 2020-07-10 | Overhead | R16 | 2020-06-11 | 2 |  | 18 | 22 | 40 | 2020 | 2020 | R16
169191233125 | 161126233125 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-04-10 | 2020-04-16 | 2021-06-01 |  | 2022-09-20 | Underground | R16 | 2021-04-07 | 5 | 294 |  | 380 | 638 | 2020 | 2022 | R16
167559193327 | 160397193327 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-05 | 2020-06-05 | 2020-06-05 | 2020-06-09 | 2020-06-25 | Overhead | R16 | 2020-06-09 | 1 |  | 3 | 13 | 15 | 2020 | 2020 | R16
167915196905 | 163183196905 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2020-06-18 | 2020-06-18 | 2020-07-09 | 2021-07-12 | 2021-12-03 | Underground | R16 | 2021-07-12 | 1 | 16 | 263 | 105 | 382 | 2020 | 2021 | R16
162136192435 | 163091192435 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-21 | 2020-04-21 | 2020-05-28 | 2020-06-09 | 2020-06-24 | Underground | R16 | 2020-06-09 | 1 | 28 | 9 | 12 | 47 | 2020 | 2020 | R16
168050183595 | 169509183595 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-23 | 2020-01-02 | 2020-03-10 | 2020-04-08 | 2020-06-23 | Underground | R16 | 2020-04-08 | 9 | 49 | 22 | 55 | 132 | 2019 | 2020 | R16
166448194683 | 166720194683 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-17 | 2020-03-17 | 2020-06-17 |  | 2020-10-06 | Underground | R16 | 2020-08-28 | 1 | 67 | 53 | 28 | 146 | 2020 | 2020 | R16
163879197555 | 167685197555 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-13 | 2020-07-13 | 2020-07-17 |  | 2022-12-13 | Overhead | R16 |  | 1 | 5 |  |  | 632 | 2020 | 2022 | R16
169687187575 | 161926187575 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-15 | 2020-04-15 | 2020-04-15 | 2020-04-22 | 2022-09-11 | Overhead | R16 | 2020-04-22 | 1 |  | 6 | 623 | 628 | 2020 | 2022 | R16
162437178575 | 162376178575 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2020-01-09 | 2020-01-09 | 2020-01-29 |  | 2021-03-12 | Underground | R16 |  | 1 | 15 |  |  | 307 | 2020 | 2021 | R16
163748189150 | 164828189150 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-09 | 2020-03-09 | 2020-04-28 | 2022-04-25 | 2022-06-06 | Underground | R16 | 2022-04-25 | 1 | 37 | 520 | 31 | 586 | 2020 | 2022 | R16
162912177950 | 165851177950 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-24 | 2020-01-24 | 2020-01-24 | 2020-04-24 | 2020-04-29 | Overhead | R16 | 2020-04-24 | 1 |  | 66 | 4 | 69 | 2020 | 2020 | R16
163524189416 | 164997189416 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-22 | 2020-01-22 | 2020-04-29 | 2020-05-07 | 2020-05-22 | Underground | R16 | 2020-05-07 | 1 | 71 | 7 | 12 | 88 | 2020 | 2020 | R16
168978190801 | 168627190801 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE FOR UPGRADE UD | Commercial | 2020-02-07 | 2020-02-10 | 2020-05-11 | 2020-08-11 | 2020-10-05 | Underground | R16 | 2020-08-11 | 2 | 66 | 67 | 40 | 172 | 2020 | 2020 | R16
164210205874 | 163100205874 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-04-21 | 2020-09-25 | 2020-10-01 | 2020-10-16 | 2021-02-03 | Overhead | R16 | 2020-10-16 | 114 | 5 | 12 | 79 | 207 | 2020 | 2021 | R16
165436172089 | 164477172089 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-03 | 2019-11-12 | 2019-11-18 |  | 2021-11-10 | Overhead | R16 |  | 29 | 5 |  |  | 550 | 2019 | 2021 | R16
162973180051 | 168992180051 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-10 | 2020-02-10 | 2020-02-10 | 2020-06-09 | 2020-07-14 | Overhead | R16 | 2020-06-09 | 1 |  | 87 | 26 | 112 | 2020 | 2020 | R16
162434190767 | 164748190767 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-30 | 2020-04-30 | 2020-05-12 |  | 2022-06-24 | Underground | R16 | 2020-06-15 | 1 | 9 | 25 | 530 | 562 | 2020 | 2022 | R16
160862190364 | 165991190364 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-07 | 2020-05-07 | 2020-05-07 |  | 2020-07-08 | Overhead | R16 | 2020-05-26 | 1 |  | 14 | 32 | 45 | 2020 | 2020 | R16
166069191364 | 167564191364 | SDG&E | UG ELEC MISC SVC US | Residential | 2020-05-18 | 2020-05-18 | 2020-05-19 | 2020-09-22 | 2023-10-06 | Underground | R16 | 2020-09-22 | 1 | 2 | 91 | 794 | 885 | 2020 | 2023 | R16
162036189084 | 163849189084 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-04-27 | 2020-04-27 | 2020-04-27 |  | 2020-07-02 | Overhead | R16 | 2020-04-30 | 1 |  | 4 | 46 | 49 | 2020 | 2020 | R16
162966196049 | 165591196049 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-30 | 2020-06-30 | 2020-07-01 |  | 2020-10-06 | Overhead | R16 | 2020-07-13 | 1 | 2 | 9 | 62 | 71 | 2020 | 2020 | R16
169633191733 | 168421191733 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-21 | 2020-05-21 | 2020-05-21 |  | 2020-07-09 | Overhead | R16 | 2020-06-02 | 1 |  | 9 | 28 | 36 | 2020 | 2020 | R16
162908196486 | 162944196486 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-17 | 2020-06-17 | 2020-07-06 |  | 2020-10-06 | Underground | R16 | 2020-07-21 | 1 | 14 | 12 | 56 | 80 | 2020 | 2020 | R16
165783199578 | 161641199578 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-06-10 | 2020-06-11 | 2020-08-04 |  | 2021-06-03 | Underground | R16 |  | 2 | 39 |  |  | 257 | 2020 | 2021 | R16
166165140229 | 167311140229 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-01-15 | 2019-01-15 | 2019-01-15 |  | 2019-02-21 | Overhead | R16 | 2019-02-14 | 1 |  | 23 | 6 | 28 | 2019 | 2019 | R16
163780178731 | 164393178731 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-18 | 2020-01-18 | 2020-01-30 | 2020-03-17 | 2020-03-19 | Underground | R16 | 2020-03-17 | 0 | 9 | 34 | 3 | 44 | 2020 | 2020 | R16
166260139901 | 164800139901 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-03 | 2019-01-03 | 2019-01-10 |  | 2019-08-12 | Underground | R16 | 2019-06-04 | 1 | 6 | 104 | 50 | 158 | 2019 | 2019 | R16
165456192153 | 160442192153 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-14 | 2020-02-18 | 2020-05-26 | 2020-07-22 | 2020-07-23 | Underground | R16 | 2020-07-22 | 3 | 71 | 42 | 2 | 115 | 2020 | 2020 | R16
163092186692 | 160591186692 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-07 | 2020-04-07 | 2020-04-07 | 2020-04-22 | 2020-07-02 | Overhead | R16 | 2020-04-22 | 1 |  | 12 | 52 | 63 | 2020 | 2020 | R16
167309185973 | 162309185973 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-09 | 2020-01-09 | 2020-04-01 | 2020-05-05 | 2020-07-06 | Underground | R16 | 2020-05-05 | 1 | 60 | 25 | 45 | 128 | 2020 | 2020 | R16
168954200073 | 169900200073 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-31 | 2020-05-31 | 2020-08-11 |  | 2020-10-06 | Underground | R16 | 2020-08-24 | 0 | 52 | 10 | 32 | 92 | 2020 | 2020 | R16
164355197560 | 165963197560 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-02 | 2020-07-16 | 2020-07-16 | 2020-08-13 | 2021-03-11 | Overhead | R16 | 2020-08-13 | 11 |  | 21 | 151 | 181 | 2020 | 2021 | R16
160459186704 | 160308186704 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-07 | 2020-04-07 | 2020-04-07 |  | 2022-10-19 | Overhead | R16 |  | 1 |  |  |  | 662 | 2020 | 2022 | R16
160179178367 | 166099178367 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-27 | 2020-01-27 | 2020-01-27 |  | 2020-06-09 | Overhead | R16 | 2020-03-09 | 1 |  | 31 | 67 | 97 | 2020 | 2020 | R16
167251199336 | 167137199336 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-02-01 | 2020-02-01 | 2020-08-03 | 2021-01-27 | 2021-01-28 | Underground | R16 | 2021-01-27 | 0 | 131 | 128 | 2 | 259 | 2020 | 2021 | R16
166358187065 | 160987187065 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-04-10 | 2020-04-10 | 2020-04-10 | 2023-07-30 | 2023-08-04 | Overhead | R16 | 2023-07-30 | 1 |  | 861 | 5 | 866 | 2020 | 2023 | R16
169185219103 | 160788219103 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OD | Residential | 2020-04-09 | 2021-01-28 | 2021-01-29 |  | 2021-09-01 | Overhead | R16 |  | 211 | 2 |  |  | 365 | 2020 | 2021 | R16
165539180364 | 169655180364 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-02-12 | 2020-02-12 | 2020-02-12 |  | 2021-04-29 | Underground | R16 | 2021-02-10 | 1 |  | 261 | 57 | 317 | 2020 | 2021 | R16
169648187259 | 161889187259 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-04-15 | 2020-04-15 | 2020-04-15 |  | 2020-08-28 | Overhead | R16 | 2020-06-29 | 1 |  | 54 | 45 | 98 | 2020 | 2020 | R16
165925184985 | 167501184985 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-23 | 2020-03-23 | 2020-03-23 | 2020-04-10 | 2020-07-09 | Overhead | R16 | 2020-04-10 | 1 |  | 15 | 65 | 79 | 2020 | 2020 | R16
161740183957 | 165804183957 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-12 | 2020-03-13 | 2020-03-13 | 2020-03-30 | 2020-07-08 | Overhead | R16 | 2020-03-30 | 2 |  | 12 | 73 | 85 | 2020 | 2020 | R16
169360230069 | 165034230069 | NON-RESIDENTIAL - WAREHOUSE | R16 RESD AND NON RESD US | Commercial | 2020-06-29 | 2021-05-07 | 2021-05-10 | 2022-04-15 | 2022-05-18 | Underground | R16 | 2022-04-15 | 225 | 2 | 245 | 24 | 493 | 2020 | 2022 | R16
167860209714 | 167806209714 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-19 | 2020-05-19 | 2020-11-07 | 2021-03-02 | 2022-08-03 | Overhead | R16 | 2021-03-02 | 1 | 124 | 82 | 372 | 577 | 2020 | 2022 | R16
163549174519 | 168925174519 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-17 | 2019-12-17 | 2019-12-17 | 2020-01-28 | 2020-01-29 | Overhead | R16 | 2020-01-28 | 1 |  | 31 | 2 | 32 | 2019 | 2020 | R16
169398183746 | 165248183746 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-10 | 2020-03-10 | 2020-03-10 |  | 2020-07-09 | Overhead | R16 | 2020-05-27 | 1 |  | 57 | 32 | 88 | 2020 | 2020 | R16
165167184755 | 166717184755 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-17 | 2020-03-20 | 2020-03-20 | 2020-04-14 | 2020-05-26 | Overhead | R16 | 2020-04-14 | 4 |  | 18 | 31 | 51 | 2020 | 2020 | R16
163300182224 | 168056182224 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-02-05 | 2020-02-07 | 2020-02-27 |  | 2020-06-09 | Overhead | R16 |  | 3 | 15 |  |  | 90 | 2020 | 2020 | R16
166353185111 | 161961185111 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-24 | 2020-03-06 | 2020-03-23 |  | 2021-04-15 | Overhead | R16 |  | 10 | 12 |  |  | 299 | 2020 | 2021 | R16
165990192810 | 169904192810 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-06-01 | 2020-06-01 | 2020-06-01 |  | 2022-04-20 | Underground | R16 | 2022-03-28 | 1 |  | 476 | 18 | 493 | 2020 | 2022 | R16
161697188898 | 163612188898 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-24 | 2020-04-24 | 2020-04-24 | 2020-07-09 | 2020-07-10 | Overhead | R16 | 2020-07-09 | 1 |  | 55 | 2 | 56 | 2020 | 2020 | R16
161089196652 | 166601196652 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2020-07-08 | 2020-07-08 | 2020-07-08 |  | 2021-07-14 | Overhead | R16 | 2020-11-20 | 1 |  | 98 | 169 | 266 | 2020 | 2021 | R16
162554180025 | 168953180025 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-02-10 | 2020-02-10 | 2020-02-10 |  | 2022-05-17 | Underground | R16 | 2020-06-19 | 1 |  | 95 | 498 | 592 | 2020 | 2022 | R16
166382184620 | 166677184620 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-03-18 | 2020-03-18 | 2020-03-18 |  | 2022-10-17 | Overhead | R16 |  | 1 |  |  |  | 674 | 2020 | 2022 | R16
169549189841 | 165292189841 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-05-04 | 2020-05-04 | 2020-05-04 |  | 2020-07-07 | Overhead | R16 | 2020-05-08 | 1 |  | 5 | 43 | 47 | 2020 | 2020 | R16
163752183696 | 165394183696 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-10 | 2020-03-10 | 2020-03-10 |  | 2022-10-17 | Overhead | R16 |  | 1 |  |  |  | 680 | 2020 | 2022 | R16
166550182052 | 162515182052 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-26 | 2020-02-26 | 2020-02-26 | 2020-03-24 | 2020-06-09 | Overhead | R16 | 2020-03-24 | 1 |  | 20 | 56 | 75 | 2020 | 2020 | R16
169261237462 | 165472237462 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Commercial | 2020-03-10 | 2020-10-28 | 2021-07-01 | 2022-10-11 | 2022-11-04 | Underground | R16 | 2022-10-11 | 167 | 177 | 334 | 19 | 694 | 2020 | 2022 | R16
169800158154 | 163112158154 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-10 | 2019-07-11 | 2019-07-17 |  | 2019-09-10 | Overhead | R16 |  | 24 | 5 |  |  | 67 | 2019 | 2019 | R16
167894184114 | 166335184114 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-17 | 2020-03-17 | 2020-03-17 |  | 2020-07-09 | Overhead | R16 | 2020-05-05 | 1 |  | 36 | 48 | 83 | 2020 | 2020 | R16
169800210015 | 166400210015 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-07 | 2020-10-26 | 2020-11-09 |  | 2021-07-12 | Overhead | R16 |  | 14 | 11 |  |  | 199 | 2020 | 2021 | R16
166691233354 | 165969233354 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH CP R16 WORK RELO TO UG | Residential | 2020-03-12 | 2020-03-17 | 2021-06-03 | 2021-06-17 | 2021-11-15 | Overhead | R16 | 2021-06-17 | 4 | 318 | 11 | 108 | 438 | 2020 | 2021 | R16
166378193168 | 167949193168 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-19 | 2020-06-01 | 2020-06-05 | 2020-06-10 | 2020-08-28 | Overhead | R16 | 2020-06-10 | 10 | 5 | 4 | 58 | 74 | 2020 | 2020 | R16
167976195182 | 163947195182 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-24 | 2020-06-24 | 2020-06-24 |  | 2020-10-06 | Overhead | R16 | 2020-07-16 | 1 |  | 17 | 59 | 75 | 2020 | 2020 | R16
166987183015 | 164364183015 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-05 | 2020-03-05 | 2020-03-05 | 2020-04-24 | 2020-05-01 | Overhead | R16 | 2020-04-24 | 1 |  | 37 | 6 | 42 | 2020 | 2020 | R16
167867181370 | 161654181370 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-21 | 2020-02-21 | 2020-02-21 | 2020-04-01 | 2020-07-02 | Overhead | R16 | 2020-04-01 | 1 |  | 29 | 67 | 95 | 2020 | 2020 | R16
162100184424 | 166686184424 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-17 | 2020-03-17 | 2020-03-17 |  | 2020-07-08 | Overhead | R16 | 2020-05-21 | 1 |  | 48 | 35 | 82 | 2020 | 2020 | R16
166719178894 | 166488178894 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-30 | 2020-01-30 | 2020-01-31 | 2020-03-15 | 2020-04-15 | Overhead | R16 | 2020-03-15 | 1 | 2 | 31 | 23 | 55 | 2020 | 2020 | R16
160398147861 | 168789147861 | GENERAL/OTHER | R16 RESD AND NON RESD US | Commercial | 2019-03-19 | 2019-03-19 | 2019-04-01 |  | 2019-08-26 | Underground | R16 |  | 1 | 10 |  |  | 115 | 2019 | 2019 | R16
163844197507 | 166208197507 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2020-07-06 | 2020-07-06 | 2020-07-15 | 2020-07-23 | 2020-07-29 | Overhead | R16 | 2020-07-23 | 1 | 8 | 7 | 5 | 18 | 2020 | 2020 | R16
167109191533 | 167974191533 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-19 | 2020-05-19 | 2020-05-19 | 2020-05-27 | 2020-05-28 | Overhead | R16 | 2020-05-27 | 1 |  | 7 | 2 | 8 | 2020 | 2020 | R16
160501183801 | 169786183801 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-05-18 | 2019-05-18 | 2020-03-11 |  | 2021-07-07 | Underground | R16 |  | 0 | 213 |  |  | 558 | 2019 | 2021 | R16
160501206605 | 161921206605 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-09-18 | 2020-09-24 | 2020-10-08 |  | 2021-06-03 | Overhead | R16 |  | 5 | 11 |  |  | 185 | 2020 | 2021 | R16
167220202990 | 166062202990 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-13 | 2020-03-18 | 2020-09-06 | 2020-10-06 | 2020-10-06 | Overhead | R16 | 2020-10-06 | 4 | 123 | 22 |  | 148 | 2020 | 2020 | R16
163826182795 | 163905182795 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-03 | 2020-03-03 | 2020-03-03 | 2021-06-29 | 2021-06-30 | Overhead | R16 | 2021-06-29 | 1 |  | 346 | 2 | 347 | 2020 | 2021 | R16
168395187513 | 161884187513 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-15 | 2020-04-15 | 2020-04-15 | 2020-04-16 | 2020-07-07 | Overhead | R16 | 2020-04-16 | 1 |  | 2 | 59 | 60 | 2020 | 2020 | R16
161326196773 | 166767196773 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-09 | 2020-07-09 | 2020-07-09 | 2020-07-23 | 2020-10-06 | Overhead | R16 | 2020-07-23 | 1 |  | 11 | 54 | 64 | 2020 | 2020 | R16
167708182556 | 163683182556 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-03 | 2020-03-03 | 2020-03-03 |  | 2020-06-09 | Underground | R16 | 2020-04-07 | 1 |  | 26 | 46 | 71 | 2020 | 2020 | R16
161011172463 | 163902172463 | NON-RESIDENTIAL - LODGING | OH R16 RES NON RES OS | Commercial | 2019-11-19 | 2019-11-20 | 2019-11-20 |  | 2020-08-14 | Overhead | R16 |  | 2 |  |  |  | 194 | 2019 | 2020 | R16
160507196221 | 162232196221 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-15 | 2020-06-15 | 2020-06-30 | 2020-08-04 | 2020-10-06 | Underground | R16 | 2020-08-04 | 1 | 12 | 26 | 46 | 82 | 2020 | 2020 | R16
161060158859 | 168045158859 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-07-05 | 2019-07-10 | 2019-07-24 |  | 2022-10-29 | Underground | R16 |  | 4 | 11 |  |  | 866 | 2019 | 2022 | R16
161161216660 | 162395216660 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH CP R16 WORK RELO TO UG | Commercial | 2020-06-16 | 2020-10-20 | 2021-01-07 | 2021-03-22 | 2021-05-26 | Overhead | R16 | 2021-03-22 | 91 | 58 | 53 | 48 | 247 | 2020 | 2021 | R16
169611193861 | 163525193861 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2020-03-02 | 2020-05-19 | 2020-06-09 | 2020-09-23 | 2020-10-20 | Underground | R16 | 2020-09-23 | 57 | 16 | 77 | 20 | 167 | 2020 | 2020 | R16
161082238220 | 169495238220 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2020-05-28 | 2021-03-24 | 2021-07-08 |  | 2022-01-11 | Overhead | R16 |  | 215 | 77 |  |  | 424 | 2020 | 2022 | R16
169295177749 | 169302177749 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-12-18 | 2019-12-18 | 2020-01-22 | 2021-09-21 | 2021-10-22 | Underground | R16 | 2021-09-21 | 1 | 26 | 435 | 24 | 483 | 2019 | 2021 | R16
163298194563 | 165105194563 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-01 | 2020-06-06 | 2020-06-16 |  | 2020-10-06 | Overhead | R16 |  | 26 | 7 |  |  | 113 | 2020 | 2020 | R16
161010194628 | 162972194628 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-17 | 2020-06-17 | 2020-06-17 | 2020-07-20 | 2023-06-07 | Overhead | R16 | 2020-07-20 | 1 |  | 24 | 753 | 776 | 2020 | 2023 | R16
163132187227 | 161507187227 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-04-13 | 2020-04-13 | 2020-04-13 |  | 2020-09-16 | Underground | R16 | 2020-07-08 | 1 |  | 63 | 51 | 113 | 2020 | 2020 | R16
162562183389 | 167625183389 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-04 | 2020-02-04 | 2020-03-10 |  | 2020-07-08 | Underground | R16 | 2020-05-15 | 1 | 26 | 49 | 39 | 112 | 2020 | 2020 | R16
163236197974 | 163323197974 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-01-14 | 2020-01-14 | 2020-07-22 |  | 2021-06-02 | Underground | R16 |  | 1 | 137 |  |  | 362 | 2020 | 2021 | R16
163348178922 | 166110178922 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-01-27 | 2020-01-27 | 2020-01-31 |  | 2022-03-25 | Underground | R16 | 2022-03-25 | 1 | 5 | 561 |  | 565 | 2020 | 2022 | R16
162065177554 | 164743177554 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-01-21 | 2020-01-21 | 2020-01-21 | 2020-02-24 | 2020-06-09 | Overhead | R16 | 2020-02-24 | 1 |  | 25 | 77 | 101 | 2020 | 2020 | R16
166127181323 | 161132181323 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-20 | 2020-02-20 | 2020-02-20 |  | 2020-06-09 | Overhead | R16 | 2020-04-02 | 1 |  | 31 | 49 | 79 | 2020 | 2020 | R16
161189182816 | 164004182816 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-04 | 2020-03-04 | 2020-03-04 | 2020-04-01 | 2020-04-02 | Overhead | R16 | 2020-04-01 | 1 |  | 21 | 2 | 22 | 2020 | 2020 | R16
167899185626 | 168605185626 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-27 | 2020-03-27 | 2020-03-27 | 2020-04-09 | 2020-07-02 | Overhead | R16 | 2020-04-09 | 1 |  | 10 | 61 | 70 | 2020 | 2020 | R16
164414193195 | 166430193195 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-16 | 2020-06-04 | 2020-06-04 | 2020-08-07 | 2020-10-29 | Overhead | R16 | 2020-08-07 | 59 |  | 47 | 60 | 164 | 2020 | 2020 | R16
164128193916 | 165245193916 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-04 | 2020-06-10 | 2020-06-10 | 2020-07-30 | 2020-10-06 | Overhead | R16 | 2020-07-30 | 28 |  | 37 | 49 | 112 | 2020 | 2020 | R16
161542193033 | 165133193033 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-22 | 2020-01-27 | 2020-06-03 | 2020-08-12 | 2020-08-13 | Underground | R16 | 2020-08-12 | 4 | 93 | 51 | 2 | 147 | 2020 | 2020 | R16
162037193875 | 161510193875 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-06-10 | 2020-06-10 | 2020-06-10 | 2020-11-13 | 2021-07-15 | Overhead | R16 | 2020-11-13 | 1 |  | 113 | 175 | 287 | 2020 | 2021 | R16
165354192241 | 166925192241 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-13 | 2020-05-13 | 2020-05-26 | 2020-06-24 | 2020-08-28 | Underground | R16 | 2020-06-24 | 1 | 10 | 22 | 48 | 78 | 2020 | 2020 | R16
164679200123 | 166139200123 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-05-08 | 2020-07-07 | 2020-08-08 | 2021-02-17 | 2021-05-06 | Underground | R16 | 2021-02-17 | 43 | 24 | 138 | 57 | 260 | 2020 | 2021 | R16
161546184465 | 164845184465 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-09 | 2020-03-09 | 2020-03-18 | 2020-07-13 | 2020-10-06 | Underground | R16 | 2020-07-13 | 1 | 8 | 84 | 62 | 152 | 2020 | 2020 | R16
163769199427 | 167950199427 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-07-13 | 2020-07-13 | 2020-08-03 |  | 2021-07-24 | Underground | R16 | 2020-11-05 | 1 | 16 | 69 | 187 | 270 | 2020 | 2021 | R16
168451179617 | 168921179617 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-16 | 2019-12-16 | 2020-02-07 |  | 2020-06-09 | Underground | R16 | 2020-03-02 | 1 | 40 | 17 | 72 | 127 | 2019 | 2020 | R16
162537189456 | 164650189456 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-04-29 | 2020-04-29 | 2020-04-29 |  | 2020-07-10 | Overhead | R16 | 2020-06-11 | 1 |  | 32 | 22 | 53 | 2020 | 2020 | R16
169227181409 | 165559181409 | CUSTOMER UPGRADE IN SERVICE | UG SVC CONVERSION | Residential | 2020-01-23 | 2020-02-18 | 2020-02-21 |  | 2021-11-05 | Underground | R16 | 2021-04-16 | 19 | 4 | 301 | 146 | 467 | 2020 | 2021 | R16
163005200434 | 163444200434 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-23 | 2020-04-23 | 2020-08-13 |  | 2020-12-14 | Underground | R16 | 2020-09-09 | 1 | 81 | 20 | 69 | 168 | 2020 | 2020 | R16
161743197415 | 162040197415 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-06-12 | 2020-06-15 | 2020-07-16 |  | 2023-05-12 | Underground | R16 |  | 2 | 24 |  |  | 761 | 2020 | 2023 | R16
166497216511 | 168502216511 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-05-21 | 2020-05-21 | 2021-01-07 |  | 2023-12-14 | Underground | R16 |  | 1 | 166 |  |  | 931 | 2020 | 2023 | R16
163886205597 | 166277205597 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-07 | 2020-09-29 | 2020-09-29 | 2020-11-18 | 2021-04-14 | Overhead | R16 | 2020-11-18 | 61 |  | 37 | 106 | 202 | 2020 | 2021 | R16
163958245332 | 168980245332 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-03-30 | 2020-04-10 | 2021-08-26 |  | 2021-10-26 | Overhead | R16 |  | 10 | 360 |  |  | 412 | 2020 | 2021 | R16
161786188536 | 163137188536 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-22 | 2020-04-22 | 2020-04-22 | 2020-06-10 | 2020-10-06 | Overhead | R16 | 2020-06-10 | 1 |  | 36 | 85 | 120 | 2020 | 2020 | R16
162347178821 | 166904178821 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-30 | 2020-01-30 | 2020-01-30 | 2020-02-28 | 2020-06-09 | Overhead | R16 | 2020-02-28 | 1 |  | 22 | 73 | 94 | 2020 | 2020 | R16
163641194958 | 163686194958 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-22 | 2020-06-22 | 2020-06-22 | 2020-07-23 | 2020-10-06 | Underground | R16 | 2020-07-23 | 1 |  | 24 | 54 | 77 | 2020 | 2020 | R16
169346183596 | 169595183596 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-12 | 2020-02-12 | 2020-03-10 |  | 2020-07-14 | Underground | R16 | 2020-06-18 | 1 | 20 | 73 | 19 | 110 | 2020 | 2020 | R16
162209212255 | 169828212255 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OD | Residential | 2020-02-14 | 2020-02-14 | 2020-12-01 | 2021-08-24 | 2022-02-02 | Overhead | R16 | 2021-08-24 | 1 | 208 | 191 | 117 | 514 | 2020 | 2022 | R16
162707145771 | 166825145771 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-07 | 2019-03-07 | 2019-03-11 |  | 2022-10-27 | Overhead | R16 |  | 1 | 3 |  |  | 951 | 2019 | 2022 | R16
162707145764 | 166828145764 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-07 | 2019-03-08 | 2019-03-11 |  | 2019-12-09 | Overhead | R16 |  | 2 | 2 |  |  | 198 | 2019 | 2019 | R16
162857197728 | 165933197728 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-05-07 | 2020-05-29 | 2020-07-17 |  | 2021-07-13 | Underground | R16 | 2020-11-20 | 17 | 36 | 91 | 168 | 309 | 2020 | 2021 | R16
162707146553 | 167020146553 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-07 | 2019-03-19 | 2019-03-20 |  | 2021-11-13 | Overhead | R16 |  | 9 | 2 |  |  | 702 | 2019 | 2021 | R16
168361177666 | 164759177666 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-21 | 2020-01-21 | 2020-01-21 |  | 2020-06-09 | Overhead | R16 | 2020-03-11 | 1 |  | 37 | 65 | 101 | 2020 | 2020 | R16
162707146551 | 167021146551 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-07 | 2019-03-19 | 2019-03-20 |  | 2021-11-10 | Overhead | R16 |  | 9 | 2 |  |  | 700 | 2019 | 2021 | R16
161011190435 | 163634190435 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-02 | 2020-03-06 | 2020-05-09 | 2020-06-17 | 2020-06-18 | Underground | R16 | 2020-06-17 | 5 | 46 | 28 | 2 | 79 | 2020 | 2020 | R16
165619182239 | 163136182239 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2020-02-28 | 2020-02-28 | 2020-02-28 | 2020-07-16 | 2020-07-17 | Underground | R16 | 2020-07-16 | 1 |  | 100 | 2 | 101 | 2020 | 2020 | R16
166381181014 | 160610181014 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-18 | 2020-02-18 | 2020-02-19 |  | 2021-07-02 | Overhead | R16 | 2020-10-23 | 1 | 2 | 178 | 181 | 359 | 2020 | 2021 | R16
162707154667 | 162005154667 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-03 | 2019-06-03 | 2019-06-07 |  | 2021-08-23 | Overhead | R16 |  | 1 | 5 |  |  | 581 | 2019 | 2021 | R16
162707155218 | 162006155218 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-03 | 2019-06-04 | 2019-06-13 |  | 2020-10-06 | Underground | R16 |  | 2 | 8 |  |  | 352 | 2019 | 2020 | R16
163472195037 | 165266195037 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-04 | 2020-06-23 | 2020-06-23 | 2020-09-10 | 2020-12-15 | Overhead | R16 | 2020-09-10 | 37 |  | 58 | 69 | 162 | 2020 | 2020 | R16
168397186709 | 160377186709 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-07 | 2020-04-07 | 2020-04-07 |  | 2020-07-01 | Overhead | R16 | 2020-04-30 | 1 |  | 18 | 45 | 62 | 2020 | 2020 | R16
167126196799 | 166924196799 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-09 | 2020-07-09 | 2020-07-09 | 2020-10-08 | 2020-10-09 | Overhead | R16 | 2020-10-08 | 1 |  | 66 | 2 | 67 | 2020 | 2020 | R16
164633177457 | 165420177457 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-23 | 2020-01-23 | 2020-01-23 |  | 2020-07-07 | Underground | R16 | 2020-05-07 | 1 |  | 76 | 44 | 119 | 2020 | 2020 | R16
165267189061 | 163731189061 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-04-24 | 2020-04-24 | 2020-04-27 |  | 2021-07-01 | Overhead | R16 | 2020-09-11 | 1 | 2 | 100 | 210 | 310 | 2020 | 2021 | R16
165671196489 | 168335196489 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-21 | 2020-05-21 | 2020-07-06 | 2020-09-02 | 2021-01-08 | Underground | R16 | 2020-09-02 | 1 | 33 | 43 | 93 | 167 | 2020 | 2021 | R16
164096187701 | 161983187701 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-15 | 2020-04-15 | 2020-04-15 |  | 2020-12-18 | Overhead | R16 |  | 1 |  |  |  | 178 | 2020 | 2020 | R16
164339200484 | 165934200484 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-07-02 | 2020-07-16 | 2020-08-12 |  | 2021-04-06 | Underground | R16 |  | 11 | 20 |  |  | 199 | 2020 | 2021 | R16
161561177929 | 165650177929 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-23 | 2020-01-23 | 2020-01-23 |  | 2020-07-09 | Overhead | R16 | 2020-05-29 | 1 |  | 92 | 30 | 121 | 2020 | 2020 | R16
160452187846 | 162124187846 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-16 | 2020-04-16 | 2020-04-16 |  | 2020-07-09 | Underground | R16 | 2020-05-27 | 1 |  | 30 | 32 | 61 | 2020 | 2020 | R16
169543187515 | 161888187515 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-15 | 2020-04-15 | 2020-04-15 |  | 2021-11-10 | Overhead | R16 | 2020-06-25 | 1 |  | 52 | 360 | 411 | 2020 | 2021 | R16
167197191748 | 167303191748 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-20 | 2020-03-20 | 2020-05-21 | 2021-12-17 | 2021-12-20 | Underground | R16 | 2021-12-17 | 1 | 45 | 412 | 2 | 457 | 2020 | 2021 | R16
163204146865 | 165076146865 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-02-25 | 2019-02-25 | 2019-03-22 |  | 2019-05-20 | Underground | R16 | 2019-04-18 | 1 | 20 | 20 | 23 | 61 | 2019 | 2019 | R16
165829181821 | 169191181821 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-12-18 | 2019-12-18 | 2020-02-24 |  | 2020-12-21 | Underground | R16 |  | 1 | 49 |  |  | 264 | 2019 | 2020 | R16
162195186223 | 167570186223 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-03 | 2020-02-03 | 2020-04-02 |  | 2020-06-09 | Overhead | R16 | 2020-04-03 | 1 | 44 | 2 | 48 | 92 | 2020 | 2020 | R16
168477197232 | 161411197232 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-06-09 | 2020-06-09 | 2020-07-14 |  | 2021-11-03 | Underground | R16 | 2021-06-18 | 1 | 26 | 244 | 99 | 367 | 2020 | 2021 | R16
165553191110 | 167447191110 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-15 | 2020-05-15 | 2020-05-15 |  | 2020-10-06 | Overhead | R16 | 2020-07-13 | 1 |  | 42 | 62 | 103 | 2020 | 2020 | R16
163970157560 | 161577157560 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2019-05-30 | 2019-05-31 | 2019-07-10 |  | 2021-10-25 | Underground | R16 |  | 2 | 29 |  |  | 628 | 2019 | 2021 | R16
163775181321 | 161255181321 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-20 | 2020-02-20 | 2020-02-20 | 2020-02-25 | 2020-06-09 | Overhead | R16 | 2020-02-25 | 1 |  | 4 | 76 | 79 | 2020 | 2020 | R16
163970219162 | 164848219162 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2021-01-05 | 2021-01-05 | 2021-01-29 |  | 2021-10-26 | Underground | R16 |  | 1 | 19 |  |  | 211 | 2021 | 2021 | R16
162467189309 | 163900189309 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-27 | 2020-04-29 | 2020-04-29 | 2020-06-08 | 2020-06-10 | Overhead | R16 | 2020-06-08 | 3 |  | 29 | 3 | 33 | 2020 | 2020 | R16
161694194353 | 165121194353 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-05-01 | 2020-06-02 | 2020-06-16 |  | 2021-07-26 | Underground | R16 |  | 23 | 11 |  |  | 322 | 2020 | 2021 | R16
163971157533 | 161237157533 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-05-29 | 2019-05-30 | 2019-07-10 |  | 2021-10-25 | Underground | R16 |  | 2 | 30 |  |  | 629 | 2019 | 2021 | R16
163971157532 | 161238157532 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-05-29 | 2019-05-30 | 2019-07-10 |  | 2021-11-11 | Underground | R16 |  | 2 | 30 |  |  | 642 | 2019 | 2021 | R16
166621219856 | 163626219856 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-04-24 | 2021-01-14 | 2021-02-08 |  | 2022-01-14 | Underground | R16 |  | 190 | 18 |  |  | 451 | 2020 | 2022 | R16
163674190667 | 166428190667 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-11 | 2020-05-11 | 2020-05-11 | 2020-09-08 | 2020-09-09 | Overhead | R16 | 2020-09-08 | 1 |  | 87 | 2 | 88 | 2020 | 2020 | R16
161806174986 | 168967174986 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-17 | 2019-12-23 | 2019-12-23 | 2020-08-04 | 2020-08-05 | Overhead | R16 | 2020-08-04 | 5 |  | 162 | 2 | 167 | 2019 | 2020 | R16
162238188361 | 169786188361 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-04-02 | 2020-04-17 | 2020-04-20 |  | 2020-07-01 | Overhead | R16 |  | 12 | 2 |  |  | 65 | 2020 | 2020 | R16
169936180914 | 169927180914 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-12-23 | 2019-12-23 | 2020-02-18 | 2020-04-16 | 2020-04-17 | Underground | R16 | 2020-04-16 | 1 | 42 | 43 | 2 | 85 | 2019 | 2020 | R16
166203194596 | 167737194596 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-05-18 | 2020-06-09 | 2020-06-18 | 2022-10-26 | 2023-01-10 | Overhead | R16 | 2022-10-26 | 17 | 8 | 615 | 55 | 692 | 2020 | 2023 | R16
169095187583 | 163880187583 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-16 | 2020-01-16 | 2020-04-14 | 2020-05-19 | 2020-05-20 | Underground | R16 | 2020-05-19 | 1 | 64 | 26 | 2 | 90 | 2020 | 2020 | R16
160634203729 | 160836203729 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG R16 RESD AND NON RESD UD | Commercial | 2020-06-05 | 2020-08-23 | 2020-09-13 | 2022-03-18 | 2022-04-05 | Underground | R16 | 2022-03-18 | 56 | 15 | 395 | 13 | 478 | 2020 | 2022 | R16
169192182234 | 163054182234 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-27 | 2020-02-27 | 2020-02-27 |  | 2020-06-09 | Overhead | R16 | 2020-03-24 | 1 |  | 19 | 56 | 74 | 2020 | 2020 | R16
162606186575 | 160456186575 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-07 | 2020-04-07 | 2020-04-07 | 2020-06-04 | 2020-06-17 | Overhead | R16 | 2020-06-04 | 1 |  | 43 | 10 | 52 | 2020 | 2020 | R16
167056184967 | 167172184967 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential Subdivision | 2020-03-19 | 2020-03-19 | 2020-03-23 |  | 2022-08-29 | Underground | R16 |  | 1 | 3 |  |  | 638 | 2020 | 2022 | R16
169529197842 | 167649197842 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2020-03-23 | 2020-03-23 | 2020-07-20 | 2022-01-27 | 2022-06-16 | Underground | R16 | 2022-01-27 | 1 | 86 | 399 | 101 | 584 | 2020 | 2022 | R16
165238185088 | 167560185088 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-23 | 2020-03-23 | 2020-03-23 |  | 2020-06-09 | Underground | R16 | 2020-03-24 | 1 |  | 2 | 56 | 57 | 2020 | 2020 | R16
164858143903 | 165870143903 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-01-08 | 2019-01-15 | 2019-02-20 |  | 2021-04-15 | Underground | R16 |  | 6 | 27 |  |  | 593 | 2019 | 2021 | R16
168680204233 | 162886204233 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential Subdivision | 2020-06-17 | 2020-06-17 | 2020-09-18 |  | 2022-03-03 | Underground | R16 |  | 1 | 68 |  |  | 447 | 2020 | 2022 | R16
164893143904 | 165807143904 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-01-08 | 2019-01-15 | 2019-02-20 |  | 2021-06-03 | Underground | R16 |  | 6 | 27 |  |  | 628 | 2019 | 2021 | R16
167882175535 | 160842175535 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-01-02 | 2020-01-02 | 2020-01-02 | 2020-02-03 | 2020-02-04 | Overhead | R16 | 2020-02-03 | 1 |  | 23 | 2 | 24 | 2020 | 2020 | R16
166246192994 | 167432192994 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-15 | 2020-05-15 | 2020-06-02 | 2020-06-08 | 2020-08-27 | Underground | R16 | 2020-06-08 | 1 | 13 | 5 | 59 | 75 | 2020 | 2020 | R16
168473178535 | 166557178535 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-29 | 2020-01-29 | 2020-01-29 |  | 2020-06-09 | Overhead | R16 | 2020-02-26 | 1 |  | 21 | 75 | 95 | 2020 | 2020 | R16
165098144502 | 168328144502 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-01-22 | 2019-02-04 | 2019-02-28 |  | 2019-04-15 | Overhead | R16 |  | 10 | 19 |  |  | 60 | 2019 | 2019 | R16
166247197100 | 167270197100 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-10 | 2020-07-13 | 2020-07-13 | 2020-08-10 | 2020-08-11 | Overhead | R16 | 2020-08-10 | 2 |  | 21 | 2 | 23 | 2020 | 2020 | R16
160373194452 | 162452194452 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-16 | 2020-06-16 | 2020-06-16 |  | 2020-10-06 | Underground | R16 | 2020-07-22 | 1 |  | 27 | 55 | 81 | 2020 | 2020 | R16
167937186731 | 169287186731 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-31 | 2020-03-31 | 2020-04-07 | 2020-04-10 | 2020-04-22 | Overhead | R16 | 2020-04-10 | 1 | 6 | 4 | 9 | 17 | 2020 | 2020 | R16
160044180368 | 169969180368 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-12-26 | 2019-12-26 | 2020-02-13 |  | 2021-08-02 | Underground | R16 | 2021-03-31 | 1 | 36 | 295 | 89 | 418 | 2019 | 2021 | R16
162546196749 | 166825196749 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-09 | 2020-07-09 | 2020-07-09 | 2021-01-20 | 2021-04-21 | Overhead | R16 | 2021-01-20 | 1 |  | 140 | 66 | 205 | 2020 | 2021 | R16
168170192395 | 169397192395 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-28 | 2020-05-28 | 2020-05-28 | 2020-06-24 | 2020-08-28 | Overhead | R16 | 2020-06-24 | 1 |  | 20 | 48 | 67 | 2020 | 2020 | R16
169453194329 | 164393194329 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-04-28 | 2020-04-30 | 2020-06-15 | 2020-08-28 | 2020-11-02 | Overhead | R16 | 2020-08-28 | 3 | 33 | 55 | 47 | 135 | 2020 | 2020 | R16
161753175845 | 169800175845 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-12-20 | 2019-12-20 | 2020-01-06 |  | 2021-06-02 | Underground | R16 |  | 1 | 12 |  |  | 379 | 2019 | 2021 | R16
169506180077 | 168404180077 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-02-06 | 2020-02-06 | 2020-02-11 | 2020-04-15 | 2020-05-27 | Underground | R16 | 2020-04-15 | 1 | 4 | 47 | 31 | 80 | 2020 | 2020 | R16
167473191183 | 167480191183 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2020-05-15 | 2020-05-15 | 2020-05-15 |  | 2021-01-12 | Overhead | R16 | 2020-08-17 | 1 |  | 67 | 107 | 173 | 2020 | 2021 | R16
165988142632 | 168744142632 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-01-24 | 2019-01-28 | 2019-02-08 |  | 2020-06-09 | Underground | R16 |  | 3 | 10 |  |  | 359 | 2019 | 2020 | R16
166006179055 | 163448179055 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2020-01-14 | 2020-01-14 | 2020-02-03 |  | 2020-06-09 | Overhead | R16 |  | 1 | 15 |  |  | 106 | 2020 | 2020 | R16
162046183513 | 160281183513 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | R16 RESD AND NON RESD US | Commercial | 2019-12-29 | 2020-02-18 | 2020-03-09 |  | 2020-06-09 | Underground | R16 |  | 37 | 15 |  |  | 117 | 2019 | 2020 | R16
169996193934 | 161616193934 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-10 | 2020-06-10 | 2020-06-10 |  | 2021-02-17 | Underground | R16 | 2020-10-19 | 1 |  | 94 | 88 | 181 | 2020 | 2021 | R16
169849178866 | 161343178866 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-06 | 2020-01-31 | 2020-01-31 | 2020-09-02 | 2021-02-17 | Overhead | R16 | 2020-09-02 | 20 |  | 154 | 121 | 293 | 2020 | 2021 | R16
169700180385 | 169753180385 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-13 | 2020-02-13 | 2020-02-13 |  | 2021-04-21 | Overhead | R16 | 2021-01-19 | 1 |  | 244 | 67 | 310 | 2020 | 2021 | R16
163281188131 | 168913188131 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-10 | 2020-02-10 | 2020-04-18 | 2020-07-30 | 2020-07-30 | Underground | R16 | 2020-07-30 | 1 | 50 | 74 |  | 124 | 2020 | 2020 | R16
160488197152 | 164524197152 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-25 | 2020-06-25 | 2020-07-14 |  | 2022-01-12 | Overhead | R16 | 2021-12-02 | 1 | 14 | 363 | 30 | 405 | 2020 | 2022 | R16
165710217389 | 160272217389 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-04-06 | 2020-04-29 | 2021-01-14 |  | 2021-06-02 | Underground | R16 |  | 18 | 187 |  |  | 303 | 2020 | 2021 | R16
168614181009 | 169676181009 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-12 | 2020-02-12 | 2020-02-18 |  | 2020-10-06 | Underground | R16 | 2020-07-17 | 1 | 5 | 109 | 58 | 170 | 2020 | 2020 | R16
167682186941 | 163759186941 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-01-16 | 2020-01-16 | 2020-04-09 |  | 2020-07-09 | Overhead | R16 | 2020-06-02 | 1 | 61 | 39 | 28 | 126 | 2020 | 2020 | R16
163885197892 | 167791197892 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-13 | 2020-07-21 | 2020-07-21 | 2020-07-22 | 2020-10-06 | Overhead | R16 | 2020-07-22 | 7 |  | 2 | 55 | 62 | 2020 | 2020 | R16
169484194160 | 168260194160 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-20 | 2020-05-20 | 2020-06-12 |  | 2020-10-06 | Overhead | R16 |  | 1 | 18 |  |  | 100 | 2020 | 2020 | R16
167229150207 | 165119150207 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-04-24 | 2019-04-24 | 2019-04-24 |  | 2019-05-28 | Overhead | R16 | 2019-05-01 | 1 |  | 6 | 20 | 25 | 2019 | 2019 | R16
163775183869 | 165786183869 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-03-11 | 2020-03-12 | 2020-03-12 | 2020-03-26 | 2020-06-09 | Overhead | R16 | 2020-03-26 | 2 |  | 11 | 54 | 65 | 2020 | 2020 | R16
167235160413 | 169839160413 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-07-15 | 2019-07-15 | 2019-08-07 |  | 2020-12-29 | Underground | R16 |  | 1 | 18 |  |  | 382 | 2019 | 2020 | R16
168362182141 | 162932182141 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-27 | 2020-02-27 | 2020-02-27 |  | 2020-07-08 | Overhead | R16 | 2020-05-14 | 1 |  | 56 | 40 | 95 | 2020 | 2020 | R16
169789195306 | 164337195306 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-25 | 2020-06-25 | 2020-06-25 | 2020-07-13 | 2020-10-06 | Overhead | R16 | 2020-07-13 | 1 |  | 13 | 62 | 74 | 2020 | 2020 | R16
160070177779 | 160690177779 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-01-02 | 2020-01-02 | 2020-01-24 | 2020-06-22 | 2020-08-20 | Underground | R16 | 2020-06-22 | 1 | 17 | 107 | 44 | 166 | 2020 | 2020 | R16
162989193276 | 165752193276 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-06 | 2020-05-06 | 2020-06-05 | 2020-06-16 | 2020-12-09 | Overhead | R16 | 2020-06-16 | 1 | 23 | 8 | 127 | 156 | 2020 | 2020 | R16
162830177818 | 165464177818 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-23 | 2020-01-23 | 2020-01-23 |  | 2020-06-09 | Overhead | R16 | 2020-02-18 | 1 |  | 19 | 81 | 99 | 2020 | 2020 | R16
163900197351 | 167976197351 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-14 | 2020-07-14 | 2020-07-14 |  | 2020-10-06 | Overhead | R16 | 2020-07-27 | 1 |  | 10 | 52 | 61 | 2020 | 2020 | R16
167884188830 | 161553188830 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-20 | 2020-02-20 | 2020-04-24 | 2020-10-27 | 2023-06-07 | Underground | R16 | 2020-10-27 | 1 | 47 | 133 | 682 | 860 | 2020 | 2023 | R16
169577198184 | 167039198184 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-07-10 | 2020-07-10 | 2020-07-23 |  | 2021-11-18 | Overhead | R16 | 2021-10-26 | 1 | 10 | 329 | 18 | 355 | 2020 | 2021 | R16
161989175201 | 169962175201 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-26 | 2019-12-26 | 2019-12-26 | 2020-02-26 | 2020-02-26 | Overhead | R16 | 2020-02-26 | 1 |  | 45 |  | 45 | 2019 | 2020 | R16
164934192169 | 168640192169 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-22 | 2020-05-22 | 2020-05-26 | 2021-03-03 | 2021-11-08 | Overhead | R16 | 2021-03-03 | 1 | 3 | 202 | 179 | 382 | 2020 | 2021 | R16
164342188029 | 161508188029 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-13 | 2020-04-13 | 2020-04-17 |  | 2021-07-19 | Underground | R16 | 2020-11-19 | 1 | 5 | 155 | 173 | 331 | 2020 | 2021 | R16
168718243107 | 167838243107 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2021-06-29 | 2021-06-29 | 2021-08-11 |  | 2022-08-29 | Overhead | R16 |  | 1 | 32 |  |  | 305 | 2021 | 2022 | R16
165633193400 | 165690193400 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-05 | 2020-05-05 | 2020-06-05 | 2020-06-05 | 2021-11-10 | Underground | R16 | 2020-06-05 | 1 | 24 |  | 374 | 397 | 2020 | 2021 | R16
169636182201 | 162277182201 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-26 | 2020-02-27 | 2020-02-27 |  | 2020-07-08 | Overhead | R16 | 2020-05-21 | 2 |  | 61 | 35 | 96 | 2020 | 2020 | R16
160694192829 | 163501192829 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-04-23 | 2020-04-28 | 2020-06-02 | 2022-03-26 | 2022-03-29 | Underground | R16 | 2022-03-26 | 4 | 26 | 474 | 2 | 504 | 2020 | 2022 | R16
163139183768 | 165641183768 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-11 | 2020-03-11 | 2020-03-11 |  | 2020-06-16 | Underground | R16 | 2020-04-13 | 1 |  | 24 | 47 | 70 | 2020 | 2020 | R16
165685198100 | 166859198100 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-07-09 | 2020-07-09 | 2020-07-22 | 2021-02-26 | 2021-03-01 | Underground | R16 | 2021-02-26 | 1 | 10 | 158 | 2 | 168 | 2020 | 2021 | R16
167608183843 | 165642183843 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-11 | 2020-03-11 | 2020-03-11 | 2020-06-02 | 2020-07-14 | Overhead | R16 | 2020-06-02 | 1 |  | 60 | 31 | 90 | 2020 | 2020 | R16
161067196696 | 166765196696 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-08 | 2020-07-08 | 2020-07-08 | 2020-07-27 | 2023-06-08 | Overhead | R16 | 2020-07-27 | 1 |  | 14 | 749 | 762 | 2020 | 2023 | R16
163336190001 | 163694190001 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-24 | 2020-04-24 | 2020-05-04 |  | 2021-10-28 | Underground | R16 | 2020-06-04 | 1 | 7 | 24 | 366 | 395 | 2020 | 2021 | R16
169304151039 | 166756151039 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-05-02 | 2019-05-02 | 2019-05-02 |  | 2021-08-23 | Overhead | R16 | 2021-08-02 | 1 |  | 588 | 16 | 603 | 2019 | 2021 | R16
161443192921 | 162923192921 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-21 | 2020-04-21 | 2020-06-01 | 2020-08-31 | 2021-07-07 | Underground | R16 | 2020-08-31 | 1 | 30 | 66 | 223 | 317 | 2020 | 2021 | R16
169578140668 | 167332140668 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-01-15 | 2019-01-16 | 2019-01-17 |  | 2019-05-20 | Underground | R16 |  | 2 | 2 |  |  | 90 | 2019 | 2019 | R16
169868182788 | 163791182788 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-03 | 2020-03-03 | 2020-03-03 | 2020-04-14 | 2020-07-01 | Overhead | R16 | 2020-04-14 | 1 |  | 31 | 57 | 87 | 2020 | 2020 | R16
163627186576 | 166640186576 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-03-17 | 2020-03-17 | 2020-04-07 | 2020-09-03 | 2020-12-15 | Underground | R16 | 2020-09-03 | 1 | 16 | 108 | 74 | 196 | 2020 | 2020 | R16
160404196963 | 166981196963 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-09 | 2020-07-09 | 2020-07-09 | 2020-09-17 | 2020-12-29 | Overhead | R16 | 2020-09-17 | 1 |  | 51 | 74 | 124 | 2020 | 2020 | R16
169735168406 | 167324168406 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-16 | 2019-10-16 | 2019-10-16 |  | 2019-11-06 | Overhead | R16 | 2019-10-28 | 1 |  | 9 | 8 | 16 | 2019 | 2019 | R16
162797189170 | 166335189170 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-01-29 | 2020-04-06 | 2020-04-28 | 2020-07-13 | 2020-09-30 | Underground | R16 | 2020-07-13 | 49 | 17 | 55 | 58 | 176 | 2020 | 2020 | R16
169323181925 | 162166181925 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-25 | 2020-02-25 | 2020-02-25 |  | 2022-10-20 | Overhead | R16 |  | 1 |  |  |  | 693 | 2020 | 2022 | R16
164999176494 | 162773176494 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-11 | 2020-01-11 | 2020-01-11 |  | 2020-10-06 | Overhead | R16 | 2020-08-21 | 0 |  | 160 | 33 | 192 | 2020 | 2020 | R16
164485188513 | 163386188513 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-23 | 2020-04-23 | 2020-04-23 | 2020-07-13 | 2020-07-14 | Overhead | R16 | 2020-07-13 | 1 |  | 58 | 2 | 59 | 2020 | 2020 | R16
163357194185 | 161984194185 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-12 | 2020-06-12 | 2020-06-12 |  | 2020-10-06 | Overhead | R16 | 2020-07-20 | 1 |  | 27 | 57 | 83 | 2020 | 2020 | R16
163034193186 | 164358193186 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-28 | 2020-06-03 | 2020-06-03 | 2020-08-21 | 2021-03-11 | Overhead | R16 | 2020-08-21 | 27 |  | 58 | 145 | 228 | 2020 | 2021 | R16
162981186845 | 164975186845 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-22 | 2020-01-22 | 2020-04-08 |  | 2022-10-20 | Underground | R16 |  | 1 | 56 |  |  | 717 | 2020 | 2022 | R16
166703179858 | 166894179858 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-01-30 | 2020-02-10 | 2020-02-12 |  | 2020-06-09 | Overhead | R16 |  | 8 | 3 |  |  | 94 | 2020 | 2020 | R16
168165197393 | 166363197393 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2020-07-07 | 2020-07-07 | 2020-07-15 |  | 2021-01-21 | Overhead | R16 | 2020-10-14 | 1 | 7 | 66 | 72 | 143 | 2020 | 2021 | R16
161683177685 | 165005177685 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-01-22 | 2020-01-22 | 2020-01-22 |  | 2020-10-06 | Overhead | R16 | 2020-07-09 | 1 |  | 122 | 64 | 185 | 2020 | 2020 | R16
160508195219 | 162244195219 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-15 | 2020-06-15 | 2020-06-26 | 2020-09-02 | 2021-01-21 | Underground | R16 | 2020-09-02 | 1 | 10 | 49 | 102 | 159 | 2020 | 2021 | R16
169248188515 | 163500188515 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-23 | 2020-04-23 | 2020-04-23 | 2020-05-21 | 2020-05-21 | Underground | R16 | 2020-05-21 | 1 |  | 21 |  | 21 | 2020 | 2020 | R16
160562139160 | 164759139160 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-01-03 | 2019-01-03 | 2019-01-03 |  | 2019-08-26 | Underground | R16 |  | 1 |  |  |  | 168 | 2019 | 2019 | R16
162820197422 | 167714197422 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-07-13 | 2020-07-13 | 2020-07-15 |  | 2021-07-26 | Overhead | R16 | 2020-10-22 | 1 | 3 | 72 | 198 | 271 | 2020 | 2021 | R16
169106188492 | 163118188492 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-04-22 | 2020-04-22 | 2020-04-22 | 2020-05-13 | 2020-05-15 | Underground | R16 | 2020-05-13 | 1 |  | 16 | 3 | 18 | 2020 | 2020 | R16
164379199227 | 164455199227 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-29 | 2020-04-29 | 2020-07-31 | 2020-09-17 | 2020-09-18 | Underground | R16 | 2020-09-17 | 1 | 68 | 35 | 2 | 103 | 2020 | 2020 | R16
168466184494 | 167090184494 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-19 | 2020-03-19 | 2020-03-19 |  | 2020-07-09 | Overhead | R16 | 2020-06-05 | 1 |  | 57 | 25 | 81 | 2020 | 2020 | R16
166554182695 | 163632182695 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-02 | 2020-03-02 | 2020-03-02 | 2020-05-11 | 2020-05-13 | Overhead | R16 | 2020-05-11 | 1 |  | 51 | 3 | 53 | 2020 | 2020 | R16
168531195740 | 164898195740 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-29 | 2020-06-29 | 2020-06-29 |  | 2021-01-21 | Overhead | R16 | 2020-10-14 | 1 |  | 78 | 72 | 149 | 2020 | 2021 | R16
161697142380 | 167625142380 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-01-16 | 2019-02-01 | 2019-02-05 |  | 2019-08-26 | Underground | R16 |  | 13 | 3 |  |  | 159 | 2019 | 2019 | R16
164666198618 | 166353198618 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2020-07-07 | 2020-07-07 | 2020-07-29 |  | 2021-04-13 | Overhead | R16 |  | 1 | 17 |  |  | 201 | 2020 | 2021 | R16
164903212540 | 167057212540 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-03-19 | 2020-03-19 | 2020-12-02 |  | 2021-04-23 | Underground | R16 | 2021-02-03 | 1 | 185 | 46 | 58 | 287 | 2020 | 2021 | R16
168422186468 | 160195186468 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-04-06 | 2020-04-06 | 2020-04-06 |  | 2020-12-29 | Underground | R16 | 2020-09-30 | 1 |  | 128 | 65 | 192 | 2020 | 2020 | R16
164539178024 | 164590178024 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-18 | 2020-01-18 | 2020-01-24 | 2022-09-01 | 2023-10-02 | Underground | R16 | 2022-09-01 | 0 | 5 | 680 | 283 | 966 | 2020 | 2023 | R16
160537206371 | 169831206371 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-05-29 | 2020-06-01 | 2020-10-07 | 2020-10-27 | 2020-12-07 | Underground | R16 | 2020-10-27 | 2 | 93 | 15 | 30 | 137 | 2020 | 2020 | R16
163481185622 | 164842185622 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-21 | 2020-01-21 | 2020-03-27 |  | 2022-10-19 | Underground | R16 |  | 1 | 49 |  |  | 717 | 2020 | 2022 | R16
163451204178 | 164764204178 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2020-04-30 | 2020-04-30 | 2021-11-03 |  | 2021-09-14 | Underground | R16 |  | 1 | 395 |  |  | 359 | 2020 | 2021 | R16
162261190661 | 166400190661 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-11 | 2020-05-11 | 2020-05-11 |  | 2021-07-01 | Overhead | R16 | 2020-06-15 | 1 |  | 26 | 274 | 299 | 2020 | 2021 | R16
162629198976 | 164156198976 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-24 | 2020-06-30 | 2020-07-30 | 2020-10-12 | 2020-10-15 | Underground | R16 | 2020-10-12 | 5 | 23 | 53 | 4 | 82 | 2020 | 2020 | R16
162552144499 | 165502144499 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-27 | 2019-02-27 | 2019-03-01 |  | 2019-04-30 | Overhead | R16 | 2019-04-05 | 1 | 3 | 26 | 18 | 45 | 2019 | 2019 | R16
169227178591 | 163851178591 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-16 | 2020-01-30 | 2020-01-30 | 2020-02-20 | 2020-06-09 | Overhead | R16 | 2020-02-20 | 11 |  | 16 | 79 | 104 | 2020 | 2020 | R16
168897195461 | 164615195461 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-26 | 2020-06-26 | 2020-06-26 |  | 2021-05-07 | Overhead | R16 | 2021-02-24 | 1 |  | 174 | 53 | 226 | 2020 | 2021 | R16
164320191603 | 167814191603 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-19 | 2020-05-19 | 2020-05-19 |  | 2020-07-10 | Overhead | R16 | 2020-06-11 | 1 |  | 18 | 22 | 39 | 2020 | 2020 | R16
166443174692 | 169374174692 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-12-19 | 2019-12-19 | 2019-12-19 | 2020-01-14 | 2021-11-10 | Overhead | R16 | 2020-01-14 | 1 |  | 19 | 477 | 495 | 2019 | 2021 | R16
164205200083 | 165512200083 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-30 | 2020-06-30 | 2020-08-09 |  | 2021-04-16 | Underground | R16 | 2020-10-21 | 1 | 29 | 53 | 128 | 209 | 2020 | 2021 | R16
169893191819 | 168592191819 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-22 | 2020-05-22 | 2020-05-22 |  | 2020-10-06 | Overhead | R16 | 2020-07-29 | 1 |  | 49 | 50 | 98 | 2020 | 2020 | R16
163369182832 | 165893182832 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-06-24 | 2019-06-24 | 2020-03-04 |  | 2020-06-09 | Overhead | R16 |  | 1 | 183 |  |  | 252 | 2019 | 2020 | R16
165683217374 | 162434217374 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-06-16 | 2020-11-05 | 2021-01-15 | 2021-04-23 | 2021-06-02 | Underground | R16 | 2021-04-23 | 103 | 52 | 71 | 29 | 252 | 2020 | 2021 | R16
163393172775 | 162568172775 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-11 | 2019-11-13 | 2019-11-25 |  | 2020-01-03 | Overhead | R16 |  | 3 | 9 |  |  | 40 | 2019 | 2020 | R16
163393179130 | 163231179130 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-14 | 2020-01-23 | 2020-02-04 |  | 2023-10-06 | Overhead | R16 |  | 8 | 9 |  |  | 974 | 2020 | 2023 | R16
162418196381 | 165958196381 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-02 | 2020-07-02 | 2020-07-02 | 2021-09-15 | 2021-11-08 | Overhead | R16 | 2021-09-15 | 1 |  | 315 | 39 | 353 | 2020 | 2021 | R16
168801222131 | 165013222131 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-03-09 | 2021-02-12 | 2021-03-01 |  | 2022-01-24 | Overhead | R16 | 2021-12-27 | 245 | 12 | 216 | 21 | 491 | 2020 | 2022 | R16
163393285747 | 166077285747 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-13 | 2022-07-13 | 2022-07-15 |  | 2023-03-17 | Overhead | R16 |  | 1 | 3 |  |  | 178 | 2022 | 2023 | R16
164981189550 | 165000189550 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2020-05-01 | 2020-05-01 | 2020-05-01 |  | 2021-04-07 | Overhead | R16 | 2020-12-02 | 1 |  | 154 | 91 | 244 | 2020 | 2021 | R16
166666187200 | 160604187200 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-04-07 | 2020-04-08 | 2020-04-11 |  | 2020-08-20 | Overhead | R16 | 2020-06-24 | 2 | 3 | 53 | 42 | 98 | 2020 | 2020 | R16
163393299703 | 168720299703 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-21 | 2022-11-01 | 2022-11-07 |  | 2023-02-03 | Overhead | R16 |  | 8 | 5 |  |  | 76 | 2022 | 2023 | R16
162275174514 | 168923174514 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-17 | 2019-12-17 | 2019-12-17 |  | 2020-07-09 | Overhead | R16 | 2020-06-01 | 1 |  | 120 | 29 | 148 | 2019 | 2020 | R16
167398188141 | 167837188141 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-24 | 2020-03-24 | 2020-04-17 | 2020-04-20 | 2020-07-08 | Underground | R16 | 2020-04-20 | 1 | 19 | 2 | 58 | 77 | 2020 | 2020 | R16
160078200042 | 165589200042 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-01-24 | 2020-04-27 | 2020-08-07 | 2021-03-26 | 2021-06-02 | Underground | R16 | 2021-03-26 | 67 | 75 | 166 | 49 | 354 | 2020 | 2021 | R16
167900276416 | 160496276416 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-06-04 | 2020-07-02 | 2022-04-20 | 2023-01-05 | 2023-01-05 | Underground | R16 | 2023-01-05 | 21 | 470 | 187 |  | 676 | 2020 | 2023 | R16
163405162421 | 167374162421 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-08-26 | 2019-08-26 | 2019-08-26 |  | 2019-11-14 | Overhead | R16 | 2019-11-07 | 1 |  | 54 | 6 | 59 | 2019 | 2019 | R16
169324178207 | 161497178207 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-01-06 | 2020-01-06 | 2020-01-27 |  | 2020-06-29 | Overhead | R16 |  | 1 | 16 |  |  | 126 | 2020 | 2020 | R16
165661191123 | 167296191123 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-15 | 2020-05-15 | 2020-05-15 |  | 2020-10-06 | Overhead | R16 | 2020-07-24 | 1 |  | 51 | 53 | 103 | 2020 | 2020 | R16
164733178532 | 166499178532 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-29 | 2020-01-29 | 2020-01-29 |  | 2020-08-28 | Overhead | R16 | 2020-06-29 | 1 |  | 109 | 45 | 153 | 2020 | 2020 | R16
167509186693 | 160547186693 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-07 | 2020-04-07 | 2020-04-07 |  | 2020-10-06 | Overhead | R16 | 2020-06-05 | 1 |  | 44 | 88 | 131 | 2020 | 2020 | R16
168576193085 | 160360193085 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-03 | 2020-06-03 | 2020-06-03 | 2020-06-24 | 2020-06-26 | Overhead | R16 | 2020-06-24 | 1 |  | 16 | 3 | 18 | 2020 | 2020 | R16
163446179296 | 167698179296 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-02-04 | 2020-02-04 | 2020-02-04 |  | 2020-07-02 | Underground | R16 | 2020-05-05 | 1 |  | 66 | 43 | 108 | 2020 | 2020 | R16
169125180343 | 169680180343 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-12 | 2020-02-12 | 2020-02-12 |  | 2021-11-10 | Underground | R16 | 2020-04-16 | 1 |  | 47 | 410 | 456 | 2020 | 2021 | R16
162955192272 | 169065192272 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-26 | 2020-05-26 | 2020-05-26 |  | 2022-10-17 | Overhead | R16 |  | 1 |  |  |  | 625 | 2020 | 2022 | R16
166847185559 | 168686185559 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-03-27 | 2020-03-27 | 2020-03-27 |  | 2021-11-09 | Overhead | R16 | 2021-10-12 | 1 |  | 403 | 21 | 423 | 2020 | 2021 | R16
163045196780 | 165538196780 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-06-30 | 2020-07-01 | 2020-07-08 |  | 2020-10-06 | Overhead | R16 |  | 2 | 6 |  |  | 71 | 2020 | 2020 | R16
162662190242 | 163372190242 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-01 | 2020-03-01 | 2020-05-06 |  | 2020-11-06 | Underground | R16 | 2020-07-10 | 0 | 48 | 48 | 86 | 180 | 2020 | 2020 | R16
167659191779 | 168277191779 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-25 | 2020-03-25 | 2020-05-22 |  | 2021-01-22 | Underground | R16 | 2020-07-28 | 1 | 43 | 48 | 129 | 218 | 2020 | 2021 | R16
161987190289 | 165858190289 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-07 | 2020-05-07 | 2020-05-07 | 2020-07-07 | 2020-10-06 | Overhead | R16 | 2020-07-07 | 1 |  | 44 | 66 | 109 | 2020 | 2020 | R16
167446183073 | 160075183073 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-12-26 | 2019-12-26 | 2020-03-05 | 2020-03-06 | 2020-09-23 | Underground | R16 | 2020-03-06 | 1 | 51 | 2 | 144 | 195 | 2019 | 2020 | R16
164594184705 | 166985184705 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-18 | 2020-03-19 | 2020-03-19 |  | 2020-07-01 | Overhead | R16 | 2020-04-29 | 2 |  | 30 | 46 | 76 | 2020 | 2020 | R16
163457182885 | 163306182885 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-15 | 2020-01-15 | 2020-03-04 |  | 2021-06-30 | Overhead | R16 | 2021-06-30 | 1 | 36 | 346 |  | 381 | 2020 | 2021 | R16
168933214257 | 169852214257 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-23 | 2020-12-17 | 2020-12-17 | 2021-07-29 | 2021-09-07 | Overhead | R16 | 2021-07-29 | 259 |  | 161 | 29 | 447 | 2019 | 2021 | R16
165091200572 | 164568200572 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-03-06 | 2020-07-23 | 2020-08-13 |  | 2021-09-13 | Underground | R16 |  | 100 | 16 |  |  | 397 | 2020 | 2021 | R16
165296182791 | 169552182791 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-12 | 2020-02-12 | 2020-03-03 | 2020-04-10 | 2021-11-03 | Underground | R16 | 2020-04-10 | 1 | 15 | 29 | 409 | 451 | 2020 | 2021 | R16
166536185803 | 168913185803 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-03-30 | 2020-03-30 | 2020-03-30 |  | 2021-01-20 | Overhead | R16 | 2020-10-09 | 1 |  | 140 | 74 | 213 | 2020 | 2021 | R16
160589183826 | 166229183826 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-01-28 | 2020-01-28 | 2020-03-11 |  | 2020-07-01 | Overhead | R16 |  | 1 | 32 |  |  | 112 | 2020 | 2020 | R16
168174182909 | 163999182909 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-04 | 2020-03-04 | 2020-03-04 |  | 2021-11-10 | Overhead | R16 | 2020-04-08 | 1 |  | 26 | 416 | 441 | 2020 | 2021 | R16
166489189177 | 164287189177 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-28 | 2020-04-28 | 2020-04-28 | 2020-05-20 | 2020-05-22 | Overhead | R16 | 2020-05-20 | 1 |  | 17 | 3 | 19 | 2020 | 2020 | R16
161181196733 | 166575196733 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2020-07-08 | 2020-07-08 | 2020-07-08 |  | 2021-07-14 | Overhead | R16 | 2020-11-20 | 1 |  | 98 | 169 | 266 | 2020 | 2021 | R16
164572198683 | 165292198683 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-03-10 | 2020-03-10 | 2020-07-27 |  | 2023-10-18 | Underground | R16 |  | 1 | 100 |  |  | 942 | 2020 | 2023 | R16
164981179284 | 167517179284 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-03 | 2020-02-03 | 2020-02-03 |  | 2020-06-09 | Overhead | R16 | 2020-03-19 | 1 |  | 34 | 59 | 92 | 2020 | 2020 | R16
163970201227 | 167973201227 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-13 | 2020-08-18 | 2020-08-20 | 2020-12-04 | 2021-04-16 | Underground | R16 | 2020-12-04 | 27 | 3 | 77 | 96 | 200 | 2020 | 2021 | R16
163131188327 | 164986188327 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-09 | 2020-03-09 | 2020-04-20 | 2020-05-13 | 2020-05-14 | Underground | R16 | 2020-05-13 | 1 | 31 | 18 | 2 | 49 | 2020 | 2020 | R16
161061195264 | 164092195264 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2020-06-24 | 2020-06-24 | 2020-06-24 |  | 2021-04-07 | Overhead | R16 | 2020-12-01 | 1 |  | 115 | 92 | 206 | 2020 | 2021 | R16
164214196935 | 167367196935 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-13 | 2020-07-13 | 2020-07-13 |  | 2020-10-06 | Overhead | R16 | 2020-07-17 | 1 |  | 5 | 58 | 62 | 2020 | 2020 | R16
168701186539 | 160370186539 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-06 | 2020-04-06 | 2020-04-06 |  | 2020-06-29 | Overhead | R16 | 2020-04-23 | 1 |  | 14 | 48 | 61 | 2020 | 2020 | R16
169912194005 | 160427194005 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-04 | 2020-06-04 | 2020-06-11 |  | 2020-10-06 | Underground | R16 | 2020-07-14 | 1 | 6 | 24 | 61 | 89 | 2020 | 2020 | R16
166353209572 | 160075209572 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-23 | 2020-10-30 | 2020-11-04 |  | 2021-11-08 | Overhead | R16 |  | 6 | 4 |  |  | 272 | 2020 | 2021 | R16
168298198974 | 169438198974 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-28 | 2020-05-28 | 2020-07-30 | 2020-09-23 | 2020-09-24 | Underground | R16 | 2020-09-23 | 1 | 46 | 40 | 2 | 86 | 2020 | 2020 | R16
168171177638 | 164133177638 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-17 | 2020-01-22 | 2020-01-22 | 2020-02-26 | 2020-02-27 | Overhead | R16 | 2020-02-26 | 4 |  | 26 | 2 | 30 | 2020 | 2020 | R16
169207230241 | 164922230241 | NON-RESIDENTIAL - WAREHOUSE | R16 RESD AND NON RESD US | Commercial | 2020-06-29 | 2021-04-28 | 2021-05-10 | 2022-04-18 | 2022-05-18 | Underground | R16 | 2022-04-18 | 218 | 9 | 246 | 23 | 493 | 2020 | 2022 | R16
165175194631 | 166083194631 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-08 | 2020-05-08 | 2020-06-18 | 2020-07-17 | 2020-07-20 | Underground | R16 | 2020-07-17 | 1 | 30 | 22 | 2 | 52 | 2020 | 2020 | R16
160869202549 | 162307202549 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-15 | 2020-07-25 | 2020-09-02 |  | 2021-04-07 | Overhead | R16 |  | 30 | 28 |  |  | 213 | 2020 | 2021 | R16
162399188504 | 162521188504 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-17 | 2020-04-21 | 2020-04-21 |  | 2020-07-01 | Overhead | R16 | 2020-04-27 | 3 |  | 5 | 48 | 54 | 2020 | 2020 | R16
169717175563 | 169012175563 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-12-17 | 2019-12-17 | 2020-01-02 | 2020-03-21 | 2020-03-23 | Underground | R16 | 2020-03-21 | 1 | 13 | 57 | 1 | 70 | 2019 | 2020 | R16
162243196286 | 165940196286 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-07-02 | 2020-07-02 | 2020-07-02 |  | 2021-11-02 | Underground | R16 | 2021-06-15 | 1 |  | 249 | 101 | 349 | 2020 | 2021 | R16
167125200153 | 168349200153 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-02-06 | 2020-02-06 | 2020-08-11 | 2021-04-01 | 2021-11-05 | Underground | R16 | 2021-04-01 | 1 | 134 | 168 | 157 | 457 | 2020 | 2021 | R16
161188178126 | 164733178126 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-01-21 | 2020-01-21 | 2020-01-27 |  | 2021-07-24 | Underground | R16 | 2020-11-06 | 1 | 5 | 205 | 186 | 394 | 2020 | 2021 | R16
168675236014 | 163223236014 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-06-18 | 2021-06-09 | 2021-06-22 |  | 2021-11-10 | Overhead | R16 |  | 255 | 10 |  |  | 365 | 2020 | 2021 | R16
165904187560 | 161712187560 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-14 | 2020-04-14 | 2020-04-14 | 2021-08-09 | 2021-08-10 | Overhead | R16 | 2021-08-09 | 1 |  | 345 | 2 | 346 | 2020 | 2021 | R16
168454176958 | 162609176958 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-01-10 | 2020-01-10 | 2020-01-15 |  | 2020-06-09 | Overhead | R16 | 2020-02-06 | 1 | 4 | 17 | 89 | 108 | 2020 | 2020 | R16
163236208915 | 164193208915 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-01-17 | 2020-02-05 | 2020-10-28 |  | 2021-04-13 | Underground | R16 |  | 14 | 191 |  |  | 323 | 2020 | 2021 | R16
165455184041 | 168261184041 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-02-05 | 2020-02-05 | 2020-03-13 | 2022-12-22 | 2022-12-22 | Underground | R16 | 2022-12-22 | 1 | 28 | 725 |  | 752 | 2020 | 2022 | R16
168910196408 | 162515196408 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-01-09 | 2020-01-09 | 2020-07-03 | 2021-09-30 | 2021-09-30 | Underground | R16 | 2021-09-30 | 1 | 127 | 325 |  | 451 | 2020 | 2021 | R16
161828202702 | 167727202702 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-13 | 2020-07-30 | 2020-09-03 |  | 2021-07-24 | Underground | R16 |  | 14 | 26 |  |  | 270 | 2020 | 2021 | R16
167696304958 | 160228304958 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-04-06 | 2020-04-10 | 2023-01-30 | 2023-02-14 | 2023-02-06 | Overhead | R16 | 2023-02-14 | 5 | 732 | 12 |  | 741 | 2020 | 2023 | R16
167330176418 | 169286176418 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-19 | 2020-01-11 | 2020-01-11 |  | 2020-06-09 | Overhead | R16 | 2020-04-02 | 17 |  | 59 | 49 | 124 | 2019 | 2020 | R16
160162178861 | 167016178861 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-31 | 2020-01-31 | 2020-01-31 | 2020-03-13 | 2020-06-09 | Overhead | R16 | 2020-03-13 | 1 |  | 31 | 63 | 93 | 2020 | 2020 | R16
161058178829 | 166947178829 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-31 | 2020-01-31 | 2020-01-31 | 2020-02-25 | 2020-02-26 | Overhead | R16 | 2020-02-25 | 1 |  | 18 | 2 | 19 | 2020 | 2020 | R16
167652194388 | 167632194388 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-18 | 2020-05-18 | 2020-06-16 |  | 2020-10-06 | Underground | R16 | 2020-08-17 | 1 | 22 | 45 | 37 | 102 | 2020 | 2020 | R16
166800208613 | 168609208613 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2020-05-22 | 2020-05-22 | 2020-10-28 |  | 2021-07-19 | Underground | R16 | 2020-11-10 | 1 | 114 | 10 | 180 | 302 | 2020 | 2021 | R16
167940144764 | 166041144764 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-04 | 2019-03-04 | 2019-03-04 |  | 2019-04-24 | Underground | R16 | 2019-03-20 | 1 |  | 13 | 26 | 38 | 2019 | 2019 | R16
164340177716 | 164191177716 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-01-17 | 2020-01-17 | 2020-01-22 | 2020-09-02 | 2020-09-03 | Overhead | R16 | 2020-09-02 | 1 | 4 | 161 | 2 | 165 | 2020 | 2020 | R16
161280192832 | 162020192832 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-04-15 | 2020-04-15 | 2020-06-02 |  | 2021-08-12 | Underground | R16 | 2021-07-09 | 1 | 35 | 289 | 25 | 347 | 2020 | 2021 | R16
165919186862 | 160516186862 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-04-08 | 2020-04-08 | 2020-04-08 |  | 2021-04-16 | Underground | R16 | 2020-12-30 | 1 |  | 191 | 78 | 268 | 2020 | 2021 | R16
162430181277 | 168668181277 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-02-07 | 2020-02-21 | 2020-02-21 |  | 2020-06-09 | Overhead | R16 |  | 11 |  |  |  | 88 | 2020 | 2020 | R16
162931185248 | 167894185248 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-24 | 2020-03-24 | 2020-03-24 | 2020-04-21 | 2020-07-02 | Overhead | R16 | 2020-04-21 | 1 |  | 21 | 53 | 73 | 2020 | 2020 | R16
168463192781 | 169984192781 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-01 | 2020-06-01 | 2020-06-01 |  | 2020-08-20 | Underground | R16 | 2020-06-24 | 1 |  | 18 | 42 | 59 | 2020 | 2020 | R16
163632204637 | 164959204637 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-06-29 | 2020-06-30 | 2020-09-22 |  | 2021-08-06 | Underground | R16 | 2021-08-06 | 2 | 61 | 229 |  | 290 | 2020 | 2021 | R16
167441198505 | 160563198505 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-06-04 | 2020-06-08 | 2020-07-27 |  | 2021-06-03 | Overhead | R16 | 2021-03-09 | 3 | 36 | 162 | 63 | 261 | 2020 | 2021 | R16
162504186818 | 160860186818 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2020-04-09 | 2020-04-09 | 2020-04-09 | 2021-02-02 | 2021-04-20 | Underground | R16 | 2021-02-02 | 1 |  | 214 | 56 | 269 | 2020 | 2021 | R16
160324177640 | 160518177640 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-31 | 2020-01-16 | 2020-01-21 | 2020-03-09 | 2020-06-09 | Overhead | R16 | 2020-03-09 | 13 | 4 | 35 | 67 | 116 | 2019 | 2020 | R16
162467263079 | 166566263079 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-07-08 | 2020-07-08 | 2022-01-01 |  | 2023-01-10 | Underground | R16 |  | 1 | 388 |  |  | 655 | 2020 | 2023 | R16
163382198863 | 160212198863 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-02 | 2020-06-02 | 2020-07-29 | 2020-12-16 | 2021-04-21 | Overhead | R16 | 2020-12-16 | 1 | 42 | 101 | 91 | 232 | 2020 | 2021 | R16
161074186919 | 161193186919 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-02-20 | 2020-02-20 | 2020-04-10 | 2023-12-21 | 2023-12-21 | Underground | R16 | 2023-12-21 | 1 | 37 | 965 |  | 1001 | 2020 | 2023 | R16
164883186511 | 166808186511 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-17 | 2020-03-24 | 2020-04-06 |  | 2020-07-09 | Underground | R16 | 2020-06-08 | 6 | 10 | 46 | 24 | 83 | 2020 | 2020 | R16
161318199683 | 166185199683 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-07-06 | 2020-07-17 | 2020-08-04 | 2021-03-16 | 2021-05-26 | Underground | R16 | 2021-03-16 | 10 | 13 | 161 | 52 | 233 | 2020 | 2021 | R16
169762181859 | 160767181859 | NON-RESIDENTIAL - SMALL RETAIL | OH R16 RES NON RES OS | Commercial | 2020-02-18 | 2020-02-23 | 2020-02-26 |  | 2021-08-16 | Overhead | R16 |  | 4 | 3 |  |  | 390 | 2020 | 2021 | R16
169221196815 | 167106196815 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-10 | 2020-07-10 | 2020-07-10 | 2021-03-19 | 2021-06-30 | Overhead | R16 | 2021-03-19 | 1 |  | 181 | 74 | 254 | 2020 | 2021 | R16
169727193486 | 165321193486 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH CP R16 WORK RELO TO UG | Commercial | 2020-03-10 | 2020-03-10 | 2020-06-08 | 2020-08-28 | 2020-11-25 | Overhead | R16 | 2020-08-28 | 1 | 65 | 60 | 64 | 187 | 2020 | 2020 | R16
165292182058 | 162755182058 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-26 | 2020-02-26 | 2020-02-26 | 2020-05-21 | 2020-05-22 | Overhead | R16 | 2020-05-21 | 1 |  | 62 | 2 | 63 | 2020 | 2020 | R16
169424182882 | 163928182882 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-03 | 2020-03-03 | 2020-03-03 | 2020-06-04 | 2020-06-05 | Overhead | R16 | 2020-06-04 | 1 |  | 68 | 2 | 69 | 2020 | 2020 | R16
166703201943 | 167113201943 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2020-03-19 | 2020-03-24 | 2020-08-26 |  | 2021-10-25 | Underground | R16 |  | 4 | 112 |  |  | 418 | 2020 | 2021 | R16
169669225406 | 161911225406 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-06-11 | 2020-10-26 | 2021-03-31 |  | 2023-03-14 | Underground | R16 |  | 98 | 113 |  |  | 719 | 2020 | 2023 | R16
169084158966 | 160882158966 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-18 | 2019-07-18 | 2019-07-24 |  | 2019-09-24 | Underground | R16 |  | 1 | 5 |  |  | 49 | 2019 | 2019 | R16
167985191803 | 168203191803 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-20 | 2020-05-21 | 2020-05-21 |  | 2020-07-09 | Overhead | R16 | 2020-06-01 | 2 |  | 8 | 29 | 37 | 2020 | 2020 | R16
165621185551 | 168496185551 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-27 | 2020-03-27 | 2020-03-27 | 2020-04-28 | 2020-04-29 | Overhead | R16 | 2020-04-28 | 1 |  | 23 | 2 | 24 | 2020 | 2020 | R16
169101164032 | 168239164032 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-29 | 2019-09-09 | 2019-09-10 |  | 2019-10-16 | Overhead | R16 |  | 8 | 2 |  |  | 35 | 2019 | 2019 | R16
169101219060 | 169780219060 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-09 | 2021-01-20 | 2021-01-29 |  | 2021-06-03 | Overhead | R16 |  | 31 | 8 |  |  | 127 | 2020 | 2021 | R16
160806189981 | 162489189981 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-02-26 | 2020-05-04 | 2020-05-04 | 2020-08-05 | 2020-08-11 | Underground | R16 | 2020-08-05 | 49 |  | 68 | 5 | 120 | 2020 | 2020 | R16
169101246363 | 162072246363 | CUSTOMER UPGRADE IN SERVICE | UG SVC CONVERSION | Residential | 2021-08-30 | 2021-08-30 | 2021-09-02 |  | 2022-03-28 | Underground | R16 |  | 1 | 4 |  |  | 151 | 2021 | 2022 | R16
164593185984 | 169139185984 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-31 | 2020-03-31 | 2020-03-31 |  | 2020-08-28 | Overhead | R16 | 2020-07-02 | 1 |  | 68 | 42 | 109 | 2020 | 2020 | R16
166722198973 | 168220198973 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-20 | 2020-05-29 | 2020-07-30 | 2020-12-14 | 2020-12-18 | Underground | R16 | 2020-12-14 | 8 | 45 | 98 | 5 | 153 | 2020 | 2020 | R16
162155177887 | 165246177887 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-22 | 2020-01-22 | 2020-01-23 |  | 2020-06-09 | Overhead | R16 | 2020-04-03 | 1 | 2 | 52 | 48 | 100 | 2020 | 2020 | R16
162396179346 | 167812179346 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-04 | 2020-02-04 | 2020-02-04 | 2020-12-07 | 2021-04-14 | Overhead | R16 | 2020-12-07 | 1 |  | 220 | 93 | 312 | 2020 | 2021 | R16
168765190064 | 165468190064 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2020-05-05 | 2020-05-05 | 2020-05-05 |  | 2020-07-09 | Underground | R16 | 2020-05-28 | 1 |  | 18 | 31 | 48 | 2020 | 2020 | R16
169353144959 | 160291144959 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-01-30 | 2019-01-30 | 2019-03-07 |  | 2019-05-28 | Overhead | R16 |  | 1 | 27 |  |  | 85 | 2019 | 2019 | R16
164289201250 | 164975201250 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2020-06-29 | 2020-06-29 | 2020-08-21 | 2020-11-19 | 2021-02-08 | Overhead | R16 | 2020-11-19 | 1 | 40 | 65 | 58 | 161 | 2020 | 2021 | R16
166912180987 | 167623180987 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-04 | 2020-02-04 | 2020-02-18 | 2023-01-20 | 2023-07-23 | Underground | R16 | 2023-01-20 | 1 | 11 | 764 | 131 | 904 | 2020 | 2023 | R16
160876201266 | 160886201266 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-08 | 2020-06-08 | 2020-08-20 |  | 2022-10-20 | Underground | R16 |  | 1 | 54 |  |  | 619 | 2020 | 2022 | R16
163207188750 | 163297188750 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-22 | 2020-04-22 | 2020-04-22 |  | 2020-07-01 | Overhead | R16 | 2020-04-27 | 1 |  | 4 | 48 | 51 | 2020 | 2020 | R16
167143193390 | 167802193390 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-03-24 | 2020-03-24 | 2020-06-05 |  | 2020-10-06 | Overhead | R16 | 2020-07-20 | 1 | 54 | 32 | 57 | 141 | 2020 | 2020 | R16
167129184726 | 165584184726 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-01-23 | 2020-01-23 | 2020-03-19 |  | 2021-04-29 | Underground | R16 |  | 1 | 41 |  |  | 331 | 2020 | 2021 | R16
169423195002 | 169537195002 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-29 | 2020-05-29 | 2020-06-22 |  | 2020-10-06 | Underground | R16 | 2020-07-16 | 1 | 17 | 19 | 59 | 93 | 2020 | 2020 | R16
165552192517 | 169627192517 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-29 | 2020-05-29 | 2020-05-29 |  | 2020-08-28 | Overhead | R16 | 2020-06-26 | 1 |  | 21 | 46 | 66 | 2020 | 2020 | R16
168124193651 | 161137193651 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-08 | 2020-06-08 | 2020-06-08 | 2020-07-27 | 2020-12-18 | Overhead | R16 | 2020-07-27 | 1 |  | 36 | 105 | 140 | 2020 | 2020 | R16
164244190193 | 165731190193 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-06 | 2020-05-06 | 2020-05-06 |  | 2020-07-10 | Overhead | R16 | 2020-06-10 | 1 |  | 26 | 23 | 48 | 2020 | 2020 | R16
161721177296 | 162557177296 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-01-10 | 2020-01-15 | 2020-01-17 |  | 2020-06-09 | Overhead | R16 |  | 4 | 3 |  |  | 108 | 2020 | 2020 | R16
163826247871 | 168958247871 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-05-26 | 2021-08-12 | 2021-09-15 |  | 2023-06-20 | Underground | R16 |  | 318 | 25 |  |  | 801 | 2020 | 2023 | R16
160353150705 | 165862150705 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-28 | 2019-04-28 | 2019-04-29 |  | 2019-08-26 | Overhead | R16 | 2019-07-30 | 0 | 1 | 67 | 20 | 86 | 2019 | 2019 | R16
165300188534 | 164324188534 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-05 | 2020-03-05 | 2020-04-22 |  | 2020-07-01 | Overhead | R16 | 2020-04-27 | 1 | 35 | 4 | 48 | 85 | 2020 | 2020 | R16
167807193190 | 168818193190 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-02-10 | 2020-02-10 | 2020-06-04 |  | 2023-07-28 | Underground | R16 | 2023-07-18 | 1 | 84 | 814 | 9 | 905 | 2020 | 2023 | R16
160379159514 | 163242159514 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-08-01 | 2019-08-01 | 2019-08-01 |  | 2021-01-08 | Underground | R16 |  | 1 |  |  |  | 377 | 2019 | 2021 | R16
161564195703 | 164769195703 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2022-10-24 | 2023-01-05 | Overhead | R16 | 2022-10-24 | 1 |  | 606 | 54 | 659 | 2020 | 2023 | R16
160392161874 | 160418161874 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-03-28 | 2019-04-03 | 2019-08-21 |  | 2021-11-08 | Underground | R16 |  | 5 | 101 |  |  | 683 | 2019 | 2021 | R16
164360204749 | 165935204749 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-02 | 2020-09-25 | 2020-09-25 | 2020-11-24 | 2021-02-26 | Overhead | R16 | 2020-11-24 | 62 |  | 43 | 69 | 172 | 2020 | 2021 | R16
160392169314 | 160403169314 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential Subdivision | 2019-09-11 | 2019-09-11 | 2019-10-24 |  | 2021-07-24 | Underground | R16 |  | 1 | 32 |  |  | 488 | 2019 | 2021 | R16
166795178745 | 166729178745 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-30 | 2020-01-30 | 2020-01-30 |  | 2022-10-19 | Overhead | R16 |  | 1 |  |  |  | 710 | 2020 | 2022 | R16
168493185916 | 167901185916 | NON-RESIDENTIAL - LARGE OFFICE | R16 RESD AND NON RESD US | Commercial | 2020-03-24 | 2020-03-24 | 2020-03-31 | 2021-05-24 | 2021-11-02 | Underground | R16 | 2021-05-24 | 1 | 6 | 300 | 117 | 421 | 2020 | 2021 | R16
163652203509 | 161962203509 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-04-15 | 2020-07-01 | 2020-09-10 | 2020-12-01 | 2021-03-27 | Underground | R16 | 2020-12-01 | 56 | 52 | 59 | 84 | 248 | 2020 | 2021 | R16
169571209637 | 169594209637 | INDUSTRIAL | UG R16 RESD AND NON RESD UD | Commercial | 2020-05-28 | 2020-07-02 | 2020-11-05 | 2022-04-21 | 2022-05-04 | Underground | R16 | 2022-04-21 | 26 | 91 | 381 | 10 | 505 | 2020 | 2022 | R16
160392171245 | 162134171245 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-11-08 | 2019-11-08 | 2019-11-08 |  | 2021-12-08 | Underground | R16 |  | 1 |  |  |  | 544 | 2019 | 2021 | R16
168217189630 | 168245189630 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-02-05 | 2020-02-05 | 2020-05-01 | 2022-11-18 | 2022-11-21 | Underground | R16 | 2022-11-18 | 1 | 63 | 666 | 2 | 729 | 2020 | 2022 | R16
161733199233 | 161735199233 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-11 | 2020-06-11 | 2020-08-03 |  | 2020-10-06 | Underground | R16 | 2020-10-06 | 1 | 38 | 47 |  | 84 | 2020 | 2020 | R16
165722180753 | 160526180753 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-14 | 2020-02-14 | 2020-02-14 |  | 2020-10-06 | Overhead | R16 | 2020-08-07 | 1 |  | 126 | 43 | 168 | 2020 | 2020 | R16
160392182340 | 167450182340 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential Subdivision | 2020-02-03 | 2020-02-03 | 2020-02-28 |  | 2021-08-26 | Underground | R16 |  | 1 | 20 |  |  | 409 | 2020 | 2021 | R16
160392205968 | 165187205968 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential Subdivision | 2020-10-01 | 2020-10-01 | 2020-10-01 |  | 2021-11-08 | Underground | R16 |  | 1 |  |  |  | 288 | 2020 | 2021 | R16
168413183663 | 164815183663 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-03-09 | 2020-03-09 | 2020-03-10 | 2020-11-03 | 2023-06-07 | Underground | R16 | 2020-11-03 | 1 | 2 | 171 | 677 | 848 | 2020 | 2023 | R16
169781193957 | 162102193957 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-12 | 2020-06-12 | 2020-06-12 | 2020-08-11 | 2020-10-06 | Overhead | R16 | 2020-08-11 | 1 |  | 43 | 41 | 83 | 2020 | 2020 | R16
167040201600 | 161261201600 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-10 | 2020-04-10 | 2020-08-24 |  | 2021-07-26 | Overhead | R16 | 2020-11-02 | 1 | 97 | 51 | 191 | 337 | 2020 | 2021 | R16
167662193229 | 160724193229 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-05 | 2020-06-05 | 2020-06-05 | 2021-01-19 | 2023-06-07 | Overhead | R16 | 2021-01-19 | 1 |  | 163 | 622 | 784 | 2020 | 2023 | R16
169918195090 | 163853195090 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-23 | 2020-06-23 | 2020-06-23 |  | 2021-04-29 | Overhead | R16 | 2021-02-08 | 1 |  | 165 | 59 | 223 | 2020 | 2021 | R16
168487183845 | 165672183845 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-03-11 | 2020-03-11 | 2020-03-11 |  | 2020-10-06 | Overhead | R16 |  | 1 |  |  |  | 150 | 2020 | 2020 | R16
166546182833 | 164070182833 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-04 | 2020-03-04 | 2020-03-04 | 2020-06-24 | 2020-06-26 | Overhead | R16 | 2020-06-24 | 1 |  | 81 | 3 | 83 | 2020 | 2020 | R16
169061182940 | 162058182940 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2020-01-08 | 2020-02-13 | 2020-03-04 | 2020-05-04 | 2020-12-21 | Underground | R16 | 2020-05-04 | 27 | 15 | 44 | 166 | 249 | 2020 | 2020 | R16
160894148738 | 160209148738 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-03-28 | 2019-03-28 | 2019-04-11 |  | 2020-07-09 | Underground | R16 | 2020-06-03 | 1 | 11 | 300 | 27 | 336 | 2019 | 2020 | R16
165856188715 | 163283188715 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-22 | 2020-04-22 | 2020-04-22 |  | 2020-07-02 | Overhead | R16 | 2020-05-04 | 1 |  | 9 | 44 | 52 | 2020 | 2020 | R16
167946199632 | 169550199632 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-28 | 2020-05-28 | 2020-08-05 |  | 2020-10-06 | Underground | R16 | 2020-08-20 | 1 | 50 | 12 | 34 | 94 | 2020 | 2020 | R16
164343194094 | 160438194094 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-08 | 2020-04-08 | 2020-06-12 |  | 2021-07-14 | Overhead | R16 | 2020-11-20 | 1 | 48 | 116 | 169 | 331 | 2020 | 2021 | R16
160138200558 | 161315200558 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-09 | 2020-06-19 | 2020-08-17 | 2020-10-06 | 2020-10-06 | Underground | R16 | 2020-10-06 | 9 | 42 | 37 |  | 86 | 2020 | 2020 | R16
163596175395 | 160964175395 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-01-02 | 2020-01-02 | 2020-01-03 | 2021-03-08 | 2021-04-09 | Overhead | R16 | 2021-03-08 | 1 | 2 | 307 | 25 | 332 | 2020 | 2021 | R16
166598181383 | 161336181383 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-20 | 2020-02-20 | 2020-02-20 | 2020-03-30 | 2020-03-30 | Overhead | R16 | 2020-03-30 | 1 |  | 28 |  | 28 | 2020 | 2020 | R16
160192181685 | 160826181685 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2020-02-19 | 2020-02-20 | 2020-02-24 |  | 2020-07-01 | Underground | R16 | 2020-05-01 | 2 | 3 | 50 | 44 | 96 | 2020 | 2020 | R16
169385180746 | 160197180746 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-27 | 2019-12-27 | 2020-02-14 |  | 2021-04-14 | Underground | R16 | 2020-12-09 | 1 | 36 | 214 | 91 | 339 | 2019 | 2021 | R16
163431193892 | 163334193892 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-23 | 2020-04-23 | 2020-06-10 |  | 2020-10-06 | Underground | R16 | 2020-07-09 | 1 | 35 | 22 | 64 | 119 | 2020 | 2020 | R16
169391186706 | 165434186706 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-03-11 | 2020-03-11 | 2020-04-07 |  | 2020-08-20 | Overhead | R16 | 2020-06-24 | 1 | 20 | 57 | 42 | 117 | 2020 | 2020 | R16
167821309652 | 161198309652 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-17 | 2023-02-17 | 2023-02-17 | 2023-02-22 | 2023-05-26 | Overhead | R16 | 2023-02-22 | 1 |  | 4 | 68 | 71 | 2023 | 2023 | R16
162647310614 | 162716310614 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-02-24 | 2023-02-24 | 2023-02-24 | 2023-06-12 | 2023-07-06 | Underground | R16 | 2023-06-12 | 1 |  | 77 | 19 | 95 | 2023 | 2023 | R16
160100332240 | 166846332240 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-01 | 2023-09-11 | 2023-09-11 | 2023-10-27 | 2023-11-08 | Overhead | R16 | 2023-10-27 | 96 |  | 35 | 9 | 138 | 2023 | 2023 | R16
169020315272 | 160881315272 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-15 | 2023-02-16 | 2023-04-10 |  | 2023-06-06 | Underground | R16 | 2023-04-14 | 2 | 38 | 5 | 38 | 80 | 2023 | 2023 | R16
165957312388 | 166090312388 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-13 | 2023-03-13 | 2023-03-13 | 2023-04-19 | 2023-08-09 | Overhead | R16 | 2023-04-19 | 1 |  | 28 | 81 | 108 | 2023 | 2023 | R16
165072319568 | 165887319568 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-25 | 2023-04-25 | 2023-05-19 |  | 2023-09-05 | Underground | R16 | 2023-05-19 | 1 | 19 |  | 78 | 96 | 2023 | 2023 | R16
161976144551 | 166454144551 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2019-01-09 | 2019-01-09 | 2019-03-01 |  | 2019-10-09 | Underground | R16 |  | 1 | 38 |  |  | 196 | 2019 | 2019 | R16
165240303327 | 168112303327 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2022-12-14 | 2022-12-14 | 2022-12-21 |  | 2023-05-02 | Overhead | R16 | 2023-01-24 | 1 | 6 | 25 | 71 | 100 | 2022 | 2023 | R16
167560317799 | 165640317799 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-24 | 2023-05-03 | 2023-05-03 | 2023-05-19 | 2023-09-06 | Overhead | R16 | 2023-05-19 | 8 |  | 13 | 79 | 98 | 2023 | 2023 | R16
160187314165 | 160087314165 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-29 | 2023-03-30 | 2023-03-30 | 2023-09-14 | 2023-09-19 | Overhead | R16 | 2023-09-14 | 2 |  | 121 | 4 | 125 | 2023 | 2023 | R16
167603244297 | 169913244297 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-19 | 2021-08-19 | 2021-08-19 | 2021-08-20 | 2021-10-25 | Underground | R16 | 2021-08-20 | 1 |  | 2 | 47 | 48 | 2021 | 2021 | R16
162995242083 | 165810242083 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-03 | 2021-08-03 | 2021-08-03 | 2021-10-05 | 2021-11-09 | Overhead | R16 | 2021-10-05 | 1 |  | 46 | 26 | 71 | 2021 | 2021 | R16
164621313237 | 166565313237 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-03-15 | 2023-03-15 | 2023-03-22 |  | 2023-10-04 | Underground | R16 |  | 1 | 6 |  |  | 146 | 2023 | 2023 | R16
168205242876 | 167303242876 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-10 | 2021-08-10 | 2021-08-10 |  | 2021-10-25 | Overhead | R16 | 2021-09-21 | 1 |  | 31 | 25 | 55 | 2021 | 2021 | R16
162158153050 | 163640153050 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-04-15 | 2019-04-16 | 2019-05-22 |  | 2019-12-06 | Underground | R16 |  | 2 | 27 |  |  | 170 | 2019 | 2019 | R16
166410308751 | 169172308751 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-08 | 2023-02-08 | 2023-02-08 |  | 2023-07-28 | Overhead | R16 | 2023-04-13 | 1 |  | 47 | 77 | 123 | 2023 | 2023 | R16
168796307147 | 163924307147 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-01-17 | 2023-01-25 | 2023-01-25 | 2023-03-21 | 2023-03-22 | Overhead | R16 | 2023-03-21 | 7 |  | 40 | 2 | 47 | 2023 | 2023 | R16
161332309534 | 169380309534 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2023-02-08 | 2023-02-08 | 2023-02-16 | 2023-08-01 | 2023-10-16 | Underground | R16 | 2023-08-01 | 1 | 7 | 119 | 55 | 179 | 2023 | 2023 | R16
162196177505 | 166690177505 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-10-12 | 2020-01-03 | 2020-01-21 |  | 2020-06-09 | Underground | R16 | 2020-03-18 | 60 | 13 | 42 | 60 | 172 | 2019 | 2020 | R16
160781305014 | 161196305014 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-05 | 2023-01-05 | 2023-01-05 | 2023-04-04 | 2023-04-10 | Overhead | R16 | 2023-04-04 | 1 |  | 64 | 5 | 68 | 2023 | 2023 | R16
166308313457 | 168540313457 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2023-03-23 | 2023-03-23 | 2023-03-23 | 2023-09-28 | 2023-11-02 | Underground | R16 | 2023-09-28 | 1 |  | 136 | 26 | 161 | 2023 | 2023 | R16
166396313168 | 167322313168 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-17 | 2023-03-17 | 2023-03-21 | 2023-05-25 | 2023-08-02 | Overhead | R16 | 2023-05-25 | 1 | 3 | 48 | 50 | 99 | 2023 | 2023 | R16
162775313101 | 167483313101 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2023-03-20 | 2023-03-20 | 2023-03-20 |  | 2023-05-18 | Overhead | R16 | 2023-03-20 | 1 |  |  | 44 | 44 | 2023 | 2023 | R16
168435321249 | 162449321249 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-10 | 2023-04-10 | 2023-06-05 | 2023-08-30 | 2023-09-13 | Underground | R16 | 2023-08-30 | 1 | 41 | 63 | 11 | 113 | 2023 | 2023 | R16
162881186684 | 162268186684 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-11-09 | 2019-11-20 | 2020-04-07 |  | 2020-10-06 | Underground | R16 |  | 8 | 100 |  |  | 237 | 2019 | 2020 | R16
163267322335 | 168637322335 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-06 | 2023-02-06 | 2023-06-16 | 2023-07-27 | 2023-08-01 | Overhead | R16 | 2023-07-27 | 1 | 95 | 30 | 4 | 127 | 2023 | 2023 | R16
166201311267 | 163944311267 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-02 | 2023-03-02 | 2023-03-02 |  | 2023-05-05 | Overhead | R16 | 2023-03-14 | 1 |  | 9 | 39 | 47 | 2023 | 2023 | R16
165556316338 | 164086316338 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-17 | 2023-04-17 | 2023-04-20 | 2023-07-25 | 2023-08-25 | Underground | R16 | 2023-07-25 | 1 | 4 | 69 | 24 | 95 | 2023 | 2023 | R16
167111318766 | 166497318766 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-01-26 | 2023-01-31 | 2023-05-10 |  | 2023-09-27 | Overhead | R16 |  | 4 | 72 |  |  | 175 | 2023 | 2023 | R16
167781242787 | 166926242787 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-08-09 | 2021-08-09 | 2021-08-09 |  | 2021-10-25 | Overhead | R16 | 2021-09-02 | 1 |  | 19 | 38 | 56 | 2021 | 2021 | R16
167878323993 | 169167323993 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-05 | 2023-07-05 | 2023-07-05 | 2023-09-11 | 2023-10-19 | Overhead | R16 | 2023-09-11 | 1 |  | 49 | 29 | 77 | 2023 | 2023 | R16
169955309451 | 160499309451 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-14 | 2023-02-14 | 2023-02-15 | 2023-12-11 | 2023-12-20 | Overhead | R16 | 2023-12-11 | 1 | 2 | 214 | 8 | 222 | 2023 | 2023 | R16
163242144826 | 164203144826 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2019-02-20 | 2019-02-22 | 2019-03-04 |  | 2021-04-13 | Underground | R16 |  | 3 | 7 |  |  | 560 | 2019 | 2021 | R16
169298322253 | 160628322253 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-18 | 2023-05-18 | 2023-06-15 | 2023-07-05 | 2023-09-06 | Underground | R16 | 2023-07-05 | 1 | 21 | 15 | 46 | 80 | 2023 | 2023 | R16
164624328450 | 164047328450 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-07 | 2023-06-08 | 2023-08-16 | 2023-08-21 | 2023-09-27 | Underground | R16 | 2023-08-21 | 2 | 50 | 4 | 28 | 81 | 2023 | 2023 | R16
166788321064 | 161085321064 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-23 | 2023-06-02 | 2023-06-02 | 2023-10-25 | 2023-11-03 | Overhead | R16 | 2023-10-25 | 9 |  | 104 | 8 | 119 | 2023 | 2023 | R16
166474306517 | 165056306517 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-20 | 2023-01-20 | 2023-01-20 |  | 2023-05-16 | Overhead | R16 | 2023-02-03 | 1 |  | 11 | 73 | 83 | 2023 | 2023 | R16
163373316002 | 168960316002 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-24 | 2023-03-24 | 2023-04-16 | 2023-09-05 | 2023-06-29 | Overhead | R16 | 2023-09-05 | 1 | 16 | 102 |  | 70 | 2023 | 2023 | R16
163750247111 | 160005247111 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-19 | 2021-08-26 | 2021-09-09 |  | 2023-06-22 | Overhead | R16 |  | 6 | 11 |  |  | 481 | 2021 | 2023 | R16
163465149597 | 163445149597 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-04-15 | 2019-04-15 | 2019-04-19 |  | 2020-07-07 | Underground | R16 | 2020-05-07 | 1 | 5 | 275 | 44 | 322 | 2019 | 2020 | R16
169407304970 | 161133304970 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-04 | 2023-01-04 | 2023-01-30 | 2023-01-04 | 2023-04-27 | Overhead | R16 | 2023-01-04 | 1 | 19 |  | 82 | 82 | 2023 | 2023 | R16
160233324685 | 165405324685 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-14 | 2023-06-16 | 2023-07-10 | 2023-08-24 | 2023-08-28 | Underground | R16 | 2023-08-24 | 3 | 17 | 34 | 3 | 54 | 2023 | 2023 | R16
166357324742 | 165525324742 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-24 | 2023-04-24 | 2023-07-10 | 2023-10-11 | 2023-10-18 | Underground | R16 | 2023-10-11 | 1 | 56 | 68 | 6 | 128 | 2023 | 2023 | R16
164938246971 | 167082246971 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-10 | 2021-08-10 | 2021-09-09 | 2021-12-01 | 2022-02-02 | Underground | R16 | 2021-12-01 | 1 | 23 | 60 | 46 | 127 | 2021 | 2022 | R16
165035322050 | 163442322050 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-13 |  | 2023-06-13 | 2023-10-04 | 2023-10-13 | Overhead | R16 | 2023-10-04 |  |  | 82 | 8 | 132 | 2023 | 2023 | R16
163201244323 | 169651244323 | CUSTOMER UPGRADE IN SERVICE | OH R16 RES NON RES OS | Residential | 2021-08-18 | 2021-08-18 | 2021-08-18 | 2021-12-13 | 2022-01-18 | Overhead | R16 | 2021-12-13 | 1 |  | 84 | 27 | 110 | 2021 | 2022 | R16
164651166444 | 169967166444 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2019-09-09 | 2019-09-10 | 2019-10-01 |  | 2021-01-12 | Underground | R16 |  | 2 | 16 |  |  | 352 | 2019 | 2021 | R16
163196312557 | 166935312557 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-16 | 2023-03-16 | 2023-03-16 |  | 2023-07-31 | Overhead | R16 | 2023-03-17 | 1 |  | 2 | 97 | 98 | 2023 | 2023 | R16
169053326648 | 160734326648 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-13 | 2023-07-13 | 2023-07-28 | 2023-10-18 | 2023-12-11 | Underground | R16 | 2023-10-18 | 1 | 12 | 59 | 39 | 108 | 2023 | 2023 | R16
167619314173 | 167950314173 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-03-21 | 2023-03-21 | 2023-03-30 | 2023-04-24 | 2023-05-17 | Underground | R16 | 2023-04-24 | 1 | 8 | 18 | 18 | 42 | 2023 | 2023 | R16
169717315732 | 165402315732 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-08 | 2023-04-13 | 2023-04-13 | 2023-08-11 | 2023-08-29 | Overhead | R16 | 2023-08-11 | 27 |  | 87 | 13 | 125 | 2023 | 2023 | R16
165414308097 | 166124308097 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-25 | 2023-02-03 | 2023-02-03 | 2023-03-07 | 2023-03-09 | Overhead | R16 | 2023-03-07 | 8 |  | 23 | 3 | 32 | 2023 | 2023 | R16
164343276824 | 165292276824 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH CP R16 WORK RELO TO UG | Residential | 2021-08-02 | 2021-11-03 | 2022-04-22 | 2022-05-12 | 2022-06-13 | Overhead | R16 | 2022-05-12 | 68 | 123 | 15 | 23 | 226 | 2021 | 2022 | R16
160163304025 | 169450304025 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-22 | 2022-12-22 | 2022-12-27 |  | 2023-08-04 | Overhead | R16 | 2023-04-06 | 1 | 4 | 73 | 87 | 162 | 2022 | 2023 | R16
161007247955 | 164994247955 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-13 | 2021-09-15 | 2021-09-15 |  | 2023-11-14 | Overhead | R16 | 2023-09-20 | 3 |  | 526 | 40 | 567 | 2021 | 2023 | R16
166525313240 | 166964313240 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-16 | 2023-03-16 | 2023-03-21 |  | 2023-08-14 | Overhead | R16 | 2023-04-14 | 1 | 4 | 19 | 87 | 108 | 2023 | 2023 | R16
165803322745 | 166232322745 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2023-06-19 | 2023-06-20 | 2023-06-20 | 2023-09-13 | 2023-10-02 | Overhead | R16 | 2023-09-13 | 2 |  | 62 | 14 | 76 | 2023 | 2023 | R16
161033249100 | 161549249100 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-08-26 | 2021-09-02 | 2021-09-22 | 2021-09-24 | 2021-11-09 | Overhead | R16 | 2021-09-24 | 6 | 15 | 3 | 33 | 54 | 2021 | 2021 | R16
164876240910 | 163968240910 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-27 | 2021-07-27 | 2021-07-27 | 2021-08-31 | 2021-10-25 | Overhead | R16 | 2021-08-31 | 1 |  | 26 | 40 | 65 | 2021 | 2021 | R16
163874310503 | 162249310503 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-09 | 2023-01-09 | 2023-02-24 |  | 2023-08-18 | Overhead | R16 | 2023-08-03 | 1 | 35 | 115 | 12 | 160 | 2023 | 2023 | R16
168084320020 | 161181320020 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-23 | 2023-05-23 | 2023-05-23 |  | 2023-06-29 | Overhead | R16 | 2023-05-25 | 1 |  | 3 | 26 | 28 | 2023 | 2023 | R16
166265155758 | 165024155758 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-06-18 | 2019-06-19 | 2019-06-19 |  | 2019-12-19 | Underground | R16 | 2019-12-05 | 2 |  | 122 | 11 | 133 | 2019 | 2019 | R16
164476321594 | 163480321594 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-05 | 2023-06-05 | 2023-06-08 | 2023-08-10 | 2023-08-16 | Underground | R16 | 2023-08-10 | 1 | 4 | 46 | 5 | 53 | 2023 | 2023 | R16
166331274223 | 166176274223 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-08-05 | 2021-08-05 | 2022-03-29 |  | 2022-05-12 | Underground | R16 |  | 1 | 169 |  |  | 201 | 2021 | 2022 | R16
165602308797 | 167363308797 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-31 | 2023-02-09 | 2023-02-09 |  | 2023-08-14 | Overhead | R16 | 2023-03-06 | 8 |  | 18 | 116 | 140 | 2023 | 2023 | R16
167048251980 | 168694251980 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-16 | 2021-08-25 | 2021-10-13 | 2021-12-13 | 2022-01-20 | Underground | R16 | 2021-12-13 | 8 | 36 | 44 | 29 | 114 | 2021 | 2022 | R16
161007322070 | 163100322070 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2023-06-02 | 2023-06-13 | 2023-06-13 | 2023-07-17 | 2023-08-16 | Overhead | R16 | 2023-07-17 | 8 |  | 25 | 23 | 54 | 2023 | 2023 | R16
168610323716 | 168438323716 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-23 | 2023-06-30 | 2023-06-30 | 2023-07-18 | 2023-07-25 | Overhead | R16 | 2023-07-18 | 72 |  | 13 | 6 | 89 | 2023 | 2023 | R16
166458175583 | 169287175583 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2019-12-19 | 2019-12-19 | 2020-01-02 |  | 2020-06-09 | Underground | R16 |  | 1 | 11 |  |  | 124 | 2019 | 2020 | R16
162578330668 | 160054330668 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-10 | 2023-07-10 | 2023-08-25 | 2023-11-10 | 2023-11-22 | Underground | R16 | 2023-11-10 | 1 | 35 | 56 | 9 | 98 | 2023 | 2023 | R16
160565246385 | 163076246385 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-02 | 2021-09-02 | 2021-09-02 | 2021-10-19 | 2021-11-02 | Overhead | R16 | 2021-10-19 | 1 |  | 34 | 11 | 44 | 2021 | 2021 | R16
163386251760 | 165206251760 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-13 | 2021-10-12 | 2021-10-12 | 2022-01-07 | 2022-02-07 | Overhead | R16 | 2022-01-07 | 22 |  | 64 | 22 | 106 | 2021 | 2022 | R16
161988242094 | 165911242094 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-04 | 2021-08-04 | 2021-08-04 | 2021-12-09 | 2022-02-02 | Overhead | R16 | 2021-12-09 | 1 |  | 92 | 40 | 131 | 2021 | 2022 | R16
162381333895 | 169462333895 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-27 | 2023-09-28 | 2023-09-28 |  | 2023-11-30 | Overhead | R16 | 2023-11-15 | 134 |  | 35 | 12 | 179 | 2023 | 2023 | R16
167010156127 | 165260156127 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-06-19 | 2019-06-20 | 2019-06-24 |  | 2023-06-02 | Overhead | R16 | 2020-09-04 | 2 | 3 | 315 | 716 | 1033 | 2019 | 2023 | R16
167010156127 | 165260156127 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-06-19 | 2019-06-20 | 2019-06-24 |  | 2023-06-02 | Underground | R16 | 2020-09-04 | 2 | 3 | 315 | 716 | 1033 | 2019 | 2023 | R16
161823324390 | 168525324390 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-29 | 2023-06-29 | 2023-07-07 | 2023-08-14 | 2023-09-01 | Overhead | R16 | 2023-08-14 | 1 | 7 | 27 | 15 | 47 | 2023 | 2023 | R16
164415321621 | 164096321621 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-08 | 2023-06-08 | 2023-06-08 | 2023-07-03 | 2023-07-26 | Overhead | R16 | 2023-07-03 | 1 |  | 18 | 18 | 35 | 2023 | 2023 | R16
160128242947 | 163905242947 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2021-07-27 | 2021-07-30 | 2021-08-10 |  | 2022-10-26 | Underground | R16 |  | 4 | 8 |  |  | 327 | 2021 | 2022 | R16
160184315707 | 162079315707 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-07 | 2023-04-07 | 2023-04-13 | 2023-05-18 | 2023-06-12 | Underground | R16 | 2023-05-18 | 1 | 5 | 26 | 18 | 47 | 2023 | 2023 | R16
164959319642 | 162820319642 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2023-04-11 | 2023-04-11 | 2023-05-19 | 2023-07-26 | 2023-10-04 | Underground | R16 | 2023-07-26 | 1 | 29 | 49 | 51 | 127 | 2023 | 2023 | R16
160620241418 | 165035241418 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-30 | 2021-07-30 | 2021-07-30 | 2021-09-21 | 2021-11-01 | Overhead | R16 | 2021-09-21 | 1 |  | 38 | 30 | 67 | 2021 | 2021 | R16
162265252970 | 162451252970 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-31 | 2021-10-18 | 2021-10-19 |  | 2022-06-01 | Overhead | R16 | 2022-05-03 | 35 | 2 | 141 | 22 | 197 | 2021 | 2022 | R16
161235314524 | 161013314524 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-03 | 2023-04-03 | 2023-04-03 | 2023-04-14 | 2023-06-13 | Overhead | R16 | 2023-04-14 | 1 |  | 10 | 43 | 52 | 2023 | 2023 | R16
167875323247 | 165865323247 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-17 | 2023-06-26 | 2023-06-26 | 2023-08-09 | 2023-08-14 | Overhead | R16 | 2023-08-09 | 6 |  | 33 | 4 | 41 | 2023 | 2023 | R16
166359324740 | 165485324740 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-24 | 2023-04-24 | 2023-07-10 | 2023-10-11 | 2023-10-18 | Underground | R16 | 2023-10-11 | 1 | 56 | 68 | 6 | 128 | 2023 | 2023 | R16
163790316824 | 165561316824 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-10-02 | 2023-10-18 | Overhead | R16 | 2023-10-02 | 1 |  | 116 | 13 | 128 | 2023 | 2023 | R16
165318243026 | 167502243026 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2022-06-27 | 2022-06-28 | Overhead | R16 | 2022-06-27 | 1 |  | 230 | 2 | 231 | 2021 | 2022 | R16
162463315782 | 162759315782 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-11 | 2023-04-14 | 2023-04-14 | 2023-08-24 | 2023-11-09 | Underground | R16 | 2023-08-24 | 4 |  | 95 | 56 | 153 | 2023 | 2023 | R16
163680247137 | 164821247137 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-11-11 | 2021-12-02 | Overhead | R16 | 2021-11-11 | 1 |  | 45 | 16 | 60 | 2021 | 2021 | R16
166363285432 | 166421285432 | SPECIFIC BUDGET PROJECTS | UG R16 RESD AND NON RESD UD | Commercial | 2021-08-05 | 2021-08-05 | 2022-07-13 |  | 2022-12-02 | Underground | R16 |  | 1 | 245 |  |  | 347 | 2021 | 2022 | R16
167717323672 | 168352323672 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-29 |  | 2023-06-29 | 2023-07-10 | 2023-08-28 | Overhead | R16 | 2023-07-10 |  |  | 8 | 36 | 43 | 2023 | 2023 | R16
165617312791 | 163855312791 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-01 | 2023-03-01 | 2023-03-17 |  | 2023-05-18 | Underground | R16 | 2023-04-12 | 1 | 13 | 19 | 27 | 57 | 2023 | 2023 | R16
167459226080 | 167895226080 | NON-RESIDENTIAL - SMALL RETAIL | R16 RESD AND NON RESD US | Commercial | 2019-01-17 | 2019-01-17 | 2021-04-07 |  | 2021-11-10 | Underground | R16 |  | 1 | 580 |  |  | 735 | 2019 | 2021 | R16
165530245261 | 166173245261 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2021-08-05 | 2021-08-05 | 2021-08-25 | 2022-01-20 | 2022-03-03 | Underground | R16 | 2022-01-20 | 1 | 15 | 107 | 31 | 151 | 2021 | 2022 | R16
165608306943 | 165570306943 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-23 | 2023-01-23 | 2023-01-30 | 2023-01-23 | 2023-08-21 | Overhead | R16 | 2023-01-23 | 1 | 6 |  | 151 | 151 | 2023 | 2023 | R16
166012320030 | 161109320030 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-05-23 | 2023-05-23 | 2023-05-23 | 2023-08-14 | 2023-08-17 | Overhead | R16 | 2023-08-14 | 1 |  | 60 | 4 | 63 | 2023 | 2023 | R16
167632155879 | 163609155879 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-06-12 | 2019-06-12 | 2019-06-20 |  | 2019-10-30 | Overhead | R16 | 2019-10-22 | 1 | 7 | 89 | 7 | 101 | 2019 | 2019 | R16
160276316551 | 166642316551 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-15 | 2023-03-15 | 2023-04-21 | 2023-08-21 | 2023-08-23 | Underground | R16 | 2023-08-21 | 1 | 28 | 87 | 3 | 116 | 2023 | 2023 | R16
169833324953 | 160130324953 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-10 | 2023-07-10 | 2023-07-13 | 2023-07-26 | 2023-07-27 | Overhead | R16 | 2023-07-26 | 1 | 4 | 10 | 2 | 14 | 2023 | 2023 | R16
167653150241 | 161776150241 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2019-04-04 | 2019-04-10 | 2019-04-24 |  | 2019-10-28 | Underground | R16 |  | 5 | 11 |  |  | 148 | 2019 | 2019 | R16
163147313845 | 166893313845 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-16 | 2023-03-27 | 2023-03-27 |  | 2023-09-27 | Underground | R16 | 2023-06-19 | 8 |  | 61 | 73 | 140 | 2023 | 2023 | R16
168505324132 | 169257324132 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-05 | 2023-07-05 | 2023-07-05 | 2023-07-06 | 2023-07-31 | Overhead | R16 | 2023-07-06 | 1 |  | 2 | 18 | 19 | 2023 | 2023 | R16
168975320622 | 160679320622 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2023-05-19 | 2023-05-19 | 2023-05-30 |  | 2023-10-13 | Underground | R16 |  | 1 | 8 |  |  | 106 | 2023 | 2023 | R16
164839322228 | 165079322228 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-13 | 2023-06-13 | 2023-06-14 | 2023-07-24 | 2023-09-14 | Underground | R16 | 2023-07-24 | 1 | 2 | 29 | 39 | 68 | 2023 | 2023 | R16
169492324254 | 165025324254 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-13 | 2023-06-13 | 2023-07-06 | 2023-09-13 | 2023-10-26 | Overhead | R16 | 2023-09-13 | 1 | 18 | 50 | 32 | 98 | 2023 | 2023 | R16
167990160943 | 164379160943 | NON-RESIDENTIAL - SMALL OFFICE | R16 RESD AND NON RESD US | Commercial | 2019-08-08 | 2019-08-08 | 2019-08-12 |  | 2021-11-08 | Underground | R16 |  | 1 | 3 |  |  | 588 | 2019 | 2021 | R16
165621319248 | 160014319248 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-16 | 2023-05-16 | 2023-05-16 | 2023-08-02 | 2023-08-03 | Overhead | R16 | 2023-08-02 | 1 |  | 57 | 2 | 58 | 2023 | 2023 | R16
168046309273 | 169608309273 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-09 | 2023-02-10 | 2023-02-13 |  | 2023-03-31 | Overhead | R16 | 2023-02-16 | 2 | 2 | 4 | 32 | 37 | 2023 | 2023 | R16
169253245969 | 162235245969 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-08-30 | 2021-08-30 | 2021-08-30 |  | 2021-10-25 | Overhead | R16 | 2021-09-13 | 1 |  | 11 | 31 | 41 | 2021 | 2021 | R16
165017317821 | 167343317821 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-05-02 | 2023-05-02 | 2023-05-02 | 2023-12-26 | 2023-12-27 | Underground | R16 | 2023-12-26 | 1 |  | 171 | 2 | 172 | 2023 | 2023 | R16
161539315766 | 167681315766 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-20 | 2023-03-20 | 2023-04-14 | 2023-07-18 | 2023-09-27 | Underground | R16 | 2023-07-18 | 1 | 20 | 68 | 52 | 138 | 2023 | 2023 | R16
163984246093 | 160978246093 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-24 | 2021-08-24 | 2021-09-01 | 2021-11-04 | 2021-12-03 | Underground | R16 | 2021-11-04 | 1 | 7 | 47 | 22 | 74 | 2021 | 2021 | R16
166805245199 | 161350245199 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-25 | 2021-08-25 | 2021-08-25 |  | 2022-08-02 | Overhead | R16 | 2022-06-13 | 1 |  | 209 | 37 | 245 | 2021 | 2022 | R16
166050312103 | 165502312103 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-09 | 2023-03-09 | 2023-03-10 | 2023-09-28 | 2023-10-05 | Overhead | R16 | 2023-09-28 | 1 | 2 | 145 | 6 | 151 | 2023 | 2023 | R16
167889323781 | 168418323781 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-29 | 2023-06-29 | 2023-06-29 | 2023-09-12 | 2023-10-23 | Overhead | R16 | 2023-09-12 | 1 |  | 54 | 30 | 83 | 2023 | 2023 | R16
161425244246 | 169218244246 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-17 | 2021-08-18 | 2021-08-18 | 2022-03-03 | 2022-03-14 | Overhead | R16 | 2022-03-03 | 2 |  | 142 | 8 | 150 | 2021 | 2022 | R16
162923260693 | 168382260693 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-13 | 2021-08-13 | 2021-12-10 |  | 2022-06-12 | Underground | R16 | 2022-05-26 | 1 | 86 | 120 | 12 | 216 | 2021 | 2022 | R16
166814313520 | 167761313520 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-20 |  | 2023-03-23 | 2023-07-05 | 2023-07-20 | Overhead | R16 | 2023-07-05 |  |  | 75 | 12 | 89 | 2023 | 2023 | R16
168201254228 | 164558254228 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-10 | 2021-10-10 | 2021-10-28 | 2022-03-16 | 2022-06-02 | Underground | R16 | 2022-03-16 | 21 | 14 | 100 | 57 | 190 | 2021 | 2022 | R16
166958308986 | 164597308986 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-18 | 2023-01-18 | 2023-02-09 | 2023-07-19 | 2023-08-11 | Underground | R16 | 2023-07-19 | 1 | 17 | 115 | 18 | 148 | 2023 | 2023 | R16
163015310610 | 162310310610 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-23 | 2023-02-24 | 2023-02-24 | 2023-07-21 | 2023-09-18 | Overhead | R16 | 2023-07-21 | 2 |  | 106 | 42 | 148 | 2023 | 2023 | R16
169745323081 | 165606323081 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-24 | 2023-06-22 | 2023-06-22 | 2023-11-03 | 2023-11-28 | Overhead | R16 | 2023-11-03 | 44 |  | 97 | 18 | 157 | 2023 | 2023 | R16
162965331391 | 163420331391 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-05 | 2023-08-31 | 2023-08-31 | 2023-09-14 | 2023-10-30 | Overhead | R16 | 2023-09-14 | 64 |  | 11 | 33 | 106 | 2023 | 2023 | R16
164581254898 | 162524254898 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-31 | 2021-09-02 | 2021-11-03 | 2022-01-05 | 2022-01-05 | Underground | R16 | 2022-01-05 | 3 | 45 | 46 |  | 92 | 2021 | 2022 | R16
165021312386 | 164476312386 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-03 | 2023-03-06 | 2023-03-13 | 2023-05-31 | 2023-06-22 | Overhead | R16 | 2023-05-31 | 2 | 6 | 58 | 17 | 80 | 2023 | 2023 | R16
164294313841 | 161170313841 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-04 | 2023-01-04 | 2023-03-27 |  | 2023-08-22 | Underground | R16 | 2023-05-17 | 1 | 59 | 38 | 70 | 165 | 2023 | 2023 | R16
166804314882 | 160378314882 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-02-14 | 2023-03-27 | 2023-04-05 | 2023-05-30 | 2023-07-03 | Underground | R16 | 2023-05-30 | 30 | 8 | 40 | 25 | 100 | 2023 | 2023 | R16
168906250107 | 168534250107 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-13 | 2021-09-29 | 2021-09-29 |  | 2023-03-09 | Underground | R16 | 2022-02-17 | 34 |  | 102 | 276 | 410 | 2021 | 2023 | R16
166857249778 | 162879249778 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-09-02 | 2021-09-02 | 2021-09-28 | 2022-12-02 | 2022-12-13 | Underground | R16 | 2022-12-02 | 1 | 19 | 309 | 8 | 334 | 2021 | 2022 | R16
162609322598 | 165097322598 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-06-13 | 2023-06-19 | 2023-06-19 | 2023-10-20 | 2023-11-02 | Overhead | R16 | 2023-10-20 | 5 |  | 90 | 10 | 103 | 2023 | 2023 | R16
160903244820 | 160564244820 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-22 | 2021-08-22 | 2021-08-23 |  | 2021-10-25 | Overhead | R16 | 2021-09-21 | 0 | 1 | 22 | 25 | 46 | 2021 | 2021 | R16
167768242862 | 165707242862 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-04 | 2021-08-09 | 2021-08-09 |  | 2022-01-24 | Underground | R16 | 2021-12-28 | 4 |  | 102 | 20 | 124 | 2021 | 2022 | R16
166016330227 | 164128330227 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG R16 RESD AND NON RESD UD | Residential | 2023-06-08 | 2023-07-19 | 2023-08-22 | 2023-10-19 | 2023-11-07 | Underground | R16 | 2023-10-19 | 30 | 25 | 43 | 14 | 109 | 2023 | 2023 | R16
167080245384 | 161397245384 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-10-22 | 2021-11-13 | Underground | R16 | 2021-10-22 | 1 |  | 43 | 16 | 58 | 2021 | 2021 | R16
164426303931 | 168844303931 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-12-19 |  | 2022-12-22 |  | 2023-02-06 | Underground | R16 | 2023-01-23 |  |  | 23 | 11 | 36 | 2022 | 2023 | R16
166054318030 | 165472318030 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-23 | 2023-05-04 | 2023-05-04 | 2023-05-19 | 2023-08-30 | Overhead | R16 | 2023-05-19 | 9 |  | 12 | 74 | 93 | 2023 | 2023 | R16
167078246360 | 162847246360 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-01 | 2021-09-01 | 2021-09-01 |  | 2021-11-09 | Overhead | R16 | 2021-10-11 | 1 |  | 29 | 22 | 50 | 2021 | 2021 | R16
161476247162 | 164306247162 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-09 | 2021-09-09 | 2021-09-09 |  | 2021-11-13 | Overhead | R16 | 2021-10-20 | 1 |  | 30 | 18 | 47 | 2021 | 2021 | R16
161975322163 | 165126322163 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-13 | 2023-06-13 | 2023-06-13 | 2023-06-30 | 2023-07-12 | Overhead | R16 | 2023-06-30 | 1 |  | 14 | 9 | 22 | 2023 | 2023 | R16
165193306748 | 164494306748 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-18 | 2023-01-21 | 2023-01-30 | 2023-01-22 | 2023-06-16 | Overhead | R16 | 2023-01-22 | 3 | 6 |  | 105 | 108 | 2023 | 2023 | R16
169278240673 | 163565240673 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-26 | 2021-07-26 | 2021-07-26 | 2022-02-02 | 2022-02-03 | Overhead | R16 | 2022-02-02 | 1 |  | 138 | 2 | 139 | 2021 | 2022 | R16
160846307711 | 165426307711 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-01-23 | 2023-01-23 | 2023-01-30 |  | 2023-08-14 | Underground | R16 | 2023-04-27 | 1 | 6 | 64 | 78 | 146 | 2023 | 2023 | R16
168961182086 | 166640182086 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-10-12 | 2019-12-17 | 2020-02-26 |  | 2020-10-06 | Underground | R16 |  | 47 | 52 |  |  | 257 | 2019 | 2020 | R16
160007332853 | 166668332853 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-21 | 2023-07-28 | 2023-09-18 | 2023-09-21 | 2023-09-27 | Overhead | R16 | 2023-09-21 | 28 | 37 | 4 | 5 | 71 | 2023 | 2023 | R16
165509245907 | 162246245907 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-30 | 2021-08-30 | 2021-08-30 |  | 2022-02-09 | Underground | R16 | 2022-01-06 | 1 |  | 94 | 25 | 118 | 2021 | 2022 | R16
168961182264 | 166642182264 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-10-12 | 2019-12-02 | 2020-02-27 |  | 2020-10-06 | Underground | R16 |  | 36 | 64 |  |  | 257 | 2019 | 2020 | R16
168961185498 | 166643185498 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-10-12 | 2019-12-23 | 2020-03-27 |  | 2020-10-06 | Underground | R16 |  | 51 | 70 |  |  | 257 | 2019 | 2020 | R16
163664246947 | 164011246947 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-08 | 2021-09-08 | 2021-09-08 | 2022-01-04 | 2022-01-05 | Underground | R16 | 2022-01-04 | 1 |  | 85 | 2 | 86 | 2021 | 2022 | R16
168531324269 | 169530324269 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-06 | 2023-07-06 | 2023-07-06 | 2023-08-15 | 2023-09-20 | Overhead | R16 | 2023-08-15 | 1 |  | 29 | 27 | 55 | 2023 | 2023 | R16
167267308247 | 167636308247 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-01 | 2023-02-03 | 2023-02-03 |  | 2023-09-13 | Underground | R16 | 2023-04-27 | 3 |  | 60 | 100 | 161 | 2023 | 2023 | R16
169026146205 | 167440146205 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-11 | 2019-03-15 | 2019-03-15 |  | 2019-12-06 | Underground | R16 | 2019-08-12 | 5 |  | 107 | 85 | 195 | 2019 | 2019 | R16
160781323590 | 166671323590 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-21 | 2023-06-28 | 2023-06-28 |  | 2023-07-26 | Overhead | R16 | 2023-07-06 | 6 |  | 7 | 15 | 26 | 2023 | 2023 | R16
166452314947 | 160944314947 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-03 | 2023-04-06 | 2023-04-06 |  | 2023-08-10 | Overhead | R16 | 2023-04-21 | 4 |  | 12 | 80 | 94 | 2023 | 2023 | R16
162561306587 | 162838306587 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2023-01-10 | 2023-01-10 | 2023-01-27 | 2023-07-03 | 2023-07-06 | Overhead | R16 | 2023-07-03 | 1 | 14 | 112 | 4 | 128 | 2023 | 2023 | R16
161817246594 | 165648246594 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-03 | 2021-08-03 | 2021-09-03 |  | 2022-02-09 | Overhead | R16 | 2022-01-06 | 1 | 24 | 90 | 25 | 137 | 2021 | 2022 | R16
167324319443 | 160343319443 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-17 | 2023-05-17 | 2023-05-17 | 2023-08-23 | 2023-10-04 | Overhead | R16 | 2023-08-23 | 1 |  | 71 | 31 | 101 | 2023 | 2023 | R16
169889303707 | 168737303707 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-19 | 2022-12-19 | 2022-12-22 |  | 2023-08-16 | Overhead | R16 | 2023-04-18 | 1 | 4 | 84 | 87 | 173 | 2022 | 2023 | R16
163203303766 | 168779303766 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-19 | 2022-12-19 | 2022-12-22 | 2023-10-20 | 2023-10-23 | Overhead | R16 | 2023-10-20 | 1 | 4 | 217 | 2 | 221 | 2022 | 2023 | R16
167077324152 | 167419324152 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-26 | 2023-06-26 | 2023-07-05 | 2023-10-10 | 2023-10-13 | Overhead | R16 | 2023-10-10 | 1 | 8 | 70 | 4 | 80 | 2023 | 2023 | R16
160438310965 | 163307310965 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-02-28 | 2023-02-28 | 2023-02-28 | 2023-02-28 | 2023-06-08 | Overhead | R16 | 2023-02-28 | 1 |  |  | 73 | 73 | 2023 | 2023 | R16
161385315141 | 169729315141 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-28 | 2023-03-28 | 2023-04-07 | 2023-05-15 | 2023-05-18 | Underground | R16 | 2023-05-15 | 1 | 9 | 27 | 4 | 38 | 2023 | 2023 | R16
169446139460 | 165580139460 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-07 | 2019-01-07 | 2019-01-07 |  | 2019-02-19 | Overhead | R16 | 2019-02-04 | 1 |  | 21 | 12 | 32 | 2019 | 2019 | R16
162216311314 | 169323311314 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-02-08 | 2023-02-08 | 2023-03-03 | 2023-05-17 | 2023-06-22 | Underground | R16 | 2023-05-17 | 1 | 18 | 54 | 27 | 97 | 2023 | 2023 | R16
161765313463 | 162409313463 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-09 | 2023-03-20 | 2023-03-23 | 2023-08-14 | 2023-08-25 | Underground | R16 | 2023-08-14 | 51 | 4 | 103 | 10 | 165 | 2023 | 2023 | R16
168988311618 | 161273311618 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-17 | 2023-03-07 | 2023-03-07 | 2023-05-07 | 2023-05-10 | Overhead | R16 | 2023-05-07 | 13 |  | 44 | 3 | 59 | 2023 | 2023 | R16
167635246035 | 162547246035 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2022-06-21 | 2023-01-05 | Overhead | R16 | 2022-06-21 | 1 |  | 211 | 143 | 353 | 2021 | 2023 | R16
162626316572 | 165258316572 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-21 | 2023-04-21 | 2023-04-21 | 2023-07-27 | 2023-09-18 | Overhead | R16 | 2023-07-27 | 1 |  | 70 | 38 | 107 | 2023 | 2023 | R16
165506311061 | 162429311061 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-23 | 2023-02-27 | 2023-03-01 |  | 2023-05-05 | Overhead | R16 | 2023-03-14 | 3 | 3 | 10 | 39 | 52 | 2023 | 2023 | R16
168598310983 | 163427310983 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2023-02-28 | 2023-02-28 | 2023-02-28 |  | 2023-07-06 | Underground | R16 |  | 1 |  |  |  | 93 | 2023 | 2023 | R16
160098165653 | 169098165653 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2019-09-04 | 2019-09-04 | 2019-09-24 |  | 2019-11-27 | Underground | R16 |  | 1 | 15 |  |  | 61 | 2019 | 2019 | R16
168981242704 | 166925242704 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-09 | 2021-08-09 | 2021-08-09 |  | 2021-11-01 | Overhead | R16 | 2021-09-29 | 1 |  | 38 | 24 | 61 | 2021 | 2021 | R16
161731325354 | 169287325354 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-05 | 2023-07-18 | 2023-07-18 | 2023-08-10 | 2023-08-25 | Underground | R16 | 2023-08-10 | 10 |  | 18 | 12 | 38 | 2023 | 2023 | R16
169007246062 | 163488246062 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-26 | 2021-08-31 | 2021-08-31 | 2021-11-18 | 2022-01-07 | Overhead | R16 | 2021-11-18 | 27 |  | 58 | 37 | 120 | 2021 | 2022 | R16
160472308084 | 167900308084 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-02 | 2023-02-02 | 2023-02-02 |  | 2023-10-11 | Overhead | R16 | 2023-06-20 | 1 |  | 99 | 82 | 180 | 2023 | 2023 | R16
160245159716 | 160546159716 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-07-17 | 2019-07-17 | 2019-08-01 |  | 2019-10-30 | Underground | R16 |  | 1 | 12 |  |  | 76 | 2019 | 2019 | R16
169727306615 | 165198306615 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-01-20 |  | 2023-01-30 | 2023-07-06 | 2023-07-21 | Overhead | R16 | 2023-07-06 |  |  | 114 | 12 | 131 | 2023 | 2023 | R16
166231319955 | 166775319955 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-05-01 |  | 2023-05-01 | 2023-10-26 | 2023-11-10 | Underground | R16 | 2023-10-26 |  |  | 129 | 12 | 140 | 2023 | 2023 | R16
162372308646 | 166233308646 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-25 | 2023-02-06 | 2023-02-06 |  | 2023-09-13 | Underground | R16 | 2023-05-15 | 9 |  | 71 | 88 | 166 | 2023 | 2023 | R16
165546308545 | 163876308545 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2023-01-17 | 2023-01-17 | 2023-02-06 | 2023-05-08 | 2023-05-09 | Overhead | R16 | 2023-05-08 | 1 | 15 | 66 | 2 | 81 | 2023 | 2023 | R16
160320200375 | 163227200375 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-08-11 | 2020-08-13 | 2020-08-13 |  | 2021-07-24 | Underground | R16 |  | 3 |  |  |  | 249 | 2020 | 2021 | R16
162830306547 | 169940306547 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-28 |  | 2023-01-30 | 2023-11-06 | 2023-11-16 | Overhead | R16 | 2023-11-06 |  |  | 201 | 9 | 232 | 2022 | 2023 | R16
169521308183 | 167432308183 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-31 | 2023-02-02 | 2023-02-02 |  | 2023-08-14 | Overhead | R16 | 2023-04-21 | 3 |  | 57 | 82 | 140 | 2023 | 2023 | R16
164543265266 | 165518265266 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-15 | 2021-09-15 | 2022-01-19 | 2022-03-10 | 2022-03-11 | Underground | R16 | 2022-03-10 | 1 | 91 | 37 | 2 | 128 | 2021 | 2022 | R16
160913246738 | 163444246738 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-03 | 2021-09-03 | 2021-09-08 | 2022-03-14 | 2022-04-12 | Overhead | R16 | 2022-03-14 | 1 | 4 | 134 | 22 | 158 | 2021 | 2022 | R16
160729247782 | 161324247782 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-26 | 2021-09-13 | 2021-09-13 |  | 2022-05-09 | Underground | R16 | 2022-04-14 | 13 |  | 154 | 18 | 183 | 2021 | 2022 | R16
166399321469 | 164140321469 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2023-04-17 | 2023-04-17 | 2023-06-07 | 2023-08-30 | 2023-10-11 | Underground | R16 | 2023-08-30 | 1 | 38 | 61 | 31 | 128 | 2023 | 2023 | R16
160723160295 | 161815160295 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-07-24 | 2019-07-24 | 2019-08-06 |  | 2020-06-09 | Underground | R16 | 2020-01-09 | 1 | 10 | 113 | 109 | 230 | 2019 | 2020 | R16
164910324811 | 167516324811 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-27 | 2023-07-13 | 2023-07-13 | 2023-08-07 | 2023-08-07 | Overhead | R16 | 2023-08-07 | 13 |  | 18 |  | 30 | 2023 | 2023 | R16
160750173554 | 163899173554 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-04-17 | 2019-05-17 | 2019-12-06 |  | 2020-10-06 | Underground | R16 |  | 23 | 146 |  |  | 385 | 2019 | 2020 | R16
164905249401 | 160580249401 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-22 | 2021-08-22 | 2021-09-24 | 2022-03-31 | 2022-05-18 | Underground | R16 | 2022-03-31 | 0 | 25 | 135 | 35 | 193 | 2021 | 2022 | R16
160814162417 | 163820162417 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2019-06-13 | 2019-06-19 | 2019-08-27 |  | 2021-11-10 | Underground | R16 |  | 5 | 50 |  |  | 630 | 2019 | 2021 | R16
168968250478 | 162000250478 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-28 | 2021-10-04 | 2021-10-04 | 2021-11-26 | 2021-11-29 | Overhead | R16 | 2021-11-26 | 26 |  | 40 | 2 | 66 | 2021 | 2021 | R16
160858153266 | 167806153266 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-03-12 | 2019-03-12 | 2019-05-23 |  | 2019-09-03 | Underground | R16 | 2019-08-06 | 1 | 53 | 54 | 21 | 126 | 2019 | 2019 | R16
163444318064 | 160958318064 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-03 | 2023-05-04 | 2023-05-04 | 2023-06-14 | 2023-06-22 | Overhead | R16 | 2023-06-14 | 24 |  | 30 | 7 | 59 | 2023 | 2023 | R16
162350316000 | 168876316000 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-24 | 2023-03-24 | 2023-04-16 |  | 2023-08-22 | Overhead | R16 | 2023-05-17 | 1 | 16 | 23 | 70 | 108 | 2023 | 2023 | R16
162104242666 | 166952242666 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-09 | 2021-08-09 | 2021-08-09 | 2021-09-15 | 2021-11-09 | Overhead | R16 | 2021-09-15 | 1 |  | 28 | 40 | 67 | 2021 | 2021 | R16
164609304069 | 169453304069 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-22 | 2022-12-22 | 2022-12-27 |  | 2023-12-07 | Overhead | R16 | 2023-09-01 | 1 | 4 | 179 | 70 | 251 | 2022 | 2023 | R16
160007315449 | 160507315449 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2023-02-14 | 2023-02-14 | 2023-04-11 |  | 2023-09-29 | Underground | R16 |  | 1 | 41 |  |  | 164 | 2023 | 2023 | R16
167477307457 | 160964307457 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-04 | 2023-01-28 | 2023-01-28 |  | 2023-06-09 | Overhead | R16 | 2023-02-06 | 18 |  | 6 | 90 | 113 | 2023 | 2023 | R16
167512308298 | 168425308298 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-04 | 2023-02-04 | 2023-02-04 | 2023-04-04 | 2023-04-10 | Overhead | R16 | 2023-04-04 | 0 |  | 42 | 5 | 46 | 2023 | 2023 | R16
164291251447 | 165321251447 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-13 | 2021-09-22 | 2021-10-09 | 2022-03-07 | 2022-03-28 | Underground | R16 | 2022-03-07 | 8 | 13 | 106 | 16 | 141 | 2021 | 2022 | R16
169867308697 | 167661308697 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-12 | 2022-12-12 | 2023-02-07 | 2023-04-28 | 2023-06-12 | Underground | R16 | 2023-04-28 | 1 | 42 | 59 | 32 | 131 | 2022 | 2023 | R16
168468321541 | 163943321541 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-07-13 | 2023-07-31 | Overhead | R16 | 2023-07-13 | 1 |  | 27 | 13 | 39 | 2023 | 2023 | R16
168684247781 | 165436247781 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-08-03 | 2021-08-03 | 2021-09-13 |  | 2023-10-20 | Underground | R16 | 2023-10-05 | 1 | 30 | 539 | 12 | 579 | 2021 | 2023 | R16
160135242998 | 166293242998 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-05 | 2021-08-05 | 2021-08-11 | 2021-11-05 | 2021-11-08 | Underground | R16 | 2021-11-05 | 1 | 5 | 63 | 2 | 68 | 2021 | 2021 | R16
164617303274 | 168101303274 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-14 | 2022-12-14 | 2022-12-21 |  | 2023-03-31 | Overhead | R16 | 2023-02-22 | 1 | 6 | 46 | 28 | 78 | 2022 | 2023 | R16
168424248970 | 162445248970 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2021-08-31 | 2021-08-31 | 2021-09-22 | 2021-11-10 | 2021-11-29 | Overhead | R16 | 2021-11-10 | 1 | 17 | 36 | 14 | 65 | 2021 | 2021 | R16
162435322353 | 162346322353 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-30 | 2023-06-16 | 2023-06-16 | 2023-08-09 | 2023-10-25 | Overhead | R16 | 2023-08-09 | 14 |  | 39 | 56 | 107 | 2023 | 2023 | R16
168590313045 | 167040313045 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-16 | 2023-03-16 | 2023-03-20 |  | 2023-05-18 | Overhead | R16 | 2023-03-27 | 1 | 3 | 6 | 39 | 46 | 2023 | 2023 | R16
169730246366 | 163404246366 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-03 |  | 2021-09-03 | 2022-05-02 | 2022-06-02 | Overhead | R16 | 2022-05-02 |  |  | 172 | 24 | 195 | 2021 | 2022 | R16
165987311449 | 162342311449 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-23 | 2023-02-27 | 2023-03-03 |  | 2023-05-18 | Underground | R16 | 2023-03-24 | 3 | 5 | 16 | 40 | 61 | 2023 | 2023 | R16
168507315070 | 169632315070 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-28 | 2023-03-28 | 2023-04-07 |  | 2023-06-05 | Underground | R16 | 2023-05-08 | 1 | 9 | 22 | 21 | 50 | 2023 | 2023 | R16
161092314854 | 161591314854 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-05 | 2023-04-05 | 2023-04-05 | 2023-07-27 | 2023-07-31 | Overhead | R16 | 2023-07-27 | 1 |  | 82 | 3 | 84 | 2023 | 2023 | R16
165683244046 | 166306244046 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-05 | 2021-08-05 | 2021-08-17 | 2022-04-12 | 2022-04-13 | Underground | R16 | 2022-04-12 | 1 | 9 | 171 | 2 | 180 | 2021 | 2022 | R16
164906282327 | 165275282327 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential Subdivision | 2021-08-02 | 2021-09-28 | 2022-06-10 | 2022-11-09 | 2022-12-06 | Underground | R16 | 2022-11-09 | 42 | 184 | 109 | 20 | 352 | 2021 | 2022 | R16
165692243491 | 168372243491 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-13 | 2021-08-13 | 2021-08-13 |  | 2022-05-18 | Overhead | R16 | 2022-04-25 | 1 |  | 182 | 18 | 199 | 2021 | 2022 | R16
167780313191 | 167990313191 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-21 | 2023-03-21 | 2023-03-21 | 2023-05-03 | 2023-06-13 | Overhead | R16 | 2023-05-03 | 1 |  | 32 | 30 | 61 | 2023 | 2023 | R16
160234313229 | 162823313229 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-24 | 2023-02-24 | 2023-03-21 | 2023-07-26 | 2023-08-03 | Underground | R16 | 2023-07-26 | 1 | 18 | 92 | 7 | 115 | 2023 | 2023 | R16
160263240638 | 163636240638 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-26 | 2021-07-26 | 2021-07-27 |  | 2021-10-25 | Underground | R16 | 2021-08-23 | 1 | 2 | 20 | 46 | 66 | 2021 | 2021 | R16
163301146210 | 163268146210 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-02-13 | 2019-02-13 | 2019-03-15 |  | 2020-01-08 | Underground | R16 | 2020-01-02 | 1 | 23 | 210 | 5 | 236 | 2019 | 2020 | R16
165921319497 | 160741319497 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-31 | 2023-03-31 | 2023-05-18 | 2023-10-24 | 2023-10-26 | Underground | R16 | 2023-10-24 | 1 | 35 | 114 | 3 | 150 | 2023 | 2023 | R16
164616245493 | 161559245493 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-27 | 2021-08-27 | 2021-08-27 | 2021-09-15 | 2021-09-16 | Overhead | R16 | 2021-09-15 | 1 |  | 14 | 2 | 15 | 2021 | 2021 | R16
164236322214 | 166150322214 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-13 | 2023-03-13 | 2023-06-14 | 2023-10-18 | 2023-11-16 | Underground | R16 | 2023-10-18 | 1 | 68 | 91 | 22 | 179 | 2023 | 2023 | R16
162516328271 | 163784328271 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2023-06-06 | 2023-06-06 | 2023-08-15 | 2023-11-08 | 2023-11-28 | Underground | R16 | 2023-11-08 | 1 | 51 | 62 | 15 | 126 | 2023 | 2023 | R16
168702322434 | 162940322434 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2023-06-01 | 2023-06-01 | 2023-06-16 | 2023-07-25 | 2023-07-27 | Underground | R16 | 2023-07-25 | 1 | 12 | 28 | 3 | 41 | 2023 | 2023 | R16
166652312520 | 160808312520 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-15 | 2023-02-15 | 2023-03-14 |  | 2023-08-11 | Underground | R16 | 2023-04-19 | 1 | 20 | 27 | 83 | 128 | 2023 | 2023 | R16
164260311208 | 163866311208 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-02 | 2023-03-02 | 2023-03-02 | 2023-03-31 | 2023-04-03 | Overhead | R16 | 2023-03-31 | 1 |  | 22 | 2 | 23 | 2023 | 2023 | R16
164275327029 | 165166327029 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-21 | 2023-04-21 | 2023-08-01 | 2023-09-12 | 2023-10-06 | Underground | R16 | 2023-09-12 | 1 | 73 | 31 | 19 | 121 | 2023 | 2023 | R16
161586315071 | 161984315071 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-06 | 2023-04-07 | 2023-04-07 | 2023-09-14 | 2023-11-09 | Overhead | R16 | 2023-09-14 | 2 |  | 115 | 41 | 156 | 2023 | 2023 | R16
169055303721 | 168339303721 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2022-12-16 | 2022-12-16 | 2022-12-20 |  | 2023-08-17 | Overhead | R16 |  | 1 | 3 |  |  | 175 | 2022 | 2023 | R16
164219140647 | 167849140647 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-18 | 2019-01-18 | 2019-01-18 |  | 2019-04-22 | Overhead | R16 | 2019-04-15 | 1 |  | 62 | 6 | 67 | 2019 | 2019 | R16
161288323638 | 168526323638 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-29 | 2023-06-29 | 2023-06-29 | 2023-06-30 | 2023-08-07 | Overhead | R16 | 2023-06-30 | 1 |  | 2 | 27 | 28 | 2023 | 2023 | R16
164305182935 | 164451182935 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-05 | 2020-03-06 | 2020-03-06 |  | 2022-03-08 | Overhead | R16 |  | 2 |  |  |  | 524 | 2020 | 2022 | R16
169119246524 | 167699246524 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-11 | 2021-09-02 | 2021-09-02 |  | 2021-11-13 | Overhead | R16 | 2021-10-20 | 17 |  | 35 | 18 | 68 | 2021 | 2021 | R16
168185242057 | 166057242057 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-04 | 2021-08-04 | 2021-08-04 |  | 2021-10-25 | Overhead | R16 |  | 1 |  |  |  | 59 | 2021 | 2021 | R16
162447247341 | 164681247341 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-10-07 | 2021-11-10 | Underground | R16 | 2021-10-07 | 1 |  | 20 | 25 | 44 | 2021 | 2021 | R16
169469310855 | 163194310855 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-28 | 2023-02-28 | 2023-02-28 | 2023-08-11 | 2023-08-25 | Overhead | R16 | 2023-08-11 | 1 |  | 119 | 11 | 129 | 2023 | 2023 | R16
166849324246 | 169399324246 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2023-07-06 | 2023-07-06 | 2023-07-06 | 2023-07-31 | 2023-10-14 | Overhead | R16 | 2023-07-31 | 1 |  | 18 | 55 | 72 | 2023 | 2023 | R16
160281314909 | 163347314909 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-28 | 2023-02-28 | 2023-04-06 |  | 2023-07-12 | Underground | R16 | 2023-06-14 | 1 | 28 | 50 | 21 | 97 | 2023 | 2023 | R16
165913265170 | 165515265170 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-14 | 2021-09-22 | 2022-01-18 |  | 2022-08-11 | Underground | R16 | 2022-06-29 | 7 | 85 | 117 | 32 | 238 | 2021 | 2022 | R16
162933315866 | 163663315866 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-14 | 2023-04-14 | 2023-04-14 | 2023-04-25 | 2023-08-22 | Overhead | R16 | 2023-04-25 | 1 |  | 8 | 86 | 93 | 2023 | 2023 | R16
167079309492 | 160119309492 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-13 | 2023-02-15 | 2023-02-15 | 2023-05-27 | 2023-05-30 | Overhead | R16 | 2023-05-27 | 3 |  | 73 | 2 | 77 | 2023 | 2023 | R16
162563322710 | 166358322710 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2023-06-20 | 2023-06-20 | 2023-06-20 | 2023-12-19 | 2023-12-27 | Underground | R16 | 2023-12-19 | 1 |  | 131 | 7 | 137 | 2023 | 2023 | R16
164575303529 | 168076303529 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2022-12-14 | 2022-12-16 | 2022-12-16 | 2022-12-21 | 2023-04-25 | Overhead | R16 | 2022-12-21 | 3 |  | 4 | 90 | 95 | 2022 | 2023 | R16
168730307292 | 166431307292 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-26 | 2023-01-26 | 2023-01-26 | 2023-05-17 | 2023-06-12 | Underground | R16 | 2023-05-17 | 1 |  | 80 | 19 | 98 | 2023 | 2023 | R16
166934308671 | 168477308671 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-06 | 2023-02-06 | 2023-02-07 | 2023-04-25 | 2023-06-12 | Overhead | R16 | 2023-04-25 | 1 | 2 | 56 | 35 | 91 | 2023 | 2023 | R16
164134328019 | 164317328019 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-18 | 2023-04-18 | 2023-08-11 | 2023-09-22 | 2023-10-03 | Underground | R16 | 2023-09-22 | 1 | 84 | 31 | 8 | 121 | 2023 | 2023 | R16
161670327301 | 166374327301 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-14 | 2023-03-14 | 2023-08-03 | 2023-09-05 | 2023-10-26 | Underground | R16 | 2023-09-05 | 1 | 103 | 24 | 38 | 163 | 2023 | 2023 | R16
169748328187 | 164976328187 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-20 | 2023-04-28 | 2023-08-14 | 2023-09-26 | 2023-09-27 | Overhead | R16 | 2023-09-26 | 7 | 77 | 32 | 2 | 115 | 2023 | 2023 | R16
160236308214 | 167976308214 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-02 | 2023-02-03 | 2023-02-03 | 2023-05-01 | 2023-06-12 | Overhead | R16 | 2023-05-01 | 2 |  | 62 | 31 | 93 | 2023 | 2023 | R16
165840308812 | 166421308812 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-26 | 2023-01-26 | 2023-02-08 |  | 2023-07-25 | Underground | R16 | 2023-06-30 | 1 | 10 | 103 | 18 | 129 | 2023 | 2023 | R16
168350308541 | 168218308541 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-03 | 2023-02-06 | 2023-02-06 |  | 2023-06-26 | Overhead | R16 | 2023-03-07 | 2 |  | 22 | 80 | 102 | 2023 | 2023 | R16
168016290289 | 161186290289 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-08-25 | 2021-08-25 | 2022-08-24 | 2022-12-28 | 2023-06-08 | Underground | R16 | 2022-12-28 | 1 | 261 | 91 | 117 | 467 | 2021 | 2023 | R16
164013311071 | 163399311071 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-02-28 | 2023-02-28 | 2023-03-01 |  | 2023-09-13 | Overhead | R16 |  | 1 | 2 |  |  | 142 | 2023 | 2023 | R16
160624243170 | 167881243170 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-11 | 2021-08-11 | 2021-08-11 | 2022-05-03 | 2022-06-06 | Overhead | R16 | 2022-05-03 | 1 |  | 190 | 25 | 214 | 2021 | 2022 | R16
162625244031 | 165429244031 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-02 | 2021-08-17 | 2021-08-17 |  | 2021-12-14 | Overhead | R16 | 2021-12-08 | 12 |  | 82 | 5 | 97 | 2021 | 2021 | R16
164129304741 | 160669304741 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-03 | 2023-01-03 | 2023-01-30 | 2023-02-28 | 2023-04-05 | Overhead | R16 | 2023-02-28 | 1 | 20 | 22 | 27 | 67 | 2023 | 2023 | R16
164922316554 | 165287316554 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-04-21 | 2023-04-21 | 2023-04-21 |  | 2023-10-06 | Underground | R16 | 2023-07-13 | 1 |  | 60 | 62 | 121 | 2023 | 2023 | R16
167725251057 | 165775251057 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-08-03 | 2021-10-08 | 2021-10-08 |  | 2023-05-30 | Underground | R16 | 2023-02-28 | 49 |  | 363 | 66 | 476 | 2021 | 2023 | R16
168713244442 | 166858244442 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-09 | 2021-08-19 | 2021-08-19 | 2021-12-23 | 2021-12-27 | Overhead | R16 | 2021-12-23 | 9 |  | 91 | 3 | 101 | 2021 | 2021 | R16
169788310008 | 162080310008 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-22 | 2023-02-22 | 2023-02-22 |  | 2023-05-18 | Overhead | R16 | 2023-04-10 | 1 |  | 34 | 29 | 62 | 2023 | 2023 | R16
161955322083 | 162490322083 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-31 | 2023-06-06 | 2023-06-13 | 2023-08-01 | 2023-09-11 | Underground | R16 | 2023-08-01 | 5 | 6 | 36 | 30 | 74 | 2023 | 2023 | R16
161773318831 | 169235318831 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-11 | 2023-05-11 | 2023-05-11 |  | 2023-06-13 | Overhead | R16 | 2023-05-18 | 1 |  | 6 | 19 | 24 | 2023 | 2023 | R16
167720311582 | 162670311582 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-02-24 | 2023-03-04 | 2023-03-06 |  | 2023-09-29 | Overhead | R16 | 2023-06-14 | 6 | 1 | 73 | 78 | 156 | 2023 | 2023 | R16
163548309213 | 160128309213 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-08-17 | 2023-10-13 | Overhead | R16 | 2023-08-17 | 1 |  | 134 | 42 | 175 | 2023 | 2023 | R16
161987313917 | 169512313917 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-28 | 2023-03-28 | 2023-03-28 | 2023-12-04 | 2023-12-05 | Overhead | R16 | 2023-12-04 | 1 |  | 180 | 2 | 181 | 2023 | 2023 | R16
168060305481 | 161840305481 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-05 | 2023-01-06 | 2023-01-30 | 2023-03-09 | 2023-03-14 | Underground | R16 | 2023-03-09 | 2 | 17 | 29 | 4 | 49 | 2023 | 2023 | R16
161078308631 | 168539308631 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-06 | 2023-02-07 | 2023-02-07 | 2023-04-08 | 2023-04-22 | Overhead | R16 | 2023-04-08 | 2 |  | 44 | 10 | 55 | 2023 | 2023 | R16
168782325648 | 160091325648 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-10 | 2023-07-20 | 2023-07-20 | 2023-07-31 | 2023-08-30 | Overhead | R16 | 2023-07-31 | 9 |  | 8 | 23 | 38 | 2023 | 2023 | R16
166415146387 | 162387146387 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-08 | 2019-02-08 | 2019-03-18 |  | 2019-05-28 | Overhead | R16 |  | 1 | 27 |  |  | 78 | 2019 | 2019 | R16
163845308520 | 168471308520 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-05 | 2023-02-05 | 2023-02-05 |  | 2023-04-03 | Overhead | R16 | 2023-03-17 | 0 |  | 30 | 12 | 41 | 2023 | 2023 | R16
164211313138 | 161650313138 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-20 | 2023-02-22 | 2023-03-21 | 2023-04-29 | 2023-06-15 | Underground | R16 | 2023-04-29 | 3 | 20 | 29 | 34 | 84 | 2023 | 2023 | R16
166268242729 | 166982242729 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-09 | 2021-08-09 | 2021-08-09 |  | 2021-10-26 | Overhead | R16 | 2021-09-01 | 1 |  | 18 | 40 | 57 | 2021 | 2021 | R16
169723241332 | 164800241332 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-29 | 2021-07-29 | 2021-07-29 |  | 2021-08-06 | Overhead | R16 | 2021-11-04 | 1 |  | 71 |  | 7 | 2021 | 2021 | R16
166447147801 | 160151147801 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-03-26 | 2019-03-31 | 2019-03-31 |  | 2019-05-20 | Overhead | R16 | 2019-04-15 | 4 |  | 11 | 26 | 40 | 2019 | 2019 | R16
166050276651 | 167180276651 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2021-08-10 | 2021-08-10 | 2022-04-21 | 2022-05-03 | 2022-06-23 | Overhead | R16 | 2022-05-03 | 1 | 183 | 9 | 38 | 228 | 2021 | 2022 | R16
166447157609 | 164363157609 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-17 | 2019-07-10 | 2019-07-11 |  | 2023-06-08 | Overhead | R16 |  | 18 | 2 |  |  | 1039 | 2019 | 2023 | R16
160494245005 | 160881245005 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-24 | 2021-08-24 | 2021-08-24 |  | 2022-04-26 | Overhead | R16 | 2022-04-05 | 1 |  | 161 | 16 | 176 | 2021 | 2022 | R16
166447167490 | 165663167490 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-10-08 | 2019-10-10 | 2019-10-10 |  | 2019-11-26 | Overhead | R16 | 2019-11-18 | 3 |  | 28 | 7 | 36 | 2019 | 2019 | R16
164642317845 | 165393317845 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-08 | 2023-03-08 | 2023-05-03 | 2023-06-20 | 2023-06-30 | Overhead | R16 | 2023-06-20 | 1 | 41 | 35 | 9 | 83 | 2023 | 2023 | R16
166447175885 | 169068175885 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-10-24 | 2019-12-31 | 2020-01-06 |  | 2021-11-10 | Overhead | R16 |  | 49 | 5 |  |  | 535 | 2019 | 2021 | R16
164957304263 | 168284304263 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-15 | 2022-12-15 | 2022-12-27 |  | 2023-04-19 | Overhead | R16 | 2023-01-13 | 1 | 9 | 14 | 69 | 90 | 2022 | 2023 | R16
163562303216 | 168139303216 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-14 | 2022-12-15 | 2022-12-14 | 2023-02-03 | 2023-02-06 | Overhead | R16 | 2023-02-03 | 2 |  | 38 | 2 | 39 | 2022 | 2023 | R16
166447201881 | 163560201881 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-08-13 | 2020-08-18 | 2020-08-26 |  | 2021-01-08 | Underground | R16 |  | 4 | 7 |  |  | 107 | 2020 | 2021 | R16
160159242342 | 166029242342 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-08-05 | 2021-08-05 | 2021-08-05 | 2023-05-14 | 2023-05-17 | Overhead | R16 | 2023-05-14 | 1 |  | 462 | 3 | 465 | 2021 | 2023 | R16
163691243302 | 167849243302 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-12 | 2021-08-12 | 2021-08-12 |  | 2021-10-25 | Overhead | R16 | 2021-09-08 | 1 |  | 20 | 34 | 53 | 2021 | 2021 | R16
166841155720 | 164802155720 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-18 | 2019-06-18 | 2019-06-18 |  | 2019-11-15 | Overhead | R16 | 2019-11-08 | 1 |  | 104 | 6 | 109 | 2019 | 2019 | R16
166240308628 | 167632308628 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-01 | 2023-02-03 | 2023-02-07 | 2023-02-23 | 2023-06-13 | Overhead | R16 | 2023-02-23 | 3 | 3 | 13 | 79 | 95 | 2023 | 2023 | R16
167698318025 | 167839318025 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-04 | 2023-05-04 | 2023-05-04 | 2023-08-04 | 2023-09-01 | Overhead | R16 | 2023-08-04 | 1 |  | 67 | 21 | 87 | 2023 | 2023 | R16
163554312058 | 165981312058 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-11 | 2023-03-11 | 2023-03-11 |  | 2023-08-14 | Overhead | R16 | 2023-03-28 | 0 |  | 12 | 100 | 111 | 2023 | 2023 | R16
166200306461 | 164650306461 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-18 | 2023-01-19 | 2023-01-30 | 2023-03-09 | 2023-03-10 | Overhead | R16 | 2023-03-09 | 2 | 8 | 29 | 2 | 38 | 2023 | 2023 | R16
165623304388 | 168795304388 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-19 | 2022-12-30 | 2022-12-30 | 2023-01-18 | 2023-03-31 | Overhead | R16 | 2023-01-18 | 10 |  | 14 | 53 | 75 | 2022 | 2023 | R16
160061312530 | 166487312530 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-15 | 2023-03-15 | 2023-03-15 |  | 2023-07-28 | Overhead | R16 | 2023-03-21 | 1 |  | 5 | 94 | 98 | 2023 | 2023 | R16
167861336003 | 169008336003 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-05 |  | 2023-07-05 | 2023-11-16 | 2023-12-08 | Underground | R16 | 2023-11-16 |  |  | 97 | 17 | 113 | 2023 | 2023 | R16
162760320630 | 162420320630 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-30 | 2023-05-30 | 2023-05-30 | 2023-06-02 | 2023-07-10 | Overhead | R16 | 2023-06-02 | 1 |  | 4 | 27 | 30 | 2023 | 2023 | R16
168915241408 | 163729241408 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-27 | 2021-07-28 | 2021-07-30 | 2021-09-29 | 2021-10-01 | Overhead | R16 | 2021-09-29 | 2 | 3 | 44 | 3 | 49 | 2021 | 2021 | R16
165814255481 | 169914255481 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-08-19 | 2021-11-03 | 2021-11-07 | 2022-05-19 | 2022-06-07 | Underground | R16 | 2022-05-19 | 55 | 3 | 139 | 14 | 209 | 2021 | 2022 | R16
168868316827 | 161330316827 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2023-04-04 | 2023-04-04 | 2023-04-24 |  | 2023-09-14 | Underground | R16 | 2023-05-15 | 1 | 15 | 16 | 89 | 118 | 2023 | 2023 | R16
169395313953 | 165950313953 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-10 | 2023-03-10 | 2023-03-28 | 2023-04-07 | 2023-08-08 | Underground | R16 | 2023-04-07 | 1 | 13 | 9 | 88 | 108 | 2023 | 2023 | R16
166399318921 | 169320318921 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-11 | 2023-05-11 | 2023-05-11 | 2023-07-17 | 2023-10-12 | Overhead | R16 | 2023-07-17 | 1 |  | 48 | 64 | 111 | 2023 | 2023 | R16
166073304211 | 169971304211 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-28 | 2022-12-28 | 2023-01-30 | 2022-12-28 | 2023-03-31 | Overhead | R16 | 2022-12-28 | 1 | 24 |  | 68 | 68 | 2022 | 2023 | R16
168503316997 | 165591316997 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-24 | 2023-04-24 | 2023-04-26 |  | 2023-07-13 | Overhead | R16 | 2023-06-23 | 1 | 3 | 43 | 15 | 59 | 2023 | 2023 | R16
163805315269 | 164907315269 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-07 | 2023-03-07 | 2023-04-10 |  | 2023-08-08 | Underground | R16 | 2023-04-13 | 1 | 25 | 4 | 84 | 111 | 2023 | 2023 | R16
168375241283 | 164506241283 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-29 | 2021-07-29 | 2021-07-29 |  | 2022-01-18 | Overhead | R16 | 2021-12-16 | 1 |  | 101 | 24 | 124 | 2021 | 2022 | R16
167040245924 | 169648245924 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-19 | 2021-08-27 | 2021-08-30 | 2021-10-26 | 2023-03-31 | Overhead | R16 | 2021-10-26 | 7 | 2 | 42 | 374 | 422 | 2021 | 2023 | R16
168002247037 | 164243247037 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-08 | 2021-09-08 | 2021-09-08 | 2021-12-29 | 2022-03-04 | Underground | R16 | 2021-12-29 | 1 |  | 81 | 48 | 128 | 2021 | 2022 | R16
168671246191 | 169569246191 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-08-18 | 2021-08-18 | 2021-09-01 | 2022-03-24 | 2022-04-19 | Overhead | R16 | 2022-03-24 | 1 | 11 | 147 | 19 | 175 | 2021 | 2022 | R16
168351162597 | 161418162597 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-07-22 | 2019-07-22 | 2019-08-29 |  | 2020-07-01 | Overhead | R16 |  | 1 | 29 |  |  | 248 | 2019 | 2020 | R16
168441153577 | 168522153577 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-05-12 | 2019-05-21 | 2019-05-29 |  | 2021-07-24 | Underground | R16 |  | 7 | 7 |  |  | 575 | 2019 | 2021 | R16
169523246044 | 162441246044 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-11-04 | 2022-03-11 | Overhead | R16 | 2021-11-04 | 1 |  | 48 | 92 | 139 | 2021 | 2022 | R16
161495307168 | 163110307168 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-11 |  | 2023-01-25 | 2023-02-23 | 2023-03-07 | Overhead | R16 | 2023-02-23 |  |  | 22 | 9 | 40 | 2023 | 2023 | R16
165497319063 | 169646319063 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-07-05 | 2023-07-05 | Overhead | R16 | 2023-07-05 | 1 |  | 38 |  | 38 | 2023 | 2023 | R16
162612325128 | 167644325128 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-27 | 2023-06-27 | 2023-07-14 | 2023-10-18 | 2023-10-26 | Underground | R16 | 2023-10-18 | 1 | 14 | 69 | 7 | 88 | 2023 | 2023 | R16
165638312550 | 166730312550 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-15 | 2023-03-15 | 2023-03-15 | 2023-04-21 | 2023-06-12 | Overhead | R16 | 2023-04-21 | 1 |  | 28 | 37 | 64 | 2023 | 2023 | R16
168838145688 | 162932145688 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-12 | 2019-02-26 | 2019-03-11 |  | 2021-11-08 | Underground | R16 | 2021-09-21 | 11 | 10 | 662 | 35 | 715 | 2019 | 2021 | R16
165922307339 | 166809307339 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-27 | 2023-01-27 | 2023-01-27 |  | 2023-07-31 | Overhead | R16 | 2023-03-30 | 1 |  | 45 | 88 | 132 | 2023 | 2023 | R16
162168309164 | 169486309164 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-22 | 2022-12-22 | 2023-02-13 | 2023-04-17 | 2023-04-18 | Underground | R16 | 2023-04-17 | 1 | 38 | 46 | 2 | 84 | 2022 | 2023 | R16
169030156515 | 166589156515 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-06-28 | 2019-06-28 | 2019-06-28 |  | 2019-08-26 | Overhead | R16 | 2019-07-16 | 1 |  | 13 | 30 | 42 | 2019 | 2019 | R16
161328325477 | 169351325477 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-03-27 | 2023-03-27 | 2023-07-19 | 2023-09-05 | 2023-10-03 | Overhead | R16 | 2023-09-05 | 1 | 83 | 35 | 21 | 137 | 2023 | 2023 | R16
169050139665 | 166190139665 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-09 | 2019-01-09 | 2019-01-09 |  | 2019-02-19 | Underground | R16 | 2019-01-30 | 1 |  | 16 | 15 | 30 | 2019 | 2019 | R16
164358308820 | 164398308820 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-18 | 2023-02-07 | 2023-02-07 |  | 2023-07-11 | Underground | R16 | 2023-05-24 | 15 |  | 77 | 35 | 125 | 2023 | 2023 | R16
169301245386 | 160750245386 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-08-23 | 2021-08-23 | 2021-08-26 |  | 2023-03-13 | Overhead | R16 | 2022-02-18 | 1 | 4 | 127 | 277 | 406 | 2021 | 2023 | R16
161979304439 | 169290304439 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2022-12-21 | 2022-12-29 | 2023-01-30 | 2023-03-19 | 2023-03-22 | Underground | R16 | 2023-03-19 | 7 | 23 | 35 | 3 | 66 | 2022 | 2023 | R16
166510310980 | 161735310980 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-06 | 2023-01-06 | 2023-02-28 |  | 2023-05-18 | Underground | R16 | 2023-03-01 | 1 | 38 | 2 | 57 | 95 | 2023 | 2023 | R16
168238244415 | 167698244415 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-11 | 2021-08-20 | 2021-08-20 |  | 2021-11-01 | Overhead | R16 | 2021-09-29 | 8 |  | 29 | 24 | 59 | 2021 | 2021 | R16
163445323133 | 167570323133 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-03-20 | 2023-06-23 | 2023-06-23 | 2023-08-22 | 2023-08-23 | Overhead | R16 | 2023-08-22 | 70 |  | 43 | 2 | 113 | 2023 | 2023 | R16
161942308813 | 169267308813 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-08 | 2023-02-08 | 2023-02-08 |  | 2023-05-18 | Overhead | R16 | 2023-03-22 | 1 |  | 31 | 42 | 72 | 2023 | 2023 | R16
163927257573 | 164864257573 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-07-30 | 2021-07-30 | 2021-11-19 | 2022-03-03 | 2022-04-06 | Underground | R16 | 2022-03-03 | 1 | 81 | 75 | 25 | 179 | 2021 | 2022 | R16
169351163514 | 160957163514 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-02-01 | 2019-02-01 | 2019-09-06 |  | 2019-10-11 | Underground | R16 | 2019-09-30 | 1 | 156 | 17 | 10 | 181 | 2019 | 2019 | R16
160436249060 | 163794249060 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-07 | 2021-09-07 | 2021-09-22 |  | 2022-03-14 | Underground | R16 | 2022-02-24 | 1 | 12 | 112 | 13 | 135 | 2021 | 2022 | R16
167166323977 | 166624323977 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-21 | 2023-06-21 | 2023-07-06 | 2023-09-05 | 2023-10-05 | Underground | R16 | 2023-09-05 | 1 | 12 | 44 | 23 | 77 | 2023 | 2023 | R16
167880320073 | 161327320073 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-24 | 2023-05-24 | 2023-05-24 | 2023-08-11 | 2023-08-16 | Overhead | R16 | 2023-08-11 | 1 |  | 58 | 4 | 61 | 2023 | 2023 | R16
162522312794 | 167034312794 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-03-17 | 2023-03-17 | 2023-03-17 | 2023-03-30 | 2023-07-26 | Overhead | R16 | 2023-03-30 | 1 |  | 10 | 85 | 94 | 2023 | 2023 | R16
169418165447 | 162405165447 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-09-23 | 2019-09-23 | 2019-09-23 |  | 2021-11-10 | Underground | R16 | 2020-01-16 | 1 |  | 84 | 475 | 558 | 2019 | 2021 | R16
166370304739 | 160310304739 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-29 | 2023-01-03 | 2023-01-30 | 2023-04-14 | 2023-08-02 | Overhead | R16 | 2023-04-14 | 4 | 20 | 55 | 79 | 155 | 2022 | 2023 | R16
163885321890 | 160953321890 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-03 | 2023-06-12 | 2023-06-12 | 2023-12-11 | 2023-12-20 | Overhead | R16 | 2023-12-11 | 51 |  | 131 | 8 | 188 | 2023 | 2023 | R16
162132320965 | 160429320965 | RESIDENTIAL - MOBILE HOME | OH R16 RES NON RES OS | Residential | 2023-05-17 | 2023-06-02 | 2023-06-02 |  | 2023-12-04 | Overhead | R16 | 2023-11-16 | 13 |  | 120 | 13 | 144 | 2023 | 2023 | R16
169528145176 | 166673145176 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-01-10 | 2019-01-10 | 2019-03-07 |  | 2019-08-12 | Overhead | R16 | 2019-06-03 | 1 | 41 | 63 | 51 | 153 | 2019 | 2019 | R16
169544186240 | 169385186240 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-10-26 | 2019-10-26 | 2020-04-02 |  | 2021-08-23 | Underground | R16 |  | 0 | 114 |  |  | 476 | 2019 | 2021 | R16
165308240750 | 163723240750 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-26 | 2021-07-26 | 2021-07-26 | 2022-03-20 | 2022-03-23 | Overhead | R16 | 2022-03-20 | 1 |  | 170 | 3 | 173 | 2021 | 2022 | R16
169544186253 | 169444186253 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-10-26 | 2019-10-26 | 2020-04-02 |  | 2021-11-05 | Underground | R16 |  | 0 | 114 |  |  | 530 | 2019 | 2021 | R16
167315307897 | 167750307897 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-01 | 2023-02-01 | 2023-02-01 | 2023-02-09 | 2023-03-31 | Overhead | R16 | 2023-02-09 | 1 |  | 7 | 37 | 43 | 2023 | 2023 | R16
167359305791 | 160241305791 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-29 | 2023-01-12 | 2023-01-25 | 2023-06-09 | 2023-06-21 | Overhead | R16 | 2023-06-09 | 11 | 10 | 98 | 9 | 125 | 2022 | 2023 | R16
169865143633 | 164179143633 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-20 | 2019-02-20 | 2019-02-20 |  | 2019-04-15 | Underground | R16 | 2019-03-25 | 1 |  | 24 | 16 | 39 | 2019 | 2019 | R16
161139331102 | 167147331102 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-03-17 | 2023-03-17 | 2023-08-29 | 2023-12-06 | 2023-12-07 | Underground | R16 | 2023-12-06 | 1 | 118 | 72 | 2 | 190 | 2023 | 2023 | R16
161523246386 | 163252246386 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-02 | 2021-09-02 | 2021-09-02 | 2021-09-29 | 2021-11-02 | Overhead | R16 | 2021-09-29 | 1 |  | 20 | 25 | 44 | 2021 | 2021 | R16
164306325677 | 166146325677 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-19 | 2023-06-19 | 2023-07-20 | 2023-09-27 | 2023-09-29 | Underground | R16 | 2023-09-27 | 1 | 24 | 50 | 3 | 75 | 2023 | 2023 | R16
166850243120 | 167036243120 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2021-10-04 | 2022-12-01 | Overhead | R16 | 2021-10-04 | 1 |  | 40 | 304 | 343 | 2021 | 2022 | R16
165398311870 | 162305311870 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-23 | 2023-02-23 | 2023-03-09 |  | 2023-07-20 | Underground | R16 | 2023-03-09 | 1 | 11 |  | 96 | 106 | 2023 | 2023 | R16
167894303834 | 169112303834 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-20 | 2022-12-20 | 2022-12-22 |  | 2023-08-01 | Overhead | R16 | 2023-07-19 | 1 | 3 | 150 | 10 | 161 | 2022 | 2023 | R16
161197312612 | 164262312612 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2023-03-03 | 2023-03-03 | 2023-03-16 | 2023-08-03 | 2023-08-21 | Underground | R16 | 2023-08-03 | 1 | 10 | 101 | 13 | 122 | 2023 | 2023 | R16
160098164905 | 162312164905 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-07-26 | 2019-09-17 | 2019-09-17 |  | 2020-11-23 | Underground | R16 |  | 38 |  |  |  | 347 | 2019 | 2020 | R16
161538313518 | 168738313518 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-23 | 2023-03-23 | 2023-03-24 |  | 2023-08-11 | Overhead | R16 | 2023-04-14 | 1 | 2 | 16 | 86 | 102 | 2023 | 2023 | R16
164598248347 | 165581248347 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-02 | 2021-09-17 | 2021-09-17 | 2023-07-31 | 2023-11-02 | Overhead | R16 | 2023-07-31 | 35 |  | 487 | 69 | 589 | 2021 | 2023 | R16
166892319182 | 169672319182 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-06-26 | 2023-07-18 | Overhead | R16 | 2023-06-26 | 1 |  | 31 | 17 | 47 | 2023 | 2023 | R16
168904254581 | 166612254581 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-06 | 2021-08-06 | 2021-11-01 |  | 2022-10-20 | Underground | R16 |  | 1 | 62 |  |  | 315 | 2021 | 2022 | R16
167126324285 | 166619324285 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-21 | 2023-06-21 | 2023-07-06 | 2023-07-06 | 2023-10-13 | Underground | R16 | 2023-07-06 | 1 | 12 |  | 72 | 83 | 2023 | 2023 | R16
164399321467 | 163887321467 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-27 | 2023-08-17 | Overhead | R16 | 2023-06-27 | 1 |  | 15 | 38 | 52 | 2023 | 2023 | R16
168296313386 | 167716313386 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-21 | 2023-03-21 | 2023-03-22 |  | 2023-07-07 | Overhead | R16 | 2023-04-05 | 1 | 2 | 11 | 68 | 79 | 2023 | 2023 | R16
161193243303 | 164647243303 | NON-RESIDENTIAL - LODGING | R16 RESD AND NON RESD US | Residential | 2021-07-29 | 2021-07-30 | 2021-08-12 |  | 2021-10-25 | Underground | R16 |  | 2 | 10 |  |  | 63 | 2021 | 2021 | R16
160428148950 | 162320148950 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-04-08 | 2019-04-08 | 2019-04-11 |  | 2019-08-26 | Underground | R16 |  | 1 | 4 |  |  | 101 | 2019 | 2019 | R16
165213314611 | 165569314611 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-09 | 2023-04-03 | 2023-04-03 | 2023-08-23 | 2023-08-31 | Underground | R16 | 2023-08-23 | 18 |  | 103 | 7 | 126 | 2023 | 2023 | R16
162100316317 | 163194316317 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-04-12 | 2023-04-19 | 2023-04-19 |  | 2023-11-20 | Overhead | R16 | 2023-11-13 | 6 |  | 149 | 6 | 159 | 2023 | 2023 | R16
160730251786 | 165035251786 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-13 | 2021-09-13 | 2021-10-12 |  | 2022-02-02 | Underground | R16 | 2021-12-15 | 1 | 22 | 47 | 36 | 103 | 2021 | 2022 | R16
166513243805 | 166208243805 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-05 | 2021-08-05 | 2021-08-16 | 2021-12-14 | 2021-12-15 | Underground | R16 | 2021-12-14 | 1 | 8 | 87 | 2 | 95 | 2021 | 2021 | R16
162394250905 | 163832250905 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-07 | 2021-09-07 | 2021-10-06 | 2022-02-07 | 2022-03-23 | Underground | R16 | 2022-02-07 | 1 | 22 | 89 | 33 | 142 | 2021 | 2022 | R16
166155307451 | 166770307451 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-27 | 2023-01-27 | 2023-01-27 |  | 2023-05-18 | Overhead | R16 | 2023-03-17 | 1 |  | 36 | 45 | 80 | 2023 | 2023 | R16
164679304905 | 160776304905 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-04 | 2023-01-04 | 2023-01-04 | 2023-02-10 | 2023-02-13 | Overhead | R16 | 2023-02-10 | 1 |  | 28 | 2 | 29 | 2023 | 2023 | R16
164906282324 | 165274282324 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OD | Residential Subdivision | 2021-08-02 | 2021-09-28 | 2022-06-10 |  | 2022-09-13 | Overhead | R16 | 2022-08-08 | 42 | 184 | 42 | 27 | 292 | 2021 | 2022 | R16
160653202582 | 168059202582 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-10-21 | 2019-11-04 | 2020-09-02 |  | 2020-12-29 | Overhead | R16 |  | 11 | 218 |  |  | 312 | 2019 | 2020 | R16
164237317345 | 163433317345 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-13 | 2023-04-13 | 2023-04-29 |  | 2023-09-28 | Overhead | R16 | 2023-06-02 | 1 | 12 | 25 | 85 | 121 | 2023 | 2023 | R16
161812309257 | 168212309257 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-15 | 2023-01-07 | 2023-02-14 |  | 2023-08-30 | Underground | R16 | 2023-05-16 | 17 | 27 | 66 | 77 | 185 | 2022 | 2023 | R16
167230252029 | 168817252029 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-16 | 2021-10-14 | 2021-10-14 | 2021-10-26 | 2021-12-01 | Overhead | R16 | 2021-10-26 | 44 |  | 9 | 27 | 78 | 2021 | 2021 | R16
160973247021 | 162875247021 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-01 | 2021-09-08 | 2021-09-08 |  | 2022-01-18 | Overhead | R16 | 2021-11-01 | 6 |  | 39 | 57 | 100 | 2021 | 2022 | R16
167008244351 | 168802244351 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-16 |  | 2021-08-16 | 2021-11-18 | 2022-01-07 | Underground | R16 | 2021-11-18 |  |  | 69 | 37 | 105 | 2021 | 2022 | R16
166967245394 | 161594245394 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-26 | 2021-08-26 | 2021-08-26 |  | 2021-11-10 | Overhead | R16 | 2021-10-18 | 1 |  | 38 | 18 | 55 | 2021 | 2021 | R16
166100321701 | 163075321701 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-02 | 2023-06-08 | 2023-06-08 |  | 2023-08-20 | Overhead | R16 | 2023-06-30 | 5 |  | 17 | 36 | 56 | 2023 | 2023 | R16
160919208575 | 168413208575 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-10-16 | 2020-10-16 | 2020-10-26 |  | 2021-11-08 | Underground | R16 |  | 1 | 7 |  |  | 277 | 2020 | 2021 | R16
160921316176 | 164087316176 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-04-17 | 2023-04-18 | 2023-04-18 | 2023-04-18 | 2023-04-18 | Overhead | R16 | 2023-04-18 | 2 |  |  |  | 2 | 2023 | 2023 | R16
163697252045 | 165211252045 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-13 | 2021-09-13 | 2021-10-13 | 2021-11-29 | 2022-01-11 | Underground | R16 | 2021-11-29 | 1 | 23 | 34 | 32 | 87 | 2021 | 2022 | R16
160425304455 | 169472304455 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-12-22 | 2022-12-22 | 2023-01-30 | 2022-12-30 | 2023-12-28 | Underground | R16 | 2022-12-30 | 1 | 28 |  | 260 | 266 | 2022 | 2023 | R16
165567305601 | 167968305601 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-13 | 2022-12-13 | 2023-01-30 | 2023-02-23 | 2023-05-17 | Underground | R16 | 2023-02-23 | 1 | 35 | 19 | 60 | 112 | 2022 | 2023 | R16
166845249127 | 164748249127 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-09-10 | 2021-09-23 | 2021-09-23 |  | 2021-11-09 | Overhead | R16 | 2021-10-07 | 10 |  | 11 | 24 | 43 | 2021 | 2021 | R16
167824245267 | 161370245267 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-10-18 | 2021-11-13 | Overhead | R16 | 2021-10-18 | 1 |  | 39 | 20 | 58 | 2021 | 2021 | R16
161822254571 | 160717254571 | CUSTOMER UPGRADE IN SERVICE | UG SVC CONVERSION | Residential | 2021-08-23 | 2021-08-27 | 2021-11-01 |  | 2022-03-31 | Underground | R16 | 2022-03-04 | 5 | 47 | 90 | 20 | 159 | 2021 | 2022 | R16
164923317759 | 165903317759 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-04-25 | 2023-04-25 | 2023-05-03 | 2023-07-26 | 2023-10-16 | Overhead | R16 | 2023-07-26 | 1 | 7 | 61 | 59 | 125 | 2023 | 2023 | R16
168457323433 | 164088323433 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-07 | 2023-06-28 | 2023-06-28 | 2023-07-18 | 2023-08-24 | Overhead | R16 | 2023-07-18 | 16 |  | 15 | 28 | 57 | 2023 | 2023 | R16
163658315771 | 163780315771 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-14 | 2023-04-14 | 2023-04-14 | 2023-08-08 | 2023-11-07 | Overhead | R16 | 2023-08-08 | 1 |  | 83 | 66 | 148 | 2023 | 2023 | R16
167817327365 | 160788327365 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-13 | 2023-07-13 | 2023-08-04 | 2023-08-29 | 2023-10-03 | Underground | R16 | 2023-08-29 | 1 | 17 | 18 | 26 | 59 | 2023 | 2023 | R16
169640308463 | 167430308463 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-01-31 | 2023-02-06 | 2023-02-06 |  | 2023-08-10 | Overhead | R16 | 2023-05-08 | 5 |  | 66 | 69 | 138 | 2023 | 2023 | R16
168127324311 | 169936324311 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-16 | 2023-05-16 | 2023-07-07 | 2023-09-14 | 2023-09-21 | Underground | R16 | 2023-09-14 | 1 | 39 | 50 | 6 | 93 | 2023 | 2023 | R16
161651246277 | 162877246277 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-02 | 2021-09-02 | 2021-09-02 | 2022-01-07 | 2022-02-07 | Overhead | R16 | 2022-01-07 | 1 |  | 92 | 22 | 113 | 2021 | 2022 | R16
169103307203 | 166270307203 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-25 | 2023-01-25 | 2023-01-25 |  | 2023-03-31 | Overhead | R16 | 2023-02-13 | 1 |  | 14 | 35 | 48 | 2023 | 2023 | R16
166268308105 | 167859308105 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-02 | 2023-02-02 | 2023-02-02 |  | 2023-04-07 | Overhead | R16 | 2023-03-09 | 1 |  | 26 | 22 | 47 | 2023 | 2023 | R16
165173319241 | 164351319241 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-18 | 2023-04-18 | 2023-05-15 | 2023-06-02 | 2023-06-05 | Underground | R16 | 2023-06-02 | 1 | 20 | 15 | 2 | 35 | 2023 | 2023 | R16
167536317194 | 166347317194 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-27 | 2023-04-27 | 2023-04-28 | 2023-08-15 | 2023-08-16 | Overhead | R16 | 2023-08-15 | 1 | 2 | 78 | 2 | 80 | 2023 | 2023 | R16
165890319628 | 160672319628 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-19 | 2023-05-19 | 2023-05-19 | 2023-07-28 | 2023-08-25 | Overhead | R16 | 2023-07-28 | 1 |  | 51 | 21 | 71 | 2023 | 2023 | R16
169422308913 | 167387308913 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-31 | 2023-02-09 | 2023-02-09 | 2023-03-07 | 2023-03-08 | Overhead | R16 | 2023-03-07 | 8 |  | 19 | 2 | 27 | 2023 | 2023 | R16
165539321891 | 161011321891 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-03 | 2023-06-12 | 2023-06-12 | 2023-07-24 | 2023-07-24 | Overhead | R16 | 2023-07-24 | 51 |  | 31 |  | 81 | 2023 | 2023 | R16
161738275944 | 162245275944 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-14 | 2022-04-14 | 2022-04-14 |  | 2022-08-03 | Overhead | R16 | 2022-06-20 | 1 |  | 48 | 33 | 80 | 2022 | 2022 | R16
161461306519 | 165206306519 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-01-20 | 2023-01-20 | 2023-01-30 | 2023-01-20 | 2023-11-08 | Overhead | R16 | 2023-01-20 | 1 | 7 |  | 209 | 209 | 2023 | 2023 | R16
161005317893 | 167789317893 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-04 | 2023-05-04 | 2023-05-04 | 2023-07-27 | 2023-08-02 | Overhead | R16 | 2023-07-27 | 1 |  | 61 | 5 | 65 | 2023 | 2023 | R16
164525309410 | 164149309410 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-18 | 2023-02-13 | 2023-02-14 |  | 2023-07-07 | Overhead | R16 | 2023-02-14 | 19 | 2 |  | 104 | 123 | 2023 | 2023 | R16
166186317510 | 166797317510 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-01 | 2023-05-01 | 2023-05-01 | 2023-05-26 | 2023-06-19 | Overhead | R16 | 2023-05-26 | 1 |  | 20 | 17 | 36 | 2023 | 2023 | R16
168097247319 | 162975247319 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES UD | Residential | 2021-09-02 | 2021-09-02 | 2021-09-10 | 2021-12-20 | 2021-12-21 | Underground | R16 | 2021-12-20 | 1 | 7 | 72 | 2 | 79 | 2021 | 2021 | R16
164471327637 | 165792327637 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-25 | 2023-08-08 | 2023-08-08 | 2023-11-14 | 2023-12-01 | Underground | R16 | 2023-11-14 | 76 |  | 71 | 14 | 159 | 2023 | 2023 | R16
169951317993 | 167708317993 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-04 | 2023-05-04 | 2023-05-04 | 2023-10-25 | 2023-11-21 | Underground | R16 | 2023-10-25 | 1 |  | 125 | 20 | 144 | 2023 | 2023 | R16
162283318557 | 168817318557 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-09 | 2023-05-09 | 2023-05-10 | 2023-06-12 | 2023-06-13 | Overhead | R16 | 2023-06-12 | 1 | 2 | 24 | 2 | 26 | 2023 | 2023 | R16
168542241323 | 164684241323 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-29 | 2021-07-29 | 2021-07-29 |  | 2023-07-07 | Overhead | R16 | 2021-10-25 | 1 |  | 63 | 445 | 507 | 2021 | 2023 | R16
168025259991 | 162873259991 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE NON RES US | Commercial | 2021-09-01 | 2021-09-01 | 2021-12-06 | 2022-05-31 | 2022-06-15 | Underground | R16 | 2022-05-31 | 1 | 69 | 127 | 12 | 206 | 2021 | 2022 | R16
160704324142 | 166368324142 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-20 | 2023-06-20 | 2023-07-05 | 2023-10-23 | 2023-11-01 | Overhead | R16 | 2023-10-23 | 1 | 12 | 79 | 8 | 97 | 2023 | 2023 | R16
167554323478 | 168127323478 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-28 | 2023-06-28 | 2023-06-28 | 2023-08-21 | 2023-09-28 | Overhead | R16 | 2023-08-21 | 1 |  | 39 | 29 | 67 | 2023 | 2023 | R16
165081304484 | 169120304484 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-12-20 | 2022-12-20 | 2023-01-30 | 2023-04-11 | 2023-08-08 | Underground | R16 | 2023-04-11 | 1 | 30 | 52 | 86 | 166 | 2022 | 2023 | R16
161449311833 | 165204311833 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-03-23 | 2023-03-24 | Underground | R16 | 2023-03-23 | 1 |  | 12 | 2 | 13 | 2023 | 2023 | R16
160088314239 | 160574314239 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-31 | 2023-03-31 | 2023-03-31 | 2023-06-09 | 2023-06-30 | Overhead | R16 | 2023-06-09 | 1 |  | 51 | 16 | 66 | 2023 | 2023 | R16
167138324792 | 169965324792 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-16 | 2023-06-16 | 2023-07-12 | 2023-08-16 | 2023-08-31 | Underground | R16 | 2023-08-16 | 24 | 19 | 26 | 12 | 78 | 2023 | 2023 | R16
168364308590 | 168464308590 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-06 | 2023-02-06 | 2023-02-06 |  | 2023-05-04 | Overhead | R16 | 2023-02-09 | 1 |  | 4 | 61 | 64 | 2023 | 2023 | R16
167591312639 | 166314312639 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-14 | 2023-03-14 | 2023-03-16 | 2023-05-08 | 2023-06-12 | Overhead | R16 | 2023-05-08 | 1 | 3 | 38 | 26 | 65 | 2023 | 2023 | R16
165152322591 | 166008322591 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-19 | 2023-06-19 | 2023-06-19 | 2023-06-22 | 2023-08-01 | Overhead | R16 | 2023-06-22 | 1 |  | 4 | 29 | 32 | 2023 | 2023 | R16
168764308361 | 168242308361 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-03 | 2023-02-03 | 2023-02-03 | 2023-04-06 | 2023-04-07 | Overhead | R16 | 2023-04-06 | 1 |  | 45 | 2 | 46 | 2023 | 2023 | R16
168948323675 | 168326323675 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-29 | 2023-06-29 | 2023-06-29 | 2023-08-08 | 2023-08-23 | Overhead | R16 | 2023-08-08 | 1 |  | 29 | 12 | 40 | 2023 | 2023 | R16
165727244806 | 160052244806 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-19 | 2021-08-23 | 2021-08-23 | 2022-01-21 | 2022-03-25 | Overhead | R16 | 2022-01-21 | 3 |  | 110 | 46 | 157 | 2021 | 2022 | R16
165758308749 | 163415308749 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-12 | 2023-01-12 | 2023-02-08 | 2023-04-24 | 2023-08-18 | Underground | R16 | 2023-04-24 | 1 | 20 | 54 | 85 | 157 | 2023 | 2023 | R16
167887323462 | 167589323462 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-27 |  | 2023-06-27 | 2023-09-13 | 2023-10-10 | Overhead | R16 | 2023-09-13 |  |  | 57 | 20 | 76 | 2023 | 2023 | R16
160255322618 | 165045322618 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-13 | 2023-06-13 | 2023-06-19 | 2023-07-18 | 2023-07-18 | Overhead | R16 | 2023-07-18 | 1 | 5 | 22 |  | 26 | 2023 | 2023 | R16
168658328542 | 169642328542 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-07 | 2023-07-07 | 2023-08-16 | 2023-10-03 | 2023-11-03 | Underground | R16 | 2023-10-03 | 1 | 29 | 35 | 24 | 86 | 2023 | 2023 | R16
163654318829 | 168258318829 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-22 | 2023-03-22 | 2023-05-11 | 2023-07-28 | 2023-09-25 | Overhead | R16 | 2023-07-28 | 1 | 37 | 57 | 42 | 134 | 2023 | 2023 | R16
169802314952 | 167030314952 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-16 | 2023-03-16 | 2023-04-06 | 2023-06-16 | 2023-06-29 | Underground | R16 | 2023-06-16 | 1 | 16 | 52 | 10 | 76 | 2023 | 2023 | R16
161662307322 | 166434307322 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-26 | 2023-01-26 | 2023-01-26 |  | 2023-06-27 | Overhead | R16 | 2023-06-06 | 1 |  | 94 | 16 | 109 | 2023 | 2023 | R16
162241319222 | 169709319222 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-06-21 | 2023-06-22 | Overhead | R16 | 2023-06-21 | 1 |  | 28 | 2 | 29 | 2023 | 2023 | R16
166520306941 | 165416306941 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-23 | 2023-01-23 | 2023-01-30 | 2023-01-23 | 2023-05-16 | Overhead | R16 | 2023-01-23 | 1 | 6 |  | 82 | 82 | 2023 | 2023 | R16
166053320648 | 162460320648 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-30 | 2023-05-30 | 2023-05-30 | 2023-07-18 | 2023-08-09 | Overhead | R16 | 2023-07-18 | 1 |  | 36 | 17 | 52 | 2023 | 2023 | R16
169588242305 | 166340242305 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-05 | 2021-08-05 | 2021-08-05 |  | 2021-10-25 | Overhead | R16 | 2021-09-08 | 1 |  | 25 | 34 | 58 | 2021 | 2021 | R16
167498325892 | 168249325892 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-29 | 2023-06-29 | 2023-07-21 | 2023-09-14 | 2023-09-29 | Underground | R16 | 2023-09-14 | 1 | 17 | 40 | 12 | 67 | 2023 | 2023 | R16
164569283266 | 162567283266 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-31 | 2022-06-09 | 2022-06-20 | 2022-07-06 | 2022-08-10 | Overhead | R16 | 2022-07-06 | 203 | 8 | 13 | 26 | 247 | 2021 | 2022 | R16
164696174913 | 160361174913 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2019-01-30 | 2019-01-31 | 2019-12-19 |  | 2020-06-09 | Underground | R16 | 2020-03-09 | 2 | 231 | 58 | 67 | 355 | 2019 | 2020 | R16
168514308055 | 165487308055 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-23 | 2023-01-23 | 2023-02-02 | 2023-06-30 | 2023-07-21 | Underground | R16 | 2023-06-30 | 1 | 9 | 107 | 16 | 130 | 2023 | 2023 | R16
163352313455 | 161850313455 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-21 | 2023-02-21 | 2023-03-23 | 2023-06-28 | 2023-06-29 | Underground | R16 | 2023-06-28 | 1 | 23 | 70 | 2 | 93 | 2023 | 2023 | R16
167839243306 | 167846243306 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-12 | 2021-08-12 | 2021-08-12 |  | 2021-10-25 | Overhead | R16 | 2021-09-02 | 1 |  | 16 | 38 | 53 | 2021 | 2021 | R16
164738143664 | 161853143664 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-02-06 | 2019-02-19 | 2019-02-19 |  | 2019-08-12 | Underground | R16 | 2019-05-28 | 10 |  | 71 | 55 | 134 | 2019 | 2019 | R16
167587314887 | 160248314887 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2022-12-29 | 2023-01-03 | 2023-04-06 |  | 2023-05-24 | Overhead | R16 |  | 4 | 68 |  |  | 105 | 2022 | 2023 | R16
164692243345 | 168042243345 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-12 | 2021-08-12 | 2021-08-12 |  | 2022-10-19 | Overhead | R16 |  | 1 |  |  |  | 310 | 2021 | 2022 | R16
161251253835 | 166647253835 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2021-08-06 | 2021-08-27 | 2021-10-26 | 2022-06-23 | 2022-07-18 | Underground | R16 | 2022-06-23 | 16 | 43 | 173 | 18 | 247 | 2021 | 2022 | R16
168253325399 | 164520325399 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-09 | 2023-06-09 | 2023-07-18 | 2023-10-18 | 2023-10-25 | Overhead | R16 | 2023-10-18 | 1 | 28 | 67 | 6 | 99 | 2023 | 2023 | R16
163640309335 | 169833309335 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-10 | 2023-02-10 | 2023-02-13 | 2023-04-14 | 2023-04-17 | Overhead | R16 | 2023-04-14 | 1 | 2 | 45 | 2 | 47 | 2023 | 2023 | R16
169562304604 | 160601304604 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-03 | 2023-01-03 | 2023-01-03 | 2023-01-03 | 2023-02-01 | Overhead | R16 | 2023-01-03 | 1 |  |  | 22 | 22 | 2023 | 2023 | R16
165462313581 | 166068313581 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-13 | 2023-03-24 | 2023-03-24 | 2023-04-05 | 2023-04-10 | Overhead | R16 | 2023-04-05 | 10 |  | 9 | 4 | 21 | 2023 | 2023 | R16
163722315614 | 160131315614 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-29 | 2023-04-13 | 2023-04-13 |  | 2023-05-18 | Overhead | R16 | 2023-04-24 | 12 |  | 8 | 19 | 37 | 2023 | 2023 | R16
165437242214 | 166262242214 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-08-05 | 2021-08-05 | 2021-08-05 | 2021-10-27 | 2021-12-02 | Underground | R16 | 2021-10-27 | 1 |  | 60 | 27 | 86 | 2021 | 2021 | R16
168280306859 | 165191306859 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-01-20 | 2023-01-20 | 2023-01-30 | 2023-01-24 | 2023-05-11 | Overhead | R16 | 2023-01-24 | 1 | 7 |  | 78 | 80 | 2023 | 2023 | R16
165165149738 | 164488149738 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-04-19 | 2019-04-19 | 2019-04-19 |  | 2023-06-08 | Underground | R16 |  | 1 |  |  |  | 1080 | 2019 | 2023 | R16
169615240937 | 164405240937 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-28 |  | 2021-07-28 | 2021-11-16 | 2022-01-04 | Overhead | R16 | 2021-11-16 |  |  | 80 | 36 | 115 | 2021 | 2022 | R16
166330323480 | 167313323480 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2023-05-02 | 2023-05-02 | 2023-06-27 | 2023-09-20 | 2023-10-20 | Underground | R16 | 2023-09-20 | 1 | 41 | 62 | 23 | 124 | 2023 | 2023 | R16
169750320266 | 161693320266 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-25 | 2023-05-25 | 2023-05-25 | 2023-07-06 | 2023-07-07 | Overhead | R16 | 2023-07-06 | 1 |  | 31 | 2 | 32 | 2023 | 2023 | R16
164646317856 | 167806317856 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-05-04 | 2023-05-04 | 2023-05-04 | 2023-11-27 | 2023-12-13 | Underground | R16 | 2023-11-27 | 1 |  | 148 | 13 | 160 | 2023 | 2023 | R16
163829247010 | 164405247010 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-09 | 2021-09-09 | 2021-09-09 | 2021-09-20 | 2021-11-01 | Overhead | R16 | 2021-09-20 | 1 |  | 8 | 31 | 38 | 2021 | 2021 | R16
164575276395 | 163818276395 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-07-27 | 2022-01-24 | 2022-04-19 |  | 2022-05-19 | Overhead | R16 |  | 130 | 62 |  |  | 213 | 2021 | 2022 | R16
164034247923 | 164376247923 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2021-09-09 | 2021-09-09 | 2021-09-14 | 2023-08-03 | 2023-09-17 | Underground | R16 | 2023-08-03 | 1 | 4 | 493 | 32 | 527 | 2021 | 2023 | R16
164321323004 | 166432323004 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-20 | 2023-06-20 | 2023-06-22 | 2023-08-02 | 2023-08-16 | Overhead | R16 | 2023-08-02 | 1 | 3 | 30 | 11 | 42 | 2023 | 2023 | R16
161239241716 | 165584241716 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-03 | 2021-08-03 | 2021-08-03 |  | 2021-10-11 | Overhead | R16 | 2021-09-13 | 1 |  | 30 | 21 | 50 | 2021 | 2021 | R16
168020307025 | 165671307025 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-24 | 2023-01-24 | 2023-01-30 | 2023-08-16 | 2023-10-20 | Overhead | R16 | 2023-08-16 | 1 | 5 | 143 | 48 | 194 | 2023 | 2023 | R16
160570323639 | 168561323639 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-29 | 2023-06-29 | 2023-06-29 | 2023-07-31 | 2023-09-05 | Overhead | R16 | 2023-07-31 | 1 |  | 23 | 27 | 49 | 2023 | 2023 | R16
165174305335 | 167967305335 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-13 | 2022-12-13 | 2023-01-30 | 2023-03-01 | 2023-03-31 | Underground | R16 | 2023-03-01 | 1 | 35 | 23 | 23 | 79 | 2022 | 2023 | R16
169262333198 | 160440333198 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-11 | 2023-07-11 | 2023-09-21 | 2023-11-27 | 2023-12-21 | Underground | R16 | 2023-11-27 | 1 | 53 | 48 | 19 | 118 | 2023 | 2023 | R16
164276323735 | 169773323735 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-28 | 2023-06-30 | 2023-06-30 | 2023-08-23 | 2023-08-28 | Overhead | R16 | 2023-08-23 | 69 |  | 39 | 4 | 110 | 2023 | 2023 | R16
160221324380 | 166616324380 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-15 | 2023-03-15 | 2023-07-07 | 2023-08-22 | 2023-08-29 | Underground | R16 | 2023-08-22 | 1 | 83 | 33 | 6 | 120 | 2023 | 2023 | R16
167672244909 | 160383244909 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-08-20 | 2021-08-20 | 2021-08-23 |  | 2022-08-11 | Underground | R16 | 2022-07-01 | 1 | 2 | 225 | 30 | 255 | 2021 | 2022 | R16
163617245251 | 161306245251 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-26 | 2021-08-26 | 2021-08-26 |  | 2022-02-02 | Overhead | R16 | 2021-12-15 | 1 |  | 80 | 36 | 115 | 2021 | 2022 | R16
160014323852 | 166289323852 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-20 | 2023-06-20 | 2023-06-30 | 2023-08-09 | 2023-09-28 | Underground | R16 | 2023-08-09 | 1 | 9 | 29 | 37 | 73 | 2023 | 2023 | R16
166945244116 | 169517244116 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-18 | 2021-08-18 | 2021-08-18 |  | 2021-10-28 | Overhead | R16 | 2021-09-27 | 1 |  | 29 | 24 | 52 | 2021 | 2021 | R16
163213243030 | 167826243030 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-11 | 2021-08-11 | 2021-08-11 |  | 2022-02-10 | Overhead | R16 |  | 1 |  |  |  | 132 | 2021 | 2022 | R16
168235327750 | 165038327750 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-06-13 | 2023-07-07 | 2023-08-09 | 2023-10-13 | 2023-10-20 | Overhead | R16 | 2023-10-13 | 19 | 24 | 48 | 6 | 94 | 2023 | 2023 | R16
161918244290 | 166337244290 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-05 | 2021-08-18 | 2021-08-19 | 2023-08-08 | 2023-07-03 | Overhead | R16 | 2023-08-08 | 10 | 2 | 514 |  | 498 | 2021 | 2023 | R16
161629331886 | 168514331886 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-23 | 2023-03-23 | 2023-09-07 | 2023-09-11 | 2023-10-31 | Underground | R16 | 2023-09-11 | 1 | 121 | 3 | 37 | 159 | 2023 | 2023 | R16
168073310210 | 168460310210 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-05 | 2023-02-05 | 2023-02-23 | 2023-08-03 | 2023-10-04 | Underground | R16 | 2023-08-03 | 0 | 14 | 116 | 45 | 173 | 2023 | 2023 | R16
161312243711 | 168439243711 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-14 | 2021-08-14 | 2021-08-14 | 2021-11-30 | 2022-01-13 | Underground | R16 | 2021-11-30 | 0 |  | 77 | 33 | 109 | 2021 | 2022 | R16
165967139801 | 166503139801 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-10 | 2019-01-10 | 2019-01-10 |  | 2019-04-08 | Overhead | R16 | 2019-03-05 | 1 |  | 39 | 25 | 63 | 2019 | 2019 | R16
160041245393 | 161587245393 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-10-27 | 2022-04-01 | Overhead | R16 | 2021-10-27 | 1 |  | 45 | 113 | 157 | 2021 | 2022 | R16
164967322120 | 165050322120 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-13 | 2023-06-13 | 2023-06-13 | 2023-06-19 | 2023-12-05 | Overhead | R16 | 2023-06-19 | 1 |  | 5 | 122 | 126 | 2023 | 2023 | R16
164742324318 | 169748324318 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-07 | 2023-07-07 | 2023-07-07 | 2023-08-10 | 2023-08-10 | Overhead | R16 | 2023-08-10 | 1 |  | 25 |  | 25 | 2023 | 2023 | R16
166141142920 | 167590142920 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-01-16 | 2019-01-16 | 2019-02-11 |  | 2019-10-30 | Underground | R16 | 2019-10-25 | 1 | 19 | 185 | 4 | 206 | 2019 | 2019 | R16
165575245843 | 161519245843 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-26 | 2021-08-30 | 2021-08-30 | 2021-10-25 | 2023-06-09 | Overhead | R16 | 2021-10-25 | 3 |  | 41 | 425 | 467 | 2021 | 2023 | R16
168287245551 | 161840245551 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-27 | 2021-08-27 | 2021-08-27 |  | 2022-05-19 | Overhead | R16 | 2022-04-28 | 1 |  | 175 | 16 | 190 | 2021 | 2022 | R16
166226203176 | 168984203176 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2020-05-26 | 2020-05-26 | 2020-09-09 |  | 2021-04-23 | Underground | R16 | 2021-02-03 | 1 | 77 | 106 | 58 | 239 | 2020 | 2021 | R16
166228153762 | 161373153762 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-29 | 2019-05-29 | 2019-05-29 |  | 2019-09-03 | Overhead | R16 | 2019-08-26 | 1 |  | 64 | 7 | 70 | 2019 | 2019 | R16
163577308567 | 168612308567 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-06 | 2023-02-06 | 2023-02-06 |  | 2023-04-07 | Overhead | R16 | 2023-02-13 | 1 |  | 6 | 40 | 45 | 2023 | 2023 | R16
168167320401 | 165394320401 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-08 | 2023-03-08 | 2023-05-25 | 2023-09-28 | 2023-10-11 | Overhead | R16 | 2023-09-28 | 1 | 57 | 91 | 10 | 156 | 2023 | 2023 | R16
166318149982 | 168909149982 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2019-03-19 | 2019-03-20 | 2019-04-22 |  | 2021-11-13 | Underground | R16 |  | 2 | 24 |  |  | 694 | 2019 | 2021 | R16
162653315139 | 162391315139 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-08 | 2023-04-08 | 2023-04-08 | 2023-10-19 | 2023-12-05 | Overhead | R16 | 2023-10-19 | 0 |  | 139 | 34 | 172 | 2023 | 2023 | R16
166118328737 | 160509328737 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-12 | 2023-08-18 | 2023-08-18 | 2023-10-02 | 2023-12-04 | Overhead | R16 | 2023-10-02 | 28 |  | 32 | 46 | 104 | 2023 | 2023 | R16
164997316148 | 162652316148 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-10 | 2023-04-10 | 2023-04-18 | 2023-07-20 | 2023-08-10 | Underground | R16 | 2023-07-20 | 1 | 7 | 68 | 16 | 89 | 2023 | 2023 | R16
168316324320 | 164796324320 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-12 | 2023-06-12 | 2023-07-06 | 2023-07-17 | 2023-08-03 | Overhead | R16 | 2023-07-17 | 1 | 19 | 8 | 14 | 39 | 2023 | 2023 | R16
164594319282 | 164350319282 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-18 | 2023-04-18 | 2023-05-16 | 2023-07-31 | 2023-08-09 | Underground | R16 | 2023-07-31 | 1 | 21 | 55 | 8 | 82 | 2023 | 2023 | R16
167246306106 | 163929306106 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-17 | 2023-01-17 | 2023-01-25 | 2023-03-07 | 2023-04-08 | Overhead | R16 | 2023-03-07 | 1 | 7 | 30 | 24 | 59 | 2023 | 2023 | R16
161362325350 | 169286325350 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-05 | 2023-07-18 | 2023-07-18 | 2023-07-27 | 2023-10-02 | Underground | R16 | 2023-07-27 | 10 |  | 8 | 48 | 64 | 2023 | 2023 | R16
166580235454 | 162563235454 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2021-06-07 | 2021-06-07 | 2021-06-18 |  | 2023-06-08 | Underground | R16 |  | 1 | 10 |  |  | 524 | 2021 | 2023 | R16
168997322116 | 164348322116 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-18 | 2023-04-18 | 2023-06-15 | 2023-09-19 | 2023-09-27 | Underground | R16 | 2023-09-19 | 1 | 43 | 69 | 7 | 117 | 2023 | 2023 | R16
164357325668 | 166183325668 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-19 | 2023-06-19 | 2023-07-20 |  | 2023-08-25 | Underground | R16 | 2023-07-20 | 1 | 24 |  | 27 | 50 | 2023 | 2023 | R16
161666310902 | 162281310902 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-09 | 2023-01-09 | 2023-02-27 |  | 2023-06-07 | Underground | R16 | 2023-06-06 | 1 | 36 | 72 | 2 | 108 | 2023 | 2023 | R16
163638304120 | 169483304120 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-22 | 2022-12-22 | 2022-12-27 |  | 2023-02-12 | Overhead | R16 | 2023-01-25 | 1 | 4 | 22 | 13 | 37 | 2022 | 2023 | R16
164813324816 | 168583324816 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-30 | 2023-06-30 | 2023-07-13 | 2023-07-20 | 2023-08-18 | Overhead | R16 | 2023-07-20 | 1 | 10 | 6 | 22 | 36 | 2023 | 2023 | R16
160814316721 | 165510316721 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-23 | 2023-04-23 | 2023-04-23 |  | 2023-08-18 | Overhead | R16 | 2023-05-04 | 0 |  | 9 | 77 | 85 | 2023 | 2023 | R16
169735308096 | 168112308096 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-03 | 2023-02-03 | 2023-02-03 | 2023-02-24 | 2023-03-17 | Overhead | R16 | 2023-02-24 | 1 |  | 16 | 16 | 31 | 2023 | 2023 | R16
169829322059 | 162488322059 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-24 | 2023-02-24 | 2023-06-14 | 2023-10-23 | 2023-11-01 | Underground | R16 | 2023-10-23 | 1 | 79 | 94 | 8 | 179 | 2023 | 2023 | R16
169564314077 | 168975314077 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2023-03-24 | 2023-03-24 | 2023-03-30 |  | 2023-10-04 | Underground | R16 |  | 1 | 5 |  |  | 139 | 2023 | 2023 | R16
168746312493 | 169411312493 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-08 | 2023-02-08 | 2023-03-14 | 2023-12-28 | 2023-12-29 | Underground | R16 | 2023-12-28 | 1 | 25 | 208 | 2 | 233 | 2023 | 2023 | R16
169403246136 | 162931246136 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-09-01 | 2021-09-01 | 2021-09-01 |  | 2023-02-03 | Overhead | R16 | 2022-11-23 | 1 |  | 321 | 53 | 373 | 2021 | 2023 | R16
166369307286 | 160713307286 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-03 | 2023-01-03 | 2023-01-26 |  | 2023-11-30 | Underground | R16 | 2023-03-01 | 1 | 18 | 25 | 197 | 238 | 2023 | 2023 | R16
166795159336 | 162393159336 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-07-29 | 2019-07-29 | 2019-07-30 |  | 2019-12-06 | Underground | R16 |  | 1 | 2 |  |  | 95 | 2019 | 2019 | R16
166757324359 | 167699324359 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-20 | 2023-07-07 | 2023-07-07 | 2023-10-26 | 2023-11-13 | Overhead | R16 | 2023-10-26 | 80 |  | 80 | 13 | 171 | 2023 | 2023 | R16
167910319402 | 163932319402 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-16 | 2023-01-16 | 2023-05-17 | 2023-08-10 | 2023-12-07 | Underground | R16 | 2023-08-10 | 1 | 88 | 62 | 86 | 234 | 2023 | 2023 | R16
165461245780 | 162020245780 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-29 | 2021-08-29 | 2021-08-29 | 2021-12-10 | 2021-12-10 | Underground | R16 | 2021-12-10 | 0 |  | 75 |  | 75 | 2021 | 2021 | R16
165343303021 | 167482303021 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-11 | 2022-12-11 | 2023-01-30 | 2022-12-11 | 2023-11-02 | Overhead | R16 | 2022-12-11 | 0 | 36 |  | 234 | 234 | 2022 | 2023 | R16
167940314341 | 168002314341 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-21 | 2023-03-31 | 2023-03-31 |  | 2023-08-18 | Overhead | R16 | 2023-05-04 | 9 |  | 25 | 77 | 109 | 2023 | 2023 | R16
166950149288 | 163841149288 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-04-16 | 2019-04-16 | 2019-04-16 |  | 2019-06-03 | Underground | R16 | 2019-05-07 | 1 |  | 16 | 20 | 35 | 2019 | 2019 | R16
166861317141 | 166148317141 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-27 | 2023-04-27 | 2023-04-27 | 2023-05-04 | 2023-06-12 | Overhead | R16 | 2023-05-04 | 1 |  | 6 | 28 | 33 | 2023 | 2023 | R16
169569323865 | 163762323865 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-06 | 2023-06-08 | 2023-06-30 | 2023-10-16 | 2023-11-03 | Underground | R16 | 2023-10-16 | 3 | 17 | 77 | 15 | 109 | 2023 | 2023 | R16
166956149375 | 163408149375 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-04-15 | 2019-04-17 | 2019-04-17 |  | 2019-06-03 | Overhead | R16 | 2019-05-08 | 3 |  | 16 | 19 | 36 | 2019 | 2019 | R16
163247307484 | 161728307484 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-05 | 2023-01-27 | 2023-01-27 |  | 2023-06-22 | Overhead | R16 | 2023-06-06 | 17 |  | 93 | 13 | 121 | 2023 | 2023 | R16
165666245095 | 161112245095 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-08-24 | 2021-08-24 | 2021-08-24 |  | 2022-03-14 | Overhead | R16 |  | 1 |  |  |  | 145 | 2021 | 2022 | R16
167547324666 | 169157324666 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2023-05-11 | 2023-05-18 | 2023-07-10 |  | 2023-09-25 | Underground | R16 | 2023-09-05 | 6 | 38 | 42 | 15 | 98 | 2023 | 2023 | R16
169601315529 | 167715315529 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-02-01 | 2023-02-01 | 2023-04-12 | 2023-11-03 | 2023-11-15 | Underground | R16 | 2023-11-03 | 1 | 51 | 148 | 9 | 206 | 2023 | 2023 | R16
162540326469 | 162326326469 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-30 | 2023-05-30 | 2023-07-26 | 2023-08-18 | 2023-09-28 | Underground | R16 | 2023-08-18 | 1 | 42 | 18 | 30 | 88 | 2023 | 2023 | R16
169185306680 | 165033306680 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-01-19 | 2023-01-20 | 2023-01-30 | 2023-01-20 | 2023-03-31 | Overhead | R16 | 2023-01-20 | 2 | 7 |  | 51 | 52 | 2023 | 2023 | R16
161246252254 | 162197252254 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2021-08-31 | 2021-08-31 | 2021-10-15 | 2022-04-08 | 2022-04-27 | Underground | R16 | 2022-04-08 | 1 | 34 | 126 | 14 | 172 | 2021 | 2022 | R16
169171254980 | 168571254980 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-08-13 | 2021-08-13 | 2021-11-03 |  | 2022-02-18 | Underground | R16 |  | 1 | 59 |  |  | 136 | 2021 | 2022 | R16
164561249710 | 164178249710 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2021-09-09 | 2021-09-09 | 2021-09-27 | 2022-06-30 | 2022-04-01 | Underground | R16 | 2022-06-30 | 1 | 13 | 199 |  | 147 | 2021 | 2022 | R16
166466307678 | 165732307678 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-24 | 2023-01-31 | 2023-01-31 | 2023-02-27 | 2023-03-25 | Overhead | R16 | 2023-02-27 | 6 |  | 20 | 20 | 44 | 2023 | 2023 | R16
168243308705 | 167103308705 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-30 | 2023-02-07 | 2023-02-07 |  | 2023-08-09 | Overhead | R16 | 2023-04-14 | 7 |  | 49 | 84 | 138 | 2023 | 2023 | R16
167108156938 | 161147156938 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-05-28 | 2019-05-29 | 2019-07-02 |  | 2020-08-20 | Underground | R16 | 2020-06-19 | 2 | 25 | 254 | 45 | 323 | 2019 | 2020 | R16
162108317277 | 163296317277 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-12 | 2023-04-28 | 2023-04-28 | 2023-10-19 | 2023-11-08 | Underground | R16 | 2023-10-19 | 13 |  | 125 | 15 | 151 | 2023 | 2023 | R16
166510317694 | 167164317694 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-02 | 2023-05-02 | 2023-05-02 | 2023-09-20 | 2023-10-09 | Overhead | R16 | 2023-09-20 | 1 |  | 102 | 14 | 115 | 2023 | 2023 | R16
164604306202 | 161292306202 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-05 | 2023-01-05 | 2023-01-30 | 2023-03-01 | 2023-03-02 | Underground | R16 | 2023-03-01 | 1 | 18 | 23 | 2 | 41 | 2023 | 2023 | R16
164533314532 | 162392314532 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-23 | 2023-03-29 | 2023-04-03 | 2023-08-01 | 2023-08-04 | Underground | R16 | 2023-08-01 | 25 | 4 | 87 | 4 | 117 | 2023 | 2023 | R16
160674317568 | 166888317568 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-05-01 | 2023-05-01 | 2023-05-01 | 2023-05-18 | 2023-05-19 | Overhead | R16 | 2023-05-18 | 1 |  | 14 | 2 | 15 | 2023 | 2023 | R16
166642306551 | 165217306551 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-20 | 2023-01-20 | 2023-01-20 |  | 2023-08-28 | Overhead | R16 | 2023-07-21 | 1 |  | 131 | 27 | 157 | 2023 | 2023 | R16
164255251503 | 163442251503 | NON-RESIDENTIAL - HEALTH CARE | UG R16 RESD AND NON RESD UD | Commercial | 2021-07-24 | 2021-09-08 | 2021-10-11 | 2022-04-28 | 2022-05-17 | Underground | R16 | 2022-04-28 | 33 | 24 | 144 | 14 | 212 | 2021 | 2022 | R16
167304244106 | 169096244106 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-17 | 2021-08-17 | 2021-08-17 |  | 2021-10-25 | Overhead | R16 | 2021-09-02 | 1 |  | 13 | 38 | 50 | 2021 | 2021 | R16
167616141873 | 166106141873 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-01-08 | 2019-01-08 | 2019-02-01 |  | 2020-06-09 | Underground | R16 | 2020-01-29 | 1 | 19 | 259 | 95 | 371 | 2019 | 2020 | R16
164204241333 | 163227241333 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-23 | 2021-07-23 | 2021-07-29 | 2023-10-18 | 2023-11-20 | Underground | R16 | 2023-10-18 | 1 | 5 | 580 | 24 | 607 | 2021 | 2023 | R16
160435247062 | 164093247062 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-09-08 | 2021-09-08 | 2021-09-08 | 2021-09-09 | 2021-10-26 | Overhead | R16 | 2021-09-09 | 1 |  | 2 | 34 | 35 | 2021 | 2021 | R16
169187245014 | 160970245014 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-24 | 2021-08-24 | 2021-08-24 | 2021-09-01 | 2021-11-08 | Overhead | R16 | 2021-09-01 | 1 |  | 7 | 49 | 55 | 2021 | 2021 | R16
165358248275 | 161474248275 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-08-26 | 2021-09-15 | 2021-09-17 |  | 2021-11-09 | Underground | R16 |  | 15 | 3 |  |  | 54 | 2021 | 2021 | R16
167310335724 | 160003335724 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-10 | 2023-07-10 | 2023-10-13 |  | 2023-12-19 | Underground | R16 | 2023-11-08 | 1 | 70 | 19 | 30 | 117 | 2023 | 2023 | R16
165735318107 | 166131318107 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-26 | 2023-05-05 | 2023-05-05 | 2023-09-15 | 2023-09-22 | Overhead | R16 | 2023-09-15 | 8 |  | 96 | 6 | 108 | 2023 | 2023 | R16
167729203943 | 167793203943 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-08-31 | 2020-09-15 | 2020-09-15 |  | 2022-02-28 | Overhead | R16 |  | 12 |  |  |  | 391 | 2020 | 2022 | R16
165365319720 | 160782319720 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-19 | 2023-05-19 | 2023-05-19 | 2023-07-27 | 2023-08-20 | Overhead | R16 | 2023-07-27 | 1 |  | 50 | 17 | 66 | 2023 | 2023 | R16
165781325294 | 168698325294 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-30 | 2023-07-17 | 2023-07-17 | 2023-10-05 | 2023-11-17 | Overhead | R16 | 2023-10-05 | 12 |  | 59 | 32 | 101 | 2023 | 2023 | R16
169642315309 | 168098315309 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-22 | 2023-04-10 | 2023-04-10 |  | 2023-06-14 | Overhead | R16 | 2023-06-13 | 14 |  | 47 | 2 | 61 | 2023 | 2023 | R16
167578314069 | 164609314069 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-06 | 2023-03-06 | 2023-03-29 |  | 2023-09-06 | Underground | R16 | 2023-05-25 | 1 | 18 | 42 | 75 | 133 | 2023 | 2023 | R16
168040323988 | 161899323988 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-25 | 2023-05-25 | 2023-07-03 | 2023-09-15 | 2023-09-20 | Underground | R16 | 2023-09-15 | 1 | 28 | 55 | 4 | 85 | 2023 | 2023 | R16
168381322755 | 166460322755 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-20 | 2023-06-20 | 2023-06-20 | 2023-10-12 | 2023-10-25 | Overhead | R16 | 2023-10-12 | 1 |  | 83 | 10 | 92 | 2023 | 2023 | R16
167587314927 | 160183314927 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2022-12-29 | 2022-12-29 | 2023-04-06 | 2023-05-19 | 2023-05-24 | Overhead | R16 | 2023-05-19 | 1 | 71 | 32 | 4 | 105 | 2022 | 2023 | R16
168972244997 | 160239244997 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-08-20 | 2021-08-20 | 2021-08-24 | 2022-03-18 | 2022-03-21 | Underground | R16 | 2022-03-18 | 1 | 3 | 149 | 2 | 152 | 2021 | 2022 | R16
160237308369 | 168412308369 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-03 | 2023-02-03 | 2023-02-03 | 2023-04-04 | 2023-04-18 | Overhead | R16 | 2023-04-04 | 1 |  | 43 | 11 | 53 | 2023 | 2023 | R16
160724248462 | 163062248462 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-02 | 2021-09-02 | 2021-09-17 |  | 2022-02-28 | Underground | R16 | 2022-01-25 | 1 | 12 | 93 | 25 | 128 | 2021 | 2022 | R16
161325316054 | 167033316054 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-30 | 2023-01-30 | 2023-04-17 | 2023-06-22 | 2023-06-23 | Underground | R16 | 2023-06-22 | 1 | 56 | 49 | 2 | 105 | 2023 | 2023 | R16
169565281143 | 162597281143 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-01 | 2021-09-01 | 2022-05-31 | 2022-08-02 | 2022-08-03 | Underground | R16 | 2022-08-02 | 1 | 195 | 46 | 2 | 241 | 2021 | 2022 | R16
166808321923 | 163004321923 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-11 | 2023-04-11 | 2023-06-12 | 2023-07-17 | 2023-08-04 | Underground | R16 | 2023-07-17 | 1 | 45 | 26 | 15 | 84 | 2023 | 2023 | R16
161945335781 | 168887335781 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-07-03 | 2023-10-03 | 2023-10-16 | 2023-12-15 | 2023-12-28 | Underground | R16 | 2023-12-15 | 67 | 10 | 45 | 10 | 129 | 2023 | 2023 | R16
169219339286 | 164112339286 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-07 | 2023-06-09 | 2023-11-10 | 2023-11-14 | 2023-12-05 | Overhead | R16 | 2023-11-14 | 3 | 111 | 3 | 16 | 130 | 2023 | 2023 | R16
167939306408 | 167496306408 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-12 | 2022-12-12 | 2023-01-30 | 2023-03-22 | 2023-03-22 | Underground | R16 | 2023-03-22 | 1 | 36 | 38 |  | 73 | 2022 | 2023 | R16
165230310181 | 161551310181 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-20 | 2023-02-22 | 2023-02-22 | 2023-03-07 | 2023-03-25 | Underground | R16 | 2023-03-07 | 3 |  | 10 | 14 | 25 | 2023 | 2023 | R16
165296245133 | 161252245133 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-09-13 | 2021-10-25 | Underground | R16 | 2021-09-13 | 1 |  | 14 | 31 | 44 | 2021 | 2021 | R16
165295303642 | 168065303642 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-14 | 2022-12-19 | 2022-12-22 |  | 2023-06-26 | Overhead | R16 | 2023-01-31 | 4 | 4 | 29 | 105 | 139 | 2022 | 2023 | R16
166822322277 | 165641322277 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-15 | 2023-06-15 | 2023-06-15 | 2023-07-17 | 2023-07-17 | Overhead | R16 | 2023-07-17 | 1 |  | 23 |  | 23 | 2023 | 2023 | R16
169785323398 | 168640323398 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-06 | 2023-02-06 | 2023-06-27 | 2023-12-16 | 2023-12-19 | Underground | R16 | 2023-12-16 | 1 | 102 | 124 | 2 | 227 | 2023 | 2023 | R16
166622322190 | 165151322190 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-13 | 2023-06-14 | 2023-06-14 | 2023-07-18 | 2023-09-06 | Overhead | R16 | 2023-07-18 | 2 |  | 25 | 37 | 62 | 2023 | 2023 | R16
168434139409 | 165746139409 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-08 | 2019-01-08 | 2019-01-08 |  | 2019-02-21 | Overhead | R16 | 2019-02-12 | 1 |  | 26 | 8 | 33 | 2019 | 2019 | R16
161484316562 | 162941316562 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2023-01-11 | 2023-03-22 | 2023-04-21 | 2023-12-08 | 2023-12-19 | Underground | R16 | 2023-12-08 | 51 | 23 | 166 | 8 | 245 | 2023 | 2023 | R16
167467319470 | 160489319470 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-05-18 | 2023-05-18 | 2023-05-18 |  | 2023-09-29 | Overhead | R16 | 2023-09-22 | 1 |  | 92 | 6 | 97 | 2023 | 2023 | R16
168489304923 | 161091304923 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-04 | 2023-01-04 | 2023-01-04 |  | 2023-04-20 | Overhead | R16 | 2023-02-21 | 1 |  | 35 | 43 | 77 | 2023 | 2023 | R16
163396255554 | 160625255554 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-08-23 | 2021-08-23 | 2021-11-09 | 2022-03-04 | 2022-06-22 | Underground | R16 | 2022-03-04 | 1 | 57 | 84 | 79 | 218 | 2021 | 2022 | R16
165666245168 | 169421245168 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-08-17 | 2021-08-25 | 2021-08-25 | 2022-08-04 | 2022-08-08 | Overhead | R16 | 2022-08-04 | 7 |  | 247 | 3 | 255 | 2021 | 2022 | R16
169051249128 | 163837249128 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2021-09-07 | 2021-09-07 | 2021-09-23 |  | 2023-04-12 | Overhead | R16 |  | 1 | 13 |  |  | 417 | 2021 | 2023 | R16
160942324236 | 167268324236 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH R16 SVC RELOCATION OD | Commercial | 2023-05-03 | 2023-05-23 | 2023-07-07 | 2023-10-24 | 2023-12-12 | Overhead | R16 | 2023-10-24 | 15 | 34 | 78 | 36 | 160 | 2023 | 2023 | R16
168549150314 | 167921150314 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-12 | 2019-04-22 | 2019-04-25 |  | 2022-11-01 | Overhead | R16 |  | 30 | 4 |  |  | 951 | 2019 | 2022 | R16
168686244352 | 165924244352 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-04 | 2021-08-19 | 2021-08-19 |  | 2021-11-13 | Overhead | R16 | 2021-10-22 | 12 |  | 47 | 16 | 73 | 2021 | 2021 | R16
167841306942 | 165525306942 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-23 | 2023-01-23 | 2023-01-30 | 2023-01-23 | 2023-06-05 | Overhead | R16 | 2023-01-23 | 1 | 6 |  | 96 | 96 | 2023 | 2023 | R16
165543306255 | 164164306255 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-18 | 2023-01-18 | 2023-01-30 | 2023-04-24 | 2023-06-13 | Overhead | R16 | 2023-04-24 | 1 | 9 | 61 | 37 | 105 | 2023 | 2023 | R16
164275325012 | 163978325012 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-03-02 | 2023-03-02 | 2023-07-13 | 2023-07-17 | 2023-10-13 | Overhead | R16 | 2023-07-17 | 1 | 96 | 3 | 65 | 162 | 2023 | 2023 | R16
161945241117 | 164502241117 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-29 | 2021-07-29 | 2021-07-29 |  | 2021-10-25 | Underground | R16 | 2021-08-25 | 1 |  | 20 | 44 | 63 | 2021 | 2021 | R16
162514251992 | 161036251992 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-24 | 2021-09-07 | 2021-10-13 |  | 2022-06-22 | Underground | R16 | 2022-03-08 | 11 | 27 | 105 | 77 | 217 | 2021 | 2022 | R16
163402320814 | 162421320814 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-05-30 | 2023-05-31 | 2023-06-01 |  | 2023-10-13 | Overhead | R16 |  | 2 | 2 |  |  | 99 | 2023 | 2023 | R16
160500316346 | 163568316346 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-13 | 2023-04-19 | 2023-04-19 |  | 2023-08-18 | Overhead | R16 | 2023-05-08 | 5 |  | 14 | 75 | 92 | 2023 | 2023 | R16
165363312084 | 163104312084 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2023-02-27 | 2023-02-27 | 2023-03-10 |  | 2023-08-09 | Underground | R16 | 2023-03-15 | 1 | 10 | 4 | 106 | 118 | 2023 | 2023 | R16
164513321542 | 164016321542 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-07-17 | 2023-08-18 | Overhead | R16 | 2023-07-17 | 1 |  | 29 | 25 | 53 | 2023 | 2023 | R16
163643310509 | 161822310509 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-21 | 2023-02-21 | 2023-02-24 |  | 2023-07-20 | Overhead | R16 | 2023-03-27 | 1 | 4 | 22 | 84 | 108 | 2023 | 2023 | R16
168235321929 | 165602321929 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-24 | 2023-06-12 | 2023-06-12 | 2023-12-19 | 2023-12-28 | Overhead | R16 | 2023-12-19 | 36 |  | 137 | 8 | 179 | 2023 | 2023 | R16
163442247057 | 165623247057 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-03 | 2021-08-03 | 2021-09-09 | 2021-12-05 | 2022-01-31 | Underground | R16 | 2021-12-05 | 1 | 28 | 62 | 41 | 130 | 2021 | 2022 | R16
167867241075 | 164311241075 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-28 | 2021-07-28 | 2021-07-28 | 2021-11-10 | 2021-12-29 | Overhead | R16 | 2021-11-10 | 1 |  | 76 | 36 | 111 | 2021 | 2021 | R16
161888245197 | 161320245197 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-25 | 2021-08-25 | 2021-08-25 |  | 2023-08-15 | Overhead | R16 | 2023-05-18 | 1 |  | 452 | 64 | 515 | 2021 | 2023 | R16
164765244422 | 169416244422 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-18 | 2021-08-19 | 2021-08-19 | 2021-11-10 | 2021-12-28 | Overhead | R16 | 2021-11-10 | 2 |  | 60 | 35 | 95 | 2021 | 2021 | R16
168868248326 | 162824248326 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-01 | 2021-09-16 | 2021-09-16 |  | 2022-02-02 | Overhead | R16 | 2021-12-15 | 12 |  | 65 | 36 | 111 | 2021 | 2022 | R16
169130176927 | 160721176927 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2020-01-02 | 2020-01-02 | 2020-01-14 |  | 2020-06-09 | Underground | R16 |  | 1 | 9 |  |  | 114 | 2020 | 2020 | R16
166344241233 | 164633241233 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2022-02-03 | 2022-03-04 | Overhead | R16 | 2022-02-03 | 1 |  | 136 | 22 | 157 | 2021 | 2022 | R16
166089321261 | 164141321261 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-17 | 2023-04-17 | 2023-06-05 | 2023-06-27 | 2023-07-19 | Underground | R16 | 2023-06-27 | 1 | 36 | 17 | 17 | 68 | 2023 | 2023 | R16
166700311448 | 167198311448 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-31 | 2023-01-31 | 2023-03-03 | 2023-09-19 | 2023-09-28 | Underground | R16 | 2023-09-19 | 1 | 24 | 143 | 8 | 173 | 2023 | 2023 | R16
169168245546 | 161607245546 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-27 | 2021-08-27 | 2021-08-27 | 2021-10-20 | 2021-11-18 | Overhead | R16 | 2021-10-20 | 1 |  | 39 | 22 | 60 | 2021 | 2021 | R16
161270318131 | 168142318131 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-05 | 2023-05-05 | 2023-05-05 |  | 2023-08-18 | Overhead | R16 | 2023-05-08 | 1 |  | 2 | 75 | 76 | 2023 | 2023 | R16
165960317165 | 166286317165 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-27 | 2023-04-27 | 2023-04-27 | 2023-04-28 | 2023-06-13 | Overhead | R16 | 2023-04-28 | 1 |  | 2 | 33 | 34 | 2023 | 2023 | R16
164585303822 | 168797303822 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-19 | 2022-12-20 | 2022-12-22 |  | 2023-02-27 | Overhead | R16 | 2023-01-04 | 2 | 3 | 10 | 39 | 51 | 2022 | 2023 | R16
163855293007 | 165158293007 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-13 | 2021-09-13 | 2022-09-07 | 2022-10-18 | 2022-10-27 | Underground | R16 | 2022-10-18 | 1 | 258 | 30 | 8 | 294 | 2021 | 2022 | R16
161078318694 | 169054318694 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-10 | 2023-05-10 | 2023-05-10 | 2023-08-01 | 2023-06-19 | Overhead | R16 | 2023-08-01 | 1 |  | 60 |  | 29 | 2023 | 2023 | R16
166225244772 | 167073244772 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-09 | 2021-08-10 | 2021-08-24 | 2021-08-24 | 2021-10-25 | Underground | R16 | 2021-08-24 | 2 | 11 |  | 45 | 56 | 2021 | 2021 | R16
167166245881 | 168374245881 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-13 | 2021-08-13 | 2021-08-30 |  | 2022-04-21 | Underground | R16 | 2022-03-21 | 1 | 12 | 146 | 24 | 180 | 2021 | 2022 | R16
169532255946 | 163503255946 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Commercial | 2021-09-03 | 2021-09-03 | 2021-11-10 | 2022-10-20 | 2022-11-16 | Overhead | R16 | 2022-10-20 | 1 | 49 | 247 | 20 | 314 | 2021 | 2022 | R16
162340245352 | 161297245352 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-11-18 | 2022-01-07 | Overhead | R16 | 2021-11-18 | 1 |  | 61 | 37 | 97 | 2021 | 2022 | R16
163313305012 | 161149305012 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-05 | 2023-01-05 | 2023-01-05 |  | 2023-04-07 | Overhead | R16 | 2023-03-01 | 1 |  | 40 | 28 | 67 | 2023 | 2023 | R16
165326259772 | 165382259772 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-08-02 | 2021-08-02 | 2021-12-03 | 2022-04-07 | 2022-04-11 | Underground | R16 | 2022-04-07 | 1 | 90 | 90 | 3 | 181 | 2021 | 2022 | R16
167963241133 | 163637241133 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-26 | 2021-07-29 | 2021-07-29 | 2021-09-21 | 2021-11-09 | Overhead | R16 | 2021-09-21 | 4 |  | 39 | 36 | 77 | 2021 | 2021 | R16
167154322945 | 168977322945 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-10 | 2023-05-10 | 2023-06-21 | 2023-11-06 | 2023-11-13 | Underground | R16 | 2023-11-06 | 1 | 31 | 99 | 6 | 134 | 2023 | 2023 | R16
162710314579 | 168443314579 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-23 | 2023-03-31 | 2023-04-04 |  | 2023-06-14 | Underground | R16 | 2023-06-07 | 7 | 3 | 47 | 6 | 60 | 2023 | 2023 | R16
169155246140 | 162495246140 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2022-12-21 | 2022-12-22 | Overhead | R16 | 2022-12-21 | 1 |  | 342 | 2 | 343 | 2021 | 2022 | R16
163097311594 | 164714311594 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-06 | 2023-03-06 | 2023-03-06 | 2023-05-01 | 2023-05-02 | Overhead | R16 | 2023-05-01 | 1 |  | 41 | 2 | 42 | 2023 | 2023 | R16
168619322654 | 165673322654 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-24 | 2023-06-19 | 2023-06-19 | 2023-07-10 | 2023-08-04 | Overhead | R16 | 2023-07-10 | 41 |  | 16 | 20 | 75 | 2023 | 2023 | R16
169716282679 | 165766282679 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-04-29 | 2022-04-29 | 2022-06-15 |  | 2023-05-19 | Underground | R16 |  | 1 | 34 |  |  | 276 | 2022 | 2023 | R16
166690244856 | 161124244856 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-31 | 2021-10-25 | Overhead | R16 | 2021-08-31 | 1 |  | 5 | 40 | 44 | 2021 | 2021 | R16
163954241022 | 164012241022 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2021-07-27 | 2021-07-27 | 2021-07-27 |  | 2022-10-21 | Underground | R16 | 2022-08-11 | 1 |  | 273 | 52 | 324 | 2021 | 2022 | R16
169796144244 | 163942144244 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-02-19 | 2019-02-20 | 2019-02-25 |  | 2019-08-12 | Underground | R16 |  | 2 | 4 |  |  | 125 | 2019 | 2019 | R16
167182244289 | 169225244289 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-17 | 2021-08-18 | 2021-08-19 | 2022-08-24 | 2022-10-21 | Overhead | R16 | 2022-08-24 | 2 | 2 | 265 | 43 | 309 | 2021 | 2022 | R16
169824142603 | 161719142603 | NON-RESIDENTIAL - WAREHOUSE | OH R16 RES NON RES OS | Commercial | 2019-02-06 | 2019-02-06 | 2019-02-08 |  | 2019-08-12 | Overhead | R16 |  | 1 | 3 |  |  | 134 | 2019 | 2019 | R16
164608243603 | 168440243603 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-13 | 2021-08-13 | 2021-08-13 |  | 2021-10-25 | Overhead | R16 | 2021-09-14 | 1 |  | 23 | 30 | 52 | 2021 | 2021 | R16
165592241645 | 165243241645 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-08-02 | 2021-08-02 | 2021-08-02 | 2021-09-10 | 2021-09-10 | Underground | R16 | 2021-09-10 | 1 |  | 30 |  | 30 | 2021 | 2021 | R16
169628246719 | 163719246719 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-08 | 2021-09-08 | 2021-09-08 |  | 2021-12-17 | Overhead | R16 | 2021-11-18 | 1 |  | 52 | 22 | 73 | 2021 | 2021 | R16
169966320388 | 168946320388 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-10 | 2023-05-26 | 2023-05-26 | 2023-08-21 | 2023-09-26 | Overhead | R16 | 2023-08-21 | 13 |  | 62 | 27 | 100 | 2023 | 2023 | R16
169397308690 | 168701308690 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-06 | 2023-02-06 | 2023-02-07 |  | 2023-07-24 | Overhead | R16 | 2023-03-08 | 1 | 2 | 22 | 99 | 121 | 2023 | 2023 | R16
169068320435 | 160513320435 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-14 | 2023-02-14 | 2023-05-26 | 2023-06-28 | 2023-06-29 | Underground | R16 | 2023-06-28 | 1 | 74 | 24 | 2 | 98 | 2023 | 2023 | R16
163845250265 | 162522250265 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-31 | 2021-09-01 | 2021-10-01 | 2021-10-26 | 2021-10-26 | Underground | R16 | 2021-10-26 | 2 | 23 | 18 |  | 41 | 2021 | 2021 | R16
163586316867 | 165202316867 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-08 | 2023-03-08 | 2023-04-25 | 2023-06-14 | 2023-06-15 | Underground | R16 | 2023-06-14 | 1 | 35 | 37 | 2 | 72 | 2023 | 2023 | R16
165412311456 | 165154311456 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-20 | 2023-01-23 | 2023-03-03 |  | 2023-07-28 | Underground | R16 | 2023-03-06 | 2 | 30 | 2 | 105 | 136 | 2023 | 2023 | R16
166828242691 | 167185242691 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2021-10-07 | 2021-11-15 | Overhead | R16 | 2021-10-07 | 1 |  | 43 | 28 | 70 | 2021 | 2021 | R16
162704251205 | 165064251205 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-09-13 | 2021-09-13 | 2021-10-08 |  | 2022-02-10 | Underground | R16 | 2022-01-05 | 1 | 20 | 64 | 27 | 109 | 2021 | 2022 | R16
167821322215 | 165371322215 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-14 | 2023-06-14 | 2023-06-14 |  | 2023-10-13 | Overhead | R16 | 2023-06-22 | 1 |  | 7 | 82 | 88 | 2023 | 2023 | R16
160756309332 | 160232309332 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-07-12 | 2023-07-13 | Overhead | R16 | 2023-07-12 | 1 |  | 108 | 2 | 109 | 2023 | 2023 | R16
162086319162 | 164671319162 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-18 | 2023-05-15 | 2023-05-15 | 2023-07-17 | 2023-07-25 | Overhead | R16 | 2023-07-17 | 84 |  | 46 | 7 | 135 | 2023 | 2023 | R16
167295322955 | 166912322955 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-22 | 2023-06-22 | 2023-06-22 | 2023-06-23 | 2023-07-07 | Overhead | R16 | 2023-06-23 | 1 |  | 2 | 11 | 12 | 2023 | 2023 | R16
160120186886 | 160046186886 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-05-21 | 2019-05-21 | 2020-04-08 |  | 2020-07-08 | Underground | R16 |  | 1 | 232 |  |  | 297 | 2019 | 2020 | R16
168865315072 | 161566315072 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-05 | 2023-04-05 | 2023-04-07 | 2023-06-08 | 2023-06-12 | Overhead | R16 | 2023-06-08 | 1 | 3 | 45 | 3 | 49 | 2023 | 2023 | R16
169898304871 | 160347304871 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-30 | 2023-01-04 | 2023-01-30 | 2023-01-04 | 2023-05-11 | Underground | R16 | 2023-01-04 | 4 | 19 |  | 92 | 95 | 2022 | 2023 | R16
165930319760 | 167564319760 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-03 | 2023-05-04 | 2023-05-19 |  | 2023-09-28 | Underground | R16 | 2023-05-30 | 2 | 12 | 8 | 88 | 107 | 2023 | 2023 | R16
162062252143 | 163247252143 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-07-23 | 2021-07-28 | 2021-10-14 | 2022-05-09 | 2022-05-12 | Underground | R16 | 2022-05-09 | 4 | 57 | 148 | 4 | 210 | 2021 | 2022 | R16
160361185296 | 168264185296 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2020-03-25 | 2020-03-25 | 2020-03-26 |  | 2021-10-26 | Underground | R16 |  | 1 | 2 |  |  | 415 | 2020 | 2021 | R16
169959262768 | 162205262768 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-08-30 | 2021-11-10 | 2021-12-28 | 2022-05-03 | 2022-05-25 | Underground | R16 | 2022-05-03 | 53 | 35 | 91 | 17 | 193 | 2021 | 2022 | R16
169381251752 | 164734251752 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-09-10 | 2021-09-10 | 2021-10-12 | 2022-02-08 | 2022-02-11 | Underground | R16 | 2022-02-08 | 1 | 23 | 86 | 4 | 111 | 2021 | 2022 | R16
164229266628 | 161153266628 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-08-25 | 2021-09-30 | 2022-01-28 | 2023-02-16 | 2023-03-03 | Underground | R16 | 2023-02-16 | 27 | 87 | 275 | 12 | 398 | 2021 | 2023 | R16
164128242394 | 166707242394 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-06 | 2021-08-06 | 2021-08-06 |  | 2021-10-27 | Overhead | R16 | 2021-08-12 | 1 |  | 5 | 55 | 59 | 2021 | 2021 | R16
164293315292 | 162555315292 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-10 | 2023-04-10 | 2023-04-10 | 2023-05-26 | 2023-06-13 | Overhead | R16 | 2023-05-26 | 1 |  | 35 | 13 | 47 | 2023 | 2023 | R16
164028310713 | 163107310713 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-27 | 2023-02-27 | 2023-02-27 | 2023-04-07 | 2023-08-09 | Overhead | R16 | 2023-04-07 | 1 |  | 30 | 89 | 118 | 2023 | 2023 | R16
166731311524 | 169830311524 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-10 | 2023-02-10 | 2023-03-06 | 2023-12-01 | 2023-12-05 | Underground | R16 | 2023-12-01 | 1 | 17 | 195 | 3 | 213 | 2023 | 2023 | R16
167577305116 | 169284305116 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-21 | 2022-12-21 | 2023-01-30 | 2023-01-06 | 2023-04-05 | Underground | R16 | 2023-01-06 | 1 | 29 |  | 64 | 76 | 2022 | 2023 | R16
166443322675 | 164672322675 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-06-12 | 2023-06-12 | 2023-06-20 | 2023-09-25 | 2023-09-28 | Underground | R16 | 2023-09-25 | 1 | 7 | 70 | 4 | 79 | 2023 | 2023 | R16
167682324067 | 167772324067 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-27 | 2023-07-05 | 2023-07-05 | 2023-07-11 | 2023-08-02 | Overhead | R16 | 2023-07-11 | 7 |  | 5 | 17 | 27 | 2023 | 2023 | R16
160492141128 | 168723141128 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-24 | 2019-01-24 | 2019-01-24 |  | 2019-02-22 | Overhead | R16 |  | 1 |  |  |  | 22 | 2019 | 2019 | R16
168438321997 | 164747321997 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-13 | 2023-06-13 | 2023-06-13 | 2023-10-16 | 2023-12-06 | Overhead | R16 | 2023-10-16 | 1 |  | 90 | 38 | 127 | 2023 | 2023 | R16
160519160942 | 168038160942 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-07-03 | 2019-07-10 | 2019-08-12 |  | 2019-10-28 | Underground | R16 |  | 6 | 24 |  |  | 84 | 2019 | 2019 | R16
165077246586 | 163254246586 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-02 | 2021-09-02 | 2021-09-03 |  | 2022-08-03 | Underground | R16 | 2022-06-21 | 1 | 2 | 208 | 32 | 240 | 2021 | 2022 | R16
167707308865 | 169007308865 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-08 | 2023-02-08 | 2023-02-08 | 2023-08-11 | 2023-08-21 | Overhead | R16 | 2023-08-11 | 1 |  | 133 | 7 | 139 | 2023 | 2023 | R16
167329319297 | 167448319297 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-20 | 2023-03-20 | 2023-05-17 | 2023-06-30 | 2023-07-14 | Underground | R16 | 2023-06-30 | 1 | 43 | 33 | 11 | 85 | 2023 | 2023 | R16
160360308669 | 168628308669 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-06 | 2023-02-06 | 2023-02-07 | 2023-09-20 | 2023-09-21 | Underground | R16 | 2023-09-20 | 1 | 2 | 162 | 2 | 164 | 2023 | 2023 | R16
166844243740 | 168625243740 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-13 | 2021-08-13 | 2021-08-13 | 2021-10-04 | 2021-11-09 | Overhead | R16 | 2021-10-04 | 1 |  | 37 | 27 | 63 | 2021 | 2021 | R16
164423304266 | 169846304266 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-27 | 2022-12-27 | 2022-12-27 |  | 2023-08-09 | Overhead | R16 | 2023-07-31 | 1 |  | 155 | 8 | 162 | 2022 | 2023 | R16
163194325584 | 162252325584 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-23 | 2023-02-27 | 2023-07-19 | 2023-08-27 | 2023-12-07 | Overhead | R16 | 2023-08-27 | 3 | 103 | 28 | 74 | 206 | 2023 | 2023 | R16
162336320806 | 168633320806 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-23 | 2023-03-23 | 2023-06-01 |  | 2023-07-06 | Overhead | R16 | 2023-06-02 | 1 | 51 | 2 | 25 | 76 | 2023 | 2023 | R16
169650241375 | 164971241375 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-30 | 2021-07-30 | 2021-07-30 | 2022-01-14 | 2022-05-12 | Overhead | R16 | 2022-01-14 | 1 |  | 121 | 85 | 205 | 2021 | 2022 | R16
167405157577 | 167757157577 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-07-02 | 2019-07-02 | 2019-07-10 |  | 2019-11-08 | Underground | R16 |  | 1 | 7 |  |  | 94 | 2019 | 2019 | R16
160342207192 | 166077207192 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-09 | 2020-10-14 | 2020-10-14 |  | 2021-11-05 | Underground | R16 | 2021-05-07 | 266 |  | 148 | 131 | 543 | 2019 | 2021 | R16
162421165286 | 162279165286 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-21 | 2019-09-21 | 2019-09-21 | 2019-10-09 | 2019-10-10 | Overhead | R16 | 2019-10-09 | 0 |  | 13 | 2 | 14 | 2019 | 2019 | R16
163168170802 | 165387170802 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-07 | 2019-10-07 | 2019-11-05 |  | 2020-06-09 | Overhead | R16 | 2020-02-14 | 1 | 22 | 74 | 83 | 177 | 2019 | 2020 | R16
168975166344 | 163677166344 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-30 | 2019-09-30 | 2019-09-30 | 2020-03-09 | 2020-06-09 | Overhead | R16 | 2020-03-09 | 1 |  | 116 | 67 | 182 | 2019 | 2020 | R16
160830173384 | 168757173384 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-05-13 | 2019-11-26 | 2019-12-02 |  | 2020-06-09 | Underground | R16 |  | 142 | 5 |  |  | 282 | 2019 | 2020 | R16
168855161614 | 166298161614 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-19 | 2019-08-19 | 2019-08-19 |  | 2019-11-26 | Overhead | R16 | 2019-11-19 | 1 |  | 67 | 6 | 72 | 2019 | 2019 | R16
169199164670 | 161228164670 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-16 | 2019-09-16 | 2019-09-16 |  | 2019-10-17 | Overhead | R16 | 2019-10-09 | 1 |  | 18 | 7 | 24 | 2019 | 2019 | R16
165963157136 | 168450157136 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-06 | 2019-07-06 | 2019-07-06 | 2019-09-03 | 2019-09-03 | Overhead | R16 | 2019-09-03 | 0 |  | 42 |  | 42 | 2019 | 2019 | R16
169300156218 | 165869156218 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-25 | 2019-06-25 | 2019-06-25 |  | 2019-10-30 | Overhead | R16 | 2019-10-24 | 1 |  | 88 | 5 | 92 | 2019 | 2019 | R16
165247174061 | 166965174061 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-12-10 | 2019-12-10 | 2019-12-10 |  | 2021-11-10 | Underground | R16 | 2019-12-20 | 1 |  | 9 | 494 | 502 | 2019 | 2021 | R16
165109159818 | 163555159818 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-02 | 2019-08-02 | 2019-08-02 |  | 2019-08-06 | Overhead | R16 |  | 1 |  |  |  | 3 | 2019 | 2019 | R16
160580166320 | 163166166320 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-26 | 2019-09-30 | 2019-09-30 |  | 2020-07-09 | Underground | R16 | 2020-06-02 | 3 |  | 177 | 28 | 206 | 2019 | 2020 | R16
163533155694 | 164953155694 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-18 | 2019-06-18 | 2019-06-18 |  | 2019-07-18 | Overhead | R16 | 2019-07-03 | 1 |  | 12 | 12 | 23 | 2019 | 2019 | R16
164987162502 | 167626162502 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-27 | 2019-08-27 | 2019-08-27 | 2019-09-25 | 2019-09-26 | Overhead | R16 | 2019-09-25 | 1 |  | 22 | 2 | 23 | 2019 | 2019 | R16
169182159890 | 168490159890 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-06 | 2019-08-02 | 2019-08-02 |  | 2023-06-08 | Overhead | R16 | 2019-09-24 | 20 |  | 38 | 968 | 1024 | 2019 | 2023 | R16
165181160216 | 161822160216 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-24 | 2019-07-24 | 2019-08-07 |  | 2020-07-09 | Overhead | R16 | 2020-06-04 | 1 | 11 | 217 | 26 | 252 | 2019 | 2020 | R16
166277174636 | 166297174636 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-10-10 | 2019-10-10 | 2019-12-18 |  | 2021-07-14 | Underground | R16 | 2020-11-20 | 1 | 50 | 243 | 169 | 460 | 2019 | 2021 | R16
168142163544 | 168313163544 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-05 | 2019-07-05 | 2019-09-06 | 2019-11-05 | 2019-11-06 | Underground | R16 | 2019-11-05 | 1 | 46 | 43 | 2 | 89 | 2019 | 2019 | R16
164291173673 | 164228173673 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-20 | 2019-11-20 | 2019-12-06 | 2020-01-02 | 2020-01-21 | Underground | R16 | 2020-01-02 | 1 | 13 | 20 | 14 | 45 | 2019 | 2020 | R16
168328165664 | 162339165664 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-23 | 2019-09-24 | 2019-09-24 |  | 2020-10-06 | Underground | R16 | 2020-06-26 | 2 |  | 199 | 73 | 272 | 2019 | 2020 | R16
163110168357 | 165153168357 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-07 | 2019-10-07 | 2019-10-17 | 2020-02-24 | 2020-06-09 | Underground | R16 | 2020-02-24 | 1 | 9 | 93 | 77 | 177 | 2019 | 2020 | R16
162018173432 | 165100173432 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-07 | 2019-10-07 | 2019-12-03 |  | 2022-08-02 | Underground | R16 |  | 1 | 42 |  |  | 737 | 2019 | 2022 | R16
164811172417 | 165102172417 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-07 | 2019-10-07 | 2019-11-20 | 2020-01-28 | 2020-01-30 | Underground | R16 | 2020-01-28 | 1 | 33 | 50 | 3 | 84 | 2019 | 2020 | R16
161217148230 | 161748148230 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-04-04 | 2019-04-04 | 2019-04-04 |  | 2019-05-28 | Underground | R16 | 2019-05-02 | 1 |  | 21 | 19 | 39 | 2019 | 2019 | R16
161229167644 | 166119167644 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-10 | 2019-10-10 | 2019-10-10 |  | 2022-08-02 | Overhead | R16 |  | 1 |  |  |  | 734 | 2019 | 2022 | R16
168305171009 | 160799171009 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-01 | 2019-11-01 | 2019-11-07 |  | 2020-06-09 | Overhead | R16 | 2020-01-22 | 1 | 5 | 55 | 100 | 158 | 2019 | 2020 | R16
168903164655 | 161317164655 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-17 | 2019-09-17 | 2019-09-17 |  | 2019-11-21 | Overhead | R16 | 2019-10-31 | 1 |  | 33 | 16 | 48 | 2019 | 2019 | R16
166134176682 | 166873176682 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-14 | 2019-10-14 | 2020-01-13 | 2020-03-12 | 2020-09-15 | Overhead | R16 | 2020-03-12 | 1 | 66 | 44 | 134 | 242 | 2019 | 2020 | R16
165785181049 | 169371181049 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-11 | 2019-07-11 | 2020-02-19 |  | 2020-10-06 | Underground | R16 | 2020-07-27 | 1 | 160 | 114 | 52 | 324 | 2019 | 2020 | R16
169873161323 | 163050161323 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-31 | 2019-07-31 | 2019-08-15 |  | 2019-10-11 | Underground | R16 | 2019-10-01 | 1 | 12 | 34 | 9 | 53 | 2019 | 2019 | R16
164993156230 | 165695156230 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-24 | 2019-06-24 | 2019-06-24 | 2019-09-17 | 2019-10-30 | Overhead | R16 | 2019-09-17 | 1 |  | 62 | 32 | 93 | 2019 | 2019 | R16
164817166657 | 164444166657 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-03 | 2019-10-03 | 2019-10-03 | 2019-10-30 | 2019-10-31 | Overhead | R16 | 2019-10-30 | 1 |  | 20 | 2 | 21 | 2019 | 2019 | R16
162029173983 | 166726173983 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-06 | 2019-12-09 | 2019-12-09 | 2020-01-08 | 2020-01-08 | Overhead | R16 | 2020-01-08 | 2 |  | 23 |  | 24 | 2019 | 2020 | R16
160534159755 | 161986159755 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-25 | 2019-08-01 | 2019-08-01 | 2019-09-04 | 2023-06-07 | Overhead | R16 | 2019-09-04 | 6 |  | 25 | 981 | 1010 | 2019 | 2023 | R16
161277174121 | 168030174121 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-07-03 | 2019-07-03 | 2019-12-10 | 2020-05-12 | 2020-07-29 | Underground | R16 | 2020-05-12 | 1 | 115 | 111 | 57 | 281 | 2019 | 2020 | R16
165813163093 | 169038163093 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-04 | 2019-09-04 | 2019-09-04 | 2019-09-13 | 2019-12-06 | Overhead | R16 | 2019-09-13 | 1 |  | 8 | 61 | 68 | 2019 | 2019 | R16
164089175802 | 164723175802 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-22 | 2019-11-22 | 2020-01-06 |  | 2020-07-09 | Underground | R16 | 2020-06-04 | 1 | 32 | 109 | 26 | 165 | 2019 | 2020 | R16
160887191616 | 162873191616 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-25 | 2019-09-25 | 2020-05-20 | 2021-01-19 | 2021-01-21 | Underground | R16 | 2021-01-19 | 1 | 171 | 175 | 3 | 347 | 2019 | 2021 | R16
161457139489 | 165896139489 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-08 | 2019-01-08 | 2019-01-08 |  | 2019-02-21 | Overhead | R16 | 2019-02-12 | 1 |  | 26 | 8 | 33 | 2019 | 2019 | R16
169438164039 | 160394164039 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-11 | 2019-09-11 | 2019-09-11 |  | 2021-11-10 | Overhead | R16 | 2020-01-10 | 1 |  | 88 | 479 | 566 | 2019 | 2021 | R16
161468165412 | 167974165412 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2019-08-28 | 2019-08-28 | 2019-09-24 |  | 2019-12-12 | Underground | R16 |  | 1 | 20 |  |  | 77 | 2019 | 2019 | R16
160581167613 | 165651167613 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-08 | 2019-10-08 | 2019-10-10 |  | 2020-07-08 | Overhead | R16 | 2020-05-15 | 1 | 3 | 157 | 39 | 197 | 2019 | 2020 | R16
166873159365 | 162452159365 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-29 | 2019-07-29 | 2019-07-29 |  | 2019-09-03 | Overhead | R16 |  | 1 |  |  |  | 27 | 2019 | 2019 | R16
166041201622 | 167889201622 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-10-19 | 2019-10-19 | 2020-08-24 | 2020-09-22 | 2020-10-12 | Underground | R16 | 2020-09-22 | 0 | 221 | 22 | 15 | 256 | 2019 | 2020 | R16
161496139846 | 166511139846 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-10 | 2019-01-10 | 2019-01-10 |  | 2019-02-19 | Overhead | R16 | 2019-02-06 | 1 |  | 20 | 10 | 29 | 2019 | 2019 | R16
167899176666 | 168171176666 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-13 | 2019-12-13 | 2020-01-13 | 2020-03-03 | 2020-03-05 | Underground | R16 | 2020-03-03 | 1 | 22 | 37 | 3 | 60 | 2019 | 2020 | R16
165095192400 | 166987192400 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-12-10 | 2019-12-10 | 2020-05-27 | 2020-09-09 | 2021-03-19 | Underground | R16 | 2020-09-09 | 1 | 122 | 76 | 138 | 334 | 2019 | 2021 | R16
163114162901 | 163550162901 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-02 | 2019-08-02 | 2019-08-30 |  | 2021-11-09 | Underground | R16 | 2019-12-18 | 1 | 21 | 79 | 495 | 593 | 2019 | 2021 | R16
161580158501 | 161078158501 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-20 | 2019-07-20 | 2019-07-20 | 2019-09-03 | 2019-09-04 | Overhead | R16 | 2019-09-03 | 0 |  | 32 | 2 | 33 | 2019 | 2019 | R16
166437193491 | 167685193491 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-27 | 2019-09-05 | 2022-08-08 | 2022-09-30 | 2022-10-18 | Underground | R16 | 2022-09-30 | 8 | 763 | 40 | 13 | 821 | 2019 | 2022 | R16
165053174007 | 161929174007 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-11-07 | 2019-11-07 | 2019-12-10 | 2021-09-29 | 2021-11-09 | Underground | R16 | 2021-09-29 | 1 | 24 | 472 | 30 | 524 | 2019 | 2021 | R16
160045164133 | 160427164133 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-11 | 2019-09-11 | 2019-09-11 |  | 2022-07-19 | Overhead | R16 |  | 1 |  |  |  | 745 | 2019 | 2022 | R16
163243168088 | 166813168088 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-14 | 2019-10-14 | 2019-10-14 |  | 2019-11-27 | Overhead | R16 | 2019-11-22 | 1 |  | 30 | 4 | 33 | 2019 | 2019 | R16
163485165071 | 165962165071 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2019-06-25 | 2019-06-27 | 2019-09-19 |  | 2020-05-21 | Overhead | R16 |  | 3 | 61 |  |  | 238 | 2019 | 2020 | R16
163251171487 | 163253171487 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-09-26 | 2019-09-26 | 2019-11-12 | 2019-12-27 | 2022-08-11 | Underground | R16 | 2019-12-27 | 1 | 34 | 34 | 685 | 751 | 2019 | 2022 | R16
165231167882 | 166555167882 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2019-10-11 | 2019-10-11 | 2019-10-11 | 2019-11-11 | 2019-11-13 | Overhead | R16 | 2019-11-11 | 1 |  | 22 | 3 | 24 | 2019 | 2019 | R16
165142168741 | 165498168741 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-14 | 2019-08-16 | 2019-10-18 | 2020-08-17 | 2020-08-18 | Underground | R16 | 2020-08-17 | 3 | 46 | 217 | 2 | 265 | 2019 | 2020 | R16
161736142186 | 161109142186 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-02-04 | 2019-02-04 | 2019-02-04 |  | 2019-09-11 | Underground | R16 |  | 1 |  |  |  | 158 | 2019 | 2019 | R16
161743146762 | 166680146762 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-03-06 | 2019-03-08 | 2019-03-21 |  | 2019-05-20 | Overhead | R16 |  | 3 | 10 |  |  | 54 | 2019 | 2019 | R16
161743146763 | 167220146763 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-03-08 | 2019-03-11 | 2019-03-21 |  | 2019-05-20 | Overhead | R16 |  | 2 | 9 |  |  | 52 | 2019 | 2019 | R16
166221174499 | 160354174499 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-31 | 2019-10-31 | 2019-12-17 |  | 2020-06-09 | Underground | R16 | 2020-01-13 | 1 | 34 | 20 | 107 | 159 | 2019 | 2020 | R16
161743146764 | 167221146764 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-03-08 | 2019-03-11 | 2019-03-21 |  | 2019-05-20 | Overhead | R16 |  | 2 | 9 |  |  | 52 | 2019 | 2019 | R16
168838166282 | 163710166282 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-30 | 2019-09-30 | 2019-09-30 |  | 2020-06-09 | Overhead | R16 | 2020-02-13 | 1 |  | 99 | 84 | 182 | 2019 | 2020 | R16
160270164293 | 166014164293 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-08-16 | 2019-08-16 | 2019-09-13 | 2019-11-25 | 2020-04-10 | Underground | R16 | 2019-11-25 | 1 | 21 | 52 | 100 | 171 | 2019 | 2020 | R16
167674157323 | 168821157323 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-08-26 | Overhead | R16 | 2019-07-08 | 1 |  |  | 36 | 36 | 2019 | 2019 | R16
167454160782 | 164841160782 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-09 | 2019-08-09 | 2019-08-09 | 2019-09-10 | 2019-09-12 | Overhead | R16 | 2019-09-10 | 1 |  | 23 | 3 | 25 | 2019 | 2019 | R16
167501165450 | 162425165450 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-23 | 2019-09-23 | 2019-09-23 |  | 2019-11-14 | Overhead | R16 | 2019-11-07 | 1 |  | 34 | 6 | 39 | 2019 | 2019 | R16
161762166525 | 162678166525 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-24 | 2019-09-24 | 2019-10-02 |  | 2021-08-12 | Underground | R16 | 2021-07-09 | 1 | 7 | 463 | 25 | 493 | 2019 | 2021 | R16
161950140032 | 166808140032 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-12 | 2019-01-12 | 2019-01-12 |  | 2019-02-21 | Overhead | R16 | 2019-02-15 | 0 |  | 25 | 5 | 29 | 2019 | 2019 | R16
161966140170 | 166806140170 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-11 | 2019-01-11 | 2019-01-14 |  | 2019-02-19 | Overhead | R16 | 2019-02-06 | 1 | 2 | 18 | 10 | 28 | 2019 | 2019 | R16
160839196797 | 166987196797 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-22 | 2019-08-22 | 2020-07-09 |  | 2020-10-06 | Underground | R16 | 2020-08-21 | 1 | 231 | 32 | 33 | 294 | 2019 | 2020 | R16
169290161783 | 160628161783 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-18 | 2019-07-18 | 2019-08-20 | 2019-09-19 | 2019-09-20 | Overhead | R16 | 2019-09-19 | 1 | 24 | 23 | 2 | 47 | 2019 | 2019 | R16
161981139155 | 164893139155 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-03 | 2019-01-03 | 2019-01-03 |  | 2019-03-14 | Overhead | R16 | 2019-02-25 | 1 |  | 38 | 14 | 51 | 2019 | 2019 | R16
162011150000 | 168572150000 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-03-18 | 2019-03-18 | 2019-04-22 |  | 2019-08-26 | Underground | R16 | 2019-06-24 | 1 | 26 | 46 | 46 | 116 | 2019 | 2019 | R16
164387166655 | 160334166655 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-11 | 2019-09-11 | 2019-10-03 |  | 2020-06-09 | Underground | R16 | 2020-03-17 | 1 | 17 | 119 | 61 | 195 | 2019 | 2020 | R16
162064143037 | 162976143037 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-12 | 2019-02-12 | 2019-02-12 |  | 2019-08-12 | Overhead | R16 | 2019-06-19 | 1 |  | 92 | 39 | 130 | 2019 | 2019 | R16
165266165793 | 162800165793 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-24 | 2019-09-24 | 2019-09-25 |  | 2019-10-30 | Overhead | R16 | 2019-10-23 | 1 | 2 | 21 | 6 | 27 | 2019 | 2019 | R16
164486169560 | 164984169560 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-12 | 2019-08-12 | 2019-10-24 |  | 2020-09-18 | Underground | R16 |  | 1 | 54 |  |  | 290 | 2019 | 2020 | R16
169199165602 | 162470165602 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-09-23 | 2019-09-23 | 2019-09-23 |  | 2021-01-21 | Underground | R16 | 2020-10-13 | 1 |  | 277 | 73 | 349 | 2019 | 2021 | R16
162084167460 | 167867167460 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2019-05-08 | 2019-05-08 | 2019-10-08 |  | 2021-08-23 | Underground | R16 |  | 1 | 110 |  |  | 599 | 2019 | 2021 | R16
165208162038 | 166662162038 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-08-21 | 2019-08-21 | 2019-08-23 |  | 2020-01-02 | Overhead | R16 | 2019-12-11 | 1 | 3 | 79 | 17 | 97 | 2019 | 2020 | R16
164020170106 | 163067170106 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-26 | 2019-10-30 | 2019-10-30 |  | 2021-11-13 | Overhead | R16 | 2020-01-08 | 25 |  | 51 | 483 | 557 | 2019 | 2021 | R16
167985165448 | 162412165448 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-23 | 2019-09-23 | 2019-09-23 | 2019-11-27 | 2019-12-12 | Overhead | R16 | 2019-11-27 | 1 |  | 48 | 12 | 59 | 2019 | 2019 | R16
164114178749 | 166567178749 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-10-12 | 2019-10-16 | 2020-01-30 |  | 2020-12-29 | Underground | R16 |  | 3 | 77 |  |  | 317 | 2019 | 2020 | R16
163751161656 | 166680161656 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-21 | 2019-08-21 | 2019-08-21 |  | 2019-10-30 | Overhead | R16 | 2019-10-21 | 1 |  | 44 | 8 | 51 | 2019 | 2019 | R16
168894168787 | 161714168787 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-24 | 2019-07-24 | 2019-10-18 | 2019-11-05 | 2019-11-06 | Underground | R16 | 2019-11-05 | 1 | 63 | 13 | 2 | 76 | 2019 | 2019 | R16
160537172609 | 161573172609 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-06 | 2019-11-06 | 2019-11-22 |  | 2020-06-09 | Underground | R16 | 2020-03-26 | 1 | 13 | 90 | 54 | 155 | 2019 | 2020 | R16
166189169943 | 166565169943 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-11 | 2019-10-11 | 2019-10-28 |  | 2020-06-09 | Underground | R16 | 2020-02-05 | 1 | 12 | 73 | 90 | 173 | 2019 | 2020 | R16
162133169008 | 167480169008 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-17 | 2019-10-17 | 2019-10-21 |  | 2021-01-20 | Underground | R16 | 2020-10-09 | 1 | 3 | 255 | 74 | 330 | 2019 | 2021 | R16
166556170644 | 161048170644 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-04 | 2019-11-04 | 2019-11-04 | 2020-01-30 | 2020-01-31 | Overhead | R16 | 2020-01-30 | 1 |  | 64 | 2 | 65 | 2019 | 2020 | R16
166041196526 | 162012196526 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-07-25 | 2019-11-11 | 2020-07-06 | 2020-09-07 | 2020-11-16 | Underground | R16 | 2020-09-07 | 78 | 171 | 46 | 51 | 343 | 2019 | 2020 | R16
164190171089 | 166770171089 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-14 | 2019-11-07 | 2019-11-08 | 2020-02-06 | 2020-02-19 | Overhead | R16 | 2020-02-06 | 19 | 2 | 65 | 10 | 93 | 2019 | 2020 | R16
167703164864 | 167496164864 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-08-27 | 2019-08-27 | 2019-09-17 | 2020-04-02 | 2020-04-14 | Overhead | R16 | 2020-04-02 | 1 | 16 | 143 | 9 | 166 | 2019 | 2020 | R16
163783176147 | 169295176147 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG R16 ELECTRIC RELOCATION UD | Residential | 2019-09-05 | 2019-09-05 | 2020-01-07 | 2020-03-31 | 2020-12-21 | Underground | R16 | 2020-03-31 | 1 | 89 | 61 | 190 | 338 | 2019 | 2020 | R16
162397140312 | 167414140312 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-15 | 2019-01-15 | 2019-01-15 |  | 2023-06-08 | Overhead | R16 | 2019-09-27 | 1 |  | 184 | 965 | 1148 | 2019 | 2023 | R16
163610175558 | 163684175558 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-11-18 | 2019-11-18 | 2020-01-02 |  | 2022-09-30 | Underground | R16 | 2022-10-21 | 1 | 34 | 732 |  | 750 | 2019 | 2022 | R16
162986225247 | 164345225247 | Electric Vehicle | UG R16 RESD AND NON RESD UD | Commercial | 2019-11-20 | 2020-01-29 | 2021-03-30 | 2021-07-19 | 2021-10-19 | Underground | R16 | 2021-07-19 | 51 | 305 | 80 | 67 | 500 | 2019 | 2021 | R16
160336163906 | 165297163906 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-08-14 | 2019-08-29 | 2019-09-09 |  | 2019-10-30 | Overhead | R16 | 2019-10-28 | 12 | 8 | 36 | 3 | 56 | 2019 | 2019 | R16
168254159883 | 163407159883 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-02 | 2019-08-02 | 2019-08-02 |  | 2019-09-10 | Overhead | R16 | 2019-09-03 | 1 |  | 23 | 6 | 28 | 2019 | 2019 | R16
167518173468 | 160984173468 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-11-04 | 2019-11-26 | 2019-12-03 | 2020-08-04 | 2020-11-04 | Underground | R16 | 2020-08-04 | 17 | 6 | 176 | 67 | 263 | 2019 | 2020 | R16
166041168090 | 169497168090 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-07-11 | 2019-07-18 | 2019-10-14 | 2020-01-10 | 2021-04-05 | Underground | R16 | 2020-01-10 | 6 | 63 | 65 | 322 | 453 | 2019 | 2021 | R16
162533140377 | 167442140377 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-15 | 2019-01-15 | 2019-01-16 |  | 2019-02-19 | Overhead | R16 | 2019-02-01 | 1 | 2 | 13 | 13 | 26 | 2019 | 2019 | R16
161681178911 | 163189178911 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-09-26 | 2019-09-26 | 2020-01-31 | 2021-08-26 | 2021-08-27 | Underground | R16 | 2021-08-26 | 1 | 92 | 410 | 2 | 502 | 2019 | 2021 | R16
161902178306 | 168508178306 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-12-16 | 2019-12-16 | 2020-01-28 |  | 2020-06-09 | Overhead | R16 |  | 1 | 32 |  |  | 127 | 2019 | 2020 | R16
162632144575 | 165761144575 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2019-03-01 | 2019-03-01 | 2019-03-01 |  | 2019-06-03 | Underground | R16 | 2019-05-14 | 1 |  | 53 | 15 | 67 | 2019 | 2019 | R16
165719166300 | 160035166300 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-09 | 2019-09-09 | 2019-09-30 |  | 2019-11-13 | Underground | R16 | 2019-11-04 | 1 | 16 | 26 | 8 | 48 | 2019 | 2019 | R16
167954165828 | 163056165828 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-26 | 2019-09-26 | 2019-09-26 | 2019-11-18 | 2020-05-19 | Overhead | R16 | 2019-11-18 | 1 |  | 38 | 132 | 169 | 2019 | 2020 | R16
167358165191 | 168940165191 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-09-03 | 2019-09-03 | 2019-09-20 |  | 2021-11-05 | Underground | R16 | 2021-04-16 | 1 | 14 | 411 | 146 | 569 | 2019 | 2021 | R16
162993158633 | 160950158633 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-07-19 | 2019-07-19 | 2019-07-23 | 2019-08-06 | 2019-09-13 | Underground | R16 | 2019-08-06 | 1 | 3 | 11 | 29 | 41 | 2019 | 2019 | R16
166461158401 | 168740158401 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-08 | 2019-07-08 | 2019-07-18 | 2019-09-07 | 2019-09-10 | Overhead | R16 | 2019-09-07 | 1 | 9 | 37 | 2 | 47 | 2019 | 2019 | R16
168450178022 | 168927178022 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-03 | 2019-09-03 | 2020-01-24 | 2020-08-11 | 2020-10-06 | Underground | R16 | 2020-08-11 | 1 | 104 | 143 | 41 | 286 | 2019 | 2020 | R16
162358172690 | 164764172690 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-22 | 2019-11-22 | 2019-11-22 |  | 2020-06-09 | Overhead | R16 | 2020-01-21 | 1 |  | 43 | 101 | 143 | 2019 | 2020 | R16
165556169085 | 168170169085 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-21 | 2019-10-21 | 2019-10-21 |  | 2020-06-09 | Overhead | R16 | 2020-02-28 | 1 |  | 95 | 73 | 167 | 2019 | 2020 | R16
164167162723 | 166306162723 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-19 | 2019-08-19 | 2019-08-29 | 2019-11-27 | 2019-12-12 | Underground | R16 | 2019-11-27 | 1 | 9 | 65 | 12 | 84 | 2019 | 2019 | R16
167998170383 | 160599170383 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-31 | 2019-10-31 | 2019-10-31 | 2020-03-03 | 2020-06-09 | Underground | R16 | 2020-03-03 | 1 |  | 89 | 71 | 159 | 2019 | 2020 | R16
169897244216 | 163534244216 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-06-12 | 2021-08-19 | 2021-08-19 | 2021-11-29 | 2022-01-04 | Underground | R16 | 2021-11-29 | 572 |  | 73 | 27 | 670 | 2019 | 2022 | R16
162179163326 | 169158163326 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-04 | 2019-09-04 | 2019-09-04 | 2019-11-08 | 2019-11-08 | Overhead | R16 | 2019-11-08 | 1 |  | 48 |  | 48 | 2019 | 2019 | R16
162405157575 | 164305157575 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-06-17 | 2019-07-10 | 2019-07-10 | 2019-08-23 | 2019-09-06 | Underground | R16 | 2019-08-23 | 18 |  | 33 | 11 | 60 | 2019 | 2019 | R16
169008180321 | 169160180321 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2019-09-04 | 2020-02-07 | 2020-02-12 | 2020-04-07 | 2021-01-04 | Overhead | R16 | 2020-04-07 | 113 | 4 | 40 | 195 | 349 | 2019 | 2021 | R16
167741168046 | 160899168046 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-13 | 2019-09-18 | 2019-10-14 |  | 2019-11-21 | Overhead | R16 |  | 4 | 19 |  |  | 50 | 2019 | 2019 | R16
160072167279 | 160450167279 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-11 | 2019-09-11 | 2019-10-08 | 2019-11-20 | 2019-11-21 | Underground | R16 | 2019-11-20 | 1 | 20 | 32 | 2 | 52 | 2019 | 2019 | R16
166331178511 | 166172178511 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-06-25 | 2019-07-18 | 2020-01-29 | 2020-10-23 | 2021-11-12 | Underground | R16 | 2020-10-23 | 18 | 140 | 193 | 276 | 624 | 2019 | 2021 | R16
162894139642 | 166075139642 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-08 | 2019-01-08 | 2019-01-08 |  | 2019-04-15 | Overhead | R16 | 2019-03-08 | 1 |  | 44 | 27 | 70 | 2019 | 2019 | R16
165187171369 | 162457171369 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-11-11 | 2019-11-11 | 2019-11-11 |  | 2019-11-22 | Overhead | R16 | 2019-11-15 | 1 |  | 5 | 6 | 10 | 2019 | 2019 | R16
163421172617 | 164725172617 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-22 | 2019-11-22 | 2019-11-22 | 2020-02-24 | 2020-06-09 | Overhead | R16 | 2020-02-24 | 1 |  | 67 | 77 | 143 | 2019 | 2020 | R16
168309167374 | 169203167374 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-09-04 | 2019-09-26 | 2019-10-08 |  | 2020-06-09 | Underground | R16 |  | 17 | 9 |  |  | 200 | 2019 | 2020 | R16
167976171983 | 169054171983 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-25 | 2019-11-15 | 2019-11-15 | 2020-03-10 | 2020-06-09 | Overhead | R16 | 2020-03-10 | 16 |  | 83 | 66 | 163 | 2019 | 2020 | R16
166972174575 | 164782174575 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-11-22 | 2019-11-22 | 2019-12-17 |  | 2021-11-10 | Overhead | R16 |  | 1 | 18 |  |  | 514 | 2019 | 2021 | R16
169659170874 | 160718170874 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-01 | 2019-11-01 | 2019-11-06 |  | 2019-11-26 | Overhead | R16 | 2019-11-19 | 1 | 4 | 10 | 6 | 18 | 2019 | 2019 | R16
164596170861 | 162669170861 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-24 | 2019-09-24 | 2019-11-05 | 2019-12-06 | 2019-12-09 | Underground | R16 | 2019-12-06 | 1 | 31 | 24 | 2 | 55 | 2019 | 2019 | R16
161968160355 | 164079160355 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-07 | 2019-08-07 | 2019-08-07 | 2020-03-19 | 2020-03-23 | Underground | R16 | 2020-03-19 | 1 |  | 162 | 3 | 164 | 2019 | 2020 | R16
168901159882 | 163014159882 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-31 | 2019-07-31 | 2019-08-02 |  | 2019-11-13 | Underground | R16 | 2019-11-04 | 1 | 3 | 67 | 8 | 76 | 2019 | 2019 | R16
166084158311 | 166417158311 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-06-27 | 2019-07-17 | 2019-07-19 | 2019-12-17 | 2020-04-27 | Underground | R16 | 2019-12-17 | 15 | 3 | 108 | 95 | 218 | 2019 | 2020 | R16
165183174133 | 165509174133 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-27 | 2019-11-27 | 2019-12-11 |  | 2020-06-09 | Underground | R16 | 2020-06-08 | 1 | 11 | 129 | 2 | 140 | 2019 | 2020 | R16
163170184943 | 164787184943 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-09 | 2019-08-15 | 2020-03-20 | 2023-01-11 | 2022-12-01 | Underground | R16 | 2023-01-11 | 5 | 157 | 734 |  | 865 | 2019 | 2022 | R16
163161208795 | 161501208795 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2019-09-17 | 2020-07-16 | 2020-10-29 | 2022-12-30 | 2023-01-06 | Underground | R16 | 2022-12-30 | 218 | 76 | 567 | 6 | 864 | 2019 | 2023 | R16
163365167185 | 165130167185 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-07 | 2019-10-07 | 2019-10-07 | 2019-11-11 | 2019-11-14 | Overhead | R16 | 2019-11-11 | 1 |  | 26 | 4 | 29 | 2019 | 2019 | R16
160981173912 | 167017173912 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-10 | 2019-12-10 | 2019-12-10 |  | 2020-06-09 | Overhead | R16 | 2020-02-19 | 1 |  | 52 | 80 | 131 | 2019 | 2020 | R16
160061170947 | 160142170947 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-30 | 2019-10-30 | 2019-11-06 | 2020-10-28 | 2020-08-13 | Underground | R16 | 2020-10-28 | 1 | 6 | 256 |  | 207 | 2019 | 2020 | R16
161789159151 | 161846159151 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-24 | 2019-07-26 | 2019-07-26 |  | 2019-08-28 | Overhead | R16 | 2019-08-19 | 3 |  | 17 | 8 | 26 | 2019 | 2019 | R16
163114140415 | 167515140415 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-16 | 2019-01-16 | 2019-01-16 |  | 2019-02-19 | Overhead | R16 | 2019-02-06 | 1 |  | 16 | 10 | 25 | 2019 | 2019 | R16
167716165874 | 168411165874 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-29 | 2019-08-29 | 2019-09-26 |  | 2021-12-16 | Underground | R16 | 2020-01-07 | 1 | 21 | 74 | 508 | 601 | 2019 | 2021 | R16
163405172227 | 163577172227 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-18 | 2019-11-18 | 2019-11-18 |  | 2021-12-16 | Overhead | R16 | 2019-12-05 | 1 |  | 14 | 531 | 544 | 2019 | 2021 | R16
164432165039 | 161824165039 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-09-19 | 2019-09-19 | 2019-09-19 |  | 2019-10-08 | Overhead | R16 | 2019-09-24 | 1 |  | 4 | 11 | 14 | 2019 | 2019 | R16
165368170611 | 163021170611 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-31 | 2019-11-05 | 2019-11-05 |  | 2020-01-08 | Overhead | R16 | 2019-12-31 | 70 |  | 41 | 7 | 116 | 2019 | 2020 | R16
168408166554 | 168991166554 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-03 | 2019-09-03 | 2019-10-03 | 2020-08-17 | 2020-10-06 | Underground | R16 | 2020-08-17 | 1 | 23 | 228 | 37 | 286 | 2019 | 2020 | R16
169136165870 | 163064165870 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-26 | 2019-09-26 | 2019-09-26 | 2019-12-09 | 2019-12-11 | Overhead | R16 | 2019-12-09 | 1 |  | 53 | 3 | 55 | 2019 | 2019 | R16
163231141332 | 169193141332 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-26 | 2019-01-26 | 2019-01-26 |  | 2019-04-15 | Overhead | R16 | 2019-03-25 | 0 |  | 41 | 16 | 56 | 2019 | 2019 | R16
169733172808 | 162035172808 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-08 | 2019-11-19 | 2019-11-25 | 2020-05-11 | 2020-05-12 | Underground | R16 | 2020-05-11 | 8 | 5 | 121 | 2 | 133 | 2019 | 2020 | R16
166468157585 | 168446157585 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-08 | 2019-07-08 | 2019-07-11 | 2019-08-01 | 2019-08-01 | Underground | R16 | 2019-08-01 | 1 | 4 | 16 |  | 19 | 2019 | 2019 | R16
163755160065 | 168789160065 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-08 | 2019-07-10 | 2019-08-05 | 2019-10-08 | 2019-10-09 | Underground | R16 | 2019-10-08 | 3 | 19 | 47 | 2 | 68 | 2019 | 2019 | R16
165700177663 | 166287177663 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-10 | 2019-10-10 | 2020-01-21 | 2020-02-20 | 2020-03-09 | Overhead | R16 | 2020-02-20 | 1 | 74 | 23 | 13 | 108 | 2019 | 2020 | R16
168463191771 | 169441191771 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2019-10-26 | 2019-11-11 | 2020-05-22 | 2021-06-16 | 2021-07-13 | Underground | R16 | 2021-06-16 | 11 | 140 | 279 | 20 | 447 | 2019 | 2021 | R16
165492159665 | 160625159665 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-17 | 2019-07-17 | 2019-08-01 | 2019-08-27 | 2019-08-27 | Underground | R16 | 2019-08-27 | 1 | 12 | 19 |  | 30 | 2019 | 2019 | R16
168578173597 | 166249173597 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2019-12-05 | 2019-12-05 | 2019-12-05 | 2020-12-18 | 2021-04-15 | Overhead | R16 | 2020-12-18 | 1 |  | 272 | 85 | 356 | 2019 | 2021 | R16
162867158944 | 167193158944 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-01 | 2019-07-03 | 2019-07-24 | 2019-09-30 | 2019-10-01 | Underground | R16 | 2019-09-30 | 3 | 16 | 49 | 2 | 67 | 2019 | 2019 | R16
163318138966 | 164731138966 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-02 | 2019-01-02 | 2019-01-02 |  | 2019-04-01 | Overhead | R16 | 2019-01-29 | 1 |  | 20 | 45 | 64 | 2019 | 2019 | R16
167750169952 | 169719169952 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-28 | 2019-10-28 | 2019-10-28 | 2019-12-10 | 2020-01-06 | Overhead | R16 | 2019-12-10 | 1 |  | 32 | 20 | 51 | 2019 | 2020 | R16
168890173174 | 163842173174 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-01 | 2019-11-27 | 2019-11-27 |  | 2020-10-08 | Overhead | R16 | 2020-08-14 | 42 |  | 188 | 40 | 268 | 2019 | 2020 | R16
167124166705 | 169875166705 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-09-09 | 2019-09-09 | 2019-10-03 |  | 2020-12-29 | Underground | R16 |  | 1 | 19 |  |  | 342 | 2019 | 2020 | R16
160018165916 | 163235165916 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-27 | 2019-09-27 | 2019-09-27 |  | 2019-12-03 | Overhead | R16 | 2019-11-20 | 1 |  | 39 | 10 | 48 | 2019 | 2019 | R16
168793197796 | 160242197796 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-30 | 2019-10-30 | 2020-07-21 | 2020-10-12 | 2020-10-14 | Underground | R16 | 2020-10-12 | 1 | 190 | 60 | 3 | 251 | 2019 | 2020 | R16
165143173724 | 165247173724 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-08-13 | 2019-12-03 | 2019-12-06 |  | 2022-08-04 | Underground | R16 |  | 81 | 4 |  |  | 778 | 2019 | 2022 | R16
163439154651 | 162900154651 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2019-06-07 | 2019-06-07 | 2019-06-07 |  | 2019-08-12 | Overhead | R16 | 2019-06-19 | 1 |  | 9 | 39 | 47 | 2019 | 2019 | R16
168770159584 | 162754159584 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-07-30 | 2019-07-30 | 2019-07-30 |  | 2023-06-07 | Overhead | R16 | 2019-11-22 | 1 |  | 84 | 924 | 1007 | 2019 | 2023 | R16
169194171774 | 161199171774 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-05 | 2019-11-05 | 2019-11-13 |  | 2020-01-08 | Underground | R16 | 2020-01-03 | 1 | 7 | 38 | 4 | 47 | 2019 | 2020 | R16
167926155569 | 164486155569 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-17 | 2019-06-17 | 2019-06-17 |  | 2020-10-06 | Underground | R16 | 2020-07-10 | 1 |  | 280 | 63 | 342 | 2019 | 2020 | R16
161884157388 | 169092157388 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-09 | 2019-07-09 | 2019-07-09 | 2019-10-15 | 2019-10-21 | Overhead | R16 | 2019-10-15 | 1 |  | 71 | 5 | 75 | 2019 | 2019 | R16
162041161154 | 163213161154 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-01 | 2019-08-01 | 2019-08-15 | 2019-10-01 | 2019-10-02 | Underground | R16 | 2019-10-01 | 1 | 11 | 34 | 2 | 45 | 2019 | 2019 | R16
164446190260 | 162544190260 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-09-23 | 2019-10-05 | 2020-05-06 |  | 2020-07-10 | Underground | R16 | 2020-10-12 | 10 | 153 | 114 |  | 210 | 2019 | 2020 | R16
160648171220 | 162170171220 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-08 | 2019-11-08 | 2019-11-08 |  | 2021-11-10 | Overhead | R16 | 2020-01-10 | 1 |  | 46 | 479 | 524 | 2019 | 2021 | R16
166673165659 | 167424165659 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-26 | 2019-08-26 | 2019-09-25 | 2019-10-18 | 2019-10-23 | Underground | R16 | 2019-10-18 | 1 | 23 | 18 | 4 | 43 | 2019 | 2019 | R16
162744166318 | 165898166318 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-16 | 2019-08-16 | 2019-10-01 |  | 2019-12-30 | Underground | R16 | 2019-12-06 | 1 | 33 | 49 | 17 | 97 | 2019 | 2019 | R16
163506173884 | 165123173884 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-25 | 2019-11-25 | 2019-12-07 |  | 2020-10-06 | Underground | R16 | 2020-07-29 | 1 | 10 | 168 | 50 | 227 | 2019 | 2020 | R16
169898157129 | 168293157129 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-05 | 2019-07-05 | 2019-07-05 | 2019-07-26 | 2019-08-08 | Underground | R16 | 2019-07-26 | 1 |  | 16 | 10 | 25 | 2019 | 2019 | R16
164398172156 | 165052172156 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-12 | 2019-08-12 | 2019-11-18 |  | 2021-12-16 | Underground | R16 | 2020-02-10 | 1 | 71 | 61 | 484 | 614 | 2019 | 2021 | R16
166944162579 | 168019162579 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-28 | 2019-08-28 | 2019-08-28 |  | 2019-10-16 | Underground | R16 | 2019-10-07 | 1 |  | 29 | 8 | 36 | 2019 | 2019 | R16
167192251021 | 162725251021 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-09-24 | 2021-02-13 | 2021-10-06 | 2022-02-09 | 2022-08-22 | Underground | R16 | 2022-02-09 | 364 | 168 | 91 | 139 | 760 | 2019 | 2022 | R16
164327162821 | 168168162821 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-29 | 2019-08-29 | 2019-08-29 | 2019-12-06 | 2019-12-19 | Underground | R16 | 2019-12-06 | 1 |  | 72 | 10 | 81 | 2019 | 2019 | R16
165756162568 | 167904162568 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-28 | 2019-08-28 | 2019-08-28 |  | 2019-10-08 | Overhead | R16 | 2019-09-24 | 1 |  | 20 | 11 | 30 | 2019 | 2019 | R16
162447159742 | 162757159742 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-30 | 2019-07-31 | 2019-07-31 | 2019-08-20 | 2019-08-21 | Overhead | R16 | 2019-08-20 | 2 |  | 15 | 2 | 17 | 2019 | 2019 | R16
163683143280 | 161585143280 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-06 | 2019-02-06 | 2019-02-14 |  | 2019-05-20 | Underground | R16 | 2019-04-15 | 1 | 7 | 43 | 26 | 74 | 2019 | 2019 | R16
166416186525 | 166771186525 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-12-07 | 2019-12-07 | 2020-04-06 |  | 2020-07-09 | Underground | R16 | 2020-06-19 | 0 | 86 | 55 | 15 | 154 | 2019 | 2020 | R16
165694162419 | 167760162419 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-27 | 2019-08-27 | 2019-08-27 |  | 2019-10-14 | Underground | R16 | 2019-10-03 | 1 |  | 28 | 8 | 35 | 2019 | 2019 | R16
163700139717 | 166366139717 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-09 | 2019-01-09 | 2019-01-10 |  | 2019-04-08 | Overhead | R16 | 2019-03-04 | 1 | 2 | 38 | 26 | 64 | 2019 | 2019 | R16
163425161340 | 164448161340 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-08-09 | 2019-08-15 | 2019-08-15 | 2019-08-29 | 2019-09-05 | Overhead | R16 | 2019-08-29 | 5 |  | 11 | 6 | 20 | 2019 | 2019 | R16
164805174197 | 168313174197 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-13 | 2019-12-13 | 2019-12-13 | 2020-03-03 | 2020-06-09 | Overhead | R16 | 2020-03-03 | 1 |  | 58 | 71 | 128 | 2019 | 2020 | R16
167361184365 | 168292184365 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-22 | 2019-10-23 | 2020-03-17 | 2020-05-12 | 2020-05-13 | Underground | R16 | 2020-05-12 | 2 | 105 | 41 | 2 | 147 | 2019 | 2020 | R16
162811172260 | 164548172260 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-09 | 2019-11-18 | 2019-11-18 | 2020-01-10 | 2021-11-10 | Overhead | R16 | 2020-01-10 | 72 |  | 40 | 479 | 589 | 2019 | 2021 | R16
161035175128 | 169892175128 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-07-15 | 2019-07-15 | 2019-12-23 | 2020-01-21 | 2020-06-09 | Underground | R16 | 2020-01-21 | 1 | 116 | 22 | 101 | 237 | 2019 | 2020 | R16
165060159366 | 162438159366 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-07-29 | 2019-07-29 | 2019-07-29 | 2020-02-21 | 2020-02-24 | Underground | R16 | 2020-02-21 | 1 |  | 150 | 2 | 151 | 2019 | 2020 | R16
165909305549 | 162784305549 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-01-10 | 2023-01-10 | 2023-01-30 | 2023-07-14 | 2023-07-27 | Overhead | R16 | 2023-07-14 | 1 | 15 | 120 | 10 | 143 | 2023 | 2023 | R16
161356173527 | 165946173527 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-03 | 2019-12-03 | 2019-12-03 |  | 2020-06-09 | Overhead | R16 | 2020-02-07 | 1 |  | 49 | 88 | 136 | 2019 | 2020 | R16
169731172396 | 163947172396 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-20 | 2019-11-20 | 2019-11-20 | 2020-01-21 | 2021-10-14 | Overhead | R16 | 2020-01-21 | 1 |  | 45 | 453 | 497 | 2019 | 2021 | R16
163180157705 | 169571157705 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-11 | 2019-07-11 | 2019-07-11 |  | 2021-11-03 | Overhead | R16 | 2019-08-26 | 1 |  | 33 | 573 | 605 | 2019 | 2021 | R16
163924156997 | 160824156997 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-05-24 | 2019-06-18 | 2019-07-02 |  | 2020-08-28 | Underground | R16 |  | 18 | 11 |  |  | 331 | 2019 | 2020 | R16
165075204164 | 168304204164 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-29 | 2019-08-29 | 2020-09-17 |  | 2021-04-21 | Underground | R16 | 2021-01-27 | 1 | 276 | 95 | 61 | 430 | 2019 | 2021 | R16
169142166206 | 169968166206 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-09 | 2019-09-09 | 2019-09-30 |  | 2020-06-09 | Underground | R16 | 2020-02-12 | 1 | 16 | 98 | 85 | 197 | 2019 | 2020 | R16
163924157060 | 160826157060 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-05-24 | 2019-06-18 | 2019-07-02 |  | 2020-08-28 | Underground | R16 |  | 18 | 11 |  |  | 331 | 2019 | 2020 | R16
167103183837 | 162031183837 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-09-19 | 2019-11-07 | 2020-03-12 |  | 2020-12-15 | Underground | R16 |  | 36 | 91 |  |  | 324 | 2019 | 2020 | R16
164102168337 | 167217168337 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-16 | 2019-10-16 | 2019-10-17 |  | 2021-11-10 | Overhead | R16 | 2020-01-29 | 1 | 2 | 75 | 466 | 541 | 2019 | 2021 | R16
167825159585 | 162688159585 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-30 | 2019-07-30 | 2019-07-30 | 2019-11-14 | 2019-12-19 | Overhead | R16 | 2019-11-14 | 1 |  | 78 | 26 | 103 | 2019 | 2019 | R16
168159176471 | 168851176471 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-09-03 | 2019-09-03 | 2020-01-10 |  | 2020-06-09 | Underground | R16 |  | 1 | 94 |  |  | 201 | 2019 | 2020 | R16
161374156683 | 166713156683 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-28 | 2019-06-28 | 2019-06-29 |  | 2019-12-06 | Overhead | R16 | 2019-08-14 | 1 | 1 | 33 | 83 | 116 | 2019 | 2019 | R16
167807158916 | 166683158916 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-28 | 2019-07-25 | 2019-07-25 | 2019-10-08 | 2019-10-09 | Overhead | R16 | 2019-10-08 | 20 |  | 54 | 2 | 74 | 2019 | 2019 | R16
164097160565 | 164374160565 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-08 | 2019-08-08 | 2019-08-08 |  | 2020-06-09 | Overhead | R16 | 2020-01-09 | 1 |  | 111 | 109 | 219 | 2019 | 2020 | R16
167815174364 | 165473174364 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-27 | 2019-11-27 | 2019-12-13 |  | 2022-08-02 | Underground | R16 |  | 1 | 13 |  |  | 700 | 2019 | 2022 | R16
164081145743 | 166490145743 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2019-03-05 | 2019-03-05 | 2019-03-11 |  | 2019-05-20 | Overhead | R16 |  | 1 | 5 |  |  | 55 | 2019 | 2019 | R16
168704187848 | 162793187848 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-09-24 | 2019-09-25 | 2020-04-16 |  | 2021-01-08 | Underground | R16 | 2020-10-06 | 2 | 147 | 124 | 69 | 339 | 2019 | 2021 | R16
164081145744 | 166952145744 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2019-03-07 | 2019-03-07 | 2019-03-11 |  | 2019-05-20 | Overhead | R16 |  | 1 | 3 |  |  | 53 | 2019 | 2019 | R16
162563170113 | 160150170113 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-30 | 2019-10-30 | 2019-10-30 |  | 2020-06-09 | Overhead | R16 | 2020-04-10 | 1 |  | 118 | 43 | 160 | 2019 | 2020 | R16
163574202722 | 167649202722 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-01 | 2019-07-02 | 2020-09-03 | 2021-04-28 | 2021-05-03 | Underground | R16 | 2021-04-28 | 2 | 308 | 170 | 4 | 481 | 2019 | 2021 | R16
161051162468 | 162038162468 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-25 | 2019-07-25 | 2019-08-27 |  | 2021-10-14 | Underground | R16 | 2020-11-19 | 1 | 24 | 323 | 236 | 581 | 2019 | 2021 | R16
161355162816 | 168539162816 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-30 | 2019-08-30 | 2019-08-30 | 2019-10-16 | 2019-10-17 | Overhead | R16 | 2019-10-16 | 1 |  | 34 | 2 | 35 | 2019 | 2019 | R16
166272162619 | 168331162619 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-08-29 | 2019-08-29 | 2019-08-29 |  | 2021-11-13 | Overhead | R16 | 2020-01-14 | 1 |  | 99 | 479 | 577 | 2019 | 2021 | R16
164204147984 | 166099147984 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-01-09 | 2019-04-02 | 2019-04-02 |  | 2019-09-17 | Underground | R16 | 2019-08-29 | 60 |  | 108 | 14 | 180 | 2019 | 2019 | R16
163677160484 | 163975160484 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-08-06 | 2019-08-06 | 2019-08-07 |  | 2019-11-15 | Underground | R16 | 2019-08-14 | 1 | 2 | 6 | 68 | 74 | 2019 | 2019 | R16
161864157546 | 169279157546 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-10 | 2019-07-10 | 2019-07-10 | 2020-02-05 | 2020-02-06 | Overhead | R16 | 2020-02-05 | 1 |  | 151 | 2 | 152 | 2019 | 2020 | R16
164145158743 | 161324158743 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-07-23 | 2019-07-23 | 2019-07-23 | 2020-04-21 | 2020-06-24 | Overhead | R16 | 2020-04-21 | 1 |  | 196 | 47 | 242 | 2019 | 2020 | R16
161656164727 | 168864164727 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-09-03 | 2019-09-03 | 2019-09-16 |  | 2020-06-09 | Overhead | R16 | 2020-02-28 | 1 | 10 | 120 | 73 | 201 | 2019 | 2020 | R16
169766159721 | 161575159721 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-07-23 | 2019-07-23 | 2019-07-31 |  | 2020-07-09 | Underground | R16 | 2020-06-09 | 1 | 7 | 225 | 23 | 253 | 2019 | 2020 | R16
166941172918 | 169357172918 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-05 | 2019-09-05 | 2019-11-26 |  | 2021-11-13 | Overhead | R16 | 2019-12-04 | 1 | 59 | 7 | 508 | 572 | 2019 | 2021 | R16
162760167226 | 165331167226 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-07 | 2019-10-07 | 2019-10-07 |  | 2021-11-10 | Overhead | R16 | 2019-12-19 | 1 |  | 54 | 495 | 548 | 2019 | 2021 | R16
169974174879 | 160040174879 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | R16 RESD AND NON RESD US | Commercial | 2019-10-29 | 2019-10-30 | 2019-12-20 |  | 2020-12-29 | Underground | R16 |  | 2 | 38 |  |  | 306 | 2019 | 2020 | R16
165120171481 | 163745171481 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-05 | 2019-08-05 | 2019-11-11 | 2021-01-05 | 2021-01-06 | Underground | R16 | 2021-01-05 | 1 | 71 | 302 | 2 | 373 | 2019 | 2021 | R16
163501170967 | 161603170967 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-06 | 2019-11-06 | 2019-11-06 | 2020-01-21 | 2021-11-10 | Overhead | R16 | 2020-01-21 | 1 |  | 55 | 472 | 526 | 2019 | 2021 | R16
168402158844 | 161742158844 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-07-24 | 2019-07-24 | 2019-07-24 |  | 2021-11-08 | Underground | R16 | 2021-04-20 | 1 |  | 455 | 145 | 599 | 2019 | 2021 | R16
164346143465 | 163773143465 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-02-15 | 2019-02-15 | 2019-02-15 |  | 2021-01-21 | Overhead | R16 | 2020-10-14 | 1 |  | 434 | 72 | 505 | 2019 | 2021 | R16
162759158578 | 161380158578 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-22 | 2019-07-22 | 2019-07-22 | 2019-11-25 | 2021-12-16 | Overhead | R16 | 2019-11-25 | 1 |  | 91 | 539 | 629 | 2019 | 2021 | R16
165934157037 | 168290157037 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-07-05 | 2019-07-05 | 2019-07-05 | 2020-02-21 | 2020-02-24 | Underground | R16 | 2020-02-21 | 1 |  | 166 | 2 | 167 | 2019 | 2020 | R16
162831173938 | 164917173938 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-11-25 | 2019-12-09 | 2019-12-10 |  | 2021-11-13 | Overhead | R16 |  | 11 | 2 |  |  | 515 | 2019 | 2021 | R16
162054175647 | 164964175647 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-18 | 2019-06-18 | 2020-01-02 |  | 2020-07-02 | Underground | R16 | 2020-05-06 | 1 | 143 | 90 | 42 | 273 | 2019 | 2020 | R16
162832160999 | 163999160999 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-06 | 2019-08-13 | 2019-08-14 | 2020-04-17 | 2020-04-17 | Overhead | R16 | 2020-04-17 | 6 | 2 | 178 |  | 184 | 2019 | 2020 | R16
167456165928 | 163213165928 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-26 | 2019-09-26 | 2019-09-26 | 2020-01-29 | 2021-11-13 | Overhead | R16 | 2020-01-29 | 1 |  | 90 | 468 | 557 | 2019 | 2021 | R16
167086171691 | 162887171691 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-13 | 2019-11-13 | 2019-11-13 |  | 2020-07-01 | Overhead | R16 | 2020-03-31 | 1 |  | 100 | 67 | 166 | 2019 | 2020 | R16
164463150295 | 165810150295 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-26 | 2019-04-26 | 2019-04-26 |  | 2019-08-12 | Overhead | R16 | 2019-06-17 | 1 |  | 37 | 41 | 77 | 2019 | 2019 | R16
160007174146 | 165601174146 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-08 | 2019-10-08 | 2019-12-11 |  | 2020-06-09 | Underground | R16 | 2020-02-25 | 1 | 47 | 55 | 76 | 176 | 2019 | 2020 | R16
161855163236 | 163362163236 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-01 | 2019-08-05 | 2019-09-03 |  | 2019-10-30 | Underground | R16 | 2019-10-21 | 3 | 22 | 35 | 8 | 65 | 2019 | 2019 | R16
166337156896 | 167970156896 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-07-02 | 2019-07-02 | 2019-07-03 | 2019-07-05 | 2019-07-08 | Underground | R16 | 2019-07-05 | 1 | 2 | 3 | 2 | 5 | 2019 | 2019 | R16
163423162578 | 168150162578 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-28 | 2019-08-28 | 2019-08-28 | 2019-10-01 | 2019-10-01 | Underground | R16 | 2019-10-01 | 1 |  | 25 |  | 25 | 2019 | 2019 | R16
169763159531 | 162756159531 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-07-30 | 2019-07-30 | 2019-07-31 |  | 2020-10-06 | Underground | R16 | 2020-08-27 | 1 | 2 | 282 | 29 | 311 | 2019 | 2020 | R16
163749161141 | 165159161141 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-13 | 2019-08-13 | 2019-08-13 |  | 2019-11-08 | Overhead | R16 | 2019-11-01 | 1 |  | 59 | 6 | 64 | 2019 | 2019 | R16
160783161090 | 165293161090 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-13 | 2019-08-13 | 2019-08-13 |  | 2020-07-14 | Overhead | R16 | 2020-06-19 | 1 |  | 224 | 18 | 241 | 2019 | 2020 | R16
161045172428 | 161309172428 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-16 | 2019-09-16 | 2019-11-20 | 2022-11-30 | 2023-06-07 | Underground | R16 | 2022-11-30 | 1 | 48 | 791 | 136 | 973 | 2019 | 2023 | R16
169236157105 | 167621157105 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-01 | 2019-07-01 | 2019-07-03 |  | 2019-11-15 | Underground | R16 | 2019-08-08 | 1 | 3 | 27 | 72 | 100 | 2019 | 2019 | R16
164424222362 | 164337222362 | RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Residential Subdivision | 2019-08-08 | 2019-08-08 | 2021-03-03 | 2021-12-08 | 2022-01-04 | Underground | R16 | 2021-12-08 | 1 | 410 | 201 | 20 | 629 | 2019 | 2022 | R16
160815166911 | 164600166911 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-10-03 | 2019-10-04 | 2019-10-04 |  | 2020-12-14 | Overhead | R16 | 2020-09-09 | 2 |  | 244 | 69 | 313 | 2019 | 2020 | R16
164766178699 | 166257178699 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-05 | 2019-12-05 | 2020-01-30 | 2020-03-09 | 2020-06-09 | Underground | R16 | 2020-03-09 | 1 | 41 | 28 | 67 | 134 | 2019 | 2020 | R16
168930165607 | 162418165607 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-09-23 | 2019-09-23 | 2019-09-24 | 2020-03-11 | 2020-08-28 | Overhead | R16 | 2020-03-11 | 1 | 2 | 122 | 123 | 245 | 2019 | 2020 | R16
164776147222 | 163676147222 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-14 | 2019-02-19 | 2019-03-25 |  | 2019-06-03 | Underground | R16 | 2019-05-13 | 4 | 25 | 36 | 16 | 78 | 2019 | 2019 | R16
168075175432 | 168076175432 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-12 | 2019-12-13 | 2019-12-31 |  | 2021-11-10 | Underground | R16 | 2020-01-29 | 2 | 13 | 22 | 466 | 500 | 2019 | 2021 | R16
167558165151 | 167336165151 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-26 | 2019-08-26 | 2019-09-19 |  | 2020-06-09 | Underground | R16 | 2020-01-28 | 1 | 19 | 94 | 96 | 207 | 2019 | 2020 | R16
166362161924 | 163705161924 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-08-05 | 2019-08-05 | 2019-08-22 |  | 2020-06-09 | Underground | R16 | 2020-03-26 | 1 | 14 | 156 | 54 | 222 | 2019 | 2020 | R16
164189181325 | 168359181325 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-12-16 | 2020-02-20 | 2020-02-21 | 2020-06-29 | 2020-10-02 | Overhead | R16 | 2020-06-29 | 49 | 2 | 92 | 70 | 210 | 2019 | 2020 | R16
168176159733 | 162478159733 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-29 | 2019-08-01 | 2019-08-01 |  | 2019-10-16 | Underground | R16 | 2019-10-10 | 4 |  | 51 | 5 | 58 | 2019 | 2019 | R16
166486156496 | 166562156496 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-27 | 2019-06-27 | 2019-06-28 | 2019-07-11 | 2019-07-12 | Overhead | R16 | 2019-07-11 | 1 | 2 | 10 | 2 | 12 | 2019 | 2019 | R16
165558155063 | 163440155063 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-11 | 2019-06-11 | 2019-06-11 | 2019-10-29 | 2019-11-07 | Overhead | R16 | 2019-10-29 | 1 |  | 101 | 8 | 108 | 2019 | 2019 | R16
164930141898 | 160853141898 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-01 | 2019-02-01 | 2019-02-01 |  | 2019-04-01 | Overhead | R16 | 2019-02-25 | 1 |  | 17 | 26 | 42 | 2019 | 2019 | R16
160613168888 | 164182168888 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-02 | 2019-10-02 | 2019-10-19 | 2019-12-18 | 2019-12-18 | Underground | R16 | 2019-12-18 | 1 | 13 | 43 |  | 56 | 2019 | 2019 | R16
160064172913 | 162281172913 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-08 | 2019-11-26 | 2019-11-26 | 2020-02-24 | 2020-06-09 | Overhead | R16 | 2020-02-24 | 13 |  | 65 | 77 | 153 | 2019 | 2020 | R16
165152182405 | 160051182405 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-07-15 | 2019-07-15 | 2020-02-28 | 2021-04-20 | 2021-05-20 | Underground | R16 | 2021-04-20 | 1 | 165 | 298 | 23 | 484 | 2019 | 2021 | R16
164933155458 | 163774155458 | CUSTOMER UPGRADE IN SERVICE | UG SVC CONVERSION | Residential | 2019-06-13 | 2019-06-13 | 2019-06-19 |  | 2020-06-29 | Underground | R16 | 2020-04-24 | 1 | 5 | 223 | 47 | 273 | 2019 | 2020 | R16
164287161540 | 166140161540 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-18 | 2019-08-18 | 2019-08-18 | 2019-09-06 | 2019-09-09 | Overhead | R16 | 2019-09-06 | 0 |  | 15 | 2 | 16 | 2019 | 2019 | R16
162766157154 | 168866157154 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-09 | 2019-07-09 | 2019-07-09 |  | 2019-08-28 | Overhead | R16 | 2019-08-22 | 1 |  | 33 | 5 | 37 | 2019 | 2019 | R16
163277156564 | 165083156564 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-19 | 2019-06-19 | 2019-06-27 | 2019-08-04 | 2019-12-06 | Underground | R16 | 2019-08-04 | 1 | 7 | 27 | 90 | 123 | 2019 | 2019 | R16
168402158907 | 161719158907 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-25 | 2019-07-25 | 2019-07-25 |  | 2019-12-17 | Overhead | R16 | 2019-12-05 | 1 |  | 96 | 9 | 104 | 2019 | 2019 | R16
163117161720 | 166214161720 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-19 | 2019-08-19 | 2019-08-19 |  | 2022-08-02 | Overhead | R16 |  | 1 |  |  |  | 772 | 2019 | 2022 | R16
161332325007 | 160095325007 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-11 | 2023-07-11 | 2023-07-13 | 2023-07-17 | 2023-08-07 | Overhead | R16 | 2023-07-17 | 1 | 3 | 3 | 16 | 20 | 2023 | 2023 | R16
162428160448 | 169410160448 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-11 | 2019-07-11 | 2019-08-07 |  | 2019-10-04 | Underground | R16 | 2019-09-23 | 1 | 20 | 34 | 10 | 62 | 2019 | 2019 | R16
160817163784 | 169975163784 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-09 | 2019-09-09 | 2019-09-09 | 2019-09-25 | 2019-09-25 | Overhead | R16 | 2019-09-25 | 1 |  | 13 |  | 13 | 2019 | 2019 | R16
160959186901 | 163088186901 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-13 | 2019-11-13 | 2020-04-08 | 2020-07-15 | 2020-07-16 | Underground | R16 | 2020-07-15 | 1 | 106 | 71 | 2 | 177 | 2019 | 2020 | R16
160442169165 | 160912169165 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-18 | 2019-07-18 | 2019-10-21 | 2020-02-07 | 2020-02-18 | Underground | R16 | 2020-02-07 | 1 | 68 | 80 | 8 | 154 | 2019 | 2020 | R16
167613168281 | 166839168281 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-14 | 2019-10-14 | 2019-10-14 | 2019-10-16 | 2019-11-26 | Overhead | R16 | 2019-10-16 | 1 |  | 3 | 30 | 32 | 2019 | 2019 | R16
168523167288 | 165360167288 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-07 | 2019-10-07 | 2019-10-07 | 2019-12-10 | 2020-01-06 | Overhead | R16 | 2019-12-10 | 1 |  | 47 | 20 | 66 | 2019 | 2020 | R16
161038167512 | 166084167512 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-10 | 2019-10-10 | 2019-10-10 | 2019-12-31 | 2020-01-08 | Overhead | R16 | 2019-12-31 | 1 |  | 59 | 7 | 65 | 2019 | 2020 | R16
165224149178 | 166112149178 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-03-04 | 2019-03-04 | 2019-04-15 |  | 2021-10-25 | Underground | R16 |  | 1 | 31 |  |  | 691 | 2019 | 2021 | R16
160144156958 | 168248156958 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-05 | 2019-07-05 | 2019-07-05 |  | 2021-11-11 | Overhead | R16 | 2019-07-15 | 1 |  | 7 | 609 | 615 | 2019 | 2021 | R16
164463163151 | 168318163151 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-29 | 2019-08-29 | 2019-09-03 | 2019-10-08 | 2019-10-09 | Underground | R16 | 2019-10-08 | 1 | 4 | 26 | 2 | 30 | 2019 | 2019 | R16
160791173976 | 164871173976 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-11-22 | 2019-11-22 | 2019-12-10 | 2021-03-23 | 2021-11-05 | Underground | R16 | 2021-03-23 | 1 | 13 | 336 | 164 | 511 | 2019 | 2021 | R16
165233141827 | 160451141827 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-30 | 2019-01-30 | 2019-01-30 |  | 2019-04-01 | Underground | R16 | 2019-02-26 | 1 |  | 20 | 25 | 44 | 2019 | 2019 | R16
168795179466 | 160124179466 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-30 | 2019-10-30 | 2020-02-05 | 2020-04-23 | 2020-04-30 | Underground | R16 | 2020-04-23 | 1 | 71 | 57 | 6 | 132 | 2019 | 2020 | R16
169432161801 | 166421161801 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-20 | 2019-08-20 | 2019-08-20 | 2019-09-04 | 2019-09-06 | Overhead | R16 | 2019-09-04 | 1 |  | 12 | 3 | 14 | 2019 | 2019 | R16
163965172978 | 162017172978 | NON-RESIDENTIAL - HEALTH CARE | R16 RESD AND NON RESD US | Commercial | 2019-11-08 | 2019-11-08 | 2019-11-26 | 2020-05-15 | 2021-07-11 | Underground | R16 | 2020-05-15 | 1 | 13 | 124 | 301 | 436 | 2019 | 2021 | R16
169446165763 | 162816165763 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-09-25 | 2019-09-25 | 2019-09-25 |  | 2021-12-16 | Overhead | R16 | 2019-01-09 | 1 |  |  | 767 | 582 | 2019 | 2021 | R16
160357179974 | 168011179974 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-10-21 | 2019-10-21 | 2020-02-11 | 2020-04-29 | 2020-07-07 | Underground | R16 | 2020-04-29 | 1 | 82 | 57 | 50 | 187 | 2019 | 2020 | R16
166716157991 | 169967157991 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-15 | 2019-07-16 | 2019-07-16 |  | 2019-12-06 | Overhead | R16 | 2019-09-13 | 2 |  | 44 | 61 | 105 | 2019 | 2019 | R16
169124169602 | 169069169602 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-24 | 2019-10-24 | 2019-10-24 | 2019-12-11 | 2019-12-12 | Overhead | R16 | 2019-12-11 | 1 |  | 35 | 2 | 36 | 2019 | 2019 | R16
165268142060 | 160796142060 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-02 | 2019-02-02 | 2019-02-02 |  | 2019-04-15 | Overhead | R16 | 2019-03-07 | 0 |  | 24 | 28 | 51 | 2019 | 2019 | R16
163270158811 | 161626158811 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-24 | 2019-07-24 | 2019-07-24 |  | 2019-09-04 | Underground | R16 | 2019-08-28 | 1 |  | 26 | 6 | 31 | 2019 | 2019 | R16
163500169845 | 169600169845 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-28 | 2019-10-28 | 2019-10-28 |  | 2020-06-09 | Overhead | R16 | 2020-02-19 | 1 |  | 83 | 80 | 162 | 2019 | 2020 | R16
167438164659 | 169890164659 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-09 | 2019-09-13 | 2019-09-17 | 2019-10-01 | 2022-05-17 | Overhead | R16 | 2019-10-01 | 5 | 3 | 11 | 686 | 702 | 2019 | 2022 | R16
163829164156 | 160784164156 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2019-09-12 | 2019-09-12 | 2019-09-12 | 2020-01-15 | 2020-01-17 | Overhead | R16 | 2020-01-15 | 1 |  | 90 | 3 | 92 | 2019 | 2020 | R16
169546165456 | 162413165456 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-23 | 2019-09-23 | 2019-09-23 | 2019-12-20 | 2021-11-10 | Overhead | R16 | 2019-12-20 | 1 |  | 65 | 494 | 558 | 2019 | 2021 | R16
165356141181 | 168731141181 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-23 | 2019-01-23 | 2019-01-23 |  | 2022-07-19 | Overhead | R16 |  | 1 |  |  |  | 910 | 2019 | 2022 | R16
164592167362 | 165190167362 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-07 | 2019-10-07 | 2019-10-07 | 2020-02-18 | 2020-02-20 | Overhead | R16 | 2020-02-18 | 1 |  | 97 | 3 | 99 | 2019 | 2020 | R16
167453260020 | 167878260020 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-12-12 | 2021-11-01 | 2021-12-06 | 2023-03-29 | 2023-05-05 | Underground | R16 | 2023-03-29 | 493 | 26 | 343 | 28 | 887 | 2019 | 2023 | R16
165382146941 | 169426146941 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-22 | 2019-03-22 | 2019-03-22 |  | 2019-04-25 | Underground | R16 | 2019-04-01 | 1 |  | 7 | 19 | 25 | 2019 | 2019 | R16
168406165445 | 162403165445 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-23 | 2019-09-23 | 2019-09-23 | 2019-11-13 | 2019-11-21 | Overhead | R16 | 2019-11-13 | 1 |  | 38 | 7 | 44 | 2019 | 2019 | R16
168953173843 | 161151173843 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-16 | 2019-09-19 | 2019-12-06 | 2020-02-14 | 2020-06-09 | Underground | R16 | 2020-02-14 | 4 | 57 | 51 | 83 | 192 | 2019 | 2020 | R16
166532168761 | 166814168761 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-10-14 | 2019-10-15 | 2019-10-18 |  | 2020-06-09 | Overhead | R16 |  | 2 | 4 |  |  | 172 | 2019 | 2020 | R16
160680172134 | 163703172134 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-19 | 2019-11-19 | 2019-11-19 | 2020-01-15 | 2020-01-16 | Overhead | R16 | 2020-01-15 | 1 |  | 42 | 2 | 43 | 2019 | 2020 | R16
163821165937 | 163304165937 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-09-27 | 2019-09-27 | 2019-09-27 |  | 2021-05-07 | Underground | R16 | 2021-02-25 | 1 |  | 370 | 52 | 421 | 2019 | 2021 | R16
166019173702 | 161070173702 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-11-04 | 2019-11-04 | 2019-12-05 | 2020-07-07 | 2020-07-10 | Underground | R16 | 2020-07-07 | 1 | 24 | 154 | 4 | 180 | 2019 | 2020 | R16
166627170590 | 161102170590 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-04 | 2019-11-04 | 2019-11-04 |  | 2021-11-13 | Overhead | R16 | 2020-01-08 | 1 |  | 48 | 483 | 530 | 2019 | 2021 | R16
169280156000 | 163442156000 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-11 | 2019-06-11 | 2019-06-21 |  | 2019-08-28 | Underground | R16 | 2019-08-20 | 1 | 9 | 43 | 7 | 57 | 2019 | 2019 | R16
165648169875 | 166312169875 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-10 | 2019-10-10 | 2019-10-29 | 2020-04-29 | 2020-07-09 | Underground | R16 | 2020-04-29 | 1 | 14 | 132 | 52 | 196 | 2019 | 2020 | R16
164687170035 | 165001170035 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-08-12 | 2019-08-12 | 2019-10-28 |  | 2019-12-11 | Overhead | R16 |  | 1 | 56 |  |  | 88 | 2019 | 2019 | R16
160209162344 | 163620162344 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-12 | 2019-06-17 | 2019-08-26 |  | 2019-10-30 | Underground | R16 | 2019-10-22 | 4 | 51 | 42 | 7 | 101 | 2019 | 2019 | R16
165567174581 | 166497174581 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-11 | 2019-10-11 | 2019-12-16 |  | 2021-07-12 | Underground | R16 | 2020-11-24 | 1 | 47 | 247 | 165 | 457 | 2019 | 2021 | R16
165568140953 | 168187140953 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-22 | 2019-01-22 | 2019-01-23 |  | 2019-04-08 | Overhead | R16 | 2019-03-04 | 1 | 2 | 29 | 26 | 55 | 2019 | 2019 | R16
164699166795 | 164831166795 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-04 | 2019-10-04 | 2019-10-04 |  | 2019-10-16 | Overhead | R16 | 2019-10-11 | 1 |  | 6 | 4 | 9 | 2019 | 2019 | R16
163280172678 | 164993172678 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-25 | 2019-11-25 | 2019-11-25 |  | 2021-11-10 | Overhead | R16 | 2020-01-15 | 1 |  | 38 | 476 | 513 | 2019 | 2021 | R16
168403174144 | 169788174144 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-29 | 2019-10-31 | 2019-12-10 | 2020-02-11 | 2020-02-12 | Underground | R16 | 2020-02-11 | 3 | 29 | 46 | 2 | 77 | 2019 | 2020 | R16
168144161625 | 166125161625 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-19 | 2019-08-19 | 2019-08-19 | 2019-09-10 | 2019-09-12 | Overhead | R16 | 2019-09-10 | 1 |  | 17 | 3 | 19 | 2019 | 2019 | R16
162881206402 | 166636206402 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE FOR UPGRADE UD | Commercial | 2019-06-28 | 2019-10-15 | 2020-10-06 | 2021-10-06 | 2023-09-23 | Underground | R16 | 2021-10-06 | 78 | 256 | 262 | 513 | 1106 | 2019 | 2023 | R16
165663142184 | 161124142184 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-02-04 | 2019-02-04 | 2019-02-04 |  | 2021-08-11 | Overhead | R16 | 2021-08-11 | 1 |  | 658 |  | 658 | 2019 | 2021 | R16
165678141987 | 164713141987 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-01-02 | 2019-01-28 | 2019-02-01 |  | 2019-09-03 | Overhead | R16 |  | 19 | 5 |  |  | 175 | 2019 | 2019 | R16
169567165668 | 162646165668 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-24 | 2019-09-24 | 2019-09-24 | 2020-10-06 | 2021-02-04 | Underground | R16 | 2020-10-06 | 1 |  | 271 | 88 | 358 | 2019 | 2021 | R16
167183169787 | 161692169787 | NON-RESIDENTIAL - HEALTH CARE | UG R16 RESD AND NON RESD UD | Commercial | 2019-07-24 | 2019-07-24 | 2019-10-28 |  | 2020-11-05 | Underground | R16 | 2020-06-16 | 1 | 69 | 167 | 103 | 337 | 2019 | 2020 | R16
161716155256 | 164076155256 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-06-14 | 2019-06-14 | 2019-06-14 |  | 2020-07-09 | Underground | R16 |  | 1 |  |  |  | 280 | 2019 | 2020 | R16
163065161262 | 165395161262 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-14 | 2019-08-14 | 2019-08-14 |  | 2019-12-06 | Overhead | R16 | 2019-10-14 | 1 |  | 44 | 40 | 83 | 2019 | 2019 | R16
167181174471 | 168349174471 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-16 | 2019-12-17 | 2019-12-17 | 2020-03-03 | 2020-12-18 | Overhead | R16 | 2020-03-03 | 2 |  | 56 | 209 | 265 | 2019 | 2020 | R16
169721166301 | 162783166301 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-24 | 2019-09-24 | 2019-09-30 |  | 2019-11-21 | Underground | R16 | 2019-11-13 | 1 | 5 | 33 | 7 | 43 | 2019 | 2019 | R16
167352213902 | 165837213902 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-09 | 2020-11-05 | 2020-12-14 | 2023-06-07 | 2023-07-03 | Underground | R16 | 2023-06-07 | 282 | 28 | 648 | 19 | 974 | 2019 | 2023 | R16
162388179418 | 165821179418 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-03 | 2019-12-03 | 2020-02-06 |  | 2020-06-09 | Underground | R16 | 2020-03-30 | 1 | 48 | 38 | 52 | 136 | 2019 | 2020 | R16
161157159652 | 162807159652 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-30 | 2019-07-31 | 2019-07-31 |  | 2019-09-24 | Overhead | R16 | 2019-09-16 | 2 |  | 34 | 7 | 41 | 2019 | 2019 | R16
167985170945 | 168246170945 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-10-22 | 2019-10-22 | 2019-11-06 | 2020-01-30 | 2020-02-03 | Underground | R16 | 2020-01-30 | 1 | 12 | 62 | 3 | 75 | 2019 | 2020 | R16
162925182345 | 169692182345 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-06 | 2019-09-06 | 2020-02-28 |  | 2023-06-02 | Underground | R16 | 2020-04-22 | 1 | 126 | 39 | 813 | 976 | 2019 | 2023 | R16
165897176762 | 161784176762 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-07-24 | 2019-08-29 | 2020-01-13 | 2020-05-13 | 2020-08-31 | Underground | R16 | 2020-05-13 | 27 | 98 | 88 | 79 | 289 | 2019 | 2020 | R16
164218165209 | 168879165209 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-03 | 2019-09-03 | 2019-09-20 |  | 2019-11-08 | Underground | R16 | 2019-10-31 | 1 | 14 | 30 | 7 | 49 | 2019 | 2019 | R16
165830158290 | 160828158290 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-18 | 2019-07-18 | 2019-07-18 |  | 2019-09-26 | Overhead | R16 | 2019-09-18 | 1 |  | 45 | 7 | 51 | 2019 | 2019 | R16
168930164759 | 161553164759 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-17 | 2019-09-17 | 2019-09-18 |  | 2019-11-21 | Overhead | R16 | 2019-11-14 | 1 | 2 | 42 | 6 | 48 | 2019 | 2019 | R16
169931170299 | 161181170299 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-07-22 | 2019-07-22 | 2019-10-31 | 2019-11-14 | 2020-04-27 | Overhead | R16 | 2019-11-14 | 1 | 74 | 11 | 118 | 201 | 2019 | 2020 | R16
162146167669 | 166146167669 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-10 | 2019-10-10 | 2019-10-10 | 2019-11-13 | 2019-11-21 | Overhead | R16 | 2019-11-13 | 1 |  | 25 | 7 | 31 | 2019 | 2019 | R16
163717168945 | 167093168945 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-15 | 2019-10-15 | 2019-10-21 | 2019-12-19 | 2022-05-17 | Overhead | R16 | 2019-12-19 | 1 | 5 | 44 | 629 | 676 | 2019 | 2022 | R16
165221164920 | 162451164920 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-07-29 | 2019-08-14 | 2019-09-17 | 2020-02-20 | 2020-07-07 | Underground | R16 | 2020-02-20 | 13 | 25 | 113 | 99 | 247 | 2019 | 2020 | R16
165592174439 | 161968174439 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-11-08 | 2019-12-14 | 2019-12-15 | 2020-02-11 | 2020-02-12 | Overhead | R16 | 2020-02-11 | 26 | 0 | 42 | 2 | 69 | 2019 | 2020 | R16
168923172915 | 165322172915 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-26 | 2019-11-26 | 2019-11-26 |  | 2020-06-09 | Overhead | R16 | 2019-12-23 | 1 |  | 20 | 122 | 141 | 2019 | 2020 | R16
169293169388 | 168815169388 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-24 | 2019-10-24 | 2019-10-24 |  | 2020-01-06 | Overhead | R16 | 2019-12-13 | 1 |  | 37 | 17 | 53 | 2019 | 2020 | R16
160732157265 | 168453157265 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-07 | 2019-07-07 | 2019-07-07 | 2019-08-06 | 2019-08-06 | Overhead | R16 | 2019-08-06 | 0 |  | 22 |  | 22 | 2019 | 2019 | R16
167996167645 | 167986167645 | NON-RESIDENTIAL - LARGE OFFICE | UG R16 RESD AND NON RESD UD | Commercial | 2019-07-03 | 2019-07-03 | 2019-10-10 | 2020-02-24 | 2020-07-09 | Underground | R16 | 2020-02-24 | 1 | 72 | 98 | 99 | 267 | 2019 | 2020 | R16
165988146811 | 167881146811 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-03-12 | 2019-03-12 | 2019-03-22 |  | 2019-08-12 | Underground | R16 |  | 1 | 9 |  |  | 110 | 2019 | 2019 | R16
166678157058 | 168128157058 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-03 | 2019-07-03 | 2019-07-03 | 2020-03-25 | 2019-07-18 | Underground | R16 | 2020-03-25 | 1 |  | 191 |  | 12 | 2019 | 2019 | R16
166014148164 | 164836148164 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-01-03 | 2019-01-28 | 2019-04-04 |  | 2019-05-28 | Underground | R16 |  | 18 | 49 |  |  | 104 | 2019 | 2019 | R16
162431321709 | 162726321709 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-01 | 2023-06-01 | 2023-06-09 | 2023-08-15 | 2023-10-24 | Underground | R16 | 2023-08-15 | 1 | 7 | 48 | 51 | 104 | 2023 | 2023 | R16
167535180084 | 160370180084 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-30 | 2019-10-30 | 2020-02-11 |  | 2020-07-07 | Underground | R16 | 2020-05-13 | 1 | 75 | 67 | 40 | 180 | 2019 | 2020 | R16
166064146049 | 162735146049 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-02-11 | 2019-02-11 | 2019-03-14 |  | 2019-12-19 | Overhead | R16 | 2019-08-13 | 1 | 24 | 109 | 93 | 224 | 2019 | 2019 | R16
164406163458 | 169229163458 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-05 | 2019-09-05 | 2019-09-05 | 2019-11-27 | 2019-12-09 | Overhead | R16 | 2019-11-27 | 1 |  | 60 | 9 | 68 | 2019 | 2019 | R16
164438160119 | 168722160119 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-08 | 2019-07-08 | 2019-08-06 | 2019-08-28 | 2019-09-04 | Underground | R16 | 2019-08-28 | 1 | 22 | 17 | 6 | 43 | 2019 | 2019 | R16
160098159377 | 162310159377 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-07-26 | 2019-07-26 | 2019-07-30 | 2019-08-21 | 2020-04-01 | Underground | R16 | 2019-08-21 | 1 | 3 | 17 | 161 | 179 | 2019 | 2020 | R16
165569175588 | 164317175588 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-11-20 | 2019-11-20 | 2020-01-02 |  | 2020-06-09 | Underground | R16 | 2020-03-04 | 1 | 32 | 45 | 70 | 145 | 2019 | 2020 | R16
166093152231 | 164099152231 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-20 | 2019-04-29 | 2019-05-13 |  | 2019-11-08 | Underground | R16 |  | 49 | 11 |  |  | 188 | 2019 | 2019 | R16
162486157579 | 164929157579 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-18 | 2019-06-18 | 2019-07-10 |  | 2019-12-06 | Underground | R16 | 2019-08-13 | 1 | 17 | 25 | 84 | 124 | 2019 | 2019 | R16
166093148654 | 164262148654 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-20 | 2019-04-05 | 2019-04-10 |  | 2019-10-16 | Underground | R16 |  | 33 | 4 |  |  | 171 | 2019 | 2019 | R16
164926169897 | 169807169897 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-29 | 2019-10-29 | 2019-10-29 | 2020-01-22 | 2021-11-10 | Overhead | R16 | 2020-01-22 | 1 |  | 62 | 471 | 532 | 2019 | 2021 | R16
162222155688 | 164943155688 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-18 | 2019-06-18 | 2019-06-18 |  | 2023-06-07 | Overhead | R16 | 2019-11-04 | 1 |  | 100 | 938 | 1037 | 2019 | 2023 | R16
169626163305 | 169022163305 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-03 | 2019-09-03 | 2019-09-03 | 2019-10-01 | 2019-10-02 | Overhead | R16 | 2019-10-01 | 1 |  | 21 | 2 | 22 | 2019 | 2019 | R16
166093148842 | 164265148842 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-20 | 2019-04-05 | 2019-04-10 |  | 2019-10-28 | Underground | R16 |  | 33 | 4 |  |  | 179 | 2019 | 2019 | R16
167348172674 | 163898172674 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-10-01 | 2019-10-01 | 2019-11-25 | 2020-01-03 | 2020-01-17 | Overhead | R16 | 2020-01-03 | 1 | 40 | 30 | 11 | 79 | 2019 | 2020 | R16
162225322471 | 165924322471 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2023-06-16 | 2023-06-16 | 2023-06-16 | 2023-12-05 | 2023-12-29 | Overhead | R16 | 2023-12-05 | 1 |  | 123 | 19 | 141 | 2023 | 2023 | R16
162406173473 | 166201173473 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-04 | 2019-12-04 | 2019-12-04 |  | 2021-11-10 | Overhead | R16 | 2019-12-20 | 1 |  | 13 | 494 | 506 | 2019 | 2021 | R16
166093148841 | 164269148841 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-20 | 2019-04-02 | 2019-04-10 |  | 2019-12-09 | Underground | R16 |  | 30 | 7 |  |  | 209 | 2019 | 2019 | R16
166093148658 | 164270148658 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-20 | 2019-04-03 | 2019-04-10 |  | 2022-08-29 | Underground | R16 |  | 31 | 6 |  |  | 919 | 2019 | 2022 | R16
164927158794 | 160974158794 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-19 | 2019-07-19 | 2019-07-23 |  | 2019-09-04 | Overhead | R16 | 2019-08-28 | 1 | 3 | 27 | 6 | 34 | 2019 | 2019 | R16
162562172322 | 164442172322 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-03 | 2019-10-03 | 2019-11-19 | 2020-03-10 | 2020-03-11 | Underground | R16 | 2020-03-10 | 1 | 34 | 81 | 2 | 115 | 2019 | 2020 | R16
161271163174 | 168941163174 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-03 | 2019-09-03 | 2019-09-03 |  | 2019-10-16 | Overhead | R16 | 2019-10-09 | 1 |  | 27 | 6 | 32 | 2019 | 2019 | R16
166093156511 | 164275156511 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-20 | 2019-06-21 | 2019-06-27 |  | 2019-11-14 | Underground | R16 |  | 88 | 5 |  |  | 192 | 2019 | 2019 | R16
165188178485 | 161224178485 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-11-04 | 2019-12-03 | 2020-01-28 |  | 2022-06-08 | Underground | R16 |  | 22 | 41 |  |  | 678 | 2019 | 2022 | R16
166093152235 | 164277152235 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-20 | 2019-05-01 | 2019-05-13 |  | 2022-08-29 | Underground | R16 |  | 51 | 9 |  |  | 919 | 2019 | 2022 | R16
162784205853 | 160204205853 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-10 | 2019-09-10 | 2020-10-01 |  | 2022-01-04 | Underground | R16 | 2021-11-22 | 1 | 278 | 298 | 32 | 606 | 2019 | 2022 | R16
168126161196 | 165975161196 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-17 | 2019-08-17 | 2019-08-17 | 2019-11-20 | 2019-11-21 | Overhead | R16 | 2019-11-20 | 0 |  | 68 | 2 | 69 | 2019 | 2019 | R16
166093156510 | 164281156510 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-20 | 2019-06-21 | 2019-06-27 |  | 2020-06-09 | Underground | R16 |  | 88 | 5 |  |  | 340 | 2019 | 2020 | R16
161411171477 | 165645171477 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-10-08 | 2019-10-08 | 2019-11-12 |  | 2021-07-01 | Underground | R16 |  | 1 | 26 |  |  | 453 | 2019 | 2021 | R16
166093156509 | 164282156509 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-20 | 2019-06-21 | 2019-06-27 |  | 2019-10-30 | Underground | R16 |  | 88 | 5 |  |  | 181 | 2019 | 2019 | R16
162420167816 | 166154167816 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-10 | 2019-10-10 | 2019-10-11 |  | 2021-11-13 | Overhead | R16 | 2020-01-08 | 1 | 2 | 64 | 483 | 547 | 2019 | 2021 | R16
166881173565 | 166144173565 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-12-04 | 2019-12-04 | 2019-12-04 | 2020-01-13 | 2020-01-14 | Overhead | R16 | 2020-01-13 | 1 |  | 29 | 2 | 30 | 2019 | 2020 | R16
166093157277 | 164285157277 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-20 | 2019-06-28 | 2019-07-09 |  | 2019-10-14 | Underground | R16 |  | 93 | 8 |  |  | 169 | 2019 | 2019 | R16
168659171988 | 161778171988 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-11-08 | 2019-11-08 | 2019-11-15 |  | 2021-11-10 | Overhead | R16 | 2020-01-22 | 1 | 6 | 49 | 471 | 524 | 2019 | 2021 | R16
166093159766 | 164289159766 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-20 | 2019-07-22 | 2019-08-01 |  | 2019-10-28 | Underground | R16 |  | 109 | 9 |  |  | 179 | 2019 | 2019 | R16
165187160473 | 164482160473 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-08 | 2019-08-08 | 2019-08-08 |  | 2019-08-28 | Overhead | R16 | 2019-08-20 | 1 |  | 9 | 7 | 15 | 2019 | 2019 | R16
165900182735 | 161039182735 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-11-04 | 2019-11-04 | 2020-03-03 |  | 2020-06-16 | Overhead | R16 |  | 1 | 87 |  |  | 162 | 2019 | 2020 | R16
166066157389 | 169074157389 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-09 | 2019-07-09 | 2019-07-09 | 2019-11-02 | 2019-11-05 | Overhead | R16 | 2019-11-02 | 1 |  | 84 | 2 | 86 | 2019 | 2019 | R16
166046176771 | 166899176771 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-22 | 2019-08-22 | 2020-01-13 | 2020-01-24 | 2022-05-02 | Underground | R16 | 2020-01-24 | 1 | 103 | 10 | 592 | 703 | 2019 | 2022 | R16
163729163785 | 168961163785 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-03 | 2019-09-03 | 2019-09-09 | 2019-11-11 | 2019-11-21 | Overhead | R16 | 2019-11-11 | 1 | 5 | 46 | 9 | 58 | 2019 | 2019 | R16
166146230051 | 166897230051 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Commercial | 2021-04-09 | 2021-04-09 | 2021-05-10 |  | 2021-10-25 | Underground | R16 |  | 1 | 22 |  |  | 142 | 2021 | 2021 | R16
164389168401 | 164410168401 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-17 | 2019-06-17 | 2019-10-16 | 2019-11-22 | 2019-11-25 | Overhead | R16 | 2019-11-22 | 1 | 88 | 28 | 2 | 116 | 2019 | 2019 | R16
164960175342 | 165019175342 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-05 | 2019-10-05 | 2019-12-30 | 2022-05-20 | 2022-06-07 | Underground | R16 | 2022-05-20 | 0 | 61 | 625 | 13 | 697 | 2019 | 2022 | R16
166173139324 | 165378139324 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-05 | 2019-01-05 | 2019-01-05 |  | 2019-03-14 | Overhead | R16 | 2019-02-25 | 0 |  | 36 | 14 | 49 | 2019 | 2019 | R16
165875159623 | 169175159623 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-10 | 2019-07-30 | 2019-07-31 |  | 2019-10-11 | Overhead | R16 | 2019-09-30 | 15 | 2 | 44 | 10 | 68 | 2019 | 2019 | R16
164119156923 | 166523156923 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2019-06-27 | 2019-06-27 | 2019-07-01 | 2019-09-07 | 2021-07-07 | Underground | R16 | 2019-09-07 | 1 | 3 | 50 | 478 | 530 | 2019 | 2021 | R16
166230138935 | 164744138935 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-03 | 2019-01-03 | 2019-01-03 |  | 2019-03-11 | Overhead | R16 | 2019-02-22 | 1 |  | 37 | 12 | 48 | 2019 | 2019 | R16
160333170682 | 160921170682 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-11-04 | 2019-11-04 | 2019-11-04 |  | 2020-06-09 | Overhead | R16 | 2020-02-14 | 1 |  | 75 | 83 | 157 | 2019 | 2020 | R16
166465159163 | 168031159163 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-03 | 2019-07-25 | 2019-07-26 | 2019-09-25 | 2019-10-09 | Overhead | R16 | 2019-09-25 | 17 | 2 | 44 | 11 | 71 | 2019 | 2019 | R16
163809157390 | 169039157390 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-09 | 2019-07-09 | 2019-07-09 |  | 2022-08-02 | Overhead | R16 |  | 1 |  |  |  | 801 | 2019 | 2022 | R16
162501160976 | 165066160976 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-08-13 | 2019-08-13 | 2019-08-13 | 2019-10-11 | 2019-10-16 | Underground | R16 | 2019-10-11 | 1 |  | 44 | 4 | 47 | 2019 | 2019 | R16
161630171427 | 161118171427 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-11-05 | 2019-11-05 | 2019-11-11 |  | 2019-12-30 | Underground | R16 |  | 1 | 5 |  |  | 40 | 2019 | 2019 | R16
165964174803 | 167813174803 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-08-27 | 2019-11-11 | 2019-12-18 | 2020-04-09 | 2021-07-08 | Underground | R16 | 2020-04-09 | 55 | 28 | 82 | 326 | 488 | 2019 | 2021 | R16
166401140994 | 168339140994 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-22 | 2019-01-22 | 2019-01-23 |  | 2019-04-08 | Underground | R16 | 2019-03-29 | 1 | 2 | 48 | 7 | 55 | 2019 | 2019 | R16
166402172247 | 165339172247 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2019-08-14 | 2019-08-14 | 2019-11-19 |  | 2021-04-16 | Underground | R16 | 2020-12-29 | 1 | 70 | 291 | 79 | 438 | 2019 | 2021 | R16
160449170765 | 163210170765 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-26 | 2019-09-26 | 2019-11-04 |  | 2021-07-19 | Underground | R16 | 2020-11-13 | 1 | 28 | 270 | 177 | 473 | 2019 | 2021 | R16
166443139045 | 164515139045 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-02 | 2019-01-02 | 2019-01-02 |  | 2019-01-28 | Overhead | R16 | 2019-01-22 | 1 |  | 15 | 5 | 19 | 2019 | 2019 | R16
161255169467 | 169151169467 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-24 | 2019-10-24 | 2019-10-24 |  | 2020-06-09 | Overhead | R16 | 2020-01-09 | 1 |  | 56 | 109 | 164 | 2019 | 2020 | R16
164764169899 | 160140169899 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-30 | 2019-10-30 | 2019-10-30 | 2020-02-05 | 2020-02-06 | Overhead | R16 | 2020-02-05 | 1 |  | 71 | 2 | 72 | 2019 | 2020 | R16
166452143979 | 164744143979 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-22 | 2019-02-22 | 2019-02-22 |  | 2022-08-02 | Overhead | R16 |  | 1 |  |  |  | 898 | 2019 | 2022 | R16
164207170296 | 168258170296 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-22 | 2019-10-22 | 2019-10-31 |  | 2022-04-05 | Underground | R16 | 2022-03-15 | 1 | 8 | 619 | 16 | 641 | 2019 | 2022 | R16
165461160499 | 164554160499 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-08-08 | 2019-08-08 | 2019-08-08 | 2019-08-16 | 2019-08-19 | Overhead | R16 | 2019-08-16 | 1 |  | 7 | 2 | 8 | 2019 | 2019 | R16
166481142740 | 164788142740 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-03 | 2019-01-03 | 2019-02-08 |  | 2019-04-15 | Underground | R16 | 2019-03-28 | 1 | 27 | 35 | 13 | 73 | 2019 | 2019 | R16
165408163237 | 167950163237 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-28 | 2019-09-03 | 2019-09-03 |  | 2019-10-14 | Underground | R16 | 2019-10-02 | 5 |  | 22 | 9 | 34 | 2019 | 2019 | R16
165178158884 | 169523158884 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-11 | 2019-07-11 | 2019-07-25 | 2019-08-16 | 2019-08-19 | Underground | R16 | 2019-08-16 | 1 | 11 | 17 | 2 | 28 | 2019 | 2019 | R16
163406161816 | 164963161816 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-12 | 2019-08-12 | 2019-08-21 |  | 2020-07-14 | Underground | R16 | 2020-06-18 | 1 | 8 | 217 | 19 | 242 | 2019 | 2020 | R16
160815167286 | 165144167286 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-10-07 | 2019-10-07 | 2019-10-07 |  | 2020-12-14 | Overhead | R16 | 2020-09-09 | 1 |  | 243 | 69 | 311 | 2019 | 2020 | R16
167753156009 | 165457156009 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-22 | 2019-06-22 | 2019-06-22 |  | 2019-08-26 | Overhead | R16 | 2019-07-17 | 0 |  | 18 | 29 | 46 | 2019 | 2019 | R16
166505141702 | 169399141702 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-28 | 2019-01-28 | 2019-01-28 |  | 2019-04-15 | Overhead | R16 | 2019-02-26 | 1 |  | 22 | 35 | 56 | 2019 | 2019 | R16
162887160525 | 164212160525 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-07 | 2019-08-07 | 2019-08-08 |  | 2023-01-10 | Underground | R16 |  | 1 | 2 |  |  | 895 | 2019 | 2023 | R16
166506142153 | 161410142153 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-05 | 2019-02-05 | 2019-02-05 |  | 2019-04-15 | Overhead | R16 | 2019-03-13 | 1 |  | 27 | 24 | 50 | 2019 | 2019 | R16
162400157552 | 169422157552 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-11 | 2019-07-11 | 2019-07-11 |  | 2019-10-28 | Overhead | R16 | 2019-10-14 | 1 |  | 68 | 11 | 78 | 2019 | 2019 | R16
166538142409 | 161551142409 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-05 | 2019-02-05 | 2019-02-05 |  | 2019-04-01 | Overhead | R16 | 2019-02-28 | 1 |  | 18 | 23 | 40 | 2019 | 2019 | R16
165241161193 | 165581161193 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-08-15 | 2019-08-16 | 2019-08-16 | 2019-09-11 | 2019-09-12 | Underground | R16 | 2019-09-11 | 2 |  | 19 | 2 | 21 | 2019 | 2019 | R16
166550143873 | 164611143873 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-21 | 2019-02-21 | 2019-02-21 |  | 2019-04-15 | Overhead | R16 | 2019-03-28 | 1 |  | 26 | 13 | 38 | 2019 | 2019 | R16
162948170134 | 160314170134 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-30 | 2019-10-30 | 2019-10-30 |  | 2021-11-11 | Overhead | R16 | 2019-11-21 | 1 |  | 17 | 516 | 532 | 2019 | 2021 | R16
166551140434 | 167443140434 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-16 | 2019-01-16 | 2019-01-16 |  | 2019-02-21 | Overhead | R16 | 2019-02-07 | 1 |  | 17 | 11 | 27 | 2019 | 2019 | R16
160273159410 | 161344159410 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-07-22 | 2019-07-22 | 2019-07-29 | 2020-04-10 | 2020-04-20 | Underground | R16 | 2020-04-10 | 1 | 6 | 185 | 7 | 196 | 2019 | 2020 | R16
161983166566 | 160098166566 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-10 | 2019-09-10 | 2019-10-02 | 2021-11-24 | 2021-11-24 | Underground | R16 | 2021-11-24 | 1 | 17 | 561 |  | 577 | 2019 | 2021 | R16
166459170141 | 169978170141 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-29 | 2019-10-29 | 2019-10-29 |  | 2019-12-04 | Underground | R16 | 2019-11-25 | 1 |  | 20 | 8 | 27 | 2019 | 2019 | R16
167261172019 | 163417172019 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-16 | 2019-11-16 | 2019-11-16 | 2020-03-25 | 2020-03-26 | Overhead | R16 | 2020-03-25 | 0 |  | 93 | 2 | 94 | 2019 | 2020 | R16
167547155549 | 163466155549 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-12 | 2019-06-17 | 2019-06-17 |  | 2019-09-03 | Underground | R16 | 2019-08-27 | 4 |  | 52 | 6 | 60 | 2019 | 2019 | R16
168050160892 | 165141160892 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-12 | 2019-08-12 | 2019-08-12 | 2019-11-15 | 2019-11-18 | Overhead | R16 | 2019-11-15 | 1 |  | 70 | 2 | 71 | 2019 | 2019 | R16
166610140941 | 164838140941 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-03 | 2019-01-03 | 2019-01-22 |  | 2019-02-19 | Underground | R16 | 2019-02-06 | 1 | 14 | 12 | 10 | 34 | 2019 | 2019 | R16
166003157006 | 167921157006 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-02 | 2019-07-02 | 2019-07-02 | 2019-07-25 | 2019-07-25 | Overhead | R16 | 2019-07-25 | 1 |  | 18 |  | 18 | 2019 | 2019 | R16
169502180263 | 163302180263 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-26 | 2019-09-26 | 2020-02-12 |  | 2020-07-09 | Underground | R16 | 2020-06-05 | 1 | 100 | 83 | 25 | 206 | 2019 | 2020 | R16
169225172623 | 160950172623 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-04 | 2019-11-21 | 2019-11-21 | 2020-02-06 | 2020-06-09 | Overhead | R16 | 2020-02-06 | 14 |  | 56 | 89 | 157 | 2019 | 2020 | R16
166618154726 | 162674154726 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-07 | 2019-06-07 | 2019-06-07 |  | 2019-09-03 | Overhead | R16 | 2019-07-30 | 1 |  | 38 | 26 | 63 | 2019 | 2019 | R16
169999158953 | 161979158953 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-25 | 2019-07-25 | 2019-07-25 |  | 2019-10-11 | Overhead | R16 | 2019-09-30 | 1 |  | 48 | 10 | 57 | 2019 | 2019 | R16
162843156902 | 167492156902 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-01 | 2019-07-01 | 2019-07-01 |  | 2021-11-18 | Overhead | R16 | 2019-09-18 | 1 |  | 58 | 567 | 624 | 2019 | 2021 | R16
167236171093 | 167788171093 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-18 | 2019-10-18 | 2019-11-08 |  | 2020-06-09 | Underground | R16 | 2020-03-03 | 1 | 16 | 83 | 71 | 168 | 2019 | 2020 | R16
166636140945 | 168211140945 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-22 | 2019-01-22 | 2019-01-22 |  | 2019-02-21 | Overhead | R16 | 2019-02-11 | 1 |  | 15 | 9 | 23 | 2019 | 2019 | R16
166646141784 | 164720141784 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-02 | 2019-01-02 | 2019-01-30 |  | 2019-04-15 | Underground | R16 |  | 1 | 21 |  |  | 74 | 2019 | 2019 | R16
166666182799 | 167816182799 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-11 | 2019-12-11 | 2020-03-04 |  | 2020-08-20 | Underground | R16 | 2020-06-24 | 1 | 61 | 81 | 42 | 182 | 2019 | 2020 | R16
167213176697 | 169691176697 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-06 | 2020-01-13 | 2020-01-13 |  | 2020-11-11 | Overhead | R16 | 2020-09-15 | 92 |  | 177 | 42 | 309 | 2019 | 2020 | R16
166685143588 | 164184143588 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-20 | 2019-02-20 | 2019-02-20 |  | 2019-04-22 | Underground | R16 | 2019-03-19 | 1 |  | 20 | 25 | 44 | 2019 | 2019 | R16
163741158931 | 167613158931 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-01 | 2019-07-02 | 2019-07-25 | 2019-08-14 | 2019-08-15 | Underground | R16 | 2019-08-14 | 2 | 18 | 15 | 2 | 34 | 2019 | 2019 | R16
160813166092 | 163267166092 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-27 | 2019-09-27 | 2019-09-27 |  | 2019-11-14 | Overhead | R16 | 2019-11-05 | 1 |  | 28 | 8 | 35 | 2019 | 2019 | R16
169094170787 | 165470170787 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-14 | 2019-10-11 | 2019-11-06 | 2020-10-14 | 2021-02-20 | Underground | R16 | 2020-10-14 | 43 | 19 | 246 | 93 | 398 | 2019 | 2021 | R16
166754158914 | 165363158914 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-06-20 | 2019-07-25 | 2019-07-25 |  | 2019-12-06 | Overhead | R16 | 2019-08-14 | 26 |  | 15 | 83 | 122 | 2019 | 2019 | R16
168361169537 | 169079169537 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-24 | 2019-10-24 | 2019-10-24 |  | 2022-10-17 | Overhead | R16 |  | 1 |  |  |  | 778 | 2019 | 2022 | R16
167727169367 | 168791169367 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-23 | 2019-10-23 | 2019-10-23 |  | 2021-11-10 | Overhead | R16 | 2020-01-21 | 1 |  | 65 | 472 | 536 | 2019 | 2021 | R16
166292174807 | 166515174807 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-06 | 2019-12-06 | 2019-12-18 | 2020-02-19 | 2020-02-19 | Underground | R16 | 2020-02-19 | 1 | 9 | 46 |  | 54 | 2019 | 2020 | R16
168633160456 | 164160160456 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2019-08-06 | 2019-08-06 | 2019-08-07 |  | 2021-04-14 | Overhead | R16 | 2020-12-11 | 1 | 2 | 353 | 89 | 442 | 2019 | 2021 | R16
167977261082 | 167978261082 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH R16 SVC RELOCATION OD | Commercial | 2019-10-21 | 2019-10-21 | 2021-12-13 | 2022-01-03 | 2022-01-19 | Overhead | R16 | 2022-01-03 | 1 | 561 | 16 | 13 | 588 | 2019 | 2022 | R16
160844171889 | 163252171889 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-14 | 2019-11-14 | 2019-11-14 | 2020-02-24 | 2022-05-17 | Overhead | R16 | 2020-02-24 | 1 |  | 73 | 582 | 654 | 2019 | 2022 | R16
166804149574 | 163845149574 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-04-17 | 2019-04-17 | 2019-04-17 |  | 2019-05-28 | Overhead | R16 |  | 1 |  |  |  | 30 | 2019 | 2019 | R16
168077158983 | 169632158983 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-12 | 2019-07-12 | 2019-07-24 |  | 2019-10-28 | Underground | R16 | 2019-10-18 | 1 | 9 | 63 | 7 | 77 | 2019 | 2019 | R16
167363170875 | 160535170875 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-31 | 2019-10-31 | 2019-11-06 |  | 2020-06-09 | Underground | R16 | 2020-05-15 | 1 | 5 | 138 | 18 | 159 | 2019 | 2020 | R16
166804170225 | 169029170225 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 ELEC DEVELOPMENT | Residential | 2019-05-14 | 2019-05-14 | 2019-10-30 |  | 2021-11-12 | Underground | R16 |  | 1 | 122 |  |  | 654 | 2019 | 2021 | R16
169050157550 | 169347157550 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-07-10 | 2019-07-10 | 2019-07-11 |  | 2021-12-16 | Overhead | R16 | 2019-07-15 | 1 | 2 | 3 | 634 | 637 | 2019 | 2021 | R16
166853164004 | 166832164004 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-05-02 | 2019-05-02 | 2019-09-10 |  | 2020-09-16 | Underground | R16 |  | 1 | 94 |  |  | 360 | 2019 | 2020 | R16
167422157231 | 163547157231 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-12 | 2019-06-17 | 2019-07-08 |  | 2020-12-18 | Underground | R16 | 2020-09-17 | 4 | 16 | 314 | 67 | 398 | 2019 | 2020 | R16
160824172521 | 164258172521 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-20 | 2019-11-20 | 2019-11-20 |  | 2021-11-01 | Overhead | R16 | 2020-01-21 | 1 |  | 45 | 465 | 509 | 2019 | 2021 | R16
166884153585 | 169893153585 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-05-20 | 2019-05-20 | 2019-05-29 |  | 2021-12-08 | Underground | R16 |  | 1 | 8 |  |  | 668 | 2019 | 2021 | R16
162634164945 | 161733164945 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-18 | 2019-09-18 | 2019-09-18 |  | 2020-11-02 | Overhead | R16 | 2020-09-02 | 1 |  | 251 | 44 | 294 | 2019 | 2020 | R16
166891142314 | 169297142314 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-28 | 2019-02-05 | 2019-02-05 |  | 2019-04-25 | Overhead | R16 | 2019-04-01 | 7 |  | 40 | 19 | 64 | 2019 | 2019 | R16
165366173134 | 165544173134 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-06-21 | 2019-09-19 | 2019-12-02 | 2020-07-07 | 2020-10-21 | Underground | R16 | 2020-07-07 | 65 | 53 | 157 | 77 | 349 | 2019 | 2020 | R16
166907139808 | 166653139808 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-10 | 2019-01-10 | 2019-01-10 |  | 2019-02-21 | Overhead | R16 | 2019-02-12 | 1 |  | 24 | 8 | 31 | 2019 | 2019 | R16
168326229749 | 167799229749 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-07-02 | 2019-07-02 | 2021-05-06 | 2021-07-29 | 2021-07-30 | Underground | R16 | 2021-07-29 | 1 | 483 | 61 | 2 | 544 | 2019 | 2021 | R16
166466156897 | 168013156897 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-03 | 2019-07-03 | 2019-07-03 |  | 2019-08-26 | Overhead | R16 | 2019-07-23 | 1 |  | 15 | 25 | 39 | 2019 | 2019 | R16
161059184414 | 162627184414 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2019-09-24 | 2020-01-28 | 2020-03-17 | 2020-05-08 | 2022-08-25 | Overhead | R16 | 2020-05-08 | 91 | 36 | 39 | 600 | 763 | 2019 | 2022 | R16
165585213201 | 165586213201 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-08-15 | 2020-09-29 | 2020-12-08 | 2021-09-10 | 2023-05-02 | Underground | R16 | 2021-09-10 | 294 | 51 | 199 | 428 | 969 | 2019 | 2023 | R16
163138161745 | 166239161745 | RESIDENTIAL - MOBILE HOME | R16 RESD AND NON RESD US | Residential | 2019-08-20 | 2019-08-20 | 2019-08-20 |  | 2023-06-07 | Underground | R16 | 2019-11-13 | 1 |  | 62 | 931 | 992 | 2019 | 2023 | R16
169326168642 | 163286168642 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-26 | 2019-09-26 | 2019-10-17 |  | 2020-06-09 | Underground | R16 | 2020-04-02 | 1 | 16 | 121 | 49 | 184 | 2019 | 2020 | R16
168047166033 | 168219166033 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-29 | 2019-08-29 | 2019-09-28 | 2019-10-28 | 2019-10-28 | Underground | R16 | 2019-10-28 | 1 | 22 | 21 |  | 43 | 2019 | 2019 | R16
161701207361 | 167689207361 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-03 | 2019-07-03 | 2020-10-14 |  | 2021-04-14 | Overhead | R16 |  | 1 | 336 |  |  | 466 | 2019 | 2021 | R16
165071163846 | 169896163846 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-09 | 2019-09-09 | 2019-09-09 | 2019-10-28 | 2019-10-28 | Overhead | R16 | 2019-10-28 | 1 |  | 36 |  | 36 | 2019 | 2019 | R16
167031142431 | 161801142431 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-06 | 2019-02-06 | 2019-02-06 |  | 2019-04-15 | Underground | R16 | 2019-03-14 | 1 |  | 27 | 23 | 49 | 2019 | 2019 | R16
161052173279 | 162569173279 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-24 | 2019-09-24 | 2019-12-03 | 2020-02-05 | 2020-02-07 | Underground | R16 | 2020-02-05 | 1 | 51 | 47 | 3 | 99 | 2019 | 2020 | R16
167033142415 | 161506142415 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-05 | 2019-02-05 | 2019-02-05 |  | 2019-04-15 | Overhead | R16 | 2019-03-07 | 1 |  | 23 | 28 | 50 | 2019 | 2019 | R16
167036141544 | 169277141544 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-28 | 2019-01-28 | 2019-01-28 |  | 2023-06-07 | Overhead | R16 |  | 1 |  |  |  | 1138 | 2019 | 2023 | R16
162532160876 | 169283160876 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-07-10 | 2019-07-30 | 2019-08-13 |  | 2019-10-09 | Underground | R16 |  | 15 | 11 |  |  | 66 | 2019 | 2019 | R16
161505171147 | 161531171147 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-09-17 | 2019-09-17 | 2019-11-08 | 2019-11-29 | 2019-12-16 | Overhead | R16 | 2019-11-29 | 1 | 39 | 16 | 12 | 65 | 2019 | 2019 | R16
163366159564 | 167622159564 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-01 | 2019-07-02 | 2019-07-30 | 2019-08-31 | 2019-09-03 | Underground | R16 | 2019-08-31 | 2 | 21 | 24 | 2 | 47 | 2019 | 2019 | R16
161630171766 | 162033171766 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-11-07 | 2019-11-08 | 2019-11-13 |  | 2019-11-27 | Underground | R16 |  | 2 | 4 |  |  | 15 | 2019 | 2019 | R16
165863162765 | 168317162765 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-29 | 2019-08-29 | 2019-08-29 | 2021-03-22 | 2021-03-25 | Underground | R16 | 2021-03-22 | 1 |  | 408 | 4 | 411 | 2019 | 2021 | R16
167108142525 | 161819142525 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-06 | 2019-02-06 | 2019-02-06 |  | 2019-04-15 | Overhead | R16 | 2019-03-13 | 1 |  | 26 | 24 | 49 | 2019 | 2019 | R16
161741155562 | 163862155562 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-13 | 2019-06-17 | 2019-06-17 |  | 2019-10-10 | Overhead | R16 | 2019-09-27 | 3 |  | 75 | 10 | 86 | 2019 | 2019 | R16
160266171094 | 162080171094 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-08 | 2019-11-08 | 2019-11-08 | 2020-02-18 | 2020-02-20 | Overhead | R16 | 2020-02-18 | 1 |  | 73 | 3 | 75 | 2019 | 2020 | R16
167155143244 | 163423143244 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-13 | 2019-02-13 | 2019-02-14 |  | 2019-08-12 | Overhead | R16 | 2019-05-29 | 1 | 2 | 75 | 54 | 129 | 2019 | 2019 | R16
161241157233 | 167910157233 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-02 | 2019-07-02 | 2019-07-08 | 2019-11-13 | 2019-11-21 | Overhead | R16 | 2019-11-13 | 1 | 5 | 93 | 7 | 103 | 2019 | 2019 | R16
160954161735 | 160876161735 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-19 | 2019-07-19 | 2019-08-21 | 2019-11-05 | 2019-11-06 | Underground | R16 | 2019-11-05 | 1 | 24 | 55 | 2 | 79 | 2019 | 2019 | R16
167184142528 | 161851142528 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-06 | 2019-02-06 | 2019-02-06 |  | 2019-04-15 | Overhead | R16 | 2019-03-13 | 1 |  | 26 | 24 | 49 | 2019 | 2019 | R16
163451173861 | 166745173861 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-07 | 2019-12-07 | 2019-12-07 | 2020-01-24 | 2020-01-27 | Overhead | R16 | 2020-01-24 | 0 |  | 35 | 2 | 36 | 2019 | 2020 | R16
164120158404 | 160888158404 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-07-18 | 2019-07-18 | 2019-07-18 | 2019-08-05 | 2019-08-05 | Underground | R16 | 2019-08-05 | 1 |  | 13 |  | 13 | 2019 | 2019 | R16
160669155565 | 164460155565 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-17 | 2019-06-17 | 2019-06-17 |  | 2019-08-26 | Underground | R16 | 2019-07-10 | 1 |  | 18 | 34 | 51 | 2019 | 2019 | R16
167232141597 | 169298141597 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-28 | 2019-01-28 | 2019-01-28 |  | 2019-03-11 | Overhead | R16 | 2019-02-19 | 1 |  | 17 | 15 | 31 | 2019 | 2019 | R16
160344161095 | 165235161095 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-13 | 2019-08-13 | 2019-08-13 |  | 2019-10-28 | Underground | R16 | 2019-10-17 | 1 |  | 48 | 8 | 55 | 2019 | 2019 | R16
160529161005 | 167508161005 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-02 | 2019-07-02 | 2019-08-13 |  | 2019-10-17 | Underground | R16 | 2019-10-09 | 1 | 31 | 42 | 7 | 78 | 2019 | 2019 | R16
162326165146 | 169490165146 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-05 | 2019-09-05 | 2019-09-19 | 2020-04-06 | 2020-04-07 | Underground | R16 | 2020-04-06 | 1 | 11 | 143 | 2 | 154 | 2019 | 2020 | R16
160275188870 | 162914188870 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-09-25 | 2019-09-25 | 2020-04-23 |  | 2021-11-11 | Underground | R16 |  | 1 | 152 |  |  | 557 | 2019 | 2021 | R16
167298140428 | 167338140428 | GENERAL/OTHER | R16 RESD AND NON RESD US | Commercial | 2019-01-15 | 2019-01-15 | 2019-01-15 |  | 2019-08-12 | Underground | R16 | 2019-05-29 | 1 |  | 97 | 54 | 150 | 2019 | 2019 | R16
166099171206 | 166068171206 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-09 | 2019-10-09 | 2019-11-09 |  | 2020-08-14 | Underground | R16 | 2020-06-22 | 1 | 23 | 161 | 40 | 223 | 2019 | 2020 | R16
162552322232 | 163391322232 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-05 | 2023-06-14 | 2023-06-14 | 2023-10-03 | 2023-10-24 | Overhead | R16 | 2023-10-03 | 8 |  | 80 | 16 | 102 | 2023 | 2023 | R16
167321142489 | 166646142489 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-10 | 2019-02-06 | 2019-02-06 |  | 2019-05-20 | Overhead | R16 | 2019-04-09 | 20 |  | 45 | 30 | 93 | 2019 | 2019 | R16
163088175062 | 165091175062 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-07 | 2019-10-07 | 2019-12-20 |  | 2020-06-09 | Underground | R16 | 2020-01-28 | 1 | 55 | 28 | 96 | 177 | 2019 | 2020 | R16
164188159130 | 162269159130 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-26 | 2019-07-26 | 2019-07-26 |  | 2019-12-06 | Overhead | R16 | 2019-08-13 | 1 |  | 13 | 84 | 96 | 2019 | 2019 | R16
164989160567 | 164490160567 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-08 | 2019-08-08 | 2019-08-08 |  | 2019-09-24 | Overhead | R16 | 2019-09-16 | 1 |  | 28 | 7 | 34 | 2019 | 2019 | R16
167488139449 | 165665139449 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-07 | 2019-01-07 | 2019-01-07 |  | 2019-04-01 | Underground | R16 | 2019-02-26 | 1 |  | 37 | 25 | 61 | 2019 | 2019 | R16
169815155366 | 164163155366 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-15 | 2019-06-15 | 2019-06-15 | 2019-08-04 | 2019-12-06 | Overhead | R16 | 2019-08-04 | 0 |  | 35 | 90 | 125 | 2019 | 2019 | R16
161970213221 | 161885213221 | NON-RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Commercial | 2019-07-25 | 2019-07-25 | 2020-12-08 | 2021-07-27 | 2022-01-07 | Underground | R16 | 2021-07-27 | 1 | 359 | 166 | 119 | 642 | 2019 | 2022 | R16
168906158291 | 160668158291 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-18 | 2019-07-18 | 2019-07-18 | 2019-08-09 | 2019-08-29 | Overhead | R16 | 2019-08-09 | 1 |  | 17 | 15 | 31 | 2019 | 2019 | R16
167303169648 | 169149169648 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-25 | 2019-10-25 | 2019-10-25 |  | 2021-11-13 | Overhead | R16 | 2020-01-06 | 1 |  | 52 | 485 | 536 | 2019 | 2021 | R16
164440155636 | 165298155636 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-20 | 2019-06-20 | 2019-06-20 |  | 2020-06-09 | Overhead | R16 | 2019-12-17 | 1 |  | 129 | 126 | 254 | 2019 | 2020 | R16
167545139805 | 166611139805 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-10 | 2019-01-10 | 2019-01-10 |  | 2019-04-15 | Overhead | R16 | 2019-03-07 | 1 |  | 41 | 28 | 68 | 2019 | 2019 | R16
167737142417 | 161610142417 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-05 | 2019-02-05 | 2019-02-05 |  | 2019-08-12 | Overhead | R16 | 2019-06-13 | 1 |  | 93 | 43 | 135 | 2019 | 2019 | R16
167105338679 | 163994338679 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-12-13 | 2023-12-15 | Overhead | R16 | 2023-12-13 | 1 |  | 28 | 3 | 30 | 2023 | 2023 | R16
163942339108 | 164586339108 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-11-08 | 2023-11-08 | 2023-11-08 | 2023-12-19 | 2023-12-29 | Overhead | R16 | 2023-12-19 | 1 |  | 30 | 9 | 38 | 2023 | 2023 | R16
167756141140 | 168509141140 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-23 | 2019-01-23 | 2019-01-23 |  | 2019-05-20 | Underground | R16 | 2019-04-11 | 1 |  | 57 | 28 | 84 | 2019 | 2019 | R16
162698340576 | 166840340576 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-11-22 | 2023-11-22 | 2023-11-22 | 2023-12-07 | 2023-12-20 | Overhead | R16 | 2023-12-07 | 1 |  | 12 | 10 | 21 | 2023 | 2023 | R16
167790141107 | 168928141107 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-24 | 2019-01-24 | 2019-01-24 |  | 2019-04-22 | Overhead | R16 | 2019-03-15 | 1 |  | 37 | 27 | 63 | 2019 | 2019 | R16
164018339766 | 165170339766 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-11-11 | 2023-11-15 | 2023-11-15 | 2023-11-27 | 2023-12-07 | Overhead | R16 | 2023-11-27 | 3 |  | 9 | 9 | 19 | 2023 | 2023 | R16
167845139653 | 166456139653 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-09 | 2019-01-09 | 2019-01-09 |  | 2019-02-21 | Overhead | R16 | 2019-02-12 | 1 |  | 25 | 8 | 32 | 2019 | 2019 | R16
165657342303 | 169156342303 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-12-08 | 2023-12-11 | 2023-12-11 | 2023-12-15 | 2023-12-28 | Overhead | R16 | 2023-12-15 | 2 |  | 5 | 10 | 15 | 2023 | 2023 | R16
167859141115 | 166061141115 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-08 | 2019-01-25 | 2019-01-25 |  | 2019-04-15 | Overhead | R16 | 2019-03-13 | 14 |  | 34 | 24 | 70 | 2019 | 2019 | R16
167871142375 | 161902142375 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-07 | 2019-02-07 | 2019-02-07 |  | 2019-04-22 | Overhead | R16 | 2019-03-15 | 1 |  | 27 | 27 | 53 | 2019 | 2019 | R16
167969144490 | 165335144490 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-27 | 2019-02-27 | 2019-02-28 |  | 2023-06-09 | Overhead | R16 |  | 1 | 2 |  |  | 1118 | 2019 | 2023 | R16
167979140527 | 167730140527 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-16 | 2019-01-16 | 2019-01-16 |  | 2019-02-21 | Overhead | R16 | 2019-02-07 | 1 |  | 17 | 11 | 27 | 2019 | 2019 | R16
164044338782 | 164033338782 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-30 | Overhead | R16 | 2023-11-06 | 1 |  |  | 19 | 19 | 2023 | 2023 | R16
168042141558 | 160219141558 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-30 | 2019-01-30 | 2019-01-30 |  | 2019-03-08 | Overhead | R16 | 2019-02-18 | 1 |  | 14 | 15 | 28 | 2019 | 2019 | R16
163989339414 | 165124339414 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-11-11 | 2023-11-11 | 2023-11-11 | 2023-12-11 | 2023-12-14 | Overhead | R16 | 2023-12-11 | 0 |  | 21 | 4 | 24 | 2023 | 2023 | R16
168115147258 | 160070147258 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-26 | 2019-03-26 | 2019-03-26 |  | 2019-06-03 | Overhead | R16 | 2019-05-13 | 1 |  | 35 | 16 | 50 | 2019 | 2019 | R16
168685339892 | 165303339892 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-11-13 | 2023-11-16 | 2023-11-16 |  | 2023-12-18 | Overhead | R16 | 2023-12-11 | 4 |  | 18 | 6 | 26 | 2023 | 2023 | R16
168163144135 | 165242144135 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-02-26 | 2019-02-26 | 2019-02-26 |  | 2019-04-26 | Underground | R16 | 2019-04-03 | 1 |  | 27 | 18 | 44 | 2019 | 2019 | R16
165986341996 | 169272341996 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-12-08 | 2023-12-08 | 2023-12-08 | 2023-12-20 | 2023-12-28 | Overhead | R16 | 2023-12-20 | 1 |  | 9 | 7 | 15 | 2023 | 2023 | R16
168166150640 | 165890150640 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-04-28 | 2019-04-28 | 2019-04-28 |  | 2019-09-03 | Underground | R16 | 2019-07-31 | 0 |  | 68 | 25 | 92 | 2019 | 2019 | R16
167500342471 | 169457342471 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-12-12 | 2023-12-13 | 2023-12-13 | 2023-12-19 | 2023-12-19 | Overhead | R16 | 2023-12-19 | 2 |  | 5 |  | 6 | 2023 | 2023 | R16
168167152592 | 168498152592 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-01-23 | 2019-05-02 | 2019-05-16 |  | 2019-10-08 | Underground | R16 | 2019-09-24 | 72 | 11 | 94 | 11 | 185 | 2019 | 2019 | R16
162857339706 | 165460339706 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-11-14 | 2023-11-14 | 2023-11-14 | 2023-12-08 | 2023-12-20 | Overhead | R16 | 2023-12-08 | 1 |  | 19 | 9 | 27 | 2023 | 2023 | R16
164669341111 | 167649341111 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-11-29 | 2023-11-30 | 2023-11-30 | 2023-12-04 | 2023-12-14 | Overhead | R16 | 2023-12-04 | 2 |  | 3 | 9 | 12 | 2023 | 2023 | R16
168250150620 | 165871150620 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-04-28 | 2019-04-28 | 2019-04-28 |  | 2019-08-12 | Underground | R16 | 2019-05-29 | 0 |  | 23 | 54 | 76 | 2019 | 2019 | R16
165831338686 | 163998338686 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-12-18 | 2023-12-21 | Overhead | R16 | 2023-12-18 | 1 |  | 31 | 4 | 34 | 2023 | 2023 | R16
162019341162 | 165482341162 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-11-14 | 2023-11-30 | 2023-11-30 | 2023-12-08 | 2023-12-19 | Overhead | R16 | 2023-12-08 | 13 |  | 7 | 8 | 26 | 2023 | 2023 | R16
168289140292 | 166181140292 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-09 | 2019-01-14 | 2019-01-14 |  | 2019-04-15 | Underground | R16 | 2019-03-08 | 4 |  | 40 | 27 | 69 | 2019 | 2019 | R16
168306138985 | 164663138985 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-02 | 2019-01-02 | 2019-01-02 |  | 2019-01-25 | Overhead | R16 | 2019-01-16 | 1 |  | 11 | 8 | 18 | 2019 | 2019 | R16
168718153915 | 161697153915 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-31 | 2019-05-31 | 2019-05-31 | 2019-06-24 | 2019-09-03 | Overhead | R16 | 2019-06-24 | 1 |  | 17 | 52 | 68 | 2019 | 2019 | R16
166066147899 | 161492147899 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-03 | 2019-04-03 | 2019-04-03 |  | 2019-08-12 | Overhead | R16 | 2019-06-18 | 1 |  | 55 | 40 | 94 | 2019 | 2019 | R16
168316141672 | 167835141672 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-01-17 | 2019-01-17 | 2019-01-30 |  | 2019-04-15 | Underground | R16 | 2019-03-14 | 1 | 10 | 32 | 23 | 63 | 2019 | 2019 | R16
162676155780 | 161530155780 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-02-05 | 2019-02-05 | 2019-06-19 | 2020-05-05 | 2020-07-29 | Underground | R16 | 2020-05-05 | 1 | 97 | 230 | 62 | 387 | 2019 | 2020 | R16
162096145464 | 167402145464 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-09 | 2019-03-09 | 2019-03-09 |  | 2019-06-03 | Overhead | R16 | 2019-05-14 | 0 |  | 47 | 15 | 61 | 2019 | 2019 | R16
161353216389 | 166491216389 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-22 | 2021-01-07 | 2021-01-07 | 2021-06-18 | 2021-11-04 | Overhead | R16 | 2021-06-18 | 34 |  | 117 | 100 | 249 | 2020 | 2021 | R16
168046150161 | 162153150161 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-08 | 2019-04-23 | 2019-04-23 | 2019-04-26 | 2019-05-23 | Overhead | R16 | 2019-04-26 | 12 |  | 4 | 20 | 34 | 2019 | 2019 | R16
168361139217 | 165377139217 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-05 | 2019-01-05 | 2019-01-05 |  | 2019-06-03 | Underground | R16 | 2019-05-08 | 0 |  | 88 | 19 | 106 | 2019 | 2019 | R16
169119212536 | 166442212536 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-23 | 2020-12-03 | 2020-12-03 | 2021-02-22 | 2021-11-03 | Underground | R16 | 2021-02-22 | 9 |  | 58 | 183 | 248 | 2020 | 2021 | R16
161815149351 | 163742149351 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-16 | 2019-04-16 | 2019-04-16 |  | 2019-08-26 | Overhead | R16 | 2019-06-24 | 1 |  | 50 | 46 | 95 | 2019 | 2019 | R16
168366143021 | 162711143021 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-11 | 2019-02-11 | 2019-02-11 |  | 2019-04-25 | Underground | R16 | 2019-03-22 | 1 |  | 30 | 25 | 54 | 2019 | 2019 | R16
168367143287 | 163671143287 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-14 | 2019-02-14 | 2019-02-14 |  | 2019-04-22 | Overhead | R16 | 2019-03-18 | 1 |  | 23 | 26 | 48 | 2019 | 2019 | R16
168409146221 | 163241146221 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-13 | 2019-02-13 | 2019-03-15 |  | 2019-08-12 | Underground | R16 | 2019-05-28 | 1 | 23 | 53 | 55 | 129 | 2019 | 2019 | R16
162798146546 | 168876146546 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-19 | 2019-03-19 | 2019-03-19 |  | 2019-08-12 | Overhead | R16 | 2019-06-04 | 1 |  | 56 | 50 | 105 | 2019 | 2019 | R16
161594203062 | 169126203062 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-21 | 2020-07-21 | 2020-09-08 |  | 2021-08-12 | Underground | R16 | 2021-03-16 | 1 | 36 | 136 | 108 | 278 | 2020 | 2021 | R16
169420219070 | 165348219070 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-06 | 2021-01-14 | 2021-02-01 | 2023-01-11 | 2022-09-25 | Underground | R16 | 2023-01-11 | 7 | 13 | 508 |  | 448 | 2021 | 2022 | R16
168498151221 | 168201151221 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-03-14 | 2019-03-14 | 2019-05-03 |  | 2021-04-07 | Underground | R16 |  | 1 | 37 |  |  | 540 | 2019 | 2021 | R16
168118238264 | 165953238264 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-23 | 2021-02-23 | 2021-07-09 | 2022-05-09 | 2022-06-03 | Underground | R16 | 2022-05-09 | 1 | 99 | 217 | 20 | 334 | 2021 | 2022 | R16
168963144491 | 165548144491 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-28 | 2019-02-28 | 2019-02-28 |  | 2019-04-22 | Underground | R16 | 2019-03-18 | 1 |  | 13 | 26 | 38 | 2019 | 2019 | R16
168807227173 | 166755227173 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-04-08 | 2021-04-14 | 2021-04-16 | 2022-01-30 | 2022-02-02 | Underground | R16 | 2022-01-30 | 5 | 3 | 206 | 3 | 215 | 2021 | 2022 | R16
162519239306 | 166452239306 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-07 | 2021-04-07 | 2021-07-16 |  | 2021-10-25 | Underground | R16 | 2021-08-26 | 1 | 73 | 30 | 43 | 144 | 2021 | 2021 | R16
169293149192 | 163593149192 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-15 | 2019-04-15 | 2019-04-15 | 2019-08-22 | 2019-08-28 | Overhead | R16 | 2019-08-22 | 1 |  | 94 | 5 | 98 | 2019 | 2019 | R16
165852145255 | 165766145255 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-01 | 2019-03-06 | 2019-03-08 |  | 2019-04-25 | Overhead | R16 | 2019-04-02 | 4 | 3 | 18 | 18 | 40 | 2019 | 2019 | R16
160284149647 | 162498149647 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-09 | 2019-04-09 | 2019-04-19 |  | 2019-08-26 | Underground | R16 | 2019-07-10 | 1 | 9 | 59 | 34 | 100 | 2019 | 2019 | R16
161763213282 | 169764213282 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-22 | 2020-12-09 | 2020-12-09 | 2021-03-23 | 2021-08-09 | Overhead | R16 | 2021-03-23 | 35 |  | 75 | 100 | 208 | 2020 | 2021 | R16
168827200885 | 161974200885 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2020-08-04 | 2020-08-05 | 2020-08-18 |  | 2021-11-04 | Underground | R16 |  | 2 | 10 |  |  | 328 | 2020 | 2021 | R16
162641140893 | 168680140893 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-23 | 2019-01-23 | 2019-01-23 |  | 2019-10-16 | Overhead | R16 | 2019-10-11 | 1 |  | 188 | 4 | 191 | 2019 | 2019 | R16
168094205913 | 165287205913 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-01 | 2020-10-01 | 2020-10-01 | 2021-05-11 | 2021-11-04 | Overhead | R16 | 2021-05-11 | 1 |  | 159 | 128 | 286 | 2020 | 2021 | R16
168943149594 | 161570149594 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-02-05 | 2019-03-20 | 2019-04-19 |  | 2019-10-11 | Underground | R16 |  | 32 | 23 |  |  | 179 | 2019 | 2019 | R16
169001179568 | 168422179568 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2020-02-06 | 2020-02-06 | 2020-02-07 |  | 2020-06-24 | Underground | R16 |  | 1 | 2 |  |  | 100 | 2020 | 2020 | R16
164321222372 | 168072222372 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-03-03 | 2021-03-03 | 2021-03-03 | 2021-10-20 | 2021-11-18 | Overhead | R16 | 2021-10-20 | 1 |  | 166 | 22 | 187 | 2021 | 2021 | R16
162733223854 | 161005223854 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-03-16 | 2021-03-16 | 2021-03-16 |  | 2021-11-09 | Underground | R16 | 2021-04-27 | 1 |  | 31 | 141 | 171 | 2021 | 2021 | R16
169005143632 | 163979143632 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-20 | 2019-02-20 | 2019-02-20 |  | 2019-04-15 | Overhead | R16 | 2019-03-07 | 1 |  | 12 | 28 | 39 | 2019 | 2019 | R16
169007145994 | 168164145994 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-14 | 2019-03-14 | 2019-03-14 |  | 2022-08-02 | Overhead | R16 |  | 1 |  |  |  | 884 | 2019 | 2022 | R16
163601200527 | 163677200527 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-08-14 | 2020-08-14 | 2020-08-14 |  | 2021-04-16 | Overhead | R16 | 2020-12-30 | 1 |  | 99 | 78 | 176 | 2020 | 2021 | R16
169059143289 | 163634143289 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-14 | 2019-02-14 | 2019-02-14 |  | 2019-04-01 | Overhead | R16 | 2019-02-26 | 1 |  | 9 | 25 | 33 | 2019 | 2019 | R16
164348150105 | 165180150105 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-24 | 2019-04-24 | 2019-04-24 | 2019-08-28 | 2019-08-29 | Overhead | R16 | 2019-08-28 | 1 |  | 91 | 2 | 92 | 2019 | 2019 | R16
169119139849 | 164653139849 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-02 | 2019-01-03 | 2019-01-10 |  | 2019-11-14 | Underground | R16 | 2019-10-30 | 2 | 6 | 210 | 12 | 227 | 2019 | 2019 | R16
163474160910 | 168035160910 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-09 | 2019-05-09 | 2019-08-12 |  | 2020-06-09 | Underground | R16 | 2020-01-17 | 1 | 68 | 115 | 103 | 284 | 2019 | 2020 | R16
160967213062 | 169036213062 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-07 | 2020-12-07 | 2020-12-07 |  | 2021-11-09 | Overhead | R16 | 2020-12-23 | 1 |  | 13 | 230 | 242 | 2020 | 2021 | R16
169139158873 | 165476158873 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-06-20 | 2019-06-22 | 2019-07-25 |  | 2021-07-07 | Underground | R16 |  | 2 | 24 |  |  | 535 | 2019 | 2021 | R16
162462237833 | 166136237833 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-07 | 2021-04-07 | 2021-07-06 | 2021-11-13 | 2021-11-16 | Underground | R16 | 2021-11-13 | 1 | 65 | 94 | 2 | 160 | 2021 | 2021 | R16
161175155821 | 160367155821 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-05-22 | 2019-05-31 | 2019-06-19 |  | 2019-12-06 | Overhead | R16 | 2019-08-08 | 8 | 14 | 37 | 87 | 143 | 2019 | 2019 | R16
165731225555 | 160649225555 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-15 | 2021-04-01 | 2021-04-01 | 2021-06-04 | 2021-08-31 | Overhead | R16 | 2021-06-04 | 14 |  | 47 | 63 | 122 | 2021 | 2021 | R16
169230140264 | 167149140264 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-14 | 2019-01-14 | 2019-01-14 |  | 2019-05-20 | Underground | R16 | 2019-04-09 | 1 |  | 62 | 30 | 91 | 2019 | 2019 | R16
169236141711 | 169438141711 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-29 | 2019-01-29 | 2019-01-29 |  | 2019-04-01 | Overhead | R16 | 2019-02-28 | 1 |  | 23 | 23 | 45 | 2019 | 2019 | R16
164331215613 | 163589215613 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-29 | 2020-12-29 | 2020-12-29 | 2021-01-07 | 2021-12-17 | Underground | R16 | 2021-01-07 | 1 |  | 8 | 247 | 254 | 2020 | 2021 | R16
168399203803 | 164410203803 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-08-18 | 2020-08-18 | 2020-09-14 | 2021-07-08 | 2021-07-09 | Underground | R16 | 2021-07-08 | 1 | 20 | 214 | 2 | 234 | 2020 | 2021 | R16
160358204375 | 161114204375 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-15 | 2020-09-19 | 2020-09-19 | 2020-11-13 | 2021-02-26 | Overhead | R16 | 2020-11-13 | 4 |  | 40 | 76 | 119 | 2020 | 2021 | R16
161288207110 | 165261207110 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-01 | 2020-10-01 | 2020-10-13 |  | 2021-07-24 | Underground | R16 | 2020-10-28 | 1 | 9 | 12 | 193 | 212 | 2020 | 2021 | R16
166502215961 | 163945215961 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-30 | 2020-12-30 | 2020-12-30 |  | 2021-09-02 | Overhead | R16 | 2021-08-10 | 1 |  | 160 | 18 | 177 | 2020 | 2021 | R16
169617222509 | 168287222509 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-04 | 2021-03-04 | 2021-03-04 |  | 2021-11-05 | Underground | R16 | 2021-04-14 | 1 |  | 30 | 148 | 177 | 2021 | 2021 | R16
168200198921 | 160643198921 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-28 | 2020-07-28 | 2020-07-28 | 2020-09-28 | 2021-01-22 | Overhead | R16 | 2020-09-28 | 1 |  | 45 | 85 | 129 | 2020 | 2021 | R16
169432139215 | 165336139215 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-04 | 2019-01-04 | 2019-01-05 |  | 2019-01-31 | Overhead | R16 | 2019-01-23 | 1 | 1 | 13 | 7 | 20 | 2019 | 2019 | R16
165927217828 | 168414217828 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-20 | 2021-01-20 | 2021-01-20 |  | 2021-11-04 | Overhead | R16 | 2021-04-06 | 1 |  | 55 | 153 | 207 | 2021 | 2021 | R16
166082150403 | 165620150403 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-25 | 2019-04-26 | 2019-04-26 |  | 2019-06-03 | Overhead | R16 | 2019-05-14 | 2 |  | 13 | 15 | 28 | 2019 | 2019 | R16
169437266174 | 169649266174 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2021-11-15 | 2021-11-15 | 2022-01-26 |  | 2023-05-04 | Underground | R16 |  | 1 | 53 |  |  | 384 | 2021 | 2023 | R16
163541225663 | 168792225663 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-07 | 2021-04-01 | 2021-04-01 | 2021-05-17 | 2021-11-08 | Overhead | R16 | 2021-05-17 | 19 |  | 33 | 126 | 176 | 2021 | 2021 | R16
169437265722 | 163002265722 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-01-20 | 2022-01-20 | 2022-01-21 |  | 2023-05-30 | Underground | R16 |  | 1 | 2 |  |  | 354 | 2022 | 2023 | R16
164118152913 | 160471152913 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-22 | 2019-05-22 | 2019-05-22 |  | 2019-07-10 | Overhead | R16 | 2019-07-02 | 1 |  | 30 | 7 | 36 | 2019 | 2019 | R16
169437276825 | 169007276825 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2022-03-30 | 2022-03-30 | 2022-04-22 |  | 2023-09-27 | Underground | R16 |  | 1 | 18 |  |  | 391 | 2022 | 2023 | R16
168410222644 | 168610222644 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-08-03 | 2021-08-04 | Overhead | R16 | 2021-08-03 | 1 |  | 108 | 2 | 109 | 2021 | 2021 | R16
164497197476 | 168602197476 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-16 | 2020-07-16 | 2020-07-16 |  | 2020-10-06 | Overhead | R16 | 2020-08-13 | 1 |  | 21 | 39 | 59 | 2020 | 2020 | R16
167267201793 | 162863201793 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-10 | 2020-08-10 | 2020-08-26 |  | 2021-07-07 | Underground | R16 | 2020-10-21 | 1 | 13 | 41 | 186 | 238 | 2020 | 2021 | R16
168601152483 | 169217152483 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-15 | 2019-05-15 | 2019-05-15 | 2019-06-03 | 2019-06-03 | Overhead | R16 | 2019-06-03 | 1 |  | 14 |  | 14 | 2019 | 2019 | R16
169875214384 | 161317214384 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-17 | 2020-12-17 | 2020-12-17 | 2021-01-26 | 2021-11-09 | Overhead | R16 | 2021-01-26 | 1 |  | 29 | 206 | 234 | 2020 | 2021 | R16
169488139867 | 166599139867 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-10 | 2019-01-10 | 2019-01-10 |  | 2019-04-01 | Underground | R16 | 2019-02-26 | 1 |  | 34 | 25 | 58 | 2019 | 2019 | R16
164044213312 | 169699213312 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-09 | 2020-12-09 | 2020-12-09 |  | 2021-05-05 | Overhead | R16 | 2021-02-16 | 1 |  | 50 | 57 | 106 | 2020 | 2021 | R16
168856220588 | 164160220588 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-02-12 | 2021-02-16 | 2021-02-16 |  | 2021-05-07 | Underground | R16 |  | 3 |  |  |  | 61 | 2021 | 2021 | R16
169502173935 | 161812173935 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-09-18 | 2019-09-18 | 2019-12-10 |  | 2021-11-16 | Underground | R16 |  | 1 | 60 |  |  | 565 | 2019 | 2021 | R16
161474234209 | 161298234209 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-06-02 | 2021-06-09 | 2021-06-09 |  | 2021-10-26 | Underground | R16 | 2021-09-01 | 6 |  | 61 | 40 | 105 | 2021 | 2021 | R16
169502190792 | 160580190792 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2020-02-14 | 2020-02-14 | 2020-05-12 |  | 2021-07-01 | Underground | R16 |  | 1 | 63 |  |  | 360 | 2020 | 2021 | R16
167080203980 | 161004203980 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-09-15 | 2020-09-15 | 2020-09-15 |  | 2021-07-26 | Overhead | R16 | 2020-11-12 | 1 |  | 43 | 183 | 225 | 2020 | 2021 | R16
160475179539 | 162349179539 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-02-08 | 2019-05-21 | 2020-02-06 |  | 2023-06-08 | Underground | R16 |  | 73 | 188 |  |  | 1130 | 2019 | 2023 | R16
169575148567 | 167663148567 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-03-11 | 2019-03-11 | 2019-04-08 |  | 2019-08-29 | Underground | R16 | 2019-08-23 | 1 | 21 | 100 | 5 | 124 | 2019 | 2019 | R16
169596163856 | 165438163856 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-04-25 | 2019-04-25 | 2019-09-10 |  | 2019-10-28 | Overhead | R16 |  | 1 | 99 |  |  | 133 | 2019 | 2019 | R16
164974153860 | 160640153860 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-05-23 | 2019-05-28 | 2019-05-30 | 2019-06-07 | 2023-06-08 | Overhead | R16 | 2019-06-07 | 4 | 3 | 7 | 1045 | 1056 | 2019 | 2023 | R16
165509214220 | 161132214220 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-15 | 2020-12-15 | 2020-12-15 |  | 2022-10-20 | Overhead | R16 |  | 1 |  |  |  | 483 | 2020 | 2022 | R16
160555236909 | 164180236909 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-10 | 2021-06-28 | 2021-06-28 | 2021-08-12 | 2021-09-14 | Overhead | R16 | 2021-08-12 | 36 |  | 34 | 24 | 92 | 2021 | 2021 | R16
160577221689 | 161759221689 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-02-02 | 2021-02-02 | 2021-02-26 | 2021-05-10 | 2021-05-11 | Underground | R16 | 2021-05-10 | 1 | 19 | 52 | 2 | 71 | 2021 | 2021 | R16
167863215655 | 163504215655 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-29 | 2020-12-29 | 2020-12-29 | 2021-03-01 | 2021-03-02 | Overhead | R16 | 2021-03-01 | 1 |  | 45 | 2 | 46 | 2020 | 2021 | R16
164527240500 | 160899240500 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-01 | 2021-06-02 | 2021-07-23 | 2021-08-17 | 2021-08-18 | Underground | R16 | 2021-08-17 | 2 | 38 | 18 | 2 | 57 | 2021 | 2021 | R16
167466215323 | 164194215323 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-11 | 2020-11-11 | 2020-12-22 | 2020-12-29 | 2021-04-29 | Underground | R16 | 2020-12-29 | 1 | 30 | 6 | 88 | 122 | 2020 | 2021 | R16
169690160550 | 164584160550 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-04-19 | 2019-06-18 | 2019-08-08 |  | 2021-11-05 | Overhead | R16 |  | 43 | 38 |  |  | 666 | 2019 | 2021 | R16
166369212140 | 167454212140 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-12 | 2020-10-12 | 2020-11-25 | 2021-04-30 | 2021-11-05 | Underground | R16 | 2021-04-30 | 1 | 33 | 113 | 136 | 280 | 2020 | 2021 | R16
164312144784 | 166121144784 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-04 | 2019-03-04 | 2019-03-04 | 2019-05-22 | 2019-05-23 | Overhead | R16 | 2019-05-22 | 1 |  | 58 | 2 | 59 | 2019 | 2019 | R16
164518245800 | 160431245800 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-25 | 2021-05-20 | 2021-08-29 | 2021-11-19 | 2022-04-26 | Overhead | R16 | 2021-11-19 | 149 | 72 | 60 | 113 | 392 | 2020 | 2022 | R16
168739245921 | 162492245921 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-22 | 2021-03-22 | 2021-08-30 | 2022-03-25 | 2022-10-18 | Underground | R16 | 2022-03-25 | 1 | 116 | 150 | 148 | 412 | 2021 | 2022 | R16
169716140940 | 168152140940 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-21 | 2019-01-21 | 2019-01-21 |  | 2019-04-15 | Overhead | R16 | 2019-03-27 | 1 |  | 48 | 14 | 61 | 2019 | 2019 | R16
168431142859 | 163385142859 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-13 | 2019-02-13 | 2019-02-13 |  | 2019-05-20 | Underground | R16 | 2019-04-11 | 1 |  | 42 | 28 | 69 | 2019 | 2019 | R16
164132223979 | 167736223979 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-01 | 2021-01-29 | 2021-03-19 |  | 2021-11-05 | Underground | R16 | 2021-04-12 | 44 | 36 | 17 | 150 | 244 | 2020 | 2021 | R16
164480201280 | 165392201280 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-20 | 2020-08-20 | 2020-08-20 | 2021-03-22 | 2022-07-20 | Overhead | R16 | 2021-03-22 | 1 |  | 153 | 348 | 500 | 2020 | 2022 | R16
167897232095 | 162220232095 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-01 | 2021-05-01 | 2021-05-25 | 2023-11-06 | 2023-11-17 | Underground | R16 | 2023-11-06 | 0 | 17 | 640 | 10 | 665 | 2021 | 2023 | R16
164340227572 | 164315227572 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-31 | 2020-12-31 | 2021-04-19 | 2021-06-10 | 2021-06-11 | Underground | R16 | 2021-06-10 | 1 | 78 | 39 | 2 | 117 | 2020 | 2021 | R16
161903211235 | 165625211235 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-11-18 | 2020-11-19 | 2020-11-19 | 2021-02-05 | 2021-04-29 | Overhead | R16 | 2021-02-05 | 2 |  | 57 | 60 | 117 | 2020 | 2021 | R16
169328151019 | 164128151019 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-17 | 2019-04-17 | 2019-05-02 |  | 2019-08-12 | Underground | R16 | 2019-05-30 | 1 | 12 | 21 | 53 | 84 | 2019 | 2019 | R16
166648232749 | 162311232749 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-03 | 2021-05-03 | 2021-05-28 |  | 2021-10-25 | Underground | R16 | 2021-08-31 | 1 | 20 | 68 | 40 | 126 | 2021 | 2021 | R16
169832144614 | 165469144614 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-28 | 2019-03-01 | 2019-03-01 |  | 2019-08-12 | Overhead | R16 | 2019-06-20 | 2 |  | 80 | 38 | 118 | 2019 | 2019 | R16
163282215743 | 163499215743 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-28 | 2020-12-28 | 2020-12-28 | 2021-01-07 | 2021-05-06 | Overhead | R16 | 2021-01-07 | 1 |  | 9 | 86 | 94 | 2020 | 2021 | R16
169846141599 | 169440141599 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-28 | 2019-01-28 | 2019-01-28 |  | 2019-04-01 | Overhead | R16 | 2019-02-28 | 1 |  | 24 | 23 | 46 | 2019 | 2019 | R16
168207151437 | 161734151437 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-04 | 2019-04-04 | 2019-05-07 | 2019-05-29 | 2019-05-30 | Underground | R16 | 2019-05-29 | 1 | 24 | 17 | 2 | 41 | 2019 | 2019 | R16
168326143341 | 163616143341 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-14 | 2019-02-14 | 2019-02-14 |  | 2019-05-28 | Overhead | R16 | 2019-04-26 | 1 |  | 52 | 23 | 74 | 2019 | 2019 | R16
169881146822 | 169420146822 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-21 | 2019-03-21 | 2019-03-22 |  | 2019-11-14 | Overhead | R16 | 2019-11-06 | 1 | 2 | 164 | 7 | 171 | 2019 | 2019 | R16
161396223182 | 169811223182 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-10 | 2021-03-10 | 2021-03-10 | 2021-06-16 | 2021-08-23 | Overhead | R16 | 2021-06-16 | 1 |  | 71 | 49 | 119 | 2021 | 2021 | R16
161393207252 | 167577207252 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-14 | 2020-10-14 | 2020-10-14 | 2020-11-03 | 2021-04-07 | Underground | R16 | 2020-11-03 | 1 |  | 15 | 112 | 126 | 2020 | 2021 | R16
169687208088 | 160040208088 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-23 | 2020-10-23 | 2020-10-23 |  | 2021-04-16 | Overhead | R16 | 2020-12-29 | 1 |  | 48 | 79 | 126 | 2020 | 2021 | R16
161254143100 | 162724143100 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-11 | 2019-02-12 | 2019-02-12 | 2019-02-22 | 2019-02-25 | Underground | R16 | 2019-02-22 | 2 |  | 9 | 2 | 11 | 2019 | 2019 | R16
166088226554 | 168844226554 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-08 | 2021-03-08 | 2021-04-12 |  | 2021-08-31 | Underground | R16 | 2021-06-10 | 1 | 26 | 44 | 59 | 127 | 2021 | 2021 | R16
164545172469 | 169466172469 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-05-16 | 2019-08-05 | 2019-11-20 | 2021-09-01 | 2021-09-29 | Underground | R16 | 2021-09-01 | 58 | 78 | 466 | 21 | 620 | 2019 | 2021 | R16
164141243263 | 165948243263 | Electric Vehicle | UG R16 RESD AND NON RESD UD | Commercial | 2021-02-23 | 2021-03-31 | 2021-08-12 | 2022-08-10 | 2022-10-03 | Underground | R16 | 2022-08-10 | 27 | 97 | 260 | 39 | 420 | 2021 | 2022 | R16
163285153489 | 169301153489 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-15 | 2019-05-15 | 2019-05-29 |  | 2019-08-12 | Underground | R16 | 2019-06-19 | 1 | 11 | 16 | 39 | 64 | 2019 | 2019 | R16
162838198065 | 169547198065 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-22 | 2020-07-22 | 2020-07-22 |  | 2020-10-06 | Overhead | R16 | 2020-08-20 | 1 |  | 22 | 34 | 55 | 2020 | 2020 | R16
167770206269 | 165598206269 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-05 | 2020-10-05 | 2020-10-05 |  | 2021-11-08 | Underground | R16 | 2021-04-29 | 1 |  | 149 | 138 | 286 | 2020 | 2021 | R16
168635154946 | 168695154946 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-13 | 2019-05-13 | 2019-06-10 | 2019-10-21 | 2019-10-22 | Underground | R16 | 2019-10-21 | 1 | 21 | 96 | 2 | 117 | 2019 | 2019 | R16
168732225447 | 162390225447 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-22 | 2021-03-22 | 2021-03-31 |  | 2021-11-04 | Underground | R16 | 2021-06-02 | 1 | 8 | 46 | 112 | 164 | 2021 | 2021 | R16
169834210662 | 160956210662 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-30 | 2020-07-30 | 2020-11-13 | 2020-11-24 | 2020-12-16 | Underground | R16 | 2020-11-24 | 1 | 77 | 8 | 17 | 100 | 2020 | 2020 | R16
169978143935 | 164678143935 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-22 | 2019-02-22 | 2019-02-22 |  | 2022-08-24 | Overhead | R16 | 2019-03-11 | 1 |  | 12 | 903 | 914 | 2019 | 2022 | R16
168317199421 | 161522199421 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-07-31 | 2020-07-31 | 2020-07-31 |  | 2020-10-06 | Overhead | R16 | 2020-08-18 | 1 |  | 13 | 36 | 48 | 2020 | 2020 | R16
168300143567 | 163765143567 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-15 | 2019-02-19 | 2019-02-19 | 2019-05-22 | 2019-06-07 | Overhead | R16 | 2019-05-22 | 3 |  | 67 | 13 | 81 | 2019 | 2019 | R16
168135201382 | 165330201382 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-19 | 2020-08-20 | 2020-08-20 | 2020-08-28 | 2021-02-17 | Overhead | R16 | 2020-08-28 | 2 |  | 7 | 124 | 131 | 2020 | 2021 | R16
160011144145 | 168988144145 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-25 | 2019-01-25 | 2019-02-25 |  | 2019-05-28 | Underground | R16 | 2019-04-22 | 1 | 22 | 41 | 27 | 88 | 2019 | 2019 | R16
163752152768 | 169525152768 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-18 | 2019-05-18 | 2019-05-18 | 2019-06-24 | 2019-08-26 | Overhead | R16 | 2019-06-24 | 0 |  | 26 | 46 | 71 | 2019 | 2019 | R16
160020141708 | 169493141708 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-29 | 2019-01-29 | 2019-01-29 |  | 2019-04-01 | Underground | R16 | 2019-02-26 | 1 |  | 21 | 25 | 45 | 2019 | 2019 | R16
162948150359 | 165752150359 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-26 | 2019-04-26 | 2019-04-26 | 2019-05-13 | 2019-05-13 | Overhead | R16 | 2019-05-13 | 1 |  | 12 |  | 12 | 2019 | 2019 | R16
160124139984 | 166738139984 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-11 | 2019-01-11 | 2019-01-11 |  | 2019-04-01 | Overhead | R16 | 2019-02-26 | 1 |  | 33 | 25 | 57 | 2019 | 2019 | R16
162550198501 | 160316198501 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-27 | 2020-07-27 | 2020-07-27 |  | 2021-06-03 | Overhead | R16 | 2021-03-09 | 1 |  | 162 | 63 | 224 | 2020 | 2021 | R16
165460224232 | 168552224232 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-03 | 2020-12-03 | 2021-03-19 |  | 2021-08-26 | Underground | R16 | 2021-06-07 | 1 | 77 | 57 | 59 | 191 | 2020 | 2021 | R16
166645141728 | 169528141728 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-30 | 2019-01-30 | 2019-01-30 | 2019-03-19 | 2019-03-20 | Overhead | R16 | 2019-03-19 | 1 |  | 35 | 2 | 36 | 2019 | 2019 | R16
161701232340 | 168056232340 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2021-04-14 | 2021-05-18 | 2021-05-25 |  | 2023-06-26 | Underground | R16 |  | 25 | 6 |  |  | 574 | 2021 | 2023 | R16
166629157953 | 168491157953 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-11 | 2019-05-11 | 2019-07-17 |  | 2019-12-06 | Underground | R16 | 2019-08-27 | 0 | 48 | 30 | 74 | 150 | 2019 | 2019 | R16
160236141636 | 169435141636 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-29 | 2019-01-29 | 2019-01-29 |  | 2019-04-15 | Underground | R16 | 2019-03-07 | 1 |  | 28 | 28 | 55 | 2019 | 2019 | R16
161520145650 | 166963145650 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-07 | 2019-03-11 | 2019-03-11 |  | 2019-05-20 | Overhead | R16 | 2019-04-10 | 3 |  | 23 | 29 | 53 | 2019 | 2019 | R16
160782253581 | 160361253581 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-05-27 | 2021-05-27 | 2021-10-24 | 2021-12-28 | 2022-04-01 | Underground | R16 | 2021-12-28 | 1 | 107 | 47 | 69 | 222 | 2021 | 2022 | R16
166717265167 | 166691265167 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG R16 RESD AND NON RESD UD | Commercial | 2021-04-08 | 2021-04-08 | 2022-01-18 | 2022-08-31 | 2022-09-21 | Underground | R16 | 2022-08-31 | 1 | 204 | 162 | 16 | 380 | 2021 | 2022 | R16
160423205806 | 164853205806 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-30 | 2020-09-30 | 2020-09-30 |  | 2021-07-19 | Underground | R16 | 2020-11-11 | 1 |  | 31 | 179 | 209 | 2020 | 2021 | R16
169893251107 | 164923251107 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2021-05-13 | 2021-06-07 | 2021-10-07 | 2022-03-23 | 2022-04-25 | Underground | R16 | 2022-03-23 | 18 | 89 | 120 | 24 | 248 | 2021 | 2022 | R16
160256140384 | 167334140384 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-15 | 2019-01-15 | 2019-01-15 |  | 2019-04-22 | Overhead | R16 | 2019-03-18 | 1 |  | 45 | 26 | 70 | 2019 | 2019 | R16
168625205803 | 164509205803 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-30 | 2020-09-30 | 2020-09-30 |  | 2021-04-07 | Overhead | R16 | 2020-12-02 | 1 |  | 46 | 91 | 136 | 2020 | 2021 | R16
168291211206 | 165532211206 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2019-02-28 | 2019-02-28 | 2020-11-18 | 2022-12-22 | 2023-08-02 | Underground | R16 | 2022-12-22 | 1 | 450 | 547 | 160 | 1155 | 2019 | 2023 | R16
169180233026 | 169253233026 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2021-05-24 | 2021-05-24 | 2021-06-01 |  | 2023-08-23 | Underground | R16 |  | 1 | 7 |  |  | 588 | 2021 | 2023 | R16
160270139759 | 166387139759 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-10 | 2019-01-10 | 2019-01-10 |  | 2019-04-15 | Overhead | R16 | 2019-02-05 | 1 |  | 19 | 50 | 68 | 2019 | 2019 | R16
165660216268 | 165052216268 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-05 | 2021-01-05 | 2021-01-05 |  | 2021-06-02 | Overhead | R16 | 2021-03-05 | 1 |  | 44 | 64 | 107 | 2021 | 2021 | R16
168624205030 | 168769205030 | NON-RESIDENTIAL - WAREHOUSE | R16 RESD AND NON RESD US | Commercial | 2020-09-05 | 2020-09-05 | 2020-09-25 |  | 2021-08-31 | Underground | R16 |  | 0 | 15 |  |  | 257 | 2020 | 2021 | R16
166053194163 | 160545194163 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-03-28 | 2019-04-04 | 2020-06-12 |  | 2021-06-02 | Underground | R16 |  | 6 | 312 |  |  | 570 | 2019 | 2021 | R16
160290141341 | 169006141341 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-25 | 2019-01-25 | 2019-01-25 |  | 2019-04-15 | Overhead | R16 | 2019-03-07 | 1 |  | 30 | 28 | 57 | 2019 | 2019 | R16
168237228430 | 160490228430 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-26 | 2021-04-26 | 2021-04-26 | 2021-04-27 | 2021-11-03 | Overhead | R16 | 2021-04-27 | 1 |  | 2 | 137 | 138 | 2021 | 2021 | R16
160298145152 | 166565145152 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-06 | 2019-03-06 | 2019-03-06 |  | 2019-04-30 | Overhead | R16 | 2019-04-04 | 1 |  | 22 | 19 | 40 | 2019 | 2019 | R16
169880219606 | 164396219606 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG R16 RESD AND NON RESD UD | Commercial | 2020-08-18 | 2020-12-09 | 2021-02-04 | 2022-12-01 | 2022-12-19 | Underground | R16 | 2022-12-01 | 82 | 42 | 476 | 13 | 610 | 2020 | 2022 | R16
160625227065 | 168361227065 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-15 | 2021-04-15 | 2021-04-15 |  | 2021-11-05 | Overhead | R16 | 2021-11-05 | 1 |  | 147 |  | 147 | 2021 | 2021 | R16
166462232396 | 160584232396 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-26 | 2021-05-03 | 2021-05-26 | 2021-08-27 | 2021-10-25 | Underground | R16 | 2021-08-27 | 6 | 18 | 68 | 42 | 131 | 2021 | 2021 | R16
169925231948 | 164486231948 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-05-11 | 2021-05-11 | 2021-05-21 | 2021-11-08 | 2021-12-29 | Underground | R16 | 2021-11-08 | 1 | 9 | 122 | 38 | 167 | 2021 | 2021 | R16
160608149924 | 164803149924 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-22 | 2019-04-22 | 2019-04-22 | 2019-05-17 | 2019-08-12 | Overhead | R16 | 2019-05-17 | 1 |  | 20 | 62 | 81 | 2019 | 2019 | R16
162216205702 | 164515205702 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2020-09-29 | 2020-09-29 | 2020-09-29 |  | 2021-04-21 | Overhead | R16 | 2021-01-22 | 1 |  | 84 | 64 | 147 | 2020 | 2021 | R16
162183224691 | 163584224691 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-11-09 | 2020-12-22 | 2021-03-25 |  | 2022-08-03 | Overhead | R16 | 2022-06-28 | 32 | 68 | 329 | 27 | 453 | 2020 | 2022 | R16
160533214525 | 168996214525 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-12-07 | 2020-12-07 | 2020-12-18 | 2020-12-21 | 2021-02-18 | Underground | R16 | 2020-12-21 | 1 | 10 | 2 | 44 | 54 | 2020 | 2021 | R16
161894214123 | 167571214123 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-30 | 2020-12-15 | 2020-12-15 | 2021-01-26 | 2021-02-01 | Underground | R16 | 2021-01-26 | 12 |  | 31 | 5 | 46 | 2020 | 2021 | R16
164156141667 | 160199141667 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-30 | 2019-01-30 | 2019-01-30 | 2019-03-28 | 2019-03-29 | Overhead | R16 | 2019-03-28 | 1 |  | 42 | 2 | 43 | 2019 | 2019 | R16
166869218334 | 169432218334 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-25 | 2021-01-25 | 2021-01-25 | 2021-03-31 | 2022-08-03 | Overhead | R16 | 2021-03-31 | 1 |  | 48 | 351 | 398 | 2021 | 2022 | R16
160327204036 | 167636204036 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-08-31 | 2020-08-31 | 2020-09-16 |  | 2021-04-21 | Overhead | R16 |  | 1 | 13 |  |  | 168 | 2020 | 2021 | R16
164209204139 | 161601204139 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-17 | 2020-09-17 | 2020-09-17 | 2020-11-19 | 2021-07-26 | Overhead | R16 | 2020-11-19 | 1 |  | 46 | 178 | 223 | 2020 | 2021 | R16
160327204030 | 167639204030 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-08-31 | 2020-08-31 | 2020-09-16 |  | 2021-04-21 | Overhead | R16 |  | 1 | 13 |  |  | 168 | 2020 | 2021 | R16
163785237224 | 169775237224 | NON-RESIDENTIAL - MISCELLANEOUS | UG ELEC MISC SVC US | Commercial | 2021-03-10 | 2021-03-11 | 2021-06-29 |  | 2021-11-16 | Underground | R16 |  | 2 | 79 |  |  | 180 | 2021 | 2021 | R16
167585148932 | 162944148932 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-11 | 2019-04-11 | 2019-04-12 |  | 2019-08-12 | Underground | R16 | 2019-05-23 | 1 | 2 | 30 | 58 | 88 | 2019 | 2019 | R16
160327204032 | 167850204032 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-08-31 | 2020-08-31 | 2020-09-16 |  | 2021-04-21 | Overhead | R16 |  | 1 | 13 |  |  | 168 | 2020 | 2021 | R16
161403153473 | 166752153473 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-05-01 | 2019-05-01 | 2019-05-29 |  | 2019-08-12 | Underground | R16 | 2019-06-05 | 1 | 21 | 6 | 49 | 74 | 2019 | 2019 | R16
161636147468 | 168666147468 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-03-18 | 2019-03-18 | 2019-03-28 |  | 2021-11-13 | Underground | R16 |  | 1 | 9 |  |  | 695 | 2019 | 2021 | R16
167339228354 | 169585228354 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-21 | 2021-04-21 | 2021-04-27 |  | 2022-06-30 | Underground | R16 | 2022-06-02 | 1 | 5 | 288 | 21 | 312 | 2021 | 2022 | R16
160327210506 | 169454210506 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-09-09 | 2020-09-09 | 2020-11-12 |  | 2021-11-05 | Overhead | R16 |  | 1 | 47 |  |  | 303 | 2020 | 2021 | R16
167484203236 | 169360203236 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-08 | 2020-09-08 | 2020-09-08 | 2021-12-28 | 2021-12-28 | Underground | R16 | 2021-12-28 | 1 |  | 341 |  | 341 | 2020 | 2021 | R16
166618156589 | 161532156589 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-02-05 | 2019-02-05 | 2019-06-27 | 2020-11-24 | 2021-03-27 | Underground | R16 | 2020-11-24 | 1 | 103 | 369 | 89 | 559 | 2019 | 2021 | R16
160327210504 | 169729210504 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-09-09 | 2020-09-10 | 2020-11-12 |  | 2021-04-29 | Overhead | R16 |  | 2 | 46 |  |  | 167 | 2020 | 2021 | R16
167222219801 | 162479219801 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-05 | 2021-02-05 | 2021-02-05 | 2021-04-19 | 2022-03-22 | Overhead | R16 | 2021-04-19 | 1 |  | 52 | 242 | 293 | 2021 | 2022 | R16
166557152584 | 169405152584 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-16 | 2019-05-16 | 2019-05-16 |  | 2019-08-12 | Overhead | R16 | 2019-06-21 | 1 |  | 27 | 37 | 63 | 2019 | 2019 | R16
160333148118 | 168235148118 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-01-22 | 2019-01-22 | 2019-04-05 |  | 2020-06-09 | Underground | R16 | 2020-02-14 | 1 | 54 | 226 | 83 | 361 | 2019 | 2020 | R16
168524228403 | 169228228403 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-01-25 | 2021-01-25 | 2021-04-26 |  | 2022-04-05 | Underground | R16 |  | 1 | 66 |  |  | 312 | 2021 | 2022 | R16
160337142955 | 162898142955 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-12 | 2019-02-12 | 2019-02-12 |  | 2019-04-26 | Overhead | R16 | 2019-04-03 | 1 |  | 37 | 18 | 54 | 2019 | 2019 | R16
160343236292 | 164620236292 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-03-30 | 2021-03-30 | 2021-06-23 |  | 2021-11-09 | Underground | R16 |  | 1 | 62 |  |  | 161 | 2021 | 2021 | R16
165008152476 | 169475152476 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-16 | 2019-05-16 | 2019-05-16 | 2019-08-20 | 2019-08-28 | Overhead | R16 | 2019-08-20 | 1 |  | 69 | 7 | 75 | 2019 | 2019 | R16
163751222662 | 163701222662 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-29 | 2020-12-29 | 2021-03-05 |  | 2022-03-08 | Underground | R16 | 2022-02-11 | 1 | 49 | 246 | 18 | 311 | 2020 | 2022 | R16
163863219577 | 162295219577 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-04 | 2021-02-04 | 2021-02-04 |  | 2021-10-25 | Underground | R16 | 2021-07-22 | 1 |  | 121 | 68 | 188 | 2021 | 2021 | R16
166755150257 | 165475150257 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-25 | 2019-04-25 | 2019-04-25 | 2019-05-14 | 2019-05-15 | Overhead | R16 | 2019-05-14 | 1 |  | 14 | 2 | 15 | 2019 | 2019 | R16
168815199619 | 162272199619 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-06 | 2020-08-06 | 2020-08-06 |  | 2020-10-06 | Overhead | R16 | 2020-08-26 | 1 |  | 15 | 30 | 44 | 2020 | 2020 | R16
168330141632 | 169374141632 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-28 | 2019-01-28 | 2019-01-28 | 2019-03-19 | 2019-03-20 | Underground | R16 | 2019-03-19 | 1 |  | 37 | 2 | 38 | 2019 | 2019 | R16
161532263950 | 169622263950 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2021-04-21 | 2021-06-24 | 2022-01-07 | 2023-06-15 | 2023-07-28 | Underground | R16 | 2023-06-15 | 47 | 142 | 375 | 32 | 593 | 2021 | 2023 | R16
167314146589 | 168889146589 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-03-20 | 2019-03-20 | 2019-03-20 |  | 2019-05-20 | Overhead | R16 | 2019-04-17 | 1 |  | 21 | 24 | 44 | 2019 | 2019 | R16
160538140633 | 167767140633 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-17 | 2019-01-17 | 2019-01-17 |  | 2019-04-25 | Overhead | R16 | 2019-04-02 | 1 |  | 54 | 18 | 71 | 2019 | 2019 | R16
162361247000 | 167129247000 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-12 | 2021-04-20 | 2021-09-08 |  | 2021-10-25 | Overhead | R16 | 2021-09-16 | 7 | 102 | 7 | 28 | 141 | 2021 | 2021 | R16
160539143151 | 163238143151 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-13 | 2019-02-13 | 2019-02-13 |  | 2019-04-15 | Overhead | R16 | 2019-03-11 | 1 |  | 19 | 26 | 44 | 2019 | 2019 | R16
161977243591 | 162924243591 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-23 | 2021-05-06 | 2021-08-14 | 2021-10-28 | 2021-10-28 | Underground | R16 | 2021-10-28 | 33 | 72 | 54 |  | 158 | 2021 | 2021 | R16
163244249819 | 168487249819 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-12-03 | 2021-09-22 | 2021-09-28 | 2021-11-01 | 2021-11-01 | Underground | R16 | 2021-11-01 | 210 | 5 | 25 |  | 238 | 2020 | 2021 | R16
166820233961 | 167934233961 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-03-02 | 2021-03-02 | 2021-06-07 | 2022-08-25 | 2022-08-26 | Underground | R16 | 2022-08-25 | 1 | 70 | 319 | 2 | 389 | 2021 | 2022 | R16
169924232620 | 160002232620 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES UD | Residential | 2021-05-26 | 2021-05-26 | 2021-05-26 |  | 2021-09-02 | Underground | R16 | 2021-08-10 | 1 |  | 55 | 18 | 72 | 2021 | 2021 | R16
162935144957 | 163132144957 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-12 | 2019-02-12 | 2019-03-06 | 2019-04-17 | 2019-12-06 | Underground | R16 | 2019-04-17 | 1 | 17 | 31 | 168 | 214 | 2019 | 2019 | R16
168575145987 | 169291145987 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-28 | 2019-01-28 | 2019-03-13 | 2019-06-24 | 2023-06-08 | Underground | R16 | 2019-06-24 | 1 | 33 | 74 | 1034 | 1139 | 2019 | 2023 | R16
165858160156 | 168607160156 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-13 | 2019-05-13 | 2019-08-05 |  | 2019-12-04 | Underground | R16 |  | 1 | 61 |  |  | 148 | 2019 | 2019 | R16
160580142173 | 161290142173 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-02-04 | 2019-02-04 | 2019-02-04 |  | 2020-06-09 | Overhead | R16 | 2020-03-27 | 1 |  | 300 | 53 | 352 | 2019 | 2020 | R16
166229149564 | 163993149564 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-17 | 2019-04-17 | 2019-04-17 | 2019-05-08 | 2019-05-09 | Overhead | R16 | 2019-05-08 | 1 |  | 16 | 2 | 17 | 2019 | 2019 | R16
168824144944 | 168951144944 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-24 | 2019-01-24 | 2019-03-04 | 2019-04-30 | 2019-04-30 | Underground | R16 | 2019-04-30 | 1 | 28 | 42 |  | 69 | 2019 | 2019 | R16
160613197844 | 169039197844 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-20 | 2020-07-20 | 2020-07-20 |  | 2021-06-30 | Overhead | R16 | 2020-10-29 | 1 |  | 74 | 175 | 248 | 2020 | 2021 | R16
161987229620 | 166376229620 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2021-04-07 | 2021-05-05 | 2022-01-13 | 2022-01-13 | 2021-11-13 | Overhead | R16 | 2022-01-13 | 21 | 182 |  |  | 158 | 2021 | 2021 | R16
168390204034 | 160789204034 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-09-15 | 2020-09-15 | 2020-09-16 |  | 2020-12-18 | Overhead | R16 |  | 1 | 2 |  |  | 69 | 2020 | 2020 | R16
163385221259 | 165811221259 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-22 | 2021-02-23 | 2021-02-23 |  | 2021-10-25 | Overhead | R16 | 2021-04-29 | 2 |  | 48 | 128 | 176 | 2021 | 2021 | R16
160715160925 | 164952160925 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-08-12 | 2019-08-12 | 2019-08-12 |  | 2019-10-09 | Overhead | R16 | 2019-09-25 | 1 |  | 33 | 11 | 43 | 2019 | 2019 | R16
169719160312 | 161964160312 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-03 | 2019-06-03 | 2019-08-06 | 2020-12-29 | 2021-11-11 | Underground | R16 | 2020-12-29 | 1 | 47 | 366 | 228 | 639 | 2019 | 2021 | R16
163880201304 | 165383201304 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-20 | 2020-08-20 | 2020-08-20 | 2020-09-02 | 2020-12-18 | Overhead | R16 | 2020-09-02 | 1 |  | 10 | 78 | 87 | 2020 | 2020 | R16
162999214177 | 169178214177 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-07 | 2020-12-17 | 2020-12-17 |  | 2021-04-23 | Overhead | R16 | 2021-02-03 | 9 |  | 35 | 58 | 100 | 2020 | 2021 | R16
160722148081 | 161377148081 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-03 | 2019-04-03 | 2019-04-03 |  | 2019-06-03 | Underground | R16 | 2019-05-08 | 1 |  | 26 | 19 | 44 | 2019 | 2019 | R16
166351225803 | 167932225803 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-02 | 2021-03-02 | 2021-04-05 | 2021-05-26 | 2021-05-28 | Underground | R16 | 2021-05-26 | 1 | 25 | 38 | 3 | 64 | 2021 | 2021 | R16
160747158592 | 161783158592 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-24 | 2019-07-24 | 2019-07-24 |  | 2019-09-06 | Overhead | R16 | 2019-08-30 | 1 |  | 28 | 6 | 33 | 2019 | 2019 | R16
164166153048 | 166451153048 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-30 | 2019-05-14 | 2019-05-22 |  | 2019-06-18 | Overhead | R16 |  | 11 | 7 |  |  | 36 | 2019 | 2019 | R16
160756143606 | 163953143606 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-19 | 2019-02-19 | 2019-02-19 |  | 2019-04-25 | Overhead | R16 | 2019-04-01 | 1 |  | 30 | 19 | 48 | 2019 | 2019 | R16
160814154970 | 163049154970 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-10 | 2019-06-10 | 2019-06-10 |  | 2021-11-11 | Underground | R16 | 2021-06-04 | 1 |  | 520 | 115 | 634 | 2019 | 2021 | R16
160781156281 | 165905156281 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-06-25 | 2019-06-25 | 2019-06-25 |  | 2020-07-07 | Underground | R16 | 2020-05-07 | 1 |  | 228 | 44 | 271 | 2019 | 2020 | R16
166557232195 | 160086232195 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2021-04-23 | 2021-04-28 | 2021-05-25 |  | 2021-11-18 | Underground | R16 | 2021-10-25 | 4 | 20 | 110 | 19 | 150 | 2021 | 2021 | R16
160783142250 | 161247142250 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-04 | 2019-02-04 | 2019-02-04 |  | 2019-04-15 | Overhead | R16 | 2019-03-13 | 1 |  | 28 | 24 | 51 | 2019 | 2019 | R16
160415234167 | 165528234167 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-14 | 2021-05-14 | 2021-06-09 | 2021-09-05 | 2021-11-09 | Underground | R16 | 2021-09-05 | 1 | 19 | 63 | 47 | 128 | 2021 | 2021 | R16
161564152497 | 166239152497 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-03-05 | 2019-03-05 | 2019-05-16 | 2020-04-30 | 2020-05-01 | Underground | R16 | 2020-04-30 | 1 | 53 | 251 | 2 | 304 | 2019 | 2020 | R16
169670212116 | 165585212116 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-18 | 2020-11-30 | 2020-11-30 | 2021-02-23 | 2021-06-02 | Overhead | R16 | 2021-02-23 | 9 |  | 62 | 72 | 141 | 2020 | 2021 | R16
160799140263 | 165688140263 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-07 | 2019-01-07 | 2019-01-14 |  | 2019-06-03 | Underground | R16 | 2019-05-06 | 1 | 6 | 81 | 21 | 106 | 2019 | 2019 | R16
169292232470 | 169320232470 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-01-28 | 2021-04-06 | 2021-05-26 | 2021-12-09 | 2022-03-30 | Underground | R16 | 2021-12-09 | 572 | 37 | 142 | 80 | 828 | 2019 | 2022 | R16
161991203050 | 169402203050 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-08 | 2020-09-08 | 2020-09-08 | 2020-09-16 | 2021-01-08 | Overhead | R16 | 2020-09-16 | 1 |  | 7 | 83 | 89 | 2020 | 2021 | R16
169179210545 | 164591210545 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-12 | 2020-11-12 | 2020-11-12 | 2020-12-08 | 2021-04-21 | Overhead | R16 | 2020-12-08 | 1 |  | 19 | 97 | 115 | 2020 | 2021 | R16
168865232823 | 161566232823 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2021-04-30 | 2021-04-30 | 2021-05-28 | 2022-10-24 | 2022-10-25 | Underground | R16 | 2022-10-24 | 1 | 21 | 367 | 2 | 388 | 2021 | 2022 | R16
164151201621 | 164255201621 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-08-18 | 2020-08-18 | 2020-08-24 |  | 2020-11-02 | Underground | R16 |  | 1 | 5 |  |  | 55 | 2020 | 2020 | R16
160847140576 | 167679140576 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-18 | 2019-01-18 | 2019-01-18 |  | 2019-02-21 | Overhead | R16 | 2019-02-12 | 1 |  | 18 | 8 | 25 | 2019 | 2019 | R16
161421204536 | 168325204536 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-02 | 2020-09-02 | 2020-09-22 | 2020-11-19 | 2021-04-16 | Underground | R16 | 2020-11-19 | 1 | 15 | 43 | 107 | 163 | 2020 | 2021 | R16
160919142997 | 162686142997 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-11 | 2019-02-11 | 2019-02-11 |  | 2019-04-25 | Overhead | R16 | 2019-04-02 | 1 |  | 37 | 18 | 54 | 2019 | 2019 | R16
169283147843 | 160821147843 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-29 | 2019-03-29 | 2019-04-01 | 2019-07-17 | 2019-10-09 | Overhead | R16 | 2019-07-17 | 1 | 2 | 78 | 61 | 139 | 2019 | 2019 | R16
165265223232 | 168621223232 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-03-05 | 2021-03-11 | 2021-03-11 |  | 2022-01-04 | Overhead | R16 | 2021-11-22 | 5 |  | 183 | 32 | 218 | 2021 | 2022 | R16
160971145976 | 168015145976 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-13 | 2019-03-13 | 2019-03-14 |  | 2019-05-20 | Overhead | R16 | 2019-04-18 | 1 | 2 | 26 | 23 | 49 | 2019 | 2019 | R16
169452224559 | 160674224559 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-15 | 2021-03-15 | 2021-03-24 |  | 2021-11-05 | Underground | R16 | 2021-05-06 | 1 | 8 | 32 | 132 | 170 | 2021 | 2021 | R16
163007202764 | 168676202764 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-04 | 2020-09-04 | 2020-09-04 | 2020-10-08 | 2021-07-19 | Overhead | R16 | 2020-10-08 | 1 |  | 25 | 203 | 227 | 2020 | 2021 | R16
163657229358 | 162759229358 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-04 | 2021-05-04 | 2021-05-04 | 2021-07-14 | 2021-07-15 | Overhead | R16 | 2021-07-14 | 1 |  | 52 | 2 | 53 | 2021 | 2021 | R16
161071145280 | 169087145280 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-25 | 2019-01-25 | 2019-03-07 |  | 2019-08-12 | Underground | R16 | 2019-06-17 | 1 | 30 | 73 | 41 | 142 | 2019 | 2019 | R16
166294152660 | 169095152660 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-15 | 2019-05-16 | 2019-05-16 | 2019-08-26 | 2019-09-04 | Overhead | R16 | 2019-08-26 | 2 |  | 73 | 8 | 81 | 2019 | 2019 | R16
161561222795 | 168924222795 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-08 | 2021-03-08 | 2021-03-08 |  | 2023-03-23 | Overhead | R16 | 2023-03-23 | 1 |  | 534 |  | 534 | 2021 | 2023 | R16
163703149003 | 160093149003 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-26 | 2019-04-11 | 2019-04-12 | 2019-05-07 | 2019-05-08 | Overhead | R16 | 2019-05-07 | 13 | 2 | 18 | 2 | 32 | 2019 | 2019 | R16
169267147465 | 160541147465 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-28 | 2019-03-28 | 2019-03-28 | 2019-05-09 | 2019-06-03 | Overhead | R16 | 2019-05-09 | 1 |  | 31 | 18 | 48 | 2019 | 2019 | R16
168560224915 | 160934224915 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-16 | 2021-03-24 | 2021-03-26 | 2021-05-15 | 2021-05-19 | Underground | R16 | 2021-05-15 | 7 | 3 | 36 | 3 | 47 | 2021 | 2021 | R16
165652144851 | 166225144851 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-04 | 2019-03-04 | 2019-03-04 |  | 2019-05-20 | Overhead | R16 | 2019-04-12 | 1 |  | 30 | 27 | 56 | 2019 | 2019 | R16
161343205986 | 165248205986 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-01 | 2020-10-01 | 2020-10-01 |  | 2021-04-21 | Overhead | R16 | 2021-01-20 | 1 |  | 80 | 66 | 145 | 2020 | 2021 | R16
168687152972 | 167808152972 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-07 | 2019-05-07 | 2019-05-20 |  | 2019-08-12 | Underground | R16 | 2019-06-07 | 1 | 10 | 15 | 47 | 70 | 2019 | 2019 | R16
165373214354 | 161443214354 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-17 | 2020-12-17 | 2020-12-17 |  | 2021-04-29 | Underground | R16 | 2021-02-08 | 1 |  | 38 | 59 | 96 | 2020 | 2021 | R16
161883217616 | 167934217616 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-01 | 2020-12-01 |  | 2021-01-19 | 2021-04-22 | Underground | R16 | 2021-01-19 | 1 |  |  | 68 | 103 | 2020 | 2021 | R16
161201142972 | 162831142972 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-11 | 2019-02-11 | 2019-02-11 |  | 2019-09-11 | Overhead | R16 | 2019-09-05 | 1 |  | 149 | 5 | 153 | 2019 | 2019 | R16
162118209055 | 161370209055 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-29 | 2020-10-29 | 2020-10-29 | 2021-01-07 | 2021-07-28 | Overhead | R16 | 2021-01-07 | 1 |  | 51 | 145 | 195 | 2020 | 2021 | R16
162995148839 | 160532148839 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-03-28 | 2019-03-28 | 2019-04-11 |  | 2019-08-12 | Overhead | R16 | 2019-06-12 | 1 | 11 | 45 | 44 | 98 | 2019 | 2019 | R16
161237154871 | 161244154871 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-05-29 | 2019-05-29 | 2019-06-11 |  | 2021-11-05 | Underground | R16 |  | 1 | 10 |  |  | 638 | 2019 | 2021 | R16
167391213610 | 160218213610 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-11 | 2020-12-11 | 2020-12-11 | 2021-02-12 | 2021-05-06 | Overhead | R16 | 2021-02-12 | 1 |  | 46 | 60 | 105 | 2020 | 2021 | R16
162664207861 | 162750207861 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-07 | 2020-08-07 | 2020-10-21 |  | 2021-04-16 | Underground | R16 | 2021-01-08 | 1 | 54 | 58 | 71 | 181 | 2020 | 2021 | R16
161238148116 | 163999148116 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-19 | 2019-02-19 | 2019-04-05 |  | 2019-05-28 | Underground | R16 | 2019-04-23 | 1 | 34 | 13 | 26 | 71 | 2019 | 2019 | R16
166353219903 | 167875219903 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-09-01 | 2020-09-16 | 2021-02-08 | 2021-03-18 | 2021-04-16 | Underground | R16 | 2021-03-18 | 12 | 104 | 29 | 22 | 164 | 2020 | 2021 | R16
161246141859 | 160775141859 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-01 | 2019-02-01 | 2019-02-01 |  | 2019-05-28 | Overhead | R16 | 2019-05-01 | 1 |  | 64 | 20 | 83 | 2019 | 2019 | R16
167566153262 | 160497153262 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-22 | 2019-05-22 | 2019-05-22 |  | 2023-06-09 | Overhead | R16 | 2019-09-18 | 1 |  | 86 | 973 | 1058 | 2019 | 2023 | R16
164424215926 | 163991215926 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-30 | 2020-12-30 | 2020-12-30 | 2021-03-23 | 2021-03-23 | Overhead | R16 | 2021-03-23 | 1 |  | 60 |  | 60 | 2020 | 2021 | R16
169370218112 | 168991218112 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-22 | 2021-01-22 | 2021-01-22 | 2021-06-23 | 2021-08-11 | Overhead | R16 | 2021-06-23 | 1 |  | 109 | 36 | 144 | 2021 | 2021 | R16
160859215157 | 161905215157 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2021-01-20 | 2022-06-01 | Overhead | R16 | 2021-01-20 | 1 |  | 23 | 356 | 378 | 2020 | 2022 | R16
165235232093 | 165033232093 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2021-05-13 | 2021-05-13 | 2021-05-25 |  | 2021-11-11 | Underground | R16 | 2021-06-04 | 1 | 9 | 9 | 115 | 131 | 2021 | 2021 | R16
163358211694 | 166894211694 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-24 | 2020-11-24 | 2020-11-24 |  | 2021-04-23 | Overhead | R16 | 2021-02-02 | 1 |  | 51 | 59 | 109 | 2020 | 2021 | R16
161318141615 | 169498141615 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-29 | 2019-01-29 | 2019-01-29 |  | 2019-08-12 | Overhead | R16 | 2019-05-20 | 1 |  | 80 | 61 | 140 | 2019 | 2019 | R16
169789202878 | 164547202878 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-18 | 2020-08-18 | 2020-09-08 |  | 2021-04-16 | Underground | R16 | 2020-11-11 | 1 | 16 | 47 | 113 | 174 | 2020 | 2021 | R16
167901217005 | 165546217005 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-07 | 2021-01-12 | 2021-01-12 |  | 2021-08-12 | Underground | R16 | 2021-03-03 | 4 |  | 37 | 117 | 156 | 2021 | 2021 | R16
161383155303 | 169682155303 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2019-03-25 | 2019-06-03 | 2019-06-13 |  | 2019-08-26 | Overhead | R16 |  | 51 | 9 |  |  | 111 | 2019 | 2019 | R16
165895229022 | 161946229022 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-07-07 | 2021-12-02 | Overhead | R16 | 2021-07-07 | 1 |  | 49 | 107 | 155 | 2021 | 2021 | R16
161411141571 | 169431141571 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-28 | 2019-01-28 | 2019-01-28 |  | 2019-03-14 | Overhead | R16 | 2019-02-25 | 1 |  | 21 | 14 | 34 | 2019 | 2019 | R16
168458146883 | 168425146883 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-22 | 2019-01-22 | 2019-03-22 | 2019-04-22 | 2019-04-23 | Underground | R16 | 2019-04-22 | 1 | 44 | 22 | 2 | 66 | 2019 | 2019 | R16
165211153882 | 168995153882 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-14 | 2019-05-14 | 2019-05-30 |  | 2019-07-23 | Underground | R16 | 2019-07-15 | 1 | 13 | 33 | 7 | 51 | 2019 | 2019 | R16
160245216921 | 166099216921 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-11 | 2021-01-11 | 2021-01-11 |  | 2021-11-08 | Overhead | R16 | 2021-05-12 | 1 |  | 88 | 129 | 216 | 2021 | 2021 | R16
167482222516 | 163129222516 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-02-09 | 2021-02-09 | 2021-03-04 |  | 2021-12-01 | Underground | R16 | 2021-11-04 | 1 | 18 | 176 | 20 | 212 | 2021 | 2021 | R16
167991150683 | 165907150683 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-29 | 2019-04-29 | 2019-04-29 |  | 2019-07-18 | Overhead | R16 | 2019-07-03 | 1 |  | 48 | 12 | 59 | 2019 | 2019 | R16
165762232708 | 160407232708 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-27 | 2021-05-27 | 2021-05-27 | 2021-06-11 | 2021-08-23 | Overhead | R16 | 2021-06-11 | 1 |  | 12 | 52 | 63 | 2021 | 2021 | R16
161497142243 | 161240142243 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-04 | 2019-02-04 | 2019-02-04 |  | 2019-04-15 | Underground | R16 | 2019-03-28 | 1 |  | 39 | 13 | 51 | 2019 | 2019 | R16
162851279444 | 167750279444 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-31 | 2020-08-31 | 2022-05-16 | 2023-09-26 | 2023-10-05 | Underground | R16 | 2023-09-26 | 1 | 446 | 357 | 8 | 809 | 2020 | 2023 | R16
161499142522 | 161712142522 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-06 | 2019-02-06 | 2019-02-06 |  | 2019-04-22 | Underground | R16 | 2019-03-18 | 1 |  | 29 | 26 | 54 | 2019 | 2019 | R16
161511157914 | 161622157914 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-05 | 2019-02-11 | 2019-07-16 |  | 2019-10-28 | Underground | R16 | 2019-10-17 | 5 | 112 | 68 | 8 | 190 | 2019 | 2019 | R16
165707269502 | 168553269502 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-05-19 | 2021-05-19 | 2022-02-17 |  | 2022-06-30 | Underground | R16 |  | 1 | 197 |  |  | 292 | 2021 | 2022 | R16
164729139761 | 164811139761 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-01-03 | 2019-01-09 | 2019-01-09 |  | 2019-08-12 | Underground | R16 | 2019-06-05 | 5 |  | 106 | 49 | 158 | 2019 | 2019 | R16
166670224573 | 163020224573 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-24 | 2021-03-24 | 2021-03-24 | 2021-04-20 | 2021-11-03 | Overhead | R16 | 2021-04-20 | 1 |  | 20 | 142 | 161 | 2021 | 2021 | R16
161525143520 | 163746143520 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-15 | 2019-02-15 | 2019-02-15 |  | 2019-06-03 | Underground | R16 | 2019-03-27 | 1 |  | 29 | 49 | 77 | 2019 | 2019 | R16
161529144020 | 164613144020 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-22 | 2019-02-22 | 2019-02-22 |  | 2019-04-15 | Overhead | R16 | 2019-03-06 | 1 |  | 9 | 29 | 37 | 2019 | 2019 | R16
166274216547 | 165009216547 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-05 | 2021-01-07 | 2021-01-07 |  | 2021-05-07 | Underground | R16 | 2021-02-24 | 3 |  | 35 | 53 | 89 | 2021 | 2021 | R16
161573143799 | 164590143799 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-21 | 2019-02-21 | 2019-02-21 |  | 2019-06-10 | Overhead | R16 | 2019-05-07 | 1 |  | 54 | 25 | 78 | 2019 | 2019 | R16
165744148266 | 161782148266 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-04 | 2019-04-04 | 2019-04-04 | 2019-05-07 | 2019-05-08 | Overhead | R16 | 2019-05-07 | 1 |  | 24 | 2 | 25 | 2019 | 2019 | R16
160167216075 | 164576216075 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-04 | 2021-01-04 | 2021-01-05 | 2021-01-06 | 2021-05-05 | Overhead | R16 | 2021-01-06 | 1 | 2 | 2 | 86 | 88 | 2021 | 2021 | R16
168293220650 | 164446220650 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-02-16 | 2021-02-17 | 2021-02-17 |  | 2021-08-02 | Overhead | R16 | 2021-03-29 | 2 |  | 29 | 91 | 120 | 2021 | 2021 | R16
163672145437 | 163626145437 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-14 | 2019-02-14 | 2019-03-08 | 2019-04-30 | 2019-04-30 | Underground | R16 | 2019-04-30 | 1 | 17 | 38 |  | 54 | 2019 | 2019 | R16
167975198914 | 160759198914 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-29 | 2020-07-29 | 2020-07-29 | 2020-09-28 | 2020-09-29 | Overhead | R16 | 2020-09-28 | 1 |  | 44 | 2 | 45 | 2020 | 2020 | R16
166014217902 | 166793217902 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-23 | 2020-12-01 | 2021-01-21 | 2021-03-04 | 2021-03-08 | Underground | R16 | 2021-03-04 | 7 | 38 | 31 | 3 | 76 | 2020 | 2021 | R16
161605150460 | 167097150460 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-01-14 | 2019-01-14 | 2019-04-26 |  | 2020-06-09 | Underground | R16 | 2020-04-14 | 1 | 75 | 253 | 41 | 367 | 2019 | 2020 | R16
160551226609 | 161620226609 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-30 | 2020-10-30 | 2021-04-13 |  | 2021-09-10 | Underground | R16 | 2021-07-12 | 1 | 118 | 65 | 45 | 226 | 2020 | 2021 | R16
163120226101 | 163142226101 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-24 | 2021-03-24 | 2021-04-07 |  | 2021-08-16 | Underground | R16 | 2021-06-14 | 1 | 11 | 49 | 46 | 104 | 2021 | 2021 | R16
161614141616 | 169516141616 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-29 | 2019-01-29 | 2019-01-29 |  | 2019-04-15 | Underground | R16 | 2019-03-13 | 1 |  | 32 | 24 | 55 | 2019 | 2019 | R16
167764144847 | 166179144847 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-04 | 2019-03-04 | 2019-03-04 |  | 2019-06-03 | Overhead | R16 | 2019-05-08 | 1 |  | 48 | 19 | 66 | 2019 | 2019 | R16
161615142444 | 161573142444 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-05 | 2019-02-05 | 2019-02-05 |  | 2019-04-25 | Overhead | R16 | 2019-03-21 | 1 |  | 33 | 26 | 58 | 2019 | 2019 | R16
168680292996 | 166169292996 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2021-05-18 | 2021-05-19 | 2022-09-08 | 2023-01-05 | 2023-01-05 | Underground | R16 | 2023-01-05 | 2 | 342 | 86 |  | 428 | 2021 | 2023 | R16
161616163366 | 160253163366 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-30 | 2019-01-30 | 2019-09-05 |  | 2019-10-30 | Underground | R16 | 2019-10-24 | 1 | 157 | 36 | 5 | 196 | 2019 | 2019 | R16
163025229139 | 162653229139 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-05-04 | 2021-05-04 | 2021-05-04 |  | 2021-09-07 | Overhead | R16 | 2021-08-10 | 1 |  | 71 | 21 | 91 | 2021 | 2021 | R16
169498150668 | 166081150668 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-30 | 2019-04-30 | 2019-04-30 | 2019-05-23 | 2019-08-12 | Overhead | R16 | 2019-05-23 | 1 |  | 18 | 58 | 75 | 2019 | 2019 | R16
168580145098 | 166747145098 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-07 | 2019-03-07 | 2019-03-07 | 2019-04-02 | 2019-04-03 | Underground | R16 | 2019-04-02 | 1 |  | 19 | 2 | 20 | 2019 | 2019 | R16
161655140388 | 167432140388 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-15 | 2019-01-15 | 2019-01-15 |  | 2019-05-20 | Overhead | R16 | 2019-04-08 | 1 |  | 60 | 31 | 90 | 2019 | 2019 | R16
168960210794 | 169997210794 | NON-RESIDENTIAL - SMALL RETAIL | R16 RESD AND NON RESD US | Commercial | 2020-10-24 | 2020-11-13 | 2020-11-16 | 2021-07-27 | 2021-10-25 | Underground | R16 | 2021-07-27 | 15 | 2 | 182 | 65 | 261 | 2020 | 2021 | R16
161677147502 | 164297147502 | AGRICULTURAL | R16 RESD AND NON RESD US | Residential Subdivision | 2019-02-20 | 2019-02-21 | 2019-03-28 |  | 2019-05-16 | Underground | R16 |  | 2 | 26 |  |  | 62 | 2019 | 2019 | R16
166232209383 | 163859209383 | INDUSTRIAL | R16 RESD AND NON RESD US | Commercial | 2020-08-14 | 2020-09-21 | 2020-11-02 |  | 2021-05-06 | Underground | R16 |  | 27 | 31 |  |  | 190 | 2020 | 2021 | R16
161654220568 | 164119220568 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-02-12 | 2021-02-13 | 2021-02-14 | 2021-07-30 | 2021-11-08 | Underground | R16 | 2021-07-30 | 1 | 0 | 120 | 72 | 192 | 2021 | 2021 | R16
167457215364 | 162962215364 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-22 | 2020-12-22 | 2020-12-22 |  | 2021-04-20 | Overhead | R16 | 2021-01-15 | 1 |  | 19 | 68 | 86 | 2020 | 2021 | R16
168181216192 | 168115216192 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-01 | 2020-09-01 | 2021-01-06 |  | 2021-10-27 | Underground | R16 | 2021-08-13 | 1 | 92 | 158 | 54 | 302 | 2020 | 2021 | R16
169721225149 | 164223225149 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-29 | 2021-03-29 | 2021-03-29 |  | 2021-10-28 | Overhead | R16 | 2021-05-19 | 1 |  | 38 | 117 | 154 | 2021 | 2021 | R16
168367143791 | 164400143791 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-20 | 2019-02-20 | 2019-02-20 |  | 2019-04-25 | Overhead | R16 | 2019-03-21 | 1 |  | 22 | 26 | 47 | 2019 | 2019 | R16
168357151821 | 163903151821 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-16 | 2019-04-16 | 2019-05-08 |  | 2019-08-12 | Underground | R16 | 2019-05-23 | 1 | 17 | 12 | 58 | 85 | 2019 | 2019 | R16
161756157494 | 162217157494 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-05 | 2019-07-03 | 2019-07-09 |  | 2019-10-16 | Overhead | R16 |  | 21 | 5 |  |  | 96 | 2019 | 2019 | R16
166637144276 | 165047144276 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-26 | 2019-02-26 | 2019-02-26 | 2019-04-24 | 2019-04-24 | Overhead | R16 | 2019-04-24 | 1 |  | 42 |  | 42 | 2019 | 2019 | R16
161756168448 | 162866168448 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-25 | 2019-10-01 | 2019-10-17 |  | 2019-11-15 | Overhead | R16 |  | 5 | 13 |  |  | 38 | 2019 | 2019 | R16
161756175050 | 168545175050 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-16 | 2019-12-18 | 2019-12-23 |  | 2020-06-17 | Overhead | R16 |  | 3 | 4 |  |  | 133 | 2019 | 2020 | R16
167647211375 | 166189211375 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-20 | 2020-11-20 | 2020-11-20 | 2021-02-05 | 2021-02-08 | Overhead | R16 | 2021-02-05 | 1 |  | 56 | 2 | 57 | 2020 | 2021 | R16
166250236019 | 162924236019 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2019-02-12 | 2019-02-15 | 2021-06-22 | 2022-01-04 | 2022-01-24 | Underground | R16 | 2022-01-04 | 4 | 613 | 141 | 15 | 770 | 2019 | 2022 | R16
169032197426 | 168323197426 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-15 | 2020-07-15 | 2020-07-15 |  | 2022-10-18 | Overhead | R16 |  | 1 |  |  |  | 590 | 2020 | 2022 | R16
161763200864 | 164247200864 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-18 | 2020-08-18 | 2020-08-18 |  | 2020-12-29 | Overhead | R16 | 2020-09-29 | 1 |  | 31 | 66 | 96 | 2020 | 2020 | R16
168101204013 | 161480204013 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-17 | 2020-09-17 | 2020-09-17 | 2020-10-09 | 2022-02-07 | Overhead | R16 | 2020-10-09 | 1 |  | 17 | 347 | 363 | 2020 | 2022 | R16
162206212016 | 168550212016 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-16 | 2020-10-16 | 2020-11-25 |  | 2022-05-18 | Underground | R16 |  | 1 | 29 |  |  | 414 | 2020 | 2022 | R16
165382143706 | 164116143706 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-19 | 2019-02-19 | 2019-02-19 |  | 2019-04-15 | Overhead | R16 | 2019-03-07 | 1 |  | 13 | 28 | 40 | 2019 | 2019 | R16
169357147517 | 160466147517 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-28 | 2019-03-28 | 2019-03-28 | 2019-04-12 | 2019-04-17 | Overhead | R16 | 2019-04-12 | 1 |  | 12 | 4 | 15 | 2019 | 2019 | R16
162787229825 | 162884229825 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2021-05-04 | 2021-05-05 | 2021-05-06 | 2022-01-19 | 2021-11-03 | Underground | R16 | 2022-01-19 | 2 | 2 | 185 |  | 132 | 2021 | 2021 | R16
160309215945 | 161873215945 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2020-12-21 | 2020-12-21 | 2020-12-30 |  | 2021-10-25 | Underground | R16 |  | 1 | 8 |  |  | 221 | 2020 | 2021 | R16
161813141931 | 160583141931 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-31 | 2019-01-31 | 2019-01-31 |  | 2019-04-15 | Overhead | R16 | 2019-03-27 | 1 |  | 40 | 14 | 53 | 2019 | 2019 | R16
167663201228 | 165238201228 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-19 | 2020-08-20 | 2020-08-20 | 2020-10-22 | 2021-07-07 | Overhead | R16 | 2020-10-22 | 2 |  | 46 | 185 | 231 | 2020 | 2021 | R16
161838158658 | 162861158658 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-11 | 2019-07-16 | 2019-07-24 |  | 2019-10-04 | Underground | R16 | 2019-09-24 | 112 | 7 | 45 | 9 | 170 | 2019 | 2019 | R16
166645224637 | 163162224637 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-24 | 2021-03-24 | 2021-03-24 | 2021-12-01 | 2022-05-03 | Overhead | R16 | 2021-12-01 | 1 |  | 181 | 110 | 290 | 2021 | 2022 | R16
166824276881 | 163420276881 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-02-10 | 2021-02-10 | 2022-04-22 |  | 2022-05-04 | Overhead | R16 | 2022-04-26 | 1 | 313 | 3 | 7 | 321 | 2021 | 2022 | R16
161860140401 | 167340140401 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-15 | 2019-01-15 | 2019-01-15 |  | 2019-02-12 | Overhead | R16 | 2019-01-31 | 1 |  | 13 | 9 | 21 | 2019 | 2019 | R16
168134149915 | 165122149915 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-23 | 2019-04-23 | 2019-04-23 | 2019-05-07 | 2019-05-08 | Overhead | R16 | 2019-05-07 | 1 |  | 11 | 2 | 12 | 2019 | 2019 | R16
161909168943 | 167865168943 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-10-19 | 2019-10-19 | 2019-10-21 |  | 2019-11-21 | Overhead | R16 |  | 0 | 1 |  |  | 24 | 2019 | 2019 | R16
167524223168 | 165113223168 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-05 | 2021-03-10 | 2021-03-10 |  | 2021-11-05 | Overhead | R16 | 2021-05-04 | 47 |  | 40 | 134 | 219 | 2021 | 2021 | R16
161955139854 | 166664139854 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-10 | 2019-01-10 | 2019-01-10 |  | 2023-06-08 | Overhead | R16 | 2019-06-26 | 1 |  | 120 | 1032 | 1151 | 2019 | 2023 | R16
166950224570 | 162947224570 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-03-24 | 2021-03-24 | 2021-03-24 | 2021-03-25 | 2021-11-08 | Overhead | R16 | 2021-03-25 | 1 |  | 2 | 163 | 164 | 2021 | 2021 | R16
161958138958 | 164710138958 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-02 | 2019-01-02 | 2019-01-02 |  | 2019-01-25 | Overhead | R16 | 2019-01-14 | 1 |  | 9 | 10 | 18 | 2019 | 2019 | R16
160040209539 | 167146209539 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-12 | 2020-10-12 | 2020-11-03 |  | 2021-04-22 | Underground | R16 | 2021-01-28 | 1 | 17 | 63 | 61 | 139 | 2020 | 2021 | R16
161990145302 | 163640145302 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-14 | 2019-03-07 | 2019-03-07 |  | 2019-04-30 | Underground | R16 | 2019-04-04 | 16 |  | 21 | 19 | 54 | 2019 | 2019 | R16
162012144305 | 165081144305 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-25 | 2019-02-25 | 2019-02-25 |  | 2022-08-03 | Overhead | R16 |  | 1 |  |  |  | 898 | 2019 | 2022 | R16
166212211393 | 166035211393 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-20 | 2020-11-20 | 2020-11-20 |  | 2021-04-22 | Overhead | R16 | 2021-04-15 | 1 |  | 105 | 6 | 110 | 2020 | 2021 | R16
163446201119 | 165309201119 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-21 | 2020-08-21 | 2020-08-21 |  | 2020-12-18 | Overhead | R16 | 2020-09-22 | 1 |  | 23 | 64 | 86 | 2020 | 2020 | R16
161101150900 | 166351150900 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-04-30 | 2019-04-30 | 2019-04-30 |  | 2019-06-03 | Overhead | R16 | 2019-04-01 | 1 |  |  | 46 | 25 | 2019 | 2019 | R16
162036141772 | 160270141772 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-30 | 2019-01-30 | 2019-01-30 |  | 2019-04-15 | Underground | R16 | 2019-03-08 | 1 |  | 28 | 27 | 54 | 2019 | 2019 | R16
164973222737 | 167265222737 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-28 | 2021-03-09 | 2021-03-09 | 2021-03-31 | 2021-11-08 | Overhead | R16 | 2021-03-31 | 7 |  | 17 | 159 | 181 | 2021 | 2021 | R16
162493154294 | 161509154294 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-05-30 | 2019-05-30 | 2019-06-04 | 2019-12-05 | 2019-12-06 | Overhead | R16 | 2019-12-05 | 1 | 4 | 133 | 2 | 137 | 2019 | 2019 | R16
162929152325 | 168963152325 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-14 | 2019-05-14 | 2019-05-14 |  | 2019-08-12 | Overhead | R16 | 2019-06-06 | 1 |  | 18 | 48 | 65 | 2019 | 2019 | R16
166306209615 | 162832209615 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-04 | 2020-11-04 | 2020-11-04 | 2020-11-18 | 2021-04-13 | Overhead | R16 | 2020-11-18 | 1 |  | 11 | 105 | 115 | 2020 | 2021 | R16
167262218261 | 166757218261 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-25 | 2020-11-25 | 2021-01-24 | 2021-04-30 | 2021-05-03 | Underground | R16 | 2021-04-30 | 1 | 43 | 70 | 2 | 114 | 2020 | 2021 | R16
169887223566 | 160244223566 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-03-12 | 2021-03-12 | 2021-03-12 | 2021-11-05 | 2022-06-20 | Overhead | R16 | 2021-11-05 | 1 |  | 171 | 162 | 332 | 2021 | 2022 | R16
162105142607 | 162375142607 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-08 | 2019-02-08 | 2019-02-08 |  | 2019-04-15 | Underground | R16 | 2019-03-26 | 1 |  | 33 | 15 | 47 | 2019 | 2019 | R16
169488213921 | 160129213921 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-12-11 | 2020-12-14 | 2020-12-14 |  | 2021-04-15 | Underground | R16 | 2020-12-23 | 2 |  | 8 | 82 | 90 | 2020 | 2021 | R16
160567236708 | 166180236708 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-18 | 2021-05-18 | 2021-06-25 | 2021-09-15 | 2021-10-01 | Underground | R16 | 2021-09-15 | 1 | 29 | 59 | 13 | 99 | 2021 | 2021 | R16
162162142857 | 169230142857 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-01-28 | 2019-01-28 | 2019-02-13 |  | 2021-11-13 | Overhead | R16 | 2019-12-16 | 1 | 13 | 219 | 500 | 730 | 2019 | 2021 | R16
165206207403 | 168077207403 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-15 | 2020-10-15 | 2020-10-15 |  | 2021-05-06 | Overhead | R16 | 2020-02-18 | 1 |  |  | 318 | 146 | 2020 | 2021 | R16
162163146557 | 168426146557 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-15 | 2019-03-15 | 2019-03-20 |  | 2019-05-28 | Underground | R16 | 2019-04-23 | 1 | 4 | 25 | 26 | 53 | 2019 | 2019 | R16
167042153224 | 160564153224 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-23 | 2019-05-23 | 2019-05-23 | 2019-07-24 | 2019-07-24 | Overhead | R16 | 2019-07-24 | 1 |  | 45 |  | 45 | 2019 | 2019 | R16
162206144973 | 166115144973 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-03-04 | 2019-03-04 | 2019-03-05 |  | 2019-05-28 | Underground | R16 |  | 1 | 2 |  |  | 62 | 2019 | 2019 | R16
160560207614 | 168909207614 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-20 | 2020-10-20 | 2020-10-20 |  | 2021-08-26 | Overhead | R16 | 2021-06-09 | 1 |  | 167 | 57 | 223 | 2020 | 2021 | R16
162253141031 | 168319141031 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-23 | 2019-01-23 | 2019-01-23 |  | 2019-08-12 | Overhead | R16 | 2019-05-23 | 1 |  | 87 | 58 | 144 | 2019 | 2019 | R16
165069155501 | 167902155501 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-08 | 2019-05-08 | 2019-06-17 | 2019-08-23 | 2019-08-26 | Underground | R16 | 2019-08-23 | 1 | 29 | 50 | 2 | 79 | 2019 | 2019 | R16
162049198120 | 169432198120 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-22 | 2020-07-22 | 2020-07-22 |  | 2020-10-06 | Overhead | R16 | 2020-08-06 | 1 |  | 12 | 44 | 55 | 2020 | 2020 | R16
168132149883 | 164703149883 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-22 | 2019-04-22 | 2019-04-22 | 2019-05-01 | 2019-05-01 | Overhead | R16 | 2019-05-01 | 1 |  | 8 |  | 8 | 2019 | 2019 | R16
162321168506 | 163159168506 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-09-26 | 2019-09-26 | 2019-10-17 |  | 2020-07-01 | Underground | R16 |  | 1 | 16 |  |  | 200 | 2019 | 2020 | R16
164962227789 | 168727227789 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-17 | 2021-04-17 | 2021-04-21 |  | 2021-08-12 | Overhead | R16 | 2021-07-07 | 0 | 3 | 56 | 27 | 84 | 2021 | 2021 | R16
162563206463 | 166457206463 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-08-25 | 2020-08-25 | 2020-10-07 |  | 2021-04-16 | Overhead | R16 | 2021-01-04 | 1 | 32 | 64 | 75 | 169 | 2020 | 2021 | R16
162454139851 | 166661139851 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-10 | 2019-01-10 | 2019-01-10 |  | 2019-02-19 | Overhead | R16 | 2019-02-04 | 1 |  | 18 | 12 | 29 | 2019 | 2019 | R16
162595142600 | 162075142600 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-02-07 | 2019-02-07 | 2019-02-07 |  | 2019-04-30 | Underground | R16 | 2019-04-05 | 1 |  | 42 | 18 | 59 | 2019 | 2019 | R16
169125147440 | 169015147440 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential Subdivision | 2019-03-20 | 2019-03-20 | 2019-03-27 |  | 2019-09-12 | Underground | R16 |  | 1 | 6 |  |  | 127 | 2019 | 2019 | R16
165535221152 | 165536221152 | AGRICULTURAL | OH R16 RES NON RES OS | Commercial | 2021-02-20 | 2021-02-20 | 2021-02-20 |  | 2021-11-05 | Overhead | R16 | 2021-05-05 | 0 |  | 53 | 133 | 185 | 2021 | 2021 | R16
162614153197 | 162879153197 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2019-04-11 | 2019-05-08 | 2019-05-23 |  | 2019-08-26 | Overhead | R16 |  | 20 | 12 |  |  | 98 | 2019 | 2019 | R16
162614153196 | 162990153196 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2019-04-11 | 2019-05-08 | 2019-05-23 |  | 2020-06-09 | Overhead | R16 |  | 20 | 12 |  |  | 304 | 2019 | 2020 | R16
168836204008 | 168840204008 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-17 | 2020-07-17 | 2020-09-16 | 2020-12-21 | 2021-04-20 | Underground | R16 | 2020-12-21 | 1 | 44 | 69 | 87 | 198 | 2020 | 2021 | R16
160680157649 | 162677157649 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-06-07 | 2019-06-07 | 2019-07-11 | 2020-03-30 | 2020-05-27 | Underground | R16 | 2020-03-30 | 1 | 25 | 188 | 43 | 254 | 2019 | 2020 | R16
166598269547 | 160805269547 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-04-27 | 2022-02-17 | 2022-02-17 |  | 2022-05-09 | Overhead | R16 | 2022-04-15 | 213 |  | 42 | 17 | 270 | 2021 | 2022 | R16
163002159565 | 164702159565 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-04-22 | 2019-04-22 | 2019-07-30 | 2019-11-27 | 2019-12-16 | Underground | R16 | 2019-11-27 | 1 | 72 | 87 | 14 | 171 | 2019 | 2019 | R16
162626142393 | 167084142393 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-14 | 2019-01-14 | 2019-02-06 |  | 2019-08-12 | Underground | R16 | 2019-06-12 | 1 | 18 | 91 | 44 | 151 | 2019 | 2019 | R16
168405232497 | 163430232497 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-12-28 | 2020-12-28 | 2021-05-27 |  | 2023-01-10 | Underground | R16 |  | 1 | 109 |  |  | 532 | 2020 | 2023 | R16
167301217860 | 166860217860 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-13 | 2021-01-19 | 2021-01-20 |  | 2021-05-05 | Underground | R16 | 2021-02-17 | 5 | 2 | 21 | 56 | 81 | 2021 | 2021 | R16
162648143861 | 164171143861 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-20 | 2019-02-20 | 2019-02-20 |  | 2019-04-25 | Overhead | R16 | 2019-04-02 | 1 |  | 30 | 18 | 47 | 2019 | 2019 | R16
167221219663 | 161573219663 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-02 | 2021-02-02 | 2021-02-04 |  | 2021-08-12 | Overhead | R16 | 2021-03-17 | 1 | 3 | 30 | 107 | 138 | 2021 | 2021 | R16
162995230798 | 164619230798 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-11 | 2021-05-11 | 2021-05-15 | 2023-05-22 | 2023-06-13 | Underground | R16 | 2023-05-22 | 1 | 4 | 526 | 17 | 546 | 2021 | 2023 | R16
168873219039 | 161365219039 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-01 | 2021-02-01 | 2021-02-01 |  | 2021-08-30 | Overhead | R16 | 2021-06-10 | 1 |  | 94 | 58 | 151 | 2021 | 2021 | R16
161250230738 | 165548230738 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-14 | 2021-05-14 | 2021-05-14 | 2021-06-09 | 2021-11-10 | Overhead | R16 | 2021-06-09 | 1 |  | 19 | 111 | 129 | 2021 | 2021 | R16
162663142258 | 161094142258 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-02-04 | 2019-02-05 | 2019-02-05 |  | 2020-01-02 | Underground | R16 | 2019-12-11 | 2 |  | 222 | 17 | 239 | 2019 | 2020 | R16
161074224753 | 162358224753 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-22 | 2020-09-22 | 2021-03-26 |  | 2021-08-23 | Underground | R16 | 2021-07-14 | 1 | 134 | 79 | 29 | 240 | 2020 | 2021 | R16
162677144462 | 165096144462 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-02-25 | 2019-02-27 | 2019-02-27 |  | 2023-01-05 | Underground | R16 | 2022-10-07 | 3 |  | 943 | 65 | 1009 | 2019 | 2023 | R16
169757200084 | 169779200084 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential Subdivision | 2020-07-23 | 2020-07-29 | 2020-08-10 |  | 2021-04-29 | Underground | R16 |  | 5 | 9 |  |  | 201 | 2020 | 2021 | R16
167040141946 | 160666141946 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-31 | 2019-01-31 | 2019-01-31 | 2019-03-18 | 2019-03-19 | Overhead | R16 | 2019-03-18 | 1 |  | 33 | 2 | 34 | 2019 | 2019 | R16
162690141761 | 169524141761 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-29 | 2019-01-29 | 2019-01-29 |  | 2019-04-22 | Overhead | R16 | 2019-03-19 | 1 |  | 36 | 25 | 60 | 2019 | 2019 | R16
165469154190 | 169593154190 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-17 | 2019-05-17 | 2019-06-03 |  | 2019-12-06 | Underground | R16 | 2019-08-14 | 1 | 12 | 53 | 83 | 146 | 2019 | 2019 | R16
167904232336 | 163448232336 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-06 | 2021-05-06 | 2021-05-26 |  | 2022-01-11 | Overhead | R16 |  | 1 | 15 |  |  | 179 | 2021 | 2022 | R16
164855141010 | 168236141010 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-01-22 | 2019-01-22 | 2019-01-22 |  | 2019-11-27 | Overhead | R16 | 2019-11-21 | 1 |  | 218 | 5 | 222 | 2019 | 2019 | R16
162698184127 | 166433184127 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-03-16 | 2020-03-16 | 2020-03-16 |  | 2020-10-06 | Overhead | R16 | 2020-08-21 | 1 |  | 115 | 33 | 147 | 2020 | 2020 | R16
168370221973 | 166866221973 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-14 | 2021-03-02 | 2021-03-02 | 2021-03-29 | 2021-11-05 | Overhead | R16 | 2021-03-29 | 34 |  | 20 | 160 | 212 | 2021 | 2021 | R16
162699139830 | 164651139830 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-02 | 2019-01-02 | 2019-01-10 |  | 2019-06-06 | Underground | R16 | 2019-05-24 | 1 | 7 | 97 | 10 | 112 | 2019 | 2019 | R16
163729227062 | 168213227062 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-15 | 2021-04-15 | 2021-04-15 |  | 2021-11-08 | Underground | R16 | 2021-05-24 | 1 |  | 28 | 121 | 148 | 2021 | 2021 | R16
162364238983 | 166702238983 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-18 | 2021-07-14 | 2021-07-14 | 2021-09-21 | 2021-11-18 | Overhead | R16 | 2021-09-21 | 42 |  | 50 | 43 | 133 | 2021 | 2021 | R16
162707142407 | 161489142407 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-05 | 2019-02-05 | 2019-02-05 |  | 2019-05-20 | Overhead | R16 | 2019-04-09 | 1 |  | 46 | 30 | 75 | 2019 | 2019 | R16
162740141962 | 168157141962 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-22 | 2019-01-31 | 2019-01-31 |  | 2019-04-15 | Underground | R16 | 2019-03-14 | 8 |  | 31 | 23 | 60 | 2019 | 2019 | R16
163019146208 | 163575146208 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-02-14 | 2019-02-14 | 2019-03-15 | 2021-03-17 | 2021-08-05 | Underground | R16 | 2021-03-17 | 1 | 22 | 524 | 102 | 646 | 2019 | 2021 | R16
162891141849 | 160393141849 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-30 | 2019-01-30 | 2019-01-30 |  | 2019-04-01 | Overhead | R16 | 2019-02-27 | 1 |  | 21 | 24 | 44 | 2019 | 2019 | R16
162945139510 | 165743139510 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-07 | 2019-01-07 | 2019-01-07 |  | 2019-04-22 | Overhead | R16 | 2019-03-18 | 1 |  | 51 | 26 | 76 | 2019 | 2019 | R16
167620152277 | 163439152277 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-04-15 | 2019-04-16 | 2019-05-14 |  | 2019-08-26 | Underground | R16 | 2019-07-18 | 2 | 21 | 48 | 28 | 96 | 2019 | 2019 | R16
163227221082 | 163079221082 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2021-02-09 | 2021-02-09 | 2021-02-19 |  | 2021-11-16 | Underground | R16 |  | 1 | 9 |  |  | 201 | 2021 | 2021 | R16
162972146341 | 166722146341 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-03-06 | 2019-03-06 | 2019-03-18 |  | 2019-11-08 | Underground | R16 | 2019-10-31 | 1 | 9 | 164 | 7 | 178 | 2019 | 2019 | R16
169347210803 | 161777210803 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-03 | 2020-08-03 | 2020-11-14 | 2020-12-31 | 2021-01-04 | Underground | R16 | 2020-12-31 | 1 | 75 | 34 | 3 | 111 | 2020 | 2021 | R16
167715227482 | 169307227482 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-09 | 2021-03-09 | 2021-04-19 | 2021-04-21 | 2021-11-08 | Overhead | R16 | 2021-04-21 | 1 | 30 | 3 | 144 | 175 | 2021 | 2021 | R16
169549237066 | 165310237066 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-13 | 2021-06-28 | 2021-06-28 |  | 2021-08-23 | Overhead | R16 | 2021-07-27 | 33 |  | 22 | 20 | 73 | 2021 | 2021 | R16
163004141756 | 160366141756 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-30 | 2019-01-30 | 2019-01-30 |  | 2019-04-15 | Overhead | R16 | 2019-03-14 | 1 |  | 32 | 23 | 54 | 2019 | 2019 | R16
163014143824 | 164428143824 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-02-21 | 2019-02-21 | 2019-02-21 |  | 2022-07-26 | Underground | R16 | 2022-06-10 | 1 |  | 862 | 33 | 894 | 2019 | 2022 | R16
160395274347 | 168207274347 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-19 | 2021-05-19 | 2022-03-30 |  | 2022-06-10 | Overhead | R16 | 2022-05-18 | 1 | 226 | 36 | 18 | 278 | 2021 | 2022 | R16
163099141093 | 168164141093 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-22 | 2019-01-22 | 2019-01-24 |  | 2019-04-01 | Underground | R16 | 2019-02-28 | 1 | 3 | 26 | 23 | 50 | 2019 | 2019 | R16
162795158125 | 168582158125 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-18 | 2019-04-30 | 2019-07-17 | 2019-12-26 | 2020-01-08 | Underground | R16 | 2019-12-26 | 32 | 57 | 117 | 10 | 213 | 2019 | 2020 | R16
163117146788 | 169251146788 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-03-21 | 2019-03-21 | 2019-03-21 |  | 2022-06-01 | Underground | R16 | 2020-08-19 | 1 |  | 370 | 466 | 835 | 2019 | 2022 | R16
160783231184 | 164541231184 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-11 | 2021-05-11 | 2021-05-17 | 2021-06-25 | 2021-06-29 | Underground | R16 | 2021-06-25 | 1 | 5 | 30 | 3 | 36 | 2021 | 2021 | R16
164206229163 | 166441229163 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-07 | 2021-04-12 | 2021-05-03 | 2021-07-13 | 2021-07-19 | Underground | R16 | 2021-07-13 | 4 | 16 | 52 | 5 | 74 | 2021 | 2021 | R16
165214216488 | 165336216488 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-06 | 2021-01-06 | 2021-01-07 |  | 2021-08-11 | Overhead | R16 | 2021-03-17 | 1 | 2 | 50 | 106 | 156 | 2021 | 2021 | R16
164148220291 | 161395220291 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-01 | 2021-02-11 | 2021-02-11 | 2021-08-20 | 2021-08-23 | Underground | R16 | 2021-08-20 | 9 |  | 137 | 2 | 146 | 2021 | 2021 | R16
163157143649 | 168393143649 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-22 | 2019-02-04 | 2019-02-19 |  | 2019-04-15 | Overhead | R16 | 2019-03-13 | 10 | 12 | 17 | 24 | 60 | 2019 | 2019 | R16
163161143326 | 163363143326 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-13 | 2019-02-14 | 2019-02-14 |  | 2019-04-22 | Underground | R16 | 2019-03-18 | 2 |  | 23 | 26 | 49 | 2019 | 2019 | R16
165826212427 | 167921212427 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-01 | 2020-12-01 | 2020-12-01 | 2021-02-23 | 2021-08-10 | Overhead | R16 | 2021-02-23 | 1 |  | 61 | 121 | 181 | 2020 | 2021 | R16
168016230125 | 164259230125 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Commercial | 2021-05-10 | 2021-05-10 | 2021-05-10 | 2022-02-09 | 2022-03-29 | Overhead | R16 | 2022-02-09 | 1 |  | 198 | 35 | 232 | 2021 | 2022 | R16
163169146053 | 166165146053 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-03-04 | 2019-03-04 | 2019-03-14 |  | 2020-06-09 | Overhead | R16 | 2020-03-12 | 1 | 9 | 261 | 64 | 332 | 2019 | 2020 | R16
169061140608 | 167825140608 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-01-17 | 2019-01-17 | 2019-01-17 | 2019-03-15 | 2019-03-19 | Overhead | R16 | 2019-03-15 | 1 |  | 42 | 3 | 44 | 2019 | 2019 | R16
163172143932 | 164598143932 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-21 | 2019-02-22 | 2019-02-22 |  | 2019-04-25 | Overhead | R16 | 2019-03-21 | 2 |  | 20 | 26 | 46 | 2019 | 2019 | R16
168375203985 | 161055203985 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-15 | 2020-09-15 | 2020-09-15 |  | 2021-04-14 | Overhead | R16 | 2020-12-16 | 1 |  | 67 | 86 | 152 | 2020 | 2021 | R16
161880140148 | 167044140148 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-14 | 2019-01-14 | 2019-01-14 | 2019-11-12 | 2019-11-13 | Overhead | R16 | 2019-11-12 | 1 |  | 217 | 2 | 218 | 2019 | 2019 | R16
163227138954 | 164656138954 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-01-02 | 2019-01-02 | 2019-01-02 |  | 2021-04-16 | Overhead | R16 | 2020-12-29 | 1 |  | 520 | 79 | 598 | 2019 | 2021 | R16
167322229712 | 169794229712 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-09 | 2020-12-09 | 2021-05-06 |  | 2021-09-10 | Underground | R16 | 2021-08-16 | 1 | 107 | 73 | 20 | 198 | 2020 | 2021 | R16
167196153781 | 169884153781 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-05-20 | 2019-05-29 | 2019-05-29 | 2019-07-05 | 2019-07-05 | Overhead | R16 | 2019-07-05 | 8 |  | 28 |  | 35 | 2019 | 2019 | R16
163252142288 | 165600142288 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-07 | 2019-01-07 | 2019-02-06 |  | 2019-08-26 | Underground | R16 | 2019-07-18 | 1 | 23 | 117 | 28 | 166 | 2019 | 2019 | R16
167024223011 | 169747223011 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-10 | 2021-03-10 | 2021-03-10 | 2021-05-25 | 2021-05-27 | Overhead | R16 | 2021-05-25 | 1 |  | 55 | 3 | 57 | 2021 | 2021 | R16
161243147372 | 169978147372 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-26 | 2019-03-26 | 2019-03-28 |  | 2019-05-28 | Underground | R16 | 2019-04-23 | 1 | 3 | 19 | 26 | 46 | 2019 | 2019 | R16
169268165501 | 161194165501 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-05-29 | 2019-06-25 | 2019-09-23 | 2019-12-06 | 2019-12-09 | Overhead | R16 | 2019-12-06 | 20 | 65 | 55 | 2 | 139 | 2019 | 2019 | R16
164056213619 | 160242213619 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-11 | 2020-12-11 | 2020-12-11 | 2021-02-10 | 2022-02-07 | Overhead | R16 | 2021-02-10 | 1 |  | 44 | 259 | 302 | 2020 | 2022 | R16
163350148106 | 161276148106 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-02-04 | 2019-03-25 | 2019-04-03 |  | 2019-08-26 | Underground | R16 |  | 36 | 8 |  |  | 146 | 2019 | 2019 | R16
167097200670 | 169976200670 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-24 | 2020-07-24 | 2020-08-17 | 2020-10-20 | 2021-06-30 | Underground | R16 | 2020-10-20 | 1 | 17 | 47 | 182 | 244 | 2020 | 2021 | R16
166889206457 | 163020206457 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-24 | 2020-09-24 | 2020-10-08 |  | 2021-08-12 | Overhead | R16 | 2021-03-17 | 1 | 11 | 115 | 107 | 231 | 2020 | 2021 | R16
163501176146 | 166244176146 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-12-04 | 2019-12-09 | 2020-01-07 |  | 2020-06-09 | Underground | R16 |  | 4 | 22 |  |  | 135 | 2019 | 2020 | R16
163371220605 | 164264220605 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-11-03 | 2021-11-04 | Overhead | R16 | 2021-11-03 | 1 |  | 187 | 2 | 188 | 2021 | 2021 | R16
163504145595 | 162755145595 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-11 | 2019-02-11 | 2019-03-13 |  | 2019-05-20 | Underground | R16 | 2019-04-19 | 1 | 23 | 28 | 22 | 71 | 2019 | 2019 | R16
163163208734 | 161123208734 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-28 | 2020-10-28 | 2020-10-28 |  | 2021-11-13 | Overhead | R16 | 2021-04-30 | 1 |  | 133 | 141 | 273 | 2020 | 2021 | R16
163093220448 | 163976220448 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-12 | 2021-02-12 | 2021-02-12 | 2021-03-18 | 2021-11-08 | Overhead | R16 | 2021-03-18 | 1 |  | 25 | 168 | 192 | 2021 | 2021 | R16
162033147360 | 160004147360 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-26 | 2019-03-26 | 2019-03-26 |  | 2019-05-20 | Overhead | R16 | 2019-04-10 | 1 |  | 12 | 29 | 40 | 2019 | 2019 | R16
163528142474 | 161992142474 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-07 | 2019-02-07 | 2019-02-07 |  | 2019-04-15 | Overhead | R16 | 2019-03-11 | 1 |  | 23 | 26 | 48 | 2019 | 2019 | R16
169726230382 | 162477230382 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-22 | 2021-05-11 | 2021-05-11 |  | 2022-02-09 | Overhead | R16 | 2022-01-06 | 37 |  | 173 | 25 | 233 | 2021 | 2022 | R16
160544148314 | 160791148314 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-29 | 2019-03-29 | 2019-04-05 | 2019-05-02 | 2019-05-02 | Underground | R16 | 2019-05-02 | 1 | 6 | 20 |  | 25 | 2019 | 2019 | R16
169587224309 | 162321224309 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-20 | 2021-03-20 | 2021-03-20 |  | 2021-10-26 | Overhead | R16 | 2021-04-23 | 0 |  | 25 | 133 | 157 | 2021 | 2021 | R16
163563141621 | 169261141621 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-28 | 2019-01-28 | 2019-01-28 |  | 2019-04-01 | Overhead | R16 | 2019-02-26 | 1 |  | 22 | 25 | 46 | 2019 | 2019 | R16
168472211822 | 163692211822 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-09 | 2020-11-24 | 2020-11-24 | 2021-01-08 | 2021-04-20 | Overhead | R16 | 2021-01-08 | 12 |  | 34 | 73 | 117 | 2020 | 2021 | R16
165134155456 | 161849155456 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-04 | 2019-06-04 | 2019-06-19 |  | 2023-06-05 | Overhead | R16 | 2019-09-03 | 1 | 12 | 55 | 980 | 1045 | 2019 | 2023 | R16
165758226414 | 167411226414 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-12 | 2021-04-12 | 2021-04-12 | 2021-06-09 | 2021-08-17 | Overhead | R16 | 2021-06-09 | 1 |  | 43 | 50 | 92 | 2021 | 2021 | R16
161912212370 | 166694212370 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-23 | 2020-12-01 | 2020-12-01 |  | 2021-04-16 | Underground | R16 | 2020-12-29 | 7 |  | 21 | 79 | 105 | 2020 | 2021 | R16
163599141850 | 160338141850 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-30 | 2019-01-30 | 2019-01-30 |  | 2019-08-12 | Overhead | R16 | 2019-06-03 | 1 |  | 89 | 51 | 139 | 2019 | 2019 | R16
160683139212 | 165058139212 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-04 | 2019-01-04 | 2019-01-04 | 2019-02-22 | 2023-02-06 | Overhead | R16 | 2019-02-22 | 1 |  | 36 | 1032 | 1067 | 2019 | 2023 | R16
162019225632 | 167829225632 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-03-02 | 2021-03-26 | 2021-04-02 | 2021-09-07 | 2021-11-09 | Underground | R16 | 2021-09-07 | 19 | 6 | 113 | 46 | 181 | 2021 | 2021 | R16
163811146309 | 168837146309 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-19 | 2019-03-19 | 2019-03-19 |  | 2019-05-28 | Overhead | R16 | 2019-04-23 | 1 |  | 26 | 26 | 51 | 2019 | 2019 | R16
167547151414 | 167064151414 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-03 | 2019-05-06 | 2019-05-06 |  | 2019-12-06 | Underground | R16 | 2019-08-09 | 2 |  | 70 | 86 | 156 | 2019 | 2019 | R16
163853147292 | 169987147292 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-26 | 2019-03-26 | 2019-03-26 |  | 2019-06-10 | Overhead | R16 | 2019-05-09 | 1 |  | 33 | 23 | 55 | 2019 | 2019 | R16
163861143896 | 163155143896 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-13 | 2019-02-21 | 2019-02-21 |  | 2019-04-25 | Overhead | R16 | 2019-04-02 | 7 |  | 29 | 18 | 52 | 2019 | 2019 | R16
160838237023 | 162264237023 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-03 | 2021-06-10 | 2021-06-28 | 2021-08-05 | 2021-10-27 | Overhead | R16 | 2021-08-05 | 29 | 13 | 29 | 60 | 128 | 2021 | 2021 | R16
163888142470 | 161261142470 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-04 | 2019-02-07 | 2019-02-07 |  | 2019-04-15 | Overhead | R16 | 2019-03-27 | 4 |  | 35 | 14 | 51 | 2019 | 2019 | R16
164323149194 | 163555149194 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-15 | 2019-04-15 | 2019-04-15 | 2019-05-08 | 2019-06-03 | Overhead | R16 | 2019-05-08 | 1 |  | 18 | 19 | 36 | 2019 | 2019 | R16
166736222162 | 167655222162 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-02 | 2021-03-02 | 2021-03-02 |  | 2021-11-04 | Overhead | R16 | 2021-04-06 | 1 |  | 26 | 153 | 178 | 2021 | 2021 | R16
168330230735 | 164839230735 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-12 | 2021-05-14 | 2021-05-14 | 2021-07-26 | 2021-08-23 | Overhead | R16 | 2021-07-26 | 3 |  | 52 | 21 | 74 | 2021 | 2021 | R16
161147143176 | 163565143176 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-14 | 2019-02-14 | 2019-02-14 |  | 2019-05-28 | Overhead | R16 | 2019-04-29 | 1 |  | 53 | 22 | 74 | 2019 | 2019 | R16
160973214053 | 160983214053 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-15 | 2020-12-15 | 2020-12-15 |  | 2022-08-03 | Overhead | R16 |  | 1 |  |  |  | 427 | 2020 | 2022 | R16
164424203999 | 161332203999 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-09-16 | 2020-09-16 | 2020-09-16 |  | 2021-02-17 | Overhead | R16 | 2020-10-19 | 1 |  | 24 | 88 | 111 | 2020 | 2021 | R16
162015145678 | 167459145678 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-11 | 2019-03-12 | 2019-03-12 |  | 2019-05-20 | Overhead | R16 | 2019-04-16 | 2 |  | 26 | 25 | 51 | 2019 | 2019 | R16
168099148574 | 162339148574 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-08 | 2019-04-08 | 2019-04-09 |  | 2019-08-12 | Overhead | R16 | 2019-05-24 | 1 | 2 | 34 | 57 | 91 | 2019 | 2019 | R16
160911209938 | 163639209938 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2020-11-09 | 2020-11-09 | 2020-11-09 |  | 2021-08-09 | Overhead | R16 | 2021-03-22 | 1 |  | 96 | 101 | 196 | 2020 | 2021 | R16
164041139683 | 166067139683 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-09 | 2019-01-09 | 2019-01-09 |  | 2019-02-21 | Underground | R16 | 2019-02-15 | 1 |  | 28 | 5 | 32 | 2019 | 2019 | R16
169328266031 | 167484266031 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-04-13 | 2021-12-14 | 2022-01-25 |  | 2022-05-03 | Underground | R16 | 2022-05-03 | 176 | 31 | 71 |  | 276 | 2021 | 2022 | R16
164047144471 | 165490144471 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-27 | 2019-02-28 | 2019-02-28 |  | 2019-04-30 | Overhead | R16 | 2019-04-04 | 2 |  | 26 | 19 | 45 | 2019 | 2019 | R16
168743219670 | 162368219670 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-05 | 2021-02-05 | 2021-02-05 | 2021-03-05 | 2021-10-14 | Overhead | R16 | 2021-03-05 | 1 |  | 21 | 160 | 180 | 2021 | 2021 | R16
168864198619 | 168537198619 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-07-16 | 2020-07-16 | 2020-07-29 | 2021-02-20 | 2021-02-28 | Underground | R16 | 2021-02-20 | 1 | 10 | 148 | 5 | 162 | 2020 | 2021 | R16
162051154884 | 160131154884 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG R16 ELECTRIC RELOCATION UD | Residential | 2019-05-21 | 2019-05-21 | 2019-06-10 | 2020-09-08 | 2020-12-22 | Underground | R16 | 2020-09-08 | 1 | 15 | 327 | 76 | 416 | 2019 | 2020 | R16
164195139685 | 166392139685 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-09 | 2019-01-09 | 2019-01-09 |  | 2019-02-21 | Underground | R16 | 2019-02-07 | 1 |  | 22 | 11 | 32 | 2019 | 2019 | R16
162145239526 | 168729239526 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | R16 RESD AND NON RESD US | Commercial | 2020-10-19 | 2021-06-25 | 2021-07-19 | 2022-09-01 | 2022-09-13 | Underground | R16 | 2022-09-01 | 180 | 17 | 294 | 9 | 497 | 2020 | 2022 | R16
166737213983 | 160720213983 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-14 | 2020-12-14 | 2020-12-14 | 2021-03-01 | 2021-05-17 | Overhead | R16 | 2021-03-01 | 1 |  | 56 | 56 | 111 | 2020 | 2021 | R16
164224145315 | 167391145315 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-09 | 2019-03-09 | 2019-03-09 |  | 2019-05-20 | Overhead | R16 | 2019-04-17 | 0 |  | 28 | 24 | 51 | 2019 | 2019 | R16
164225143408 | 163587143408 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-15 | 2019-02-15 | 2019-02-15 |  | 2019-04-15 | Overhead | R16 | 2019-03-26 | 1 |  | 28 | 15 | 42 | 2019 | 2019 | R16
160429289321 | 161788289321 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-11-01 | 2021-01-30 | 2022-08-16 | 2022-08-18 | 2022-10-21 | Overhead | R16 | 2022-08-18 | 65 | 402 | 3 | 47 | 515 | 2020 | 2022 | R16
169564148010 | 161452148010 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-03 | 2019-04-03 | 2019-04-03 |  | 2019-06-03 | Overhead | R16 | 2019-05-06 | 1 |  | 24 | 21 | 44 | 2019 | 2019 | R16
164267151938 | 168210151938 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-05-09 | 2019-05-09 | 2019-05-09 |  | 2023-01-10 | Overhead | R16 | 2023-01-03 | 1 |  | 954 | 6 | 959 | 2019 | 2023 | R16
167320211094 | 165915211094 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-19 | 2020-11-19 | 2020-11-19 | 2021-08-13 | 2021-10-25 | Overhead | R16 | 2021-08-13 | 1 |  | 192 | 52 | 243 | 2020 | 2021 | R16
161689204096 | 164182204096 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-17 | 2020-08-17 | 2020-09-17 | 2021-11-15 | 2021-12-21 | Underground | R16 | 2021-11-15 | 1 | 24 | 303 | 27 | 352 | 2020 | 2021 | R16
164297145321 | 161210145321 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-04 | 2019-02-04 | 2019-03-07 |  | 2019-05-20 | Underground | R16 | 2019-04-09 | 1 | 24 | 24 | 30 | 76 | 2019 | 2019 | R16
163314150285 | 165563150285 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-25 | 2019-04-25 | 2019-04-25 | 2019-07-12 | 2019-07-15 | Overhead | R16 | 2019-07-12 | 1 |  | 57 | 2 | 58 | 2019 | 2019 | R16
162785221303 | 169131221303 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-25 | 2021-02-22 | 2021-02-22 |  | 2021-10-25 | Underground | R16 | 2021-08-25 | 21 |  | 133 | 44 | 196 | 2021 | 2021 | R16
164333200322 | 163171200322 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-11 | 2020-08-11 | 2020-08-11 |  | 2020-12-14 | Overhead | R16 | 2020-09-09 | 1 |  | 22 | 69 | 90 | 2020 | 2020 | R16
163788154141 | 163808154141 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-16 | 2019-04-16 | 2019-06-03 | 2019-07-01 | 2019-07-31 | Underground | R16 | 2019-07-01 | 1 | 35 | 21 | 23 | 77 | 2019 | 2019 | R16
165450153568 | 161022153568 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-28 | 2019-05-28 | 2019-05-28 | 2019-08-04 | 2019-09-03 | Overhead | R16 | 2019-08-04 | 1 |  | 49 | 22 | 71 | 2019 | 2019 | R16
164411146748 | 169209146748 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-21 | 2019-03-21 | 2019-03-21 |  | 2020-07-02 | Overhead | R16 | 2020-05-04 | 1 |  | 293 | 44 | 336 | 2019 | 2020 | R16
162695215983 | 166002215983 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-06 | 2020-10-07 | 2020-12-30 | 2021-03-03 | 2021-03-09 | Underground | R16 | 2021-03-03 | 2 | 61 | 46 | 5 | 111 | 2020 | 2021 | R16
166369224048 | 161317224048 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2021-03-17 | 2021-03-18 | 2021-03-18 |  | 2021-11-11 | Overhead | R16 | 2021-04-19 | 2 |  | 23 | 149 | 172 | 2021 | 2021 | R16
163177206917 | 167723206917 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-14 | 2020-10-14 | 2020-10-14 |  | 2021-07-14 | Overhead | R16 | 2020-11-20 | 1 |  | 28 | 169 | 196 | 2020 | 2021 | R16
164309210391 | 164380210391 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-11-11 | 2020-11-11 | 2020-11-11 |  | 2021-07-19 | Underground | R16 | 2020-11-13 | 1 |  | 3 | 177 | 179 | 2020 | 2021 | R16
161246148910 | 162832148910 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-10 | 2019-04-10 | 2019-04-11 |  | 2019-08-12 | Underground | R16 | 2019-05-20 | 1 | 2 | 28 | 61 | 89 | 2019 | 2019 | R16
164463147422 | 162880147422 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-11 | 2019-02-11 | 2019-03-27 |  | 2019-06-03 | Overhead | R16 | 2019-05-17 | 1 | 33 | 38 | 12 | 81 | 2019 | 2019 | R16
160710211063 | 169160211063 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-10-20 | 2020-11-09 | 2020-11-17 | 2021-06-10 | 2021-08-18 | Underground | R16 | 2021-06-10 | 15 | 7 | 148 | 50 | 217 | 2020 | 2021 | R16
164488148473 | 164827148473 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-02-22 | 2019-02-25 | 2019-04-08 |  | 2020-06-09 | Underground | R16 | 2020-03-06 | 2 | 31 | 240 | 68 | 338 | 2019 | 2020 | R16
168735217667 | 166871217667 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-01-13 | 2021-01-19 | 2021-01-19 |  | 2022-01-14 | Overhead | R16 | 2021-12-09 | 5 |  | 233 | 27 | 263 | 2021 | 2022 | R16
160555202360 | 167704202360 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-31 | 2020-08-31 | 2020-08-31 |  | 2020-12-18 | Overhead | R16 | 2020-09-22 | 1 |  | 17 | 64 | 80 | 2020 | 2020 | R16
163165213206 | 169530213206 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-08 | 2020-12-08 | 2020-12-08 | 2021-03-27 | 2021-10-27 | Overhead | R16 | 2021-03-27 | 1 |  | 79 | 153 | 232 | 2020 | 2021 | R16
165842229698 | 162574229698 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-09-22 | 2021-03-29 | 2021-05-06 |  | 2021-08-31 | Underground | R16 |  | 135 | 29 |  |  | 246 | 2020 | 2021 | R16
164648142979 | 163462142979 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-14 | 2019-02-14 | 2019-02-14 |  | 2019-04-15 | Underground | R16 | 2019-03-26 | 1 |  | 29 | 15 | 43 | 2019 | 2019 | R16
164924212931 | 168878212931 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-05 | 2020-12-05 | 2020-12-05 | 2021-03-11 | 2021-03-12 | Overhead | R16 | 2021-03-11 | 0 |  | 69 | 2 | 70 | 2020 | 2021 | R16
163769203043 | 169125203043 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-08 | 2020-09-08 | 2020-09-08 |  | 2021-01-22 | Overhead | R16 | 2020-10-15 | 1 |  | 28 | 72 | 99 | 2020 | 2021 | R16
169506177173 | 161017177173 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Commercial | 2019-05-28 | 2019-05-31 | 2020-01-16 | 2020-04-15 | 2020-05-27 | Underground | R16 | 2020-04-15 | 4 | 165 | 65 | 31 | 262 | 2019 | 2020 | R16
164694145788 | 161111145788 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-04 | 2019-02-04 | 2019-03-11 |  | 2019-04-15 | Underground | R16 | 2019-03-28 | 1 | 26 | 14 | 13 | 51 | 2019 | 2019 | R16
164696143257 | 167171143257 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-14 | 2019-01-14 | 2019-02-14 |  | 2019-04-24 | Underground | R16 | 2019-03-20 | 1 | 24 | 25 | 26 | 73 | 2019 | 2019 | R16
169249231266 | 168123231266 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-03-03 | 2021-03-03 | 2021-05-18 |  | 2021-12-17 | Underground | R16 |  | 1 | 55 |  |  | 208 | 2021 | 2021 | R16
164724147828 | 169054147828 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-20 | 2019-04-01 | 2019-04-01 |  | 2019-04-25 | Overhead | R16 | 2019-04-02 | 9 |  | 2 | 18 | 27 | 2019 | 2019 | R16
167457217411 | 167281217411 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-14 | 2021-01-14 | 2021-01-14 | 2023-03-02 | 2023-03-07 | Overhead | R16 | 2023-03-02 | 1 |  | 556 | 4 | 559 | 2021 | 2023 | R16
164725146056 | 168234146056 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-14 | 2019-03-14 | 2019-03-14 |  | 2021-11-17 | Overhead | R16 | 2019-08-29 | 1 |  | 121 | 580 | 700 | 2019 | 2021 | R16
164733139870 | 166574139870 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-10 | 2019-01-10 | 2019-01-10 |  | 2019-03-11 | Overhead | R16 | 2019-02-19 | 1 |  | 29 | 15 | 43 | 2019 | 2019 | R16
162499213541 | 169944213541 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-10 | 2020-12-10 | 2020-12-10 | 2021-05-04 | 2021-08-11 | Overhead | R16 | 2021-05-04 | 1 |  | 104 | 72 | 175 | 2020 | 2021 | R16
160752145782 | 164218145782 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-20 | 2019-02-20 | 2019-03-11 |  | 2019-05-28 | Underground | R16 | 2019-04-22 | 1 | 14 | 31 | 27 | 70 | 2019 | 2019 | R16
162008224285 | 162380224285 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-07-09 | 2021-08-23 | Overhead | R16 | 2021-07-09 | 1 |  | 80 | 32 | 111 | 2021 | 2021 | R16
164782147757 | 161055147757 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-01 | 2019-04-01 | 2019-04-01 |  | 2019-06-03 | Overhead | R16 | 2019-05-08 | 1 |  | 28 | 19 | 46 | 2019 | 2019 | R16
167783200350 | 161817200350 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-04 | 2020-08-11 | 2020-08-11 | 2020-09-30 | 2021-01-08 | Underground | R16 | 2020-09-30 | 6 |  | 37 | 73 | 114 | 2020 | 2021 | R16
164789144474 | 165612144474 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-28 | 2019-02-28 | 2019-02-28 |  | 2019-06-03 | Underground | R16 | 2019-05-14 | 1 |  | 54 | 15 | 68 | 2019 | 2019 | R16
165574140041 | 166787140041 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-11 | 2019-01-11 | 2019-01-11 |  | 2019-05-20 | Overhead | R16 | 2019-04-12 | 1 |  | 66 | 27 | 92 | 2019 | 2019 | R16
168364148529 | 162204148529 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-08 | 2019-04-08 | 2019-04-08 |  | 2019-06-03 | Overhead | R16 | 2019-05-14 | 1 |  | 27 | 15 | 41 | 2019 | 2019 | R16
165202207219 | 168195207219 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-15 | 2020-10-15 | 2020-10-15 |  | 2021-05-06 | Overhead | R16 | 2021-02-18 | 1 |  | 91 | 56 | 146 | 2020 | 2021 | R16
164833143638 | 164195143638 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-20 | 2019-02-20 | 2019-02-20 |  | 2019-05-20 | Overhead | R16 | 2019-04-10 | 1 |  | 36 | 29 | 64 | 2019 | 2019 | R16
166973209431 | 166138209431 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-24 | 2020-08-24 | 2020-11-03 |  | 2021-04-20 | Underground | R16 | 2021-01-15 | 1 | 52 | 54 | 68 | 172 | 2020 | 2021 | R16
163345228889 | 164764228889 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-31 | 2021-04-20 | 2021-04-30 | 2021-06-04 | 2021-08-30 | Underground | R16 | 2021-06-04 | 15 | 9 | 26 | 62 | 109 | 2021 | 2021 | R16
163753153210 | 160463153210 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-22 | 2019-05-23 | 2019-05-23 |  | 2023-06-08 | Overhead | R16 | 2019-07-09 | 2 |  | 34 | 1023 | 1057 | 2019 | 2023 | R16
165722218745 | 160242218745 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-27 | 2021-01-27 | 2021-01-27 |  | 2021-11-11 | Overhead | R16 | 2021-05-17 | 1 |  | 79 | 129 | 207 | 2021 | 2021 | R16
168385207912 | 169876207912 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-22 | 2020-10-22 | 2020-10-22 | 2020-11-04 | 2021-04-07 | Overhead | R16 | 2020-11-04 | 1 |  | 10 | 111 | 120 | 2020 | 2021 | R16
165055146150 | 166372146150 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-05 | 2019-03-15 | 2019-03-15 |  | 2019-04-15 | Overhead | R16 | 2019-03-28 | 9 |  | 10 | 13 | 30 | 2019 | 2019 | R16
166833226349 | 162493226349 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-11-03 | 2021-04-05 | 2021-04-09 | 2021-05-12 | 2021-10-06 | Underground | R16 | 2021-05-12 | 110 | 5 | 24 | 106 | 242 | 2020 | 2021 | R16
165282151464 | 167377151464 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-05-06 | 2019-05-06 | 2019-05-06 |  | 2019-09-26 | Underground | R16 | 2019-09-17 | 1 |  | 97 | 8 | 104 | 2019 | 2019 | R16
169350151031 | 166755151031 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-02 | 2019-05-02 | 2019-05-02 |  | 2019-10-11 | Overhead | R16 | 2019-09-30 | 1 |  | 108 | 10 | 117 | 2019 | 2019 | R16
166421155866 | 166445155866 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-30 | 2019-04-30 | 2019-06-20 | 2019-09-27 | 2019-09-30 | Underground | R16 | 2019-09-27 | 1 | 38 | 72 | 2 | 110 | 2019 | 2019 | R16
164367142373 | 161816142373 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-06 | 2019-02-06 | 2019-02-06 | 2019-02-25 | 2019-02-26 | Overhead | R16 | 2019-02-25 | 1 |  | 14 | 2 | 15 | 2019 | 2019 | R16
162575149994 | 164998149994 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-23 | 2019-04-23 | 2019-04-23 |  | 2019-08-12 | Overhead | R16 | 2019-05-21 | 1 |  | 21 | 60 | 80 | 2019 | 2019 | R16
163203232682 | 169281232682 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-07-21 | 2020-10-23 | 2021-05-27 | 2021-07-04 | 2023-01-27 | Underground | R16 | 2021-07-04 | 69 | 155 | 27 | 410 | 659 | 2020 | 2023 | R16
165286141600 | 169310141600 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-28 | 2019-01-28 | 2019-01-28 |  | 2019-08-12 | Overhead | R16 | 2019-06-03 | 1 |  | 91 | 51 | 141 | 2019 | 2019 | R16
169810154214 | 162132154214 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-04 | 2019-06-04 | 2019-06-04 | 2019-08-28 | 2020-06-09 | Overhead | R16 | 2019-08-28 | 1 |  | 62 | 205 | 266 | 2019 | 2020 | R16
160730156359 | 160666156359 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-23 | 2019-05-23 | 2019-06-26 | 2019-08-20 | 2019-08-21 | Underground | R16 | 2019-08-20 | 1 | 25 | 40 | 2 | 65 | 2019 | 2019 | R16
168664202762 | 165297202762 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-08-19 | 2020-09-03 | 2020-09-03 | 2023-05-26 | 2023-08-21 | Underground | R16 | 2023-05-26 | 12 |  | 712 | 62 | 784 | 2020 | 2023 | R16
168053153705 | 161354153705 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-29 | 2019-05-29 | 2019-05-29 | 2019-09-03 | 2019-11-14 | Overhead | R16 | 2019-09-03 | 1 |  | 70 | 53 | 122 | 2019 | 2019 | R16
165297143118 | 163133143118 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-12 | 2019-02-12 | 2019-02-12 |  | 2019-04-15 | Underground | R16 | 2019-03-05 | 1 |  | 16 | 30 | 45 | 2019 | 2019 | R16
165884236522 | 165756236522 | NON-RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Commercial | 2020-11-19 | 2020-11-19 | 2021-06-24 | 2023-03-07 | 2023-04-05 | Underground | R16 | 2023-03-07 | 1 | 156 | 444 | 22 | 620 | 2020 | 2023 | R16
165307145776 | 164612145776 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-22 | 2019-03-11 | 2019-03-11 |  | 2019-04-25 | Overhead | R16 | 2019-04-01 | 12 |  | 16 | 19 | 45 | 2019 | 2019 | R16
165309143989 | 167455143989 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-15 | 2019-01-15 | 2019-02-22 |  | 2019-06-03 | Underground | R16 |  | 1 | 29 |  |  | 100 | 2019 | 2019 | R16
164824223169 | 166656223169 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-13 | 2021-01-20 | 2021-03-10 |  | 2021-11-10 | Underground | R16 | 2021-10-18 | 6 | 36 | 159 | 18 | 216 | 2021 | 2021 | R16
160873200028 | 162768200028 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-09 | 2020-08-09 | 2020-08-09 |  | 2020-10-06 | Overhead | R16 | 2020-08-27 | 0 |  | 14 | 29 | 42 | 2020 | 2020 | R16
166754154707 | 162396154707 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-06-05 | 2019-06-07 | 2019-06-07 |  | 2019-08-26 | Underground | R16 | 2019-07-16 | 3 |  | 28 | 30 | 59 | 2019 | 2019 | R16
165339145065 | 165960145065 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-03 | 2019-03-03 | 2019-03-05 |  | 2019-04-15 | Underground | R16 |  | 0 | 2 |  |  | 31 | 2019 | 2019 | R16
166165200998 | 164548200998 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-19 | 2020-08-19 | 2020-08-19 |  | 2020-11-02 | Overhead | R16 | 2020-09-02 | 1 |  | 11 | 44 | 54 | 2020 | 2020 | R16
163652207216 | 165989207216 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-10-06 | 2020-10-07 | 2020-10-15 | 2020-12-01 | 2021-03-27 | Underground | R16 | 2020-12-01 | 2 | 7 | 34 | 84 | 124 | 2020 | 2021 | R16
165582141601 | 169233141601 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-28 | 2019-01-28 | 2019-01-28 |  | 2019-02-19 | Overhead | R16 | 2019-02-04 | 1 |  | 6 | 12 | 17 | 2019 | 2019 | R16
161611226021 | 164501226021 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-30 | 2021-03-30 | 2021-04-06 |  | 2021-11-03 | Overhead | R16 | 2021-06-23 | 1 | 6 | 57 | 96 | 157 | 2021 | 2021 | R16
162249158564 | 162761158564 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-07 | 2019-06-07 | 2019-07-22 |  | 2022-08-02 | Underground | R16 |  | 1 | 32 |  |  | 823 | 2019 | 2022 | R16
163448145442 | 167216145442 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-08 | 2019-03-08 | 2019-03-08 |  | 2019-05-20 | Underground | R16 | 2019-04-08 | 1 |  | 22 | 31 | 52 | 2019 | 2019 | R16
162141207794 | 168400207794 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-15 | 2020-10-21 | 2020-10-21 |  | 2021-07-22 | Overhead | R16 | 2020-11-10 | 5 |  | 15 | 183 | 201 | 2020 | 2021 | R16
165671143164 | 163057143164 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-02-13 | 2019-02-13 | 2019-02-13 |  | 2019-03-11 | Overhead | R16 | 2019-02-21 | 1 |  | 7 | 13 | 19 | 2019 | 2019 | R16
164833160281 | 167154160281 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-05-03 | 2019-05-03 | 2019-08-05 | 2019-09-13 | 2020-01-10 | Underground | R16 | 2019-09-13 | 1 | 67 | 30 | 86 | 181 | 2019 | 2020 | R16
165676152503 | 169076152503 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-15 | 2019-05-15 | 2019-05-15 |  | 2021-12-10 | Overhead | R16 | 2019-08-19 | 1 |  | 69 | 605 | 673 | 2019 | 2021 | R16
162055156904 | 162875156904 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-07 | 2019-06-07 | 2019-07-01 |  | 2019-10-09 | Underground | R16 | 2019-09-25 | 1 | 17 | 63 | 11 | 89 | 2019 | 2019 | R16
163481150081 | 165061150081 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-23 | 2019-04-23 | 2019-04-23 | 2019-07-21 | 2019-07-24 | Overhead | R16 | 2019-07-21 | 1 |  | 64 | 3 | 67 | 2019 | 2019 | R16
165689143964 | 164653143964 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-21 | 2019-02-21 | 2019-02-21 |  | 2019-04-15 | Overhead | R16 | 2019-03-11 | 1 |  | 13 | 26 | 38 | 2019 | 2019 | R16
165697145177 | 165639145177 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-03-01 | 2019-03-01 | 2019-03-07 |  | 2019-06-19 | Overhead | R16 | 2019-06-10 | 1 | 5 | 68 | 8 | 79 | 2019 | 2019 | R16
165704142248 | 167900142248 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-17 | 2019-01-17 | 2019-02-04 |  | 2019-04-30 | Underground | R16 | 2019-04-04 | 1 | 13 | 44 | 19 | 74 | 2019 | 2019 | R16
163076147521 | 160349147521 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-28 | 2019-03-28 | 2019-03-28 | 2019-04-17 | 2019-05-28 | Overhead | R16 | 2019-04-17 | 1 |  | 15 | 30 | 44 | 2019 | 2019 | R16
161406202119 | 167553202119 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-28 | 2020-08-29 | 2020-08-29 | 2020-09-24 | 2021-02-17 | Overhead | R16 | 2020-09-24 | 1 |  | 19 | 105 | 124 | 2020 | 2021 | R16
165725158594 | 167572158594 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-06 | 2019-07-18 | 2019-07-24 |  | 2020-06-09 | Overhead | R16 | 2020-04-08 | 54 | 5 | 186 | 45 | 287 | 2019 | 2020 | R16
164505214352 | 161412214352 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-17 | 2020-12-17 | 2020-12-17 | 2020-12-28 | 2021-04-29 | Underground | R16 | 2020-12-28 | 1 |  | 8 | 89 | 96 | 2020 | 2021 | R16
165774152202 | 165823152202 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-08 | 2019-01-08 | 2019-05-13 |  | 2019-08-12 | Underground | R16 | 2019-06-13 | 1 | 90 | 24 | 43 | 155 | 2019 | 2019 | R16
165809142423 | 161606142423 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-06 | 2019-02-06 | 2019-02-06 |  | 2019-04-15 | Overhead | R16 | 2019-03-28 | 1 |  | 37 | 13 | 49 | 2019 | 2019 | R16
160727209823 | 162980209823 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2020-11-05 | 2020-11-05 | 2020-11-05 | 2021-06-28 | 2022-03-09 | Overhead | R16 | 2021-06-28 | 1 |  | 168 | 183 | 350 | 2020 | 2022 | R16
169492144979 | 167140144979 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Commercial | 2019-01-14 | 2019-02-21 | 2019-03-05 | 2019-05-21 | 2019-10-26 | Underground | R16 | 2019-05-21 | 29 | 9 | 56 | 114 | 205 | 2019 | 2019 | R16
167895223916 | 162824223916 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-02-08 | 2021-03-05 | 2021-03-17 |  | 2021-11-08 | Overhead | R16 | 2021-04-22 | 20 | 9 | 27 | 143 | 196 | 2021 | 2021 | R16
165855145349 | 167155145349 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-08 | 2019-03-08 | 2019-03-08 |  | 2019-05-20 | Overhead | R16 | 2019-04-16 | 1 |  | 28 | 25 | 52 | 2019 | 2019 | R16
168943246994 | 168906246994 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-10-19 | 2020-10-19 | 2021-09-09 | 2021-11-12 | 2022-02-08 | Underground | R16 | 2021-11-12 | 1 | 234 | 47 | 63 | 342 | 2020 | 2022 | R16
167331221375 | 163779221375 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-02-11 | 2021-02-23 | 2021-02-23 |  | 2021-08-11 | Overhead | R16 | 2021-06-30 | 9 |  | 92 | 31 | 130 | 2021 | 2021 | R16
165858160157 | 168608160157 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-05-13 | 2019-05-23 | 2019-08-05 |  | 2019-12-04 | Underground | R16 |  | 9 | 53 |  |  | 148 | 2019 | 2019 | R16
165862144771 | 166076144771 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-04 | 2019-03-04 | 2019-03-04 |  | 2019-04-30 | Overhead | R16 | 2019-04-04 | 1 |  | 24 | 19 | 42 | 2019 | 2019 | R16
166345221592 | 166582221592 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-25 | 2021-02-25 | 2021-02-25 | 2021-05-27 | 2021-06-21 | Overhead | R16 | 2021-05-27 | 1 |  | 66 | 18 | 83 | 2021 | 2021 | R16
165871148900 | 160743148900 | AGRICULTURAL | R16 RESD AND NON RESD US | Residential Subdivision | 2019-01-31 | 2019-02-05 | 2019-04-11 |  | 2019-09-10 | Underground | R16 |  | 4 | 48 |  |  | 159 | 2019 | 2019 | R16
169888220662 | 162670220662 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-06 | 2021-02-06 | 2021-02-16 | 2021-04-06 | 2021-04-09 | Overhead | R16 | 2021-04-06 | 0 | 7 | 36 | 4 | 45 | 2021 | 2021 | R16
166331144235 | 165228144235 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-02-26 | 2019-02-26 | 2019-02-26 |  | 2019-06-03 | Underground | R16 | 2019-05-16 | 1 |  | 58 | 13 | 70 | 2019 | 2019 | R16
165690153320 | 160577153320 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-23 | 2019-05-23 | 2019-05-23 |  | 2019-11-01 | Overhead | R16 | 2019-06-25 | 1 |  | 24 | 94 | 117 | 2019 | 2019 | R16
167853229811 | 162930229811 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-23 | 2021-03-29 | 2021-05-06 |  | 2021-10-25 | Underground | R16 | 2021-07-28 | 5 | 29 | 60 | 64 | 155 | 2021 | 2021 | R16
169082147232 | 169921147232 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-25 | 2019-03-25 | 2019-03-25 |  | 2019-05-28 | Underground | R16 | 2019-04-30 | 1 |  | 27 | 21 | 47 | 2019 | 2019 | R16
166053194161 | 160583194161 | NON-RESIDENTIAL - SMALL RETAIL | R16 RESD AND NON RESD US | Residential | 2019-03-28 | 2019-04-04 | 2020-06-12 |  | 2022-10-29 | Underground | R16 |  | 6 | 312 |  |  | 937 | 2019 | 2022 | R16
168336228108 | 162591228108 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-22 | 2021-04-23 | 2021-04-23 | 2021-06-11 | 2021-11-03 | Overhead | R16 | 2021-06-11 | 25 |  | 36 | 104 | 163 | 2021 | 2021 | R16
166055140202 | 165788140202 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-08 | 2019-01-08 | 2019-01-14 |  | 2019-03-11 | Underground | R16 | 2019-02-19 | 1 | 5 | 27 | 15 | 45 | 2019 | 2019 | R16
166101161247 | 165334161247 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-13 | 2019-08-13 | 2019-08-14 |  | 2019-10-28 | Underground | R16 | 2019-10-15 | 1 | 2 | 45 | 10 | 55 | 2019 | 2019 | R16
167784139840 | 166385139840 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-10 | 2019-01-10 | 2019-01-10 | 2019-01-24 | 2019-01-24 | Overhead | R16 | 2019-01-24 | 1 |  | 11 |  | 11 | 2019 | 2019 | R16
163742227060 | 168253227060 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-15 | 2021-04-15 | 2021-04-15 |  | 2021-09-13 | Overhead | R16 | 2021-08-18 | 1 |  | 90 | 19 | 108 | 2021 | 2021 | R16
166133145185 | 161086145185 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-04 | 2019-02-04 | 2019-03-06 |  | 2019-05-20 | Underground | R16 | 2019-04-10 | 1 | 23 | 26 | 29 | 76 | 2019 | 2019 | R16
169565206388 | 165986206388 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-10-05 | 2020-10-06 | 2020-10-06 | 2020-10-09 | 2022-08-03 | Underground | R16 | 2020-10-09 | 2 |  | 4 | 474 | 478 | 2020 | 2022 | R16
166141144515 | 162893144515 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH R16 SVC RELOCATION OD | Commercial | 2019-02-11 | 2019-02-11 | 2019-03-01 |  | 2019-09-06 | Overhead | R16 | 2019-09-01 | 1 | 15 | 131 | 5 | 150 | 2019 | 2019 | R16
162868208615 | 169510208615 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-21 | 2020-10-28 | 2020-10-28 |  | 2021-04-16 | Underground | R16 | 2021-01-05 | 6 |  | 50 | 74 | 128 | 2020 | 2021 | R16
164899224106 | 161410224106 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2021-02-01 | 2021-02-01 | 2021-03-18 |  | 2022-05-03 | Underground | R16 |  | 1 | 34 |  |  | 327 | 2021 | 2022 | R16
169764230345 | 164466230345 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-06-01 | 2021-11-04 | Overhead | R16 | 2021-06-01 | 1 |  | 16 | 113 | 128 | 2021 | 2021 | R16
164076147549 | 160620147549 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-03-28 | 2019-03-28 | 2019-03-29 | 2020-01-14 | 2020-01-15 | Underground | R16 | 2020-01-14 | 1 | 2 | 208 | 2 | 210 | 2019 | 2020 | R16
169410229553 | 163010229553 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-05 | 2021-05-05 | 2021-05-05 |  | 2021-10-25 | Overhead | R16 | 2021-09-20 | 1 |  | 99 | 26 | 124 | 2021 | 2021 | R16
166219145189 | 161447145189 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-05 | 2019-02-05 | 2019-03-06 |  | 2019-10-30 | Underground | R16 | 2019-10-22 | 1 | 22 | 165 | 7 | 192 | 2019 | 2019 | R16
167645230516 | 160924230516 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-27 | 2021-04-28 | 2021-05-13 |  | 2021-10-27 | Underground | R16 | 2021-06-21 | 2 | 12 | 28 | 93 | 132 | 2021 | 2021 | R16
166337150247 | 165313150247 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-24 | 2019-04-24 | 2019-04-24 |  | 2019-08-12 | Overhead | R16 | 2019-05-22 | 1 |  | 21 | 59 | 79 | 2019 | 2019 | R16
163019218930 | 166091218930 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-11 | 2021-01-11 | 2021-01-29 | 2021-07-08 | 2021-07-09 | Underground | R16 | 2021-07-08 | 1 | 15 | 115 | 2 | 130 | 2021 | 2021 | R16
166358141329 | 169039141329 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-26 | 2019-01-26 | 2019-01-26 |  | 2019-06-03 | Overhead | R16 | 2019-05-08 | 0 |  | 73 | 19 | 91 | 2019 | 2019 | R16
167149207556 | 169173207556 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-20 | 2020-10-20 | 2020-10-20 | 2020-12-23 | 2021-04-23 | Overhead | R16 | 2020-12-23 | 1 |  | 47 | 88 | 134 | 2020 | 2021 | R16
169319149801 | 164130149801 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-17 | 2019-04-17 | 2019-04-19 |  | 2019-06-03 | Underground | R16 | 2019-05-10 | 1 | 3 | 16 | 17 | 34 | 2019 | 2019 | R16
166363144627 | 165632144627 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-28 | 2019-02-28 | 2019-02-28 |  | 2019-04-15 | Overhead | R16 | 2019-03-29 | 1 |  | 22 | 12 | 33 | 2019 | 2019 | R16
163065228446 | 166863228446 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2021-04-09 | 2021-04-09 | 2021-04-26 |  | 2021-11-09 | Overhead | R16 |  | 1 | 12 |  |  | 153 | 2021 | 2021 | R16
163396211161 | 165555211161 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-11-18 | 2020-11-18 | 2020-11-18 |  | 2021-04-13 | Overhead | R16 | 2020-12-07 | 1 |  | 14 | 92 | 105 | 2020 | 2021 | R16
166449143109 | 162974143109 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-12 | 2019-02-12 | 2019-02-12 |  | 2019-04-25 | Underground | R16 | 2019-03-21 | 1 |  | 28 | 26 | 53 | 2019 | 2019 | R16
162345225810 | 163691225810 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-11 | 2021-02-11 | 2021-04-05 |  | 2022-07-22 | Underground | R16 | 2022-07-18 | 1 | 38 | 336 | 5 | 377 | 2021 | 2022 | R16
163962143701 | 163964143701 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-02-19 | 2019-02-19 | 2019-02-19 |  | 2022-10-29 | Underground | R16 |  | 1 |  |  |  | 964 | 2019 | 2022 | R16
166475147218 | 164487147218 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-21 | 2019-02-21 | 2019-03-28 |  | 2019-05-20 | Underground | R16 | 2019-04-15 | 1 | 26 | 13 | 26 | 63 | 2019 | 2019 | R16
165790212386 | 167847212386 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-01 | 2020-12-01 | 2020-12-01 | 2021-01-08 | 2021-04-20 | Overhead | R16 | 2021-01-08 | 1 |  | 29 | 73 | 101 | 2020 | 2021 | R16
162389230053 | 167983230053 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-04-14 | 2021-04-14 | 2021-05-10 | 2021-08-02 | 2021-09-01 | Overhead | R16 | 2021-08-02 | 1 | 19 | 61 | 23 | 101 | 2021 | 2021 | R16
162700209825 | 162962209825 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-09-24 | 2020-09-24 | 2020-11-05 | 2021-11-29 | 2022-01-13 | Underground | R16 | 2021-11-29 | 1 | 31 | 278 | 34 | 341 | 2020 | 2022 | R16
169360209387 | 160890209387 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-10-27 | 2020-11-02 | 2020-11-02 |  | 2021-11-04 | Underground | R16 | 2021-04-06 | 5 |  | 112 | 153 | 268 | 2020 | 2021 | R16
163344217604 | 164993217604 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-05 | 2021-01-05 | 2021-01-19 |  | 2021-08-11 | Underground | R16 | 2021-03-24 | 1 | 11 | 47 | 101 | 157 | 2021 | 2021 | R16
164878218696 | 164976218696 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-16 | 2020-11-16 | 2021-01-27 |  | 2021-11-05 | Underground | R16 | 2021-05-10 | 1 | 53 | 74 | 130 | 255 | 2020 | 2021 | R16
166513144577 | 165175144577 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-26 | 2019-02-26 | 2019-03-01 |  | 2019-04-24 | Overhead | R16 | 2019-03-20 | 1 | 4 | 14 | 26 | 42 | 2019 | 2019 | R16
167401223749 | 160854223749 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-16 | 2021-03-16 | 2021-03-16 | 2021-04-26 | 2021-11-08 | Overhead | R16 | 2021-04-26 | 1 |  | 30 | 141 | 170 | 2021 | 2021 | R16
168586215652 | 162991215652 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-22 | 2020-12-22 | 2020-12-28 |  | 2021-08-02 | Underground | R16 | 2021-03-29 | 1 | 5 | 66 | 91 | 160 | 2020 | 2021 | R16
162332202235 | 165168202235 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-19 | 2020-08-31 | 2020-08-31 |  | 2021-01-08 | Overhead | R16 | 2020-10-07 | 9 |  | 28 | 68 | 103 | 2020 | 2021 | R16
166562144767 | 165977144767 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-04 | 2019-03-04 | 2019-03-04 |  | 2019-04-25 | Overhead | R16 | 2019-04-02 | 1 |  | 22 | 18 | 39 | 2019 | 2019 | R16
165859148505 | 169700148505 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-24 | 2019-03-24 | 2019-04-08 |  | 2019-05-28 | Underground | R16 | 2019-05-01 | 0 | 11 | 18 | 20 | 47 | 2019 | 2019 | R16
166569200569 | 163994200569 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2020-06-23 | 2020-07-10 | 2020-08-13 |  | 2021-11-05 | Underground | R16 |  | 14 | 25 |  |  | 359 | 2020 | 2021 | R16
168346144605 | 161457144605 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-05 | 2019-02-05 | 2019-02-28 | 2019-05-14 | 2019-05-16 | Underground | R16 | 2019-05-14 | 1 | 18 | 54 | 3 | 73 | 2019 | 2019 | R16
166581144624 | 165627144624 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-28 | 2019-02-28 | 2019-02-28 |  | 2019-08-26 | Overhead | R16 | 2019-07-09 | 1 |  | 94 | 35 | 128 | 2019 | 2019 | R16
167366143544 | 162149143544 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-07 | 2019-02-07 | 2019-02-19 |  | 2019-04-15 | Underground | R16 | 2019-03-27 | 1 | 9 | 27 | 14 | 48 | 2019 | 2019 | R16
166595143115 | 162896143115 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-12 | 2019-02-12 | 2019-02-12 |  | 2019-05-28 | Underground | R16 | 2019-04-22 | 1 |  | 50 | 27 | 76 | 2019 | 2019 | R16
166505228069 | 160063228069 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-23 | 2021-04-23 | 2021-04-23 | 2021-06-28 | 2021-07-15 | Overhead | R16 | 2021-06-28 | 1 |  | 47 | 14 | 60 | 2021 | 2021 | R16
164021212898 | 169113212898 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-07 | 2020-12-07 | 2020-12-07 |  | 2021-11-05 | Overhead | R16 | 2021-05-11 | 1 |  | 112 | 129 | 240 | 2020 | 2021 | R16
166669146564 | 168905146564 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-19 | 2019-03-19 | 2019-03-19 |  | 2019-05-28 | Overhead | R16 | 2019-04-22 | 1 |  | 25 | 27 | 51 | 2019 | 2019 | R16
164003232043 | 169143232043 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2021-05-22 | 2021-05-22 | 2021-05-22 | 2022-01-20 | 2022-01-21 | Overhead | R16 | 2022-01-20 | 0 |  | 174 | 2 | 175 | 2021 | 2022 | R16
168296221180 | 161216221180 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-01 | 2021-02-01 | 2021-02-19 |  | 2021-11-05 | Underground | R16 | 2021-05-04 | 1 | 15 | 53 | 134 | 200 | 2021 | 2021 | R16
166755206723 | 166961206723 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-09 | 2020-10-09 | 2020-10-09 | 2021-02-25 | 2021-02-26 | Overhead | R16 | 2021-02-25 | 1 |  | 100 | 2 | 101 | 2020 | 2021 | R16
166691147389 | 160289147389 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-27 | 2019-03-27 | 2019-03-27 |  | 2019-05-20 | Overhead | R16 | 2019-04-08 | 1 |  | 9 | 31 | 39 | 2019 | 2019 | R16
161276228716 | 166137228716 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-24 | 2021-02-24 | 2021-04-29 |  | 2022-05-12 | Underground | R16 | 2022-04-20 | 1 | 47 | 255 | 17 | 317 | 2021 | 2022 | R16
166502222754 | 168895222754 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-08 | 2021-03-08 | 2021-03-08 |  | 2021-11-05 | Overhead | R16 | 2021-05-05 | 1 |  | 43 | 133 | 175 | 2021 | 2021 | R16
168215220309 | 163890220309 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-11 | 2021-02-11 | 2021-02-11 |  | 2021-11-08 | Overhead | R16 |  | 1 |  |  |  | 193 | 2021 | 2021 | R16
161143221517 | 167738221517 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-02 | 2020-12-15 | 2021-02-25 |  | 2021-11-13 | Underground | R16 | 2021-06-07 | 10 | 53 | 73 | 115 | 248 | 2020 | 2021 | R16
164976233032 | 161249233032 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-06-01 | 2021-06-01 | 2021-06-02 |  | 2021-11-03 | Overhead | R16 |  | 1 | 2 |  |  | 112 | 2021 | 2021 | R16
166881147165 | 169159147165 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-21 | 2019-03-21 | 2019-03-25 |  | 2019-05-20 | Overhead | R16 |  | 1 | 3 |  |  | 43 | 2019 | 2019 | R16
167142213688 | 169497213688 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2020-12-08 | 2020-12-08 | 2020-12-11 |  | 2022-01-14 | Underground | R16 |  | 1 | 4 |  |  | 289 | 2020 | 2022 | R16
166895144886 | 166082144886 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-04 | 2019-03-04 | 2019-03-04 |  | 2019-04-26 | Overhead | R16 | 2019-04-03 | 1 |  | 23 | 18 | 40 | 2019 | 2019 | R16
164119198488 | 160323198488 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-07-27 | 2020-07-27 | 2020-07-27 |  | 2020-10-06 | Overhead | R16 | 2020-08-11 | 1 |  | 12 | 41 | 52 | 2020 | 2020 | R16
165898231524 | 168474231524 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-19 | 2021-05-19 | 2021-05-19 |  | 2021-09-01 | Overhead | R16 | 2021-08-09 | 1 |  | 59 | 18 | 76 | 2021 | 2021 | R16
166904151888 | 167994151888 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-05-08 | 2019-05-08 | 2019-05-09 |  | 2020-06-09 | Overhead | R16 |  | 1 | 2 |  |  | 285 | 2019 | 2020 | R16
162839212630 | 168400212630 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-03 | 2020-12-03 | 2020-12-03 | 2021-06-02 | 2021-08-26 | Underground | R16 | 2021-06-02 | 1 |  | 130 | 62 | 191 | 2020 | 2021 | R16
166920143018 | 162758143018 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-11 | 2019-02-13 | 2019-02-13 |  | 2019-04-30 | Overhead | R16 | 2019-04-04 | 3 |  | 37 | 19 | 57 | 2019 | 2019 | R16
160841238822 | 165810238822 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-17 | 2021-07-13 | 2021-07-13 | 2021-07-19 | 2021-07-29 | Underground | R16 | 2021-07-19 | 42 |  | 5 | 9 | 54 | 2021 | 2021 | R16
166947140942 | 167578140942 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-16 | 2019-01-18 | 2019-01-22 |  | 2019-03-20 | Underground | R16 |  | 3 | 3 |  |  | 46 | 2019 | 2019 | R16
161702154360 | 161634154360 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2019-02-05 | 2019-02-05 | 2019-06-04 |  | 2022-08-29 | Underground | R16 |  | 1 | 86 |  |  | 930 | 2019 | 2022 | R16
168679147462 | 169255147462 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-21 | 2019-03-28 | 2019-03-28 | 2019-04-17 | 2019-05-28 | Underground | R16 | 2019-04-17 | 6 |  | 15 | 30 | 49 | 2019 | 2019 | R16
167047145031 | 166544145031 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-06 | 2019-03-06 | 2019-03-06 |  | 2019-04-30 | Overhead | R16 | 2019-04-05 | 1 |  | 23 | 18 | 40 | 2019 | 2019 | R16
167080142521 | 161614142521 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-06 | 2019-02-06 | 2019-02-06 |  | 2019-03-11 | Overhead | R16 | 2019-02-22 | 1 |  | 13 | 12 | 24 | 2019 | 2019 | R16
161061254201 | 165163254201 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2021-05-13 | 2021-05-13 | 2021-10-28 | 2022-10-05 | 2022-10-05 | Underground | R16 | 2022-10-05 | 1 | 121 | 245 |  | 365 | 2021 | 2022 | R16
167094198685 | 163271198685 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-13 | 2019-02-13 | 2020-07-27 |  | 2021-07-24 | Underground | R16 | 2020-11-04 | 1 | 379 | 73 | 188 | 638 | 2019 | 2021 | R16
165115225548 | 165763225548 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-22 | 2021-04-01 | 2021-04-01 | 2021-05-17 | 2021-11-08 | Overhead | R16 | 2021-05-17 | 29 |  | 33 | 126 | 186 | 2021 | 2021 | R16
167141224209 | 166506224209 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2020-08-25 | 2020-11-16 | 2021-03-19 | 2023-11-10 | 2023-11-28 | Underground | R16 | 2023-11-10 | 60 | 90 | 691 | 13 | 851 | 2020 | 2023 | R16
166216211507 | 166116211507 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2020-11-20 | 2020-11-20 | 2020-11-20 |  | 2023-08-18 | Underground | R16 | 2023-05-10 | 1 |  | 644 | 73 | 716 | 2020 | 2023 | R16
167102182380 | 168854182380 | FOREIGN UTILITY | ELEC OH MISC SVC OS | Commercial | 2019-12-16 | 2019-12-17 | 2020-02-28 |  | 2023-11-03 | Overhead | R16 |  | 2 | 54 |  |  | 1015 | 2019 | 2023 | R16
160469148608 | 162257148608 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-08 | 2019-04-08 | 2019-04-08 |  | 2021-01-22 | Underground | R16 | 2020-10-15 | 1 |  | 399 | 72 | 470 | 2019 | 2021 | R16
160429201500 | 166020201500 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2020-08-23 | 2020-08-23 | 2020-08-23 |  | 2021-04-21 | Overhead | R16 | 2021-01-22 | 0 |  | 110 | 64 | 173 | 2020 | 2021 | R16
167103143692 | 160545143692 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-01-31 | 2019-02-01 | 2019-02-19 |  | 2019-04-15 | Underground | R16 |  | 2 | 13 |  |  | 53 | 2019 | 2019 | R16
169669207180 | 163628207180 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-14 | 2020-08-14 | 2020-10-13 |  | 2021-07-12 | Underground | R16 | 2020-11-24 | 1 | 43 | 31 | 165 | 237 | 2020 | 2021 | R16
167103166262 | 163908166262 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-08-05 | 2019-08-05 | 2019-09-30 |  | 2019-11-08 | Underground | R16 |  | 1 | 41 |  |  | 70 | 2019 | 2019 | R16
164593231370 | 168440231370 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-19 | 2021-05-19 | 2021-05-19 |  | 2021-08-17 | Overhead | R16 |  | 1 |  |  |  | 65 | 2021 | 2021 | R16
162497227184 | 161573227184 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2021-03-18 | 2021-03-18 | 2021-04-16 |  | 2023-08-23 | Underground | R16 |  | 1 | 22 |  |  | 635 | 2021 | 2023 | R16
163026149913 | 165143149913 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-23 | 2019-04-23 | 2019-04-23 |  | 2019-08-12 | Overhead | R16 | 2019-06-03 | 1 |  | 30 | 51 | 80 | 2019 | 2019 | R16
169231237648 | 166165237648 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-18 | 2021-05-20 | 2021-07-02 |  | 2021-09-13 | Underground | R16 | 2021-08-18 | 3 | 32 | 34 | 19 | 85 | 2021 | 2021 | R16
168864231559 | 168633231559 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-20 | 2021-05-20 | 2021-05-20 |  | 2021-11-02 | Overhead | R16 | 2021-06-17 | 1 |  | 21 | 99 | 119 | 2021 | 2021 | R16
167105206035 | 167416206035 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-08-26 | 2020-02-06 | 2020-10-02 |  | 2021-07-26 | Underground | R16 |  | 119 | 172 |  |  | 501 | 2019 | 2021 | R16
161323158917 | 162709158917 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-06-06 | 2019-06-06 | 2019-07-25 |  | 2021-11-13 | Underground | R16 | 2020-01-24 | 1 | 36 | 132 | 471 | 637 | 2019 | 2021 | R16
169165152979 | 169391152979 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-05-16 | 2019-05-21 | 2019-05-21 |  | 2019-09-12 | Overhead | R16 | 2019-09-06 | 4 |  | 79 | 5 | 86 | 2019 | 2019 | R16
164930203445 | 160068203445 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-10 | 2020-09-10 | 2020-09-10 |  | 2021-07-19 | Overhead | R16 | 2020-11-10 | 1 |  | 44 | 180 | 223 | 2020 | 2021 | R16
164166149932 | 164913149932 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-22 | 2019-04-22 | 2019-04-22 | 2021-09-02 | 2021-11-08 | Overhead | R16 | 2021-09-02 | 1 |  | 619 | 48 | 666 | 2019 | 2021 | R16
163223145909 | 167860145909 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-12 | 2019-03-12 | 2019-03-12 | 2019-03-24 | 2019-03-27 | Overhead | R16 | 2019-03-24 | 1 |  | 9 | 3 | 12 | 2019 | 2019 | R16
167105196902 | 162919196902 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-04-21 | 2020-05-13 | 2020-07-09 |  | 2020-10-06 | Underground | R16 |  | 17 | 42 |  |  | 121 | 2020 | 2020 | R16
163560232661 | 165105232661 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-13 | 2021-05-13 | 2021-05-27 |  | 2021-11-03 | Underground | R16 | 2021-11-03 | 1 | 11 | 115 |  | 125 | 2021 | 2021 | R16
167106152022 | 165476152022 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Commercial | 2019-04-25 | 2019-05-06 | 2019-05-10 |  | 2019-10-28 | Underground | R16 |  | 8 | 5 |  |  | 133 | 2019 | 2019 | R16
167106157437 | 165116157437 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Commercial | 2019-06-20 | 2019-07-09 | 2019-07-10 |  | 2019-10-30 | Underground | R16 |  | 14 | 2 |  |  | 95 | 2019 | 2019 | R16
167107152243 | 161624152243 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-04-04 | 2019-05-10 | 2019-05-13 |  | 2019-12-30 | Underground | R16 |  | 27 | 2 |  |  | 193 | 2019 | 2019 | R16
160259215389 | 163191215389 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-23 | 2020-12-23 | 2020-12-23 | 2021-01-04 | 2021-04-21 | Overhead | R16 | 2021-01-04 | 1 |  | 9 | 78 | 86 | 2020 | 2021 | R16
167107152242 | 161625152242 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-04-04 | 2019-05-10 | 2019-05-13 |  | 2019-12-30 | Underground | R16 |  | 27 | 2 |  |  | 193 | 2019 | 2019 | R16
162204201135 | 165214201135 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-19 | 2020-08-20 | 2020-08-20 |  | 2021-07-23 | Overhead | R16 | 2020-11-04 | 2 |  | 55 | 188 | 243 | 2020 | 2021 | R16
163052213575 | 160253213575 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-11 | 2020-12-11 | 2020-12-11 | 2020-12-22 | 2021-04-21 | Overhead | R16 | 2020-12-22 | 1 |  | 8 | 87 | 94 | 2020 | 2021 | R16
167109177897 | 162616177897 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-09-24 | 2019-12-02 | 2020-01-23 |  | 2020-10-06 | Underground | R16 |  | 50 | 39 |  |  | 271 | 2019 | 2020 | R16
165720150237 | 165292150237 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-24 | 2019-04-24 | 2019-04-24 | 2019-05-16 | 2019-05-30 | Overhead | R16 | 2019-05-16 | 1 |  | 17 | 11 | 27 | 2019 | 2019 | R16
165782226030 | 166391226030 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-10-07 | 2021-01-27 | 2021-04-07 | 2021-09-23 | 2021-10-27 | Underground | R16 | 2021-09-23 | 81 | 51 | 122 | 25 | 276 | 2020 | 2021 | R16
167124160951 | 163242160951 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Commercial | 2019-06-10 | 2019-06-19 | 2019-08-13 |  | 2023-10-01 | Underground | R16 |  | 8 | 40 |  |  | 1125 | 2019 | 2023 | R16
160419222738 | 167240222738 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-28 | 2021-03-07 | 2021-03-09 | 2021-03-09 | 2021-11-08 | Overhead | R16 | 2021-03-09 | 5 | 2 |  | 175 | 181 | 2021 | 2021 | R16
166674224507 | 162740224507 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-23 | 2021-03-23 | 2021-03-23 | 2021-05-10 | 2021-08-11 | Overhead | R16 | 2021-05-10 | 1 |  | 35 | 68 | 102 | 2021 | 2021 | R16
167124169144 | 169876169144 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-09-09 | 2019-09-09 | 2019-10-22 |  | 2020-12-29 | Underground | R16 |  | 1 | 32 |  |  | 342 | 2019 | 2020 | R16
169184208807 | 160976208807 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-28 | 2020-10-28 | 2020-10-28 |  | 2021-04-15 | Overhead | R16 | 2020-12-28 | 1 |  | 44 | 79 | 122 | 2020 | 2021 | R16
167550149990 | 164631149990 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-20 | 2019-04-20 | 2019-04-23 |  | 2019-05-28 | Overhead | R16 | 2019-04-29 | 0 | 2 | 5 | 22 | 27 | 2019 | 2019 | R16
165515145984 | 167932145984 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-13 | 2019-03-13 | 2019-03-13 |  | 2019-08-12 | Overhead | R16 | 2019-05-28 | 1 |  | 55 | 55 | 109 | 2019 | 2019 | R16
167127176460 | 166884176460 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-08-22 | 2019-08-22 | 2020-01-09 |  | 2020-06-09 | Underground | R16 |  | 1 | 101 |  |  | 209 | 2019 | 2020 | R16
167128157432 | 160262157432 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-03-27 | 2019-03-27 | 2019-07-10 |  | 2019-12-18 | Underground | R16 |  | 1 | 76 |  |  | 191 | 2019 | 2019 | R16
163397230495 | 165211230495 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-13 | 2021-05-13 | 2021-05-13 |  | 2021-11-03 | Overhead | R16 | 2021-06-17 | 1 |  | 26 | 100 | 125 | 2021 | 2021 | R16
169911202781 | 168798202781 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-07-20 | 2020-09-04 | 2020-09-04 | 2021-06-14 | 2021-09-17 | Underground | R16 | 2021-06-14 | 35 |  | 202 | 70 | 305 | 2020 | 2021 | R16
162315201480 | 165841201480 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-21 | 2020-08-21 | 2020-08-21 |  | 2021-01-20 | Overhead | R16 | 2020-10-09 | 1 |  | 36 | 74 | 109 | 2020 | 2021 | R16
169062153327 | 160827153327 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-24 | 2019-05-24 | 2019-05-24 | 2019-07-10 | 2019-07-10 | Overhead | R16 | 2019-07-10 | 1 |  | 34 |  | 34 | 2019 | 2019 | R16
167130162007 | 165683162007 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-02-28 | 2019-02-28 | 2019-08-22 |  | 2019-11-06 | Underground | R16 |  | 1 | 126 |  |  | 180 | 2019 | 2019 | R16
160927227150 | 168489227150 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-04-16 | 2021-04-16 | 2021-04-16 | 2021-07-26 | 2021-10-27 | Overhead | R16 | 2021-07-26 | 1 |  | 72 | 68 | 139 | 2021 | 2021 | R16
167130159945 | 163183159945 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-04-12 | 2019-05-09 | 2019-08-02 |  | 2020-02-26 | Underground | R16 |  | 20 | 62 |  |  | 229 | 2019 | 2020 | R16
167130159947 | 168687159947 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-05-13 | 2019-06-07 | 2019-08-02 |  | 2023-09-26 | Underground | R16 |  | 20 | 41 |  |  | 1142 | 2019 | 2023 | R16
161613207268 | 167843207268 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2020-10-14 | 2020-10-14 | 2020-10-14 |  | 2021-11-01 | Overhead | R16 | 2021-04-22 | 1 |  | 137 | 138 | 274 | 2020 | 2021 | R16
167130219480 | 169888219480 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-09-09 | 2019-10-04 | 2021-02-03 |  | 2022-05-12 | Underground | R16 |  | 20 | 349 |  |  | 699 | 2019 | 2022 | R16
164031173033 | 164425173033 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-02-20 | 2019-02-20 | 2019-11-26 | 2021-08-25 | 2021-09-30 | Underground | R16 | 2021-08-25 | 1 | 200 | 457 | 27 | 682 | 2019 | 2021 | R16
163542151741 | 167832151741 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-07 | 2019-05-07 | 2019-05-07 | 2019-06-04 | 2019-08-12 | Overhead | R16 | 2019-06-04 | 1 |  | 21 | 50 | 70 | 2019 | 2019 | R16
167684204367 | 161982204367 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-19 | 2020-09-19 | 2020-09-19 |  | 2021-11-09 | Overhead | R16 | 2020-09-30 | 0 |  | 8 | 290 | 297 | 2020 | 2021 | R16
167147146544 | 168873146544 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-19 | 2019-03-19 | 2019-03-19 |  | 2019-05-28 | Overhead | R16 | 2019-04-23 | 1 |  | 26 | 26 | 51 | 2019 | 2019 | R16
167954213121 | 167973213121 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-12-01 | 2020-12-01 | 2020-12-07 | 2021-09-15 | 2021-09-16 | Underground | R16 | 2021-09-15 | 1 | 5 | 203 | 2 | 208 | 2020 | 2021 | R16
169154150125 | 165164150125 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-24 | 2019-04-24 | 2019-04-24 | 2020-11-10 | 2020-11-19 | Underground | R16 | 2020-11-10 | 1 |  | 405 | 8 | 412 | 2019 | 2020 | R16
162945199837 | 161803199837 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2020-08-03 | 2020-08-05 | 2020-08-07 |  | 2021-07-12 | Underground | R16 |  | 3 | 3 |  |  | 246 | 2020 | 2021 | R16
168492209436 | 162440209436 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-03 | 2020-11-03 | 2020-11-03 | 2021-03-09 | 2021-11-05 | Overhead | R16 | 2021-03-09 | 1 |  | 91 | 174 | 264 | 2020 | 2021 | R16
167183147560 | 166429147560 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-03-06 | 2019-03-11 | 2019-03-28 |  | 2019-09-17 | Underground | R16 | 2019-08-27 | 4 | 14 | 109 | 16 | 140 | 2019 | 2019 | R16
169266147563 | 160549147563 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-03-29 | 2019-03-29 | 2019-03-29 | 2019-10-16 | 2020-06-22 | Overhead | R16 | 2019-10-16 | 1 |  | 144 | 179 | 322 | 2019 | 2020 | R16
168457145351 | 167224145351 | RESIDENTIAL - SINGLE FAMILY DETACHED | ELEC OH MISC SVC OS | Residential | 2019-03-08 | 2019-03-08 | 2019-03-08 |  | 2019-06-03 | Overhead | R16 | 2019-05-09 | 1 |  | 45 | 18 | 62 | 2019 | 2019 | R16
164425228135 | 160009228135 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-23 | 2021-04-23 | 2021-04-23 | 2021-09-09 | 2021-10-27 | Overhead | R16 | 2021-09-09 | 1 |  | 100 | 35 | 134 | 2021 | 2021 | R16
163376205339 | 165181205339 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-19 | 2020-08-19 | 2020-09-28 |  | 2021-04-20 | Underground | R16 | 2021-01-13 | 1 | 29 | 78 | 70 | 175 | 2020 | 2021 | R16
162813204872 | 164309204872 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-17 | 2020-08-17 | 2020-09-24 |  | 2021-07-02 | Underground | R16 | 2020-10-26 | 1 | 29 | 23 | 180 | 230 | 2020 | 2021 | R16
162553150831 | 166328150831 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-30 | 2019-04-30 | 2019-04-30 |  | 2019-08-26 | Underground | R16 | 2019-07-24 | 1 |  | 62 | 24 | 85 | 2019 | 2019 | R16
167209141323 | 167702141323 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-16 | 2019-01-25 | 2019-01-25 |  | 2019-04-01 | Underground | R16 | 2019-03-01 | 8 |  | 26 | 22 | 54 | 2019 | 2019 | R16
165179224714 | 163384224714 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-25 | 2021-03-25 | 2021-03-25 |  | 2021-11-03 | Overhead | R16 | 2021-06-23 | 1 |  | 65 | 96 | 160 | 2021 | 2021 | R16
167225144374 | 165456144374 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-27 | 2019-02-27 | 2019-02-27 |  | 2019-05-20 | Overhead | R16 | 2019-04-02 | 1 |  | 25 | 35 | 59 | 2019 | 2019 | R16
167226143229 | 163494143229 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-14 | 2019-02-14 | 2019-02-14 |  | 2019-04-15 | Overhead | R16 | 2019-03-07 | 1 |  | 16 | 28 | 43 | 2019 | 2019 | R16
164004229492 | 165283229492 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2021-04-02 | 2021-04-02 | 2021-05-05 |  | 2023-08-23 | Underground | R16 |  | 1 | 24 |  |  | 624 | 2021 | 2023 | R16
167289142300 | 169022142300 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-01-25 | 2019-01-25 | 2019-02-04 |  | 2019-06-03 | Underground | R16 | 2019-05-14 | 1 | 7 | 72 | 15 | 92 | 2019 | 2019 | R16
163374143552 | 164186143552 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-02-20 | 2019-02-20 | 2019-02-20 | 2019-04-24 | 2019-04-24 | Underground | R16 | 2019-04-24 | 1 |  | 46 |  | 46 | 2019 | 2019 | R16
162456216026 | 164540216026 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-04 | 2021-01-04 | 2021-01-04 | 2022-09-06 | 2022-09-02 | Overhead | R16 | 2022-09-06 | 1 |  | 437 |  | 435 | 2021 | 2022 | R16
164424236305 | 165316236305 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-04-02 | 2021-04-02 | 2021-06-23 |  | 2021-11-09 | Underground | R16 | 2021-09-24 | 1 | 59 | 68 | 33 | 158 | 2021 | 2021 | R16
167328141889 | 167685141889 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-01-16 | 2019-01-16 | 2019-01-31 |  | 2020-07-01 | Underground | R16 | 2020-04-28 | 1 | 12 | 324 | 47 | 381 | 2019 | 2020 | R16
162671209323 | 161896209323 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-02 | 2020-11-02 | 2020-11-02 | 2021-01-16 | 2021-01-19 | Underground | R16 | 2021-01-16 | 1 |  | 55 | 2 | 57 | 2020 | 2021 | R16
167335159518 | 167319159518 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2019-07-01 | 2019-07-01 | 2019-08-02 |  | 2021-11-30 | Underground | R16 | 2019-10-07 | 1 | 25 | 47 | 562 | 632 | 2019 | 2021 | R16
166986240759 | 161015240759 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-27 | 2021-04-27 | 2021-07-26 |  | 2022-02-02 | Underground | R16 | 2021-10-26 | 1 | 65 | 67 | 72 | 202 | 2021 | 2022 | R16
167944155230 | 169611155230 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-17 | 2019-05-17 | 2019-06-13 |  | 2019-09-04 | Underground | R16 | 2019-08-28 | 1 | 20 | 55 | 6 | 79 | 2019 | 2019 | R16
165334212718 | 165119212718 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-17 | 2020-11-17 | 2020-12-03 | 2020-12-15 | 2020-12-18 | Overhead | R16 | 2020-12-15 | 1 | 13 | 9 | 4 | 24 | 2020 | 2020 | R16
160829227767 | 165258227767 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-04-01 | 2021-04-01 | 2021-04-21 |  | 2021-11-05 | Overhead | R16 |  | 1 | 15 |  |  | 157 | 2021 | 2021 | R16
167367147397 | 160327147397 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-03-27 | 2019-03-27 | 2019-03-27 |  | 2019-05-28 | Overhead | R16 | 2019-04-30 | 1 |  | 25 | 21 | 45 | 2019 | 2019 | R16
167355203068 | 169148203068 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-08 | 2020-09-08 | 2020-09-08 | 2020-10-07 | 2021-01-11 | Overhead | R16 | 2020-10-07 | 1 |  | 22 | 69 | 90 | 2020 | 2021 | R16
167387145529 | 167326145529 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-09 | 2019-03-09 | 2019-03-09 |  | 2019-08-12 | Overhead | R16 | 2019-05-22 | 0 |  | 53 | 59 | 111 | 2019 | 2019 | R16
167388141024 | 168245141024 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-01-22 | 2019-01-22 | 2019-01-22 |  | 2019-04-15 | Underground | R16 | 2019-03-14 | 1 |  | 38 | 23 | 60 | 2019 | 2019 | R16
163707142364 | 167365142364 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-15 | 2019-01-24 | 2019-02-05 | 2019-10-01 | 2020-06-09 | Overhead | R16 | 2019-10-01 | 8 | 9 | 171 | 181 | 366 | 2019 | 2020 | R16
167389141933 | 160585141933 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-31 | 2019-01-31 | 2019-01-31 |  | 2019-08-12 | Overhead | R16 | 2019-06-18 | 1 |  | 99 | 40 | 138 | 2019 | 2019 | R16
165666210817 | 165758210817 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-10-05 | 2020-10-05 | 2020-11-16 |  | 2021-12-02 | Underground | R16 | 2021-11-05 | 1 | 31 | 255 | 20 | 304 | 2020 | 2021 | R16
168266217751 | 167466217751 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-15 | 2021-01-20 | 2021-01-20 | 2021-04-30 | 2021-11-05 | Underground | R16 | 2021-04-30 | 4 |  | 73 | 136 | 211 | 2021 | 2021 | R16
164187204743 | 162935204743 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-24 | 2020-09-24 | 2020-09-24 | 2020-10-09 | 2021-02-17 | Overhead | R16 | 2020-10-09 | 1 |  | 12 | 94 | 105 | 2020 | 2021 | R16
167468142519 | 162171142519 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-07 | 2019-02-07 | 2019-02-07 |  | 2019-04-22 | Overhead | R16 | 2019-03-19 | 1 |  | 29 | 25 | 53 | 2019 | 2019 | R16
164773300520 | 167882300520 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2021-04-13 | 2021-08-05 | 2022-11-14 | 2023-05-25 | 2023-08-10 | Underground | R16 | 2023-05-25 | 83 | 333 | 139 | 56 | 608 | 2021 | 2023 | R16
163303144139 | 165361144139 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-27 | 2019-02-27 | 2019-02-27 | 2019-07-11 | 2019-07-11 | Overhead | R16 | 2019-07-11 | 1 |  | 97 |  | 97 | 2019 | 2019 | R16
169723150959 | 165297150959 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-25 | 2019-04-25 | 2019-05-03 |  | 2019-08-26 | Underground | R16 | 2019-06-24 | 1 | 7 | 37 | 46 | 88 | 2019 | 2019 | R16
165135242417 | 164688242417 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-31 | 2021-03-31 | 2021-08-06 |  | 2021-09-13 | Overhead | R16 | 2021-08-18 | 1 | 93 | 9 | 19 | 119 | 2021 | 2021 | R16
167491140881 | 168212140881 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-22 | 2019-01-22 | 2019-01-22 |  | 2019-03-11 | Overhead | R16 | 2019-02-22 | 1 |  | 24 | 12 | 35 | 2019 | 2019 | R16
167513160596 | 163554160596 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential Subdivision | 2019-08-02 | 2019-08-02 | 2019-08-09 |  | 2022-08-29 | Underground | R16 |  | 1 | 6 |  |  | 802 | 2019 | 2022 | R16
167530165838 | 166743165838 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-03-07 | 2019-07-09 | 2019-09-26 |  | 2019-11-27 | Underground | R16 |  | 89 | 58 |  |  | 190 | 2019 | 2019 | R16
163381213214 | 169140213214 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-07 | 2020-12-09 | 2020-12-09 | 2021-02-04 | 2021-02-17 | Overhead | R16 | 2021-02-04 | 3 |  | 42 | 10 | 53 | 2020 | 2021 | R16
167163151983 | 168116151983 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-09 | 2019-05-09 | 2019-05-09 |  | 2019-08-12 | Underground | R16 | 2019-06-10 | 1 |  | 23 | 46 | 68 | 2019 | 2019 | R16
168328211218 | 165135211218 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-17 | 2020-11-17 | 2020-11-19 |  | 2021-06-02 | Underground | R16 | 2021-03-01 | 1 | 3 | 73 | 68 | 142 | 2020 | 2021 | R16
165683217678 | 165673217678 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-18 | 2020-11-18 | 2021-01-20 | 2023-04-28 | 2023-04-28 | Underground | R16 | 2023-04-28 | 1 | 46 | 593 |  | 638 | 2020 | 2023 | R16
167588209676 | 160697209676 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-06-05 | 2020-09-22 | 2020-11-05 |  | 2021-10-21 | Underground | R16 |  | 78 | 33 |  |  | 360 | 2020 | 2021 | R16
164803251592 | 164955251592 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-03-31 | 2021-10-05 | 2021-10-11 |  | 2022-03-08 | Underground | R16 |  | 135 | 5 |  |  | 245 | 2021 | 2022 | R16
165851139417 | 165839139417 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-01-08 | 2019-01-08 | 2019-01-08 | 2021-06-14 | 2019-09-03 | Underground | R16 | 2021-06-14 | 1 |  | 635 |  | 171 | 2019 | 2019 | R16
167626164737 | 168857164737 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-07-08 | 2019-09-04 | 2019-09-17 |  | 2019-10-31 | Overhead | R16 |  | 43 | 10 |  |  | 84 | 2019 | 2019 | R16
161522200619 | 163927200619 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-08-17 | 2020-08-17 | 2020-08-17 |  | 2020-11-02 | Overhead | R16 | 2020-09-04 | 1 |  | 15 | 42 | 56 | 2020 | 2020 | R16
167628152591 | 167802152591 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-07 | 2019-05-07 | 2019-05-16 |  | 2019-09-18 | Overhead | R16 |  | 1 | 8 |  |  | 97 | 2019 | 2019 | R16
167842141286 | 168953141286 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-24 | 2019-01-25 | 2019-01-25 | 2019-01-29 | 2019-02-25 | Overhead | R16 | 2019-01-29 | 2 |  | 3 | 20 | 23 | 2019 | 2019 | R16
167774206432 | 166186206432 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-07 | 2020-10-07 | 2020-10-07 | 2020-10-09 | 2021-07-24 | Overhead | R16 | 2020-10-09 | 1 |  | 3 | 206 | 208 | 2020 | 2021 | R16
165217216964 | 166355216964 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-12 | 2021-01-12 | 2021-01-12 | 2021-02-19 | 2021-11-11 | Overhead | R16 | 2021-02-19 | 1 |  | 29 | 190 | 218 | 2021 | 2021 | R16
166793200075 | 163137200075 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2020-08-11 | 2020-08-11 | 2020-08-11 |  | 2020-11-02 | Overhead | R16 | 2020-09-02 | 1 |  | 17 | 44 | 60 | 2020 | 2020 | R16
160049157229 | 160869157229 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-24 | 2019-05-29 | 2019-07-08 | 2019-09-06 | 2019-09-10 | Underground | R16 | 2019-09-06 | 4 | 29 | 45 | 3 | 78 | 2019 | 2019 | R16
168977221851 | 169577221851 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-07-22 | 2020-10-09 | 2021-02-26 | 2021-09-14 | 2021-09-30 | Underground | R16 | 2021-09-14 | 58 | 101 | 143 | 13 | 312 | 2020 | 2021 | R16
167692147144 | 161647147144 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-02-06 | 2019-02-12 | 2019-03-25 |  | 2019-09-03 | Overhead | R16 | 2019-07-31 | 5 | 30 | 93 | 25 | 150 | 2019 | 2019 | R16
164980203830 | 161635203830 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-08-03 | 2020-08-03 | 2020-09-15 |  | 2021-05-06 | Overhead | R16 | 2021-02-22 | 1 | 32 | 115 | 54 | 199 | 2020 | 2021 | R16
167711144045 | 164746144045 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-23 | 2019-02-23 | 2019-02-23 |  | 2019-05-20 | Overhead | R16 | 2019-04-17 | 0 |  | 38 | 24 | 61 | 2019 | 2019 | R16
161092148512 | 162471148512 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-09 | 2019-04-09 | 2019-04-09 |  | 2019-04-24 | Overhead | R16 | 2019-04-16 | 1 |  | 6 | 7 | 12 | 2019 | 2019 | R16
169138206262 | 169287206262 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-21 | 2020-10-04 | 2020-10-04 |  | 2021-04-16 | Overhead | R16 | 2021-01-05 | 54 |  | 67 | 74 | 194 | 2020 | 2021 | R16
161049232374 | 162707232374 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-05-04 | 2021-05-04 | 2021-05-26 | 2021-08-09 | 2021-10-25 | Underground | R16 | 2021-08-09 | 1 | 17 | 54 | 56 | 125 | 2021 | 2021 | R16
167744145306 | 167105145306 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-07 | 2019-03-07 | 2019-03-07 |  | 2019-05-20 | Overhead | R16 | 2019-04-09 | 1 |  | 24 | 30 | 53 | 2019 | 2019 | R16
165116232702 | 160275232702 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-27 | 2021-05-27 | 2021-05-27 | 2021-08-26 | 2021-10-25 | Overhead | R16 | 2021-08-26 | 1 |  | 66 | 43 | 108 | 2021 | 2021 | R16
167150148514 | 161903148514 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-05 | 2019-04-05 | 2019-04-09 | 2019-06-04 | 2019-06-05 | Underground | R16 | 2019-06-04 | 1 | 3 | 41 | 2 | 44 | 2019 | 2019 | R16
167765155013 | 169379155013 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-01-29 | 2019-04-02 | 2019-06-11 |  | 2020-06-23 | Underground | R16 |  | 46 | 51 |  |  | 366 | 2019 | 2020 | R16
168478217426 | 164739217426 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-05 | 2021-01-05 | 2021-01-15 | 2021-01-29 | 2021-06-02 | Underground | R16 | 2021-01-29 | 1 | 9 | 11 | 89 | 107 | 2021 | 2021 | R16
167796148940 | 162834148940 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-11 | 2019-04-11 | 2019-04-11 |  | 2019-06-03 | Overhead | R16 | 2019-05-14 | 1 |  | 24 | 15 | 38 | 2019 | 2019 | R16
166585229988 | 163725229988 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-05-07 | 2021-05-07 | 2021-05-07 | 2023-07-14 | 2023-08-16 | Underground | R16 | 2023-07-14 | 1 |  | 571 | 24 | 594 | 2021 | 2023 | R16
167799142605 | 168937142605 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-01-25 | 2019-01-25 | 2019-02-08 |  | 2019-11-13 | Underground | R16 | 2019-11-05 | 1 | 11 | 193 | 7 | 209 | 2019 | 2019 | R16
165214220339 | 162889220339 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-08 | 2021-02-11 | 2021-02-11 | 2021-08-26 | 2021-10-25 | Overhead | R16 | 2021-08-26 | 4 |  | 141 | 43 | 186 | 2021 | 2021 | R16
165090204881 | 162843204881 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-23 | 2020-09-23 | 2020-09-23 |  | 2021-07-26 | Overhead | R16 | 2021-05-12 | 1 |  | 166 | 54 | 219 | 2020 | 2021 | R16
167829222189 | 164769222189 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2021-01-05 | 2021-02-12 | 2021-03-02 |  | 2021-11-03 | Underground | R16 |  | 29 | 13 |  |  | 217 | 2021 | 2021 | R16
164039144458 | 165267144458 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-02-27 | 2019-03-01 | 2019-03-01 |  | 2019-05-28 | Overhead | R16 |  | 3 |  |  |  | 65 | 2019 | 2019 | R16
168045237844 | 166882237844 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-11-24 | 2021-05-25 | 2021-07-06 | 2021-08-13 | 2022-03-29 | Underground | R16 | 2021-08-13 | 131 | 31 | 29 | 163 | 351 | 2020 | 2022 | R16
167839140559 | 168088140559 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-01-18 | 2019-01-18 | 2019-01-18 |  | 2019-04-08 | Overhead | R16 | 2019-03-04 | 1 |  | 32 | 26 | 57 | 2019 | 2019 | R16
160901224450 | 160638224450 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-16 | 2021-03-16 | 2021-03-23 |  | 2021-08-12 | Underground | R16 | 2021-04-12 | 1 | 6 | 15 | 89 | 108 | 2021 | 2021 | R16
165207177656 | 167424177656 | NON-RESIDENTIAL - SMALL OFFICE | UG R16 RESD AND NON RESD UD | Commercial | 2019-05-06 | 2019-05-06 | 2020-01-21 | 2020-06-15 | 2020-11-23 | Underground | R16 | 2020-06-15 | 1 | 187 | 105 | 116 | 406 | 2019 | 2020 | R16
167852144256 | 167896144256 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-17 | 2019-01-17 | 2019-02-27 |  | 2019-08-12 | Underground | R16 | 2019-06-04 | 1 | 30 | 70 | 50 | 148 | 2019 | 2019 | R16
167854142762 | 162516142762 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-09 | 2019-02-09 | 2019-02-09 |  | 2019-04-24 | Overhead | R16 | 2019-03-20 | 0 |  | 28 | 26 | 53 | 2019 | 2019 | R16
164569154410 | 162375154410 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-05 | 2019-06-05 | 2019-06-05 |  | 2019-08-26 | Overhead | R16 | 2019-07-11 | 1 |  | 27 | 33 | 59 | 2019 | 2019 | R16
167862144315 | 167871144315 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-17 | 2019-01-17 | 2019-02-26 |  | 2019-10-14 | Underground | R16 | 2019-10-03 | 1 | 29 | 158 | 8 | 193 | 2019 | 2019 | R16
165120205714 | 160945205714 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-15 | 2020-09-30 | 2020-09-30 | 2020-10-30 | 2021-04-13 | Overhead | R16 | 2020-10-30 | 12 |  | 23 | 118 | 151 | 2020 | 2021 | R16
160014229663 | 163126229663 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-05 | 2021-05-05 | 2021-05-05 | 2021-05-11 | 2021-08-16 | Overhead | R16 | 2021-05-11 | 1 |  | 5 | 70 | 74 | 2021 | 2021 | R16
167866145527 | 167327145527 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-09 | 2019-03-09 | 2019-03-09 |  | 2019-08-12 | Overhead | R16 | 2019-05-21 | 0 |  | 52 | 60 | 111 | 2019 | 2019 | R16
166650226617 | 167664226617 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-13 | 2021-04-13 | 2021-04-13 |  | 2021-11-09 | Overhead | R16 | 2021-10-07 | 1 |  | 128 | 24 | 151 | 2021 | 2021 | R16
160708215412 | 163167215412 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-23 | 2020-12-23 | 2020-12-23 |  | 2021-06-03 | Overhead | R16 | 2021-03-26 | 1 |  | 68 | 50 | 117 | 2020 | 2021 | R16
164146203890 | 160991203890 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-15 | 2020-09-15 | 2020-09-15 |  | 2020-12-18 | Overhead | R16 | 2020-09-21 | 1 |  | 5 | 65 | 69 | 2020 | 2020 | R16
167880142970 | 162729142970 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-02-11 | 2019-02-11 | 2019-02-11 |  | 2019-03-11 | Overhead | R16 | 2019-02-20 | 1 |  | 8 | 14 | 21 | 2019 | 2019 | R16
167916145528 | 167328145528 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-09 | 2019-03-09 | 2019-03-09 |  | 2019-04-15 | Overhead | R16 | 2019-03-25 | 0 |  | 11 | 16 | 26 | 2019 | 2019 | R16
167974145526 | 163232145526 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-13 | 2019-02-13 | 2019-03-09 |  | 2019-05-20 | Underground | R16 | 2019-04-17 | 1 | 18 | 28 | 24 | 69 | 2019 | 2019 | R16
168425217487 | 167522217487 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-15 | 2021-01-15 | 2021-01-15 | 2022-03-22 | 2022-06-01 | Overhead | R16 | 2022-03-22 | 1 |  | 308 | 52 | 359 | 2021 | 2022 | R16
164273206539 | 161571206539 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-17 | 2020-09-17 | 2020-10-08 | 2020-10-20 | 2021-07-02 | Overhead | R16 | 2020-10-20 | 1 | 16 | 9 | 184 | 207 | 2020 | 2021 | R16
168366144783 | 164434144783 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-20 | 2019-03-04 | 2019-03-04 |  | 2019-05-20 | Overhead | R16 | 2019-04-11 | 9 |  | 29 | 28 | 64 | 2019 | 2019 | R16
168069144126 | 164397144126 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-20 | 2019-02-25 | 2019-02-25 |  | 2019-04-26 | Underground | R16 | 2019-04-03 | 4 |  | 28 | 18 | 48 | 2019 | 2019 | R16
163253144367 | 165301144367 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-26 | 2019-02-26 | 2019-02-26 | 2021-04-26 | 2021-05-10 | Overhead | R16 | 2021-04-26 | 1 |  | 565 | 11 | 575 | 2019 | 2021 | R16
165106220692 | 161590220692 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-12-18 | 2020-12-18 | 2021-02-17 | 2021-08-24 | 2023-06-08 | Underground | R16 | 2021-08-24 | 1 | 44 | 135 | 468 | 645 | 2020 | 2023 | R16
168092145163 | 163154145163 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-13 | 2019-02-13 | 2019-03-06 |  | 2019-04-15 | Underground | R16 | 2019-03-29 | 1 | 16 | 18 | 12 | 44 | 2019 | 2019 | R16
168096143666 | 164047143666 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-19 | 2019-02-19 | 2019-02-19 |  | 2019-04-25 | Underground | R16 | 2019-04-01 | 1 |  | 30 | 19 | 48 | 2019 | 2019 | R16
161857145520 | 165512145520 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2019-02-28 | 2019-03-08 | 2019-03-08 |  | 2019-04-15 | Overhead | R16 | 2019-03-29 | 7 |  | 16 | 12 | 33 | 2019 | 2019 | R16
162014218790 | 160589218790 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-28 | 2021-01-28 | 2021-01-28 |  | 2021-10-25 | Underground | R16 | 2021-09-09 | 1 |  | 161 | 33 | 193 | 2021 | 2021 | R16
160631212682 | 161260212682 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-28 | 2020-11-17 | 2020-12-02 |  | 2021-11-05 | Overhead | R16 |  | 15 | 12 |  |  | 268 | 2020 | 2021 | R16
166229199914 | 162613199914 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-08-07 | 2020-08-07 | 2020-08-07 |  | 2022-02-07 | Underground | R16 | 2022-01-14 | 1 |  | 376 | 17 | 392 | 2020 | 2022 | R16
168142145781 | 161433145781 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-05 | 2019-02-05 | 2019-03-11 |  | 2019-04-25 | Underground | R16 | 2019-04-01 | 1 | 25 | 16 | 19 | 58 | 2019 | 2019 | R16
162140210822 | 165050210822 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-16 | 2020-11-16 | 2020-11-16 | 2020-11-19 | 2021-07-28 | Overhead | R16 | 2020-11-19 | 1 |  | 4 | 180 | 183 | 2020 | 2021 | R16
162941210134 | 169136210134 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-20 | 2020-10-26 | 2020-11-10 |  | 2021-04-14 | Underground | R16 | 2020-12-09 | 5 | 12 | 22 | 91 | 127 | 2020 | 2021 | R16
164632139748 | 166439139748 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-09 | 2019-01-09 | 2019-01-09 | 2019-04-16 | 2019-04-16 | Overhead | R16 | 2019-04-16 | 1 |  | 70 |  | 70 | 2019 | 2019 | R16
166309200327 | 168439200327 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-15 | 2020-07-16 | 2020-08-11 | 2020-09-28 | 2020-09-30 | Underground | R16 | 2020-09-28 | 2 | 19 | 35 | 3 | 56 | 2020 | 2020 | R16
168204147456 | 163769147456 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-16 | 2019-03-29 | 2019-03-29 |  | 2019-05-28 | Overhead | R16 | 2019-04-29 | 30 |  | 22 | 22 | 72 | 2019 | 2019 | R16
162211207987 | 169643207987 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2020-10-22 | 2020-10-22 | 2020-10-22 | 2021-01-22 | 2021-01-25 | Overhead | R16 | 2021-01-22 | 1 |  | 67 | 2 | 68 | 2020 | 2021 | R16
168512213881 | 165224213881 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-16 | 2020-11-25 | 2020-12-14 |  | 2021-08-23 | Underground | R16 | 2021-07-14 | 8 | 14 | 153 | 29 | 201 | 2020 | 2021 | R16
162332238133 | 165842238133 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-05 | 2021-07-08 | 2021-07-08 |  | 2023-01-10 | Underground | R16 | 2022-11-07 | 69 |  | 348 | 47 | 462 | 2021 | 2023 | R16
167628151790 | 162886151790 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-11 | 2019-04-11 | 2019-05-08 | 2019-09-19 | 2019-09-19 | Underground | R16 | 2019-09-19 | 1 | 20 | 97 |  | 116 | 2019 | 2019 | R16
168293145786 | 165402145786 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-27 | 2019-02-27 | 2019-03-11 |  | 2019-08-12 | Underground | R16 | 2019-06-11 | 1 | 9 | 67 | 45 | 119 | 2019 | 2019 | R16
165897154268 | 160284154268 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-22 | 2019-05-22 | 2019-06-03 | 2019-06-07 | 2019-08-26 | Underground | R16 | 2019-06-07 | 1 | 9 | 5 | 57 | 69 | 2019 | 2019 | R16
168301145525 | 167375145525 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-09 | 2019-03-09 | 2019-03-09 |  | 2019-08-12 | Overhead | R16 | 2019-05-31 | 0 |  | 60 | 52 | 111 | 2019 | 2019 | R16
169343148820 | 165484148820 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-27 | 2019-03-21 | 2019-04-09 |  | 2019-06-03 | Underground | R16 | 2019-05-09 | 17 | 14 | 23 | 18 | 69 | 2019 | 2019 | R16
164170147314 | 160182147314 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-27 | 2019-03-28 | 2019-03-28 |  | 2019-05-28 | Overhead | R16 | 2019-04-24 | 2 |  | 20 | 25 | 45 | 2019 | 2019 | R16
168308156588 | 166294156588 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-27 | 2019-06-27 | 2019-06-27 |  | 2019-08-26 | Overhead | R16 | 2019-07-24 | 1 |  | 20 | 24 | 43 | 2019 | 2019 | R16
161658151626 | 167716151626 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-07 | 2019-05-07 | 2019-05-07 |  | 2019-08-12 | Overhead | R16 | 2019-06-04 | 1 |  | 21 | 50 | 70 | 2019 | 2019 | R16
167055142406 | 161492142406 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-05 | 2019-02-05 | 2019-02-05 | 2019-03-06 | 2019-03-06 | Overhead | R16 | 2019-03-06 | 1 |  | 22 |  | 22 | 2019 | 2019 | R16
163738211485 | 166963211485 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-09 | 2020-10-09 | 2020-11-20 | 2020-12-28 | 2021-04-16 | Underground | R16 | 2020-12-28 | 1 | 31 | 27 | 80 | 136 | 2020 | 2021 | R16
164942147755 | 167880147755 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-03-12 | 2019-03-12 | 2019-04-01 |  | 2020-08-20 | Underground | R16 | 2020-06-24 | 1 | 15 | 323 | 42 | 378 | 2019 | 2020 | R16
168343146438 | 168885146438 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-03-19 | 2019-03-19 | 2019-03-19 |  | 2019-04-26 | Overhead | R16 | 2019-04-03 | 1 |  | 12 | 18 | 29 | 2019 | 2019 | R16
168229235923 | 162847235923 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-05 | 2021-06-21 | 2021-06-21 | 2021-11-30 | 2022-01-14 | Overhead | R16 | 2021-11-30 | 34 |  | 117 | 34 | 183 | 2021 | 2022 | R16
168352144818 | 166376144818 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-05 | 2019-03-05 | 2019-03-05 |  | 2020-06-09 | Overhead | R16 | 2020-02-04 | 1 |  | 241 | 91 | 331 | 2019 | 2020 | R16
163333220237 | 163321220237 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-28 | 2020-12-28 | 2021-02-12 |  | 2021-08-23 | Underground | R16 | 2021-07-13 | 1 | 35 | 108 | 30 | 171 | 2020 | 2021 | R16
168356161819 | 164912161819 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-08-12 | 2019-08-12 | 2019-08-21 |  | 2020-01-09 | Underground | R16 | 2020-01-02 | 1 | 8 | 97 | 6 | 109 | 2019 | 2020 | R16
166388230556 | 164976230556 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-13 | 2021-05-13 | 2021-05-13 |  | 2021-09-10 | Overhead | R16 | 2021-08-17 | 1 |  | 69 | 19 | 87 | 2021 | 2021 | R16
167788224532 | 169706224532 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-23 | 2020-08-10 | 2021-03-24 | 2022-10-25 | 2022-11-21 | Underground | R16 | 2022-10-25 | 13 | 163 | 415 | 20 | 608 | 2020 | 2022 | R16
160596167591 | 168252167591 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-03-14 | 2019-03-14 | 2019-10-09 |  | 2020-06-09 | Overhead | R16 | 2020-02-03 | 1 | 150 | 84 | 92 | 324 | 2019 | 2020 | R16
162013197916 | 168411197916 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-15 | 2020-07-15 | 2020-07-21 |  | 2021-07-14 | Underground | R16 | 2020-11-19 | 1 | 5 | 88 | 170 | 261 | 2020 | 2021 | R16
169719224311 | 167254224311 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2021-03-01 | 2021-03-01 | 2021-03-21 |  | 2021-11-01 | Overhead | R16 |  | 1 | 15 |  |  | 176 | 2021 | 2021 | R16
168369168340 | 164772168340 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-08-09 | 2019-08-09 | 2019-10-15 |  | 2019-12-19 | Underground | R16 | 2019-12-09 | 1 | 48 | 40 | 9 | 95 | 2019 | 2019 | R16
160042150425 | 164132150425 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-04-17 | 2019-04-17 | 2019-04-26 | 2019-07-17 | 2023-06-07 | Underground | R16 | 2019-07-17 | 1 | 8 | 59 | 1016 | 1081 | 2019 | 2023 | R16
168381177815 | 165375177815 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-01-23 | 2020-01-23 | 2020-01-23 |  | 2021-01-12 | Underground | R16 | 2020-08-17 | 1 |  | 148 | 107 | 254 | 2020 | 2021 | R16
161420224116 | 161764224116 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-18 | 2021-03-18 | 2021-03-18 | 2021-05-10 | 2021-05-11 | Underground | R16 | 2021-05-10 | 1 |  | 38 | 2 | 39 | 2021 | 2021 | R16
168382141565 | 168404141565 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-23 | 2019-01-23 | 2019-01-28 |  | 2019-03-11 | Underground | R16 | 2019-02-19 | 1 | 4 | 17 | 15 | 34 | 2019 | 2019 | R16
160101223797 | 160104223797 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-10 | 2020-12-10 | 2021-03-17 |  | 2021-10-25 | Underground | R16 | 2021-04-29 | 1 | 70 | 32 | 128 | 228 | 2020 | 2021 | R16
160882208504 | 165453208504 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-10-02 | 2020-10-26 | 2020-10-26 |  | 2023-03-13 | Underground | R16 | 2022-02-18 | 17 |  | 345 | 277 | 637 | 2020 | 2023 | R16
168406142360 | 161332142360 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-05 | 2019-02-05 | 2019-02-05 |  | 2023-02-03 | Overhead | R16 |  | 1 |  |  |  | 1044 | 2019 | 2023 | R16
160394152867 | 169904152867 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-20 | 2019-05-20 | 2019-05-21 |  | 2019-09-03 | Overhead | R16 | 2019-07-29 | 1 | 2 | 50 | 27 | 77 | 2019 | 2019 | R16
168407151104 | 161298151104 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-05 | 2019-02-05 | 2019-05-02 |  | 2019-08-12 | Underground | R16 | 2019-06-07 | 1 | 63 | 27 | 47 | 135 | 2019 | 2019 | R16
169538200809 | 164341200809 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-17 | 2020-08-17 | 2020-08-17 |  | 2022-08-03 | Overhead | R16 |  | 1 |  |  |  | 513 | 2020 | 2022 | R16
168408146723 | 169144146723 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-20 | 2019-03-20 | 2019-03-20 |  | 2019-08-26 | Overhead | R16 | 2019-07-10 | 1 |  | 81 | 34 | 114 | 2019 | 2019 | R16
168097219552 | 168182219552 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-01 | 2020-09-01 | 2021-02-05 | 2021-04-12 | 2021-04-14 | Underground | R16 | 2021-04-12 | 1 | 114 | 47 | 3 | 162 | 2020 | 2021 | R16
168549222933 | 160553222933 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-14 | 2020-12-14 | 2021-03-09 | 2021-06-11 | 2021-06-14 | Underground | R16 | 2021-06-11 | 1 | 62 | 69 | 2 | 131 | 2020 | 2021 | R16
167566222449 | 161092222449 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-01-29 | 2021-01-29 | 2021-03-04 |  | 2021-08-26 | Underground | R16 | 2021-06-08 | 1 | 25 | 69 | 58 | 150 | 2021 | 2021 | R16
168417153370 | 163922153370 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-02-17 | 2019-04-05 | 2019-05-24 |  | 2022-04-05 | Underground | R16 |  | 35 | 36 |  |  | 817 | 2019 | 2022 | R16
167274223065 | 169668223065 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-10 | 2021-03-10 | 2021-03-10 |  | 2021-06-17 | Overhead | R16 |  | 1 |  |  |  | 72 | 2021 | 2021 | R16
162157200492 | 163617200492 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-13 | 2020-08-13 | 2020-08-13 | 2022-03-01 | 2022-03-04 | Overhead | R16 | 2022-03-01 | 1 |  | 404 | 4 | 407 | 2020 | 2022 | R16
164296151084 | 165775151084 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-26 | 2019-04-26 | 2019-05-02 |  | 2019-08-12 | Underground | R16 | 2019-05-22 | 1 | 5 | 15 | 59 | 77 | 2019 | 2019 | R16
168441145651 | 164986145651 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-25 | 2019-02-26 | 2019-03-11 |  | 2019-08-12 | Underground | R16 | 2019-06-21 | 2 | 10 | 75 | 37 | 121 | 2019 | 2019 | R16
164185145221 | 166784145221 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-03-06 | 2019-03-06 | 2019-03-06 | 2019-05-03 | 2019-05-03 | Overhead | R16 | 2019-05-03 | 1 |  | 43 |  | 43 | 2019 | 2019 | R16
168462229637 | 162312229637 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-05-03 | 2021-05-03 | 2021-05-06 |  | 2022-08-29 | Underground | R16 |  | 1 | 4 |  |  | 346 | 2021 | 2022 | R16
168528153646 | 167587153646 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-03-11 | 2019-03-12 | 2019-05-28 |  | 2019-09-18 | Overhead | R16 | 2019-09-10 | 2 | 56 | 76 | 7 | 138 | 2019 | 2019 | R16
163853216454 | 163942216454 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-12-30 | 2020-12-30 | 2021-01-07 | 2021-01-08 | 2021-03-27 | Underground | R16 | 2021-01-08 | 1 | 7 | 2 | 56 | 63 | 2020 | 2021 | R16
165821206221 | 165778206221 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-05 | 2020-10-05 | 2020-10-05 | 2020-11-03 | 2021-11-10 | Overhead | R16 | 2020-11-03 | 1 |  | 22 | 267 | 288 | 2020 | 2021 | R16
168572149841 | 161881149841 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-05 | 2019-04-05 | 2019-04-22 |  | 2019-06-03 | Underground | R16 | 2019-05-13 | 1 | 12 | 16 | 16 | 42 | 2019 | 2019 | R16
161589203356 | 169759203356 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-09-09 | 2020-09-10 | 2020-09-10 |  | 2021-04-23 | Overhead | R16 | 2021-02-05 | 2 |  | 107 | 56 | 163 | 2020 | 2021 | R16
166034206342 | 166005206342 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-06 | 2020-10-06 | 2020-10-06 | 2020-11-17 | 2023-04-12 | Overhead | R16 | 2020-11-17 | 1 |  | 31 | 627 | 657 | 2020 | 2023 | R16
168627145045 | 166462145045 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-05 | 2019-03-05 | 2019-03-05 |  | 2019-05-28 | Overhead | R16 | 2019-05-03 | 1 |  | 44 | 18 | 61 | 2019 | 2019 | R16
168629155701 | 169984155701 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-03-26 | 2019-03-26 | 2019-06-18 |  | 2019-09-03 | Underground | R16 | 2019-07-30 | 1 | 61 | 31 | 26 | 116 | 2019 | 2019 | R16
160418275989 | 162863275989 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-23 | 2021-04-15 | 2022-04-15 |  | 2023-06-09 | Underground | R16 | 2023-03-02 | 18 | 262 | 230 | 72 | 579 | 2021 | 2023 | R16
168972255160 | 163445255160 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-06 | 2021-11-04 | 2021-11-04 | 2022-10-26 | 2022-10-27 | Overhead | R16 | 2022-10-26 | 131 |  | 255 | 2 | 386 | 2021 | 2022 | R16
167737211455 | 166118211455 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-20 | 2020-11-20 | 2020-11-20 | 2020-12-22 | 2021-01-05 | Overhead | R16 | 2020-12-22 | 1 |  | 23 | 11 | 33 | 2020 | 2021 | R16
168675146507 | 166020146507 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-03 | 2019-03-03 | 2019-03-19 |  | 2019-05-28 | Underground | R16 | 2019-04-25 | 0 | 12 | 28 | 24 | 62 | 2019 | 2019 | R16
161653212474 | 168068212474 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-02 | 2020-12-02 | 2020-12-02 |  | 2021-10-25 | Underground | R16 | 2021-09-21 | 1 |  | 210 | 25 | 234 | 2020 | 2021 | R16
168694147072 | 169347147072 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-22 | 2019-03-22 | 2019-03-26 |  | 2019-06-03 | Overhead | R16 | 2019-05-15 | 1 | 3 | 37 | 14 | 52 | 2019 | 2019 | R16
166207224429 | 168920224429 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-03-08 | 2021-03-08 | 2021-03-23 | 2021-08-26 | 2021-08-26 | Overhead | R16 | 2021-08-26 | 1 | 12 | 113 |  | 124 | 2021 | 2021 | R16
168759148893 | 162639148893 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-10 | 2019-04-10 | 2019-04-12 |  | 2019-06-03 | Overhead | R16 | 2019-05-08 | 1 | 3 | 19 | 19 | 39 | 2019 | 2019 | R16
160835212813 | 168793212813 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-04 | 2020-12-04 | 2020-12-04 | 2021-03-01 | 2021-11-04 | Underground | R16 | 2021-03-01 | 1 |  | 62 | 179 | 240 | 2020 | 2021 | R16
168778141836 | 160710141836 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-31 | 2019-01-31 | 2019-01-31 |  | 2019-04-01 | Overhead | R16 | 2019-02-28 | 1 |  | 21 | 23 | 43 | 2019 | 2019 | R16
167719225822 | 162050225822 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-19 | 2021-04-05 | 2021-04-05 |  | 2021-10-25 | Overhead | R16 | 2021-07-22 | 12 |  | 79 | 68 | 157 | 2021 | 2021 | R16
168017154751 | 161556154751 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-05-30 | 2019-05-30 | 2019-06-07 | 2020-08-05 | 2020-08-07 | Underground | R16 | 2020-08-05 | 1 | 7 | 304 | 3 | 312 | 2019 | 2020 | R16
164737146427 | 165864146427 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-01 | 2019-03-01 | 2019-03-18 | 2019-03-25 | 2019-03-25 | Underground | R16 | 2019-03-25 | 1 | 12 | 6 |  | 17 | 2019 | 2019 | R16
168798150675 | 166267150675 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-05 | 2019-04-30 | 2019-04-30 |  | 2019-08-26 | Overhead | R16 | 2019-06-24 | 41 |  | 40 | 46 | 125 | 2019 | 2019 | R16
161533222036 | 167502222036 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-01 | 2021-03-01 | 2021-03-01 |  | 2021-08-23 | Overhead | R16 | 2021-07-15 | 1 |  | 99 | 28 | 126 | 2021 | 2021 | R16
165605216096 | 164055216096 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-30 | 2021-01-05 | 2021-01-05 | 2021-02-22 | 2021-03-01 | Overhead | R16 | 2021-02-22 | 5 |  | 35 | 6 | 44 | 2020 | 2021 | R16
164924151500 | 167378151500 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-05-06 | 2019-05-06 | 2019-05-06 | 2019-10-29 | 2019-11-13 | Underground | R16 | 2019-10-29 | 1 |  | 127 | 12 | 138 | 2019 | 2019 | R16
168835144962 | 166170144962 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-04 | 2019-03-04 | 2019-03-04 |  | 2019-08-12 | Overhead | R16 | 2019-05-31 | 1 |  | 65 | 52 | 116 | 2019 | 2019 | R16
168839143925 | 164558143925 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-21 | 2019-02-21 | 2019-02-21 |  | 2020-06-09 | Overhead | R16 | 2020-01-30 | 1 |  | 246 | 94 | 339 | 2019 | 2020 | R16
164055236902 | 169035236902 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-21 | 2021-05-21 | 2021-06-28 | 2022-03-04 | 2022-03-25 | Underground | R16 | 2022-03-04 | 1 | 27 | 180 | 16 | 221 | 2021 | 2022 | R16
168840144563 | 165200144563 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-26 | 2019-02-28 | 2019-02-28 |  | 2019-12-19 | Underground | R16 | 2019-08-16 | 3 |  | 122 | 90 | 213 | 2019 | 2019 | R16
164059154558 | 162871154558 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-07 | 2019-06-07 | 2019-06-07 |  | 2019-10-28 | Overhead | R16 | 2019-10-16 | 1 |  | 94 | 9 | 102 | 2019 | 2019 | R16
165850223710 | 160606223710 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-15 | 2021-03-15 | 2021-03-15 | 2021-05-21 | 2021-08-23 | Overhead | R16 | 2021-05-21 | 1 |  | 50 | 67 | 116 | 2021 | 2021 | R16
168290229220 | 162293229220 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-02 | 2021-05-02 | 2021-05-02 |  | 2022-02-02 | Overhead | R16 | 2021-12-15 | 0 |  | 163 | 36 | 198 | 2021 | 2022 | R16
164929210995 | 165327210995 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-17 | 2020-11-17 | 2020-11-17 | 2021-11-30 | 2022-01-13 | Overhead | R16 | 2021-11-30 | 1 |  | 271 | 33 | 303 | 2020 | 2022 | R16
168852142233 | 161375142233 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-02-05 | 2019-02-05 | 2019-02-05 |  | 2021-06-03 | Underground | R16 | 2021-03-12 | 1 |  | 549 | 60 | 608 | 2019 | 2021 | R16
160903201271 | 165510201271 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-20 | 2020-08-20 | 2020-08-20 | 2020-08-21 | 2020-10-06 | Underground | R16 | 2020-08-21 | 1 |  | 2 | 33 | 34 | 2020 | 2020 | R16
168056226122 | 166362226122 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-07 | 2021-04-07 | 2021-04-07 |  | 2022-10-17 | Overhead | R16 |  | 1 |  |  |  | 399 | 2021 | 2022 | R16
168858234833 | 164782234833 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-02-22 | 2019-02-22 | 2021-06-15 |  | 2021-10-25 | Underground | R16 | 2021-09-17 | 1 | 603 | 69 | 27 | 697 | 2019 | 2021 | R16
161274151982 | 168164151982 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-09 | 2019-05-09 | 2019-05-09 |  | 2019-09-03 | Overhead | R16 | 2019-07-30 | 1 |  | 59 | 26 | 84 | 2019 | 2019 | R16
167224222810 | 169338222810 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2021-03-09 | 2021-03-09 | 2021-03-09 | 2021-03-23 | 2021-08-06 | Overhead | R16 | 2021-03-23 | 1 |  | 11 | 99 | 109 | 2021 | 2021 | R16
163615155752 | 169586155752 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-05-17 | 2019-05-17 | 2019-06-19 |  | 2019-09-03 | Overhead | R16 | 2019-08-05 | 1 | 24 | 34 | 22 | 78 | 2019 | 2019 | R16
168886142213 | 161079142213 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-02-04 | 2019-02-04 | 2019-02-04 |  | 2020-06-08 | Underground | R16 | 2020-02-03 | 1 |  | 261 | 91 | 351 | 2019 | 2020 | R16
160114149435 | 164193149435 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-04-18 | 2019-04-18 | 2019-04-18 |  | 2019-08-12 | Overhead | R16 | 2019-06-21 | 1 |  | 47 | 37 | 83 | 2019 | 2019 | R16
168716213618 | 167889213618 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-01 | 2020-12-01 | 2020-12-11 | 2021-02-01 | 2021-04-29 | Underground | R16 | 2021-02-01 | 1 | 9 | 37 | 64 | 108 | 2020 | 2021 | R16
160908228058 | 163689228058 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-11 | 2021-02-11 | 2021-04-23 | 2021-05-05 | 2021-11-02 | Underground | R16 | 2021-05-05 | 1 | 52 | 9 | 130 | 189 | 2021 | 2021 | R16
164849235506 | 165353235506 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-14 | 2021-05-14 | 2021-06-18 |  | 2021-10-25 | Underground | R16 | 2021-09-09 | 1 | 26 | 60 | 33 | 117 | 2021 | 2021 | R16
168171222031 | 164479222031 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-16 | 2021-03-01 | 2021-03-01 | 2021-11-11 | 2022-04-01 | Overhead | R16 | 2021-11-11 | 10 |  | 184 | 102 | 294 | 2021 | 2022 | R16
166479157913 | 160906157913 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-04-01 | 2019-06-06 | 2019-07-16 | 2019-08-26 | 2019-11-12 | Underground | R16 | 2019-08-26 | 49 | 29 | 30 | 57 | 162 | 2019 | 2019 | R16
162410206495 | 166385206495 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-07 | 2020-10-07 | 2020-10-07 |  | 2021-07-14 | Overhead | R16 | 2020-11-23 | 1 |  | 34 | 168 | 201 | 2020 | 2021 | R16
163536217870 | 167753217870 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-01-18 | 2021-01-18 | 2021-01-21 |  | 2021-04-29 | Underground | R16 | 2021-02-09 | 1 | 4 | 14 | 58 | 74 | 2021 | 2021 | R16
168897196726 | 164725196726 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-02-22 | 2019-02-22 | 2020-07-08 | 2020-07-14 | 2020-10-06 | Underground | R16 | 2020-07-14 | 1 | 359 | 5 | 61 | 423 | 2019 | 2020 | R16
168662218839 | 160638218839 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-28 | 2021-01-28 | 2021-01-28 |  | 2021-10-28 | Overhead | R16 | 2021-06-02 | 1 |  | 90 | 107 | 196 | 2021 | 2021 | R16
168977276393 | 168749276393 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-03-30 | 2022-03-30 | 2022-04-19 |  | 2023-03-02 | Underground | R16 |  | 1 | 15 |  |  | 242 | 2022 | 2023 | R16
163443209922 | 160878209922 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-27 | 2020-10-27 | 2020-11-06 | 2021-06-02 | 2021-08-26 | Underground | R16 | 2021-06-02 | 1 | 9 | 149 | 62 | 218 | 2020 | 2021 | R16
168978142707 | 162412142707 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-08 | 2019-02-08 | 2019-02-08 |  | 2019-05-28 | Overhead | R16 | 2019-04-23 | 1 |  | 53 | 26 | 78 | 2019 | 2019 | R16
168987141867 | 160587141867 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-31 | 2019-01-31 | 2019-01-31 |  | 2019-04-15 | Overhead | R16 | 2019-03-08 | 1 |  | 27 | 27 | 53 | 2019 | 2019 | R16
163048222400 | 167767222400 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-03 | 2021-03-03 | 2021-03-03 |  | 2021-08-23 | Overhead | R16 | 2021-07-15 | 1 |  | 97 | 28 | 124 | 2021 | 2021 | R16
169017149570 | 164066149570 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-17 | 2019-04-17 | 2019-04-17 |  | 2019-06-03 | Overhead | R16 | 2019-05-06 | 1 |  | 14 | 21 | 34 | 2019 | 2019 | R16
161245211233 | 166801211233 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-10-08 | 2020-11-03 | 2020-11-19 |  | 2021-07-12 | Overhead | R16 |  | 19 | 13 |  |  | 198 | 2020 | 2021 | R16
169053162543 | 168409162543 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-05-10 | 2019-05-10 | 2019-08-27 |  | 2020-06-09 | Overhead | R16 |  | 1 | 78 |  |  | 283 | 2019 | 2020 | R16
169062170214 | 169239170214 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-05-15 | 2019-06-07 | 2019-10-31 |  | 2020-09-01 | Underground | R16 |  | 18 | 105 |  |  | 340 | 2019 | 2020 | R16
166864151362 | 166870151362 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-02 | 2019-05-02 | 2019-05-06 |  | 2019-08-12 | Overhead | R16 | 2019-06-05 | 1 | 3 | 23 | 49 | 73 | 2019 | 2019 | R16
161619230508 | 161635230508 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-02-02 | 2021-04-16 | 2021-05-13 |  | 2021-10-25 | Overhead | R16 |  | 54 | 20 |  |  | 190 | 2021 | 2021 | R16
169083142256 | 169140142256 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-25 | 2019-01-25 | 2019-02-05 |  | 2019-04-01 | Underground | R16 | 2019-02-28 | 1 | 8 | 18 | 23 | 47 | 2019 | 2019 | R16
169711213176 | 169458213176 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-08 | 2020-12-08 | 2020-12-08 |  | 2021-04-23 | Overhead | R16 | 2021-02-02 | 1 |  | 41 | 59 | 99 | 2020 | 2021 | R16
169094209526 | 161645209526 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-31 | 2020-10-31 | 2020-11-03 |  | 2021-07-19 | Underground | R16 |  | 0 | 2 |  |  | 186 | 2020 | 2021 | R16
168680247847 | 162251247847 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-22 | 2021-03-22 | 2021-09-14 |  | 2022-08-24 | Underground | R16 | 2022-08-23 | 1 | 127 | 246 | 2 | 373 | 2021 | 2022 | R16
169153191367 | 169715191367 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-25 | 2019-03-25 | 2020-05-19 |  | 2020-09-16 | Underground | R16 | 2020-07-08 | 1 | 302 | 37 | 51 | 388 | 2019 | 2020 | R16
169155141886 | 160643141886 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-31 | 2019-01-31 | 2019-01-31 |  | 2019-04-08 | Overhead | R16 | 2019-03-05 | 1 |  | 24 | 25 | 48 | 2019 | 2019 | R16
162803234083 | 160182234083 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-07-27 | 2020-12-17 | 2021-06-08 | 2021-08-19 | 2021-10-18 | Underground | R16 | 2021-08-19 | 104 | 124 | 53 | 43 | 321 | 2020 | 2021 | R16
169171239340 | 162608239340 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2019-07-29 | 2019-09-05 | 2021-07-16 |  | 2021-08-23 | Overhead | R16 |  | 29 | 487 |  |  | 541 | 2019 | 2021 | R16
163701227683 | 165559227683 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-05 | 2021-04-05 | 2021-04-19 |  | 2021-12-02 | Underground | R16 | 2021-11-04 | 1 | 11 | 144 | 21 | 174 | 2021 | 2021 | R16
169279149305 | 169514149305 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-23 | 2019-03-23 | 2019-04-15 |  | 2019-08-12 | Underground | R16 | 2019-05-29 | 0 | 16 | 33 | 54 | 101 | 2019 | 2019 | R16
161421236963 | 160952236963 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-06-01 | 2021-06-01 | 2021-06-28 | 2021-12-28 | 2021-12-30 | Underground | R16 | 2021-12-28 | 1 | 20 | 132 | 3 | 153 | 2021 | 2021 | R16
168785154755 | 162902154755 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-08 | 2019-06-08 | 2019-06-08 | 2019-07-16 | 2019-08-26 | Overhead | R16 | 2019-07-16 | 0 |  | 27 | 30 | 56 | 2019 | 2019 | R16
160941222358 | 166200222358 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2021-01-11 | 2021-03-03 | 2021-03-03 | 2021-03-08 | 2021-03-31 | Overhead | R16 | 2021-03-08 | 38 |  | 4 | 18 | 58 | 2021 | 2021 | R16
169354185349 | 166572185349 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-03-17 | 2020-03-18 | 2020-03-25 |  | 2022-02-01 | Underground | R16 |  | 2 | 6 |  |  | 491 | 2020 | 2022 | R16
162512223318 | 167927223318 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-01-19 | 2021-01-19 | 2021-03-11 |  | 2021-11-05 | Underground | R16 |  | 1 | 38 |  |  | 209 | 2021 | 2021 | R16
169364142923 | 162367142923 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-02-08 | 2019-02-08 | 2019-02-11 |  | 2019-08-12 | Underground | R16 | 2019-06-03 | 1 | 2 | 81 | 51 | 132 | 2019 | 2019 | R16
169330209321 | 163494209321 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-08-12 | 2020-09-28 | 2020-11-02 | 2021-05-05 | 2022-08-03 | Underground | R16 | 2021-05-05 | 34 | 26 | 133 | 326 | 516 | 2020 | 2022 | R16
169369144222 | 164981144222 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-25 | 2019-02-25 | 2019-02-25 |  | 2019-04-22 | Overhead | R16 | 2019-03-15 | 1 |  | 15 | 27 | 41 | 2019 | 2019 | R16
169452146854 | 169581146854 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-22 | 2019-03-23 | 2019-03-23 |  | 2019-05-20 | Overhead | R16 | 2019-04-18 | 1 |  | 19 | 23 | 42 | 2019 | 2019 | R16
160528203773 | 160972203773 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-09-15 | 2020-09-15 | 2020-09-15 | 2020-10-13 | 2020-10-14 | Underground | R16 | 2020-10-13 | 1 |  | 21 | 2 | 22 | 2020 | 2020 | R16
169454143829 | 164488143829 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-21 | 2019-02-21 | 2019-02-21 |  | 2019-04-22 | Overhead | R16 | 2019-04-12 | 1 |  | 37 | 7 | 43 | 2019 | 2019 | R16
164860140397 | 167407140397 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-15 | 2019-01-15 | 2019-01-16 | 2021-11-16 | 2022-01-04 | Overhead | R16 | 2021-11-16 | 1 | 2 | 740 | 36 | 776 | 2019 | 2022 | R16
169472151108 | 166823151108 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-02 | 2019-05-02 | 2019-05-02 |  | 2019-08-12 | Overhead | R16 | 2019-05-22 | 1 |  | 15 | 59 | 73 | 2019 | 2019 | R16
164929151837 | 168284151837 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-10 | 2019-05-10 | 2019-05-10 | 2019-08-20 | 2019-12-04 | Overhead | R16 | 2019-08-20 | 1 |  | 73 | 77 | 149 | 2019 | 2019 | R16
169495145910 | 167890145910 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-12 | 2019-03-12 | 2019-03-12 |  | 2019-05-20 | Overhead | R16 | 2019-04-17 | 1 |  | 27 | 24 | 50 | 2019 | 2019 | R16
160916220989 | 162801220989 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-23 | 2020-09-23 | 2021-02-19 | 2021-03-15 | 2021-08-02 | Underground | R16 | 2021-03-15 | 1 | 108 | 17 | 101 | 224 | 2020 | 2021 | R16
167147149054 | 161754149054 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-04-05 | 2019-04-05 | 2019-04-12 |  | 2019-05-28 | Overhead | R16 |  | 1 | 6 |  |  | 38 | 2019 | 2019 | R16
160906220925 | 164731220925 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-18 | 2021-02-18 | 2021-02-18 | 2021-04-30 | 2021-11-05 | Overhead | R16 | 2021-04-30 | 1 |  | 52 | 136 | 187 | 2021 | 2021 | R16
164511153854 | 160691153854 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-05-23 | 2019-05-24 | 2019-05-31 |  | 2019-08-12 | Overhead | R16 |  | 2 | 6 |  |  | 58 | 2019 | 2019 | R16
169566145732 | 167696145732 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-12 | 2019-03-12 | 2019-03-12 |  | 2019-04-15 | Underground | R16 | 2019-03-28 | 1 |  | 13 | 13 | 25 | 2019 | 2019 | R16
162816150630 | 165185150630 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-24 | 2019-04-24 | 2019-04-30 |  | 2022-09-29 | Overhead | R16 |  | 1 | 5 |  |  | 897 | 2019 | 2022 | R16
165929153124 | 160295153124 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-22 | 2019-05-22 | 2019-05-22 | 2019-06-24 | 2023-06-08 | Overhead | R16 | 2019-06-24 | 1 |  | 24 | 1034 | 1057 | 2019 | 2023 | R16
169580150249 | 165331150249 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-24 | 2019-04-24 | 2019-04-24 |  | 2019-07-08 | Overhead | R16 | 2019-07-01 | 1 |  | 49 | 6 | 54 | 2019 | 2019 | R16
169581155235 | 164110155235 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-14 | 2019-06-14 | 2019-06-14 |  | 2019-10-30 | Underground | R16 | 2019-10-22 | 1 |  | 93 | 7 | 99 | 2019 | 2019 | R16
167164144271 | 165088144271 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-25 | 2019-02-25 | 2019-02-26 | 2020-03-19 | 2023-01-23 | Overhead | R16 | 2020-03-19 | 1 | 2 | 278 | 743 | 1021 | 2019 | 2023 | R16
169584149027 | 163356149027 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-13 | 2019-04-13 | 2019-04-13 |  | 2019-05-28 | Overhead | R16 | 2019-05-01 | 0 |  | 13 | 20 | 32 | 2019 | 2019 | R16
169189212541 | 168212212541 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-12-02 | 2020-12-02 | 2020-12-02 | 2021-01-11 | 2021-04-20 | Overhead | R16 | 2021-01-11 | 1 |  | 29 | 72 | 100 | 2020 | 2021 | R16
168600227939 | 169685227939 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-21 | 2021-04-21 | 2021-04-21 | 2021-05-18 | 2021-11-08 | Underground | R16 | 2021-05-18 | 1 |  | 20 | 125 | 144 | 2021 | 2021 | R16
161685222017 | 166239222017 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-24 | 2021-02-24 | 2021-03-03 |  | 2021-11-05 | Underground | R16 | 2021-04-09 | 1 | 6 | 28 | 151 | 183 | 2021 | 2021 | R16
160932241856 | 168206241856 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-03-04 | 2021-03-04 | 2021-08-03 | 2021-08-26 | 2021-08-30 | Overhead | R16 | 2021-08-26 | 1 | 109 | 18 | 3 | 128 | 2021 | 2021 | R16
160218144407 | 165368144407 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-27 | 2019-02-27 | 2019-02-27 |  | 2019-04-15 | Overhead | R16 | 2019-03-26 | 1 |  | 20 | 15 | 34 | 2019 | 2019 | R16
167409240275 | 160097240275 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-03-11 | 2021-07-22 | 2021-07-23 | 2021-08-31 | 2021-09-01 | Overhead | R16 | 2021-08-31 | 96 | 2 | 28 | 2 | 125 | 2021 | 2021 | R16
167742214436 | 162617214436 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-22 | 2020-12-22 | 2020-12-22 |  | 2021-11-10 | Overhead | R16 | 2021-10-14 | 1 |  | 213 | 20 | 232 | 2020 | 2021 | R16
164577201185 | 165171201185 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-19 | 2020-08-19 | 2020-08-19 | 2020-08-24 | 2020-10-06 | Overhead | R16 | 2020-08-24 | 1 |  | 4 | 32 | 35 | 2020 | 2020 | R16
160252142971 | 162698142971 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-11 | 2019-02-11 | 2019-02-11 |  | 2019-04-15 | Underground | R16 | 2019-03-12 | 1 |  | 22 | 25 | 46 | 2019 | 2019 | R16
169701205658 | 164487205658 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-29 | 2020-09-29 | 2020-09-29 |  | 2021-01-20 | Overhead | R16 | 2020-10-12 | 1 |  | 10 | 73 | 82 | 2020 | 2021 | R16
160259145034 | 166694145034 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-06 | 2019-03-06 | 2019-03-06 |  | 2019-08-12 | Overhead | R16 | 2019-06-05 | 1 |  | 66 | 49 | 114 | 2019 | 2019 | R16
160287145901 | 167851145901 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-12 | 2019-03-12 | 2019-03-12 |  | 2019-05-20 | Overhead | R16 | 2019-04-17 | 1 |  | 27 | 24 | 50 | 2019 | 2019 | R16
163753226332 | 165947226332 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-06 | 2021-04-06 | 2021-04-09 | 2021-05-24 | 2021-11-04 | Underground | R16 | 2021-05-24 | 1 | 4 | 32 | 119 | 153 | 2021 | 2021 | R16
160288146846 | 166645146846 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-06 | 2019-03-06 | 2019-03-22 |  | 2021-11-13 | Overhead | R16 | 2019-12-23 | 1 | 13 | 197 | 495 | 703 | 2019 | 2021 | R16
160018210785 | 164906210785 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-15 | 2020-11-15 | 2020-11-15 |  | 2022-09-01 | Overhead | R16 |  | 0 |  |  |  | 469 | 2020 | 2022 | R16
164183237920 | 161225237920 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-02 | 2021-06-02 | 2021-07-06 | 2021-09-01 | 2021-10-27 | Underground | R16 | 2021-09-01 | 1 | 25 | 42 | 41 | 106 | 2021 | 2021 | R16
160292151897 | 163006151897 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2019-04-11 | 2019-04-12 | 2019-05-10 |  | 2020-06-09 | Underground | R16 |  | 2 | 21 |  |  | 304 | 2019 | 2020 | R16
160894233083 | 164702233083 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-05-11 | 2021-06-01 | 2021-06-01 |  | 2022-01-12 | Underground | R16 | 2021-12-03 | 16 |  | 134 | 29 | 177 | 2021 | 2022 | R16
160297148011 | 161495148011 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-03 | 2019-04-03 | 2019-04-03 |  | 2019-05-28 | Overhead | R16 | 2019-05-02 | 1 |  | 22 | 19 | 40 | 2019 | 2019 | R16
160439170471 | 165958170471 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-04-29 | 2019-05-03 | 2019-11-01 | 2019-12-23 | 2019-12-26 | Underground | R16 | 2019-12-23 | 5 | 131 | 37 | 4 | 174 | 2019 | 2019 | R16
160299150074 | 164165150074 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-04-18 | 2019-04-18 | 2019-04-23 |  | 2019-08-12 | Underground | R16 | 2019-05-22 | 1 | 4 | 22 | 59 | 83 | 2019 | 2019 | R16
160333188935 | 164771188935 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-02-22 | 2020-02-06 | 2020-04-24 |  | 2021-11-10 | Underground | R16 | 2020-05-11 | 250 | 57 | 12 | 393 | 709 | 2019 | 2021 | R16
162437150281 | 165225150281 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-24 | 2019-04-24 | 2019-04-24 |  | 2019-08-26 | Overhead | R16 | 2019-07-26 | 1 |  | 68 | 22 | 89 | 2019 | 2019 | R16
160342151855 | 166940151855 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-02 | 2019-05-02 | 2019-05-09 |  | 2019-08-12 | Overhead | R16 | 2019-06-12 | 1 | 6 | 25 | 44 | 73 | 2019 | 2019 | R16
165428152772 | 169684152772 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-18 | 2019-05-18 | 2019-05-18 | 2019-07-30 | 2019-09-03 | Overhead | R16 | 2019-07-30 | 0 |  | 52 | 26 | 77 | 2019 | 2019 | R16
166025154680 | 166084154680 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-04-30 | 2019-04-30 | 2019-06-06 |  | 2019-12-30 | Underground | R16 |  | 1 | 28 |  |  | 175 | 2019 | 2019 | R16
160356145390 | 167304145390 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-08 | 2019-03-08 | 2019-03-08 |  | 2019-11-13 | Overhead | R16 | 2019-11-04 | 1 |  | 172 | 8 | 179 | 2019 | 2019 | R16
164126226581 | 166309226581 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2021-02-24 | 2021-03-24 | 2021-04-12 | 2021-08-19 | 2022-05-11 | Underground | R16 | 2021-08-19 | 21 | 14 | 94 | 190 | 316 | 2021 | 2022 | R16
164320221601 | 166275221601 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-24 | 2021-02-24 | 2021-02-24 | 2021-03-17 | 2021-08-11 | Overhead | R16 | 2021-03-17 | 1 |  | 16 | 106 | 121 | 2021 | 2021 | R16
160408145352 | 167267145352 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-08 | 2019-03-08 | 2019-03-08 |  | 2023-06-07 | Overhead | R16 | 2019-04-04 | 1 |  | 20 | 1090 | 1109 | 2019 | 2023 | R16
161742213499 | 169914213499 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-12-10 | 2020-12-10 | 2020-12-10 | 2021-05-10 | 2021-06-15 | Overhead | R16 | 2021-05-10 | 1 |  | 108 | 27 | 134 | 2020 | 2021 | R16
163683200156 | 160018200156 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-07-24 | 2020-07-29 | 2020-08-11 |  | 2021-08-23 | Underground | R16 |  | 4 | 10 |  |  | 282 | 2020 | 2021 | R16
160443141797 | 160415141797 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-31 | 2019-01-31 | 2019-01-31 |  | 2019-04-01 | Overhead | R16 | 2019-03-01 | 1 |  | 22 | 22 | 43 | 2019 | 2019 | R16
163713151636 | 167951151636 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-08 | 2019-05-08 | 2019-05-08 |  | 2019-10-16 | Overhead | R16 | 2019-10-08 | 1 |  | 110 | 7 | 116 | 2019 | 2019 | R16
166743197680 | 168639197680 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-16 | 2020-07-16 | 2020-07-16 |  | 2020-12-29 | Overhead | R16 | 2020-09-30 | 1 |  | 55 | 65 | 119 | 2020 | 2020 | R16
166987227639 | 169360227639 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-20 | 2021-04-20 | 2021-04-20 |  | 2023-01-12 | Overhead | R16 |  | 1 |  |  |  | 453 | 2021 | 2023 | R16
162852222344 | 166339222344 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-10-07 | 2020-10-28 | 2021-03-03 |  | 2021-11-08 | Overhead | R16 | 2021-05-18 | 16 | 91 | 55 | 125 | 284 | 2020 | 2021 | R16
160465146261 | 161256146261 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-05 | 2019-02-05 | 2019-03-15 |  | 2019-06-03 | Underground | R16 | 2019-05-10 | 1 | 29 | 41 | 17 | 85 | 2019 | 2019 | R16
166444145933 | 167893145933 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-12 | 2019-03-12 | 2019-03-12 | 2019-12-11 | 2019-12-17 | Overhead | R16 | 2019-12-11 | 1 |  | 197 | 5 | 201 | 2019 | 2019 | R16
160554144167 | 164982144167 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-02-25 | 2019-02-25 | 2019-02-25 |  | 2021-11-15 | Underground | R16 | 2019-09-18 | 1 |  | 148 | 564 | 711 | 2019 | 2021 | R16
166134221994 | 167452221994 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-01 | 2021-03-01 | 2021-03-01 |  | 2022-02-28 | Overhead | R16 | 2022-01-26 | 1 |  | 238 | 24 | 261 | 2021 | 2022 | R16
160558143810 | 164519143810 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-02-21 | 2019-02-21 | 2019-02-21 |  | 2019-05-20 | Overhead | R16 | 2019-04-12 | 1 |  | 37 | 27 | 63 | 2019 | 2019 | R16
169737148676 | 162418148676 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-09 | 2019-04-09 | 2019-04-09 |  | 2020-10-06 | Overhead | R16 |  | 1 |  |  |  | 391 | 2019 | 2020 | R16
160616149079 | 163128149079 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-12 | 2019-04-12 | 2019-04-12 |  | 2019-11-08 | Overhead | R16 | 2019-10-30 | 1 |  | 144 | 8 | 151 | 2019 | 2019 | R16
161887218510 | 166937218510 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-11-24 | 2020-11-24 | 2021-01-26 | 2021-01-27 | 2021-02-04 | Overhead | R16 | 2021-01-27 | 1 | 46 | 2 | 7 | 53 | 2020 | 2021 | R16
169802157009 | 161712157009 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-31 | 2019-05-31 | 2019-07-03 | 2019-07-25 | 2019-08-26 | Underground | R16 | 2019-07-25 | 1 | 24 | 17 | 23 | 62 | 2019 | 2019 | R16
160624143818 | 164823143818 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-22 | 2019-02-22 | 2019-02-22 |  | 2019-05-20 | Overhead | R16 | 2019-04-19 | 1 |  | 41 | 22 | 62 | 2019 | 2019 | R16
163170219140 | 169480219140 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-25 | 2021-01-29 | 2021-01-29 | 2021-03-17 | 2021-08-11 | Overhead | R16 | 2021-03-17 | 5 |  | 34 | 106 | 143 | 2021 | 2021 | R16
160645152617 | 167551152617 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-05-06 | 2019-05-07 | 2019-05-17 |  | 2020-01-08 | Overhead | R16 | 2019-12-30 | 2 | 9 | 162 | 8 | 178 | 2019 | 2020 | R16
162197207660 | 168611207660 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-10-18 | 2020-10-18 | 2020-10-18 |  | 2021-11-08 | Overhead | R16 | 2021-05-12 | 0 |  | 148 | 129 | 276 | 2020 | 2021 | R16
165020210176 | 162921210176 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-08-10 | 2020-08-10 | 2020-11-10 |  | 2022-03-07 | Overhead | R16 |  | 1 | 67 |  |  | 411 | 2020 | 2022 | R16
161000202312 | 166201202312 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-24 | 2020-08-24 | 2020-09-01 |  | 2023-02-06 | Underground | R16 |  | 1 | 7 |  |  | 641 | 2020 | 2023 | R16
165824210787 | 164012210787 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-10 | 2020-11-16 | 2020-11-16 | 2020-11-22 | 2021-03-22 | Underground | R16 | 2020-11-22 | 5 |  | 5 | 86 | 95 | 2020 | 2021 | R16
160622156244 | 160912156244 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-24 | 2019-05-24 | 2019-06-24 |  | 2019-09-03 | Underground | R16 | 2019-08-05 | 1 | 22 | 31 | 22 | 73 | 2019 | 2019 | R16
168743151105 | 166901151105 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-05-02 | 2019-05-02 | 2019-05-02 |  | 2022-06-01 | Underground | R16 |  | 1 |  |  |  | 805 | 2019 | 2022 | R16
167695148983 | 162809148983 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-10 | 2019-04-10 | 2019-04-11 | 2019-09-17 | 2023-06-08 | Overhead | R16 | 2019-09-17 | 1 | 2 | 114 | 973 | 1087 | 2019 | 2023 | R16
160768145682 | 167501145682 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-03-11 | 2019-03-11 | 2019-03-11 |  | 2020-07-14 | Underground | R16 | 2020-06-18 | 1 |  | 334 | 19 | 352 | 2019 | 2020 | R16
163357197674 | 168838197674 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-17 | 2020-07-17 | 2020-07-17 |  | 2021-07-01 | Overhead | R16 | 2020-08-05 | 1 |  | 14 | 237 | 250 | 2020 | 2021 | R16
168807249131 | 166759249131 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-04-08 | 2021-09-22 | 2021-09-23 | 2022-04-22 | 2022-04-29 | Underground | R16 | 2022-04-22 | 120 | 2 | 152 | 6 | 277 | 2021 | 2022 | R16
169366213416 | 167769213416 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-10-14 | 2020-12-10 | 2020-12-10 | 2021-01-05 | 2021-04-16 | Overhead | R16 | 2021-01-05 | 42 |  | 19 | 74 | 133 | 2020 | 2021 | R16
163691221015 | 165025221015 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-18 | 2021-02-22 | 2021-02-22 | 2021-04-01 | 2021-11-04 | Overhead | R16 | 2021-04-01 | 3 |  | 29 | 156 | 186 | 2021 | 2021 | R16
168260151633 | 167835151633 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-07 | 2019-05-07 | 2019-05-07 |  | 2019-08-12 | Overhead | R16 | 2019-06-14 | 1 |  | 29 | 42 | 70 | 2019 | 2019 | R16
160820142168 | 161083142168 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-02-04 | 2019-02-04 | 2019-02-04 |  | 2019-04-01 | Overhead | R16 | 2019-02-26 | 1 |  | 17 | 25 | 41 | 2019 | 2019 | R16
168524230317 | 164401230317 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-30 | 2021-05-12 | 2021-05-12 | 2021-05-19 | 2021-08-23 | Overhead | R16 | 2021-05-19 | 32 |  | 6 | 69 | 105 | 2021 | 2021 | R16
160731160526 | 161887160526 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-03 | 2019-06-03 | 2019-08-08 | 2019-10-16 | 2019-10-17 | Underground | R16 | 2019-10-16 | 1 | 49 | 50 | 2 | 99 | 2019 | 2019 | R16
160825183065 | 162757183065 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-02-26 | 2020-02-26 | 2020-03-05 |  | 2020-11-02 | Overhead | R16 |  | 1 | 7 |  |  | 179 | 2020 | 2020 | R16
160834144643 | 160857144643 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-01 | 2019-02-01 | 2019-03-01 |  | 2021-04-15 | Underground | R16 | 2020-12-22 | 1 | 21 | 473 | 83 | 575 | 2019 | 2021 | R16
164660149029 | 169660149029 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-24 | 2019-03-24 | 2019-04-13 |  | 2019-08-12 | Underground | R16 | 2019-06-19 | 0 | 15 | 48 | 39 | 101 | 2019 | 2019 | R16
164077230820 | 164092230820 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-05-10 | 2021-05-10 | 2021-05-14 | 2021-07-15 | 2021-07-19 | Underground | R16 | 2021-07-15 | 1 | 5 | 45 | 3 | 51 | 2021 | 2021 | R16
167091212080 | 167230212080 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-12 | 2020-10-12 | 2020-11-25 |  | 2021-04-16 | Underground | R16 | 2021-01-06 | 1 | 33 | 31 | 73 | 135 | 2020 | 2021 | R16
161560152491 | 169151152491 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-03-20 | 2019-03-20 | 2019-05-16 |  | 2020-06-09 | Underground | R16 | 2020-01-21 | 1 | 42 | 179 | 101 | 320 | 2019 | 2020 | R16
160959147589 | 160722147589 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-29 | 2019-03-29 | 2019-03-29 |  | 2019-05-28 | Overhead | R16 | 2019-04-23 | 1 |  | 18 | 26 | 43 | 2019 | 2019 | R16
162100208670 | 164266208670 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-28 | 2020-10-06 | 2020-10-27 | 2021-01-05 | 2021-01-05 | Underground | R16 | 2021-01-05 | 7 | 16 | 51 |  | 72 | 2020 | 2021 | R16
160962149041 | 162778149041 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-10 | 2019-04-10 | 2019-04-12 |  | 2019-06-03 | Overhead | R16 | 2019-05-06 | 1 | 3 | 17 | 21 | 39 | 2019 | 2019 | R16
163552151795 | 168279151795 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-10 | 2019-05-10 | 2019-05-10 |  | 2019-08-12 | Overhead | R16 | 2019-06-18 | 1 |  | 28 | 40 | 67 | 2019 | 2019 | R16
161220149359 | 168199149359 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | R16 RESD AND NON RESD US | Commercial | 2019-03-14 | 2019-03-14 | 2019-04-17 | 2019-07-09 | 2019-07-09 | Underground | R16 | 2019-07-09 | 1 | 25 | 60 |  | 84 | 2019 | 2019 | R16
160536226143 | 166397226143 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-07 | 2021-04-07 | 2021-04-07 |  | 2021-08-26 | Overhead | R16 | 2021-06-07 | 1 |  | 44 | 59 | 102 | 2021 | 2021 | R16
161105147348 | 169285147348 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-21 | 2019-03-27 | 2019-03-27 |  | 2019-05-20 | Overhead | R16 | 2019-04-18 | 5 |  | 17 | 23 | 43 | 2019 | 2019 | R16
161115145652 | 166715145652 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-07 | 2019-03-07 | 2019-03-11 |  | 2019-08-26 | Overhead | R16 | 2019-07-22 | 1 | 3 | 96 | 26 | 123 | 2019 | 2019 | R16
161118144586 | 165631144586 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-28 | 2019-02-28 | 2019-02-28 |  | 2020-06-09 | Underground | R16 | 2020-02-06 | 1 |  | 246 | 89 | 334 | 2019 | 2020 | R16
161574172458 | 166794172458 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential Subdivision | 2019-01-11 | 2019-05-12 | 2019-11-22 | 2021-09-27 | 2021-10-13 | Underground | R16 | 2021-09-27 | 86 | 140 | 482 | 13 | 719 | 2019 | 2021 | R16
161121143369 | 163775143369 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-02-15 | 2019-02-15 | 2019-02-15 |  | 2019-04-25 | Underground | R16 | 2019-03-21 | 1 |  | 25 | 26 | 50 | 2019 | 2019 | R16
164316209607 | 160918209607 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-28 | 2020-11-04 | 2020-11-04 |  | 2021-04-07 | Underground | R16 | 2020-11-30 | 6 |  | 19 | 93 | 116 | 2020 | 2021 | R16
160667221546 | 160802221546 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-29 | 2021-01-29 | 2021-02-24 |  | 2021-11-08 | Underground | R16 | 2021-05-26 | 1 | 19 | 66 | 119 | 202 | 2021 | 2021 | R16
161148147821 | 160950147821 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-31 | 2019-03-31 | 2019-03-31 |  | 2019-06-03 | Underground | R16 | 2019-05-07 | 0 |  | 27 | 20 | 46 | 2019 | 2019 | R16
161205152722 | 169365152722 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-16 | 2019-05-16 | 2019-05-16 |  | 2019-08-26 | Overhead | R16 | 2019-06-25 | 1 |  | 29 | 45 | 73 | 2019 | 2019 | R16
161163149882 | 163229149882 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-12 | 2019-04-12 | 2019-04-22 |  | 2022-08-02 | Overhead | R16 |  | 1 | 7 |  |  | 863 | 2019 | 2022 | R16
169768229360 | 162523229360 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-03 | 2021-05-03 | 2021-05-03 |  | 2022-02-07 | Overhead | R16 | 2022-01-11 | 1 |  | 182 | 20 | 201 | 2021 | 2022 | R16
164330204846 | 162909204846 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-24 | 2020-09-24 | 2020-09-24 | 2020-10-02 | 2021-07-26 | Overhead | R16 | 2020-10-02 | 1 |  | 7 | 212 | 218 | 2020 | 2021 | R16
161181147515 | 160421147515 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-28 | 2019-03-28 | 2019-03-28 |  | 2019-06-03 | Overhead | R16 | 2019-05-14 | 1 |  | 34 | 15 | 48 | 2019 | 2019 | R16
161185202819 | 169175202819 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-08 | 2020-09-08 | 2020-09-08 | 2020-10-07 | 2020-10-08 | Overhead | R16 | 2020-10-07 | 1 |  | 22 | 2 | 23 | 2020 | 2020 | R16
161260149013 | 161203149013 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-04-02 | 2019-04-02 | 2019-04-12 | 2019-06-11 | 2019-07-02 | Overhead | R16 | 2019-06-11 | 1 | 9 | 43 | 16 | 66 | 2019 | 2019 | R16
161197143307 | 163662143307 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-14 | 2019-02-14 | 2019-02-15 |  | 2019-06-03 | Underground | R16 | 2019-05-07 | 1 | 2 | 58 | 20 | 78 | 2019 | 2019 | R16
163645204491 | 162552204491 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-22 | 2020-09-22 | 2020-09-22 |  | 2021-04-14 | Overhead | R16 | 2020-12-10 | 1 |  | 58 | 90 | 147 | 2020 | 2021 | R16
167664271269 | 167045271269 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2021-04-09 | 2021-04-29 | 2022-03-03 | 2022-06-14 | 2022-10-04 | Underground | R16 | 2022-06-14 | 15 | 221 | 74 | 81 | 388 | 2021 | 2022 | R16
161223145820 | 167608145820 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-11 | 2019-03-12 | 2019-03-12 |  | 2019-04-15 | Overhead | R16 | 2019-03-26 | 2 |  | 11 | 15 | 26 | 2019 | 2019 | R16
161224144829 | 163250144829 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-13 | 2019-02-13 | 2019-03-04 |  | 2019-04-30 | Underground | R16 | 2019-04-04 | 1 | 14 | 24 | 19 | 55 | 2019 | 2019 | R16
160391204080 | 160783204080 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-09-14 | 2020-09-14 | 2020-09-16 | 2020-09-21 | 2020-09-22 | Underground | R16 | 2020-09-21 | 1 | 3 | 4 | 2 | 7 | 2020 | 2020 | R16
161229142307 | 161039142307 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-04 | 2019-02-04 | 2019-02-04 |  | 2022-08-02 | Overhead | R16 |  | 1 |  |  |  | 912 | 2019 | 2022 | R16
161241147195 | 169915147195 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-26 | 2019-03-26 | 2019-03-26 |  | 2019-08-12 | Overhead | R16 | 2019-06-12 | 1 |  | 57 | 44 | 100 | 2019 | 2019 | R16
160646200921 | 164468200921 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-18 | 2020-08-18 | 2020-08-18 |  | 2020-12-29 | Overhead | R16 | 2020-09-29 | 1 |  | 31 | 66 | 96 | 2020 | 2020 | R16
161225231169 | 165994231169 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-17 | 2021-05-17 | 2021-05-17 |  | 2021-10-25 | Overhead | R16 | 2021-09-21 | 1 |  | 92 | 25 | 116 | 2021 | 2021 | R16
161246143310 | 161776143310 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-06 | 2019-02-15 | 2019-02-15 |  | 2019-04-08 | Underground | R16 | 2019-03-04 | 8 |  | 12 | 26 | 44 | 2019 | 2019 | R16
164193218405 | 169363218405 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-12-08 | 2020-12-08 | 2021-01-25 |  | 2021-10-28 | Underground | R16 | 2021-07-29 | 1 | 35 | 134 | 66 | 233 | 2020 | 2021 | R16
161267154477 | 162573154477 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-06 | 2019-06-06 | 2019-06-06 |  | 2019-08-12 | Underground | R16 | 2019-06-20 | 1 |  | 11 | 38 | 48 | 2019 | 2019 | R16
161268153727 | 169215153727 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-05-15 | 2019-05-15 | 2019-05-29 |  | 2019-08-12 | Underground | R16 | 2019-06-05 | 1 | 11 | 6 | 49 | 64 | 2019 | 2019 | R16
161269164619 | 166672164619 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-05-01 | 2019-05-01 | 2019-09-17 |  | 2019-09-25 | Underground | R16 | 2019-09-18 | 1 | 100 | 2 | 6 | 106 | 2019 | 2019 | R16
160632254737 | 163695254737 | NON-RESIDENTIAL - MISCELLANEOUS | UG ELEC MISC SVC US | Commercial | 2021-05-07 | 2021-05-07 | 2021-11-03 |  | 2023-05-11 | Underground | R16 |  | 1 | 129 |  |  | 525 | 2021 | 2023 | R16
161287144802 | 161821144802 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-02-06 | 2019-02-06 | 2019-03-04 |  | 2019-06-03 | Overhead | R16 | 2019-05-14 | 1 | 19 | 52 | 15 | 84 | 2019 | 2019 | R16
164320201208 | 165478201208 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-21 | 2020-08-21 | 2020-08-21 | 2022-07-22 | 2022-07-28 | Overhead | R16 | 2022-07-22 | 1 |  | 501 | 5 | 505 | 2020 | 2022 | R16
161330145856 | 168071145856 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-03-13 | 2019-03-13 | 2019-03-13 |  | 2019-04-22 | Overhead | R16 | 2019-03-22 | 1 |  | 8 | 22 | 29 | 2019 | 2019 | R16
164117223196 | 160122223196 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-11 | 2021-03-11 | 2021-03-11 | 2021-03-26 | 2021-11-05 | Overhead | R16 | 2021-03-26 | 1 |  | 12 | 161 | 172 | 2021 | 2021 | R16
161331144396 | 165561144396 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-28 | 2019-02-28 | 2019-02-28 |  | 2019-06-03 | Overhead | R16 | 2019-05-16 | 1 |  | 56 | 13 | 68 | 2019 | 2019 | R16
168258236002 | 162815236002 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-04 | 2021-05-04 | 2021-06-21 | 2021-06-30 | 2022-03-08 | Underground | R16 | 2021-06-30 | 1 | 35 | 8 | 180 | 221 | 2021 | 2022 | R16
161429225969 | 164484225969 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-30 | 2021-03-30 | 2021-04-07 | 2021-04-12 | 2021-11-03 | Overhead | R16 | 2021-04-12 | 1 | 7 | 4 | 148 | 157 | 2021 | 2021 | R16
164522203307 | 169655203307 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-09 | 2020-09-09 | 2020-09-09 |  | 2021-01-20 | Overhead | R16 | 2020-10-08 | 1 |  | 22 | 75 | 96 | 2020 | 2021 | R16
161186167330 | 162325167330 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-04-08 | 2019-05-07 | 2019-10-08 | 2019-11-19 | 2019-11-19 | Underground | R16 | 2019-11-19 | 22 | 111 | 31 |  | 162 | 2019 | 2019 | R16
160732219673 | 162369219673 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-05 | 2021-02-05 | 2021-02-05 | 2021-03-26 | 2021-11-08 | Overhead | R16 | 2021-03-26 | 1 |  | 36 | 162 | 197 | 2021 | 2021 | R16
169753296081 | 169698296081 | NON-RESIDENTIAL - WAREHOUSE | UG R16 RESD AND NON RESD UD | Commercial | 2021-05-25 | 2021-05-25 | 2022-10-05 | 2023-06-23 | 2023-10-03 | Underground | R16 | 2023-06-23 | 1 | 357 | 188 | 73 | 616 | 2021 | 2023 | R16
163418226821 | 164763226821 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-17 | 2021-02-17 | 2021-04-13 |  | 2021-11-02 | Underground | R16 | 2021-06-03 | 1 | 40 | 38 | 109 | 185 | 2021 | 2021 | R16
161408142445 | 161446142445 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-02-05 | 2019-02-05 | 2019-02-05 |  | 2019-03-11 | Overhead | R16 |  | 1 |  |  |  | 25 | 2019 | 2019 | R16
164756216124 | 164516216124 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-04 | 2021-01-04 | 2021-01-04 | 2021-01-07 | 2021-05-06 | Overhead | R16 | 2021-01-07 | 1 |  | 4 | 86 | 89 | 2021 | 2021 | R16
166886218100 | 168851218100 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-01-22 | 2021-01-22 | 2021-01-22 | 2021-02-19 | 2021-09-09 | Overhead | R16 | 2021-02-19 | 1 |  | 21 | 145 | 165 | 2021 | 2021 | R16
161453143551 | 162890143551 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-11 | 2019-02-19 | 2019-02-20 |  | 2019-04-24 | Overhead | R16 | 2019-03-20 | 7 | 2 | 21 | 26 | 53 | 2019 | 2019 | R16
167323142376 | 161889142376 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-07 | 2019-02-07 | 2019-02-07 | 2019-02-26 | 2019-04-15 | Overhead | R16 | 2019-02-26 | 1 |  | 14 | 35 | 48 | 2019 | 2019 | R16
166542222251 | 167695222251 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-03-02 | 2021-03-02 | 2021-03-02 |  | 2021-11-04 | Overhead | R16 | 2021-06-02 | 1 |  | 67 | 112 | 178 | 2021 | 2021 | R16
168172157587 | 160071157587 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-20 | 2019-05-20 | 2019-07-11 | 2019-07-19 | 2019-09-03 | Underground | R16 | 2019-07-19 | 1 | 39 | 7 | 33 | 77 | 2019 | 2019 | R16
169264229201 | 162424229201 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-03 | 2021-05-03 | 2021-05-03 |  | 2021-11-02 | Overhead | R16 | 2021-06-15 | 1 |  | 32 | 101 | 132 | 2021 | 2021 | R16
167548154553 | 162549154553 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-06-06 | 2019-06-07 | 2019-06-07 | 2020-02-28 | 2021-11-15 | Underground | R16 | 2020-02-28 | 2 |  | 191 | 447 | 638 | 2019 | 2021 | R16
160507219614 | 162293219614 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-04 | 2021-02-04 | 2021-02-04 | 2021-06-29 | 2022-08-03 | Overhead | R16 | 2021-06-29 | 1 |  | 104 | 287 | 390 | 2021 | 2022 | R16
164023216344 | 165286216344 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-01-06 | 2021-01-06 | 2021-01-06 |  | 2021-08-23 | Overhead | R16 | 2021-06-21 | 1 |  | 119 | 46 | 164 | 2021 | 2021 | R16
163465238871 | 162042238871 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2020-09-21 | 2021-05-12 | 2021-07-14 | 2021-10-29 | 2022-06-23 | Overhead | R16 | 2021-10-29 | 168 | 46 | 78 | 170 | 459 | 2020 | 2022 | R16
162865150340 | 163034150340 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-12 | 2019-04-12 | 2019-04-25 | 2019-10-19 | 2020-02-06 | Underground | R16 | 2019-10-19 | 1 | 10 | 127 | 79 | 215 | 2019 | 2020 | R16
168320146325 | 167613146325 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-11 | 2019-03-11 | 2019-03-18 | 2019-04-04 | 2019-04-04 | Underground | R16 | 2019-04-04 | 1 | 6 | 14 |  | 19 | 2019 | 2019 | R16
164704139391 | 165586139391 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-01-07 | 2019-01-07 | 2019-01-07 | 2020-05-13 | 2020-07-09 | Overhead | R16 | 2020-05-13 | 1 |  | 353 | 42 | 394 | 2019 | 2020 | R16
161467152495 | 167012152495 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-05-02 | 2019-05-02 | 2019-05-16 |  | 2019-12-17 | Underground | R16 | 2019-12-05 | 1 | 11 | 146 | 9 | 164 | 2019 | 2019 | R16
161468164140 | 168236164140 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-29 | 2019-08-29 | 2019-09-11 |  | 2020-08-28 | Underground | R16 | 2020-07-01 | 1 | 10 | 211 | 43 | 262 | 2019 | 2020 | R16
166984204935 | 163493204935 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-02 | 2021-07-26 | Overhead | R16 | 2020-11-02 | 1 |  | 27 | 191 | 217 | 2020 | 2021 | R16
161511168275 | 163443168275 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-02 | 2019-10-07 | 2019-10-15 |  | 2021-11-10 | Overhead | R16 |  | 47 | 7 |  |  | 594 | 2019 | 2021 | R16
160928147750 | 164211147750 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-20 | 2019-02-20 | 2019-04-01 | 2020-07-09 | 2020-07-10 | Overhead | R16 | 2020-07-09 | 1 | 29 | 334 | 2 | 363 | 2019 | 2020 | R16
160410232603 | 164151232603 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-10 | 2021-05-27 | 2021-05-27 | 2021-07-16 | 2021-08-23 | Overhead | R16 | 2021-07-16 | 14 |  | 37 | 27 | 76 | 2021 | 2021 | R16
162253158143 | 162261158143 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-08 | 2019-04-08 | 2019-07-17 | 2019-08-02 | 2019-08-12 | Underground | R16 | 2019-08-02 | 1 | 73 | 13 | 7 | 91 | 2019 | 2019 | R16
161547162453 | 163121162453 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-02-12 | 2019-02-13 | 2019-08-27 |  | 2020-07-14 | Underground | R16 |  | 2 | 140 |  |  | 371 | 2019 | 2020 | R16
167113235932 | 166689235932 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-08 | 2021-06-15 | 2021-06-21 | 2021-09-15 | 2022-01-12 | Overhead | R16 | 2021-09-15 | 49 | 5 | 63 | 86 | 200 | 2021 | 2022 | R16
166630226119 | 166712226119 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-09-08 | 2021-10-25 | Overhead | R16 | 2021-09-08 | 1 |  | 110 | 34 | 143 | 2021 | 2021 | R16
161575142490 | 161787142490 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-02-06 | 2019-02-07 | 2019-02-07 |  | 2019-02-21 | Overhead | R16 | 2019-02-07 | 2 |  |  | 11 | 12 | 2019 | 2019 | R16
161592148341 | 161145148341 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-02 | 2019-04-02 | 2019-04-05 |  | 2020-06-09 | Underground | R16 | 2020-02-24 | 1 | 4 | 232 | 77 | 311 | 2019 | 2020 | R16
162721227696 | 168305227696 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-16 | 2021-04-20 | 2021-04-20 | 2021-05-18 | 2021-10-25 | Overhead | R16 | 2021-05-18 | 3 |  | 21 | 115 | 137 | 2021 | 2021 | R16
163101153604 | 163591153604 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-02-14 | 2019-02-14 | 2019-05-28 | 2020-06-03 | 2020-08-12 | Underground | R16 | 2020-06-03 | 1 | 74 | 267 | 51 | 390 | 2019 | 2020 | R16
161617147331 | 160050147331 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-26 | 2019-03-26 | 2019-03-26 |  | 2019-08-28 | Underground | R16 | 2019-08-21 | 1 |  | 107 | 6 | 112 | 2019 | 2019 | R16
161517203874 | 167946203874 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-01 | 2020-09-01 | 2020-09-15 |  | 2021-07-26 | Underground | R16 | 2020-11-02 | 1 | 11 | 35 | 191 | 235 | 2020 | 2021 | R16
166769232225 | 160669232225 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-15 | 2021-05-24 | 2021-05-24 | 2021-09-10 | 2021-10-25 | Overhead | R16 | 2021-09-10 | 51 |  | 80 | 32 | 161 | 2021 | 2021 | R16
161705152869 | 162264152869 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-04-08 | 2019-05-21 | 2019-05-21 |  | 2020-06-09 | Underground | R16 | 2020-03-04 | 32 |  | 207 | 70 | 307 | 2019 | 2020 | R16
167304198650 | 160293198650 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-27 | 2020-07-27 | 2020-07-28 |  | 2021-07-28 | Overhead | R16 | 2021-01-20 | 1 | 2 | 127 | 136 | 263 | 2020 | 2021 | R16
161707153778 | 169074153778 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-05-15 | 2019-05-15 | 2019-05-30 |  | 2020-07-08 | Underground | R16 | 2020-04-20 | 1 | 12 | 233 | 58 | 301 | 2019 | 2020 | R16
163068210824 | 165316210824 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-01 | 2020-10-01 | 2020-11-16 |  | 2023-06-07 | Overhead | R16 |  | 1 | 33 |  |  | 700 | 2020 | 2023 | R16
168437201205 | 165340201205 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-20 | 2020-08-20 | 2020-08-20 | 2020-09-24 | 2020-12-29 | Overhead | R16 | 2020-09-24 | 1 |  | 26 | 69 | 94 | 2020 | 2020 | R16
166667156535 | 167970156535 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-08 | 2019-05-08 | 2019-06-28 | 2019-09-18 | 2019-09-19 | Underground | R16 | 2019-09-18 | 1 | 38 | 59 | 2 | 97 | 2019 | 2019 | R16
165887212494 | 167693212494 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-01 | 2020-12-01 | 2020-12-02 | 2021-01-27 | 2021-05-05 | Overhead | R16 | 2021-01-27 | 1 | 2 | 41 | 71 | 112 | 2020 | 2021 | R16
165072154527 | 162524154527 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-06 | 2019-06-06 | 2019-06-06 |  | 2019-07-18 | Overhead | R16 | 2019-07-03 | 1 |  | 20 | 12 | 31 | 2019 | 2019 | R16
161735147701 | 160900147701 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-31 | 2019-03-31 | 2019-03-31 |  | 2019-05-28 | Overhead | R16 | 2019-04-24 | 0 |  | 18 | 25 | 42 | 2019 | 2019 | R16
160282147997 | 160239147997 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-27 | 2019-03-27 | 2019-04-05 |  | 2019-06-03 | Underground | R16 | 2019-05-08 | 1 | 8 | 24 | 19 | 49 | 2019 | 2019 | R16
161736148907 | 161296148907 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-02 | 2019-04-02 | 2019-04-11 |  | 2019-06-03 | Underground | R16 | 2019-05-06 | 1 | 8 | 18 | 21 | 45 | 2019 | 2019 | R16
164873235536 | 160339235536 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES UD | Residential | 2021-05-27 | 2021-06-19 | 2021-06-19 |  | 2023-03-07 | Underground | R16 | 2021-07-07 | 17 |  | 13 | 435 | 464 | 2021 | 2023 | R16
161221210899 | 165394210899 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-17 | 2020-11-17 | 2020-11-17 | 2021-01-08 | 2021-04-29 | Overhead | R16 | 2021-01-08 | 1 |  | 39 | 80 | 118 | 2020 | 2021 | R16
160840251582 | 167263251582 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-28 | 2021-03-02 | 2021-10-11 | 2022-01-10 | 2022-02-07 | Underground | R16 | 2022-01-10 | 2 | 160 | 66 | 21 | 246 | 2021 | 2022 | R16
162097205656 | 164471205656 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-29 | 2020-09-29 | 2020-09-29 | 2021-02-25 | 2021-06-02 | Underground | R16 | 2021-02-25 | 1 |  | 108 | 70 | 177 | 2020 | 2021 | R16
161750147999 | 161931147999 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-05 | 2019-04-05 | 2019-04-05 |  | 2019-10-16 | Overhead | R16 | 2019-10-03 | 1 |  | 130 | 10 | 139 | 2019 | 2019 | R16
161757145106 | 166602145106 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-06 | 2019-03-06 | 2019-03-06 |  | 2019-08-12 | Overhead | R16 | 2019-06-03 | 1 |  | 64 | 51 | 114 | 2019 | 2019 | R16
166322233547 | 169401233547 | NON-RESIDENTIAL - HEALTH CARE | R16 RESD AND NON RESD US | Commercial | 2020-12-08 | 2021-06-03 | 2021-06-04 | 2021-09-24 | 2021-09-28 | Underground | R16 | 2021-09-24 | 128 | 2 | 81 | 3 | 211 | 2020 | 2021 | R16
161802155922 | 160845155922 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-05-24 | 2019-05-24 | 2019-06-20 |  | 2020-06-09 | Underground | R16 | 2020-04-03 | 1 | 20 | 207 | 48 | 273 | 2019 | 2020 | R16
167677153054 | 160457153054 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-22 | 2019-05-22 | 2019-05-22 |  | 2019-06-18 | Overhead | R16 | 2019-06-10 | 1 |  | 14 | 7 | 20 | 2019 | 2019 | R16
161820147957 | 168969147957 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-03-20 | 2019-03-20 | 2019-04-04 |  | 2020-08-28 | Underground | R16 |  | 1 | 12 |  |  | 378 | 2019 | 2020 | R16
162322173503 | 165813173503 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-01-08 | 2019-01-08 | 2019-12-03 | 2020-06-15 | 2020-08-31 | Underground | R16 | 2020-06-15 | 1 | 236 | 140 | 56 | 430 | 2019 | 2020 | R16
169159207378 | 168495207378 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-16 | 2020-10-16 | 2020-10-16 |  | 2021-05-06 | Overhead | R16 |  | 1 |  |  |  | 145 | 2020 | 2021 | R16
168683216008 | 164294216008 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-31 | 2020-12-31 | 2020-12-31 |  | 2021-04-21 | Overhead | R16 | 2021-01-26 | 1 |  | 19 | 62 | 80 | 2020 | 2021 | R16
166229222009 | 162508222009 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-08-07 | 2020-08-07 | 2021-03-01 |  | 2022-02-07 | Underground | R16 | 2022-01-14 | 1 | 147 | 230 | 17 | 392 | 2020 | 2022 | R16
162651151937 | 168165151937 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-09 | 2019-05-09 | 2019-05-09 |  | 2019-08-12 | Overhead | R16 | 2019-06-13 | 1 |  | 26 | 43 | 68 | 2019 | 2019 | R16
167955147732 | 161093147732 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-01 | 2019-04-01 | 2019-04-01 |  | 2019-06-03 | Overhead | R16 | 2019-05-14 | 1 |  | 32 | 15 | 46 | 2019 | 2019 | R16
167566219142 | 161110219142 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-01-29 | 2021-01-29 | 2021-01-29 |  | 2021-11-05 | Underground | R16 | 2021-04-13 | 1 |  | 53 | 149 | 201 | 2021 | 2021 | R16
161900148919 | 162804148919 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-10 | 2019-04-10 | 2019-04-12 |  | 2019-05-28 | Overhead | R16 | 2019-04-30 | 1 | 3 | 13 | 21 | 35 | 2019 | 2019 | R16
164463261148 | 169965261148 | NON-RESIDENTIAL - LODGING | UG R16 RESD AND NON RESD UD | Commercial | 2021-05-26 | 2021-08-30 | 2021-12-14 | 2023-11-06 | 2023-11-20 | Underground | R16 | 2023-11-06 | 69 | 77 | 495 | 11 | 649 | 2021 | 2023 | R16
165483256838 | 164082256838 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-12-30 | 2021-04-28 | 2021-11-17 | 2023-09-27 | 2023-10-20 | Underground | R16 | 2023-09-27 | 86 | 146 | 486 | 18 | 733 | 2020 | 2023 | R16
162267232475 | 169983232475 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-26 | 2021-05-26 | 2021-05-26 | 2021-07-07 | 2021-08-23 | Overhead | R16 | 2021-07-07 | 1 |  | 31 | 34 | 64 | 2021 | 2021 | R16
161445148848 | 163040148848 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-11 | 2019-04-11 | 2019-04-11 |  | 2019-08-12 | Underground | R16 | 2019-06-10 | 1 |  | 43 | 46 | 88 | 2019 | 2019 | R16
162034145906 | 167687145906 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-12 | 2019-03-12 | 2019-03-12 |  | 2019-05-28 | Overhead | R16 | 2019-04-30 | 1 |  | 36 | 21 | 56 | 2019 | 2019 | R16
164657204731 | 162658204731 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-23 | 2020-09-23 | 2020-09-23 |  | 2021-04-20 | Overhead | R16 | 2021-01-14 | 1 |  | 82 | 69 | 150 | 2020 | 2021 | R16
167238221727 | 165467221727 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-22 | 2021-02-25 | 2021-02-25 | 2021-03-29 | 2021-11-11 | Overhead | R16 | 2021-03-29 | 4 |  | 23 | 164 | 189 | 2021 | 2021 | R16
165458148150 | 161868148150 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-05 | 2019-04-05 | 2019-04-05 |  | 2020-06-09 | Overhead | R16 | 2020-03-24 | 1 |  | 253 | 56 | 308 | 2019 | 2020 | R16
167122245428 | 160338245428 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-04-26 | 2021-04-27 | 2021-08-26 | 2021-09-04 | 2021-09-07 | Overhead | R16 | 2021-09-04 | 2 | 88 | 7 | 2 | 97 | 2021 | 2021 | R16
162139146890 | 169473146890 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-22 | 2019-03-22 | 2019-03-22 |  | 2019-05-28 | Overhead | R16 | 2019-04-23 | 1 |  | 23 | 26 | 48 | 2019 | 2019 | R16
165013151478 | 167279151478 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-04 | 2019-05-04 | 2019-05-07 | 2020-02-07 | 2020-02-11 | Overhead | R16 | 2020-02-07 | 0 | 2 | 199 | 3 | 202 | 2019 | 2020 | R16
169413230791 | 165425230791 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-14 | 2021-05-14 | 2021-05-14 |  | 2021-10-25 | Overhead | R16 | 2021-09-15 | 1 |  | 89 | 29 | 117 | 2021 | 2021 | R16
160473208453 | 165011208453 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-30 | 2020-10-26 | 2020-10-26 |  | 2021-06-03 | Underground | R16 | 2021-03-08 | 19 |  | 96 | 64 | 177 | 2020 | 2021 | R16
167045157160 | 169665157160 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-17 | 2019-05-17 | 2019-07-03 | 2019-08-12 | 2019-12-06 | Underground | R16 | 2019-08-12 | 1 | 34 | 29 | 85 | 146 | 2019 | 2019 | R16
166115211504 | 166170211504 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-20 | 2020-11-20 | 2020-11-20 | 2020-12-31 | 2021-04-16 | Overhead | R16 | 2020-12-31 | 1 |  | 30 | 77 | 106 | 2020 | 2021 | R16
162170188766 | 160642188766 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2020-04-08 | 2020-04-08 | 2020-04-22 |  | 2020-07-08 | Underground | R16 |  | 1 | 11 |  |  | 66 | 2020 | 2020 | R16
166553168151 | 160096168151 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-05-21 | 2019-10-12 | 2019-10-14 |  | 2020-06-09 | Underground | R16 |  | 104 | 1 |  |  | 276 | 2019 | 2020 | R16
162182145967 | 167867145967 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-12 | 2019-03-12 | 2019-03-12 |  | 2019-08-12 | Overhead | R16 | 2019-05-21 | 1 |  | 51 | 60 | 110 | 2019 | 2019 | R16
165795276504 | 162474276504 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-09-22 | 2020-09-22 | 2022-04-20 |  | 2023-10-02 | Overhead | R16 | 2023-06-22 | 1 | 412 | 307 | 73 | 790 | 2020 | 2023 | R16
165614240038 | 166679240038 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-02-25 | 2021-03-05 | 2021-07-22 | 2022-11-13 | 2023-06-07 | Underground | R16 | 2022-11-13 | 7 | 100 | 342 | 148 | 595 | 2021 | 2023 | R16
166146220504 | 167894220504 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-19 | 2021-01-19 | 2021-02-12 |  | 2021-11-11 | Underground | R16 | 2021-03-31 | 1 | 19 | 34 | 162 | 213 | 2021 | 2021 | R16
162357146409 | 168566146409 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-03-18 | 2019-03-18 | 2019-03-18 |  | 2019-04-25 | Overhead | R16 | 2019-04-01 | 1 |  | 11 | 19 | 29 | 2019 | 2019 | R16
160259211510 | 160277211510 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-28 | 2020-07-28 | 2020-11-20 | 2021-01-20 | 2021-01-21 | Underground | R16 | 2021-01-20 | 1 | 84 | 44 | 2 | 128 | 2020 | 2021 | R16
162357158812 | 163003158812 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-06-10 | 2019-06-10 | 2019-07-24 |  | 2019-09-10 | Underground | R16 | 2019-09-03 | 1 | 33 | 30 | 6 | 67 | 2019 | 2019 | R16
161408202289 | 166561202289 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-25 | 2020-08-29 | 2020-08-29 | 2020-10-26 | 2021-04-07 | Overhead | R16 | 2020-10-26 | 4 |  | 41 | 118 | 162 | 2020 | 2021 | R16
162364161796 | 165877161796 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-16 | 2019-08-16 | 2019-08-21 |  | 2020-10-06 | Underground | R16 | 2020-07-20 | 1 | 4 | 239 | 57 | 298 | 2019 | 2020 | R16
162365203641 | 163580203641 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-30 | 2019-09-30 | 2020-09-11 |  | 2022-09-20 | Underground | R16 |  | 1 | 250 |  |  | 777 | 2019 | 2022 | R16
160362205723 | 164525205723 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-29 | 2020-09-29 | 2020-09-29 | 2020-11-06 | 2020-11-16 | Overhead | R16 | 2020-11-06 | 1 |  | 29 | 7 | 35 | 2020 | 2020 | R16
160357233328 | 163736233328 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-07 | 2021-05-13 | 2021-06-03 |  | 2021-08-23 | Underground | R16 | 2021-07-26 | 5 | 16 | 38 | 21 | 77 | 2021 | 2021 | R16
162041201343 | 165477201343 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-21 | 2020-08-21 | 2020-08-21 |  | 2021-04-16 | Overhead | R16 | 2020-01-06 | 1 |  |  | 335 | 171 | 2020 | 2021 | R16
162303210253 | 166499210253 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-25 | 2020-08-25 | 2020-11-11 | 2021-02-06 | 2021-02-18 | Underground | R16 | 2021-02-06 | 1 | 57 | 63 | 9 | 128 | 2020 | 2021 | R16
161831155632 | 163217155632 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-12 | 2019-04-12 | 2019-06-19 | 2019-07-02 | 2021-11-01 | Underground | R16 | 2019-07-02 | 1 | 49 | 10 | 610 | 667 | 2019 | 2021 | R16
160698208035 | 160026208035 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-23 | 2020-10-23 | 2020-10-23 | 2020-11-03 | 2021-11-09 | Overhead | R16 | 2020-11-03 | 1 |  | 8 | 266 | 273 | 2020 | 2021 | R16
162491159571 | 162739159571 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-07-30 | 2019-07-30 | 2019-07-30 |  | 2023-06-07 | Overhead | R16 | 2019-11-13 | 1 |  | 77 | 931 | 1007 | 2019 | 2023 | R16
169059148149 | 169254148149 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-21 | 2019-03-21 | 2019-04-05 | 2019-04-19 | 2019-04-22 | Underground | R16 | 2019-04-19 | 1 | 12 | 11 | 2 | 23 | 2019 | 2019 | R16
160358219593 | 162294219593 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-04 | 2021-02-04 | 2021-02-04 |  | 2021-11-11 | Overhead | R16 | 2021-03-30 | 1 |  | 39 | 163 | 201 | 2021 | 2021 | R16
161170210522 | 164473210522 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-12 | 2020-11-12 | 2020-11-12 |  | 2021-04-16 | Overhead | R16 | 2020-12-30 | 1 |  | 35 | 78 | 112 | 2020 | 2021 | R16
166118199515 | 160559199515 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-29 | 2020-07-29 | 2020-08-03 | 2020-08-20 | 2020-12-18 | Underground | R16 | 2020-08-20 | 1 | 4 | 14 | 87 | 103 | 2020 | 2020 | R16
162563146681 | 168335146681 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-14 | 2019-03-14 | 2019-03-20 |  | 2019-08-12 | Overhead | R16 | 2019-06-20 | 1 | 5 | 67 | 38 | 108 | 2019 | 2019 | R16
163990221506 | 166172221506 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-02-24 | 2021-02-24 | 2021-02-24 |  | 2021-11-08 | Underground | R16 | 2021-04-29 | 1 |  | 47 | 138 | 184 | 2021 | 2021 | R16
162672148151 | 161911148151 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-05 | 2019-04-05 | 2019-04-05 |  | 2019-05-28 | Overhead | R16 | 2019-05-01 | 1 |  | 19 | 20 | 38 | 2019 | 2019 | R16
163485219622 | 161098219622 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-31 | 2021-02-04 | 2021-02-04 | 2021-03-24 | 2021-11-05 | Overhead | R16 | 2021-03-24 | 4 |  | 35 | 163 | 200 | 2021 | 2021 | R16
160010163543 | 169868163543 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-26 | 2019-03-26 | 2019-09-06 | 2019-11-05 | 2019-10-25 | Overhead | R16 | 2019-11-05 | 1 | 119 | 43 |  | 154 | 2019 | 2019 | R16
169675219199 | 160544219199 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-26 | 2021-02-02 | 2021-02-02 | 2021-04-03 | 2021-04-06 | Underground | R16 | 2021-04-03 | 72 |  | 44 | 2 | 117 | 2020 | 2021 | R16
168527251757 | 165304251757 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH CP R16 WORK RELO TO UG | Commercial | 2021-02-18 | 2021-03-02 | 2021-10-12 | 2021-10-25 | 2021-11-12 | Overhead | R16 | 2021-10-25 | 9 | 161 | 10 | 15 | 192 | 2021 | 2021 | R16
169429148445 | 162086148445 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-06 | 2019-04-06 | 2019-04-06 | 2019-04-17 | 2019-04-17 | Overhead | R16 | 2019-04-17 | 0 |  | 8 |  | 8 | 2019 | 2019 | R16
162869146637 | 169074146637 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-03-20 | 2019-03-20 | 2019-03-20 |  | 2019-10-17 | Overhead | R16 |  | 1 |  |  |  | 152 | 2019 | 2019 | R16
162248151876 | 168151151876 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-09 | 2019-05-09 | 2019-05-09 |  | 2019-08-26 | Overhead | R16 | 2019-06-24 | 1 |  | 33 | 46 | 78 | 2019 | 2019 | R16
168872151828 | 169280151828 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-21 | 2019-03-21 | 2019-05-08 |  | 2022-10-20 | Underground | R16 |  | 1 | 35 |  |  | 936 | 2019 | 2022 | R16
162882145079 | 166791145079 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-03-06 | 2019-03-06 | 2019-03-06 |  | 2019-05-20 | Overhead | R16 | 2019-04-10 | 1 |  | 26 | 29 | 54 | 2019 | 2019 | R16
164280211358 | 166007211358 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-19 | 2020-11-19 | 2020-11-19 | 2021-06-09 | 2021-08-17 | Overhead | R16 | 2021-06-09 | 1 |  | 145 | 50 | 194 | 2020 | 2021 | R16
162900175740 | 165535175740 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-11-27 | 2019-11-27 | 2020-01-03 |  | 2020-06-09 | Overhead | R16 |  | 1 | 28 |  |  | 140 | 2019 | 2020 | R16
161376224445 | 162478224445 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-31 | 2021-06-09 | Overhead | R16 | 2021-03-31 | 1 |  | 8 | 51 | 58 | 2021 | 2021 | R16
168841164025 | 169485164025 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-22 | 2019-03-26 | 2019-09-10 | 2019-09-27 | 2019-09-30 | Overhead | R16 | 2019-09-27 | 3 | 121 | 14 | 2 | 137 | 2019 | 2019 | R16
166866155988 | 169888155988 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-05-20 | 2019-05-20 | 2019-06-21 |  | 2021-11-09 | Underground | R16 | 2021-04-29 | 1 | 25 | 485 | 139 | 647 | 2019 | 2021 | R16
162966149300 | 163470149300 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-15 | 2019-04-15 | 2019-04-15 |  | 2019-08-12 | Overhead | R16 | 2019-05-31 | 1 |  | 35 | 52 | 86 | 2019 | 2019 | R16
167181142127 | 161285142127 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-02-04 | 2019-02-04 | 2019-02-04 |  | 2019-03-04 | Overhead | R16 |  | 1 |  |  |  | 21 | 2019 | 2019 | R16
161813147833 | 169075147833 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-03-20 | 2019-03-20 | 2019-04-02 | 2020-02-20 | 2020-06-09 | Underground | R16 | 2020-02-20 | 1 | 10 | 233 | 79 | 320 | 2019 | 2020 | R16
162159208961 | 161092208961 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-28 | 2020-10-28 | 2020-10-28 | 2020-11-11 | 2021-11-30 | Overhead | R16 | 2020-11-11 | 1 |  | 11 | 275 | 285 | 2020 | 2021 | R16
163078148916 | 161067148916 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-01 | 2019-04-01 | 2019-04-11 |  | 2019-08-12 | Overhead | R16 | 2019-05-23 | 1 | 9 | 31 | 58 | 96 | 2019 | 2019 | R16
163089145601 | 165830145601 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-03-01 | 2019-03-01 | 2019-03-11 |  | 2019-05-20 | Overhead | R16 | 2019-04-15 | 1 | 7 | 26 | 26 | 57 | 2019 | 2019 | R16
168617208725 | 160831208725 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-27 | 2020-10-27 | 2020-10-27 | 2020-12-11 | 2020-12-11 | Underground | R16 | 2020-12-11 | 1 |  | 34 |  | 34 | 2020 | 2020 | R16
163104146921 | 169477146921 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-22 | 2019-03-22 | 2019-03-22 |  | 2019-05-28 | Overhead | R16 | 2019-04-24 | 1 |  | 24 | 25 | 48 | 2019 | 2019 | R16
164307221591 | 165527221591 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-21 | 2021-02-25 | 2021-02-25 | 2021-11-29 | 2022-01-27 | Overhead | R16 | 2021-11-29 | 4 |  | 198 | 44 | 244 | 2021 | 2022 | R16
163105150113 | 168175150113 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2019-03-15 | 2019-04-03 | 2019-04-24 |  | 2019-08-12 | Underground | R16 |  | 14 | 16 |  |  | 107 | 2019 | 2019 | R16
165965226295 | 167933226295 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-03-02 | 2021-03-12 | 2021-04-09 | 2021-06-21 | 2021-06-24 | Underground | R16 | 2021-06-21 | 9 | 21 | 52 | 4 | 83 | 2021 | 2021 | R16
163017219717 | 162584219717 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-05 | 2021-02-05 | 2021-02-05 | 2021-06-09 | 2021-08-12 | Overhead | R16 | 2021-06-09 | 1 |  | 89 | 47 | 135 | 2021 | 2021 | R16
163109147087 | 169742147087 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-25 | 2019-03-25 | 2019-03-25 |  | 2019-05-20 | Overhead | R16 | 2019-04-18 | 1 |  | 19 | 23 | 41 | 2019 | 2019 | R16
163433144121 | 163425144121 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2019-02-13 | 2019-02-14 | 2019-02-25 | 2021-04-16 | 2020-09-18 | Underground | R16 | 2021-04-16 | 2 | 8 | 560 |  | 418 | 2019 | 2020 | R16
164509223623 | 168076223623 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-03 | 2021-03-11 | 2021-03-15 |  | 2021-11-01 | Underground | R16 | 2021-04-01 | 7 | 3 | 14 | 153 | 174 | 2021 | 2021 | R16
163240220987 | 163117220987 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-24 | 2020-09-24 | 2021-02-18 |  | 2021-11-11 | Underground | R16 | 2021-04-19 | 1 | 106 | 43 | 149 | 296 | 2020 | 2021 | R16
160349211462 | 162402211462 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-22 | 2020-09-22 | 2020-11-20 |  | 2021-11-09 | Underground | R16 | 2021-04-26 | 1 | 44 | 112 | 142 | 296 | 2020 | 2021 | R16
163789152220 | 168551152220 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-13 | 2019-05-13 | 2019-05-13 | 2019-06-10 | 2019-10-30 | Overhead | R16 | 2019-06-10 | 1 |  | 21 | 103 | 123 | 2019 | 2019 | R16
163150147603 | 168825147603 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-19 | 2019-03-19 | 2019-03-29 |  | 2021-04-14 | Underground | R16 | 2020-12-31 | 1 | 9 | 460 | 75 | 542 | 2019 | 2021 | R16
163168144861 | 163387144861 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-13 | 2019-02-13 | 2019-03-04 |  | 2019-10-04 | Underground | R16 | 2019-03-19 | 1 | 14 | 12 | 144 | 168 | 2019 | 2019 | R16
163175148222 | 161555148222 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-04 | 2019-04-04 | 2019-04-04 |  | 2019-06-03 | Overhead | R16 | 2019-05-08 | 1 |  | 25 | 19 | 43 | 2019 | 2019 | R16
168734222254 | 164889222254 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-05 | 2021-01-05 | 2021-03-03 |  | 2021-11-08 | Underground | R16 | 2021-05-17 | 1 | 42 | 54 | 126 | 220 | 2021 | 2021 | R16
163178149989 | 169650149989 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-24 | 2019-03-24 | 2019-04-23 |  | 2019-08-12 | Underground | R16 | 2019-05-07 | 0 | 22 | 11 | 70 | 101 | 2019 | 2019 | R16
161504217591 | 164596217591 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-30 | 2020-11-12 | 2021-01-19 | 2021-06-02 | 2021-08-26 | Overhead | R16 | 2021-06-02 | 32 | 49 | 97 | 62 | 237 | 2020 | 2021 | R16
169408209881 | 160099209881 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-26 | 2020-10-27 | 2020-11-05 | 2021-03-17 | 2021-11-05 | Underground | R16 | 2021-03-17 | 2 | 8 | 95 | 168 | 270 | 2020 | 2021 | R16
161872149808 | 164612149808 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-20 | 2019-04-20 | 2019-04-20 | 2020-09-24 | 2020-09-24 | Overhead | R16 | 2020-09-24 | 0 |  | 374 |  | 374 | 2019 | 2020 | R16
162281224484 | 162009224484 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-12-13 | 2023-06-08 | Overhead | R16 | 2021-12-13 | 1 |  | 191 | 389 | 579 | 2021 | 2023 | R16
161402144146 | 164985144146 | GENERAL/OTHER | R16 RESD AND NON RESD US | Commercial | 2019-02-25 | 2019-02-25 | 2019-02-25 | 2019-09-05 | 2019-12-04 | Underground | R16 | 2019-09-05 | 1 |  | 139 | 65 | 203 | 2019 | 2019 | R16
163353143602 | 163933143602 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-19 | 2019-02-19 | 2019-02-19 |  | 2019-03-11 | Underground | R16 | 2019-02-22 | 1 |  | 4 | 12 | 15 | 2019 | 2019 | R16
163357144398 | 165524144398 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-28 | 2019-02-28 | 2019-02-28 |  | 2019-04-15 | Overhead | R16 | 2019-03-27 | 1 |  | 20 | 14 | 33 | 2019 | 2019 | R16
163365143323 | 163561143323 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-14 | 2019-02-14 | 2019-02-14 |  | 2019-03-14 | Overhead | R16 | 2019-02-25 | 1 |  | 8 | 14 | 21 | 2019 | 2019 | R16
164342220506 | 164216220506 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-12 | 2021-02-12 | 2021-02-12 |  | 2021-08-16 | Overhead | R16 | 2021-03-25 | 1 |  | 30 | 103 | 132 | 2021 | 2021 | R16
164984144700 | 165669144700 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2019-03-01 | 2019-03-01 | 2019-03-01 | 2019-05-29 | 2020-07-21 | Overhead | R16 | 2019-05-29 | 1 |  | 64 | 300 | 363 | 2019 | 2020 | R16
163840146545 | 168764146545 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-19 | 2019-03-19 | 2019-03-19 |  | 2019-05-20 | Overhead | R16 | 2019-04-18 | 1 |  | 23 | 23 | 45 | 2019 | 2019 | R16
163413149020 | 162260149020 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-08 | 2019-04-11 | 2019-04-11 |  | 2021-11-17 | Overhead | R16 | 2019-09-10 | 4 |  | 109 | 572 | 683 | 2019 | 2021 | R16
162500231516 | 165361231516 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-10-02 | 2020-12-16 | 2021-05-20 | 2023-10-17 | 2023-12-12 | Underground | R16 | 2023-10-17 | 54 | 112 | 629 | 41 | 833 | 2020 | 2023 | R16
163176212847 | 163977212847 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-10 | 2020-11-10 | 2020-12-04 |  | 2021-04-29 | Underground | R16 | 2021-02-08 | 1 | 19 | 47 | 59 | 123 | 2020 | 2021 | R16
168664201193 | 169626201193 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-07-22 | 2020-07-22 | 2020-08-19 | 2020-09-11 | 2021-02-08 | Overhead | R16 | 2020-09-11 | 1 | 21 | 18 | 107 | 144 | 2020 | 2021 | R16
161077237181 | 167499237181 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-11-30 | 2020-12-15 | 2021-06-29 |  | 2022-03-08 | Underground | R16 | 2022-02-09 | 12 | 141 | 162 | 20 | 332 | 2020 | 2022 | R16
166038229962 | 169909229962 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2020-07-23 | 2021-02-25 | 2021-05-07 |  | 2021-11-18 | Overhead | R16 |  | 156 | 52 |  |  | 346 | 2020 | 2021 | R16
161051207954 | 167227207954 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-12 | 2020-10-23 | 2020-10-23 | 2020-12-02 | 2021-04-21 | Overhead | R16 | 2020-12-02 | 10 |  | 29 | 101 | 138 | 2020 | 2021 | R16
163537211465 | 166212211465 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-20 | 2020-11-20 | 2020-11-20 | 2020-12-02 | 2021-11-11 | Overhead | R16 | 2020-12-02 | 1 |  | 9 | 247 | 255 | 2020 | 2021 | R16
163354230291 | 162732230291 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-04 | 2021-05-11 | 2021-05-11 |  | 2021-11-02 | Overhead | R16 | 2021-06-17 | 6 |  | 28 | 99 | 131 | 2021 | 2021 | R16
162261208002 | 169768208002 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-22 | 2020-10-22 | 2020-10-22 |  | 2021-11-05 | Overhead | R16 | 2021-05-05 | 1 |  | 140 | 133 | 272 | 2020 | 2021 | R16
163487146607 | 168320146607 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-14 | 2019-03-18 | 2019-03-20 |  | 2019-06-06 | Underground | R16 | 2019-05-24 | 3 | 3 | 48 | 10 | 61 | 2019 | 2019 | R16
165723235010 | 160699235010 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-15 | 2021-06-14 | 2021-06-14 | 2021-12-13 | 2022-01-18 | Overhead | R16 | 2021-12-13 | 66 |  | 131 | 27 | 222 | 2021 | 2022 | R16
163089275205 | 165165275205 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-04-02 | 2021-05-14 | 2022-04-07 | 2022-04-08 | 2022-04-28 | Underground | R16 | 2022-04-08 | 31 | 235 | 2 | 15 | 280 | 2021 | 2022 | R16
163558146068 | 168103146068 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-14 | 2019-03-14 | 2019-03-14 |  | 2019-04-30 | Overhead | R16 | 2019-04-04 | 1 |  | 16 | 19 | 34 | 2019 | 2019 | R16
164538211174 | 165682211174 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-18 | 2020-11-18 | 2020-11-18 | 2021-01-27 | 2021-01-27 | Overhead | R16 | 2021-01-27 | 1 |  | 51 |  | 51 | 2020 | 2021 | R16
163571149806 | 164585149806 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-20 | 2019-04-20 | 2019-04-20 |  | 2019-06-03 | Overhead | R16 | 2019-05-08 | 0 |  | 13 | 19 | 31 | 2019 | 2019 | R16
163604143634 | 164365143634 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-20 | 2019-02-20 | 2019-02-20 |  | 2019-04-15 | Overhead | R16 | 2019-03-07 | 1 |  | 12 | 28 | 39 | 2019 | 2019 | R16
163994203908 | 160805203908 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2020-09-15 | 2020-09-15 | 2020-09-15 | 2021-07-23 | 2021-02-27 | Underground | R16 | 2021-07-23 | 1 |  | 224 |  | 119 | 2020 | 2021 | R16
165943232720 | 160340232720 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-27 | 2021-05-27 | 2021-05-27 | 2022-05-04 | 2022-06-30 | Overhead | R16 | 2022-05-04 | 1 |  | 245 | 42 | 286 | 2021 | 2022 | R16
161441237025 | 165863237025 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-17 | 2021-06-28 | 2021-06-28 | 2021-07-01 | 2021-08-23 | Overhead | R16 | 2021-07-01 | 31 |  | 4 | 38 | 71 | 2021 | 2021 | R16
163648146240 | 168432146240 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-15 | 2019-03-15 | 2019-03-15 |  | 2019-11-08 | Underground | R16 | 2019-10-29 | 1 |  | 163 | 9 | 171 | 2019 | 2019 | R16
163651145791 | 167535145791 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-11 | 2019-03-11 | 2019-03-11 |  | 2019-04-30 | Underground | R16 | 2019-04-04 | 1 |  | 19 | 19 | 37 | 2019 | 2019 | R16
161431151624 | 167654151624 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-07 | 2019-05-07 | 2019-05-07 |  | 2019-08-26 | Overhead | R16 | 2019-07-08 | 1 |  | 45 | 36 | 80 | 2019 | 2019 | R16
168967223770 | 160991223770 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-30 | 2020-07-30 | 2021-03-17 |  | 2021-11-05 | Underground | R16 | 2021-05-10 | 1 | 165 | 39 | 130 | 332 | 2020 | 2021 | R16
163677149992 | 165012149992 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-23 | 2019-04-23 | 2019-04-23 |  | 2019-08-12 | Overhead | R16 | 2019-05-20 | 1 |  | 20 | 61 | 80 | 2019 | 2019 | R16
165284143922 | 164422143922 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-20 | 2019-02-21 | 2019-02-21 | 2019-03-10 | 2019-03-13 | Overhead | R16 | 2019-03-10 | 2 |  | 12 | 3 | 16 | 2019 | 2019 | R16
160286147328 | 164437147328 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-02-21 | 2019-03-12 | 2019-03-26 | 2020-08-04 | 2020-11-04 | Underground | R16 | 2020-08-04 | 14 | 11 | 356 | 67 | 445 | 2019 | 2020 | R16
163705152548 | 169032152548 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-14 | 2019-05-14 | 2019-05-15 |  | 2019-08-12 | Overhead | R16 | 2019-06-13 | 1 | 2 | 22 | 43 | 65 | 2019 | 2019 | R16
161264218355 | 169516218355 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-02-05 | 2021-06-03 | Overhead | R16 | 2021-02-05 | 1 |  | 9 | 85 | 93 | 2021 | 2021 | R16
163713161595 | 166354161595 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-19 | 2019-08-19 | 2019-08-19 |  | 2021-04-07 | Underground | R16 | 2020-12-01 | 1 |  | 337 | 92 | 428 | 2019 | 2021 | R16
161875218406 | 168981218406 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-22 | 2021-01-22 | 2021-01-25 | 2021-02-18 | 2021-04-29 | Overhead | R16 | 2021-02-18 | 1 | 2 | 19 | 51 | 70 | 2021 | 2021 | R16
163752149405 | 169863149405 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-25 | 2019-03-25 | 2019-04-16 |  | 2019-08-12 | Underground | R16 | 2019-05-20 | 1 | 17 | 25 | 61 | 101 | 2019 | 2019 | R16
162219144835 | 162306144835 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-07 | 2019-02-07 | 2019-03-04 | 2019-04-29 | 2019-06-07 | Underground | R16 | 2019-04-29 | 1 | 18 | 41 | 30 | 87 | 2019 | 2019 | R16
160190228557 | 169100228557 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-19 | 2021-04-29 | 2021-04-29 |  | 2022-08-11 | Underground | R16 | 2022-06-20 | 9 |  | 298 | 39 | 344 | 2021 | 2022 | R16
162038147819 | 166595147819 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-06 | 2019-03-06 | 2019-04-03 | 2020-02-19 | 2020-02-21 | Underground | R16 | 2020-02-19 | 1 | 21 | 231 | 3 | 253 | 2019 | 2020 | R16
166635225126 | 163048225126 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-24 | 2021-03-24 | 2021-03-29 | 2021-05-06 | 2021-05-10 | Overhead | R16 | 2021-05-06 | 1 | 4 | 29 | 3 | 34 | 2021 | 2021 | R16
166016197608 | 168599197608 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-16 | 2020-07-16 | 2020-07-16 | 2020-07-22 | 2020-10-06 | Overhead | R16 | 2020-07-22 | 1 |  | 5 | 55 | 59 | 2020 | 2020 | R16
164117213016 | 165314213016 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-10-01 | 2020-10-01 | 2020-12-08 | 2021-09-22 | 2021-11-01 | Underground | R16 | 2021-09-22 | 1 | 49 | 207 | 29 | 283 | 2020 | 2021 | R16
163928148508 | 162391148508 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-08 | 2019-04-08 | 2019-04-08 |  | 2019-05-28 | Overhead | R16 | 2019-04-24 | 1 |  | 13 | 25 | 37 | 2019 | 2019 | R16
167206152582 | 169394152582 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-16 | 2019-05-16 | 2019-05-16 |  | 2019-08-12 | Overhead | R16 | 2019-06-14 | 1 |  | 22 | 42 | 63 | 2019 | 2019 | R16
163725230381 | 168650230381 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-04-16 | 2021-04-28 | 2021-05-11 |  | 2021-11-11 | Overhead | R16 | 2021-07-08 | 9 | 10 | 43 | 91 | 150 | 2021 | 2021 | R16
163938146571 | 169022146571 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-19 | 2019-03-19 | 2019-03-19 |  | 2019-05-20 | Overhead | R16 | 2019-04-09 | 1 |  | 16 | 30 | 45 | 2019 | 2019 | R16
162286156207 | 167883156207 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-07 | 2019-05-07 | 2019-06-25 | 2019-10-01 | 2019-10-14 | Underground | R16 | 2019-10-01 | 1 | 36 | 71 | 10 | 115 | 2019 | 2019 | R16
161474220184 | 163313220184 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-09 | 2021-02-09 | 2021-02-09 | 2021-03-24 | 2021-11-05 | Overhead | R16 | 2021-03-24 | 1 |  | 32 | 163 | 194 | 2021 | 2021 | R16
164011147780 | 160891147780 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-31 | 2019-03-31 | 2019-03-31 |  | 2019-08-12 | Overhead | R16 | 2019-05-30 | 0 |  | 44 | 53 | 96 | 2019 | 2019 | R16
168880224530 | 163146224530 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-11 | 2020-08-11 | 2021-03-24 | 2022-03-22 | 2022-04-22 | Underground | R16 | 2022-03-22 | 1 | 162 | 260 | 24 | 444 | 2020 | 2022 | R16
164033158672 | 161306158672 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-22 | 2019-07-22 | 2019-07-22 |  | 2020-01-08 | Underground | R16 | 2020-01-02 | 1 |  | 119 | 5 | 123 | 2019 | 2020 | R16
162729223235 | 168747223235 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-07 | 2021-03-11 | 2021-03-11 | 2021-06-22 | 2021-08-11 | Overhead | R16 | 2021-06-22 | 4 |  | 74 | 37 | 113 | 2021 | 2021 | R16
164038152861 | 166935152861 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-05-02 | 2019-05-02 | 2019-05-19 |  | 2019-08-12 | Underground | R16 | 2019-06-12 | 1 | 12 | 18 | 44 | 73 | 2019 | 2019 | R16
160355233055 | 161265233055 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-06-02 | 2021-06-02 | 2021-06-02 | 2021-09-02 | 2021-09-02 | Overhead | R16 | 2021-09-02 | 1 |  | 67 |  | 67 | 2021 | 2021 | R16
164051147290 | 166961147290 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-07 | 2019-03-07 | 2019-03-26 |  | 2020-01-02 | Overhead | R16 | 2019-12-27 | 1 | 14 | 199 | 5 | 216 | 2019 | 2020 | R16
166689198494 | 160448198494 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-07-28 | 2020-07-28 | 2020-07-28 |  | 2020-10-06 | Overhead | R16 | 2020-08-10 | 1 |  | 10 | 42 | 51 | 2020 | 2020 | R16
164052144901 | 165647144901 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-28 | 2019-02-28 | 2019-03-04 |  | 2019-04-25 | Overhead | R16 | 2019-04-02 | 1 | 3 | 22 | 18 | 41 | 2019 | 2019 | R16
164612204090 | 161367204090 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-17 | 2020-09-17 | 2020-09-17 | 2023-02-07 | 2023-05-30 | Overhead | R16 | 2023-02-07 | 1 |  | 624 | 81 | 704 | 2020 | 2023 | R16
160258148037 | 161503148037 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-04-03 | 2019-04-03 | 2019-04-03 | 2019-05-07 | 2019-05-08 | Overhead | R16 | 2019-05-07 | 1 |  | 25 | 2 | 26 | 2019 | 2019 | R16
166668144339 | 165321144339 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-26 | 2019-02-26 | 2019-02-27 | 2019-06-18 | 2019-06-19 | Underground | R16 | 2019-06-18 | 1 | 2 | 80 | 2 | 82 | 2019 | 2019 | R16
163567150368 | 165584150368 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-25 | 2019-04-25 | 2019-04-25 |  | 2019-08-12 | Overhead | R16 | 2019-05-20 | 1 |  | 18 | 61 | 78 | 2019 | 2019 | R16
166421147718 | 161007147718 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-01 | 2019-04-01 | 2019-04-01 |  | 2019-05-28 | Overhead | R16 | 2019-05-02 | 1 |  | 24 | 19 | 42 | 2019 | 2019 | R16
166200222523 | 161765222523 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential Subdivision | 2020-09-18 | 2020-12-14 | 2021-03-04 | 2021-05-26 | 2021-06-21 | Underground | R16 | 2021-05-26 | 62 | 59 | 60 | 19 | 197 | 2020 | 2021 | R16
164104148250 | 161724148250 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-04 | 2019-04-04 | 2019-04-05 |  | 2019-09-12 | Overhead | R16 | 2019-08-30 | 1 | 2 | 106 | 10 | 116 | 2019 | 2019 | R16
168097211217 | 165807211217 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-19 | 2020-11-19 | 2020-11-19 |  | 2021-05-06 | Overhead | R16 | 2021-02-18 | 1 |  | 66 | 56 | 121 | 2020 | 2021 | R16
165835229583 | 163074229583 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-05 | 2021-05-05 | 2021-05-05 | 2021-10-07 | 2021-11-10 | Underground | R16 | 2021-10-07 | 1 |  | 112 | 25 | 136 | 2021 | 2021 | R16
164119147606 | 160694147606 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-29 | 2019-03-29 | 2019-03-29 |  | 2021-11-10 | Underground | R16 | 2020-01-31 | 1 |  | 221 | 464 | 684 | 2019 | 2021 | R16
161820220931 | 169896220931 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-26 | 2021-02-19 | 2021-02-19 | 2021-03-23 | 2021-11-04 | Overhead | R16 | 2021-03-23 | 19 |  | 23 | 163 | 203 | 2021 | 2021 | R16
164165148909 | 160621148909 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-28 | 2019-03-28 | 2019-04-11 |  | 2019-06-03 | Overhead | R16 | 2019-05-13 | 1 | 11 | 23 | 16 | 48 | 2019 | 2019 | R16
163224149703 | 164560149703 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-19 | 2019-04-19 | 2019-04-19 |  | 2019-06-03 | Overhead | R16 | 2019-05-15 | 1 |  | 19 | 14 | 32 | 2019 | 2019 | R16
164167145016 | 166184145016 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-04 | 2019-03-04 | 2019-03-06 |  | 2019-05-20 | Overhead | R16 | 2019-04-16 | 1 | 3 | 30 | 25 | 56 | 2019 | 2019 | R16
169217212768 | 168634212768 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-12-04 | 2020-12-04 | 2020-12-04 |  | 2021-04-15 | Overhead | R16 | 2020-12-22 | 1 |  | 13 | 83 | 95 | 2020 | 2021 | R16
161990201523 | 166281201523 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-24 | 2020-08-24 | 2020-08-24 |  | 2021-04-15 | Overhead | R16 | 2020-12-21 | 1 |  | 86 | 84 | 169 | 2020 | 2021 | R16
161266154112 | 161909154112 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-03 | 2019-06-03 | 2019-06-03 |  | 2019-08-26 | Overhead | R16 | 2019-08-01 | 1 |  | 44 | 18 | 61 | 2019 | 2019 | R16
169474199225 | 161426199225 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-31 | 2020-07-31 | 2020-07-31 | 2020-08-21 | 2020-08-24 | Overhead | R16 | 2020-08-21 | 1 |  | 16 | 2 | 17 | 2020 | 2020 | R16
164228148126 | 160002148126 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-03-26 | 2019-03-26 | 2019-04-03 |  | 2019-05-28 | Overhead | R16 |  | 1 | 7 |  |  | 46 | 2019 | 2019 | R16
166580229909 | 163600229909 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-25 | 2020-09-25 | 2021-05-07 |  | 2021-08-11 | Underground | R16 | 2021-06-29 | 1 | 161 | 38 | 32 | 229 | 2020 | 2021 | R16
164229146891 | 169530146891 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-22 | 2019-03-22 | 2019-03-22 |  | 2019-05-20 | Overhead | R16 | 2019-04-17 | 1 |  | 19 | 24 | 42 | 2019 | 2019 | R16
162110204626 | 162073204626 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2020-09-21 | 2020-09-21 | 2020-09-21 |  | 2021-06-03 | Overhead | R16 | 2021-03-30 | 1 |  | 137 | 48 | 184 | 2020 | 2021 | R16
164235201115 | 165286201115 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-08-19 | 2020-08-20 | 2020-08-20 |  | 2020-11-02 | Overhead | R16 |  | 2 |  |  |  | 54 | 2020 | 2020 | R16
163090153743 | 161159153743 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-29 | 2019-05-29 | 2019-05-29 |  | 2019-08-12 | Overhead | R16 | 2019-06-21 | 1 |  | 18 | 37 | 54 | 2019 | 2019 | R16
168645210670 | 164811210670 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-13 | 2020-11-13 | 2020-11-13 |  | 2021-04-21 | Overhead | R16 | 2021-01-27 | 1 |  | 54 | 61 | 114 | 2020 | 2021 | R16
168516224666 | 163170224666 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-24 | 2021-03-24 | 2021-03-24 | 2021-06-08 | 2021-06-08 | Overhead | R16 | 2021-06-08 | 1 |  | 55 |  | 55 | 2021 | 2021 | R16
161631209271 | 169230209271 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-10-20 | 2020-10-20 | 2020-10-31 |  | 2021-11-08 | Underground | R16 | 2021-09-22 | 1 | 9 | 233 | 34 | 275 | 2020 | 2021 | R16
166875205609 | 164083205609 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-28 | 2020-09-28 | 2020-09-28 | 2020-10-07 | 2021-07-19 | Overhead | R16 | 2020-10-07 | 1 |  | 8 | 204 | 211 | 2020 | 2021 | R16
164259145199 | 167000145199 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-07 | 2019-03-07 | 2019-03-07 |  | 2022-08-16 | Underground | R16 | 2019-09-11 | 1 |  | 135 | 765 | 899 | 2019 | 2022 | R16
162078202937 | 167889202937 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-01 | 2020-09-08 | 2020-09-08 | 2020-10-28 | 2021-04-07 | Overhead | R16 | 2020-10-28 | 6 |  | 37 | 116 | 157 | 2020 | 2021 | R16
164311150186 | 165363150186 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-24 | 2019-04-24 | 2019-04-24 |  | 2019-05-28 | Overhead | R16 | 2019-04-30 | 1 |  | 5 | 21 | 25 | 2019 | 2019 | R16
169559154869 | 163095154869 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-10 | 2019-06-10 | 2019-06-10 | 2019-09-24 | 2019-09-25 | Overhead | R16 | 2019-09-24 | 1 |  | 77 | 2 | 78 | 2019 | 2019 | R16
160967199926 | 161784199926 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-08-04 | 2020-08-04 | 2020-08-06 |  | 2020-10-06 | Overhead | R16 |  | 1 | 3 |  |  | 46 | 2020 | 2020 | R16
164175209984 | 163689209984 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-09 | 2020-11-09 | 2020-11-09 | 2020-11-13 | 2021-04-29 | Overhead | R16 | 2020-11-13 | 1 |  | 5 | 120 | 124 | 2020 | 2021 | R16
164326183650 | 165352183650 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-10 | 2020-03-10 | 2020-03-10 |  | 2020-06-09 | Overhead | R16 | 2020-03-24 | 1 |  | 11 | 56 | 66 | 2020 | 2020 | R16
168551219132 | 164965219132 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-05 | 2021-01-05 | 2021-02-01 | 2021-02-04 | 2021-08-11 | Underground | R16 | 2021-02-04 | 1 | 20 | 4 | 135 | 157 | 2021 | 2021 | R16
166985205891 | 163276205891 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-24 | 2020-09-30 | 2020-09-30 | 2020-11-02 | 2021-07-26 | Overhead | R16 | 2020-11-02 | 5 |  | 24 | 191 | 218 | 2020 | 2021 | R16
168344145939 | 161497145939 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-05 | 2019-02-05 | 2019-03-13 | 2019-11-05 | 2019-11-06 | Underground | R16 | 2019-11-05 | 1 | 27 | 170 | 2 | 197 | 2019 | 2019 | R16
166742224643 | 169806224643 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-03-10 | 2021-03-10 | 2021-03-24 | 2021-07-13 | 2021-08-02 | Underground | R16 | 2021-07-13 | 1 | 11 | 80 | 15 | 104 | 2021 | 2021 | R16
163537213216 | 169088213216 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-07 | 2020-12-09 | 2020-12-09 |  | 2021-04-21 | Underground | R16 | 2021-01-21 | 3 |  | 32 | 65 | 98 | 2020 | 2021 | R16
164430155315 | 163938155315 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-06-14 | 2019-06-14 | 2019-06-14 |  | 2019-08-12 | Overhead | R16 | 2019-06-21 | 1 |  | 6 | 37 | 42 | 2019 | 2019 | R16
162442149847 | 164821149847 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-04-22 | 2019-04-22 | 2019-04-22 | 2019-05-03 | 2019-05-03 | Overhead | R16 | 2019-05-03 | 1 |  | 10 |  | 10 | 2019 | 2019 | R16
167031285564 | 162821285564 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-02-08 | 2022-07-13 | 2022-07-13 |  | 2023-08-02 | Underground | R16 | 2023-03-03 | 373 |  | 168 | 109 | 648 | 2021 | 2023 | R16
164454148224 | 161704148224 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-04 | 2019-04-04 | 2019-04-04 |  | 2019-05-28 | Underground | R16 | 2019-05-01 | 1 |  | 20 | 20 | 39 | 2019 | 2019 | R16
164467146893 | 169561146893 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-22 | 2019-03-22 | 2019-03-22 |  | 2019-08-12 | Overhead | R16 | 2019-05-29 | 1 |  | 49 | 54 | 102 | 2019 | 2019 | R16
164974153516 | 161193153516 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-29 | 2019-05-29 | 2019-05-29 | 2019-06-04 | 2021-12-11 | Overhead | R16 | 2019-06-04 | 1 |  | 5 | 659 | 663 | 2019 | 2021 | R16
161502209062 | 169152209062 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-20 | 2020-10-29 | 2020-10-29 | 2020-12-07 | 2021-04-21 | Overhead | R16 | 2020-12-07 | 8 |  | 28 | 98 | 132 | 2020 | 2021 | R16
164084144180 | 164920144180 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-25 | 2019-02-25 | 2019-02-25 | 2019-09-13 | 2019-09-16 | Overhead | R16 | 2019-09-13 | 1 |  | 145 | 2 | 146 | 2019 | 2019 | R16
165235225310 | 164529225310 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-30 | 2021-03-30 | 2021-03-30 | 2021-05-05 | 2021-11-08 | Overhead | R16 | 2021-05-05 | 1 |  | 27 | 134 | 160 | 2021 | 2021 | R16
164549149896 | 165035149896 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-04-23 | 2019-04-23 | 2019-04-23 |  | 2019-08-12 | Overhead | R16 | 2019-06-14 | 1 |  | 39 | 42 | 80 | 2019 | 2019 | R16
169269154449 | 161391154449 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-29 | 2019-05-29 | 2019-06-05 | 2019-08-04 | 2019-09-06 | Underground | R16 | 2019-08-04 | 1 | 6 | 43 | 25 | 73 | 2019 | 2019 | R16
169450154443 | 161838154443 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2019-06-03 | 2019-06-03 | 2019-06-05 |  | 2019-11-14 | Underground | R16 |  | 1 | 3 |  |  | 119 | 2019 | 2019 | R16
167606208351 | 160532208351 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-26 | 2020-10-26 | 2020-10-26 |  | 2021-07-26 | Overhead | R16 | 2020-11-03 | 1 |  | 7 | 190 | 196 | 2020 | 2021 | R16
164562150685 | 166027150685 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-29 | 2019-04-29 | 2019-04-29 |  | 2019-08-12 | Overhead | R16 | 2019-05-22 | 1 |  | 18 | 59 | 76 | 2019 | 2019 | R16
162647260203 | 168720260203 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-04-16 | 2021-04-26 | 2021-12-07 |  | 2023-05-11 | Overhead | R16 | 2023-02-13 | 7 | 162 | 310 | 64 | 540 | 2021 | 2023 | R16
166672149846 | 161433149846 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-04-03 | 2019-04-11 | 2019-04-22 |  | 2023-06-08 | Underground | R16 | 2023-06-01 | 7 | 8 | 1074 | 6 | 1092 | 2019 | 2023 | R16
164588145431 | 164991145431 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-25 | 2019-02-25 | 2019-03-08 |  | 2019-04-25 | Underground | R16 | 2019-03-21 | 1 | 10 | 10 | 26 | 44 | 2019 | 2019 | R16
169990243944 | 165234243944 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-13 | 2021-05-13 | 2021-08-16 | 2021-10-08 | 2021-10-11 | Underground | R16 | 2021-10-08 | 1 | 68 | 40 | 2 | 108 | 2021 | 2021 | R16
164622179646 | 163113179646 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-06-10 | 2019-06-11 | 2020-02-06 |  | 2020-10-06 | Underground | R16 |  | 2 | 173 |  |  | 347 | 2019 | 2020 | R16
160353202524 | 164288202524 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-17 | 2020-08-17 | 2020-09-01 |  | 2020-12-15 | Overhead | R16 | 2020-09-10 | 1 | 12 | 8 | 69 | 87 | 2020 | 2020 | R16
164630149016 | 162703149016 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-04-10 | 2019-04-10 | 2019-04-12 |  | 2019-06-03 | Underground | R16 | 2019-05-13 | 1 | 3 | 22 | 16 | 39 | 2019 | 2019 | R16
169546201671 | 166455201671 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-25 | 2020-08-25 | 2020-08-25 | 2020-09-08 | 2020-12-18 | Overhead | R16 | 2020-09-08 | 1 |  | 11 | 74 | 84 | 2020 | 2020 | R16
164633144393 | 165501144393 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-02-27 | 2019-02-27 | 2019-02-27 |  | 2019-04-24 | Overhead | R16 | 2019-03-06 | 1 |  | 6 | 36 | 41 | 2019 | 2019 | R16
166802149573 | 164014149573 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-17 | 2019-04-17 | 2019-04-17 |  | 2019-12-12 | Overhead | R16 | 2019-12-03 | 1 |  | 165 | 8 | 172 | 2019 | 2019 | R16
164134208794 | 162208208794 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-08-06 | 2020-08-06 | 2020-10-29 | 2021-01-26 | 2021-01-27 | Underground | R16 | 2021-01-26 | 1 | 61 | 64 | 2 | 125 | 2020 | 2021 | R16
163679160781 | 163293160781 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-04-12 | 2019-08-09 | 2019-08-09 | 2019-11-25 | 2023-06-08 | Overhead | R16 | 2019-11-25 | 86 |  | 77 | 924 | 1085 | 2019 | 2023 | R16
160593229226 | 161391229226 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-04-29 | 2021-05-03 | 2021-05-03 | 2021-05-15 | 2021-10-05 | Overhead | R16 | 2021-05-15 | 3 |  | 10 | 102 | 114 | 2021 | 2021 | R16
164735154938 | 163387154938 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-12 | 2019-06-12 | 2019-06-12 |  | 2022-08-02 | Overhead | R16 |  | 1 |  |  |  | 820 | 2019 | 2022 | R16
164777146655 | 167791146655 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-03-12 | 2019-03-12 | 2019-03-21 |  | 2020-10-06 | Underground | R16 | 2020-07-27 | 1 | 8 | 353 | 52 | 411 | 2019 | 2020 | R16
164784158084 | 167709158084 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-03-12 | 2019-03-12 | 2019-07-17 |  | 2020-10-06 | Underground | R16 | 2020-07-27 | 1 | 92 | 269 | 52 | 411 | 2019 | 2020 | R16
161660218160 | 168901218160 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-22 | 2021-01-22 | 2021-01-22 | 2022-03-02 | 2022-03-17 | Overhead | R16 | 2022-03-02 | 1 |  | 289 | 12 | 300 | 2021 | 2022 | R16
164786153322 | 167683153322 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-03-12 | 2019-03-12 | 2019-05-23 |  | 2020-10-06 | Underground | R16 | 2020-07-28 | 1 | 53 | 309 | 51 | 411 | 2019 | 2020 | R16
164796207645 | 168444207645 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-02-06 | 2020-03-23 | 2020-10-19 |  | 2021-11-09 | Underground | R16 |  | 33 | 151 |  |  | 459 | 2020 | 2021 | R16
166124281544 | 166887281544 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-26 | 2021-08-11 | 2022-06-03 |  | 2022-10-21 | Overhead | R16 |  | 119 | 213 |  |  | 431 | 2021 | 2022 | R16
168181156215 | 160316156215 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-22 | 2019-05-22 | 2019-06-25 |  | 2020-06-09 | Underground | R16 | 2020-02-14 | 1 | 25 | 169 | 83 | 275 | 2019 | 2020 | R16
164913146797 | 167807146797 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-03-12 | 2019-03-12 | 2019-03-22 |  | 2021-07-12 | Underground | R16 | 2020-11-24 | 1 | 9 | 438 | 165 | 610 | 2019 | 2021 | R16
164914146212 | 168417146212 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-03-15 | 2019-03-15 | 2019-03-15 |  | 2021-01-08 | Underground | R16 | 2020-10-05 | 1 |  | 407 | 70 | 476 | 2019 | 2021 | R16
163614230376 | 164698230376 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-07-08 | 2021-08-23 | Overhead | R16 | 2021-07-08 | 1 |  | 43 | 33 | 75 | 2021 | 2021 | R16
164916191758 | 167800191758 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-03-12 | 2019-03-12 | 2020-05-21 |  | 2020-10-06 | Underground | R16 | 2020-09-18 | 1 | 313 | 87 | 13 | 411 | 2019 | 2020 | R16
165712215603 | 163532215603 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-28 | 2020-12-28 | 2020-12-28 | 2021-02-05 | 2021-06-03 | Overhead | R16 | 2021-02-05 | 1 |  | 30 | 85 | 114 | 2020 | 2021 | R16
169297149162 | 163411149162 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-14 | 2019-04-14 | 2019-04-14 |  | 2019-06-03 | Overhead | R16 | 2019-05-08 | 0 |  | 18 | 19 | 36 | 2019 | 2019 | R16
165954231055 | 166117231055 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-18 | 2021-05-18 | 2021-05-18 | 2021-05-20 | 2021-08-16 | Overhead | R16 | 2021-05-20 | 1 |  | 3 | 63 | 65 | 2021 | 2021 | R16
166463232389 | 169203232389 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-20 | 2021-04-20 | 2021-05-26 | 2021-07-13 | 2021-07-16 | Underground | R16 | 2021-07-13 | 1 | 27 | 35 | 4 | 64 | 2021 | 2021 | R16
164956146798 | 167842146798 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-03-12 | 2019-03-12 | 2019-03-22 |  | 2021-11-02 | Underground | R16 | 2021-06-15 | 1 | 9 | 583 | 101 | 691 | 2019 | 2021 | R16
163655154198 | 162171154198 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-04 | 2019-06-04 | 2019-06-04 | 2019-07-19 | 2019-07-19 | Overhead | R16 | 2019-07-19 | 1 |  | 34 |  | 34 | 2019 | 2019 | R16
168314223463 | 160282223463 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-03-12 | 2021-03-12 | 2021-03-12 |  | 2021-08-23 | Overhead | R16 | 2021-07-26 | 1 |  | 97 | 21 | 117 | 2021 | 2021 | R16
169616232427 | 162534232427 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-22 | 2021-05-25 | 2021-05-25 | 2021-07-02 | 2021-08-12 | Overhead | R16 | 2021-07-02 | 47 |  | 29 | 30 | 104 | 2021 | 2021 | R16
166489274923 | 166497274923 | NON-RESIDENTIAL - LODGING | UG R16 RESD AND NON RESD UD | Commercial | 2019-05-01 | 2019-05-01 | 2022-04-05 | 2022-12-01 | 2022-12-22 | Underground | R16 | 2022-12-01 | 1 | 765 | 173 | 16 | 952 | 2019 | 2022 | R16
165058145350 | 167169145350 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-08 | 2019-03-08 | 2019-03-08 |  | 2019-05-20 | Overhead | R16 | 2019-04-11 | 1 |  | 25 | 28 | 52 | 2019 | 2019 | R16
165504197606 | 168557197606 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-16 | 2020-07-16 | 2020-07-16 | 2020-07-20 | 2020-10-06 | Overhead | R16 | 2020-07-20 | 1 |  | 3 | 57 | 59 | 2020 | 2020 | R16
165082161644 | 160777161644 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-29 | 2019-03-29 | 2019-08-20 |  | 2019-11-13 | Underground | R16 | 2019-11-05 | 1 | 103 | 56 | 7 | 164 | 2019 | 2019 | R16
167983216685 | 169441216685 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-08 | 2020-12-08 | 2021-01-08 | 2021-02-08 | 2021-06-03 | Underground | R16 | 2021-02-08 | 1 | 24 | 22 | 84 | 128 | 2020 | 2021 | R16
164233234290 | 169321234290 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-24 | 2021-05-24 | 2021-06-10 |  | 2022-02-11 | Underground | R16 | 2022-02-08 | 1 | 14 | 174 | 4 | 190 | 2021 | 2022 | R16
165119149164 | 163298149164 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-12 | 2019-04-15 | 2019-04-15 |  | 2019-05-28 | Overhead | R16 | 2019-04-25 | 2 |  | 9 | 24 | 33 | 2019 | 2019 | R16
163221148050 | 168421148050 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-15 | 2019-03-18 | 2019-04-02 | 2019-06-06 | 2019-06-07 | Underground | R16 | 2019-06-06 | 2 | 12 | 48 | 2 | 61 | 2019 | 2019 | R16
165137176941 | 160503176941 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-30 | 2020-01-02 | 2020-01-14 |  | 2021-11-10 | Overhead | R16 |  | 4 | 9 |  |  | 488 | 2019 | 2021 | R16
165139149074 | 161169149074 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-03 | 2019-04-03 | 2019-04-12 |  | 2019-06-03 | Underground | R16 | 2019-05-06 | 1 | 8 | 17 | 21 | 44 | 2019 | 2019 | R16
169483147748 | 160932147748 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-01 | 2019-04-01 | 2019-04-01 |  | 2019-05-28 | Overhead | R16 | 2019-04-29 | 1 |  | 21 | 22 | 42 | 2019 | 2019 | R16
162462152883 | 169690152883 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-17 | 2019-05-17 | 2019-05-20 |  | 2019-08-12 | Overhead | R16 | 2019-06-04 | 1 | 2 | 12 | 50 | 62 | 2019 | 2019 | R16
162051222385 | 168064222385 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-03 | 2021-03-03 | 2021-03-03 | 2021-03-31 | 2023-06-07 | Overhead | R16 | 2021-03-31 | 1 |  | 21 | 571 | 591 | 2021 | 2023 | R16
165179173215 | 165602173215 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-12-02 | 2019-12-02 | 2019-12-02 |  | 2021-04-22 | Underground | R16 | 2021-01-29 | 1 |  | 305 | 60 | 364 | 2019 | 2021 | R16
162954248441 | 168499248441 | SPECIFIC BUDGET PROJECTS | OH R16 RES NON RES OD | Commercial | 2021-05-19 | 2021-05-19 | 2021-09-17 |  | 2022-03-23 | Overhead | R16 |  | 1 | 88 |  |  | 221 | 2021 | 2022 | R16
166161224952 | 160937224952 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-16 | 2021-03-25 | 2021-03-26 | 2021-06-08 | 2021-08-04 | Underground | R16 | 2021-06-08 | 8 | 2 | 53 | 42 | 102 | 2021 | 2021 | R16
165847282779 | 166696282779 | NON-RESIDENTIAL - HEALTH CARE | UG R16 RESD AND NON RESD UD | Commercial | 2021-02-25 | 2021-02-25 | 2022-06-16 | 2022-12-28 | 2023-01-13 | Underground | R16 | 2022-12-28 | 1 | 341 | 140 | 13 | 492 | 2021 | 2023 | R16
162617156451 | 169364156451 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-16 | 2019-05-16 | 2019-06-27 | 2019-07-29 | 2019-07-31 | Overhead | R16 | 2019-07-29 | 1 | 31 | 23 | 3 | 55 | 2019 | 2019 | R16
165270146899 | 169554146899 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-23 | 2019-03-23 | 2019-03-23 |  | 2019-06-03 | Overhead | R16 | 2019-05-13 | 0 |  | 36 | 16 | 51 | 2019 | 2019 | R16
167640149885 | 167650149885 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-11 | 2019-03-11 | 2019-04-22 | 2019-06-28 | 2019-07-31 | Underground | R16 | 2019-06-28 | 1 | 31 | 50 | 24 | 103 | 2019 | 2019 | R16
165273186104 | 169377186104 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2020-04-01 | 2020-04-01 | 2020-04-01 |  | 2021-05-07 | Underground | R16 | 2021-02-26 | 1 |  | 238 | 51 | 288 | 2020 | 2021 | R16
165278145709 | 166763145709 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-07 | 2019-03-07 | 2019-03-11 |  | 2019-08-26 | Overhead | R16 | 2019-07-05 | 1 | 3 | 85 | 37 | 123 | 2019 | 2019 | R16
168340152296 | 168726152296 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-14 | 2019-05-14 | 2019-05-14 | 2019-07-08 | 2019-07-08 | Overhead | R16 | 2019-07-08 | 1 |  | 40 |  | 40 | 2019 | 2019 | R16
165888154376 | 160263154376 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-21 | 2019-05-21 | 2019-06-05 |  | 2019-09-03 | Underground | R16 | 2019-08-06 | 1 | 12 | 45 | 21 | 76 | 2019 | 2019 | R16
164348230302 | 165873230302 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-22 | 2021-02-22 | 2021-05-11 | 2021-06-09 | 2021-06-10 | Underground | R16 | 2021-06-09 | 1 | 57 | 22 | 2 | 79 | 2021 | 2021 | R16
160980144361 | 161429144361 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-05 | 2019-02-05 | 2019-02-26 | 2019-04-23 | 2019-04-24 | Underground | R16 | 2019-04-23 | 1 | 16 | 41 | 2 | 57 | 2019 | 2019 | R16
165927220117 | 168106220117 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-10-15 | 2020-12-08 | 2021-02-10 |  | 2021-11-09 | Underground | R16 |  | 39 | 47 |  |  | 279 | 2020 | 2021 | R16
165699264714 | 165704264714 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Residential | 2019-04-26 | 2019-04-26 | 2022-01-13 | 2022-02-03 | 2023-11-09 | Underground | R16 | 2022-02-03 | 1 | 710 | 16 | 461 | 1185 | 2019 | 2023 | R16
165404289046 | 167388289046 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2022-06-01 | 2022-06-07 | 2022-08-15 |  | 2023-09-06 | Underground | R16 |  | 5 | 50 |  |  | 331 | 2022 | 2023 | R16
168168155908 | 163050155908 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-10 | 2019-06-10 | 2019-06-20 |  | 2022-05-17 | Underground | R16 | 2019-12-13 | 1 | 9 | 127 | 633 | 767 | 2019 | 2022 | R16
160657148117 | 167528148117 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Commercial | 2019-03-11 | 2019-03-21 | 2019-04-05 | 2019-04-15 | 2019-07-01 | Overhead | R16 | 2019-04-15 | 9 | 12 | 7 | 56 | 81 | 2019 | 2019 | R16
166014156722 | 168222156722 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-05-09 | 2019-05-09 | 2019-07-01 | 2019-09-25 | 2019-09-26 | Underground | R16 | 2019-09-25 | 1 | 38 | 63 | 2 | 101 | 2019 | 2019 | R16
166282219332 | 163601219332 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-28 | 2021-01-07 | 2021-02-02 | 2021-03-23 | 2021-11-05 | Underground | R16 | 2021-03-23 | 9 | 19 | 36 | 164 | 225 | 2020 | 2021 | R16
165463149525 | 162188149525 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-08 | 2019-04-08 | 2019-04-17 |  | 2021-11-05 | Underground | R16 | 2021-05-10 | 1 | 8 | 539 | 130 | 675 | 2019 | 2021 | R16
163590144833 | 163582144833 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-14 | 2019-02-14 | 2019-03-04 | 2019-04-25 | 2019-04-25 | Underground | R16 | 2019-04-25 | 1 | 13 | 39 |  | 51 | 2019 | 2019 | R16
167195226500 | 164024226500 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2021-03-29 | 2021-03-29 | 2021-04-10 |  | 2022-01-04 | Underground | R16 | 2021-11-10 | 1 | 10 | 153 | 40 | 202 | 2021 | 2022 | R16
165247205005 | 163361205005 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-06 | 2021-07-26 | Underground | R16 | 2020-11-06 | 1 |  | 31 | 187 | 217 | 2020 | 2021 | R16
163475149948 | 164850149948 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-22 | 2019-04-22 | 2019-04-22 |  | 2019-06-03 | Overhead | R16 | 2019-05-16 | 1 |  | 19 | 13 | 31 | 2019 | 2019 | R16
162322166689 | 165814166689 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-01-08 | 2019-01-08 | 2019-10-04 | 2020-07-08 | 2020-10-21 | Underground | R16 | 2020-07-08 | 1 | 194 | 199 | 76 | 467 | 2019 | 2020 | R16
164277222159 | 164316222159 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-16 | 2021-02-16 | 2021-03-02 | 2021-04-30 | 2021-11-05 | Underground | R16 | 2021-04-30 | 1 | 11 | 44 | 136 | 189 | 2021 | 2021 | R16
166694210311 | 162842210311 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-23 | 2020-09-30 | 2020-11-11 |  | 2021-04-16 | Overhead | R16 | 2020-12-30 | 6 | 31 | 36 | 78 | 148 | 2020 | 2021 | R16
163203148368 | 162055148368 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-06 | 2019-04-06 | 2019-04-06 | 2019-06-04 | 2019-06-05 | Overhead | R16 | 2019-06-04 | 0 |  | 42 | 2 | 43 | 2019 | 2019 | R16
165615150261 | 169277150261 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-03-21 | 2019-04-24 | 2019-04-25 |  | 2019-06-03 | Overhead | R16 |  | 25 | 2 |  |  | 53 | 2019 | 2019 | R16
168772145902 | 169229145902 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-01-28 | 2019-01-28 | 2019-03-12 | 2019-06-25 | 2019-11-20 | Underground | R16 | 2019-06-25 | 1 | 32 | 76 | 107 | 213 | 2019 | 2019 | R16
165616146157 | 168412146157 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-15 | 2019-03-15 | 2019-03-15 |  | 2019-04-24 | Underground | R16 | 2019-03-20 | 1 |  | 4 | 26 | 29 | 2019 | 2019 | R16
169725208201 | 169011208201 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-20 | 2020-10-23 | 2020-10-23 | 2021-03-04 | 2021-06-03 | Overhead | R16 | 2021-03-04 | 4 |  | 95 | 66 | 163 | 2020 | 2021 | R16
169510225526 | 169534225526 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2021-03-09 | 2021-03-21 | 2021-04-01 |  | 2022-06-20 | Overhead | R16 |  | 9 | 9 |  |  | 335 | 2021 | 2022 | R16
164316147998 | 161901147998 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-05 | 2019-04-05 | 2019-04-05 | 2019-05-28 | 2019-06-14 | Overhead | R16 | 2019-05-28 | 1 |  | 38 | 14 | 51 | 2019 | 2019 | R16
163583223466 | 163487223466 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-28 | 2020-12-28 | 2021-03-12 | 2021-06-03 | 2021-06-03 | Underground | R16 | 2021-06-03 | 1 | 55 | 60 |  | 114 | 2020 | 2021 | R16
163873227181 | 169514227181 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-09 | 2021-03-15 | 2021-04-16 |  | 2021-11-04 | Overhead | R16 | 2021-06-24 | 5 | 25 | 50 | 96 | 173 | 2021 | 2021 | R16
165829210642 | 161813210642 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-01 | 2020-11-13 | 2020-11-13 | 2020-12-29 | 2021-04-16 | Overhead | R16 | 2020-12-29 | 10 |  | 33 | 79 | 120 | 2020 | 2021 | R16
161547218902 | 160594218902 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-28 | 2021-01-28 | 2021-01-28 | 2021-12-09 | 2022-02-01 | Overhead | R16 | 2021-12-09 | 1 |  | 226 | 39 | 264 | 2021 | 2022 | R16
164904201350 | 165818201350 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-08-21 | 2020-08-21 | 2020-08-21 | 2020-09-22 | 2020-09-23 | Overhead | R16 | 2020-09-22 | 1 |  | 23 | 2 | 24 | 2020 | 2020 | R16
164550200900 | 161086200900 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG R16 RESD AND NON RESD UD | Commercial | 2019-05-28 | 2019-05-28 | 2020-08-18 | 2022-05-16 | 2022-06-01 | Underground | R16 | 2022-05-16 | 1 | 321 | 455 | 13 | 787 | 2019 | 2022 | R16
164241199501 | 161711199501 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-03 | 2020-08-03 | 2020-08-03 |  | 2021-09-13 | Underground | R16 | 2021-08-18 | 1 |  | 273 | 19 | 291 | 2020 | 2021 | R16
167620221527 | 166524221527 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2021-02-25 | 2021-02-25 | 2021-02-25 |  | 2021-10-26 | Overhead | R16 | 2021-09-10 | 1 |  | 142 | 33 | 174 | 2021 | 2021 | R16
168260219279 | 169297219279 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-25 | 2021-01-25 | 2021-02-03 | 2021-07-14 | 2021-08-05 | Underground | R16 | 2021-07-14 | 1 | 8 | 116 | 17 | 139 | 2021 | 2021 | R16
168778229237 | 165422229237 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2021-04-02 | 2021-04-02 | 2021-05-04 | 2021-06-17 | 2021-06-18 | Overhead | R16 | 2021-06-17 | 1 | 23 | 33 | 2 | 56 | 2021 | 2021 | R16
166918217827 | 168293217827 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-20 | 2021-01-20 | 2021-01-20 |  | 2021-04-29 | Overhead | R16 | 2021-02-08 | 1 |  | 14 | 59 | 72 | 2021 | 2021 | R16
165810148048 | 169709148048 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-03-25 | 2019-03-25 | 2019-04-02 |  | 2019-05-10 | Overhead | R16 |  | 1 | 7 |  |  | 35 | 2019 | 2019 | R16
169002201079 | 161066201079 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-07-30 | 2020-07-30 | 2020-08-20 |  | 2021-11-05 | Underground | R16 |  | 1 | 16 |  |  | 332 | 2020 | 2021 | R16
165812176982 | 161127176982 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-01-03 | 2020-01-03 | 2020-01-14 |  | 2021-11-10 | Underground | R16 |  | 1 | 8 |  |  | 484 | 2020 | 2021 | R16
169015232166 | 161525232166 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-29 | 2021-04-29 | 2021-05-24 |  | 2021-11-11 | Underground | R16 | 2021-07-20 | 1 | 18 | 42 | 83 | 141 | 2021 | 2021 | R16
164636149464 | 167199149464 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-08 | 2019-03-08 | 2019-04-17 | 2020-04-28 | 2020-04-29 | Underground | R16 | 2020-04-28 | 1 | 29 | 270 | 2 | 299 | 2019 | 2020 | R16
164998211159 | 165019211159 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-16 | 2020-11-16 | 2020-11-19 | 2021-02-18 | 2021-05-05 | Overhead | R16 | 2021-02-18 | 1 | 4 | 66 | 55 | 123 | 2020 | 2021 | R16
160686223917 | 160336223917 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-03-12 | 2021-03-12 | 2021-03-17 | 2021-08-03 | 2021-12-17 | Underground | R16 | 2021-08-03 | 1 | 4 | 100 | 99 | 201 | 2021 | 2021 | R16
169126216342 | 165079216342 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-06 | 2021-01-06 | 2021-01-06 | 2021-01-15 | 2021-04-29 | Underground | R16 | 2021-01-15 | 1 |  | 8 | 75 | 82 | 2021 | 2021 | R16
161221146584 | 167777146584 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-12 | 2019-03-12 | 2019-03-19 | 2019-06-24 | 2019-06-26 | Underground | R16 | 2019-06-24 | 1 | 6 | 70 | 3 | 77 | 2019 | 2019 | R16
168541220801 | 164574220801 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-16 | 2021-02-17 | 2021-02-17 |  | 2021-06-02 | Overhead | R16 | 2021-03-04 | 2 |  | 12 | 65 | 77 | 2021 | 2021 | R16
165894148243 | 161489148243 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-04 | 2019-04-04 | 2019-04-04 |  | 2019-05-28 | Overhead | R16 | 2019-05-02 | 1 |  | 21 | 19 | 39 | 2019 | 2019 | R16
162776144406 | 162777144406 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-02-11 | 2019-02-11 | 2019-02-27 | 2019-05-06 | 2019-05-15 | Overhead | R16 | 2019-05-06 | 1 | 13 | 49 | 8 | 68 | 2019 | 2019 | R16
163830157216 | 166116157216 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-30 | 2019-04-30 | 2019-07-06 | 2019-10-23 | 2019-10-24 | Underground | R16 | 2019-10-23 | 1 | 49 | 78 | 2 | 128 | 2019 | 2019 | R16
165963160454 | 162942160454 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-11 | 2019-04-11 | 2019-08-07 |  | 2019-09-11 | Underground | R16 | 2019-09-04 | 1 | 85 | 21 | 6 | 110 | 2019 | 2019 | R16
162615210135 | 163889210135 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-10 | 2020-11-10 | 2020-11-10 |  | 2021-11-04 | Overhead | R16 | 2021-06-03 | 1 |  | 148 | 111 | 258 | 2020 | 2021 | R16
166034156808 | 167497156808 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-07-01 | 2019-07-01 | 2019-07-01 |  | 2020-06-09 | Underground | R16 | 2020-04-03 | 1 |  | 200 | 48 | 247 | 2019 | 2020 | R16
169736214312 | 167082214312 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-09 | 2020-10-15 | 2020-12-18 | 2021-02-09 | 2021-04-29 | Underground | R16 | 2021-02-09 | 5 | 47 | 38 | 58 | 145 | 2020 | 2021 | R16
166035166562 | 164097166562 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2019-10-02 | 2019-10-02 | 2019-10-02 |  | 2021-11-05 | Overhead | R16 | 2021-05-07 | 1 |  | 418 | 131 | 548 | 2019 | 2021 | R16
166554229479 | 164315229479 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-03-30 | 2021-03-30 | 2021-05-05 |  | 2022-06-20 | Overhead | R16 | 2022-05-23 | 1 | 27 | 274 | 21 | 320 | 2021 | 2022 | R16
166065149670 | 163571149670 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-15 | 2019-04-15 | 2019-04-19 |  | 2019-08-12 | Underground | R16 | 2019-05-20 | 1 | 5 | 22 | 61 | 86 | 2019 | 2019 | R16
162708228118 | 167529228118 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-13 | 2021-04-13 | 2021-04-23 | 2021-08-05 | 2021-09-02 | Underground | R16 | 2021-08-05 | 1 | 9 | 75 | 21 | 103 | 2021 | 2021 | R16
168984156801 | 162056156801 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-04 | 2019-06-04 | 2019-07-01 |  | 2019-08-26 | Underground | R16 | 2019-07-23 | 1 | 20 | 17 | 25 | 60 | 2019 | 2019 | R16
166079149991 | 164660149991 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-21 | 2019-04-21 | 2019-04-23 |  | 2019-06-04 | Overhead | R16 | 2019-05-29 | 0 | 2 | 27 | 5 | 32 | 2019 | 2019 | R16
168635203777 | 168574203777 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-16 | 2020-07-16 | 2020-09-15 |  | 2021-01-08 | Underground | R16 | 2020-10-05 | 1 | 44 | 15 | 70 | 127 | 2020 | 2021 | R16
167546216627 | 165617216627 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-07 | 2021-01-07 | 2021-01-07 |  | 2021-04-20 | Overhead | R16 | 2021-01-13 | 1 |  | 5 | 70 | 74 | 2021 | 2021 | R16
166123153412 | 160940153412 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-24 | 2019-05-24 | 2019-05-24 |  | 2022-08-02 | Overhead | R16 |  | 1 |  |  |  | 833 | 2019 | 2022 | R16
169578202189 | 167443202189 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-28 | 2020-08-28 | 2020-08-28 |  | 2021-10-28 | Overhead | R16 | 2021-05-11 | 1 |  | 183 | 123 | 305 | 2020 | 2021 | R16
168019206925 | 167342206925 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-12 | 2020-10-12 | 2020-10-12 |  | 2021-07-07 | Overhead | R16 | 2020-10-21 | 1 |  | 8 | 186 | 193 | 2020 | 2021 | R16
166641202236 | 165552202236 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-21 | 2020-08-21 | 2020-08-31 | 2021-02-21 | 2021-05-05 | Overhead | R16 | 2021-02-21 | 1 | 7 | 125 | 53 | 184 | 2020 | 2021 | R16
166186151672 | 167293151672 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-03-08 | 2019-03-08 | 2019-05-07 |  | 2020-12-14 | Underground | R16 | 2020-09-21 | 1 | 43 | 360 | 61 | 462 | 2019 | 2020 | R16
168552217589 | 169513217589 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-09 | 2020-12-09 | 2021-01-19 |  | 2021-08-23 | Underground | R16 | 2021-07-13 | 1 | 30 | 126 | 30 | 184 | 2020 | 2021 | R16
163664204270 | 161451204270 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-17 | 2020-09-18 | 2020-09-18 | 2020-09-30 | 2021-07-26 | Overhead | R16 | 2020-09-30 | 2 |  | 9 | 214 | 223 | 2020 | 2021 | R16
166237149635 | 164370149635 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-18 | 2019-04-18 | 2019-04-18 |  | 2019-06-03 | Overhead | R16 | 2019-05-10 | 1 |  | 17 | 17 | 33 | 2019 | 2019 | R16
169499212434 | 165554212434 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-08-21 | 2020-08-21 | 2020-12-02 |  | 2023-08-14 | Underground | R16 |  | 1 | 74 |  |  | 777 | 2020 | 2023 | R16
168043151939 | 168117151939 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-09 | 2019-05-09 | 2019-05-09 |  | 2022-01-24 | Overhead | R16 | 2019-06-25 | 1 |  | 34 | 675 | 708 | 2019 | 2022 | R16
163376202557 | 168459202557 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-03 | 2020-09-03 | 2020-09-03 |  | 2020-12-17 | Overhead | R16 | 2020-09-16 | 1 |  | 10 | 67 | 76 | 2020 | 2020 | R16
163407203101 | 168878203101 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-08 | 2020-09-08 | 2020-09-08 |  | 2022-10-20 | Overhead | R16 |  | 1 |  |  |  | 553 | 2020 | 2022 | R16
162878205467 | 162892205467 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-10 | 2020-08-10 | 2020-09-28 |  | 2021-11-10 | Underground | R16 | 2020-11-16 | 1 | 36 | 36 | 258 | 328 | 2020 | 2021 | R16
166414157251 | 162870157251 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-04-10 | 2019-05-24 | 2019-07-08 |  | 2019-10-04 | Underground | R16 |  | 33 | 32 |  |  | 128 | 2019 | 2019 | R16
166417149451 | 162459149451 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-09 | 2019-04-16 | 2019-04-17 |  | 2019-06-03 | Overhead | R16 | 2019-05-14 | 6 | 2 | 20 | 15 | 40 | 2019 | 2019 | R16
163960203372 | 166212203372 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-24 | 2020-08-24 | 2020-09-10 |  | 2021-01-08 | Underground | R16 | 2020-10-05 | 1 | 14 | 18 | 70 | 100 | 2020 | 2021 | R16
166440147795 | 160491147795 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-28 | 2019-03-29 | 2019-04-02 |  | 2019-06-03 | Underground | R16 |  | 2 | 3 |  |  | 48 | 2019 | 2019 | R16
163922216293 | 165157216293 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-06 | 2021-01-06 | 2021-01-06 |  | 2021-08-26 | Overhead | R16 | 2021-06-07 | 1 |  | 109 | 59 | 167 | 2021 | 2021 | R16
167563221371 | 164092221371 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-12 | 2021-02-23 | 2021-02-23 |  | 2021-08-11 | Underground | R16 | 2021-03-23 | 8 |  | 21 | 102 | 129 | 2021 | 2021 | R16
166491212938 | 166379212938 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2019-08-20 | 2020-12-07 | 2020-12-07 |  | 2022-06-10 | Overhead | R16 |  | 340 |  |  |  | 734 | 2019 | 2022 | R16
166496155889 | 162633155889 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-06 | 2019-06-06 | 2019-06-20 |  | 2019-08-09 | Underground | R16 | 2019-07-19 | 1 | 11 | 22 | 16 | 47 | 2019 | 2019 | R16
166497158196 | 162670158196 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-06 | 2019-06-06 | 2019-07-18 |  | 2019-09-12 | Underground | R16 | 2019-09-06 | 1 | 31 | 37 | 5 | 71 | 2019 | 2019 | R16
164562211038 | 165566211038 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-11-18 | 2020-11-18 | 2020-11-18 |  | 2021-04-14 | Underground | R16 | 2020-12-16 | 1 |  | 21 | 86 | 106 | 2020 | 2021 | R16
166533182164 | 166825182164 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-06-28 | 2019-06-28 | 2020-02-27 |  | 2020-06-09 | Overhead | R16 |  | 1 | 175 |  |  | 248 | 2019 | 2020 | R16
160835222432 | 168128222432 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2021-03-23 | 2021-08-09 | Overhead | R16 | 2021-03-23 | 1 |  | 14 | 100 | 113 | 2021 | 2021 | R16
166533215631 | 169633215631 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-12-09 | 2020-12-10 | 2020-12-28 |  | 2022-02-22 | Underground | R16 |  | 2 | 13 |  |  | 315 | 2020 | 2022 | R16
167872271478 | 168604271478 | NON-RESIDENTIAL - SMALL RETAIL | R16 RESD AND NON RESD US | Commercial | 2021-04-16 | 2021-04-16 | 2022-03-04 | 2022-04-20 | 2022-12-05 | Underground | R16 | 2022-04-20 | 1 | 231 | 34 | 164 | 427 | 2021 | 2022 | R16
165298207258 | 168689207258 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-09-05 | 2020-09-05 | 2020-10-14 | 2021-05-12 | 2021-06-14 | Underground | R16 | 2021-05-12 | 0 | 28 | 151 | 24 | 201 | 2020 | 2021 | R16
166626146710 | 169266146710 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-21 | 2019-03-21 | 2019-03-21 |  | 2019-05-28 | Underground | R16 | 2019-04-26 | 1 |  | 27 | 23 | 49 | 2019 | 2019 | R16
166637150317 | 165642150317 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-26 | 2019-04-26 | 2019-04-26 |  | 2019-07-08 | Overhead | R16 | 2019-07-01 | 1 |  | 47 | 6 | 52 | 2019 | 2019 | R16
166644147077 | 169454147077 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-03-22 | 2019-03-22 | 2019-03-26 |  | 2019-06-03 | Underground | R16 | 2019-05-10 | 1 | 3 | 34 | 17 | 52 | 2019 | 2019 | R16
166622213233 | 169344213233 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-08 | 2020-12-08 | 2020-12-09 | 2020-12-31 | 2021-05-05 | Overhead | R16 | 2020-12-31 | 1 | 2 | 17 | 90 | 107 | 2020 | 2021 | R16
162530223359 | 160301223359 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-03-12 | 2021-03-12 | 2021-03-12 | 2021-05-18 | 2021-11-08 | Overhead | R16 | 2021-05-18 | 1 |  | 48 | 125 | 172 | 2021 | 2021 | R16
166726149681 | 163749149681 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-16 | 2019-04-18 | 2019-04-18 |  | 2019-08-26 | Overhead | R16 | 2019-07-22 | 3 |  | 68 | 26 | 95 | 2019 | 2019 | R16
161210165905 | 169688165905 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-05-20 | 2019-09-16 | 2019-09-26 | 2020-04-21 | 2020-09-18 | Overhead | R16 | 2020-04-21 | 86 | 9 | 149 | 109 | 350 | 2019 | 2020 | R16
168039200420 | 163259200420 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-12 | 2020-08-12 | 2020-08-12 |  | 2020-10-06 | Overhead | R16 | 2020-09-04 | 1 |  | 18 | 23 | 40 | 2020 | 2020 | R16
166789160527 | 169619160527 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-07-12 | 2019-07-12 | 2019-08-08 |  | 2021-11-13 | Underground | R16 | 2020-01-14 | 1 | 20 | 114 | 479 | 611 | 2019 | 2021 | R16
168891229554 | 163025229554 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-05 | 2021-05-05 | 2021-05-05 | 2021-07-07 | 2022-01-11 | Overhead | R16 | 2021-07-07 | 1 |  | 46 | 135 | 180 | 2021 | 2022 | R16
162853201312 | 165514201312 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-20 | 2020-08-20 | 2020-08-20 | 2020-09-02 | 2021-01-08 | Overhead | R16 | 2020-09-02 | 1 |  | 10 | 93 | 102 | 2020 | 2021 | R16
166953151726 | 167870151726 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-07 | 2019-05-07 | 2019-05-07 |  | 2019-08-12 | Overhead | R16 | 2019-06-03 | 1 |  | 20 | 51 | 70 | 2019 | 2019 | R16
166983145980 | 167834145980 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-12 | 2019-03-13 | 2019-03-13 |  | 2019-08-26 | Overhead | R16 | 2019-07-17 | 2 |  | 91 | 29 | 120 | 2019 | 2019 | R16
167004146689 | 169095146689 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-20 | 2019-03-21 | 2019-03-21 |  | 2019-11-13 | Overhead | R16 | 2019-11-05 | 2 |  | 164 | 7 | 171 | 2019 | 2019 | R16
169356212760 | 166672212760 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-23 | 2020-12-03 | 2020-12-03 | 2021-01-05 | 2021-01-20 | Overhead | R16 | 2021-01-05 | 9 |  | 24 | 12 | 43 | 2020 | 2021 | R16
167139149324 | 163550149324 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-15 | 2019-04-15 | 2019-04-15 |  | 2019-08-26 | Overhead | R16 | 2019-05-28 | 1 |  | 32 | 65 | 96 | 2019 | 2019 | R16
163523265265 | 164441265265 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-04 | 2021-09-17 | 2022-01-19 |  | 2022-03-21 | Overhead | R16 |  | 185 | 89 |  |  | 316 | 2021 | 2022 | R16
169708205565 | 163513205565 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-09-25 | 2020-09-28 | 2020-09-28 |  | 2021-11-09 | Overhead | R16 | 2020-10-09 | 2 |  | 10 | 283 | 293 | 2020 | 2021 | R16
165463209678 | 160861209678 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-27 | 2020-11-05 | 2020-11-05 | 2020-12-01 | 2023-06-02 | Overhead | R16 | 2020-12-01 | 8 |  | 19 | 654 | 679 | 2020 | 2023 | R16
167151149255 | 168170149255 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-14 | 2019-03-14 | 2019-04-16 |  | 2019-05-20 | Overhead | R16 | 2019-04-19 | 1 | 24 | 4 | 22 | 48 | 2019 | 2019 | R16
160302216620 | 165568216620 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-01-07 | 2021-01-07 | 2021-01-07 |  | 2021-05-06 | Overhead | R16 | 2021-02-24 | 1 |  | 35 | 52 | 86 | 2021 | 2021 | R16
163636201882 | 166265201882 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-24 | 2020-08-24 | 2020-08-26 | 2020-09-16 | 2020-12-17 | Underground | R16 | 2020-09-16 | 1 | 3 | 16 | 67 | 84 | 2020 | 2020 | R16
162136221402 | 162385221402 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-09-22 | 2020-09-22 | 2021-02-23 | 2021-02-23 | 2021-02-26 | Overhead | R16 | 2021-02-23 | 1 | 111 |  | 4 | 114 | 2020 | 2021 | R16
162277232758 | 160554232758 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-28 | 2021-05-28 | 2021-05-28 | 2022-06-07 | 2022-08-03 | Overhead | R16 | 2022-06-07 | 1 |  | 268 | 42 | 309 | 2021 | 2022 | R16
167218148719 | 167291148719 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-03-08 | 2019-03-26 | 2019-04-11 |  | 2019-09-26 | Underground | R16 |  | 13 | 13 |  |  | 145 | 2019 | 2019 | R16
167233155702 | 166023155702 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-29 | 2019-04-29 | 2019-06-18 |  | 2019-10-28 | Underground | R16 | 2019-10-16 | 1 | 37 | 87 | 9 | 131 | 2019 | 2019 | R16
164431142555 | 162317142555 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-08 | 2019-02-08 | 2019-02-08 | 2019-03-13 | 2019-03-13 | Overhead | R16 | 2019-03-13 | 1 |  | 24 |  | 24 | 2019 | 2019 | R16
165152153139 | 160681153139 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-23 | 2019-05-23 | 2019-05-23 |  | 2019-09-03 | Overhead | R16 | 2019-08-01 | 1 |  | 51 | 24 | 74 | 2019 | 2019 | R16
167237151940 | 167264151940 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-03 | 2019-05-03 | 2019-05-09 |  | 2019-08-12 | Underground | R16 | 2019-06-11 | 1 | 5 | 24 | 45 | 72 | 2019 | 2019 | R16
167239154209 | 160678154209 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2019-05-23 | 2019-05-23 | 2019-06-04 |  | 2023-06-08 | Underground | R16 | 2022-12-06 | 1 | 9 | 916 | 133 | 1056 | 2019 | 2023 | R16
167242191398 | 162384191398 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-08 | 2019-04-08 | 2020-05-19 |  | 2020-08-28 | Underground | R16 | 2020-07-01 | 1 | 292 | 32 | 43 | 365 | 2019 | 2020 | R16
167243147237 | 169697147237 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-03-26 | 2019-03-26 | 2019-03-26 |  | 2019-04-15 | Overhead | R16 | 2019-03-28 | 1 |  | 3 | 13 | 15 | 2019 | 2019 | R16
168901229478 | 160672229478 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-26 | 2021-04-26 | 2021-05-05 |  | 2021-08-13 | Overhead | R16 | 2021-07-16 | 1 | 8 | 53 | 21 | 80 | 2021 | 2021 | R16
167243173870 | 165749173870 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-10-09 | 2019-12-03 | 2019-12-09 |  | 2020-06-09 | Overhead | R16 | 2020-03-24 | 40 | 5 | 77 | 56 | 175 | 2019 | 2020 | R16
162411216890 | 166559216890 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-08-25 | 2020-08-25 | 2021-01-11 |  | 2021-10-28 | Underground | R16 | 2021-09-27 | 1 | 100 | 186 | 24 | 308 | 2020 | 2021 | R16
167879154894 | 161891154894 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-02-06 | 2019-02-06 | 2019-06-11 | 2019-08-06 | 2019-12-31 | Underground | R16 | 2019-08-06 | 1 | 90 | 41 | 106 | 235 | 2019 | 2019 | R16
167247148223 | 161672148223 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-04 | 2019-04-04 | 2019-04-04 |  | 2019-08-12 | Overhead | R16 | 2019-05-22 | 1 |  | 35 | 59 | 93 | 2019 | 2019 | R16
167259148671 | 162361148671 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-08 | 2019-04-09 | 2019-04-09 |  | 2019-10-28 | Overhead | R16 | 2019-10-15 | 2 |  | 136 | 10 | 146 | 2019 | 2019 | R16
167575214153 | 161252214153 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-12-16 | 2020-12-16 | 2020-12-16 | 2021-07-24 | 2021-07-27 | Overhead | R16 | 2021-07-24 | 1 |  | 158 | 2 | 160 | 2020 | 2021 | R16
161854157333 | 162941157333 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-10 | 2019-07-09 | 2019-07-09 | 2019-08-15 | 2019-12-06 | Overhead | R16 | 2019-08-15 | 22 |  | 28 | 82 | 130 | 2019 | 2019 | R16
162343197701 | 168663197701 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-17 | 2020-07-17 | 2020-07-17 | 2020-08-18 | 2020-10-29 | Overhead | R16 | 2020-08-18 | 1 |  | 23 | 53 | 75 | 2020 | 2020 | R16
161959145303 | 161583145303 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-02-05 | 2019-03-07 | 2019-03-07 | 2019-08-04 | 2019-09-06 | Overhead | R16 | 2019-08-04 | 23 |  | 107 | 25 | 154 | 2019 | 2019 | R16
160706181854 | 161927181854 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2019-06-03 | 2019-06-13 | 2020-02-25 | 2020-04-21 | 2020-07-28 | Overhead | R16 | 2020-04-21 | 9 | 184 | 41 | 71 | 302 | 2019 | 2020 | R16
167361151119 | 167131151119 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-03 | 2019-05-03 | 2019-05-03 |  | 2019-08-12 | Overhead | R16 | 2019-05-29 | 1 |  | 19 | 54 | 72 | 2019 | 2019 | R16
167372148708 | 162680148708 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-09 | 2019-04-09 | 2019-04-09 |  | 2019-08-12 | Overhead | R16 | 2019-06-03 | 1 |  | 40 | 51 | 90 | 2019 | 2019 | R16
164551221399 | 166066221399 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-02-23 | 2021-02-23 | 2021-02-23 | 2022-11-29 | 2022-12-01 | Overhead | R16 | 2022-11-29 | 1 |  | 461 | 3 | 463 | 2021 | 2022 | R16
166209216379 | 166233216379 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-06 | 2020-10-06 | 2021-01-06 | 2021-03-10 | 2021-11-09 | Underground | R16 | 2021-03-10 | 1 | 67 | 46 | 175 | 286 | 2020 | 2021 | R16
167432175526 | 165037175526 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2019-10-05 | 2019-10-07 | 2019-12-31 |  | 2021-11-10 | Overhead | R16 |  | 1 | 62 |  |  | 548 | 2019 | 2021 | R16
169174148148 | 161796148148 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-05 | 2019-04-05 | 2019-04-05 | 2019-07-11 | 2019-07-12 | Overhead | R16 | 2019-07-11 | 1 |  | 70 | 2 | 71 | 2019 | 2019 | R16
167438148628 | 162372148628 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-08 | 2019-04-08 | 2019-04-08 |  | 2019-05-20 | Overhead | R16 | 2019-04-15 | 1 |  | 6 | 26 | 31 | 2019 | 2019 | R16
164655206229 | 166908206229 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-26 | 2020-10-05 | 2020-10-05 | 2020-10-30 | 2023-06-07 | Overhead | R16 | 2020-10-30 | 29 |  | 20 | 679 | 726 | 2020 | 2023 | R16
167475148739 | 162686148739 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-10 | 2019-04-10 | 2019-04-11 |  | 2019-10-28 | Overhead | R16 | 2019-10-14 | 1 | 2 | 133 | 11 | 144 | 2019 | 2019 | R16
161538209248 | 161611209248 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-30 | 2020-10-30 | 2020-10-30 |  | 2021-04-16 | Overhead | R16 | 2020-12-29 | 1 |  | 43 | 79 | 121 | 2020 | 2021 | R16
160463202282 | 167519202282 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-28 | 2020-08-29 | 2020-08-29 | 2020-09-24 | 2021-01-20 | Overhead | R16 | 2020-09-24 | 1 |  | 19 | 85 | 104 | 2020 | 2021 | R16
161256229594 | 163098229594 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-05 | 2021-05-05 | 2021-05-05 |  | 2021-11-03 | Overhead | R16 | 2021-06-22 | 1 |  | 35 | 97 | 131 | 2021 | 2021 | R16
167582151386 | 167452151386 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-06 | 2019-05-06 | 2019-05-06 |  | 2023-06-08 | Overhead | R16 | 2019-05-16 | 1 |  | 9 | 1061 | 1069 | 2019 | 2023 | R16
163354242864 | 163356242864 | Electric Vehicle | UG R16 RESD AND NON RESD UD | Commercial | 2020-11-06 | 2020-11-06 | 2021-08-09 | 2021-10-21 | 2021-11-03 | Underground | R16 | 2021-10-21 | 1 | 197 | 54 | 10 | 259 | 2020 | 2021 | R16
162504206484 | 166259206484 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-10-06 | 2020-10-07 | 2020-10-07 | 2020-10-07 | 2020-10-08 | Underground | R16 | 2020-10-07 | 2 |  |  | 2 | 3 | 2020 | 2020 | R16
167599157127 | 168049157127 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-07-05 | 2019-07-05 | 2019-07-05 |  | 2019-08-09 | Underground | R16 | 2019-07-26 | 1 |  | 16 | 11 | 26 | 2019 | 2019 | R16
163863220587 | 163614220587 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-09-25 | 2021-01-04 | 2021-02-16 | 2021-09-30 | 2021-10-19 | Underground | R16 | 2021-09-30 | 72 | 32 | 163 | 14 | 278 | 2020 | 2021 | R16
167671149083 | 163287149083 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-12 | 2019-04-12 | 2019-04-12 |  | 2019-06-03 | Overhead | R16 | 2019-05-15 | 1 |  | 24 | 14 | 37 | 2019 | 2019 | R16
168052231833 | 168449231833 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-19 | 2021-05-19 | 2021-05-21 |  | 2021-08-23 | Overhead | R16 | 2021-07-26 | 1 | 3 | 47 | 21 | 69 | 2021 | 2021 | R16
169636202623 | 167091202623 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2020-08-27 | 2020-08-27 | 2020-09-02 | 2022-10-03 | 2022-10-06 | Underground | R16 | 2022-10-03 | 1 | 5 | 544 | 4 | 551 | 2020 | 2022 | R16
167706152293 | 168347152293 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-10 | 2019-05-10 | 2019-05-13 |  | 2019-08-26 | Overhead | R16 | 2019-06-28 | 1 | 2 | 35 | 42 | 77 | 2019 | 2019 | R16
162714212968 | 168908212968 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-05 | 2020-12-05 | 2020-12-05 | 2021-02-03 | 2021-02-04 | Underground | R16 | 2021-02-03 | 0 |  | 43 | 2 | 44 | 2020 | 2021 | R16
167760156441 | 165688156441 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-04-27 | 2019-04-27 | 2019-06-25 |  | 2019-08-26 | Underground | R16 | 2019-07-02 | 0 | 42 | 6 | 40 | 86 | 2019 | 2019 | R16
167778154911 | 162968154911 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-06-11 | 2019-06-11 | 2019-06-11 |  | 2019-08-26 | Underground | R16 | 2019-06-25 | 1 |  | 11 | 45 | 55 | 2019 | 2019 | R16
167787146697 | 169376146697 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-21 | 2019-03-21 | 2019-03-21 |  | 2019-10-16 | Overhead | R16 | 2019-10-08 | 1 |  | 144 | 7 | 150 | 2019 | 2019 | R16
169127217394 | 166812217394 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-13 | 2021-01-15 | 2021-01-15 |  | 2021-11-05 | Overhead | R16 | 2021-04-07 | 3 |  | 59 | 153 | 213 | 2021 | 2021 | R16
167797165115 | 167883165115 | NON-RESIDENTIAL - LARGE OFFICE | UG R16 RESD AND NON RESD UD | Commercial | 2019-03-12 | 2019-03-12 | 2019-09-20 |  | 2020-11-19 | Underground | R16 | 2020-04-07 | 1 | 139 | 143 | 163 | 443 | 2019 | 2020 | R16
167816149463 | 163876149463 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-16 | 2019-04-16 | 2019-04-17 |  | 2019-08-12 | Overhead | R16 | 2019-06-13 | 1 | 2 | 42 | 43 | 85 | 2019 | 2019 | R16
160535202412 | 167905202412 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-09-09 | 2021-03-12 | Overhead | R16 | 2020-09-09 | 1 |  | 8 | 133 | 140 | 2020 | 2021 | R16
161899150156 | 160038150156 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-03-26 | 2019-04-02 | 2019-04-25 | 2019-08-05 | 2019-12-31 | Overhead | R16 | 2019-08-05 | 6 | 18 | 73 | 107 | 201 | 2019 | 2019 | R16
163010156346 | 162974156346 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-06-10 | 2019-06-23 | 2019-06-25 |  | 2019-08-26 | Overhead | R16 |  | 10 | 2 |  |  | 56 | 2019 | 2019 | R16
168039145033 | 166665145033 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-06 | 2019-03-06 | 2019-03-06 | 2019-12-26 | 2020-01-08 | Overhead | R16 | 2019-12-26 | 1 |  | 212 | 10 | 221 | 2019 | 2020 | R16
164637145161 | 169023145161 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-01-25 | 2019-02-07 | 2019-03-06 | 2019-03-21 | 2019-05-26 | Underground | R16 | 2019-03-21 | 10 | 20 | 12 | 47 | 86 | 2019 | 2019 | R16
167902148247 | 161820148247 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-04-04 | 2019-04-04 | 2019-04-04 |  | 2020-06-09 | Underground | R16 | 2019-12-20 | 1 |  | 187 | 123 | 309 | 2019 | 2020 | R16
162705227168 | 168404227168 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-16 | 2021-04-16 | 2021-04-16 | 2021-07-16 | 2021-10-25 | Overhead | R16 | 2021-07-16 | 1 |  | 66 | 72 | 137 | 2021 | 2021 | R16
160472251530 | 165235251530 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-13 | 2021-05-13 | 2021-10-11 |  | 2022-01-18 | Underground | R16 | 2021-12-22 | 1 | 108 | 53 | 20 | 179 | 2021 | 2022 | R16
169420210243 | 163886210243 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-10 | 2020-11-10 | 2020-11-10 |  | 2021-04-16 | Overhead | R16 | 2021-01-20 | 1 |  | 52 | 63 | 114 | 2020 | 2021 | R16
167963147716 | 161073147716 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-01 | 2019-04-01 | 2019-04-01 |  | 2019-05-20 | Overhead | R16 | 2019-04-11 | 1 |  | 9 | 28 | 36 | 2019 | 2019 | R16
161780142888 | 165854142888 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-08 | 2019-01-08 | 2019-02-12 | 2019-09-06 | 2019-09-10 | Underground | R16 | 2019-09-06 | 1 | 26 | 149 | 3 | 176 | 2019 | 2019 | R16
167111265712 | 165336265712 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-11-17 | 2021-10-28 | 2022-01-21 | 2022-04-12 | 2022-04-22 | Underground | R16 | 2022-04-12 | 248 | 62 | 58 | 9 | 374 | 2020 | 2022 | R16
162587172343 | 163009172343 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-12 | 2019-04-12 | 2019-11-19 | 2020-01-24 | 2023-06-07 | Underground | R16 | 2020-01-24 | 1 | 158 | 49 | 879 | 1084 | 2019 | 2023 | R16
168019222911 | 165015222911 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-17 | 2021-03-09 | 2021-03-09 |  | 2021-10-26 | Overhead | R16 | 2021-04-23 | 15 |  | 34 | 133 | 180 | 2021 | 2021 | R16
164841222593 | 162930222593 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-08 | 2021-02-26 | 2021-03-05 | 2022-03-15 | 2022-04-01 | Underground | R16 | 2022-03-15 | 15 | 6 | 268 | 14 | 300 | 2021 | 2022 | R16
168109147820 | 160941147820 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-31 | 2019-03-31 | 2019-03-31 |  | 2019-10-09 | Overhead | R16 | 2019-09-25 | 0 |  | 128 | 11 | 138 | 2019 | 2019 | R16
169589257057 | 168843257057 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2021-05-21 | 2021-10-22 | 2021-11-17 | 2022-04-28 | 2022-05-17 | Underground | R16 | 2022-04-28 | 111 | 19 | 117 | 14 | 258 | 2021 | 2022 | R16
160494233541 | 165197233541 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-13 | 2021-06-03 | 2021-06-03 | 2021-06-11 | 2021-08-03 | Overhead | R16 | 2021-06-11 | 16 |  | 7 | 38 | 59 | 2021 | 2021 | R16
168181148933 | 163025148933 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-11 | 2019-04-11 | 2019-04-12 |  | 2019-06-03 | Underground | R16 | 2019-05-08 | 1 | 2 | 19 | 19 | 38 | 2019 | 2019 | R16
168182147466 | 160377147466 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-03-28 | 2019-03-28 | 2019-03-28 |  | 2020-06-09 | Underground | R16 | 2020-03-10 | 1 |  | 249 | 66 | 314 | 2019 | 2020 | R16
168183148970 | 162415148970 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-09 | 2019-04-09 | 2019-04-12 |  | 2019-06-03 | Underground | R16 | 2019-05-07 | 1 | 4 | 18 | 20 | 40 | 2019 | 2019 | R16
168186150637 | 165280150637 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-04-24 | 2019-04-24 | 2019-04-30 |  | 2019-08-26 | Underground | R16 | 2019-07-16 | 1 | 5 | 56 | 30 | 89 | 2019 | 2019 | R16
166766207357 | 168475207357 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-16 | 2020-10-16 | 2020-10-16 | 2020-11-10 | 2021-07-19 | Overhead | R16 | 2020-11-10 | 1 |  | 18 | 180 | 197 | 2020 | 2021 | R16
168190152970 | 167877152970 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-08 | 2019-05-08 | 2019-05-20 |  | 2019-08-26 | Overhead | R16 | 2019-07-23 | 1 | 9 | 47 | 25 | 79 | 2019 | 2019 | R16
166391218309 | 168928218309 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-22 | 2021-01-22 | 2021-01-25 | 2021-03-11 | 2021-03-15 | Overhead | R16 | 2021-03-11 | 1 | 2 | 34 | 3 | 37 | 2021 | 2021 | R16
168200150092 | 165109150092 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-24 | 2019-04-24 | 2019-04-24 |  | 2019-08-12 | Overhead | R16 | 2019-05-29 | 1 |  | 26 | 54 | 79 | 2019 | 2019 | R16
168202227642 | 167122227642 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-08-23 | 2019-08-23 | 2021-04-19 |  | 2022-02-01 | Underground | R16 |  | 1 | 432 |  |  | 638 | 2019 | 2022 | R16
161142200316 | 163418200316 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-12 | 2020-08-12 | 2020-08-12 |  | 2020-11-02 | Overhead | R16 | 2020-09-02 | 1 |  | 16 | 44 | 59 | 2020 | 2020 | R16
168448203735 | 160515203735 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-13 | 2020-09-13 | 2020-09-14 |  | 2021-02-17 | Overhead | R16 | 2020-08-20 | 0 | 1 |  | 130 | 113 | 2020 | 2021 | R16
165121204736 | 162777204736 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-23 | 2020-09-23 | 2020-09-23 |  | 2021-07-24 | Overhead | R16 | 2020-11-17 | 1 |  | 40 | 179 | 218 | 2020 | 2021 | R16
168262151886 | 166676151886 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-02 | 2019-05-02 | 2019-05-09 |  | 2019-08-12 | Underground | R16 | 2019-05-29 | 1 | 6 | 15 | 54 | 73 | 2019 | 2019 | R16
168201236546 | 161739236546 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-01 | 2021-06-24 | 2021-06-24 | 2021-10-26 | 2021-12-01 | Overhead | R16 | 2021-10-26 | 169 |  | 89 | 27 | 283 | 2020 | 2021 | R16
168838222206 | 164386222206 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-16 | 2021-03-02 | 2021-03-02 |  | 2021-08-16 | Overhead | R16 | 2021-03-24 | 11 |  | 17 | 104 | 130 | 2021 | 2021 | R16
161714251098 | 168954251098 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2021-03-08 | 2021-03-08 | 2021-10-08 | 2022-09-22 | 2022-10-18 | Underground | R16 | 2022-09-22 | 1 | 155 | 250 | 19 | 422 | 2021 | 2022 | R16
168291148565 | 162216148565 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-08 | 2019-04-08 | 2019-04-08 |  | 2019-05-28 | Underground | R16 | 2019-04-25 | 1 |  | 14 | 24 | 37 | 2019 | 2019 | R16
168329179771 | 162246179771 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2019-06-04 | 2019-09-25 | 2020-02-07 |  | 2022-06-30 | Overhead | R16 |  | 82 | 98 |  |  | 803 | 2019 | 2022 | R16
163736218901 | 160542218901 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-28 | 2021-01-28 | 2021-01-28 |  | 2021-11-05 | Overhead | R16 | 2021-05-11 | 1 |  | 74 | 129 | 202 | 2021 | 2021 | R16
168341148282 | 161984148282 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-05 | 2019-04-05 | 2019-04-05 |  | 2019-08-12 | Overhead | R16 | 2019-05-22 | 1 |  | 34 | 59 | 92 | 2019 | 2019 | R16
161384205098 | 164200205098 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-28 | 2020-09-28 | 2020-09-28 |  | 2021-04-14 | Overhead | R16 | 2020-12-17 | 1 |  | 59 | 85 | 143 | 2020 | 2021 | R16
161283206576 | 164284206576 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-28 | 2020-10-06 | 2020-10-09 | 2020-11-21 | 2020-11-24 | Underground | R16 | 2020-11-21 | 7 | 4 | 31 | 2 | 42 | 2020 | 2020 | R16
164121208952 | 169512208952 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-21 | 2020-10-29 | 2020-10-29 |  | 2021-04-07 | Overhead | R16 | 2020-12-02 | 7 |  | 25 | 91 | 121 | 2020 | 2021 | R16
164059211252 | 165997211252 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-19 | 2020-11-19 | 2020-11-19 |  | 2021-04-29 | Overhead | R16 | 2021-02-04 | 1 |  | 56 | 61 | 116 | 2020 | 2021 | R16
168388148257 | 160247148257 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-03-27 | 2019-03-28 | 2019-04-05 |  | 2019-05-20 | Overhead | R16 |  | 2 | 7 |  |  | 39 | 2019 | 2019 | R16
164930232637 | 168791232637 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-20 | 2021-05-27 | 2021-05-27 |  | 2021-11-03 | Overhead | R16 | 2021-06-22 | 6 |  | 19 | 97 | 120 | 2021 | 2021 | R16
168423165563 | 162963165563 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-04-11 | 2019-04-11 | 2019-09-23 |  | 2020-06-09 | Underground | R16 | 2020-03-05 | 1 | 118 | 119 | 69 | 304 | 2019 | 2020 | R16
168462146814 | 168464146814 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-15 | 2019-03-15 | 2019-03-22 |  | 2019-05-20 | Underground | R16 | 2019-04-08 | 1 | 6 | 12 | 31 | 47 | 2019 | 2019 | R16
168481152886 | 166671152886 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-01 | 2019-05-01 | 2019-05-20 |  | 2019-08-12 | Overhead | R16 | 2019-06-19 | 1 | 14 | 23 | 39 | 74 | 2019 | 2019 | R16
166862200074 | 162672200074 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-07 | 2020-08-11 | 2020-08-11 | 2020-09-24 | 2021-07-15 | Overhead | R16 | 2020-09-24 | 3 |  | 33 | 211 | 245 | 2020 | 2021 | R16
168596148488 | 162169148488 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-09 | 2019-04-09 | 2019-04-09 |  | 2019-06-04 | Overhead | R16 | 2019-06-04 | 1 |  | 41 |  | 41 | 2019 | 2019 | R16
168858232062 | 162275232062 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-03 | 2021-05-23 | 2021-05-23 | 2021-07-14 | 2021-08-13 | Overhead | R16 | 2021-07-14 | 15 |  | 38 | 23 | 75 | 2021 | 2021 | R16
160391225958 | 166226225958 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-04-07 | 2021-04-07 | 2021-04-07 |  | 2021-11-09 | Underground | R16 |  | 1 |  |  |  | 155 | 2021 | 2021 | R16
168634151975 | 168099151975 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-05-09 | 2019-05-09 | 2019-05-09 |  | 2019-10-10 | Overhead | R16 | 2019-09-27 | 1 |  | 102 | 10 | 111 | 2019 | 2019 | R16
167164143328 | 163369143328 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-14 | 2019-02-14 | 2019-02-14 | 2019-04-01 | 2019-04-04 | Underground | R16 | 2019-04-01 | 1 |  | 33 | 4 | 36 | 2019 | 2019 | R16
165360211501 | 162387211501 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-03 | 2020-11-03 | 2020-11-20 | 2020-12-02 | 2021-07-28 | Underground | R16 | 2020-12-02 | 1 | 14 | 9 | 171 | 192 | 2020 | 2021 | R16
168675150293 | 165724150293 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-26 | 2019-04-26 | 2019-04-26 |  | 2019-08-12 | Overhead | R16 | 2019-06-03 | 1 |  | 27 | 51 | 77 | 2019 | 2019 | R16
168678146498 | 168763146498 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-19 | 2019-03-19 | 2019-03-19 |  | 2019-05-28 | Underground | R16 | 2019-04-22 | 1 |  | 25 | 27 | 51 | 2019 | 2019 | R16
161456209627 | 168977209627 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-20 | 2020-10-20 | 2020-11-04 | 2020-12-31 | 2021-04-22 | Underground | R16 | 2020-12-31 | 1 | 12 | 42 | 81 | 133 | 2020 | 2021 | R16
160020154116 | 162140154116 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-04 | 2019-06-04 | 2019-06-04 |  | 2019-08-26 | Overhead | R16 | 2019-07-08 | 1 |  | 25 | 36 | 60 | 2019 | 2019 | R16
163412204088 | 160409204088 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-09-14 | 2020-09-17 | 2020-09-17 | 2021-01-08 | 2021-04-20 | Underground | R16 | 2021-01-08 | 4 |  | 82 | 73 | 157 | 2020 | 2021 | R16
169010200768 | 169008200768 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-07-20 | 2020-07-20 | 2020-08-18 | 2021-08-13 | 2021-10-25 | Underground | R16 | 2021-08-13 | 1 | 22 | 259 | 52 | 331 | 2020 | 2021 | R16
164476224271 | 162008224271 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-22 | 2021-03-22 | 2021-03-22 |  | 2023-08-30 | Overhead | R16 | 2023-04-19 | 1 |  | 543 | 96 | 638 | 2021 | 2023 | R16
168757160465 | 168032160465 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-08 | 2019-05-08 | 2019-08-07 |  | 2019-10-28 | Underground | R16 | 2019-10-15 | 1 | 66 | 50 | 10 | 124 | 2019 | 2019 | R16
169867202342 | 166538202342 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-25 | 2020-08-30 | 2020-08-30 | 2020-10-06 | 2021-01-20 | Overhead | R16 | 2020-10-06 | 4 |  | 27 | 77 | 107 | 2020 | 2021 | R16
167217230093 | 160944230093 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-27 | 2021-05-10 | 2021-05-10 |  | 2021-08-23 | Underground | R16 | 2021-08-02 | 10 |  | 61 | 16 | 85 | 2021 | 2021 | R16
168807147244 | 168901147244 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-03-19 | 2019-03-20 | 2019-03-25 |  | 2019-08-12 | Overhead | R16 |  | 2 | 4 |  |  | 105 | 2019 | 2019 | R16
168808149671 | 163434149671 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-15 | 2019-04-15 | 2019-04-19 |  | 2019-08-12 | Underground | R16 | 2019-06-17 | 1 | 5 | 42 | 41 | 86 | 2019 | 2019 | R16
163630218558 | 167556218558 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-30 | 2020-11-30 | 2021-01-26 |  | 2021-08-11 | Underground | R16 | 2021-07-01 | 1 | 42 | 113 | 30 | 183 | 2020 | 2021 | R16
168840147342 | 169989147342 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-26 | 2019-03-26 | 2019-03-26 |  | 2019-05-28 | Overhead | R16 | 2019-04-29 | 1 |  | 25 | 22 | 46 | 2019 | 2019 | R16
169693203358 | 169688203358 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-23 | 2020-07-23 | 2020-09-10 | 2020-10-02 | 2020-10-05 | Underground | R16 | 2020-10-02 | 1 | 36 | 17 | 2 | 53 | 2020 | 2020 | R16
169723286472 | 165601286472 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-02-22 | 2021-03-30 | 2022-07-22 |  | 2023-04-19 | Underground | R16 | 2023-01-27 | 27 | 344 | 136 | 59 | 563 | 2021 | 2023 | R16
165638277252 | 162223277252 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-11-03 | 2020-11-03 | 2022-04-27 |  | 2022-08-03 | Underground | R16 |  | 1 | 387 |  |  | 457 | 2020 | 2022 | R16
164996221317 | 167828221317 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2021-01-19 | 2021-01-22 | 2021-02-24 |  | 2021-11-08 | Underground | R16 |  | 4 | 24 |  |  | 210 | 2021 | 2021 | R16
168875156345 | 166041156345 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-06-25 | 2019-06-25 | 2019-06-25 |  | 2020-10-06 | Underground | R16 | 2020-08-11 | 1 |  | 296 | 41 | 336 | 2019 | 2020 | R16
168894152579 | 169623152579 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-05-17 | 2019-05-17 | 2019-05-17 |  | 2019-08-12 | Overhead | R16 | 2019-05-30 | 1 |  | 10 | 53 | 62 | 2019 | 2019 | R16
168898147897 | 161336147897 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-03 | 2019-04-03 | 2019-04-03 |  | 2019-05-28 | Overhead | R16 | 2019-05-01 | 1 |  | 21 | 20 | 40 | 2019 | 2019 | R16
169384220017 | 162878220017 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-09 | 2021-02-09 | 2021-02-09 | 2021-03-23 | 2021-11-05 | Overhead | R16 | 2021-03-23 | 1 |  | 31 | 164 | 194 | 2021 | 2021 | R16
160391150865 | 166310150865 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-30 | 2019-04-30 | 2019-04-30 | 2019-05-23 | 2019-08-12 | Overhead | R16 | 2019-05-23 | 1 |  | 18 | 58 | 75 | 2019 | 2019 | R16
160420232606 | 164049232606 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-10 | 2021-05-27 | 2021-05-27 | 2021-07-08 | 2021-08-23 | Overhead | R16 | 2021-07-08 | 14 |  | 31 | 33 | 76 | 2021 | 2021 | R16
168954150829 | 166341150829 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-04-30 | 2019-04-30 | 2019-04-30 |  | 2019-10-14 | Underground | R16 | 2019-10-03 | 1 |  | 113 | 8 | 120 | 2019 | 2019 | R16
164540145707 | 166699145707 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-03-06 | 2019-03-06 | 2019-03-11 | 2019-03-12 | 2019-03-20 | Underground | R16 | 2019-03-12 | 1 | 4 | 2 | 7 | 11 | 2019 | 2019 | R16
168963157124 | 168048157124 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-07-05 | 2019-07-05 | 2019-07-05 |  | 2020-06-29 | Underground | R16 | 2020-04-22 | 1 |  | 209 | 49 | 257 | 2019 | 2020 | R16
166018225048 | 164151225048 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-03-30 | 2021-08-06 | Overhead | R16 | 2021-03-30 | 1 |  | 2 | 94 | 95 | 2021 | 2021 | R16
167027139541 | 165570139541 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-07 | 2019-01-07 | 2019-01-07 | 2019-01-31 | 2019-10-01 | Overhead | R16 | 2019-01-31 | 1 |  | 19 | 174 | 192 | 2019 | 2019 | R16
169003172055 | 162185172055 | NON-RESIDENTIAL - SMALL RETAIL | R16 RESD AND NON RESD US | Commercial | 2019-04-08 | 2019-11-17 | 2019-11-18 |  | 2021-07-06 | Underground | R16 |  | 160 | 1 |  |  | 587 | 2019 | 2021 | R16
161259231606 | 168760231606 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-20 | 2021-05-20 | 2021-05-20 |  | 2021-08-23 | Underground | R16 | 2021-08-04 | 1 |  | 55 | 14 | 68 | 2021 | 2021 | R16
169008157113 | 167234157113 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-03 | 2019-05-03 | 2019-07-03 |  | 2019-09-03 | Underground | R16 | 2019-08-26 | 1 | 44 | 39 | 7 | 88 | 2019 | 2019 | R16
167236148763 | 162231148763 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-04-08 | 2019-04-08 | 2019-04-09 |  | 2019-09-18 | Underground | R16 |  | 1 | 2 |  |  | 118 | 2019 | 2019 | R16
162996147842 | 168562147842 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-18 | 2019-04-01 | 2019-04-01 | 2019-08-30 | 2023-06-08 | Overhead | R16 | 2019-08-30 | 11 |  | 110 | 985 | 1104 | 2019 | 2023 | R16
165400218410 | 169326218410 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-25 | 2021-01-25 | 2021-01-25 |  | 2023-05-18 | Overhead | R16 | 2023-04-21 | 1 |  | 585 | 20 | 604 | 2021 | 2023 | R16
169056194396 | 167512194396 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2020-05-16 | 2020-06-15 | 2020-06-16 |  | 2022-05-20 | Underground | R16 |  | 21 | 2 |  |  | 525 | 2020 | 2022 | R16
167642150400 | 165601150400 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-25 | 2019-04-25 | 2019-04-25 | 2019-05-28 | 2023-06-08 | Overhead | R16 | 2019-05-28 | 1 |  | 24 | 1053 | 1076 | 2019 | 2023 | R16
169097208003 | 164379208003 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-06-25 | 2020-08-07 | 2020-10-22 |  | 2021-05-07 | Underground | R16 |  | 32 | 55 |  |  | 227 | 2020 | 2021 | R16
165054200433 | 168931200433 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-20 | 2020-07-20 | 2020-08-13 | 2023-04-14 | 2023-06-08 | Underground | R16 | 2023-04-14 | 1 | 19 | 697 | 40 | 754 | 2020 | 2023 | R16
162359172181 | 168851172181 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-05-13 | 2019-05-13 | 2019-11-18 |  | 2020-12-11 | Underground | R16 |  | 1 | 136 |  |  | 415 | 2019 | 2020 | R16
169104149637 | 164209149637 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-18 | 2019-04-18 | 2019-04-18 |  | 2019-08-26 | Overhead | R16 | 2019-07-26 | 1 |  | 72 | 22 | 93 | 2019 | 2019 | R16
165090152968 | 169943152968 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-05-20 | 2019-05-20 | 2019-05-20 | 2020-03-09 | 2020-06-09 | Underground | R16 | 2020-03-09 | 1 |  | 211 | 67 | 277 | 2019 | 2020 | R16
169120157003 | 167747157003 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-07-02 | 2019-07-02 | 2019-07-02 |  | 2023-06-08 | Overhead | R16 | 2019-09-16 | 1 |  | 55 | 974 | 1028 | 2019 | 2023 | R16
168012221187 | 165506221187 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-21 | 2021-02-21 | 2021-02-21 | 2022-04-19 | 2022-05-12 | Overhead | R16 | 2022-04-19 | 0 |  | 302 | 18 | 319 | 2021 | 2022 | R16
169162159710 | 163065159710 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-31 | 2019-07-31 | 2019-08-01 |  | 2022-08-02 | Overhead | R16 |  | 1 | 2 |  |  | 785 | 2019 | 2022 | R16
163365209673 | 162970209673 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-05 | 2020-11-05 | 2020-11-05 | 2020-11-09 | 2021-04-16 | Overhead | R16 | 2020-11-09 | 1 |  | 3 | 115 | 117 | 2020 | 2021 | R16
162320144806 | 164874144806 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-23 | 2019-02-23 | 2019-03-04 | 2019-03-12 | 2019-04-15 | Overhead | R16 | 2019-03-12 | 0 | 6 | 7 | 25 | 36 | 2019 | 2019 | R16
165068170877 | 165043170877 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-02-25 | 2019-02-25 | 2019-11-06 |  | 2022-08-29 | Underground | R16 |  | 1 | 183 |  |  | 916 | 2019 | 2022 | R16
169461227014 | 163696227014 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-26 | 2021-03-26 | 2021-04-15 | 2021-06-14 | 2021-06-15 | Underground | R16 | 2021-06-14 | 1 | 15 | 43 | 2 | 58 | 2021 | 2021 | R16
166521223955 | 169094223955 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-25 | 2021-01-25 | 2021-03-18 | 2021-06-10 | 2021-10-25 | Underground | R16 | 2021-06-10 | 1 | 39 | 61 | 98 | 196 | 2021 | 2021 | R16
162101211355 | 165991211355 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-19 | 2020-11-19 | 2020-11-19 | 2020-12-03 | 2021-08-16 | Overhead | R16 | 2020-12-03 | 1 |  | 11 | 183 | 193 | 2020 | 2021 | R16
161906218277 | 169845218277 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-10 | 2020-12-10 | 2021-01-26 |  | 2021-11-08 | Underground | R16 | 2021-05-27 | 1 | 34 | 88 | 118 | 238 | 2020 | 2021 | R16
168670153628 | 161033153628 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-28 | 2019-05-28 | 2019-05-28 |  | 2019-08-12 | Overhead | R16 | 2019-06-20 | 1 |  | 18 | 38 | 55 | 2019 | 2019 | R16
167005219126 | 164810219126 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-05 | 2021-01-30 | 2021-01-30 | 2021-03-23 | 2021-11-05 | Overhead | R16 | 2021-03-23 | 19 |  | 37 | 164 | 219 | 2021 | 2021 | R16
162493153884 | 161508153884 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-05-30 | 2019-05-30 | 2019-05-30 | 2019-12-05 | 2019-12-05 | Overhead | R16 | 2019-12-05 | 1 |  | 136 |  | 136 | 2019 | 2019 | R16
169406154417 | 167637154417 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-07 | 2019-05-07 | 2019-06-05 |  | 2019-09-18 | Underground | R16 | 2019-09-10 | 1 | 22 | 70 | 7 | 97 | 2019 | 2019 | R16
161394214621 | 169824214621 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-10-22 | 2020-10-22 | 2020-12-21 |  | 2022-06-06 | Underground | R16 |  | 1 | 43 |  |  | 423 | 2020 | 2022 | R16
161966220326 | 164940220326 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-05 | 2021-02-11 | 2021-02-11 | 2021-04-13 | 2021-07-14 | Overhead | R16 | 2021-04-13 | 28 |  | 44 | 67 | 137 | 2021 | 2021 | R16
169448150681 | 165892150681 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-29 | 2019-04-29 | 2019-04-29 |  | 2019-08-12 | Overhead | R16 | 2019-05-20 | 1 |  | 16 | 61 | 76 | 2019 | 2019 | R16
166732210414 | 168199210414 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-15 | 2020-10-15 | 2020-11-11 | 2021-03-08 | 2021-03-09 | Overhead | R16 | 2021-03-08 | 1 | 20 | 84 | 2 | 104 | 2020 | 2021 | R16
169450148017 | 161595148017 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-04 | 2019-04-04 | 2019-04-04 |  | 2019-05-28 | Overhead | R16 | 2019-04-23 | 1 |  | 14 | 26 | 39 | 2019 | 2019 | R16
165414202680 | 168437202680 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-03 | 2020-09-03 | 2020-09-03 | 2020-10-09 | 2021-02-17 | Overhead | R16 | 2020-10-09 | 1 |  | 27 | 94 | 120 | 2020 | 2021 | R16
168681190276 | 160913190276 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-24 | 2019-05-24 | 2020-05-08 |  | 2020-07-09 | Underground | R16 | 2020-06-09 | 1 | 251 | 23 | 23 | 295 | 2019 | 2020 | R16
163869197461 | 168299197461 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-15 | 2020-07-15 | 2020-07-15 | 2020-07-31 | 2020-10-06 | Overhead | R16 | 2020-07-31 | 1 |  | 13 | 48 | 60 | 2020 | 2020 | R16
169493151581 | 167247151581 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-04 | 2019-05-04 | 2019-05-06 |  | 2019-11-15 | Overhead | R16 | 2019-08-14 | 0 | 1 | 73 | 68 | 140 | 2019 | 2019 | R16
169502147814 | 161273147814 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-02 | 2019-04-02 | 2019-04-02 |  | 2019-08-26 | Underground | R16 | 2019-06-25 | 1 |  | 61 | 45 | 105 | 2019 | 2019 | R16
161288147986 | 161214147986 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-02 | 2019-04-02 | 2019-04-02 |  | 2019-04-26 | Underground | R16 | 2019-04-03 | 1 |  | 2 | 18 | 19 | 2019 | 2019 | R16
169537155133 | 163655155133 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-13 | 2019-06-13 | 2019-06-13 |  | 2019-08-26 | Overhead | R16 | 2019-07-22 | 1 |  | 28 | 26 | 53 | 2019 | 2019 | R16
162325240199 | 165695240199 | NON-RESIDENTIAL - WAREHOUSE | UG R16 RESD AND NON RESD UD | Commercial | 2021-02-22 | 2021-02-22 | 2021-07-23 | 2021-09-20 | 2021-10-12 | Underground | R16 | 2021-09-20 | 1 | 110 | 42 | 17 | 167 | 2021 | 2021 | R16
169652149205 | 161636149205 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-04-04 | 2019-04-04 | 2019-04-15 |  | 2019-08-12 | Overhead | R16 |  | 1 | 8 |  |  | 93 | 2019 | 2019 | R16
165258222971 | 169598222971 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-10 | 2021-03-10 | 2021-03-10 | 2021-03-23 | 2021-08-23 | Overhead | R16 | 2021-03-23 | 1 |  | 10 | 110 | 119 | 2021 | 2021 | R16
169679163078 | 166277163078 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-19 | 2019-08-19 | 2019-09-04 |  | 2020-07-01 | Underground | R16 | 2020-04-27 | 1 | 13 | 169 | 48 | 228 | 2019 | 2020 | R16
163046223282 | 169860223282 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-10 | 2021-03-11 | 2021-03-11 | 2021-03-24 | 2021-11-05 | Overhead | R16 | 2021-03-24 | 2 |  | 10 | 163 | 173 | 2021 | 2021 | R16
169712148128 | 169713148128 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-25 | 2019-03-25 | 2019-04-03 |  | 2019-05-28 | Underground | R16 | 2019-05-03 | 1 | 8 | 23 | 18 | 47 | 2019 | 2019 | R16
163434206393 | 166469206393 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-10-07 | 2020-10-07 | 2020-10-07 | 2020-12-04 | 2020-12-17 | Underground | R16 | 2020-12-04 | 1 |  | 43 | 10 | 52 | 2020 | 2020 | R16
161343226434 | 167204226434 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-12 | 2021-04-12 | 2021-04-12 |  | 2021-09-13 | Overhead | R16 | 2021-08-18 | 1 |  | 93 | 19 | 111 | 2021 | 2021 | R16
167115227083 | 168236227083 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-15 | 2021-04-15 | 2021-04-15 |  | 2021-11-03 | Overhead | R16 | 2021-06-23 | 1 |  | 50 | 96 | 145 | 2021 | 2021 | R16
161577144874 | 165824144874 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-03-01 | 2019-03-01 | 2019-03-05 | 2019-04-12 | 2019-04-12 | Underground | R16 | 2019-04-12 | 1 | 3 | 29 |  | 31 | 2019 | 2019 | R16
160214154508 | 161901154508 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-03 | 2019-06-03 | 2019-06-06 |  | 2019-10-09 | Overhead | R16 | 2019-09-25 | 1 | 4 | 80 | 11 | 93 | 2019 | 2019 | R16
169744150669 | 166150150669 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-30 | 2019-04-30 | 2019-04-30 |  | 2021-11-10 | Overhead | R16 | 2019-12-17 | 1 |  | 166 | 497 | 662 | 2019 | 2021 | R16
167408227401 | 168657227401 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-17 | 2021-04-17 | 2021-04-17 | 2021-05-04 | 2021-11-08 | Underground | R16 | 2021-05-04 | 0 |  | 12 | 135 | 146 | 2021 | 2021 | R16
169755148859 | 162855148859 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-11 | 2019-04-11 | 2019-04-11 |  | 2019-06-03 | Overhead | R16 | 2019-05-07 | 1 |  | 19 | 20 | 38 | 2019 | 2019 | R16
160829153481 | 160898153481 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-24 | 2019-05-24 | 2019-05-28 | 2019-08-09 | 2019-12-06 | Overhead | R16 | 2019-08-09 | 1 | 3 | 54 | 86 | 141 | 2019 | 2019 | R16
169762238365 | 166535238365 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-05-11 | 2020-05-11 | 2021-07-09 |  | 2021-09-14 | Underground | R16 | 2021-08-19 | 1 | 305 | 30 | 19 | 352 | 2020 | 2021 | R16
162865224561 | 169293224561 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-09 | 2021-03-09 | 2021-03-23 | 2021-08-30 | 2023-04-13 | Underground | R16 | 2021-08-30 | 1 | 11 | 115 | 424 | 548 | 2021 | 2023 | R16
169777157547 | 162948157547 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-10 | 2019-06-10 | 2019-07-10 |  | 2022-08-01 | Underground | R16 |  | 1 | 23 |  |  | 821 | 2019 | 2022 | R16
168389213531 | 169947213531 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-10 | 2020-12-10 | 2020-12-10 |  | 2021-08-11 | Overhead | R16 | 2021-03-17 | 1 |  | 70 | 106 | 175 | 2020 | 2021 | R16
169781151788 | 167972151788 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-08 | 2019-05-08 | 2019-05-08 |  | 2019-06-03 | Overhead | R16 | 2019-05-21 | 1 |  | 10 | 10 | 19 | 2019 | 2019 | R16
161348216323 | 166810216323 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-24 | 2021-01-05 | 2021-01-05 | 2021-02-08 | 2021-05-05 | Overhead | R16 | 2021-02-08 | 31 |  | 25 | 63 | 117 | 2020 | 2021 | R16
169683212159 | 162581212159 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-04 | 2020-11-04 | 2020-12-01 |  | 2021-05-06 | Underground | R16 | 2021-02-23 | 1 | 20 | 61 | 53 | 132 | 2020 | 2021 | R16
169790155801 | 165084155801 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-19 | 2019-06-19 | 2019-06-19 |  | 2022-08-02 | Overhead | R16 |  | 1 |  |  |  | 815 | 2019 | 2022 | R16
161288225592 | 165586225592 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-18 | 2021-04-02 | 2021-04-02 | 2021-07-09 | 2021-10-28 | Overhead | R16 | 2021-07-09 | 98 |  | 71 | 80 | 247 | 2020 | 2021 | R16
169793148856 | 162970148856 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-11 | 2019-04-11 | 2019-04-11 |  | 2019-08-12 | Overhead | R16 | 2019-05-08 | 1 |  | 20 | 69 | 88 | 2019 | 2019 | R16
169439276955 | 166405276955 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG R16 RESD AND NON RESD UD | Commercial | 2021-04-08 | 2021-06-03 | 2022-04-27 | 2023-05-11 | 2023-11-20 | Underground | R16 | 2023-05-11 | 41 | 235 | 272 | 138 | 683 | 2021 | 2023 | R16
169807154455 | 168428154455 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-05-10 | 2019-05-29 | 2019-06-06 |  | 2019-08-19 | Overhead | R16 |  | 14 | 7 |  |  | 72 | 2019 | 2019 | R16
164477275825 | 167016275825 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-04-09 | 2021-09-22 | 2022-04-13 | 2023-01-05 | 2023-01-05 | Underground | R16 | 2023-01-05 | 119 | 146 | 192 |  | 455 | 2021 | 2023 | R16
169827149186 | 163481149186 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-15 | 2019-04-15 | 2019-04-15 |  | 2019-08-26 | Overhead | R16 | 2019-06-25 | 1 |  | 52 | 45 | 96 | 2019 | 2019 | R16
166176257160 | 168776257160 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-19 | 2021-07-07 | 2021-11-17 | 2022-01-06 | 2022-01-24 | Overhead | R16 | 2022-01-06 | 58 | 96 | 37 | 13 | 201 | 2021 | 2022 | R16
169828159356 | 168965159356 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-07-09 | 2019-07-09 | 2019-07-29 |  | 2022-07-27 | Underground | R16 |  | 1 | 15 |  |  | 797 | 2019 | 2022 | R16
168789216140 | 160510216140 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-12 | 2020-12-12 | 2021-01-04 | 2021-03-03 | 2021-03-04 | Underground | R16 | 2021-03-03 | 0 | 16 | 43 | 2 | 59 | 2020 | 2021 | R16
165968223071 | 168249223071 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-04 | 2021-03-10 | 2021-03-10 | 2021-04-22 | 2021-04-23 | Overhead | R16 | 2021-04-22 | 5 |  | 32 | 2 | 37 | 2021 | 2021 | R16
167658142890 | 167853142890 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-17 | 2019-01-17 | 2019-02-12 | 2019-05-21 | 2019-05-21 | Underground | R16 | 2019-05-21 | 1 | 19 | 71 |  | 89 | 2019 | 2019 | R16
168450150749 | 166026150749 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-29 | 2019-04-29 | 2019-04-29 | 2019-05-23 | 2019-08-12 | Overhead | R16 | 2019-05-23 | 1 |  | 19 | 58 | 76 | 2019 | 2019 | R16
169991150812 | 166732150812 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-02 | 2019-05-02 | 2019-05-02 |  | 2019-08-26 | Underground | R16 | 2019-07-10 | 1 |  | 50 | 34 | 83 | 2019 | 2019 | R16
164353218666 | 160564218666 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-13 | 2020-12-29 | 2021-01-26 | 2021-03-16 | 2021-08-16 | Overhead | R16 | 2021-03-16 | 12 | 21 | 36 | 110 | 176 | 2020 | 2021 | R16
167297212991 | 165453212991 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-17 | 2020-12-08 | 2020-12-08 | 2021-01-21 | 2021-11-05 | Underground | R16 | 2021-01-21 | 16 |  | 33 | 207 | 254 | 2020 | 2021 | R16
160075185364 | 165423185364 | NON-RESIDENTIAL - WAREHOUSE | UG R16 RESD AND NON RESD UD | Commercial | 2019-02-27 | 2019-03-05 | 2020-03-25 | 2020-06-18 | 2020-09-30 | Underground | R16 | 2020-06-18 | 5 | 277 | 62 | 75 | 416 | 2019 | 2020 | R16
160057149241 | 161001149241 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-01 | 2019-04-01 | 2019-04-15 |  | 2019-05-28 | Underground | R16 | 2019-04-25 | 1 | 11 | 9 | 24 | 42 | 2019 | 2019 | R16
167539272616 | 160417272616 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-25 | 2020-11-20 |  | 2022-03-15 | 2022-04-01 | Overhead | R16 | 2022-03-15 | 20 |  |  | 14 | 375 | 2020 | 2022 | R16
166882155985 | 169961155985 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-05-20 | 2019-05-20 | 2019-06-21 | 2020-10-07 | 2021-01-20 | Underground | R16 | 2020-10-07 | 1 | 25 | 339 | 76 | 438 | 2019 | 2021 | R16
160045151243 | 164065151243 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-17 | 2019-04-17 | 2019-05-03 |  | 2019-08-12 | Underground | R16 | 2019-06-14 | 1 | 13 | 31 | 42 | 84 | 2019 | 2019 | R16
169521216961 | 166195216961 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-12 | 2021-01-12 | 2021-01-12 | 2021-01-22 | 2021-06-02 | Overhead | R16 | 2021-01-22 | 1 |  | 9 | 94 | 102 | 2021 | 2021 | R16
169279222591 | 165488222591 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-21 | 2021-02-26 | 2021-03-05 | 2021-11-10 | 2021-12-29 | Overhead | R16 | 2021-11-10 | 5 | 6 | 179 | 36 | 223 | 2021 | 2021 | R16
163144186231 | 169538186231 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE FOR UPGRADE UD | Commercial | 2019-05-17 | 2019-07-19 | 2020-04-02 | 2020-10-08 | 2021-11-29 | Underground | R16 | 2020-10-08 | 46 | 185 | 136 | 298 | 662 | 2019 | 2021 | R16
162045154339 | 161918154339 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-06-03 | 2019-06-03 | 2019-06-05 | 2021-01-26 | 2022-08-01 | Underground | R16 | 2021-01-26 | 1 | 3 | 430 | 395 | 826 | 2019 | 2022 | R16
167300202390 | 167966202390 | RESIDENTIAL - SINGLE FAMILY ATTACHED | OH R16 RES NON RES OS | Residential | 2020-09-01 | 2020-09-01 | 2020-09-01 |  | 2021-10-25 | Overhead | R16 | 2021-08-24 | 1 |  | 256 | 45 | 300 | 2020 | 2021 | R16
161565220939 | 169905220939 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-26 | 2021-02-19 | 2021-02-19 | 2021-04-23 | 2021-11-11 | Overhead | R16 | 2021-04-23 | 19 |  | 46 | 145 | 208 | 2021 | 2021 | R16
167771218359 | 169461218359 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-25 | 2021-01-25 | 2021-01-26 |  | 2021-11-04 | Underground | R16 | 2021-06-02 | 1 | 2 | 92 | 112 | 204 | 2021 | 2021 | R16
160140150104 | 165140150104 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-23 | 2019-04-23 | 2019-04-23 |  | 2019-08-12 | Overhead | R16 | 2019-06-18 | 1 |  | 41 | 40 | 80 | 2019 | 2019 | R16
165532217684 | 162789217684 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-22 | 2020-12-22 | 2021-01-19 |  | 2021-11-08 | Overhead | R16 |  | 1 | 21 |  |  | 230 | 2020 | 2021 | R16
160143148204 | 161671148204 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-04-04 | 2019-04-04 | 2019-04-04 |  | 2019-05-28 | Underground | R16 | 2019-04-29 | 1 |  | 18 | 22 | 39 | 2019 | 2019 | R16
160147210007 | 161961210007 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-11-02 | 2020-11-06 | 2020-11-09 |  | 2021-07-12 | Underground | R16 |  | 5 | 2 |  |  | 181 | 2020 | 2021 | R16
160147272509 | 162682272509 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-03-01 | 2022-03-01 | 2022-03-14 |  | 2022-06-09 | Underground | R16 |  | 1 | 10 |  |  | 73 | 2022 | 2022 | R16
160147272510 | 162683272510 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-03-01 | 2022-03-01 | 2022-03-14 |  | 2022-06-09 | Underground | R16 |  | 1 | 10 |  |  | 73 | 2022 | 2022 | R16
163142225005 | 163845225005 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-27 | 2021-03-27 | 2021-03-27 | 2021-07-08 | 2021-07-09 | Overhead | R16 | 2021-07-08 | 0 |  | 74 | 2 | 75 | 2021 | 2021 | R16
160147288808 | 162381288808 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-08-08 | 2022-08-11 | 2022-08-12 |  | 2022-10-26 | Underground | R16 |  | 4 | 2 |  |  | 58 | 2022 | 2022 | R16
160226152295 | 167940152295 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-08 | 2019-05-08 | 2019-05-13 |  | 2020-06-09 | Overhead | R16 | 2020-01-22 | 1 | 4 | 183 | 100 | 285 | 2019 | 2020 | R16
165777150432 | 165778150432 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-27 | 2019-04-27 | 2019-04-27 |  | 2019-08-26 | Underground | R16 | 2019-06-25 | 0 |  | 42 | 45 | 86 | 2019 | 2019 | R16
169832202835 | 169081202835 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-09-04 | 2020-09-04 | 2020-09-04 | 2020-12-17 | 2021-02-26 | Overhead | R16 | 2020-12-17 | 1 |  | 75 | 52 | 126 | 2020 | 2021 | R16
165217211387 | 165262211387 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Commercial | 2020-10-01 | 2020-10-02 | 2020-11-19 | 2021-02-04 | 2021-10-06 | Underground | R16 | 2021-02-04 | 2 | 35 | 56 | 175 | 265 | 2020 | 2021 | R16
164785148636 | 169654148636 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-03-25 | 2019-03-27 | 2019-04-09 | 2020-06-29 | 2020-09-30 | Underground | R16 | 2020-06-29 | 3 | 10 | 320 | 68 | 398 | 2019 | 2020 | R16
165128224059 | 169829224059 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-03-10 | 2021-03-10 | 2021-03-19 |  | 2021-11-05 | Underground | R16 |  | 1 | 8 |  |  | 173 | 2021 | 2021 | R16
160307188947 | 160843188947 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-02 | 2020-01-02 | 2020-04-24 |  | 2020-10-06 | Underground | R16 | 2020-07-20 | 1 | 82 | 62 | 57 | 199 | 2020 | 2020 | R16
160308148981 | 163022148981 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-11 | 2019-04-11 | 2019-04-11 |  | 2019-06-03 | Underground | R16 | 2019-05-07 | 1 |  | 19 | 20 | 38 | 2019 | 2019 | R16
163221154111 | 167215154111 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-03 | 2019-05-03 | 2019-06-03 |  | 2019-08-26 | Underground | R16 | 2019-06-24 | 1 | 22 | 16 | 46 | 82 | 2019 | 2019 | R16
162789207646 | 162776207646 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-10 | 2020-08-10 | 2020-10-19 |  | 2021-04-13 | Underground | R16 | 2020-12-07 | 1 | 51 | 36 | 92 | 177 | 2020 | 2021 | R16
160356157520 | 168806157520 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-08 | 2019-07-08 | 2019-07-09 |  | 2021-07-07 | Underground | R16 | 2020-10-21 | 1 | 2 | 337 | 186 | 523 | 2019 | 2021 | R16
163076208471 | 160077208471 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-10-23 | 2020-10-27 | 2020-10-27 | 2021-02-26 | 2021-06-08 | Overhead | R16 | 2021-02-26 | 3 |  | 89 | 73 | 163 | 2020 | 2021 | R16
165319271952 | 166416271952 | NON-RESIDENTIAL - LODGING | R16 RESD AND NON RESD US | Commercial | 2020-11-21 | 2021-10-25 | 2022-03-08 |  | 2022-10-21 | Underground | R16 |  | 241 | 97 |  |  | 500 | 2020 | 2022 | R16
164533214426 | 161537214426 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-18 | 2020-12-18 | 2020-12-18 |  | 2021-08-03 | Overhead | R16 | 2021-03-29 | 1 |  | 72 | 92 | 163 | 2020 | 2021 | R16
160448151731 | 167923151731 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-05-08 | 2019-05-08 | 2019-05-08 |  | 2020-11-02 | Underground | R16 | 2020-09-04 | 1 |  | 348 | 42 | 389 | 2019 | 2020 | R16
160501150322 | 165567150322 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-25 | 2019-04-25 | 2019-04-25 |  | 2019-08-12 | Overhead | R16 | 2019-06-13 | 1 |  | 36 | 43 | 78 | 2019 | 2019 | R16
160503151732 | 167794151732 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-05-08 | 2019-05-08 | 2019-05-08 |  | 2020-10-06 | Underground | R16 | 2020-08-07 | 1 |  | 328 | 43 | 370 | 2019 | 2020 | R16
167138163149 | 168913163149 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-05-14 | 2019-05-14 | 2019-09-03 | 2020-11-16 | 2021-01-27 | Underground | R16 | 2020-11-16 | 1 | 81 | 315 | 53 | 447 | 2019 | 2021 | R16
164191232752 | 160418232752 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-28 | 2021-05-28 | 2021-05-28 | 2021-10-04 | 2021-11-09 | Underground | R16 | 2021-10-04 | 1 |  | 92 | 27 | 118 | 2021 | 2021 | R16
160510151861 | 167931151861 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-05-08 | 2019-05-08 | 2019-05-08 |  | 2022-06-01 | Underground | R16 | 2020-08-28 | 1 |  | 343 | 459 | 801 | 2019 | 2022 | R16
168423216020 | 164197216020 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-31 | 2020-12-31 | 2020-12-31 |  | 2021-11-04 | Overhead | R16 | 2021-06-03 | 1 |  | 111 | 111 | 221 | 2020 | 2021 | R16
160555151736 | 165201151736 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-24 | 2019-04-24 | 2019-05-08 |  | 2019-08-12 | Underground | R16 | 2019-06-11 | 1 | 11 | 25 | 45 | 79 | 2019 | 2019 | R16
162874203668 | 160403203668 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-11 | 2020-09-11 | 2020-09-11 | 2022-01-07 | 2022-02-07 | Overhead | R16 | 2022-01-07 | 1 |  | 346 | 22 | 367 | 2020 | 2022 | R16
160580153138 | 166428153138 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-01 | 2019-05-01 | 2019-05-23 |  | 2019-12-18 | Underground | R16 | 2019-12-09 | 1 | 17 | 143 | 8 | 166 | 2019 | 2019 | R16
168321141218 | 169052141218 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-01-25 | 2019-01-25 | 2019-01-25 | 2019-07-05 | 2019-09-12 | Underground | R16 | 2019-07-05 | 1 |  | 116 | 50 | 165 | 2019 | 2019 | R16
163132142458 | 161751142458 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-06 | 2019-02-06 | 2019-02-07 | 2019-03-15 | 2019-05-28 | Overhead | R16 | 2019-03-15 | 1 | 2 | 27 | 53 | 80 | 2019 | 2019 | R16
160650181304 | 167358181304 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-05-06 | 2019-05-06 | 2020-02-20 |  | 2021-08-10 | Overhead | R16 | 2021-03-26 | 1 | 209 | 287 | 98 | 592 | 2019 | 2021 | R16
168232219747 | 162531219747 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2021-02-05 | 2021-02-05 | 2021-02-05 |  | 2021-10-26 | Overhead | R16 | 2021-09-10 | 1 |  | 156 | 33 | 188 | 2021 | 2021 | R16
167956213197 | 167995213197 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-12-01 | 2020-12-01 | 2020-12-08 | 2022-10-06 | 2022-10-10 | Overhead | R16 | 2022-10-06 | 1 | 6 | 478 | 3 | 485 | 2020 | 2022 | R16
164714217976 | 167226217976 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-01-14 | 2021-01-22 | 2021-01-22 | 2022-11-03 | 2023-02-22 | Overhead | R16 | 2022-11-03 | 7 |  | 465 | 80 | 550 | 2021 | 2023 | R16
160691149871 | 163320149871 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-12 | 2019-04-12 | 2019-04-22 |  | 2019-05-28 | Underground | R16 | 2019-05-01 | 1 | 7 | 8 | 20 | 33 | 2019 | 2019 | R16
168294219941 | 162764219941 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2021-02-08 | 2021-02-08 | 2021-02-08 | 2021-03-01 | 2021-04-30 | Overhead | R16 | 2021-03-01 | 1 |  | 16 | 45 | 60 | 2021 | 2021 | R16
160700152332 | 167978152332 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-05-08 | 2019-05-10 | 2019-05-14 |  | 2019-09-18 | Underground | R16 | 2019-09-10 | 3 | 3 | 86 | 7 | 96 | 2019 | 2019 | R16
169244147388 | 169252147388 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-21 | 2019-03-21 | 2019-03-27 | 2019-11-03 | 2019-11-06 | Overhead | R16 | 2019-11-03 | 1 | 5 | 158 | 3 | 165 | 2019 | 2019 | R16
160705154645 | 164513154645 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-19 | 2019-04-19 | 2019-06-07 |  | 2019-08-26 | Underground | R16 | 2019-07-25 | 1 | 36 | 35 | 23 | 92 | 2019 | 2019 | R16
169899144858 | 166159144858 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-05 | 2019-03-05 | 2019-03-05 | 2019-03-07 | 2019-04-24 | Overhead | R16 | 2019-03-07 | 1 |  | 3 | 35 | 37 | 2019 | 2019 | R16
169275206354 | 166190206354 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-24 | 2020-08-24 | 2020-10-07 |  | 2021-04-14 | Underground | R16 | 2020-12-15 | 1 | 33 | 50 | 87 | 168 | 2020 | 2021 | R16
164973147451 | 160456147451 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-28 | 2019-03-28 | 2019-03-28 | 2019-04-10 | 2019-04-10 | Overhead | R16 | 2019-04-10 | 1 |  | 10 |  | 10 | 2019 | 2019 | R16
165577146623 | 167641146623 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-11 | 2019-03-11 | 2019-03-20 | 2019-10-16 | 2023-02-06 | Underground | R16 | 2019-10-16 | 1 | 8 | 151 | 864 | 1021 | 2019 | 2023 | R16
160749151794 | 166401151794 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-30 | 2019-04-30 | 2019-05-10 |  | 2019-08-28 | Overhead | R16 | 2019-08-22 | 1 | 9 | 75 | 5 | 87 | 2019 | 2019 | R16
160758153164 | 160229153164 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-22 | 2019-05-22 | 2019-05-22 |  | 2019-08-26 | Overhead | R16 | 2019-06-28 | 1 |  | 28 | 42 | 69 | 2019 | 2019 | R16
166668228694 | 161544228694 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-29 | 2021-04-29 | 2021-04-29 | 2021-05-03 | 2021-11-04 | Overhead | R16 | 2021-05-03 | 1 |  | 3 | 134 | 136 | 2021 | 2021 | R16
163671207115 | 166057207115 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-10-07 | 2020-10-14 | 2020-10-14 | 2021-02-24 | 2021-06-02 | Underground | R16 | 2021-02-24 | 6 |  | 96 | 71 | 171 | 2020 | 2021 | R16
160783149252 | 163656149252 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-04-16 | 2019-04-16 | 2019-04-16 |  | 2019-12-06 | Overhead | R16 | 2019-08-14 | 1 |  | 87 | 83 | 169 | 2019 | 2019 | R16
164884217724 | 165054217724 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-16 | 2020-11-16 | 2021-01-19 |  | 2021-11-05 | Underground | R16 | 2021-05-07 | 1 | 47 | 79 | 131 | 255 | 2020 | 2021 | R16
160786216340 | 161098216340 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 ELEC DEVELOPMENT | Residential Subdivision | 2020-12-16 | 2020-12-21 | 2021-01-05 |  | 2022-04-05 | Underground | R16 |  | 4 | 12 |  |  | 340 | 2020 | 2022 | R16
163040207503 | 168451207503 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-16 | 2020-10-16 | 2020-10-16 |  | 2021-04-20 | Overhead | R16 | 2021-01-11 | 1 |  | 62 | 72 | 133 | 2020 | 2021 | R16
169383216909 | 161483216909 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-12-18 | 2020-12-18 | 2021-01-12 |  | 2022-02-10 | Underground | R16 | 2022-01-06 | 1 | 18 | 258 | 26 | 300 | 2020 | 2022 | R16
160832150132 | 165226150132 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-24 | 2019-04-25 | 2019-04-25 |  | 2019-08-12 | Overhead | R16 | 2019-06-03 | 2 |  | 28 | 51 | 79 | 2019 | 2019 | R16
164114178802 | 161587178802 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-04-04 | 2019-04-04 | 2020-01-30 | 2020-07-07 | 2020-09-22 | Underground | R16 | 2020-07-07 | 1 | 216 | 114 | 56 | 384 | 2019 | 2020 | R16
167545214422 | 161455214422 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-18 | 2020-12-18 | 2020-12-18 |  | 2021-04-23 | Overhead | R16 | 2021-02-04 | 1 |  | 35 | 57 | 91 | 2020 | 2021 | R16
161040232366 | 169804232366 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-25 | 2021-05-26 | 2021-05-26 |  | 2022-10-17 | Overhead | R16 |  | 2 |  |  |  | 365 | 2021 | 2022 | R16
160871150106 | 165300150106 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-24 | 2019-04-24 | 2019-04-24 |  | 2019-08-26 | Underground | R16 | 2019-07-24 | 1 |  | 66 | 24 | 89 | 2019 | 2019 | R16
160874152188 | 165446152188 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-25 | 2019-04-25 | 2019-05-13 |  | 2019-11-27 | Underground | R16 | 2019-11-21 | 1 | 13 | 139 | 5 | 155 | 2019 | 2019 | R16
165960202120 | 167149202120 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-27 | 2020-08-27 | 2020-08-27 | 2021-05-07 | 2021-05-10 | Overhead | R16 | 2021-05-07 | 1 |  | 182 | 2 | 183 | 2020 | 2021 | R16
166938205834 | 162031205834 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-04 | 2020-08-04 | 2020-09-30 |  | 2021-08-17 | Underground | R16 | 2021-06-14 | 1 | 42 | 184 | 47 | 271 | 2020 | 2021 | R16
161772232124 | 169380232124 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-05-24 | 2021-05-24 | 2021-05-24 |  | 2021-10-25 | Underground | R16 | 2021-08-27 | 1 |  | 70 | 42 | 111 | 2021 | 2021 | R16
160985158678 | 164760158678 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE FOR UPGRADE UD | Commercial | 2019-04-22 | 2019-04-25 | 2019-07-24 |  | 2019-10-29 | Underground | R16 | 2019-10-01 | 4 | 65 | 50 | 21 | 137 | 2019 | 2019 | R16
161180174064 | 169283174064 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-03-21 | 2019-03-21 | 2019-12-10 |  | 2021-07-08 | Underground | R16 |  | 1 | 189 |  |  | 601 | 2019 | 2021 | R16
166890151848 | 167947151848 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-08 | 2019-05-08 | 2019-05-09 |  | 2019-08-26 | Overhead | R16 | 2019-07-05 | 1 | 2 | 42 | 37 | 79 | 2019 | 2019 | R16
160999150429 | 165855150429 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-27 | 2019-04-27 | 2019-04-27 |  | 2019-08-12 | Overhead | R16 | 2019-05-23 | 0 |  | 19 | 58 | 76 | 2019 | 2019 | R16
166454241803 | 160747241803 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-01-29 | 2021-02-09 | 2021-08-02 |  | 2022-03-31 | Underground | R16 |  | 8 | 125 |  |  | 305 | 2021 | 2022 | R16
165393229510 | 169974229510 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Commercial | 2021-04-23 | 2021-04-26 | 2021-05-05 | 2022-01-10 | 2022-02-08 | Overhead | R16 | 2022-01-10 | 2 | 8 | 179 | 22 | 208 | 2021 | 2022 | R16
169565203744 | 160404203744 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-09-11 | 2020-09-11 | 2020-09-11 |  | 2021-11-05 | Overhead | R16 | 2021-05-05 | 1 |  | 169 | 133 | 301 | 2020 | 2021 | R16
164190207516 | 168917207516 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-20 | 2020-10-20 | 2020-10-20 | 2021-01-22 | 2021-01-25 | Overhead | R16 | 2021-01-22 | 1 |  | 69 | 2 | 70 | 2020 | 2021 | R16
161079150209 | 165195150209 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-24 | 2019-04-24 | 2019-04-24 |  | 2019-08-12 | Overhead | R16 | 2019-06-03 | 1 |  | 29 | 51 | 79 | 2019 | 2019 | R16
167723152742 | 169456152742 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-16 | 2019-05-16 | 2019-05-16 |  | 2019-08-26 | Underground | R16 | 2019-07-11 | 1 |  | 41 | 33 | 73 | 2019 | 2019 | R16
164880224618 | 163149224618 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-25 | 2021-03-25 | 2021-03-25 | 2021-06-04 | 2021-08-30 | Overhead | R16 | 2021-06-04 | 1 |  | 52 | 62 | 113 | 2021 | 2021 | R16
168464203503 | 169135203503 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-08 | 2020-09-08 | 2020-09-10 |  | 2021-01-07 | Overhead | R16 | 2020-10-01 | 1 | 3 | 16 | 71 | 88 | 2020 | 2021 | R16
164462220811 | 165130220811 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-18 | 2021-02-18 | 2021-02-18 | 2021-03-29 | 2021-04-14 | Overhead | R16 | 2021-03-29 | 1 |  | 28 | 13 | 40 | 2021 | 2021 | R16
162954316552 | 167638316552 | SPECIFIC BUDGET PROJECTS | UG R16 RESD AND NON RESD UD | Commercial | 2021-04-13 | 2021-04-13 | 2023-04-21 | 2023-07-24 | 2023-08-31 | Underground | R16 | 2023-07-24 | 1 | 529 | 67 | 29 | 623 | 2021 | 2023 | R16
161178153706 | 164730153706 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-22 | 2019-05-29 | 2019-05-29 |  | 2023-06-08 | Overhead | R16 | 2019-07-10 | 28 |  | 31 | 1022 | 1079 | 2019 | 2023 | R16
161924223758 | 161985223758 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-02 | 2020-11-02 | 2021-03-16 |  | 2021-11-13 | Underground | R16 | 2021-04-08 | 1 | 97 | 18 | 157 | 270 | 2020 | 2021 | R16
161675158674 | 162993158674 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-10 | 2019-07-23 | 2019-07-23 | 2019-09-09 | 2019-09-26 | Overhead | R16 | 2019-09-09 | 32 |  | 35 | 14 | 79 | 2019 | 2019 | R16
168490218794 | 168308218794 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-03 | 2020-12-03 | 2021-01-28 | 2021-06-08 | 2021-06-08 | Underground | R16 | 2021-06-08 | 1 | 41 | 94 |  | 134 | 2020 | 2021 | R16
160467204538 | 162475204538 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-22 | 2020-09-22 | 2020-09-22 | 2020-09-30 | 2021-01-08 | Overhead | R16 | 2020-09-30 | 1 |  | 7 | 73 | 79 | 2020 | 2021 | R16
161227153980 | 161695153980 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-31 | 2019-05-31 | 2019-05-31 |  | 2019-08-26 | Overhead | R16 | 2019-06-27 | 1 |  | 20 | 43 | 62 | 2019 | 2019 | R16
161242157467 | 163431157467 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-11 | 2019-06-11 | 2019-07-09 |  | 2023-06-09 | Underground | R16 |  | 1 | 21 |  |  | 1044 | 2019 | 2023 | R16
166766216546 | 161447216546 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-17 | 2020-12-17 | 2021-01-07 |  | 2021-04-21 | Overhead | R16 | 2021-01-11 | 1 | 16 | 3 | 73 | 90 | 2020 | 2021 | R16
164312211123 | 165572211123 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-18 | 2020-11-18 | 2020-11-18 | 2021-11-15 | 2021-11-16 | Underground | R16 | 2021-11-15 | 1 |  | 259 | 2 | 260 | 2020 | 2021 | R16
165186211116 | 165648211116 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-18 | 2020-11-18 | 2020-11-18 |  | 2021-07-12 | Overhead | R16 | 2020-11-23 | 1 |  | 4 | 166 | 169 | 2020 | 2021 | R16
160786230666 | 165138230666 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-13 | 2021-05-13 | 2021-05-13 |  | 2022-06-22 | Overhead | R16 | 2022-06-22 | 1 |  | 290 |  | 290 | 2021 | 2022 | R16
162365230351 | 164538230351 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-05-17 | 2021-11-03 | Overhead | R16 | 2021-05-17 | 1 |  | 5 | 123 | 127 | 2021 | 2021 | R16
161604226400 | 166947226400 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-09 | 2021-04-09 | 2021-04-09 | 2021-04-21 | 2021-11-08 | Overhead | R16 | 2021-04-21 | 1 |  | 9 | 144 | 152 | 2021 | 2021 | R16
164358232694 | 160663232694 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-03-15 | 2021-03-15 | 2021-05-28 |  | 2021-09-14 | Overhead | R16 | 2021-07-23 | 1 | 55 | 41 | 38 | 132 | 2021 | 2021 | R16
161300271228 | 162927271228 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential Subdivision | 2022-03-02 | 2022-03-02 | 2022-03-02 |  | 2023-02-03 | Underground | R16 | 2022-11-14 | 1 |  | 184 | 60 | 243 | 2022 | 2023 | R16
161523213623 | 168741213623 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-07-17 | 2020-08-20 | 2020-12-10 | 2021-01-26 | 2021-04-20 | Underground | R16 | 2021-01-26 | 25 | 81 | 34 | 61 | 198 | 2020 | 2021 | R16
166397234027 | 160301234027 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2021-05-27 | 2021-06-04 | 2021-06-08 |  | 2022-03-03 | Underground | R16 |  | 7 | 3 |  |  | 201 | 2021 | 2022 | R16
161412151148 | 166669151148 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-01 | 2019-05-01 | 2019-05-03 |  | 2019-08-12 | Overhead | R16 | 2019-06-06 | 1 | 3 | 25 | 48 | 74 | 2019 | 2019 | R16
167296310300 | 167900310300 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-01-19 | 2022-12-06 | 2023-02-23 | 2023-10-27 | 2023-11-21 | Underground | R16 | 2023-10-27 | 491 | 58 | 177 | 18 | 741 | 2021 | 2023 | R16
160040203692 | 160537203692 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-14 | 2020-09-14 | 2020-09-14 |  | 2021-02-17 | Overhead | R16 | 2020-10-16 | 1 |  | 25 | 89 | 113 | 2020 | 2021 | R16
164306218087 | 161763218087 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-12-20 | 2020-12-20 | 2021-01-22 |  | 2022-08-29 | Underground | R16 |  | 0 | 25 |  |  | 441 | 2020 | 2022 | R16
169354206292 | 166075206292 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-06 | 2020-10-06 | 2020-10-06 |  | 2021-07-26 | Overhead | R16 | 2020-11-05 | 1 |  | 23 | 188 | 210 | 2020 | 2021 | R16
161446148914 | 162975148914 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-11 | 2019-04-11 | 2019-04-11 |  | 2019-08-12 | Underground | R16 | 2019-05-23 | 1 |  | 31 | 58 | 88 | 2019 | 2019 | R16
163680229123 | 162285229123 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-05-03 | 2021-05-03 | 2021-05-03 | 2021-09-23 | 2021-09-24 | Overhead | R16 | 2021-09-23 | 1 |  | 104 | 2 | 105 | 2021 | 2021 | R16
168547226116 | 166594226116 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-08 | 2021-04-08 | 2021-04-08 |  | 2021-08-23 | Overhead | R16 | 2021-07-13 | 1 |  | 69 | 30 | 98 | 2021 | 2021 | R16
162208150373 | 163911150373 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-04-16 | 2019-04-26 | 2019-04-26 |  | 2019-06-03 | Overhead | R16 | 2019-05-09 | 9 |  | 10 | 18 | 35 | 2019 | 2019 | R16
161070234287 | 162342234287 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-03 | 2021-06-09 | 2021-06-09 | 2021-09-03 | 2021-10-25 | Overhead | R16 | 2021-09-03 | 28 |  | 63 | 37 | 126 | 2021 | 2021 | R16
168430229481 | 162793229481 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-04 | 2021-05-04 | 2021-05-04 | 2021-05-17 | 2021-11-03 | Overhead | R16 | 2021-05-17 | 1 |  | 10 | 123 | 132 | 2021 | 2021 | R16
161579179255 | 163037179255 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-06-10 | 2019-08-09 | 2020-02-04 |  | 2020-06-09 | Overhead | R16 |  | 45 | 128 |  |  | 262 | 2019 | 2020 | R16
168065239780 | 160607239780 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2020-10-26 | 2020-10-26 | 2021-07-20 | 2021-08-09 | 2021-12-09 | Underground | R16 | 2021-08-09 | 1 | 192 | 15 | 89 | 294 | 2020 | 2021 | R16
166367218818 | 163515218818 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-25 | 2020-09-25 | 2021-01-29 |  | 2021-06-03 | Underground | R16 | 2021-03-09 | 1 | 91 | 28 | 63 | 180 | 2020 | 2021 | R16
161618150360 | 165504150360 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-25 | 2019-04-25 | 2019-04-25 |  | 2019-12-06 | Overhead | R16 | 2019-08-14 | 1 |  | 80 | 83 | 162 | 2019 | 2019 | R16
169286199549 | 161795199549 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-03 | 2020-08-04 | 2020-08-04 |  | 2020-12-14 | Overhead | R16 | 2020-09-08 | 2 |  | 26 | 70 | 96 | 2020 | 2020 | R16
164871224083 | 161233224083 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-17 | 2021-03-17 | 2021-03-17 | 2021-04-27 | 2021-05-03 | Underground | R16 | 2021-04-27 | 1 |  | 30 | 5 | 34 | 2021 | 2021 | R16
161572213548 | 169354213548 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-12-08 | 2020-12-10 | 2020-12-10 | 2021-02-02 | 2021-04-29 | Overhead | R16 | 2021-02-02 | 3 |  | 39 | 63 | 103 | 2020 | 2021 | R16
164421221595 | 166738221595 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-25 | 2021-02-25 | 2021-02-25 |  | 2021-11-13 | Overhead | R16 | 2021-04-19 | 1 |  | 38 | 150 | 187 | 2021 | 2021 | R16
168246262013 | 162518262013 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-05-03 | 2021-09-28 | 2021-12-20 |  | 2022-05-09 | Underground | R16 |  | 107 | 60 |  |  | 266 | 2021 | 2022 | R16
161663150704 | 165876150704 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-29 | 2019-04-29 | 2019-04-29 |  | 2019-08-12 | Overhead | R16 | 2019-06-19 | 1 |  | 38 | 39 | 76 | 2019 | 2019 | R16
162735227969 | 161404227969 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-12-17 | 2021-03-15 | 2021-04-22 | 2021-08-09 | 2021-12-09 | Underground | R16 | 2021-08-09 | 63 | 29 | 78 | 89 | 256 | 2020 | 2021 | R16
168208198063 | 169319198063 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-22 | 2020-07-22 | 2020-07-22 |  | 2021-07-07 | Overhead | R16 | 2020-07-21 | 1 |  |  | 252 | 251 | 2020 | 2021 | R16
164465228322 | 160425228322 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-26 | 2021-04-26 | 2021-04-26 |  | 2021-10-25 | Overhead | R16 | 2021-07-21 | 1 |  | 63 | 69 | 131 | 2021 | 2021 | R16
169723224486 | 162649224486 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-23 | 2021-03-23 | 2021-03-23 |  | 2022-02-02 | Overhead | R16 | 2022-01-12 | 1 |  | 212 | 16 | 227 | 2021 | 2022 | R16
162671220470 | 164168220470 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-12 | 2021-02-12 | 2021-02-12 |  | 2021-08-02 | Overhead | R16 | 2021-03-24 | 1 |  | 29 | 94 | 122 | 2021 | 2021 | R16
161702151455 | 167659151455 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-07 | 2019-05-07 | 2019-05-07 |  | 2019-08-12 | Overhead | R16 | 2019-06-05 | 1 |  | 22 | 49 | 70 | 2019 | 2019 | R16
167262207413 | 167228207413 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-13 | 2020-10-13 | 2020-10-15 |  | 2021-04-13 | Overhead | R16 | 2020-12-08 | 1 | 3 | 39 | 91 | 131 | 2020 | 2021 | R16
163161311007 | 166192311007 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-10-06 | 2020-10-06 | 2023-02-28 |  | 2023-06-26 | Overhead | R16 |  | 1 | 626 |  |  | 710 | 2020 | 2023 | R16
166646228589 | 161037228589 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-28 | 2021-04-28 | 2021-04-28 | 2021-04-30 | 2021-10-14 | Overhead | R16 | 2021-04-30 | 1 |  | 3 | 120 | 122 | 2021 | 2021 | R16
161749151506 | 167484151506 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-06 | 2019-05-06 | 2019-05-06 |  | 2019-11-14 | Overhead | R16 | 2019-06-04 | 1 |  | 22 | 118 | 139 | 2019 | 2019 | R16
162543206416 | 166445206416 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-07 | 2020-10-07 | 2020-10-07 |  | 2021-04-07 | Overhead | R16 | 2020-12-03 | 1 |  | 42 | 90 | 131 | 2020 | 2021 | R16
161787151153 | 166622151153 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-01 | 2019-05-01 | 2019-05-03 |  | 2019-08-12 | Underground | R16 | 2019-06-11 | 1 | 3 | 28 | 45 | 74 | 2019 | 2019 | R16
167878234534 | 161890234534 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-30 | 2021-04-30 | 2021-06-11 |  | 2023-02-03 | Underground | R16 | 2022-12-02 | 1 | 31 | 386 | 46 | 461 | 2021 | 2023 | R16
161807150773 | 166602150773 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-01 | 2019-05-01 | 2019-05-01 |  | 2019-08-12 | Underground | R16 | 2019-06-17 | 1 |  | 34 | 41 | 74 | 2019 | 2019 | R16
161483206254 | 162422206254 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-22 | 2020-09-22 | 2020-10-07 |  | 2021-06-30 | Underground | R16 | 2020-10-28 | 1 | 12 | 16 | 176 | 202 | 2020 | 2021 | R16
162423227902 | 167897227902 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-03-03 | 2021-03-03 | 2021-04-21 |  | 2021-11-05 | Underground | R16 | 2021-04-26 | 1 | 36 | 4 | 140 | 178 | 2021 | 2021 | R16
161935149453 | 164057149453 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-17 | 2019-04-17 | 2019-04-17 |  | 2019-08-26 | Underground | R16 | 2019-07-08 | 1 |  | 59 | 36 | 94 | 2019 | 2019 | R16
165949153927 | 168576153927 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-13 | 2019-05-13 | 2019-05-31 |  | 2019-08-26 | Underground | R16 | 2019-07-23 | 1 | 15 | 38 | 25 | 76 | 2019 | 2019 | R16
169273230705 | 165149230705 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-14 | 2021-05-14 | 2021-05-14 | 2022-01-12 | 2022-01-13 | Overhead | R16 | 2022-01-12 | 1 |  | 174 | 2 | 175 | 2021 | 2022 | R16
162506211208 | 165611211208 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-18 | 2020-11-18 | 2020-11-18 | 2021-10-18 | 2021-11-13 | Overhead | R16 | 2021-10-18 | 1 |  | 239 | 20 | 258 | 2020 | 2021 | R16
167375152177 | 166613152177 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-01 | 2019-05-01 | 2019-05-14 | 2019-08-22 | 2021-04-05 | Underground | R16 | 2019-08-22 | 1 | 10 | 73 | 423 | 504 | 2019 | 2021 | R16
163202206584 | 163250206584 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-11 | 2020-08-11 | 2020-10-08 |  | 2022-10-19 | Underground | R16 |  | 1 | 43 |  |  | 572 | 2020 | 2022 | R16
161970150768 | 166227150768 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-30 | 2019-04-30 | 2019-04-30 |  | 2019-08-12 | Overhead | R16 | 2019-06-05 | 1 |  | 27 | 49 | 75 | 2019 | 2019 | R16
165433145949 | 165441145949 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-27 | 2019-02-27 | 2019-03-13 | 2019-05-08 | 2019-07-31 | Underground | R16 | 2019-05-08 | 1 | 11 | 41 | 61 | 111 | 2019 | 2019 | R16
161975152996 | 167792152996 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-07 | 2019-05-07 | 2019-05-22 |  | 2019-08-12 | Underground | R16 | 2019-06-17 | 1 | 12 | 19 | 41 | 70 | 2019 | 2019 | R16
165836220449 | 163979220449 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-12 | 2021-02-12 | 2021-02-12 | 2021-03-11 | 2021-11-05 | Overhead | R16 | 2021-03-11 | 1 |  | 20 | 172 | 191 | 2021 | 2021 | R16
161990157104 | 160906157104 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-05-24 | 2019-06-19 | 2019-07-03 |  | 2019-12-19 | Overhead | R16 | 2019-08-15 | 19 | 11 | 32 | 91 | 150 | 2019 | 2019 | R16
169900149187 | 163483149187 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-15 | 2019-04-15 | 2019-04-15 | 2019-04-30 | 2019-05-06 | Overhead | R16 | 2019-04-30 | 1 |  | 12 | 5 | 16 | 2019 | 2019 | R16
162009157625 | 169518157625 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-11 | 2019-07-11 | 2019-07-11 |  | 2019-08-26 | Overhead | R16 | 2019-07-25 | 1 |  | 11 | 23 | 33 | 2019 | 2019 | R16
168314223375 | 160179223375 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-03-12 | 2021-03-12 | 2021-03-12 |  | 2021-11-05 | Overhead | R16 | 2021-04-14 | 1 |  | 24 | 148 | 171 | 2021 | 2021 | R16
166675226536 | 167701226536 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-13 | 2021-04-13 | 2021-04-13 | 2021-07-07 | 2021-10-25 | Overhead | R16 | 2021-07-07 | 1 |  | 62 | 79 | 140 | 2021 | 2021 | R16
163537223467 | 163590223467 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-28 | 2020-12-28 | 2021-03-12 |  | 2021-11-08 | Underground | R16 | 2021-05-25 | 1 | 55 | 53 | 120 | 226 | 2020 | 2021 | R16
162049177451 | 163989177451 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-04-17 | 2019-05-29 | 2020-01-22 |  | 2020-08-28 | Underground | R16 |  | 31 | 171 |  |  | 358 | 2019 | 2020 | R16
163758204326 | 168087204326 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-02 | 2020-09-02 | 2020-09-18 |  | 2022-09-11 | Underground | R16 | 2022-09-11 | 1 | 13 | 516 |  | 528 | 2020 | 2022 | R16
166579209455 | 167808209455 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-31 | 2020-08-31 | 2020-11-04 | 2021-02-04 | 2021-05-06 | Underground | R16 | 2021-02-04 | 1 | 48 | 67 | 66 | 179 | 2020 | 2021 | R16
162054157312 | 168819157312 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-08 | 2019-07-08 | 2019-07-08 |  | 2019-09-03 | Overhead | R16 | 2019-07-31 | 1 |  | 18 | 25 | 42 | 2019 | 2019 | R16
169945220871 | 165023220871 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-18 | 2021-02-18 | 2021-02-18 | 2021-03-23 | 2021-11-04 | Overhead | R16 | 2021-03-23 | 1 |  | 24 | 163 | 186 | 2021 | 2021 | R16
162283151823 | 168030151823 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-08 | 2019-05-08 | 2019-05-08 |  | 2019-08-12 | Overhead | R16 | 2019-06-17 | 1 |  | 29 | 41 | 69 | 2019 | 2019 | R16
162129207907 | 168223207907 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-15 | 2020-10-22 | 2020-10-22 |  | 2021-07-26 | Overhead | R16 | 2020-11-04 | 6 |  | 10 | 189 | 203 | 2020 | 2021 | R16
162343153426 | 160048153426 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-21 | 2019-05-21 | 2019-05-23 |  | 2019-08-26 | Underground | R16 | 2019-06-26 | 1 | 3 | 25 | 44 | 70 | 2019 | 2019 | R16
162348151630 | 167649151630 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-07 | 2019-05-07 | 2019-05-07 |  | 2019-08-12 | Overhead | R16 | 2019-05-23 | 1 |  | 13 | 58 | 70 | 2019 | 2019 | R16
161655229485 | 163439229485 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-08-12 | 2021-05-04 | 2021-05-05 | 2022-01-31 | 2022-02-23 | Underground | R16 | 2022-01-31 | 190 | 2 | 194 | 18 | 401 | 2020 | 2022 | R16
165503220701 | 162908220701 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-08 | 2021-02-16 | 2021-02-16 |  | 2021-08-03 | Overhead | R16 | 2021-03-15 | 7 |  | 20 | 102 | 127 | 2021 | 2021 | R16
164424222720 | 166302222720 | NON-RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Residential | 2020-08-24 | 2020-09-14 | 2021-03-05 | 2023-05-25 | 2023-08-17 | Underground | R16 | 2023-05-25 | 16 | 125 | 580 | 61 | 779 | 2020 | 2023 | R16
164356212192 | 167468212192 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-30 | 2020-11-30 | 2020-11-30 |  | 2021-11-05 | Overhead | R16 | 2021-04-08 | 1 |  | 94 | 152 | 245 | 2020 | 2021 | R16
162377153203 | 169003153203 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-14 | 2019-05-22 | 2019-05-22 |  | 2019-08-12 | Overhead | R16 | 2019-05-31 | 7 |  | 8 | 52 | 65 | 2019 | 2019 | R16
169549197717 | 168616197717 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-07-17 | 2020-07-17 | 2020-07-17 |  | 2020-10-06 | Overhead | R16 | 2020-08-05 | 1 |  | 14 | 45 | 58 | 2020 | 2020 | R16
162381150454 | 165684150454 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-27 | 2019-04-27 | 2019-04-27 |  | 2019-08-12 | Overhead | R16 | 2019-05-24 | 0 |  | 20 | 57 | 76 | 2019 | 2019 | R16
161951161832 | 162770161832 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-06-07 | 2019-08-21 | 2019-08-21 | 2020-05-13 | 2020-07-07 | Underground | R16 | 2020-05-13 | 54 |  | 191 | 40 | 283 | 2019 | 2020 | R16
162383153733 | 167865153733 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-08 | 2019-05-08 | 2019-05-30 |  | 2020-06-23 | Underground | R16 | 2020-04-15 | 1 | 17 | 230 | 50 | 295 | 2019 | 2020 | R16
162452150832 | 164093150832 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-17 | 2019-04-17 | 2019-04-30 |  | 2019-06-18 | Underground | R16 | 2019-06-10 | 1 | 10 | 30 | 7 | 45 | 2019 | 2019 | R16
162453149530 | 164202149530 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-18 | 2019-04-18 | 2019-04-18 |  | 2019-05-28 | Overhead | R16 | 2019-04-26 | 1 |  | 7 | 23 | 29 | 2019 | 2019 | R16
166000153110 | 160291153110 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-21 | 2019-05-21 | 2019-05-21 |  | 2023-06-08 | Overhead | R16 | 2019-07-23 | 1 |  | 46 | 1013 | 1058 | 2019 | 2023 | R16
166655147145 | 169489147145 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-22 | 2019-03-25 | 2019-03-25 | 2019-04-09 | 2019-04-09 | Overhead | R16 | 2019-04-09 | 2 |  | 12 |  | 13 | 2019 | 2019 | R16
160859210065 | 160662210065 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-09-14 | 2020-09-14 | 2020-11-09 |  | 2023-04-07 | Underground | R16 |  | 1 | 41 |  |  | 670 | 2020 | 2023 | R16
162489159620 | 162803159620 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-30 | 2019-07-30 | 2019-07-30 |  | 2019-09-03 | Overhead | R16 | 2019-08-01 | 1 |  | 3 | 24 | 26 | 2019 | 2019 | R16
162495154530 | 162561154530 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-06 | 2019-06-06 | 2019-06-06 |  | 2019-06-20 | Overhead | R16 | 2019-06-12 | 1 |  | 5 | 7 | 11 | 2019 | 2019 | R16
169795216289 | 165167216289 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-06 | 2021-01-06 | 2021-01-06 |  | 2021-04-29 | Overhead | R16 | 2021-02-11 | 1 |  | 27 | 56 | 82 | 2021 | 2021 | R16
163356147113 | 169902147113 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-25 | 2019-03-25 | 2019-03-25 | 2019-06-10 | 2019-08-12 | Overhead | R16 | 2019-06-10 | 1 |  | 56 | 46 | 101 | 2019 | 2019 | R16
162514150208 | 165197150208 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-24 | 2019-04-24 | 2019-04-24 |  | 2020-07-08 | Overhead | R16 | 2020-05-15 | 1 |  | 278 | 39 | 316 | 2019 | 2020 | R16
163497220517 | 164537220517 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-16 | 2021-02-17 | 2021-02-17 |  | 2021-11-05 | Overhead | R16 | 2021-05-10 | 2 |  | 59 | 130 | 189 | 2021 | 2021 | R16
162540151854 | 163401151854 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-15 | 2019-04-15 | 2019-05-09 |  | 2019-08-12 | Underground | R16 | 2019-06-17 | 1 | 19 | 28 | 41 | 86 | 2019 | 2019 | R16
168464216164 | 167334216164 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-11-25 | 2020-12-21 | 2021-01-05 |  | 2021-08-31 | Overhead | R16 |  | 19 | 12 |  |  | 200 | 2020 | 2021 | R16
165835229584 | 163044229584 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-05 | 2021-05-05 | 2021-05-05 | 2021-10-07 | 2021-11-10 | Overhead | R16 | 2021-10-07 | 1 |  | 112 | 25 | 136 | 2021 | 2021 | R16
162555153833 | 160241153833 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2019-05-21 | 2019-05-21 | 2019-05-31 |  | 2022-05-18 | Underground | R16 | 2019-07-26 | 1 | 9 | 41 | 734 | 782 | 2019 | 2022 | R16
168943229203 | 162322229203 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-03 | 2021-05-03 | 2021-05-03 |  | 2021-10-27 | Overhead | R16 | 2021-07-28 | 1 |  | 63 | 66 | 128 | 2021 | 2021 | R16
160670230790 | 165314230790 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-14 | 2021-05-14 | 2021-05-14 | 2021-08-16 | 2021-10-25 | Overhead | R16 | 2021-08-16 | 1 |  | 67 | 51 | 117 | 2021 | 2021 | R16
162133205719 | 162077205719 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-09-22 | 2020-09-22 | 2020-10-01 | 2021-09-07 | 2021-09-27 | Overhead | R16 | 2021-09-07 | 1 | 8 | 244 | 15 | 265 | 2020 | 2021 | R16
162604170434 | 167855170434 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-07-02 | 2019-09-03 | 2019-11-01 |  | 2021-07-13 | Underground | R16 |  | 46 | 44 |  |  | 531 | 2019 | 2021 | R16
164947152966 | 167742152966 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-05-07 | 2019-05-07 | 2019-05-20 | 2020-03-20 | 2020-06-09 | Underground | R16 | 2020-03-20 | 1 | 10 | 220 | 58 | 286 | 2019 | 2020 | R16
162658153234 | 160753153234 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-24 | 2019-05-24 | 2019-05-24 |  | 2020-06-09 | Overhead | R16 | 2020-03-16 | 1 |  | 212 | 62 | 273 | 2019 | 2020 | R16
163030237430 | 167039237430 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-12 | 2021-07-02 | 2021-07-02 | 2021-09-29 | 2023-04-13 | Overhead | R16 | 2021-09-29 | 60 |  | 64 | 402 | 524 | 2021 | 2023 | R16
166877220077 | 160578220077 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-14 | 2020-12-14 | 2021-02-11 |  | 2022-10-19 | Underground | R16 |  | 1 | 44 |  |  | 483 | 2020 | 2022 | R16
162726163399 | 169578163399 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-06 | 2019-09-06 | 2019-09-06 |  | 2019-10-08 | Overhead | R16 | 2019-09-24 | 1 |  | 13 | 11 | 23 | 2019 | 2019 | R16
168717220916 | 162477220916 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-05 | 2021-02-05 | 2021-02-19 |  | 2021-08-10 | Overhead | R16 | 2021-03-22 | 1 | 11 | 22 | 102 | 133 | 2021 | 2021 | R16
161165147645 | 160731147645 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-29 | 2019-03-29 | 2019-03-29 | 2019-08-26 | 2023-06-08 | Overhead | R16 | 2019-08-26 | 1 |  | 107 | 989 | 1095 | 2019 | 2023 | R16
166215216659 | 161906216659 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-21 | 2021-01-08 | 2021-01-08 | 2021-03-04 | 2021-06-03 | Overhead | R16 | 2021-03-04 | 15 |  | 40 | 66 | 119 | 2020 | 2021 | R16
165185230730 | 169718230730 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-21 | 2021-04-21 | 2021-05-13 | 2021-07-26 | 2021-08-23 | Underground | R16 | 2021-07-26 | 1 | 17 | 53 | 21 | 89 | 2021 | 2021 | R16
162752163110 | 166703163110 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-01 | 2019-05-01 | 2019-09-04 |  | 2019-10-11 | Underground | R16 | 2019-09-27 | 1 | 91 | 18 | 11 | 118 | 2019 | 2019 | R16
163084158666 | 160585158666 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-03-28 | 2019-03-28 | 2019-07-22 | 2019-09-21 | 2019-09-24 | Underground | R16 | 2019-09-21 | 1 | 83 | 45 | 2 | 129 | 2019 | 2019 | R16
162758158379 | 160959158379 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-19 | 2019-07-19 | 2019-07-19 |  | 2019-11-17 | Overhead | R16 | 2019-08-09 | 1 |  | 16 | 71 | 86 | 2019 | 2019 | R16
167870224344 | 168092224344 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2021-01-19 | 2021-02-17 | 2021-03-22 | 2021-07-03 | 2021-10-05 | Underground | R16 | 2021-07-03 | 22 | 24 | 75 | 67 | 186 | 2021 | 2021 | R16
162690206188 | 168224206188 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-02 | 2020-09-02 | 2020-10-06 |  | 2021-04-16 | Underground | R16 | 2021-01-08 | 1 | 25 | 69 | 71 | 163 | 2020 | 2021 | R16
163163142928 | 162695142928 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-11 | 2019-02-11 | 2019-02-11 | 2019-03-01 | 2019-03-04 | Underground | R16 | 2019-03-01 | 1 |  | 15 | 2 | 16 | 2019 | 2019 | R16
162828176643 | 162922176643 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-01-13 | 2020-01-13 | 2020-01-13 |  | 2021-12-08 | Overhead | R16 | 2021-11-12 | 1 |  | 480 | 19 | 498 | 2020 | 2021 | R16
162843159081 | 161541159081 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-05-30 | 2019-05-30 | 2019-07-25 |  | 2020-06-09 | Underground | R16 | 2019-12-18 | 1 | 41 | 105 | 125 | 269 | 2019 | 2020 | R16
161280236726 | 166300236726 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2021-02-24 | 2021-05-03 | 2021-06-25 | 2021-07-13 | 2021-08-25 | Underground | R16 | 2021-07-13 | 49 | 40 | 13 | 32 | 131 | 2021 | 2021 | R16
167948200421 | 163295200421 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-12 | 2020-08-12 | 2020-08-12 | 2020-08-31 | 2020-09-14 | Overhead | R16 | 2020-08-31 | 1 |  | 14 | 11 | 24 | 2020 | 2020 | R16
169951219961 | 160441219961 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-09-11 | 2020-09-11 | 2021-02-08 | 2021-03-09 | 2021-05-21 | Underground | R16 | 2021-03-09 | 1 | 107 | 22 | 54 | 181 | 2020 | 2021 | R16
165850146330 | 168688146330 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-18 | 2019-03-18 | 2019-03-18 | 2019-04-04 | 2019-04-05 | Overhead | R16 | 2019-04-04 | 1 |  | 14 | 2 | 15 | 2019 | 2019 | R16
169312207191 | 166015207191 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-06 | 2020-10-06 | 2020-10-14 | 2020-10-14 | 2021-07-07 | Underground | R16 | 2020-10-14 | 1 | 7 |  | 191 | 197 | 2020 | 2021 | R16
167559204820 | 169829204820 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-24 | 2020-07-24 | 2020-09-23 | 2020-11-02 | 2021-04-20 | Underground | R16 | 2020-11-02 | 1 | 44 | 29 | 122 | 193 | 2020 | 2021 | R16
162954149625 | 164109149625 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-18 | 2019-04-18 | 2019-04-18 |  | 2019-08-26 | Overhead | R16 | 2019-07-25 | 1 |  | 71 | 23 | 93 | 2019 | 2019 | R16
166029213545 | 163298213545 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-06 | 2020-12-10 | 2020-12-10 |  | 2021-11-08 | Underground | R16 | 2021-05-20 | 25 |  | 116 | 123 | 262 | 2020 | 2021 | R16
163011153558 | 166543153558 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2019-05-01 | 2019-05-28 | 2019-05-28 |  | 2023-06-07 | Underground | R16 | 2019-10-29 | 20 |  | 111 | 942 | 1071 | 2019 | 2023 | R16
167203258987 | 163129258987 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-09-24 | 2021-11-19 | 2021-11-29 |  | 2023-03-13 | Overhead | R16 | 2022-05-03 | 302 | 7 | 112 | 225 | 643 | 2020 | 2023 | R16
169067204892 | 162858204892 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-24 | 2020-09-24 | 2020-09-24 |  | 2021-07-26 | Overhead | R16 | 2020-11-02 | 1 |  | 28 | 191 | 218 | 2020 | 2021 | R16
163312206675 | 166593206675 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-08-26 | 2020-10-09 | 2020-10-09 |  | 2021-08-12 | Overhead | R16 | 2021-07-07 | 33 |  | 194 | 27 | 252 | 2020 | 2021 | R16
162529224070 | 160538224070 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2020-09-14 | 2021-02-05 | 2021-03-18 | 2022-04-18 | 2022-05-27 | Overhead | R16 | 2022-04-18 | 105 | 30 | 283 | 30 | 445 | 2020 | 2022 | R16
162229200429 | 163396200429 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-13 | 2020-08-13 | 2020-08-13 |  | 2020-12-14 | Underground | R16 | 2020-09-09 | 1 |  | 20 | 69 | 88 | 2020 | 2020 | R16
163467208616 | 169985208616 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-23 | 2020-10-28 | 2020-10-28 |  | 2021-07-28 | Overhead | R16 | 2021-01-19 | 4 |  | 60 | 137 | 199 | 2020 | 2021 | R16
163103151638 | 167879151638 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-08 | 2019-05-08 | 2019-05-08 |  | 2019-08-12 | Overhead | R16 | 2019-05-22 | 1 |  | 11 | 59 | 69 | 2019 | 2019 | R16
163134153408 | 166693153408 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-01 | 2019-05-01 | 2019-05-24 |  | 2019-08-12 | Underground | R16 | 2019-06-19 | 1 | 18 | 19 | 39 | 74 | 2019 | 2019 | R16
160693225775 | 167242225775 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-28 | 2021-03-31 | 2021-04-05 | 2021-05-17 | 2021-11-08 | Overhead | R16 | 2021-05-17 | 23 | 4 | 31 | 126 | 181 | 2021 | 2021 | R16
167279223816 | 160521223816 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-15 | 2021-03-15 | 2021-03-16 | 2021-04-30 | 2021-05-03 | Underground | R16 | 2021-04-30 | 1 | 2 | 34 | 2 | 36 | 2021 | 2021 | R16
163200151930 | 168155151930 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-09 | 2019-05-09 | 2019-05-09 |  | 2019-08-12 | Overhead | R16 | 2019-06-03 | 1 |  | 18 | 51 | 68 | 2019 | 2019 | R16
166860206340 | 165940206340 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-10-05 | 2020-10-06 | 2020-10-06 | 2022-04-01 | 2022-04-04 | Overhead | R16 | 2022-04-01 | 2 |  | 389 | 2 | 391 | 2020 | 2022 | R16
168548149264 | 168642149264 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2019-01-23 | 2019-02-22 | 2019-04-15 | 2019-05-18 | 2019-12-03 | Overhead | R16 | 2019-05-18 | 23 | 37 | 25 | 142 | 225 | 2019 | 2019 | R16
163235152556 | 168932152556 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-14 | 2019-05-15 | 2019-05-15 |  | 2020-06-09 | Overhead | R16 | 2020-03-19 | 2 |  | 222 | 59 | 281 | 2019 | 2020 | R16
163239149690 | 164292149690 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-18 | 2019-04-18 | 2019-04-19 |  | 2019-05-28 | Overhead | R16 | 2019-05-03 | 1 | 2 | 11 | 18 | 29 | 2019 | 2019 | R16
163055208765 | 165498208765 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-04 | 2020-10-04 | 2020-10-28 | 2021-08-01 | 2023-06-07 | Underground | R16 | 2021-08-01 | 0 | 18 | 198 | 483 | 698 | 2020 | 2023 | R16
167639214409 | 161486214409 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-18 | 2020-12-18 | 2020-12-18 | 2021-03-26 | 2021-03-26 | Overhead | R16 | 2021-03-26 | 1 |  | 71 |  | 71 | 2020 | 2021 | R16
167967203077 | 169405203077 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2020-09-09 | 2020-09-09 | 2020-09-09 | 2021-01-20 | 2021-01-21 | Overhead | R16 | 2021-01-20 | 1 |  | 96 | 2 | 97 | 2020 | 2021 | R16
169964208589 | 169141208589 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-20 | 2020-10-26 | 2020-10-27 |  | 2021-08-10 | Overhead | R16 | 2021-03-18 | 5 | 2 | 103 | 104 | 211 | 2020 | 2021 | R16
163960211398 | 165580211398 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-18 | 2020-11-20 | 2020-11-20 |  | 2021-04-16 | Underground | R16 | 2021-01-07 | 3 |  | 35 | 72 | 108 | 2020 | 2021 | R16
161384150846 | 166220150846 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2019-04-30 | 2019-04-30 | 2019-04-30 | 2019-12-27 | 2019-12-27 | Overhead | R16 | 2019-12-27 | 1 |  | 174 |  | 174 | 2019 | 2019 | R16
163301153536 | 161324153536 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-29 | 2019-05-29 | 2019-05-29 |  | 2019-08-26 | Underground | R16 | 2019-07-17 | 1 |  | 36 | 29 | 64 | 2019 | 2019 | R16
162722229109 | 161849229109 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-30 | 2021-05-03 | 2021-05-03 | 2021-08-05 | 2021-09-02 | Overhead | R16 | 2021-08-05 | 2 |  | 69 | 21 | 90 | 2021 | 2021 | R16
163303153366 | 169724153366 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-17 | 2019-05-21 | 2019-05-23 |  | 2020-06-09 | Underground | R16 | 2020-01-13 | 3 | 3 | 168 | 107 | 278 | 2019 | 2020 | R16
162907236383 | 167038236383 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-04-12 | 2021-06-23 | 2021-06-23 | 2021-07-26 | 2021-10-28 | Overhead | R16 | 2021-07-26 | 53 |  | 24 | 69 | 144 | 2021 | 2021 | R16
163958148845 | 162478148845 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-09 | 2019-04-10 | 2019-04-10 | 2019-09-25 | 2019-11-20 | Overhead | R16 | 2019-09-25 | 2 |  | 121 | 41 | 162 | 2019 | 2019 | R16
160929151341 | 167410151341 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-06 | 2019-05-06 | 2019-05-06 | 2019-06-04 | 2019-08-12 | Overhead | R16 | 2019-06-04 | 1 |  | 22 | 50 | 71 | 2019 | 2019 | R16
163100220512 | 162233220512 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-02-04 | 2021-02-05 | 2021-02-16 |  | 2021-08-06 | Underground | R16 |  | 2 | 8 |  |  | 132 | 2021 | 2021 | R16
167484202721 | 168540202721 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-09-03 | 2020-09-03 | 2020-09-03 |  | 2021-01-07 | Overhead | R16 | 2020-10-01 | 1 |  | 21 | 71 | 91 | 2020 | 2021 | R16
163544152176 | 168983152176 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-14 | 2019-05-14 | 2019-05-14 |  | 2019-07-10 | Underground | R16 | 2019-07-02 | 1 |  | 36 | 7 | 42 | 2019 | 2019 | R16
168595214306 | 168154214306 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-02 | 2020-12-18 | 2020-12-18 |  | 2021-12-02 | Overhead | R16 | 2021-11-04 | 13 |  | 230 | 21 | 262 | 2020 | 2021 | R16
168933200720 | 164001200720 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-14 | 2020-08-14 | 2020-08-14 | 2020-09-11 | 2020-12-18 | Overhead | R16 | 2020-09-11 | 1 |  | 21 | 71 | 91 | 2020 | 2020 | R16
165326210839 | 165492210839 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-17 | 2020-11-18 | 2020-11-18 | 2021-03-23 | 2021-08-09 | Overhead | R16 | 2021-03-23 | 2 |  | 90 | 100 | 190 | 2020 | 2021 | R16
165900231065 | 165783231065 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-17 | 2021-05-17 | 2021-05-17 |  | 2021-11-08 | Overhead | R16 | 2021-05-19 | 1 |  | 3 | 124 | 126 | 2021 | 2021 | R16
160853264669 | 160802264669 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2020-09-14 | 2020-09-14 | 2022-01-13 | 2022-10-19 | 2022-11-14 | Underground | R16 | 2022-10-19 | 1 | 349 | 200 | 19 | 566 | 2020 | 2022 | R16
163588153564 | 168987153564 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-14 | 2019-05-14 | 2019-05-28 |  | 2019-08-12 | Underground | R16 | 2019-06-21 | 1 | 11 | 19 | 37 | 65 | 2019 | 2019 | R16
163594149923 | 164554149923 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-19 | 2019-04-19 | 2019-04-22 |  | 2019-08-26 | Overhead | R16 | 2019-06-28 | 1 | 2 | 50 | 42 | 92 | 2019 | 2019 | R16
165602216166 | 164547216166 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-05 | 2021-01-05 | 2021-01-05 |  | 2021-06-02 | Overhead | R16 | 2021-03-02 | 1 |  | 41 | 67 | 107 | 2021 | 2021 | R16
166514235993 | 160934235993 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-27 | 2021-04-28 | 2021-06-22 |  | 2022-01-07 | Underground | R16 | 2021-11-18 | 2 | 40 | 108 | 37 | 184 | 2021 | 2022 | R16
160325150871 | 166340150871 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-30 | 2019-04-30 | 2019-04-30 | 2019-06-04 | 2023-06-08 | Overhead | R16 | 2019-06-04 | 1 |  | 26 | 1048 | 1073 | 2019 | 2023 | R16
163636151797 | 168323151797 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-10 | 2019-05-10 | 2019-05-10 |  | 2019-08-26 | Overhead | R16 | 2019-07-09 | 1 |  | 43 | 35 | 77 | 2019 | 2019 | R16
163232231219 | 163250231219 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2021-05-05 | 2021-05-05 | 2021-05-17 | 2021-08-19 | 2021-08-23 | Overhead | R16 | 2021-08-19 | 1 | 9 | 69 | 3 | 79 | 2021 | 2021 | R16
168993202220 | 167299202220 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-28 | 2020-08-28 | 2020-08-28 | 2020-10-14 | 2021-02-17 | Overhead | R16 | 2020-10-14 | 1 |  | 34 | 91 | 124 | 2020 | 2021 | R16
168624205802 | 164796205802 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-30 | 2020-09-30 | 2020-09-30 |  | 2021-07-26 | Overhead | R16 | 2020-11-02 | 1 |  | 24 | 191 | 214 | 2020 | 2021 | R16
162806221415 | 166014221415 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-23 | 2021-02-23 | 2021-02-23 | 2021-03-08 | 2021-06-03 | Overhead | R16 | 2021-03-08 | 1 |  | 10 | 64 | 73 | 2021 | 2021 | R16
163836226381 | 166951226381 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-09 | 2021-04-09 | 2021-04-09 |  | 2022-02-10 | Underground | R16 | 2022-01-05 | 1 |  | 194 | 27 | 220 | 2021 | 2022 | R16
163714149993 | 164807149993 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-23 | 2019-04-23 | 2019-04-23 |  | 2019-08-26 | Overhead | R16 | 2019-06-26 | 1 |  | 47 | 44 | 90 | 2019 | 2019 | R16
169832213020 | 168952213020 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-12-04 | 2020-12-04 | 2020-12-04 | 2020-12-17 | 2021-02-26 | Overhead | R16 | 2020-12-17 | 1 |  | 10 | 52 | 61 | 2020 | 2021 | R16
163740151034 | 166929151034 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-02 | 2019-05-02 | 2019-05-02 |  | 2019-08-12 | Overhead | R16 | 2019-06-05 | 1 |  | 25 | 49 | 73 | 2019 | 2019 | R16
168077230978 | 162298230978 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-03 | 2021-05-17 | 2021-05-17 | 2021-07-26 | 2021-08-23 | Overhead | R16 | 2021-07-26 | 11 |  | 51 | 21 | 81 | 2021 | 2021 | R16
169282145053 | 166512145053 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-05 | 2019-03-05 | 2019-03-05 | 2019-04-16 | 2019-04-17 | Overhead | R16 | 2019-04-16 | 1 |  | 31 | 2 | 32 | 2019 | 2019 | R16
165912142183 | 161080142183 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-04 | 2019-02-04 | 2019-02-04 | 2019-03-21 | 2019-03-22 | Overhead | R16 | 2019-03-21 | 1 |  | 34 | 2 | 35 | 2019 | 2019 | R16
161919212143 | 167209212143 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-25 | 2020-11-25 | 2020-11-25 |  | 2021-04-23 | Overhead | R16 | 2021-02-03 | 1 |  | 51 | 58 | 108 | 2020 | 2021 | R16
163236254452 | 162694254452 | NON-RESIDENTIAL - MISCELLANEOUS | UG ELEC MISC SVC US | Commercial | 2021-03-23 | 2021-03-25 | 2021-11-01 |  | 2021-12-17 | Underground | R16 |  | 3 | 158 |  |  | 194 | 2021 | 2021 | R16
163834150268 | 165473150268 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-25 | 2019-04-25 | 2019-04-25 |  | 2019-08-12 | Underground | R16 | 2019-05-24 | 1 |  | 22 | 57 | 78 | 2019 | 2019 | R16
165899245609 | 164194245609 | FOREIGN UTILITY | UG R16 RESD AND NON RESD UD | Commercial | 2020-09-28 | 2020-09-28 | 2021-08-27 | 2021-12-14 | 2022-01-11 | Underground | R16 | 2021-12-14 | 1 | 240 | 78 | 21 | 337 | 2020 | 2022 | R16
163885153493 | 161426153493 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-30 | 2019-05-30 | 2019-05-30 |  | 2019-07-11 | Underground | R16 | 2019-07-02 | 1 |  | 24 | 8 | 31 | 2019 | 2019 | R16
164801207669 | 167077207669 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-09 | 2020-10-19 | 2020-10-19 | 2020-11-19 | 2020-12-08 | Underground | R16 | 2020-11-19 | 7 |  | 24 | 14 | 43 | 2020 | 2020 | R16
163891153700 | 161170153700 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-28 | 2019-05-29 | 2019-05-29 |  | 2020-06-09 | Overhead | R16 | 2019-11-20 | 2 |  | 126 | 145 | 271 | 2019 | 2020 | R16
167022224193 | 160540224193 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-15 | 2021-03-22 | 2021-03-22 | 2021-06-03 | 2021-06-03 | Overhead | R16 | 2021-06-03 | 6 |  | 54 |  | 59 | 2021 | 2021 | R16
163915151116 | 167015151116 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-03 | 2019-05-03 | 2019-05-03 |  | 2019-11-14 | Overhead | R16 | 2019-06-26 | 1 |  | 39 | 102 | 140 | 2019 | 2019 | R16
163954153437 | 160843153437 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-24 | 2019-05-24 | 2019-05-24 |  | 2020-06-24 | Overhead | R16 | 2020-04-21 | 1 |  | 238 | 47 | 284 | 2019 | 2020 | R16
160077225189 | 164199225189 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-30 | 2021-03-30 | 2021-03-30 |  | 2021-08-23 | Overhead | R16 | 2021-07-14 | 1 |  | 77 | 29 | 105 | 2021 | 2021 | R16
164012153167 | 160364153167 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-22 | 2019-05-22 | 2019-05-22 |  | 2021-11-01 | Underground | R16 | 2021-09-28 | 1 |  | 615 | 25 | 639 | 2019 | 2021 | R16
164166207846 | 167849207846 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2020-10-14 | 2020-10-14 | 2020-10-21 | 2021-06-29 | 2022-02-01 | Overhead | R16 | 2021-06-29 | 1 | 6 | 180 | 156 | 340 | 2020 | 2022 | R16
160571232201 | 169341232201 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-24 | 2021-05-24 | 2021-05-24 | 2021-05-28 | 2023-06-08 | Overhead | R16 | 2021-05-28 | 1 |  | 5 | 530 | 534 | 2021 | 2023 | R16
164119223845 | 160334223845 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-27 | 2020-07-29 | 2021-03-16 |  | 2021-08-02 | Underground | R16 | 2021-03-31 | 3 | 165 | 12 | 89 | 266 | 2020 | 2021 | R16
160606205667 | 164429205667 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-29 | 2020-09-29 | 2020-09-29 | 2021-07-06 | 2021-07-07 | Overhead | R16 | 2021-07-06 | 1 |  | 201 | 2 | 202 | 2020 | 2021 | R16
164734221141 | 166947221141 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH CP R16 WORK RELO TO UG | Residential | 2020-10-09 | 2020-11-02 | 2021-02-19 | 2021-03-03 | 2021-04-06 | Overhead | R16 | 2021-03-03 | 17 | 80 | 9 | 25 | 128 | 2020 | 2021 | R16
164121192385 | 161614192385 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-07-23 | 2019-08-19 | 2020-05-27 |  | 2020-07-10 | Overhead | R16 |  | 20 | 203 |  |  | 254 | 2019 | 2020 | R16
164157152154 | 168401152154 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-10 | 2019-05-13 | 2019-05-14 |  | 2019-12-06 | Overhead | R16 | 2019-08-15 | 2 | 2 | 68 | 82 | 151 | 2019 | 2019 | R16
166448227733 | 169179227733 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-20 | 2021-04-20 | 2021-04-20 |  | 2021-08-23 | Overhead | R16 | 2021-07-14 | 1 |  | 62 | 29 | 90 | 2021 | 2021 | R16
164158156577 | 166047156577 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-30 | 2019-04-30 | 2019-06-28 |  | 2021-11-17 | Underground | R16 | 2019-08-08 | 1 | 44 | 30 | 595 | 667 | 2019 | 2021 | R16
163042208697 | 168105208697 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-10-15 | 2020-10-15 | 2020-10-27 |  | 2021-04-13 | Underground | R16 | 2020-12-08 | 1 | 9 | 31 | 91 | 129 | 2020 | 2021 | R16
165002228613 | 161451228613 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-10-30 | 2020-11-19 | 2021-04-28 |  | 2021-10-26 | Underground | R16 | 2021-09-10 | 15 | 115 | 98 | 33 | 258 | 2020 | 2021 | R16
161709147962 | 168154147962 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-03-14 | 2019-03-14 | 2019-04-02 | 2019-11-20 | 2019-11-19 | Underground | R16 | 2019-11-20 | 1 | 14 | 167 |  | 179 | 2019 | 2019 | R16
164232153403 | 160655153403 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-23 | 2019-05-23 | 2019-05-23 |  | 2023-06-08 | Overhead | R16 | 2019-06-27 | 1 |  | 26 | 1031 | 1056 | 2019 | 2023 | R16
166711233740 | 160397233740 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-26 | 2021-04-27 | 2021-06-05 | 2021-07-29 | 2021-07-30 | Underground | R16 | 2021-07-29 | 2 | 29 | 39 | 2 | 70 | 2021 | 2021 | R16
162500231515 | 165420231515 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH CP R16 WORK RELO TO UG | Residential | 2020-10-02 | 2020-12-16 | 2021-05-20 | 2022-01-13 | 2022-02-01 | Overhead | R16 | 2022-01-13 | 54 | 112 | 171 | 14 | 348 | 2020 | 2022 | R16
169297142271 | 161584142271 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-06 | 2019-02-06 | 2019-02-06 | 2019-03-07 | 2019-03-08 | Overhead | R16 | 2019-03-07 | 1 |  | 22 | 2 | 23 | 2019 | 2019 | R16
161551143045 | 162857143045 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-12 | 2019-02-12 | 2019-02-12 | 2019-03-25 | 2019-03-25 | Overhead | R16 | 2019-03-25 | 1 |  | 30 |  | 30 | 2019 | 2019 | R16
164331152183 | 168570152183 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-05-13 | 2019-05-13 | 2019-05-13 |  | 2022-06-01 | Underground | R16 | 2020-08-28 | 1 |  | 340 | 459 | 798 | 2019 | 2022 | R16
161079222850 | 162656222850 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-04 | 2020-11-04 | 2021-03-08 | 2021-03-31 | 2023-06-07 | Underground | R16 | 2021-03-31 | 1 | 89 | 18 | 571 | 676 | 2020 | 2023 | R16
168633158620 | 169542158620 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-17 | 2019-05-17 | 2019-07-22 | 2019-11-13 | 2019-11-14 | Underground | R16 | 2019-11-13 | 1 | 47 | 83 | 2 | 130 | 2019 | 2019 | R16
167002200485 | 167022200485 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2019-01-14 | 2019-01-14 | 2020-08-13 | 2020-11-12 | 2021-03-30 | Underground | R16 | 2020-11-12 | 1 | 414 | 66 | 99 | 577 | 2019 | 2021 | R16
164360175573 | 163365175573 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-01 | 2019-11-11 | 2020-01-03 |  | 2020-06-09 | Underground | R16 |  | 73 | 40 |  |  | 224 | 2019 | 2020 | R16
167957218792 | 169692218792 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-09 | 2020-12-09 | 2021-01-28 | 2021-03-25 | 2022-07-27 | Underground | R16 | 2021-03-25 | 1 | 37 | 41 | 350 | 426 | 2020 | 2022 | R16
164385231705 | 169206231705 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-07-21 | 2021-05-19 | 2021-05-20 |  | 2021-08-26 | Overhead | R16 | 2021-06-09 | 217 | 2 | 15 | 57 | 288 | 2020 | 2021 | R16
164428153562 | 161061153562 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-28 | 2019-05-28 | 2019-05-28 |  | 2019-08-26 | Overhead | R16 | 2019-06-25 | 1 |  | 21 | 45 | 65 | 2019 | 2019 | R16
166959210700 | 164649210700 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-13 | 2020-11-13 | 2020-11-13 | 2021-02-01 | 2021-04-23 | Overhead | R16 | 2021-02-01 | 1 |  | 57 | 60 | 116 | 2020 | 2021 | R16
161349219026 | 169145219026 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE FOR UPGRADE UD | Commercial | 2020-10-21 | 2020-11-07 | 2021-01-29 | 2021-08-05 | 2021-12-01 | Underground | R16 | 2021-08-05 | 13 | 60 | 135 | 85 | 291 | 2020 | 2021 | R16
164492151083 | 165036151083 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-23 | 2019-04-23 | 2019-05-02 |  | 2019-08-12 | Underground | R16 | 2019-06-20 | 1 | 8 | 36 | 38 | 80 | 2019 | 2019 | R16
164510246125 | 162502246125 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2021-08-31 | 2021-08-31 | 2021-09-01 |  | 2022-01-07 | Underground | R16 |  | 1 | 2 |  |  | 94 | 2021 | 2022 | R16
164066234859 | 165968234859 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-06 | 2021-06-14 | 2021-06-14 | 2021-08-31 | 2021-09-01 | Overhead | R16 | 2021-08-31 | 50 |  | 57 | 2 | 107 | 2021 | 2021 | R16
163220207943 | 169236207943 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-20 | 2020-10-22 | 2020-10-22 | 2020-10-28 | 2020-10-29 | Overhead | R16 | 2020-10-28 | 3 |  | 5 | 2 | 8 | 2020 | 2020 | R16
164511174147 | 168695174147 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential Subdivision | 2019-10-23 | 2019-10-23 | 2019-12-11 |  | 2020-12-14 | Underground | R16 |  | 1 | 36 |  |  | 299 | 2019 | 2020 | R16
162817203138 | 166210203138 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-24 | 2020-08-24 | 2020-09-09 | 2020-09-16 | 2020-12-18 | Underground | R16 | 2020-09-16 | 1 | 13 | 6 | 68 | 85 | 2020 | 2020 | R16
164520153788 | 160867153788 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-24 | 2019-05-24 | 2019-05-30 |  | 2019-10-28 | Overhead | R16 | 2019-10-16 | 1 | 5 | 100 | 9 | 112 | 2019 | 2019 | R16
166675230289 | 164403230289 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2021-05-11 | 2021-05-11 | 2021-05-11 |  | 2022-09-12 | Underground | R16 |  | 1 |  |  |  | 350 | 2021 | 2022 | R16
161345231686 | 160655231686 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-03-15 | 2021-03-15 | 2021-05-20 |  | 2022-09-26 | Underground | R16 | 2022-09-20 | 1 | 49 | 349 | 5 | 401 | 2021 | 2022 | R16
168276212355 | 163547212355 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-25 | 2020-09-25 | 2020-12-01 | 2021-01-29 | 2021-04-29 | Underground | R16 | 2021-01-29 | 1 | 48 | 44 | 65 | 155 | 2020 | 2021 | R16
160996207565 | 166526207565 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-25 | 2020-10-17 | 2020-10-17 | 2020-12-28 | 2021-07-28 | Overhead | R16 | 2020-12-28 | 39 |  | 51 | 153 | 242 | 2020 | 2021 | R16
164683160330 | 163871160330 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-13 | 2019-06-13 | 2019-08-06 |  | 2022-08-02 | Underground | R16 |  | 1 | 39 |  |  | 819 | 2019 | 2022 | R16
164811150267 | 165336150267 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-25 | 2019-04-25 | 2019-04-25 |  | 2019-12-06 | Underground | R16 | 2019-08-12 | 1 |  | 78 | 85 | 162 | 2019 | 2019 | R16
164814151525 | 164918151525 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-22 | 2019-05-06 | 2019-05-06 |  | 2019-06-06 | Overhead | R16 | 2019-05-31 | 11 |  | 20 | 5 | 34 | 2019 | 2019 | R16
167632206524 | 166481206524 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-07 | 2020-10-07 | 2020-10-07 |  | 2021-04-07 | Overhead | R16 | 2020-12-02 | 1 |  | 41 | 91 | 131 | 2020 | 2021 | R16
169861203064 | 165305203064 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-20 | 2020-08-25 | 2020-09-08 |  | 2021-07-26 | Underground | R16 | 2020-10-22 | 4 | 11 | 33 | 198 | 243 | 2020 | 2021 | R16
164866154577 | 162765154577 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-07 | 2019-06-07 | 2019-06-07 |  | 2019-08-26 | Overhead | R16 | 2019-06-25 | 1 |  | 13 | 45 | 57 | 2019 | 2019 | R16
164162148219 | 169094148219 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2019-03-20 | 2019-03-20 | 2019-04-05 | 2019-04-30 | 2019-10-26 | Underground | R16 | 2019-04-30 | 1 | 13 | 18 | 129 | 158 | 2019 | 2019 | R16
165131273298 | 160618273298 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-28 | 2021-05-28 | 2022-03-22 | 2023-01-06 | 2023-01-09 | Underground | R16 | 2023-01-06 | 1 | 213 | 209 | 2 | 422 | 2021 | 2023 | R16
167234225092 | 164122225092 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-29 | 2021-03-31 | 2021-03-31 | 2021-06-08 | 2021-06-09 | Overhead | R16 | 2021-06-08 | 3 |  | 50 | 2 | 53 | 2021 | 2021 | R16
164933153441 | 160261153441 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-05-21 | 2019-05-24 | 2019-05-24 |  | 2019-12-19 | Underground | R16 | 2019-08-15 | 4 |  | 60 | 91 | 153 | 2019 | 2019 | R16
164941161165 | 160656161165 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-05-23 | 2019-08-08 | 2019-08-13 |  | 2020-06-09 | Overhead | R16 | 2020-02-13 | 56 | 4 | 133 | 84 | 274 | 2019 | 2020 | R16
161615219096 | 169405219096 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-25 | 2021-01-31 | 2021-01-31 | 2021-05-12 | 2021-11-11 | Overhead | R16 | 2021-05-12 | 5 |  | 73 | 132 | 209 | 2021 | 2021 | R16
167236148460 | 162150148460 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-07 | 2019-04-07 | 2019-04-07 | 2019-04-19 | 2019-04-22 | Overhead | R16 | 2019-04-19 | 0 |  | 10 | 2 | 11 | 2019 | 2019 | R16
169614228738 | 161870228738 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-05-10 | 2021-08-11 | Overhead | R16 | 2021-05-10 | 1 |  | 7 | 68 | 74 | 2021 | 2021 | R16
161691203133 | 169574203133 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-09 | 2020-09-09 | 2020-09-09 |  | 2021-01-08 | Overhead | R16 | 2020-10-05 | 1 |  | 19 | 70 | 88 | 2020 | 2021 | R16
163043223134 | 167627223134 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-03-02 | 2021-03-02 | 2021-03-12 |  | 2023-08-02 | Overhead | R16 |  | 1 | 9 |  |  | 632 | 2021 | 2023 | R16
169813140002 | 166775140002 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-11 | 2019-01-11 | 2019-01-11 | 2019-02-27 | 2019-03-01 | Overhead | R16 | 2019-02-27 | 1 |  | 34 | 3 | 36 | 2019 | 2019 | R16
164065207462 | 168343207462 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2020-10-15 | 2020-10-15 | 2020-10-16 | 2021-03-02 | 2022-07-29 | Overhead | R16 | 2021-03-02 | 1 | 2 | 98 | 369 | 467 | 2020 | 2022 | R16
165028207475 | 168207207475 | STREET AND HIGHWAY RELOCATION | R16 ELECTRIC RELOCATION US | Commercial | 2020-10-15 | 2020-10-17 | 2020-10-17 |  | 2021-02-01 | Underground | R16 |  | 2 |  |  |  | 78 | 2020 | 2021 | R16
165028293772 | 161532293772 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2022-09-14 | 2022-09-14 | 2022-09-15 |  | 2022-10-25 | Underground | R16 | 2022-09-26 | 1 | 2 | 8 | 22 | 30 | 2022 | 2022 | R16
161293219352 | 161656219352 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-02 | 2021-02-02 | 2021-02-02 | 2021-05-17 | 2021-05-18 | Underground | R16 | 2021-05-17 | 1 |  | 75 | 2 | 76 | 2021 | 2021 | R16
165030154740 | 162814154740 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-07 | 2019-06-07 | 2019-06-07 |  | 2019-08-26 | Overhead | R16 | 2019-06-25 | 1 |  | 13 | 45 | 57 | 2019 | 2019 | R16
163403166973 | 163463166973 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-04-15 | 2019-04-15 | 2019-10-05 | 2020-05-08 | 2020-05-08 | Overhead | R16 | 2020-05-08 | 1 | 125 | 155 |  | 280 | 2019 | 2020 | R16
165040154172 | 166366154172 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-30 | 2019-04-30 | 2019-06-04 |  | 2019-07-18 | Underground | R16 | 2019-07-11 | 1 | 26 | 28 | 6 | 58 | 2019 | 2019 | R16
161544172955 | 162516172955 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-06-06 | 2019-08-12 | 2019-11-27 | 2020-08-21 | 2020-11-06 | Underground | R16 | 2020-08-21 | 48 | 78 | 193 | 56 | 372 | 2019 | 2020 | R16
164765224014 | 161400224014 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-17 | 2021-03-17 | 2021-03-17 |  | 2021-08-26 | Overhead | R16 | 2021-06-09 | 1 |  | 61 | 57 | 117 | 2021 | 2021 | R16
169047199642 | 161877199642 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-08-04 | 2020-08-04 | 2020-08-04 | 2022-07-06 | 2022-07-07 | Overhead | R16 | 2022-07-06 | 1 |  | 502 | 2 | 503 | 2020 | 2022 | R16
165085152479 | 169513152479 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-16 | 2019-05-16 | 2019-05-16 |  | 2019-08-26 | Overhead | R16 | 2019-07-17 | 1 |  | 45 | 29 | 73 | 2019 | 2019 | R16
160955212034 | 165834212034 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-19 | 2020-11-23 | 2020-11-25 |  | 2021-04-23 | Overhead | R16 | 2021-02-03 | 3 | 3 | 51 | 58 | 112 | 2020 | 2021 | R16
161158232373 | 162621232373 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-04 | 2021-05-04 | 2021-05-26 |  | 2021-11-09 | Underground | R16 | 2021-10-07 | 1 | 17 | 97 | 24 | 136 | 2021 | 2021 | R16
160307223948 | 161568223948 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-18 | 2021-03-18 | 2021-03-18 | 2021-04-19 | 2021-11-08 | Overhead | R16 | 2021-04-19 | 1 |  | 23 | 146 | 168 | 2021 | 2021 | R16
166399279024 | 166430279024 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH CP R16 WORK RELO TO UG | Residential | 2019-03-05 | 2019-04-30 | 2022-05-11 | 2023-03-20 | 2023-05-22 | Overhead | R16 | 2023-03-20 | 41 | 792 | 224 | 46 | 1100 | 2019 | 2023 | R16
161488214037 | 167505214037 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-10-13 | 2020-10-30 | 2020-12-15 |  | 2021-04-15 | Overhead | R16 |  | 14 | 33 |  |  | 133 | 2020 | 2021 | R16
165242157083 | 167771157083 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-07 | 2019-05-07 | 2019-07-03 |  | 2019-11-08 | Underground | R16 | 2019-10-29 | 1 | 42 | 85 | 9 | 134 | 2019 | 2019 | R16
165243154375 | 160193154375 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-21 | 2019-05-21 | 2019-06-05 |  | 2019-08-26 | Underground | R16 | 2019-07-11 | 1 | 12 | 27 | 33 | 70 | 2019 | 2019 | R16
168408213607 | 168503213607 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-16 | 2020-10-16 | 2020-12-11 |  | 2021-08-10 | Underground | R16 | 2021-03-23 | 1 | 41 | 73 | 101 | 213 | 2020 | 2021 | R16
165247153060 | 169903153060 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-20 | 2019-05-20 | 2019-05-20 |  | 2023-06-07 | Overhead | R16 | 2019-07-22 | 1 |  | 46 | 1013 | 1058 | 2019 | 2023 | R16
163084153427 | 160747153427 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-24 | 2019-05-24 | 2019-05-24 | 2019-06-18 | 2019-06-19 | Overhead | R16 | 2019-06-18 | 1 |  | 18 | 2 | 19 | 2019 | 2019 | R16
165262153294 | 160812153294 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-24 | 2019-05-24 | 2019-05-24 |  | 2019-08-26 | Overhead | R16 | 2019-07-25 | 1 |  | 45 | 23 | 67 | 2019 | 2019 | R16
164509168106 | 168297168106 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-05-10 | 2019-05-10 | 2019-10-14 | 2020-03-09 | 2021-04-05 | Underground | R16 | 2020-03-09 | 1 | 112 | 106 | 281 | 497 | 2019 | 2021 | R16
164006223347 | 160166223347 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-03-11 | 2021-03-11 | 2021-03-11 | 2021-05-13 | 2022-10-17 | Overhead | R16 | 2021-05-13 | 1 |  | 46 | 373 | 418 | 2021 | 2022 | R16
165278168069 | 164404168069 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2019-06-17 | 2019-06-17 | 2019-10-14 |  | 2020-06-09 | Underground | R16 |  | 1 | 86 |  |  | 257 | 2019 | 2020 | R16
164030214054 | 167581214054 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-30 | 2020-11-30 | 2020-12-15 |  | 2021-11-05 | Underground | R16 | 2021-05-03 | 1 | 12 | 100 | 135 | 245 | 2020 | 2021 | R16
165283159658 | 162995159658 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-31 | 2019-07-31 | 2019-07-31 |  | 2022-08-03 | Overhead | R16 |  | 1 |  |  |  | 786 | 2019 | 2022 | R16
165285174117 | 165592174117 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-12-02 | 2019-12-02 | 2019-12-12 |  | 2021-11-10 | Overhead | R16 |  | 1 | 9 |  |  | 508 | 2019 | 2021 | R16
169075212172 | 165651212172 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-18 | 2020-11-30 | 2020-11-30 | 2021-03-19 | 2021-11-11 | Overhead | R16 | 2021-03-19 | 9 |  | 80 | 170 | 257 | 2020 | 2021 | R16
160722214491 | 166697214491 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-24 | 2020-12-18 | 2020-12-18 | 2020-12-21 | 2021-04-22 | Overhead | R16 | 2020-12-21 | 19 |  | 2 | 89 | 108 | 2020 | 2021 | R16
163598207896 | 169780207896 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-22 | 2020-10-22 | 2020-10-22 | 2021-05-24 | 2021-11-04 | Overhead | R16 | 2021-05-24 | 1 |  | 153 | 119 | 271 | 2020 | 2021 | R16
165376159411 | 162395159411 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-29 | 2019-07-29 | 2019-07-29 |  | 2023-06-08 | Overhead | R16 | 2019-08-19 | 1 |  | 16 | 994 | 1009 | 2019 | 2023 | R16
162408209876 | 163400209876 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-06 | 2020-11-06 | 2020-11-06 |  | 2021-04-16 | Underground | R16 | 2021-01-07 | 1 |  | 45 | 72 | 116 | 2020 | 2021 | R16
162688210111 | 163737210111 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-10 | 2020-11-10 | 2020-11-10 | 2020-11-11 | 2021-04-14 | Overhead | R16 | 2020-11-11 | 1 |  | 2 | 111 | 112 | 2020 | 2021 | R16
166965231737 | 168788231737 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-20 | 2021-05-20 | 2021-05-20 | 2021-05-28 | 2021-08-23 | Overhead | R16 | 2021-05-28 | 1 |  | 7 | 62 | 68 | 2021 | 2021 | R16
165698198761 | 160445198761 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-28 | 2020-07-28 | 2020-07-28 | 2020-08-20 | 2020-10-06 | Overhead | R16 | 2020-08-20 | 1 |  | 18 | 34 | 51 | 2020 | 2020 | R16
165453153738 | 169455153738 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-16 | 2019-05-16 | 2019-05-30 |  | 2023-06-08 | Underground | R16 | 2020-02-19 | 1 | 11 | 190 | 862 | 1061 | 2019 | 2023 | R16
160484204932 | 163510204932 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-25 | 2020-09-25 | 2020-09-25 |  | 2021-07-01 | Overhead | R16 | 2020-10-28 | 1 |  | 24 | 177 | 200 | 2020 | 2021 | R16
160617227204 | 167176227204 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-04-12 | 2021-04-12 |  | 2021-04-16 | 2021-11-08 | Overhead | R16 | 2021-04-16 | 1 |  |  | 147 | 151 | 2021 | 2021 | R16
165494157029 | 168107157029 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-03 | 2019-07-03 | 2019-07-03 |  | 2019-08-26 | Overhead | R16 | 2019-07-22 | 1 |  | 14 | 26 | 39 | 2019 | 2019 | R16
161771222568 | 168414222568 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-04 | 2021-03-04 | 2021-03-04 | 2021-07-06 | 2021-07-07 | Overhead | R16 | 2021-07-06 | 1 |  | 89 | 2 | 90 | 2021 | 2021 | R16
163724234846 | 162007234846 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2021-03-22 | 2021-03-22 | 2021-06-14 |  | 2022-01-14 | Underground | R16 | 2021-12-09 | 1 | 61 | 129 | 27 | 215 | 2021 | 2022 | R16
165546155100 | 160293155100 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-22 | 2019-05-22 | 2019-06-11 |  | 2019-09-18 | Underground | R16 | 2019-08-03 | 1 | 15 | 39 | 33 | 86 | 2019 | 2019 | R16
165298207257 | 168603207257 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-09-03 | 2020-09-05 | 2020-10-14 | 2021-05-12 | 2021-06-14 | Underground | R16 | 2021-05-12 | 2 | 28 | 151 | 24 | 203 | 2020 | 2021 | R16
165568157193 | 168672157193 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-08 | 2019-07-08 | 2019-07-08 |  | 2021-04-20 | Overhead | R16 | 2021-01-14 | 1 |  | 399 | 69 | 467 | 2019 | 2021 | R16
165586178206 | 161019178206 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-05-28 | 2019-05-30 | 2020-01-27 |  | 2020-06-09 | Underground | R16 |  | 3 | 173 |  |  | 271 | 2019 | 2020 | R16
167759150272 | 168242150272 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-14 | 2019-03-14 | 2019-04-26 | 2019-07-15 | 2022-11-24 | Underground | R16 | 2019-07-15 | 1 | 32 | 57 | 879 | 966 | 2019 | 2022 | R16
162620238334 | 162731238334 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-04 | 2021-05-07 | 2021-07-09 |  | 2023-02-06 | Overhead | R16 | 2023-01-23 | 4 | 46 | 402 | 11 | 460 | 2021 | 2023 | R16
164202238065 | 161910238065 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-30 | 2021-07-07 | 2021-07-07 | 2022-07-17 | 2023-12-08 | Overhead | R16 | 2022-07-17 | 49 |  | 268 | 365 | 681 | 2021 | 2023 | R16
169263159012 | 169608159012 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-05-17 | 2019-05-30 | 2019-07-25 | 2020-12-28 | 2021-03-27 | Underground | R16 | 2020-12-28 | 10 | 41 | 373 | 65 | 486 | 2019 | 2021 | R16
161588226451 | 166746226451 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-09 | 2021-04-12 | 2021-04-12 | 2021-06-09 | 2021-08-17 | Overhead | R16 | 2021-06-09 | 2 |  | 43 | 50 | 93 | 2021 | 2021 | R16
162481225116 | 164226225116 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-04-01 | 2021-11-08 | Overhead | R16 | 2021-04-01 | 1 |  | 4 | 158 | 161 | 2021 | 2021 | R16
165677151468 | 167480151468 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-06 | 2019-05-06 | 2019-05-06 |  | 2019-08-26 | Underground | R16 | 2019-06-27 | 1 |  | 39 | 43 | 81 | 2019 | 2019 | R16
162121210692 | 162385210692 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-03 | 2020-11-03 | 2020-11-13 | 2021-01-19 | 2023-04-12 | Underground | R16 | 2021-01-19 | 1 | 9 | 48 | 582 | 637 | 2020 | 2023 | R16
165742154944 | 162971154944 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2019-06-10 | 2019-06-10 | 2019-06-10 |  | 2019-09-03 | Overhead | R16 | 2019-08-06 | 1 |  | 42 | 21 | 62 | 2019 | 2019 | R16
164667142535 | 164711142535 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-01-02 | 2019-01-02 | 2019-02-07 | 2019-04-15 | 2019-04-15 | Overhead | R16 | 2019-04-15 | 1 | 27 | 48 |  | 74 | 2019 | 2019 | R16
165749151774 | 166650151774 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-01 | 2019-05-01 | 2019-05-09 |  | 2019-08-26 | Underground | R16 | 2019-06-28 | 1 | 7 | 37 | 42 | 84 | 2019 | 2019 | R16
166330231848 | 160488231848 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-26 | 2021-05-03 | 2021-05-20 | 2021-11-16 | 2022-01-04 | Underground | R16 | 2021-11-16 | 6 | 14 | 129 | 36 | 182 | 2021 | 2022 | R16
160409140520 | 167337140520 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-01-15 | 2019-01-15 | 2019-01-16 | 2019-01-16 | 2019-03-11 | Overhead | R16 | 2019-01-16 | 1 | 2 |  | 39 | 40 | 2019 | 2019 | R16
165791157134 | 168393157134 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-06 | 2019-07-06 | 2019-07-06 |  | 2019-09-03 | Overhead | R16 | 2019-07-22 | 0 |  | 11 | 32 | 42 | 2019 | 2019 | R16
165965164950 | 163852164950 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-13 | 2019-06-13 | 2019-09-18 |  | 2022-08-02 | Underground | R16 |  | 1 | 70 |  |  | 819 | 2019 | 2022 | R16
165981161654 | 161330161654 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-07-22 | 2019-07-22 | 2019-08-21 |  | 2021-02-17 | Underground | R16 | 2020-09-29 | 1 | 23 | 290 | 102 | 413 | 2019 | 2021 | R16
160796238023 | 168883238023 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-04-19 | 2021-04-19 | 2021-07-07 |  | 2022-05-05 | Underground | R16 |  | 1 | 58 |  |  | 274 | 2021 | 2022 | R16
160174224962 | 161413224962 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-17 | 2021-03-25 | 2021-03-26 |  | 2021-11-05 | Overhead | R16 | 2021-04-15 | 7 | 2 | 15 | 147 | 168 | 2021 | 2021 | R16
169219231323 | 167473231323 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-18 | 2021-05-18 | 2021-05-18 | 2021-07-20 | 2021-07-22 | Overhead | R16 | 2021-07-20 | 1 |  | 46 | 3 | 48 | 2021 | 2021 | R16
166006152588 | 169139152588 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-16 | 2019-05-16 | 2019-05-16 |  | 2019-08-12 | Underground | R16 | 2019-06-18 | 1 |  | 24 | 40 | 63 | 2019 | 2019 | R16
162722223154 | 169784223154 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-10 | 2021-03-10 | 2021-03-10 |  | 2021-11-08 | Overhead | R16 | 2021-04-20 | 1 |  | 30 | 145 | 174 | 2021 | 2021 | R16
166011150806 | 166358150806 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-01 | 2019-05-01 | 2019-05-01 |  | 2019-08-12 | Overhead | R16 | 2019-05-24 | 1 |  | 18 | 57 | 74 | 2019 | 2019 | R16
166041217587 | 165738217587 | NON-RESIDENTIAL - MISCELLANEOUS | UG ELEC MISC SVC US | Commercial | 2021-01-08 | 2021-01-08 | 2021-01-19 |  | 2021-10-26 | Underground | R16 |  | 1 | 8 |  |  | 208 | 2021 | 2021 | R16
166041222186 | 165804222186 | NON-RESIDENTIAL - MISCELLANEOUS | UG ELEC MISC SVC US | Commercial | 2021-01-08 | 2021-02-22 | 2021-03-02 |  | 2021-11-04 | Underground | R16 |  | 32 | 7 |  |  | 215 | 2021 | 2021 | R16
164955194847 | 160112194847 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG R16 RESD AND NON RESD UD | Commercial | 2019-05-21 | 2019-07-08 | 2020-06-19 | 2020-09-16 | 2020-12-02 | Underground | R16 | 2020-09-16 | 35 | 250 | 64 | 56 | 402 | 2019 | 2020 | R16
161849205776 | 162258205776 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-09-21 | 2020-09-21 | 2020-09-30 |  | 2022-03-08 | Underground | R16 | 2022-01-19 | 1 | 8 | 341 | 35 | 382 | 2020 | 2022 | R16
160558231078 | 165781231078 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-05 | 2021-05-18 | 2021-05-18 | 2021-06-21 | 2021-08-13 | Overhead | R16 | 2021-06-21 | 32 |  | 25 | 40 | 95 | 2021 | 2021 | R16
166727221212 | 162823221212 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-08 | 2021-02-10 | 2021-02-22 |  | 2021-11-02 | Underground | R16 | 2021-06-25 | 3 | 9 | 90 | 93 | 192 | 2021 | 2021 | R16
166051153219 | 160592153219 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-23 | 2019-05-23 | 2019-05-23 |  | 2019-08-26 | Overhead | R16 | 2019-06-27 | 1 |  | 26 | 43 | 68 | 2019 | 2019 | R16
166059191905 | 168388191905 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-05-21 | 2020-05-21 | 2020-05-21 |  | 2021-07-01 | Overhead | R16 | 2020-06-18 | 1 |  | 21 | 271 | 291 | 2020 | 2021 | R16
166015234200 | 160660234200 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-04-26 | 2021-06-08 | 2021-06-08 | 2021-06-12 | 2021-09-28 | Overhead | R16 | 2021-06-12 | 32 |  | 4 | 77 | 112 | 2021 | 2021 | R16
169530201599 | 166359201599 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-08-24 | 2020-08-24 | 2020-08-25 |  | 2021-04-15 | Underground | R16 |  | 1 | 2 |  |  | 169 | 2020 | 2021 | R16
160348147346 | 160083147346 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-27 | 2019-03-27 | 2019-03-27 | 2019-07-26 | 2019-07-26 | Overhead | R16 | 2019-07-26 | 1 |  | 88 |  | 88 | 2019 | 2019 | R16
163953141360 | 169058141360 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-25 | 2019-01-25 | 2019-01-25 | 2019-02-01 | 2019-08-12 | Overhead | R16 | 2019-02-01 | 1 |  | 6 | 137 | 142 | 2019 | 2019 | R16
167432226081 | 165752226081 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-04-05 | 2021-04-05 | 2021-04-07 |  | 2021-08-11 | Underground | R16 | 2021-07-01 | 1 | 3 | 62 | 30 | 93 | 2021 | 2021 | R16
164471236683 | 160985236683 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-06-01 | 2021-06-25 | 2021-06-25 | 2022-05-17 | 2022-05-25 | Underground | R16 | 2022-05-17 | 19 |  | 233 | 7 | 257 | 2021 | 2022 | R16
161129213609 | 168214213609 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-02 | 2020-12-11 | 2020-12-11 | 2021-05-04 | 2021-05-05 | Overhead | R16 | 2021-05-04 | 8 |  | 103 | 2 | 111 | 2020 | 2021 | R16
166323150872 | 166360150872 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-04-30 | 2019-04-30 | 2019-04-30 |  | 2020-05-06 | Underground | R16 | 2020-05-06 | 1 |  | 267 |  | 267 | 2019 | 2020 | R16
166376157169 | 168316157169 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-08 | 2019-07-08 | 2019-07-08 |  | 2019-08-26 | Overhead | R16 | 2019-07-22 | 1 |  | 11 | 26 | 36 | 2019 | 2019 | R16
167537201544 | 163254201544 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-11 | 2020-08-11 | 2020-08-24 |  | 2020-12-18 | Underground | R16 | 2020-09-21 | 1 | 10 | 21 | 65 | 94 | 2020 | 2020 | R16
162651229544 | 162881229544 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-04 | 2021-05-04 | 2021-05-04 |  | 2021-09-10 | Overhead | R16 | 2021-08-16 | 1 |  | 75 | 20 | 94 | 2021 | 2021 | R16
164801148762 | 162572148762 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-04-09 | 2019-04-09 | 2019-04-09 | 2019-10-21 | 2019-10-22 | Overhead | R16 | 2019-10-21 | 1 |  | 140 | 2 | 141 | 2019 | 2019 | R16
166546164014 | 164521164014 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-06-17 | 2019-06-17 | 2019-09-11 |  | 2019-11-21 | Underground | R16 |  | 1 | 63 |  |  | 114 | 2019 | 2019 | R16
162803213106 | 169214213106 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-07 | 2020-12-07 | 2020-12-07 | 2021-02-01 | 2021-02-02 | Overhead | R16 | 2021-02-01 | 1 |  | 41 | 2 | 42 | 2020 | 2021 | R16
167095200060 | 162653200060 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-07 | 2020-08-07 | 2020-08-07 | 2020-11-16 | 2021-04-20 | Overhead | R16 | 2020-11-16 | 1 |  | 72 | 112 | 183 | 2020 | 2021 | R16
164195226733 | 169580226733 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-09 | 2021-04-14 | 2021-04-14 |  | 2021-11-08 | Overhead | R16 | 2021-05-13 | 27 |  | 22 | 128 | 175 | 2021 | 2021 | R16
165027197928 | 169285197928 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-21 | 2020-07-21 | 2020-07-21 | 2020-08-17 | 2020-12-18 | Overhead | R16 | 2020-08-17 | 1 |  | 20 | 90 | 109 | 2020 | 2020 | R16
166562156932 | 162742156932 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-07 | 2019-06-07 | 2019-07-01 |  | 2019-08-26 | Underground | R16 | 2019-07-18 | 1 | 17 | 14 | 28 | 57 | 2019 | 2019 | R16
161903242410 | 165831242410 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-05-17 | 2021-05-24 | 2021-08-06 | 2022-01-06 | 2022-01-24 | Overhead | R16 | 2022-01-06 | 6 | 55 | 110 | 13 | 181 | 2021 | 2022 | R16
167076210704 | 164776210704 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-13 | 2020-11-13 | 2020-11-13 |  | 2021-04-15 | Overhead | R16 | 2020-12-23 | 1 |  | 29 | 82 | 110 | 2020 | 2021 | R16
166632156645 | 163463156645 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-12 | 2019-06-12 | 2019-06-28 |  | 2019-12-04 | Underground | R16 | 2019-11-25 | 1 | 13 | 107 | 8 | 126 | 2019 | 2019 | R16
168809224749 | 165823224749 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-22 | 2021-03-26 | 2021-03-26 | 2021-05-17 | 2021-11-08 | Overhead | R16 | 2021-05-17 | 25 |  | 37 | 126 | 186 | 2021 | 2021 | R16
166665154569 | 162537154569 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-07 | 2019-06-07 | 2019-06-07 |  | 2021-11-17 | Overhead | R16 | 2019-08-01 | 1 |  | 40 | 600 | 639 | 2019 | 2021 | R16
162637141077 | 168716141077 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-24 | 2019-01-24 | 2019-01-24 | 2019-02-11 | 2019-04-26 | Overhead | R16 | 2019-02-11 | 1 |  | 13 | 55 | 67 | 2019 | 2019 | R16
169873212605 | 168228212605 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-03 | 2020-12-03 | 2020-12-03 | 2020-12-31 | 2021-06-03 | Underground | R16 | 2020-12-31 | 1 |  | 21 | 111 | 131 | 2020 | 2021 | R16
165215204847 | 162238204847 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-21 | 2020-09-21 | 2020-09-24 | 2020-10-28 | 2021-07-26 | Underground | R16 | 2020-10-28 | 1 | 4 | 25 | 194 | 221 | 2020 | 2021 | R16
166704254938 | 164335254938 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2021-10-22 | 2021-11-02 | 2021-11-04 |  | 2022-01-14 | Overhead | R16 |  | 8 | 3 |  |  | 61 | 2021 | 2022 | R16
160003224939 | 163686224939 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-26 | 2021-03-26 | 2021-03-26 |  | 2021-11-03 | Overhead | R16 | 2021-06-24 | 1 |  | 65 | 95 | 159 | 2021 | 2021 | R16
166704255154 | 164481255154 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2021-10-22 | 2021-11-03 | 2021-11-05 |  | 2022-02-01 | Overhead | R16 |  | 9 | 3 |  |  | 73 | 2021 | 2022 | R16
161717154444 | 162324154444 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-05 | 2019-06-05 | 2019-06-05 |  | 2020-07-08 | Overhead | R16 | 2020-05-26 | 1 |  | 255 | 32 | 286 | 2019 | 2020 | R16
166714165136 | 163546165136 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-12 | 2019-06-27 | 2019-09-19 |  | 2020-06-09 | Underground | R16 | 2020-02-20 | 12 | 61 | 111 | 79 | 260 | 2019 | 2020 | R16
166716156020 | 165483156020 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-06-21 | 2019-06-21 | 2019-06-21 |  | 2019-08-28 | Overhead | R16 | 2019-08-20 | 1 |  | 43 | 7 | 49 | 2019 | 2019 | R16
162453207474 | 164115207474 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-28 | 2020-10-01 | 2020-10-17 |  | 2021-11-05 | Overhead | R16 | 2021-04-08 | 4 | 12 | 124 | 152 | 290 | 2020 | 2021 | R16
168668242245 | 166184242245 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-11-20 | 2021-03-25 | 2021-08-05 | 2022-05-20 | 2022-06-08 | Underground | R16 | 2022-05-20 | 90 | 96 | 207 | 14 | 404 | 2020 | 2022 | R16
166797156992 | 167875156992 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-02 | 2019-07-02 | 2019-07-02 |  | 2019-08-26 | Overhead | R16 | 2019-07-11 | 1 |  | 8 | 33 | 40 | 2019 | 2019 | R16
166850158615 | 161530158615 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-23 | 2019-07-23 | 2019-07-23 |  | 2019-10-09 | Overhead | R16 | 2019-08-21 | 1 |  | 22 | 36 | 57 | 2019 | 2019 | R16
167103139323 | 165422139323 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-05 | 2019-01-05 | 2019-01-05 | 2019-03-13 | 2019-03-14 | Overhead | R16 | 2019-03-13 | 0 |  | 48 | 2 | 49 | 2019 | 2019 | R16
166855158300 | 167351158300 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-06 | 2019-05-06 | 2019-07-17 |  | 2020-07-08 | Underground | R16 | 2020-04-20 | 1 | 53 | 199 | 58 | 308 | 2019 | 2020 | R16
161057153406 | 165821153406 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-04-26 | 2019-05-05 | 2019-05-23 | 2019-12-20 | 2020-02-06 | Underground | R16 | 2019-12-20 | 6 | 14 | 152 | 35 | 205 | 2019 | 2020 | R16
163858210795 | 165160210795 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-16 | 2020-11-16 | 2020-11-16 | 2021-02-23 | 2023-06-09 | Overhead | R16 | 2021-02-23 | 1 |  | 72 | 599 | 670 | 2020 | 2023 | R16
166867154529 | 169914154529 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-20 | 2019-05-20 | 2019-06-06 |  | 2019-12-06 | Underground | R16 | 2019-08-07 | 1 | 14 | 45 | 88 | 145 | 2019 | 2019 | R16
169874228572 | 160537228572 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-26 | 2021-04-27 | 2021-04-27 |  | 2021-11-08 | Overhead | R16 | 2021-05-12 | 2 |  | 12 | 129 | 141 | 2021 | 2021 | R16
162844211460 | 166034211460 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-20 | 2020-11-20 | 2020-11-20 |  | 2021-05-06 | Overhead | R16 | 2021-02-24 | 1 |  | 69 | 52 | 120 | 2020 | 2021 | R16
166873158776 | 168994158776 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-09 | 2019-07-09 | 2019-07-25 |  | 2019-10-16 | Overhead | R16 |  | 1 | 13 |  |  | 72 | 2019 | 2019 | R16
166879151980 | 168163151980 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-09 | 2019-05-09 | 2019-05-09 |  | 2019-08-12 | Overhead | R16 | 2019-06-04 | 1 |  | 19 | 50 | 68 | 2019 | 2019 | R16
163317230301 | 169599230301 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-04-22 | 2021-05-11 | 2022-12-02 |  | 2023-06-07 | Overhead | R16 |  | 14 | 409 |  |  | 555 | 2021 | 2023 | R16
166885155420 | 163869155420 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-06-14 | 2019-06-14 | 2019-06-14 |  | 2019-08-28 | Overhead | R16 | 2019-08-21 | 1 |  | 49 | 6 | 54 | 2019 | 2019 | R16
167876235510 | 169102235510 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-20 | 2021-04-20 | 2021-06-18 |  | 2022-03-08 | Underground | R16 | 2021-01-18 | 1 | 44 |  | 297 | 231 | 2021 | 2022 | R16
166888210431 | 165580210431 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-06-21 | 2020-05-19 | 2020-11-12 |  | 2021-05-07 | Overhead | R16 |  | 238 | 128 |  |  | 491 | 2019 | 2021 | R16
166215204269 | 161720204269 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-17 | 2020-09-17 | 2020-09-17 | 2020-11-02 | 2021-07-26 | Overhead | R16 | 2020-11-02 | 1 |  | 33 | 191 | 223 | 2020 | 2021 | R16
166888210432 | 165581210432 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-06-21 | 2020-05-19 | 2020-11-12 |  | 2021-05-07 | Overhead | R16 |  | 238 | 128 |  |  | 491 | 2019 | 2021 | R16
168648203737 | 160731203737 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-14 | 2020-09-14 | 2020-09-14 |  | 2021-11-05 | Overhead | R16 | 2021-05-07 | 1 |  | 170 | 131 | 300 | 2020 | 2021 | R16
160967199927 | 161785199927 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-08-04 | 2020-08-04 | 2020-08-06 |  | 2020-10-06 | Overhead | R16 |  | 1 | 3 |  |  | 46 | 2020 | 2020 | R16
167900204832 | 162821204832 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-23 | 2020-09-23 | 2020-09-23 |  | 2021-01-20 | Overhead | R16 | 2020-10-08 | 1 |  | 12 | 75 | 86 | 2020 | 2021 | R16
166894155794 | 169951155794 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-05-20 | 2019-05-20 | 2019-06-21 |  | 2020-08-14 | Underground | R16 | 2020-06-22 | 1 | 25 | 262 | 40 | 325 | 2019 | 2020 | R16
160475233291 | 164968233291 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-13 | 2021-05-13 | 2021-06-02 |  | 2021-08-11 | Underground | R16 | 2021-06-29 | 1 | 15 | 20 | 32 | 65 | 2021 | 2021 | R16
168193224768 | 166944224768 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-09 | 2020-10-09 | 2021-03-25 |  | 2021-11-13 | Underground | R16 | 2021-04-19 | 1 | 120 | 18 | 150 | 286 | 2020 | 2021 | R16
166907162479 | 169628162479 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-17 | 2019-05-17 | 2019-08-29 |  | 2023-06-07 | Underground | R16 | 2019-11-01 | 1 | 75 | 47 | 939 | 1059 | 2019 | 2023 | R16
164326143281 | 163466143281 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-14 | 2019-02-14 | 2019-02-14 | 2019-03-06 | 2019-03-06 | Overhead | R16 | 2019-03-06 | 1 |  | 15 |  | 15 | 2019 | 2019 | R16
164622202112 | 167470202112 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-28 | 2020-08-28 | 2020-08-28 | 2020-09-30 | 2020-10-01 | Overhead | R16 | 2020-09-30 | 1 |  | 24 | 2 | 25 | 2020 | 2020 | R16
166927153100 | 169986153100 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-21 | 2019-05-21 | 2019-05-21 |  | 2023-06-07 | Overhead | R16 | 2019-07-01 | 1 |  | 30 | 1028 | 1057 | 2019 | 2023 | R16
169249223980 | 168094223980 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Commercial | 2021-03-03 | 2021-03-03 | 2021-03-17 |  | 2021-12-17 | Overhead | R16 |  | 1 | 11 |  |  | 208 | 2021 | 2021 | R16
167018255538 | 163642255538 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2021-10-19 | 2021-10-22 | 2021-11-08 |  | 2021-12-21 | Overhead | R16 |  | 4 | 12 |  |  | 46 | 2021 | 2021 | R16
160609205786 | 164888205786 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-30 | 2020-09-30 | 2020-09-30 |  | 2021-04-23 | Underground | R16 | 2021-02-02 | 1 |  | 90 | 59 | 148 | 2020 | 2021 | R16
164723229119 | 168918229119 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-19 | 2021-05-03 | 2021-05-03 |  | 2021-08-11 | Overhead | R16 | 2021-06-28 | 11 |  | 41 | 33 | 83 | 2021 | 2021 | R16
167040155224 | 163223155224 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-10 | 2019-06-13 | 2019-06-13 |  | 2019-07-01 | Overhead | R16 | 2019-07-01 | 4 |  | 13 |  | 16 | 2019 | 2019 | R16
168473218242 | 169233218242 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-25 | 2021-01-25 | 2021-01-25 | 2021-08-12 | 2021-04-07 | Overhead | R16 | 2021-08-12 | 1 |  | 144 |  | 53 | 2021 | 2021 | R16
164270224545 | 161533224545 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-02 | 2021-02-02 | 2021-03-23 | 2021-11-01 | 2023-04-13 | Underground | R16 | 2021-11-01 | 1 | 36 | 160 | 379 | 573 | 2021 | 2023 | R16
167166151778 | 168156151778 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-09 | 2019-05-09 | 2019-05-09 |  | 2019-08-12 | Underground | R16 | 2019-06-13 | 1 |  | 26 | 43 | 68 | 2019 | 2019 | R16
167371228610 | 161051228610 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-04-28 | 2021-04-28 | 2021-04-28 |  | 2022-08-30 | Overhead | R16 |  | 1 |  |  |  | 350 | 2021 | 2022 | R16
167198155199 | 163899155199 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-14 | 2019-06-14 | 2019-06-14 |  | 2019-08-26 | Overhead | R16 | 2019-06-24 | 1 |  | 7 | 46 | 52 | 2019 | 2019 | R16
164045219659 | 162502219659 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-05 | 2021-02-05 | 2021-02-05 | 2021-03-23 | 2021-08-06 | Overhead | R16 | 2021-03-23 | 1 |  | 33 | 99 | 131 | 2021 | 2021 | R16
167202153391 | 169995153391 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-05-20 | 2019-05-20 | 2019-05-24 |  | 2020-06-09 | Underground | R16 | 2020-02-25 | 1 | 5 | 198 | 76 | 277 | 2019 | 2020 | R16
165668251015 | 161307251015 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-04-28 | 2021-09-20 | 2021-10-07 |  | 2022-01-11 | Overhead | R16 |  | 104 | 14 |  |  | 185 | 2021 | 2022 | R16
169398209264 | 160791209264 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-29 | 2020-07-29 | 2020-10-30 |  | 2023-06-02 | Underground | R16 | 2022-02-02 | 1 | 68 | 329 | 348 | 743 | 2020 | 2023 | R16
167451230368 | 160052230368 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-11 | 2021-03-11 | 2021-05-11 |  | 2021-10-25 | Underground | R16 | 2021-09-02 | 1 | 44 | 83 | 38 | 163 | 2021 | 2021 | R16
168244199196 | 161741199196 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-03 | 2020-08-03 | 2020-08-03 |  | 2021-07-26 | Underground | R16 | 2020-11-03 | 1 |  | 67 | 190 | 256 | 2020 | 2021 | R16
164617211759 | 161432211759 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-29 | 2020-10-29 | 2020-11-24 |  | 2021-04-15 | Underground | R16 | 2020-12-28 | 1 | 19 | 25 | 79 | 121 | 2020 | 2021 | R16
163206143421 | 163532143421 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-14 | 2019-02-14 | 2019-02-14 | 2019-02-27 | 2019-03-05 | Overhead | R16 | 2019-02-27 | 1 |  | 10 | 5 | 14 | 2019 | 2019 | R16
162225255898 | 162782255898 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-12-22 | 2020-12-22 | 2021-11-10 |  | 2022-08-03 | Underground | R16 |  | 1 | 232 |  |  | 422 | 2020 | 2022 | R16
167369155733 | 162716155733 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2019-06-07 | 2019-06-10 | 2019-06-20 |  | 2020-06-09 | Underground | R16 |  | 2 | 9 |  |  | 263 | 2019 | 2020 | R16
169476233169 | 163996233169 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-28 | 2021-06-01 | 2021-06-01 | 2021-09-10 | 2021-10-25 | Overhead | R16 | 2021-09-10 | 47 |  | 74 | 32 | 151 | 2021 | 2021 | R16
167421153787 | 160865153787 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-24 | 2019-05-24 | 2019-05-30 |  | 2021-07-15 | Overhead | R16 | 2020-11-18 | 1 | 5 | 385 | 172 | 560 | 2019 | 2021 | R16
163190198358 | 160092198358 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-25 | 2020-07-25 | 2020-07-25 | 2020-08-20 | 2020-10-06 | Overhead | R16 | 2020-08-20 | 0 |  | 19 | 34 | 52 | 2020 | 2020 | R16
166955219243 | 161363219243 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-01 | 2021-02-01 | 2021-02-01 | 2022-02-25 | 2023-11-30 | Overhead | R16 | 2022-02-25 | 1 |  | 280 | 460 | 739 | 2021 | 2023 | R16
168534197559 | 168516197559 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-01-23 | 2019-01-23 | 2020-07-20 | 2020-07-22 | 2022-08-29 | Overhead | R16 | 2020-07-22 | 1 | 389 | 3 | 549 | 939 | 2019 | 2022 | R16
167443154485 | 162451154485 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-05 | 2019-06-05 | 2019-06-05 |  | 2019-10-16 | Overhead | R16 | 2019-10-11 | 1 |  | 93 | 4 | 96 | 2019 | 2019 | R16
164951148263 | 161745148263 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-04 | 2019-04-04 | 2019-04-04 | 2019-06-04 | 2019-08-12 | Underground | R16 | 2019-06-04 | 1 |  | 44 | 50 | 93 | 2019 | 2019 | R16
163402227671 | 169755227671 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Commercial | 2021-01-27 | 2021-02-01 | 2021-04-20 | 2021-09-21 | 2022-03-23 | Underground | R16 | 2021-09-21 | 4 | 57 | 111 | 132 | 301 | 2021 | 2022 | R16
167256221336 | 161114221336 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2021-01-29 | 2021-01-29 | 2021-02-24 | 2021-04-09 | 2021-06-02 | Underground | R16 | 2021-04-09 | 1 | 19 | 33 | 39 | 89 | 2021 | 2021 | R16
167460155761 | 165057155761 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-18 | 2019-06-18 | 2019-06-18 |  | 2019-08-26 | Overhead | R16 | 2019-06-26 | 1 |  | 7 | 44 | 50 | 2019 | 2019 | R16
161251225411 | 164763225411 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-31 | 2021-03-31 | 2021-03-31 |  | 2022-05-03 | Overhead | R16 | 2022-04-28 | 1 |  | 282 | 4 | 285 | 2021 | 2022 | R16
167855239075 | 161007239075 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-16 | 2021-07-15 | 2021-07-15 |  | 2022-03-08 | Underground | R16 | 2022-01-19 | 88 |  | 135 | 35 | 256 | 2021 | 2022 | R16
165844208842 | 160565208842 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2020-10-26 | 2020-10-26 | 2020-10-28 | 2020-10-29 | 2022-08-25 | Overhead | R16 | 2020-10-29 | 1 | 3 | 2 | 476 | 479 | 2020 | 2022 | R16
167581155676 | 165047155676 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-18 | 2019-06-18 | 2019-06-19 |  | 2019-12-06 | Overhead | R16 | 2019-08-08 | 1 | 2 | 37 | 87 | 124 | 2019 | 2019 | R16
160537172272 | 160654172272 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-01-31 | 2019-04-15 | 2019-11-19 | 2020-03-02 | 2020-05-05 | Underground | R16 | 2020-03-02 | 53 | 157 | 75 | 47 | 329 | 2019 | 2020 | R16
167582155316 | 163939155316 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-14 | 2019-06-14 | 2019-06-14 |  | 2019-08-26 | Overhead | R16 | 2019-07-08 | 1 |  | 17 | 36 | 52 | 2019 | 2019 | R16
167718194464 | 162228194464 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2020-06-15 | 2020-06-15 | 2020-06-15 |  | 2021-04-23 | Underground | R16 |  | 1 |  |  |  | 225 | 2020 | 2021 | R16
161319213280 | 167935213280 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-01 | 2020-12-01 | 2020-12-08 | 2021-06-22 | 2021-08-11 | Underground | R16 | 2021-06-22 | 1 | 6 | 141 | 37 | 182 | 2020 | 2021 | R16
162923156968 | 167705156968 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-05-07 | 2019-05-13 | 2019-07-03 | 2019-09-03 | 2020-02-04 | Underground | R16 | 2019-09-03 | 5 | 38 | 45 | 111 | 196 | 2019 | 2020 | R16
167718198519 | 160617198519 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2020-07-29 | 2020-07-29 | 2020-07-29 |  | 2022-07-27 | Underground | R16 |  | 1 |  |  |  | 521 | 2020 | 2022 | R16
168843210437 | 164617210437 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-12 | 2020-11-12 | 2020-11-12 | 2021-01-13 | 2021-01-14 | Overhead | R16 | 2021-01-13 | 1 |  | 45 | 2 | 46 | 2020 | 2021 | R16
166504223751 | 167995223751 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-03 | 2021-03-03 | 2021-03-16 |  | 2021-11-08 | Underground | R16 | 2021-05-19 | 1 | 10 | 47 | 124 | 179 | 2021 | 2021 | R16
163353211383 | 164382211383 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-11 | 2020-11-11 | 2020-11-19 | 2021-02-04 | 2021-02-08 | Underground | R16 | 2021-02-04 | 1 | 7 | 56 | 3 | 64 | 2020 | 2021 | R16
167727152542 | 169220152542 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-15 | 2019-05-15 | 2019-05-15 |  | 2019-08-12 | Overhead | R16 | 2019-06-13 | 1 |  | 22 | 43 | 64 | 2019 | 2019 | R16
161295226410 | 167323226410 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-12 | 2021-04-12 | 2021-04-12 | 2021-06-30 | 2021-07-01 | Overhead | R16 | 2021-06-30 | 1 |  | 58 | 2 | 59 | 2021 | 2021 | R16
167850154373 | 162296154373 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-05 | 2019-06-05 | 2019-06-05 |  | 2019-08-26 | Overhead | R16 | 2019-07-16 | 1 |  | 30 | 30 | 59 | 2019 | 2019 | R16
160851226044 | 166135226044 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-07 | 2021-04-07 | 2021-04-07 |  | 2021-11-08 | Overhead | R16 | 2021-05-12 | 1 |  | 26 | 129 | 154 | 2021 | 2021 | R16
167491203658 | 160831203658 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-14 | 2020-09-14 | 2020-09-14 | 2020-10-21 | 2021-07-02 | Overhead | R16 | 2020-10-21 | 1 |  | 28 | 183 | 210 | 2020 | 2021 | R16
164712237885 | 169297237885 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-10-21 | 2021-07-02 | 2021-07-06 |  | 2023-08-02 | Overhead | R16 |  | 183 | 3 |  |  | 726 | 2020 | 2023 | R16
161734169081 | 161764169081 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-02-06 | 2019-07-24 | 2019-10-21 | 2020-09-21 | 2020-10-16 | Underground | R16 | 2020-09-21 | 121 | 64 | 241 | 20 | 443 | 2019 | 2020 | R16
164215210005 | 169114210005 | Fleet Chargers | UG R16 RESD AND NON RESD UD | Commercial | 2020-07-21 | 2020-07-21 | 2020-11-09 | 2020-12-21 | 2021-03-03 | Underground | R16 | 2020-12-21 | 1 | 80 | 31 | 53 | 162 | 2020 | 2021 | R16
167961155568 | 164318155568 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-17 | 2019-06-17 | 2019-06-17 |  | 2020-10-06 | Underground | R16 | 2020-08-07 | 1 |  | 300 | 43 | 342 | 2019 | 2020 | R16
167487226593 | 165798226593 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-22 | 2021-02-22 | 2021-04-13 |  | 2021-11-08 | Underground | R16 | 2021-05-28 | 1 | 37 | 34 | 117 | 186 | 2021 | 2021 | R16
165079206933 | 167378206933 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-13 | 2020-10-13 | 2020-10-13 |  | 2021-07-19 | Overhead | R16 | 2020-11-23 | 1 |  | 30 | 171 | 200 | 2020 | 2021 | R16
166990225982 | 165962225982 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-06 | 2021-04-06 | 2021-04-06 |  | 2021-11-08 | Overhead | R16 | 2021-05-17 | 1 |  | 30 | 126 | 155 | 2021 | 2021 | R16
167215220608 | 162798220608 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-08 | 2021-02-16 | 2021-02-16 |  | 2021-08-03 | Overhead | R16 | 2021-03-31 | 7 |  | 32 | 90 | 127 | 2021 | 2021 | R16
162343222895 | 165941222895 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-22 | 2021-03-09 | 2021-03-09 |  | 2021-08-03 | Underground | R16 | 2021-03-29 | 12 |  | 15 | 92 | 117 | 2021 | 2021 | R16
168040164913 | 163763164913 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-06-13 | 2019-08-02 | 2019-09-19 |  | 2020-12-14 | Underground | R16 |  | 37 | 35 |  |  | 393 | 2019 | 2020 | R16
168048153162 | 169950153162 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-20 | 2019-05-20 | 2019-05-22 |  | 2019-08-26 | Overhead | R16 | 2019-07-25 | 1 | 3 | 47 | 23 | 71 | 2019 | 2019 | R16
167219207937 | 160017207937 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-23 | 2020-10-23 | 2020-10-23 |  | 2021-04-14 | Overhead | R16 | 2020-12-09 | 1 |  | 34 | 91 | 124 | 2020 | 2021 | R16
168118164851 | 161594164851 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-18 | 2019-09-18 | 2019-09-18 |  | 2019-11-08 | Underground | R16 | 2019-11-01 | 1 |  | 33 | 6 | 38 | 2019 | 2019 | R16
168130153067 | 160008153067 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-20 | 2019-05-20 | 2019-05-21 |  | 2019-09-03 | Overhead | R16 | 2019-07-31 | 1 | 2 | 52 | 25 | 77 | 2019 | 2019 | R16
168347207057 | 167389207057 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-13 | 2020-10-13 | 2020-10-13 | 2020-11-19 | 2021-04-14 | Overhead | R16 | 2020-11-19 | 1 |  | 28 | 105 | 132 | 2020 | 2021 | R16
168173156169 | 165845156169 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-24 | 2019-06-24 | 2019-06-24 |  | 2019-08-26 | Underground | R16 | 2019-07-09 | 1 |  | 12 | 35 | 46 | 2019 | 2019 | R16
165501206313 | 162048206313 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Commercial | 2020-08-05 | 2020-09-18 | 2020-10-06 | 2021-10-26 | 2021-11-12 | Underground | R16 | 2021-10-26 | 33 | 13 | 276 | 14 | 333 | 2020 | 2021 | R16
168213158161 | 160044158161 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-15 | 2019-07-15 | 2019-07-17 |  | 2019-12-06 | Overhead | R16 | 2019-08-07 | 1 | 3 | 16 | 88 | 105 | 2019 | 2019 | R16
165084152508 | 168179152508 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-09 | 2019-05-15 | 2019-05-15 | 2019-05-23 | 2019-08-26 | Overhead | R16 | 2019-05-23 | 5 |  | 7 | 68 | 78 | 2019 | 2019 | R16
168231153283 | 160619153283 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-23 | 2019-05-23 | 2019-05-23 |  | 2019-08-26 | Overhead | R16 | 2019-06-27 | 1 |  | 26 | 43 | 68 | 2019 | 2019 | R16
169267243456 | 165180243456 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH CP R16 WORK RELO TO UG | Residential | 2021-02-18 | 2021-02-18 | 2021-08-13 | 2021-12-09 | 2022-01-05 | Overhead | R16 | 2021-12-09 | 1 | 127 | 85 | 20 | 230 | 2021 | 2022 | R16
168257153274 | 160647153274 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-23 | 2019-05-23 | 2019-05-23 |  | 2019-10-16 | Overhead | R16 | 2019-10-07 | 1 |  | 98 | 8 | 105 | 2019 | 2019 | R16
169746222608 | 168520222608 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-05-05 | 2021-05-05 | Overhead | R16 | 2021-05-05 | 1 |  | 44 |  | 44 | 2021 | 2021 | R16
167238220940 | 165841220940 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-01-08 | 2021-01-25 | 2021-02-18 |  | 2021-10-25 | Underground | R16 |  | 12 | 19 |  |  | 207 | 2021 | 2021 | R16
168343164363 | 163659164363 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-13 | 2019-07-09 | 2019-09-13 |  | 2019-10-16 | Underground | R16 |  | 19 | 49 |  |  | 90 | 2019 | 2019 | R16
169262154758 | 162931154758 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-08 | 2019-06-08 | 2019-06-08 |  | 2019-09-03 | Overhead | R16 | 2019-08-26 | 0 |  | 56 | 7 | 62 | 2019 | 2019 | R16
167803214264 | 161189214264 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-16 | 2020-12-16 | 2020-12-16 |  | 2021-11-08 | Overhead | R16 | 2021-04-21 | 1 |  | 91 | 144 | 234 | 2020 | 2021 | R16
168388152545 | 168937152545 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-14 | 2019-05-14 | 2019-05-15 |  | 2019-08-26 | Overhead | R16 | 2019-06-25 | 1 | 2 | 30 | 45 | 75 | 2019 | 2019 | R16
164269202601 | 168230202601 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-02 | 2020-09-02 | 2020-09-02 |  | 2021-07-26 | Overhead | R16 | 2020-11-05 | 1 |  | 47 | 188 | 234 | 2020 | 2021 | R16
168396154972 | 161102154972 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-05-28 | 2019-06-10 | 2019-06-10 |  | 2020-07-10 | Underground | R16 | 2020-06-11 | 10 |  | 264 | 22 | 294 | 2019 | 2020 | R16
168399155833 | 163386155833 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-11 | 2019-06-11 | 2019-06-20 |  | 2019-09-18 | Overhead | R16 | 2019-09-10 | 1 | 8 | 59 | 7 | 72 | 2019 | 2019 | R16
166914205717 | 163306205717 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-24 | 2020-09-30 | 2020-10-01 | 2020-10-22 | 2021-11-10 | Overhead | R16 | 2020-10-22 | 5 | 2 | 16 | 275 | 295 | 2020 | 2021 | R16
169575199269 | 160632199269 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-07-29 | 2020-07-31 | 2020-07-31 | 2020-10-05 | 2021-01-20 | Overhead | R16 | 2020-10-05 | 3 |  | 47 | 78 | 126 | 2020 | 2021 | R16
168405158648 | 161402158648 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-07-22 | 2019-07-22 | 2019-07-22 |  | 2019-10-17 | Overhead | R16 | 2019-10-11 | 1 |  | 60 | 5 | 64 | 2019 | 2019 | R16
169741228352 | 160750228352 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-26 | 2021-04-26 | 2021-04-26 | 2021-06-08 | 2021-08-23 | Underground | R16 | 2021-06-08 | 1 |  | 32 | 55 | 86 | 2021 | 2021 | R16
168412157109 | 167894157109 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-02 | 2019-07-03 | 2019-07-03 |  | 2019-10-18 | Overhead | R16 | 2019-10-07 | 2 |  | 69 | 10 | 79 | 2019 | 2019 | R16
163031223340 | 169703223340 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-10 | 2021-03-10 | 2021-03-11 | 2021-03-12 | 2021-11-08 | Overhead | R16 | 2021-03-12 | 1 | 2 | 2 | 172 | 174 | 2021 | 2021 | R16
168415155760 | 165056155760 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-18 | 2019-06-18 | 2019-06-18 |  | 2019-08-26 | Overhead | R16 | 2019-07-16 | 1 |  | 21 | 30 | 50 | 2019 | 2019 | R16
161075214401 | 161382214401 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-17 | 2020-12-17 | 2020-12-17 |  | 2022-10-19 | Overhead | R16 |  | 1 |  |  |  | 480 | 2020 | 2022 | R16
166781205608 | 164261205608 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-28 | 2020-09-28 | 2020-09-28 | 2022-01-25 | 2022-02-28 | Overhead | R16 | 2022-01-25 | 1 |  | 347 | 25 | 371 | 2020 | 2022 | R16
168422172634 | 164611172634 | NON-RESIDENTIAL - MISCELLANEOUS | UG ELEC MISC SVC US | Commercial | 2019-11-21 | 2019-11-21 | 2019-11-22 |  | 2021-11-02 | Underground | R16 |  | 1 | 2 |  |  | 509 | 2019 | 2021 | R16
160235233194 | 160636233194 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-28 | 2021-05-28 | 2021-06-02 |  | 2021-08-13 | Underground | R16 | 2021-07-19 | 1 | 4 | 34 | 20 | 56 | 2021 | 2021 | R16
168625204085 | 169424204085 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-21 | 2020-07-21 | 2020-09-16 | 2020-10-14 | 2020-10-15 | Underground | R16 | 2020-10-14 | 1 | 42 | 21 | 2 | 63 | 2020 | 2020 | R16
166854142483 | 161710142483 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-06 | 2019-02-06 | 2019-02-06 | 2019-03-04 | 2019-04-22 | Overhead | R16 | 2019-03-04 | 1 |  | 19 | 36 | 54 | 2019 | 2019 | R16
168651156415 | 166111156415 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-25 | 2019-06-26 | 2019-06-26 |  | 2019-08-26 | Overhead | R16 | 2019-07-09 | 2 |  | 10 | 35 | 45 | 2019 | 2019 | R16
168655153328 | 160841153328 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-24 | 2019-05-24 | 2019-05-24 |  | 2022-10-17 | Overhead | R16 |  | 1 |  |  |  | 887 | 2019 | 2022 | R16
168659156419 | 165904156419 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-06-25 | 2019-06-26 | 2019-06-26 |  | 2019-08-26 | Overhead | R16 | 2019-07-08 | 2 |  | 9 | 36 | 45 | 2019 | 2019 | R16
161669218815 | 169450218815 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-25 | 2021-01-29 | 2021-01-29 | 2021-03-19 | 2021-08-10 | Overhead | R16 | 2021-03-19 | 5 |  | 36 | 103 | 142 | 2021 | 2021 | R16
164099222364 | 161374222364 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-01 | 2021-03-03 | 2021-03-03 | 2021-04-15 | 2021-11-08 | Overhead | R16 | 2021-04-15 | 23 |  | 32 | 148 | 201 | 2021 | 2021 | R16
162354139893 | 166697139893 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-11 | 2019-01-11 | 2019-01-11 | 2019-01-30 | 2019-01-30 | Overhead | R16 | 2019-01-30 | 1 |  | 14 |  | 14 | 2019 | 2019 | R16
168707155170 | 163580155170 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-12 | 2019-06-12 | 2019-06-12 |  | 2019-09-03 | Overhead | R16 | 2019-08-26 | 1 |  | 54 | 7 | 60 | 2019 | 2019 | R16
165321218931 | 167233218931 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-14 | 2021-01-14 | 2021-01-29 | 2021-06-17 | 2021-06-17 | Underground | R16 | 2021-06-17 | 1 | 12 | 100 |  | 111 | 2021 | 2021 | R16
160687222461 | 167478222461 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-15 | 2021-03-04 | 2021-03-04 |  | 2021-10-28 | Overhead | R16 | 2021-07-29 | 35 |  | 106 | 66 | 205 | 2021 | 2021 | R16
168710156848 | 167614156848 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-01 | 2019-07-01 | 2019-07-01 |  | 2020-07-02 | Overhead | R16 | 2020-05-04 | 1 |  | 221 | 44 | 264 | 2019 | 2020 | R16
169979209009 | 160963209009 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-28 | 2020-10-28 | 2020-10-29 |  | 2021-07-26 | Overhead | R16 | 2020-11-04 | 1 | 2 | 5 | 189 | 194 | 2020 | 2021 | R16
168713154757 | 162839154757 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-08 | 2019-06-08 | 2019-06-08 |  | 2023-06-07 | Overhead | R16 | 2019-07-17 | 0 |  | 28 | 1016 | 1043 | 2019 | 2023 | R16
162239212880 | 168628212880 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-12-04 | 2020-12-04 | 2020-12-04 | 2021-02-23 | 2021-08-02 | Underground | R16 | 2021-02-23 | 1 |  | 58 | 115 | 172 | 2020 | 2021 | R16
168729153431 | 160727153431 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-23 | 2019-05-23 | 2019-05-24 |  | 2019-08-12 | Underground | R16 | 2019-06-13 | 1 | 2 | 15 | 43 | 58 | 2019 | 2019 | R16
169377233459 | 161117233459 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-02 | 2021-06-04 | 2021-06-04 | 2021-08-04 | 2021-08-05 | Overhead | R16 | 2021-08-04 | 3 |  | 44 | 2 | 47 | 2021 | 2021 | R16
168765153551 | 161038153551 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-28 | 2019-05-28 | 2019-05-28 |  | 2019-09-03 | Overhead | R16 | 2019-07-31 | 1 |  | 47 | 25 | 71 | 2019 | 2019 | R16
166348153307 | 166304153307 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-30 | 2019-04-30 | 2019-05-23 | 2019-08-07 | 2019-08-09 | Underground | R16 | 2019-08-07 | 1 | 18 | 55 | 3 | 74 | 2019 | 2019 | R16
167536220044 | 168609220044 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-09-03 | 2020-12-14 | 2021-02-09 | 2021-03-10 | 2022-08-22 | Underground | R16 | 2021-03-10 | 73 | 42 | 22 | 379 | 513 | 2020 | 2022 | R16
160612217521 | 167352217521 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-15 | 2021-01-15 | 2021-01-15 | 2021-03-26 | 2021-03-26 | Overhead | R16 | 2021-03-26 | 1 |  | 51 |  | 51 | 2021 | 2021 | R16
168780158360 | 160488158360 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-17 | 2019-07-18 | 2019-07-18 |  | 2019-10-30 | Overhead | R16 | 2019-10-23 | 2 |  | 70 | 6 | 76 | 2019 | 2019 | R16
162998206528 | 166761206528 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-08 | 2020-10-08 | 2020-10-08 | 2021-01-08 | 2021-04-29 | Overhead | R16 | 2021-01-08 | 1 |  | 67 | 80 | 146 | 2020 | 2021 | R16
169831228529 | 160892228529 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-27 | 2021-04-27 | 2021-04-27 | 2021-08-26 | 2021-08-26 | Overhead | R16 | 2021-08-26 | 1 |  | 88 |  | 88 | 2021 | 2021 | R16
166030219846 | 165865219846 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-11 | 2021-02-06 | 2021-02-06 |  | 2021-11-05 | Overhead | R16 | 2021-04-14 | 20 |  | 48 | 148 | 215 | 2021 | 2021 | R16
168901155649 | 164416155649 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-17 | 2019-06-18 | 2019-06-18 |  | 2020-10-06 | Underground | R16 | 2020-07-10 | 2 |  | 279 | 63 | 342 | 2019 | 2020 | R16
168905153598 | 161410153598 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-05-29 | 2019-05-30 | 2019-05-30 |  | 2020-10-06 | Underground | R16 | 2020-07-24 | 2 |  | 302 | 53 | 355 | 2019 | 2020 | R16
160452158660 | 169099158660 | FOREIGN UTILITY | OH R16 RES NON RES OD | Residential | 2019-03-21 | 2019-04-25 | 2019-07-22 | 2019-08-26 | 2020-01-09 | Overhead | R16 | 2019-08-26 | 26 | 63 | 26 | 99 | 211 | 2019 | 2020 | R16
168943155730 | 165184155730 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-19 | 2019-06-19 | 2019-06-19 |  | 2019-08-26 | Underground | R16 | 2019-07-18 | 1 |  | 22 | 28 | 49 | 2019 | 2019 | R16
161245216598 | 161480216598 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-31 | 2020-07-31 | 2021-01-11 |  | 2021-10-26 | Underground | R16 | 2021-04-09 | 1 | 117 | 65 | 143 | 323 | 2020 | 2021 | R16
167824222858 | 168049222858 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-03-03 | 2021-03-09 | 2021-03-09 | 2021-03-11 | 2021-03-11 | Underground | R16 | 2021-03-11 | 5 |  | 3 |  | 7 | 2021 | 2021 | R16
164424274777 | 164723274777 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential Subdivision | 2021-02-17 | 2021-02-17 | 2022-04-05 | 2023-02-27 | 2023-05-12 | Underground | R16 | 2023-02-27 | 1 | 295 | 235 | 55 | 583 | 2021 | 2023 | R16
169010170546 | 163314170546 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2019-09-27 | 2019-09-27 | 2019-11-04 |  | 2022-05-13 | Underground | R16 |  | 1 | 27 |  |  | 686 | 2019 | 2022 | R16
163849220875 | 164623220875 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-01-05 | 2021-01-05 | 2021-02-18 |  | 2022-08-16 | Overhead | R16 |  | 1 | 33 |  |  | 421 | 2021 | 2022 | R16
165874151702 | 167544151702 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-05-07 | 2019-05-07 | 2019-05-07 | 2023-06-06 | 2023-08-17 | Underground | R16 | 2023-06-06 | 1 |  | 1066 | 53 | 1118 | 2019 | 2023 | R16
164138231575 | 161255231575 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-04-29 | 2021-05-20 | 2021-05-20 | 2021-05-21 | 2021-08-23 | Overhead | R16 | 2021-05-21 | 16 |  | 2 | 67 | 83 | 2021 | 2021 | R16
169133196087 | 169211196087 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2019-05-15 | 2019-05-15 | 2020-06-30 | 2021-06-30 | 2022-08-03 | Underground | R16 | 2021-06-30 | 1 | 295 | 262 | 286 | 841 | 2019 | 2022 | R16
169066156736 | 167761156736 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-02 | 2019-07-02 | 2019-07-02 |  | 2019-09-03 | Overhead | R16 | 2019-07-29 | 1 |  | 20 | 27 | 46 | 2019 | 2019 | R16
169133181615 | 169210181615 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-05-15 | 2019-05-15 | 2020-02-25 |  | 2021-11-10 | Overhead | R16 |  | 1 | 205 |  |  | 651 | 2019 | 2021 | R16
168200221133 | 165540221133 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-19 | 2021-02-19 | 2021-02-19 |  | 2022-01-18 | Overhead | R16 | 2021-12-08 | 1 |  | 209 | 30 | 238 | 2021 | 2022 | R16
163088214140 | 160424214140 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-25 | 2020-12-15 | 2020-12-15 | 2021-03-23 | 2021-08-06 | Overhead | R16 | 2021-03-23 | 37 |  | 71 | 99 | 205 | 2020 | 2021 | R16
160013227713 | 169198227713 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-04-21 | 2021-04-21 | 2021-04-21 | 2023-10-24 | 2022-07-19 | Underground | R16 | 2023-10-24 | 1 |  | 655 |  | 325 | 2021 | 2022 | R16
169176154517 | 162558154517 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-06 | 2019-06-06 | 2019-06-06 |  | 2019-08-26 | Overhead | R16 | 2019-07-24 | 1 |  | 35 | 24 | 58 | 2019 | 2019 | R16
162665220197 | 162576220197 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-02-06 | 2021-02-06 | 2021-02-10 | 2021-06-24 | 2023-10-04 | Overhead | R16 | 2021-06-24 | 0 | 3 | 97 | 595 | 693 | 2021 | 2023 | R16
160928225251 | 164508225251 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-30 | 2021-03-30 | 2021-03-30 | 2021-04-02 | 2021-11-08 | Underground | R16 | 2021-04-02 | 1 |  | 4 | 157 | 160 | 2021 | 2021 | R16
169221158471 | 168115158471 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-03 | 2019-07-03 | 2019-07-20 |  | 2019-08-26 | Underground | R16 |  | 1 | 13 |  |  | 39 | 2019 | 2019 | R16
165156245295 | 164988245295 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-01-06 | 2021-01-06 | 2021-08-26 |  | 2022-05-10 | Underground | R16 |  | 1 | 167 |  |  | 350 | 2021 | 2022 | R16
163539210789 | 165015210789 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-16 | 2020-11-16 | 2020-11-16 | 2021-03-03 | 2021-03-04 | Overhead | R16 | 2021-03-03 | 1 |  | 78 | 2 | 79 | 2020 | 2021 | R16
164708217372 | 167500217372 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-15 | 2021-01-15 | 2021-01-15 | 2022-02-03 | 2022-03-04 | Overhead | R16 | 2022-02-03 | 1 |  | 275 | 22 | 296 | 2021 | 2022 | R16
161064229597 | 163202229597 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-05 | 2021-05-05 | 2021-05-05 |  | 2021-08-30 | Underground | R16 | 2021-06-10 | 1 |  | 27 | 58 | 84 | 2021 | 2021 | R16
162472207961 | 162490207961 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-22 | 2020-09-22 | 2020-10-22 | 2021-06-04 | 2021-06-07 | Underground | R16 | 2021-06-04 | 1 | 23 | 162 | 2 | 185 | 2020 | 2021 | R16
167128151747 | 160263151747 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-03-27 | 2019-03-27 | 2019-05-08 | 2019-07-08 | 2019-08-21 | Overhead | R16 | 2019-07-08 | 1 | 31 | 44 | 33 | 106 | 2019 | 2019 | R16
169328154863 | 161974154863 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-03 | 2019-06-03 | 2019-06-10 |  | 2019-10-30 | Underground | R16 | 2019-10-22 | 1 | 6 | 97 | 7 | 108 | 2019 | 2019 | R16
160613225309 | 164413225309 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-30 | 2021-03-30 | 2021-03-30 | 2021-04-05 | 2021-11-08 | Overhead | R16 | 2021-04-05 | 1 |  | 5 | 156 | 160 | 2021 | 2021 | R16
169406162334 | 167750162334 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-27 | 2019-08-27 | 2019-08-27 |  | 2019-11-21 | Overhead | R16 | 2019-11-12 | 1 |  | 56 | 8 | 63 | 2019 | 2019 | R16
162207219057 | 162696219057 | NON-RESIDENTIAL - SMALL RETAIL | R16 RESD AND NON RESD US | Commercial | 2020-08-07 | 2020-08-31 | 2021-02-01 |  | 2021-10-28 | Underground | R16 |  | 17 | 111 |  |  | 320 | 2020 | 2021 | R16
168068237022 | 164166237022 | AGRICULTURAL | OH R16 RES NON RES OS | Commercial | 2021-03-29 | 2021-04-28 | 2021-06-28 | 2021-08-12 | 2021-09-23 | Overhead | R16 | 2021-08-12 | 23 | 44 | 34 | 31 | 129 | 2021 | 2021 | R16
169426154181 | 161912154181 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-03 | 2019-06-03 | 2019-06-03 |  | 2019-08-12 | Overhead | R16 | 2019-06-14 | 1 |  | 10 | 42 | 51 | 2019 | 2019 | R16
168581216914 | 165760216914 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2021-01-08 | 2021-01-08 | 2021-01-12 |  | 2021-11-02 | Underground | R16 |  | 1 | 3 |  |  | 213 | 2021 | 2021 | R16
162969238101 | 166880238101 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-18 | 2021-05-18 | 2021-07-07 | 2021-10-20 | 2021-11-18 | Underground | R16 | 2021-10-20 | 1 | 37 | 76 | 22 | 133 | 2021 | 2021 | R16
168069214212 | 169886214212 | AGRICULTURAL | OH R16 RES NON RES OS | Commercial | 2020-12-10 | 2020-12-10 | 2020-12-17 | 2021-08-27 | 2022-02-04 | Overhead | R16 | 2021-08-27 | 1 | 6 | 182 | 116 | 302 | 2020 | 2022 | R16
167699150699 | 163004150699 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-11 | 2019-04-11 | 2019-04-30 | 2019-09-18 | 2019-09-18 | Underground | R16 | 2019-09-18 | 1 | 14 | 102 |  | 115 | 2019 | 2019 | R16
168323207393 | 168294207393 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-10-15 | 2020-10-15 | 2020-10-15 |  | 2021-08-12 | Overhead | R16 | 2021-07-08 | 1 |  | 191 | 26 | 216 | 2020 | 2021 | R16
169512157085 | 165304157085 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-20 | 2019-06-20 | 2019-07-03 |  | 2019-10-14 | Underground | R16 | 2019-10-02 | 1 | 10 | 66 | 9 | 83 | 2019 | 2019 | R16
166438218893 | 161050218893 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-29 | 2021-01-29 | 2021-01-29 |  | 2021-11-08 | Overhead | R16 | 2021-05-13 | 1 |  | 75 | 128 | 202 | 2021 | 2021 | R16
169533155117 | 162662155117 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-06 | 2019-06-10 | 2019-06-13 |  | 2019-10-28 | Underground | R16 | 2019-07-25 | 3 | 4 | 31 | 68 | 103 | 2019 | 2019 | R16
169554154671 | 162625154671 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-06 | 2019-06-06 | 2019-06-07 |  | 2022-07-25 | Underground | R16 | 2022-06-08 | 1 | 2 | 784 | 34 | 818 | 2019 | 2022 | R16
167477158617 | 162938158617 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-11 | 2019-04-11 | 2019-07-23 | 2019-08-28 | 2019-09-19 | Underground | R16 | 2019-08-28 | 1 | 74 | 27 | 17 | 116 | 2019 | 2019 | R16
169566157052 | 166698157052 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-28 | 2019-06-28 | 2019-07-03 |  | 2021-01-20 | Underground | R16 | 2020-10-13 | 1 | 4 | 335 | 72 | 409 | 2019 | 2021 | R16
169600157564 | 161545157564 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-05-30 | 2019-05-30 | 2019-07-10 |  | 2020-08-28 | Underground | R16 | 2020-06-30 | 1 | 30 | 255 | 44 | 327 | 2019 | 2020 | R16
167899227800 | 169208227800 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-20 | 2021-04-20 | 2021-04-20 |  | 2021-08-23 | Overhead | R16 | 2021-07-26 | 1 |  | 70 | 21 | 90 | 2021 | 2021 | R16
169601157051 | 166704157051 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-28 | 2019-06-28 | 2019-07-03 |  | 2021-11-18 | Underground | R16 | 2021-10-29 | 1 | 4 | 608 | 15 | 625 | 2019 | 2021 | R16
169603157562 | 166801157562 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-28 | 2019-06-28 | 2019-07-10 |  | 2020-10-06 | Underground | R16 | 2020-07-28 | 1 | 9 | 275 | 51 | 333 | 2019 | 2020 | R16
165789230464 | 169483230464 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-04-20 | 2021-05-12 | 2021-05-12 |  | 2021-12-29 | Underground | R16 | 2021-11-19 | 17 |  | 138 | 29 | 182 | 2021 | 2021 | R16
169607156739 | 167684156739 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-02 | 2019-07-02 | 2019-07-02 |  | 2019-09-26 | Overhead | R16 | 2019-09-18 | 1 |  | 57 | 7 | 63 | 2019 | 2019 | R16
163676212973 | 169014212973 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-07 | 2020-12-07 | 2020-12-07 | 2021-06-21 | 2021-08-11 | Overhead | R16 | 2021-06-21 | 1 |  | 141 | 38 | 178 | 2020 | 2021 | R16
169638157217 | 168375157217 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-06 | 2019-07-06 | 2019-07-06 |  | 2019-09-03 | Overhead | R16 | 2019-07-31 | 0 |  | 18 | 25 | 42 | 2019 | 2019 | R16
169374219877 | 163159219877 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-09 | 2021-02-09 | 2021-02-09 | 2021-04-19 | 2021-11-08 | Overhead | R16 | 2021-04-19 | 1 |  | 50 | 146 | 195 | 2021 | 2021 | R16
169639154781 | 162821154781 | AGRICULTURAL | OH R16 RES NON RES OS | Commercial | 2019-06-07 | 2019-06-07 | 2019-06-07 |  | 2023-01-10 | Overhead | R16 | 2022-11-02 | 1 |  | 889 | 50 | 938 | 2019 | 2023 | R16
169642153824 | 161475153824 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-05-30 | 2019-05-30 | 2019-05-30 |  | 2021-11-05 | Overhead | R16 | 2021-05-07 | 1 |  | 507 | 131 | 637 | 2019 | 2021 | R16
169695155763 | 160453155763 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-05-22 | 2019-05-22 | 2019-06-18 |  | 2019-08-26 | Underground | R16 | 2019-07-17 | 1 | 20 | 22 | 29 | 69 | 2019 | 2019 | R16
168188229114 | 160538229114 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-26 | 2021-05-03 | 2021-05-03 |  | 2021-08-11 | Overhead | R16 | 2021-06-28 | 6 |  | 41 | 33 | 78 | 2021 | 2021 | R16
161919201561 | 165475201561 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-21 | 2020-08-24 | 2020-08-24 |  | 2021-04-16 | Overhead | R16 | 2021-01-19 | 2 |  | 107 | 64 | 171 | 2020 | 2021 | R16
166921210914 | 164817210914 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-13 | 2020-11-17 | 2020-11-17 |  | 2021-04-14 | Overhead | R16 | 2020-12-10 | 3 |  | 18 | 90 | 109 | 2020 | 2021 | R16
169918165200 | 160594165200 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-23 | 2019-05-23 | 2019-09-19 |  | 2019-11-15 | Underground | R16 | 2019-11-08 | 1 | 86 | 37 | 6 | 127 | 2019 | 2019 | R16
162388140228 | 167173140228 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-15 | 2019-01-15 | 2019-01-15 | 2019-02-17 | 2019-02-20 | Overhead | R16 | 2019-02-17 | 1 |  | 24 | 3 | 27 | 2019 | 2019 | R16
162819147979 | 161488147979 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-04 | 2019-04-04 | 2019-04-04 | 2019-04-16 | 2019-04-17 | Overhead | R16 | 2019-04-16 | 1 |  | 9 | 2 | 10 | 2019 | 2019 | R16
161415216691 | 161416216691 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-12-17 | 2020-12-17 | 2021-01-08 | 2022-05-23 | 2022-05-24 | Overhead | R16 | 2022-05-23 | 1 | 17 | 357 | 2 | 374 | 2020 | 2022 | R16
168754219790 | 162493219790 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-05 | 2021-02-05 | 2021-02-05 |  | 2021-11-08 | Overhead | R16 | 2021-05-25 | 1 |  | 78 | 120 | 197 | 2021 | 2021 | R16
162008198782 | 160590198782 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-28 | 2020-07-28 | 2020-07-28 | 2020-10-01 | 2020-10-02 | Overhead | R16 | 2020-10-01 | 1 |  | 48 | 2 | 49 | 2020 | 2020 | R16
160029156352 | 166204156352 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-26 | 2019-06-26 | 2019-06-26 |  | 2019-09-03 | Overhead | R16 | 2019-07-30 | 1 |  | 25 | 26 | 50 | 2019 | 2019 | R16
163212226168 | 163886226168 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-02-12 | 2021-02-12 | 2021-04-08 |  | 2021-11-08 | Overhead | R16 | 2021-05-26 | 1 | 40 | 35 | 119 | 192 | 2021 | 2021 | R16
160058159070 | 162302159070 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-27 | 2019-07-27 | 2019-07-27 |  | 2021-04-20 | Overhead | R16 | 2021-01-13 | 0 |  | 383 | 70 | 452 | 2019 | 2021 | R16
160072157766 | 165588157766 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-22 | 2019-06-22 | 2019-07-13 |  | 2019-12-06 | Underground | R16 | 2019-08-08 | 0 | 15 | 19 | 87 | 120 | 2019 | 2019 | R16
163798198514 | 160459198514 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-28 | 2020-07-28 | 2020-07-28 |  | 2020-12-29 | Overhead | R16 | 2020-09-24 | 1 |  | 43 | 69 | 111 | 2020 | 2020 | R16
160145159094 | 161971159094 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-03 | 2019-06-03 | 2019-07-26 |  | 2019-12-19 | Underground | R16 | 2019-12-10 | 1 | 40 | 98 | 8 | 144 | 2019 | 2019 | R16
160162158407 | 160916158407 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-19 | 2019-07-19 | 2019-07-19 |  | 2020-06-09 | Overhead | R16 | 2019-12-26 | 1 |  | 115 | 119 | 233 | 2019 | 2020 | R16
161279213824 | 160585213824 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-14 | 2020-12-14 | 2020-12-14 |  | 2021-04-21 | Overhead | R16 | 2021-02-17 | 1 |  | 48 | 46 | 93 | 2020 | 2021 | R16
168983142927 | 161869142927 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-02-07 | 2019-02-07 | 2019-02-11 | 2020-04-23 | 2020-07-01 | Underground | R16 | 2020-04-23 | 1 | 3 | 314 | 50 | 365 | 2019 | 2020 | R16
160186155740 | 164916155740 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-18 | 2019-06-18 | 2019-06-18 |  | 2019-08-28 | Overhead | R16 | 2019-08-20 | 1 |  | 46 | 7 | 52 | 2019 | 2019 | R16
160187159335 | 169838159335 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-15 | 2019-07-15 | 2019-07-30 |  | 2019-09-11 | Underground | R16 | 2019-09-04 | 1 | 12 | 27 | 6 | 43 | 2019 | 2019 | R16
165500147745 | 160961147745 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-01 | 2019-04-01 | 2019-04-01 | 2019-05-01 | 2019-05-28 | Overhead | R16 | 2019-05-01 | 1 |  | 23 | 20 | 42 | 2019 | 2019 | R16
160655209668 | 162841209668 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-04 | 2020-11-04 | 2020-11-04 |  | 2021-07-12 | Overhead | R16 | 2020-11-24 | 1 |  | 15 | 165 | 179 | 2020 | 2021 | R16
168274213446 | 167285213446 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-11-25 | 2020-11-25 | 2020-12-10 | 2021-02-10 | 2022-02-07 | Overhead | R16 | 2021-02-10 | 1 | 12 | 45 | 259 | 314 | 2020 | 2022 | R16
160218156555 | 166613156555 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-28 | 2019-06-28 | 2019-06-28 |  | 2019-10-28 | Overhead | R16 | 2019-10-16 | 1 |  | 79 | 9 | 87 | 2019 | 2019 | R16
168028247584 | 168082247584 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2021-05-18 | 2021-06-02 | 2021-09-13 |  | 2023-10-02 | Underground | R16 |  | 12 | 74 |  |  | 620 | 2021 | 2023 | R16
163061146388 | 163578146388 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-02-14 | 2019-02-14 | 2019-03-18 | 2019-11-08 | 2019-11-19 | Underground | R16 | 2019-11-08 | 1 | 23 | 170 | 8 | 199 | 2019 | 2019 | R16
160262161220 | 166452161220 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-27 | 2019-06-27 | 2019-08-14 |  | 2023-06-08 | Underground | R16 | 2019-12-18 | 1 | 35 | 91 | 907 | 1031 | 2019 | 2023 | R16
165694147423 | 160230147423 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-27 | 2019-03-27 | 2019-03-27 | 2019-04-23 | 2019-04-26 | Overhead | R16 | 2019-04-23 | 1 |  | 20 | 4 | 23 | 2019 | 2019 | R16
160318160884 | 161436160884 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-30 | 2019-05-30 | 2019-08-12 |  | 2021-11-09 | Underground | R16 | 2020-11-16 | 1 | 53 | 331 | 257 | 639 | 2019 | 2021 | R16
166815222668 | 166784222668 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-08 | 2020-10-08 | 2021-03-05 | 2021-11-11 | 2021-11-13 | Underground | R16 | 2021-11-11 | 1 | 107 | 180 | 2 | 287 | 2020 | 2021 | R16
164379140970 | 166634140970 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-10 | 2019-01-10 | 2019-01-22 | 2019-08-04 | 2019-12-06 | Underground | R16 | 2019-08-04 | 1 | 9 | 139 | 90 | 237 | 2019 | 2019 | R16
166148218859 | 160901218859 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-29 | 2021-01-29 | 2021-01-29 | 2021-03-12 | 2021-11-08 | Overhead | R16 | 2021-03-12 | 1 |  | 31 | 172 | 202 | 2021 | 2021 | R16
166414177089 | 167710177089 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-05-07 | 2019-05-07 | 2020-01-15 | 2021-06-16 | 2023-04-17 | Underground | R16 | 2021-06-16 | 1 | 182 | 371 | 479 | 1030 | 2019 | 2023 | R16
160354168525 | 160875168525 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-19 | 2019-07-19 | 2019-10-17 |  | 2020-06-09 | Underground | R16 | 2020-03-25 | 1 | 65 | 115 | 55 | 233 | 2019 | 2020 | R16
161473233742 | 164441233742 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-05-10 | 2021-05-10 | 2021-06-05 | 2021-08-09 | 2021-08-10 | Underground | R16 | 2021-08-09 | 1 | 20 | 46 | 2 | 67 | 2021 | 2021 | R16
160795232768 | 162766232768 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-04 | 2021-05-04 | 2021-05-28 |  | 2021-10-25 | Underground | R16 | 2021-09-08 | 1 | 19 | 74 | 34 | 125 | 2021 | 2021 | R16
160130200139 | 162647200139 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-10 | 2020-08-10 | 2020-08-10 |  | 2020-12-18 | Underground | R16 | 2020-09-23 | 1 |  | 33 | 63 | 95 | 2020 | 2020 | R16
160379163837 | 162036163837 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-25 | 2019-07-25 | 2019-09-10 |  | 2020-06-09 | Underground | R16 | 2020-04-01 | 1 | 34 | 147 | 50 | 229 | 2019 | 2020 | R16
163437222253 | 164330222253 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-15 | 2021-03-03 | 2021-03-03 | 2021-04-09 | 2021-11-05 | Overhead | R16 | 2021-04-09 | 13 |  | 28 | 151 | 190 | 2021 | 2021 | R16
160600212597 | 162212212597 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-02 | 2020-11-02 | 2020-12-03 | 2021-01-20 | 2021-04-21 | Underground | R16 | 2021-01-20 | 1 | 24 | 35 | 66 | 123 | 2020 | 2021 | R16
166791144302 | 165003144302 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-25 | 2019-02-25 | 2019-02-25 | 2019-03-26 | 2019-08-16 | Overhead | R16 | 2019-03-26 | 1 |  | 22 | 104 | 125 | 2019 | 2019 | R16
168375216688 | 169442216688 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-08 | 2020-12-08 | 2021-01-08 |  | 2022-06-01 | Underground | R16 | 2021-03-30 | 1 | 24 | 58 | 307 | 387 | 2020 | 2022 | R16
160414175051 | 161710175051 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-24 | 2019-07-24 | 2019-12-23 |  | 2021-07-26 | Underground | R16 | 2020-11-05 | 1 | 109 | 229 | 188 | 524 | 2019 | 2021 | R16
163485191855 | 163486191855 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-02-13 | 2020-01-22 | 2020-05-22 | 2021-03-18 | 2021-05-17 | Underground | R16 | 2021-03-18 | 246 | 88 | 215 | 43 | 589 | 2019 | 2021 | R16
160422155560 | 160569155560 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-23 | 2019-05-23 | 2019-06-17 |  | 2019-08-26 | Overhead | R16 | 2019-07-24 | 1 | 18 | 28 | 24 | 68 | 2019 | 2019 | R16
160046218308 | 169323218308 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-25 | 2021-01-25 | 2021-01-25 |  | 2022-08-25 | Overhead | R16 | 2022-08-24 | 1 |  | 413 | 2 | 414 | 2021 | 2022 | R16
168830148985 | 162846148985 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-04-10 | 2019-04-10 | 2019-04-11 | 2019-05-01 | 2019-05-01 | Overhead | R16 | 2019-05-01 | 1 | 2 | 15 |  | 16 | 2019 | 2019 | R16
160432158938 | 162210158938 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-07-26 | 2019-07-26 | 2019-07-26 |  | 2020-06-09 | Overhead | R16 | 2020-04-01 | 1 |  | 179 | 50 | 228 | 2019 | 2020 | R16
163611198355 | 160162198355 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-25 | 2020-07-25 | 2020-07-25 | 2020-08-06 | 2020-10-06 | Overhead | R16 | 2020-08-06 | 0 |  | 9 | 44 | 52 | 2020 | 2020 | R16
168889152670 | 168003152670 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-05-08 | 2019-05-08 | 2019-05-17 | 2020-05-27 | 2020-05-28 | Underground | R16 | 2020-05-27 | 1 | 8 | 269 | 2 | 277 | 2019 | 2020 | R16
160501171652 | 162403171652 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-05 | 2019-06-05 | 2019-11-13 |  | 2020-06-09 | Underground | R16 | 2020-02-24 | 1 | 116 | 74 | 77 | 265 | 2019 | 2020 | R16
163129259197 | 163879259197 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-30 | 2021-10-07 | 2021-11-30 |  | 2022-06-06 | Underground | R16 | 2022-05-09 | 202 | 39 | 115 | 21 | 374 | 2020 | 2022 | R16
168058226722 | 169306226722 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-09 | 2021-03-09 | 2021-04-13 |  | 2021-10-25 | Underground | R16 | 2021-07-28 | 1 | 26 | 77 | 64 | 165 | 2021 | 2021 | R16
160508157345 | 168762157345 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-08 | 2019-07-08 | 2019-07-08 |  | 2020-07-09 | Overhead | R16 | 2020-05-28 | 1 |  | 234 | 31 | 264 | 2019 | 2020 | R16
167214142175 | 161274142175 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-04 | 2019-02-04 | 2019-02-05 | 2019-02-22 | 2019-03-21 | Overhead | R16 | 2019-02-22 | 1 | 2 | 14 | 20 | 34 | 2019 | 2019 | R16
160509160785 | 164773160785 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-10 | 2019-08-10 | 2019-08-10 |  | 2019-09-19 | Overhead | R16 | 2019-09-11 | 0 |  | 23 | 7 | 29 | 2019 | 2019 | R16
166028150500 | 165776150500 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-26 | 2019-04-26 | 2019-04-26 | 2019-09-25 | 2023-06-08 | Overhead | R16 | 2019-09-25 | 1 |  | 109 | 967 | 1075 | 2019 | 2023 | R16
160553154390 | 162500154390 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-05 | 2019-06-05 | 2019-06-05 |  | 2019-11-21 | Underground | R16 | 2019-11-13 | 1 |  | 116 | 7 | 122 | 2019 | 2019 | R16
161859233495 | 165748233495 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-05 | 2021-06-04 | 2021-06-04 | 2021-07-28 | 2021-08-23 | Overhead | R16 | 2021-07-28 | 45 |  | 39 | 19 | 101 | 2021 | 2021 | R16
160555155258 | 164170155258 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-14 | 2019-06-14 | 2019-06-14 |  | 2019-08-26 | Overhead | R16 | 2019-07-11 | 1 |  | 20 | 33 | 52 | 2019 | 2019 | R16
160559156125 | 160909156125 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-24 | 2019-05-24 | 2019-06-24 |  | 2019-08-26 | Underground | R16 | 2019-07-24 | 1 | 22 | 23 | 24 | 67 | 2019 | 2019 | R16
168636148315 | 160174148315 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-27 | 2019-03-27 | 2019-04-05 | 2019-04-30 | 2019-06-07 | Underground | R16 | 2019-04-30 | 1 | 8 | 18 | 29 | 53 | 2019 | 2019 | R16
160560157200 | 166783157200 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-28 | 2019-06-28 | 2019-07-05 |  | 2019-08-26 | Underground | R16 | 2019-07-25 | 1 | 6 | 15 | 23 | 42 | 2019 | 2019 | R16
160570160061 | 162963160061 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-10 | 2019-08-05 | 2019-08-05 |  | 2019-10-28 | Overhead | R16 | 2019-10-16 | 41 |  | 53 | 9 | 101 | 2019 | 2019 | R16
167019200311 | 163297200311 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-12 | 2020-08-12 | 2020-08-12 | 2020-08-21 | 2020-08-27 | Underground | R16 | 2020-08-21 | 1 |  | 8 | 5 | 12 | 2020 | 2020 | R16
169599208055 | 163476208055 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-25 | 2020-09-25 | 2020-10-23 |  | 2021-11-04 | Underground | R16 | 2021-04-05 | 1 | 21 | 117 | 154 | 290 | 2020 | 2021 | R16
160591157144 | 168353157144 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-05 | 2019-07-05 | 2019-07-05 |  | 2019-09-10 | Overhead | R16 | 2019-09-03 | 1 |  | 43 | 6 | 48 | 2019 | 2019 | R16
162704142392 | 161250142392 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-04 | 2019-02-06 | 2019-02-06 | 2019-02-27 | 2019-03-05 | Overhead | R16 | 2019-02-27 | 3 |  | 16 | 5 | 22 | 2019 | 2019 | R16
166001221125 | 167361221125 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-28 | 2020-08-28 | 2021-02-19 |  | 2021-11-08 | Underground | R16 | 2021-05-26 | 1 | 126 | 69 | 119 | 312 | 2020 | 2021 | R16
160635153498 | 161560153498 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-30 | 2019-05-30 | 2019-05-30 |  | 2019-08-26 | Overhead | R16 | 2019-07-16 | 1 |  | 34 | 30 | 63 | 2019 | 2019 | R16
160659158055 | 165945158055 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-25 | 2019-06-25 | 2019-07-16 |  | 2023-01-10 | Underground | R16 | 2022-11-03 | 1 | 16 | 863 | 49 | 926 | 2019 | 2023 | R16
161742205757 | 164872205757 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-09-30 | 2020-09-30 | 2020-09-30 | 2021-01-08 | 2021-04-20 | Overhead | R16 | 2021-01-08 | 1 |  | 73 | 73 | 145 | 2020 | 2021 | R16
160750156284 | 166044156284 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-25 | 2019-06-25 | 2019-06-25 |  | 2021-10-28 | Underground | R16 | 2021-07-30 | 1 |  | 549 | 65 | 613 | 2019 | 2021 | R16
162449216637 | 167575216637 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-30 | 2020-12-02 |  | 2021-01-08 | 2021-05-05 | Overhead | R16 | 2021-01-08 | 3 |  |  | 84 | 113 | 2020 | 2021 | R16
169328142993 | 169258142993 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-28 | 2019-01-28 | 2019-02-11 | 2019-03-07 | 2019-03-07 | Underground | R16 | 2019-03-07 | 1 | 11 | 19 |  | 29 | 2019 | 2019 | R16
165150204106 | 160043204106 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-09-10 | 2020-09-16 | 2020-09-17 |  | 2020-12-29 | Overhead | R16 | 2020-09-25 | 5 | 2 | 7 | 68 | 79 | 2020 | 2020 | R16
160863157053 | 167811157053 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-02 | 2019-07-02 | 2019-07-03 |  | 2020-06-23 | Underground | R16 | 2020-04-16 | 1 | 2 | 207 | 49 | 256 | 2019 | 2020 | R16
160647200556 | 163917200556 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-15 | 2020-08-15 | 2020-08-17 |  | 2021-04-14 | Underground | R16 | 2020-12-10 | 0 | 1 | 84 | 90 | 173 | 2020 | 2021 | R16
160885156282 | 166009156282 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-25 | 2019-06-25 | 2019-06-25 |  | 2021-09-14 | Underground | R16 | 2021-08-19 | 1 |  | 563 | 19 | 581 | 2019 | 2021 | R16
163066208908 | 161040208908 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-28 | 2020-10-28 | 2020-10-28 | 2021-01-16 | 2021-01-19 | Overhead | R16 | 2021-01-16 | 1 |  | 58 | 2 | 60 | 2020 | 2021 | R16
160915156803 | 165755156803 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-24 | 2019-06-24 | 2019-07-01 |  | 2021-11-13 | Underground | R16 | 2019-08-27 | 1 | 6 | 42 | 579 | 625 | 2019 | 2021 | R16
161908213646 | 160270213646 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-11 | 2020-12-11 | 2020-12-11 |  | 2021-04-29 | Overhead | R16 | 2021-02-11 | 1 |  | 45 | 56 | 100 | 2020 | 2021 | R16
161006155504 | 164335155504 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-17 | 2019-06-17 | 2019-06-17 |  | 2019-08-26 | Overhead | R16 | 2019-07-11 | 1 |  | 19 | 33 | 51 | 2019 | 2019 | R16
163153223035 | 161193223035 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-31 | 2021-03-10 | 2021-03-10 | 2021-03-17 | 2021-11-09 | Overhead | R16 | 2021-03-17 | 28 |  | 6 | 170 | 202 | 2021 | 2021 | R16
161009156256 | 165997156256 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-26 | 2019-06-26 | 2019-06-26 |  | 2019-11-15 | Overhead | R16 | 2019-08-09 | 1 |  | 33 | 71 | 103 | 2019 | 2019 | R16
167805211007 | 165364211007 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-17 | 2020-11-17 | 2020-11-17 |  | 2021-04-21 | Overhead | R16 | 2021-01-20 | 1 |  | 47 | 66 | 112 | 2020 | 2021 | R16
161068169161 | 168106169161 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-21 | 2019-10-21 | 2019-10-21 |  | 2021-11-09 | Overhead | R16 | 2019-12-18 | 1 |  | 43 | 495 | 537 | 2019 | 2021 | R16
164800209978 | 163725209978 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-09 | 2020-11-09 | 2020-11-09 |  | 2021-07-09 | Overhead | R16 | 2020-12-23 | 1 |  | 33 | 143 | 175 | 2020 | 2021 | R16
167955230686 | 169240230686 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2021-04-20 | 2021-05-13 | 2021-05-13 | 2021-05-19 | 2021-08-25 | Overhead | R16 | 2021-05-19 | 18 |  | 5 | 71 | 92 | 2021 | 2021 | R16
161318212954 | 169141212954 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-07 | 2020-12-07 | 2020-12-07 | 2021-01-29 | 2021-04-23 | Overhead | R16 | 2021-01-29 | 1 |  | 40 | 61 | 100 | 2020 | 2021 | R16
161109179874 | 168796179874 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2020-02-10 | 2020-02-10 | 2020-02-11 |  | 2022-08-29 | Underground | R16 |  | 1 | 2 |  |  | 666 | 2020 | 2022 | R16
162469152064 | 168391152064 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-10 | 2019-05-10 | 2019-05-10 | 2019-05-13 | 2019-08-12 | Overhead | R16 | 2019-05-13 | 1 |  | 2 | 66 | 67 | 2019 | 2019 | R16
164199140937 | 168413140937 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-03-12 | 2019-03-13 | Overhead | R16 | 2019-03-12 | 1 |  | 35 | 2 | 36 | 2019 | 2019 | R16
169990212299 | 168059212299 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-12-02 | 2020-12-02 | 2020-12-02 |  | 2021-08-11 | Underground | R16 | 2021-07-02 | 1 |  | 153 | 29 | 181 | 2020 | 2021 | R16
161076220170 | 161436220170 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-02 | 2021-02-02 | 2021-02-10 |  | 2021-11-05 | Underground | R16 | 2021-05-06 | 1 | 7 | 62 | 132 | 199 | 2021 | 2021 | R16
161130157013 | 168285157013 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-05 | 2019-07-05 | 2019-07-05 |  | 2019-08-26 | Overhead | R16 | 2019-07-15 | 1 |  | 7 | 31 | 37 | 2019 | 2019 | R16
161894229464 | 166977229464 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-09 | 2021-04-09 | 2021-05-04 |  | 2021-08-11 | Underground | R16 | 2021-06-29 | 1 | 18 | 41 | 32 | 89 | 2021 | 2021 | R16
162878145348 | 163714145348 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-14 | 2019-02-14 | 2019-03-08 | 2019-04-08 | 2019-04-09 | Underground | R16 | 2019-04-08 | 1 | 17 | 22 | 2 | 39 | 2019 | 2019 | R16
162985225217 | 162986225217 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-24 | 2021-03-24 | 2021-03-31 |  | 2021-08-26 | Overhead | R16 |  | 1 | 6 |  |  | 112 | 2021 | 2021 | R16
161166157230 | 161931157230 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-03 | 2019-06-03 | 2019-07-08 |  | 2019-12-06 | Underground | R16 | 2019-09-23 | 1 | 26 | 56 | 55 | 135 | 2019 | 2019 | R16
161167156754 | 167586156754 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-02 | 2019-07-02 | 2019-07-02 |  | 2019-08-28 | Overhead | R16 | 2019-08-21 | 1 |  | 37 | 6 | 42 | 2019 | 2019 | R16
161235169530 | 168172169530 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2019-08-28 | 2019-09-23 | 2019-10-24 |  | 2020-06-09 | Underground | R16 |  | 19 | 24 |  |  | 205 | 2019 | 2020 | R16
167203227779 | 162357227779 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-22 | 2021-03-22 | 2021-04-22 | 2021-11-29 | 2021-11-29 | Underground | R16 | 2021-11-29 | 1 | 24 | 158 |  | 181 | 2021 | 2021 | R16
167763149880 | 161800149880 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-04-04 | 2019-04-04 | 2019-04-22 | 2019-06-11 | 2019-06-12 | Underground | R16 | 2019-06-11 | 1 | 13 | 37 | 2 | 50 | 2019 | 2019 | R16
161576242355 | 161517242355 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-10-30 | 2020-10-30 | 2021-08-06 | 2022-04-19 | 2022-05-04 | Underground | R16 | 2022-04-19 | 1 | 201 | 183 | 12 | 394 | 2020 | 2022 | R16
161259155077 | 163572155077 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-12 | 2019-06-12 | 2019-06-13 |  | 2019-07-23 | Overhead | R16 | 2019-07-15 | 1 | 2 | 23 | 7 | 30 | 2019 | 2019 | R16
164924199264 | 160210199264 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2020-07-26 | 2020-07-31 | 2020-07-31 | 2022-03-15 | 2022-04-01 | Overhead | R16 | 2022-03-15 | 5 |  | 423 | 14 | 440 | 2020 | 2022 | R16
160473232526 | 169812232526 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-25 | 2021-05-26 | 2021-05-26 | 2022-01-03 | 2022-01-04 | Overhead | R16 | 2022-01-03 | 2 |  | 159 | 2 | 161 | 2021 | 2022 | R16
163561221134 | 169114221134 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-01-25 | 2021-02-19 | 2021-02-19 |  | 2022-01-14 | Underground | R16 | 2021-12-10 | 20 |  | 211 | 26 | 255 | 2021 | 2022 | R16
165906241029 | 160981241029 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-01 | 2021-06-04 | 2021-07-27 | 2021-08-20 | 2021-09-02 | Underground | R16 | 2021-08-20 | 4 | 38 | 19 | 10 | 68 | 2021 | 2021 | R16
161308155281 | 163639155281 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-13 | 2019-06-13 | 2019-06-13 |  | 2019-08-26 | Overhead | R16 | 2019-07-23 | 1 |  | 29 | 25 | 53 | 2019 | 2019 | R16
165009228223 | 169801228223 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2021-04-22 | 2021-04-23 | 2021-04-23 | 2021-07-06 | 2023-09-14 | Underground | R16 | 2021-07-06 | 2 |  | 53 | 573 | 626 | 2021 | 2023 | R16
165160229545 | 162891229545 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2021-05-04 | 2021-05-04 | 2021-05-04 |  | 2021-08-31 | Overhead | R16 | 2021-06-11 | 1 |  | 29 | 58 | 86 | 2021 | 2021 | R16
161972149902 | 161929149902 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-05 | 2019-04-05 | 2019-04-22 | 2019-06-14 | 2019-06-17 | Underground | R16 | 2019-06-14 | 1 | 12 | 40 | 2 | 52 | 2019 | 2019 | R16
161320161388 | 165312161388 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-06-20 | 2019-06-24 | 2019-08-16 |  | 2019-09-26 | Overhead | R16 |  | 3 | 40 |  |  | 71 | 2019 | 2019 | R16
168815211728 | 166628211728 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-23 | 2020-11-23 | 2020-11-23 |  | 2021-04-23 | Overhead | R16 | 2021-02-02 | 1 |  | 52 | 59 | 110 | 2020 | 2021 | R16
161320161389 | 165322161389 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-06-20 | 2019-06-24 | 2019-08-16 |  | 2019-09-03 | Overhead | R16 |  | 3 | 40 |  |  | 54 | 2019 | 2019 | R16
161320161390 | 165323161390 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-06-20 | 2019-06-24 | 2019-08-16 |  | 2019-09-03 | Overhead | R16 |  | 3 | 40 |  |  | 54 | 2019 | 2019 | R16
161320176812 | 166837176812 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-12-09 | 2020-01-06 | 2020-01-13 |  | 2021-04-20 | Underground | R16 |  | 21 | 6 |  |  | 357 | 2019 | 2021 | R16
169987231552 | 163022231552 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG R16 ELECTRIC RELOCATION UD | Commercial | 2020-11-05 | 2020-11-05 | 2021-05-20 | 2021-09-21 | 2022-09-16 | Underground | R16 | 2021-09-21 | 1 | 141 | 89 | 259 | 487 | 2020 | 2022 | R16
161320267627 | 166844267627 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-12-09 | 2020-01-06 | 2022-02-04 |  | 2022-03-14 | Underground | R16 |  | 21 | 545 |  |  | 591 | 2019 | 2022 | R16
161346160688 | 167793160688 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-02 | 2019-07-02 | 2019-08-10 |  | 2019-09-19 | Underground | R16 | 2019-09-11 | 1 | 29 | 23 | 7 | 58 | 2019 | 2019 | R16
169205214095 | 161187214095 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-16 | 2020-12-16 | 2020-12-16 |  | 2021-08-10 | Overhead | R16 | 2021-03-19 | 1 |  | 68 | 103 | 170 | 2020 | 2021 | R16
168936155593 | 169578155593 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-17 | 2019-05-28 | 2019-06-18 | 2019-07-19 | 2019-07-23 | Underground | R16 | 2019-07-19 | 8 | 16 | 24 | 3 | 48 | 2019 | 2019 | R16
166561144199 | 167673144199 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-01-16 | 2019-01-16 | 2019-02-26 | 2019-04-09 | 2019-09-11 | Underground | R16 | 2019-04-09 | 1 | 30 | 31 | 112 | 171 | 2019 | 2019 | R16
169793220964 | 160717220964 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-29 | 2021-01-29 | 2021-02-18 |  | 2021-11-05 | Underground | R16 | 2021-05-06 | 1 | 15 | 56 | 132 | 201 | 2021 | 2021 | R16
161399156558 | 166669156558 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-28 | 2019-06-28 | 2019-06-28 |  | 2019-09-26 | Overhead | R16 | 2019-09-18 | 1 |  | 59 | 7 | 65 | 2019 | 2019 | R16
166648226167 | 166416226167 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-07 | 2021-04-07 | 2021-04-07 | 2021-05-10 | 2021-08-23 | Overhead | R16 | 2021-05-10 | 1 |  | 24 | 76 | 99 | 2021 | 2021 | R16
161413169219 | 166399169219 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-12 | 2019-10-12 | 2019-10-25 |  | 2021-11-08 | Overhead | R16 |  | 0 | 10 |  |  | 541 | 2019 | 2021 | R16
162520208721 | 160476208721 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-10-26 | 2020-10-27 | 2020-10-27 |  | 2022-03-14 | Underground | R16 | 2022-02-23 | 2 |  | 347 | 14 | 361 | 2020 | 2022 | R16
166749220276 | 163307220276 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-12-28 | 2021-02-11 | 2021-02-11 | 2022-03-17 | 2022-03-24 | Underground | R16 | 2022-03-17 | 34 |  | 286 | 6 | 324 | 2020 | 2022 | R16
169164233301 | 169350233301 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2021-05-24 | 2021-05-24 | 2021-06-02 |  | 2023-08-23 | Underground | R16 |  | 1 | 8 |  |  | 588 | 2021 | 2023 | R16
160711144061 | 164825144061 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-22 | 2019-02-22 | 2019-02-22 | 2019-03-26 | 2019-03-26 | Overhead | R16 | 2019-03-26 | 1 |  | 23 |  | 23 | 2019 | 2019 | R16
161524157167 | 168108157167 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-03 | 2019-07-03 | 2019-07-08 |  | 2019-12-06 | Overhead | R16 | 2019-08-15 | 1 | 4 | 29 | 82 | 113 | 2019 | 2019 | R16
162079218290 | 161755218290 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-21 | 2021-01-25 | 2021-01-25 |  | 2021-11-08 | Underground | R16 | 2021-05-17 | 26 |  | 81 | 126 | 231 | 2020 | 2021 | R16
161528165898 | 169994165898 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-15 | 2019-07-15 | 2019-09-26 |  | 2020-01-03 | Underground | R16 | 2019-12-12 | 1 | 54 | 56 | 17 | 125 | 2019 | 2020 | R16
165148223157 | 169805223157 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-10 | 2021-03-10 | 2021-03-10 |  | 2021-11-05 | Overhead | R16 | 2021-05-05 | 1 |  | 41 | 133 | 173 | 2021 | 2021 | R16
160188205048 | 162391205048 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-07 | 2020-08-07 | 2020-09-25 | 2020-12-04 | 2020-12-07 | Underground | R16 | 2020-12-04 | 1 | 36 | 51 | 2 | 87 | 2020 | 2020 | R16
169946207020 | 167211207020 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-12 | 2020-10-12 | 2020-10-12 | 2021-01-13 | 2021-01-14 | Underground | R16 | 2021-01-13 | 1 |  | 68 | 2 | 69 | 2020 | 2021 | R16
163646151898 | 168320151898 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-05-10 | 2019-05-10 | 2019-05-10 | 2019-07-02 | 2023-06-07 | Overhead | R16 | 2019-07-02 | 1 |  | 38 | 1027 | 1064 | 2019 | 2023 | R16
165151161583 | 165144161583 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-23 | 2019-04-23 | 2019-08-19 | 2019-09-27 | 2019-09-30 | Underground | R16 | 2019-09-27 | 1 | 85 | 30 | 2 | 115 | 2019 | 2019 | R16
161536210106 | 163687210106 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-09 | 2020-11-09 | 2020-11-09 |  | 2021-04-15 | Overhead | R16 | 2020-12-28 | 1 |  | 36 | 79 | 114 | 2020 | 2021 | R16
169810212520 | 164647212520 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-13 | 2020-11-13 | 2020-12-02 |  | 2021-11-05 | Overhead | R16 |  | 1 | 14 |  |  | 256 | 2020 | 2021 | R16
165590204636 | 160303204636 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-07-27 | 2020-09-01 | 2020-09-22 | 2020-10-05 | 2022-03-23 | Underground | R16 | 2020-10-05 | 27 | 16 | 10 | 383 | 433 | 2020 | 2022 | R16
161676155989 | 165486155989 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-21 | 2019-06-21 | 2019-06-21 |  | 2020-06-09 | Underground | R16 | 2020-02-03 | 1 |  | 162 | 92 | 253 | 2019 | 2020 | R16
168806151662 | 167703151662 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-07 | 2019-05-07 | 2019-05-07 | 2019-06-17 | 2019-06-17 | Overhead | R16 | 2019-06-17 | 1 |  | 30 |  | 30 | 2019 | 2019 | R16
167292199516 | 161693199516 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-03 | 2020-08-04 | 2020-08-04 |  | 2021-07-26 | Overhead | R16 | 2020-11-03 | 2 |  | 66 | 190 | 256 | 2020 | 2021 | R16
161701207363 | 161193207363 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-22 | 2019-07-22 | 2020-10-14 |  | 2021-04-14 | Overhead | R16 |  | 1 | 323 |  |  | 453 | 2019 | 2021 | R16
161610227870 | 169583227870 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-21 | 2021-04-21 | 2021-04-21 | 2021-10-26 | 2021-12-01 | Overhead | R16 | 2021-10-26 | 1 |  | 135 | 27 | 161 | 2021 | 2021 | R16
161719156163 | 163588156163 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-13 | 2019-06-24 | 2019-06-24 |  | 2019-12-03 | Overhead | R16 | 2019-11-21 | 8 |  | 109 | 9 | 124 | 2019 | 2019 | R16
164341221392 | 161774221392 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-03 | 2021-02-03 | 2021-02-23 | 2021-05-10 | 2021-11-08 | Underground | R16 | 2021-05-10 | 1 | 15 | 55 | 131 | 199 | 2021 | 2021 | R16
161108205827 | 161533205827 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-09-17 | 2020-09-17 | 2020-09-30 | 2021-10-14 | 2021-11-30 | Underground | R16 | 2021-10-14 | 1 | 10 | 272 | 34 | 314 | 2020 | 2021 | R16
161728155079 | 163628155079 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-13 | 2019-06-13 | 2019-06-13 |  | 2019-08-26 | Overhead | R16 | 2019-07-18 | 1 |  | 26 | 28 | 53 | 2019 | 2019 | R16
167174217557 | 161232217557 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OD | Residential | 2020-12-16 | 2021-01-06 | 2021-01-15 |  | 2022-07-25 | Overhead | R16 |  | 16 | 8 |  |  | 419 | 2020 | 2022 | R16
160040225841 | 165348225841 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-02 | 2021-04-05 | 2021-04-05 | 2021-05-18 | 2021-11-08 | Overhead | R16 | 2021-05-18 | 2 |  | 32 | 125 | 157 | 2021 | 2021 | R16
162953147788 | 169570147788 | GENERAL/OTHER | R16 RESD AND NON RESD US | Commercial | 2019-03-22 | 2019-03-22 | 2019-04-02 | 2020-02-10 | 2020-06-09 | Underground | R16 | 2020-02-10 | 1 | 8 | 225 | 87 | 318 | 2019 | 2020 | R16
161782155289 | 163851155289 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-13 | 2019-06-13 | 2019-06-14 |  | 2019-09-03 | Underground | R16 | 2019-07-29 | 1 | 2 | 32 | 27 | 59 | 2019 | 2019 | R16
165460214286 | 166647214286 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-23 | 2020-11-24 | 2020-12-17 | 2021-04-01 | 2021-11-04 | Underground | R16 | 2021-04-01 | 2 | 18 | 76 | 156 | 249 | 2020 | 2021 | R16
168373272131 | 166767272131 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-09 | 2021-04-15 | 2022-03-11 |  | 2023-02-14 | Overhead | R16 | 2023-01-31 | 5 | 237 | 233 | 11 | 483 | 2021 | 2023 | R16
161054171697 | 162933171697 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-02-12 | 2019-08-28 | 2019-11-13 | 2020-11-11 | 2021-01-21 | Underground | R16 | 2020-11-11 | 142 | 56 | 261 | 52 | 508 | 2019 | 2021 | R16
161801169320 | 167763169320 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-02 | 2019-07-02 | 2019-10-23 |  | 2019-12-18 | Underground | R16 | 2019-12-09 | 1 | 82 | 34 | 8 | 122 | 2019 | 2019 | R16
166692235953 | 160711235953 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-14 | 2020-12-14 | 2021-06-21 | 2021-10-15 | 2021-10-18 | Underground | R16 | 2021-10-15 | 1 | 136 | 85 | 2 | 221 | 2020 | 2021 | R16
161812157602 | 168755157602 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-08 | 2019-07-08 | 2019-07-10 |  | 2019-11-14 | Overhead | R16 | 2019-10-31 | 1 | 3 | 82 | 11 | 94 | 2019 | 2019 | R16
168846237064 | 163701237064 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-06 | 2021-05-06 | 2021-06-28 |  | 2021-11-13 | Underground | R16 | 2021-10-22 | 1 | 38 | 85 | 16 | 137 | 2021 | 2021 | R16
161869155287 | 163833155287 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-13 | 2019-06-13 | 2019-06-13 |  | 2019-08-26 | Overhead | R16 | 2019-07-23 | 1 |  | 29 | 25 | 53 | 2019 | 2019 | R16
165060232946 | 160920232946 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-06-01 | 2021-06-01 | 2021-06-01 |  | 2021-08-12 | Overhead | R16 | 2021-07-08 | 1 |  | 28 | 26 | 53 | 2021 | 2021 | R16
161877159789 | 163184159789 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-01 | 2019-08-01 | 2019-08-01 |  | 2019-09-10 | Overhead | R16 | 2019-09-03 | 1 |  | 24 | 6 | 29 | 2019 | 2019 | R16
161929160400 | 164131160400 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-08-06 | 2019-08-06 | 2019-08-06 |  | 2019-08-28 | Overhead | R16 | 2019-08-21 | 1 |  | 12 | 6 | 17 | 2019 | 2019 | R16
163845205989 | 161688205989 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-18 | 2020-09-18 | 2020-10-01 |  | 2021-04-15 | Overhead | R16 | 2020-12-21 | 1 | 10 | 58 | 84 | 150 | 2020 | 2021 | R16
160876236195 | 168065236195 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-19 | 2021-05-20 | 2021-06-23 | 2021-08-16 | 2021-08-18 | Overhead | R16 | 2021-08-16 | 2 | 25 | 39 | 3 | 66 | 2021 | 2021 | R16
169267198818 | 160022198818 | NON-RESIDENTIAL - SMALL RETAIL | OH R16 RES NON RES OS | Residential | 2020-07-24 | 2020-07-24 | 2020-07-29 |  | 2020-10-06 | Overhead | R16 |  | 1 | 4 |  |  | 53 | 2020 | 2020 | R16
161984158782 | 164963158782 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-18 | 2019-06-18 | 2019-07-23 |  | 2019-12-06 | Underground | R16 | 2019-08-14 | 1 | 26 | 17 | 83 | 124 | 2019 | 2019 | R16
164146199991 | 162646199991 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-09 | 2020-08-09 | 2020-08-09 |  | 2020-10-06 | Overhead | R16 | 2020-08-27 | 0 |  | 14 | 29 | 42 | 2020 | 2020 | R16
161987157610 | 163007157610 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-10 | 2019-06-10 | 2019-07-11 |  | 2019-09-26 | Underground | R16 | 2019-09-20 | 1 | 24 | 52 | 5 | 79 | 2019 | 2019 | R16
161639150428 | 165824150428 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-27 | 2019-04-27 | 2019-04-27 | 2019-05-17 | 2019-08-12 | Overhead | R16 | 2019-05-17 | 0 |  | 15 | 62 | 76 | 2019 | 2019 | R16
162022154194 | 162035154194 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-06-03 | 2019-06-03 | 2019-06-03 |  | 2022-07-15 | Overhead | R16 |  | 1 |  |  |  | 815 | 2019 | 2022 | R16
163488210970 | 165425210970 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-17 | 2020-11-17 | 2020-11-17 | 2020-12-31 | 2021-04-16 | Underground | R16 | 2020-12-31 | 1 |  | 33 | 77 | 109 | 2020 | 2021 | R16
160019154511 | 163960154511 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-04-17 | 2019-05-29 | 2019-06-06 | 2020-07-09 | 2020-10-06 | Underground | R16 | 2020-07-09 | 31 | 7 | 286 | 64 | 385 | 2019 | 2020 | R16
167347221741 | 166652221741 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-25 | 2021-02-25 | 2021-02-25 |  | 2021-11-05 | Overhead | R16 | 2021-04-14 | 1 |  | 35 | 148 | 182 | 2021 | 2021 | R16
162045160323 | 161708160323 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-07-24 | 2019-07-24 | 2019-08-06 |  | 2020-06-09 | Underground | R16 |  | 1 | 10 |  |  | 230 | 2019 | 2020 | R16
168194143830 | 162720143830 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-11 | 2019-02-11 | 2019-02-21 | 2019-03-12 | 2019-04-15 | Underground | R16 | 2019-03-12 | 1 | 9 | 14 | 25 | 46 | 2019 | 2019 | R16
167907150639 | 162426150639 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-08 | 2019-04-08 | 2019-04-30 | 2019-07-30 | 2019-09-03 | Underground | R16 | 2019-07-30 | 1 | 17 | 66 | 26 | 107 | 2019 | 2019 | R16
162057159790 | 163229159790 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-01 | 2019-08-01 | 2019-08-01 |  | 2019-09-18 | Overhead | R16 | 2019-09-10 | 1 |  | 29 | 7 | 35 | 2019 | 2019 | R16
166488246985 | 167094246985 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-02-26 | 2021-05-21 | 2021-09-08 | 2022-09-20 | 2023-02-03 | Overhead | R16 | 2022-09-20 | 61 | 79 | 270 | 99 | 506 | 2021 | 2023 | R16
162156161661 | 165039161661 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-06-19 | 2019-06-19 | 2019-08-19 |  | 2019-11-27 | Underground | R16 |  | 1 | 44 |  |  | 116 | 2019 | 2019 | R16
162157159086 | 162151159086 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-25 | 2019-07-25 | 2019-07-25 |  | 2019-10-18 | Overhead | R16 | 2019-10-08 | 1 |  | 54 | 9 | 62 | 2019 | 2019 | R16
165142227916 | 169981227916 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-26 | 2021-11-04 | Overhead | R16 | 2021-04-26 | 1 |  | 3 | 139 | 141 | 2021 | 2021 | R16
161127241069 | 165922241069 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-06 | 2021-05-04 | 2021-07-28 | 2022-01-18 | 2022-02-22 | Underground | R16 | 2022-01-18 | 21 | 62 | 125 | 26 | 231 | 2021 | 2022 | R16
169887174944 | 162387174944 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-05 | 2019-06-05 | 2019-12-19 | 2020-04-23 | 2021-06-30 | Underground | R16 | 2020-04-23 | 1 | 142 | 91 | 310 | 541 | 2019 | 2021 | R16
168727244232 | 166478244232 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-08-25 | 2021-01-28 | 2021-08-18 | 2023-05-11 | 2023-07-18 | Underground | R16 | 2023-05-11 | 113 | 145 | 452 | 49 | 756 | 2020 | 2023 | R16
168081199282 | 161261199282 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-31 | 2020-07-31 | 2020-07-31 | 2020-09-17 | 2020-09-18 | Overhead | R16 | 2020-09-17 | 1 |  | 35 | 2 | 36 | 2020 | 2020 | R16
160197232928 | 163482232928 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-05-06 | 2021-05-06 | 2021-06-01 |  | 2023-08-17 | Underground | R16 | 2023-05-09 | 1 | 19 | 506 | 73 | 596 | 2021 | 2023 | R16
162241231816 | 162670231816 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2019-09-24 | 2019-10-26 | 2021-05-20 |  | 2021-11-03 | Overhead | R16 |  | 24 | 409 |  |  | 552 | 2019 | 2021 | R16
161914227921 | 161372227921 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Residential | 2020-09-16 | 2021-01-26 | 2021-04-21 | 2021-06-24 | 2021-07-13 | Underground | R16 | 2021-06-24 | 95 | 62 | 47 | 14 | 215 | 2020 | 2021 | R16
162241180254 | 162671180254 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-09-24 | 2020-01-15 | 2020-02-13 |  | 2020-06-09 | Overhead | R16 |  | 82 | 22 |  |  | 186 | 2019 | 2020 | R16
162550229439 | 163032229439 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2021-05-05 | 2021-05-05 | 2021-05-05 |  | 2022-02-22 | Overhead | R16 | 2022-01-21 | 1 |  | 188 | 23 | 210 | 2021 | 2022 | R16
166964221370 | 164167221370 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-12 | 2021-02-23 | 2021-02-23 |  | 2021-08-03 | Underground | R16 | 2021-03-29 | 8 |  | 25 | 92 | 123 | 2021 | 2021 | R16
162269161155 | 165722161155 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2019-08-15 | 2019-08-15 | 2019-08-15 |  | 2020-06-09 | Overhead | R16 | 2020-03-11 | 1 |  | 150 | 65 | 214 | 2019 | 2020 | R16
162281158411 | 160994158411 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-19 | 2019-07-19 | 2019-07-19 |  | 2019-12-06 | Overhead | R16 | 2019-08-27 | 1 |  | 28 | 74 | 101 | 2019 | 2019 | R16
164897227068 | 168401227068 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-15 | 2021-04-15 | 2021-04-15 | 2021-05-26 | 2021-11-08 | Overhead | R16 | 2021-05-26 | 1 |  | 30 | 119 | 148 | 2021 | 2021 | R16
164706217747 | 166863217747 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-13 | 2021-01-14 | 2021-01-20 |  | 2021-11-04 | Underground | R16 | 2021-04-05 | 2 | 5 | 54 | 154 | 212 | 2021 | 2021 | R16
162358159643 | 162902159643 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-30 | 2019-07-30 | 2019-07-30 |  | 2019-09-03 | Overhead | R16 | 2019-08-26 | 1 |  | 20 | 7 | 26 | 2019 | 2019 | R16
168115216536 | 165298216536 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-06 | 2021-01-07 | 2021-01-07 | 2021-03-23 | 2021-04-12 | Overhead | R16 | 2021-03-23 | 2 |  | 54 | 15 | 69 | 2021 | 2021 | R16
162425160891 | 163290160891 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-11 | 2019-06-11 | 2019-08-12 |  | 2020-07-07 | Underground | R16 | 2020-05-07 | 1 | 45 | 194 | 44 | 281 | 2019 | 2020 | R16
163391215330 | 169121215330 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-07 | 2020-12-22 | 2020-12-22 | 2021-01-12 | 2023-06-02 | Overhead | R16 | 2021-01-12 | 12 |  | 16 | 624 | 650 | 2020 | 2023 | R16
162475157168 | 163304157168 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-11 | 2019-06-11 | 2019-07-08 |  | 2023-08-29 | Underground | R16 | 2023-08-23 | 1 | 20 | 1078 | 5 | 1101 | 2019 | 2023 | R16
168584221305 | 160528221305 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-09-11 | 2021-02-22 | 2021-02-22 | 2022-08-04 | 2022-08-08 | Underground | R16 | 2022-08-04 | 117 |  | 379 | 3 | 497 | 2020 | 2022 | R16
160795212185 | 167319212185 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-25 | 2020-11-25 | 2020-11-25 | 2020-12-21 | 2021-04-22 | Underground | R16 | 2020-12-21 | 1 |  | 19 | 89 | 107 | 2020 | 2021 | R16
162477158500 | 163295158500 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-11 | 2019-06-11 | 2019-07-19 |  | 2023-06-22 | Underground | R16 | 2023-04-04 | 1 | 29 | 968 | 58 | 1053 | 2019 | 2023 | R16
165552226258 | 164157226258 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-14 | 2021-02-14 | 2021-04-09 |  | 2021-11-04 | Underground | R16 | 2021-06-02 | 0 | 40 | 39 | 112 | 189 | 2021 | 2021 | R16
162479156259 | 166197156259 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-26 | 2019-06-26 | 2019-06-26 |  | 2019-08-26 | Overhead | R16 | 2019-07-22 | 1 |  | 19 | 26 | 44 | 2019 | 2019 | R16
167348236523 | 166838236523 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2021-05-18 | 2021-05-18 | 2021-06-24 | 2021-07-28 | 2022-03-23 | Underground | R16 | 2021-07-28 | 1 | 28 | 25 | 171 | 222 | 2021 | 2022 | R16
161846211414 | 164290211414 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-28 | 2020-10-06 | 2020-11-21 | 2021-01-22 | 2021-03-01 | Underground | R16 | 2021-01-22 | 7 | 34 | 45 | 27 | 111 | 2020 | 2021 | R16
168392207003 | 166226207003 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-06 | 2020-10-06 | 2020-10-12 | 2020-10-26 | 2021-04-07 | Underground | R16 | 2020-10-26 | 1 | 5 | 11 | 118 | 132 | 2020 | 2021 | R16
162566160150 | 161542160150 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-07-23 | 2019-07-23 | 2019-08-05 |  | 2020-06-09 | Underground | R16 | 2020-02-12 | 1 | 10 | 138 | 85 | 231 | 2019 | 2020 | R16
169331218936 | 167568218936 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-01-15 | 2021-01-15 | 2021-01-29 |  | 2021-04-23 | Overhead | R16 |  | 1 | 11 |  |  | 71 | 2021 | 2021 | R16
162571168345 | 167196168345 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2019-10-16 | 2019-10-16 | 2019-10-16 |  | 2020-01-08 | Overhead | R16 | 2020-01-03 | 1 |  | 58 | 4 | 61 | 2019 | 2020 | R16
167275154523 | 167280154523 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-03-08 | 2019-03-08 | 2019-06-05 | 2019-08-13 | 2019-08-16 | Underground | R16 | 2019-08-13 | 1 | 64 | 50 | 4 | 116 | 2019 | 2019 | R16
167952256054 | 164295256054 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-16 | 2021-11-10 | 2021-11-10 |  | 2022-04-26 | Underground | R16 | 2022-04-05 | 192 |  | 105 | 16 | 311 | 2021 | 2022 | R16
162614158781 | 164960158781 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-18 | 2019-06-18 | 2019-07-23 |  | 2019-10-11 | Underground | R16 | 2019-10-01 | 1 | 26 | 51 | 9 | 84 | 2019 | 2019 | R16
163208148124 | 168594148124 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-01-23 | 2019-01-28 | 2019-04-03 | 2019-11-14 | 2019-11-15 | Underground | R16 | 2019-11-14 | 4 | 48 | 162 | 2 | 213 | 2019 | 2019 | R16
167750139450 | 165750139450 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-07 | 2019-01-07 | 2019-01-07 | 2019-03-04 | 2019-03-07 | Overhead | R16 | 2019-03-04 | 1 |  | 41 | 4 | 44 | 2019 | 2019 | R16
160593226454 | 166920226454 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-09 | 2021-04-12 | 2021-04-12 | 2021-05-27 | 2021-11-04 | Overhead | R16 | 2021-05-27 | 2 |  | 34 | 116 | 150 | 2021 | 2021 | R16
165333209260 | 166435209260 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-07 | 2020-10-07 | 2020-10-30 |  | 2021-07-14 | Underground | R16 | 2020-11-23 | 1 | 18 | 17 | 168 | 201 | 2020 | 2021 | R16
162628156583 | 166570156583 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-27 | 2019-06-27 | 2019-06-27 |  | 2019-12-09 | Overhead | R16 | 2019-08-22 | 1 |  | 41 | 78 | 118 | 2019 | 2019 | R16
166837210915 | 164880210915 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-13 | 2020-11-17 | 2020-11-17 |  | 2021-04-16 | Overhead | R16 | 2021-01-07 | 3 |  | 38 | 72 | 111 | 2020 | 2021 | R16
162631158195 | 160804158195 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-18 | 2019-07-18 | 2019-07-18 |  | 2019-12-19 | Overhead | R16 | 2019-10-29 | 1 |  | 74 | 38 | 111 | 2019 | 2019 | R16
169692225427 | 164845225427 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-31 | 2021-03-31 | 2021-03-31 |  | 2021-11-08 | Overhead | R16 | 2021-05-13 | 1 |  | 32 | 128 | 159 | 2021 | 2021 | R16
164790140697 | 168045140697 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-18 | 2019-01-18 | 2019-01-18 | 2021-03-30 | 2021-03-31 | Overhead | R16 | 2021-03-30 | 1 |  | 573 | 2 | 574 | 2019 | 2021 | R16
162722156940 | 167487156940 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-07-01 | 2019-07-01 | 2019-07-01 |  | 2020-01-08 | Underground | R16 | 2019-12-31 | 1 |  | 132 | 7 | 138 | 2019 | 2020 | R16
160015180086 | 162438180086 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-06-05 | 2019-11-21 | 2020-02-11 |  | 2021-04-29 | Underground | R16 |  | 122 | 59 |  |  | 497 | 2019 | 2021 | R16
162758170186 | 164309170186 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-17 | 2019-06-17 | 2019-10-30 |  | 2020-06-09 | Underground | R16 | 2020-03-03 | 1 | 98 | 90 | 71 | 257 | 2019 | 2020 | R16
160537226252 | 162768226252 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-23 | 2021-03-26 | 2021-04-08 | 2021-09-05 | 2021-09-08 | Underground | R16 | 2021-09-05 | 4 | 10 | 107 | 3 | 122 | 2021 | 2021 | R16
162782157023 | 167588157023 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-02 | 2019-07-02 | 2019-07-02 |  | 2019-08-26 | Overhead | R16 | 2019-07-12 | 1 |  | 9 | 32 | 40 | 2019 | 2019 | R16
168560215610 | 163580215610 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-28 | 2020-12-28 | 2020-12-28 | 2020-12-31 | 2021-04-23 | Overhead | R16 | 2020-12-31 | 1 |  | 4 | 82 | 85 | 2020 | 2021 | R16
162787156591 | 166605156591 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-27 | 2019-06-27 | 2019-06-27 |  | 2019-09-03 | Overhead | R16 | 2019-08-26 | 1 |  | 43 | 7 | 49 | 2019 | 2019 | R16
166784204811 | 162824204811 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-23 | 2020-09-23 | 2020-09-23 | 2020-10-21 | 2021-07-07 | Overhead | R16 | 2020-10-21 | 1 |  | 21 | 186 | 206 | 2020 | 2021 | R16
161284223358 | 160394223358 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-12 | 2021-03-12 | 2021-03-12 |  | 2021-08-23 | Overhead | R16 | 2021-07-13 | 1 |  | 88 | 30 | 117 | 2021 | 2021 | R16
167053222985 | 169445222985 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-09 | 2021-03-09 | 2021-03-09 |  | 2022-10-18 | Overhead | R16 |  | 1 |  |  |  | 421 | 2021 | 2022 | R16
167147211618 | 166802211618 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-24 | 2020-11-24 | 2020-11-24 | 2020-12-01 | 2021-07-28 | Overhead | R16 | 2020-12-01 | 1 |  | 6 | 172 | 177 | 2020 | 2021 | R16
161384145254 | 167088145254 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-08 | 2019-03-08 | 2019-03-08 | 2019-06-04 | 2023-06-08 | Overhead | R16 | 2019-06-04 | 1 |  | 63 | 1048 | 1110 | 2019 | 2023 | R16
162846214088 | 165276214088 | NON-RESIDENTIAL - SMALL RETAIL | R16 RESD AND NON RESD US | Commercial | 2020-03-10 | 2020-10-06 | 2020-12-15 |  | 2021-08-30 | Underground | R16 |  | 151 | 51 |  |  | 385 | 2020 | 2021 | R16
161624222762 | 160413222762 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-28 | 2021-03-05 | 2021-03-05 | 2021-03-11 | 2021-11-13 | Overhead | R16 | 2021-03-11 | 27 |  | 5 | 177 | 207 | 2021 | 2021 | R16
168468230362 | 164677230362 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-08-19 | 2020-10-12 | 2021-05-11 | 2021-07-22 | 2021-08-25 | Underground | R16 | 2021-07-22 | 39 | 152 | 53 | 25 | 266 | 2020 | 2021 | R16
162864182177 | 163160182177 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-28 | 2020-02-28 | 2020-02-28 |  | 2021-09-13 | Underground | R16 | 2021-08-18 | 1 |  | 384 | 19 | 402 | 2020 | 2021 | R16
168814215342 | 162625215342 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-22 | 2020-12-22 | 2020-12-22 | 2021-02-08 | 2021-02-09 | Overhead | R16 | 2021-02-08 | 1 |  | 35 | 2 | 36 | 2020 | 2021 | R16
162865157322 | 163658157322 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-13 | 2019-06-13 | 2019-07-08 |  | 2019-09-03 | Underground | R16 | 2019-07-29 | 1 | 18 | 16 | 27 | 59 | 2019 | 2019 | R16
162886168505 | 163576168505 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-30 | 2019-09-30 | 2019-10-17 |  | 2023-12-11 | Underground | R16 | 2023-09-29 | 1 | 14 | 1032 | 52 | 1096 | 2019 | 2023 | R16
161886149949 | 164836149949 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-22 | 2019-04-22 | 2019-04-22 | 2019-05-06 | 2019-05-06 | Overhead | R16 | 2019-05-06 | 1 |  | 11 |  | 11 | 2019 | 2019 | R16
162887162599 | 165893162599 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-16 | 2019-08-16 | 2019-08-29 |  | 2022-04-12 | Underground | R16 | 2022-03-28 | 1 | 10 | 673 | 12 | 693 | 2019 | 2022 | R16
162168213578 | 160325213578 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-11 | 2020-12-11 | 2020-12-11 | 2021-02-24 | 2021-06-02 | Overhead | R16 | 2021-02-24 | 1 |  | 54 | 71 | 124 | 2020 | 2021 | R16
161177162712 | 161373162712 | NON-RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Commercial | 2019-02-05 | 2019-02-05 | 2019-08-29 | 2020-05-26 | 2021-11-23 | Underground | R16 | 2020-05-26 | 1 | 148 | 194 | 391 | 731 | 2019 | 2021 | R16
168546229895 | 163705229895 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-07 | 2021-05-07 | 2021-05-07 | 2021-06-15 | 2021-06-16 | Overhead | R16 | 2021-06-15 | 1 |  | 28 | 2 | 29 | 2021 | 2021 | R16
163027180047 | 165684180047 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2020-01-23 | 2020-01-23 | 2020-02-10 |  | 2020-08-28 | Underground | R16 |  | 1 | 13 |  |  | 157 | 2020 | 2020 | R16
163028157619 | 169445157619 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-11 | 2019-07-11 | 2019-07-11 |  | 2019-09-03 | Underground | R16 | 2019-07-31 | 1 |  | 15 | 25 | 39 | 2019 | 2019 | R16
165122202607 | 168204202607 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-02 | 2020-09-02 | 2020-09-02 | 2021-04-26 | 2021-11-05 | Overhead | R16 | 2021-04-26 | 1 |  | 169 | 140 | 308 | 2020 | 2021 | R16
169391249225 | 160827249225 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-16 | 2021-03-30 | 2021-09-23 | 2022-02-14 | 2022-03-11 | Underground | R16 | 2022-02-14 | 11 | 128 | 103 | 20 | 259 | 2021 | 2022 | R16
160392169265 | 160413169265 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-03-28 | 2019-10-07 | 2019-10-23 | 2020-11-11 | 2021-06-16 | Underground | R16 | 2020-11-11 | 138 | 13 | 276 | 156 | 580 | 2019 | 2021 | R16
163043160357 | 164363160357 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-07 | 2019-08-07 | 2019-08-07 |  | 2019-09-10 | Overhead | R16 | 2019-09-03 | 1 |  | 20 | 6 | 25 | 2019 | 2019 | R16
160357154286 | 161949154286 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-06-03 | 2019-06-03 | 2019-06-03 | 2019-09-12 | 2019-09-13 | Underground | R16 | 2019-09-12 | 1 |  | 74 | 2 | 75 | 2019 | 2019 | R16
164726222832 | 169016222832 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-08 | 2021-03-08 | 2021-03-08 | 2021-04-30 | 2021-11-05 | Overhead | R16 | 2021-04-30 | 1 |  | 40 | 136 | 175 | 2021 | 2021 | R16
161471204661 | 162453204661 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-22 | 2020-09-22 | 2020-09-22 | 2020-11-23 | 2021-04-07 | Overhead | R16 | 2020-11-23 | 1 |  | 45 | 98 | 142 | 2020 | 2021 | R16
163070183129 | 164114183129 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-06-14 | 2019-06-17 | 2020-03-06 |  | 2022-08-29 | Underground | R16 |  | 2 | 190 |  |  | 837 | 2019 | 2022 | R16
161018206149 | 165841206149 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-05 | 2020-10-05 | 2020-10-05 | 2021-06-25 | 2021-07-08 | Overhead | R16 | 2021-06-25 | 1 |  | 190 | 10 | 199 | 2020 | 2021 | R16
163073158554 | 167754158554 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-02 | 2019-07-02 | 2019-07-23 |  | 2019-12-06 | Overhead | R16 | 2019-08-14 | 1 | 16 | 17 | 83 | 114 | 2019 | 2019 | R16
161194229062 | 166114229062 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-06 | 2021-04-13 | 2021-04-30 |  | 2021-11-08 | Underground | R16 | 2021-05-26 | 6 | 14 | 19 | 119 | 155 | 2021 | 2021 | R16
167461146585 | 163127146585 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-13 | 2019-02-13 | 2019-03-19 | 2019-06-14 | 2019-06-17 | Underground | R16 | 2019-06-14 | 1 | 25 | 64 | 2 | 89 | 2019 | 2019 | R16
169540209172 | 169471209172 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-22 | 2020-07-22 | 2020-10-30 |  | 2021-04-07 | Underground | R16 | 2020-11-30 | 1 | 73 | 22 | 93 | 186 | 2020 | 2021 | R16
163109161641 | 169540161641 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-11 | 2019-07-11 | 2019-08-19 |  | 2021-11-10 | Underground | R16 | 2020-01-22 | 1 | 28 | 113 | 471 | 610 | 2019 | 2021 | R16
160282231252 | 163009231252 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-12-23 | 2021-04-22 | 2021-05-18 | 2021-11-30 | 2022-01-06 | Underground | R16 | 2021-11-30 | 87 | 19 | 141 | 28 | 272 | 2020 | 2022 | R16
160971215639 | 163319215639 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-29 | 2020-12-29 | 2020-12-29 | 2021-02-02 | 2021-02-03 | Overhead | R16 | 2021-02-02 | 1 |  | 26 | 2 | 27 | 2020 | 2021 | R16
160599200381 | 162988200381 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-11 | 2020-08-11 | 2020-08-11 | 2021-07-21 | 2021-09-13 | Underground | R16 | 2021-07-21 | 1 |  | 247 | 39 | 285 | 2020 | 2021 | R16
163224155156 | 163895155156 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-14 | 2019-06-14 | 2019-06-14 |  | 2019-12-30 | Overhead | R16 | 2019-12-26 | 1 |  | 140 | 3 | 142 | 2019 | 2019 | R16
163834233161 | 168201233161 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-19 | 2021-06-01 | 2021-06-01 |  | 2021-11-02 | Overhead | R16 | 2021-10-07 | 10 |  | 93 | 19 | 120 | 2021 | 2021 | R16
166126250998 | 161397250998 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-02-01 | 2021-02-12 | 2021-10-07 |  | 2022-07-19 | Underground | R16 |  | 10 | 170 |  |  | 382 | 2021 | 2022 | R16
164046219335 | 161105219335 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-31 | 2021-02-02 | 2021-02-02 | 2021-03-26 | 2021-11-08 | Overhead | R16 | 2021-03-26 | 2 |  | 39 | 162 | 201 | 2021 | 2021 | R16
161105207898 | 167357207898 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-12 | 2020-10-22 | 2020-10-22 | 2020-11-25 | 2021-04-14 | Overhead | R16 | 2020-11-25 | 9 |  | 25 | 101 | 133 | 2020 | 2021 | R16
163812226365 | 169397226365 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-09 | 2021-04-09 | 2021-04-09 | 2021-06-30 | 2021-08-12 | Overhead | R16 | 2021-06-30 | 24 |  | 59 | 32 | 113 | 2021 | 2021 | R16
163338170655 | 168654170655 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-10-23 | 2019-10-23 | 2019-11-05 |  | 2021-10-25 | Overhead | R16 | 2021-09-08 | 1 | 10 | 482 | 34 | 524 | 2019 | 2021 | R16
168491218991 | 160212218991 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-11 | 2020-12-11 | 2021-01-29 | 2021-06-01 | 2021-11-04 | Underground | R16 | 2021-06-01 | 1 | 36 | 88 | 113 | 235 | 2020 | 2021 | R16
163341159758 | 163003159758 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-31 | 2019-07-31 | 2019-08-02 |  | 2019-09-04 | Overhead | R16 | 2019-08-28 | 1 | 3 | 19 | 6 | 26 | 2019 | 2019 | R16
161386232067 | 165822232067 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-17 | 2021-05-24 | 2021-05-24 |  | 2021-11-03 | Overhead | R16 | 2021-06-23 | 6 |  | 23 | 96 | 123 | 2021 | 2021 | R16
163343159429 | 162899159429 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-31 | 2019-07-31 | 2019-07-31 |  | 2019-11-14 | Underground | R16 | 2019-11-13 | 1 |  | 76 | 2 | 77 | 2019 | 2019 | R16
165061220975 | 165188220975 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-05-26 | 2022-08-03 | Overhead | R16 | 2021-05-26 | 1 |  | 69 | 311 | 379 | 2021 | 2022 | R16
163345159404 | 160939159404 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-19 | 2019-07-22 | 2019-07-29 |  | 2021-07-14 | Overhead | R16 |  | 2 | 6 |  |  | 519 | 2019 | 2021 | R16
163346160563 | 160993160563 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-19 | 2019-07-19 | 2019-08-08 |  | 2019-10-28 | Underground | R16 | 2019-10-17 | 1 | 15 | 51 | 8 | 72 | 2019 | 2019 | R16
163365157304 | 164057157304 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-06-14 | 2019-07-03 | 2019-07-08 |  | 2021-07-01 | Underground | R16 |  | 14 | 4 |  |  | 535 | 2019 | 2021 | R16
167821154762 | 166251154762 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-30 | 2019-04-30 | 2019-06-07 | 2019-06-12 | 2020-02-25 | Overhead | R16 | 2019-06-12 | 1 | 29 | 4 | 185 | 216 | 2019 | 2020 | R16
160550232369 | 169815232369 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-25 | 2021-05-26 | 2021-05-26 |  | 2023-06-26 | Overhead | R16 | 2023-06-16 | 2 |  | 538 | 7 | 545 | 2021 | 2023 | R16
167617213612 | 160254213612 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-11 | 2020-12-11 | 2020-12-11 | 2021-08-26 | 2021-10-07 | Overhead | R16 | 2021-08-26 | 1 |  | 185 | 31 | 215 | 2020 | 2021 | R16
163462158048 | 160111158048 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-15 | 2019-07-15 | 2019-07-15 |  | 2019-09-03 | Overhead | R16 | 2019-07-29 | 1 |  | 11 | 27 | 37 | 2019 | 2019 | R16
161572223023 | 164876223023 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-05 | 2021-01-15 | 2021-03-09 | 2021-04-16 | 2021-04-20 | Underground | R16 | 2021-04-16 | 9 | 38 | 29 | 3 | 76 | 2021 | 2021 | R16
166203197504 | 168430197504 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-15 | 2020-07-15 | 2020-07-15 | 2020-07-31 | 2020-10-06 | Overhead | R16 | 2020-07-31 | 1 |  | 13 | 48 | 60 | 2020 | 2020 | R16
163490156646 | 166760156646 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-06-28 | 2019-06-28 | 2019-06-28 |  | 2020-06-09 | Overhead | R16 | 2020-02-06 | 1 |  | 160 | 89 | 248 | 2019 | 2020 | R16
161214218559 | 168431218559 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-20 | 2021-01-26 | 2021-01-27 |  | 2021-08-03 | Underground | R16 | 2021-03-31 | 5 | 2 | 46 | 90 | 140 | 2021 | 2021 | R16
160375202093 | 160425202093 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-27 | 2020-07-27 | 2020-08-27 |  | 2022-10-20 | Underground | R16 |  | 1 | 24 |  |  | 584 | 2020 | 2022 | R16
163532157140 | 164423157140 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-17 | 2019-06-17 | 2019-07-03 |  | 2020-01-08 | Underground | R16 | 2019-12-31 | 1 | 13 | 130 | 7 | 148 | 2019 | 2020 | R16
168927224589 | 168739224589 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-01-22 | 2021-01-22 | 2021-03-24 | 2021-05-04 | 2021-05-06 | Underground | R16 | 2021-05-04 | 1 | 44 | 30 | 3 | 75 | 2021 | 2021 | R16
163548155734 | 163653155734 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-12 | 2019-06-17 | 2019-06-20 |  | 2019-09-03 | Underground | R16 | 2019-08-06 | 4 | 4 | 34 | 21 | 60 | 2019 | 2019 | R16
166428221394 | 161883221394 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-03 | 2021-02-03 | 2021-02-23 |  | 2021-08-16 | Underground | R16 | 2021-03-25 | 1 | 15 | 23 | 103 | 139 | 2021 | 2021 | R16
163552158568 | 161186158568 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-22 | 2019-07-22 | 2019-07-22 |  | 2019-12-06 | Overhead | R16 | 2019-08-12 | 1 |  | 16 | 85 | 100 | 2019 | 2019 | R16
169749227928 | 161771227928 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-18 | 2021-03-18 | 2021-04-21 |  | 2022-02-10 | Underground | R16 | 2022-01-05 | 1 | 25 | 186 | 27 | 236 | 2021 | 2022 | R16
163564157279 | 163721157279 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-13 | 2019-06-13 | 2019-07-09 |  | 2019-08-26 | Underground | R16 | 2019-07-24 | 1 | 19 | 12 | 24 | 53 | 2019 | 2019 | R16
166666213532 | 160031213532 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-10 | 2020-12-10 | 2020-12-10 |  | 2022-09-02 | Overhead | R16 |  | 1 |  |  |  | 452 | 2020 | 2022 | R16
163971226626 | 169190226626 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-07 | 2021-04-08 | 2021-04-12 |  | 2021-11-05 | Overhead | R16 |  | 89 | 3 |  |  | 240 | 2020 | 2021 | R16
163608160358 | 164334160358 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-07 | 2019-08-07 | 2019-08-07 |  | 2019-10-28 | Overhead | R16 | 2019-10-04 | 1 |  | 43 | 17 | 59 | 2019 | 2019 | R16
163642155658 | 164934155658 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-18 | 2019-06-18 | 2019-06-18 |  | 2019-08-26 | Overhead | R16 | 2019-07-11 | 1 |  | 18 | 33 | 50 | 2019 | 2019 | R16
169390227043 | 168065227043 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-04-15 | 2021-04-15 | 2021-04-15 |  | 2021-11-05 | Overhead | R16 | 2021-05-07 | 1 |  | 17 | 131 | 147 | 2021 | 2021 | R16
163699161546 | 166224161546 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-19 | 2019-08-19 | 2019-08-19 |  | 2021-08-30 | Underground | R16 | 2021-06-10 | 1 |  | 474 | 58 | 531 | 2019 | 2021 | R16
167458216666 | 160838216666 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-14 | 2020-12-14 | 2021-01-08 |  | 2023-07-31 | Underground | R16 | 2021-01-27 | 1 | 20 | 14 | 654 | 686 | 2020 | 2023 | R16
167904232334 | 163449232334 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-06 | 2021-05-06 | 2021-05-26 |  | 2022-01-18 | Overhead | R16 |  | 1 | 15 |  |  | 184 | 2021 | 2022 | R16
163155222361 | 169319222361 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-25 | 2021-03-02 | 2021-03-02 | 2021-03-29 | 2021-11-11 | Underground | R16 | 2021-03-29 | 27 |  | 20 | 164 | 209 | 2021 | 2021 | R16
168492198064 | 169570198064 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-22 | 2020-07-22 | 2020-07-22 |  | 2020-10-06 | Overhead | R16 | 2020-08-12 | 1 |  | 16 | 40 | 55 | 2020 | 2020 | R16
166757204324 | 162022204324 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-04 | 2020-08-04 | 2020-09-18 | 2020-11-02 | 2021-07-26 | Underground | R16 | 2020-11-02 | 1 | 34 | 32 | 191 | 255 | 2020 | 2021 | R16
160534154503 | 162456154503 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-05 | 2019-06-05 | 2019-06-05 | 2019-07-05 | 2019-07-15 | Overhead | R16 | 2019-07-05 | 1 |  | 23 | 7 | 29 | 2019 | 2019 | R16
162592216060 | 169811216060 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-22 | 2020-12-29 | 2021-01-04 | 2021-01-05 | 2021-08-16 | Underground | R16 | 2021-01-05 | 49 | 5 | 2 | 160 | 213 | 2020 | 2021 | R16
169084203665 | 160396203665 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-11 | 2020-09-11 | 2020-09-11 |  | 2021-11-10 | Overhead | R16 | 2020-11-24 | 1 |  | 53 | 252 | 304 | 2020 | 2021 | R16
165961216177 | 164881216177 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-05 | 2021-01-05 | 2021-01-05 | 2021-01-06 | 2021-04-23 | Overhead | R16 | 2021-01-06 | 1 |  | 2 | 78 | 79 | 2021 | 2021 | R16
163811156880 | 167393156880 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-01 | 2019-07-01 | 2019-07-01 |  | 2019-12-19 | Underground | R16 | 2019-08-29 | 1 |  | 44 | 81 | 124 | 2019 | 2019 | R16
160729211736 | 162069211736 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-02 | 2020-11-02 | 2020-11-25 | 2020-12-21 | 2021-04-22 | Underground | R16 | 2020-12-21 | 1 | 18 | 19 | 89 | 124 | 2020 | 2021 | R16
163853156530 | 166445156530 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-27 | 2019-06-27 | 2019-06-27 |  | 2019-10-16 | Overhead | R16 | 2019-10-09 | 1 |  | 75 | 6 | 80 | 2019 | 2019 | R16
160215201368 | 165492201368 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-21 | 2020-08-21 | 2020-08-21 |  | 2021-07-26 | Underground | R16 | 2020-10-28 | 1 |  | 49 | 194 | 242 | 2020 | 2021 | R16
163176203904 | 160674203904 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-14 | 2020-09-14 | 2020-09-14 |  | 2021-01-08 | Overhead | R16 | 2020-10-07 | 1 |  | 18 | 68 | 85 | 2020 | 2021 | R16
161787223283 | 168652223283 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-19 | 2020-10-19 | 2021-03-11 |  | 2021-08-23 | Underground | R16 | 2021-08-04 | 1 | 104 | 105 | 14 | 221 | 2020 | 2021 | R16
164123156884 | 167653156884 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-01 | 2019-07-01 | 2019-07-01 |  | 2019-07-18 | Overhead | R16 | 2019-07-03 | 1 |  | 3 | 12 | 14 | 2019 | 2019 | R16
165857230788 | 169358230788 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-04-21 | 2021-05-06 | 2021-05-14 |  | 2021-08-26 | Underground | R16 |  | 12 | 7 |  |  | 92 | 2021 | 2021 | R16
168228200422 | 163401200422 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-12 | 2020-08-12 | 2020-08-12 |  | 2020-12-17 | Overhead | R16 | 2020-09-16 | 1 |  | 26 | 67 | 92 | 2020 | 2020 | R16
164361158152 | 160457158152 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-17 | 2019-07-17 | 2019-07-17 |  | 2021-07-07 | Overhead | R16 | 2020-10-21 | 1 |  | 331 | 186 | 516 | 2019 | 2021 | R16
166735223684 | 160579223684 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-15 | 2021-03-15 | 2021-03-15 | 2021-06-17 | 2021-06-18 | Overhead | R16 | 2021-06-17 | 1 |  | 69 | 2 | 70 | 2021 | 2021 | R16
164362158567 | 161257158567 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-22 | 2019-07-22 | 2019-07-22 |  | 2021-12-06 | Overhead | R16 | 2019-08-26 | 1 |  | 26 | 596 | 621 | 2019 | 2021 | R16
163134222382 | 168005222382 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-03-03 | 2021-03-03 | 2021-03-03 |  | 2021-11-08 | Overhead | R16 | 2021-05-20 | 1 |  | 57 | 123 | 179 | 2021 | 2021 | R16
164118219656 | 162470219656 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-05 | 2021-02-05 | 2021-02-05 | 2021-03-09 | 2021-11-05 | Overhead | R16 | 2021-03-09 | 1 |  | 23 | 174 | 196 | 2021 | 2021 | R16
161584228466 | 160368228466 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-26 | 2021-04-26 | 2021-04-26 |  | 2022-06-20 | Underground | R16 | 2022-05-25 | 1 |  | 283 | 19 | 301 | 2021 | 2022 | R16
164464159543 | 162585159543 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-29 | 2019-07-29 | 2019-07-29 |  | 2019-11-08 | Overhead | R16 | 2019-10-29 | 1 |  | 67 | 9 | 75 | 2019 | 2019 | R16
160468210643 | 162474210643 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-04 | 2020-11-04 | 2020-11-13 |  | 2022-06-28 | Underground | R16 |  | 1 | 8 |  |  | 430 | 2020 | 2022 | R16
169779231327 | 167936231327 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-18 | 2021-05-18 | 2021-05-18 |  | 2022-02-28 | Overhead | R16 | 2022-01-26 | 1 |  | 182 | 24 | 205 | 2021 | 2022 | R16
161098232680 | 160184232680 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-27 | 2021-05-27 | 2021-05-27 | 2021-08-12 | 2021-09-14 | Overhead | R16 | 2021-08-12 | 1 |  | 56 | 24 | 79 | 2021 | 2021 | R16
163315213220 | 166932213220 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-24 | 2020-12-07 | 2020-12-08 |  | 2021-11-08 | Underground | R16 | 2021-05-27 | 10 | 2 | 123 | 118 | 250 | 2020 | 2021 | R16
164480158861 | 167407158861 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-01 | 2019-07-23 | 2019-07-24 |  | 2019-10-11 | Overhead | R16 | 2019-09-30 | 17 | 2 | 49 | 10 | 75 | 2019 | 2019 | R16
164863154922 | 166583154922 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-01 | 2019-05-01 | 2019-06-10 | 2019-10-18 | 2019-10-21 | Underground | R16 | 2019-10-18 | 1 | 29 | 95 | 2 | 124 | 2019 | 2019 | R16
167301198180 | 169667198180 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-23 | 2020-07-23 | 2020-07-23 | 2020-08-13 | 2020-08-17 | Overhead | R16 | 2020-08-13 | 1 |  | 16 | 3 | 18 | 2020 | 2020 | R16
165267151916 | 168260151916 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-09 | 2019-05-09 | 2019-05-09 | 2019-06-03 | 2019-08-26 | Overhead | R16 | 2019-06-03 | 1 |  | 18 | 61 | 78 | 2019 | 2019 | R16
164854162144 | 167081162144 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-23 | 2019-08-23 | 2019-08-23 |  | 2020-06-17 | Underground | R16 | 2020-02-20 | 1 |  | 130 | 85 | 214 | 2019 | 2020 | R16
164858177446 | 168203177446 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-28 | 2019-08-29 | 2020-01-21 |  | 2021-11-03 | Underground | R16 | 2021-06-24 | 2 | 104 | 373 | 95 | 571 | 2019 | 2021 | R16
168661223341 | 165014223341 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-05 | 2021-01-05 | 2021-03-11 |  | 2021-11-13 | Underground | R16 | 2021-04-26 | 1 | 48 | 33 | 145 | 224 | 2021 | 2021 | R16
164887159417 | 162596159417 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-29 | 2019-07-29 | 2019-07-30 |  | 2019-09-04 | Overhead | R16 | 2019-08-28 | 1 | 2 | 22 | 6 | 28 | 2019 | 2019 | R16
164888158045 | 160081158045 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-15 | 2019-07-15 | 2019-07-15 |  | 2019-11-26 | Overhead | R16 | 2019-11-18 | 1 |  | 91 | 7 | 97 | 2019 | 2019 | R16
169273221826 | 165622221826 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-21 | 2021-02-26 | 2021-02-26 | 2021-04-26 | 2021-11-08 | Overhead | R16 | 2021-04-26 | 5 |  | 42 | 141 | 186 | 2021 | 2021 | R16
164898161821 | 166531161821 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-20 | 2019-08-20 | 2019-08-20 |  | 2019-10-28 | Overhead | R16 | 2019-10-15 | 1 |  | 41 | 10 | 50 | 2019 | 2019 | R16
165350217665 | 166826217665 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-13 | 2021-01-19 | 2021-01-19 |  | 2021-11-08 | Overhead | R16 | 2021-05-26 | 5 |  | 92 | 119 | 214 | 2021 | 2021 | R16
164900175505 | 169921175505 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-07-15 | 2019-07-15 | 2019-12-31 |  | 2020-12-18 | Underground | R16 | 2020-09-18 | 1 | 122 | 189 | 66 | 375 | 2019 | 2020 | R16
169582233160 | 169500233160 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-05-24 | 2021-05-24 | 2021-06-01 |  | 2022-05-03 | Overhead | R16 | 2022-04-11 | 1 | 7 | 225 | 17 | 247 | 2021 | 2022 | R16
164613248897 | 168079248897 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-05-19 | 2021-05-19 | 2021-09-21 | 2021-11-05 | 2023-06-07 | Underground | R16 | 2021-11-05 | 1 | 90 | 34 | 414 | 536 | 2021 | 2023 | R16
166658230619 | 165370230619 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-05-14 | 2021-05-14 | 2021-05-14 |  | 2021-08-26 | Overhead | R16 | 2021-06-09 | 1 |  | 19 | 57 | 75 | 2021 | 2021 | R16
167154142195 | 161395142195 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-02-05 | 2019-02-05 | 2019-02-05 |  | 2019-03-04 | Overhead | R16 |  | 1 |  |  |  | 20 | 2019 | 2019 | R16
160512216153 | 166670216153 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-23 | 2020-11-23 | 2021-01-05 | 2022-02-01 | 2022-03-03 | Underground | R16 | 2022-02-01 | 1 | 32 | 281 | 23 | 334 | 2020 | 2022 | R16
161133156879 | 161837156879 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-03 | 2019-06-03 | 2019-07-03 | 2019-12-03 | 2021-11-10 | Underground | R16 | 2019-12-03 | 1 | 23 | 110 | 507 | 638 | 2019 | 2021 | R16
163679215737 | 163704215737 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-29 | 2020-12-29 | 2020-12-29 | 2021-01-21 | 2021-01-28 | Overhead | R16 | 2021-01-21 | 1 |  | 18 | 6 | 23 | 2020 | 2021 | R16
165015157706 | 168159157706 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-03 | 2019-07-03 | 2019-07-11 |  | 2019-12-06 | Underground | R16 | 2019-08-15 | 1 | 7 | 26 | 82 | 113 | 2019 | 2019 | R16
164343221619 | 162414221619 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-02-04 | 2021-02-18 | 2021-02-26 |  | 2021-06-02 | Overhead | R16 |  | 11 | 7 |  |  | 85 | 2021 | 2021 | R16
165017157618 | 169483157618 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-11 | 2019-07-11 | 2019-07-11 |  | 2019-12-06 | Overhead | R16 | 2019-08-15 | 1 |  | 26 | 82 | 107 | 2019 | 2019 | R16
168131230420 | 164555230420 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-06-24 | 2023-04-13 | Overhead | R16 | 2021-06-24 | 1 |  | 33 | 471 | 503 | 2021 | 2023 | R16
162114158799 | 161788158799 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-04-05 | 2019-05-08 | 2019-07-24 | 2019-08-22 | 2020-02-06 | Overhead | R16 | 2019-08-22 | 24 | 56 | 22 | 121 | 220 | 2019 | 2020 | R16
163691245802 | 165991245802 | NON-RESIDENTIAL - SMALL RETAIL | R16 RESD AND NON RESD US | Commercial | 2020-10-06 | 2021-08-12 | 2021-08-30 |  | 2022-07-25 | Underground | R16 |  | 223 | 13 |  |  | 470 | 2020 | 2022 | R16
166377203066 | 169133203066 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-08 | 2020-09-08 | 2020-09-08 |  | 2021-04-20 | Overhead | R16 | 2021-01-12 | 1 |  | 91 | 71 | 161 | 2020 | 2021 | R16
165031164120 | 160366164120 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-11 | 2019-09-11 | 2019-09-11 |  | 2020-08-28 | Overhead | R16 | 2020-06-30 | 1 |  | 210 | 44 | 253 | 2019 | 2020 | R16
166454232083 | 167585232083 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-08-29 | 2020-11-18 | 2021-05-24 | 2021-11-30 | 2022-01-11 | Underground | R16 | 2021-11-30 | 58 | 134 | 137 | 31 | 357 | 2020 | 2022 | R16
163602228897 | 168526228897 | RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Residential | 2020-10-16 | 2020-12-29 | 2021-04-30 | 2021-07-28 | 2021-08-25 | Underground | R16 | 2021-07-28 | 53 | 89 | 64 | 21 | 224 | 2020 | 2021 | R16
165098256120 | 168977256120 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2021-11-11 | 2021-11-11 | 2021-11-11 |  | 2022-10-21 | Underground | R16 | 2022-08-29 | 1 |  | 208 | 40 | 247 | 2021 | 2022 | R16
160593229224 | 161396229224 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-04-29 | 2021-05-03 | 2021-05-03 | 2021-05-15 | 2021-10-08 | Overhead | R16 | 2021-05-15 | 3 |  | 10 | 105 | 117 | 2021 | 2021 | R16
165107191096 | 167373191096 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-15 | 2020-05-15 | 2020-05-15 |  | 2020-07-08 | Underground | R16 | 2020-05-18 | 1 |  | 2 | 38 | 39 | 2020 | 2020 | R16
165108158483 | 161056158483 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-19 | 2019-07-19 | 2019-07-19 |  | 2019-08-28 | Overhead | R16 | 2019-08-20 | 1 |  | 23 | 7 | 29 | 2019 | 2019 | R16
166794197668 | 168766197668 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-17 | 2020-07-17 | 2020-07-17 | 2020-09-23 | 2020-12-18 | Overhead | R16 | 2020-09-23 | 1 |  | 49 | 63 | 111 | 2020 | 2020 | R16
168462207803 | 168656207803 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-09-03 | 2020-09-03 | 2020-10-20 | 2020-12-05 | 2021-03-27 | Overhead | R16 | 2020-12-05 | 1 | 34 | 34 | 80 | 147 | 2020 | 2021 | R16
160910146021 | 169120146021 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-25 | 2019-01-25 | 2019-03-13 | 2020-10-12 | 2021-02-17 | Underground | R16 | 2020-10-12 | 1 | 34 | 414 | 93 | 539 | 2019 | 2021 | R16
165118161006 | 162466161006 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-07-29 | 2019-07-29 | 2019-08-13 |  | 2021-01-07 | Underground | R16 | 2020-10-02 | 1 | 12 | 299 | 70 | 379 | 2019 | 2021 | R16
169816210320 | 161300210320 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-29 | 2020-10-29 | 2020-11-10 |  | 2022-06-28 | Underground | R16 |  | 1 | 9 |  |  | 434 | 2020 | 2022 | R16
165141163114 | 169266163114 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-05 | 2019-09-05 | 2019-09-05 |  | 2021-05-06 | Overhead | R16 | 2021-02-22 | 1 |  | 383 | 54 | 436 | 2019 | 2021 | R16
161836146148 | 165230146148 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-26 | 2019-02-26 | 2019-03-15 | 2019-07-02 | 2019-07-02 | Underground | R16 | 2019-07-02 | 1 | 14 | 78 |  | 91 | 2019 | 2019 | R16
168242198652 | 160435198652 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-28 | 2020-07-28 | 2020-07-28 |  | 2020-10-29 | Overhead | R16 | 2020-09-01 | 1 |  | 26 | 43 | 68 | 2020 | 2020 | R16
167070209646 | 169955209646 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Commercial | 2020-10-23 | 2020-10-23 | 2020-11-05 |  | 2022-01-12 | Underground | R16 |  | 1 | 10 |  |  | 319 | 2020 | 2022 | R16
165167161085 | 165065161085 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-13 | 2019-08-13 | 2019-08-13 |  | 2019-09-18 | Overhead | R16 | 2019-09-10 | 1 |  | 21 | 7 | 27 | 2019 | 2019 | R16
165175161712 | 168109161712 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-03 | 2019-07-03 | 2019-08-20 |  | 2019-11-21 | Underground | R16 | 2019-11-15 | 1 | 35 | 64 | 5 | 102 | 2019 | 2019 | R16
160585156842 | 161054156842 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-28 | 2019-05-28 | 2019-07-01 | 2019-07-29 | 2019-07-31 | Underground | R16 | 2019-07-29 | 1 | 25 | 21 | 3 | 47 | 2019 | 2019 | R16
165185160588 | 164667160588 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-08 | 2019-08-08 | 2019-08-08 |  | 2019-09-05 | Overhead | R16 | 2019-08-29 | 1 |  | 16 | 6 | 21 | 2019 | 2019 | R16
161742210976 | 165510210976 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-11-17 | 2020-11-17 | 2020-11-17 | 2020-12-18 | 2021-11-09 | Overhead | R16 | 2020-12-18 | 1 |  | 24 | 233 | 256 | 2020 | 2021 | R16
165192161365 | 165951161365 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-16 | 2019-08-16 | 2019-08-16 |  | 2021-11-03 | Overhead | R16 | 2019-09-30 | 1 |  | 32 | 548 | 579 | 2019 | 2021 | R16
165200157617 | 169186157617 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-07-10 | 2019-07-11 | 2019-07-11 |  | 2020-06-24 | Overhead | R16 | 2020-04-21 | 2 |  | 204 | 47 | 251 | 2019 | 2020 | R16
169586218732 | 160568218732 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-28 | 2021-01-28 | 2021-01-28 | 2021-03-01 | 2021-03-02 | Overhead | R16 | 2021-03-01 | 1 |  | 23 | 2 | 24 | 2021 | 2021 | R16
169571153896 | 164793153896 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-03 | 2019-01-03 | 2019-05-31 | 2019-08-20 | 2019-08-20 | Underground | R16 | 2019-08-20 | 1 | 107 | 58 |  | 164 | 2019 | 2019 | R16
165140205529 | 164262205529 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-28 | 2020-09-28 | 2020-09-29 | 2020-12-01 | 2021-04-13 | Overhead | R16 | 2020-12-01 | 1 | 2 | 46 | 96 | 142 | 2020 | 2021 | R16
165281187616 | 162494187616 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-11-11 | 2019-11-11 | 2020-04-15 |  | 2021-08-26 | Underground | R16 | 2021-06-08 | 1 | 113 | 300 | 58 | 469 | 2019 | 2021 | R16
167806241526 | 168504241526 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-19 | 2021-05-19 | 2021-09-20 |  | 2021-09-16 | Underground | R16 | 2021-09-28 | 1 | 89 | 7 |  | 87 | 2021 | 2021 | R16
165331161629 | 166205161629 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-19 | 2019-08-19 | 2019-08-19 |  | 2019-10-11 | Overhead | R16 | 2019-09-30 | 1 |  | 31 | 10 | 40 | 2019 | 2019 | R16
160163230411 | 164850230411 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-12 | 2021-05-12 | 2021-05-12 |  | 2021-11-13 | Overhead | R16 | 2021-10-20 | 1 |  | 116 | 18 | 133 | 2021 | 2021 | R16
169189246051 | 166059246051 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-11-20 | 2020-11-20 | 2021-08-31 |  | 2021-11-01 | Overhead | R16 | 2021-09-29 | 1 | 203 | 22 | 24 | 247 | 2020 | 2021 | R16
166249199434 | 161534199434 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-03 | 2020-08-03 | 2020-08-03 |  | 2021-06-30 | Overhead | R16 | 2020-10-27 | 1 |  | 62 | 177 | 238 | 2020 | 2021 | R16
165359158738 | 161702158738 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-24 | 2019-07-24 | 2019-07-24 |  | 2019-08-28 | Overhead | R16 | 2019-08-20 | 1 |  | 20 | 7 | 26 | 2019 | 2019 | R16
162866214219 | 161257214219 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-17 | 2020-12-17 | 2020-12-17 | 2021-01-15 | 2021-06-03 | Underground | R16 | 2021-01-15 | 1 |  | 22 | 100 | 121 | 2020 | 2021 | R16
161248207942 | 166941207942 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-09 | 2020-10-09 | 2020-10-22 |  | 2021-06-30 | Underground | R16 | 2020-10-29 | 1 | 10 | 6 | 175 | 189 | 2020 | 2021 | R16
161490153911 | 165137153911 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-24 | 2019-05-31 | 2019-05-31 | 2019-08-12 | 2019-12-06 | Overhead | R16 | 2019-08-12 | 28 |  | 52 | 85 | 163 | 2019 | 2019 | R16
165384156630 | 166179156630 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-26 | 2019-06-28 | 2019-06-28 |  | 2019-08-28 | Overhead | R16 | 2019-08-23 | 3 |  | 41 | 4 | 46 | 2019 | 2019 | R16
165390162320 | 169537162320 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-12 | 2019-07-12 | 2019-08-26 |  | 2019-09-03 | Overhead | R16 | 2019-08-27 | 1 | 32 | 2 | 6 | 38 | 2019 | 2019 | R16
166492197459 | 168334197459 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-15 | 2020-07-15 | 2020-07-16 |  | 2020-08-07 | Overhead | R16 |  | 1 | 2 |  |  | 18 | 2020 | 2020 | R16
168283218639 | 160358218639 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-28 | 2021-01-28 | 2021-01-28 | 2021-02-19 | 2021-11-11 | Overhead | R16 | 2021-02-19 | 1 |  | 17 | 190 | 206 | 2021 | 2021 | R16
165431157381 | 168748157381 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-08 | 2019-07-08 | 2019-07-08 |  | 2019-11-27 | Overhead | R16 | 2019-11-22 | 1 |  | 100 | 4 | 103 | 2019 | 2019 | R16
163338224415 | 163365224415 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-28 | 2020-12-28 | 2021-03-23 |  | 2021-11-08 | Underground | R16 | 2021-05-24 | 1 | 62 | 45 | 121 | 226 | 2020 | 2021 | R16
161686248192 | 169332248192 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-05-24 | 2021-08-25 | 2021-09-16 |  | 2021-12-01 | Overhead | R16 |  | 68 | 17 |  |  | 138 | 2021 | 2021 | R16
169700207409 | 168276207409 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-15 | 2020-10-15 | 2020-10-15 | 2020-12-03 | 2021-04-21 | Overhead | R16 | 2020-12-03 | 1 |  | 36 | 100 | 135 | 2020 | 2021 | R16
165527158285 | 167394158285 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-01 | 2019-07-01 | 2019-07-18 |  | 2019-09-24 | Underground | R16 | 2019-09-17 | 1 | 14 | 44 | 6 | 62 | 2019 | 2019 | R16
162396226738 | 167912226738 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-14 | 2021-04-14 | 2021-04-14 |  | 2021-11-08 | Overhead | R16 | 2021-05-25 | 1 |  | 30 | 120 | 149 | 2021 | 2021 | R16
164084220444 | 160554220444 | NON-RESIDENTIAL - WAREHOUSE | UG R16 RESD AND NON RESD UD | Commercial | 2020-09-12 | 2020-09-15 | 2021-02-12 | 2021-07-28 | 2021-08-25 | Underground | R16 | 2021-07-28 | 2 | 109 | 119 | 21 | 248 | 2020 | 2021 | R16
165541158278 | 161047158278 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-19 | 2019-07-19 | 2019-07-19 |  | 2019-08-28 | Overhead | R16 | 2019-08-22 | 1 |  | 25 | 5 | 29 | 2019 | 2019 | R16
160283139764 | 166402139764 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-01-09 | 2019-01-09 | 2019-01-09 | 2019-07-05 | 2019-07-26 | Underground | R16 | 2019-07-05 | 1 |  | 128 | 16 | 143 | 2019 | 2019 | R16
165569165211 | 166246165211 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-26 | 2019-06-26 | 2019-09-20 |  | 2022-06-20 | Underground | R16 | 2022-05-23 | 1 | 63 | 697 | 21 | 779 | 2019 | 2022 | R16
167207228592 | 161190228592 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-28 | 2021-04-28 | 2021-04-28 |  | 2021-08-26 | Overhead | R16 | 2021-06-07 | 1 |  | 29 | 59 | 87 | 2021 | 2021 | R16
165399227816 | 168818227816 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-19 | 2021-04-21 | 2021-04-22 |  | 2021-12-03 | Underground | R16 | 2021-11-09 | 3 | 2 | 144 | 19 | 165 | 2021 | 2021 | R16
165616161829 | 166355161829 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-20 | 2019-08-21 | 2019-08-21 |  | 2019-10-16 | Overhead | R16 | 2019-10-10 | 2 |  | 37 | 5 | 42 | 2019 | 2019 | R16
161888202445 | 168091202445 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-01 | 2020-09-01 | 2020-09-01 | 2020-09-16 | 2023-06-08 | Overhead | R16 | 2020-09-16 | 1 |  | 12 | 712 | 723 | 2020 | 2023 | R16
168074284880 | 160528284880 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-10-26 | 2022-06-15 | 2022-07-07 |  | 2022-10-29 | Underground | R16 |  | 428 | 17 |  |  | 525 | 2020 | 2022 | R16
165708157879 | 160199157879 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-16 | 2019-07-16 | 2019-07-17 |  | 2019-09-03 | Overhead | R16 | 2019-08-27 | 1 | 2 | 30 | 6 | 36 | 2019 | 2019 | R16
165081201446 | 165169201446 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Commercial | 2020-08-19 | 2020-08-19 | 2020-08-21 | 2020-09-01 | 2021-02-16 | Overhead | R16 | 2020-09-01 | 1 | 3 | 8 | 121 | 130 | 2020 | 2021 | R16
160418237781 | 163012237781 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-05 | 2021-05-05 | 2021-07-06 | 2022-01-12 | 2022-03-28 | Underground | R16 | 2022-01-12 | 1 | 45 | 137 | 54 | 234 | 2021 | 2022 | R16
162295154156 | 162131154156 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-04 | 2019-06-04 | 2019-06-04 | 2019-10-15 | 2019-10-16 | Overhead | R16 | 2019-10-15 | 1 |  | 96 | 2 | 97 | 2019 | 2019 | R16
165709281997 | 163058281997 | AGRICULTURAL | R16 RESD AND NON RESD US | Residential Subdivision | 2021-07-23 | 2021-08-24 | 2022-06-08 |  | 2023-01-10 | Underground | R16 |  | 23 | 207 |  |  | 383 | 2021 | 2023 | R16
165709261989 | 163059261989 | AGRICULTURAL | R16 RESD AND NON RESD US | Residential Subdivision | 2021-07-23 | 2021-09-10 | 2021-12-21 |  | 2023-08-16 | Underground | R16 |  | 36 | 73 |  |  | 539 | 2021 | 2023 | R16
161088225315 | 164593225315 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-30 | 2021-03-30 | 2021-03-30 | 2021-10-07 | 2023-06-08 | Overhead | R16 | 2021-10-07 | 1 |  | 138 | 436 | 573 | 2021 | 2023 | R16
165782169120 | 167835169120 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-18 | 2019-10-18 | 2019-10-21 |  | 2021-10-27 | Underground | R16 | 2021-08-13 | 1 | 2 | 475 | 54 | 529 | 2019 | 2021 | R16
167412142441 | 161437142441 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-05 | 2019-02-05 | 2019-02-05 | 2019-04-15 | 2019-04-18 | Underground | R16 | 2019-04-15 | 1 |  | 50 | 4 | 53 | 2019 | 2019 | R16
165786159460 | 160862159460 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-18 | 2019-07-18 | 2019-07-29 |  | 2020-07-10 | Underground | R16 | 2020-06-11 | 1 | 8 | 229 | 22 | 257 | 2019 | 2020 | R16
165816162537 | 168105162537 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-28 | 2019-08-28 | 2019-08-28 |  | 2021-11-11 | Underground | R16 | 2021-06-04 | 1 |  | 463 | 115 | 577 | 2019 | 2021 | R16
160127200211 | 162968200211 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-10 | 2020-08-11 | 2020-08-11 |  | 2021-01-20 | Underground | R16 | 2020-10-12 | 2 |  | 45 | 73 | 118 | 2020 | 2021 | R16
166411216982 | 167412216982 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-12 | 2020-10-13 | 2021-01-12 | 2021-04-21 | 2021-11-09 | Underground | R16 | 2021-04-21 | 2 | 66 | 72 | 145 | 282 | 2020 | 2021 | R16
165829160987 | 165005160987 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-12 | 2019-08-12 | 2019-08-12 |  | 2019-11-17 | Overhead | R16 | 2019-09-09 | 1 |  | 21 | 50 | 70 | 2019 | 2019 | R16
168468228880 | 161573228880 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-29 | 2021-04-29 | 2021-04-29 | 2021-06-11 | 2021-06-14 | Overhead | R16 | 2021-06-11 | 1 |  | 32 | 2 | 33 | 2021 | 2021 | R16
165890161007 | 165009161007 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-08-12 | 2019-08-13 | 2019-08-13 |  | 2020-06-09 | Overhead | R16 | 2020-03-20 | 2 |  | 159 | 58 | 217 | 2019 | 2020 | R16
166876231253 | 166681231253 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-18 | 2021-05-18 | 2021-05-18 |  | 2021-09-01 | Underground | R16 | 2021-08-09 | 1 |  | 60 | 18 | 77 | 2021 | 2021 | R16
165891195101 | 163356195101 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-06-19 | 2020-06-19 | 2020-06-23 |  | 2021-01-08 | Underground | R16 |  | 1 | 3 |  |  | 146 | 2020 | 2021 | R16
165941163456 | 169482163456 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-05 | 2019-09-05 | 2019-09-05 |  | 2019-11-13 | Overhead | R16 | 2019-11-04 | 1 |  | 43 | 8 | 50 | 2019 | 2019 | R16
168071234095 | 160971234095 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-04-27 | 2021-05-26 | 2021-06-08 | 2023-07-31 | 2023-07-31 | Underground | R16 | 2023-07-31 | 22 | 10 | 560 |  | 590 | 2021 | 2023 | R16
165960158921 | 160767158921 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-18 | 2019-07-18 | 2019-07-24 |  | 2019-10-04 | Underground | R16 | 2019-09-23 | 1 | 5 | 44 | 10 | 57 | 2019 | 2019 | R16
165963158292 | 160840158292 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-18 | 2019-07-18 | 2019-07-18 |  | 2019-12-06 | Overhead | R16 | 2019-08-14 | 1 |  | 20 | 83 | 102 | 2019 | 2019 | R16
162125207957 | 169725207957 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-22 | 2020-10-23 | 2020-10-23 | 2020-12-04 | 2021-04-15 | Overhead | R16 | 2020-12-04 | 2 |  | 31 | 95 | 126 | 2020 | 2021 | R16
163202222236 | 168023222236 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-03-03 | 2021-03-03 | 2021-03-03 |  | 2021-11-05 | Overhead | R16 | 2021-09-10 | 1 |  | 138 | 41 | 178 | 2021 | 2021 | R16
165981259880 | 163182259880 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2021-07-23 | 2021-11-03 | 2021-12-03 |  | 2022-09-14 | Underground | R16 |  | 74 | 23 |  |  | 299 | 2021 | 2022 | R16
167536220043 | 168670220043 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-09-03 | 2020-12-28 | 2021-02-09 | 2022-08-08 | 2022-08-11 | Underground | R16 | 2022-08-08 | 83 | 32 | 390 | 4 | 506 | 2020 | 2022 | R16
163360226630 | 163709226630 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-28 | 2021-04-12 | 2021-04-12 | 2021-06-23 | 2021-09-10 | Overhead | R16 | 2021-06-23 | 11 |  | 53 | 58 | 120 | 2021 | 2021 | R16
162679237686 | 163404237686 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-02-10 | 2021-02-10 | 2021-07-02 |  | 2022-03-08 | Underground | R16 |  | 1 | 103 |  |  | 280 | 2021 | 2022 | R16
168453205729 | 169737205729 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-24 | 2020-07-24 | 2020-09-30 |  | 2021-05-07 | Underground | R16 | 2021-02-25 | 1 | 49 | 107 | 52 | 206 | 2020 | 2021 | R16
164252210404 | 164232210404 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-11 | 2020-11-11 | 2020-11-11 | 2021-01-04 | 2021-01-04 | Overhead | R16 | 2021-01-04 | 1 |  | 39 |  | 39 | 2020 | 2021 | R16
161842155245 | 167262155245 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-03 | 2019-05-03 | 2019-06-13 | 2019-07-17 | 2019-07-17 | Underground | R16 | 2019-07-17 | 1 | 30 | 25 |  | 54 | 2019 | 2019 | R16
162776225813 | 163163225813 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2021-03-24 | 2021-03-24 | 2021-04-05 |  | 2022-06-30 | Overhead | R16 | 2022-06-02 | 1 | 9 | 304 | 21 | 332 | 2021 | 2022 | R16
166068157094 | 168246157094 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-05 | 2019-07-05 | 2019-07-05 |  | 2022-10-19 | Overhead | R16 |  | 1 |  |  |  | 859 | 2019 | 2022 | R16
163186232848 | 169233232848 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-24 | 2021-05-28 | 2021-05-28 |  | 2023-03-13 | Overhead | R16 | 2022-02-18 | 5 |  | 191 | 277 | 471 | 2021 | 2023 | R16
166071157309 | 168902157309 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-08 | 2019-07-08 | 2019-07-08 |  | 2019-08-26 | Underground | R16 | 2019-07-22 | 1 |  | 11 | 26 | 36 | 2019 | 2019 | R16
166573218597 | 166567218597 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-23 | 2020-11-23 | 2021-01-27 |  | 2021-11-08 | Underground | R16 | 2021-03-31 | 1 | 48 | 46 | 159 | 251 | 2020 | 2021 | R16
164384228908 | 160502228908 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-26 | 2021-04-26 | 2021-04-30 | 2021-08-10 | 2021-10-25 | Overhead | R16 | 2021-08-10 | 1 | 5 | 73 | 55 | 131 | 2021 | 2021 | R16
166087158424 | 160987158424 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-19 | 2019-07-19 | 2019-07-19 |  | 2019-12-06 | Overhead | R16 | 2019-08-14 | 1 |  | 19 | 83 | 101 | 2019 | 2019 | R16
160120231712 | 165830231712 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-17 | 2021-05-20 | 2021-05-20 | 2021-05-24 | 2021-11-03 | Overhead | R16 | 2021-05-24 | 4 |  | 3 | 118 | 123 | 2021 | 2021 | R16
166090158257 | 168671158257 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-08 | 2019-07-08 | 2019-07-18 |  | 2019-09-19 | Overhead | R16 | 2019-09-12 | 1 | 9 | 41 | 6 | 54 | 2019 | 2019 | R16
165799224199 | 168293224199 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-04 | 2021-03-05 | 2021-03-22 | 2021-06-16 | 2021-06-17 | Underground | R16 | 2021-06-16 | 2 | 12 | 63 | 2 | 76 | 2021 | 2021 | R16
166091158251 | 169687158251 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-12 | 2019-07-12 | 2019-07-18 |  | 2019-12-19 | Overhead | R16 | 2019-08-16 | 1 | 5 | 22 | 90 | 115 | 2019 | 2019 | R16
166106160186 | 163761160186 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-05 | 2019-08-05 | 2019-08-05 |  | 2019-09-10 | Overhead | R16 | 2019-09-03 | 1 |  | 22 | 6 | 27 | 2019 | 2019 | R16
166133161852 | 168280161852 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-05 | 2019-07-05 | 2019-08-21 |  | 2019-09-24 | Underground | R16 | 2019-09-17 | 1 | 34 | 20 | 6 | 58 | 2019 | 2019 | R16
166149157110 | 168135157110 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-03 | 2019-07-03 | 2019-07-03 |  | 2019-08-26 | Overhead | R16 | 2019-07-24 | 1 |  | 16 | 24 | 39 | 2019 | 2019 | R16
167887214437 | 162682214437 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-22 | 2020-12-22 | 2020-12-22 |  | 2021-05-06 | Underground | R16 | 2021-02-24 | 1 |  | 47 | 52 | 98 | 2020 | 2021 | R16
166152158286 | 160770158286 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-07-18 | 2019-07-18 | 2019-07-18 |  | 2020-10-06 | Overhead | R16 | 2020-09-24 | 1 |  | 311 | 9 | 319 | 2019 | 2020 | R16
166646152080 | 167814152080 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-08 | 2019-05-10 | 2019-05-10 | 2019-06-14 | 2019-06-27 | Overhead | R16 | 2019-06-14 | 3 |  | 26 | 10 | 37 | 2019 | 2019 | R16
166203157537 | 169191157537 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-10 | 2019-07-10 | 2019-07-10 |  | 2019-08-28 | Overhead | R16 | 2019-08-23 | 1 |  | 33 | 4 | 36 | 2019 | 2019 | R16
162639144765 | 165994144765 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-04 | 2019-03-04 | 2019-03-04 | 2019-04-26 | 2019-04-26 | Overhead | R16 | 2019-04-26 | 1 |  | 40 |  | 40 | 2019 | 2019 | R16
166253159045 | 162086159045 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-25 | 2019-07-25 | 2019-07-25 |  | 2019-12-06 | Overhead | R16 | 2019-09-05 | 1 |  | 31 | 67 | 97 | 2019 | 2019 | R16
169105202088 | 167178202088 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-27 | 2020-08-27 | 2020-08-27 | 2020-09-16 | 2021-04-20 | Overhead | R16 | 2020-09-16 | 1 |  | 15 | 155 | 169 | 2020 | 2021 | R16
166339174175 | 168310174175 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-05 | 2019-07-05 | 2019-12-12 |  | 2020-06-24 | Underground | R16 | 2020-04-22 | 1 | 115 | 95 | 46 | 254 | 2019 | 2020 | R16
166380157183 | 168087157183 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-03 | 2019-07-03 | 2019-07-05 |  | 2019-09-03 | Overhead | R16 | 2019-08-05 | 1 | 3 | 22 | 22 | 45 | 2019 | 2019 | R16
166397241717 | 163069241717 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-07-23 | 2021-07-30 | 2021-08-03 |  | 2022-01-11 | Underground | R16 |  | 6 | 3 |  |  | 123 | 2021 | 2022 | R16
167179228463 | 160541228463 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-15 | 2021-03-15 | 2021-04-26 | 2021-08-12 | 2021-08-12 | Underground | R16 | 2021-08-12 | 1 | 31 | 79 |  | 109 | 2021 | 2021 | R16
166399158555 | 168319158555 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-08 | 2019-07-08 | 2019-07-23 |  | 2019-11-13 | Underground | R16 | 2019-11-04 | 1 | 12 | 75 | 8 | 93 | 2019 | 2019 | R16
162205211614 | 166669211614 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-24 | 2020-11-24 | 2020-11-24 | 2020-12-03 | 2021-07-28 | Overhead | R16 | 2020-12-03 | 1 |  | 8 | 170 | 177 | 2020 | 2021 | R16
166455161212 | 165648161212 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-15 | 2019-08-15 | 2019-08-15 |  | 2019-09-04 | Overhead | R16 | 2019-08-28 | 1 |  | 10 | 6 | 15 | 2019 | 2019 | R16
169119156846 | 161930156846 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-06-03 | 2019-07-01 | 2019-07-01 | 2020-03-04 | 2020-03-05 | Overhead | R16 | 2020-03-04 | 21 |  | 178 | 2 | 199 | 2019 | 2020 | R16
166641142287 | 161556142287 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-06 | 2019-02-06 | 2019-02-06 | 2019-06-05 | 2021-11-03 | Overhead | R16 | 2019-06-05 | 1 |  | 86 | 631 | 716 | 2019 | 2021 | R16
166532168760 | 166755168760 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-10-14 | 2019-10-15 | 2019-10-18 |  | 2020-06-09 | Overhead | R16 |  | 2 | 4 |  |  | 172 | 2019 | 2020 | R16
160027203707 | 167603203707 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-08-29 | 2020-09-10 | 2020-09-14 |  | 2022-01-11 | Overhead | R16 |  | 9 | 3 |  |  | 357 | 2020 | 2022 | R16
166534160574 | 164498160574 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-08-08 | 2019-08-08 | 2019-08-08 |  | 2019-11-17 | Overhead | R16 | 2019-08-12 | 1 |  | 3 | 70 | 72 | 2019 | 2019 | R16
166535160508 | 164306160508 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-07 | 2019-08-07 | 2019-08-07 |  | 2019-09-18 | Overhead | R16 | 2019-09-09 | 1 |  | 24 | 8 | 31 | 2019 | 2019 | R16
168905218362 | 169366218362 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-25 | 2021-01-25 | 2021-01-25 |  | 2021-06-03 | Overhead | R16 | 2021-03-08 | 1 |  | 31 | 64 | 94 | 2021 | 2021 | R16
165587202297 | 167740202297 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-10-09 | 2021-02-17 | Overhead | R16 | 2020-10-09 | 1 |  | 30 | 94 | 123 | 2020 | 2021 | R16
167302200424 | 163430200424 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-12 | 2020-08-12 | 2020-08-12 | 2020-09-10 | 2020-12-15 | Overhead | R16 | 2020-09-10 | 1 |  | 22 | 69 | 90 | 2020 | 2020 | R16
165088225971 | 166193225971 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-04-07 | 2021-04-07 | 2021-04-07 |  | 2021-08-26 | Underground | R16 | 2021-06-09 | 1 |  | 46 | 57 | 102 | 2021 | 2021 | R16
166609158963 | 168742158963 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-08 | 2019-07-08 | 2019-07-24 |  | 2019-12-06 | Underground | R16 | 2019-08-14 | 1 | 13 | 16 | 83 | 110 | 2019 | 2019 | R16
162434226145 | 166450226145 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-07 | 2021-04-07 | 2021-04-07 |  | 2021-11-08 | Overhead | R16 | 2021-05-14 | 1 |  | 28 | 127 | 154 | 2021 | 2021 | R16
166639160110 | 168047160110 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-05 | 2019-07-05 | 2019-08-05 |  | 2021-12-16 | Underground | R16 | 2019-09-04 | 1 | 22 | 23 | 597 | 640 | 2019 | 2021 | R16
169695140696 | 165597140696 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-01-07 | 2019-01-07 | 2019-01-18 | 2019-09-09 | 2019-09-19 | Underground | R16 | 2019-09-09 | 1 | 10 | 167 | 9 | 184 | 2019 | 2019 | R16
169597226014 | 164767226014 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-31 | 2021-03-31 | 2021-04-08 | 2021-09-01 | 2021-10-25 | Overhead | R16 | 2021-09-01 | 1 | 7 | 105 | 39 | 149 | 2021 | 2021 | R16
166672161320 | 161195161320 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-22 | 2019-07-22 | 2019-08-15 |  | 2019-11-08 | Underground | R16 | 2019-10-29 | 1 | 19 | 54 | 9 | 80 | 2019 | 2019 | R16
160524205046 | 163460205046 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-30 | 2020-09-30 | Underground | R16 | 2020-09-30 | 1 |  | 4 |  | 4 | 2020 | 2020 | R16
163795204553 | 162464204553 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-09-22 | 2020-09-22 | 2020-09-22 | 2021-03-16 | 2021-11-08 | Underground | R16 | 2021-03-16 | 1 |  | 126 | 170 | 295 | 2020 | 2021 | R16
166733160311 | 169249160311 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-10 | 2019-08-06 | 2019-08-06 |  | 2019-09-24 | Overhead | R16 | 2019-09-16 | 20 |  | 30 | 7 | 55 | 2019 | 2019 | R16
163423223103 | 167849223103 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-02 | 2021-03-10 | 2021-03-10 |  | 2021-08-09 | Overhead | R16 | 2021-03-30 | 7 |  | 15 | 95 | 115 | 2021 | 2021 | R16
167376231514 | 168667231514 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2021-05-20 | 2021-05-20 | 2021-05-20 |  | 2022-09-08 | Overhead | R16 | 2022-09-02 | 1 |  | 337 | 5 | 341 | 2021 | 2022 | R16
164334202594 | 164326202594 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-04-19 | 2019-04-19 | 2020-09-04 | 2020-12-12 | 2020-12-16 | Underground | R16 | 2020-12-12 | 1 | 361 | 71 | 3 | 434 | 2019 | 2020 | R16
168794206458 | 166568206458 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-08 | 2020-10-08 | 2020-10-08 | 2021-01-29 | 2021-04-23 | Overhead | R16 | 2021-01-29 | 1 |  | 82 | 61 | 142 | 2020 | 2021 | R16
166815161322 | 161215161322 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-22 | 2019-07-22 | 2019-08-15 |  | 2019-10-11 | Underground | R16 | 2019-10-01 | 1 | 19 | 34 | 9 | 60 | 2019 | 2019 | R16
161402202280 | 167541202280 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-28 | 2020-08-29 | 2020-08-29 | 2020-09-24 | 2021-07-19 | Overhead | R16 | 2020-09-24 | 1 |  | 19 | 213 | 232 | 2020 | 2021 | R16
168033139321 | 164779139321 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-04 | 2019-01-05 | 2019-01-05 | 2019-01-25 | 2019-02-19 | Overhead | R16 | 2019-01-25 | 1 |  | 15 | 18 | 33 | 2019 | 2019 | R16
167459164157 | 167355164157 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-26 | 2019-08-26 | 2019-09-12 |  | 2022-08-02 | Underground | R16 |  | 1 | 14 |  |  | 767 | 2019 | 2022 | R16
167511159803 | 161848159803 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-24 | 2019-08-01 | 2019-08-01 |  | 2023-06-05 | Overhead | R16 | 2019-09-24 | 7 |  | 39 | 965 | 1009 | 2019 | 2023 | R16
167523158950 | 168444158950 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-08 | 2019-07-08 | 2019-07-25 |  | 2019-10-14 | Underground | R16 | 2019-10-03 | 1 | 14 | 51 | 8 | 71 | 2019 | 2019 | R16
168434214536 | 161687214536 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2020-12-23 | 2021-04-23 | Overhead | R16 | 2020-12-23 | 1 |  | 3 | 88 | 90 | 2020 | 2021 | R16
167553157992 | 169914157992 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-15 | 2019-07-16 | 2019-07-16 |  | 2019-09-12 | Overhead | R16 | 2019-09-06 | 2 |  | 39 | 5 | 44 | 2019 | 2019 | R16
165792223974 | 161463223974 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-18 | 2021-03-18 | 2021-03-18 | 2021-04-01 | 2021-11-08 | Underground | R16 | 2021-04-01 | 1 |  | 11 | 158 | 168 | 2021 | 2021 | R16
167568164320 | 167412164320 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-26 | 2019-08-26 | 2019-09-12 |  | 2019-10-28 | Underground | R16 | 2019-10-14 | 1 | 14 | 23 | 11 | 46 | 2019 | 2019 | R16
160486222701 | 166307222701 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-02-24 | 2021-03-05 | 2021-03-05 |  | 2021-11-05 | Overhead | R16 | 2021-05-06 | 8 |  | 45 | 132 | 183 | 2021 | 2021 | R16
166142154847 | 168777154847 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-25 | 2019-01-25 | 2019-06-10 | 2019-09-04 | 2019-09-04 | Underground | R16 | 2019-09-04 | 1 | 97 | 63 |  | 159 | 2019 | 2019 | R16
167616162676 | 168380162676 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-29 | 2019-08-29 | 2019-08-29 |  | 2019-11-14 | Overhead | R16 | 2019-09-12 | 1 |  | 11 | 46 | 56 | 2019 | 2019 | R16
167640163368 | 169389163368 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-09-05 | 2019-09-05 | 2019-09-05 |  | 2020-07-01 | Underground | R16 | 2020-04-29 | 1 |  | 170 | 46 | 215 | 2019 | 2020 | R16
166992237426 | 163732237426 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-09 | 2021-07-01 | 2021-07-01 | 2023-06-21 | 2023-06-08 | Overhead | R16 | 2023-06-21 | 169 |  | 515 |  | 674 | 2020 | 2023 | R16
166630215589 | 163525215589 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-28 | 2020-12-28 | 2020-12-28 |  | 2021-04-23 | Overhead | R16 | 2021-02-04 | 1 |  | 29 | 57 | 85 | 2020 | 2021 | R16
163253142884 | 162751142884 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-11 | 2019-02-12 | 2019-02-12 | 2019-02-26 | 2019-04-15 | Overhead | R16 | 2019-02-26 | 2 |  | 11 | 35 | 46 | 2019 | 2019 | R16
163857218452 | 169671218452 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-26 | 2021-01-26 | 2021-01-26 |  | 2021-06-03 | Overhead | R16 | 2021-03-08 | 1 |  | 30 | 64 | 93 | 2021 | 2021 | R16
161777213945 | 160214213945 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-11 | 2020-12-14 | 2020-12-14 | 2021-03-03 | 2021-03-04 | Underground | R16 | 2021-03-03 | 2 |  | 58 | 2 | 60 | 2020 | 2021 | R16
167772159579 | 162825159579 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-30 | 2019-07-30 | 2019-07-30 |  | 2019-09-25 | Overhead | R16 | 2019-09-17 | 1 |  | 36 | 7 | 42 | 2019 | 2019 | R16
163403203432 | 169775203432 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-10 | 2020-09-10 | 2020-09-11 |  | 2021-04-20 | Underground | R16 | 2021-01-21 | 1 | 2 | 95 | 64 | 159 | 2020 | 2021 | R16
168394212153 | 166674212153 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-23 | 2020-11-30 | 2020-11-30 |  | 2021-04-21 | Overhead | R16 | 2021-01-21 | 6 |  | 39 | 65 | 108 | 2020 | 2021 | R16
167774159663 | 163018159663 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-31 | 2019-07-31 | 2019-07-31 |  | 2021-11-10 | Overhead | R16 | 2020-01-23 | 1 |  | 127 | 470 | 596 | 2019 | 2021 | R16
167800163409 | 169314163409 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-05 | 2019-09-05 | 2019-09-05 |  | 2020-06-09 | Overhead | R16 | 2020-02-03 | 1 |  | 108 | 92 | 199 | 2019 | 2020 | R16
160346221956 | 161387221956 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-02 | 2021-03-02 | 2021-03-02 | 2021-09-21 | 2021-11-09 | Overhead | R16 | 2021-09-21 | 21 |  | 146 | 36 | 201 | 2021 | 2021 | R16
167801169163 | 168283169163 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-05 | 2019-07-05 | 2019-10-21 |  | 2019-11-27 | Underground | R16 | 2019-11-21 | 1 | 77 | 24 | 5 | 104 | 2019 | 2019 | R16
163257204100 | 161236204100 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-09-16 | 2020-09-16 | 2020-09-16 |  | 2021-07-19 | Overhead | R16 | 2020-11-18 | 1 |  | 46 | 174 | 219 | 2020 | 2021 | R16
163317228619 | 167570228619 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-01-15 | 2021-04-28 | 2021-04-29 |  | 2021-11-05 | Overhead | R16 | 2021-05-05 | 74 | 2 | 5 | 133 | 211 | 2021 | 2021 | R16
167812161235 | 163323161235 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-01 | 2019-08-09 | 2019-08-15 |  | 2019-09-05 | Underground | R16 | 2019-08-29 | 7 | 5 | 11 | 6 | 26 | 2019 | 2019 | R16
167816167488 | 167949167488 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-28 | 2019-08-28 | 2019-10-10 |  | 2020-06-09 | Underground | R16 | 2020-01-29 | 1 | 32 | 80 | 95 | 205 | 2019 | 2020 | R16
169895218274 | 169462218274 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-25 | 2021-01-25 | 2021-01-25 | 2021-03-23 | 2021-11-04 | Overhead | R16 | 2021-03-23 | 1 |  | 42 | 163 | 204 | 2021 | 2021 | R16
167825164149 | 160562164149 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-11 | 2019-09-11 | 2019-09-12 |  | 2019-10-16 | Overhead | R16 | 2019-10-01 | 1 | 2 | 14 | 12 | 26 | 2019 | 2019 | R16
162819209763 | 160438209763 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-26 | 2020-11-05 | 2020-11-05 | 2021-01-27 | 2021-04-23 | Overhead | R16 | 2021-01-27 | 9 |  | 60 | 63 | 130 | 2020 | 2021 | R16
162016216499 | 165577216499 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-07 | 2021-01-07 | 2021-01-07 | 2021-01-08 | 2021-05-05 | Overhead | R16 | 2021-01-08 | 1 |  | 2 | 84 | 85 | 2021 | 2021 | R16
167847158275 | 161024158275 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-19 | 2019-07-19 | 2019-07-19 |  | 2019-09-05 | Overhead | R16 | 2019-08-29 | 1 |  | 30 | 6 | 35 | 2019 | 2019 | R16
161645223902 | 160966223902 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-16 | 2021-03-16 | 2021-03-16 | 2021-04-01 | 2021-12-16 | Overhead | R16 | 2021-04-01 | 1 |  | 13 | 186 | 198 | 2021 | 2021 | R16
160383209222 | 169058209222 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-20 | 2020-10-30 | 2020-10-30 | 2020-11-11 | 2021-04-21 | Overhead | R16 | 2020-11-11 | 9 |  | 9 | 116 | 132 | 2020 | 2021 | R16
167862158277 | 161022158277 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-19 | 2019-07-19 | 2019-07-19 |  | 2019-09-03 | Overhead | R16 | 2019-08-26 | 1 |  | 27 | 7 | 33 | 2019 | 2019 | R16
169532254839 | 165206254839 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-05-13 | 2021-05-13 | 2021-11-04 | 2022-10-20 | 2022-11-16 | Underground | R16 | 2022-10-20 | 1 | 126 | 251 | 20 | 395 | 2021 | 2022 | R16
162517223338 | 160343223338 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-12 | 2021-03-12 | 2021-03-12 |  | 2021-08-18 | Overhead | R16 | 2021-06-16 | 1 |  | 69 | 46 | 114 | 2021 | 2021 | R16
162855206266 | 165659206266 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-05 | 2020-10-05 | 2020-10-05 | 2020-10-21 | 2021-07-07 | Overhead | R16 | 2020-10-21 | 1 |  | 13 | 186 | 198 | 2020 | 2021 | R16
167161147786 | 161172147786 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-02 | 2019-04-02 | 2019-04-02 | 2019-04-24 | 2019-04-24 | Overhead | R16 | 2019-04-24 | 1 |  | 17 |  | 17 | 2019 | 2019 | R16
161380224422 | 162383224422 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-04-01 | 2021-11-08 | Overhead | R16 | 2021-04-01 | 1 |  | 9 | 158 | 166 | 2021 | 2021 | R16
161662150431 | 165683150431 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-27 | 2019-04-27 | 2019-04-27 | 2019-12-19 | 2020-06-09 | Underground | R16 | 2019-12-19 | 0 |  | 169 | 124 | 292 | 2019 | 2020 | R16
167939162241 | 167330162241 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-25 | 2019-08-25 | 2019-08-25 |  | 2019-11-14 | Underground | R16 | 2019-11-06 | 0 |  | 53 | 7 | 59 | 2019 | 2019 | R16
166697148675 | 162375148675 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-09 | 2019-04-09 | 2019-04-09 | 2019-06-04 | 2019-08-12 | Overhead | R16 | 2019-06-04 | 1 |  | 41 | 50 | 90 | 2019 | 2019 | R16
167946161935 | 165594161935 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-08-15 | 2019-08-15 | 2019-08-22 |  | 2023-06-07 | Overhead | R16 | 2019-10-31 | 1 | 6 | 51 | 940 | 995 | 2019 | 2023 | R16
169305207567 | 168639207567 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-19 | 2020-10-19 | 2020-10-19 | 2020-10-28 | 2023-04-12 | Overhead | R16 | 2020-10-28 | 1 |  | 8 | 641 | 648 | 2020 | 2023 | R16
168011161866 | 168284161866 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-05 | 2019-07-05 | 2019-08-21 |  | 2019-10-08 | Underground | R16 | 2019-09-24 | 1 | 34 | 25 | 11 | 68 | 2019 | 2019 | R16
167013202595 | 169980202595 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-24 | 2020-07-24 | 2020-09-04 | 2020-09-14 | 2020-12-18 | Underground | R16 | 2020-09-14 | 1 | 31 | 7 | 70 | 106 | 2020 | 2020 | R16
168017160474 | 164462160474 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-08 | 2019-08-08 | 2019-08-08 |  | 2019-10-28 | Overhead | R16 | 2019-10-14 | 1 |  | 48 | 11 | 58 | 2019 | 2019 | R16
164884218779 | 166096218779 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-11 | 2021-01-11 | 2021-01-29 |  | 2021-08-10 | Underground | R16 | 2021-03-18 | 1 | 15 | 35 | 104 | 152 | 2021 | 2021 | R16
168020162757 | 168014162757 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-28 | 2019-08-30 | 2019-08-30 |  | 2021-05-20 | Overhead | R16 |  | 3 |  |  |  | 452 | 2019 | 2021 | R16
160126217794 | 166720217794 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-01-13 | 2021-01-21 | 2021-01-21 |  | 2021-11-05 | Overhead | R16 | 2021-05-10 | 7 |  | 78 | 130 | 213 | 2021 | 2021 | R16
160773220969 | 165271220969 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-18 | 2021-02-18 | 2021-02-18 | 2021-02-25 | 2021-11-08 | Overhead | R16 | 2021-02-25 | 1 |  | 6 | 183 | 188 | 2021 | 2021 | R16
162082216619 | 165786216619 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-08 | 2021-01-08 | 2021-01-08 | 2021-03-04 | 2021-06-03 | Overhead | R16 | 2021-03-04 | 1 |  | 40 | 66 | 105 | 2021 | 2021 | R16
168074164347 | 168814164347 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2019-09-03 | 2019-09-13 | 2019-09-13 |  | 2019-11-08 | Overhead | R16 | 2019-11-01 | 9 |  | 36 | 6 | 49 | 2019 | 2019 | R16
169091208010 | 165877208010 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-05 | 2020-10-05 | 2020-10-23 | 2020-11-19 | 2021-07-26 | Underground | R16 | 2020-11-19 | 1 | 15 | 20 | 178 | 211 | 2020 | 2021 | R16
168093158922 | 161806158922 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-24 | 2019-07-24 | 2019-07-24 |  | 2019-10-28 | Overhead | R16 | 2019-10-15 | 1 |  | 60 | 10 | 69 | 2019 | 2019 | R16
164074146817 | 169417146817 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-22 | 2019-03-22 | 2019-03-22 | 2019-04-23 | 2019-04-23 | Overhead | R16 | 2019-04-23 | 1 |  | 23 |  | 23 | 2019 | 2019 | R16
160448210033 | 169042210033 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-20 | 2020-10-20 | 2020-11-09 | 2021-08-16 | 2021-10-25 | Underground | R16 | 2021-08-16 | 1 | 15 | 201 | 51 | 265 | 2020 | 2021 | R16
168110159862 | 161371159862 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-22 | 2019-08-01 | 2019-08-02 |  | 2022-09-17 | Underground | R16 | 2019-09-20 | 9 | 2 | 36 | 781 | 825 | 2019 | 2022 | R16
161546226177 | 166057226177 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-11 | 2021-01-11 | 2021-04-09 | 2021-08-05 | 2021-12-09 | Underground | R16 | 2021-08-05 | 1 | 65 | 85 | 91 | 239 | 2021 | 2021 | R16
168138159872 | 162620159872 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-29 | 2019-08-02 | 2019-08-02 |  | 2019-11-08 | Underground | R16 | 2019-11-01 | 5 |  | 66 | 6 | 75 | 2019 | 2019 | R16
163449247800 | 164294247800 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2021-05-10 | 2021-07-09 | 2021-09-13 |  | 2021-11-09 | Overhead | R16 |  | 45 | 47 |  |  | 132 | 2021 | 2021 | R16
161294220789 | 162659220789 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-08 | 2021-02-18 | 2021-02-18 |  | 2021-10-25 | Overhead | R16 | 2021-04-28 | 9 |  | 50 | 129 | 186 | 2021 | 2021 | R16
166463148461 | 169691148461 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-24 | 2019-03-24 | 2019-04-07 | 2019-08-08 | 2023-06-08 | Underground | R16 | 2019-08-08 | 0 | 10 | 89 | 1001 | 1099 | 2019 | 2023 | R16
167541220618 | 162871220618 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-08 | 2021-02-16 | 2021-02-16 | 2021-02-27 | 2021-04-14 | Underground | R16 | 2021-02-27 | 7 |  | 9 | 33 | 48 | 2021 | 2021 | R16
161571236598 | 165864236598 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2021-05-17 | 2021-05-17 | 2021-06-26 | 2021-11-17 | 2021-12-08 | Underground | R16 | 2021-11-17 | 1 | 30 | 103 | 16 | 148 | 2021 | 2021 | R16
163445203045 | 169087203045 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-08 | 2020-09-08 | 2020-09-08 |  | 2021-07-02 | Overhead | R16 | 2020-10-22 | 1 |  | 33 | 182 | 214 | 2020 | 2021 | R16
167198230981 | 161014230981 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-27 | 2021-04-27 | 2021-05-16 |  | 2021-08-23 | Underground | R16 | 2021-07-28 | 1 | 14 | 53 | 19 | 85 | 2021 | 2021 | R16
162456145228 | 166841145228 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-07 | 2019-03-07 | 2019-03-07 | 2020-06-24 | 2020-07-07 | Overhead | R16 | 2020-06-24 | 1 |  | 340 | 10 | 349 | 2019 | 2020 | R16
167269198504 | 160208198504 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-27 | 2020-07-27 | 2020-07-27 |  | 2020-11-02 | Overhead | R16 | 2020-09-02 | 1 |  | 28 | 44 | 71 | 2020 | 2020 | R16
163207155003 | 169471155003 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-01-28 | 2019-01-29 | 2019-06-11 | 2019-11-14 | 2019-11-15 | Underground | R16 | 2019-11-14 | 2 | 96 | 113 | 2 | 210 | 2019 | 2019 | R16
168276158899 | 162182158899 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-26 | 2019-07-26 | 2019-07-26 |  | 2019-09-12 | Overhead | R16 | 2019-09-06 | 1 |  | 31 | 5 | 35 | 2019 | 2019 | R16
166886206702 | 167010206702 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-09 | 2020-10-09 | 2020-10-09 |  | 2021-04-14 | Overhead | R16 | 2020-12-14 | 1 |  | 47 | 88 | 134 | 2020 | 2021 | R16
168331159583 | 162770159583 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-30 | 2019-07-30 | 2019-07-30 |  | 2020-08-14 | Overhead | R16 | 2020-06-22 | 1 |  | 235 | 40 | 274 | 2019 | 2020 | R16
161318233510 | 163666233510 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-11-09 | 2020-11-24 | 2021-06-04 | 2021-07-21 | 2021-12-29 | Underground | R16 | 2021-07-21 | 12 | 139 | 34 | 116 | 298 | 2020 | 2021 | R16
161751229180 | 167260229180 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-28 | 2021-04-30 | 2021-05-02 | 2021-06-30 | 2021-08-12 | Overhead | R16 | 2021-06-30 | 45 | 1 | 43 | 32 | 119 | 2021 | 2021 | R16
168346162602 | 167795162602 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-27 | 2019-08-27 | 2019-08-27 |  | 2019-09-26 | Overhead | R16 | 2019-09-19 | 1 |  | 18 | 6 | 23 | 2019 | 2019 | R16
165430229470 | 161871229470 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-30 | 2021-04-30 | 2021-05-04 | 2021-05-23 | 2023-10-16 | Overhead | R16 | 2021-05-23 | 1 | 3 | 14 | 626 | 642 | 2021 | 2023 | R16
162476146639 | 167565146639 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-03-11 | 2019-03-11 | 2019-03-20 | 2019-06-14 | 2019-06-17 | Overhead | R16 | 2019-06-14 | 1 | 8 | 63 | 2 | 71 | 2019 | 2019 | R16
163252152240 | 166009152240 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-29 | 2019-04-29 | 2019-05-13 | 2020-10-28 | 2021-04-14 | Underground | R16 | 2020-10-28 | 1 | 11 | 383 | 121 | 513 | 2019 | 2021 | R16
168515221435 | 161880221435 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-02 | 2020-11-02 | 2021-02-24 | 2021-03-24 | 2021-08-05 | Overhead | R16 | 2021-03-24 | 1 | 83 | 21 | 97 | 199 | 2020 | 2021 | R16
168692161030 | 161767161030 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-07-24 | 2019-07-24 | 2019-08-12 |  | 2021-11-13 | Underground | R16 | 2020-02-20 | 1 | 14 | 139 | 452 | 603 | 2019 | 2021 | R16
169874233701 | 168147233701 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2021-05-19 | 2021-05-19 | 2021-06-05 | 2021-09-07 | 2021-09-08 | Underground | R16 | 2021-09-07 | 1 | 13 | 67 | 2 | 81 | 2021 | 2021 | R16
165678212755 | 163344212755 | NON-RESIDENTIAL - HEALTH CARE | R16 RESD AND NON RESD US | Commercial | 2020-08-12 | 2020-08-12 | 2020-12-04 | 2023-04-03 | 2023-07-05 | Underground | R16 | 2023-04-03 | 1 | 83 | 607 | 68 | 756 | 2020 | 2023 | R16
163873152347 | 165983152347 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-04-29 | 2019-05-13 | 2019-05-14 | 2019-07-26 | 2020-01-24 | Underground | R16 | 2019-07-26 | 11 | 2 | 54 | 131 | 195 | 2019 | 2020 | R16
166466225311 | 163390225311 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-25 | 2021-03-30 | 2021-03-30 |  | 2023-06-10 | Underground | R16 | 2023-01-25 | 4 |  | 477 | 98 | 577 | 2021 | 2023 | R16
162777226580 | 167572226580 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-01 | 2021-04-07 | 2021-04-12 |  | 2023-04-19 | Overhead | R16 |  | 28 | 4 |  |  | 558 | 2021 | 2023 | R16
168705164287 | 160855164287 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-12 | 2019-09-12 | 2019-09-12 |  | 2022-08-02 | Overhead | R16 |  | 1 |  |  |  | 754 | 2019 | 2022 | R16
168708159626 | 162750159626 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-30 | 2019-07-31 | 2019-07-31 |  | 2020-06-09 | Overhead | R16 | 2020-04-06 | 2 |  | 179 | 47 | 226 | 2019 | 2020 | R16
168744163400 | 167331163400 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-26 | 2019-08-26 | 2019-09-05 |  | 2019-10-28 | Underground | R16 | 2019-10-17 | 1 | 9 | 31 | 8 | 46 | 2019 | 2019 | R16
168759159944 | 163418159944 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-02 | 2019-08-02 | 2019-08-02 |  | 2019-09-18 | Underground | R16 | 2019-09-09 | 1 |  | 27 | 8 | 34 | 2019 | 2019 | R16
168784262930 | 164239262930 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-11-21 | 2019-11-21 | 2021-12-30 |  | 2023-02-03 | Underground | R16 |  | 1 | 551 |  |  | 837 | 2019 | 2023 | R16
168794160237 | 163876160237 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-06 | 2019-08-06 | 2019-08-06 |  | 2019-09-11 | Overhead | R16 | 2019-09-11 | 1 |  | 27 |  | 27 | 2019 | 2019 | R16
162780228344 | 166732228344 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-08 | 2021-04-26 | 2021-04-26 | 2021-06-30 | 2021-07-01 | Overhead | R16 | 2021-06-30 | 13 |  | 48 | 2 | 61 | 2021 | 2021 | R16
168833178520 | 166357178520 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-28 | 2020-01-28 | 2020-01-28 |  | 2020-07-08 | Overhead | R16 | 2020-04-20 | 1 |  | 60 | 58 | 117 | 2020 | 2020 | R16
162281223034 | 161671223034 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2021-02-02 | 2021-02-02 | 2021-03-10 | 2021-03-16 | 2021-05-11 | Overhead | R16 | 2021-03-16 | 1 | 27 | 5 | 41 | 71 | 2021 | 2021 | R16
166819281933 | 163194281933 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-05-05 | 2021-05-05 | 2022-06-08 |  | 2023-04-03 | Overhead | R16 | 2023-02-28 | 1 | 286 | 190 | 25 | 499 | 2021 | 2023 | R16
165711215875 | 164312215875 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-31 | 2020-12-31 | 2020-12-31 | 2021-01-07 | 2021-05-05 | Overhead | R16 | 2021-01-07 | 1 |  | 6 | 85 | 90 | 2020 | 2021 | R16
168896162774 | 168491162774 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-30 | 2019-08-30 | 2019-08-30 |  | 2019-09-26 | Overhead | R16 | 2019-09-20 | 1 |  | 16 | 5 | 20 | 2019 | 2019 | R16
168897158022 | 160176158022 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-16 | 2019-07-16 | 2019-07-16 |  | 2019-09-11 | Overhead | R16 | 2019-09-05 | 1 |  | 38 | 5 | 42 | 2019 | 2019 | R16
161236250163 | 163371250163 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-06 | 2021-05-06 | 2021-09-30 |  | 2021-11-08 | Underground | R16 | 2021-11-04 | 1 | 106 | 26 | 3 | 133 | 2021 | 2021 | R16
169000158721 | 169001158721 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-09 | 2019-07-09 | 2019-07-22 |  | 2019-09-11 | Overhead | R16 | 2019-09-04 | 1 | 10 | 33 | 6 | 47 | 2019 | 2019 | R16
163986252192 | 161519252192 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-02 | 2021-02-02 | 2021-10-15 | 2021-12-22 | 2022-01-24 | Underground | R16 | 2021-12-22 | 1 | 184 | 49 | 24 | 255 | 2021 | 2022 | R16
169009159749 | 163221159749 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-01 | 2019-08-01 | 2019-08-01 |  | 2019-10-28 | Underground | R16 | 2019-10-18 | 1 |  | 57 | 7 | 63 | 2019 | 2019 | R16
169020161984 | 165675161984 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-15 | 2019-08-22 | 2019-08-22 |  | 2019-11-27 | Overhead | R16 | 2019-11-22 | 6 |  | 67 | 4 | 75 | 2019 | 2019 | R16
165578214127 | 160125214127 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-11 | 2020-12-14 | 2020-12-15 | 2020-12-16 | 2021-01-08 | Underground | R16 | 2020-12-16 | 2 | 2 | 2 | 18 | 21 | 2020 | 2021 | R16
168133227638 | 168569227638 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-16 | 2021-04-20 | 2021-04-20 |  | 2021-08-18 | Overhead | R16 | 2021-06-16 | 3 |  | 42 | 46 | 89 | 2021 | 2021 | R16
169029168156 | 166804168156 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-14 | 2019-10-14 | 2019-10-14 |  | 2019-12-30 | Overhead | R16 | 2019-12-04 | 1 |  | 38 | 19 | 56 | 2019 | 2019 | R16
166860145311 | 167389145311 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-09 | 2019-03-09 | 2019-03-09 | 2019-09-19 | 2019-12-03 | Overhead | R16 | 2019-09-19 | 0 |  | 139 | 54 | 192 | 2019 | 2019 | R16
169037159791 | 163280159791 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-08-01 | 2019-08-01 | 2019-08-02 |  | 2020-06-09 | Overhead | R16 | 2020-03-06 | 1 | 2 | 156 | 68 | 224 | 2019 | 2020 | R16
169752207351 | 168321207351 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-15 | 2020-10-15 | 2020-10-15 | 2020-11-25 | 2021-04-07 | Overhead | R16 | 2020-11-25 | 1 |  | 30 | 96 | 125 | 2020 | 2021 | R16
168433222334 | 162939222334 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-24 | 2020-09-24 | 2021-03-03 |  | 2021-11-05 | Underground | R16 | 2021-05-07 | 1 | 115 | 48 | 131 | 292 | 2020 | 2021 | R16
169091158958 | 162071158958 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-25 | 2019-07-25 | 2019-07-25 |  | 2023-06-05 | Overhead | R16 | 2019-09-11 | 1 |  | 35 | 974 | 1008 | 2019 | 2023 | R16
160349202413 | 167873202413 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-31 | 2020-08-31 | 2020-08-31 |  | 2022-03-25 | Underground | R16 | 2022-03-24 | 1 |  | 409 | 2 | 410 | 2020 | 2022 | R16
167290268328 | 166859268328 | NON-RESIDENTIAL - WAREHOUSE | UG R16 RESD AND NON RESD UD | Commercial | 2021-01-14 | 2021-01-14 | 2022-02-09 | 2022-04-29 | 2022-05-11 | Underground | R16 | 2022-04-29 | 1 | 280 | 58 | 9 | 345 | 2021 | 2022 | R16
169095161596 | 166401161596 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-20 | 2019-08-20 | 2019-08-20 |  | 2019-10-09 | Overhead | R16 | 2019-09-25 | 1 |  | 27 | 11 | 37 | 2019 | 2019 | R16
169268202059 | 165803202059 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-21 | 2020-08-29 | 2020-08-29 | 2020-10-15 | 2021-02-23 | Overhead | R16 | 2020-10-15 | 6 |  | 34 | 94 | 133 | 2020 | 2021 | R16
166439200207 | 162846200207 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-10 | 2020-08-10 | 2020-08-10 |  | 2020-10-06 | Overhead | R16 | 2020-08-27 | 1 |  | 14 | 29 | 42 | 2020 | 2020 | R16
169102161808 | 166528161808 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-21 | 2019-08-21 | 2019-08-21 |  | 2019-09-24 | Overhead | R16 | 2019-09-17 | 1 |  | 20 | 6 | 25 | 2019 | 2019 | R16
166303218402 | 169023218402 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-22 | 2021-01-22 | 2021-01-25 | 2021-02-14 | 2021-02-24 | Overhead | R16 | 2021-02-14 | 1 | 2 | 15 | 8 | 24 | 2021 | 2021 | R16
169103163836 | 160083163836 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-09 | 2019-09-10 | 2019-09-10 |  | 2021-11-10 | Overhead | R16 | 2019-12-19 | 2 |  | 73 | 495 | 568 | 2019 | 2021 | R16
160430231500 | 168068231500 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-19 | 2021-05-19 | 2021-05-19 | 2021-08-09 | 2021-08-10 | Overhead | R16 | 2021-08-09 | 1 |  | 59 | 2 | 60 | 2021 | 2021 | R16
161819210471 | 164609210471 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-12 | 2020-11-12 | 2020-11-12 | 2020-12-18 | 2021-04-16 | Overhead | R16 | 2020-12-18 | 1 |  | 27 | 86 | 112 | 2020 | 2021 | R16
161033221745 | 166770221745 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-25 | 2021-02-25 | 2021-02-25 |  | 2021-11-08 | Overhead | R16 | 2021-09-22 | 1 |  | 150 | 34 | 183 | 2021 | 2021 | R16
169211160215 | 162789160215 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-30 | 2019-07-30 | 2019-08-07 |  | 2019-11-08 | Underground | R16 | 2019-10-29 | 1 | 7 | 60 | 9 | 74 | 2019 | 2019 | R16
169241161284 | 165591161284 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-14 | 2019-08-14 | 2019-08-15 |  | 2019-10-28 | Overhead | R16 | 2019-10-15 | 1 | 2 | 44 | 10 | 54 | 2019 | 2019 | R16
163452223073 | 169845223073 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-10 | 2021-03-10 | 2021-03-10 |  | 2022-10-19 | Overhead | R16 |  | 1 |  |  |  | 421 | 2021 | 2022 | R16
163574150162 | 160061150162 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-26 | 2019-04-23 | 2019-04-23 | 2019-05-14 | 2019-05-15 | Overhead | R16 | 2019-05-14 | 21 |  | 16 | 2 | 37 | 2019 | 2019 | R16
169243163185 | 168899163185 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-09-03 | 2019-09-03 | 2019-09-03 |  | 2019-09-19 | Overhead | R16 | 2019-09-12 | 1 |  | 8 | 6 | 13 | 2019 | 2019 | R16
165780210618 | 162227210618 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-03 | 2020-11-16 | 2020-11-16 |  | 2021-04-20 | Overhead | R16 | 2021-01-11 | 10 |  | 41 | 72 | 121 | 2020 | 2021 | R16
169247180944 | 160791180944 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-07-18 | 2019-07-18 | 2020-02-18 |  | 2020-07-10 | Underground | R16 | 2020-06-10 | 1 | 154 | 82 | 23 | 257 | 2019 | 2020 | R16
169336209832 | 163128209832 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-06 | 2020-11-06 | 2020-11-06 |  | 2021-04-07 | Overhead | R16 | 2020-12-01 | 1 |  | 18 | 92 | 109 | 2020 | 2021 | R16
169980252563 | 169150252563 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-10-20 | 2021-07-20 | 2021-10-18 | 2021-12-30 | 2022-02-11 | Underground | R16 | 2021-12-30 | 196 | 65 | 54 | 32 | 344 | 2020 | 2022 | R16
169255159885 | 162962159885 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-31 | 2019-07-31 | 2019-08-02 |  | 2021-11-13 | Underground | R16 | 2019-12-17 | 1 | 3 | 98 | 499 | 598 | 2019 | 2021 | R16
169261164404 | 163637164404 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-08-05 | 2019-08-16 | 2019-09-13 |  | 2019-10-15 | Underground | R16 |  | 10 | 21 |  |  | 52 | 2019 | 2019 | R16
161564217424 | 164857217424 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-05 | 2021-01-11 | 2021-01-14 | 2021-02-24 | 2021-04-16 | Underground | R16 | 2021-02-24 | 5 | 4 | 30 | 38 | 74 | 2021 | 2021 | R16
164750214367 | 160753214367 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-14 | 2020-12-17 | 2020-12-17 | 2021-02-08 | 2021-08-11 | Overhead | R16 | 2021-02-08 | 4 |  | 38 | 133 | 173 | 2020 | 2021 | R16
161277149881 | 162382149881 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-04-08 | 2019-04-08 | 2019-04-22 | 2019-06-11 | 2019-06-12 | Underground | R16 | 2019-06-11 | 1 | 11 | 37 | 2 | 48 | 2019 | 2019 | R16
168798207332 | 168359207332 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-16 | 2020-10-16 | 2020-10-16 | 2020-11-09 | 2023-04-12 | Overhead | R16 | 2020-11-09 | 1 |  | 17 | 633 | 649 | 2020 | 2023 | R16
164103228615 | 163090228615 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-24 | 2021-03-24 | 2021-04-28 | 2023-02-06 | 2023-02-13 | Underground | R16 | 2023-02-06 | 1 | 26 | 464 | 6 | 494 | 2021 | 2023 | R16
162248231554 | 168576231554 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-20 | 2021-05-20 | 2021-05-20 | 2021-07-16 | 2021-10-25 | Overhead | R16 | 2021-07-16 | 1 |  | 42 | 72 | 113 | 2021 | 2021 | R16
165104234511 | 163457234511 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2020-11-07 | 2021-06-02 | 2021-06-10 |  | 2022-05-05 | Overhead | R16 |  | 148 | 7 |  |  | 389 | 2020 | 2022 | R16
166908217442 | 164910217442 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-05 | 2021-01-14 | 2021-01-14 | 2021-04-22 | 2021-11-13 | Overhead | R16 | 2021-04-22 | 8 |  | 71 | 147 | 224 | 2021 | 2021 | R16
166622286519 | 160365286519 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-26 | 2022-07-22 | 2022-07-22 |  | 2022-10-26 | Overhead | R16 | 2022-09-15 | 325 |  | 40 | 30 | 393 | 2021 | 2022 | R16
166867198128 | 169634198128 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-22 | 2020-07-22 | 2020-07-22 | 2021-01-22 | 2021-04-21 | Overhead | R16 | 2021-01-22 | 1 |  | 133 | 64 | 196 | 2020 | 2021 | R16
162080244884 | 164487244884 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-30 | 2021-03-30 | 2021-08-23 | 2021-09-28 | 2021-11-13 | Underground | R16 | 2021-09-28 | 1 | 105 | 27 | 34 | 164 | 2021 | 2021 | R16
165598228844 | 168962228844 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-04-19 | 2021-04-29 | 2021-04-29 |  | 2021-10-25 | Underground | R16 | 2021-09-17 | 9 |  | 102 | 27 | 136 | 2021 | 2021 | R16
169421162864 | 168447162864 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-30 | 2019-08-30 | 2019-08-30 |  | 2019-11-13 | Overhead | R16 | 2019-11-04 | 1 |  | 47 | 8 | 54 | 2019 | 2019 | R16
161054156703 | 163005156703 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2019-06-10 | 2019-06-10 | 2019-06-28 | 2019-12-12 | 2020-02-06 | Underground | R16 | 2019-12-12 | 1 | 15 | 120 | 41 | 174 | 2019 | 2020 | R16
168356152123 | 161126152123 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-04-02 | 2019-04-02 | 2019-05-13 | 2019-07-15 | 2019-12-31 | Underground | R16 | 2019-07-15 | 1 | 30 | 46 | 122 | 196 | 2019 | 2019 | R16
169507166222 | 167432166222 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-26 | 2019-08-26 | 2019-09-30 |  | 2019-11-13 | Underground | R16 | 2019-11-05 | 1 | 26 | 27 | 7 | 58 | 2019 | 2019 | R16
162496151266 | 167253151266 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-08-28 | 2019-09-18 | Overhead | R16 | 2019-08-28 | 1 |  | 84 | 16 | 99 | 2019 | 2019 | R16
160874238555 | 165794238555 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-16 | 2021-05-18 | 2021-07-13 | 2021-07-26 | 2021-07-29 | Underground | R16 | 2021-07-26 | 2 | 41 | 10 | 4 | 54 | 2021 | 2021 | R16
169545158985 | 161813158985 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-24 | 2019-07-24 | 2019-07-24 |  | 2019-09-05 | Overhead | R16 | 2019-08-29 | 1 |  | 27 | 6 | 32 | 2019 | 2019 | R16
160257155185 | 164100155185 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-04-17 | 2019-06-10 | 2019-06-12 | 2019-06-24 | 2019-06-24 | Underground | R16 | 2019-06-24 | 39 | 3 | 9 |  | 49 | 2019 | 2019 | R16
163115197857 | 169302197857 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-21 | 2020-07-21 | 2020-07-21 |  | 2021-07-26 | Overhead | R16 | 2020-11-06 | 1 |  | 79 | 187 | 265 | 2020 | 2021 | R16
169629159698 | 162090159698 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-07-25 | 2019-07-25 | 2019-08-01 |  | 2020-12-29 | Underground | R16 | 2020-09-25 | 1 | 6 | 302 | 68 | 374 | 2019 | 2020 | R16
169637162586 | 165080162586 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-12 | 2019-08-12 | 2019-08-27 |  | 2019-10-28 | Underground | R16 | 2019-10-17 | 1 | 12 | 38 | 8 | 56 | 2019 | 2019 | R16
168386217848 | 165631217848 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-10-02 | 2020-10-02 | 2021-01-20 |  | 2021-08-23 | Underground | R16 | 2021-07-15 | 1 | 79 | 127 | 28 | 232 | 2020 | 2021 | R16
163184219619 | 162243219619 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-04 | 2021-02-04 | 2021-02-04 |  | 2021-11-05 | Overhead | R16 | 2021-05-05 | 1 |  | 65 | 133 | 197 | 2021 | 2021 | R16
160583225479 | 165256225479 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2021-04-01 | 2021-04-02 | 2021-04-02 | 2021-05-20 | 2023-06-07 | Overhead | R16 | 2021-05-20 | 2 |  | 35 | 535 | 570 | 2021 | 2023 | R16
160792199438 | 161644199438 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-08-03 | 2020-08-03 | 2020-08-03 | 2020-08-04 | 2020-11-23 | Underground | R16 | 2020-08-04 | 1 |  | 2 | 80 | 81 | 2020 | 2020 | R16
169658165028 | 167373165028 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-26 | 2019-08-26 | 2019-09-18 |  | 2019-11-21 | Underground | R16 | 2019-11-13 | 1 | 18 | 41 | 7 | 64 | 2019 | 2019 | R16
160703206479 | 161681206479 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-17 | 2020-10-09 | 2020-10-09 | 2021-01-12 | 2021-04-21 | Overhead | R16 | 2021-01-12 | 17 |  | 68 | 72 | 155 | 2020 | 2021 | R16
167111153293 | 160749153293 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-24 | 2019-05-24 | 2019-05-24 | 2019-06-10 | 2019-06-13 | Overhead | R16 | 2019-06-10 | 1 |  | 12 | 4 | 15 | 2019 | 2019 | R16
169701165832 | 163036165832 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-26 | 2019-09-26 | 2019-09-26 |  | 2019-12-16 | Overhead | R16 | 2019-12-05 | 1 |  | 51 | 8 | 58 | 2019 | 2019 | R16
169736160351 | 162931160351 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-31 | 2019-08-06 | 2019-08-07 |  | 2019-10-16 | Overhead | R16 | 2019-10-08 | 5 | 2 | 45 | 7 | 56 | 2019 | 2019 | R16
164546214082 | 160971214082 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-15 | 2020-12-15 | 2020-12-15 |  | 2022-10-20 | Overhead | R16 |  | 1 |  |  |  | 483 | 2020 | 2022 | R16
165048152315 | 169288152315 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-15 | 2019-05-15 | 2019-05-15 | 2019-08-28 | 2019-09-11 | Overhead | R16 | 2019-08-28 | 1 |  | 76 | 11 | 86 | 2019 | 2019 | R16
168278227479 | 169332227479 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-20 | 2021-04-20 | 2021-04-20 |  | 2021-10-25 | Underground | R16 | 2021-07-22 | 1 |  | 68 | 68 | 135 | 2021 | 2021 | R16
164063203995 | 161330203995 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2020-09-16 | 2020-09-16 | 2020-09-16 |  | 2023-01-05 | Overhead | R16 |  | 1 |  |  |  | 602 | 2020 | 2023 | R16
163696141593 | 169339141593 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-28 | 2019-01-28 | 2019-01-28 | 2019-02-12 | 2019-02-13 | Underground | R16 | 2019-02-12 | 1 |  | 12 | 2 | 13 | 2019 | 2019 | R16
169831162357 | 167621162357 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-26 | 2019-08-26 | 2019-08-26 |  | 2019-09-25 | Overhead | R16 | 2019-09-25 | 1 |  | 23 |  | 23 | 2019 | 2019 | R16
169853158954 | 162026158954 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-25 | 2019-07-25 | 2019-07-25 |  | 2019-09-24 | Overhead | R16 | 2019-09-17 | 1 |  | 39 | 6 | 44 | 2019 | 2019 | R16
162335154879 | 162648154879 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-07 | 2019-06-07 | 2019-06-12 | 2020-05-07 | 2020-05-26 | Underground | R16 | 2020-05-07 | 1 | 4 | 237 | 14 | 253 | 2019 | 2020 | R16
167224204406 | 161991204406 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-19 | 2020-09-19 | 2020-09-19 |  | 2020-12-29 | Overhead | R16 | 2020-09-28 | 0 |  | 6 | 67 | 72 | 2020 | 2020 | R16
162235209363 | 162145209363 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-11-02 | 2020-11-02 | 2020-11-02 | 2020-11-05 | 2021-07-26 | Overhead | R16 | 2020-11-05 | 1 |  | 4 | 188 | 191 | 2020 | 2021 | R16
169930160575 | 164349160575 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-08 | 2019-08-08 | 2019-08-08 |  | 2021-06-29 | Overhead | R16 | 2019-10-03 | 1 |  | 41 | 454 | 494 | 2019 | 2021 | R16
161639144268 | 162341144268 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-02-08 | 2019-02-08 | 2019-02-25 | 2019-11-20 | 2020-01-02 | Underground | R16 | 2019-11-20 | 1 | 12 | 193 | 32 | 235 | 2019 | 2020 | R16
169072221561 | 160613221561 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-27 | 2020-10-27 | 2021-02-24 | 2021-08-12 | 2021-09-13 | Underground | R16 | 2021-08-12 | 1 | 87 | 122 | 23 | 230 | 2020 | 2021 | R16
163254223465 | 160389223465 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-12 |  | 2021-03-12 |  | 2021-11-09 | Overhead | R16 | 2021-10-05 |  |  | 148 | 26 | 173 | 2021 | 2021 | R16
169951173137 | 161240173137 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-16 | 2019-09-16 | 2019-12-02 |  | 2020-06-09 | Underground | R16 | 2019-12-31 | 1 | 56 | 22 | 116 | 192 | 2019 | 2020 | R16
169973160362 | 163884160362 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-06 | 2019-08-06 | 2019-08-06 |  | 2023-06-08 | Overhead | R16 | 2019-10-29 | 1 |  | 61 | 943 | 1003 | 2019 | 2023 | R16
161844212241 | 167349212241 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-30 | 2020-11-30 | 2020-11-30 | 2021-01-29 | 2021-02-01 | Overhead | R16 | 2021-01-29 | 1 |  | 45 | 2 | 46 | 2020 | 2021 | R16
164567214383 | 165315214383 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-17 | 2020-12-17 | 2020-12-17 | 2021-02-03 | 2021-05-06 | Overhead | R16 | 2021-02-03 | 23 |  | 35 | 67 | 123 | 2020 | 2021 | R16
160063164756 | 165848164756 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2019-08-16 | 2019-08-16 | 2019-09-18 |  | 2019-12-18 | Underground | R16 | 2019-12-09 | 1 | 24 | 59 | 8 | 89 | 2019 | 2019 | R16
168304144233 | 161368144233 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-05 | 2019-02-05 | 2019-02-26 | 2019-05-25 | 2019-05-28 | Underground | R16 | 2019-05-25 | 1 | 16 | 64 | 2 | 81 | 2019 | 2019 | R16
167464216548 | 164948216548 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-05 | 2021-01-07 | 2021-01-07 |  | 2021-11-08 | Overhead | R16 | 2021-04-20 | 3 |  | 74 | 145 | 220 | 2021 | 2021 | R16
160123162786 | 166800162786 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-21 | 2019-08-21 | 2019-08-30 |  | 2019-10-14 | Underground | R16 | 2019-10-03 | 1 | 8 | 25 | 8 | 39 | 2019 | 2019 | R16
160164160226 | 163700160226 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-05 | 2019-08-05 | 2019-08-05 |  | 2019-10-28 | Overhead | R16 | 2019-10-16 | 1 |  | 53 | 9 | 61 | 2019 | 2019 | R16
168394161279 | 165778161279 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-03-01 | 2019-06-04 | 2019-08-15 | 2020-06-22 | 2020-08-31 | Underground | R16 | 2020-06-22 | 68 | 53 | 223 | 51 | 392 | 2019 | 2020 | R16
162458212097 | 166393212097 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-07 | 2020-10-07 | 2020-11-30 |  | 2022-08-03 | Underground | R16 | 2022-06-16 | 1 | 39 | 404 | 35 | 476 | 2020 | 2022 | R16
163370225469 | 162649225469 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-08-10 | 2020-09-24 | 2021-04-01 |  | 2021-11-03 | Underground | R16 |  | 34 | 136 |  |  | 323 | 2020 | 2021 | R16
162415203478 | 160398203478 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-11 | 2020-09-11 | 2020-09-11 | 2021-05-03 | 2021-11-08 | Overhead | R16 | 2021-05-03 | 1 |  | 167 | 136 | 302 | 2020 | 2021 | R16
160593229773 | 161390229773 | RULE 20.B | UG DIST R20B CONV SINGLE SVC US | Residential | 2021-04-29 | 2021-04-29 | 2021-05-06 | 2022-04-20 | 2021-10-05 | Underground | R16 | 2022-04-20 | 1 | 6 | 250 |  | 114 | 2021 | 2021 | R16
160294176764 | 162937176764 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2020-01-13 | 2020-01-13 | 2020-01-13 |  | 2020-07-09 | Underground | R16 | 2020-05-28 | 1 |  | 99 | 31 | 129 | 2020 | 2020 | R16
167733217172 | 167371217172 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-15 | 2021-01-15 | 2021-01-15 |  | 2021-05-05 | Overhead | R16 | 2021-02-17 | 1 |  | 24 | 56 | 79 | 2021 | 2021 | R16
160333143951 | 164769143951 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-02-22 | 2019-02-22 | 2019-02-22 | 2019-03-26 | 2019-03-26 | Overhead | R16 | 2019-03-26 | 1 |  | 23 |  | 23 | 2019 | 2019 | R16
160461151591 | 167665151591 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-05-07 | 2019-05-07 | 2019-05-07 | 2020-02-21 | 2021-03-10 | Underground | R16 | 2020-02-21 | 1 |  | 209 | 274 | 482 | 2019 | 2021 | R16
163417247677 | 169593247677 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Residential | 2020-07-22 | 2020-07-22 | 2021-09-14 | 2022-05-13 | 2022-06-03 | Underground | R16 | 2022-05-13 | 1 | 300 | 174 | 16 | 488 | 2020 | 2022 | R16
160325162087 | 167255162087 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-24 | 2019-08-24 | 2019-08-24 |  | 2019-10-08 | Overhead | R16 | 2019-09-24 | 0 |  | 22 | 11 | 32 | 2019 | 2019 | R16
166099201133 | 165237201133 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-08-19 | 2020-08-19 | 2020-08-19 |  | 2020-10-29 | Underground | R16 | 2020-09-02 | 1 |  | 11 | 42 | 52 | 2020 | 2020 | R16
168739225576 | 169294225576 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-25 | 2021-01-25 | 2021-04-05 |  | 2021-08-30 | Underground | R16 | 2021-06-10 | 1 | 51 | 49 | 58 | 156 | 2021 | 2021 | R16
160428158720 | 161222158720 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-22 | 2019-07-22 | 2019-07-22 |  | 2019-11-17 | Overhead | R16 |  | 1 |  |  |  | 85 | 2019 | 2019 | R16
168074233038 | 160254233038 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-27 | 2021-06-03 | 2021-06-03 | 2021-11-18 | 2021-11-19 | Overhead | R16 | 2021-11-18 | 6 |  | 121 | 2 | 127 | 2021 | 2021 | R16
167209205985 | 165223205985 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-01 | 2020-10-01 | 2020-10-01 |  | 2022-09-28 | Overhead | R16 |  | 1 |  |  |  | 520 | 2020 | 2022 | R16
165857148534 | 167556148534 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-16 | 2019-01-16 | 2019-04-09 | 2019-07-03 | 2019-07-03 | Underground | R16 | 2019-07-03 | 1 | 60 | 62 |  | 121 | 2019 | 2019 | R16
161059208665 | 160710208665 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-27 | 2020-10-27 | 2020-10-27 |  | 2021-04-22 | Overhead | R16 | 2021-02-01 | 1 |  | 70 | 59 | 128 | 2020 | 2021 | R16
160568167651 | 166186167651 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-10 | 2019-10-10 | 2019-10-10 |  | 2022-08-02 | Overhead | R16 |  | 1 |  |  |  | 734 | 2019 | 2022 | R16
160571163348 | 168999163348 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-04 | 2019-09-04 | 2019-09-04 |  | 2022-10-20 | Overhead | R16 |  | 1 |  |  |  | 817 | 2019 | 2022 | R16
163505224615 | 163359224615 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-25 | 2021-03-25 | 2021-03-25 | 2021-10-07 | 2022-02-09 | Overhead | R16 | 2021-10-07 | 1 |  | 141 | 90 | 230 | 2021 | 2022 | R16
169376217479 | 162717217479 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-22 | 2020-12-22 | 2021-01-19 |  | 2021-08-23 | Underground | R16 | 2021-04-06 | 1 | 21 | 56 | 100 | 175 | 2020 | 2021 | R16
167803202789 | 164505202789 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-18 | 2020-08-18 | 2020-09-04 | 2020-09-16 | 2021-07-07 | Underground | R16 | 2020-09-16 | 1 | 14 | 9 | 211 | 232 | 2020 | 2021 | R16
166681228702 | 161140228702 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-28 | 2021-04-28 | 2021-04-28 |  | 2021-09-01 | Overhead | R16 | 2021-08-09 | 1 |  | 74 | 18 | 91 | 2021 | 2021 | R16
169812222078 | 167970222078 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-03 | 2021-03-03 | 2021-03-03 | 2021-05-07 | 2021-05-10 | Overhead | R16 | 2021-05-07 | 1 |  | 48 | 2 | 49 | 2021 | 2021 | R16
160657161732 | 166515161732 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-20 | 2019-08-20 | 2019-08-20 |  | 2019-10-28 | Overhead | R16 | 2019-10-14 | 1 |  | 40 | 11 | 50 | 2019 | 2019 | R16
160659161648 | 163670161648 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-05 | 2019-08-05 | 2019-08-20 |  | 2019-11-21 | Underground | R16 | 2019-11-12 | 1 | 12 | 61 | 8 | 79 | 2019 | 2019 | R16
160886143098 | 163151143098 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-02-12 | 2019-02-13 | 2019-02-13 |  | 2019-03-08 | Overhead | R16 |  | 2 |  |  |  | 19 | 2019 | 2019 | R16
167248216114 | 161390216114 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-12-17 | 2020-12-17 | 2021-01-05 |  | 2022-03-09 | Underground | R16 |  | 1 | 14 |  |  | 320 | 2020 | 2022 | R16
161789145609 | 162366145609 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-08 | 2019-02-08 | 2019-03-11 | 2022-09-16 | 2022-09-19 | Underground | R16 | 2022-09-16 | 1 | 22 | 920 | 2 | 942 | 2019 | 2022 | R16
161538204952 | 166185204952 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-24 | 2020-08-24 | 2020-09-25 |  | 2021-04-14 | Underground | R16 | 2020-12-17 | 1 | 25 | 60 | 85 | 168 | 2020 | 2021 | R16
162142210453 | 164552210453 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-12 | 2020-11-12 | 2020-11-12 |  | 2021-12-06 | Overhead | R16 | 2020-12-29 | 1 |  | 34 | 245 | 278 | 2020 | 2021 | R16
160819174290 | 166181174290 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-19 | 2019-09-23 | 2019-12-12 |  | 2021-11-13 | Overhead | R16 |  | 26 | 59 |  |  | 585 | 2019 | 2021 | R16
168041204833 | 169973204833 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-24 | 2020-07-24 | 2020-09-23 | 2021-02-08 | 2021-08-06 | Underground | R16 | 2021-02-08 | 1 | 44 | 99 | 130 | 271 | 2020 | 2021 | R16
169083201945 | 166811201945 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-26 | 2020-08-26 | 2020-08-26 |  | 2021-06-14 | Overhead | R16 | 2020-09-25 | 1 |  | 23 | 187 | 209 | 2020 | 2021 | R16
160833161003 | 164968161003 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-12 | 2019-08-12 | 2019-08-12 |  | 2019-09-12 | Overhead | R16 | 2019-08-30 | 1 |  | 15 | 10 | 24 | 2019 | 2019 | R16
161399241163 | 168872241163 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2020-10-19 | 2021-03-29 | 2021-07-28 |  | 2022-04-20 | Overhead | R16 |  | 116 | 88 |  |  | 393 | 2020 | 2022 | R16
160835164871 | 161634164871 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-18 | 2019-09-18 | 2019-09-18 |  | 2019-10-30 | Overhead | R16 | 2019-10-21 | 1 |  | 24 | 8 | 31 | 2019 | 2019 | R16
165378205605 | 164094205605 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-28 | 2020-09-28 | 2020-09-28 | 2021-02-03 | 2021-06-02 | Overhead | R16 | 2021-02-03 | 1 |  | 93 | 86 | 178 | 2020 | 2021 | R16
160836252583 | 160131252583 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-04-23 | 2021-04-28 | 2021-10-18 |  | 2022-01-18 | Overhead | R16 |  | 4 | 124 |  |  | 193 | 2021 | 2022 | R16
165025199076 | 168867199076 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-20 | 2020-07-30 | 2020-07-30 | 2020-10-06 | 2021-01-22 | Overhead | R16 | 2020-10-06 | 9 |  | 49 | 79 | 135 | 2020 | 2021 | R16
160764205097 | 169127205097 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-08 | 2020-09-08 | 2020-09-28 |  | 2021-07-26 | Underground | R16 | 2020-11-05 | 1 | 15 | 29 | 188 | 230 | 2020 | 2021 | R16
160842161818 | 166784161818 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-21 | 2019-08-21 | 2019-08-21 |  | 2019-11-25 | Overhead | R16 | 2019-09-11 | 1 |  | 16 | 54 | 69 | 2019 | 2019 | R16
163242212267 | 162369212267 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-22 | 2020-09-22 | 2020-12-01 |  | 2021-11-08 | Underground | R16 | 2021-05-13 | 1 | 51 | 118 | 128 | 295 | 2020 | 2021 | R16
162590206577 | 163765206577 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-14 | 2020-08-14 | 2020-10-09 | 2021-03-16 | 2021-03-17 | Underground | R16 | 2021-03-16 | 1 | 41 | 113 | 2 | 154 | 2020 | 2021 | R16
162727227112 | 168473227112 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-16 | 2021-04-16 | 2021-04-16 | 2023-06-06 | 2023-06-07 | Overhead | R16 | 2023-06-06 | 1 |  | 558 | 2 | 559 | 2021 | 2023 | R16
160880159645 | 162828159645 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-30 | 2019-07-31 | 2019-07-31 |  | 2019-09-24 | Overhead | R16 | 2019-09-16 | 2 |  | 34 | 7 | 41 | 2019 | 2019 | R16
160881166108 | 163443166108 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-27 | 2019-09-27 | 2019-09-27 |  | 2019-10-30 | Underground | R16 | 2019-10-22 | 1 |  | 18 | 7 | 24 | 2019 | 2019 | R16
160944162558 | 166699162558 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-22 | 2019-08-22 | 2019-08-30 |  | 2020-06-09 | Overhead | R16 | 2019-12-18 | 1 | 7 | 79 | 125 | 209 | 2019 | 2020 | R16
160946164893 | 167756164893 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-08-27 | 2019-08-30 | 2019-09-18 |  | 2020-07-08 | Underground | R16 |  | 4 | 14 |  |  | 227 | 2019 | 2020 | R16
161771219624 | 162200219624 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-04 | 2021-02-04 | 2021-02-04 | 2021-03-23 | 2021-08-31 | Overhead | R16 | 2021-03-23 | 1 |  | 34 | 116 | 149 | 2021 | 2021 | R16
160978160470 | 164133160470 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-06 | 2019-08-06 | 2019-08-08 |  | 2019-11-08 | Overhead | R16 | 2019-11-01 | 1 | 3 | 62 | 6 | 69 | 2019 | 2019 | R16
161012163768 | 161480163768 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-23 | 2019-07-23 | 2019-09-09 |  | 2020-06-09 | Underground | R16 | 2020-04-09 | 1 | 35 | 154 | 44 | 231 | 2019 | 2020 | R16
169820223978 | 160785223978 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-16 | 2021-03-16 | 2021-03-19 | 2021-03-31 | 2021-11-05 | Underground | R16 | 2021-03-31 | 1 | 4 | 9 | 158 | 169 | 2021 | 2021 | R16
168686160464 | 161358160464 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-29 | 2019-05-29 | 2019-08-07 | 2019-10-01 | 2019-10-14 | Underground | R16 | 2019-10-01 | 1 | 51 | 40 | 10 | 99 | 2019 | 2019 | R16
166890141313 | 167996141313 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-18 | 2019-01-18 | 2019-01-25 | 2019-02-25 | 2019-02-26 | Underground | R16 | 2019-02-25 | 1 | 6 | 22 | 2 | 28 | 2019 | 2019 | R16
161053164136 | 160624164136 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-11 | 2019-09-11 | 2019-09-11 |  | 2019-10-11 | Overhead | R16 | 2019-10-01 | 1 |  | 15 | 9 | 23 | 2019 | 2019 | R16
166600140416 | 167460140416 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-15 | 2019-01-16 | 2019-01-16 | 2019-02-22 | 2019-02-25 | Overhead | R16 | 2019-02-22 | 2 |  | 28 | 2 | 30 | 2019 | 2019 | R16
161059174284 | 162620174284 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-09-24 | 2019-11-19 | 2019-12-12 |  | 2020-06-09 | Overhead | R16 |  | 41 | 18 |  |  | 186 | 2019 | 2020 | R16
160289222679 | 160058222679 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-27 | 2021-01-27 | 2021-03-08 | 2021-05-13 | 2021-05-14 | Overhead | R16 | 2021-05-13 | 1 | 29 | 49 | 2 | 78 | 2021 | 2021 | R16
161059174287 | 162622174287 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-09-24 | 2019-11-21 | 2019-12-12 |  | 2020-06-09 | Overhead | R16 |  | 43 | 16 |  |  | 186 | 2019 | 2020 | R16
163386271097 | 164548271097 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-01-05 | 2021-01-21 | 2022-03-02 | 2022-06-07 | 2022-08-03 | Underground | R16 | 2022-06-07 | 13 | 290 | 70 | 42 | 412 | 2021 | 2022 | R16
164736147943 | 161134147943 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-02 | 2019-04-02 | 2019-04-02 | 2019-06-11 | 2019-06-12 | Overhead | R16 | 2019-06-11 | 1 |  | 51 | 2 | 52 | 2019 | 2019 | R16
164804271833 | 167234271833 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-14 | 2021-01-14 | 2022-03-07 | 2022-04-20 | 2022-04-22 | Underground | R16 | 2022-04-20 | 1 | 298 | 33 | 3 | 332 | 2021 | 2022 | R16
161194266307 | 164410266307 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2022-01-26 | 2022-01-26 | 2022-01-26 |  | 2022-04-22 | Underground | R16 |  | 1 |  |  |  | 63 | 2022 | 2022 | R16
161194266276 | 164437266276 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2022-01-26 | 2022-01-26 | 2022-01-27 |  | 2023-01-05 | Underground | R16 |  | 1 | 2 |  |  | 247 | 2022 | 2023 | R16
165312154107 | 162003154107 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-03 | 2019-06-03 | 2019-06-03 | 2019-06-14 | 2019-06-17 | Overhead | R16 | 2019-06-14 | 1 |  | 10 | 2 | 11 | 2019 | 2019 | R16
166390198170 | 169776198170 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-23 | 2020-07-23 | 2020-07-23 | 2020-09-30 | 2021-01-08 | Overhead | R16 | 2020-09-30 | 1 |  | 50 | 73 | 122 | 2020 | 2021 | R16
165311221704 | 166745221704 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-25 | 2021-02-25 | 2021-02-25 | 2021-04-21 | 2021-04-22 | Overhead | R16 | 2021-04-21 | 1 |  | 40 | 2 | 41 | 2021 | 2021 | R16
160810230569 | 163653230569 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-06 | 2021-05-06 | 2021-05-13 | 2021-05-30 | 2023-12-08 | Overhead | R16 | 2021-05-30 | 1 | 6 | 12 | 660 | 677 | 2021 | 2023 | R16
162384147875 | 161069147875 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-02 | 2019-04-02 | 2019-04-02 | 2019-04-12 | 2019-05-14 | Underground | R16 | 2019-04-12 | 1 |  | 9 | 23 | 31 | 2019 | 2019 | R16
165757226309 | 167021226309 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-04-09 | 2021-04-09 | 2021-04-09 |  | 2021-08-23 | Overhead | R16 | 2021-07-12 | 1 |  | 67 | 31 | 97 | 2021 | 2021 | R16
161248165747 | 168813165747 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-03 | 2019-09-03 | 2019-09-25 |  | 2022-08-02 | Underground | R16 |  | 1 | 17 |  |  | 761 | 2019 | 2022 | R16
169173153739 | 161505153739 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-30 | 2019-05-30 | 2019-05-30 | 2020-07-20 | 2020-10-06 | Overhead | R16 | 2020-07-20 | 1 |  | 298 | 57 | 354 | 2019 | 2020 | R16
161250163234 | 162755163234 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-30 | 2019-07-30 | 2019-09-03 |  | 2020-01-03 | Underground | R16 | 2019-12-12 | 1 | 26 | 73 | 17 | 114 | 2019 | 2020 | R16
168399210152 | 160531210152 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-11 | 2020-09-11 | 2020-11-09 | 2021-01-27 | 2021-02-02 | Underground | R16 | 2021-01-27 | 1 | 42 | 58 | 5 | 103 | 2020 | 2021 | R16
161254166217 | 163696166217 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-09-30 | 2019-09-30 | 2019-10-01 |  | 2020-10-06 | Underground | R16 | 2020-07-30 | 1 | 2 | 218 | 49 | 267 | 2019 | 2020 | R16
169278199005 | 160847199005 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-30 | 2020-07-30 | 2020-07-30 |  | 2020-12-18 | Overhead | R16 | 2020-10-13 | 1 |  | 54 | 49 | 102 | 2020 | 2020 | R16
161258161840 | 166517161840 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-20 | 2019-08-20 | 2019-08-20 |  | 2019-10-28 | Overhead | R16 | 2019-10-16 | 1 |  | 42 | 9 | 50 | 2019 | 2019 | R16
168006139062 | 164647139062 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-02 | 2019-01-02 | 2019-01-02 | 2019-01-28 | 2019-01-28 | Overhead | R16 | 2019-01-28 | 1 |  | 19 |  | 19 | 2019 | 2019 | R16
161278162841 | 168417162841 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-29 | 2019-08-29 | 2019-08-30 |  | 2019-09-11 | Overhead | R16 | 2019-09-05 | 1 | 2 | 5 | 5 | 10 | 2019 | 2019 | R16
168180222975 | 168190222975 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-01 | 2020-09-01 | 2021-03-10 | 2021-05-12 | 2021-05-13 | Underground | R16 | 2021-05-12 | 1 | 137 | 46 | 2 | 183 | 2020 | 2021 | R16
169191206430 | 166262206430 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-07 | 2020-10-07 | 2020-10-07 | 2020-11-10 | 2021-07-19 | Overhead | R16 | 2020-11-10 | 1 |  | 25 | 180 | 204 | 2020 | 2021 | R16
160888206609 | 166640206609 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-08 | 2020-10-08 | 2020-10-08 |  | 2021-11-10 | Overhead | R16 | 2021-10-14 | 1 |  | 266 | 20 | 285 | 2020 | 2021 | R16
164252146858 | 169580146858 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-22 | 2019-03-23 | 2019-03-23 | 2019-04-24 | 2019-05-28 | Overhead | R16 | 2019-04-24 | 1 |  | 23 | 25 | 48 | 2019 | 2019 | R16
161336163100 | 168740163100 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-01 | 2019-09-01 | 2019-09-01 |  | 2019-10-28 | Overhead | R16 | 2019-10-15 | 0 |  | 32 | 10 | 41 | 2019 | 2019 | R16
169692204207 | 161647204207 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-17 | 2020-09-18 | 2020-09-18 |  | 2021-07-02 | Overhead | R16 | 2020-10-21 | 2 |  | 24 | 183 | 207 | 2020 | 2021 | R16
166080234120 | 167428234120 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH CP R16 WORK RELO TO UG | Residential | 2020-08-29 | 2020-09-05 | 2021-06-08 | 2021-09-28 | 2021-11-22 | Overhead | R16 | 2021-09-28 | 5 | 197 | 81 | 40 | 321 | 2020 | 2021 | R16
169748156549 | 161680156549 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-31 | 2019-06-19 | 2019-06-28 | 2019-10-01 | 2019-10-14 | Underground | R16 | 2019-10-01 | 14 | 8 | 68 | 10 | 97 | 2019 | 2019 | R16
164382207548 | 166327207548 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-07 | 2020-10-16 | 2020-10-16 | 2021-01-04 | 2021-03-31 | Overhead | R16 | 2021-01-04 | 8 |  | 57 | 63 | 126 | 2020 | 2021 | R16
161482163177 | 168964163177 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-03 | 2019-09-03 | 2019-09-03 |  | 2019-10-16 | Overhead | R16 | 2019-10-09 | 1 |  | 27 | 6 | 32 | 2019 | 2019 | R16
166331240926 | 167970240926 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Commercial | 2021-04-14 | 2021-04-28 | 2021-07-27 | 2022-02-17 | 2022-03-10 | Underground | R16 | 2022-02-17 | 11 | 65 | 148 | 16 | 237 | 2021 | 2022 | R16
160961226972 | 168426226972 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-01-20 | 2021-02-10 | 2021-04-16 |  | 2021-09-13 | Underground | R16 | 2021-08-18 | 16 | 48 | 89 | 19 | 169 | 2021 | 2021 | R16
161447226635 | 167382226635 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-04-12 | 2021-04-13 | 2021-04-13 | 2022-09-22 | 2022-09-23 | Underground | R16 | 2022-09-22 | 2 |  | 378 | 2 | 380 | 2021 | 2022 | R16
161501163771 | 169592163771 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-09-06 | 2019-09-06 | 2019-09-09 |  | 2019-09-25 | Overhead | R16 |  | 1 | 2 |  |  | 14 | 2019 | 2019 | R16
164554226542 | 169591226542 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-03-09 | 2021-04-09 | 2021-04-12 |  | 2022-10-21 | Overhead | R16 | 2022-08-12 | 24 | 2 | 350 | 51 | 424 | 2021 | 2022 | R16
164593226296 | 161763226296 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2021-03-18 | 2021-03-18 | 2021-04-09 | 2022-08-31 | 2022-09-16 | Overhead | R16 | 2022-08-31 | 1 | 17 | 364 | 13 | 392 | 2021 | 2022 | R16
161509159741 | 162865159741 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-30 | 2019-07-31 | 2019-07-31 |  | 2019-11-27 | Overhead | R16 | 2019-11-21 | 2 |  | 82 | 5 | 87 | 2019 | 2019 | R16
160255216531 | 160326216531 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-11 | 2020-12-11 | 2021-01-07 | 2021-02-11 | 2021-05-06 | Underground | R16 | 2021-02-11 | 1 | 20 | 26 | 61 | 105 | 2020 | 2021 | R16
161520158939 | 162083158939 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-25 | 2019-07-25 | 2019-07-26 |  | 2019-09-26 | Overhead | R16 | 2019-09-18 | 1 | 2 | 39 | 7 | 46 | 2019 | 2019 | R16
163654216690 | 164851216690 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-05 | 2021-01-08 | 2021-01-08 | 2021-04-28 | 2021-04-29 | Overhead | R16 | 2021-04-28 | 4 |  | 79 | 2 | 83 | 2021 | 2021 | R16
161522163345 | 169028163345 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-04 | 2019-09-04 | 2019-09-04 |  | 2019-10-14 | Overhead | R16 | 2019-10-02 | 1 |  | 21 | 9 | 29 | 2019 | 2019 | R16
168242211245 | 164975211245 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-16 | 2020-11-16 | 2020-11-19 | 2021-01-05 | 2021-01-08 | Overhead | R16 | 2021-01-05 | 1 | 4 | 34 | 4 | 40 | 2020 | 2021 | R16
161536164803 | 168767164803 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-03 | 2019-09-03 | 2019-09-16 |  | 2020-10-06 | Underground | R16 | 2020-07-27 | 1 | 10 | 226 | 52 | 286 | 2019 | 2020 | R16
167829221995 | 167446221995 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-01 | 2021-03-01 | 2021-03-01 |  | 2021-11-04 | Overhead | R16 | 2021-05-28 | 1 |  | 65 | 115 | 179 | 2021 | 2021 | R16
161548241860 | 161011241860 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2020-09-15 | 2020-09-17 | 2021-08-02 |  | 2023-08-18 | Underground | R16 |  | 3 | 228 |  |  | 764 | 2020 | 2023 | R16
168039230677 | 160756230677 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-27 | 2021-04-28 | 2021-05-14 |  | 2021-08-23 | Underground | R16 | 2021-08-05 | 2 | 13 | 60 | 13 | 85 | 2021 | 2021 | R16
164988203875 | 168520203875 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-16 | 2020-09-15 | 2020-09-15 | 2020-09-16 | 2020-12-17 | Overhead | R16 | 2020-09-16 | 44 |  | 2 | 67 | 111 | 2020 | 2020 | R16
164576225541 | 168037225541 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-03 | 2021-03-03 | 2021-03-31 |  | 2021-10-25 | Underground | R16 | 2021-09-02 | 1 | 21 | 112 | 38 | 169 | 2021 | 2021 | R16
161564159889 | 163494159889 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-08-02 | 2019-08-02 | 2019-08-02 |  | 2019-08-28 | Underground | R16 | 2019-08-19 | 1 |  | 12 | 8 | 19 | 2019 | 2019 | R16
163971204190 | 162513204190 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-07 | 2020-08-07 | 2020-09-17 |  | 2021-01-08 | Overhead | R16 | 2020-10-06 | 1 | 30 | 14 | 69 | 111 | 2020 | 2021 | R16
161568164918 | 168773164918 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-03 | 2019-09-03 | 2019-09-19 |  | 2020-06-09 | Underground | R16 | 2020-01-16 | 1 | 13 | 86 | 104 | 201 | 2019 | 2020 | R16
161571161706 | 166209161706 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-19 | 2019-08-20 | 2019-08-20 |  | 2019-10-30 | Overhead | R16 | 2019-10-21 | 2 |  | 45 | 8 | 53 | 2019 | 2019 | R16
163749219081 | 160913219081 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-29 | 2021-01-29 | 2021-01-29 |  | 2021-11-04 | Overhead | R16 | 2021-04-05 | 1 |  | 47 | 154 | 200 | 2021 | 2021 | R16
167547221372 | 163184221372 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-09 | 2021-02-23 | 2021-02-23 |  | 2021-12-03 | Overhead | R16 | 2021-11-09 | 11 |  | 186 | 19 | 214 | 2021 | 2021 | R16
163859212974 | 164903212974 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-14 | 2020-12-07 | 2020-12-07 |  | 2021-04-20 | Overhead | R16 | 2021-01-12 | 16 |  | 27 | 71 | 112 | 2020 | 2021 | R16
161630171431 | 161326171431 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-11-05 | 2019-11-05 | 2019-11-11 |  | 2019-12-30 | Underground | R16 |  | 1 | 5 |  |  | 40 | 2019 | 2019 | R16
163074148753 | 162693148753 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-06-04 | 2019-08-12 | Overhead | R16 | 2019-06-04 | 1 |  | 40 | 50 | 89 | 2019 | 2019 | R16
161630171504 | 161459171504 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-11-06 | 2019-11-06 | 2019-11-11 |  | 2020-01-03 | Underground | R16 |  | 1 | 4 |  |  | 43 | 2019 | 2020 | R16
167466217760 | 167975217760 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-19 | 2021-01-19 | 2021-01-19 |  | 2021-11-05 | Overhead | R16 | 2021-04-13 | 1 |  | 61 | 149 | 209 | 2021 | 2021 | R16
164911154418 | 162399154418 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-05 | 2019-06-05 | 2019-06-05 | 2019-07-19 | 2019-08-01 | Overhead | R16 | 2019-07-19 | 1 |  | 33 | 10 | 42 | 2019 | 2019 | R16
161630172190 | 161607172190 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-11-06 | 2019-11-06 | 2019-11-18 |  | 2021-11-10 | Underground | R16 |  | 1 | 9 |  |  | 526 | 2019 | 2021 | R16
161342212806 | 168824212806 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-04 | 2020-12-04 | 2020-12-04 | 2021-01-05 | 2021-04-29 | Overhead | R16 | 2021-01-05 | 1 |  | 23 | 83 | 105 | 2020 | 2021 | R16
169806158224 | 161762158224 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-31 | 2019-07-17 | 2019-07-17 | 2019-08-04 | 2019-09-06 | Underground | R16 | 2019-08-04 | 34 |  | 13 | 25 | 71 | 2019 | 2019 | R16
160557152369 | 166120152369 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-29 | 2019-04-29 | 2019-05-14 | 2019-06-13 | 2019-06-14 | Underground | R16 | 2019-06-13 | 1 | 12 | 23 | 2 | 35 | 2019 | 2019 | R16
161630172193 | 161690172193 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-11-06 | 2019-11-06 | 2019-11-18 |  | 2021-11-10 | Underground | R16 |  | 1 | 9 |  |  | 526 | 2019 | 2021 | R16
161433227865 | 169500227865 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2021-04-21 | 2021-04-21 | 2021-04-21 | 2021-05-17 | 2021-05-18 | Underground | R16 | 2021-05-17 | 1 |  | 19 | 2 | 20 | 2021 | 2021 | R16
161630172198 | 161764172198 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-11-07 | 2019-11-07 | 2019-11-18 |  | 2020-01-06 | Underground | R16 |  | 1 | 8 |  |  | 43 | 2019 | 2020 | R16
161751206156 | 165325206156 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-01 | 2020-10-05 | 2020-10-06 | 2020-11-17 | 2021-04-16 | Overhead | R16 | 2020-11-17 | 3 | 2 | 31 | 109 | 142 | 2020 | 2021 | R16
168884171421 | 168887171421 | NON-RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Commercial | 2019-05-14 | 2019-05-14 | 2019-11-11 | 2020-02-05 | 2022-08-25 | Underground | R16 | 2020-02-05 | 1 | 130 | 63 | 667 | 858 | 2019 | 2022 | R16
160961140975 | 167436140975 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-16 | 2019-01-16 | 2019-01-22 | 2019-03-06 | 2019-03-07 | Overhead | R16 | 2019-03-06 | 1 | 5 | 32 | 2 | 37 | 2019 | 2019 | R16
161630171764 | 161965171764 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-11-07 | 2019-11-07 | 2019-11-13 |  | 2020-06-09 | Underground | R16 |  | 1 | 5 |  |  | 154 | 2019 | 2020 | R16
167410148892 | 162817148892 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-10 | 2019-04-10 | 2019-04-12 | 2019-04-18 | 2019-04-18 | Overhead | R16 | 2019-04-18 | 1 | 3 | 5 |  | 7 | 2019 | 2019 | R16
169281211322 | 165921211322 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-19 | 2020-11-19 | 2020-11-19 |  | 2022-04-04 | Overhead | R16 | 2022-03-14 | 1 |  | 343 | 16 | 358 | 2020 | 2022 | R16
167581278275 | 166206278275 | NON-RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Commercial | 2021-01-12 | 2021-11-22 | 2022-05-05 | 2022-10-18 | 2022-10-24 | Underground | R16 | 2022-10-18 | 225 | 119 | 119 | 5 | 465 | 2021 | 2022 | R16
165510225339 | 163575225339 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-03-26 | 2021-03-26 | 2021-03-31 | 2021-08-26 | 2022-02-16 | Underground | R16 | 2021-08-26 | 1 | 4 | 107 | 125 | 234 | 2021 | 2022 | R16
161716169132 | 165582169132 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 ELEC DEVELOPMENT | Residential | 2019-08-15 | 2019-10-21 | 2019-10-22 |  | 2020-11-23 | Underground | R16 |  | 48 | 2 |  |  | 333 | 2019 | 2020 | R16
164049216127 | 164483216127 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-04 | 2021-01-04 | 2021-01-04 | 2021-01-05 | 2021-06-02 | Overhead | R16 | 2021-01-05 | 1 |  | 2 | 107 | 108 | 2021 | 2021 | R16
167736221332 | 168519221332 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-05-13 | 2020-07-21 | 2021-02-23 | 2021-04-21 | 2021-07-29 | Underground | R16 | 2021-04-21 | 312 | 156 | 42 | 72 | 579 | 2019 | 2021 | R16
166930142120 | 161050142120 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-03 | 2019-02-03 | 2019-02-03 | 2019-08-12 | 2019-12-06 | Overhead | R16 | 2019-08-12 | 0 |  | 136 | 85 | 220 | 2019 | 2019 | R16
161986149291 | 163957149291 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-17 | 2019-04-17 | 2019-04-17 | 2019-08-15 | 2019-08-28 | Overhead | R16 | 2019-08-15 | 1 |  | 87 | 10 | 96 | 2019 | 2019 | R16
161106145465 | 167296145465 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-09 | 2019-03-09 | 2019-03-09 | 2019-04-05 | 2019-04-09 | Overhead | R16 | 2019-04-05 | 0 |  | 20 | 3 | 22 | 2019 | 2019 | R16
161851263889 | 168908263889 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-09-03 | 2021-12-10 | 2022-01-07 |  | 2022-03-03 | Overhead | R16 |  | 594 | 21 |  |  | 653 | 2019 | 2022 | R16
164535212770 | 164600212770 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-18 | 2020-08-18 | 2020-12-04 | 2021-02-04 | 2021-02-05 | Underground | R16 | 2021-02-04 | 1 | 79 | 45 | 2 | 124 | 2020 | 2021 | R16
163658235239 | 162709235239 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-04 | 2021-05-04 | 2021-06-17 |  | 2021-08-23 | Underground | R16 | 2021-07-15 | 1 | 33 | 21 | 28 | 80 | 2021 | 2021 | R16
165754222136 | 169627222136 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-01-26 | 2021-01-29 | 2021-03-02 | 2021-08-24 | 2021-09-01 | Underground | R16 | 2021-08-24 | 4 | 23 | 126 | 7 | 157 | 2021 | 2021 | R16
161952160103 | 163763160103 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-08-05 | 2019-08-05 | 2019-08-05 |  | 2019-12-19 | Overhead | R16 | 2019-08-14 | 1 |  | 8 | 92 | 99 | 2019 | 2019 | R16
161972169836 | 169943169836 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-10-29 | 2019-10-29 | 2019-10-29 |  | 2019-11-08 | Overhead | R16 |  | 1 |  |  |  | 9 | 2019 | 2019 | R16
162014162790 | 161887162790 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OD | Residential | 2019-07-25 | 2019-08-26 | 2019-08-30 |  | 2020-06-09 | Overhead | R16 |  | 23 | 5 |  |  | 229 | 2019 | 2020 | R16
162017161128 | 164098161128 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-07 | 2019-08-13 | 2019-08-13 |  | 2019-10-30 | Overhead | R16 | 2019-10-21 | 5 |  | 50 | 8 | 61 | 2019 | 2019 | R16
165531197689 | 168754197689 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-17 | 2020-07-17 | 2020-07-17 | 2020-07-22 | 2020-10-06 | Overhead | R16 | 2020-07-22 | 1 |  | 4 | 55 | 58 | 2020 | 2020 | R16
164163197440 | 164181197440 | NON-RESIDENTIAL - LODGING | UG R16 RESD AND NON RESD UD | Commercial | 2019-04-18 | 2019-04-18 | 2020-07-15 | 2022-03-18 | 2022-04-12 | Underground | R16 | 2022-03-18 | 1 | 325 | 438 | 18 | 779 | 2019 | 2022 | R16
162070161510 | 164113161510 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-06 | 2019-08-19 | 2019-08-19 |  | 2019-09-25 | Underground | R16 | 2019-09-17 | 10 |  | 22 | 7 | 37 | 2019 | 2019 | R16
166026207319 | 168431207319 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-16 | 2020-10-16 | 2020-10-16 | 2020-10-16 | 2021-07-19 | Overhead | R16 | 2020-10-16 | 1 |  |  | 197 | 197 | 2020 | 2021 | R16
161555213865 | 163228213865 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-09-25 | 2020-12-14 | 2020-12-14 |  | 2021-04-23 | Overhead | R16 |  | 57 |  |  |  | 151 | 2020 | 2021 | R16
162110172151 | 165127172151 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-08-12 | 2019-10-01 | 2019-11-18 |  | 2021-12-16 | Underground | R16 | 2020-02-10 | 37 | 35 | 61 | 484 | 614 | 2019 | 2021 | R16
160797230726 | 165164230726 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-13 | 2021-05-13 | 2021-05-13 | 2022-04-20 | 2022-05-18 | Overhead | R16 | 2022-04-20 | 1 |  | 245 | 21 | 265 | 2021 | 2022 | R16
164040217830 | 163713217830 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-28 | 2020-09-28 | 2021-01-20 |  | 2021-11-04 | Underground | R16 | 2021-04-02 | 1 | 83 | 53 | 155 | 289 | 2020 | 2021 | R16
162183174307 | 169301174307 | Fleet Chargers | R16 REWIRE UPGRADE US | Commercial | 2019-09-04 | 2019-09-14 | 2019-12-12 |  | 2020-10-06 | Underground | R16 |  | 8 | 64 |  |  | 285 | 2019 | 2020 | R16
166519218102 | 168946218102 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-01-22 | 2021-01-22 | 2021-01-22 |  | 2021-08-06 | Overhead | R16 | 2021-03-25 | 1 |  | 45 | 97 | 141 | 2021 | 2021 | R16
162189168428 | 166915168428 | Fleet Chargers | R16 RESD AND NON RESD US | Commercial | 2019-10-15 | 2019-10-16 | 2019-10-17 |  | 2021-02-17 | Underground | R16 |  | 2 | 2 |  |  | 352 | 2019 | 2021 | R16
167352219672 | 161037219672 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-01 | 2021-02-01 | 2021-02-05 | 2021-04-30 | 2021-11-05 | Underground | R16 | 2021-04-30 | 1 | 5 | 61 | 136 | 200 | 2021 | 2021 | R16
167955206409 | 166201206409 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-06 | 2020-10-06 | 2020-10-07 |  | 2021-07-16 | Overhead | R16 | 2020-11-17 | 1 | 2 | 30 | 174 | 204 | 2020 | 2021 | R16
162195172796 | 167455172796 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-18 | 2019-10-18 | 2019-11-26 |  | 2022-08-02 | Underground | R16 |  | 1 | 28 |  |  | 728 | 2019 | 2022 | R16
168309206741 | 166868206741 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-09 | 2020-10-09 | 2020-10-09 | 2020-10-13 | 2021-04-14 | Overhead | R16 | 2020-10-13 | 1 |  | 3 | 132 | 134 | 2020 | 2021 | R16
162196174755 | 164136174755 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-06 | 2019-12-19 | 2019-12-19 |  | 2020-12-18 | Underground | R16 | 2020-09-17 | 98 |  | 196 | 67 | 359 | 2019 | 2020 | R16
167731217789 | 167726217789 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-14 | 2020-10-14 | 2021-01-20 |  | 2021-08-11 | Underground | R16 | 2021-03-24 | 1 | 71 | 46 | 101 | 216 | 2020 | 2021 | R16
168563143977 | 160774143977 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-02-01 | 2019-02-01 | 2019-02-22 | 2019-07-17 | 2019-07-18 | Overhead | R16 | 2019-07-17 | 1 | 16 | 104 | 2 | 120 | 2019 | 2019 | R16
162225174217 | 168235174217 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-13 | 2019-12-13 | 2019-12-13 |  | 2020-06-09 | Overhead | R16 | 2020-02-13 | 1 |  | 45 | 84 | 128 | 2019 | 2020 | R16
162235195030 | 168443195030 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-08-30 | 2019-08-30 | 2020-06-22 |  | 2020-10-06 | Underground | R16 |  | 1 | 212 |  |  | 288 | 2019 | 2020 | R16
162471237072 | 165737237072 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-05 | 2021-04-26 | 2021-06-29 |  | 2021-12-01 | Underground | R16 | 2021-11-01 | 16 | 47 | 90 | 23 | 173 | 2021 | 2021 | R16
167002154852 | 167853154852 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-03-12 | 2019-03-12 | 2019-06-11 | 2020-01-02 | 2021-11-13 | Underground | R16 | 2020-01-02 | 1 | 66 | 148 | 487 | 699 | 2019 | 2021 | R16
169731226681 | 164023226681 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-28 | 2021-03-31 | 2021-04-13 | 2021-06-24 | 2021-08-11 | Overhead | R16 | 2021-06-24 | 3 | 10 | 53 | 35 | 98 | 2021 | 2021 | R16
163397200757 | 164538200757 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-18 | 2020-08-18 | 2020-08-18 |  | 2021-11-09 | Underground | R16 | 2020-11-10 | 1 |  | 61 | 261 | 321 | 2020 | 2021 | R16
162330166225 | 163027166225 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-07-31 | 2019-07-31 | 2019-09-30 |  | 2023-02-03 | Underground | R16 | 2022-12-01 | 1 | 44 | 829 | 47 | 918 | 2019 | 2023 | R16
162402162559 | 165073162559 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-12 | 2019-08-12 | 2019-08-30 |  | 2019-12-17 | Underground | R16 | 2019-12-05 | 1 | 15 | 70 | 9 | 92 | 2019 | 2019 | R16
161500202314 | 166252202314 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-24 | 2020-08-24 | 2020-09-01 |  | 2021-11-09 | Underground | R16 | 2020-12-30 | 1 | 7 | 87 | 225 | 317 | 2020 | 2021 | R16
162407169536 | 167923169536 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-10-19 | 2019-10-19 | 2019-10-24 |  | 2019-11-13 | Overhead | R16 |  | 0 | 4 |  |  | 18 | 2019 | 2019 | R16
169106224312 | 169012224312 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-07 | 2020-12-07 | 2021-03-22 | 2021-05-24 | 2021-05-24 | Overhead | R16 | 2021-05-24 | 1 | 76 | 46 |  | 121 | 2020 | 2021 | R16
169717154985 | 162263154985 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-06-04 | 2019-06-04 | 2019-06-10 | 2020-03-13 | 2020-06-09 | Underground | R16 | 2020-03-13 | 1 | 5 | 200 | 63 | 266 | 2019 | 2020 | R16
162416161831 | 166328161831 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-08-20 | 2019-08-21 | 2019-08-21 |  | 2020-07-08 | Overhead | R16 | 2020-05-21 | 2 |  | 197 | 35 | 232 | 2019 | 2020 | R16
161240208900 | 160867208900 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-28 | 2020-10-28 | 2020-10-28 |  | 2021-07-28 | Overhead | R16 | 2021-01-20 | 1 |  | 61 | 136 | 196 | 2020 | 2021 | R16
166319206070 | 162020206070 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-09-19 | 2020-09-19 | 2020-10-02 |  | 2021-11-09 | Underground | R16 | 2020-12-30 | 0 | 10 | 64 | 225 | 297 | 2020 | 2021 | R16
163744216930 | 166197216930 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-12 | 2021-01-12 | 2021-01-12 |  | 2021-06-02 | Overhead | R16 | 2021-03-04 | 1 |  | 38 | 65 | 102 | 2021 | 2021 | R16
162518164056 | 160703164056 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-12 | 2019-09-12 | 2019-09-12 |  | 2020-10-06 | Overhead | R16 | 2020-08-07 | 1 |  | 237 | 43 | 279 | 2019 | 2020 | R16
162954296010 | 164128296010 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-12-30 | 2021-03-23 | 2022-10-05 |  | 2022-12-15 | Underground | R16 |  | 60 | 402 |  |  | 512 | 2020 | 2022 | R16
164397233581 | 165851233581 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-17 | 2021-06-04 | 2021-06-04 | 2021-07-09 | 2021-08-23 | Overhead | R16 | 2021-07-09 | 15 |  | 26 | 32 | 71 | 2021 | 2021 | R16
162541164196 | 162953164196 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-31 | 2019-07-31 | 2019-09-13 |  | 2020-10-06 | Underground | R16 | 2020-07-14 | 1 | 33 | 218 | 61 | 310 | 2019 | 2020 | R16
162299228134 | 169918228134 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-23 | 2021-04-23 | 2021-04-23 |  | 2021-08-11 | Overhead | R16 | 2021-06-30 | 1 |  | 49 | 31 | 79 | 2021 | 2021 | R16
165813201511 | 166494201511 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-25 | 2020-08-25 | 2020-08-25 | 2020-09-10 | 2020-12-17 | Underground | R16 | 2020-09-10 | 1 |  | 13 | 71 | 83 | 2020 | 2020 | R16
164883214271 | 165014214271 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-16 | 2020-11-16 | 2020-12-16 | 2021-02-24 | 2021-02-25 | Overhead | R16 | 2021-02-24 | 1 | 23 | 51 | 2 | 74 | 2020 | 2021 | R16
168293202656 | 168680202656 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-03 | 2020-09-03 | 2020-09-03 | 2022-02-28 | 2022-03-01 | Overhead | R16 | 2022-02-28 | 1 |  | 388 | 2 | 389 | 2020 | 2022 | R16
162568167507 | 165688167507 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-15 | 2019-08-15 | 2019-10-09 |  | 2020-06-09 | Underground | R16 | 2020-02-14 | 1 | 40 | 93 | 83 | 214 | 2019 | 2020 | R16
160879236911 | 162283236911 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-03 | 2021-06-28 | 2021-06-28 | 2022-08-03 | 2022-03-08 | Overhead | R16 | 2022-08-03 | 41 |  | 288 |  | 222 | 2021 | 2022 | R16
162594163079 | 169220163079 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-04 | 2019-09-04 | 2019-09-04 |  | 2019-10-04 | Overhead | R16 | 2019-09-23 | 1 |  | 14 | 10 | 23 | 2019 | 2019 | R16
163371214252 | 169927214252 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-10 | 2020-12-10 | 2020-12-17 | 2021-01-16 | 2021-01-19 | Overhead | R16 | 2021-01-16 | 1 | 6 | 22 | 2 | 29 | 2020 | 2021 | R16
162599170325 | 165432170325 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-08 | 2019-10-08 | 2019-10-31 |  | 2021-11-11 | Underground | R16 | 2019-12-19 | 1 | 18 | 36 | 496 | 548 | 2019 | 2021 | R16
161218255213 | 161645255213 | SPECIFIC BUDGET PROJECTS | UG R16 RESD AND NON RESD UD | Commercial | 2020-08-03 | 2020-10-14 | 2021-11-05 |  | 2022-08-26 | Underground | R16 |  | 53 | 278 |  |  | 540 | 2020 | 2022 | R16
162601160493 | 164472160493 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-08 | 2019-08-08 | 2019-08-08 |  | 2019-09-19 | Underground | R16 | 2019-09-11 | 1 |  | 25 | 7 | 31 | 2019 | 2019 | R16
169280222064 | 164462222064 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-16 | 2021-03-01 | 2021-03-01 |  | 2021-08-16 | Overhead | R16 | 2021-03-25 | 10 |  | 19 | 103 | 130 | 2021 | 2021 | R16
162603161987 | 165321161987 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-13 | 2019-08-21 | 2019-08-23 |  | 2019-10-16 | Underground | R16 | 2019-10-07 | 7 | 3 | 32 | 8 | 47 | 2019 | 2019 | R16
168987230784 | 165382230784 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2021-05-14 | 2021-05-14 | 2021-05-14 | 2021-06-01 | 2023-06-08 | Overhead | R16 | 2021-06-01 | 1 |  | 13 | 528 | 540 | 2021 | 2023 | R16
162633188499 | 167072188499 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-23 | 2019-08-23 | 2020-04-23 |  | 2020-10-06 | Underground | R16 | 2020-08-18 | 1 | 175 | 84 | 36 | 293 | 2019 | 2020 | R16
160006225777 | 165743225777 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-05 | 2021-04-05 | 2021-04-05 | 2021-07-14 | 2021-08-13 | Overhead | R16 | 2021-07-14 | 1 |  | 73 | 23 | 95 | 2021 | 2021 | R16
168110220751 | 169022220751 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-22 | 2021-01-22 | 2021-02-17 | 2021-03-14 | 2021-03-17 | Overhead | R16 | 2021-03-14 | 1 | 19 | 18 | 3 | 39 | 2021 | 2021 | R16
162636168288 | 167038168288 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-10-15 | 2019-10-15 | 2019-10-15 |  | 2020-10-06 | Overhead | R16 | 2020-07-13 | 1 |  | 195 | 62 | 256 | 2019 | 2020 | R16
162672140887 | 168554140887 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-03-06 | 2019-03-07 | Overhead | R16 | 2019-03-06 | 1 |  | 31 | 2 | 32 | 2019 | 2019 | R16
162639160123 | 163631160123 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-05 | 2019-08-05 | 2019-08-05 |  | 2019-10-28 | Underground | R16 | 2019-10-18 | 1 |  | 55 | 7 | 61 | 2019 | 2019 | R16
162684168885 | 167911168885 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-10-19 | 2019-10-19 | 2019-10-19 |  | 2020-07-08 | Overhead | R16 | 2020-06-15 | 0 |  | 171 | 18 | 188 | 2019 | 2020 | R16
163627143121 | 163099143121 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-12 | 2019-02-12 | 2019-02-12 | 2019-03-18 | 2019-03-20 | Overhead | R16 | 2019-03-18 | 1 |  | 25 | 3 | 27 | 2019 | 2019 | R16
162690161672 | 166237161672 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-20 | 2019-08-20 | 2019-08-20 |  | 2019-11-14 | Overhead | R16 | 2019-11-07 | 1 |  | 58 | 6 | 63 | 2019 | 2019 | R16
162702162340 | 164868162340 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-09 | 2019-08-09 | 2019-08-26 |  | 2019-11-14 | Underground | R16 | 2019-11-06 | 1 | 12 | 53 | 7 | 70 | 2019 | 2019 | R16
161797208792 | 160833208792 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-27 | 2020-10-27 | 2020-10-28 |  | 2021-04-15 | Overhead | R16 | 2020-12-21 | 1 | 2 | 39 | 84 | 123 | 2020 | 2021 | R16
164466200546 | 163740200546 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-13 | 2020-08-13 | 2020-08-13 | 2020-11-12 | 2021-04-14 | Underground | R16 | 2020-11-12 | 1 |  | 66 | 110 | 175 | 2020 | 2021 | R16
162728175027 | 164872175027 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-11-22 | 2019-11-25 | 2019-12-20 |  | 2022-08-29 | Overhead | R16 |  | 2 | 20 |  |  | 722 | 2019 | 2022 | R16
168030222917 | 169308222917 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-09 | 2021-03-09 | 2021-03-09 |  | 2021-11-08 | Overhead | R16 | 2021-04-22 | 1 |  | 33 | 143 | 175 | 2021 | 2021 | R16
162746163889 | 162898163889 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-31 | 2019-07-31 | 2019-09-09 |  | 2019-10-16 | Underground | R16 | 2019-10-09 | 1 | 29 | 23 | 6 | 56 | 2019 | 2019 | R16
162761161086 | 164522161086 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-08 | 2019-08-08 | 2019-08-13 |  | 2019-10-28 | Overhead | R16 | 2019-10-14 | 1 | 4 | 45 | 11 | 58 | 2019 | 2019 | R16
162765160705 | 164341160705 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-07 | 2019-08-07 | 2019-08-09 |  | 2019-08-28 | Overhead | R16 | 2019-08-21 | 1 | 3 | 9 | 6 | 16 | 2019 | 2019 | R16
168669207851 | 168699207851 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-17 | 2020-07-17 | 2020-10-21 | 2020-10-22 | 2021-05-05 | Underground | R16 | 2020-10-22 | 1 | 69 | 2 | 140 | 209 | 2020 | 2021 | R16
162778159611 | 162827159611 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2019-07-30 | 2019-07-30 | 2019-07-30 |  | 2019-10-30 | Underground | R16 |  | 1 |  |  |  | 67 | 2019 | 2019 | R16
169100201031 | 163716201031 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-08-13 | 2020-08-18 | 2020-08-19 | 2021-01-19 | 2021-02-18 | Underground | R16 | 2021-01-19 | 4 | 2 | 110 | 23 | 136 | 2020 | 2021 | R16
162778165552 | 163179165552 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2019-08-01 | 2019-08-01 | 2019-09-24 |  | 2020-06-09 | Underground | R16 |  | 1 | 39 |  |  | 224 | 2019 | 2020 | R16
162832224614 | 163410224614 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-25 | 2021-03-25 | 2021-03-25 | 2021-03-31 | 2021-11-08 | Overhead | R16 | 2021-03-31 | 1 |  | 5 | 159 | 163 | 2021 | 2021 | R16
162818170618 | 161284170618 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-05 | 2019-11-05 | 2019-11-05 |  | 2019-12-12 | Overhead | R16 | 2019-12-03 | 1 |  | 21 | 8 | 28 | 2019 | 2019 | R16
163138223027 | 169654223027 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-10 | 2021-03-10 | 2021-03-10 |  | 2022-06-06 | Overhead | R16 | 2022-05-10 | 1 |  | 305 | 20 | 324 | 2021 | 2022 | R16
162836167278 | 165412167278 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-07 | 2019-10-08 | 2019-10-08 |  | 2022-08-02 | Overhead | R16 |  | 2 |  |  |  | 737 | 2019 | 2022 | R16
162877160724 | 164840160724 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-09 | 2019-08-09 | 2019-08-09 |  | 2019-11-26 | Overhead | R16 | 2019-11-19 | 1 |  | 73 | 6 | 78 | 2019 | 2019 | R16
163138202401 | 167705202401 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-31 | 2020-08-31 | 2020-08-31 |  | 2021-07-02 | Overhead | R16 | 2020-10-21 | 1 |  | 38 | 183 | 220 | 2020 | 2021 | R16
162879163252 | 169575163252 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-06 | 2019-09-06 | 2019-09-06 |  | 2021-07-16 | Overhead | R16 | 2020-11-23 | 1 |  | 317 | 170 | 486 | 2019 | 2021 | R16
163548147784 | 167156147784 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-15 | 2019-01-18 | 2019-04-01 | 2019-08-23 | 2019-08-26 | Overhead | R16 | 2019-08-23 | 4 | 52 | 105 | 2 | 160 | 2019 | 2019 | R16
162887221948 | 168958221948 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2021-01-22 | 2021-01-22 | 2021-03-01 |  | 2022-03-01 | Overhead | R16 |  | 1 | 27 |  |  | 288 | 2021 | 2022 | R16
160827151381 | 160968151381 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-01 | 2019-02-01 | 2019-05-06 | 2019-05-13 | 2019-11-12 | Overhead | R16 | 2019-05-13 | 1 | 67 | 6 | 132 | 203 | 2019 | 2019 | R16
163183230493 | 164927230493 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-13 | 2021-05-13 | 2021-05-13 | 2021-06-09 | 2021-08-26 | Overhead | R16 | 2021-06-09 | 1 |  | 20 | 57 | 76 | 2021 | 2021 | R16
162921163535 | 169730163535 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-06 | 2019-09-06 | 2019-09-06 |  | 2020-11-02 | Overhead | R16 | 2020-09-03 | 1 |  | 260 | 43 | 302 | 2019 | 2020 | R16
166008154499 | 166457154499 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-01 | 2019-05-01 | 2019-06-06 | 2019-07-10 | 2019-07-10 | Underground | R16 | 2019-07-10 | 1 | 27 | 25 |  | 51 | 2019 | 2019 | R16
168903232607 | 168108232607 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-19 | 2021-05-27 | 2021-05-27 | 2021-07-23 | 2022-08-01 | Overhead | R16 | 2021-07-23 | 7 |  | 42 | 267 | 314 | 2021 | 2022 | R16
162982160154 | 163802160154 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-05 | 2019-08-05 | 2019-08-05 |  | 2019-09-04 | Overhead | R16 | 2019-08-28 | 1 |  | 18 | 6 | 23 | 2019 | 2019 | R16
162990220943 | 162142220943 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-04-16 | 2020-11-30 | 2021-02-18 |  | 2021-10-27 | Overhead | R16 |  | 163 | 59 |  |  | 400 | 2020 | 2021 | R16
167406153926 | 160614153926 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-23 | 2019-05-23 | 2019-05-31 | 2019-06-24 | 2019-08-26 | Underground | R16 | 2019-06-24 | 1 | 7 | 17 | 46 | 68 | 2019 | 2019 | R16
160078226931 | 167900226931 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-14 | 2021-04-15 | 2021-04-15 |  | 2021-11-03 | Overhead | R16 | 2021-06-22 | 2 |  | 49 | 97 | 146 | 2021 | 2021 | R16
162791152480 | 166725152480 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-01 | 2019-05-01 | 2019-05-14 | 2019-07-20 | 2019-07-23 | Underground | R16 | 2019-07-20 | 1 | 10 | 49 | 2 | 60 | 2019 | 2019 | R16
167488231760 | 161747231760 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-02 | 2021-02-02 | 2021-05-20 |  | 2021-10-28 | Underground | R16 | 2021-07-29 | 1 | 78 | 51 | 66 | 193 | 2021 | 2021 | R16
163067164228 | 168459164228 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-08-30 | 2019-08-30 | 2019-09-12 |  | 2019-11-08 | Overhead | R16 |  | 1 | 10 |  |  | 51 | 2019 | 2019 | R16
166122207951 | 168307207951 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-15 | 2020-10-15 | 2020-10-23 | 2021-02-18 | 2021-06-03 | Underground | R16 | 2021-02-18 | 1 | 7 | 85 | 76 | 166 | 2020 | 2021 | R16
163067164229 | 168550164229 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-08-30 | 2019-08-30 | 2019-09-12 |  | 2019-11-08 | Overhead | R16 |  | 1 | 10 |  |  | 51 | 2019 | 2019 | R16
169472149512 | 160921149512 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-03-31 | 2019-03-31 | 2019-04-18 | 2019-10-01 | 2019-11-14 | Underground | R16 | 2019-10-01 | 0 | 14 | 119 | 33 | 164 | 2019 | 2019 | R16
162554226224 | 169402226224 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-09 | 2021-04-08 | 2021-04-08 | 2021-07-09 | 2021-08-23 | Overhead | R16 | 2021-07-09 | 23 |  | 67 | 32 | 120 | 2021 | 2021 | R16
168239221045 | 169520221045 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-08 | 2020-12-08 | 2021-02-19 |  | 2021-10-25 | Overhead | R16 | 2021-08-23 | 1 | 54 | 132 | 46 | 230 | 2020 | 2021 | R16
161404206610 | 166649206610 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-08 | 2020-10-08 | 2020-10-08 |  | 2021-04-20 | Overhead | R16 | 2021-01-11 | 1 |  | 68 | 72 | 139 | 2020 | 2021 | R16
164571224966 | 163638224966 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-26 | 2021-03-26 | 2021-03-26 | 2021-05-05 | 2021-09-10 | Overhead | R16 | 2021-05-05 | 1 |  | 29 | 93 | 121 | 2021 | 2021 | R16
163236161662 | 166146161662 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-08-19 | 2019-08-19 | 2019-08-19 |  | 2019-10-14 | Overhead | R16 | 2019-10-03 | 1 |  | 34 | 8 | 41 | 2019 | 2019 | R16
163287164482 | 160973164482 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-13 | 2019-09-13 | 2019-09-13 |  | 2021-04-16 | Overhead | R16 | 2021-01-07 | 1 |  | 345 | 72 | 416 | 2019 | 2021 | R16
168472212863 | 168643212863 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-04 | 2020-12-04 | 2020-12-04 | 2021-06-03 | 2021-06-03 | Overhead | R16 | 2021-06-03 | 1 |  | 130 |  | 130 | 2020 | 2021 | R16
163438238802 | 168887238802 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-04-19 | 2021-04-27 | 2021-07-12 | 2022-06-13 | 2022-07-15 | Underground | R16 | 2022-06-13 | 7 | 55 | 241 | 25 | 325 | 2021 | 2022 | R16
163296164124 | 160368164124 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-09-11 | 2019-09-11 | 2019-09-11 |  | 2020-06-09 | Underground | R16 | 2020-01-21 | 1 |  | 95 | 101 | 195 | 2019 | 2020 | R16
165145166905 | 165037166905 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-23 | 2019-04-23 | 2019-10-04 | 2021-10-05 | 2021-10-29 | Underground | R16 | 2021-10-05 | 1 | 119 | 523 | 19 | 659 | 2019 | 2021 | R16
161623225633 | 163710225633 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-03-26 | 2021-03-26 | 2021-04-02 | 2021-05-14 | 2021-05-19 | Underground | R16 | 2021-05-14 | 1 | 6 | 31 | 4 | 39 | 2021 | 2021 | R16
163338160898 | 165405160898 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-14 | 2019-08-14 | 2019-08-14 |  | 2019-09-12 | Overhead | R16 | 2019-09-06 | 1 |  | 18 | 5 | 22 | 2019 | 2019 | R16
160050161709 | 161240161709 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-29 | 2019-05-29 | 2019-08-20 | 2020-03-06 | 2020-03-09 | Underground | R16 | 2020-03-06 | 1 | 60 | 144 | 2 | 204 | 2019 | 2020 | R16
165121213044 | 168525213044 | INDUSTRIAL | OH R16 RES NON RES OS | Commercial | 2020-12-03 | 2020-12-03 | 2020-12-07 |  | 2021-08-23 | Overhead | R16 |  | 1 | 3 |  |  | 188 | 2020 | 2021 | R16
168923231103 | 164390231103 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-10 | 2021-05-17 | 2021-05-17 |  | 2021-10-25 | Overhead | R16 | 2021-08-31 | 6 |  | 77 | 40 | 121 | 2021 | 2021 | R16
165249214431 | 168369214431 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-03 | 2020-09-03 | 2020-12-21 |  | 2021-10-14 | Underground | R16 | 2021-04-20 | 1 | 78 | 87 | 128 | 291 | 2020 | 2021 | R16
163363160977 | 165217160977 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-13 | 2019-08-13 | 2019-08-13 |  | 2019-12-09 | Overhead | R16 | 2019-08-23 | 1 |  | 9 | 77 | 85 | 2019 | 2019 | R16
161721201601 | 165236201601 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-08-19 | 2020-08-20 | 2020-08-24 |  | 2021-01-22 | Overhead | R16 |  | 2 | 3 |  |  | 113 | 2020 | 2021 | R16
167655215736 | 163850215736 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-29 | 2020-12-29 | 2020-12-29 |  | 2021-11-08 | Overhead | R16 | 2021-04-22 | 1 |  | 83 | 143 | 225 | 2020 | 2021 | R16
163403164054 | 160645164054 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-12 | 2019-09-12 | 2019-09-12 |  | 2019-10-30 | Overhead | R16 | 2019-10-21 | 1 |  | 28 | 8 | 35 | 2019 | 2019 | R16
166589206123 | 166670206123 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-08-25 | 2020-09-24 | 2020-10-02 | 2022-01-10 | 2022-01-08 | Overhead | R16 | 2022-01-10 | 23 | 7 | 332 |  | 359 | 2020 | 2022 | R16
160845145842 | 167336145842 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential Subdivision | 2019-03-08 | 2019-03-11 | 2019-03-12 | 2021-04-30 | 2020-07-13 | Underground | R16 | 2021-04-30 | 2 | 2 | 559 |  | 352 | 2019 | 2020 | R16
165212211517 | 166299211517 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-07 | 2020-10-13 | 2020-11-20 | 2021-02-22 | 2021-03-01 | Underground | R16 | 2021-02-22 | 5 | 29 | 67 | 6 | 104 | 2020 | 2021 | R16
164334217168 | 167265217168 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-01-14 | 2021-01-14 | 2021-01-14 | 2021-06-01 | 2021-06-03 | Underground | R16 | 2021-06-01 | 1 |  | 99 | 3 | 101 | 2021 | 2021 | R16
163440173756 | 165596173756 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-12-02 | 2019-12-02 | 2019-12-09 |  | 2020-01-08 | Overhead | R16 |  | 1 | 6 |  |  | 28 | 2019 | 2020 | R16
168885154681 | 167530154681 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-05-06 | 2019-05-06 | 2019-06-06 | 2020-05-28 | 2022-08-03 | Underground | R16 | 2020-05-28 | 1 | 24 | 256 | 570 | 848 | 2019 | 2022 | R16
163514163935 | 163459163935 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-02 | 2019-08-02 | 2019-09-12 |  | 2020-01-08 | Underground | R16 | 2020-01-02 | 1 | 30 | 81 | 5 | 114 | 2019 | 2020 | R16
168266229458 | 162822229458 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-03-23 | 2021-05-05 | 2021-05-05 |  | 2021-11-08 | Overhead | R16 | 2021-05-24 | 32 |  | 14 | 121 | 165 | 2021 | 2021 | R16
162803209592 | 161555209592 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-30 | 2020-10-30 | 2020-11-04 | 2021-01-31 | 2021-02-10 | Overhead | R16 | 2021-01-31 | 1 | 4 | 63 | 8 | 74 | 2020 | 2021 | R16
163617170226 | 163665170226 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-05 | 2019-08-05 | 2019-10-30 |  | 2019-11-08 | Overhead | R16 | 2019-11-01 | 1 | 63 | 3 | 6 | 70 | 2019 | 2019 | R16
164426228791 | 161425228791 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-29 | 2021-04-29 | 2021-04-29 | 2021-05-14 | 2021-05-17 | Overhead | R16 | 2021-05-14 | 1 |  | 12 | 2 | 13 | 2021 | 2021 | R16
164532211726 | 166549211726 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-23 | 2020-11-23 | 2020-11-23 | 2021-05-07 | 2021-05-10 | Overhead | R16 | 2021-05-07 | 1 |  | 120 | 2 | 121 | 2020 | 2021 | R16
163684163446 | 167661163446 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-08-27 | 2019-08-27 | 2019-09-05 |  | 2019-10-16 | Underground | R16 | 2019-10-08 | 1 | 8 | 24 | 7 | 37 | 2019 | 2019 | R16
163755163109 | 168745163109 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-03 | 2019-09-03 | 2019-09-04 |  | 2019-10-09 | Overhead | R16 | 2019-09-25 | 1 | 2 | 16 | 11 | 27 | 2019 | 2019 | R16
163768165678 | 169769165678 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-07 | 2019-09-07 | 2019-09-25 |  | 2020-06-09 | Underground | R16 | 2019-12-17 | 0 | 13 | 60 | 126 | 197 | 2019 | 2020 | R16
163784184007 | 164850184007 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-10-04 | 2019-10-04 | 2020-03-13 |  | 2020-06-09 | Overhead | R16 |  | 1 | 116 |  |  | 178 | 2019 | 2020 | R16
163509218388 | 169415218388 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-25 | 2021-01-25 | 2021-01-25 |  | 2022-05-12 | Overhead | R16 | 2022-04-19 | 1 |  | 322 | 18 | 339 | 2021 | 2022 | R16
163805163937 | 164221163937 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-06 | 2019-08-06 | 2019-09-12 |  | 2021-11-13 | Underground | R16 | 2019-12-16 | 1 | 28 | 68 | 500 | 594 | 2019 | 2021 | R16
163455233222 | 161315233222 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-02 | 2021-06-02 | 2021-06-02 | 2022-01-27 | 2022-03-02 | Overhead | R16 | 2022-01-27 | 1 |  | 172 | 25 | 196 | 2021 | 2022 | R16
168060209239 | 166775209239 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-09 | 2020-10-09 | 2020-11-04 | 2020-12-21 | 2021-08-11 | Underground | R16 | 2020-12-21 | 1 | 19 | 34 | 168 | 219 | 2020 | 2021 | R16
160337225741 | 167487225741 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-01 | 2021-04-02 | 2021-04-02 | 2021-08-12 | 2021-10-27 | Overhead | R16 | 2021-08-12 | 25 |  | 95 | 55 | 173 | 2021 | 2021 | R16
166146163308 | 165636163308 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG R16 RESD AND NON RESD UD | Commercial | 2019-02-28 | 2019-03-15 | 2019-09-04 | 2022-02-24 | 2022-03-16 | Underground | R16 | 2022-02-24 | 12 | 124 | 647 | 15 | 795 | 2019 | 2022 | R16
163840179224 | 167360179224 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2020-02-03 | 2020-02-03 | 2020-02-03 |  | 2022-10-19 | Overhead | R16 |  | 1 |  |  |  | 708 | 2020 | 2022 | R16
163845177975 | 161523177975 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-17 | 2019-09-17 | 2020-01-24 |  | 2020-07-08 | Overhead | R16 |  | 1 | 94 |  |  | 212 | 2019 | 2020 | R16
165632210051 | 163453210051 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-06 | 2020-11-06 | 2020-11-10 |  | 2021-04-14 | Underground | R16 | 2020-12-14 | 1 | 3 | 25 | 88 | 114 | 2020 | 2021 | R16
168915238308 | 162997238308 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-05 | 2021-07-09 | 2021-07-09 | 2022-08-31 | 2022-10-26 | Overhead | R16 | 2022-08-31 | 48 |  | 299 | 41 | 386 | 2021 | 2022 | R16
166679220788 | 165049220788 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-18 | 2021-02-18 | 2021-02-18 | 2021-11-05 | 2021-11-08 | Overhead | R16 | 2021-11-05 | 1 |  | 187 | 2 | 188 | 2021 | 2021 | R16
162105210459 | 162420210459 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-09-22 | 2020-09-22 | 2020-11-13 |  | 2021-12-16 | Underground | R16 | 2021-11-15 | 1 | 39 | 262 | 24 | 323 | 2020 | 2021 | R16
165503198980 | 168512198980 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-16 | 2020-07-29 | 2020-07-29 |  | 2020-12-29 | Overhead | R16 | 2020-09-30 | 10 |  | 46 | 65 | 119 | 2020 | 2020 | R16
167515153550 | 167862153550 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-07 | 2019-05-07 | 2019-05-28 | 2019-09-16 | 2019-09-17 | Underground | R16 | 2019-09-16 | 1 | 16 | 80 | 2 | 96 | 2019 | 2019 | R16
163833211725 | 166476211725 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-23 | 2020-11-23 | 2020-11-23 | 2021-04-09 | 2021-04-12 | Overhead | R16 | 2021-04-09 | 1 |  | 100 | 2 | 101 | 2020 | 2021 | R16
163861163513 | 169511163513 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2019-09-05 | 2019-09-05 | 2019-09-06 |  | 2020-07-13 | Overhead | R16 | 2020-06-15 | 1 | 2 | 202 | 21 | 223 | 2019 | 2020 | R16
165376226700 | 163911226700 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-29 | 2021-04-13 | 2021-04-13 | 2021-06-09 | 2021-08-16 | Overhead | R16 | 2021-06-09 | 76 |  | 42 | 49 | 165 | 2020 | 2021 | R16
163963178547 | 162003178547 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Commercial | 2019-11-07 | 2020-01-07 | 2020-01-29 |  | 2021-02-16 | Underground | R16 |  | 44 | 17 |  |  | 334 | 2019 | 2021 | R16
160665221087 | 165728221087 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-22 | 2021-02-22 | 2021-02-22 |  | 2021-08-05 | Underground | R16 | 2021-03-29 | 1 |  | 26 | 94 | 119 | 2021 | 2021 | R16
163978165703 | 162726165703 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-24 | 2019-09-24 | 2019-09-24 |  | 2019-12-30 | Overhead | R16 | 2019-12-06 | 1 |  | 54 | 17 | 70 | 2019 | 2019 | R16
160322224751 | 165855224751 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-22 | 2021-03-26 | 2021-03-26 | 2021-05-10 | 2021-10-25 | Overhead | R16 | 2021-05-10 | 25 |  | 32 | 121 | 176 | 2021 | 2021 | R16
166318149983 | 168990149983 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2019-03-19 | 2019-03-20 | 2019-04-22 | 2019-10-22 | 2020-02-04 | Underground | R16 | 2019-10-22 | 2 | 24 | 132 | 76 | 231 | 2019 | 2020 | R16
163753209549 | 162790209549 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-04 | 2020-11-04 | 2020-11-04 | 2021-02-24 | 2021-06-02 | Underground | R16 | 2021-02-24 | 1 |  | 81 | 71 | 151 | 2020 | 2021 | R16
163989169016 | 165538169016 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-08 | 2019-10-09 | 2019-10-21 |  | 2020-07-08 | Underground | R16 | 2020-05-15 | 2 | 9 | 150 | 39 | 197 | 2019 | 2020 | R16
160596225634 | 163606225634 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-26 | 2021-03-26 | 2021-04-02 | 2022-03-21 | 2022-04-01 | Underground | R16 | 2022-03-21 | 1 | 6 | 252 | 10 | 266 | 2021 | 2022 | R16
164001181445 | 161181181445 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-09-16 | 2019-09-16 | 2020-02-21 |  | 2022-02-07 | Underground | R16 | 2022-01-14 | 1 | 115 | 496 | 17 | 626 | 2019 | 2022 | R16
163504232223 | 166560232223 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-18 | 2021-05-21 | 2021-05-24 |  | 2021-10-11 | Overhead | R16 | 2021-09-13 | 4 | 2 | 81 | 21 | 105 | 2021 | 2021 | R16
160373153199 | 160539153199 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-23 | 2019-05-23 | 2019-05-23 | 2020-01-09 | 2021-11-10 | Overhead | R16 | 2020-01-09 | 1 |  | 166 | 480 | 645 | 2019 | 2021 | R16
164068163621 | 169757163621 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-09-06 | 2019-09-06 | 2019-09-06 |  | 2019-09-25 | Overhead | R16 | 2019-09-18 | 1 |  | 9 | 6 | 14 | 2019 | 2019 | R16
169364207653 | 166980207653 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-09 | 2020-10-09 | 2020-10-19 | 2021-03-23 | 2021-08-06 | Underground | R16 | 2021-03-23 | 1 | 7 | 112 | 99 | 216 | 2020 | 2021 | R16
165235147469 | 160546147469 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-28 | 2019-03-28 | 2019-03-28 | 2019-05-02 | 2019-06-06 | Overhead | R16 | 2019-05-02 | 1 |  | 26 | 26 | 51 | 2019 | 2019 | R16
164102164262 | 160549164262 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-12 | 2019-09-12 | 2019-09-12 |  | 2022-01-14 | Overhead | R16 | 2021-07-29 | 1 |  | 491 | 122 | 612 | 2019 | 2022 | R16
164118162832 | 168591162832 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-30 | 2019-08-30 | 2019-08-30 |  | 2019-10-16 | Overhead | R16 | 2019-10-09 | 1 |  | 29 | 6 | 34 | 2019 | 2019 | R16
164163191283 | 166170191283 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-19 | 2020-05-15 | 2020-05-15 |  | 2020-08-20 | Overhead | R16 | 2020-06-24 | 195 |  | 29 | 42 | 264 | 2019 | 2020 | R16
164165162750 | 166142162750 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-19 | 2019-08-29 | 2019-08-29 |  | 2019-11-14 | Overhead | R16 | 2019-11-06 | 9 |  | 50 | 7 | 64 | 2019 | 2019 | R16
167238220941 | 165815220941 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-01-08 | 2021-01-25 | 2021-02-18 |  | 2021-10-25 | Underground | R16 |  | 12 | 19 |  |  | 207 | 2021 | 2021 | R16
163974215229 | 160826215229 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-14 | 2020-12-21 | 2020-12-21 | 2021-03-04 | 2021-06-03 | Overhead | R16 | 2021-03-04 | 6 |  | 54 | 66 | 124 | 2020 | 2021 | R16
165292228018 | 168367228018 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-04-15 | 2021-04-15 | 2021-04-22 |  | 2021-11-04 | Underground | R16 | 2021-06-24 | 1 | 6 | 46 | 96 | 146 | 2021 | 2021 | R16
167353217593 | 167980217593 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-19 | 2021-01-19 | 2021-01-19 | 2021-04-13 | 2021-04-14 | Overhead | R16 | 2021-04-13 | 1 |  | 61 | 2 | 62 | 2021 | 2021 | R16
164333210967 | 165238210967 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-11-17 | 2020-11-17 | 2020-11-17 | 2020-12-08 | 2021-04-14 | Underground | R16 | 2020-12-08 | 1 |  | 16 | 92 | 107 | 2020 | 2021 | R16
164314164720 | 161150164720 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-15 | 2019-09-15 | 2019-09-16 |  | 2019-10-28 | Overhead | R16 | 2019-10-17 | 0 | 1 | 24 | 8 | 31 | 2019 | 2019 | R16
167779203888 | 160123203888 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-09-10 | 2020-09-14 | 2020-09-15 |  | 2023-09-13 | Underground | R16 |  | 3 | 2 |  |  | 785 | 2020 | 2023 | R16
167227205752 | 164506205752 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-29 | 2020-09-30 | 2020-09-30 |  | 2021-01-22 | Overhead | R16 | 2020-10-15 | 2 |  | 12 | 72 | 84 | 2020 | 2021 | R16
164322164165 | 160656164165 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-09-11 | 2019-09-11 | 2019-09-11 |  | 2019-10-28 | Overhead | R16 | 2019-10-17 | 1 |  | 27 | 8 | 34 | 2019 | 2019 | R16
164325161748 | 166519161748 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-20 | 2019-08-20 | 2019-08-20 |  | 2019-10-10 | Underground | R16 | 2019-09-26 | 1 |  | 28 | 11 | 38 | 2019 | 2019 | R16
166760226072 | 166295226072 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-07 | 2021-04-07 | 2021-04-07 |  | 2021-11-08 | Overhead | R16 | 2021-05-21 | 1 |  | 33 | 122 | 154 | 2021 | 2021 | R16
163594235544 | 168956235544 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-22 | 2021-04-08 | 2021-06-18 |  | 2021-10-25 | Overhead | R16 |  | 55 | 52 |  |  | 197 | 2021 | 2021 | R16
165276147090 | 169694147090 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-25 | 2019-03-25 | 2019-03-25 | 2019-06-17 | 2019-06-18 | Overhead | R16 | 2019-06-17 | 1 |  | 61 | 2 | 62 | 2019 | 2019 | R16
167624148159 | 161955148159 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-05 | 2019-04-05 | 2019-04-05 | 2019-04-24 | 2019-04-25 | Overhead | R16 | 2019-04-24 | 1 |  | 14 | 2 | 15 | 2019 | 2019 | R16
164399162060 | 166878162060 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-08-22 | 2019-08-22 | 2019-08-22 |  | 2019-11-21 | Underground | R16 | 2019-11-14 | 1 |  | 61 | 6 | 66 | 2019 | 2019 | R16
166110149323 | 163553149323 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-15 | 2019-04-15 | 2019-04-15 | 2019-05-13 | 2019-05-20 | Overhead | R16 | 2019-05-13 | 1 |  | 21 | 6 | 26 | 2019 | 2019 | R16
164400162041 | 165474162041 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-14 | 2019-08-22 | 2019-08-22 |  | 2019-11-27 | Overhead | R16 | 2019-11-22 | 7 |  | 67 | 4 | 76 | 2019 | 2019 | R16
164402173658 | 163363173658 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-09-27 | 2019-09-27 | 2019-12-05 |  | 2020-07-09 | Underground | R16 |  | 1 | 50 |  |  | 205 | 2019 | 2020 | R16
161920244135 | 165361244135 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OD | Residential | 2021-01-06 | 2021-02-24 | 2021-08-19 | 2021-09-20 | 2021-10-06 | Overhead | R16 | 2021-09-20 | 36 | 127 | 23 | 13 | 196 | 2021 | 2021 | R16
167162155667 | 160526155667 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-23 | 2019-05-23 | 2019-06-18 | 2019-09-01 | 2019-09-04 | Underground | R16 | 2019-09-01 | 1 | 19 | 54 | 3 | 75 | 2019 | 2019 | R16
162503210764 | 169665210764 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-22 | 2020-10-22 | 2020-11-15 |  | 2021-04-07 | Overhead | R16 | 2020-11-30 | 1 | 17 | 11 | 93 | 120 | 2020 | 2021 | R16
163021226753 | 168027226753 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-04-14 | 2021-04-14 | 2021-04-14 | 2021-06-08 | 2021-06-08 | Overhead | R16 | 2021-06-08 | 1 |  | 40 |  | 40 | 2021 | 2021 | R16
165080229460 | 166398229460 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-04-07 | 2021-04-13 | 2021-05-04 | 2021-06-05 | 2021-06-09 | Underground | R16 | 2021-06-05 | 5 | 16 | 24 | 3 | 46 | 2021 | 2021 | R16
165892216384 | 165300216384 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-06 | 2021-01-06 | 2021-01-06 | 2021-01-08 | 2021-11-05 | Overhead | R16 | 2021-01-08 | 1 |  | 3 | 216 | 218 | 2021 | 2021 | R16
161252216959 | 166882216959 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-13 | 2021-01-13 | 2021-01-13 |  | 2021-06-02 | Overhead | R16 | 2021-03-05 | 1 |  | 38 | 64 | 101 | 2021 | 2021 | R16
160611154420 | 161087154420 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-28 | 2019-05-28 | 2019-06-04 | 2019-09-11 | 2019-09-12 | Underground | R16 | 2019-09-11 | 1 | 6 | 72 | 2 | 78 | 2019 | 2019 | R16
165201216306 | 164998216306 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-06 | 2021-01-06 | 2021-01-06 | 2021-03-19 | 2022-09-12 | Overhead | R16 | 2021-03-19 | 1 |  | 53 | 387 | 439 | 2021 | 2022 | R16
162905208719 | 169464208719 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-21 | 2020-10-28 | 2020-10-28 |  | 2021-04-14 | Underground | R16 | 2020-12-15 | 6 |  | 35 | 87 | 126 | 2020 | 2021 | R16
166410145062 | 166423145062 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-03-05 | 2019-03-05 | 2019-03-05 |  | 2019-03-07 | Underground | R16 |  | 1 |  |  |  | 3 | 2019 | 2019 | R16
164684202631 | 168095202631 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-28 | 2019-08-28 | 2020-09-02 |  | 2021-07-28 | Underground | R16 | 2021-01-15 | 1 | 266 | 98 | 139 | 501 | 2019 | 2021 | R16
164686162376 | 167746162376 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-27 | 2019-08-27 | 2019-08-27 |  | 2021-04-16 | Underground | R16 | 2021-01-08 | 1 |  | 359 | 71 | 429 | 2019 | 2021 | R16
163962161185 | 163887161185 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-04-17 | 2019-07-25 | 2019-08-14 | 2019-11-24 | 2020-04-28 | Underground | R16 | 2019-11-24 | 72 | 15 | 73 | 112 | 270 | 2019 | 2020 | R16
164690166679 | 164410166679 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-03 | 2019-10-03 | 2019-10-03 |  | 2019-11-26 | Overhead | R16 | 2019-11-11 | 1 |  | 28 | 12 | 39 | 2019 | 2019 | R16
161721216989 | 165203216989 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2021-01-06 | 2021-01-06 | 2021-01-12 | 2021-11-02 | 2021-11-08 | Underground | R16 | 2021-11-02 | 1 | 5 | 211 | 5 | 219 | 2021 | 2021 | R16
164699165056 | 162053165056 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-20 | 2019-09-20 | 2019-09-20 |  | 2019-11-15 | Overhead | R16 | 2019-10-31 | 1 |  | 30 | 12 | 41 | 2019 | 2019 | R16
162218269073 | 168240269073 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OD | Commercial | 2021-01-19 | 2021-07-06 | 2022-02-15 | 2022-05-11 | 2022-05-27 | Overhead | R16 | 2022-05-11 | 121 | 161 | 62 | 13 | 354 | 2021 | 2022 | R16
164789162372 | 167696162372 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-27 | 2019-08-27 | 2019-08-27 |  | 2021-11-02 | Underground | R16 | 2021-06-25 | 1 |  | 479 | 93 | 571 | 2019 | 2021 | R16
166676149958 | 165033149958 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-23 | 2019-04-23 | 2019-04-23 | 2019-06-04 | 2019-06-04 | Overhead | R16 | 2019-06-04 | 1 |  | 31 |  | 31 | 2019 | 2019 | R16
164796164305 | 160775164305 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-13 | 2019-09-13 | 2019-09-13 |  | 2019-10-28 | Overhead | R16 | 2019-10-14 | 1 |  | 22 | 11 | 32 | 2019 | 2019 | R16
165351203893 | 161032203893 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-15 | 2020-09-15 | 2020-09-15 |  | 2021-01-08 | Underground | R16 | 2020-10-07 | 1 |  | 17 | 68 | 84 | 2020 | 2021 | R16
166625232349 | 165596232349 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-11-18 | 2021-01-19 | 2021-05-26 | 2021-08-10 | 2022-03-23 | Underground | R16 | 2021-08-10 | 45 | 92 | 55 | 162 | 351 | 2020 | 2022 | R16
164813162538 | 167996162538 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-28 | 2019-08-28 | 2019-08-28 |  | 2021-08-11 | Underground | R16 | 2021-06-28 | 1 |  | 479 | 33 | 511 | 2019 | 2021 | R16
163449200388 | 163347200388 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-12 | 2020-08-12 | 2020-08-12 |  | 2020-12-18 | Overhead | R16 | 2020-11-04 | 1 |  | 61 | 33 | 93 | 2020 | 2020 | R16
164816163918 | 160252163918 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-10 | 2019-09-10 | 2019-09-10 |  | 2019-11-26 | Overhead | R16 | 2019-11-19 | 1 |  | 51 | 6 | 56 | 2019 | 2019 | R16
167223147895 | 161295147895 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-04-02 | 2019-04-02 | 2019-04-02 | 2019-04-24 | 2019-04-25 | Overhead | R16 | 2019-04-24 | 1 |  | 17 | 2 | 18 | 2019 | 2019 | R16
168180198593 | 169790198593 | MOBILE HOMES PARK AB622 | ELEC SVC FOR MOBILE HOMES | Residential | 2020-07-23 | 2020-07-23 | 2020-07-27 |  | 2021-07-24 | Underground | R16 |  | 1 | 3 |  |  | 262 | 2020 | 2021 | R16
162493145429 | 167241145429 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-03-08 | 2019-03-08 | 2019-03-08 | 2019-03-21 | 2019-03-22 | Overhead | R16 | 2019-03-21 | 1 |  | 10 | 2 | 11 | 2019 | 2019 | R16
167397233114 | 164230233114 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2021-05-10 | 2021-05-10 | 2021-06-02 |  | 2021-11-09 | Underground | R16 |  | 1 | 18 |  |  | 132 | 2021 | 2021 | R16
166316232936 | 169653232936 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-21 | 2021-04-26 | 2021-06-02 | 2021-06-14 | 2021-08-04 | Underground | R16 | 2021-06-14 | 4 | 28 | 9 | 38 | 76 | 2021 | 2021 | R16
162048146794 | 169452146794 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-22 | 2019-03-22 | 2019-03-22 | 2019-04-08 | 2019-04-10 | Overhead | R16 | 2019-04-08 | 1 |  | 12 | 3 | 14 | 2019 | 2019 | R16
164861196532 | 165908196532 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2020-07-06 | 2020-07-06 | 2020-07-07 |  | 2021-11-16 | Underground | R16 |  | 1 | 2 |  |  | 357 | 2020 | 2021 | R16
167212222018 | 168024222018 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-03 | 2021-03-03 | 2021-03-03 |  | 2021-08-30 | Overhead | R16 | 2021-06-10 | 1 |  | 72 | 58 | 129 | 2021 | 2021 | R16
164861264148 | 165443264148 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2021-12-13 | 2021-12-15 | 2022-01-10 |  | 2022-08-23 | Underground | R16 |  | 3 | 19 |  |  | 182 | 2021 | 2022 | R16
162322226102 | 166333226102 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-07 | 2021-04-07 | 2021-04-07 | 2021-05-10 | 2021-08-26 | Overhead | R16 | 2021-05-10 | 1 |  | 24 | 79 | 102 | 2021 | 2021 | R16
164925166829 | 160710166829 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-11 | 2019-09-11 | 2019-10-03 |  | 2019-11-26 | Underground | R16 | 2019-11-20 | 1 | 17 | 35 | 5 | 55 | 2019 | 2019 | R16
164944165753 | 162912165753 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-25 | 2019-09-25 | 2019-09-25 |  | 2019-12-30 | Overhead | R16 | 2019-12-23 | 1 |  | 64 | 6 | 69 | 2019 | 2019 | R16
164945162243 | 167290162243 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-23 | 2019-08-26 | 2019-08-26 |  | 2019-10-11 | Overhead | R16 | 2019-10-01 | 2 |  | 27 | 9 | 36 | 2019 | 2019 | R16
169994149372 | 163816149372 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-16 | 2019-04-16 | 2019-04-16 | 2019-04-22 | 2019-12-03 | Underground | R16 | 2019-04-22 | 1 |  | 5 | 162 | 166 | 2019 | 2019 | R16
164969163451 | 167025163451 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-23 | 2019-09-05 | 2019-09-05 |  | 2019-11-14 | Overhead | R16 | 2019-11-07 | 10 |  | 46 | 6 | 60 | 2019 | 2019 | R16
164987164328 | 165007164328 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-12 | 2019-08-12 | 2019-09-14 |  | 2020-06-24 | Underground | R16 | 2020-04-21 | 1 | 25 | 157 | 47 | 228 | 2019 | 2020 | R16
168065239638 | 160605239638 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2020-10-26 | 2020-10-26 | 2021-07-20 | 2022-04-11 | 2022-04-18 | Underground | R16 | 2022-04-11 | 1 | 192 | 190 | 6 | 386 | 2020 | 2022 | R16
162692228432 | 166740228432 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-08 | 2021-04-26 | 2021-04-26 | 2022-12-19 | 2022-12-20 | Overhead | R16 | 2022-12-19 | 13 |  | 431 | 2 | 444 | 2021 | 2022 | R16
164993166346 | 161111166346 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-09-14 | 2019-09-14 | 2019-09-30 |  | 2020-06-09 | Underground | R16 | 2020-01-16 | 0 | 11 | 79 | 104 | 192 | 2019 | 2020 | R16
161890148131 | 161549148131 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-04 | 2019-04-04 | 2019-04-04 | 2019-04-18 | 2019-04-18 | Overhead | R16 | 2019-04-18 | 1 |  | 11 |  | 11 | 2019 | 2019 | R16
169753207747 | 164063207747 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-28 | 2020-09-28 | 2020-10-20 |  | 2021-11-08 | Overhead | R16 | 2021-05-19 | 1 | 17 | 152 | 124 | 291 | 2020 | 2021 | R16
165034165093 | 165192165093 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-13 | 2019-08-13 | 2019-09-19 |  | 2021-10-25 | Underground | R16 | 2021-08-23 | 1 | 28 | 503 | 46 | 575 | 2019 | 2021 | R16
168535224896 | 164065224896 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Commercial | 2021-03-29 | 2021-03-29 | 2021-03-29 |  | 2021-06-05 | Overhead | R16 |  | 1 |  |  |  | 50 | 2021 | 2021 | R16
162136205053 | 162384205053 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2020-09-22 | 2020-09-22 | 2020-09-25 | 2021-11-25 | 2021-11-29 | Overhead | R16 | 2021-11-25 | 1 | 4 | 305 | 3 | 310 | 2020 | 2021 | R16
162014151340 | 167096151340 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-08 | 2019-03-08 | 2019-05-06 | 2020-01-21 | 2022-11-24 | Underground | R16 | 2020-01-21 | 1 | 42 | 187 | 743 | 970 | 2019 | 2022 | R16
169188204487 | 162270204487 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-21 | 2020-09-21 | 2020-09-21 |  | 2021-01-08 | Overhead | R16 | 2020-10-07 | 1 |  | 13 | 68 | 80 | 2020 | 2021 | R16
168630174750 | 168923174750 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-05-14 | 2019-09-24 | 2019-12-18 | 2020-05-15 | 2020-09-18 | Underground | R16 | 2020-05-15 | 96 | 62 | 108 | 91 | 354 | 2019 | 2020 | R16
164214226412 | 167191226412 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-12 | 2021-04-12 | 2021-04-12 | 2021-06-11 | 2021-08-24 | Overhead | R16 | 2021-06-11 | 1 |  | 45 | 53 | 97 | 2021 | 2021 | R16
165114164775 | 165326164775 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-13 | 2019-08-13 | 2019-09-17 |  | 2019-10-30 | Underground | R16 | 2019-10-23 | 1 | 26 | 27 | 6 | 57 | 2019 | 2019 | R16
168123151351 | 167483151351 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-06 | 2019-05-06 | 2019-05-06 | 2019-07-17 | 2019-11-15 | Overhead | R16 | 2019-07-17 | 1 |  | 53 | 88 | 140 | 2019 | 2019 | R16
163902241409 | 164381241409 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-11-11 | 2020-11-11 | 2021-07-30 | 2022-10-03 | 2022-10-11 | Underground | R16 | 2022-10-03 | 1 | 188 | 307 | 7 | 500 | 2020 | 2022 | R16
165135161678 | 166426161678 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-08-20 | 2019-08-20 | 2019-08-20 |  | 2020-07-10 | Overhead | R16 | 2020-06-10 | 1 |  | 212 | 23 | 234 | 2019 | 2020 | R16
169288140162 | 166981140162 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-14 | 2019-01-14 | 2019-01-14 | 2019-05-28 | 2019-05-29 | Overhead | R16 | 2019-05-28 | 1 |  | 97 | 2 | 98 | 2019 | 2019 | R16
162240236005 | 161013236005 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-01 | 2021-06-01 | 2021-06-21 |  | 2021-11-18 | Underground | R16 | 2021-10-28 | 1 | 15 | 94 | 16 | 123 | 2021 | 2021 | R16
165190162880 | 168298162880 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-30 | 2019-08-30 | 2019-08-30 |  | 2019-11-13 | Overhead | R16 | 2019-11-04 | 1 |  | 47 | 8 | 54 | 2019 | 2019 | R16
163866200120 | 168514200120 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-07-16 | 2020-07-16 | 2020-08-08 | 2021-01-14 | 2021-04-21 | Overhead | R16 | 2021-01-14 | 1 | 17 | 114 | 70 | 200 | 2020 | 2021 | R16
169345208044 | 168995208044 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-20 | 2020-10-22 | 2020-10-22 | 2021-05-12 | 2021-11-03 | Overhead | R16 | 2021-05-12 | 3 |  | 145 | 126 | 272 | 2020 | 2021 | R16
165242161902 | 166762161902 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-08-21 | 2019-08-21 | 2019-08-21 |  | 2019-09-19 | Overhead | R16 | 2019-09-12 | 1 |  | 17 | 6 | 22 | 2019 | 2019 | R16
160513210801 | 161948210801 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-02 | 2020-11-13 | 2020-11-13 | 2021-02-08 | 2021-02-12 | Overhead | R16 | 2021-02-08 | 10 |  | 62 | 5 | 75 | 2020 | 2021 | R16
161384150825 | 168094150825 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-13 | 2019-03-13 | 2019-04-30 | 2019-11-19 | 2019-11-27 | Underground | R16 | 2019-11-19 | 1 | 35 | 146 | 7 | 186 | 2019 | 2019 | R16
161670210171 | 163757210171 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-10 | 2020-11-10 | 2020-11-10 | 2021-01-13 | 2021-01-14 | Overhead | R16 | 2021-01-13 | 1 |  | 47 | 2 | 48 | 2020 | 2021 | R16
163355198583 | 168315198583 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-07-15 | 2020-07-15 | 2020-07-27 |  | 2020-10-06 | Overhead | R16 | 2020-08-24 | 1 | 9 | 21 | 32 | 60 | 2020 | 2020 | R16
165270166042 | 169902166042 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-09 | 2019-09-09 | 2019-09-27 |  | 2021-11-10 | Underground | R16 | 2020-07-16 | 1 | 15 | 210 | 345 | 568 | 2019 | 2021 | R16
167410199876 | 162610199876 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-07 | 2020-08-07 | 2020-08-07 | 2020-08-18 | 2020-08-20 | Overhead | R16 | 2020-08-18 | 1 |  | 8 | 3 | 10 | 2020 | 2020 | R16
165301170641 | 160972170641 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-11-04 | 2019-11-04 | 2019-11-04 |  | 2020-06-09 | Overhead | R16 | 2020-02-27 | 1 |  | 84 | 74 | 157 | 2019 | 2020 | R16
165304162731 | 168624162731 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-30 | 2019-08-30 | 2019-08-30 |  | 2019-10-14 | Overhead | R16 | 2019-10-02 | 1 |  | 24 | 9 | 32 | 2019 | 2019 | R16
164461229658 | 163600229658 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-06 | 2021-05-06 | 2021-05-06 |  | 2021-10-27 | Overhead | R16 | 2021-08-11 | 1 |  | 70 | 56 | 125 | 2021 | 2021 | R16
165430207800 | 165446207800 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-03 | 2020-10-03 | 2020-10-20 |  | 2021-08-18 | Underground | R16 | 2021-06-16 | 0 | 12 | 172 | 46 | 228 | 2020 | 2021 | R16
165315164743 | 161232164743 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-16 | 2019-09-16 | 2019-09-16 |  | 2019-10-28 | Overhead | R16 | 2019-10-15 | 1 |  | 22 | 10 | 31 | 2019 | 2019 | R16
165902223908 | 160983223908 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-16 | 2021-03-16 | 2021-03-16 |  | 2021-11-04 | Overhead | R16 | 2021-04-05 | 1 |  | 15 | 154 | 168 | 2021 | 2021 | R16
168363211429 | 166010211429 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-19 | 2020-11-20 | 2020-11-20 |  | 2021-11-05 | Overhead | R16 | 2021-04-09 | 2 |  | 101 | 151 | 252 | 2020 | 2021 | R16
168882225232 | 163363225232 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential Subdivision | 2020-12-28 | 2020-12-28 | 2022-12-30 | 2022-12-30 | 2022-12-21 | Underground | R16 | 2022-12-30 | 1 | 525 |  |  | 518 | 2020 | 2022 | R16
165353163510 | 169610163510 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-06 | 2019-09-06 | 2019-09-06 |  | 2019-10-18 | Overhead | R16 | 2019-10-08 | 1 |  | 23 | 9 | 31 | 2019 | 2019 | R16
168904244119 | 162332244119 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-03 | 2021-05-07 | 2021-08-18 | 2021-09-27 | 2021-09-28 | Underground | R16 | 2021-09-27 | 5 | 74 | 29 | 2 | 107 | 2021 | 2021 | R16
165373162638 | 168293162638 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-30 | 2019-08-30 | 2019-08-30 |  | 2019-11-15 | Overhead | R16 | 2019-11-08 | 1 |  | 51 | 6 | 56 | 2019 | 2019 | R16
162375215450 | 163152215450 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-23 | 2020-12-23 | 2020-12-23 | 2021-03-25 | 2021-11-08 | Overhead | R16 | 2021-03-25 | 1 |  | 67 | 163 | 229 | 2020 | 2021 | R16
163619157965 | 169079157965 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-15 | 2019-05-15 | 2019-07-15 | 2021-12-16 | 2021-12-17 | Underground | R16 | 2021-12-16 | 1 | 44 | 634 | 2 | 678 | 2019 | 2021 | R16
161281211253 | 165208211253 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-02 | 2020-10-02 | 2020-11-20 | 2021-03-10 | 2021-08-16 | Underground | R16 | 2021-03-10 | 1 | 36 | 79 | 114 | 227 | 2020 | 2021 | R16
165477171698 | 167601171698 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-18 | 2019-10-18 | 2019-11-13 |  | 2020-06-09 | Underground | R16 | 2020-02-19 | 1 | 19 | 71 | 80 | 168 | 2019 | 2020 | R16
167390207005 | 161852207005 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-18 | 2020-09-18 | 2020-10-12 |  | 2021-08-12 | Underground | R16 | 2021-03-18 | 1 | 17 | 114 | 106 | 235 | 2020 | 2021 | R16
165497162625 | 167955162625 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-28 | 2019-08-28 | 2019-08-28 |  | 2019-10-16 | Overhead | R16 | 2019-08-29 | 1 |  | 2 | 35 | 36 | 2019 | 2019 | R16
163364217439 | 163391217439 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-25 | 2020-09-25 | 2021-01-18 |  | 2021-08-10 | Underground | R16 | 2021-03-23 | 1 | 82 | 47 | 101 | 228 | 2020 | 2021 | R16
169619222140 | 167389222140 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-01 | 2021-03-01 | 2021-03-01 |  | 2022-03-08 | Overhead | R16 | 2022-01-18 | 1 |  | 232 | 36 | 267 | 2021 | 2022 | R16
165515164329 | 165464164329 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-14 | 2019-09-14 | 2019-09-14 |  | 2019-10-16 | Overhead | R16 | 2019-10-07 | 23 |  | 16 | 8 | 46 | 2019 | 2019 | R16
166583232663 | 160261232663 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-27 | 2021-05-27 | 2021-05-27 |  | 2021-11-04 | Overhead | R16 | 2021-06-24 | 1 |  | 21 | 96 | 116 | 2021 | 2021 | R16
165541163094 | 168998163094 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-04 | 2019-09-04 | 2019-09-04 |  | 2019-11-14 | Overhead | R16 | 2019-11-06 | 1 |  | 46 | 7 | 52 | 2019 | 2019 | R16
165550161265 | 165552161265 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC DEVELOPMENT | Residential | 2019-08-14 | 2019-08-14 | 2019-08-14 |  | 2020-11-23 | Underground | R16 |  | 1 |  |  |  | 334 | 2019 | 2020 | R16
169274230251 | 164439230251 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-08-12 | 2021-08-12 | Overhead | R16 | 2021-08-12 | 1 |  | 68 |  | 68 | 2021 | 2021 | R16
165565162906 | 168640162906 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-30 | 2019-08-30 | 2019-08-30 |  | 2019-10-09 | Overhead | R16 | 2019-09-26 | 1 |  | 20 | 10 | 29 | 2019 | 2019 | R16
165570163536 | 169277163536 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-09-05 | 2019-09-06 | 2019-09-06 |  | 2019-11-14 | Overhead | R16 | 2019-10-03 | 2 |  | 20 | 31 | 51 | 2019 | 2019 | R16
165570185198 | 168240185198 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-03-25 | 2020-03-25 | 2020-03-25 |  | 2020-07-09 | Overhead | R16 | 2020-06-01 | 1 |  | 49 | 29 | 77 | 2020 | 2020 | R16
165588163313 | 168079163313 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2019-08-28 | 2019-08-28 | 2019-09-04 |  | 2019-10-28 | Overhead | R16 |  | 1 | 6 |  |  | 44 | 2019 | 2019 | R16
167301219396 | 160442219396 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-25 | 2021-02-04 | 2021-02-04 | 2021-07-02 | 2022-01-11 | Overhead | R16 | 2021-07-02 | 74 |  | 107 | 138 | 317 | 2020 | 2022 | R16
164163263396 | 168938263396 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OD | Residential | 2021-01-22 | 2021-03-29 | 2022-01-04 | 2022-04-19 | 2022-05-16 | Overhead | R16 | 2022-04-19 | 47 | 202 | 76 | 20 | 342 | 2021 | 2022 | R16
165603163828 | 167898163828 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-28 | 2019-09-10 | 2019-09-10 |  | 2019-11-13 | Overhead | R16 | 2019-11-05 | 10 |  | 41 | 7 | 56 | 2019 | 2019 | R16
165604164084 | 160387164084 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-11 | 2019-09-11 | 2019-09-11 |  | 2021-11-10 | Overhead | R16 | 2019-12-18 | 1 |  | 71 | 496 | 566 | 2019 | 2021 | R16
161655150901 | 166283150901 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-30 | 2019-04-30 | 2019-04-30 | 2020-01-09 | 2023-06-08 | Overhead | R16 | 2020-01-09 | 1 |  | 183 | 891 | 1073 | 2019 | 2023 | R16
165693162025 | 166992162025 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-22 | 2019-08-22 | 2019-08-23 |  | 2019-11-26 | Overhead | R16 | 2019-11-19 | 1 | 2 | 63 | 6 | 69 | 2019 | 2019 | R16
168941239291 | 162325239291 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-22 | 2021-03-22 | 2021-07-16 |  | 2022-06-03 | Underground | R16 |  | 1 | 85 |  |  | 315 | 2021 | 2022 | R16
160547141932 | 160650141932 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-01-31 | 2019-01-31 | 2019-01-31 | 2019-08-06 | 2020-01-08 | Underground | R16 | 2019-08-06 | 1 |  | 134 | 112 | 245 | 2019 | 2020 | R16
165716163069 | 168609163069 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-30 | 2019-08-30 | 2019-09-03 |  | 2019-10-14 | Overhead | R16 | 2019-10-02 | 1 | 3 | 22 | 9 | 32 | 2019 | 2019 | R16
163178209011 | 161289209011 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-29 | 2020-10-29 | 2020-10-29 |  | 2022-10-18 | Overhead | R16 |  | 1 |  |  |  | 514 | 2020 | 2022 | R16
165728162730 | 168632162730 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-30 | 2019-08-30 | 2019-08-30 |  | 2019-10-09 | Overhead | R16 | 2019-09-26 | 1 |  | 20 | 10 | 29 | 2019 | 2019 | R16
167652211327 | 165964211327 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-11-19 | 2020-11-19 | 2020-11-19 |  | 2021-04-13 | Overhead | R16 | 2020-12-08 | 1 |  | 14 | 91 | 104 | 2020 | 2021 | R16
167173231589 | 168762231589 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-20 | 2021-05-20 | 2021-05-20 | 2021-07-22 | 2022-08-03 | Overhead | R16 | 2021-07-22 | 1 |  | 46 | 270 | 315 | 2021 | 2022 | R16
160868223681 | 162811223681 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-04 | 2020-11-04 | 2021-03-15 |  | 2021-08-23 | Underground | R16 | 2021-08-04 | 1 | 94 | 103 | 14 | 209 | 2020 | 2021 | R16
165736162040 | 166887162040 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-22 | 2019-08-22 | 2019-08-22 |  | 2019-10-16 | Overhead | R16 | 2019-10-04 | 1 |  | 32 | 9 | 40 | 2019 | 2019 | R16
169436146331 | 168725146331 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-18 | 2019-03-18 | 2019-03-18 | 2019-08-28 | 2023-06-07 | Overhead | R16 | 2019-08-28 | 1 |  | 118 | 986 | 1103 | 2019 | 2023 | R16
165741164110 | 169469164110 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-05 | 2019-09-05 | 2019-09-11 |  | 2021-04-29 | Overhead | R16 | 2021-02-10 | 1 | 5 | 371 | 57 | 431 | 2019 | 2021 | R16
166980217468 | 164442217468 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-04 | 2021-01-15 | 2021-01-15 | 2021-03-09 | 2021-08-11 | Overhead | R16 | 2021-03-09 | 10 |  | 38 | 112 | 158 | 2021 | 2021 | R16
167032205474 | 163169205474 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-09-24 | 2020-09-24 | 2020-09-28 |  | 2021-06-30 | Overhead | R16 | 2020-10-15 | 1 | 3 | 14 | 185 | 200 | 2020 | 2021 | R16
169394151629 | 167539151629 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-07 | 2019-05-07 | 2019-05-07 | 2019-07-12 | 2019-09-03 | Overhead | R16 | 2019-07-12 | 1 |  | 49 | 38 | 86 | 2019 | 2019 | R16
168474150894 | 161574150894 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-04 | 2019-04-04 | 2019-05-02 |  | 2019-12-31 | Overhead | R16 |  | 1 | 21 |  |  | 194 | 2019 | 2019 | R16
165804161647 | 166428161647 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-20 | 2019-08-20 | 2019-08-20 |  | 2021-04-14 | Overhead | R16 | 2020-12-10 | 1 |  | 343 | 90 | 432 | 2019 | 2021 | R16
162950229623 | 163883229623 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-02-11 | 2021-02-23 | 2021-05-05 | 2021-10-28 | 2021-10-29 | Overhead | R16 | 2021-10-28 | 9 | 52 | 127 | 2 | 187 | 2021 | 2021 | R16
160524150763 | 166065150763 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-29 | 2019-04-29 | 2019-04-29 | 2019-07-17 | 2019-08-26 | Overhead | R16 | 2019-07-17 | 1 |  | 58 | 29 | 86 | 2019 | 2019 | R16
169293210413 | 162320210413 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-11-02 | 2020-11-02 | 2020-11-11 | 2021-10-05 | 2021-10-18 | Underground | R16 | 2021-10-05 | 1 | 8 | 235 | 10 | 251 | 2020 | 2021 | R16
163695223327 | 163909223327 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-30 | 2021-02-24 | 2021-03-11 | 2021-04-01 | 2021-04-26 | Overhead | R16 | 2021-04-01 | 41 | 12 | 16 | 18 | 84 | 2020 | 2021 | R16
165861166406 | 167801166406 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-27 | 2019-08-27 | 2019-09-30 |  | 2021-04-16 | Underground | R16 | 2021-01-08 | 1 | 25 | 335 | 71 | 429 | 2019 | 2021 | R16
162773153613 | 163071153613 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-11 | 2019-04-11 | 2019-05-29 | 2019-09-26 | 2019-10-22 | Underground | R16 | 2019-09-26 | 1 | 35 | 87 | 19 | 139 | 2019 | 2019 | R16
161836220769 | 166723220769 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE FOR UPGRADE UD | Commercial | 2021-01-13 | 2021-01-19 | 2021-02-17 | 2021-03-04 | 2021-04-01 | Underground | R16 | 2021-03-04 | 5 | 22 | 12 | 21 | 57 | 2021 | 2021 | R16
160790218687 | 162718218687 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-22 | 2020-12-22 | 2021-01-27 | 2021-03-01 | 2021-11-01 | Underground | R16 | 2021-03-01 | 1 | 27 | 24 | 176 | 225 | 2020 | 2021 | R16
165987166289 | 161476166289 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-17 | 2019-09-17 | 2019-09-30 |  | 2019-10-30 | Overhead | R16 | 2019-10-22 | 1 | 10 | 17 | 7 | 32 | 2019 | 2019 | R16
165483233086 | 165052233086 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2020-11-16 | 2020-11-20 | 2021-06-01 | 2021-12-16 | 2022-01-11 | Underground | R16 | 2021-12-16 | 5 | 138 | 143 | 19 | 302 | 2020 | 2022 | R16
166000164577 | 161208164577 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-17 | 2019-09-17 | 2019-09-17 |  | 2019-12-06 | Overhead | R16 | 2019-10-16 | 1 |  | 22 | 38 | 59 | 2019 | 2019 | R16
169187206570 | 166503206570 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-08 | 2020-10-08 | 2020-10-08 | 2020-11-19 | 2021-07-13 | Overhead | R16 | 2020-11-19 | 1 |  | 31 | 169 | 199 | 2020 | 2021 | R16
160049201256 | 165817201256 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-08-21 | 2020-08-21 | 2020-08-21 | 2020-10-28 | 2021-01-29 | Underground | R16 | 2020-10-28 | 1 |  | 49 | 68 | 116 | 2020 | 2021 | R16
161401214197 | 169142214197 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-20 | 2020-10-20 | 2020-12-17 |  | 2021-11-05 | Underground | R16 | 2021-04-15 | 1 | 43 | 86 | 147 | 274 | 2020 | 2021 | R16
166009174090 | 162281174090 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-09-20 | 2019-10-28 | 2019-12-11 |  | 2021-12-28 | Overhead | R16 | 2021-11-23 | 27 | 33 | 510 | 26 | 593 | 2019 | 2021 | R16
168288234392 | 165621234392 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-21 | 2021-06-10 | 2021-06-10 | 2021-06-16 | 2021-10-25 | Overhead | R16 | 2021-06-16 | 79 |  | 5 | 94 | 176 | 2021 | 2021 | R16
166020167471 | 160432167471 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-11 | 2019-09-11 | 2019-10-09 |  | 2019-11-26 | Underground | R16 | 2019-11-19 | 1 | 21 | 30 | 6 | 55 | 2019 | 2019 | R16
168981143040 | 161885143040 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Residential | 2019-02-07 | 2019-02-07 | 2019-02-12 | 2022-04-14 | 2022-05-12 | Underground | R16 | 2022-04-14 | 1 | 4 | 828 | 21 | 851 | 2019 | 2022 | R16
166022167566 | 162243167566 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-21 | 2019-09-21 | 2019-10-09 |  | 2020-06-09 | Underground | R16 | 2019-12-17 | 0 | 13 | 50 | 126 | 187 | 2019 | 2020 | R16
165824198599 | 160442198599 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-28 | 2020-07-28 | 2020-07-28 | 2020-08-19 | 2020-10-06 | Overhead | R16 | 2020-08-19 | 1 |  | 17 | 35 | 51 | 2020 | 2020 | R16
166458199948 | 162299199948 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-06 | 2020-08-06 | 2020-08-06 | 2020-09-28 | 2020-09-29 | Overhead | R16 | 2020-09-28 | 1 |  | 38 | 2 | 39 | 2020 | 2020 | R16
166178166808 | 161106166808 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-14 | 2019-09-14 | 2019-10-04 |  | 2021-11-08 | Underground | R16 | 2021-05-27 | 0 | 15 | 430 | 118 | 561 | 2019 | 2021 | R16
165931243826 | 169998243826 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-10-24 | 2021-03-09 | 2021-08-15 | 2022-06-01 | 2022-06-16 | Underground | R16 | 2022-06-01 | 97 | 114 | 208 | 12 | 429 | 2020 | 2022 | R16
162748202014 | 167139202014 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-27 | 2020-08-27 | 2020-08-27 |  | 2021-06-14 | Overhead | R16 | 2020-10-22 | 1 |  | 41 | 168 | 208 | 2020 | 2021 | R16
169367211730 | 165841211730 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-19 | 2020-11-23 | 2020-11-23 |  | 2021-04-20 | Overhead | R16 | 2021-01-13 | 3 |  | 38 | 70 | 109 | 2020 | 2021 | R16
161664230165 | 164150230165 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-10 | 2021-05-10 | 2021-05-10 | 2021-12-29 | 2022-12-20 | Overhead | R16 | 2021-12-29 | 1 |  | 168 | 255 | 422 | 2021 | 2022 | R16
166299165484 | 162311165484 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-09-23 | 2019-09-23 | 2019-09-23 |  | 2020-07-14 | Overhead | R16 | 2020-06-16 | 1 |  | 192 | 21 | 212 | 2019 | 2020 | R16
169860231503 | 168472231503 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-19 | 2021-05-19 | 2021-05-19 |  | 2022-03-11 | Overhead | R16 | 2022-02-15 | 1 |  | 195 | 19 | 213 | 2021 | 2022 | R16
163490223378 | 160300223378 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-12 | 2021-03-12 | 2021-03-12 |  | 2022-08-24 | Overhead | R16 |  | 1 |  |  |  | 379 | 2021 | 2022 | R16
167712152649 | 169174152649 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-15 | 2019-05-15 | 2019-05-16 | 2019-09-23 | 2019-09-27 | Overhead | R16 | 2019-09-23 | 1 | 2 | 93 | 5 | 98 | 2019 | 2019 | R16
166152224970 | 167342224970 | NON-RESIDENTIAL - HEALTH CARE | UG R16 RESD AND NON RESD UD | Commercial | 2021-01-15 | 2021-02-06 | 2021-03-26 | 2021-08-30 | 2021-10-25 | Underground | R16 | 2021-08-30 | 16 | 35 | 112 | 41 | 202 | 2021 | 2021 | R16
166407194693 | 166408194693 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-08-21 | 2020-02-13 | 2020-06-18 |  | 2022-10-29 | Underground | R16 |  | 127 | 91 |  |  | 833 | 2019 | 2022 | R16
166407259341 | 166409259341 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-08-21 | 2021-11-30 | 2021-11-30 |  | 2022-01-18 | Underground | R16 |  | 595 |  |  |  | 630 | 2019 | 2022 | R16
167388217079 | 167835217079 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-14 | 2020-10-14 | 2021-01-14 |  | 2021-11-08 | Underground | R16 | 2021-05-20 | 1 | 67 | 91 | 123 | 279 | 2020 | 2021 | R16
166422202590 | 169952202590 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-09 | 2019-09-09 | 2020-09-03 |  | 2021-07-28 | Underground | R16 | 2021-01-15 | 1 | 259 | 97 | 139 | 493 | 2019 | 2021 | R16
161965142272 | 168658142272 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-23 | 2019-01-23 | 2019-02-06 | 2019-04-18 | 2019-05-20 | Underground | R16 | 2019-04-18 | 1 | 11 | 52 | 23 | 84 | 2019 | 2019 | R16
166427163131 | 168923163131 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-03 | 2019-09-03 | 2019-09-03 |  | 2021-04-16 | Underground | R16 | 2021-01-08 | 1 |  | 354 | 71 | 424 | 2019 | 2021 | R16
161156140782 | 168047140782 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-19 | 2019-01-19 | 2019-01-19 | 2019-04-09 | 2019-04-10 | Overhead | R16 | 2019-04-09 | 0 |  | 57 | 2 | 58 | 2019 | 2019 | R16
167614233283 | 161366233283 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-02 | 2021-06-02 | 2021-06-02 |  | 2021-11-09 | Overhead | R16 | 2021-10-06 | 1 |  | 91 | 25 | 115 | 2021 | 2021 | R16
166435202187 | 169375202187 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-05 | 2019-09-05 | 2020-08-28 |  | 2021-07-28 | Underground | R16 | 2021-01-15 | 1 | 257 | 101 | 139 | 495 | 2019 | 2021 | R16
166438205071 | 162355205071 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-23 | 2019-09-23 | 2020-09-25 |  | 2021-07-28 | Underground | R16 | 2021-01-15 | 1 | 265 | 81 | 139 | 483 | 2019 | 2021 | R16
166154208809 | 167419208809 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-12 | 2020-10-28 | 2020-10-28 |  | 2021-07-26 | Overhead | R16 | 2020-11-05 | 13 |  | 7 | 188 | 206 | 2020 | 2021 | R16
169287231062 | 165854231062 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-17 | 2021-05-17 | 2021-05-17 |  | 2021-08-23 | Overhead | R16 | 2021-07-14 | 1 |  | 43 | 29 | 71 | 2021 | 2021 | R16
166459174455 | 168264174455 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-13 | 2019-12-13 | 2019-12-13 |  | 2020-06-24 | Overhead | R16 | 2020-04-15 | 1 |  | 89 | 51 | 139 | 2019 | 2020 | R16
166485163130 | 168906163130 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-03 | 2019-09-03 | 2019-09-03 |  | 2021-04-16 | Underground | R16 | 2021-01-08 | 1 |  | 354 | 71 | 424 | 2019 | 2021 | R16
166559222978 | 168802222978 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-01-22 | 2021-01-29 | 2021-03-10 |  | 2022-09-29 | Overhead | R16 |  | 6 | 29 |  |  | 440 | 2021 | 2022 | R16
166497173322 | 163285173322 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-14 | 2019-12-02 | 2019-12-02 |  | 2023-06-08 | Overhead | R16 |  | 13 |  |  |  | 931 | 2019 | 2023 | R16
163863207295 | 163601207295 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-25 | 2020-10-04 | 2020-10-16 |  | 2021-04-13 | Overhead | R16 |  | 6 | 10 |  |  | 143 | 2020 | 2021 | R16
166541165494 | 162790165494 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-09-24 | 2019-09-24 | 2019-09-24 |  | 2019-11-14 | Overhead | R16 | 2019-11-06 | 1 |  | 32 | 7 | 38 | 2019 | 2019 | R16
160122230674 | 162872230674 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-05-04 | 2021-05-04 | 2021-05-14 |  | 2021-08-11 | Underground | R16 | 2021-06-28 | 1 | 9 | 32 | 33 | 72 | 2021 | 2021 | R16
166541168920 | 167941168920 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-10-19 | 2019-10-19 | 2019-10-19 |  | 2019-11-14 | Overhead | R16 | 2019-11-06 | 0 |  | 13 | 7 | 19 | 2019 | 2019 | R16
165420148610 | 162351148610 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-04-08 | 2019-04-08 | 2019-04-08 | 2019-05-09 | 2019-08-12 | Overhead | R16 | 2019-05-09 | 1 |  | 24 | 68 | 91 | 2019 | 2019 | R16
161728231372 | 166161231372 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2020-11-20 | 2021-04-29 | 2021-05-19 |  | 2021-11-03 | Overhead | R16 |  | 115 | 15 |  |  | 249 | 2020 | 2021 | R16
167663219083 | 160990219083 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2021-01-29 | 2021-01-29 | 2021-01-29 |  | 2021-11-05 | Overhead | R16 | 2021-04-07 | 1 |  | 49 | 153 | 201 | 2021 | 2021 | R16
166624193511 | 168120193511 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-10-21 | 2020-04-27 | 2020-06-09 |  | 2021-11-03 | Underground | R16 |  | 136 | 32 |  |  | 533 | 2019 | 2021 | R16
169657226786 | 168501226786 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-09-03 | 2020-09-03 | 2021-04-14 | 2021-07-26 | 2022-08-25 | Underground | R16 | 2021-07-26 | 1 | 160 | 74 | 284 | 516 | 2020 | 2022 | R16
166624184996 | 167071184996 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-03-19 | 2020-03-23 | 2020-03-23 |  | 2021-11-13 | Underground | R16 |  | 3 |  |  |  | 432 | 2020 | 2021 | R16
169754205684 | 164313205684 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-09-29 | 2020-09-29 | 2020-09-29 |  | 2021-08-05 | Underground | R16 | 2021-03-25 | 1 |  | 128 | 96 | 223 | 2020 | 2021 | R16
166377233245 | 161300233245 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-02 | 2021-06-02 | 2021-06-02 |  | 2021-10-25 | Overhead | R16 | 2021-09-16 | 1 |  | 77 | 28 | 104 | 2021 | 2021 | R16
160121226283 | 164916226283 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-03-31 | 2021-04-08 | 2021-04-08 |  | 2021-11-08 | Overhead | R16 | 2021-05-21 | 7 |  | 32 | 122 | 159 | 2021 | 2021 | R16
165720226282 | 160791226282 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-15 | 2021-03-31 | 2021-04-08 | 2021-06-23 | 2021-08-11 | Overhead | R16 | 2021-06-23 | 13 | 7 | 55 | 36 | 108 | 2021 | 2021 | R16
166706168623 | 167524168623 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-17 | 2019-10-17 | 2019-10-17 |  | 2020-10-06 | Overhead | R16 | 2020-06-30 | 1 |  | 184 | 71 | 254 | 2019 | 2020 | R16
166709164266 | 160776164266 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-13 | 2019-09-13 | 2019-09-13 |  | 2019-10-16 | Overhead | R16 | 2019-10-10 | 1 |  | 20 | 5 | 24 | 2019 | 2019 | R16
169342208049 | 168999208049 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-20 | 2020-10-22 | 2020-10-22 | 2020-12-16 | 2021-04-14 | Overhead | R16 | 2020-12-16 | 3 |  | 40 | 86 | 127 | 2020 | 2021 | R16
166713179537 | 161120179537 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-14 | 2019-09-14 | 2020-02-06 |  | 2020-06-09 | Underground | R16 | 2020-03-16 | 0 | 104 | 28 | 62 | 192 | 2019 | 2020 | R16
167060210309 | 164324210309 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-11 | 2020-11-11 | 2020-11-11 | 2021-01-03 | 2021-01-06 | Overhead | R16 | 2021-01-03 | 1 |  | 38 | 3 | 41 | 2020 | 2021 | R16
168294216015 | 164479216015 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-01-04 | 2021-01-04 | 2021-01-04 |  | 2021-11-04 | Overhead | R16 | 2021-06-02 | 1 |  | 108 | 112 | 219 | 2021 | 2021 | R16
166722228974 | 167004228974 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-10-15 | 2019-10-15 | 2021-05-01 |  | 2021-11-09 | Underground | R16 |  | 1 | 404 |  |  | 541 | 2019 | 2021 | R16
167092220399 | 164291220399 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-11 | 2020-11-11 | 2021-02-16 | 2021-04-20 | 2021-04-21 | Underground | R16 | 2021-04-20 | 1 | 70 | 46 | 2 | 116 | 2020 | 2021 | R16
168405228787 | 161289228787 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-28 | 2021-04-28 | 2021-04-28 | 2021-06-09 | 2021-08-16 | Underground | R16 | 2021-06-09 | 1 |  | 31 | 49 | 79 | 2021 | 2021 | R16
166736164125 | 160414164125 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-09-11 | 2019-09-11 | 2019-09-11 |  | 2020-01-02 | Overhead | R16 | 2019-12-11 | 1 |  | 66 | 17 | 82 | 2019 | 2020 | R16
166776163944 | 169078163944 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2019-09-04 | 2019-09-06 | 2019-09-09 |  | 2019-12-09 | Underground | R16 | 2019-12-02 | 3 | 2 | 61 | 6 | 69 | 2019 | 2019 | R16
166367216099 | 166835216099 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-24 | 2020-11-24 | 2021-01-05 | 2021-02-17 | 2021-05-06 | Underground | R16 | 2021-02-17 | 1 | 31 | 32 | 57 | 118 | 2020 | 2021 | R16
169403238009 | 163549238009 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-09-25 | 2020-10-12 | 2021-07-07 | 2021-11-18 | 2021-12-17 | Underground | R16 | 2021-11-18 | 12 | 193 | 97 | 22 | 321 | 2020 | 2021 | R16
166787179245 | 169127179245 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-12-18 | 2019-12-18 | 2020-02-03 |  | 2020-06-09 | Overhead | R16 | 2020-02-27 | 1 | 34 | 19 | 74 | 125 | 2019 | 2020 | R16
169858194087 | 161036194087 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-05-28 | 2019-10-05 | 2020-06-11 | 2021-04-06 | 2021-06-30 | Underground | R16 | 2021-04-06 | 94 | 179 | 214 | 62 | 547 | 2019 | 2021 | R16
166795168441 | 167138168441 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-24 | 2019-08-24 | 2019-10-16 |  | 2020-07-09 | Underground | R16 | 2020-06-09 | 0 | 38 | 170 | 23 | 229 | 2019 | 2020 | R16
167093145941 | 167686145941 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-12 | 2019-03-12 | 2019-03-12 | 2019-04-10 | 2019-05-28 | Overhead | R16 | 2019-04-10 | 1 |  | 22 | 35 | 56 | 2019 | 2019 | R16
166804165190 | 162035165190 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-20 | 2019-09-20 | 2019-09-20 |  | 2019-10-30 | Overhead | R16 | 2019-10-21 | 1 |  | 22 | 8 | 29 | 2019 | 2019 | R16
161619222873 | 165725222873 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-22 | 2021-03-09 | 2021-03-09 |  | 2021-08-23 | Underground | R16 | 2021-08-02 | 12 |  | 105 | 16 | 131 | 2021 | 2021 | R16
166869172129 | 161344172129 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-09-16 | 2019-09-17 | 2019-11-18 |  | 2020-06-09 | Underground | R16 |  | 2 | 45 |  |  | 192 | 2019 | 2020 | R16
163173225575 | 167749225575 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-03-02 | 2021-03-17 | 2021-04-05 |  | 2021-10-25 | Overhead | R16 | 2021-09-09 | 12 | 14 | 114 | 33 | 170 | 2021 | 2021 | R16
163164221842 | 169730221842 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-26 | 2021-02-26 | 2021-02-26 | 2021-03-23 | 2021-11-04 | Overhead | R16 | 2021-03-23 | 24 |  | 18 | 163 | 203 | 2021 | 2021 | R16
166091160944 | 166092160944 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Commercial | 2019-03-04 | 2019-03-04 | 2019-08-12 | 2020-09-02 | 2020-11-16 | Overhead | R16 | 2020-09-02 | 1 | 116 | 278 | 54 | 446 | 2019 | 2020 | R16
166991164885 | 169023164885 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-04 | 2019-09-10 | 2019-09-17 |  | 2019-11-21 | Underground | R16 | 2019-11-15 | 5 | 6 | 44 | 5 | 57 | 2019 | 2019 | R16
162994217565 | 168223217565 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-12-02 | 2021-01-11 | 2021-01-15 |  | 2021-10-26 | Underground | R16 | 2021-04-07 | 29 | 5 | 59 | 145 | 235 | 2020 | 2021 | R16
167009164915 | 161956164915 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-19 | 2019-09-19 | 2019-09-19 |  | 2019-11-15 | Overhead | R16 | 2019-11-08 | 1 |  | 37 | 6 | 42 | 2019 | 2019 | R16
167154142504 | 161389142504 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-02-05 | 2019-02-05 | 2019-02-05 | 2019-03-18 | 2019-03-29 | Overhead | R16 | 2019-03-18 | 1 |  | 30 | 10 | 39 | 2019 | 2019 | R16
167035164657 | 161277164657 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-16 | 2019-09-16 | 2019-09-17 |  | 2020-12-18 | Overhead | R16 | 2020-09-17 | 1 | 2 | 263 | 67 | 330 | 2019 | 2020 | R16
168358201145 | 160521201145 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-28 | 2020-07-28 | 2020-08-19 |  | 2021-07-06 | Underground | R16 | 2020-10-26 | 1 | 17 | 49 | 182 | 246 | 2020 | 2021 | R16
160577231512 | 168086231512 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-05-19 | 2021-05-20 | 2021-05-20 | 2021-09-22 | 2021-09-22 | Overhead | R16 | 2021-09-22 | 2 |  | 90 |  | 91 | 2021 | 2021 | R16
162834216587 | 167922216587 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-01 | 2020-12-11 | 2021-01-08 | 2021-02-01 | 2021-04-29 | Overhead | R16 | 2021-02-01 | 9 | 21 | 17 | 64 | 108 | 2020 | 2021 | R16
165369295882 | 167070295882 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-04-09 | 2021-04-09 | 2022-10-04 |  | 2023-03-23 | Overhead | R16 |  | 1 | 388 |  |  | 510 | 2021 | 2023 | R16
165333233470 | 169115233470 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2021-03-09 | 2021-04-07 | 2021-06-04 | 2021-07-02 | 2022-08-22 | Underground | R16 | 2021-07-02 | 22 | 43 | 21 | 297 | 380 | 2021 | 2022 | R16
167123171425 | 160543171425 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-09-11 | 2019-09-11 | 2019-11-11 |  | 2021-11-16 | Underground | R16 | 2019-11-12 | 1 | 44 | 2 | 526 | 570 | 2019 | 2021 | R16
166274202431 | 168071202431 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-01 | 2020-09-01 | 2020-09-01 |  | 2021-07-28 | Overhead | R16 | 2021-01-19 | 1 |  | 101 | 137 | 237 | 2020 | 2021 | R16
167299145334 | 167137145334 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-08 | 2019-03-08 | 2019-03-08 | 2019-03-19 | 2019-03-20 | Overhead | R16 | 2019-03-19 | 1 |  | 8 | 2 | 9 | 2019 | 2019 | R16
167356167205 | 168778167205 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-03 | 2019-09-03 | 2019-10-07 |  | 2020-06-09 | Underground | R16 | 2020-02-06 | 1 | 25 | 89 | 89 | 201 | 2019 | 2020 | R16
161586210365 | 164349210365 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-11 | 2020-11-11 | 2020-11-11 | 2020-11-19 | 2021-04-15 | Overhead | R16 | 2020-11-19 | 1 |  | 7 | 106 | 112 | 2020 | 2021 | R16
160230233206 | 161159233206 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-02 | 2021-06-02 | 2021-06-02 | 2021-06-25 | 2021-08-11 | Overhead | R16 | 2021-06-25 | 1 |  | 18 | 34 | 51 | 2021 | 2021 | R16
167381165875 | 163171165875 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-26 | 2019-09-26 | 2019-09-26 |  | 2021-11-10 | Overhead | R16 | 2020-01-15 | 1 |  | 80 | 476 | 555 | 2019 | 2021 | R16
167463258456 | 164298258456 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-11-11 | 2020-11-11 | 2021-11-23 | 2022-12-13 | 2023-06-07 | Underground | R16 | 2022-12-13 | 1 | 270 | 276 | 127 | 671 | 2020 | 2023 | R16
167433171957 | 163518171957 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-18 | 2019-11-18 | 2019-11-18 |  | 2020-06-09 | Overhead | R16 | 2019-12-26 | 1 |  | 29 | 119 | 147 | 2019 | 2020 | R16
164749226367 | 167730226367 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-03-02 | 2021-04-02 | 2021-04-09 | 2022-03-10 | 2022-03-15 | Underground | R16 | 2022-03-10 | 24 | 6 | 240 | 4 | 271 | 2021 | 2022 | R16
169301240159 | 164010240159 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-08 | 2021-05-08 | 2021-07-23 | 2021-10-27 | 2021-10-28 | Underground | R16 | 2021-10-27 | 0 | 55 | 69 | 2 | 124 | 2021 | 2021 | R16
167203314218 | 169323314218 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2020-07-21 | 2022-06-29 | 2023-03-30 | 2023-10-18 | 2023-11-21 | Underground | R16 | 2023-10-18 | 507 | 197 | 145 | 25 | 871 | 2020 | 2023 | R16
167436184229 | 160444184229 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2020-02-14 | 2020-02-14 | 2020-03-16 |  | 2020-06-16 | Underground | R16 |  | 1 | 22 |  |  | 88 | 2020 | 2020 | R16
167445163905 | 167475163905 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-26 | 2019-08-26 | 2019-09-09 |  | 2019-11-21 | Underground | R16 | 2019-11-13 | 1 | 11 | 48 | 7 | 64 | 2019 | 2019 | R16
167877229717 | 161538229717 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-30 | 2021-04-30 | 2021-05-06 |  | 2021-11-08 | Underground | R16 | 2021-07-21 | 1 | 5 | 55 | 79 | 137 | 2021 | 2021 | R16
168979153021 | 169856153021 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-05-20 | 2019-05-20 | 2019-05-20 | 2019-06-20 | 2019-06-21 | Underground | R16 | 2019-06-20 | 1 |  | 24 | 2 | 25 | 2019 | 2019 | R16
165793210952 | 165212210952 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-17 | 2020-11-17 | 2020-11-17 | 2021-02-08 | 2021-05-05 | Overhead | R16 | 2021-02-08 | 1 |  | 60 | 63 | 122 | 2020 | 2021 | R16
168040151355 | 167517151355 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-06 | 2019-05-06 | 2019-05-06 | 2019-05-21 | 2019-05-21 | Overhead | R16 | 2019-05-21 | 1 |  | 12 |  | 12 | 2019 | 2019 | R16
160557206127 | 162459206127 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-07 | 2020-08-07 | 2020-10-02 | 2020-11-13 | 2020-11-16 | Underground | R16 | 2020-11-13 | 1 | 41 | 31 | 2 | 72 | 2020 | 2020 | R16
161619211348 | 168560211348 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-03 | 2020-09-03 | 2020-11-19 | 2021-02-02 | 2021-04-23 | Overhead | R16 | 2021-02-02 | 1 | 56 | 54 | 59 | 167 | 2020 | 2021 | R16
167465166784 | 160937166784 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-13 | 2019-09-13 | 2019-10-03 |  | 2019-11-26 | Underground | R16 | 2019-11-18 | 1 | 15 | 33 | 7 | 53 | 2019 | 2019 | R16
165324208718 | 160959208718 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-28 | 2020-10-28 | 2020-10-28 | 2020-10-30 | 2021-04-14 | Overhead | R16 | 2020-10-30 | 1 |  | 3 | 119 | 121 | 2020 | 2021 | R16
166897217072 | 166724217072 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-13 | 2021-01-13 | 2021-01-13 | 2021-03-11 | 2021-08-16 | Overhead | R16 | 2021-03-11 | 1 |  | 42 | 113 | 154 | 2021 | 2021 | R16
167492165646 | 168742165646 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-09-03 | 2019-09-03 | 2019-09-24 |  | 2021-11-13 | Underground | R16 |  | 1 | 16 |  |  | 574 | 2019 | 2021 | R16
166075265544 | 166719265544 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-27 | 2020-08-27 | 2022-01-20 |  | 2022-03-07 | Underground | R16 | 2022-02-08 | 1 | 366 | 14 | 20 | 398 | 2020 | 2022 | R16
167528165749 | 162933165749 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-25 | 2019-09-25 | 2019-09-25 |  | 2019-11-15 | Overhead | R16 | 2019-11-08 | 1 |  | 33 | 6 | 38 | 2019 | 2019 | R16
161450198245 | 168858198245 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-20 | 2020-07-20 | 2020-07-24 | 2020-09-10 | 2021-01-08 | Underground | R16 | 2020-09-10 | 1 | 5 | 35 | 87 | 125 | 2020 | 2021 | R16
163141206887 | 167300206887 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-10-12 | 2020-10-12 | 2020-10-12 | 2021-04-22 | 2021-04-23 | Underground | R16 | 2021-04-22 | 1 |  | 139 | 2 | 140 | 2020 | 2021 | R16
163231224999 | 163173224999 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-24 | 2021-03-24 | 2021-03-29 | 2021-04-13 | 2021-04-16 | Overhead | R16 | 2021-04-13 | 1 | 4 | 12 | 4 | 18 | 2021 | 2021 | R16
168681218117 | 168992218117 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-22 | 2021-01-22 | 2021-01-22 | 2021-02-19 | 2021-11-08 | Overhead | R16 | 2021-02-19 | 1 |  | 21 | 187 | 207 | 2021 | 2021 | R16
168066227967 | 168507227967 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-04-16 | 2021-04-16 | 2021-04-22 |  | 2022-10-24 | Underground | R16 |  | 1 | 5 |  |  | 397 | 2021 | 2022 | R16
167687167469 | 161581167469 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-17 | 2019-09-17 | 2019-10-09 |  | 2019-11-26 | Underground | R16 | 2019-10-23 | 1 | 17 | 11 | 25 | 51 | 2019 | 2019 | R16
167706201153 | 160069201153 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-09 | 2019-09-09 | 2020-08-19 |  | 2021-04-21 | Underground | R16 | 2021-01-19 | 1 | 248 | 110 | 67 | 423 | 2019 | 2021 | R16
167707164611 | 161327164611 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-16 | 2019-09-16 | 2019-09-16 |  | 2019-11-21 | Overhead | R16 | 2019-11-15 | 1 |  | 45 | 5 | 49 | 2019 | 2019 | R16
167708166832 | 164670166832 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-03 | 2019-10-03 | 2019-10-03 |  | 2019-11-13 | Overhead | R16 | 2019-11-05 | 1 |  | 24 | 7 | 30 | 2019 | 2019 | R16
167717169911 | 168057169911 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-21 | 2019-10-28 | 2019-10-28 |  | 2019-12-09 | Overhead | R16 | 2019-12-02 | 6 |  | 26 | 6 | 36 | 2019 | 2019 | R16
160645200313 | 163321200313 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-12 | 2020-08-12 | 2020-08-12 |  | 2020-12-29 | Underground | R16 | 2020-09-29 | 1 |  | 35 | 66 | 100 | 2020 | 2020 | R16
161612150700 | 165832150700 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-27 | 2019-04-27 | 2019-04-29 | 2019-05-18 | 2019-05-21 | Overhead | R16 | 2019-05-18 | 0 | 1 | 15 | 2 | 17 | 2019 | 2019 | R16
162496216079 | 165960216079 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2020-11-19 | 2020-11-19 | 2021-01-05 |  | 2021-11-05 | Overhead | R16 |  | 1 | 34 |  |  | 252 | 2020 | 2021 | R16
165129221281 | 168008221281 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-19 | 2021-01-22 | 2021-02-22 | 2021-04-28 | 2021-05-03 | Underground | R16 | 2021-04-28 | 4 | 22 | 48 | 4 | 75 | 2021 | 2021 | R16
167774164045 | 160470164045 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-11 | 2019-09-11 | 2019-09-11 |  | 2019-11-14 | Overhead | R16 | 2019-11-07 | 1 |  | 42 | 6 | 47 | 2019 | 2019 | R16
164004211397 | 166227211397 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-20 | 2020-11-20 | 2020-11-20 |  | 2021-04-20 | Overhead | R16 | 2021-01-11 | 1 |  | 37 | 72 | 108 | 2020 | 2021 | R16
167837169423 | 168357169423 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-30 | 2019-08-30 | 2019-10-24 |  | 2022-08-24 | Underground | R16 | 2022-08-19 | 1 | 40 | 737 | 4 | 779 | 2019 | 2022 | R16
167867165783 | 162883165783 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-25 | 2019-09-25 | 2019-09-25 |  | 2021-10-14 | Overhead | R16 | 2020-01-08 | 1 |  | 76 | 462 | 537 | 2019 | 2021 | R16
167543224519 | 160988224519 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-03-16 | 2021-03-23 | 2021-03-23 |  | 2021-10-27 | Underground | R16 | 2021-06-21 | 6 |  | 65 | 93 | 162 | 2021 | 2021 | R16
165911221210 | 165602221210 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-04-01 | 2021-10-14 | Underground | R16 | 2021-04-01 | 1 |  | 29 | 141 | 169 | 2021 | 2021 | R16
162972144789 | 166235144789 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE FOR UPGRADE UD | Commercial | 2019-03-05 | 2019-03-05 | 2019-03-05 | 2019-03-07 | 2019-05-21 | Underground | R16 | 2019-03-07 | 1 |  | 3 | 54 | 56 | 2019 | 2019 | R16
167913165885 | 168671165885 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-30 | 2019-08-30 | 2019-09-26 |  | 2020-06-09 | Underground | R16 | 2020-03-09 | 1 | 20 | 118 | 67 | 203 | 2019 | 2020 | R16
167916164816 | 161490164816 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-17 | 2019-09-17 | 2019-09-17 |  | 2020-06-09 | Overhead | R16 | 2020-01-30 | 1 |  | 98 | 94 | 191 | 2019 | 2020 | R16
169307213488 | 166309213488 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-25 | 2020-08-25 | 2020-12-10 | 2020-12-15 | 2021-04-14 | Overhead | R16 | 2020-12-15 | 1 | 78 | 4 | 87 | 167 | 2020 | 2021 | R16
167254209205 | 164551209205 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-09-29 | 2020-09-29 | 2020-10-30 | 2020-12-30 | 2021-03-13 | Underground | R16 | 2020-12-30 | 1 | 24 | 44 | 53 | 119 | 2020 | 2021 | R16
165568231061 | 167428231061 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2021-04-13 | 2021-04-13 | 2021-05-17 |  | 2023-08-23 | Underground | R16 |  | 1 | 25 |  |  | 617 | 2021 | 2023 | R16
167953174049 | 163120174049 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-09-25 | 2019-09-25 | 2019-12-10 |  | 2020-06-09 | Underground | R16 | 2020-04-01 | 1 | 55 | 82 | 50 | 185 | 2019 | 2020 | R16
167959164254 | 160890164254 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-12 | 2019-09-12 | 2019-09-12 |  | 2019-10-30 | Overhead | R16 | 2019-10-24 | 1 |  | 31 | 5 | 35 | 2019 | 2019 | R16
167966167154 | 161051167154 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-13 | 2019-09-13 | 2019-10-08 |  | 2022-07-29 | Underground | R16 |  | 1 | 18 |  |  | 751 | 2019 | 2022 | R16
167980164815 | 161412164815 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-17 | 2019-09-17 | 2019-09-17 |  | 2020-06-09 | Overhead | R16 | 2019-12-19 | 1 |  | 68 | 124 | 191 | 2019 | 2020 | R16
168930240223 | 164969240223 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-13 | 2021-07-22 | 2021-07-22 |  | 2021-11-18 | Overhead | R16 | 2021-10-25 | 51 |  | 68 | 19 | 136 | 2021 | 2021 | R16
162948213944 | 160557213944 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-14 | 2020-12-14 | 2020-12-14 |  | 2022-10-18 | Overhead | R16 |  | 1 |  |  |  | 482 | 2020 | 2022 | R16
167989167209 | 168710167209 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-30 | 2019-08-30 | 2019-10-07 |  | 2020-07-09 | Underground | R16 | 2020-06-01 | 1 | 27 | 171 | 29 | 225 | 2019 | 2020 | R16
168002163860 | 169940163860 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-09 | 2019-09-09 | 2019-09-09 |  | 2019-10-16 | Underground | R16 | 2019-10-08 | 1 |  | 22 | 7 | 28 | 2019 | 2019 | R16
167467212128 | 169006212128 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-20 | 2020-11-25 | 2020-11-25 | 2021-04-27 | 2021-05-03 | Underground | R16 | 2021-04-27 | 27 |  | 110 | 5 | 140 | 2020 | 2021 | R16
163832209135 | 161636209135 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-30 | 2020-10-30 | 2020-10-30 | 2021-01-13 | 2021-01-14 | Overhead | R16 | 2021-01-13 | 1 |  | 54 | 2 | 55 | 2020 | 2021 | R16
168043167161 | 168283167161 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-29 | 2019-08-29 | 2019-10-07 |  | 2020-10-06 | Underground | R16 | 2020-08-17 | 1 | 28 | 226 | 37 | 289 | 2019 | 2020 | R16
168588203348 | 169712203348 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-09 | 2020-09-09 | 2020-09-09 | 2021-03-23 | 2021-11-04 | Overhead | R16 | 2021-03-23 | 1 |  | 140 | 163 | 302 | 2020 | 2021 | R16
168069191354 | 168321191354 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-08-29 | 2019-08-29 | 2020-05-20 |  | 2020-07-13 | Underground | R16 |  | 1 | 190 |  |  | 228 | 2019 | 2020 | R16
168084166182 | 160057166182 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-09 | 2019-09-09 | 2019-09-28 |  | 2021-07-26 | Underground | R16 | 2020-11-13 | 1 | 15 | 295 | 182 | 491 | 2019 | 2021 | R16
165401208127 | 169313208127 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-21 | 2020-10-21 | 2020-10-23 | 2020-12-10 | 2020-12-11 | Overhead | R16 | 2020-12-10 | 1 | 3 | 35 | 2 | 38 | 2020 | 2020 | R16
164216198356 | 160104198356 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-25 | 2020-07-25 | 2020-07-25 | 2020-08-17 | 2020-12-15 | Overhead | R16 | 2020-08-17 | 0 |  | 16 | 87 | 102 | 2020 | 2020 | R16
163609220463 | 163797220463 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-11 | 2021-02-12 | 2021-02-12 | 2022-11-21 | 2022-07-27 | Overhead | R16 | 2022-11-21 | 2 |  | 462 |  | 380 | 2021 | 2022 | R16
168112194594 | 164218194594 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-03-04 | 2020-03-04 | 2020-06-18 |  | 2021-08-31 | Underground | R16 | 2021-06-11 | 1 | 77 | 257 | 58 | 390 | 2020 | 2021 | R16
168124171848 | 163008171848 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-14 | 2019-11-14 | 2019-11-14 |  | 2020-06-09 | Overhead | R16 | 2020-01-06 | 1 |  | 38 | 112 | 149 | 2019 | 2020 | R16
169419148005 | 168279148005 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-03-14 | 2019-03-14 | 2019-04-02 |  | 2019-09-06 | Underground | R16 |  | 1 | 14 |  |  | 127 | 2019 | 2019 | R16
168528213493 | 166898213493 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-24 | 2020-11-30 | 2020-12-10 |  | 2021-12-02 | Underground | R16 | 2021-11-08 | 5 | 9 | 238 | 19 | 268 | 2020 | 2021 | R16
165127205766 | 160439205766 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-09-14 | 2020-09-14 | 2020-09-29 |  | 2021-07-24 | Underground | R16 | 2020-11-09 | 1 | 12 | 30 | 185 | 225 | 2020 | 2021 | R16
162423230250 | 164480230250 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-11 | 2021-05-11 | 2021-05-11 |  | 2021-08-26 | Overhead | R16 | 2021-06-07 | 1 |  | 20 | 59 | 78 | 2021 | 2021 | R16
169661230860 | 165426230860 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-03 | 2021-04-03 | 2021-05-14 | 2021-05-25 | 2021-10-14 | Underground | R16 | 2021-05-25 | 0 | 30 | 8 | 103 | 139 | 2021 | 2021 | R16
165216233122 | 160911233122 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-01 | 2021-06-01 | 2021-06-01 | 2021-11-15 | 2021-11-16 | Overhead | R16 | 2021-11-15 | 1 |  | 120 | 2 | 121 | 2021 | 2021 | R16
163711208395 | 169710208395 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2020-10-22 | 2020-10-23 | 2020-10-26 | 2021-07-10 | 2021-08-04 | Overhead | R16 | 2021-07-10 | 2 | 2 | 185 | 18 | 205 | 2020 | 2021 | R16
168155170870 | 169320170870 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2019-10-25 | 2019-10-25 | 2019-11-06 |  | 2020-08-28 | Underground | R16 | 2020-07-06 | 1 | 9 | 174 | 40 | 221 | 2019 | 2020 | R16
161772224310 | 162262224310 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2021-03-21 | 2021-03-21 | 2021-03-21 |  | 2021-08-11 | Overhead | R16 | 2021-07-09 | 0 |  | 80 | 24 | 103 | 2021 | 2021 | R16
160593229231 | 161399229231 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-04-29 | 2021-05-03 | 2021-05-03 | 2021-05-15 | 2021-09-23 | Overhead | R16 | 2021-05-15 | 3 |  | 10 | 94 | 106 | 2021 | 2021 | R16
164721200300 | 160183200300 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-27 | 2020-07-27 | 2020-08-11 |  | 2021-07-24 | Underground | R16 | 2020-11-04 | 1 | 12 | 62 | 188 | 260 | 2020 | 2021 | R16
168214165781 | 162853165781 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-25 | 2019-09-25 | 2019-09-25 |  | 2019-11-08 | Overhead | R16 | 2019-10-29 | 1 |  | 25 | 9 | 33 | 2019 | 2019 | R16
166368203950 | 161572203950 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-08-01 | 2020-08-01 | 2020-09-16 |  | 2021-04-21 | Overhead | R16 | 2021-01-27 | 0 | 33 | 96 | 61 | 188 | 2020 | 2021 | R16
168216209663 | 168984209663 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-09-03 | 2020-10-16 | 2020-11-04 |  | 2021-10-25 | Underground | R16 | 2021-10-25 | 294 | 14 | 254 |  | 560 | 2019 | 2021 | R16
167898225760 | 161579225760 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-02-02 | 2021-04-01 | 2021-04-02 | 2022-07-21 | 2022-07-26 | Underground | R16 | 2022-07-21 | 43 | 2 | 340 | 4 | 386 | 2021 | 2022 | R16
168276166211 | 163792166211 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-30 | 2019-09-30 | 2019-09-30 |  | 2019-12-12 | Overhead | R16 | 2019-12-03 | 1 |  | 47 | 8 | 54 | 2019 | 2019 | R16
162954284429 | 160545284429 | SPECIFIC BUDGET PROJECTS | UG R16 RESD AND NON RESD UD | Commercial | 2021-01-28 | 2021-04-19 | 2022-07-01 |  | 2023-01-27 | Underground | R16 |  | 58 | 315 |  |  | 522 | 2021 | 2023 | R16
165635226702 | 169086226702 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-09 | 2021-04-13 | 2021-04-13 | 2021-05-27 | 2021-11-02 | Overhead | R16 | 2021-05-27 | 26 |  | 33 | 114 | 171 | 2021 | 2021 | R16
166769222794 | 162815222794 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-02-08 | 2021-02-25 | 2021-03-08 |  | 2023-06-02 | Underground | R16 | 2022-05-20 | 14 | 8 | 315 | 271 | 605 | 2021 | 2023 | R16
162947154718 | 162840154718 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-06-07 | 2019-06-07 | 2019-06-07 | 2019-11-15 | 2019-11-25 | Underground | R16 | 2019-11-15 | 1 |  | 116 | 7 | 122 | 2019 | 2019 | R16
167254209206 | 164398209206 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Commercial | 2020-09-29 | 2020-09-29 | 2020-10-30 | 2020-12-28 | 2022-12-13 | Overhead | R16 | 2020-12-28 | 1 | 24 | 42 | 512 | 576 | 2020 | 2022 | R16
162066209803 | 163001209803 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-05 | 2020-11-05 | 2020-11-05 | 2020-11-10 | 2021-04-14 | Overhead | R16 | 2020-11-10 | 1 |  | 4 | 112 | 115 | 2020 | 2021 | R16
165667151156 | 166244151156 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-30 | 2019-05-03 | 2019-05-03 | 2019-08-06 | 2019-08-07 | Underground | R16 | 2019-08-06 | 4 |  | 68 | 2 | 72 | 2019 | 2019 | R16
168345165665 | 162306165665 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-23 | 2019-09-24 | 2019-09-24 |  | 2021-04-23 | Underground | R16 | 2021-02-05 | 2 |  | 359 | 56 | 415 | 2019 | 2021 | R16
168351184544 | 166627184544 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2020-03-17 | 2020-03-17 | 2020-03-18 |  | 2021-05-07 | Underground | R16 |  | 1 | 2 |  |  | 299 | 2020 | 2021 | R16
169973217752 | 168256217752 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-01-20 | 2021-01-20 | 2021-01-20 | 2022-09-28 | 2023-01-05 | Overhead | R16 | 2022-09-28 | 1 |  | 441 | 72 | 512 | 2021 | 2023 | R16
168389182910 | 160457182910 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-11 | 2019-09-11 | 2020-03-04 |  | 2020-07-10 | Underground | R16 | 2020-06-01 | 1 | 126 | 64 | 30 | 218 | 2019 | 2020 | R16
168441171987 | 162621171987 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-11-12 | 2019-11-12 | 2019-11-15 |  | 2021-11-10 | Underground | R16 | 2020-01-28 | 1 | 4 | 53 | 467 | 522 | 2019 | 2021 | R16
161704201349 | 162895201349 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-08-10 | 2020-08-10 | 2020-08-21 | 2021-03-16 | 2021-06-09 | Underground | R16 | 2021-03-16 | 1 | 10 | 148 | 62 | 218 | 2020 | 2021 | R16
168528170629 | 163287170629 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-26 | 2019-09-26 | 2019-11-04 |  | 2020-01-06 | Underground | R16 | 2019-12-13 | 1 | 28 | 30 | 17 | 73 | 2019 | 2020 | R16
160547226262 | 166685226262 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-08 | 2021-04-08 | 2021-04-08 |  | 2021-11-08 | Overhead | R16 | 2021-05-26 | 1 |  | 35 | 119 | 153 | 2021 | 2021 | R16
168556190008 | 168661190008 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-30 | 2019-08-30 | 2020-05-04 |  | 2020-08-14 | Underground | R16 | 2020-06-23 | 1 | 177 | 37 | 39 | 251 | 2019 | 2020 | R16
163757149163 | 161774149163 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-04 | 2019-04-14 | 2019-04-14 | 2019-05-23 | 2019-08-12 | Overhead | R16 | 2019-05-23 | 7 |  | 29 | 58 | 93 | 2019 | 2019 | R16
169745151597 | 164758151597 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-22 | 2019-04-22 | 2019-05-07 | 2019-06-11 | 2019-06-13 | Underground | R16 | 2019-06-11 | 1 | 12 | 26 | 3 | 39 | 2019 | 2019 | R16
160218144642 | 165643144642 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-28 | 2019-03-01 | 2019-03-01 | 2019-03-04 | 2019-03-04 | Overhead | R16 | 2019-03-04 | 2 |  | 2 |  | 3 | 2019 | 2019 | R16
168574165528 | 162459165528 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-23 | 2019-09-23 | 2019-09-23 |  | 2019-12-03 | Overhead | R16 | 2019-11-13 | 1 |  | 38 | 15 | 52 | 2019 | 2019 | R16
160316226025 | 166122226025 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-06 | 2021-04-07 | 2021-04-07 | 2021-05-17 | 2021-08-11 | Overhead | R16 | 2021-05-17 | 2 |  | 29 | 63 | 92 | 2021 | 2021 | R16
166899214010 | 160750214010 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-14 | 2020-12-14 | 2020-12-14 | 2021-01-21 | 2021-10-25 | Overhead | R16 | 2021-01-21 | 1 |  | 29 | 198 | 226 | 2020 | 2021 | R16
164352221864 | 164293221864 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-31 | 2020-12-31 | 2021-02-26 | 2021-05-24 | 2021-05-25 | Underground | R16 | 2021-05-24 | 1 | 42 | 62 | 2 | 104 | 2020 | 2021 | R16
168597164111 | 160436164111 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-11 | 2019-09-11 | 2019-09-11 |  | 2019-11-14 | Overhead | R16 | 2019-11-06 | 1 |  | 41 | 7 | 47 | 2019 | 2019 | R16
168598167964 | 166685167964 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-12 | 2019-10-12 | 2019-10-12 |  | 2020-06-09 | Overhead | R16 | 2020-01-28 | 0 |  | 77 | 96 | 172 | 2019 | 2020 | R16
168611169195 | 168810169195 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-23 | 2019-10-23 | 2019-10-23 |  | 2022-05-05 | Overhead | R16 | 2022-04-13 | 1 |  | 646 | 17 | 662 | 2019 | 2022 | R16
165155224692 | 163139224692 | STREET AND HIGHWAY RELOCATION | OH REWIRE NON CUST GEN OS | Residential | 2021-03-25 | 2021-03-25 | 2021-03-25 | 2021-04-30 | 2021-10-25 | Overhead | R16 | 2021-04-30 | 1 |  | 27 | 127 | 153 | 2021 | 2021 | R16
160701241672 | 162913241672 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-23 | 2021-03-30 | 2021-08-02 |  | 2021-09-13 | Underground | R16 |  | 6 | 90 |  |  | 125 | 2021 | 2021 | R16
168652173916 | 163115173916 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-25 | 2019-09-25 | 2019-12-11 |  | 2020-06-09 | Underground | R16 | 2020-01-23 | 1 | 56 | 32 | 99 | 185 | 2019 | 2020 | R16
164182145014 | 164049145014 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-02-19 | 2019-02-19 | 2019-03-06 | 2019-06-06 | 2019-06-14 | Overhead | R16 | 2019-06-06 | 1 | 12 | 67 | 7 | 84 | 2019 | 2019 | R16
160462215444 | 161301215444 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-29 | 2020-10-30 | 2020-12-22 | 2021-07-15 | 2022-02-02 | Overhead | R16 | 2021-07-15 | 2 | 38 | 148 | 145 | 330 | 2020 | 2022 | R16
161652221492 | 160012221492 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-26 | 2021-02-24 | 2021-02-24 | 2021-06-24 | 2021-08-11 | Overhead | R16 | 2021-06-24 | 22 |  | 87 | 35 | 142 | 2021 | 2021 | R16
169992210874 | 160885210874 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-09-15 | 2020-09-15 | 2020-11-18 |  | 2022-08-10 | Underground | R16 |  | 1 | 47 |  |  | 497 | 2020 | 2022 | R16
161726152614 | 169605152614 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-05-17 | 2019-05-17 | 2019-05-17 | 2022-01-06 | 2022-01-07 | Underground | R16 | 2022-01-06 | 1 |  | 690 | 2 | 691 | 2019 | 2022 | R16
161162154496 | 162505154496 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-06 | 2019-06-06 | 2019-06-06 | 2019-06-20 | 2022-07-15 | Overhead | R16 | 2019-06-20 | 1 |  | 11 | 802 | 812 | 2019 | 2022 | R16
165129203705 | 166805203705 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-26 | 2020-08-26 | 2020-09-14 |  | 2021-07-26 | Underground | R16 | 2020-10-23 | 1 | 14 | 30 | 197 | 239 | 2020 | 2021 | R16
165007152603 | 169384152603 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-16 | 2019-05-16 | 2019-05-16 | 2019-05-17 | 2019-08-12 | Underground | R16 | 2019-05-17 | 1 |  | 2 | 62 | 63 | 2019 | 2019 | R16
165193205718 | 163307205718 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-24 | 2020-09-25 | 2020-10-01 | 2020-11-03 | 2021-07-26 | Overhead | R16 | 2020-11-03 | 2 | 5 | 24 | 190 | 218 | 2020 | 2021 | R16
168959165207 | 168980165207 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-09-03 | 2019-09-03 | 2019-09-20 |  | 2020-01-03 | Overhead | R16 |  | 1 | 14 |  |  | 89 | 2019 | 2020 | R16
166865202434 | 168107202434 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-01 | 2020-09-01 | 2020-09-01 |  | 2021-02-17 | Overhead | R16 | 2020-10-19 | 1 |  | 35 | 88 | 122 | 2020 | 2021 | R16
165800232615 | 169305232615 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-10-21 | 2021-03-25 | 2021-05-27 | 2021-10-13 | 2021-10-21 | Underground | R16 | 2021-10-13 | 112 | 46 | 100 | 7 | 262 | 2020 | 2021 | R16
164778150393 | 165587150393 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-26 | 2019-04-26 | 2019-04-26 | 2019-06-14 | 2019-06-17 | Underground | R16 | 2019-06-14 | 1 |  | 36 | 2 | 37 | 2019 | 2019 | R16
169041168496 | 162290168496 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-21 | 2019-09-21 | 2019-10-18 |  | 2020-06-09 | Underground | R16 | 2020-03-31 | 0 | 20 | 118 | 51 | 187 | 2019 | 2020 | R16
169102165415 | 162559165415 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-24 | 2019-09-24 | 2019-09-24 |  | 2019-12-06 | Overhead | R16 | 2019-11-13 | 1 |  | 37 | 18 | 54 | 2019 | 2019 | R16
168750202148 | 166982202148 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-27 | 2020-08-27 | 2020-08-27 |  | 2021-07-26 | Overhead | R16 | 2020-11-13 | 1 |  | 57 | 182 | 238 | 2020 | 2021 | R16
166885219041 | 161025219041 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-29 | 2021-01-29 | 2021-01-29 |  | 2022-06-01 | Overhead | R16 | 2021-04-05 | 1 |  | 47 | 303 | 349 | 2021 | 2022 | R16
169134166537 | 160038166537 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-09 | 2019-09-09 | 2019-10-03 |  | 2020-10-06 | Underground | R16 | 2020-07-15 | 1 | 19 | 205 | 60 | 282 | 2019 | 2020 | R16
169140165897 | 161528165897 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-18 | 2019-09-26 | 2019-09-26 |  | 2019-10-30 | Overhead | R16 | 2019-10-21 | 7 |  | 18 | 8 | 31 | 2019 | 2019 | R16
162108143749 | 162380143749 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-08 | 2019-02-08 | 2019-02-20 | 2019-04-17 | 2019-04-17 | Underground | R16 | 2019-04-17 | 1 | 9 | 41 |  | 49 | 2019 | 2019 | R16
165235210926 | 161932210926 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-11-02 | 2020-11-02 | 2020-11-17 |  | 2021-07-12 | Overhead | R16 |  | 1 | 12 |  |  | 181 | 2020 | 2021 | R16
167302221209 | 166543221209 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-13 | 2021-01-13 | 2021-02-22 |  | 2021-10-25 | Underground | R16 | 2021-09-02 | 1 | 29 | 139 | 38 | 204 | 2021 | 2021 | R16
169169163198 | 169192163198 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential Subdivision | 2019-09-04 | 2019-09-04 | 2019-09-05 |  | 2022-08-29 | Underground | R16 |  | 1 | 2 |  |  | 779 | 2019 | 2022 | R16
169169276747 | 163654276747 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential Subdivision | 2022-04-22 | 2022-04-22 | 2022-04-22 |  | 2022-06-09 | Overhead | R16 |  | 1 |  |  |  | 35 | 2022 | 2022 | R16
169179163437 | 169381163437 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential Subdivision | 2019-09-05 | 2019-09-05 | 2019-09-06 |  | 2022-07-27 | Underground | R16 |  | 1 | 2 |  |  | 755 | 2019 | 2022 | R16
165129224196 | 161675224196 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-03-18 | 2021-03-18 | 2021-03-22 | 2021-10-17 | 2021-10-20 | Underground | R16 | 2021-10-17 | 1 | 3 | 150 | 3 | 155 | 2021 | 2021 | R16
162635213611 | 160047213611 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-11 | 2020-12-11 | 2020-12-11 |  | 2021-08-09 | Overhead | R16 | 2021-03-22 | 1 |  | 72 | 101 | 172 | 2020 | 2021 | R16
160308248936 | 161828248936 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2021-04-30 | 2021-08-02 | 2021-09-22 | 2023-02-06 | 2023-02-08 | Underground | R16 | 2023-02-06 | 67 | 38 | 359 | 3 | 464 | 2021 | 2023 | R16
166956153260 | 160533153260 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-22 | 2019-05-22 | 2019-05-22 | 2020-03-31 | 2020-04-02 | Overhead | R16 | 2020-03-31 | 1 |  | 225 | 3 | 227 | 2019 | 2020 | R16
161183225163 | 164396225163 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-03-30 | 2021-03-30 | 2021-03-30 | 2021-04-05 | 2021-04-08 | Underground | R16 | 2021-04-05 | 1 |  | 5 | 4 | 8 | 2021 | 2021 | R16
164310141018 | 168467141018 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-23 | 2019-01-23 | 2019-01-23 |  | 2019-02-28 | Underground | R16 |  | 1 |  |  |  | 27 | 2019 | 2019 | R16
169792214232 | 166518214232 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-23 | 2020-11-23 | 2020-12-17 |  | 2021-04-21 | Underground | R16 | 2021-01-25 | 1 | 19 | 28 | 63 | 108 | 2020 | 2021 | R16
166739204967 | 163162204967 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-24 | 2020-09-24 | 2020-09-25 | 2020-11-04 | 2021-01-28 | Overhead | R16 | 2020-11-04 | 1 | 2 | 29 | 62 | 91 | 2020 | 2021 | R16
169331169723 | 169139169723 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-25 | 2019-10-25 | 2019-10-25 |  | 2021-11-13 | Overhead | R16 | 2020-02-20 | 1 |  | 85 | 452 | 536 | 2019 | 2021 | R16
169333166210 | 161965166210 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2019-09-19 | 2019-09-19 | 2019-09-30 |  | 2020-01-08 | Underground | R16 | 2019-12-10 | 1 | 8 | 52 | 22 | 80 | 2019 | 2020 | R16
163853203541 | 169925203541 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2020-09-10 | 2020-09-10 | 2020-09-10 |  | 2020-12-18 | Overhead | R16 | 2020-09-25 | 1 |  | 12 | 61 | 72 | 2020 | 2020 | R16
166250236486 | 163531236486 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Commercial | 2020-11-07 | 2020-11-07 | 2021-06-24 | 2022-01-04 | 2022-01-24 | Underground | R16 | 2022-01-04 | 0 | 164 | 139 | 15 | 316 | 2020 | 2022 | R16
161220220814 | 169907220814 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-26 | 2021-02-18 | 2021-02-18 | 2021-03-08 | 2021-06-03 | Overhead | R16 | 2021-03-08 | 18 |  | 13 | 64 | 93 | 2021 | 2021 | R16
164180214084 | 160291214084 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-11 | 2020-12-15 | 2020-12-15 |  | 2021-04-21 | Underground | R16 | 2021-01-21 | 3 |  | 28 | 65 | 94 | 2020 | 2021 | R16
169345169422 | 161578169422 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-18 | 2019-10-24 | 2019-10-24 |  | 2020-01-08 | Overhead | R16 | 2020-01-02 | 27 |  | 51 | 5 | 81 | 2019 | 2020 | R16
164853223473 | 160413223473 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-13 | 2021-03-13 | 2021-03-13 | 2021-11-21 | 2021-12-02 | Underground | R16 | 2021-11-21 | 0 |  | 180 | 9 | 189 | 2021 | 2021 | R16
168680217749 | 168243217749 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-01-20 | 2021-01-20 | 2021-01-20 | 2021-03-23 | 2021-08-06 | Overhead | R16 | 2021-03-23 | 1 |  | 45 | 99 | 143 | 2021 | 2021 | R16
163397252145 | 165745252145 | NON-RESIDENTIAL - LARGE OFFICE | UG R16 RESD AND NON RESD UD | Commercial | 2021-02-22 | 2021-07-07 | 2021-10-14 | 2022-09-21 | 2022-10-24 | Underground | R16 | 2022-09-21 | 98 | 72 | 245 | 24 | 436 | 2021 | 2022 | R16
169426165150 | 162026165150 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-09-19 | 2019-09-19 | 2019-09-19 |  | 2021-11-13 | Overhead | R16 | 2019-12-13 | 1 |  | 62 | 501 | 562 | 2019 | 2021 | R16
162299221338 | 166240221338 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-02-24 | 2021-02-24 | 2021-02-24 |  | 2021-11-13 | Overhead | R16 | 2021-04-30 | 1 |  | 48 | 141 | 188 | 2021 | 2021 | R16
169427172973 | 165133172973 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-26 | 2019-11-26 | 2019-11-26 |  | 2020-06-09 | Overhead | R16 | 2020-01-22 | 1 |  | 42 | 100 | 141 | 2019 | 2020 | R16
163995215951 | 164438215951 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-04 | 2021-01-04 | 2021-01-04 | 2021-01-07 | 2021-08-11 | Overhead | R16 | 2021-01-07 | 1 |  | 4 | 155 | 158 | 2021 | 2021 | R16
161309224034 | 161669224034 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-03-18 | 2021-03-18 | 2021-03-18 |  | 2021-08-10 | Overhead | R16 | 2021-03-22 | 1 |  | 3 | 102 | 104 | 2021 | 2021 | R16
166987219566 | 165477219566 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-07 | 2021-01-25 | 2021-02-03 | 2021-05-19 | 2021-06-07 | Underground | R16 | 2021-05-19 | 13 | 8 | 76 | 14 | 108 | 2021 | 2021 | R16
164061222778 | 169613222778 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-09 | 2021-03-09 | 2021-03-09 | 2021-04-29 | 2021-10-25 | Overhead | R16 | 2021-04-29 | 1 |  | 38 | 128 | 165 | 2021 | 2021 | R16
164560203981 | 160993203981 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-15 | 2020-09-15 | 2020-09-15 |  | 2021-04-14 | Overhead | R16 | 2020-12-09 | 1 |  | 62 | 91 | 152 | 2020 | 2021 | R16
167752203721 | 160533203721 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-11 | 2020-09-11 | 2020-09-11 |  | 2021-04-16 | Underground | R16 | 2021-01-05 | 1 |  | 83 | 74 | 156 | 2020 | 2021 | R16
161742205784 | 164813205784 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-09-30 | 2020-09-30 | 2020-09-30 | 2020-10-01 | 2020-10-02 | Overhead | R16 | 2020-10-01 | 1 |  | 2 | 2 | 3 | 2020 | 2020 | R16
168395202373 | 160976202373 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-30 | 2020-07-30 | 2020-08-31 |  | 2021-08-11 | Underground | R16 | 2021-06-30 | 1 | 23 | 218 | 31 | 270 | 2020 | 2021 | R16
169701166106 | 163000166106 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-25 | 2019-09-25 | 2019-09-27 |  | 2020-06-09 | Overhead | R16 | 2020-02-19 | 1 | 3 | 104 | 80 | 185 | 2019 | 2020 | R16
166736241668 | 161744241668 | NON-RESIDENTIAL - SMALL RETAIL | R16 RESD AND NON RESD US | Commercial | 2020-09-18 | 2020-10-02 | 2021-08-02 | 2022-07-12 | 2023-11-20 | Underground | R16 | 2022-07-12 | 11 | 217 | 247 | 355 | 827 | 2020 | 2023 | R16
169309225734 | 162789225734 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-03-23 | 2021-04-05 | 2021-04-05 |  | 2021-11-13 | Underground | R16 | 2021-10-21 | 10 |  | 144 | 17 | 169 | 2021 | 2021 | R16
169761166349 | 163832166349 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-30 | 2019-09-30 | 2019-10-01 |  | 2019-11-26 | Overhead | R16 | 2019-11-19 | 1 | 2 | 36 | 6 | 42 | 2019 | 2019 | R16
160206150597 | 160159150597 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-29 | 2019-01-29 | 2019-04-29 | 2019-06-18 | 2019-06-19 | Underground | R16 | 2019-06-18 | 1 | 65 | 37 | 2 | 102 | 2019 | 2019 | R16
169851172576 | 164506172576 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-11-21 | 2019-11-21 | 2019-11-21 |  | 2020-07-10 | Overhead | R16 | 2020-06-12 | 1 |  | 147 | 21 | 167 | 2019 | 2020 | R16
163899162279 | 163681162279 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-04-15 | 2019-04-15 | 2019-08-26 | 2020-10-08 | 2020-10-16 | Underground | R16 | 2020-10-08 | 1 | 96 | 294 | 7 | 395 | 2019 | 2020 | R16
169924166716 | 161605166716 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-18 | 2019-09-30 | 2019-10-04 |  | 2021-11-10 | Overhead | R16 | 2019-12-18 | 9 | 5 | 54 | 496 | 561 | 2019 | 2021 | R16
164626211149 | 165713211149 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-18 | 2020-11-18 | 2020-11-18 | 2021-01-20 | 2021-01-21 | Overhead | R16 | 2021-01-20 | 1 |  | 46 | 2 | 47 | 2020 | 2021 | R16
164919226537 | 167695226537 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-13 | 2021-04-13 | 2021-04-13 | 2021-05-11 | 2021-05-11 | Overhead | R16 | 2021-05-11 | 1 |  | 21 |  | 21 | 2021 | 2021 | R16
169942167609 | 166176167609 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-10 | 2019-10-10 | 2019-10-10 |  | 2021-11-10 | Overhead | R16 | 2019-12-17 | 1 |  | 49 | 497 | 545 | 2019 | 2021 | R16
163209150396 | 165695150396 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-26 | 2019-04-26 | 2019-04-26 | 2019-05-14 | 2019-05-15 | Underground | R16 | 2019-05-14 | 1 |  | 13 | 2 | 14 | 2019 | 2019 | R16
163331150691 | 166171150691 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-30 | 2019-04-30 | 2019-04-30 | 2019-06-28 | 2019-07-01 | Overhead | R16 | 2019-06-28 | 1 |  | 44 | 2 | 45 | 2019 | 2019 | R16
160327219417 | 162105219417 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2021-02-04 | 2021-02-04 | 2021-02-04 | 2021-02-12 | 2021-05-06 | Overhead | R16 | 2021-02-12 | 1 |  | 7 | 60 | 66 | 2021 | 2021 | R16
162366154358 | 162520154358 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-08 | 2019-02-08 | 2019-06-05 | 2019-08-22 | 2021-04-05 | Underground | R16 | 2019-08-22 | 1 | 84 | 57 | 423 | 562 | 2019 | 2021 | R16
160030172664 | 166566172664 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-10-12 | 2019-10-12 | 2019-11-21 |  | 2021-11-10 | Underground | R16 |  | 0 | 29 |  |  | 543 | 2019 | 2021 | R16
168012223598 | 165507223598 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-21 | 2021-03-15 | 2021-03-15 |  | 2021-08-26 | Overhead | R16 | 2021-06-09 | 16 |  | 63 | 57 | 134 | 2021 | 2021 | R16
163402203433 | 160197203433 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-11 | 2020-09-11 | 2020-09-11 |  | 2021-04-16 | Underground | R16 | 2021-01-05 | 1 |  | 83 | 74 | 156 | 2020 | 2021 | R16
160110173095 | 160068173095 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-09 | 2019-09-09 | 2019-11-27 |  | 2020-06-09 | Underground | R16 | 2020-03-05 | 1 | 58 | 72 | 69 | 197 | 2019 | 2020 | R16
166179229593 | 160885229593 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2021-04-27 | 2021-05-05 | 2021-05-05 | 2021-08-23 | 2021-08-25 | Overhead | R16 | 2021-08-23 | 7 |  | 79 | 3 | 87 | 2021 | 2021 | R16
160112169338 | 160049169338 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-09 | 2019-09-09 | 2019-10-24 |  | 2022-04-01 | Underground | R16 | 2022-03-16 | 1 | 34 | 625 | 13 | 670 | 2019 | 2022 | R16
160113176178 | 160091176178 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-09 | 2019-09-09 | 2020-01-08 |  | 2020-06-09 | Underground | R16 | 2020-03-05 | 1 | 88 | 42 | 69 | 197 | 2019 | 2020 | R16
169652170172 | 161638170172 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-04-04 | 2019-04-24 | 2019-10-30 | 2020-03-28 | 2020-11-11 | Underground | R16 | 2020-03-28 | 15 | 136 | 108 | 163 | 420 | 2019 | 2020 | R16
167355228591 | 161142228591 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-28 | 2021-04-28 | 2021-04-28 |  | 2021-08-13 | Overhead | R16 | 2021-07-20 | 1 |  | 60 | 19 | 78 | 2021 | 2021 | R16
160128169951 | 169602169951 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-28 | 2019-10-28 | 2019-10-28 |  | 2019-12-12 | Overhead | R16 | 2019-12-03 | 1 |  | 27 | 8 | 34 | 2019 | 2019 | R16
169095227033 | 165255227033 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-04-01 | 2021-04-01 | 2021-04-15 |  | 2021-11-09 | Overhead | R16 |  | 1 | 11 |  |  | 159 | 2021 | 2021 | R16
160234172320 | 163663172320 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-18 | 2019-11-19 | 2019-11-19 |  | 2021-11-10 | Overhead | R16 | 2020-01-29 | 2 |  | 52 | 466 | 518 | 2019 | 2021 | R16
165770224577 | 163034224577 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-24 | 2021-03-24 | 2021-03-24 | 2021-05-17 | 2021-11-08 | Overhead | R16 | 2021-05-17 | 1 |  | 39 | 126 | 164 | 2021 | 2021 | R16
164582226945 | 166665226945 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG SVC RELOC NON CUST GEN UD | Residential | 2021-01-13 | 2021-03-29 | 2021-04-14 |  | 2022-05-11 | Underground | R16 |  | 54 | 13 |  |  | 346 | 2021 | 2022 | R16
160262166646 | 160674166646 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-12 | 2019-09-12 | 2019-10-02 |  | 2020-07-08 | Underground | R16 | 2020-04-17 | 1 | 15 | 143 | 59 | 215 | 2019 | 2020 | R16
169838208553 | 164864208553 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-09-30 | 2020-09-30 | 2020-10-26 |  | 2021-04-16 | Underground | R16 | 2021-01-06 | 1 | 19 | 53 | 73 | 143 | 2020 | 2021 | R16
169230233007 | 161071233007 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-01 | 2021-06-01 | 2021-06-01 |  | 2021-08-13 | Overhead | R16 | 2021-07-19 | 1 |  | 35 | 20 | 54 | 2021 | 2021 | R16
160281170447 | 160677170447 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-01 | 2019-11-01 | 2019-11-01 |  | 2020-06-09 | Overhead | R16 | 2020-03-03 | 1 |  | 88 | 71 | 158 | 2019 | 2020 | R16
160285166718 | 162061166718 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-20 | 2019-09-30 | 2019-10-04 |  | 2021-11-10 | Overhead | R16 | 2019-12-17 | 7 | 5 | 53 | 497 | 559 | 2019 | 2021 | R16
167328246255 | 169087246255 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-09 | 2021-03-09 | 2021-09-02 | 2021-12-16 | 2021-12-17 | Underground | R16 | 2021-12-16 | 1 | 128 | 76 | 2 | 204 | 2021 | 2021 | R16
160359166395 | 163918166395 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-01 | 2019-10-01 | 2019-10-01 |  | 2019-12-19 | Overhead | R16 | 2019-12-10 | 1 |  | 51 | 8 | 58 | 2019 | 2019 | R16
160416170321 | 164021170321 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-01 | 2019-10-01 | 2019-10-31 |  | 2022-07-29 | Underground | R16 |  | 1 | 23 |  |  | 739 | 2019 | 2022 | R16
169122217004 | 166423217004 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-12 | 2021-01-12 | 2021-01-12 |  | 2021-08-03 | Overhead | R16 | 2021-03-29 | 1 |  | 55 | 92 | 146 | 2021 | 2021 | R16
162018229672 | 160363229672 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-26 | 2021-04-26 | 2021-05-06 |  | 2022-03-28 | Underground | R16 | 2022-03-10 | 1 | 9 | 221 | 13 | 241 | 2021 | 2022 | R16
168855202085 | 167189202085 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-27 | 2020-08-27 | 2020-08-27 | 2020-09-16 | 2021-07-07 | Overhead | R16 | 2020-09-16 | 1 |  | 15 | 211 | 225 | 2020 | 2021 | R16
168282209270 | 169675209270 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-09 | 2020-09-09 | 2020-10-31 |  | 2021-07-19 | Underground | R16 | 2020-11-16 | 1 | 38 | 11 | 176 | 224 | 2020 | 2021 | R16
166137210702 | 166227210702 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-06 | 2020-10-06 | 2020-11-13 |  | 2021-04-20 | Underground | R16 | 2021-01-12 | 1 | 29 | 43 | 71 | 141 | 2020 | 2021 | R16
160478267628 | 164153267628 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-26 | 2022-01-26 | 2022-02-04 |  | 2022-04-01 | Overhead | R16 |  | 1 | 8 |  |  | 48 | 2022 | 2022 | R16
165388144864 | 166176144864 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-04 | 2019-03-04 | 2019-03-04 | 2019-06-18 | 2019-06-19 | Overhead | R16 | 2019-06-18 | 1 |  | 77 | 2 | 78 | 2019 | 2019 | R16
160490166790 | 164441166790 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-03 | 2019-10-03 | 2019-10-03 |  | 2023-06-08 | Overhead | R16 | 2019-10-25 | 1 |  | 17 | 945 | 961 | 2019 | 2023 | R16
168548231242 | 162351231242 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-03 | 2021-05-17 | 2021-05-17 | 2021-06-08 | 2021-08-23 | Overhead | R16 | 2021-06-08 | 11 |  | 17 | 55 | 81 | 2021 | 2021 | R16
161145255505 | 163796255505 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2021-05-07 | 2021-09-22 | 2021-11-08 |  | 2021-12-28 | Overhead | R16 |  | 99 | 34 |  |  | 168 | 2021 | 2021 | R16
169817200825 | 164297200825 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-17 | 2020-08-17 | 2020-08-17 |  | 2021-07-01 | Overhead | R16 | 2020-10-28 | 1 |  | 53 | 177 | 229 | 2020 | 2021 | R16
160535168580 | 163983168580 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-01 | 2019-10-01 | 2019-10-17 |  | 2022-07-29 | Underground | R16 |  | 1 | 13 |  |  | 739 | 2019 | 2022 | R16
160539167157 | 162471167157 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-23 | 2019-09-23 | 2019-10-08 |  | 2022-08-05 | Underground | R16 | 2022-08-04 | 1 | 12 | 738 | 2 | 750 | 2019 | 2022 | R16
163129230380 | 163185230380 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-05 | 2021-05-05 | 2021-05-11 | 2021-09-09 | 2021-09-13 | Overhead | R16 | 2021-09-09 | 1 | 5 | 88 | 3 | 94 | 2021 | 2021 | R16
160550167420 | 162337167420 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-23 | 2019-09-23 | 2019-10-08 |  | 2021-10-25 | Underground | R16 | 2021-09-17 | 1 | 12 | 509 | 27 | 546 | 2019 | 2021 | R16
169149210526 | 164573210526 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-12 | 2020-11-12 | 2020-11-12 |  | 2021-12-17 | Overhead | R16 | 2021-11-17 | 1 |  | 265 | 23 | 287 | 2020 | 2021 | R16
161926200641 | 163676200641 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-14 | 2020-08-14 | 2020-08-14 |  | 2020-12-14 | Overhead | R16 | 2020-09-08 | 1 |  | 18 | 70 | 87 | 2020 | 2020 | R16
160556179230 | 166455179230 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-12-05 | 2019-12-05 | 2020-02-03 |  | 2021-07-26 | Underground | R16 | 2020-11-06 | 1 | 43 | 200 | 187 | 428 | 2019 | 2021 | R16
161528209308 | 162015209308 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-02 | 2020-11-02 | 2020-11-02 | 2021-02-03 | 2021-06-03 | Overhead | R16 | 2021-02-03 | 1 |  | 68 | 87 | 154 | 2020 | 2021 | R16
163635214375 | 160095214375 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-11 | 2020-12-17 | 2020-12-18 |  | 2021-04-29 | Overhead | R16 | 2021-02-08 | 5 | 2 | 37 | 59 | 100 | 2020 | 2021 | R16
160586168630 | 160839168630 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-09-13 | 2019-09-13 | 2019-10-17 |  | 2019-12-30 | Underground | R16 | 2019-12-06 | 1 | 25 | 37 | 17 | 77 | 2019 | 2019 | R16
160610179241 | 160545179241 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-31 | 2020-01-16 | 2020-02-03 |  | 2020-06-09 | Underground | R16 |  | 56 | 13 |  |  | 159 | 2019 | 2020 | R16
162117211338 | 166111211338 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-19 | 2020-11-19 | 2020-11-19 |  | 2021-11-13 | Overhead | R16 | 2021-04-26 | 1 |  | 113 | 145 | 257 | 2020 | 2021 | R16
160617165660 | 162462165660 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-09-23 | 2019-09-24 | 2019-09-24 |  | 2020-06-09 | Underground | R16 | 2020-03-13 | 2 |  | 124 | 63 | 187 | 2019 | 2020 | R16
166663218247 | 169390218247 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-25 | 2021-01-25 | 2021-01-25 |  | 2021-08-11 | Overhead | R16 | 2021-03-17 | 1 |  | 38 | 106 | 143 | 2021 | 2021 | R16
160619166641 | 160923166641 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-13 | 2019-09-13 | 2019-10-02 |  | 2019-11-13 | Underground | R16 | 2019-11-04 | 1 | 14 | 24 | 8 | 44 | 2019 | 2019 | R16
164235226179 | 165990226179 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-06 | 2021-04-06 | 2021-04-09 |  | 2021-10-25 | Overhead | R16 | 2021-08-26 | 1 | 4 | 100 | 43 | 145 | 2021 | 2021 | R16
160623166844 | 160675166844 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-12 | 2019-09-12 | 2019-10-03 |  | 2021-10-25 | Underground | R16 | 2021-07-23 | 1 | 16 | 472 | 67 | 553 | 2019 | 2021 | R16
164295201880 | 166594201880 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-26 | 2020-08-26 | 2020-08-26 |  | 2021-11-04 | Overhead | R16 | 2021-04-05 | 1 |  | 159 | 154 | 312 | 2020 | 2021 | R16
166480219323 | 161460219323 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-01 | 2021-02-01 | 2021-02-02 |  | 2021-04-29 | Overhead | R16 | 2021-02-09 | 1 | 2 | 6 | 58 | 64 | 2021 | 2021 | R16
166271200497 | 168414200497 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-15 | 2020-07-15 | 2020-08-13 | 2020-09-09 | 2020-09-10 | Underground | R16 | 2020-09-09 | 1 | 22 | 20 | 2 | 42 | 2020 | 2020 | R16
160663166543 | 164078166543 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-01 | 2019-10-01 | 2019-10-01 |  | 2019-12-19 | Overhead | R16 | 2019-12-10 | 1 |  | 51 | 8 | 58 | 2019 | 2019 | R16
168805151606 | 164251151606 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-18 | 2019-05-07 | 2019-05-07 | 2019-05-20 | 2019-08-12 | Overhead | R16 | 2019-05-20 | 14 |  | 10 | 61 | 83 | 2019 | 2019 | R16
163623232531 | 169979232531 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-26 | 2021-05-26 | 2021-05-26 |  | 2021-08-16 | Overhead | R16 | 2021-06-14 | 1 |  | 14 | 46 | 59 | 2021 | 2021 | R16
160700167337 | 165661167337 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-08 | 2019-10-08 | 2019-10-08 |  | 2020-01-08 | Overhead | R16 | 2020-01-02 | 1 |  | 63 | 5 | 67 | 2019 | 2020 | R16
165493232176 | 169607232176 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-25 | 2021-05-25 | 2021-05-25 |  | 2021-09-13 | Overhead | R16 | 2021-08-18 | 1 |  | 62 | 19 | 80 | 2021 | 2021 | R16
160726165784 | 162874165784 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-25 | 2019-09-25 | 2019-09-25 |  | 2019-11-21 | Overhead | R16 | 2019-11-14 | 1 |  | 37 | 6 | 42 | 2019 | 2019 | R16
160734166229 | 163558166229 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-30 | 2019-09-30 | 2019-09-30 |  | 2019-11-21 | Overhead | R16 | 2019-11-12 | 1 |  | 32 | 8 | 39 | 2019 | 2019 | R16
166143219983 | 166791219983 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-23 | 2020-12-01 | 2021-02-08 |  | 2023-06-07 | Underground | R16 |  | 7 | 50 |  |  | 663 | 2020 | 2023 | R16
160625142169 | 161076142169 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-04 | 2019-02-04 | 2019-02-04 | 2019-03-07 | 2019-03-07 | Overhead | R16 | 2019-03-07 | 1 |  | 24 |  | 24 | 2019 | 2019 | R16
160757165716 | 162872165716 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-25 | 2019-09-25 | 2019-09-25 |  | 2019-12-09 | Overhead | R16 | 2019-12-02 | 1 |  | 49 | 6 | 54 | 2019 | 2019 | R16
160811181248 | 163928181248 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-11-20 | 2020-02-07 | 2020-02-20 |  | 2020-07-09 | Overhead | R16 |  | 58 | 10 |  |  | 167 | 2019 | 2020 | R16
165635209533 | 161362209533 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-29 | 2020-11-03 | 2020-11-03 | 2020-12-01 | 2020-12-16 | Underground | R16 | 2020-12-01 | 4 |  | 21 | 12 | 35 | 2020 | 2020 | R16
160859166530 | 164178166530 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-02 | 2019-10-02 | 2019-10-02 |  | 2021-11-10 | Overhead | R16 | 2020-05-13 | 1 |  | 161 | 391 | 551 | 2019 | 2021 | R16
165905207287 | 168208207287 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-15 | 2020-10-15 | 2020-10-15 |  | 2021-04-21 | Underground | R16 | 2021-01-21 | 1 |  | 71 | 65 | 135 | 2020 | 2021 | R16
160944166644 | 164183166644 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-02 | 2019-10-02 | 2019-10-02 |  | 2019-11-08 | Overhead | R16 | 2019-10-29 | 1 |  | 20 | 9 | 28 | 2019 | 2019 | R16
161397219990 | 166671219990 | INDUSTRIAL | R16 RESD AND NON RESD US | Commercial | 2021-01-13 | 2021-01-14 | 2021-02-09 | 2021-08-06 | 2021-12-09 | Underground | R16 | 2021-08-06 | 2 | 19 | 129 | 90 | 237 | 2021 | 2021 | R16
160983243994 | 161514243994 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-16 | 2021-08-17 | 2021-08-17 |  | 2021-11-09 | Overhead | R16 | 2021-09-23 | 23 |  | 28 | 34 | 83 | 2021 | 2021 | R16
160047149442 | 160155149442 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-27 | 2019-03-27 | 2019-04-16 | 2019-06-04 | 2019-06-05 | Underground | R16 | 2019-06-04 | 1 | 15 | 36 | 2 | 51 | 2019 | 2019 | R16
161008170280 | 160318170280 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-10-30 | 2019-10-30 | 2019-10-30 |  | 2019-12-05 | Overhead | R16 | 2019-11-26 | 1 |  | 20 | 8 | 27 | 2019 | 2019 | R16
161014164564 | 161081164564 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-09-13 | 2019-09-13 | 2019-09-16 |  | 2020-08-27 | Underground | R16 |  | 1 | 2 |  |  | 250 | 2019 | 2020 | R16
167415221718 | 169666221718 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-01-26 | 2021-01-26 | 2021-02-25 |  | 2021-06-02 | Overhead | R16 | 2021-03-02 | 1 | 23 | 4 | 67 | 92 | 2021 | 2021 | R16
161025177335 | 161318177335 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-17 | 2019-09-17 | 2020-01-18 |  | 2020-03-26 | Underground | R16 |  | 1 | 89 |  |  | 138 | 2019 | 2020 | R16
167425153055 | 160513153055 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-22 | 2019-05-22 | 2019-05-22 | 2019-06-18 | 2019-06-19 | Overhead | R16 | 2019-06-18 | 1 |  | 20 | 2 | 21 | 2019 | 2019 | R16
161041165976 | 163234165976 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-27 | 2019-09-27 | 2019-09-27 |  | 2020-06-09 | Overhead | R16 | 2020-02-21 | 1 |  | 106 | 78 | 183 | 2019 | 2020 | R16
161054170060 | 161319170060 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-17 | 2019-09-17 | 2019-10-29 |  | 2020-06-09 | Underground | R16 | 2020-04-08 | 1 | 31 | 117 | 45 | 191 | 2019 | 2020 | R16
163705221594 | 166733221594 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-25 | 2021-02-25 | 2021-02-25 | 2021-03-01 | 2021-11-04 | Overhead | R16 | 2021-03-01 | 1 |  | 3 | 179 | 181 | 2021 | 2021 | R16
162085287523 | 167237287523 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2021-01-14 | 2021-01-14 | 2022-08-01 |  | 2023-11-17 | Underground | R16 |  | 1 | 403 |  |  | 742 | 2021 | 2023 | R16
166512142459 | 161982142459 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-07 | 2019-02-07 | 2019-02-07 | 2019-03-01 | 2019-03-01 | Overhead | R16 | 2019-03-01 | 1 |  | 17 |  | 17 | 2019 | 2019 | R16
160574227080 | 167290227080 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-28 | 2021-03-02 | 2021-04-15 | 2021-10-06 | 2021-11-09 | Underground | R16 | 2021-10-06 | 2 | 33 | 125 | 25 | 182 | 2021 | 2021 | R16
161226153178 | 162302153178 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-08 | 2019-04-08 | 2019-05-22 | 2019-06-24 | 2019-06-24 | Underground | R16 | 2019-06-24 | 1 | 33 | 24 |  | 56 | 2019 | 2019 | R16
162292247538 | 160890247538 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-31 | 2021-05-31 | 2021-09-14 |  | 2021-11-30 | Underground | R16 | 2021-11-03 | 1 | 77 | 37 | 20 | 132 | 2021 | 2021 | R16
161259166202 | 163691166202 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-09-30 | 2019-09-30 | 2019-09-30 |  | 2019-12-12 | Overhead | R16 | 2019-12-03 | 1 |  | 47 | 8 | 54 | 2019 | 2019 | R16
169425212709 | 167559212709 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-10-13 | 2020-10-15 | 2020-12-03 |  | 2021-04-20 | Overhead | R16 |  | 3 | 36 |  |  | 136 | 2020 | 2021 | R16
161266181988 | 162734181988 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-02-26 | 2020-02-26 | 2020-02-26 |  | 2022-03-01 | Underground | R16 | 2022-01-28 | 1 |  | 503 | 23 | 525 | 2020 | 2022 | R16
161267167541 | 165790167541 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-10-09 | 2019-10-09 | 2019-10-09 |  | 2019-11-26 | Overhead | R16 | 2019-11-19 | 1 |  | 30 | 6 | 35 | 2019 | 2019 | R16
161283165099 | 161340165099 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-09-16 | 2019-09-16 | 2019-09-20 |  | 2022-07-27 | Underground | R16 |  | 1 | 5 |  |  | 748 | 2019 | 2022 | R16
161283245248 | 169548245248 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential Subdivision | 2021-08-18 | 2021-08-23 | 2021-08-26 |  | 2021-10-25 | Underground | R16 |  | 4 | 4 |  |  | 49 | 2021 | 2021 | R16
161301169010 | 161426169010 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-17 | 2019-09-17 | 2019-10-21 |  | 2019-11-14 | Underground | R16 | 2019-11-06 | 1 | 25 | 13 | 7 | 43 | 2019 | 2019 | R16
161973149553 | 161918149553 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-05 | 2019-04-05 | 2019-04-19 | 2019-06-04 | 2019-06-05 | Underground | R16 | 2019-06-04 | 1 | 11 | 33 | 2 | 44 | 2019 | 2019 | R16
161353267306 | 169547267306 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-10-01 | 2021-10-01 | 2022-02-02 |  | 2022-04-01 | Underground | R16 |  | 1 | 89 |  |  | 131 | 2021 | 2022 | R16
160631212576 | 161117212576 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-28 | 2020-11-17 | 2020-12-02 |  | 2021-11-08 | Overhead | R16 |  | 15 | 12 |  |  | 269 | 2020 | 2021 | R16
165931231170 | 168815231170 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-19 | 2021-05-17 | 2021-05-17 | 2021-08-05 | 2021-10-25 | Overhead | R16 | 2021-08-05 | 21 |  | 59 | 58 | 136 | 2021 | 2021 | R16
161392170957 | 161471170957 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-09-17 | 2019-09-17 | 2019-11-06 |  | 2021-11-15 | Underground | R16 |  | 1 | 37 |  |  | 565 | 2019 | 2021 | R16
163041220709 | 164830220709 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE NON RES OS | Residential | 2021-02-17 | 2021-02-17 | 2021-02-17 |  | 2022-06-01 | Overhead | R16 | 2021-03-30 | 1 |  | 30 | 307 | 336 | 2021 | 2022 | R16
161392251341 | 167392251341 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential Subdivision | 2021-09-23 | 2021-09-24 | 2021-10-08 |  | 2021-11-13 | Underground | R16 | 2021-10-21 | 2 | 11 | 10 | 17 | 37 | 2021 | 2021 | R16
167903216778 | 166128216778 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-11 | 2021-01-12 | 2021-01-12 | 2022-07-20 | 2022-07-21 | Overhead | R16 | 2022-07-20 | 2 |  | 397 | 2 | 399 | 2021 | 2022 | R16
164652226797 | 168147226797 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-04-15 | 2021-04-15 | 2021-04-15 | 2021-09-27 | 2021-12-15 | Underground | R16 | 2021-09-27 | 1 |  | 118 | 58 | 175 | 2021 | 2021 | R16
164679143565 | 163993143565 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-19 | 2019-02-19 | 2019-02-19 | 2019-03-11 | 2019-03-13 | Overhead | R16 | 2019-03-11 | 1 |  | 15 | 3 | 17 | 2019 | 2019 | R16
167540217167 | 166770217167 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-01-13 | 2021-01-14 | 2021-01-14 | 2021-07-18 | 2021-07-21 | Underground | R16 | 2021-07-18 | 2 |  | 132 | 3 | 136 | 2021 | 2021 | R16
161420175488 | 166436175488 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-10-11 | 2019-10-11 | 2019-12-31 |  | 2020-06-09 | Underground | R16 |  | 1 | 58 |  |  | 173 | 2019 | 2020 | R16
161309229187 | 166620229187 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-08 | 2021-04-08 | 2021-05-03 |  | 2021-11-09 | Underground | R16 | 2021-10-21 | 1 | 18 | 124 | 14 | 154 | 2021 | 2021 | R16
167523226361 | 161075226361 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-16 | 2021-03-19 | 2021-04-08 | 2021-08-25 | 2021-08-26 | Underground | R16 | 2021-08-25 | 4 | 15 | 100 | 2 | 118 | 2021 | 2021 | R16
166129225451 | 164875225451 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-31 | 2021-03-31 | 2021-03-31 |  | 2021-08-26 | Overhead | R16 | 2021-06-08 | 1 |  | 50 | 58 | 107 | 2021 | 2021 | R16
163317217432 | 167338217432 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-01-15 | 2021-01-15 | 2021-01-15 |  | 2021-05-05 | Overhead | R16 | 2021-02-12 | 1 |  | 21 | 59 | 79 | 2021 | 2021 | R16
161462171117 | 162087171117 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-08 | 2019-11-08 | 2019-11-08 |  | 2020-06-09 | Overhead | R16 | 2020-01-27 | 1 |  | 57 | 97 | 153 | 2019 | 2020 | R16
169741207352 | 168326207352 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-15 | 2020-10-15 | 2020-10-15 | 2021-01-08 | 2021-07-28 | Overhead | R16 | 2021-01-08 | 1 |  | 62 | 144 | 205 | 2020 | 2021 | R16
163350213720 | 167570213720 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-30 | 2020-12-11 | 2020-12-11 | 2021-03-17 | 2021-08-16 | Overhead | R16 | 2021-03-17 | 10 |  | 69 | 109 | 186 | 2020 | 2021 | R16
164884221446 | 161270221446 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-12-16 | 2020-12-16 | 2021-02-23 |  | 2021-08-16 | Overhead | R16 |  | 1 | 50 |  |  | 174 | 2020 | 2021 | R16
163885198862 | 160662198862 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-29 | 2020-07-29 | 2020-07-29 |  | 2020-10-06 | Overhead | R16 | 2020-08-24 | 1 |  | 19 | 32 | 50 | 2020 | 2020 | R16
161141202304 | 167782202304 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-08-31 | 2020-08-31 | 2020-08-31 |  | 2021-10-11 | Overhead | R16 | 2021-09-13 | 1 |  | 271 | 21 | 291 | 2020 | 2021 | R16
164364160374 | 169973160374 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-26 | 2019-03-26 | 2019-08-07 | 2019-10-30 | 2019-11-01 | Overhead | R16 | 2019-10-30 | 1 | 97 | 61 | 3 | 159 | 2019 | 2019 | R16
164167232583 | 160183232583 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-27 | 2021-05-27 | 2021-05-27 | 2021-07-14 | 2021-08-13 | Underground | R16 | 2021-07-14 | 1 |  | 35 | 23 | 57 | 2021 | 2021 | R16
168889223959 | 160002223959 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-26 | 2021-02-18 | 2021-03-19 | 2021-06-15 | 2021-11-02 | Underground | R16 | 2021-06-15 | 18 | 22 | 63 | 101 | 201 | 2021 | 2021 | R16
161708190653 | 164430190653 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-03 | 2019-10-03 | 2020-05-12 |  | 2020-10-06 | Underground | R16 | 2020-07-23 | 1 | 159 | 53 | 54 | 264 | 2019 | 2020 | R16
165042314540 | 169112314540 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-24 | 2021-01-24 | 2023-04-03 |  | 2023-09-29 | Underground | R16 | 2023-09-12 | 0 | 571 | 117 | 14 | 700 | 2021 | 2023 | R16
161740170806 | 165297170806 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-07 | 2019-10-07 | 2019-11-05 |  | 2021-11-13 | Overhead | R16 | 2020-01-07 | 1 | 22 | 46 | 484 | 550 | 2019 | 2021 | R16
162155162810 | 162699162810 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-07 | 2019-06-07 | 2019-08-30 | 2019-11-21 | 2019-11-19 | Underground | R16 | 2019-11-21 | 1 | 61 | 60 |  | 118 | 2019 | 2019 | R16
160572236642 | 165902236642 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-06 | 2021-04-12 | 2021-06-24 | 2021-07-28 | 2021-08-23 | Underground | R16 | 2021-07-28 | 5 | 54 | 25 | 19 | 100 | 2021 | 2021 | R16
161747168393 | 167302168393 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-16 | 2019-10-16 | 2019-10-16 |  | 2019-12-19 | Overhead | R16 | 2019-12-12 | 1 |  | 42 | 6 | 47 | 2019 | 2019 | R16
169778221102 | 165393221102 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-05-20 | 2021-05-21 | Overhead | R16 | 2021-05-20 | 1 |  | 65 | 2 | 66 | 2021 | 2021 | R16
163096217085 | 163524217085 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-09 | 2020-11-09 | 2021-01-12 |  | 2022-10-27 | Underground | R16 | 2022-10-21 | 1 | 47 | 464 | 5 | 514 | 2020 | 2022 | R16
168527251892 | 162582251892 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-09-22 | 2021-03-02 | 2021-10-13 | 2021-12-03 | 2021-12-27 | Underground | R16 | 2021-12-03 | 116 | 162 | 38 | 17 | 330 | 2020 | 2021 | R16
168376140552 | 167860140552 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-17 | 2019-01-17 | 2019-01-17 | 2019-02-26 | 2019-02-27 | Overhead | R16 | 2019-02-26 | 1 |  | 29 | 2 | 30 | 2019 | 2019 | R16
161484209420 | 164286209420 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-28 | 2020-10-06 | 2020-11-02 |  | 2023-06-07 | Underground | R16 |  | 7 | 20 |  |  | 703 | 2020 | 2023 | R16
166651220998 | 164000220998 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-08-14 | 2020-12-07 | 2021-02-19 | 2021-04-09 | 2021-11-05 | Overhead | R16 | 2021-04-09 | 82 | 55 | 36 | 151 | 321 | 2020 | 2021 | R16
164048218537 | 160563218537 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-13 | 2020-12-31 | 2021-01-26 | 2021-03-19 | 2021-08-16 | Overhead | R16 | 2021-03-19 | 14 | 19 | 39 | 107 | 176 | 2020 | 2021 | R16
161800172779 | 169561172779 | MOBILE HOMES PARK AB622 | ELEC SVC FOR MOBILE HOMES | Residential | 2019-10-28 | 2019-10-28 | 2019-11-25 |  | 2022-04-07 | Underground | R16 |  | 1 | 21 |  |  | 639 | 2019 | 2022 | R16
161604230515 | 161535230515 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-02 | 2021-02-02 | 2021-05-13 |  | 2021-11-11 | Underground | R16 | 2021-07-20 | 1 | 73 | 49 | 83 | 203 | 2021 | 2021 | R16
160549215749 | 166470215749 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-22 | 2020-12-13 | 2020-12-28 | 2020-12-29 | 2021-05-05 | Overhead | R16 | 2020-12-29 | 15 | 11 | 2 | 92 | 118 | 2020 | 2021 | R16
161814166404 | 163766166404 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-30 | 2019-09-30 | 2019-09-30 |  | 2020-08-28 | Underground | R16 | 2020-06-26 | 1 |  | 195 | 46 | 240 | 2019 | 2020 | R16
162728154994 | 164963154994 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-23 | 2019-04-23 | 2019-06-11 | 2019-09-09 | 2019-09-10 | Underground | R16 | 2019-09-09 | 1 | 36 | 65 | 2 | 101 | 2019 | 2019 | R16
162390210451 | 164632210451 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-12 | 2020-11-12 | 2020-11-12 |  | 2021-11-08 | Overhead | R16 | 2021-05-27 | 1 |  | 141 | 118 | 258 | 2020 | 2021 | R16
165373209547 | 162649209547 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-04 | 2020-11-04 | 2020-11-04 | 2021-02-05 | 2021-02-08 | Overhead | R16 | 2021-02-05 | 1 |  | 68 | 2 | 69 | 2020 | 2021 | R16
167579219130 | 160196219130 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-10 | 2020-12-10 | 2021-02-01 |  | 2021-08-11 | Underground | R16 | 2021-06-28 | 1 | 38 | 106 | 33 | 175 | 2020 | 2021 | R16
161848184286 | 166272184286 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-03-14 | 2020-03-14 | 2020-03-16 |  | 2021-11-08 | Overhead | R16 |  | 0 | 1 |  |  | 431 | 2020 | 2021 | R16
164285218320 | 168733218320 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-01-22 | 2021-01-22 | 2021-01-25 |  | 2021-11-08 | Underground | R16 |  | 1 | 2 |  |  | 207 | 2021 | 2021 | R16
160524232163 | 163610232163 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-26 | 2021-03-26 | 2021-05-24 | 2021-08-19 | 2021-11-23 | Underground | R16 | 2021-08-19 | 1 | 42 | 64 | 69 | 173 | 2021 | 2021 | R16
163720224740 | 166219224740 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-01-12 | 2021-03-24 | 2021-03-24 |  | 2021-09-10 | Underground | R16 | 2021-08-19 | 52 |  | 107 | 17 | 174 | 2021 | 2021 | R16
160522216510 | 166830216510 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-24 | 2021-01-07 | 2021-01-07 | 2021-01-27 | 2021-04-29 | Overhead | R16 | 2021-01-27 | 33 |  | 15 | 67 | 113 | 2020 | 2021 | R16
160223216062 | 164501216062 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-04 | 2021-01-04 | 2021-01-04 |  | 2022-03-25 | Overhead | R16 | 2022-03-09 | 1 |  | 308 | 13 | 320 | 2021 | 2022 | R16
167283200128 | 169751200128 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-22 | 2020-07-22 | 2020-08-08 | 2020-10-28 | 2020-10-29 | Underground | R16 | 2020-10-28 | 1 | 13 | 58 | 2 | 72 | 2020 | 2020 | R16
160291225016 | 164253225016 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-29 | 2021-03-29 | 2021-03-29 |  | 2021-08-30 | Overhead | R16 | 2021-06-10 | 1 |  | 54 | 58 | 111 | 2021 | 2021 | R16
161964173006 | 165136173006 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-27 | 2019-11-27 | 2019-11-27 |  | 2022-08-02 | Overhead | R16 |  | 1 |  |  |  | 700 | 2019 | 2022 | R16
162554199811 | 162419199811 | RESIDENTIAL - SINGLE FAMILY ATTACHED | OH R16 RES NON RES OS | Residential | 2020-08-06 | 2020-08-06 | 2020-08-06 |  | 2020-11-06 | Overhead | R16 | 2020-09-03 | 1 |  | 21 | 47 | 67 | 2020 | 2020 | R16
165513272702 | 164668272702 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-11-13 | 2021-10-01 | 2022-03-15 | 2022-04-12 | 2022-05-02 | Overhead | R16 | 2022-04-12 | 231 | 118 | 21 | 15 | 382 | 2020 | 2022 | R16
160323234781 | 165744234781 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-17 | 2021-06-11 | 2021-06-11 | 2021-08-23 | 2021-08-25 | Overhead | R16 | 2021-08-23 | 20 |  | 52 | 3 | 73 | 2021 | 2021 | R16
164260210532 | 167456210532 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-12 | 2020-10-12 | 2020-11-12 | 2020-12-23 | 2021-05-05 | Underground | R16 | 2020-12-23 | 1 | 24 | 30 | 96 | 148 | 2020 | 2021 | R16
162554151905 | 168084151905 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-09 | 2019-05-09 | 2019-05-09 | 2019-05-20 | 2019-05-20 | Overhead | R16 | 2019-05-20 | 1 |  | 8 |  | 8 | 2019 | 2019 | R16
162073171091 | 162016171091 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-08 | 2019-11-08 | 2019-11-08 |  | 2020-01-03 | Overhead | R16 | 2019-12-12 | 1 |  | 25 | 17 | 41 | 2019 | 2020 | R16
162078170023 | 169498170023 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-28 | 2019-10-28 | 2019-10-28 |  | 2020-01-03 | Underground | R16 | 2019-12-12 | 1 |  | 34 | 17 | 50 | 2019 | 2020 | R16
160733191243 | 160830191243 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-05-24 | 2019-08-16 | 2020-05-15 | 2021-04-08 | 2021-04-09 | Underground | R16 | 2021-04-08 | 61 | 196 | 235 | 2 | 491 | 2019 | 2021 | R16
162079174437 | 168439174437 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-14 | 2019-12-14 | 2019-12-14 |  | 2020-06-09 | Overhead | R16 | 2020-02-24 | 0 |  | 51 | 77 | 127 | 2019 | 2020 | R16
167806213034 | 169353213034 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-08 | 2020-12-08 | 2020-12-08 | 2020-12-22 | 2021-04-21 | Overhead | R16 | 2020-12-22 | 1 |  | 11 | 87 | 97 | 2020 | 2021 | R16
160587150940 | 166404150940 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-30 | 2019-04-30 | 2019-04-30 | 2019-06-24 | 2019-08-26 | Overhead | R16 | 2019-06-24 | 1 |  | 40 | 46 | 85 | 2019 | 2019 | R16
161903212877 | 168750212877 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-04 | 2020-12-04 | 2020-12-04 | 2021-03-23 | 2021-02-19 | Overhead | R16 | 2021-03-23 | 1 |  | 78 |  | 56 | 2020 | 2021 | R16
162644216187 | 164875216187 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-05 | 2021-01-05 | 2021-01-05 | 2021-03-03 | 2021-03-04 | Overhead | R16 | 2021-03-03 | 1 |  | 42 | 2 | 43 | 2021 | 2021 | R16
162119179051 | 162135179051 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential Subdivision | 2019-09-20 | 2019-09-22 | 2020-02-03 |  | 2021-10-19 | Underground | R16 |  | 1 | 96 |  |  | 543 | 2019 | 2021 | R16
162119179167 | 162136179167 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential Subdivision | 2019-09-20 | 2019-09-30 | 2020-02-03 |  | 2021-08-18 | Underground | R16 |  | 7 | 91 |  |  | 499 | 2019 | 2021 | R16
161523213417 | 167274213417 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-10-12 | 2020-10-13 | 2020-12-10 |  | 2021-06-03 | Underground | R16 |  | 2 | 43 |  |  | 169 | 2020 | 2021 | R16
166750153855 | 167779153855 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-08 | 2019-05-08 | 2019-05-31 | 2019-07-30 | 2019-07-30 | Underground | R16 | 2019-07-30 | 1 | 18 | 43 |  | 60 | 2019 | 2019 | R16
168408226559 | 162630226559 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-22 | 2021-03-31 | 2021-04-13 | 2021-06-24 | 2021-08-11 | Overhead | R16 | 2021-06-24 | 8 | 10 | 53 | 35 | 103 | 2021 | 2021 | R16
162144174802 | 168139174802 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-10-21 | 2019-10-22 | 2019-12-18 |  | 2020-06-09 | Underground | R16 |  | 2 | 42 |  |  | 167 | 2019 | 2020 | R16
163670242356 | 163672242356 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-11-09 | 2020-11-09 | 2021-08-06 | 2021-12-29 | 2022-01-21 | Underground | R16 | 2021-12-29 | 1 | 195 | 104 | 18 | 315 | 2020 | 2022 | R16
165401243068 | 168431243068 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-12-03 | 2020-12-03 | 2021-08-11 |  | 2022-07-03 | Underground | R16 | 2022-06-21 | 1 | 180 | 225 | 9 | 412 | 2020 | 2022 | R16
161332206540 | 164997206540 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-09-30 | 2020-09-30 | 2020-10-07 | 2021-09-22 | 2021-10-15 | Underground | R16 | 2021-09-22 | 1 | 6 | 251 | 18 | 273 | 2020 | 2021 | R16
167837204875 | 167869204875 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-31 | 2020-08-31 | 2020-09-24 |  | 2021-04-22 | Underground | R16 | 2021-01-28 | 1 | 19 | 91 | 61 | 169 | 2020 | 2021 | R16
169410237293 | 167957237293 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2021-03-02 | 2021-03-02 | 2021-07-01 |  | 2023-06-22 | Underground | R16 | 2023-03-07 | 1 | 88 | 439 | 78 | 603 | 2021 | 2023 | R16
162414167310 | 164156167310 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-03 | 2019-10-04 | 2019-10-07 |  | 2022-08-29 | Overhead | R16 |  | 2 | 2 |  |  | 758 | 2019 | 2022 | R16
162428169094 | 162359169094 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2019-09-23 | 2019-09-23 | 2019-10-22 |  | 2023-05-11 | Underground | R16 |  | 1 | 22 |  |  | 949 | 2019 | 2023 | R16
161828203598 | 168688203598 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-09-04 | 2020-09-04 | 2020-09-11 | 2020-10-06 | 2021-01-13 | Underground | R16 | 2020-10-06 | 1 | 6 | 18 | 72 | 94 | 2020 | 2021 | R16
163493223344 | 160038223344 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-11 | 2021-03-11 | 2021-03-11 | 2021-04-20 | 2021-04-21 | Overhead | R16 | 2021-04-20 | 1 |  | 29 | 2 | 30 | 2021 | 2021 | R16
162458168521 | 167374168521 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-16 | 2019-10-16 | 2019-10-16 |  | 2020-10-06 | Overhead | R16 | 2020-08-27 | 1 |  | 227 | 29 | 255 | 2019 | 2020 | R16
162692205630 | 164520205630 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-29 | 2020-09-29 | 2020-09-29 |  | 2021-02-17 | Overhead | R16 | 2020-10-16 | 1 |  | 14 | 89 | 102 | 2020 | 2021 | R16
168886214490 | 161585214490 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-18 | 2020-12-18 | 2020-12-18 | 2020-12-22 | 2021-04-23 | Overhead | R16 | 2020-12-22 | 1 |  | 3 | 89 | 91 | 2020 | 2021 | R16
162526170018 | 169063170018 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-10-24 | 2019-10-24 | 2019-10-29 |  | 2021-10-28 | Overhead | R16 | 2021-09-27 | 1 | 4 | 500 | 24 | 526 | 2019 | 2021 | R16
164426236448 | 166459236448 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-13 | 2021-01-13 | 2021-06-24 | 2021-10-20 | 2021-11-03 | Underground | R16 | 2021-10-20 | 1 | 117 | 85 | 11 | 211 | 2021 | 2021 | R16
168708209186 | 161546209186 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-30 | 2020-10-30 | 2020-10-30 |  | 2021-04-13 | Underground | R16 | 2020-12-08 | 1 |  | 28 | 91 | 118 | 2020 | 2021 | R16
162679237683 | 162103237683 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-08-05 | 2021-04-28 | 2021-07-02 |  | 2022-03-03 | Underground | R16 |  | 191 | 48 |  |  | 412 | 2020 | 2022 | R16
169439221005 | 164027221005 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-10 | 2020-11-10 | 2021-02-19 | 2021-05-27 | 2021-08-26 | Overhead | R16 | 2021-05-27 | 1 | 74 | 70 | 66 | 208 | 2020 | 2021 | R16
162710173180 | 165351173180 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-11-27 | 2019-11-27 | 2019-11-27 |  | 2020-07-09 | Overhead | R16 | 2020-05-22 | 1 |  | 128 | 35 | 162 | 2019 | 2020 | R16
162734172560 | 167194172560 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-10-15 | 2019-10-15 | 2019-11-21 |  | 2020-10-06 | Overhead | R16 | 2020-08-11 | 1 | 28 | 189 | 41 | 256 | 2019 | 2020 | R16
169685220064 | 162970220064 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-02-08 | 2021-02-09 | 2021-02-09 | 2021-04-07 | 2021-04-08 | Overhead | R16 | 2021-04-07 | 2 |  | 42 | 2 | 44 | 2021 | 2021 | R16
162746169743 | 169269169743 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-26 | 2019-10-26 | 2019-10-26 |  | 2022-05-17 | Overhead | R16 | 2020-02-20 | 0 |  | 84 | 584 | 667 | 2019 | 2022 | R16
161192171139 | 161210171139 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-04-02 | 2019-04-02 | 2019-11-08 | 2019-12-19 | 2019-12-19 | Underground | R16 | 2019-12-19 | 1 | 159 | 30 |  | 188 | 2019 | 2019 | R16
162748169628 | 169404169628 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-25 | 2019-10-25 | 2019-10-25 |  | 2019-12-17 | Overhead | R16 | 2019-12-09 | 1 |  | 32 | 7 | 38 | 2019 | 2019 | R16
163754224931 | 163746224931 | NON-RESIDENTIAL - SMALL RETAIL | UG R16 RESD AND NON RESD UD | Residential Subdivision | 2019-04-16 | 2019-04-16 | 2021-03-26 | 2022-11-01 | 2022-11-22 | Underground | R16 | 2022-11-01 | 1 | 509 | 418 | 16 | 941 | 2019 | 2022 | R16
162786177733 | 165206177733 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-22 | 2020-01-22 | 2020-01-22 |  | 2021-11-10 | Overhead | R16 | 2020-03-17 | 1 |  | 40 | 432 | 471 | 2020 | 2021 | R16
161241217993 | 168327217993 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-20 | 2021-01-22 | 2021-01-22 |  | 2021-08-12 | Overhead | R16 | 2021-03-10 | 3 |  | 34 | 112 | 147 | 2021 | 2021 | R16
165078226328 | 165808226328 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-06 | 2021-04-06 | 2021-04-09 |  | 2021-11-08 | Underground | R16 | 2021-05-26 | 1 | 4 | 34 | 119 | 155 | 2021 | 2021 | R16
162802168319 | 167273168319 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-10-16 | 2019-10-16 | 2019-10-16 |  | 2020-10-06 | Overhead | R16 | 2020-07-09 | 1 |  | 192 | 64 | 255 | 2019 | 2020 | R16
162380151577 | 167864151577 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-08 | 2019-05-08 | 2019-05-08 | 2019-06-04 | 2019-08-12 | Overhead | R16 | 2019-06-04 | 1 |  | 20 | 50 | 69 | 2019 | 2019 | R16
168210223772 | 161243223772 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-17 | 2021-03-17 | 2021-03-17 |  | 2021-11-05 | Overhead | R16 | 2021-05-04 | 1 |  | 35 | 134 | 168 | 2021 | 2021 | R16
164652150613 | 164505150613 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-02 | 2019-01-02 | 2019-04-29 | 2022-04-03 | 2022-04-21 | Overhead | R16 | 2022-04-03 | 1 | 84 | 765 | 14 | 862 | 2019 | 2022 | R16
162878170679 | 165349170679 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-07 | 2019-10-07 | 2019-11-05 |  | 2020-06-09 | Overhead | R16 | 2020-01-27 | 1 | 22 | 60 | 97 | 177 | 2019 | 2020 | R16
160750200315 | 163441200315 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-12 | 2020-08-12 | 2020-08-12 |  | 2020-12-14 | Underground | R16 | 2020-09-09 | 1 |  | 21 | 69 | 89 | 2020 | 2020 | R16
162920168196 | 166739168196 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-14 | 2019-10-14 | 2019-10-14 |  | 2021-11-10 | Overhead | R16 | 2019-12-18 | 1 |  | 48 | 496 | 543 | 2019 | 2021 | R16
162307157194 | 162464157194 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-06 | 2019-06-06 | 2019-07-08 | 2019-08-23 | 2019-08-26 | Underground | R16 | 2019-08-23 | 1 | 23 | 35 | 2 | 58 | 2019 | 2019 | R16
162715219725 | 162543219725 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-02-05 | 2021-02-05 | 2021-02-05 |  | 2021-11-05 | Underground | R16 | 2021-04-12 | 1 |  | 47 | 150 | 196 | 2021 | 2021 | R16
162181201830 | 166751201830 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-08-26 | 2020-08-26 | 2020-08-26 |  | 2020-10-29 | Overhead | R16 | 2020-09-01 | 1 |  | 5 | 43 | 47 | 2020 | 2020 | R16
162945169599 | 169443169599 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-26 | 2019-10-26 | 2019-10-26 |  | 2019-12-12 | Overhead | R16 | 2019-12-03 | 0 |  | 27 | 8 | 34 | 2019 | 2019 | R16
162969173752 | 166785173752 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-09 | 2019-12-09 | 2019-12-09 |  | 2021-11-13 | Underground | R16 | 2020-01-07 | 1 |  | 22 | 484 | 505 | 2019 | 2021 | R16
168834213100 | 169081213100 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-12-07 | 2020-12-07 | 2020-12-07 |  | 2021-04-13 | Underground | R16 |  | 1 |  |  |  | 92 | 2020 | 2021 | R16
162235201766 | 166600201766 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-25 | 2020-08-25 | 2020-08-25 |  | 2021-04-16 | Underground | R16 | 2021-01-08 | 1 |  | 99 | 71 | 169 | 2020 | 2021 | R16
167092142517 | 162035142517 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-07 | 2019-02-07 | 2019-02-07 | 2019-02-11 | 2019-04-15 | Overhead | R16 | 2019-02-11 | 1 |  | 3 | 46 | 48 | 2019 | 2019 | R16
166221215913 | 166928215913 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-24 | 2020-12-31 | 2020-12-31 | 2021-02-24 | 2021-03-01 | Overhead | R16 | 2021-02-24 | 28 |  | 40 | 4 | 70 | 2020 | 2021 | R16
160445162710 | 160470162710 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-01-30 | 2019-05-06 | 2019-08-29 | 2020-06-25 | 2020-09-30 | Underground | R16 | 2020-06-25 | 69 | 84 | 216 | 70 | 436 | 2019 | 2020 | R16
163024179426 | 164309179426 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-11-21 | 2019-12-02 | 2020-02-05 |  | 2020-07-02 | Overhead | R16 | 2020-05-05 | 8 | 48 | 65 | 43 | 161 | 2019 | 2020 | R16
163046171192 | 166279171192 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Commercial | 2019-10-11 | 2019-10-16 | 2019-11-08 |  | 2020-06-09 | Underground | R16 |  | 4 | 18 |  |  | 173 | 2019 | 2020 | R16
163046171380 | 166470171380 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-10-11 | 2019-10-16 | 2019-11-11 |  | 2020-07-08 | Underground | R16 |  | 4 | 19 |  |  | 194 | 2019 | 2020 | R16
163076166859 | 164615166859 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-03 | 2019-10-03 | 2019-10-04 |  | 2019-11-21 | Overhead | R16 | 2019-11-14 | 1 | 2 | 30 | 6 | 36 | 2019 | 2019 | R16
165612214198 | 160265214198 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-12-11 | 2020-12-11 | 2020-12-17 |  | 2021-08-16 | Overhead | R16 | 2021-03-16 | 1 | 5 | 64 | 110 | 177 | 2020 | 2021 | R16
164797142943 | 167397142943 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-15 | 2019-01-15 | 2019-02-11 |  | 2019-03-25 | Underground | R16 |  | 1 | 20 |  |  | 50 | 2019 | 2019 | R16
165332202608 | 168278202608 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-02 | 2020-09-02 | 2020-09-02 |  | 2021-01-21 | Overhead | R16 | 2020-10-13 | 1 |  | 30 | 73 | 102 | 2020 | 2021 | R16
168454213385 | 168458213385 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2020-12-03 | 2020-12-03 | 2020-12-09 | 2021-06-05 | 2021-06-08 | Underground | R16 | 2021-06-05 | 1 | 5 | 128 | 2 | 134 | 2020 | 2021 | R16
163178167267 | 164676167267 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-04 | 2019-10-04 | 2019-10-07 |  | 2020-06-09 | Underground | R16 | 2020-02-20 | 1 | 2 | 99 | 79 | 178 | 2019 | 2020 | R16
165899241030 | 160962241030 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-01 | 2021-06-02 | 2021-07-27 | 2021-09-02 | 2021-09-02 | Underground | R16 | 2021-09-02 | 2 | 40 | 28 |  | 68 | 2021 | 2021 | R16
163198170112 | 169699170112 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-29 | 2019-10-30 | 2019-10-30 |  | 2020-06-09 | Overhead | R16 | 2020-03-03 | 2 |  | 90 | 71 | 161 | 2019 | 2020 | R16
162834203537 | 160440203537 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-11 | 2020-09-11 | 2020-09-11 | 2020-10-09 | 2021-07-02 | Overhead | R16 | 2020-10-09 | 1 |  | 21 | 191 | 211 | 2020 | 2021 | R16
163220168764 | 163263168764 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-09-26 | 2019-09-26 | 2019-10-18 |  | 2023-06-02 | Underground | R16 | 2019-11-22 | 1 | 17 | 26 | 921 | 962 | 2019 | 2023 | R16
163222170081 | 169749170081 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-29 | 2019-10-29 | 2019-10-29 |  | 2021-11-04 | Overhead | R16 | 2021-06-02 | 1 |  | 417 | 112 | 528 | 2019 | 2021 | R16
163224173172 | 167043173172 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-15 | 2019-10-15 | 2019-11-27 |  | 2020-07-08 | Underground | R16 | 2020-05-18 | 1 | 32 | 124 | 38 | 192 | 2019 | 2020 | R16
164449151241 | 160148151241 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-27 | 2019-03-27 | 2019-05-03 | 2019-05-23 | 2019-11-18 | Overhead | R16 | 2019-05-23 | 1 | 28 | 15 | 128 | 169 | 2019 | 2019 | R16
166424221751 | 166805221751 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-02-26 | 2021-02-26 | 2021-02-26 |  | 2021-11-08 | Overhead | R16 | 2021-04-21 | 1 |  | 39 | 144 | 182 | 2021 | 2021 | R16
163308167140 | 164613167140 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-03 | 2019-10-03 | 2019-10-06 |  | 2019-11-21 | Overhead | R16 | 2019-11-21 | 1 | 2 | 34 |  | 36 | 2019 | 2019 | R16
163345166692 | 164750166692 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-04 | 2019-10-04 | 2019-10-04 |  | 2019-11-14 | Overhead | R16 | 2019-10-25 | 1 |  | 16 | 15 | 30 | 2019 | 2019 | R16
163348168693 | 167641168693 | NON-RESIDENTIAL - SMALL RETAIL | OH R16 RES NON RES OS | Residential | 2019-10-18 | 2019-10-18 | 2019-10-18 |  | 2021-08-23 | Overhead | R16 | 2021-07-16 | 1 |  | 456 | 27 | 482 | 2019 | 2021 | R16
165283158206 | 167670158206 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-03-11 | 2019-03-11 | 2019-07-18 | 2019-08-02 | 2019-08-07 | Underground | R16 | 2019-08-02 | 1 | 94 | 12 | 4 | 108 | 2019 | 2019 | R16
165432214134 | 161225214134 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-16 | 2020-12-16 | 2020-12-16 | 2021-07-07 | 2021-07-08 | Overhead | R16 | 2021-07-07 | 1 |  | 146 | 2 | 147 | 2020 | 2021 | R16
164981217836 | 168475217836 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2021-01-21 | 2021-01-21 | 2021-01-21 | 2021-07-20 | 2021-07-22 | Overhead | R16 | 2021-07-20 | 1 |  | 129 | 3 | 131 | 2021 | 2021 | R16
163374169563 | 163840169563 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-30 | 2019-09-30 | 2019-10-24 |  | 2021-11-10 | Underground | R16 | 2020-01-28 | 1 | 19 | 69 | 467 | 553 | 2019 | 2021 | R16
164329151098 | 167028151098 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-02 | 2019-05-02 | 2019-05-03 | 2019-08-28 | 2019-09-12 | Overhead | R16 | 2019-08-28 | 1 | 2 | 84 | 12 | 96 | 2019 | 2019 | R16
163376174137 | 164463174137 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-03 | 2019-10-03 | 2019-12-11 |  | 2021-02-17 | Underground | R16 | 2020-10-19 | 1 | 50 | 224 | 88 | 360 | 2019 | 2021 | R16
161296210858 | 165392210858 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-17 | 2020-11-17 | 2020-11-17 | 2021-03-23 | 2021-11-05 | Overhead | R16 | 2021-03-23 | 1 |  | 91 | 164 | 254 | 2020 | 2021 | R16
163421175469 | 166251175469 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-10 | 2019-10-10 | 2020-01-02 |  | 2020-06-09 | Underground | R16 | 2020-03-19 | 1 | 61 | 56 | 59 | 174 | 2019 | 2020 | R16
163299230566 | 164697230566 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-31 | 2021-04-09 | 2021-05-13 | 2021-06-24 | 2021-06-25 | Underground | R16 | 2021-06-24 | 8 | 25 | 31 | 2 | 63 | 2021 | 2021 | R16
163445168781 | 167730168781 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-18 | 2019-10-18 | 2019-10-18 |  | 2021-11-10 | Overhead | R16 | 2020-01-24 | 1 |  | 71 | 469 | 539 | 2019 | 2021 | R16
161090167500 | 165548167500 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-25 | 2019-04-25 | 2019-10-08 | 2020-01-10 | 2021-11-13 | Underground | R16 | 2020-01-10 | 1 | 119 | 69 | 481 | 667 | 2019 | 2021 | R16
165206211122 | 165525211122 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-18 | 2020-11-18 | 2020-11-18 |  | 2021-04-21 | Overhead | R16 | 2021-01-21 | 1 |  | 47 | 65 | 111 | 2020 | 2021 | R16
163471167308 | 165191167308 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-07 | 2019-10-07 | 2019-10-07 |  | 2020-06-09 | Overhead | R16 | 2019-12-18 | 1 |  | 53 | 125 | 177 | 2019 | 2020 | R16
163474167376 | 165417167376 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-08 | 2019-10-08 | 2019-10-08 |  | 2019-11-26 | Overhead | R16 | 2019-11-19 | 1 |  | 31 | 6 | 36 | 2019 | 2019 | R16
166164197615 | 168643197615 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-16 | 2020-07-16 | 2020-07-16 |  | 2020-10-06 | Overhead | R16 | 2020-08-04 | 1 |  | 14 | 46 | 59 | 2020 | 2020 | R16
168368201385 | 164643201385 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-18 | 2020-08-20 | 2020-08-20 | 2021-01-27 | 2021-04-23 | Overhead | R16 | 2021-01-27 | 3 |  | 115 | 63 | 179 | 2020 | 2021 | R16
162656204128 | 160479204128 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-11 | 2020-09-16 | 2020-09-16 | 2020-10-09 | 2021-02-17 | Overhead | R16 | 2020-10-09 | 4 |  | 18 | 94 | 114 | 2020 | 2021 | R16
167226203535 | 168340203535 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-02 | 2020-09-11 | 2020-09-11 | 2020-09-24 | 2020-12-29 | Overhead | R16 | 2020-09-24 | 8 |  | 10 | 69 | 85 | 2020 | 2020 | R16
164163227476 | 164474227476 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-03-30 | 2021-04-09 | 2021-04-20 | 2021-06-29 | 2021-07-20 | Underground | R16 | 2021-06-29 | 9 | 8 | 51 | 16 | 81 | 2021 | 2021 | R16
163560186707 | 160468186707 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-04-07 | 2020-04-07 | 2020-04-07 |  | 2020-06-16 | Overhead | R16 | 2020-04-13 | 1 |  | 5 | 47 | 51 | 2020 | 2020 | R16
162383210540 | 162232210540 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-03 | 2020-11-03 | 2020-11-12 | 2021-01-19 | 2021-01-20 | Underground | R16 | 2021-01-19 | 1 | 8 | 49 | 2 | 57 | 2020 | 2021 | R16
160806203653 | 161805203653 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-04 | 2020-08-10 | 2020-09-14 |  | 2020-12-29 | Overhead | R16 |  | 5 | 26 |  |  | 106 | 2020 | 2020 | R16
169267243612 | 161280243612 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-09-16 | 2021-06-04 | 2021-08-13 | 2022-08-05 | 2022-08-26 | Overhead | R16 | 2022-08-05 | 188 | 51 | 256 | 16 | 508 | 2020 | 2022 | R16
166013227022 | 169118227022 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-07 | 2020-12-07 | 2021-04-15 |  | 2021-11-05 | Overhead | R16 | 2021-05-03 | 1 | 94 | 13 | 135 | 240 | 2020 | 2021 | R16
166935216980 | 165634216980 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-01-07 | 2021-01-07 | 2021-01-12 |  | 2021-04-29 | Overhead | R16 |  | 1 | 4 |  |  | 81 | 2021 | 2021 | R16
168755239380 | 164304239380 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH CP R16 WORK RELO TO UG | Commercial | 2021-02-16 | 2021-02-16 | 2021-07-16 | 2021-12-10 | 2022-01-05 | Overhead | R16 | 2021-12-10 | 1 | 109 | 106 | 19 | 232 | 2021 | 2022 | R16
163724169847 | 169497169847 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-28 | 2019-10-28 | 2019-10-28 |  | 2021-12-17 | Overhead | R16 | 2019-12-05 | 1 |  | 29 | 532 | 560 | 2019 | 2021 | R16
168665217298 | 167204217298 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-14 | 2021-01-14 | 2021-01-14 | 2021-02-17 | 2021-02-18 | Overhead | R16 | 2021-02-17 | 1 |  | 25 | 2 | 26 | 2021 | 2021 | R16
163729170789 | 163827170789 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-30 | 2019-09-30 | 2019-11-06 |  | 2020-08-28 | Underground | R16 | 2020-06-30 | 1 | 28 | 170 | 44 | 240 | 2019 | 2020 | R16
164475223116 | 169725223116 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-10 | 2021-03-10 | 2021-03-10 | 2021-03-31 | 2021-08-23 | Overhead | R16 | 2021-03-31 | 1 |  | 16 | 104 | 119 | 2021 | 2021 | R16
163735169492 | 168724169492 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-23 | 2019-10-23 | 2019-10-24 |  | 2020-06-09 | Overhead | R16 | 2020-03-27 | 1 | 2 | 112 | 53 | 165 | 2019 | 2020 | R16
161240218312 | 169060218312 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2021-01-22 | 2021-01-22 | 2021-01-25 | 2023-02-23 | 2023-07-25 | Overhead | R16 | 2023-02-23 | 1 | 2 | 544 | 109 | 653 | 2021 | 2023 | R16
163708229558 | 161540229558 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-02-01 | 2021-02-17 | 2021-05-05 |  | 2021-11-04 | Overhead | R16 |  | 13 | 56 |  |  | 199 | 2021 | 2021 | R16
166375198783 | 160564198783 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-28 | 2020-07-28 | 2020-07-28 |  | 2020-10-06 | Underground | R16 | 2020-08-17 | 1 |  | 15 | 37 | 51 | 2020 | 2020 | R16
166558217410 | 164763217410 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-05 | 2021-01-14 | 2021-01-14 | 2021-03-18 | 2021-11-08 | Overhead | R16 | 2021-03-18 | 8 |  | 46 | 168 | 220 | 2021 | 2021 | R16
163784170162 | 166625170162 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-12 | 2019-10-12 | 2019-10-30 |  | 2020-01-02 | Underground | R16 | 2019-12-11 | 0 | 13 | 31 | 17 | 59 | 2019 | 2020 | R16
162827220227 | 165422220227 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-10-02 | 2020-10-02 | 2021-02-11 | 2021-03-09 | 2021-05-06 | Underground | R16 | 2021-03-09 | 1 | 95 | 19 | 43 | 155 | 2020 | 2021 | R16
163909178211 | 160568178211 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-31 | 2019-10-31 | 2020-01-27 |  | 2020-07-02 | Overhead | R16 | 2020-05-06 | 1 | 63 | 73 | 42 | 176 | 2019 | 2020 | R16
160845222941 | 168808222941 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-07 | 2021-03-07 | 2021-03-09 | 2021-07-22 | 2021-08-23 | Overhead | R16 | 2021-07-22 | 0 | 2 | 98 | 23 | 121 | 2021 | 2021 | R16
161177164193 | 161374164193 | NON-RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Commercial | 2019-02-05 | 2019-02-05 | 2019-09-12 | 2020-05-11 | 2020-09-30 | Underground | R16 | 2020-05-11 | 1 | 158 | 173 | 103 | 432 | 2019 | 2020 | R16
163991170808 | 161430170808 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-05 | 2019-11-05 | 2019-11-05 |  | 2022-02-02 | Overhead | R16 | 2021-12-15 | 1 |  | 552 | 36 | 587 | 2019 | 2022 | R16
164006169401 | 168393169401 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-22 | 2019-10-23 | 2019-10-23 |  | 2020-07-09 | Overhead | R16 | 2020-06-09 | 2 |  | 165 | 23 | 188 | 2019 | 2020 | R16
162213233826 | 161116233826 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-02 | 2021-06-07 | 2021-06-07 |  | 2021-08-23 | Overhead | R16 | 2021-08-23 | 4 |  | 56 |  | 59 | 2021 | 2021 | R16
162065208904 | 160923208904 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-10-28 | 2020-10-28 | 2020-10-28 |  | 2021-09-14 | Overhead | R16 | 2021-08-20 | 1 |  | 213 | 18 | 230 | 2020 | 2021 | R16
164079167683 | 166165167683 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-10 | 2019-10-10 | 2019-10-10 |  | 2020-06-09 | Overhead | R16 | 2020-02-21 | 1 |  | 97 | 78 | 174 | 2019 | 2020 | R16
167925151369 | 167952151369 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-01-18 | 2019-05-06 | 2019-05-06 |  | 2020-04-29 | Underground | R16 |  | 77 |  |  |  | 334 | 2019 | 2020 | R16
164087169006 | 165125169006 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-07 | 2019-10-07 | 2019-10-21 |  | 2019-12-18 | Underground | R16 | 2019-12-09 | 1 | 11 | 36 | 8 | 53 | 2019 | 2019 | R16
162808205775 | 162856205775 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-24 | 2020-09-24 | 2020-09-30 |  | 2022-02-07 | Underground | R16 | 2022-01-10 | 1 | 5 | 334 | 21 | 358 | 2020 | 2022 | R16
162607209766 | 163031209766 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-05 | 2020-11-05 | 2020-11-05 | 2021-02-23 | 2023-06-10 | Overhead | R16 | 2021-02-23 | 1 |  | 79 | 599 | 677 | 2020 | 2023 | R16
164105176695 | 162955176695 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-01-13 | 2020-01-13 | 2020-01-13 |  | 2020-10-06 | Underground | R16 | 2020-08-27 | 1 |  | 164 | 29 | 192 | 2020 | 2020 | R16
162300220813 | 165161220813 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-02-18 | 2021-02-18 | 2021-02-18 |  | 2021-11-05 | Underground | R16 | 2021-05-19 | 1 |  | 65 | 123 | 187 | 2021 | 2021 | R16
166372203333 | 169878203333 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-10 | 2020-09-10 | 2020-09-10 | 2021-07-27 | 2021-11-08 | Overhead | R16 | 2021-07-27 | 1 |  | 229 | 75 | 303 | 2020 | 2021 | R16
163076208503 | 160089208503 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-10-23 | 2020-10-26 | 2020-10-26 | 2021-03-02 | 2021-06-17 | Overhead | R16 | 2021-03-02 | 2 |  | 92 | 78 | 170 | 2020 | 2021 | R16
164201169948 | 169503169948 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-28 | 2019-10-28 | 2019-10-28 |  | 2022-12-13 | Overhead | R16 | 2019-12-09 | 1 |  | 31 | 787 | 817 | 2019 | 2022 | R16
163757228941 | 161734228941 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-05-20 | 2021-11-03 | Overhead | R16 | 2021-05-20 | 1 |  | 15 | 120 | 134 | 2021 | 2021 | R16
164203167701 | 166201167701 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-10 | 2019-10-10 | 2019-10-10 |  | 2019-12-12 | Overhead | R16 | 2019-12-02 | 1 |  | 38 | 9 | 46 | 2019 | 2019 | R16
169535218109 | 168868218109 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-22 | 2021-01-22 | 2021-01-22 | 2021-03-23 | 2021-08-09 | Overhead | R16 | 2021-03-23 | 1 |  | 43 | 100 | 142 | 2021 | 2021 | R16
162274217223 | 163397217223 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-06 | 2020-11-18 | 2021-01-14 | 2023-09-20 | 2023-10-02 | Underground | R16 | 2023-09-20 | 9 | 42 | 700 | 9 | 757 | 2020 | 2023 | R16
165379222553 | 166417222553 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-02-24 | 2021-02-24 | 2021-03-05 | 2021-05-30 | 2023-09-15 | Overhead | R16 | 2021-05-30 | 1 | 8 | 61 | 600 | 668 | 2021 | 2023 | R16
161107254504 | 166087254504 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-05-18 | 2021-06-03 | 2021-11-01 |  | 2022-05-09 | Overhead | R16 | 2022-04-14 | 13 | 108 | 119 | 18 | 255 | 2021 | 2022 | R16
164277170971 | 161770170971 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-07 | 2019-11-07 | 2019-11-07 |  | 2020-06-09 | Overhead | R16 | 2020-03-27 | 1 |  | 102 | 53 | 154 | 2019 | 2020 | R16
160558231329 | 164711231329 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-05 | 2021-01-05 | 2021-05-18 |  | 2022-01-24 | Underground | R16 | 2021-12-28 | 1 | 96 | 161 | 20 | 275 | 2021 | 2022 | R16
163472209466 | 161997209466 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-02 | 2020-11-03 | 2020-11-03 |  | 2021-08-10 | Overhead | R16 | 2021-03-19 | 2 |  | 99 | 103 | 202 | 2020 | 2021 | R16
164366183524 | 164861183524 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-03-09 | 2020-03-09 | 2020-03-09 |  | 2020-07-10 | Overhead | R16 | 2020-06-11 | 1 |  | 69 | 22 | 90 | 2020 | 2020 | R16
167712226976 | 163311226976 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-25 | 2021-04-16 | 2021-04-16 | 2021-06-30 | 2021-08-12 | Overhead | R16 | 2021-06-30 | 17 |  | 54 | 32 | 101 | 2021 | 2021 | R16
168031250344 | 160326250344 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG R16 RESD AND NON RESD UD | Residential | 2021-04-26 | 2021-08-05 | 2021-10-01 | 2021-11-18 | 2021-12-08 | Underground | R16 | 2021-11-18 | 74 | 42 | 35 | 15 | 163 | 2021 | 2021 | R16
164385169590 | 169340169590 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-25 | 2019-10-25 | 2019-10-25 |  | 2021-12-16 | Overhead | R16 | 2019-11-25 | 1 |  | 22 | 539 | 560 | 2019 | 2021 | R16
164387192220 | 168075192220 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-05-20 | 2020-05-20 | 2020-05-26 |  | 2020-07-09 | Underground | R16 | 2020-06-28 | 1 | 5 | 24 | 9 | 37 | 2020 | 2020 | R16
163474222067 | 167370222067 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2021-01-15 | 2021-01-21 | 2021-03-01 | 2021-04-30 | 2021-06-02 | Underground | R16 | 2021-04-30 | 5 | 28 | 45 | 24 | 99 | 2021 | 2021 | R16
164433170941 | 161523170941 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-06 | 2019-11-06 | 2019-11-06 |  | 2021-11-10 | Overhead | R16 | 2020-01-22 | 1 |  | 56 | 471 | 526 | 2019 | 2021 | R16
162342213922 | 160551213922 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-14 | 2020-12-14 | 2020-12-14 | 2021-02-17 | 2021-02-19 | Overhead | R16 | 2021-02-17 | 1 |  | 48 | 3 | 50 | 2020 | 2021 | R16
164498214425 | 163884214425 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Commercial | 2020-11-10 | 2020-11-10 | 2020-12-18 |  | 2021-11-08 | Underground | R16 |  | 1 | 29 |  |  | 260 | 2020 | 2021 | R16
167680287820 | 166355287820 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-11-20 | 2020-11-20 | 2022-08-03 | 2022-12-06 | 2023-01-17 | Underground | R16 | 2022-12-06 | 1 | 444 | 90 | 31 | 563 | 2020 | 2023 | R16
161088143004 | 162824143004 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-11 | 2019-02-11 | 2019-02-11 | 2019-02-12 | 2019-04-15 | Overhead | R16 | 2019-02-12 | 1 |  | 2 | 45 | 46 | 2019 | 2019 | R16
168030209685 | 161316209685 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-16 | 2020-09-16 | 2020-11-04 |  | 2021-11-05 | Underground | R16 | 2021-04-09 | 1 | 36 | 113 | 151 | 298 | 2020 | 2021 | R16
164686185070 | 167562185070 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-23 | 2020-03-23 | 2020-03-23 |  | 2020-09-16 | Overhead | R16 | 2020-07-08 | 1 |  | 78 | 51 | 128 | 2020 | 2020 | R16
165988223949 | 168858223949 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-01-22 | 2021-01-22 | 2021-03-18 | 2021-05-24 | 2021-11-11 | Underground | R16 | 2021-05-24 | 1 | 40 | 48 | 124 | 210 | 2021 | 2021 | R16
168344198998 | 161040198998 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-07-30 | 2020-07-30 | 2020-07-30 | 2021-04-09 | 2021-04-12 | Overhead | R16 | 2021-04-09 | 1 |  | 182 | 2 | 183 | 2020 | 2021 | R16
164751178579 | 166491178579 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-29 | 2020-01-29 | 2020-01-29 |  | 2021-04-15 | Overhead | R16 | 2020-12-28 | 1 |  | 239 | 79 | 317 | 2020 | 2021 | R16
161952225340 | 164523225340 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-30 | 2021-03-30 | 2021-03-30 |  | 2021-11-09 | Overhead | R16 | 2021-04-28 | 1 |  | 22 | 140 | 161 | 2021 | 2021 | R16
167074205709 | 164425205709 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-29 | 2020-09-30 | 2020-09-30 |  | 2021-02-17 | Overhead | R16 | 2020-10-20 | 2 |  | 15 | 87 | 102 | 2020 | 2021 | R16
164888192442 | 169029192442 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2020-05-27 | 2020-05-27 | 2020-05-27 |  | 2020-12-29 | Overhead | R16 | 2020-09-29 | 1 |  | 90 | 66 | 155 | 2020 | 2020 | R16
162453148504 | 162304148504 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-08 | 2019-04-08 | 2019-04-08 | 2019-07-15 | 2019-07-17 | Underground | R16 | 2019-07-15 | 1 |  | 71 | 3 | 73 | 2019 | 2019 | R16
164889172946 | 165215172946 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2019-11-26 | 2019-11-26 | 2019-11-26 |  | 2021-11-10 | Overhead | R16 | 2020-05-11 | 1 |  | 120 | 393 | 512 | 2019 | 2021 | R16
162400227059 | 168394227059 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-15 | 2021-04-15 | 2021-04-15 | 2023-04-24 | 2023-06-12 | Overhead | R16 | 2023-04-24 | 1 |  | 528 | 36 | 563 | 2021 | 2023 | R16
164901169669 | 165456169669 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-08 | 2019-10-08 | 2019-10-25 |  | 2020-06-09 | Underground | R16 | 2020-02-25 | 1 | 14 | 88 | 76 | 176 | 2019 | 2020 | R16
166839208695 | 160852208695 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-27 | 2020-10-27 | 2020-10-27 |  | 2021-07-16 | Underground | R16 | 2020-11-18 | 1 |  | 17 | 173 | 189 | 2020 | 2021 | R16
164912207298 | 163611207298 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2020-03-02 | 2020-06-09 | 2020-10-16 |  | 2021-04-23 | Overhead | R16 |  | 72 | 94 |  |  | 300 | 2020 | 2021 | R16
164917169910 | 169636169910 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-28 | 2019-10-28 | 2019-10-28 |  | 2020-06-09 | Overhead | R16 | 2020-02-03 | 1 |  | 71 | 92 | 162 | 2019 | 2020 | R16
166469160308 | 166698160308 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-01 | 2019-05-01 | 2019-08-06 | 2019-08-27 | 2019-09-04 | Underground | R16 | 2019-08-27 | 1 | 70 | 16 | 7 | 91 | 2019 | 2019 | R16
164920173852 | 166613173852 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2019-12-09 | 2019-12-09 | 2019-12-09 |  | 2022-08-29 | Overhead | R16 | 2022-08-26 | 1 |  | 710 | 2 | 711 | 2019 | 2022 | R16
163067271744 | 160440271744 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2021-04-26 | 2021-05-20 | 2022-03-07 | 2023-05-23 | 2023-08-03 | Underground | R16 | 2023-05-23 | 19 | 208 | 317 | 53 | 594 | 2021 | 2023 | R16
160077164749 | 160138164749 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-27 | 2019-03-27 | 2019-09-17 | 2019-10-01 | 2019-10-01 | Underground | R16 | 2019-10-01 | 1 | 125 | 11 |  | 135 | 2019 | 2019 | R16
160978219610 | 162252219610 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-04 | 2021-02-04 | 2021-02-04 |  | 2021-08-11 | Overhead | R16 | 2021-03-22 | 1 |  | 33 | 103 | 135 | 2021 | 2021 | R16
164937174384 | 168480174384 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-16 | 2019-12-16 | 2019-12-16 |  | 2020-06-09 | Overhead | R16 | 2020-01-28 | 1 |  | 32 | 96 | 127 | 2019 | 2020 | R16
161899214338 | 167505214338 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-30 | 2020-12-18 | 2020-12-18 |  | 2023-05-03 | Overhead | R16 | 2023-02-08 | 15 |  | 559 | 61 | 633 | 2020 | 2023 | R16
164939172693 | 164737172693 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-11-22 | 2019-11-22 | 2019-11-22 |  | 2019-12-19 | Overhead | R16 | 2019-12-10 | 1 |  | 13 | 8 | 20 | 2019 | 2019 | R16
161501210449 | 164605210449 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-12 | 2020-11-12 | 2020-11-12 | 2021-01-11 | 2021-05-06 | Overhead | R16 | 2021-01-11 | 1 |  | 43 | 84 | 126 | 2020 | 2021 | R16
165139168698 | 167331168698 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-16 | 2019-10-18 | 2019-10-18 |  | 2019-12-18 | Overhead | R16 | 2019-12-09 | 3 |  | 37 | 8 | 46 | 2019 | 2019 | R16
167759228465 | 160635228465 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-14 | 2020-12-14 | 2021-04-26 | 2021-06-25 | 2021-06-29 | Underground | R16 | 2021-06-25 | 1 | 96 | 45 | 3 | 142 | 2020 | 2021 | R16
168759209232 | 162234209232 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-03 | 2020-11-03 | 2020-11-03 |  | 2021-04-15 | Underground | R16 | 2020-12-23 | 1 |  | 37 | 82 | 118 | 2020 | 2021 | R16
165338210012 | 163425210012 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-09 | 2020-11-09 | 2020-11-09 |  | 2021-04-21 | Underground | R16 | 2021-01-27 | 1 |  | 58 | 61 | 118 | 2020 | 2021 | R16
160768230095 | 164301230095 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-10 | 2021-05-10 | 2021-05-10 |  | 2021-08-23 | Overhead | R16 | 2021-07-14 | 1 |  | 48 | 29 | 76 | 2021 | 2021 | R16
169994201381 | 165141201381 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-19 | 2020-08-20 | 2020-08-20 | 2020-10-05 | 2021-01-20 | Overhead | R16 | 2020-10-05 | 2 |  | 33 | 78 | 111 | 2020 | 2021 | R16
168272211183 | 165116211183 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-16 | 2020-11-18 | 2020-11-18 |  | 2021-04-14 | Underground | R16 | 2020-12-14 | 3 |  | 19 | 88 | 108 | 2020 | 2021 | R16
168264228659 | 161361228659 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-29 | 2021-04-29 | 2021-04-29 | 2021-09-13 | 2021-10-25 | Overhead | R16 | 2021-09-13 | 1 |  | 98 | 31 | 128 | 2021 | 2021 | R16
168109206602 | 166424206602 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-07 | 2020-10-07 | 2020-10-07 | 2020-10-28 | 2021-04-15 | Overhead | R16 | 2020-10-28 | 1 |  | 16 | 122 | 137 | 2020 | 2021 | R16
165881240671 | 167417240671 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-10-12 | 2021-02-01 | 2021-07-26 |  | 2021-12-02 | Overhead | R16 |  | 81 | 126 |  |  | 299 | 2020 | 2021 | R16
166617224505 | 162693224505 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-23 | 2021-03-23 | 2021-03-23 | 2021-05-03 | 2021-11-05 | Overhead | R16 | 2021-05-03 | 1 |  | 30 | 135 | 164 | 2021 | 2021 | R16
165299169907 | 169631169907 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-28 | 2019-10-28 | 2019-10-28 |  | 2021-11-03 | Overhead | R16 | 2020-01-09 | 1 |  | 54 | 475 | 528 | 2019 | 2021 | R16
166483225889 | 160790225889 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-15 | 2021-03-31 | 2021-04-06 | 2021-05-11 | 2021-11-08 | Overhead | R16 | 2021-05-11 | 13 | 5 | 26 | 130 | 171 | 2021 | 2021 | R16
166268228447 | 162226228447 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2020-09-21 | 2021-02-03 | 2021-04-26 |  | 2022-04-21 | Overhead | R16 |  | 98 | 59 |  |  | 414 | 2020 | 2022 | R16
169411221445 | 161367221445 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-02-01 | 2021-02-04 | 2021-02-23 | 2021-06-04 | 2021-06-08 | Underground | R16 | 2021-06-04 | 4 | 14 | 74 | 3 | 92 | 2021 | 2021 | R16
161579221122 | 164450221122 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-16 | 2021-02-16 | 2021-02-19 | 2021-08-26 | 2021-10-25 | Underground | R16 | 2021-08-26 | 1 | 4 | 135 | 43 | 180 | 2021 | 2021 | R16
166471220293 | 162778220293 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-08 | 2021-02-11 | 2021-02-11 | 2021-03-03 | 2021-08-16 | Underground | R16 | 2021-03-03 | 4 |  | 15 | 119 | 136 | 2021 | 2021 | R16
167043157716 | 166541157716 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-05-01 | 2019-05-06 | 2019-07-12 | 2019-08-27 | 2019-09-03 | Overhead | R16 | 2019-08-27 | 4 | 50 | 33 | 6 | 90 | 2019 | 2019 | R16
167371254202 | 161033254202 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-04-28 | 2021-10-28 | 2021-10-28 | 2022-05-05 | 2022-05-06 | Overhead | R16 | 2022-05-05 | 132 |  | 136 | 2 | 268 | 2021 | 2022 | R16
161302263335 | 161729263335 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2021-04-30 | 2021-04-30 | 2022-01-04 | 2022-06-01 | 2022-06-27 | Underground | R16 | 2022-06-01 | 1 | 178 | 107 | 19 | 302 | 2021 | 2022 | R16
168692144852 | 166280144852 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-04 | 2019-03-04 | 2019-03-04 | 2019-05-07 | 2019-05-08 | Overhead | R16 | 2019-05-07 | 1 |  | 47 | 2 | 48 | 2019 | 2019 | R16
161598209144 | 161511209144 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-29 | 2020-10-29 | 2020-10-29 |  | 2021-07-19 | Overhead | R16 | 2020-11-16 | 1 |  | 13 | 176 | 188 | 2020 | 2021 | R16
165555168353 | 167326168353 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-16 | 2019-10-16 | 2019-10-16 |  | 2020-06-09 | Overhead | R16 | 2020-01-16 | 1 |  | 67 | 104 | 170 | 2019 | 2020 | R16
169717227570 | 168753227570 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-04-17 | 2021-04-17 | 2021-04-19 |  | 2021-10-11 | Overhead | R16 | 2021-09-01 | 0 | 1 | 98 | 29 | 126 | 2021 | 2021 | R16
160848214086 | 160918214086 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-15 | 2020-12-15 | 2020-12-15 |  | 2021-04-21 | Overhead | R16 | 2021-01-25 | 1 |  | 30 | 63 | 92 | 2020 | 2021 | R16
164097221827 | 161082221827 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-31 | 2021-02-26 | 2021-02-26 | 2021-04-20 | 2021-11-08 | Overhead | R16 | 2021-04-20 | 20 |  | 38 | 145 | 201 | 2021 | 2021 | R16
165722193658 | 168040193658 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2020-02-05 | 2020-05-14 | 2020-06-09 |  | 2021-06-02 | Overhead | R16 |  | 72 | 19 |  |  | 346 | 2020 | 2021 | R16
163403218374 | 169588218374 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-26 | 2021-01-26 | 2021-01-26 |  | 2021-08-06 | Overhead | R16 | 2021-03-24 | 1 |  | 42 | 98 | 139 | 2021 | 2021 | R16
163525215320 | 162690215320 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2020-12-28 | 2021-05-07 | Overhead | R16 | 2020-12-28 | 1 |  | 6 | 95 | 100 | 2020 | 2021 | R16
166941152620 | 169050152620 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH CP R16 WORK RELO TO UG | Commercial | 2019-01-25 | 2019-01-31 | 2019-05-16 | 2019-10-08 | 2020-02-20 | Overhead | R16 | 2019-10-08 | 5 | 76 | 104 | 98 | 280 | 2019 | 2020 | R16
166941152620 | 169050152620 | AGRICULTURAL | UG R16 RESD AND NON RESD UD | Commercial | 2019-01-25 | 2019-01-31 | 2019-05-16 | 2019-10-08 | 2020-02-20 | Underground | R16 | 2019-10-08 | 5 | 76 | 104 | 98 | 280 | 2019 | 2020 | R16
169742222229 | 165466222229 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-21 | 2021-03-02 | 2021-03-02 | 2021-05-14 | 2021-08-26 | Overhead | R16 | 2021-05-14 | 7 |  | 54 | 75 | 134 | 2021 | 2021 | R16
165859170061 | 169887170061 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-10-29 | 2019-10-29 | 2019-10-29 |  | 2022-07-07 | Underground | R16 |  | 1 |  |  |  | 703 | 2019 | 2022 | R16
161738209204 | 161187209204 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-29 | 2020-10-30 | 2020-10-30 |  | 2021-11-08 | Underground | R16 | 2021-04-22 | 2 |  | 125 | 143 | 268 | 2020 | 2021 | R16
162728225166 | 160978225166 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-28 | 2020-10-28 | 2021-03-30 | 2022-01-24 | 2022-02-28 | Underground | R16 | 2022-01-24 | 1 | 110 | 215 | 26 | 349 | 2020 | 2022 | R16
165903172765 | 164793172765 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-22 | 2019-11-22 | 2019-11-22 |  | 2020-01-08 | Overhead | R16 | 2020-01-02 | 1 |  | 30 | 5 | 34 | 2019 | 2020 | R16
165234221664 | 169605221664 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-26 | 2021-02-25 | 2021-02-25 | 2021-03-11 | 2021-11-09 | Overhead | R16 | 2021-03-11 | 23 |  | 11 | 174 | 206 | 2021 | 2021 | R16
165916169079 | 168324169079 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-22 | 2019-10-22 | 2019-10-22 |  | 2021-11-13 | Overhead | R16 | 2020-01-07 | 1 |  | 56 | 484 | 539 | 2019 | 2021 | R16
166834210136 | 162769210136 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-04 | 2020-11-10 | 2020-11-10 |  | 2021-04-15 | Underground | R16 | 2020-12-22 | 5 |  | 31 | 83 | 117 | 2020 | 2021 | R16
160254224713 | 163404224713 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-25 | 2021-03-25 | 2021-03-25 | 2022-01-30 | 2022-02-02 | Overhead | R16 | 2022-01-30 | 1 |  | 222 | 3 | 225 | 2021 | 2022 | R16
166073169881 | 169531169881 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-28 | 2019-10-28 | 2019-10-28 |  | 2020-06-09 | Overhead | R16 | 2020-02-10 | 1 |  | 76 | 87 | 162 | 2019 | 2020 | R16
166090169337 | 165893169337 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-09 | 2019-10-09 | 2019-10-24 |  | 2022-12-30 | Underground | R16 |  | 1 | 12 |  |  | 843 | 2019 | 2022 | R16
168099216767 | 165774216767 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-11 | 2021-01-11 | 2021-01-11 | 2021-03-27 | 2022-08-03 | Overhead | R16 | 2021-03-27 | 1 |  | 55 | 353 | 408 | 2021 | 2022 | R16
166098170362 | 166111170362 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-09 | 2019-10-09 | 2019-10-31 |  | 2020-12-15 | Underground | R16 | 2020-09-11 | 1 | 17 | 227 | 68 | 310 | 2019 | 2020 | R16
167513156701 | 168738156701 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential Subdivision | 2019-01-24 | 2019-02-05 | 2019-06-28 | 2020-01-29 | 2020-04-11 | Underground | R16 | 2020-01-29 | 9 | 104 | 154 | 53 | 317 | 2019 | 2020 | R16
167725206435 | 166401206435 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-07 | 2020-10-07 | 2020-10-07 |  | 2021-07-22 | Underground | R16 | 2020-11-10 | 1 |  | 25 | 183 | 207 | 2020 | 2021 | R16
161619238831 | 160917238831 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-01 | 2021-06-01 | 2021-07-14 |  | 2022-03-07 | Overhead | R16 |  | 1 | 32 |  |  | 200 | 2021 | 2022 | R16
166144174294 | 168004174294 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-12-12 | 2019-12-12 | 2019-12-12 |  | 2023-06-07 | Overhead | R16 |  | 1 |  |  |  | 910 | 2019 | 2023 | R16
166742222188 | 167658222188 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-02 | 2021-03-02 | 2021-03-02 |  | 2021-06-03 | Overhead | R16 | 2021-03-12 | 1 |  | 9 | 60 | 68 | 2021 | 2021 | R16
162528145787 | 167590145787 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-11 | 2019-03-11 | 2019-03-11 | 2019-03-22 | 2019-03-28 | Underground | R16 | 2019-03-22 | 1 |  | 10 | 5 | 14 | 2019 | 2019 | R16
166164170839 | 166476170839 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-11 | 2019-10-11 | 2019-11-07 |  | 2021-12-16 | Underground | R16 | 2020-01-09 | 1 | 20 | 46 | 506 | 570 | 2019 | 2021 | R16
166220181822 | 161443181822 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-11-06 | 2019-12-12 | 2020-02-24 |  | 2020-07-08 | Overhead | R16 |  | 27 | 53 |  |  | 176 | 2019 | 2020 | R16
166639148603 | 167478148603 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-11 | 2019-03-11 | 2019-04-08 | 2019-05-22 | 2019-05-22 | Underground | R16 | 2019-05-22 | 1 | 21 | 33 |  | 53 | 2019 | 2019 | R16
162996208344 | 163010208344 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-11 | 2020-08-11 | 2020-10-26 |  | 2021-04-16 | Underground | R16 | 2021-01-05 | 1 | 55 | 52 | 74 | 179 | 2020 | 2021 | R16
161834146581 | 168950146581 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-19 | 2019-03-19 | 2019-03-19 | 2019-04-08 | 2019-04-08 | Overhead | R16 | 2019-04-08 | 1 |  | 15 |  | 15 | 2019 | 2019 | R16
164592228400 | 165581228400 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-18 | 2020-11-18 | 2021-04-26 |  | 2021-11-03 | Underground | R16 | 2021-06-22 | 1 | 114 | 42 | 97 | 251 | 2020 | 2021 | R16
166255178197 | 166008178197 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-27 | 2020-01-29 | 2020-01-29 |  | 2020-06-09 | Overhead | R16 | 2020-02-18 | 3 |  | 15 | 81 | 97 | 2020 | 2020 | R16
162906257177 | 165925257177 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-06 | 2020-10-06 | 2021-11-18 |  | 2022-10-21 | Underground | R16 |  | 1 | 293 |  |  | 534 | 2020 | 2022 | R16
160183213052 | 169200213052 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-07 | 2020-12-07 | 2020-12-07 | 2021-06-07 | 2021-08-12 | Underground | R16 | 2021-06-07 | 1 |  | 131 | 49 | 179 | 2020 | 2021 | R16
166462170782 | 166922170782 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-14 | 2019-10-14 | 2019-11-05 |  | 2021-11-13 | Underground | R16 | 2020-01-07 | 1 | 17 | 46 | 484 | 545 | 2019 | 2021 | R16
160256230313 | 163088230313 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-24 | 2021-05-11 | 2021-05-11 |  | 2021-09-10 | Underground | R16 | 2021-08-16 | 35 |  | 70 | 20 | 123 | 2021 | 2021 | R16
166483168412 | 167415168412 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-17 | 2019-10-17 | 2019-10-17 |  | 2020-06-09 | Overhead | R16 | 2020-02-18 | 1 |  | 89 | 81 | 169 | 2019 | 2020 | R16
163045145887 | 167685145887 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-03-12 | 2019-03-12 | 2019-03-12 | 2019-03-18 | 2019-04-15 | Overhead | R16 | 2019-03-18 | 1 |  | 5 | 21 | 25 | 2019 | 2019 | R16
163229210669 | 164739210669 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-13 | 2020-11-13 | 2020-11-13 |  | 2022-07-17 | Overhead | R16 | 2022-07-07 | 1 |  | 430 | 7 | 436 | 2020 | 2022 | R16
164504221990 | 167258221990 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-01 | 2021-03-01 | 2021-03-01 | 2021-05-21 | 2021-05-24 | Overhead | R16 | 2021-05-21 | 1 |  | 60 | 2 | 61 | 2021 | 2021 | R16
167900297946 | 169663297946 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-07-22 | 2020-08-07 | 2022-10-24 |  | 2023-07-25 | Underground | R16 |  | 13 | 577 |  |  | 785 | 2020 | 2023 | R16
169914276928 | 164691276928 | CUSTOMER UPGRADE IN SERVICE | UG SVC CONVERSION | Residential | 2021-05-11 | 2021-06-20 | 2022-04-25 |  | 2022-10-21 | Underground | R16 | 2022-08-19 | 29 | 221 | 85 | 46 | 379 | 2021 | 2022 | R16
163659237067 | 167691237067 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-13 | 2021-04-13 | 2021-06-28 |  | 2021-10-27 | Underground | R16 | 2021-08-12 | 1 | 55 | 34 | 55 | 142 | 2021 | 2021 | R16
166586172120 | 169722172120 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-28 | 2019-10-28 | 2019-11-15 |  | 2021-12-17 | Underground | R16 | 2021-11-18 | 1 | 15 | 525 | 22 | 560 | 2019 | 2021 | R16
163350227040 | 168231227040 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-15 | 2021-04-15 | 2021-04-15 |  | 2021-12-17 | Overhead | R16 | 2021-11-17 | 1 |  | 155 | 23 | 177 | 2021 | 2021 | R16
165771202763 | 168950202763 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-20 | 2020-07-20 | 2020-09-03 | 2020-09-24 | 2021-01-08 | Underground | R16 | 2020-09-24 | 1 | 34 | 16 | 77 | 125 | 2020 | 2021 | R16
166853169949 | 169691169949 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-28 | 2019-10-28 | 2019-10-28 |  | 2021-07-23 | Overhead | R16 | 2020-11-04 | 1 |  | 268 | 188 | 455 | 2019 | 2021 | R16
162467213984 | 160579213984 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-14 | 2020-12-14 | 2020-12-14 | 2021-03-18 | 2021-03-19 | Overhead | R16 | 2021-03-18 | 1 |  | 69 | 2 | 70 | 2020 | 2021 | R16
166145222196 | 168905222196 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-22 | 2021-01-22 | 2021-03-02 |  | 2021-11-13 | Underground | R16 | 2021-04-26 | 1 | 28 | 40 | 145 | 211 | 2021 | 2021 | R16
169659204103 | 164042204103 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-08-15 | 2020-08-15 | 2020-09-16 | 2021-02-25 | 2021-06-02 | Underground | R16 | 2021-02-25 | 0 | 23 | 117 | 70 | 208 | 2020 | 2021 | R16
164845255068 | 169879255068 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2020-09-10 | 2020-09-17 | 2021-11-04 |  | 2023-06-19 | Underground | R16 |  | 6 | 296 |  |  | 723 | 2020 | 2023 | R16
165143205819 | 165291205819 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-01 | 2020-10-01 | 2020-10-01 | 2020-12-10 | 2021-11-09 | Overhead | R16 | 2020-12-10 | 1 |  | 51 | 239 | 289 | 2020 | 2021 | R16
165462198045 | 167505198045 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2019-05-06 | 2020-02-23 | 2020-07-22 | 2023-06-08 | 2023-08-16 | Underground | R16 | 2023-06-08 | 210 | 108 | 752 | 50 | 1118 | 2019 | 2023 | R16
166977172467 | 164253172467 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2019-11-20 | 2019-11-20 | 2019-11-20 |  | 2020-06-09 | Overhead | R16 | 2020-02-26 | 1 |  | 71 | 75 | 145 | 2019 | 2020 | R16
165867156497 | 165868156497 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-29 | 2019-04-29 | 2019-06-28 | 2019-07-22 | 2019-07-25 | Overhead | R16 | 2019-07-22 | 1 | 45 | 17 | 4 | 64 | 2019 | 2019 | R16
166790151159 | 167195151159 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-08-14 | 2019-08-21 | Underground | R16 | 2019-08-14 | 1 |  | 74 | 6 | 79 | 2019 | 2019 | R16
163163224825 | 166802224825 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-25 | 2021-03-25 | 2021-03-25 |  | 2021-11-08 | Overhead | R16 | 2021-05-21 | 21 |  | 42 | 122 | 183 | 2021 | 2021 | R16
167092170597 | 161204170597 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-05 | 2019-11-05 | 2019-11-05 |  | 2020-06-09 | Overhead | R16 | 2020-04-08 | 1 |  | 112 | 45 | 156 | 2019 | 2020 | R16
160318237540 | 160081237540 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-03-11 | 2021-06-08 | 2021-07-01 | 2021-09-27 | 2021-10-11 | Overhead | R16 | 2021-09-27 | 64 | 18 | 63 | 11 | 153 | 2021 | 2021 | R16
167128177053 | 163700177053 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-15 | 2020-01-15 | 2020-01-16 |  | 2021-02-17 | Underground | R16 | 2020-10-16 | 1 | 2 | 197 | 89 | 286 | 2020 | 2021 | R16
163221233376 | 166205233376 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-01-12 | 2021-01-13 | 2021-06-04 |  | 2022-09-20 | Underground | R16 |  | 2 | 103 |  |  | 441 | 2021 | 2022 | R16
167131178597 | 166791178597 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-01-30 | 2020-01-30 | 2020-01-31 |  | 2020-10-06 | Overhead | R16 | 2020-07-20 | 1 | 2 | 122 | 57 | 179 | 2020 | 2020 | R16
160628207398 | 168498207398 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-16 | 2020-10-16 | 2020-10-16 |  | 2021-07-19 | Overhead | R16 | 2020-11-16 | 1 |  | 22 | 176 | 197 | 2020 | 2021 | R16
167152179217 | 167550179217 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-02-03 | 2020-02-03 | 2020-02-03 |  | 2020-10-06 | Overhead | R16 | 2020-08-12 | 1 |  | 138 | 40 | 177 | 2020 | 2020 | R16
166326228440 | 160322228440 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-26 | 2021-04-26 | 2021-04-26 | 2021-09-15 | 2021-09-16 | Overhead | R16 | 2021-09-15 | 1 |  | 103 | 2 | 104 | 2021 | 2021 | R16
165287155515 | 165029155515 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OD | Commercial | 2019-04-23 | 2019-04-23 | 2019-06-17 | 2019-06-27 | 2019-12-31 | Overhead | R16 | 2019-06-27 | 1 | 40 | 9 | 134 | 181 | 2019 | 2019 | R16
167159170467 | 160786170467 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-01 | 2019-11-01 | 2019-11-01 |  | 2021-12-16 | Overhead | R16 | 2019-12-19 | 1 |  | 35 | 521 | 555 | 2019 | 2021 | R16
167845220571 | 161757220571 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-02-02 | 2021-02-02 | 2021-02-14 | 2021-07-18 | 2021-07-29 | Overhead | R16 | 2021-07-18 | 1 | 9 | 110 | 9 | 128 | 2021 | 2021 | R16
169635141705 | 168475141705 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-01-23 | 2019-01-23 | 2019-01-29 | 2019-02-06 | 2019-08-07 | Underground | R16 | 2019-02-06 | 1 | 5 | 7 | 131 | 141 | 2019 | 2019 | R16
167192168619 | 167749168619 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-10-18 | 2019-10-18 | 2019-10-18 |  | 2020-01-08 | Overhead | R16 | 2019-12-31 | 1 |  | 53 | 7 | 59 | 2019 | 2020 | R16
162860232233 | 163389232233 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2020-09-25 | 2020-12-23 | 2021-05-25 | 2022-06-05 | 2022-06-08 | Overhead | R16 | 2022-06-05 | 64 | 110 | 269 | 3 | 444 | 2020 | 2022 | R16
160636224981 | 162923224981 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-03-23 | 2021-03-26 | 2021-03-26 | 2021-05-13 | 2021-05-13 | Underground | R16 | 2021-05-13 | 4 |  | 35 |  | 38 | 2021 | 2021 | R16
167237183068 | 167127183068 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-12-10 | 2019-12-10 | 2020-03-05 |  | 2020-12-29 | Underground | R16 |  | 1 | 63 |  |  | 276 | 2019 | 2020 | R16
169361208042 | 168983208042 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-20 | 2020-10-22 | 2020-10-22 | 2020-10-28 | 2021-04-07 | Overhead | R16 | 2020-10-28 | 3 |  | 5 | 116 | 122 | 2020 | 2021 | R16
169463220817 | 160610220817 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-28 | 2021-01-28 | 2021-02-18 |  | 2021-11-04 | Underground | R16 | 2021-04-01 | 1 | 16 | 31 | 156 | 201 | 2021 | 2021 | R16
167248173232 | 165849173232 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-04 | 2019-12-04 | 2019-12-04 |  | 2020-06-09 | Overhead | R16 | 2020-02-07 | 1 |  | 48 | 88 | 135 | 2019 | 2020 | R16
164738176177 | 160732176177 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-29 | 2019-03-29 | 2020-01-08 | 2020-03-03 | 2020-06-09 | Underground | R16 | 2020-03-03 | 1 | 204 | 40 | 71 | 313 | 2019 | 2020 | R16
167015148130 | 166705148130 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-01-10 | 2019-01-14 | 2019-04-03 | 2019-06-21 | 2019-11-12 | Underground | R16 | 2019-06-21 | 3 | 58 | 58 | 103 | 219 | 2019 | 2019 | R16
167672162124 | 167634162124 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-07 | 2019-05-07 | 2019-08-23 | 2019-09-25 | 2019-09-27 | Underground | R16 | 2019-09-25 | 1 | 79 | 24 | 3 | 104 | 2019 | 2019 | R16
169296148777 | 167965148777 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-03-13 | 2019-03-15 | 2019-04-10 | 2019-04-16 | 2019-10-02 | Overhead | R16 | 2019-04-16 | 3 | 19 | 5 | 122 | 146 | 2019 | 2019 | R16
162713204941 | 162585204941 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-23 | 2020-09-23 | 2020-09-24 |  | 2021-07-26 | Overhead | R16 |  | 1 | 2 |  |  | 219 | 2020 | 2021 | R16
167424210108 | 162011210108 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-02 | 2020-11-02 | 2020-11-10 |  | 2021-07-26 | Overhead | R16 | 2020-11-19 | 1 | 7 | 8 | 178 | 191 | 2020 | 2021 | R16
167320169826 | 169496169826 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-28 | 2019-10-28 | 2019-10-28 |  | 2020-06-09 | Overhead | R16 | 2020-02-21 | 1 |  | 85 | 78 | 162 | 2019 | 2020 | R16
168735226270 | 164111226270 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-29 | 2021-04-09 | 2021-04-09 |  | 2022-01-18 | Overhead | R16 | 2021-06-16 | 10 |  | 49 | 155 | 212 | 2021 | 2022 | R16
167382182834 | 164256182834 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-20 | 2019-11-20 | 2020-03-04 |  | 2020-06-09 | Underground | R16 | 2020-04-02 | 1 | 76 | 22 | 49 | 145 | 2019 | 2020 | R16
167407173924 | 166955173924 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-09 | 2019-12-09 | 2019-12-09 |  | 2020-06-09 | Underground | R16 | 2020-02-04 | 1 |  | 42 | 91 | 132 | 2019 | 2020 | R16
168993258510 | 161148258510 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-22 | 2021-11-22 | 2021-11-23 |  | 2022-02-24 | Overhead | R16 | 2022-02-17 | 1 | 2 | 63 | 6 | 69 | 2021 | 2022 | R16
167445181270 | 160991181270 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-04 | 2019-11-04 | 2020-02-20 |  | 2020-07-02 | Underground | R16 |  | 1 | 79 |  |  | 174 | 2019 | 2020 | R16
164524251084 | 168627251084 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-09-28 | 2021-09-30 | 2021-10-07 | 2021-11-03 | 2021-12-02 | Overhead | R16 | 2021-11-03 | 3 | 6 | 20 | 22 | 48 | 2021 | 2021 | R16
169461267723 | 164352267723 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-01-26 | 2022-01-26 | 2022-02-04 |  | 2022-03-15 | Overhead | R16 | 2022-03-11 | 1 | 8 | 26 | 3 | 35 | 2022 | 2022 | R16
169522260314 | 167424260314 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-11-04 | 2021-11-04 | 2021-12-08 |  | 2023-03-27 | Underground | R16 | 2023-01-13 | 1 | 25 | 288 | 52 | 363 | 2021 | 2023 | R16
167520235118 | 165583235118 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-06-30 | 2021-06-15 | 2021-06-16 |  | 2022-02-02 | Overhead | R16 |  | 251 | 2 |  |  | 417 | 2020 | 2022 | R16
165850284204 | 163763284204 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-29 | 2022-06-29 | 2022-06-29 | 2022-09-14 | 2022-09-15 | Overhead | R16 | 2022-09-14 | 1 |  | 56 | 2 | 57 | 2022 | 2022 | R16
160336262643 | 167827262643 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-27 | 2021-12-27 | 2021-12-27 | 2022-02-23 | 2022-03-23 | Overhead | R16 | 2022-02-23 | 1 |  | 43 | 21 | 63 | 2021 | 2022 | R16
160793264240 | 160794264240 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-11-19 | 2022-01-10 | 2022-01-10 |  | 2022-05-12 | Underground | R16 | 2022-04-19 | 37 |  | 72 | 18 | 125 | 2021 | 2022 | R16
167566174888 | 167981174888 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-12-12 | 2019-12-16 | 2019-12-20 |  | 2021-11-09 | Underground | R16 |  | 3 | 5 |  |  | 499 | 2019 | 2021 | R16
167132283763 | 162886283763 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-06-24 | 2022-06-24 | 2022-06-24 |  | 2022-08-16 | Overhead | R16 | 2022-07-11 | 1 |  | 12 | 27 | 38 | 2022 | 2022 | R16
167581169368 | 168748169368 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-23 | 2019-10-23 | 2019-10-23 |  | 2020-01-03 | Overhead | R16 | 2019-12-12 | 1 |  | 37 | 17 | 53 | 2019 | 2020 | R16
163919257062 | 166616257062 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-02 | 2021-11-03 | 2021-11-17 | 2022-02-01 | 2022-02-15 | Underground | R16 | 2022-02-01 | 2 | 11 | 55 | 11 | 76 | 2021 | 2022 | R16
167634265348 | 163869265348 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2021-12-06 | 2021-12-15 | 2022-01-20 |  | 2022-04-20 | Underground | R16 | 2022-03-07 | 8 | 27 | 33 | 33 | 98 | 2021 | 2022 | R16
169993285658 | 164024285658 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-30 | 2022-06-30 | 2022-07-15 | 2022-09-26 | 2022-09-26 | Overhead | R16 | 2022-09-26 | 1 | 12 | 52 |  | 63 | 2022 | 2022 | R16
164444251068 | 167709251068 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-23 | 2021-09-23 | 2021-10-07 | 2021-11-03 | 2022-01-13 | Underground | R16 | 2021-11-03 | 1 | 11 | 20 | 52 | 81 | 2021 | 2022 | R16
167706171574 | 167734171574 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-18 | 2019-10-18 | 2019-11-13 |  | 2021-11-10 | Underground | R16 | 2020-11-12 | 1 | 19 | 262 | 260 | 539 | 2019 | 2021 | R16
167558284131 | 163735284131 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-29 | 2022-06-29 | 2022-06-29 |  | 2022-12-06 | Overhead | R16 | 2022-11-30 | 1 |  | 111 | 5 | 115 | 2022 | 2022 | R16
161304285551 | 165886285551 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-12 | 2022-07-12 | 2022-07-13 |  | 2022-09-29 | Overhead | R16 | 2022-09-08 | 1 | 2 | 42 | 16 | 58 | 2022 | 2022 | R16
160427299513 | 161778299513 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE FOR UPGRADE UD | Commercial | 2022-04-12 | 2022-04-12 | 2022-11-04 | 2023-07-20 | 2023-08-24 | Underground | R16 | 2023-07-20 | 1 | 149 | 185 | 26 | 358 | 2022 | 2023 | R16
167759172443 | 167776172443 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-18 | 2019-10-18 | 2019-11-20 |  | 2020-06-09 | Underground | R16 | 2020-03-16 | 1 | 24 | 84 | 62 | 168 | 2019 | 2020 | R16
168525275574 | 160720275574 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-07 | 2022-04-11 | 2022-04-11 |  | 2022-08-03 | Overhead | R16 | 2022-06-20 | 3 |  | 51 | 33 | 85 | 2022 | 2022 | R16
162949284305 | 163755284305 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2022-09-15 | 2023-02-26 | Overhead | R16 | 2022-09-15 | 1 |  | 56 | 117 | 172 | 2022 | 2023 | R16
167764171910 | 162961171910 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-13 | 2019-11-13 | 2019-11-14 |  | 2020-06-09 | Overhead | R16 | 2020-01-13 | 1 | 2 | 43 | 107 | 150 | 2019 | 2020 | R16
168381270682 | 162022270682 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-25 | 2022-02-25 | 2022-02-25 |  | 2022-07-06 | Overhead | R16 | 2022-04-18 | 1 |  | 37 | 58 | 94 | 2022 | 2022 | R16
162887288120 | 168410288120 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-21 | 2022-08-05 | 2022-08-05 |  | 2022-09-14 | Overhead | R16 | 2022-09-12 | 12 |  | 27 | 3 | 40 | 2022 | 2022 | R16
161377252928 | 163812252928 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-20 | 2021-10-20 | 2021-10-20 | 2021-12-15 | 2022-01-20 | Overhead | R16 | 2021-12-15 | 1 |  | 41 | 27 | 67 | 2021 | 2022 | R16
164156285961 | 166757285961 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-14 | 2022-07-15 | 2022-07-18 | 2022-10-13 | 2023-02-17 | Overhead | R16 | 2022-10-13 | 2 | 2 | 64 | 92 | 157 | 2022 | 2023 | R16
167803174131 | 165433174131 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-27 | 2019-11-27 | 2019-12-11 |  | 2020-06-09 | Underground | R16 | 2020-01-28 | 1 | 11 | 35 | 96 | 140 | 2019 | 2020 | R16
165097287406 | 166934287406 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-27 | 2022-06-14 | 2022-07-29 | 2022-09-21 | 2023-01-05 | Overhead | R16 | 2022-09-21 | 13 | 34 | 39 | 77 | 160 | 2022 | 2023 | R16
168546255931 | 164575255931 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-10-23 | 2021-11-09 | 2021-11-10 | 2022-11-28 | 2022-12-19 | Overhead | R16 | 2022-11-28 | 12 | 2 | 274 | 16 | 301 | 2021 | 2022 | R16
165261287639 | 166403287639 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-13 | 2022-07-15 | 2022-08-03 | 2022-09-23 | 2022-09-26 | Underground | R16 | 2022-09-23 | 3 | 14 | 38 | 2 | 54 | 2022 | 2022 | R16
163828281167 | 163681281167 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-22 | 2022-04-22 | 2022-05-31 | 2022-06-12 | 2022-06-15 | Underground | R16 | 2022-06-12 | 1 | 28 | 9 | 3 | 39 | 2022 | 2022 | R16
160889268407 | 166441268407 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-02 | 2022-02-10 | 2022-02-10 |  | 2023-01-10 | Overhead | R16 | 2022-10-31 | 7 |  | 188 | 52 | 245 | 2022 | 2023 | R16
161302264497 | 165146264497 | NON-RESIDENTIAL - SMALL RETAIL | R16 RESD AND NON RESD US | Commercial | 2021-12-10 | 2021-12-10 | 2022-01-12 |  | 2022-09-15 | Underground | R16 |  | 1 | 24 |  |  | 200 | 2021 | 2022 | R16
167845169606 | 169217169606 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-25 | 2019-10-25 | 2019-10-25 |  | 2020-06-09 | Overhead | R16 | 2020-02-04 | 1 |  | 73 | 91 | 163 | 2019 | 2020 | R16
168240283620 | 162556283620 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-23 | 2022-06-23 | 2022-06-23 |  | 2022-09-30 | Overhead | R16 | 2022-08-23 | 1 |  | 44 | 29 | 72 | 2022 | 2022 | R16
165724278463 | 168643278463 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-03-28 | 2022-03-30 | 2022-05-05 |  | 2022-06-17 | Overhead | R16 |  | 3 | 27 |  |  | 60 | 2022 | 2022 | R16
167849174463 | 165521174463 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-27 | 2019-11-27 | 2019-12-14 |  | 2020-06-09 | Underground | R16 | 2020-02-05 | 1 | 13 | 38 | 90 | 140 | 2019 | 2020 | R16
169682275470 | 166341275470 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-03-16 | 2022-03-16 | 2022-04-11 |  | 2022-09-23 | Overhead | R16 | 2022-09-13 | 1 | 19 | 112 | 9 | 138 | 2022 | 2022 | R16
167883169661 | 169059169661 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-25 | 2019-10-25 | 2019-10-25 |  | 2020-07-08 | Overhead | R16 | 2020-05-20 | 1 |  | 149 | 36 | 184 | 2019 | 2020 | R16
167971175492 | 169380175492 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-19 | 2020-01-02 | 2020-01-02 |  | 2020-06-09 | Overhead | R16 | 2020-02-07 | 11 |  | 27 | 88 | 124 | 2019 | 2020 | R16
167242282216 | 168320282216 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2021-12-29 | 2021-12-29 | 2022-06-10 |  | 2022-08-11 | Underground | R16 |  | 1 | 118 |  |  | 162 | 2021 | 2022 | R16
167977265318 | 165247265318 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-10-27 | 2021-10-27 | 2022-01-20 |  | 2022-05-12 | Underground | R16 |  | 1 | 62 |  |  | 142 | 2021 | 2022 | R16
162126280512 | 165287280512 | RESIDENTIAL - SINGLE FAMILY DETACHED | ELEC OH MISC SVC OS | Residential | 2022-05-19 |  | 2022-05-19 | 2022-09-28 | 2023-01-05 | Overhead | R16 | 2022-09-28 |  |  | 95 | 72 | 166 | 2022 | 2023 | R16
164509252434 | 162822252434 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-15 | 2021-10-15 | 2021-10-15 | 2021-12-26 | 2022-01-12 | Overhead | R16 | 2021-12-26 | 1 |  | 51 | 13 | 64 | 2021 | 2022 | R16
160523260473 | 166920260473 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2021-11-03 | 2021-11-04 | 2021-12-09 | 2022-04-01 | 2022-03-23 | Underground | R16 | 2022-04-01 | 2 | 26 | 82 |  | 101 | 2021 | 2022 | R16
167989172241 | 160992172241 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-04 | 2019-11-04 | 2019-11-18 |  | 2021-04-14 | Underground | R16 | 2020-12-11 | 1 | 11 | 280 | 89 | 378 | 2019 | 2021 | R16
169074269187 | 167866269187 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-09 | 2022-02-15 | 2022-02-15 | 2022-08-20 | 2022-08-23 | Overhead | R16 | 2022-08-20 | 5 |  | 134 | 2 | 140 | 2022 | 2022 | R16
168016171738 | 168055171738 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-21 | 2019-10-21 | 2019-11-13 |  | 2021-04-07 | Underground | R16 | 2020-12-04 | 1 | 18 | 278 | 89 | 383 | 2019 | 2021 | R16
168118276203 | 161564276203 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-12 | 2022-04-18 | 2022-04-18 |  | 2022-08-18 | Overhead | R16 | 2022-07-13 | 5 |  | 63 | 27 | 93 | 2022 | 2022 | R16
161200278421 | 163882278421 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-25 | 2022-05-05 | 2022-05-05 |  | 2023-10-23 | Overhead | R16 | 2023-10-05 | 9 |  | 371 | 13 | 391 | 2022 | 2023 | R16
169701250279 | 169723250279 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-10-04 | 2021-10-04 | 2021-10-04 |  | 2023-07-31 | Overhead | R16 | 2023-12-28 | 1 |  | 584 |  | 476 | 2021 | 2023 | R16
168043170841 | 168215170841 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-22 | 2019-10-22 | 2019-11-05 |  | 2021-12-16 | Underground | R16 | 2019-12-19 | 1 | 11 | 33 | 521 | 563 | 2019 | 2021 | R16
168070182941 | 168831182941 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-10-23 | 2019-12-17 | 2020-03-04 |  | 2021-08-12 | Overhead | R16 |  | 40 | 57 |  |  | 472 | 2019 | 2021 | R16
168097172344 | 168182172344 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-22 | 2019-10-22 | 2019-11-19 |  | 2020-07-08 | Underground | R16 | 2020-04-20 | 1 | 21 | 110 | 58 | 187 | 2019 | 2020 | R16
168034267376 | 168786267376 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-03 | 2022-01-05 | 2022-02-03 | 2022-03-30 | 2022-04-27 | Underground | R16 | 2022-03-30 | 3 | 22 | 40 | 21 | 83 | 2022 | 2022 | R16
164771283579 | 161844283579 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-21 | 2022-06-21 | 2022-06-23 |  | 2022-10-23 | Overhead | R16 | 2022-10-13 | 1 | 3 | 81 | 7 | 89 | 2022 | 2022 | R16
161153276435 | 164501276435 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2022-03-08 | 2022-03-08 | 2022-04-20 | 2022-10-13 | 2022-12-08 | Underground | R16 | 2022-10-13 | 1 | 32 | 127 | 41 | 198 | 2022 | 2022 | R16
160263283592 | 167766283592 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-02-08 | 2022-02-08 | 2022-06-24 |  | 2023-01-10 | Underground | R16 |  | 1 | 99 |  |  | 241 | 2022 | 2023 | R16
168188170370 | 168918170370 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-24 | 2019-10-24 | 2019-11-01 |  | 2021-11-10 | Underground | R16 | 2020-01-30 | 1 | 7 | 65 | 465 | 535 | 2019 | 2021 | R16
160179253985 | 164192253985 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-21 | 2021-10-21 | 2021-10-27 |  | 2021-12-17 | Overhead | R16 | 2021-11-17 | 1 | 5 | 16 | 23 | 42 | 2021 | 2021 | R16
168252178481 | 168260178481 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-22 | 2019-10-22 | 2020-01-28 |  | 2021-04-14 | Underground | R16 | 2020-12-14 | 1 | 71 | 230 | 88 | 387 | 2019 | 2021 | R16
168294170821 | 161392170821 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-05 | 2019-11-05 | 2019-11-05 |  | 2020-07-08 | Overhead | R16 | 2020-05-18 | 1 |  | 140 | 38 | 177 | 2019 | 2020 | R16
162467262868 | 168395262868 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-29 | 2021-12-29 | 2021-12-29 | 2022-06-07 | 2022-08-03 | Overhead | R16 | 2022-06-07 | 1 |  | 115 | 42 | 156 | 2021 | 2022 | R16
161558271171 | 162916271171 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-03-02 | 2022-03-02 | 2022-03-02 | 2022-04-14 | 2022-05-09 | Overhead | R16 | 2022-04-14 | 1 |  | 32 | 18 | 49 | 2022 | 2022 | R16
164270293338 | 162326293338 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-10-14 | 2021-10-14 | 2022-09-13 | 2022-09-14 | 2022-12-13 | Underground | R16 | 2022-09-14 | 1 | 239 | 2 | 65 | 304 | 2021 | 2022 | R16
168308171010 | 160948171010 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-04 | 2019-11-04 | 2019-11-07 |  | 2020-06-09 | Overhead | R16 | 2020-02-19 | 1 | 4 | 75 | 80 | 157 | 2019 | 2020 | R16
164353272841 | 161758272841 | CUSTOMER UPGRADE IN SERVICE | UG SVC CONVERSION | Residential | 2022-02-25 | 2022-03-04 | 2022-03-15 | 2023-01-05 | 2023-01-05 | Underground | R16 | 2023-01-05 | 6 | 8 | 213 |  | 225 | 2022 | 2023 | R16
168379171911 | 162968171911 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-13 | 2019-11-13 | 2019-11-14 |  | 2020-01-08 | Overhead | R16 | 2019-12-31 | 1 | 2 | 34 | 7 | 41 | 2019 | 2020 | R16
167084283861 | 167262283861 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-31 | 2022-06-27 | 2022-06-27 | 2022-08-31 | 2022-10-26 | Overhead | R16 | 2022-08-31 | 20 |  | 48 | 41 | 107 | 2022 | 2022 | R16
167694269504 | 160071269504 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-17 | 2022-02-17 | 2022-02-17 | 2022-06-21 | 2023-03-16 | Overhead | R16 | 2022-06-21 | 1 |  | 89 | 193 | 281 | 2022 | 2023 | R16
168437170451 | 160729170451 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-01 | 2019-11-01 | 2019-11-01 |  | 2021-11-10 | Overhead | R16 | 2019-12-19 | 1 |  | 35 | 495 | 529 | 2019 | 2021 | R16
160380262914 | 161878262914 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-12 | 2021-10-12 | 2021-12-30 | 2022-03-09 | 2022-03-10 | Underground | R16 | 2022-03-09 | 1 | 58 | 50 | 2 | 108 | 2021 | 2022 | R16
168448174083 | 167203174083 | GENERAL/OTHER | OH R16 RES NON RES OS | Commercial | 2019-12-10 | 2019-12-10 | 2019-12-10 |  | 2020-07-08 | Overhead | R16 |  | 1 |  |  |  | 152 | 2019 | 2020 | R16
167957279664 | 168395279664 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-03 | 2022-05-03 | 2022-05-17 |  | 2022-06-20 | Overhead | R16 | 2022-05-26 | 1 | 11 | 8 | 18 | 35 | 2022 | 2022 | R16
166795256524 | 169395256524 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-11-12 | 2021-11-15 | 2021-11-15 | 2022-03-04 | 2022-08-12 | Overhead | R16 | 2022-03-04 | 2 |  | 80 | 116 | 196 | 2021 | 2022 | R16
168490182850 | 163885182850 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-03-03 | 2020-03-03 | 2020-03-04 |  | 2020-06-09 | Overhead | R16 | 2020-04-01 | 1 | 2 | 21 | 50 | 71 | 2020 | 2020 | R16
160015263697 | 160042263697 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-06 | 2022-01-06 | 2022-01-06 |  | 2022-03-03 | Overhead | R16 | 2022-02-03 | 1 |  | 21 | 21 | 41 | 2022 | 2022 | R16
168665170968 | 161701170968 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-06 | 2019-11-06 | 2019-11-06 |  | 2023-06-07 | Overhead | R16 |  | 1 |  |  |  | 936 | 2019 | 2023 | R16
165498274848 | 168511274848 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2022-03-28 | 2022-04-04 | 2022-04-04 |  | 2022-08-11 | Overhead | R16 | 2022-06-27 | 6 |  | 61 | 34 | 99 | 2022 | 2022 | R16
169177253044 | 163834253044 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-20 | 2021-10-20 | 2021-10-20 | 2021-12-20 | 2021-12-21 | Overhead | R16 | 2021-12-20 | 1 |  | 44 | 2 | 45 | 2021 | 2021 | R16
169646272729 | 165886272729 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-03-15 | 2022-03-15 | 2022-03-15 |  | 2023-02-03 | Underground | R16 | 2022-12-02 | 1 |  | 189 | 46 | 234 | 2022 | 2023 | R16
168721172349 | 163911172349 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-19 | 2019-11-19 | 2019-11-19 |  | 2019-12-12 | Overhead | R16 | 2019-12-03 | 1 |  | 11 | 8 | 18 | 2019 | 2019 | R16
164938272943 | 165734272943 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-14 | 2022-03-17 | 2022-03-17 | 2022-05-03 | 2022-06-06 | Overhead | R16 | 2022-05-03 | 4 |  | 34 | 25 | 61 | 2022 | 2022 | R16
166197275441 | 161220275441 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-10 | 2022-04-10 | 2022-04-10 |  | 2023-03-31 | Overhead | R16 | 2023-02-22 | 0 |  | 228 | 28 | 255 | 2022 | 2023 | R16
168772171801 | 163065171801 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-13 | 2019-11-13 | 2019-11-13 |  | 2020-06-09 | Overhead | R16 | 2020-03-09 | 1 |  | 84 | 67 | 150 | 2019 | 2020 | R16
168776170940 | 169131170940 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-24 | 2019-10-24 | 2019-11-06 |  | 2021-12-16 | Underground | R16 | 2019-12-18 | 1 | 10 | 31 | 522 | 561 | 2019 | 2021 | R16
168588284041 | 163139284041 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-27 | 2022-06-27 | 2022-06-27 |  | 2023-01-25 | Overhead | R16 | 2023-01-18 | 1 |  | 148 | 6 | 153 | 2022 | 2023 | R16
168848174831 | 169296174831 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-18 | 2019-12-18 | 2019-12-19 |  | 2020-06-09 | Overhead | R16 | 2020-02-13 | 1 | 2 | 41 | 84 | 125 | 2019 | 2020 | R16
164569283409 | 165736283409 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-23 | 2022-05-23 | 2022-06-22 | 2022-08-08 | 2022-08-22 | Underground | R16 | 2022-08-08 | 1 | 23 | 34 | 11 | 66 | 2022 | 2022 | R16
168871172401 | 163867172401 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-19 | 2019-11-19 | 2019-11-19 |  | 2021-07-01 | Overhead | R16 | 2020-06-11 | 1 |  | 148 | 276 | 423 | 2019 | 2021 | R16
167150281532 | 160592281532 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-18 | 2021-11-18 | 2022-06-03 |  | 2022-07-17 | Underground | R16 | 2022-06-30 | 1 | 142 | 20 | 12 | 172 | 2021 | 2022 | R16
169072207529 | 160130207529 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-10-30 | 2019-11-26 | 2020-10-19 |  | 2022-03-31 | Overhead | R16 |  | 20 | 235 |  |  | 632 | 2019 | 2022 | R16
169073171389 | 162454171389 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-11 | 2019-11-11 | 2019-11-11 |  | 2020-06-09 | Overhead | R16 | 2020-03-02 | 1 |  | 81 | 72 | 152 | 2019 | 2020 | R16
160612266878 | 164150266878 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-25 | 2022-01-31 | 2022-01-31 | 2022-04-19 | 2022-05-19 | Overhead | R16 | 2022-04-19 | 5 |  | 57 | 23 | 83 | 2022 | 2022 | R16
160668304071 | 164829304071 | NON-RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Commercial | 2022-01-27 | 2022-03-28 | 2022-12-27 | 2023-10-19 | 2023-11-03 | Underground | R16 | 2023-10-19 | 43 | 197 | 213 | 12 | 462 | 2022 | 2023 | R16
169114170867 | 161446170867 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-11-06 | 2019-11-06 | 2019-11-06 |  | 2023-06-04 | Overhead | R16 |  | 1 |  |  |  | 933 | 2019 | 2023 | R16
164547281256 | 162749281256 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-05-11 | 2022-05-11 | 2022-06-01 | 2023-11-23 | 2023-11-27 | Underground | R16 | 2023-11-23 | 1 | 16 | 387 | 3 | 404 | 2022 | 2023 | R16
165731256130 | 169103256130 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-11 | 2021-11-11 | 2021-11-11 | 2022-01-20 | 2022-02-28 | Underground | R16 | 2022-01-20 | 1 |  | 51 | 28 | 78 | 2021 | 2022 | R16
169171174024 | 165340174024 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-11-26 | 2019-11-26 | 2019-12-10 |  | 2021-11-05 | Underground | R16 | 2021-11-05 | 1 | 11 | 499 |  | 509 | 2019 | 2021 | R16
160046256128 | 162459256128 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-14 | 2021-11-03 | 2021-11-11 | 2022-03-01 | 2022-04-20 | Underground | R16 | 2022-03-01 | 15 | 7 | 79 | 37 | 135 | 2021 | 2022 | R16
169177171382 | 162423171382 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-11-11 | 2019-11-11 | 2019-11-11 |  | 2020-06-09 | Overhead | R16 | 2020-02-27 | 1 |  | 79 | 74 | 152 | 2019 | 2020 | R16
169190171736 | 163063171736 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-13 | 2019-11-13 | 2019-11-13 |  | 2020-06-09 | Overhead | R16 | 2020-01-09 | 1 |  | 42 | 109 | 150 | 2019 | 2020 | R16
169307277963 | 169547277963 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-02-15 | 2022-02-16 | 2022-05-02 |  | 2022-06-20 | Overhead | R16 |  | 2 | 54 |  |  | 90 | 2022 | 2022 | R16
169221176165 | 160920176165 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-04 | 2020-01-07 | 2020-01-07 |  | 2020-06-09 | Overhead | R16 | 2020-04-07 | 47 |  | 66 | 46 | 157 | 2019 | 2020 | R16
167319276259 | 167726276259 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-09 | 2022-02-09 | 2022-04-20 |  | 2023-01-10 | Underground | R16 | 2022-11-17 | 1 | 51 | 152 | 39 | 240 | 2022 | 2023 | R16
164074260689 | 167871260689 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-08 | 2021-11-08 | 2021-12-10 | 2021-12-22 | 2022-02-07 | Underground | R16 | 2021-12-22 | 1 | 25 | 9 | 34 | 66 | 2021 | 2022 | R16
169292171225 | 162261171225 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-08 | 2019-11-08 | 2019-11-08 |  | 2020-06-23 | Overhead | R16 | 2020-04-06 | 1 |  | 107 | 57 | 163 | 2019 | 2020 | R16
167664263478 | 169910263478 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-16 | 2021-11-16 | 2022-01-05 | 2022-04-13 | 2022-04-14 | Underground | R16 | 2022-04-13 | 1 | 37 | 71 | 2 | 108 | 2021 | 2022 | R16
169311187338 | 161522187338 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-06 | 2020-02-24 | 2020-04-14 |  | 2022-05-09 | Overhead | R16 |  | 79 | 37 |  |  | 654 | 2019 | 2022 | R16
168311259598 | 163390259598 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-12-02 | 2021-12-02 | 2021-12-02 | 2022-05-10 | 2022-05-10 | Overhead | R16 | 2022-05-10 | 1 |  | 114 |  | 114 | 2021 | 2022 | R16
165241271401 | 166446271401 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-03 | 2022-03-03 | 2022-03-03 | 2022-04-11 | 2022-05-12 | Overhead | R16 | 2022-04-11 | 21 |  | 28 | 24 | 71 | 2022 | 2022 | R16
169327177726 | 165728177726 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-03 | 2020-01-22 | 2020-01-22 |  | 2020-06-09 | Overhead | R16 | 2020-04-01 | 37 |  | 51 | 50 | 136 | 2019 | 2020 | R16
167148254704 | 161342254704 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2021-10-11 | 2021-10-12 | 2021-11-02 | 2022-02-15 | 2022-03-11 | Underground | R16 | 2022-02-15 | 2 | 16 | 76 | 19 | 110 | 2021 | 2022 | R16
169329187676 | 161908187676 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-04-15 | 2020-04-16 | 2020-04-16 |  | 2021-07-26 | Underground | R16 | 2020-10-30 | 2 |  | 142 | 192 | 334 | 2020 | 2021 | R16
165684258970 | 162385258970 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-29 | 2021-11-29 | 2021-11-29 |  | 2023-02-28 | Overhead | R16 | 2023-02-01 | 1 |  | 308 | 20 | 327 | 2021 | 2023 | R16
160021259151 | 162891259151 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-30 | 2021-11-30 | 2021-11-30 | 2022-03-09 | 2022-03-10 | Overhead | R16 | 2022-03-09 | 1 |  | 72 | 2 | 73 | 2021 | 2022 | R16
169336171686 | 162891171686 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-13 | 2019-11-13 | 2019-11-13 |  | 2020-06-09 | Overhead | R16 | 2020-01-08 | 1 |  | 41 | 110 | 150 | 2019 | 2020 | R16
163058269743 | 160344269743 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-18 | 2022-02-18 | 2022-02-18 | 2023-02-07 | 2023-02-10 | Overhead | R16 | 2023-02-07 | 1 |  | 253 | 4 | 256 | 2022 | 2023 | R16
167041286306 | 167989286306 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-20 | 2022-07-20 | 2022-07-20 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 1 |  | 122 |  | 122 | 2022 | 2023 | R16
169953277158 | 164068277158 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-04-26 | 2022-04-26 | 2022-04-26 | 2022-06-03 | 2022-06-22 | Overhead | R16 | 2022-06-03 | 1 |  | 29 | 14 | 42 | 2022 | 2022 | R16
161714251340 | 166177251340 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-09-17 | 2021-09-17 | 2021-10-08 | 2022-09-23 | 2022-10-18 | Underground | R16 | 2022-09-23 | 1 | 16 | 251 | 18 | 283 | 2021 | 2022 | R16
166078253951 | 165238253951 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-27 | 2021-10-27 | 2021-10-27 | 2021-12-29 | 2022-02-10 | Overhead | R16 | 2021-12-29 | 1 |  | 46 | 32 | 77 | 2021 | 2022 | R16
167436276209 | 166289276209 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-02 | 2022-02-07 | 2022-04-18 |  | 2023-02-03 | Underground | R16 | 2022-11-30 | 4 | 51 | 163 | 48 | 263 | 2022 | 2023 | R16
169542170311 | 160720170311 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-01 | 2019-11-01 | 2019-11-01 |  | 2019-12-17 | Overhead | R16 | 2019-12-05 | 1 |  | 25 | 9 | 33 | 2019 | 2019 | R16
160121256260 | 168693256260 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-10 | 2021-11-11 | 2021-11-11 | 2022-11-17 | 2022-11-18 | Underground | R16 | 2022-11-17 | 2 |  | 266 | 2 | 268 | 2021 | 2022 | R16
169562192679 | 162216192679 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-11-08 | 2019-12-17 | 2020-05-30 |  | 2020-10-29 | Overhead | R16 | 2020-08-31 | 28 | 119 | 66 | 44 | 255 | 2019 | 2020 | R16
169563171003 | 161760171003 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-06 | 2019-11-06 | 2019-11-06 |  | 2021-11-09 | Overhead | R16 | 2020-12-17 | 1 |  | 292 | 234 | 525 | 2019 | 2021 | R16
168229295968 | 162588295968 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-23 | 2022-06-23 | 2022-10-05 | 2022-10-05 | 2023-01-10 | Overhead | R16 | 2022-10-05 | 1 | 75 |  | 70 | 144 | 2022 | 2023 | R16
169599172347 | 160088172347 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-30 | 2019-10-30 | 2019-11-19 |  | 2020-06-09 | Underground | R16 | 2020-02-13 | 1 | 15 | 63 | 84 | 160 | 2019 | 2020 | R16
169610170816 | 161288170816 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-06 | 2019-11-06 | 2019-11-06 |  | 2019-11-26 | Overhead | R16 | 2019-11-18 | 1 |  | 9 | 7 | 15 | 2019 | 2019 | R16
165084255593 | 168319255593 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-27 | 2021-09-27 | 2021-11-08 | 2022-03-04 | 2022-09-01 | Underground | R16 | 2022-03-04 | 1 | 31 | 85 | 130 | 244 | 2021 | 2022 | R16
160722273643 | 165324273643 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-11 | 2022-03-23 | 2022-03-23 |  | 2022-06-03 | Overhead | R16 | 2022-05-12 | 9 |  | 37 | 17 | 61 | 2022 | 2022 | R16
160378250440 | 169454250440 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-10-01 | 2021-10-01 | 2021-10-01 |  | 2023-01-10 | Underground | R16 | 2022-11-17 | 1 |  | 295 | 39 | 333 | 2021 | 2023 | R16
169701172357 | 163931172357 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-19 | 2019-11-20 | 2019-11-20 |  | 2021-12-16 | Overhead | R16 | 2020-03-25 | 2 |  | 91 | 452 | 543 | 2019 | 2021 | R16
164703281456 | 166036281456 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-15 | 2021-12-15 | 2022-06-03 |  | 2022-11-08 | Underground | R16 | 2022-10-26 | 1 | 123 | 104 | 10 | 235 | 2021 | 2022 | R16
169724207741 | 165037207741 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-06-29 | 2020-07-06 | 2020-10-20 |  | 2021-07-02 | Overhead | R16 |  | 6 | 77 |  |  | 265 | 2020 | 2021 | R16
163635287991 | 168623287991 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2022-03-29 | 2022-05-09 | 2022-08-05 |  | 2023-03-20 | Overhead | R16 |  | 30 | 65 |  |  | 255 | 2022 | 2023 | R16
169735171188 | 169677171188 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-28 | 2019-10-28 | 2019-11-08 |  | 2020-06-09 | Underground | R16 | 2020-04-08 | 1 | 10 | 109 | 45 | 162 | 2019 | 2020 | R16
161344287108 | 163808287108 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-29 | 2022-06-29 | 2022-07-27 |  | 2023-02-21 | Underground | R16 |  | 1 | 21 |  |  | 170 | 2022 | 2023 | R16
163751289714 | 166495289714 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-07-13 | 2022-07-13 | 2022-08-19 | 2023-02-10 | 2023-11-17 | Underground | R16 | 2023-02-10 | 1 | 28 | 126 | 201 | 353 | 2022 | 2023 | R16
160281285800 | 163596285800 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-29 | 2022-06-29 | 2022-07-15 |  | 2022-10-04 | Underground | R16 | 2022-10-03 | 1 | 13 | 57 | 2 | 70 | 2022 | 2022 | R16
167360272550 | 161858272550 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-25 | 2022-02-25 | 2022-03-14 | 2022-05-17 | 2022-05-19 | Underground | R16 | 2022-05-17 | 1 | 12 | 47 | 3 | 60 | 2022 | 2022 | R16
161028266578 | 163286266578 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-02 | 2021-12-02 | 2022-01-28 | 2022-04-13 | 2022-04-14 | Underground | R16 | 2022-04-13 | 1 | 42 | 54 | 2 | 96 | 2021 | 2022 | R16
167379254472 | 166279254472 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-01 | 2021-11-01 | 2021-11-01 | 2021-12-16 | 2022-09-11 | Overhead | R16 | 2021-12-16 | 1 |  | 34 | 192 | 225 | 2021 | 2022 | R16
161906271197 | 162420271197 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-28 | 2022-03-03 | 2022-03-03 | 2022-04-05 | 2022-05-19 | Overhead | R16 | 2022-04-05 | 4 |  | 24 | 33 | 59 | 2022 | 2022 | R16
169882171249 | 162300171249 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-09 | 2019-11-09 | 2019-11-09 |  | 2020-01-08 | Overhead | R16 | 2020-01-02 | 0 |  | 39 | 5 | 43 | 2019 | 2020 | R16
165121275648 | 160453275648 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-04-06 | 2022-04-06 | 2022-04-12 | 2023-01-25 | 2023-02-22 | Underground | R16 | 2023-01-25 | 1 | 5 | 207 | 21 | 231 | 2022 | 2023 | R16
169917173508 | 166156173508 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-04 | 2019-12-04 | 2019-12-04 |  | 2020-06-09 | Overhead | R16 | 2020-01-31 | 1 |  | 43 | 93 | 135 | 2019 | 2020 | R16
165134265231 | 162610265231 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-19 | 2022-01-19 | 2022-01-19 | 2022-03-06 | 2022-04-01 | Overhead | R16 | 2022-03-06 | 1 |  | 33 | 20 | 53 | 2022 | 2022 | R16
169257248694 | 166012248694 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-16 | 2021-09-20 | 2021-09-20 | 2022-01-04 | 2022-01-05 | Overhead | R16 | 2022-01-04 | 3 |  | 77 | 2 | 80 | 2021 | 2022 | R16
169960171802 | 163035171802 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-13 | 2019-11-13 | 2019-11-13 |  | 2021-11-03 | Overhead | R16 | 2020-01-13 | 1 |  | 44 | 473 | 516 | 2019 | 2021 | R16
161808253356 | 164487253356 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-10-22 | 2021-10-22 | 2021-10-22 | 2022-01-03 | 2022-01-05 | Underground | R16 | 2022-01-03 | 1 |  | 52 | 3 | 54 | 2021 | 2022 | R16
168724257564 | 160798257564 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-19 | 2021-11-19 | 2021-11-19 | 2021-11-22 | 2022-01-24 | Overhead | R16 | 2021-11-22 | 1 |  | 2 | 46 | 47 | 2021 | 2022 | R16
166925263828 | 160274263828 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-07 | 2022-01-07 | 2022-01-07 |  | 2023-06-01 | Overhead | R16 | 2023-05-11 | 1 |  | 350 | 16 | 365 | 2022 | 2023 | R16
161177282600 | 164971282600 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-18 | 2022-05-18 | 2022-06-14 | 2022-12-11 | 2022-12-14 | Underground | R16 | 2022-12-11 | 1 | 20 | 129 | 3 | 151 | 2022 | 2022 | R16
169988245188 | 163547245188 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-07-26 | 2021-08-06 | 2021-08-25 |  | 2023-09-13 | Underground | R16 |  | 10 | 14 |  |  | 558 | 2021 | 2023 | R16
160015178025 | 165768178025 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-24 | 2020-01-24 | 2020-01-24 |  | 2020-06-09 | Overhead | R16 | 2020-03-02 | 1 |  | 27 | 72 | 98 | 2020 | 2020 | R16
167895274146 | 162349274146 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-28 | 2022-02-28 | 2022-03-29 | 2022-06-15 | 2022-06-16 | Underground | R16 | 2022-06-15 | 1 | 22 | 57 | 2 | 79 | 2022 | 2022 | R16
160037192514 | 160025192514 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-29 | 2019-10-29 | 2020-05-29 |  | 2021-01-08 | Underground | R16 | 2020-09-16 | 1 | 154 | 79 | 83 | 314 | 2019 | 2021 | R16
164944273975 | 167728273975 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-03-23 | 2022-03-23 | 2022-03-28 |  | 2023-02-21 | Underground | R16 | 2023-02-15 | 1 | 4 | 233 | 5 | 240 | 2022 | 2023 | R16
160180171243 | 162219171243 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-08 | 2019-11-08 | 2019-11-08 |  | 2021-11-10 | Overhead | R16 | 2019-12-18 | 1 |  | 29 | 496 | 524 | 2019 | 2021 | R16
162146255169 | 161413255169 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-11 | 2021-11-04 | 2021-11-04 | 2021-12-27 | 2022-01-24 | Underground | R16 | 2021-12-27 | 19 |  | 38 | 21 | 76 | 2021 | 2022 | R16
164761267334 | 166443267334 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-03 | 2022-02-03 | 2022-02-03 |  | 2022-03-14 | Overhead | R16 | 2022-02-24 | 1 |  | 16 | 13 | 28 | 2022 | 2022 | R16
160829259860 | 162531259860 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2021-11-29 | 2021-11-29 | 2021-12-03 |  | 2022-09-15 | Underground | R16 | 2022-07-26 | 1 | 5 | 168 | 38 | 209 | 2021 | 2022 | R16
160190170347 | 160640170347 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-31 | 2019-10-31 | 2019-10-31 |  | 2020-01-03 | Overhead | R16 | 2019-12-12 | 1 |  | 31 | 17 | 47 | 2019 | 2020 | R16
165191285342 | 164008285342 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2022-06-30 | 2022-07-05 | 2022-07-12 |  | 2023-03-01 | Overhead | R16 |  | 4 | 6 |  |  | 175 | 2022 | 2023 | R16
163436249023 | 165714249023 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-15 | 2021-09-16 | 2021-09-22 | 2022-06-07 | 2022-08-03 | Overhead | R16 | 2022-06-07 | 2 | 5 | 185 | 42 | 231 | 2021 | 2022 | R16
165148274920 | 160242274920 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-05 | 2022-04-05 | 2022-04-05 | 2022-06-21 | 2022-06-22 | Overhead | R16 | 2022-06-21 | 1 |  | 56 | 2 | 57 | 2022 | 2022 | R16
163552299660 | 166306299660 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-25 | 2022-05-25 | 2022-11-07 | 2023-02-26 | 2023-03-29 | Underground | R16 | 2023-02-26 | 1 | 119 | 80 | 23 | 221 | 2022 | 2023 | R16
160365296255 | 166705296255 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-14 | 2022-07-14 | 2022-10-07 |  | 2023-07-28 | Overhead | R16 | 2023-04-05 | 1 | 62 | 129 | 83 | 272 | 2022 | 2023 | R16
169968289378 | 163129289378 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG R16 RESD AND NON RESD UD | Residential | 2022-03-03 | 2022-03-07 | 2022-08-18 | 2023-04-27 | 2023-05-22 | Underground | R16 | 2023-04-27 | 3 | 119 | 181 | 18 | 318 | 2022 | 2023 | R16
161735272766 | 162188272766 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-18 | 2022-02-04 | 2022-03-15 | 2022-03-29 | 2022-05-12 | Underground | R16 | 2022-03-29 | 14 | 28 | 11 | 33 | 83 | 2022 | 2022 | R16
162665286250 | 163266286250 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-28 | 2022-07-01 | 2022-07-20 | 2023-10-13 | 2023-11-16 | Underground | R16 | 2023-10-13 | 4 | 14 | 323 | 25 | 363 | 2022 | 2023 | R16
162872280123 | 168015280123 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-02 | 2022-05-02 | 2022-05-20 | 2022-07-19 | 2022-07-20 | Underground | R16 | 2022-07-19 | 1 | 15 | 43 | 2 | 58 | 2022 | 2022 | R16
160512257273 | 160344257273 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2021-11-18 | 2021-11-18 | 2021-11-18 | 2021-12-31 | 2023-06-08 | Overhead | R16 | 2021-12-31 | 1 |  | 32 | 375 | 406 | 2021 | 2023 | R16
166502250293 | 167943250293 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-24 | 2021-10-01 | 2021-10-01 |  | 2022-02-02 | Overhead | R16 | 2021-12-15 | 6 |  | 54 | 36 | 94 | 2021 | 2022 | R16
160504216924 | 163494216924 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-03-02 | 2020-03-25 | 2021-01-12 |  | 2021-05-07 | Underground | R16 | 2021-02-26 | 18 | 210 | 34 | 51 | 310 | 2020 | 2021 | R16
160512172589 | 163478172589 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-11-18 | 2019-11-21 | 2019-11-21 |  | 2020-08-28 | Overhead | R16 | 2020-06-29 | 4 |  | 158 | 45 | 205 | 2019 | 2020 | R16
166803262681 | 169352262681 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-12 | 2021-11-12 | 2021-12-27 |  | 2022-02-28 | Overhead | R16 | 2022-01-26 | 1 | 32 | 23 | 24 | 77 | 2021 | 2022 | R16
160618173400 | 162407173400 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-11 | 2019-11-18 | 2019-12-02 |  | 2020-07-07 | Underground | R16 | 2020-06-05 | 6 | 11 | 135 | 23 | 172 | 2019 | 2020 | R16
164683249057 | 167377249057 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2021-11-16 | 2022-02-02 | Overhead | R16 | 2021-11-16 | 1 |  | 40 | 57 | 96 | 2021 | 2022 | R16
162332275572 | 165258275572 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-11 | 2022-03-11 | 2022-04-11 |  | 2022-07-29 | Underground | R16 | 2022-07-27 | 1 | 22 | 78 | 3 | 101 | 2022 | 2022 | R16
163717265716 | 160088265716 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-16 | 2021-11-16 | 2022-01-21 |  | 2022-08-11 | Underground | R16 | 2022-06-27 | 1 | 49 | 112 | 34 | 193 | 2021 | 2022 | R16
160678174734 | 168791174734 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-12-16 | 2019-12-18 | 2019-12-18 |  | 2020-10-06 | Underground | R16 | 2020-08-10 | 3 |  | 169 | 42 | 212 | 2019 | 2020 | R16
164940268652 | 167371268652 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-07 | 2022-02-11 | 2022-02-11 | 2022-09-26 | 2023-03-31 | Overhead | R16 | 2022-09-26 | 5 |  | 162 | 135 | 300 | 2022 | 2023 | R16
160689170614 | 161198170614 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-05 | 2019-11-05 | 2019-11-05 |  | 2022-04-29 | Overhead | R16 | 2021-12-17 | 1 |  | 554 | 96 | 649 | 2019 | 2022 | R16
163492248597 | 167095248597 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-11-04 | 2021-12-03 | Overhead | R16 | 2021-11-04 | 1 |  | 33 | 22 | 54 | 2021 | 2021 | R16
160740177170 | 163758177170 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-16 | 2020-01-16 | 2020-01-16 |  | 2020-06-09 | Overhead | R16 | 2020-04-09 | 1 |  | 61 | 44 | 104 | 2020 | 2020 | R16
160741176403 | 162038176403 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-09 | 2020-01-09 | 2020-01-09 |  | 2020-06-09 | Overhead | R16 | 2020-02-18 | 1 |  | 29 | 81 | 109 | 2020 | 2020 | R16
167620271834 | 163332271834 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-19 | 2021-12-28 | 2022-03-07 | 2022-06-24 | 2022-07-18 | Underground | R16 | 2022-06-24 | 51 | 50 | 80 | 17 | 195 | 2021 | 2022 | R16
160761199625 | 166002199625 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2020-05-07 | 2020-06-18 | 2020-08-04 |  | 2021-07-07 | Underground | R16 |  | 31 | 34 |  |  | 305 | 2020 | 2021 | R16
160770171098 | 162096171098 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-08 | 2019-11-08 | 2019-11-08 |  | 2020-01-08 | Overhead | R16 | 2019-12-31 | 1 |  | 38 | 7 | 44 | 2019 | 2020 | R16
160082267662 | 163862267662 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2022-01-24 | 2022-01-24 | 2022-02-04 | 2022-02-15 | 2022-02-17 | Overhead | R16 | 2022-02-15 | 1 | 10 | 8 | 3 | 19 | 2022 | 2022 | R16
160773171741 | 162879171741 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-13 | 2019-11-13 | 2019-11-13 |  | 2019-11-21 | Overhead | R16 |  | 1 |  |  |  | 7 | 2019 | 2019 | R16
160816174068 | 160872174068 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-02 | 2019-11-02 | 2019-12-10 |  | 2021-11-03 | Underground | R16 | 2020-01-30 | 0 | 27 | 38 | 460 | 523 | 2019 | 2021 | R16
168867285050 | 165322285050 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-07-08 | 2022-07-08 | 2022-07-08 |  | 2023-02-27 | Overhead | R16 | 2023-01-31 | 1 |  | 148 | 20 | 167 | 2022 | 2023 | R16
167374256157 | 169468256157 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2022-04-07 | 2022-06-09 | Underground | R16 | 2022-04-07 | 1 |  | 105 | 46 | 150 | 2021 | 2022 | R16
160836181001 | 160882181001 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-11-02 | 2019-11-02 | 2020-02-18 |  | 2022-05-17 | Underground | R16 | 2020-05-08 | 0 | 77 | 59 | 528 | 662 | 2019 | 2022 | R16
165983287073 | 166028287073 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-24 | 2022-05-24 | 2022-07-28 |  | 2023-02-03 | Underground | R16 | 2022-11-28 | 1 | 48 | 88 | 50 | 184 | 2022 | 2023 | R16
160849173911 | 167199173911 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-10 | 2019-12-10 | 2019-12-10 |  | 2020-06-09 | Overhead | R16 | 2020-02-03 | 1 |  | 40 | 92 | 131 | 2019 | 2020 | R16
160873177753 | 165341177753 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-22 | 2020-01-22 | 2020-01-22 |  | 2020-06-09 | Overhead | R16 | 2020-02-26 | 1 |  | 26 | 75 | 100 | 2020 | 2020 | R16
167877272284 | 169439272284 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-16 | 2022-02-16 | 2022-03-11 |  | 2022-08-24 | Underground | R16 | 2022-08-08 | 1 | 18 | 107 | 13 | 136 | 2022 | 2022 | R16
160254322326 | 162389322326 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-18 | 2022-01-18 | 2023-06-15 | 2023-07-21 | 2023-07-21 | Underground | R16 | 2023-07-21 | 1 | 368 | 27 |  | 394 | 2022 | 2023 | R16
160901176067 | 165569176067 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-02 | 2019-12-02 | 2020-01-07 |  | 2020-06-09 | Underground | R16 | 2020-02-10 | 1 | 27 | 25 | 87 | 137 | 2019 | 2020 | R16
167687273133 | 166925273133 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-18 | 2022-03-18 | 2022-03-18 | 2022-04-05 | 2022-04-26 | Overhead | R16 | 2022-04-05 | 1 |  | 13 | 16 | 28 | 2022 | 2022 | R16
163314279122 | 168246279122 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-05-02 | 2022-05-02 | 2022-05-12 |  | 2023-01-12 | Underground | R16 | 2023-01-10 | 1 | 9 | 174 | 3 | 184 | 2022 | 2023 | R16
160955171775 | 162936171775 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-13 | 2019-11-13 | 2019-11-13 |  | 2020-06-09 | Overhead | R16 | 2020-02-06 | 1 |  | 62 | 89 | 150 | 2019 | 2020 | R16
164190269927 | 160755269927 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-02-22 | 2022-02-22 | 2022-02-22 | 2022-05-04 | 2022-06-06 | Underground | R16 | 2022-05-04 | 1 |  | 52 | 24 | 75 | 2022 | 2022 | R16
160731289913 | 162764289913 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Commercial | 2022-04-19 | 2022-04-19 | 2022-08-22 | 2023-07-03 | 2023-08-21 | Underground | R16 | 2023-07-03 | 1 | 90 | 226 | 36 | 350 | 2022 | 2023 | R16
161009182902 | 168085182902 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2019-12-13 | 2019-12-13 | 2020-03-04 |  | 2021-04-07 | Underground | R16 | 2020-12-01 | 1 | 59 | 195 | 92 | 344 | 2019 | 2021 | R16
161520248213 | 166097248213 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-16 | 2021-09-16 | 2021-09-16 | 2021-11-01 | 2021-12-03 | Overhead | R16 | 2021-11-01 | 1 |  | 33 | 25 | 57 | 2021 | 2021 | R16
162568255305 | 165113255305 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-10-27 | 2021-10-27 | 2021-11-05 |  | 2021-12-17 | Overhead | R16 |  | 1 | 8 |  |  | 38 | 2021 | 2021 | R16
168261267952 | 160638267952 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-10 | 2022-02-07 | 2022-02-08 |  | 2023-01-05 | Underground | R16 | 2022-10-11 | 21 | 2 | 176 | 63 | 259 | 2022 | 2023 | R16
164851263338 | 166904263338 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-12-20 | 2021-12-20 | 2022-01-04 | 2022-03-31 | 2022-04-27 | Underground | R16 | 2022-03-31 | 1 | 12 | 63 | 20 | 93 | 2021 | 2022 | R16
166163318113 | 166221318113 | NON-RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Commercial | 2022-05-24 | 2022-05-24 | 2023-05-05 | 2023-10-06 | 2023-10-23 | Underground | R16 | 2023-10-06 | 1 | 249 | 111 | 12 | 370 | 2022 | 2023 | R16
161236172421 | 161186172421 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-05 | 2019-11-05 | 2019-11-19 |  | 2021-11-10 | Underground | R16 | 2020-01-13 | 1 | 11 | 40 | 478 | 527 | 2019 | 2021 | R16
161239177282 | 164085177282 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-16 | 2020-01-16 | 2020-01-16 |  | 2020-06-09 | Overhead | R16 | 2020-03-03 | 1 |  | 34 | 71 | 104 | 2020 | 2020 | R16
161261173207 | 164756173207 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-22 | 2019-11-22 | 2019-11-27 |  | 2020-06-09 | Overhead | R16 | 2020-02-05 | 1 | 4 | 51 | 90 | 143 | 2019 | 2020 | R16
169322265675 | 160723265675 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-10 | 2022-01-10 | 2022-01-21 | 2022-02-02 | 2022-04-01 | Underground | R16 | 2022-02-02 | 1 | 10 | 9 | 43 | 60 | 2022 | 2022 | R16
161274176458 | 161831176458 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-01-07 | 2020-01-07 | 2020-01-10 |  | 2020-06-09 | Overhead | R16 |  | 1 | 4 |  |  | 111 | 2020 | 2020 | R16
167737269122 | 168011269122 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-12-28 | 2022-02-10 | 2022-02-15 |  | 2022-08-03 | Overhead | R16 |  | 33 | 4 |  |  | 157 | 2021 | 2022 | R16
169689261749 | 166172261749 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-15 | 2021-12-17 | 2021-12-17 |  | 2023-08-21 | Underground | R16 | 2023-08-09 | 3 |  | 429 | 9 | 439 | 2021 | 2023 | R16
161323178307 | 166124178307 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-28 | 2020-01-28 | 2020-01-28 |  | 2020-08-28 | Overhead | R16 | 2020-07-02 | 1 |  | 113 | 42 | 154 | 2020 | 2020 | R16
161349198500 | 163865198500 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-23 | 2020-07-27 | 2020-07-27 |  | 2021-07-06 | Overhead | R16 | 2020-10-27 | 25 |  | 67 | 181 | 271 | 2020 | 2021 | R16
161326275816 | 162104275816 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-18 | 2022-01-21 | 2022-04-13 |  | 2022-07-29 | Underground | R16 | 2022-07-26 | 4 | 59 | 75 | 4 | 139 | 2022 | 2022 | R16
161371182092 | 162265182092 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-09 | 2019-11-09 | 2020-02-27 |  | 2020-07-02 | Underground | R16 | 2020-05-06 | 0 | 79 | 50 | 42 | 169 | 2019 | 2020 | R16
161373181202 | 162267181202 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-09 | 2019-11-09 | 2020-02-19 |  | 2022-10-20 | Underground | R16 |  | 0 | 73 |  |  | 769 | 2019 | 2022 | R16
161376171881 | 163169171881 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-14 | 2019-11-14 | 2019-11-14 |  | 2021-12-16 | Overhead | R16 | 2020-01-15 | 1 |  | 45 | 502 | 546 | 2019 | 2021 | R16
161381178947 | 167214178947 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-01 | 2020-02-01 | 2020-02-01 |  | 2020-06-09 | Overhead | R16 | 2020-03-16 | 0 |  | 31 | 62 | 92 | 2020 | 2020 | R16
161549280341 | 165840280341 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-23 | 2022-05-23 | 2022-05-23 | 2022-07-12 | 2022-08-23 | Overhead | R16 | 2022-07-12 | 1 |  | 37 | 31 | 67 | 2022 | 2022 | R16
168041283875 | 163206283875 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-27 | 2022-06-27 | 2022-06-27 | 2022-12-13 | 2022-12-14 | Overhead | R16 | 2022-12-13 | 1 |  | 122 | 2 | 123 | 2022 | 2022 | R16
161389172035 | 163870172035 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-19 | 2019-11-19 | 2019-11-19 |  | 2020-01-08 | Overhead | R16 | 2020-01-02 | 1 |  | 33 | 5 | 37 | 2019 | 2020 | R16
167356258415 | 168904258415 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-10 | 2021-11-10 | 2021-11-23 | 2021-11-29 | 2022-01-12 | Overhead | R16 | 2021-11-29 | 1 | 10 | 5 | 33 | 46 | 2021 | 2022 | R16
167203283210 | 166590283210 | NON-RESIDENTIAL - SMALL RETAIL | R16 RESD AND NON RESD US | Commercial | 2022-05-25 | 2022-05-25 | 2022-06-21 |  | 2023-05-22 | Underground | R16 |  | 1 | 20 |  |  | 259 | 2022 | 2023 | R16
168567267440 | 169283267440 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-04 | 2022-01-05 | 2022-02-03 | 2022-02-04 | 2022-04-18 | Overhead | R16 | 2022-02-04 | 2 | 22 | 2 | 52 | 75 | 2022 | 2022 | R16
164542264502 | 163731264502 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-12-04 | 2021-12-20 | 2022-01-12 |  | 2022-06-10 | Underground | R16 | 2022-05-18 | 11 | 18 | 91 | 18 | 135 | 2021 | 2022 | R16
160038303786 | 169386303786 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-07-26 | 2022-10-13 | 2022-12-20 |  | 2023-04-03 | Overhead | R16 |  | 58 | 49 |  |  | 180 | 2022 | 2023 | R16
164186289707 | 167723289707 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-19 | 2022-07-19 | 2022-08-19 |  | 2023-08-14 | Underground | R16 | 2023-04-26 | 1 | 24 | 179 | 79 | 280 | 2022 | 2023 | R16
165362281253 | 163082281253 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-11 | 2022-05-11 | 2022-06-01 |  | 2022-09-11 | Underground | R16 | 2022-08-03 | 1 | 16 | 46 | 28 | 88 | 2022 | 2022 | R16
161570173545 | 166270173545 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-04 | 2019-12-04 | 2019-12-04 |  | 2020-06-09 | Overhead | R16 | 2020-03-03 | 1 |  | 65 | 71 | 135 | 2019 | 2020 | R16
168733262127 | 165393262127 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-13 | 2021-12-21 | 2021-12-21 |  | 2022-05-18 | Overhead | R16 | 2022-03-08 | 7 |  | 56 | 52 | 113 | 2021 | 2022 | R16
163707265714 | 169982265714 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-06 | 2022-01-06 | 2022-01-21 | 2022-03-20 | 2022-03-22 | Underground | R16 | 2022-03-20 | 1 | 12 | 41 | 2 | 54 | 2022 | 2022 | R16
165594273996 | 168862273996 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-29 | 2022-03-29 | 2022-03-29 | 2022-07-06 | 2022-08-18 | Overhead | R16 | 2022-07-06 | 1 |  | 72 | 32 | 103 | 2022 | 2022 | R16
163741284206 | 163737284206 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-29 | 2022-06-29 | 2022-06-29 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 1 |  | 137 |  | 137 | 2022 | 2023 | R16
162752275011 | 165526275011 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-13 | 2021-12-13 | 2022-04-06 | 2022-06-13 | 2022-06-14 | Underground | R16 | 2022-06-13 | 1 | 83 | 49 | 2 | 132 | 2021 | 2022 | R16
161703177911 | 163320177911 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-14 | 2019-11-14 | 2020-01-23 |  | 2020-07-02 | Underground | R16 | 2020-05-04 | 1 | 51 | 73 | 44 | 166 | 2019 | 2020 | R16
164990262565 | 167873262565 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-08 | 2021-11-08 | 2021-12-27 |  | 2022-06-20 | Overhead | R16 |  | 1 | 36 |  |  | 161 | 2021 | 2022 | R16
162596287558 | 163445287558 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-28 | 2022-07-08 | 2022-08-02 | 2022-10-13 | 2022-10-29 | Underground | R16 | 2022-10-13 | 9 | 18 | 53 | 12 | 89 | 2022 | 2022 | R16
162652282761 | 166080282761 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2022-05-23 | 2022-05-23 | 2022-06-15 |  | 2022-08-11 | Underground | R16 |  | 1 | 18 |  |  | 59 | 2022 | 2022 | R16
168558280490 | 164236280490 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Commercial | 2022-05-16 | 2022-05-16 | 2022-05-24 | 2022-05-24 | 2022-06-13 | Overhead | R16 | 2022-05-24 | 1 | 7 |  | 15 | 21 | 2022 | 2022 | R16
167863282596 | 168803282596 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-07 | 2022-06-14 | 2022-06-14 |  | 2023-02-03 | Underground | R16 | 2022-12-01 | 6 |  | 123 | 47 | 174 | 2022 | 2023 | R16
161895172293 | 164300172293 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-20 | 2019-11-20 | 2019-11-20 |  | 2020-01-08 | Underground | R16 | 2020-01-03 | 1 |  | 33 | 4 | 36 | 2019 | 2020 | R16
168400276475 | 161884276475 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-13 | 2022-04-20 | 2022-04-20 | 2022-10-13 | 2022-10-18 | Overhead | R16 | 2022-10-13 | 6 |  | 127 | 4 | 135 | 2022 | 2022 | R16
163911285025 | 160372285025 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-04 | 2022-05-04 | 2022-07-08 |  | 2023-03-31 | Underground | R16 | 2023-02-24 | 1 | 48 | 166 | 26 | 238 | 2022 | 2023 | R16
162261281806 | 168463281806 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-06 |  | 2022-06-06 | 2022-08-08 | 2023-06-19 | Overhead | R16 | 2022-08-08 |  |  | 46 | 226 | 271 | 2022 | 2023 | R16
161937173573 | 161986173573 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-07 | 2019-11-07 | 2019-12-04 |  | 2020-06-24 | Underground | R16 | 2020-04-22 | 1 | 20 | 101 | 46 | 165 | 2019 | 2020 | R16
167152276890 | 163673276890 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-22 | 2022-04-22 | 2022-04-22 |  | 2022-06-30 | Overhead | R16 | 2022-05-31 | 1 |  | 28 | 23 | 50 | 2022 | 2022 | R16
161985177467 | 163354177467 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-14 | 2020-01-14 | 2020-01-21 |  | 2021-11-10 | Overhead | R16 | 2020-05-11 | 1 | 6 | 80 | 393 | 477 | 2020 | 2021 | R16
167151261948 | 163098261948 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-01 | 2021-12-20 | 2021-12-20 |  | 2022-04-20 | Overhead | R16 | 2022-03-30 | 14 |  | 73 | 16 | 101 | 2021 | 2022 | R16
161991172222 | 163630172222 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-18 | 2019-11-18 | 2019-11-18 |  | 2021-12-16 | Overhead | R16 | 2019-01-27 | 1 |  |  | 754 | 544 | 2019 | 2021 | R16
162217259829 | 164306259829 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-22 | 2021-10-22 | 2021-12-03 | 2022-02-28 | 2022-03-23 | Underground | R16 | 2022-02-28 | 1 | 31 | 62 | 18 | 109 | 2021 | 2022 | R16
162013181083 | 165638181083 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-02 | 2019-12-02 | 2020-02-18 |  | 2020-06-09 | Underground | R16 | 2020-03-26 | 1 | 57 | 28 | 54 | 137 | 2019 | 2020 | R16
162037189827 | 165334189827 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-04 | 2020-05-04 | 2020-05-04 |  | 2020-08-28 | Underground | R16 | 2020-07-06 | 1 |  | 46 | 40 | 85 | 2020 | 2020 | R16
167162253134 | 164226253134 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2022-02-24 | 2022-03-15 | Overhead | R16 | 2022-02-24 | 1 |  | 91 | 14 | 104 | 2021 | 2022 | R16
161260283151 | 164290283151 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-26 | 2022-04-26 | 2022-06-20 | 2022-07-22 | 2022-09-14 | Underground | R16 | 2022-07-22 | 1 | 40 | 25 | 39 | 102 | 2022 | 2022 | R16
166031273341 | 169898273341 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-17 | 2022-02-17 | 2022-03-21 | 2022-05-12 | 2022-05-17 | Underground | R16 | 2022-05-12 | 1 | 23 | 39 | 4 | 64 | 2022 | 2022 | R16
162057180125 | 168993180125 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-10 | 2020-02-10 | 2020-02-11 |  | 2020-06-09 | Overhead | R16 | 2020-03-23 | 1 | 2 | 30 | 57 | 87 | 2020 | 2020 | R16
167500294645 | 169173294645 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2022-03-30 | 2022-03-30 | 2022-09-23 | 2022-10-03 | 2022-10-24 | Overhead | R16 | 2022-10-03 | 1 | 128 | 7 | 16 | 149 | 2022 | 2022 | R16
168188280661 | 169103280661 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-14 | 2022-05-25 | 2022-05-25 | 2022-08-03 | 2022-10-21 | Overhead | R16 | 2022-08-03 | 73 |  | 51 | 58 | 180 | 2022 | 2022 | R16
162063172223 | 163606172223 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-18 | 2019-11-18 | 2019-11-18 |  | 2020-06-24 | Overhead | R16 | 2020-04-21 | 1 |  | 112 | 47 | 158 | 2019 | 2020 | R16
169371291004 | 167251291004 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2022-05-31 | 2022-05-31 | 2022-09-01 | 2023-07-24 | 2023-06-11 | Underground | R16 | 2023-07-24 | 1 | 68 | 233 |  | 269 | 2022 | 2023 | R16
167261280655 | 166922280655 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-18 | 2022-03-18 | 2022-05-26 |  | 2022-07-17 | Overhead | R16 | 2022-06-15 | 1 | 50 | 15 | 23 | 86 | 2022 | 2022 | R16
162468254497 | 166041254497 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2021-10-29 | 2021-10-29 | 2021-11-02 |  | 2022-06-30 | Underground | R16 |  | 1 | 3 |  |  | 175 | 2021 | 2022 | R16
162194189311 | 166513189311 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-05 | 2019-12-05 | 2020-04-29 |  | 2022-08-02 | Underground | R16 |  | 1 | 105 |  |  | 694 | 2019 | 2022 | R16
162320285704 | 167750285704 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-02-08 | 2022-06-21 | 2022-07-15 | 2023-11-16 | 2023-11-24 | Underground | R16 | 2023-11-16 | 96 | 19 | 350 | 7 | 469 | 2022 | 2023 | R16
166039252349 | 162881252349 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-15 | 2021-10-15 | 2021-10-15 | 2021-11-22 | 2022-03-11 | Overhead | R16 | 2021-11-22 | 1 |  | 27 | 80 | 106 | 2021 | 2022 | R16
162221281163 | 167242281163 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-31 | 2022-05-31 | 2022-05-31 | 2022-07-13 | 2022-07-14 | Overhead | R16 | 2022-07-13 | 1 |  | 32 | 2 | 33 | 2022 | 2022 | R16
169742275771 | 162159275771 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-14 | 2022-04-14 | 2022-04-14 |  | 2022-12-05 | Overhead | R16 | 2022-12-02 | 1 |  | 167 | 2 | 168 | 2022 | 2022 | R16
160554260659 | 164589260659 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-08 | 2021-12-09 | 2021-12-10 |  | 2022-12-06 | Overhead | R16 | 2022-11-28 | 2 | 2 | 252 | 7 | 260 | 2021 | 2022 | R16
162243171395 | 162465171395 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-11 | 2019-11-11 | 2019-11-11 |  | 2021-11-13 | Overhead | R16 | 2020-01-14 | 1 |  | 47 | 479 | 525 | 2019 | 2021 | R16
162246194045 | 163390194045 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-11-15 | 2019-11-15 | 2020-06-11 |  | 2020-10-06 | Overhead | R16 | 2020-08-13 | 1 | 150 | 46 | 39 | 233 | 2019 | 2020 | R16
166137284315 | 163947284315 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2023-01-17 | 2023-04-18 | Overhead | R16 | 2023-01-17 | 1 |  | 144 | 66 | 209 | 2022 | 2023 | R16
162273183623 | 160082183623 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-12-26 | 2019-12-26 | 2020-03-09 |  | 2022-10-17 | Underground | R16 |  | 1 | 53 |  |  | 733 | 2019 | 2022 | R16
163646273507 | 167222273507 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-21 | 2022-03-22 | 2022-03-22 | 2022-05-09 | 2022-06-21 | Overhead | R16 | 2022-05-09 | 2 |  | 35 | 32 | 67 | 2022 | 2022 | R16
160081261550 | 166327261550 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2022-04-12 | 2022-05-13 | Overhead | R16 | 2022-04-12 | 1 |  | 84 | 24 | 107 | 2021 | 2022 | R16
169681260008 | 163965260008 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-06 | 2021-12-06 | 2021-12-06 | 2022-01-12 | 2022-03-25 | Overhead | R16 | 2022-01-12 | 1 |  | 28 | 53 | 80 | 2021 | 2022 | R16
162929250795 | 168869250795 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-29 | 2021-10-06 | 2021-10-06 |  | 2021-12-17 | Overhead | R16 | 2021-12-13 | 6 |  | 49 | 5 | 58 | 2021 | 2021 | R16
162453175582 | 165698175582 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-03 | 2019-12-03 | 2020-01-02 |  | 2020-06-09 | Underground | R16 | 2020-03-17 | 1 | 23 | 54 | 61 | 136 | 2019 | 2020 | R16
164769272801 | 164801272801 | NON-RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Commercial | 2021-10-25 | 2021-10-25 | 2022-03-15 | 2022-04-27 | 2022-05-19 | Underground | R16 | 2022-04-27 | 1 | 102 | 32 | 17 | 149 | 2021 | 2022 | R16
164115278500 | 162188278500 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-06 | 2022-05-06 | 2022-05-06 |  | 2022-08-11 | Overhead | R16 | 2022-06-27 | 1 |  | 37 | 34 | 70 | 2022 | 2022 | R16
160029284004 | 161453284004 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-20 | 2022-06-20 | 2022-06-27 | 2022-08-22 | 2022-08-24 | Underground | R16 | 2022-08-22 | 1 | 6 | 41 | 3 | 48 | 2022 | 2022 | R16
162483172225 | 163516172225 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-18 | 2019-11-18 | 2019-11-18 |  | 2021-11-13 | Overhead | R16 | 2020-01-14 | 1 |  | 42 | 479 | 520 | 2019 | 2021 | R16
160672271754 | 164398271754 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-08 | 2022-03-08 | 2022-03-08 | 2022-03-17 | 2022-04-20 | Overhead | R16 | 2022-03-17 | 1 |  | 8 | 25 | 32 | 2022 | 2022 | R16
168384257089 | 160287257089 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2021-11-30 | 2022-02-28 | Overhead | R16 | 2021-11-30 | 1 |  | 10 | 65 | 74 | 2021 | 2022 | R16
162540176852 | 162511176852 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-11 | 2019-11-11 | 2020-01-14 |  | 2020-07-10 | Underground | R16 | 2020-06-10 | 1 | 47 | 107 | 23 | 175 | 2019 | 2020 | R16
162551175129 | 165311175129 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-11-26 | 2019-11-26 | 2019-12-23 |  | 2022-05-19 | Underground | R16 | 2022-04-29 | 1 | 20 | 615 | 15 | 648 | 2019 | 2022 | R16
163731278402 | 161351278402 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-05 | 2022-05-05 | 2022-05-05 | 2022-08-30 | 2022-08-31 | Overhead | R16 | 2022-08-30 | 1 |  | 84 | 2 | 85 | 2022 | 2022 | R16
167041259770 | 163533259770 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-02 | 2021-12-02 | 2021-12-02 |  | 2022-02-28 | Overhead | R16 | 2022-01-24 | 1 |  | 38 | 26 | 63 | 2021 | 2022 | R16
169666287636 | 166708287636 | NON-RESIDENTIAL - LARGE RETAIL | OH R16 RES NON RES OS | Commercial | 2022-07-14 | 2022-07-14 | 2022-08-03 |  | 2023-04-19 | Overhead | R16 |  | 1 | 15 |  |  | 200 | 2022 | 2023 | R16
165748272926 | 160890272926 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-01-11 | 2022-03-07 | 2022-03-16 |  | 2022-05-19 | Overhead | R16 |  | 40 | 8 |  |  | 93 | 2022 | 2022 | R16
162614177462 | 163435177462 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-14 | 2020-01-21 | 2020-01-21 |  | 2020-06-09 | Overhead | R16 | 2020-03-10 | 6 |  | 36 | 66 | 106 | 2020 | 2020 | R16
162617183169 | 164511183169 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-06 | 2020-03-06 | 2020-03-06 |  | 2022-10-20 | Overhead | R16 |  | 1 |  |  |  | 685 | 2020 | 2022 | R16
164370280625 | 166300280625 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-24 | 2022-05-24 | 2022-05-24 |  | 2022-07-03 | Overhead | R16 | 2022-06-30 | 1 |  | 28 | 2 | 29 | 2022 | 2022 | R16
168325275510 | 161410275510 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-11 | 2022-04-11 | 2022-04-11 |  | 2022-06-06 | Underground | R16 | 2022-05-10 | 1 |  | 22 | 20 | 41 | 2022 | 2022 | R16
169988289540 | 167887289540 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-03-24 | 2022-03-24 | 2022-08-18 |  | 2023-09-05 | Underground | R16 |  | 1 | 106 |  |  | 379 | 2022 | 2023 | R16
167750263811 | 160966263811 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-08 | 2021-10-08 | 2022-01-07 |  | 2022-06-06 | Underground | R16 | 2022-05-09 | 1 | 66 | 87 | 21 | 172 | 2021 | 2022 | R16
166639288739 | 165739288739 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-07-12 | 2022-07-25 | 2022-08-12 | 2022-12-08 | 2023-01-18 | Underground | R16 | 2022-12-08 | 10 | 15 | 85 | 30 | 137 | 2022 | 2023 | R16
162649172935 | 165018172935 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-25 | 2019-11-25 | 2019-11-25 |  | 2020-06-23 | Overhead | R16 | 2020-04-13 | 1 |  | 101 | 52 | 152 | 2019 | 2020 | R16
163332278414 | 162350278414 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-06 | 2022-05-06 | 2022-05-06 | 2022-09-08 | 2022-12-15 | Overhead | R16 | 2022-09-08 | 1 |  | 90 | 71 | 160 | 2022 | 2022 | R16
165568275833 | 167741275833 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-27 | 2021-12-27 | 2022-04-13 |  | 2022-08-29 | Underground | R16 | 2022-08-26 | 1 | 78 | 98 | 2 | 176 | 2021 | 2022 | R16
166345277278 | 165758277278 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-01-31 | 2022-02-27 | 2022-04-27 | 2022-08-12 | 2022-09-07 | Underground | R16 | 2022-08-12 | 20 | 43 | 78 | 19 | 158 | 2022 | 2022 | R16
160655267702 | 165371267702 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-01-28 | 2022-01-28 | 2022-02-04 | 2022-02-07 | 2023-03-31 | Underground | R16 | 2022-02-07 | 1 | 6 | 2 | 300 | 306 | 2022 | 2023 | R16
162675182308 | 168005182308 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-05 | 2020-02-24 | 2020-02-28 |  | 2020-06-09 | Overhead | R16 |  | 14 | 5 |  |  | 90 | 2020 | 2020 | R16
162700179041 | 167036179041 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-31 | 2020-01-31 | 2020-02-03 |  | 2020-06-09 | Overhead | R16 | 2020-02-28 | 1 | 2 | 20 | 73 | 93 | 2020 | 2020 | R16
160439298019 | 165357298019 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-08 | 2022-07-21 | 2022-10-24 |  | 2023-04-19 | Overhead | R16 | 2023-01-23 | 10 | 68 | 66 | 63 | 204 | 2022 | 2023 | R16
169719253743 | 164817253743 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2022-09-25 | 2022-09-28 | Underground | R16 | 2022-09-25 | 1 |  | 240 | 3 | 243 | 2021 | 2022 | R16
161755256552 | 169749256552 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2021-11-15 | 2021-11-15 | 2021-11-15 | 2021-11-18 | 2021-12-13 | Overhead | R16 | 2021-11-18 | 1 |  | 4 | 18 | 21 | 2021 | 2021 | R16
162764183813 | 162906183813 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-13 | 2019-11-13 | 2020-03-11 |  | 2020-08-28 | Underground | R16 | 2020-07-07 | 1 | 86 | 85 | 39 | 208 | 2019 | 2020 | R16
162662273605 | 162511273605 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-10-14 | 2021-10-14 | 2022-03-23 |  | 2023-10-06 | Underground | R16 | 2023-07-07 | 1 | 115 | 338 | 66 | 517 | 2021 | 2023 | R16
169536273361 | 162605273361 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-01-19 | 2022-01-19 | 2022-03-21 | 2022-06-21 | 2022-08-10 | Underground | R16 | 2022-06-21 | 1 | 44 | 67 | 37 | 146 | 2022 | 2022 | R16
160643266926 | 165211266926 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-28 | 2022-01-31 | 2022-01-31 | 2022-02-01 | 2022-05-13 | Overhead | R16 | 2022-02-01 | 2 |  | 2 | 74 | 76 | 2022 | 2022 | R16
166799258920 | 162373258920 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-28 | 2021-11-28 | 2021-11-28 | 2022-08-25 | 2022-08-26 | Overhead | R16 | 2022-08-25 | 0 |  | 194 | 2 | 195 | 2021 | 2022 | R16
162907172568 | 164500172568 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-21 | 2019-11-21 | 2019-11-21 |  | 2021-11-13 | Overhead | R16 | 2020-01-08 | 1 |  | 35 | 483 | 517 | 2019 | 2021 | R16
164955252629 | 163211252629 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-18 | 2021-10-18 | 2021-10-18 | 2021-11-09 | 2022-01-18 | Overhead | R16 | 2021-11-09 | 1 |  | 17 | 51 | 67 | 2021 | 2022 | R16
167122283922 | 163154283922 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-27 | 2022-06-27 | 2022-06-27 | 2022-08-12 | 2023-04-08 | Overhead | R16 | 2022-08-12 | 1 |  | 35 | 171 | 205 | 2022 | 2023 | R16
167515247916 | 165831247916 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-12-26 | 2022-01-25 | Underground | R16 | 2021-12-26 | 1 |  | 73 | 22 | 95 | 2021 | 2022 | R16
161454277923 | 168020277923 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2022-05-02 | 2022-05-02 | 2022-05-02 |  | 2022-08-18 | Overhead | R16 | 2022-07-15 | 1 |  | 55 | 25 | 79 | 2022 | 2022 | R16
168547254045 | 161318254045 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-10 | 2021-10-10 | 2021-10-27 |  | 2022-03-03 | Underground | R16 | 2022-02-03 | 0 | 13 | 72 | 21 | 104 | 2021 | 2022 | R16
167274295021 | 160055295021 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-13 | 2022-06-24 | 2022-09-26 | 2022-10-21 | 2022-10-24 | Underground | R16 | 2022-10-21 | 10 | 67 | 20 | 2 | 96 | 2022 | 2022 | R16
163048176439 | 162588176439 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-10 | 2020-01-10 | 2020-01-10 |  | 2020-06-09 | Overhead | R16 | 2020-02-25 | 1 |  | 33 | 76 | 108 | 2020 | 2020 | R16
160476260609 | 161880260609 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-22 | 2021-11-30 | 2021-12-09 | 2022-05-14 | 2022-06-20 | Underground | R16 | 2022-05-14 | 7 | 8 | 112 | 26 | 151 | 2021 | 2022 | R16
163329281225 | 167308281225 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-31 | 2022-05-31 | 2022-05-31 |  | 2022-07-03 | Overhead | R16 | 2022-06-27 | 1 |  | 20 | 5 | 24 | 2022 | 2022 | R16
163177174353 | 163248174353 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-14 | 2019-11-14 | 2019-12-13 |  | 2020-06-16 | Underground | R16 | 2020-04-13 | 1 | 22 | 87 | 47 | 154 | 2019 | 2020 | R16
160288259168 | 161058259168 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-22 | 2021-11-30 | 2021-11-30 | 2022-07-20 | 2022-09-15 | Overhead | R16 | 2022-07-20 | 7 |  | 167 | 42 | 214 | 2021 | 2022 | R16
169702287313 | 163175287313 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-27 | 2022-06-27 | 2022-07-30 |  | 2023-02-12 | Underground | R16 | 2022-12-15 | 1 | 25 | 99 | 42 | 165 | 2022 | 2023 | R16
165404258578 | 167405258578 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-22 | 2021-11-24 | 2021-11-24 | 2022-02-16 | 2022-02-25 | Underground | R16 | 2022-02-16 | 46 |  | 61 | 8 | 113 | 2021 | 2022 | R16
160781276821 | 164400276821 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-07 | 2022-03-07 | 2022-04-21 |  | 2022-07-25 | Underground | R16 | 2022-06-06 | 1 | 34 | 33 | 36 | 101 | 2022 | 2022 | R16
167788259025 | 163556259025 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-19 | 2021-10-19 | 2021-11-29 | 2022-01-07 | 2022-02-07 | Overhead | R16 | 2022-01-07 | 1 | 30 | 30 | 22 | 80 | 2021 | 2022 | R16
163237267546 | 166709267546 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-02-04 | 2022-02-04 | 2022-02-04 | 2022-03-29 | 2022-03-29 | Overhead | R16 | 2022-03-29 | 1 |  | 38 |  | 38 | 2022 | 2022 | R16
163363281313 | 167559281313 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-01 | 2022-06-01 | 2022-06-01 |  | 2023-04-01 | Overhead | R16 | 2023-01-23 | 1 |  | 169 | 50 | 218 | 2022 | 2023 | R16
163238173614 | 166447173614 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-05 | 2019-12-05 | 2019-12-05 |  | 2020-06-09 | Overhead | R16 | 2020-02-24 | 1 |  | 58 | 77 | 134 | 2019 | 2020 | R16
169791273727 | 167763273727 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-23 | 2022-03-23 | 2022-03-23 | 2022-04-24 | 2022-04-27 | Overhead | R16 | 2022-04-24 | 1 |  | 23 | 3 | 26 | 2022 | 2022 | R16
167596296746 | 167598296746 | GENERAL/OTHER | UG R16 RESD AND NON RESD UD | Commercial | 2021-09-23 | 2021-09-23 | 2022-10-11 | 2023-08-08 | 2023-09-26 | Underground | R16 | 2023-08-08 | 1 | 274 | 216 | 36 | 524 | 2021 | 2023 | R16
167752274410 | 169286274410 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-31 | 2022-03-31 | 2022-03-31 | 2022-10-14 | 2022-12-04 | Overhead | R16 | 2022-10-14 | 1 |  | 142 | 36 | 177 | 2022 | 2022 | R16
163282177744 | 169192177744 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-12-18 | 2019-12-18 | 2020-01-22 |  | 2021-11-10 | Underground | R16 | 2020-05-07 | 1 | 26 | 77 | 395 | 496 | 2019 | 2021 | R16
163289179323 | 163501179323 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-15 | 2019-11-15 | 2020-02-04 |  | 2020-07-07 | Underground | R16 | 2020-05-11 | 1 | 58 | 70 | 42 | 168 | 2019 | 2020 | R16
164916297625 | 165831297625 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-12 | 2022-10-19 | 2022-10-19 |  | 2023-02-11 | Overhead | R16 | 2022-12-07 | 72 |  | 36 | 48 | 154 | 2022 | 2023 | R16
164357280909 | 166619280909 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-05-26 | 2022-05-26 | 2022-05-27 |  | 2022-07-26 | Overhead | R16 |  | 1 | 2 |  |  | 44 | 2022 | 2022 | R16
166269255540 | 167851255540 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-07 | 2021-11-07 | 2021-11-07 | 2023-05-26 | 2023-05-26 | Overhead | R16 | 2023-05-26 | 0 |  | 405 |  | 405 | 2021 | 2023 | R16
165221269921 | 166657269921 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-03 | 2022-02-03 | 2022-02-20 | 2022-02-23 | 2022-03-25 | Underground | R16 | 2022-02-23 | 1 | 12 | 3 | 23 | 37 | 2022 | 2022 | R16
166109259543 | 163155259543 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-12-02 | 2021-12-02 | 2021-12-02 |  | 2022-03-23 | Overhead | R16 | 2022-03-01 | 1 |  | 64 | 17 | 80 | 2021 | 2022 | R16
163771273676 | 168315273676 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-25 | 2022-03-25 | 2022-03-25 | 2022-05-10 | 2022-06-06 | Overhead | R16 | 2022-05-10 | 1 |  | 33 | 20 | 52 | 2022 | 2022 | R16
164742269380 | 169594269380 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-16 | 2022-02-16 | 2022-02-16 | 2022-07-20 | 2022-09-15 | Underground | R16 | 2022-07-20 | 1 |  | 111 | 42 | 152 | 2022 | 2022 | R16
163403266501 | 164706266501 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-27 | 2022-01-27 | 2022-01-27 | 2023-09-19 | 2023-09-21 | Overhead | R16 | 2023-09-19 | 1 |  | 429 | 3 | 431 | 2022 | 2023 | R16
169986297199 | 161338297199 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-11 | 2022-04-13 | 2022-10-17 | 2023-04-05 | 2023-06-08 | Underground | R16 | 2023-04-05 | 3 | 134 | 123 | 47 | 304 | 2022 | 2023 | R16
167075303360 | 160391303360 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-02-18 | 2022-02-18 | 2022-12-21 | 2023-11-12 | 2023-11-15 | Underground | R16 | 2023-11-12 | 1 | 219 | 233 | 3 | 454 | 2022 | 2023 | R16
163451186023 | 163180186023 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-28 | 2020-03-31 | 2020-03-31 |  | 2020-06-23 | Overhead | R16 | 2020-04-14 | 23 |  | 11 | 51 | 83 | 2020 | 2020 | R16
160222285459 | 165370285459 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-08 | 2022-07-13 | 2022-07-13 | 2022-08-18 | 2022-08-22 | Overhead | R16 | 2022-08-18 | 4 |  | 27 | 3 | 32 | 2022 | 2022 | R16
160738252058 | 162530252058 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-14 | 2021-10-14 | 2021-10-14 | 2022-03-22 | 2022-04-22 | Overhead | R16 | 2022-03-22 | 1 |  | 114 | 24 | 137 | 2021 | 2022 | R16
168083257131 | 160445257131 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-11-18 | 2021-11-18 | 2021-11-18 | 2021-12-01 | 2021-12-01 | Overhead | R16 | 2021-12-01 | 1 |  | 10 |  | 10 | 2021 | 2021 | R16
166299273619 | 167136273619 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-21 | 2022-03-24 | 2022-03-24 | 2022-05-04 | 2022-06-03 | Overhead | R16 | 2022-05-04 | 4 |  | 30 | 23 | 55 | 2022 | 2022 | R16
168132297269 | 161236297269 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-01-12 | 2022-01-12 | 2022-10-18 | 2023-02-01 | 2023-02-22 | Underground | R16 | 2023-02-01 | 1 | 200 | 77 | 16 | 291 | 2022 | 2023 | R16
162628254119 | 165777254119 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-28 | 2021-10-28 | 2021-10-28 | 2022-01-28 | 2022-01-31 | Overhead | R16 | 2022-01-28 | 1 |  | 67 | 2 | 68 | 2021 | 2022 | R16
163644189437 | 165561189437 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-27 | 2020-02-21 | 2020-04-30 |  | 2020-12-18 | Underground | R16 |  | 63 | 50 |  |  | 278 | 2019 | 2020 | R16
160112257800 | 161030257800 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-22 | 2021-11-22 | 2021-11-22 | 2022-01-20 | 2022-02-28 | Overhead | R16 | 2022-01-20 | 1 |  | 44 | 28 | 71 | 2021 | 2022 | R16
167828249281 | 165992249281 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-16 | 2021-09-23 | 2021-09-23 |  | 2021-12-17 | Underground | R16 | 2021-11-18 | 6 |  | 41 | 22 | 67 | 2021 | 2021 | R16
164147287901 | 160787287901 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-04-07 | 2022-06-09 | 2022-08-03 | 2023-07-24 | 2023-09-05 | Overhead | R16 | 2023-07-24 | 46 | 40 | 254 | 32 | 369 | 2022 | 2023 | R16
163689183128 | 164643183128 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-06 | 2020-03-06 | 2020-03-06 |  | 2020-07-01 | Overhead | R16 | 2020-04-30 | 1 |  | 40 | 45 | 84 | 2020 | 2020 | R16
163835173751 | 166784173751 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-09 | 2019-12-09 | 2019-12-09 |  | 2021-11-13 | Overhead | R16 | 2020-01-14 | 1 |  | 27 | 479 | 505 | 2019 | 2021 | R16
160739281316 | 167800281316 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-02 | 2022-06-02 | 2022-06-02 |  | 2022-07-29 | Overhead | R16 | 2022-07-07 | 1 |  | 26 | 17 | 42 | 2022 | 2022 | R16
163908176259 | 165702176259 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-02 | 2019-12-02 | 2020-01-08 |  | 2021-11-03 | Underground | R16 | 2021-06-23 | 1 | 28 | 381 | 96 | 503 | 2019 | 2021 | R16
163915176857 | 164866176857 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-11-22 | 2019-12-16 | 2020-01-14 |  | 2020-06-09 | Overhead | R16 |  | 17 | 22 |  |  | 143 | 2019 | 2020 | R16
161520248214 | 166114248214 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-16 | 2021-09-16 | 2021-09-16 | 2021-12-14 | 2022-06-10 | Overhead | R16 | 2021-12-14 | 1 |  | 64 | 129 | 192 | 2021 | 2022 | R16
162123253681 | 164546253681 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2021-10-22 | 2021-10-22 | 2021-10-25 | 2022-02-28 | 2022-03-03 | Underground | R16 | 2022-02-28 | 1 | 2 | 91 | 4 | 95 | 2021 | 2022 | R16
165778254752 | 165766254752 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE NON RES US | Commercial | 2021-10-28 | 2021-10-28 | 2021-11-02 | 2021-11-11 | 2021-12-06 | Underground | R16 | 2021-11-11 | 1 | 4 | 8 | 18 | 28 | 2021 | 2021 | R16
163958280776 | 162882280776 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-05-10 | 2022-05-10 | 2022-05-25 |  | 2022-08-16 | Overhead | R16 |  | 1 | 12 |  |  | 71 | 2022 | 2022 | R16
161473280622 | 168230280622 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-02 | 2022-05-24 | 2022-05-24 |  | 2022-10-26 | Underground | R16 | 2022-09-09 | 17 |  | 79 | 34 | 128 | 2022 | 2022 | R16
164026191484 | 166369191484 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2019-12-05 | 2020-03-16 | 2020-05-18 |  | 2021-11-04 | Overhead | R16 |  | 73 | 46 |  |  | 501 | 2019 | 2021 | R16
166893270196 | 160621270196 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-02-20 | 2022-02-23 | 2022-02-23 |  | 2022-05-03 | Overhead | R16 | 2022-04-26 | 3 |  | 45 | 6 | 52 | 2022 | 2022 | R16
162770277092 | 163954277092 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-25 | 2022-04-25 | 2022-04-25 | 2022-06-21 | 2022-10-17 | Overhead | R16 | 2022-06-21 | 1 |  | 42 | 85 | 126 | 2022 | 2022 | R16
167386263446 | 169242263446 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-04 | 2022-01-04 | 2022-01-04 |  | 2022-07-22 | Overhead | R16 | 2022-07-20 | 1 |  | 142 | 3 | 144 | 2022 | 2022 | R16
167794278335 | 169119278335 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-03 | 2022-05-03 | 2022-05-05 |  | 2022-07-20 | Overhead | R16 | 2022-07-20 | 1 | 3 | 55 |  | 57 | 2022 | 2022 | R16
160174275722 | 161818275722 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-13 | 2022-04-13 | 2022-04-13 |  | 2022-08-02 | Overhead | R16 | 2022-06-13 | 1 |  | 44 | 37 | 80 | 2022 | 2022 | R16
164243178033 | 165844178033 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-25 | 2020-01-25 | 2020-01-25 |  | 2020-06-16 | Overhead | R16 | 2020-03-26 | 0 |  | 44 | 59 | 102 | 2020 | 2020 | R16
160762273642 | 162480273642 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-28 | 2022-02-28 | 2022-03-23 | 2022-03-25 | 2022-05-10 | Underground | R16 | 2022-03-25 | 1 | 18 | 3 | 33 | 52 | 2022 | 2022 | R16
164248184674 | 169866184674 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-12-23 | 2020-03-19 | 2020-03-19 |  | 2021-11-11 | Overhead | R16 | 2021-07-08 | 64 |  | 341 | 91 | 494 | 2019 | 2021 | R16
164248175110 | 169901175110 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-12-23 | 2019-12-23 | 2019-12-23 |  | 2020-06-09 | Overhead | R16 | 2020-02-07 | 1 |  | 35 | 88 | 122 | 2019 | 2020 | R16
168755285516 | 165665285516 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2022-05-21 | 2022-05-21 | 2022-07-13 | 2022-11-16 | 2022-12-06 | Underground | R16 | 2022-11-16 | 0 | 38 | 91 | 15 | 142 | 2022 | 2022 | R16
166519296666 | 164880296666 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-07 | 2022-08-18 | 2022-10-11 |  | 2023-04-25 | Underground | R16 | 2023-03-31 | 31 | 39 | 124 | 18 | 209 | 2022 | 2023 | R16
163028279015 | 165181279015 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-28 | 2022-05-12 | 2022-05-12 |  | 2023-03-23 | Overhead | R16 | 2023-01-12 | 11 |  | 176 | 51 | 236 | 2022 | 2023 | R16
164426274928 | 165920274928 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-01 | 2022-02-04 | 2022-04-05 |  | 2023-08-14 | Underground | R16 | 2023-05-02 | 4 | 43 | 281 | 75 | 400 | 2022 | 2023 | R16
164318178219 | 165021178219 | NON-RESIDENTIAL - SMALL RETAIL | R16 RESD AND NON RESD US | Commercial | 2019-11-25 | 2020-01-10 | 2020-01-28 |  | 2020-07-09 | Underground | R16 |  | 35 | 13 |  |  | 164 | 2019 | 2020 | R16
168157261953 | 164372261953 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-08 | 2021-12-20 | 2021-12-20 |  | 2022-02-28 | Overhead | R16 | 2022-01-25 | 9 |  | 27 | 25 | 59 | 2021 | 2022 | R16
164353184610 | 164665184610 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-03-06 | 2020-03-18 | 2020-03-19 |  | 2022-03-18 | Overhead | R16 | 2022-07-11 | 9 | 2 | 603 |  | 531 | 2020 | 2022 | R16
162292268074 | 167600268074 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-08 | 2022-02-09 | 2022-02-09 |  | 2023-02-17 | Overhead | R16 | 2023-01-09 | 2 |  | 239 | 30 | 269 | 2022 | 2023 | R16
161977270314 | 161626270314 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-24 | 2022-02-24 | 2022-02-24 | 2022-04-05 | 2022-05-09 | Underground | R16 | 2022-04-05 | 1 |  | 29 | 25 | 53 | 2022 | 2022 | R16
164353248403 | 166044248403 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-17 | 2021-09-17 | 2021-09-17 | 2022-02-11 | 2022-03-11 | Overhead | R16 | 2022-02-11 | 1 |  | 106 | 21 | 126 | 2021 | 2022 | R16
160462259656 | 163333259656 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-02 | 2021-12-02 | 2021-12-03 | 2022-01-27 | 2022-03-02 | Overhead | R16 | 2022-01-27 | 1 | 2 | 40 | 25 | 65 | 2021 | 2022 | R16
164390175373 | 160432175373 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-30 | 2019-12-30 | 2019-12-30 |  | 2020-06-09 | Overhead | R16 | 2020-02-04 | 1 |  | 27 | 91 | 117 | 2019 | 2020 | R16
163221284550 | 164444284550 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-05 | 2022-07-05 | 2022-07-05 |  | 2022-10-26 | Overhead | R16 | 2022-09-14 | 1 |  | 52 | 31 | 82 | 2022 | 2022 | R16
161725288691 | 165113288691 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-28 | 2022-04-28 | 2022-08-12 |  | 2023-07-31 | Underground | R16 | 2023-04-03 | 1 | 77 | 167 | 86 | 328 | 2022 | 2023 | R16
163320283938 | 169835283938 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-10 | 2022-06-10 | 2022-06-28 | 2023-08-15 | 2023-08-16 | Underground | R16 | 2023-08-15 | 1 | 13 | 296 | 2 | 309 | 2022 | 2023 | R16
164544173754 | 166817173754 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-09 | 2019-12-09 | 2019-12-09 |  | 2020-06-09 | Overhead | R16 | 2020-01-20 | 1 |  | 31 | 102 | 132 | 2019 | 2020 | R16
169655259118 | 162565259118 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-11-30 | 2021-11-30 | 2021-11-30 | 2023-05-09 | 2023-08-18 | Overhead | R16 | 2023-05-09 | 1 |  | 376 | 74 | 449 | 2021 | 2023 | R16
163947265441 | 166277265441 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-16 | 2021-12-16 | 2022-01-20 | 2022-03-01 | 2022-08-10 | Underground | R16 | 2022-03-01 | 1 | 26 | 29 | 117 | 170 | 2021 | 2022 | R16
162434276740 | 163471276740 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-21 | 2022-04-21 | 2022-04-21 | 2022-07-28 | 2022-08-01 | Overhead | R16 | 2022-07-28 | 1 |  | 71 | 3 | 73 | 2022 | 2022 | R16
164632174085 | 166854174085 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-09 | 2019-12-09 | 2019-12-10 |  | 2020-06-09 | Overhead | R16 | 2020-04-07 | 1 | 2 | 86 | 46 | 132 | 2019 | 2020 | R16
169803288541 | 163107288541 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-06-27 | 2022-06-27 | 2022-08-10 | 2023-07-18 | 2023-08-14 | Underground | R16 | 2023-07-18 | 1 | 33 | 245 | 20 | 296 | 2022 | 2023 | R16
160276262380 | 167511262380 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2022-03-30 | 2022-04-27 | Overhead | R16 | 2022-03-30 | 1 |  | 71 | 21 | 91 | 2021 | 2022 | R16
166935267823 | 167297267823 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2022-02-07 | 2022-02-07 | 2022-02-07 | 2022-05-19 | 2022-06-13 | Overhead | R16 | 2022-05-19 | 1 |  | 74 | 18 | 91 | 2022 | 2022 | R16
165120281027 | 165886281027 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-23 | 2022-05-27 | 2022-05-27 | 2022-07-26 | 2022-09-20 | Overhead | R16 | 2022-07-26 | 5 |  | 43 | 41 | 87 | 2022 | 2022 | R16
168682284733 | 160688284733 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-02-22 | 2022-02-24 | 2022-07-07 | 2023-10-20 | 2023-11-20 | Underground | R16 | 2023-10-20 | 3 | 96 | 337 | 22 | 455 | 2022 | 2023 | R16
164673177851 | 165355177851 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-23 | 2020-01-23 | 2020-01-23 |  | 2020-06-09 | Overhead | R16 | 2020-02-18 | 1 |  | 19 | 81 | 99 | 2020 | 2020 | R16
164674191860 | 168227191860 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-21 | 2020-05-21 | 2020-05-21 |  | 2020-07-14 | Overhead | R16 | 2020-06-18 | 1 |  | 21 | 19 | 39 | 2020 | 2020 | R16
165731277423 | 164010277423 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-04-25 | 2022-04-27 | 2022-04-27 |  | 2022-06-20 | Overhead | R16 | 2022-05-27 | 3 |  | 23 | 17 | 41 | 2022 | 2022 | R16
162502253116 | 163973253116 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-20 | 2021-10-20 | 2021-10-20 | 2021-11-02 | 2021-12-07 | Overhead | R16 | 2021-11-02 | 1 |  | 10 | 26 | 35 | 2021 | 2021 | R16
166995262721 | 166729262721 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-02 | 2021-12-27 | 2021-12-27 | 2022-03-22 | 2022-03-22 | Overhead | R16 | 2022-03-22 | 40 |  | 62 |  | 101 | 2021 | 2022 | R16
164763174355 | 167002174355 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-09 | 2019-12-09 | 2019-12-13 |  | 2020-06-09 | Overhead | R16 | 2020-03-24 | 1 | 5 | 73 | 56 | 132 | 2019 | 2020 | R16
160281265814 | 163444265814 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-21 | 2022-01-21 | 2022-01-21 |  | 2022-03-10 | Overhead | R16 | 2022-03-07 | 1 |  | 32 | 4 | 35 | 2022 | 2022 | R16
163295267024 | 165890267024 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-01 | 2022-02-01 | 2022-02-01 | 2022-08-31 | 2022-09-01 | Overhead | R16 | 2022-08-31 | 1 |  | 152 | 2 | 153 | 2022 | 2022 | R16
164802200596 | 163923200596 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-14 | 2020-08-14 | 2020-08-17 |  | 2021-07-14 | Underground | R16 | 2020-11-23 | 1 | 2 | 71 | 168 | 239 | 2020 | 2021 | R16
164319282794 | 167029282794 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-04 | 2022-06-08 | 2022-06-16 |  | 2022-09-11 | Underground | R16 | 2022-08-16 | 89 | 7 | 44 | 19 | 156 | 2022 | 2022 | R16
166076259655 | 168483259655 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-09 | 2021-11-09 | 2021-12-02 | 2022-04-04 | 2022-05-05 | Underground | R16 | 2022-04-04 | 1 | 18 | 88 | 24 | 128 | 2021 | 2022 | R16
164340265528 | 163606265528 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-10-19 | 2022-01-20 | 2023-01-30 | 2023-08-02 | 2023-10-06 | Underground | R16 | 2023-08-02 | 68 | 268 | 133 | 48 | 514 | 2021 | 2023 | R16
162696260399 | 163300260399 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-12-02 | 2021-12-09 | 2021-12-09 | 2021-12-18 | 2021-12-21 | Overhead | R16 | 2021-12-18 | 6 |  | 7 | 2 | 14 | 2021 | 2021 | R16
165798253138 | 163168253138 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-10-18 | 2021-10-18 | 2021-10-21 | 2023-03-31 | 2023-06-01 | Underground | R16 | 2023-03-31 | 1 | 4 | 377 | 45 | 424 | 2021 | 2023 | R16
164924188123 | 166261188123 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-12-04 | 2020-04-17 | 2020-04-17 |  | 2021-04-29 | Underground | R16 | 2021-02-09 | 98 |  | 213 | 58 | 367 | 2019 | 2021 | R16
160640251765 | 161597251765 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-11 | 2021-10-12 | 2021-10-12 |  | 2021-11-13 | Overhead | R16 | 2021-10-21 | 2 |  | 8 | 17 | 25 | 2021 | 2021 | R16
164924236307 | 164405236307 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-03-30 | 2021-04-07 | 2021-06-23 |  | 2022-07-25 | Underground | R16 | 2022-06-06 | 7 | 56 | 249 | 36 | 345 | 2021 | 2022 | R16
161078262061 | 166824262061 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-20 | 2021-12-20 | 2021-12-20 |  | 2022-09-02 | Overhead | R16 |  | 1 |  |  |  | 185 | 2021 | 2022 | R16
166647279565 | 169936279565 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-04-04 | 2022-05-13 | 2022-05-16 |  | 2022-07-25 | Overhead | R16 |  | 30 | 2 |  |  | 81 | 2022 | 2022 | R16
165662271736 | 162282271736 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-18 | 2022-02-09 | 2022-03-08 |  | 2022-05-05 | Underground | R16 | 2022-05-05 | 17 | 20 | 43 |  | 78 | 2022 | 2022 | R16
160993283762 | 160923283762 | Electric Vehicle | UG R16 RESD AND NON RESD UD | Commercial | 2022-01-11 | 2022-01-11 | 2022-06-24 | 2023-02-23 | 2023-07-06 | Underground | R16 | 2023-02-23 | 1 | 119 | 175 | 96 | 388 | 2022 | 2023 | R16
165017173236 | 166243173236 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-04 | 2019-12-04 | 2019-12-04 |  | 2021-11-13 | Overhead | R16 | 2020-01-09 | 1 |  | 27 | 482 | 508 | 2019 | 2021 | R16
163610283411 | 162191283411 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-22 | 2022-06-22 | 2022-06-22 | 2023-02-22 | 2023-02-24 | Overhead | R16 | 2023-02-22 | 1 |  | 176 | 3 | 178 | 2022 | 2023 | R16
161261251911 | 162135251911 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-13 | 2021-10-13 | 2021-10-13 | 2021-12-01 | 2022-01-14 | Overhead | R16 | 2021-12-01 | 1 |  | 36 | 33 | 68 | 2021 | 2022 | R16
165175178803 | 166934178803 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-30 | 2020-01-30 | 2020-01-30 |  | 2020-06-29 | Overhead | R16 | 2020-04-23 | 1 |  | 61 | 48 | 108 | 2020 | 2020 | R16
162876283550 | 160913283550 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-16 | 2022-06-24 | 2022-06-24 |  | 2022-08-10 | Overhead | R16 | 2022-07-07 | 7 |  | 10 | 25 | 40 | 2022 | 2022 | R16
163441281981 | 167654281981 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-06-02 | 2022-06-03 | 2022-06-07 |  | 2022-08-11 | Underground | R16 |  | 2 | 3 |  |  | 51 | 2022 | 2022 | R16
165209175433 | 160575175433 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-12-31 | 2019-12-31 | 2019-12-31 |  | 2021-11-10 | Overhead | R16 | 2020-04-08 | 1 |  | 72 | 416 | 487 | 2019 | 2021 | R16
165209182440 | 163255182440 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-02-28 | 2020-02-28 | 2020-02-28 |  | 2020-06-09 | Overhead | R16 | 2020-04-08 | 1 |  | 29 | 45 | 73 | 2020 | 2020 | R16
165233174313 | 168072174313 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-12 | 2019-12-12 | 2019-12-12 |  | 2020-07-10 | Overhead | R16 | 2020-06-12 | 1 |  | 132 | 21 | 152 | 2019 | 2020 | R16
166333269035 | 160340269035 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-06 | 2021-10-06 | 2022-02-15 | 2022-03-11 | 2022-03-14 | Underground | R16 | 2022-03-11 | 1 | 95 | 19 | 2 | 114 | 2021 | 2022 | R16
165293254708 | 166337254708 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-02 | 2021-11-02 | 2021-11-02 | 2021-11-02 | 2022-01-07 | Overhead | R16 | 2021-11-02 | 1 |  |  | 49 | 49 | 2021 | 2022 | R16
165492254317 | 165820254317 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2021-10-28 | 2021-10-28 | 2021-10-28 | 2021-12-05 | 2021-12-08 | Overhead | R16 | 2021-12-05 | 1 |  | 27 | 3 | 30 | 2021 | 2021 | R16
166377262640 | 169460262640 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-01 | 2021-10-01 | 2021-12-27 | 2022-05-25 | 2022-06-13 | Underground | R16 | 2022-05-25 | 1 | 62 | 108 | 14 | 182 | 2021 | 2022 | R16
165109255705 | 167568255705 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-11-05 | 2021-11-05 | 2021-11-09 | 2022-04-24 | 2022-04-27 | Overhead | R16 | 2022-04-24 | 1 | 3 | 119 | 3 | 124 | 2021 | 2022 | R16
162318268359 | 166030268359 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-02-01 | 2022-02-01 | 2022-02-10 |  | 2023-01-10 | Underground | R16 | 2022-11-17 | 1 | 8 | 201 | 39 | 246 | 2022 | 2023 | R16
166336269183 | 169360269183 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-12 | 2021-11-12 | 2022-02-15 |  | 2022-04-25 | Underground | R16 | 2022-04-04 | 1 | 68 | 35 | 16 | 117 | 2021 | 2022 | R16
165284176072 | 166761176072 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-06 | 2019-12-06 | 2020-01-07 |  | 2020-06-09 | Underground | R16 | 2020-01-30 | 1 | 23 | 18 | 94 | 133 | 2019 | 2020 | R16
165301174488 | 168481174488 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-16 | 2019-12-16 | 2019-12-16 |  | 2020-06-09 | Overhead | R16 | 2020-03-24 | 1 |  | 72 | 56 | 127 | 2019 | 2020 | R16
167121259293 | 162899259293 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-30 | 2021-11-30 | 2021-11-30 | 2021-12-29 | 2021-12-30 | Overhead | R16 | 2021-12-29 | 1 |  | 22 | 2 | 23 | 2021 | 2021 | R16
165304185268 | 167025185268 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2020-01-31 | 2020-02-10 | 2020-03-24 |  | 2020-07-09 | Overhead | R16 |  | 7 | 32 |  |  | 115 | 2020 | 2020 | R16
169887270763 | 162277270763 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-28 | 2022-02-28 | 2022-02-28 | 2022-07-20 | 2022-07-21 | Overhead | R16 | 2022-07-20 | 1 |  | 103 | 2 | 104 | 2022 | 2022 | R16
165857275587 | 161390275587 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-11 | 2022-04-11 | 2022-04-11 |  | 2022-12-15 | Underground | R16 | 2022-10-20 | 1 |  | 139 | 41 | 179 | 2022 | 2022 | R16
165836272206 | 162633272206 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-15 | 2021-10-15 | 2022-03-10 | 2022-12-22 | 2023-04-04 | Overhead | R16 | 2022-12-22 | 1 | 105 | 206 | 74 | 383 | 2021 | 2023 | R16
169984284310 | 163974284310 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2022-09-15 | 2022-09-16 | Overhead | R16 | 2022-09-15 | 1 |  | 56 | 2 | 57 | 2022 | 2022 | R16
164393267123 | 160377267123 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-07 | 2022-02-01 | 2022-02-01 |  | 2022-08-03 | Overhead | R16 | 2022-06-16 | 18 |  | 98 | 35 | 149 | 2022 | 2022 | R16
165325201812 | 160899201812 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-02-18 | 2020-04-23 | 2020-08-26 |  | 2021-01-07 | Overhead | R16 |  | 48 | 90 |  |  | 233 | 2020 | 2021 | R16
165325201814 | 160901201814 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-02-18 | 2020-04-24 | 2020-08-26 |  | 2021-01-07 | Overhead | R16 |  | 49 | 89 |  |  | 233 | 2020 | 2021 | R16
169295283449 | 167192283449 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-02-04 | 2022-06-22 | 2022-06-22 | 2023-01-05 | 2023-01-05 | Underground | R16 | 2023-01-05 | 99 |  | 142 |  | 240 | 2022 | 2023 | R16
163401288324 | 168315288324 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-21 | 2022-08-08 | 2022-08-08 |  | 2023-05-05 | Overhead | R16 | 2023-03-10 | 13 |  | 155 | 41 | 207 | 2022 | 2023 | R16
165325208014 | 160911208014 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-02-18 | 2020-05-08 | 2020-10-23 |  | 2021-04-07 | Overhead | R16 |  | 59 | 121 |  |  | 297 | 2020 | 2021 | R16
164569283413 | 162184283413 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2022-06-22 | 2022-06-22 | 2022-06-22 | 2022-08-09 | 2023-07-18 | Overhead | R16 | 2022-08-09 | 1 |  | 35 | 246 | 280 | 2022 | 2023 | R16
168916288520 | 160561288520 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-10 | 2022-08-05 | 2022-08-09 |  | 2022-09-28 | Overhead | R16 | 2022-09-12 | 150 | 3 | 25 | 13 | 188 | 2022 | 2022 | R16
168828283636 | 162814283636 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-24 | 2022-06-24 | 2022-06-24 |  | 2022-07-29 | Overhead | R16 | 2022-07-20 | 1 |  | 19 | 8 | 26 | 2022 | 2022 | R16
162242254833 | 163314254833 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-18 | 2021-10-18 | 2021-11-03 | 2021-12-22 | 2022-02-02 | Underground | R16 | 2021-12-22 | 1 | 13 | 36 | 31 | 78 | 2021 | 2022 | R16
166889287022 | 169134287022 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-26 | 2022-07-26 | 2022-07-26 |  | 2022-12-04 | Overhead | R16 | 2022-10-31 | 1 |  | 70 | 25 | 94 | 2022 | 2022 | R16
163028285434 | 164182285434 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-01 | 2022-07-14 | 2022-07-14 |  | 2022-10-21 | Overhead | R16 | 2022-09-08 | 10 |  | 41 | 32 | 81 | 2022 | 2022 | R16
160815280627 | 163521280627 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-21 | 2022-05-24 | 2022-05-24 |  | 2022-09-15 | Underground | R16 | 2022-07-27 | 24 |  | 47 | 37 | 106 | 2022 | 2022 | R16
160512279883 | 166819279883 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-03-18 | 2022-03-22 | 2022-05-18 |  | 2022-06-30 | Overhead | R16 |  | 3 | 42 |  |  | 75 | 2022 | 2022 | R16
165485194756 | 166626194756 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-12-06 | 2019-12-09 | 2020-06-19 |  | 2020-10-06 | Overhead | R16 | 2020-07-23 | 2 | 140 | 25 | 54 | 218 | 2019 | 2020 | R16
160783276957 | 164354276957 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-27 | 2022-04-27 | 2022-04-27 | 2022-06-01 | 2022-07-25 | Overhead | R16 | 2022-06-01 | 1 |  | 26 | 39 | 64 | 2022 | 2022 | R16
165488275971 | 167023275971 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-09-21 | 2021-09-27 | 2022-04-15 | 2022-06-17 | 2022-06-23 | Underground | R16 | 2022-06-17 | 5 | 145 | 46 | 5 | 198 | 2021 | 2022 | R16
167116263207 | 168173263207 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-28 | 2022-01-03 | 2022-01-03 | 2022-04-20 | 2022-04-21 | Overhead | R16 | 2022-04-20 | 5 |  | 78 | 2 | 83 | 2021 | 2022 | R16
168873260562 | 164629260562 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-09 | 2021-12-09 | 2021-12-09 | 2022-03-04 | 2022-03-25 | Overhead | R16 | 2022-03-04 | 1 |  | 62 | 16 | 77 | 2021 | 2022 | R16
165497282021 | 165874282021 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-05-23 | 2022-05-23 | 2022-06-08 | 2022-06-12 | 2022-08-15 | Underground | R16 | 2022-06-12 | 1 | 13 | 3 | 46 | 61 | 2022 | 2022 | R16
163507287999 | 165047287999 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-19 | 2022-08-05 | 2022-08-05 | 2023-01-31 | 2023-02-08 | Underground | R16 | 2023-01-31 | 57 |  | 128 | 7 | 190 | 2022 | 2023 | R16
166239250290 | 169381250290 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-01 | 2021-10-01 | 2021-10-01 | 2021-12-29 | 2022-02-09 | Overhead | R16 | 2021-12-29 | 1 |  | 64 | 31 | 94 | 2021 | 2022 | R16
169733264780 | 167475264780 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-22 | 2021-12-22 | 2022-01-13 | 2022-04-06 | 2022-04-05 | Overhead | R16 | 2022-04-06 | 1 | 17 | 60 |  | 75 | 2021 | 2022 | R16
165574263621 | 169346263621 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-02-18 | 2022-02-19 | Underground | R16 | 2022-02-18 | 1 |  | 33 | 1 | 33 | 2022 | 2022 | R16
160190282587 | 160211282587 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-13 | 2022-06-13 | 2022-06-13 |  | 2022-10-21 | Overhead | R16 | 2022-08-12 | 1 |  | 45 | 51 | 95 | 2022 | 2022 | R16
168525255882 | 168544255882 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-09 | 2021-11-09 | 2021-11-09 |  | 2022-01-07 | Overhead | R16 | 2021-11-29 | 1 |  | 15 | 30 | 44 | 2021 | 2022 | R16
165576174397 | 165599174397 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-02 | 2019-12-02 | 2019-12-17 |  | 2020-12-15 | Underground | R16 | 2020-09-10 | 1 | 12 | 193 | 69 | 272 | 2019 | 2020 | R16
167378251211 | 160426251211 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-06 | 2021-10-06 | 2021-10-08 | 2021-11-09 | 2022-01-05 | Underground | R16 | 2021-11-09 | 1 | 3 | 23 | 42 | 66 | 2021 | 2022 | R16
161414286784 | 163807286784 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-29 | 2022-06-29 | 2022-07-25 | 2022-09-06 | 2022-09-28 | Overhead | R16 | 2022-09-06 | 1 | 19 | 32 | 17 | 66 | 2022 | 2022 | R16
165642174230 | 166248174230 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-05 | 2019-12-05 | 2019-12-12 |  | 2020-06-09 | Underground | R16 | 2020-01-22 | 1 | 6 | 30 | 100 | 134 | 2019 | 2020 | R16
161539272462 | 162048272462 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-02-25 | 2022-02-25 | 2022-03-14 |  | 2023-05-11 | Underground | R16 | 2023-02-07 | 1 | 12 | 237 | 68 | 315 | 2022 | 2023 | R16
160306308923 | 166857308923 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-03-18 | 2022-06-01 | 2023-02-09 | 2023-02-27 | 2023-03-16 | Overhead | R16 | 2023-02-27 | 54 | 182 | 13 | 14 | 260 | 2022 | 2023 | R16
166424274238 | 169120274238 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-03-30 | 2022-03-30 | 2022-03-30 | 2023-02-16 | 2023-02-17 | Overhead | R16 | 2023-02-16 | 1 |  | 232 | 2 | 233 | 2022 | 2023 | R16
163126278042 | 169470278042 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-03 | 2022-05-03 | 2022-05-03 |  | 2022-08-03 | Overhead | R16 |  | 1 |  |  |  | 67 | 2022 | 2022 | R16
165829184117 | 163860184117 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2020-01-16 | 2020-03-17 | 2020-03-17 |  | 2020-06-29 | Underground | R16 |  | 44 |  |  |  | 118 | 2020 | 2020 | R16
166133270241 | 161130270241 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-23 | 2022-02-23 | 2022-02-23 |  | 2022-04-08 | Overhead | R16 | 2022-04-08 | 1 |  | 33 |  | 33 | 2022 | 2022 | R16
169013275280 | 160923275280 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-04-07 | 2022-04-07 | 2022-04-07 | 2022-05-18 | 2022-05-18 | Overhead | R16 | 2022-05-18 | 1 |  | 30 |  | 30 | 2022 | 2022 | R16
168316264600 | 163416264600 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-03 | 2021-12-06 | 2022-01-12 | 2022-05-16 | 2022-05-18 | Underground | R16 | 2022-05-16 | 2 | 28 | 89 | 3 | 119 | 2021 | 2022 | R16
167900272551 | 162344272551 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-28 | 2022-02-28 | 2022-03-14 | 2022-05-23 | 2022-05-26 | Underground | R16 | 2022-05-23 | 1 | 11 | 51 | 4 | 64 | 2022 | 2022 | R16
163791277089 | 168734277089 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-11 | 2022-04-25 | 2022-04-25 |  | 2022-10-21 | Underground | R16 | 2022-08-30 | 52 |  | 92 | 39 | 181 | 2022 | 2022 | R16
169065279788 | 164894279788 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-05-18 | 2022-05-18 | 2022-05-18 | 2022-11-22 | 2022-11-23 | Overhead | R16 | 2022-11-22 | 1 |  | 135 | 2 | 136 | 2022 | 2022 | R16
163412290798 | 163829290798 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-25 | 2022-04-25 | 2022-08-31 |  | 2022-12-07 | Underground | R16 | 2022-10-06 | 1 | 93 | 27 | 45 | 163 | 2022 | 2022 | R16
165906176285 | 161657176285 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-07 | 2020-01-07 | 2020-01-07 |  | 2020-06-09 | Overhead | R16 | 2020-02-04 | 1 |  | 21 | 91 | 111 | 2020 | 2020 | R16
160211256903 | 168780256903 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-28 | 2021-09-28 | 2021-11-16 |  | 2023-06-06 | Underground | R16 | 2023-02-22 | 1 | 36 | 332 | 75 | 441 | 2021 | 2023 | R16
166549282290 | 169496282290 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-09 | 2022-06-10 | 2022-06-10 | 2022-12-01 | 2022-12-02 | Overhead | R16 | 2022-12-01 | 2 |  | 125 | 2 | 127 | 2022 | 2022 | R16
165939182927 | 166210182927 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-04 | 2019-12-04 | 2020-03-05 |  | 2021-11-10 | Underground | R16 | 2020-05-11 | 1 | 67 | 48 | 393 | 506 | 2019 | 2021 | R16
163668272150 | 164594272150 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2022-03-08 | 2022-03-10 | 2022-03-10 | 2022-03-31 | 2022-05-03 | Overhead | R16 | 2022-03-31 | 3 |  | 16 | 24 | 41 | 2022 | 2022 | R16
165473275269 | 167486275269 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-09-22 | 2022-04-08 | 2022-04-08 |  | 2022-06-10 | Overhead | R16 | 2022-05-18 | 143 |  | 29 | 18 | 188 | 2021 | 2022 | R16
165952181653 | 162073181653 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-24 | 2020-02-24 | 2020-02-24 |  | 2021-04-16 | Overhead | R16 | 2020-12-29 | 1 |  | 222 | 79 | 300 | 2020 | 2021 | R16
160768287135 | 161286287135 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-11 | 2022-04-11 | 2022-07-28 | 2022-08-29 | 2022-09-07 | Underground | R16 | 2022-08-29 | 1 | 79 | 23 | 8 | 108 | 2022 | 2022 | R16
165350252144 | 168988252144 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-09-29 | 2021-09-29 | 2021-10-14 |  | 2022-07-25 | Underground | R16 | 2022-06-07 | 1 | 12 | 169 | 35 | 214 | 2021 | 2022 | R16
160845280383 | 169713280383 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-04-01 | 2022-04-01 | 2022-05-23 |  | 2022-06-30 | Overhead | R16 |  | 1 | 37 |  |  | 65 | 2022 | 2022 | R16
166134178525 | 166193178525 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-12-04 | 2019-12-04 | 2020-01-28 |  | 2022-10-20 | Underground | R16 |  | 1 | 40 |  |  | 752 | 2019 | 2022 | R16
161319248850 | 166273248850 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-17 | 2021-09-17 | 2021-09-22 | 2021-10-04 | 2022-01-13 | Overhead | R16 | 2021-10-04 | 1 | 4 | 9 | 74 | 85 | 2021 | 2022 | R16
169761261744 | 165469261744 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-13 | 2021-12-17 | 2021-12-17 |  | 2022-07-25 | Overhead | R16 | 2022-05-16 | 5 |  | 107 | 51 | 161 | 2021 | 2022 | R16
167950282746 | 165048282746 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG R16 RESD AND NON RESD UD | Residential | 2022-05-19 | 2022-05-19 | 2022-06-15 | 2022-09-01 | 2023-11-17 | Underground | R16 | 2022-09-01 | 1 | 20 | 57 | 317 | 392 | 2022 | 2023 | R16
166215180197 | 166529180197 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-06 | 2019-12-06 | 2020-02-12 |  | 2020-06-09 | Underground | R16 | 2020-03-25 | 1 | 49 | 31 | 55 | 133 | 2019 | 2020 | R16
166222176419 | 162821176419 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-11 | 2020-01-11 | 2020-01-11 |  | 2022-10-19 | Overhead | R16 |  | 0 |  |  |  | 723 | 2020 | 2022 | R16
166229173477 | 166290173477 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-12-04 | 2019-12-04 | 2019-12-04 |  | 2020-10-06 | Overhead | R16 | 2020-08-11 | 1 |  | 180 | 41 | 220 | 2019 | 2020 | R16
167894277492 | 166499277492 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-03-17 | 2022-03-17 | 2022-04-28 |  | 2022-08-10 | Overhead | R16 | 2022-07-07 | 1 | 31 | 51 | 25 | 105 | 2022 | 2022 | R16
160708276984 | 163097276984 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-20 | 2022-04-25 | 2022-04-25 |  | 2022-07-26 | Underground | R16 | 2022-06-09 | 4 |  | 34 | 34 | 70 | 2022 | 2022 | R16
166296176176 | 162153176176 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-08 | 2020-01-08 | 2020-01-08 |  | 2020-06-09 | Overhead | R16 | 2020-04-03 | 1 |  | 63 | 48 | 110 | 2020 | 2020 | R16
162088265631 | 167462265631 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-09-22 | 2022-01-21 | 2022-01-21 |  | 2022-06-01 | Overhead | R16 | 2022-05-05 | 88 |  | 75 | 20 | 181 | 2021 | 2022 | R16
166315236350 | 168886236350 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-04-19 | 2021-04-19 | 2021-06-23 |  | 2022-08-03 | Underground | R16 |  | 1 | 48 |  |  | 338 | 2021 | 2022 | R16
160017251790 | 161776251790 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-10-12 | 2021-10-12 | 2021-10-12 | 2022-04-04 | 2022-05-03 | Overhead | R16 | 2022-04-04 | 1 |  | 125 | 22 | 146 | 2021 | 2022 | R16
166115264222 | 165441264222 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-12-12 | 2021-12-12 | 2022-01-10 | 2022-05-17 | 2022-06-07 | Underground | R16 | 2022-05-17 | 0 | 21 | 92 | 16 | 127 | 2021 | 2022 | R16
163086262131 | 167105262131 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2022-05-16 | 2022-06-30 | Overhead | R16 | 2022-05-16 | 1 |  | 105 | 34 | 138 | 2021 | 2022 | R16
161908272519 | 162201272519 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-18 | 2022-01-25 | 2022-03-15 |  | 2022-07-29 | Underground | R16 | 2022-07-26 | 6 | 36 | 96 | 4 | 139 | 2022 | 2022 | R16
167388300916 | 168606300916 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-07 | 2022-08-16 | 2022-11-18 | 2023-02-24 | 2023-09-05 | Underground | R16 | 2023-02-24 | 51 | 69 | 71 | 138 | 326 | 2022 | 2023 | R16
166400175608 | 160378175608 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-02 | 2020-01-02 | 2020-01-02 |  | 2020-07-08 | Overhead | R16 | 2020-05-14 | 1 |  | 96 | 40 | 135 | 2020 | 2020 | R16
163293257525 | 169612257525 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-15 | 2021-11-19 | 2021-11-19 |  | 2022-02-22 | Underground | R16 | 2022-01-21 | 5 |  | 46 | 23 | 72 | 2021 | 2022 | R16
168873276004 | 162469276004 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2022-04-15 | 2022-04-15 | 2022-04-15 |  | 2022-09-30 | Overhead | R16 | 2022-09-26 | 1 |  | 117 | 5 | 121 | 2022 | 2022 | R16
165513262234 | 166772262234 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-19 | 2021-12-22 | 2021-12-22 | 2022-04-27 | 2022-06-01 | Overhead | R16 | 2022-04-27 | 3 |  | 91 | 26 | 118 | 2021 | 2022 | R16
165036286180 | 167069286180 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-15 | 2022-07-19 | 2022-07-19 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 3 |  | 123 |  | 125 | 2022 | 2023 | R16
165668255682 | 167279255682 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2021-11-04 | 2021-11-08 | 2021-11-08 | 2022-01-25 | 2022-02-28 | Overhead | R16 | 2022-01-25 | 3 |  | 57 | 25 | 83 | 2021 | 2022 | R16
166484179208 | 167401179208 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-03 | 2020-02-03 | 2020-02-03 |  | 2020-07-01 | Overhead | R16 | 2020-04-30 | 1 |  | 64 | 45 | 108 | 2020 | 2020 | R16
166505178217 | 163643178217 | NON-RESIDENTIAL - SMALL OFFICE | R16 RESD AND NON RESD US | Commercial | 2020-01-15 | 2020-01-28 | 2020-01-28 |  | 2020-06-09 | Underground | R16 |  | 10 |  |  |  | 105 | 2020 | 2020 | R16
166313284762 | 163980284762 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-25 | 2022-04-25 | 2022-07-06 |  | 2023-11-29 | Underground | R16 | 2023-10-06 | 1 | 53 | 328 | 39 | 418 | 2022 | 2023 | R16
161625273282 | 167121273282 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-21 | 2022-03-21 | 2022-03-21 |  | 2022-07-13 | Overhead | R16 | 2022-07-13 | 1 |  | 83 |  | 83 | 2022 | 2022 | R16
166547183701 | 166598183701 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-12-06 | 2019-12-06 | 2020-03-10 |  | 2020-07-01 | Underground | R16 | 2020-05-01 | 1 | 68 | 39 | 44 | 149 | 2019 | 2020 | R16
166757263252 | 164157263252 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2021-10-21 | 2021-10-21 | 2022-01-03 | 2022-04-12 | 2022-04-13 | Underground | R16 | 2022-04-12 | 1 | 53 | 72 | 2 | 125 | 2021 | 2022 | R16
165168274643 | 169594274643 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-31 | 2022-04-01 | 2022-04-01 |  | 2022-06-20 | Overhead | R16 | 2022-05-27 | 2 |  | 41 | 17 | 58 | 2022 | 2022 | R16
166645178940 | 161791178940 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-07 | 2020-01-07 | 2020-01-31 |  | 2020-10-06 | Underground | R16 | 2020-07-09 | 1 | 19 | 115 | 64 | 196 | 2020 | 2020 | R16
166816286200 | 167649286200 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-19 | 2022-07-19 | 2022-07-19 | 2022-08-22 | 2022-10-21 | Overhead | R16 | 2022-08-22 | 1 |  | 25 | 45 | 69 | 2022 | 2022 | R16
169313275768 | 162057275768 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-13 | 2022-04-13 | 2022-04-13 |  | 2023-06-05 | Overhead | R16 | 2023-05-24 | 1 |  | 291 | 9 | 299 | 2022 | 2023 | R16
160476274369 | 164980274369 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-09 | 2022-03-30 | 2022-03-30 | 2023-01-11 | 2023-06-13 | Overhead | R16 | 2023-01-11 | 16 |  | 206 | 110 | 330 | 2022 | 2023 | R16
166665175610 | 166763175610 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-09 | 2019-12-09 | 2020-01-02 |  | 2020-06-09 | Underground | R16 | 2020-03-02 | 1 | 19 | 43 | 72 | 132 | 2019 | 2020 | R16
166490271157 | 160180271157 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-16 | 2021-11-16 | 2022-03-03 | 2022-04-06 | 2022-04-07 | Underground | R16 | 2022-04-06 | 1 | 78 | 25 | 2 | 103 | 2021 | 2022 | R16
168915262764 | 168084262764 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-28 | 2021-12-28 | 2021-12-28 | 2022-01-20 | 2022-01-21 | Overhead | R16 | 2022-01-20 | 1 |  | 18 | 2 | 19 | 2021 | 2022 | R16
166673181333 | 161752181333 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-21 | 2020-02-21 | 2020-02-21 |  | 2020-06-09 | Overhead | R16 | 2020-03-26 | 1 |  | 25 | 54 | 78 | 2020 | 2020 | R16
166913252631 | 163196252631 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-18 | 2021-10-18 | 2021-10-18 |  | 2022-05-03 | Overhead | R16 | 2022-04-21 | 1 |  | 134 | 9 | 142 | 2021 | 2022 | R16
166700175385 | 168778175385 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-16 | 2019-12-16 | 2019-12-30 |  | 2021-11-10 | Underground | R16 | 2020-01-22 | 1 | 11 | 18 | 471 | 498 | 2019 | 2021 | R16
169084272361 | 165304272361 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-03-11 | 2022-03-11 | 2022-03-11 |  | 2022-10-26 | Underground | R16 | 2022-09-15 | 1 |  | 135 | 30 | 164 | 2022 | 2022 | R16
166702174985 | 167248174985 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-11 | 2019-12-22 | 2019-12-22 |  | 2020-07-01 | Underground | R16 | 2020-04-29 | 8 |  | 93 | 46 | 146 | 2019 | 2020 | R16
168610286982 | 161459286982 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-20 | 2022-06-20 | 2022-07-26 |  | 2022-09-11 | Underground | R16 | 2022-08-31 | 1 | 27 | 27 | 8 | 60 | 2022 | 2022 | R16
169736279228 | 163718279228 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-13 | 2022-05-13 | 2022-05-13 | 2022-05-13 | 2022-06-12 | Underground | R16 | 2022-05-13 | 1 |  |  | 21 | 21 | 2022 | 2022 | R16
166703194042 | 160775194042 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-08 | 2020-04-08 | 2020-06-11 |  | 2020-08-28 | Overhead | R16 |  | 1 | 47 |  |  | 103 | 2020 | 2020 | R16
168083283904 | 163031283904 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-06-26 | 2022-06-27 | 2022-06-27 |  | 2023-05-04 | Overhead | R16 | 2023-02-14 | 1 |  | 167 | 58 | 224 | 2022 | 2023 | R16
166934275556 | 161634275556 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2022-04-12 | 2022-04-12 | 2022-04-12 | 2022-05-29 | 2022-06-01 | Overhead | R16 | 2022-05-29 | 1 |  | 34 | 3 | 37 | 2022 | 2022 | R16
162460279668 | 164741279668 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-17 | 2022-05-17 | 2022-05-17 |  | 2022-08-03 | Overhead | R16 | 2022-06-21 | 1 |  | 26 | 32 | 57 | 2022 | 2022 | R16
160056275789 | 161416275789 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-11 | 2022-04-14 | 2022-04-14 | 2023-04-05 | 2023-06-13 | Overhead | R16 | 2023-04-05 | 4 |  | 255 | 50 | 307 | 2022 | 2023 | R16
166800181901 | 162236181901 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-25 | 2020-02-25 | 2020-02-25 |  | 2020-06-09 | Overhead | R16 | 2020-04-06 | 1 |  | 30 | 47 | 76 | 2020 | 2020 | R16
166801178747 | 166707178747 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-30 | 2020-01-30 | 2020-01-30 |  | 2022-10-19 | Overhead | R16 |  | 1 |  |  |  | 710 | 2020 | 2022 | R16
164809269192 | 169486269192 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-16 | 2022-02-16 | 2022-02-16 | 2022-03-22 | 2022-04-22 | Overhead | R16 | 2022-03-22 | 1 |  | 25 | 24 | 48 | 2022 | 2022 | R16
166821174292 | 167982174292 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-12 | 2019-12-12 | 2019-12-12 |  | 2020-01-08 | Overhead | R16 | 2019-12-31 | 1 |  | 14 | 7 | 20 | 2019 | 2020 | R16
162618295603 | 164831295603 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-30 | 2022-09-30 | 2022-10-01 | 2023-07-06 | 2023-07-31 | Overhead | R16 | 2023-07-06 | 1 | 1 | 199 | 18 | 217 | 2022 | 2023 | R16
166830175429 | 160517175429 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-31 | 2019-12-31 | 2019-12-31 |  | 2023-06-07 | Overhead | R16 | 2020-02-14 | 1 |  | 34 | 864 | 897 | 2019 | 2023 | R16
166324290791 | 165908290791 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-24 | 2022-08-30 | 2022-08-31 |  | 2023-01-10 | Overhead | R16 | 2022-11-02 | 5 | 2 | 46 | 50 | 100 | 2022 | 2023 | R16
160394328329 | 163899328329 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-31 | 2023-07-31 | 2023-08-14 | 2023-08-24 | 2023-10-11 | Underground | R16 | 2023-08-24 | 1 | 11 | 9 | 35 | 53 | 2023 | 2023 | R16
166895183032 | 167875183032 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-04 | 2020-02-04 | 2020-03-05 |  | 2020-08-28 | Underground | R16 | 2020-07-07 | 1 | 23 | 89 | 39 | 149 | 2020 | 2020 | R16
166685303289 | 160690303289 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-01 | 2022-11-01 | 2022-12-21 |  | 2023-08-09 | Underground | R16 | 2023-03-24 | 1 | 37 | 68 | 99 | 202 | 2022 | 2023 | R16
166914181364 | 168379181364 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-16 | 2019-12-16 | 2020-02-20 |  | 2021-04-16 | Underground | R16 | 2021-01-05 | 1 | 49 | 229 | 74 | 350 | 2019 | 2021 | R16
163578332122 | 167527332122 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-17 | 2023-09-08 | 2023-09-08 | 2023-09-22 | 2023-11-07 | Overhead | R16 | 2023-09-22 | 17 |  | 11 | 33 | 59 | 2023 | 2023 | R16
166117309382 | 169306309382 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-25 | 2022-10-25 | 2023-02-14 |  | 2023-06-19 | Underground | R16 | 2023-05-13 | 1 | 81 | 64 | 26 | 170 | 2022 | 2023 | R16
161750301592 | 165323301592 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-29 | 2022-11-29 | 2022-11-29 |  | 2023-05-02 | Overhead | R16 | 2023-01-12 | 1 |  | 33 | 79 | 111 | 2022 | 2023 | R16
166972182545 | 166383182545 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-29 | 2020-01-29 | 2020-03-02 |  | 2020-07-09 | Underground | R16 | 2020-06-08 | 1 | 24 | 71 | 24 | 117 | 2020 | 2020 | R16
160353288922 | 161716288922 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-04 | 2022-08-13 | 2022-08-13 | 2022-12-15 | 2022-12-20 | Overhead | R16 | 2022-12-15 | 7 |  | 89 | 4 | 99 | 2022 | 2022 | R16
166188301241 | 164255301241 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2022-11-21 | 2022-11-21 | 2022-11-21 | 2023-07-19 | 2023-07-20 | Overhead | R16 | 2023-07-19 | 1 |  | 173 | 2 | 174 | 2022 | 2023 | R16
162484300790 | 161960300790 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-08 | 2022-11-16 | 2022-11-16 |  | 2023-10-02 | Overhead | R16 | 2023-06-19 | 7 |  | 154 | 76 | 235 | 2022 | 2023 | R16
169036294394 | 162411294394 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-09-19 | 2022-09-19 | 2022-09-22 |  | 2023-04-19 | Underground | R16 |  | 1 | 4 |  |  | 153 | 2022 | 2023 | R16
161686287762 | 161292287762 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-03 | 2022-08-03 | 2022-08-03 |  | 2022-09-28 | Overhead | R16 | 2022-09-27 | 1 |  | 40 | 2 | 41 | 2022 | 2022 | R16
160848298514 | 164316298514 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-28 | 2022-10-28 | 2022-10-28 | 2022-12-27 | 2022-12-29 | Overhead | R16 | 2022-12-27 | 23 |  | 43 | 3 | 67 | 2022 | 2022 | R16
163051337060 | 165850337060 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-26 | 2023-09-26 | 2023-10-26 | 2023-11-07 | 2023-12-07 | Overhead | R16 | 2023-11-07 | 1 | 23 | 9 | 23 | 53 | 2023 | 2023 | R16
167321202107 | 166707202107 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-08-26 | 2020-08-26 | 2020-08-28 |  | 2020-12-17 | Overhead | R16 |  | 1 | 3 |  |  | 82 | 2020 | 2020 | R16
168017302811 | 167156302811 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-09 | 2022-12-09 | 2022-12-09 | 2023-11-10 | 2023-11-14 | Overhead | R16 | 2023-11-10 | 1 |  | 241 | 3 | 243 | 2022 | 2023 | R16
169762309586 | 163523309586 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-16 | 2022-11-16 | 2023-02-16 |  | 2023-08-18 | Underground | R16 | 2023-04-28 | 1 | 67 | 52 | 81 | 198 | 2022 | 2023 | R16
161157288104 | 169934288104 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2022-07-28 | 2022-07-29 | 2022-08-05 | 2022-08-10 | 2022-08-22 | Underground | R16 | 2022-08-10 | 2 | 6 | 4 | 9 | 18 | 2022 | 2022 | R16
160989295261 | 164161295261 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-09-28 | 2022-09-28 | 2022-09-28 | 2022-12-16 | 2023-01-11 | Overhead | R16 | 2022-12-16 | 1 |  | 58 | 19 | 76 | 2022 | 2023 | R16
163146295237 | 162273295237 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-19 | 2022-09-19 | 2022-09-28 | 2022-11-01 | 2022-11-03 | Underground | R16 | 2022-11-01 | 1 | 8 | 25 | 3 | 34 | 2022 | 2022 | R16
160791302383 | 162712302383 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-10 | 2022-11-13 | 2022-12-05 |  | 2023-06-05 | Underground | R16 | 2023-05-25 | 2 | 16 | 124 | 8 | 148 | 2022 | 2023 | R16
160107339004 | 162409339004 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-11-02 | 2023-11-02 | 2023-11-07 | 2023-12-13 | 2023-12-15 | Overhead | R16 | 2023-12-13 | 1 | 4 | 27 | 3 | 32 | 2023 | 2023 | R16
168032180304 | 169623180304 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-12 | 2020-02-12 | 2020-02-12 |  | 2020-06-09 | Overhead | R16 | 2020-03-12 | 1 |  | 22 | 64 | 85 | 2020 | 2020 | R16
169522325383 | 161353325383 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-17 | 2023-07-17 | 2023-07-17 |  | 2023-08-16 | Underground | R16 | 2023-07-17 | 1 |  |  | 23 | 23 | 2023 | 2023 | R16
168059175140 | 169960175140 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-23 | 2019-12-23 | 2019-12-23 |  | 2020-06-09 | Overhead | R16 | 2020-03-11 | 1 |  | 58 | 65 | 122 | 2019 | 2020 | R16
162575299392 | 161417299392 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-04 | 2022-11-04 | 2022-11-04 | 2023-01-25 | 2023-02-10 | Overhead | R16 | 2023-01-25 | 1 |  | 59 | 13 | 71 | 2022 | 2023 | R16
166619290739 | 166933290739 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-29 | 2022-09-01 | 2022-09-01 | 2022-11-03 | 2023-01-10 | Overhead | R16 | 2022-11-03 | 4 |  | 46 | 49 | 97 | 2022 | 2023 | R16
167261295344 | 161772295344 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-15 | 2022-09-15 | 2022-09-28 | 2022-10-11 | 2022-12-04 | Underground | R16 | 2022-10-11 | 1 | 10 | 10 | 39 | 57 | 2022 | 2022 | R16
163660333584 | 163749333584 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-15 | 2023-09-15 | 2023-09-25 | 2023-09-27 | 2023-10-19 | Overhead | R16 | 2023-09-27 | 1 | 7 | 3 | 17 | 25 | 2023 | 2023 | R16
165707334481 | 165918334481 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-27 | 2023-09-27 | 2023-10-03 | 2023-10-17 | 2023-11-10 | Overhead | R16 | 2023-10-17 | 1 | 5 | 11 | 19 | 33 | 2023 | 2023 | R16
169334294453 | 162473294453 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-20 | 2022-09-20 | 2022-09-21 | 2023-01-26 | 2023-04-27 | Overhead | R16 | 2023-01-26 | 1 | 2 | 92 | 66 | 158 | 2022 | 2023 | R16
168211244213 | 168261244213 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2021-08-12 | 2021-08-19 | 2021-08-19 |  | 2022-01-18 | Underground | R16 |  | 6 |  |  |  | 114 | 2021 | 2022 | R16
168116310466 | 163140310466 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2022-11-14 | 2023-01-19 | 2023-02-24 |  | 2023-06-16 | Overhead | R16 |  | 49 | 27 |  |  | 155 | 2022 | 2023 | R16
168125296321 | 165284296321 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-10-04 | 2022-10-04 | 2022-10-07 | 2023-08-02 | 2023-08-23 | Underground | R16 | 2023-08-02 | 1 | 4 | 214 | 16 | 232 | 2022 | 2023 | R16
162368315358 | 164112315358 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-11-18 | 2022-11-18 | 2023-04-10 | 2023-07-06 | 2023-10-13 | Overhead | R16 | 2023-07-06 | 1 | 102 | 64 | 72 | 236 | 2022 | 2023 | R16
168255179179 | 161040179179 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-03 | 2020-01-03 | 2020-02-04 |  | 2021-11-08 | Overhead | R16 | 2021-04-29 | 1 | 23 | 323 | 138 | 482 | 2020 | 2021 | R16
167285297406 | 167699297406 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-18 | 2022-10-18 | 2022-10-18 | 2023-01-11 | 2023-01-28 | Overhead | R16 | 2023-01-11 | 1 |  | 62 | 13 | 74 | 2022 | 2023 | R16
167933294588 | 162216294588 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-19 | 2022-09-19 | 2022-09-22 | 2022-11-23 | 2022-11-24 | Overhead | R16 | 2022-11-23 | 1 | 4 | 45 | 2 | 49 | 2022 | 2022 | R16
168299178607 | 165117178607 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-01-22 | 2020-01-22 | 2020-01-30 |  | 2020-07-08 | Overhead | R16 | 2020-04-20 | 1 | 7 | 58 | 58 | 121 | 2020 | 2020 | R16
169576336643 | 163326336643 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-27 | 2023-07-27 | 2023-10-23 | 2023-11-15 | 2023-12-14 | Underground | R16 | 2023-11-15 | 1 | 63 | 18 | 22 | 101 | 2023 | 2023 | R16
168300181085 | 167367181085 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-03 | 2020-02-03 | 2020-02-18 |  | 2022-10-20 | Underground | R16 |  | 1 | 12 |  |  | 709 | 2020 | 2022 | R16
169456325592 | 161921325592 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-19 | 2023-07-19 | 2023-07-19 | 2023-08-18 | 2023-09-27 | Overhead | R16 | 2023-08-18 | 1 |  | 23 | 29 | 51 | 2023 | 2023 | R16
164634332022 | 162385332022 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-07 | 2023-09-07 | 2023-09-07 | 2023-09-22 | 2023-11-07 | Overhead | R16 | 2023-09-22 | 1 |  | 12 | 33 | 44 | 2023 | 2023 | R16
166362290512 | 166865290512 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-08-29 | 2022-08-29 | 2022-08-29 |  | 2022-10-26 | Underground | R16 | 2022-09-12 | 1 |  | 11 | 33 | 43 | 2022 | 2022 | R16
162938326744 | 162944326744 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2023-07-25 | 2023-07-25 | 2023-07-28 | 2023-08-17 | 2023-08-18 | Underground | R16 | 2023-08-17 | 1 | 4 | 15 | 2 | 19 | 2023 | 2023 | R16
168336177894 | 165426177894 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-23 | 2020-01-23 | 2020-01-23 |  | 2020-06-09 | Overhead | R16 | 2020-03-06 | 1 |  | 32 | 68 | 99 | 2020 | 2020 | R16
162305307731 | 164268307731 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-16 | 2022-08-17 | 2023-01-31 |  | 2023-08-02 | Underground | R16 | 2023-04-18 | 2 | 120 | 56 | 77 | 252 | 2022 | 2023 | R16
165724297664 | 168247297664 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-20 | 2022-10-20 | 2022-10-20 | 2022-11-09 | 2022-12-22 | Overhead | R16 | 2022-11-09 | 1 |  | 15 | 32 | 46 | 2022 | 2022 | R16
169519299921 | 161954299921 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-08 | 2022-11-08 | 2022-11-08 | 2022-12-21 | 2023-04-01 | Overhead | R16 | 2022-12-21 | 1 |  | 32 | 73 | 104 | 2022 | 2023 | R16
164668287141 | 169556287141 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-27 | 2022-07-27 | 2022-07-27 | 2023-01-22 | 2023-07-10 | Overhead | R16 | 2023-01-22 | 1 |  | 128 | 121 | 249 | 2022 | 2023 | R16
163652332290 | 165698332290 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-08-08 | 2023-08-08 | 2023-09-11 | 2023-10-03 | 2023-11-28 | Underground | R16 | 2023-10-03 | 1 | 25 | 17 | 41 | 81 | 2023 | 2023 | R16
168648285249 | 165712285249 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2022-07-11 | 2022-07-11 | 2022-07-11 |  | 2022-09-29 | Overhead | R16 | 2022-08-15 | 1 |  | 26 | 34 | 59 | 2022 | 2022 | R16
162755264217 | 164701264217 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-08 | 2021-12-08 | 2022-01-11 | 2022-04-05 | 2022-04-05 | Underground | R16 | 2022-04-05 | 1 | 25 | 61 |  | 85 | 2021 | 2022 | R16
160270276537 | 163138276537 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-20 | 2022-04-20 | 2022-04-20 | 2022-09-06 | 2023-02-10 | Overhead | R16 | 2022-09-06 | 1 |  | 100 | 114 | 213 | 2022 | 2023 | R16
164520279108 | 163447279108 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-12 | 2022-05-12 | 2022-05-12 | 2022-05-16 | 2022-07-26 | Overhead | R16 | 2022-05-16 | 1 |  | 3 | 52 | 54 | 2022 | 2022 | R16
168383274978 | 160707274978 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential Subdivision | 2022-02-22 | 2022-02-22 | 2022-04-06 |  | 2022-05-05 | Overhead | R16 |  | 1 | 32 |  |  | 53 | 2022 | 2022 | R16
160698276290 | 162774276290 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-19 | 2022-04-19 | 2022-04-19 |  | 2022-09-22 | Overhead | R16 | 2022-09-21 | 1 |  | 112 | 2 | 113 | 2022 | 2022 | R16
166848252586 | 169086252586 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-30 | 2021-09-30 | 2021-10-18 | 2022-04-26 | 2022-05-31 | Underground | R16 | 2022-04-26 | 1 | 13 | 137 | 26 | 174 | 2021 | 2022 | R16
165561265380 | 162783265380 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-19 | 2022-01-19 | 2022-01-19 |  | 2022-03-25 | Overhead | R16 | 2022-03-10 | 1 |  | 37 | 12 | 48 | 2022 | 2022 | R16
162420268542 | 168302268542 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-10 | 2022-02-10 | 2022-02-10 | 2022-03-02 | 2022-04-01 | Overhead | R16 | 2022-03-02 | 1 |  | 15 | 23 | 37 | 2022 | 2022 | R16
162314272039 | 164593272039 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-03-08 | 2022-03-08 | 2022-03-10 |  | 2023-01-05 | Overhead | R16 | 2022-09-26 | 1 | 3 | 143 | 74 | 218 | 2022 | 2023 | R16
168682300858 | 162880300858 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-05-10 | 2022-05-31 | 2022-11-17 |  | 2023-11-02 | Underground | R16 |  | 16 | 123 |  |  | 388 | 2022 | 2023 | R16
168787180347 | 169470180347 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-19 | 2019-12-19 | 2020-02-13 |  | 2020-07-02 | Underground | R16 | 2020-05-04 | 1 | 41 | 58 | 44 | 141 | 2019 | 2020 | R16
160065277472 | 165201277472 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-28 | 2022-04-28 | 2022-04-29 |  | 2022-07-21 | Overhead | R16 | 2022-07-21 | 1 | 2 | 60 |  | 61 | 2022 | 2022 | R16
164838281333 | 167598281333 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-02 | 2022-06-02 | 2022-06-02 |  | 2022-10-21 | Overhead | R16 | 2022-08-15 | 1 |  | 53 | 50 | 102 | 2022 | 2022 | R16
166981278657 | 162758278657 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2022-05-10 | 2022-05-10 | 2022-05-10 | 2022-07-20 | 2022-09-28 | Underground | R16 | 2022-07-20 | 1 |  | 52 | 51 | 102 | 2022 | 2022 | R16
165570250447 | 169478250447 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-10-01 | 2021-10-01 | 2021-10-01 | 2021-11-29 | 2021-12-14 | Overhead | R16 | 2021-11-29 | 1 |  | 42 | 12 | 53 | 2021 | 2021 | R16
161914265077 | 166390265077 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-16 | 2021-12-16 | 2022-01-19 | 2022-10-02 | 2022-10-05 | Overhead | R16 | 2022-10-02 | 1 | 25 | 183 | 3 | 210 | 2021 | 2022 | R16
168944264257 | 161012264257 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-11-22 | 2021-12-22 | 2022-01-10 |  | 2022-02-22 | Overhead | R16 |  | 23 | 14 |  |  | 67 | 2021 | 2022 | R16
167150278199 | 163664278199 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-22 | 2022-05-04 | 2022-05-04 | 2022-08-16 | 2022-08-17 | Overhead | R16 | 2022-08-16 | 9 |  | 75 | 2 | 84 | 2022 | 2022 | R16
168463280801 | 164299280801 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-16 | 2022-05-16 | 2022-05-25 |  | 2022-10-21 | Underground | R16 | 2022-09-27 | 1 | 8 | 90 | 19 | 115 | 2022 | 2022 | R16
168892176893 | 160389176893 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-12-31 | 2020-01-02 | 2020-01-15 |  | 2020-12-14 | Underground | R16 | 2020-09-08 | 3 | 10 | 170 | 70 | 250 | 2019 | 2020 | R16
166317284274 | 164301284274 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-01 | 2022-07-01 | 2022-07-01 | 2023-08-17 | 2023-09-20 | Underground | R16 | 2023-08-17 | 1 |  | 295 | 25 | 319 | 2022 | 2023 | R16
167970270680 | 169323270680 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-15 | 2022-02-15 | 2022-02-25 | 2022-08-24 | 2022-10-21 | Underground | R16 | 2022-08-24 | 1 | 9 | 129 | 43 | 179 | 2022 | 2022 | R16
163575286158 | 167558286158 | RESIDENTIAL - MOBILE HOME | OH R16 RES NON RES OS | Residential | 2022-07-19 | 2022-07-19 | 2022-07-19 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 1 |  | 123 |  | 123 | 2022 | 2023 | R16
165309260475 | 169237260475 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-12 | 2021-11-12 | 2021-12-09 | 2022-04-19 | 2022-06-03 | Underground | R16 | 2022-04-19 | 1 | 20 | 94 | 34 | 146 | 2021 | 2022 | R16
168985176443 | 162227176443 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-09 | 2020-01-09 | 2020-01-09 |  | 2020-06-09 | Overhead | R16 | 2020-02-27 | 1 |  | 36 | 74 | 109 | 2020 | 2020 | R16
165411285357 | 160854285357 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-16 | 2022-06-16 | 2022-07-13 |  | 2022-09-30 | Underground | R16 | 2022-08-22 | 1 | 20 | 29 | 30 | 77 | 2022 | 2022 | R16
169033177536 | 164151177536 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-16 | 2020-01-16 | 2020-01-21 |  | 2020-06-09 | Underground | R16 | 2020-02-27 | 1 | 4 | 28 | 74 | 104 | 2020 | 2020 | R16
166888249932 | 168529249932 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-28 | 2021-09-29 | 2021-09-29 | 2022-03-21 | 2022-04-22 | Overhead | R16 | 2022-03-21 | 2 |  | 124 | 25 | 149 | 2021 | 2022 | R16
166925288450 | 167986288450 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-20 | 2022-07-20 | 2022-08-10 |  | 2023-01-10 | Underground | R16 | 2022-11-16 | 1 | 16 | 71 | 40 | 125 | 2022 | 2023 | R16
163680261983 | 169907261983 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-11-16 | 2021-11-16 | 2021-12-20 | 2022-12-01 | 2023-01-24 | Underground | R16 | 2022-12-01 | 1 | 25 | 249 | 39 | 311 | 2021 | 2023 | R16
169058183939 | 169534183939 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-20 | 2019-12-20 | 2020-03-13 |  | 2022-10-20 | Underground | R16 |  | 1 | 61 |  |  | 740 | 2019 | 2022 | R16
166647280122 | 160832280122 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-04-07 | 2022-04-07 | 2022-05-20 |  | 2022-07-25 | Overhead | R16 |  | 1 | 32 |  |  | 78 | 2022 | 2022 | R16
169113194543 | 162432194543 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-16 | 2020-06-16 | 2020-06-16 |  | 2020-07-14 | Underground | R16 | 2020-06-17 | 1 |  | 2 | 20 | 21 | 2020 | 2020 | R16
161057284537 | 168591284537 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-03-28 |  | 2022-04-13 | 2022-07-13 | 2022-09-16 | Overhead | R16 | 2022-07-13 |  |  | 66 | 48 | 125 | 2022 | 2022 | R16
167039258983 | 167341258983 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-04 | 2021-11-29 | 2021-11-29 |  | 2022-03-03 | Overhead | R16 | 2022-02-04 | 18 |  | 50 | 20 | 86 | 2021 | 2022 | R16
167339284727 | 165099284727 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-05-19 | 2022-06-29 | 2022-07-06 | 2023-01-05 | 2023-01-05 | Underground | R16 | 2023-01-05 | 30 | 6 | 132 |  | 166 | 2022 | 2023 | R16
169217178299 | 166092178299 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-27 | 2020-01-27 | 2020-01-27 |  | 2020-06-09 | Overhead | R16 | 2020-03-11 | 1 |  | 33 | 65 | 97 | 2020 | 2020 | R16
164867270190 | 160930270190 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-22 | 2022-02-22 | 2022-02-23 | 2022-03-08 | 2022-05-10 | Overhead | R16 | 2022-03-08 | 1 | 2 | 10 | 46 | 56 | 2022 | 2022 | R16
165105270512 | 160285270512 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-18 | 2022-02-25 | 2022-02-25 |  | 2022-04-11 | Overhead | R16 | 2022-04-11 | 6 |  | 32 |  | 37 | 2022 | 2022 | R16
169242183499 | 160984183499 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2020-01-03 | 2020-03-04 | 2020-03-10 |  | 2020-08-28 | Underground | R16 |  | 44 | 5 |  |  | 171 | 2020 | 2020 | R16
162467263120 | 168574263120 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-11-10 | 2021-11-22 | 2022-01-01 |  | 2023-08-09 | Underground | R16 |  | 9 | 30 |  |  | 456 | 2021 | 2023 | R16
160164282599 | 160183282599 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-14 | 2022-06-14 | 2022-06-14 | 2022-08-19 | 2022-08-22 | Overhead | R16 | 2022-08-19 | 1 |  | 49 | 2 | 50 | 2022 | 2022 | R16
168620254930 | 160071254930 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-05 | 2021-11-03 | 2021-11-03 | 2022-02-23 | 2022-03-31 | Underground | R16 | 2022-02-23 | 22 |  | 81 | 27 | 128 | 2021 | 2022 | R16
161347269924 | 163057269924 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-20 | 2022-02-22 | 2022-02-22 |  | 2022-06-12 | Overhead | R16 | 2022-05-23 | 24 |  | 65 | 15 | 102 | 2022 | 2022 | R16
164294282640 | 165734282640 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-23 | 2022-05-23 | 2022-06-14 | 2022-09-07 | 2022-09-08 | Underground | R16 | 2022-09-07 | 1 | 17 | 62 | 2 | 79 | 2022 | 2022 | R16
161807256255 | 169235256255 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-12-03 | 2021-12-06 | Overhead | R16 | 2021-12-03 | 1 |  | 16 | 2 | 17 | 2021 | 2021 | R16
169351265511 | 162437265511 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-18 | 2022-01-18 | 2022-01-20 | 2022-03-27 | 2022-03-30 | Overhead | R16 | 2022-03-27 | 1 | 3 | 47 | 3 | 52 | 2022 | 2022 | R16
165172270785 | 162351270785 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-28 | 2022-02-28 | 2022-02-28 | 2022-05-31 | 2022-06-30 | Overhead | R16 | 2022-05-31 | 1 |  | 67 | 23 | 89 | 2022 | 2022 | R16
169446193607 | 169072193607 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-30 | 2020-06-08 | 2020-06-08 |  | 2022-07-27 | Overhead | R16 | 2021-07-30 | 51 |  | 300 | 259 | 608 | 2020 | 2022 | R16
161771267451 | 163691267451 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-24 | 2022-02-03 | 2022-02-03 |  | 2022-06-12 | Overhead | R16 | 2022-03-07 | 9 |  | 23 | 70 | 100 | 2022 | 2022 | R16
169472179054 | 167492179054 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-03 | 2020-02-03 | 2020-02-03 |  | 2020-06-29 | Overhead | R16 | 2020-04-23 | 1 |  | 59 | 48 | 106 | 2020 | 2020 | R16
164770285616 | 169475285616 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-09 | 2022-06-09 | 2022-07-14 | 2022-09-26 | 2022-09-27 | Underground | R16 | 2022-09-26 | 1 | 26 | 53 | 2 | 79 | 2022 | 2022 | R16
165242276085 | 162311276085 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-14 | 2022-04-16 | 2022-04-16 |  | 2023-03-10 | Overhead | R16 | 2023-02-22 | 2 |  | 223 | 13 | 237 | 2022 | 2023 | R16
169520181259 | 161573181259 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-02-21 | 2020-02-21 | 2020-02-21 |  | 2020-06-09 | Overhead | R16 | 2020-03-30 | 1 |  | 27 | 52 | 78 | 2020 | 2020 | R16
163774275166 | 160234275166 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-17 | 2021-11-17 | 2022-04-07 |  | 2023-04-10 | Underground | R16 | 2023-01-19 | 1 | 102 | 206 | 58 | 364 | 2021 | 2023 | R16
161537271377 | 163467271377 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-04 | 2022-03-04 | 2022-03-04 |  | 2022-04-22 | Overhead | R16 | 2022-03-24 | 1 |  | 15 | 22 | 36 | 2022 | 2022 | R16
169531181933 | 162346181933 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-25 | 2020-02-25 | 2020-02-25 |  | 2020-07-01 | Overhead | R16 | 2020-05-01 | 1 |  | 49 | 44 | 92 | 2020 | 2020 | R16
162405260089 | 169578260089 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-15 | 2021-12-06 | 2021-12-06 |  | 2022-05-13 | Underground | R16 | 2022-04-22 | 16 |  | 100 | 16 | 130 | 2021 | 2022 | R16
165904252445 | 162886252445 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-15 | 2021-10-15 | 2021-10-15 |  | 2021-12-29 | Overhead | R16 | 2021-11-16 | 1 |  | 23 | 32 | 54 | 2021 | 2021 | R16
169558231014 | 166437231014 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-29 | 2020-01-29 | 2021-05-18 |  | 2021-12-02 | Underground | R16 | 2021-11-04 | 1 | 340 | 123 | 21 | 482 | 2020 | 2021 | R16
164167252078 | 166700252078 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-20 | 2021-09-20 | 2021-10-14 |  | 2022-02-18 | Underground | R16 | 2022-01-20 | 1 | 19 | 71 | 22 | 110 | 2021 | 2022 | R16
169559187843 | 167669187843 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-04 | 2020-02-05 | 2020-04-16 |  | 2020-07-09 | Underground | R16 | 2020-05-27 | 2 | 52 | 30 | 32 | 113 | 2020 | 2020 | R16
166427275988 | 162441275988 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-04-15 | 2022-04-15 | 2022-04-15 |  | 2022-06-20 | Overhead | R16 | 2022-05-27 | 1 |  | 31 | 17 | 47 | 2022 | 2022 | R16
164180277988 | 168915277988 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-03-29 | 2022-04-07 | 2022-05-02 |  | 2022-06-30 | Overhead | R16 |  | 8 | 18 |  |  | 68 | 2022 | 2022 | R16
163732256504 | 168476256504 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-11-09 | 2021-11-09 | 2021-11-15 |  | 2023-01-10 | Underground | R16 |  | 1 | 5 |  |  | 306 | 2021 | 2023 | R16
166132269057 | 168299269057 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-11 | 2022-02-15 | 2022-02-15 | 2022-07-20 | 2022-09-20 | Overhead | R16 | 2022-07-20 | 3 |  | 112 | 45 | 158 | 2022 | 2022 | R16
162778286214 | 162914286214 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-10 | 2022-05-10 | 2022-07-20 | 2023-01-05 | 2023-01-05 | Underground | R16 | 2023-01-05 | 1 | 52 | 122 |  | 173 | 2022 | 2023 | R16
167087281262 | 167321281262 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-31 | 2022-05-31 | 2022-05-31 | 2022-09-29 | 2023-01-05 | Overhead | R16 | 2022-09-29 | 1 |  | 88 | 71 | 158 | 2022 | 2023 | R16
164373285085 | 162196285085 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-22 | 2022-07-08 | 2022-07-08 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 13 |  | 130 |  | 142 | 2022 | 2023 | R16
169795179616 | 168469179616 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-06 | 2020-02-07 | 2020-02-07 |  | 2020-06-09 | Overhead | R16 | 2020-03-30 | 2 |  | 37 | 52 | 89 | 2020 | 2020 | R16
169801180103 | 169085180103 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-10 | 2020-02-10 | 2020-02-10 |  | 2022-06-28 | Overhead | R16 |  | 1 |  |  |  | 622 | 2020 | 2022 | R16
166035259040 | 168897259040 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-29 | 2021-10-20 | 2021-11-29 | 2022-02-08 | 2022-02-15 | Underground | R16 | 2022-02-08 | 16 | 29 | 52 | 6 | 100 | 2021 | 2022 | R16
166779286240 | 167664286240 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-19 | 2022-07-19 | 2022-07-19 |  | 2022-09-11 | Overhead | R16 | 2022-08-17 | 1 |  | 22 | 18 | 39 | 2022 | 2022 | R16
164742256539 | 169363256539 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-12 | 2021-11-15 | 2021-11-15 |  | 2022-03-25 | Overhead | R16 | 2022-03-02 | 2 |  | 78 | 18 | 96 | 2021 | 2022 | R16
160598254002 | 161899254002 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-13 | 2021-10-13 | 2021-10-27 | 2021-11-18 | 2022-01-18 | Underground | R16 | 2021-11-18 | 1 | 11 | 17 | 44 | 70 | 2021 | 2022 | R16
161776278820 | 163671278820 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-03-04 | 2022-03-04 | 2022-05-10 |  | 2022-09-09 | Underground | R16 |  | 1 | 48 |  |  | 136 | 2022 | 2022 | R16
161272277627 | 165769277627 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-29 | 2022-04-29 | 2022-04-29 | 2022-05-12 | 2022-05-13 | Overhead | R16 | 2022-05-12 | 1 |  | 10 | 2 | 11 | 2022 | 2022 | R16
167134270009 | 160888270009 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-22 | 2022-02-22 | 2022-02-22 | 2022-06-17 | 2022-07-19 | Overhead | R16 | 2022-06-17 | 1 |  | 84 | 23 | 106 | 2022 | 2022 | R16
166086273535 | 160751273535 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-22 | 2022-02-22 | 2022-03-23 | 2023-12-04 | 2023-12-04 | Underground | R16 | 2023-12-04 | 1 | 22 | 444 |  | 465 | 2022 | 2023 | R16
161947275181 | 162105275181 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-18 | 2022-04-07 | 2022-04-07 | 2022-12-07 | 2023-02-17 | Overhead | R16 | 2022-12-07 | 58 |  | 175 | 53 | 284 | 2022 | 2023 | R16
160116181614 | 162146181614 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-24 | 2020-02-24 | 2020-02-25 |  | 2023-06-09 | Overhead | R16 |  | 1 | 2 |  |  | 860 | 2020 | 2023 | R16
160173176779 | 163186176779 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-14 | 2020-01-14 | 2020-01-14 |  | 2020-06-09 | Overhead | R16 | 2020-03-04 | 1 |  | 37 | 70 | 106 | 2020 | 2020 | R16
167932289684 | 164567289684 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2022-07-06 | 2022-07-06 | 2022-08-19 |  | 2023-01-05 | Underground | R16 |  | 1 | 33 |  |  | 132 | 2022 | 2023 | R16
160175182920 | 163987182920 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-04 | 2020-03-04 | 2020-03-04 |  | 2021-06-30 | Overhead | R16 | 2020-04-20 | 1 |  | 34 | 313 | 346 | 2020 | 2021 | R16
169609250979 | 160706250979 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-07 | 2021-10-07 | 2021-10-07 |  | 2021-12-17 | Overhead | R16 | 2021-11-18 | 1 |  | 31 | 22 | 52 | 2021 | 2021 | R16
160178179638 | 166963179638 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-30 | 2020-01-30 | 2020-02-07 |  | 2020-10-06 | Underground | R16 | 2020-08-06 | 1 | 7 | 130 | 44 | 179 | 2020 | 2020 | R16
162141251558 | 161549251558 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-11 | 2021-10-11 | 2021-10-11 | 2021-10-21 | 2021-11-15 | Overhead | R16 | 2021-10-21 | 1 |  | 9 | 18 | 26 | 2021 | 2021 | R16
160210189087 | 164002189087 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-27 | 2020-04-27 | 2020-04-27 |  | 2020-07-14 | Overhead | R16 | 2020-06-17 | 1 |  | 38 | 20 | 57 | 2020 | 2020 | R16
167764273960 | 168410273960 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-27 | 2022-03-27 | 2022-03-27 | 2022-05-13 | 2022-05-16 | Overhead | R16 | 2022-05-13 | 0 |  | 35 | 2 | 36 | 2022 | 2022 | R16
160222178738 | 166759178738 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-30 | 2020-01-30 | 2020-01-30 |  | 2020-06-23 | Underground | R16 | 2020-04-14 | 1 |  | 54 | 51 | 104 | 2020 | 2020 | R16
165179290833 | 165842290833 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-23 | 2022-06-21 | 2022-08-31 |  | 2022-11-15 | Overhead | R16 | 2022-11-14 | 22 | 52 | 54 | 2 | 127 | 2022 | 2022 | R16
162692278927 | 165328278927 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-01-28 | 2022-01-31 | 2022-05-11 |  | 2022-10-28 | Underground | R16 |  | 2 | 73 |  |  | 196 | 2022 | 2022 | R16
162305276822 | 164342276822 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-07 | 2022-03-07 | 2022-04-21 | 2022-04-28 | 2022-06-10 | Underground | R16 | 2022-04-28 | 1 | 34 | 6 | 32 | 70 | 2022 | 2022 | R16
160319175396 | 161128175396 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-01-04 | 2020-01-04 | 2020-01-04 |  | 2020-06-09 | Overhead | R16 | 2020-02-28 | 0 |  | 40 | 73 | 112 | 2020 | 2020 | R16
163960271493 | 168802271493 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-03 | 2022-03-04 | 2022-03-04 |  | 2022-06-06 | Underground | R16 | 2022-05-09 | 45 |  | 47 | 21 | 111 | 2022 | 2022 | R16
168889275723 | 161084275723 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-08 | 2022-04-13 | 2022-04-13 |  | 2022-07-17 | Overhead | R16 | 2022-07-06 | 4 |  | 61 | 8 | 71 | 2022 | 2022 | R16
169831274122 | 169255274122 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2022-01-04 | 2022-02-18 | 2022-03-28 | 2023-02-13 | 2023-02-24 | Underground | R16 | 2023-02-13 | 34 | 27 | 231 | 10 | 299 | 2022 | 2023 | R16
160634281993 | 163544281993 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2022-05-12 | 2022-05-13 | 2022-06-08 |  | 2022-10-21 | Overhead | R16 |  | 2 | 19 |  |  | 117 | 2022 | 2022 | R16
166329278681 | 161753278681 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-25 | 2022-03-02 | 2022-05-09 |  | 2023-07-31 | Underground | R16 | 2023-04-28 | 4 | 49 | 255 | 67 | 372 | 2022 | 2023 | R16
160672183131 | 164692183131 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-06 | 2020-03-06 | 2020-03-06 |  | 2022-10-20 | Overhead | R16 |  | 1 |  |  |  | 685 | 2020 | 2022 | R16
168811284201 | 166940284201 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-20 | 2021-12-21 | 2022-06-29 | 2023-01-05 | 2023-01-05 | Underground | R16 | 2023-01-05 | 2 | 137 | 137 |  | 274 | 2021 | 2023 | R16
161572265727 | 163193265727 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-21 | 2022-01-21 | 2022-01-21 | 2022-07-25 | 2022-07-26 | Overhead | R16 | 2022-07-25 | 1 |  | 132 | 2 | 133 | 2022 | 2022 | R16
160210290465 | 167575290465 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2022-02-08 | 2022-02-09 | 2022-08-26 | 2023-09-07 | 2023-10-25 | Underground | R16 | 2023-09-07 | 2 | 143 | 270 | 35 | 447 | 2022 | 2023 | R16
164153260214 | 164281260214 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-07 | 2021-12-07 | 2021-12-07 |  | 2022-01-20 | Overhead | R16 | 2021-12-20 | 1 |  | 10 | 24 | 33 | 2021 | 2022 | R16
166415250561 | 168460250561 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-09-27 | 2021-10-04 | 2021-10-04 |  | 2021-11-18 | Overhead | R16 | 2021-10-28 | 6 |  | 19 | 16 | 39 | 2021 | 2021 | R16
167910272540 | 161245272540 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-23 | 2022-03-14 | 2022-03-14 |  | 2022-05-18 | Underground | R16 | 2022-04-25 | 14 |  | 31 | 18 | 61 | 2022 | 2022 | R16
164283248860 | 167064248860 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-11-10 | 2021-12-29 | Overhead | R16 | 2021-11-10 | 1 |  | 37 | 36 | 72 | 2021 | 2021 | R16
161804261676 | 166550261676 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-12-17 | 2021-12-17 | 2021-12-17 |  | 2022-08-19 | Underground | R16 | 2022-08-09 | 1 |  | 168 | 9 | 176 | 2021 | 2022 | R16
160622282157 | 162867282157 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-19 | 2022-04-19 | 2022-06-09 | 2022-09-12 | 2022-09-12 | Underground | R16 | 2022-09-12 | 1 | 38 | 68 |  | 105 | 2022 | 2022 | R16
168015274489 | 168927274489 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-30 | 2022-03-31 | 2022-03-31 | 2022-11-02 | 2023-03-25 | Overhead | R16 | 2022-11-02 | 2 |  | 155 | 103 | 258 | 2022 | 2023 | R16
167046286777 | 169040286777 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-07-25 | 2022-07-26 | 2022-07-26 | 2022-09-13 | 2022-10-26 | Overhead | R16 | 2022-09-13 | 2 |  | 36 | 32 | 68 | 2022 | 2022 | R16
167423275927 | 162189275927 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-14 | 2022-04-14 | 2022-04-14 | 2022-07-26 | 2022-09-20 | Overhead | R16 | 2022-07-26 | 1 |  | 74 | 41 | 114 | 2022 | 2022 | R16
165999261172 | 165824261172 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-12-14 | 2021-12-14 | 2021-12-14 |  | 2022-06-24 | Overhead | R16 | 2022-06-22 | 1 |  | 137 | 3 | 139 | 2021 | 2022 | R16
166183255575 | 168186255575 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-09 | 2021-11-09 | 2021-11-09 |  | 2022-06-06 | Overhead | R16 | 2022-05-10 | 1 |  | 131 | 20 | 150 | 2021 | 2022 | R16
160903177675 | 165231177675 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-22 | 2020-01-22 | 2020-01-22 |  | 2020-08-28 | Overhead | R16 | 2020-07-01 | 1 |  | 116 | 43 | 158 | 2020 | 2020 | R16
166880289352 | 169171289352 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-26 | 2022-07-26 | 2022-08-17 | 2022-10-03 | 2023-08-06 | Underground | R16 | 2022-10-03 | 1 | 17 | 34 | 220 | 269 | 2022 | 2023 | R16
161543285500 | 164392285500 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-05 | 2022-07-12 | 2022-07-12 | 2023-11-01 | 2023-11-16 | Overhead | R16 | 2023-11-01 | 6 |  | 342 | 12 | 358 | 2022 | 2023 | R16
168388271337 | 163311271337 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-03 | 2022-03-03 | 2022-03-03 |  | 2022-05-12 | Overhead | R16 | 2022-04-18 | 1 |  | 33 | 19 | 51 | 2022 | 2022 | R16
163550289706 | 167704289706 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-19 | 2022-07-19 | 2022-08-19 | 2022-11-07 | 2023-03-28 | Underground | R16 | 2022-11-07 | 1 | 24 | 57 | 102 | 181 | 2022 | 2023 | R16
162768277074 | 163255277074 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-04 | 2022-03-04 | 2022-04-26 | 2022-07-07 | 2022-07-08 | Overhead | R16 | 2022-07-07 | 1 | 38 | 53 | 2 | 91 | 2022 | 2022 | R16
160110270999 | 160444270999 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-18 | 2022-03-02 | 2022-03-02 |  | 2022-07-29 | Overhead | R16 | 2022-07-27 | 9 |  | 106 | 3 | 116 | 2022 | 2022 | R16
167657279823 | 164908279823 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-18 | 2022-05-18 | 2022-05-18 |  | 2022-09-11 | Overhead | R16 | 2022-08-25 | 1 |  | 72 | 12 | 83 | 2022 | 2022 | R16
162917287426 | 168613287426 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-22 | 2022-07-29 | 2022-07-29 |  | 2023-01-10 | Underground | R16 | 2022-11-04 | 6 |  | 71 | 48 | 123 | 2022 | 2023 | R16
169992300468 | 169422300468 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-06-09 | 2022-06-10 | 2022-11-15 | 2023-03-16 | 2023-03-17 | Overhead | R16 | 2023-03-16 | 2 | 113 | 88 | 2 | 202 | 2022 | 2023 | R16
165366311164 | 162218311164 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-22 | 2022-06-22 | 2023-03-02 |  | 2023-06-19 | Overhead | R16 | 2023-03-09 | 1 | 182 | 6 | 73 | 259 | 2022 | 2023 | R16
167471280081 | 163962280081 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2022-05-13 | 2022-05-16 | 2022-05-19 |  | 2022-06-30 | Overhead | R16 |  | 2 | 4 |  |  | 35 | 2022 | 2022 | R16
161239185914 | 161990185914 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-08 | 2020-01-08 | 2020-03-31 |  | 2020-07-02 | Underground | R16 | 2020-05-06 | 1 | 60 | 27 | 42 | 127 | 2020 | 2020 | R16
162470279674 | 164831279674 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-07-25 | 2022-07-26 | Overhead | R16 | 2022-07-25 | 1 |  | 50 | 2 | 51 | 2022 | 2022 | R16
169503271621 | 163639271621 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-04 | 2022-03-04 | 2022-03-04 |  | 2022-06-21 | Overhead | R16 | 2022-05-24 | 1 |  | 58 | 21 | 78 | 2022 | 2022 | R16
167509255320 | 165342255320 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2021-10-27 | 2021-10-28 | 2021-11-05 |  | 2021-12-17 | Overhead | R16 |  | 2 | 7 |  |  | 38 | 2021 | 2021 | R16
161501186067 | 161530186067 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-06 | 2020-01-06 | 2020-04-01 |  | 2022-06-20 | Underground | R16 | 2022-05-23 | 1 | 63 | 559 | 21 | 641 | 2020 | 2022 | R16
169784275784 | 160838275784 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-07 | 2022-04-07 | 2022-04-13 |  | 2022-09-29 | Underground | R16 | 2022-09-08 | 1 | 5 | 107 | 16 | 126 | 2022 | 2022 | R16
161551184601 | 161474184601 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-06 | 2020-01-06 | 2020-03-18 |  | 2022-03-15 | Underground | R16 | 2020-03-30 | 1 | 53 | 9 | 512 | 572 | 2020 | 2022 | R16
160277305036 | 162483305036 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-01 | 2022-03-04 | 2023-01-30 | 2023-01-06 | 2023-04-13 | Underground | R16 | 2023-01-06 | 4 | 237 |  | 70 | 293 | 2022 | 2023 | R16
162907293801 | 168078293801 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | OH R16 RES NON RES OD | Commercial | 2022-07-21 | 2022-07-21 | 2022-09-14 | 2022-10-26 | 2022-11-21 | Overhead | R16 | 2022-10-26 | 1 | 40 | 31 | 19 | 88 | 2022 | 2022 | R16
165134262188 | 167198262188 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-12-21 | 2021-12-21 | 2021-12-21 |  | 2022-03-31 | Overhead | R16 | 2022-03-31 | 1 |  | 73 |  | 73 | 2021 | 2022 | R16
168288270500 | 161488270500 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-24 | 2022-02-24 | 2022-02-24 |  | 2022-06-20 | Underground | R16 | 2022-05-27 | 1 |  | 67 | 17 | 83 | 2022 | 2022 | R16
161652177883 | 162190177883 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-08 | 2020-01-08 | 2020-01-23 |  | 2020-06-09 | Underground | R16 | 2020-03-05 | 1 | 12 | 31 | 69 | 110 | 2020 | 2020 | R16
166221277051 | 163906277051 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-25 | 2022-04-25 | 2022-04-25 |  | 2022-08-24 | Underground | R16 | 2022-08-11 | 1 |  | 79 | 10 | 88 | 2022 | 2022 | R16
160271270776 | 162362270776 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-28 | 2022-02-28 | 2022-02-28 | 2022-05-23 | 2022-05-24 | Overhead | R16 | 2022-05-23 | 1 |  | 61 | 2 | 62 | 2022 | 2022 | R16
161683181486 | 161714181486 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-07 | 2020-01-07 | 2020-02-21 |  | 2020-08-28 | Underground | R16 | 2020-08-19 | 1 | 34 | 129 | 8 | 169 | 2020 | 2020 | R16
161693184004 | 166072184004 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-13 | 2020-03-13 | 2020-03-13 |  | 2020-07-02 | Overhead | R16 | 2020-05-04 | 1 |  | 37 | 44 | 80 | 2020 | 2020 | R16
164169269728 | 160432269728 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-18 | 2022-02-18 | 2022-02-18 | 2022-02-22 | 2022-06-01 | Overhead | R16 | 2022-02-22 | 1 |  | 3 | 72 | 74 | 2022 | 2022 | R16
165694276811 | 169800276811 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-01 | 2022-04-12 | 2022-04-22 | 2023-01-05 | 2023-01-05 | Underground | R16 | 2023-01-05 | 8 | 9 | 185 |  | 200 | 2022 | 2023 | R16
164448302292 | 165410302292 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-20 | 2022-05-20 | 2022-12-05 | 2023-04-10 | 2023-04-12 | Underground | R16 | 2023-04-10 | 1 | 142 | 91 | 3 | 234 | 2022 | 2023 | R16
167519260058 | 168786260058 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-10 | 2021-11-10 | 2021-12-07 | 2022-04-17 | 2022-05-03 | Underground | R16 | 2022-04-17 | 1 | 20 | 94 | 12 | 125 | 2021 | 2022 | R16
161764179092 | 167581179092 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-03 | 2020-02-03 | 2020-02-03 |  | 2022-10-20 | Overhead | R16 |  | 1 |  |  |  | 709 | 2020 | 2022 | R16
162004177922 | 163553177922 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-15 | 2020-01-15 | 2020-01-23 |  | 2020-06-09 | Underground | R16 | 2020-04-02 | 1 | 7 | 51 | 49 | 105 | 2020 | 2020 | R16
165894258719 | 161789258719 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-12 | 2021-10-12 | 2021-11-24 |  | 2022-03-25 | Underground | R16 | 2022-03-25 | 1 | 32 | 88 |  | 119 | 2021 | 2022 | R16
162007176707 | 163022176707 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-13 | 2020-01-13 | 2020-01-13 |  | 2020-07-14 | Underground | R16 | 2020-06-18 | 1 |  | 114 | 19 | 132 | 2020 | 2020 | R16
162925280967 | 167044280967 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-27 | 2022-05-27 | 2022-05-27 |  | 2022-09-15 | Overhead | R16 | 2022-07-29 | 1 |  | 46 | 35 | 80 | 2022 | 2022 | R16
165017285164 | 163572285164 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-06-28 | 2022-07-11 | 2022-07-11 | 2023-01-05 | 2023-01-05 | Underground | R16 | 2023-01-05 | 10 |  | 129 |  | 138 | 2022 | 2023 | R16
165667278292 | 161242278292 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-05 | 2022-05-05 | 2022-05-05 |  | 2022-08-24 | Overhead | R16 | 2022-08-17 | 1 |  | 75 | 6 | 80 | 2022 | 2022 | R16
167509255181 | 165344255181 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2021-10-27 | 2021-10-28 | 2021-11-04 |  | 2022-02-11 | Overhead | R16 |  | 2 | 6 |  |  | 78 | 2021 | 2022 | R16
168931254904 | 163742254904 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-10-19 | 2021-11-02 | 2021-11-03 |  | 2022-01-11 | Overhead | R16 |  | 11 | 2 |  |  | 61 | 2021 | 2022 | R16
165244289430 | 162263289430 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-06-22 | 2022-07-15 | 2022-08-18 |  | 2023-03-17 | Underground | R16 |  | 18 | 25 |  |  | 193 | 2022 | 2023 | R16
164705266518 | 165204266518 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-28 | 2022-01-28 | 2022-01-28 | 2022-03-01 | 2022-04-01 | Overhead | R16 | 2022-03-01 | 1 |  | 23 | 24 | 46 | 2022 | 2022 | R16
162203184256 | 162582184256 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-01-10 | 2020-01-10 | 2020-03-17 |  | 2023-12-21 | Underground | R16 | 2023-10-06 | 1 | 48 | 929 | 55 | 1030 | 2020 | 2023 | R16
162623282782 | 160625282782 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-15 | 2022-06-15 | 2022-06-15 |  | 2023-02-08 | Overhead | R16 | 2023-02-06 | 1 |  | 169 | 3 | 171 | 2022 | 2023 | R16
167008264885 | 165474264885 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-13 | 2021-12-13 | 2022-01-14 | 2022-03-28 | 2022-03-29 | Underground | R16 | 2022-03-28 | 1 | 25 | 52 | 2 | 77 | 2021 | 2022 | R16
162207219055 | 162695219055 | NON-RESIDENTIAL - SMALL RETAIL | R16 RESD AND NON RESD US | Commercial | 2020-08-07 | 2020-08-31 | 2021-02-01 |  | 2022-01-07 | Underground | R16 |  | 17 | 111 |  |  | 371 | 2020 | 2022 | R16
165710280588 | 162246280588 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-02-28 | 2022-05-24 | 2022-05-24 | 2022-06-08 | 2022-07-25 | Overhead | R16 | 2022-06-08 | 62 |  | 12 | 34 | 106 | 2022 | 2022 | R16
166131248966 | 167208248966 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2021-09-28 | 2021-11-09 | Overhead | R16 | 2021-09-28 | 1 |  | 5 | 31 | 35 | 2021 | 2021 | R16
168801266374 | 164729266374 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-27 | 2022-01-27 | 2022-01-27 |  | 2022-03-23 | Overhead | R16 | 2022-02-28 | 1 |  | 23 | 18 | 40 | 2022 | 2022 | R16
162229179094 | 167485179094 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-02-03 | 2020-02-03 | 2020-02-03 |  | 2022-10-19 | Overhead | R16 |  | 1 |  |  |  | 708 | 2020 | 2022 | R16
162106263497 | 168837263497 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-01-03 | 2022-01-05 | 2022-01-05 |  | 2022-08-10 | Overhead | R16 | 2022-07-07 | 3 |  | 132 | 25 | 158 | 2022 | 2022 | R16
164523283859 | 161602283859 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-21 | 2022-06-27 | 2022-06-28 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 5 | 2 | 138 |  | 143 | 2022 | 2023 | R16
162232178280 | 165935178280 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-27 | 2020-01-27 | 2020-01-27 |  | 2020-06-09 | Overhead | R16 | 2020-05-11 | 1 |  | 76 | 22 | 97 | 2020 | 2020 | R16
162295187501 | 167873187501 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-03-24 | 2020-03-24 | 2020-04-14 |  | 2020-10-06 | Underground | R16 | 2020-07-21 | 1 | 16 | 71 | 56 | 141 | 2020 | 2020 | R16
169046262811 | 165374262811 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-13 | 2021-12-29 | 2021-12-29 |  | 2022-05-09 | Underground | R16 | 2022-04-15 | 13 |  | 78 | 17 | 106 | 2021 | 2022 | R16
162361178690 | 166724178690 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-30 | 2020-01-30 | 2020-01-30 |  | 2020-06-09 | Overhead | R16 | 2020-03-17 | 1 |  | 34 | 61 | 94 | 2020 | 2020 | R16
168296287320 | 168948287320 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-25 | 2022-07-25 | 2022-07-29 | 2023-12-04 | 2023-12-07 | Underground | R16 | 2023-12-04 | 1 | 5 | 352 | 4 | 359 | 2022 | 2023 | R16
166721320202 | 163116320202 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-02 | 2021-12-02 | 2023-05-24 | 2023-11-27 | 2023-11-30 | Underground | R16 | 2023-11-27 | 1 | 385 | 134 | 4 | 521 | 2021 | 2023 | R16
162369179485 | 168114179485 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-05 | 2020-02-05 | 2020-02-05 |  | 2020-06-09 | Overhead | R16 | 2020-03-17 | 1 |  | 30 | 61 | 90 | 2020 | 2020 | R16
162423178283 | 165952178283 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-01-27 | 2020-01-27 | 2020-01-27 |  | 2020-06-09 | Overhead | R16 | 2020-02-11 | 1 |  | 12 | 86 | 97 | 2020 | 2020 | R16
164841257122 | 166591257122 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-02 | 2021-11-03 | 2021-11-17 | 2022-01-27 | 2022-01-27 | Underground | R16 | 2022-01-27 | 2 | 11 | 52 |  | 63 | 2021 | 2022 | R16
162359300243 | 163988300243 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-06-30 |  | 2022-08-24 |  | 2023-03-03 | Underground | R16 | 2023-03-01 |  |  | 136 | 3 | 177 | 2022 | 2023 | R16
165202281665 | 164271281665 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-16 | 2022-05-16 | 2022-06-06 |  | 2022-08-24 | Underground | R16 | 2022-08-23 | 1 | 16 | 57 | 2 | 73 | 2022 | 2022 | R16
166270254653 | 165694254653 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-10-28 | 2021-10-28 | 2021-11-02 | 2021-11-16 | 2021-12-28 | Overhead | R16 | 2021-11-16 | 1 | 4 | 11 | 31 | 44 | 2021 | 2021 | R16
162443185763 | 164273185763 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-05 | 2020-03-05 | 2020-03-30 |  | 2020-07-09 | Underground | R16 | 2020-05-27 | 1 | 18 | 43 | 32 | 91 | 2020 | 2020 | R16
161175266323 | 163012266323 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-15 | 2021-11-16 | 2022-01-26 | 2022-12-13 | 2022-12-14 | Overhead | R16 | 2022-12-13 | 23 | 52 | 230 | 2 | 304 | 2021 | 2022 | R16
161948302586 | 162255302586 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-02-28 | 2022-07-12 | 2022-12-07 |  | 2023-06-23 | Overhead | R16 |  | 97 | 107 |  |  | 345 | 2022 | 2023 | R16
167138252160 | 168500252160 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-28 | 2021-09-28 | 2021-10-14 |  | 2022-01-20 | Underground | R16 | 2021-12-21 | 1 | 13 | 49 | 23 | 83 | 2021 | 2022 | R16
167429260921 | 167063260921 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-03 | 2021-11-03 | 2021-12-13 |  | 2022-06-09 | Underground | R16 | 2022-05-17 | 1 | 29 | 112 | 18 | 157 | 2021 | 2022 | R16
167094274992 | 160491274992 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-06 | 2022-04-06 | 2022-04-06 | 2022-05-09 | 2022-06-09 | Overhead | R16 | 2022-05-09 | 1 |  | 24 | 24 | 47 | 2022 | 2022 | R16
162556178044 | 165616178044 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-24 | 2020-01-24 | 2020-01-24 |  | 2021-01-21 | Overhead | R16 | 2020-10-14 | 1 |  | 189 | 72 | 260 | 2020 | 2021 | R16
160523253132 | 160790253132 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2021-10-07 | 2021-10-07 | 2021-10-21 |  | 2022-04-27 | Underground | R16 |  | 1 | 11 |  |  | 145 | 2021 | 2022 | R16
167581284536 | 165850284536 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2022-05-23 | 2022-05-23 | 2022-07-06 |  | 2023-08-02 | Underground | R16 |  | 1 | 33 |  |  | 313 | 2022 | 2023 | R16
160523253157 | 162231253157 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2021-10-13 | 2021-10-13 | 2021-10-21 |  | 2022-02-11 | Underground | R16 |  | 1 | 7 |  |  | 88 | 2021 | 2022 | R16
168280268528 | 160682268528 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-10 | 2022-02-09 | 2022-02-10 | 2022-03-01 | 2022-06-21 | Overhead | R16 | 2022-03-01 | 23 | 2 | 14 | 81 | 117 | 2022 | 2022 | R16
161669271174 | 162918271174 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-03 | 2022-03-03 | 2022-03-03 |  | 2022-08-03 | Overhead | R16 | 2022-06-14 | 1 |  | 74 | 37 | 110 | 2022 | 2022 | R16
166965256201 | 169172256201 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-11 | 2021-11-11 | 2021-11-11 | 2022-03-14 | 2022-04-05 | Overhead | R16 | 2022-03-14 | 1 |  | 88 | 17 | 104 | 2021 | 2022 | R16
168031284270 | 164052284270 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-01 | 2022-07-01 | 2022-07-01 | 2022-08-09 | 2022-09-14 | Overhead | R16 | 2022-08-09 | 1 |  | 28 | 27 | 54 | 2022 | 2022 | R16
167975254276 | 169993254276 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-05 | 2021-10-05 | 2021-10-29 | 2021-12-27 | 2022-01-24 | Underground | R16 | 2021-12-27 | 1 | 19 | 42 | 21 | 80 | 2021 | 2022 | R16
162579285313 | 164742285313 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-17 | 2022-05-19 | 2022-07-12 | 2022-08-16 | 2022-08-17 | Overhead | R16 | 2022-08-16 | 3 | 39 | 26 | 2 | 67 | 2022 | 2022 | R16
165059283931 | 166160283931 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-05-24 | 2022-05-24 | 2022-06-28 | 2023-01-05 | 2023-01-05 | Underground | R16 | 2023-01-05 | 1 | 26 | 138 |  | 163 | 2022 | 2023 | R16
162746183936 | 163726183936 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-01-16 | 2020-01-16 | 2020-03-12 |  | 2021-04-20 | Underground | R16 | 2021-01-15 | 1 | 41 | 222 | 68 | 329 | 2020 | 2021 | R16
160618285420 | 164070285420 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-30 | 2022-06-30 | 2022-07-12 |  | 2022-12-04 | Underground | R16 | 2022-10-19 | 1 | 9 | 72 | 33 | 112 | 2022 | 2022 | R16
165668268735 | 168405268735 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2022-02-10 | 2022-02-10 | 2022-02-11 |  | 2023-03-17 | Underground | R16 |  | 1 | 2 |  |  | 287 | 2022 | 2023 | R16
162907253875 | 165130253875 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-26 | 2021-10-26 | 2021-10-26 |  | 2021-12-18 | Overhead | R16 | 2021-12-17 | 1 |  | 39 | 1 | 39 | 2021 | 2021 | R16
160207286087 | 163700286087 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-29 | 2022-06-29 | 2022-07-19 | 2022-08-08 | 2022-09-21 | Underground | R16 | 2022-08-08 | 1 | 15 | 15 | 33 | 61 | 2022 | 2022 | R16
160963267225 | 166346267225 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-02 | 2022-02-02 | 2022-02-02 | 2022-03-29 | 2022-06-17 | Overhead | R16 | 2022-03-29 | 1 |  | 40 | 59 | 98 | 2022 | 2022 | R16
162860271143 | 164174271143 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-07 | 2021-12-07 | 2022-03-02 |  | 2022-05-05 | Underground | R16 | 2022-04-13 | 1 | 62 | 31 | 17 | 108 | 2021 | 2022 | R16
162814211012 | 164693211012 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-03-06 | 2020-03-06 | 2020-11-17 |  | 2021-11-18 | Underground | R16 | 2021-01-20 | 1 | 183 | 47 | 217 | 445 | 2020 | 2021 | R16
161608300682 | 164672300682 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-08 | 2022-03-09 | 2022-11-15 | 2023-02-03 | 2023-02-06 | Underground | R16 | 2023-02-03 | 2 | 180 | 59 | 2 | 240 | 2022 | 2023 | R16
160034273000 | 166359273000 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-17 | 2022-03-17 | 2022-03-17 |  | 2022-08-03 | Overhead | R16 | 2022-06-17 | 1 |  | 67 | 34 | 100 | 2022 | 2022 | R16
162840183036 | 166000183036 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-27 | 2020-02-21 | 2020-03-06 |  | 2020-10-06 | Underground | R16 | 2020-08-13 | 20 | 11 | 115 | 39 | 182 | 2020 | 2020 | R16
167395277949 | 161971277949 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-13 | 2022-04-18 | 2022-05-02 | 2023-08-11 | 2023-08-14 | Underground | R16 | 2023-08-11 | 4 | 11 | 335 | 2 | 349 | 2022 | 2023 | R16
169066259961 | 160770259961 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2021-11-19 | 2021-12-06 | 2021-12-06 |  | 2022-02-02 | Underground | R16 | 2022-01-13 | 12 |  | 29 | 15 | 54 | 2021 | 2022 | R16
162504253898 | 164803253898 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-25 | 2021-10-27 | 2021-10-27 | 2021-10-28 | 2022-01-11 | Overhead | R16 | 2021-10-28 | 3 |  | 2 | 54 | 57 | 2021 | 2022 | R16
164162284963 | 168177284963 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-02-10 | 2022-02-10 | 2022-07-08 |  | 2022-10-01 | Overhead | R16 | 2022-09-28 | 1 | 107 | 59 | 3 | 167 | 2022 | 2022 | R16
167674260939 | 162454260939 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-14 | 2021-10-14 | 2021-12-14 |  | 2022-02-07 | Overhead | R16 | 2022-01-11 | 1 | 44 | 21 | 20 | 83 | 2021 | 2022 | R16
165127255322 | 167614255322 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-05 | 2021-11-05 | 2021-11-05 | 2022-01-18 | 2022-02-21 | Overhead | R16 | 2022-01-18 | 1 |  | 53 | 25 | 77 | 2021 | 2022 | R16
161628266535 | 167621266535 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-22 | 2021-12-22 | 2022-01-28 |  | 2023-10-06 | Underground | R16 | 2023-07-10 | 1 | 28 | 377 | 65 | 468 | 2021 | 2023 | R16
168391268047 | 167100268047 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-02-04 | 2022-02-07 | 2022-02-07 |  | 2022-04-27 | Overhead | R16 | 2022-03-31 | 2 |  | 39 | 20 | 59 | 2022 | 2022 | R16
161908314862 | 161592314862 | GENERAL/OTHER | UG R16 RESD AND NON RESD UD | Commercial | 2022-02-24 | 2022-02-24 | 2023-04-05 | 2023-11-09 | 2023-12-26 | Underground | R16 | 2023-11-09 | 1 | 290 | 157 | 34 | 479 | 2022 | 2023 | R16
163445273447 | 165408273447 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-13 | 2021-12-13 | 2022-03-21 | 2022-08-12 | 2022-10-21 | Underground | R16 | 2022-08-12 | 1 | 71 | 105 | 51 | 225 | 2021 | 2022 | R16
167242282214 | 168069282214 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2021-12-29 | 2021-12-29 | 2022-06-10 |  | 2022-08-11 | Underground | R16 |  | 1 | 118 |  |  | 162 | 2021 | 2022 | R16
164137272972 | 161667272972 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-24 | 2022-02-24 | 2022-03-18 |  | 2022-06-20 | Underground | R16 | 2022-05-24 | 1 | 17 | 48 | 20 | 83 | 2022 | 2022 | R16
163008182169 | 162975182169 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-02-27 | 2020-02-27 | 2020-02-27 |  | 2020-07-09 | Overhead | R16 | 2020-06-08 | 1 |  | 73 | 24 | 96 | 2020 | 2020 | R16
168437278848 | 162908278848 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-10 | 2022-05-10 | 2022-05-10 | 2022-07-18 | 2022-07-22 | Overhead | R16 | 2022-07-18 | 1 |  | 50 | 5 | 54 | 2022 | 2022 | R16
162608280731 | 164760280731 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-12-09 | 2021-12-09 | 2022-05-25 |  | 2023-08-18 | Underground | R16 | 2023-05-16 | 1 | 120 | 255 | 69 | 442 | 2021 | 2023 | R16
160523259627 | 163293259627 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2021-12-02 | 2021-12-02 | 2021-12-02 |  | 2022-03-04 | Underground | R16 |  | 1 |  |  |  | 67 | 2021 | 2022 | R16
162323280203 | 165454280203 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-20 | 2022-05-20 | 2022-05-20 | 2022-07-06 | 2022-08-16 | Underground | R16 | 2022-07-06 | 1 |  | 34 | 30 | 63 | 2022 | 2022 | R16
161059297517 | 168403297517 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-02 | 2022-05-02 | 2022-10-19 |  | 2023-03-01 | Underground | R16 | 2022-12-12 | 1 | 123 | 39 | 58 | 218 | 2022 | 2023 | R16
163111187322 | 164735187322 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-21 | 2020-01-21 | 2020-04-13 |  | 2020-12-15 | Underground | R16 | 2020-09-10 | 1 | 60 | 109 | 69 | 236 | 2020 | 2020 | R16
166316283608 | 162565283608 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-23 | 2022-06-23 | 2022-06-23 | 2023-01-17 | 2023-01-18 | Overhead | R16 | 2023-01-17 | 1 |  | 149 | 2 | 150 | 2022 | 2023 | R16
167149294416 | 165340294416 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-07-08 | 2022-07-12 | 2022-09-23 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 3 | 54 | 75 |  | 130 | 2022 | 2023 | R16
160307279456 | 164406279456 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2022-05-17 | 2022-05-17 | 2022-05-18 |  | 2022-12-06 | Underground | R16 |  | 1 | 2 |  |  | 146 | 2022 | 2022 | R16
161866271486 | 163768271486 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-04 | 2022-03-04 | 2022-03-04 |  | 2023-04-01 | Overhead | R16 | 2023-01-23 | 1 |  | 232 | 50 | 281 | 2022 | 2023 | R16
163193193110 | 164764193110 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-21 | 2020-01-21 | 2020-06-03 |  | 2022-08-23 | Underground | R16 |  | 1 | 97 |  |  | 676 | 2020 | 2022 | R16
161450281322 | 167531281322 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-01 | 2022-06-01 | 2022-06-01 |  | 2022-10-21 | Overhead | R16 | 2022-09-01 | 1 |  | 67 | 37 | 103 | 2022 | 2022 | R16
164436250168 | 166860250168 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-09-20 | 2021-09-30 | 2021-09-30 |  | 2023-07-07 | Overhead | R16 | 2023-03-16 | 9 |  | 381 | 82 | 470 | 2021 | 2023 | R16
160943257232 | 168613257232 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-09 | 2021-11-18 | 2021-11-18 |  | 2022-03-31 | Underground | R16 | 2022-03-04 | 8 |  | 77 | 20 | 103 | 2021 | 2022 | R16
163236195342 | 163320195342 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-01-14 | 2020-01-14 | 2020-06-25 |  | 2020-10-06 | Underground | R16 |  | 1 | 118 |  |  | 191 | 2020 | 2020 | R16
163236198924 | 163321198924 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-01-14 | 2020-01-14 | 2020-07-29 |  | 2021-02-17 | Underground | R16 |  | 1 | 142 |  |  | 287 | 2020 | 2021 | R16
163841269765 | 169962269765 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-02-17 | 2022-02-17 | 2022-02-18 |  | 2022-06-01 | Overhead | R16 |  | 1 | 2 |  |  | 75 | 2022 | 2022 | R16
162085253620 | 164715253620 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-24 | 2021-10-24 | 2021-10-24 |  | 2022-02-10 | Overhead | R16 | 2022-01-05 | 0 |  | 53 | 27 | 79 | 2021 | 2022 | R16
162406277933 | 162618277933 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-18 | 2022-04-18 | 2022-05-02 |  | 2023-01-10 | Underground | R16 | 2022-11-16 | 1 | 11 | 143 | 40 | 192 | 2022 | 2023 | R16
167862280711 | 166570280711 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-25 | 2022-05-26 | 2022-05-26 |  | 2022-07-26 | Overhead | R16 | 2022-07-25 | 2 |  | 43 | 2 | 45 | 2022 | 2022 | R16
164406286293 | 161318286293 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-04-11 | 2022-04-11 | 2022-07-20 | 2022-10-27 | 2022-11-11 | Underground | R16 | 2022-10-27 | 1 | 73 | 72 | 12 | 155 | 2022 | 2022 | R16
169614273578 | 160726273578 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-22 | 2022-02-22 | 2022-03-23 |  | 2022-05-03 | Underground | R16 | 2022-04-26 | 1 | 22 | 25 | 6 | 51 | 2022 | 2022 | R16
165124270295 | 165269270295 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-28 | 2022-01-28 | 2022-02-24 | 2022-03-16 | 2022-03-17 | Overhead | R16 | 2022-03-16 | 1 | 20 | 15 | 2 | 35 | 2022 | 2022 | R16
163236206335 | 164260206335 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-01-17 | 2020-02-05 | 2020-10-08 |  | 2021-10-25 | Underground | R16 |  | 14 | 177 |  |  | 462 | 2020 | 2021 | R16
169174259042 | 163634259042 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-19 | 2021-11-02 | 2021-11-29 | 2021-12-03 | 2021-12-06 | Underground | R16 | 2021-12-03 | 11 | 20 | 5 | 2 | 35 | 2021 | 2021 | R16
163236227793 | 164433227793 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-08-18 | 2020-08-18 | 2021-04-21 |  | 2021-11-09 | Underground | R16 |  | 1 | 177 |  |  | 321 | 2020 | 2021 | R16
166860266963 | 165226266963 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-28 | 2022-01-28 | 2022-01-31 |  | 2022-02-23 | Overhead | R16 | 2022-02-22 | 1 | 2 | 17 | 2 | 19 | 2022 | 2022 | R16
166294253661 | 164680253661 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-22 | 2021-10-22 | 2021-10-25 | 2022-01-09 | 2022-01-12 | Overhead | R16 | 2022-01-09 | 1 | 2 | 55 | 3 | 59 | 2021 | 2022 | R16
163269182825 | 165939182825 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-01-27 | 2020-03-03 | 2020-03-03 |  | 2020-06-09 | Overhead | R16 | 2020-03-13 | 27 |  | 9 | 63 | 97 | 2020 | 2020 | R16
161016247988 | 165656247988 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-15 | 2021-09-15 | 2021-09-15 |  | 2022-04-01 | Underground | R16 | 2022-03-03 | 1 |  | 122 | 22 | 143 | 2021 | 2022 | R16
160331293190 | 165587293190 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-11 | 2022-09-09 | 2022-09-09 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 45 |  | 85 |  | 129 | 2022 | 2023 | R16
161760272070 | 164464272070 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-08 | 2022-03-08 | 2022-03-09 | 2022-05-09 | 2022-06-09 | Underground | R16 | 2022-05-09 | 1 | 2 | 44 | 24 | 68 | 2022 | 2022 | R16
160271253260 | 169405253260 | NON-RESIDENTIAL - SMALL RETAIL | OH R16 RES NON RES OS | Commercial | 2021-10-01 | 2021-10-12 | 2021-10-21 |  | 2023-01-05 | Overhead | R16 |  | 8 | 8 |  |  | 330 | 2021 | 2023 | R16
163812262762 | 162346262762 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-11-29 | 2021-12-28 | 2021-12-28 |  | 2022-05-04 | Overhead | R16 | 2022-05-03 | 22 |  | 91 | 2 | 113 | 2021 | 2022 | R16
163346180421 | 169343180421 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-02-11 | 2020-02-11 | 2020-02-13 |  | 2022-03-15 | Underground | R16 | 2022-03-14 | 1 | 3 | 543 | 2 | 546 | 2020 | 2022 | R16
168017274832 | 169999274832 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-04 | 2022-04-05 | 2022-04-05 | 2022-07-19 | 2022-09-15 | Overhead | R16 | 2022-07-19 | 2 |  | 76 | 43 | 119 | 2022 | 2022 | R16
165513275223 | 160351275223 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-05 | 2022-04-07 | 2022-04-07 |  | 2022-10-21 | Overhead | R16 | 2022-10-20 | 3 |  | 141 | 2 | 144 | 2022 | 2022 | R16
161953267815 | 164868267815 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-27 | 2022-01-27 | 2022-02-07 | 2022-02-14 | 2022-03-25 | Underground | R16 | 2022-02-14 | 1 | 8 | 6 | 30 | 42 | 2022 | 2022 | R16
161085267570 | 166842267570 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2022-02-03 | 2022-02-04 | 2022-02-04 | 2022-10-06 | 2023-02-10 | Underground | R16 | 2022-10-06 | 2 |  | 175 | 92 | 267 | 2022 | 2023 | R16
167500278625 | 166205278625 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2022-03-16 | 2022-03-29 | 2022-05-09 | 2022-11-09 | 2022-11-21 | Underground | R16 | 2022-11-09 | 10 | 30 | 133 | 9 | 179 | 2022 | 2022 | R16
162487254058 | 165475254058 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-27 | 2021-10-27 | 2021-10-27 | 2022-07-14 | 2022-07-15 | Overhead | R16 | 2022-07-14 | 1 |  | 187 | 2 | 188 | 2021 | 2022 | R16
163429264152 | 165453264152 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2021-12-13 | 2021-12-27 | 2022-01-10 |  | 2022-09-15 | Underground | R16 | 2022-07-19 | 11 | 11 | 137 | 43 | 199 | 2021 | 2022 | R16
161298271458 | 163683271458 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-04 | 2022-03-04 | 2022-03-04 |  | 2022-07-17 | Overhead | R16 | 2022-07-07 | 1 |  | 90 | 7 | 96 | 2022 | 2022 | R16
168327260313 | 168191260313 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-09-27 | 2021-09-27 | 2021-12-08 | 2022-02-15 | 2022-03-14 | Overhead | R16 | 2022-02-15 | 1 | 53 | 50 | 20 | 121 | 2021 | 2022 | R16
164154289708 | 167734289708 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-19 | 2022-07-19 | 2022-08-19 | 2022-10-17 | 2022-10-20 | Underground | R16 | 2022-10-17 | 1 | 24 | 42 | 4 | 68 | 2022 | 2022 | R16
165036279195 | 163824279195 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-05-13 | 2022-05-13 | 2022-05-13 |  | 2022-12-14 | Underground | R16 | 2022-11-02 | 1 |  | 124 | 31 | 154 | 2022 | 2022 | R16
163482179374 | 168224179374 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-05 | 2020-02-05 | 2020-02-05 |  | 2022-06-01 | Overhead | R16 | 2020-04-21 | 1 |  | 55 | 552 | 606 | 2020 | 2022 | R16
166172282314 | 169758282314 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-10 | 2022-06-10 | 2022-06-10 |  | 2022-08-26 | Overhead | R16 | 2022-08-08 | 1 |  | 42 | 15 | 56 | 2022 | 2022 | R16
163512178521 | 166372178521 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-28 | 2020-01-28 | 2020-01-28 |  | 2020-06-09 | Underground | R16 | 2020-03-11 | 1 |  | 32 | 65 | 96 | 2020 | 2020 | R16
160845285707 | 166924285707 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Commercial | 2022-03-18 | 2022-06-01 | 2022-07-15 | 2023-05-31 | 2023-07-17 | Overhead | R16 | 2023-05-31 | 54 | 33 | 229 | 34 | 347 | 2022 | 2023 | R16
164630286839 | 168959286839 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-25 | 2022-07-26 | 2022-07-26 | 2022-09-01 | 2022-09-02 | Overhead | R16 | 2022-09-01 | 2 |  | 28 | 2 | 30 | 2022 | 2022 | R16
168871258730 | 169932258730 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-11-16 | 2021-11-24 | 2021-11-24 | 2022-09-26 | 2023-01-05 | Overhead | R16 | 2022-09-26 | 7 |  | 219 | 74 | 298 | 2021 | 2023 | R16
161054259215 | 162892259215 | FOREIGN UTILITY | OH R16 RES NON RES OS | Residential | 2021-11-30 | 2021-11-30 | 2021-11-30 | 2022-04-20 | 2022-05-18 | Overhead | R16 | 2022-04-20 | 1 |  | 102 | 21 | 122 | 2021 | 2022 | R16
163577178506 | 166289178506 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-29 | 2020-01-29 | 2020-01-29 |  | 2020-07-07 | Overhead | R16 | 2020-05-07 | 1 |  | 72 | 44 | 115 | 2020 | 2020 | R16
162317268459 | 167349268459 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-07 | 2022-02-07 | 2022-02-10 | 2022-04-06 | 2022-05-04 | Underground | R16 | 2022-04-06 | 1 | 4 | 40 | 21 | 63 | 2022 | 2022 | R16
163649185464 | 168382185464 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-26 | 2020-03-26 | 2020-03-26 |  | 2020-07-09 | Overhead | R16 | 2020-06-03 | 1 |  | 50 | 27 | 76 | 2020 | 2020 | R16
168682319273 | 168311319273 | NON-RESIDENTIAL - MISCELLANEOUS | UG ELEC MISC SVC US | Commercial | 2022-05-02 | 2022-05-31 | 2023-05-16 |  | 2023-12-11 | Underground | R16 |  | 22 | 251 |  |  | 421 | 2022 | 2023 | R16
163655177793 | 164896177793 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-21 | 2020-01-23 | 2020-01-23 |  | 2020-06-09 | Overhead | R16 | 2020-03-10 | 3 |  | 34 | 66 | 101 | 2020 | 2020 | R16
164468268524 | 169809268524 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-05 | 2022-01-05 | 2022-02-10 | 2022-05-16 | 2022-05-17 | Underground | R16 | 2022-05-16 | 1 | 27 | 68 | 2 | 95 | 2022 | 2022 | R16
161039269521 | 169699269521 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-17 | 2022-02-17 | 2022-02-17 |  | 2022-12-06 | Overhead | R16 | 2022-09-26 | 1 |  | 158 | 52 | 209 | 2022 | 2022 | R16
167659283657 | 168623283657 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-07 | 2022-06-21 | 2022-06-24 | 2023-07-20 | 2023-08-25 | Overhead | R16 | 2023-07-20 | 11 | 4 | 280 | 27 | 319 | 2022 | 2023 | R16
168544276285 | 162712276285 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-18 | 2022-04-18 | 2022-04-18 | 2023-01-10 | 2023-01-11 | Overhead | R16 | 2023-01-10 | 1 |  | 192 | 2 | 193 | 2022 | 2023 | R16
166161281582 | 169809281582 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-05 | 2021-10-05 | 2022-06-03 | 2022-07-18 | 2022-09-14 | Underground | R16 | 2022-07-18 | 1 | 174 | 32 | 43 | 247 | 2021 | 2022 | R16
168314265260 | 165994265260 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-15 | 2021-12-15 | 2022-01-19 | 2022-03-08 | 2022-03-11 | Overhead | R16 | 2022-03-08 | 1 | 26 | 35 | 4 | 63 | 2021 | 2022 | R16
163982285980 | 167202285980 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-18 | 2022-07-18 | 2022-07-18 |  | 2023-03-03 | Overhead | R16 | 2022-12-07 | 1 |  | 103 | 63 | 165 | 2022 | 2023 | R16
160109284241 | 161508284241 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-20 | 2022-06-29 | 2022-06-29 | 2022-12-15 | 2022-12-21 | Overhead | R16 | 2022-12-15 | 8 |  | 122 | 5 | 133 | 2022 | 2022 | R16
162433260453 | 162836260453 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-15 | 2021-12-09 | 2021-12-09 | 2022-02-07 | 2023-06-08 | Overhead | R16 | 2022-02-07 | 40 |  | 43 | 349 | 430 | 2021 | 2023 | R16
164455273794 | 168142273794 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-25 | 2022-03-25 | 2022-03-25 | 2022-07-28 | 2022-08-05 | Overhead | R16 | 2022-07-28 | 1 |  | 90 | 7 | 96 | 2022 | 2022 | R16
163770207798 | 163801207798 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-04-24 | 2020-04-28 | 2020-10-22 |  | 2021-01-27 | Overhead | R16 |  | 3 | 128 |  |  | 199 | 2020 | 2021 | R16
163063268905 | 168331268905 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential Subdivision | 2022-02-10 | 2022-02-10 | 2022-02-14 |  | 2023-06-15 | Underground | R16 |  | 1 | 3 |  |  | 351 | 2022 | 2023 | R16
164786271504 | 169767271504 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-16 | 2022-02-22 | 2022-03-04 | 2022-05-31 | 2022-06-14 | Underground | R16 | 2022-05-31 | 5 | 9 | 63 | 11 | 85 | 2022 | 2022 | R16
166099281654 | 163787281654 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-13 | 2022-05-13 | 2022-06-07 |  | 2023-05-18 | Overhead | R16 | 2023-03-15 | 1 | 18 | 202 | 47 | 265 | 2022 | 2023 | R16
167578253136 | 161449253136 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-11 | 2021-10-11 | 2021-10-21 | 2021-12-06 | 2021-12-10 | Underground | R16 | 2021-12-06 | 1 | 9 | 33 | 5 | 45 | 2021 | 2021 | R16
165653282196 | 169704282196 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-10 | 2022-06-10 | 2022-06-10 |  | 2022-07-29 | Overhead | R16 | 2022-07-21 | 1 |  | 30 | 7 | 36 | 2022 | 2022 | R16
163799179246 | 166952179246 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-30 | 2020-02-03 | 2020-02-03 |  | 2020-08-28 | Overhead | R16 | 2020-07-01 | 3 |  | 108 | 43 | 152 | 2020 | 2020 | R16
164383312811 | 162422312811 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-06-23 | 2023-03-17 | 2023-03-17 | 2023-08-14 | 2023-08-21 | Underground | R16 | 2023-08-14 | 192 |  | 107 | 6 | 303 | 2022 | 2023 | R16
169055303777 | 167033303777 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2022-03-21 | 2022-12-16 | 2022-12-21 |  | 2023-08-14 | Overhead | R16 |  | 195 | 4 |  |  | 366 | 2022 | 2023 | R16
163825184063 | 165737184063 | NON-RESIDENTIAL - SMALL OFFICE | R16 RESD AND NON RESD US | Commercial | 2020-03-11 | 2020-03-11 | 2020-03-13 |  | 2020-10-06 | Underground | R16 |  | 1 | 3 |  |  | 150 | 2020 | 2020 | R16
160537277495 | 161069277495 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-08 | 2022-04-08 | 2022-04-28 |  | 2022-06-17 | Overhead | R16 |  | 1 | 15 |  |  | 51 | 2022 | 2022 | R16
168566272892 | 160228272892 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-11-17 | 2021-11-17 | 2022-03-17 | 2022-04-26 | 2022-05-11 | Underground | R16 | 2022-04-26 | 1 | 87 | 29 | 12 | 126 | 2021 | 2022 | R16
163982187341 | 169894187341 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-13 | 2020-02-13 | 2020-04-13 |  | 2020-10-06 | Underground | R16 | 2020-07-24 | 1 | 43 | 75 | 53 | 169 | 2020 | 2020 | R16
162477261313 | 165520261313 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-13 | 2021-12-13 | 2021-12-14 | 2022-02-03 | 2022-04-12 | Underground | R16 | 2022-02-03 | 1 | 2 | 38 | 49 | 87 | 2021 | 2022 | R16
163568261401 | 165990261401 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-14 | 2021-12-15 | 2021-12-15 | 2022-03-24 | 2022-05-13 | Overhead | R16 | 2022-03-24 | 2 |  | 72 | 37 | 109 | 2021 | 2022 | R16
164200180157 | 166312180157 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-28 | 2020-01-28 | 2020-02-12 |  | 2021-07-12 | Underground | R16 | 2020-11-24 | 1 | 12 | 205 | 165 | 380 | 2020 | 2021 | R16
164793267235 | 166120267235 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2022-02-01 | 2022-02-02 | 2022-02-03 |  | 2023-03-13 | Overhead | R16 |  | 2 | 2 |  |  | 290 | 2022 | 2023 | R16
164204187860 | 160458187860 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-14 | 2020-03-26 | 2020-04-16 |  | 2021-07-01 | Underground | R16 |  | 30 | 16 |  |  | 360 | 2020 | 2021 | R16
164256272035 | 164280272035 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-03-07 | 2022-03-07 | 2022-03-10 | 2022-03-14 | 2022-03-22 | Overhead | R16 | 2022-03-14 | 1 | 4 | 3 | 7 | 12 | 2022 | 2022 | R16
162982266410 | 164439266410 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-08 | 2022-01-27 | 2022-01-27 |  | 2023-03-31 | Overhead | R16 | 2023-02-17 | 37 |  | 277 | 31 | 343 | 2021 | 2023 | R16
169143282869 | 160343282869 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-14 | 2022-06-16 | 2022-06-16 |  | 2022-10-21 | Overhead | R16 | 2022-08-31 | 3 |  | 55 | 38 | 94 | 2022 | 2022 | R16
169945277056 | 161838277056 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-13 | 2022-04-13 | 2022-04-25 | 2022-05-12 | 2022-06-20 | Underground | R16 | 2022-05-12 | 1 | 9 | 14 | 28 | 49 | 2022 | 2022 | R16
165247272320 | 165709272320 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-01-31 | 2022-01-31 | 2022-03-11 |  | 2022-08-11 | Underground | R16 | 2022-06-30 | 1 | 30 | 80 | 31 | 139 | 2022 | 2022 | R16
164241265470 | 163151265470 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-20 | 2022-01-20 | 2022-01-20 | 2022-05-16 | 2022-06-30 | Overhead | R16 | 2022-05-16 | 1 |  | 83 | 34 | 116 | 2022 | 2022 | R16
165712328460 | 165677328460 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-02-01 | 2022-02-01 | 2023-08-15 |  | 2023-10-23 | Overhead | R16 | 2023-10-18 | 1 | 401 | 47 | 4 | 450 | 2022 | 2023 | R16
164836259325 | 162977259325 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2022-08-01 | 2022-08-02 | Overhead | R16 | 2022-08-01 | 1 |  | 174 | 2 | 175 | 2021 | 2022 | R16
161059268526 | 163633268526 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-10-19 | 2022-02-09 | 2022-02-10 | 2022-11-28 | 2022-11-28 | Underground | R16 | 2022-11-28 | 82 | 2 | 208 |  | 290 | 2021 | 2022 | R16
163575261709 | 166595261709 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-12-17 | 2021-12-17 | 2021-12-17 |  | 2022-03-28 | Overhead | R16 | 2022-03-10 | 1 |  | 60 | 13 | 72 | 2021 | 2022 | R16
164107284396 | 169689284396 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG R16 RESD AND NON RESD UD | Commercial | 2022-04-01 | 2022-05-04 | 2022-07-01 | 2022-10-22 | 2023-11-30 | Underground | R16 | 2022-10-22 | 24 | 43 | 81 | 289 | 435 | 2022 | 2023 | R16
169886270203 | 161051270203 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-23 | 2022-02-23 | 2022-02-23 |  | 2022-06-01 | Overhead | R16 | 2022-05-05 | 1 |  | 52 | 20 | 71 | 2022 | 2022 | R16
164877179341 | 164944179341 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2020-01-21 | 2020-01-21 | 2020-02-04 |  | 2020-10-06 | Overhead | R16 |  | 1 | 11 |  |  | 186 | 2020 | 2020 | R16
164884190988 | 160858190988 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-04-09 | 2020-05-12 | 2020-05-13 |  | 2020-07-08 | Overhead | R16 |  | 24 | 2 |  |  | 65 | 2020 | 2020 | R16
160614272118 | 165196272118 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-10 | 2022-03-10 | 2022-03-10 |  | 2022-12-13 | Overhead | R16 | 2022-12-09 | 1 |  | 197 | 3 | 199 | 2022 | 2022 | R16
165500290073 | 162566290073 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-23 | 2022-06-23 | 2022-08-23 | 2022-09-09 | 2023-03-24 | Underground | R16 | 2022-09-09 | 1 | 44 | 14 | 141 | 197 | 2022 | 2023 | R16
162805250393 | 169180250393 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-09-30 | 2021-10-04 | 2021-10-04 |  | 2021-11-13 | Overhead | R16 | 2021-10-20 | 3 |  | 13 | 18 | 32 | 2021 | 2021 | R16
164915183803 | 165596183803 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-11 | 2020-03-11 | 2020-03-11 |  | 2021-07-23 | Overhead | R16 | 2020-10-27 | 1 |  | 165 | 194 | 358 | 2020 | 2021 | R16
165536266351 | 166980266351 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-11-03 | 2021-11-03 | 2022-01-27 |  | 2022-02-11 | Underground | R16 | 2022-02-10 | 1 | 62 | 11 | 2 | 73 | 2021 | 2022 | R16
168295284980 | 165096284980 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-08 | 2022-07-08 | 2022-07-08 | 2022-08-24 | 2022-08-25 | Overhead | R16 | 2022-08-24 | 1 |  | 34 | 2 | 35 | 2022 | 2022 | R16
163857277250 | 160944277250 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-04-08 | 2022-04-08 | 2022-04-27 | 2022-08-04 | 2022-09-13 | Overhead | R16 | 2022-08-04 | 1 | 14 | 72 | 29 | 113 | 2022 | 2022 | R16
165944299562 | 163720299562 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-19 | 2022-11-04 | 2022-11-04 |  | 2023-04-12 | Overhead | R16 | 2023-01-20 | 274 |  | 56 | 59 | 387 | 2021 | 2023 | R16
165071202272 | 167114202272 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-27 | 2020-08-27 | 2020-09-01 |  | 2021-08-12 | Overhead | R16 |  | 1 | 4 |  |  | 251 | 2020 | 2021 | R16
167998257120 | 169239257120 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2021-11-12 | 2021-11-12 | 2021-11-17 | 2021-11-19 | 2021-12-08 | Overhead | R16 | 2021-11-19 | 1 | 4 | 3 | 14 | 19 | 2021 | 2021 | R16
165113188308 | 166083188308 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-01-27 | 2020-01-27 | 2020-04-20 |  | 2023-01-10 | Underground | R16 | 2022-11-17 | 1 | 61 | 674 | 39 | 772 | 2020 | 2023 | R16
165114193664 | 166068193664 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-01-27 | 2020-01-27 | 2020-06-08 |  | 2023-12-04 | Underground | R16 | 2023-10-06 | 1 | 96 | 870 | 42 | 1006 | 2020 | 2023 | R16
165158210928 | 169801210928 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-10-22 | 2020-11-13 | 2020-11-17 |  | 2023-06-27 | Underground | R16 |  | 17 | 3 |  |  | 699 | 2020 | 2023 | R16
165218250573 | 169940250573 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-04 | 2021-10-04 | 2021-10-04 |  | 2022-04-05 | Underground | R16 | 2022-03-15 | 1 |  | 117 | 16 | 132 | 2021 | 2022 | R16
165989271196 | 162889271196 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2022-03-02 | 2022-03-03 | 2022-03-03 | 2022-08-08 | 2022-08-09 | Overhead | R16 | 2022-08-08 | 2 |  | 113 | 2 | 115 | 2022 | 2022 | R16
165167184132 | 166401184132 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-16 | 2020-03-16 | 2020-03-16 |  | 2020-06-09 | Overhead | R16 | 2020-03-25 | 1 |  | 8 | 55 | 62 | 2020 | 2020 | R16
161677285957 | 167412285957 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-19 | 2022-07-19 | 2022-07-19 |  | 2022-08-30 | Underground | R16 | 2022-08-29 | 1 |  | 30 | 2 | 31 | 2022 | 2022 | R16
165775290857 | 168802290857 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-06-07 | 2022-06-29 | 2022-08-31 | 2022-12-13 | 2022-12-13 | Underground | R16 | 2022-12-13 | 17 | 46 | 75 |  | 136 | 2022 | 2022 | R16
167975258707 | 162188258707 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2022-01-21 | 2022-03-07 | Overhead | R16 | 2022-01-21 | 1 |  | 43 | 32 | 74 | 2021 | 2022 | R16
161705272228 | 163782272228 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-04 | 2022-03-04 | 2022-03-11 | 2022-03-29 | 2022-04-26 | Underground | R16 | 2022-03-29 | 1 | 6 | 13 | 21 | 38 | 2022 | 2022 | R16
160101287910 | 162645287910 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2022-04-18 | 2022-04-18 | 2022-08-04 | 2023-02-21 | 2023-09-05 | Underground | R16 | 2023-02-21 | 1 | 79 | 144 | 141 | 362 | 2022 | 2023 | R16
165265185783 | 161714185783 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-02-21 | 2020-02-21 | 2020-03-30 |  | 2020-07-02 | Underground | R16 | 2020-05-05 | 1 | 27 | 27 | 43 | 95 | 2020 | 2020 | R16
165363249244 | 167692249244 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-23 | 2021-09-23 | 2021-09-23 | 2021-10-19 | 2021-10-20 | Overhead | R16 | 2021-10-19 | 1 |  | 19 | 2 | 20 | 2021 | 2021 | R16
165273202628 | 161700202628 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-11 | 2020-09-01 | 2020-09-02 |  | 2020-12-15 | Overhead | R16 |  | 59 | 2 |  |  | 134 | 2020 | 2020 | R16
162985264151 | 169916264151 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-06 | 2022-01-10 | 2022-01-10 | 2022-03-13 | 2022-03-16 | Underground | R16 | 2022-03-13 | 3 |  | 45 | 3 | 50 | 2022 | 2022 | R16
161951268554 | 168400268554 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-10 | 2022-02-10 | 2022-02-10 |  | 2022-04-15 | Overhead | R16 | 2022-04-13 | 1 |  | 45 | 3 | 47 | 2022 | 2022 | R16
169920254684 | 166521254684 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-11-02 | 2021-11-02 | 2021-11-02 |  | 2022-04-01 | Underground | R16 | 2022-03-18 | 1 |  | 99 | 11 | 109 | 2021 | 2022 | R16
165033265098 | 162413265098 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-05-10 | 2022-05-11 | Overhead | R16 | 2022-05-10 | 1 |  | 81 | 2 | 82 | 2022 | 2022 | R16
165512310517 | 162952310517 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-10 | 2022-05-10 | 2023-02-24 | 2023-04-19 | 2023-08-14 | Underground | R16 | 2023-04-19 | 1 | 209 | 39 | 84 | 330 | 2022 | 2023 | R16
162522253972 | 162834253972 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-15 | 2021-10-27 | 2021-10-27 | 2022-04-25 | 2022-04-28 | Overhead | R16 | 2022-04-25 | 9 |  | 129 | 4 | 140 | 2021 | 2022 | R16
165319301486 | 165601301486 | NON-RESIDENTIAL - LARGE OFFICE | R16 RESD AND NON RESD US | Commercial | 2022-03-14 | 2022-09-28 | 2022-11-23 | 2023-05-25 | 2023-05-31 | Underground | R16 | 2023-05-25 | 143 | 41 | 132 | 5 | 318 | 2022 | 2023 | R16
165432178311 | 166187178311 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-28 | 2020-01-28 | 2020-01-28 |  | 2020-06-09 | Overhead | R16 | 2020-02-26 | 1 |  | 22 | 75 | 96 | 2020 | 2020 | R16
167272294216 | 169163294216 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2022-07-26 | 2022-07-26 | 2022-09-20 | 2023-03-22 | 2023-05-05 | Underground | R16 | 2023-03-22 | 1 | 41 | 132 | 33 | 204 | 2022 | 2023 | R16
165436190998 | 163639190998 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2020-04-24 | 2020-04-24 | 2020-05-14 |  | 2020-10-06 | Underground | R16 | 2020-08-27 | 1 | 15 | 76 | 29 | 118 | 2020 | 2020 | R16
165496196729 | 160891196729 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-06-08 | 2020-06-08 | 2020-07-08 |  | 2023-01-05 | Underground | R16 | 2022-10-13 | 1 | 23 | 592 | 61 | 674 | 2020 | 2023 | R16
166346265515 | 163082265515 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-20 | 2022-01-20 | 2022-01-20 |  | 2022-10-18 | Overhead | R16 | 2022-10-14 | 1 |  | 192 | 3 | 194 | 2022 | 2022 | R16
165523184253 | 168314184253 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-02-05 | 2020-02-05 | 2020-03-17 |  | 2023-08-15 | Underground | R16 | 2023-07-21 | 1 | 30 | 874 | 18 | 920 | 2020 | 2023 | R16
165570178680 | 166514178680 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-01-29 | 2020-01-29 | 2020-01-29 |  | 2021-01-07 | Underground | R16 | 2020-10-02 | 1 |  | 178 | 70 | 247 | 2020 | 2021 | R16
166152264667 | 161705264667 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-01-13 | 2022-01-13 | 2022-01-13 | 2022-03-18 | 2022-04-22 | Overhead | R16 | 2022-03-18 | 1 |  | 47 | 26 | 72 | 2022 | 2022 | R16
160322302401 | 161093302401 | NON-RESIDENTIAL - SMALL RETAIL | UG R16 RESD AND NON RESD UD | Commercial | 2022-04-08 | 2022-09-14 | 2022-12-05 | 2023-03-01 | 2023-04-20 | Underground | R16 | 2023-03-01 | 114 | 59 | 63 | 37 | 270 | 2022 | 2023 | R16
163367279234 | 165210279234 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-04-28 | 2022-05-13 | 2022-05-13 | 2023-06-22 | 2023-07-05 | Underground | R16 | 2023-06-22 | 12 |  | 290 | 10 | 310 | 2022 | 2023 | R16
165664273337 | 167069273337 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-21 | 2022-03-22 | 2022-03-22 | 2022-10-26 | 2023-01-10 | Overhead | R16 | 2022-10-26 | 2 |  | 157 | 55 | 212 | 2022 | 2023 | R16
163308259475 | 160747259475 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-19 | 2021-12-02 | 2021-12-02 | 2022-10-26 | 2022-11-17 | Underground | R16 | 2022-10-26 | 10 |  | 235 | 17 | 260 | 2021 | 2022 | R16
165824260149 | 162725260149 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-30 | 2021-12-01 | 2021-12-07 |  | 2022-05-19 | Overhead | R16 |  | 2 | 5 |  |  | 123 | 2021 | 2022 | R16
169705271479 | 161964271479 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2022-02-25 | 2022-03-04 | 2022-03-04 |  | 2022-09-20 | Overhead | R16 | 2022-08-04 | 6 |  | 110 | 34 | 148 | 2022 | 2022 | R16
168726259714 | 160338259714 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-17 | 2021-11-17 | 2021-12-03 | 2022-01-26 | 2022-03-03 | Underground | R16 | 2022-01-26 | 1 | 13 | 39 | 27 | 77 | 2021 | 2022 | R16
169276270853 | 165345270853 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-01-28 | 2022-02-28 | 2022-02-28 | 2023-07-17 | 2023-07-20 | Underground | R16 | 2023-07-17 | 22 |  | 361 | 4 | 385 | 2022 | 2023 | R16
165791190254 | 165693190254 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-01-24 | 2020-01-24 | 2020-05-07 |  | 2021-07-24 | Underground | R16 | 2020-10-30 | 1 | 75 | 127 | 191 | 391 | 2020 | 2021 | R16
166514262648 | 167861262648 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-27 | 2021-12-27 | 2021-12-27 | 2022-01-20 | 2022-03-02 | Overhead | R16 | 2022-01-20 | 1 |  | 19 | 30 | 48 | 2021 | 2022 | R16
165798188709 | 165504188709 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-01-24 | 2020-01-24 | 2020-04-22 |  | 2021-07-24 | Underground | R16 |  | 1 | 64 |  |  | 391 | 2020 | 2021 | R16
162731250832 | 160143250832 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-05 | 2021-10-05 | 2021-10-05 | 2022-02-02 | 2022-02-03 | Overhead | R16 | 2022-02-02 | 1 |  | 87 | 2 | 88 | 2021 | 2022 | R16
163399260423 | 164006260423 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-21 | 2021-12-08 | 2021-12-08 |  | 2022-05-06 | Overhead | R16 | 2022-05-06 | 35 |  | 108 |  | 142 | 2021 | 2022 | R16
169592288261 | 164007288261 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-30 | 2022-06-30 | 2022-08-08 | 2022-11-22 | 2022-11-24 | Underground | R16 | 2022-11-22 | 1 | 28 | 77 | 3 | 106 | 2022 | 2022 | R16
164454284337 | 164284284337 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-01 | 2022-07-01 | 2022-07-01 | 2022-08-22 | 2022-08-29 | Overhead | R16 | 2022-08-22 | 1 |  | 37 | 6 | 42 | 2022 | 2022 | R16
169332283206 | 164286283206 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-04-27 | 2022-04-27 | 2022-06-20 |  | 2022-08-16 | Overhead | R16 | 2022-07-12 | 1 | 39 | 17 | 26 | 80 | 2022 | 2022 | R16
165827184377 | 165737184377 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-01-24 | 2020-01-24 | 2020-03-18 |  | 2021-02-17 | Underground | R16 | 2020-10-16 | 1 | 39 | 153 | 89 | 279 | 2020 | 2021 | R16
167010303435 | 165580303435 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH CP R16 WORK RELO TO UG | Residential | 2021-12-13 | 2022-02-04 | 2022-12-19 | 2023-03-01 | 2023-05-05 | Overhead | R16 | 2023-03-01 | 40 | 227 | 53 | 48 | 365 | 2021 | 2023 | R16
164431279443 | 164237279443 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-16 | 2022-05-16 | 2022-05-16 | 2022-05-18 | 2022-06-23 | Overhead | R16 | 2022-05-18 | 1 |  | 3 | 27 | 29 | 2022 | 2022 | R16
165993186144 | 166002186144 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-27 | 2020-01-27 | 2020-04-01 |  | 2021-10-25 | Underground | R16 | 2021-09-16 | 1 | 48 | 382 | 28 | 456 | 2020 | 2021 | R16
161141277994 | 161817277994 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-13 | 2022-04-22 | 2022-05-03 |  | 2023-09-14 | Underground | R16 |  | 8 | 8 |  |  | 372 | 2022 | 2023 | R16
160845268310 | 167782268310 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-08 | 2022-02-09 | 2022-02-09 |  | 2022-05-11 | Underground | R16 | 2022-05-09 | 2 |  | 64 | 3 | 67 | 2022 | 2022 | R16
166100189684 | 164965189684 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-01 | 2020-05-01 | 2020-05-01 |  | 2021-04-07 | Overhead | R16 | 2020-12-04 | 1 |  | 156 | 89 | 244 | 2020 | 2021 | R16
163712254507 | 166230254507 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-01 | 2021-11-01 | 2021-11-01 | 2021-11-12 | 2021-12-02 | Overhead | R16 | 2021-11-12 | 1 |  | 10 | 15 | 24 | 2021 | 2021 | R16
165225267017 | 165906267017 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-01 | 2022-02-02 | 2022-02-02 |  | 2022-03-25 | Overhead | R16 | 2022-03-08 | 2 |  | 25 | 14 | 39 | 2022 | 2022 | R16
161964258985 | 161928258985 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-11-24 | 2021-11-29 | 2021-11-29 |  | 2022-01-12 | Underground | R16 | 2021-12-02 | 4 |  | 4 | 30 | 36 | 2021 | 2022 | R16
166308182973 | 164234182973 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-05 | 2020-03-05 | 2020-03-05 |  | 2020-06-09 | Overhead | R16 | 2020-04-15 | 1 |  | 30 | 40 | 69 | 2020 | 2020 | R16
163153278338 | 161330278338 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-05 | 2022-05-05 | 2022-05-05 | 2022-08-31 | 2022-10-26 | Overhead | R16 | 2022-08-31 | 1 |  | 85 | 41 | 125 | 2022 | 2022 | R16
167873277001 | 169649277001 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-16 | 2022-02-16 | 2022-04-25 | 2022-05-22 | 2023-06-10 | Underground | R16 | 2022-05-22 | 1 | 49 | 20 | 275 | 343 | 2022 | 2023 | R16
161108261564 | 163687261564 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-19 | 2021-11-02 | 2021-12-15 | 2022-02-16 | 2022-02-25 | Underground | R16 | 2022-02-16 | 11 | 32 | 46 | 8 | 94 | 2021 | 2022 | R16
166381199452 | 166508199452 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-01-29 | 2020-01-29 | 2020-08-04 |  | 2020-12-15 | Underground | R16 | 2020-09-10 | 1 | 135 | 28 | 69 | 230 | 2020 | 2020 | R16
163474280725 | 164338280725 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-16 | 2022-05-16 | 2022-05-25 |  | 2022-07-17 | Underground | R16 | 2022-07-12 | 1 | 8 | 35 | 4 | 45 | 2022 | 2022 | R16
163348273039 | 166718273039 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2022-03-18 | 2022-03-18 | 2022-03-18 |  | 2022-12-09 | Underground | R16 | 2022-10-12 | 1 |  | 149 | 43 | 191 | 2022 | 2022 | R16
168659264279 | 163133264279 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2021-12-01 | 2021-12-01 | 2022-01-11 | 2023-09-24 | 2023-09-24 | Underground | R16 | 2023-09-24 | 1 | 30 | 444 |  | 473 | 2021 | 2023 | R16
166394185035 | 167464185035 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-23 | 2020-03-23 | 2020-03-23 |  | 2020-07-02 | Overhead | R16 | 2020-05-04 | 1 |  | 31 | 44 | 74 | 2020 | 2020 | R16
165186255483 | 168024255483 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-08 | 2021-11-08 | 2021-11-08 | 2022-03-31 | 2022-08-01 | Overhead | R16 | 2022-03-31 | 1 |  | 104 | 88 | 191 | 2021 | 2022 | R16
167534269526 | 166058269526 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC DEVELOPMENT | Residential Subdivision | 2021-10-29 | 2022-02-16 | 2022-02-17 | 2023-01-20 | 2023-01-20 | Underground | R16 | 2023-01-20 | 79 | 2 | 242 |  | 321 | 2021 | 2023 | R16
168011274452 | 164855274452 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-10 | 2022-03-10 | 2022-03-31 |  | 2022-06-06 | Underground | R16 | 2022-05-09 | 1 | 16 | 28 | 21 | 63 | 2022 | 2022 | R16
165565259513 | 163118259513 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-02 | 2021-12-02 | 2021-12-02 | 2022-01-07 | 2022-03-08 | Overhead | R16 | 2022-01-07 | 1 |  | 27 | 43 | 69 | 2021 | 2022 | R16
166641256272 | 169305256272 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2022-02-09 | 2022-02-10 | Overhead | R16 | 2022-02-09 | 1 |  | 64 | 2 | 65 | 2021 | 2022 | R16
166423187870 | 161463187870 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-13 | 2020-04-14 | 2020-04-16 |  | 2020-08-20 | Overhead | R16 | 2020-05-19 | 2 | 3 | 24 | 68 | 94 | 2020 | 2020 | R16
167211270161 | 161031270161 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-23 | 2022-02-23 | 2022-02-23 |  | 2022-12-05 | Overhead | R16 | 2022-12-05 | 1 |  | 204 |  | 204 | 2022 | 2022 | R16
166494181329 | 161661181329 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-21 | 2020-02-21 | 2020-02-21 |  | 2020-07-07 | Overhead | R16 | 2020-05-07 | 1 |  | 55 | 44 | 98 | 2020 | 2020 | R16
167173256309 | 169371256309 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-12-29 | 2022-02-11 | Overhead | R16 | 2021-12-29 | 1 |  | 34 | 33 | 66 | 2021 | 2022 | R16
167076281874 | 167525281874 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-01 | 2022-06-07 | 2022-06-07 | 2022-09-15 | 2023-01-05 | Overhead | R16 | 2022-09-15 | 5 |  | 73 | 81 | 157 | 2022 | 2023 | R16
166520180133 | 168848180133 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-10 | 2020-02-11 | 2020-02-11 |  | 2020-06-09 | Underground | R16 | 2020-03-31 | 2 |  | 36 | 51 | 87 | 2020 | 2020 | R16
164207262539 | 167489262539 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-22 | 2021-12-22 | 2021-12-28 | 2022-05-28 | 2022-05-31 | Underground | R16 | 2022-05-28 | 1 | 5 | 109 | 2 | 115 | 2021 | 2022 | R16
168701283464 | 169586283464 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2022-06-10 | 2022-06-10 | 2022-06-22 | 2023-08-25 | 2023-07-11 | Underground | R16 | 2023-08-25 | 1 | 9 | 308 |  | 283 | 2022 | 2023 | R16
162417263519 | 167297263519 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-22 | 2022-01-05 | 2022-01-05 |  | 2022-03-02 | Overhead | R16 | 2022-01-31 | 11 |  | 19 | 23 | 51 | 2021 | 2022 | R16
161961284327 | 162808284327 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-15 | 2021-10-15 | 2022-07-01 | 2022-09-16 | 2023-06-08 | Underground | R16 | 2022-09-16 | 1 | 186 | 56 | 190 | 430 | 2021 | 2023 | R16
164180277986 | 168913277986 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-03-29 | 2022-04-07 | 2022-05-02 |  | 2022-06-30 | Overhead | R16 |  | 8 | 18 |  |  | 68 | 2022 | 2022 | R16
161062253211 | 163871253211 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-10-20 | 2021-10-20 | 2021-10-21 | 2022-03-29 | 2022-04-26 | Overhead | R16 | 2022-03-29 | 1 | 2 | 114 | 21 | 135 | 2021 | 2022 | R16
165606273526 | 167473273526 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-22 | 2022-03-22 | 2022-03-22 | 2022-03-29 | 2022-04-06 | Overhead | R16 | 2022-03-29 | 1 |  | 6 | 7 | 12 | 2022 | 2022 | R16
161608276551 | 162863276551 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-19 | 2022-04-21 | 2022-04-21 | 2022-07-06 | 2022-08-16 | Overhead | R16 | 2022-07-06 | 3 |  | 55 | 30 | 86 | 2022 | 2022 | R16
166667187480 | 167058187480 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-31 | 2020-01-31 | 2020-04-14 |  | 2023-02-06 | Underground | R16 |  | 1 | 53 |  |  | 787 | 2020 | 2023 | R16
167841257174 | 160257257174 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-17 | 2021-11-17 | 2021-11-18 |  | 2022-04-01 | Overhead | R16 | 2022-03-17 | 1 | 2 | 86 | 12 | 98 | 2021 | 2022 | R16
166726183732 | 165390183732 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-10 | 2020-03-10 | 2020-03-10 |  | 2020-06-24 | Overhead | R16 | 2020-04-22 | 1 |  | 32 | 46 | 77 | 2020 | 2020 | R16
164849278606 | 162569278606 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-09 | 2022-05-09 | 2022-05-09 |  | 2022-06-12 | Overhead | R16 | 2022-05-24 | 1 |  | 12 | 14 | 25 | 2022 | 2022 | R16
162278267645 | 163262267645 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-20 | 2022-01-31 | 2022-02-04 | 2022-05-21 | 2023-05-04 | Underground | R16 | 2022-05-21 | 8 | 5 | 76 | 249 | 336 | 2022 | 2023 | R16
166801179428 | 167856179428 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-05 | 2020-02-05 | 2020-02-05 |  | 2020-07-08 | Underground | R16 | 2020-05-20 | 1 |  | 76 | 36 | 111 | 2020 | 2020 | R16
161354277380 | 164424277380 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-04-27 | 2022-04-27 | 2022-04-27 |  | 2022-08-23 | Overhead | R16 | 2022-07-22 | 1 |  | 63 | 23 | 85 | 2022 | 2022 | R16
161100290596 | 160377290596 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-05-04 | 2022-05-27 | 2022-08-30 |  | 2023-03-01 | Underground | R16 |  | 18 | 68 |  |  | 216 | 2022 | 2023 | R16
164445267784 | 169240267784 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-01-04 | 2022-01-26 | 2022-02-07 |  | 2022-05-04 | Overhead | R16 | 2022-04-26 | 17 | 9 | 57 | 7 | 87 | 2022 | 2022 | R16
165261275117 | 167532275117 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-07 | 2022-04-06 | 2022-04-06 | 2022-05-16 | 2022-06-20 | Overhead | R16 | 2022-05-16 | 43 |  | 29 | 26 | 96 | 2022 | 2022 | R16
168264296344 | 169519296344 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-07-27 | 2022-09-17 | 2022-10-07 | 2022-10-25 | 2022-11-04 | Underground | R16 | 2022-10-25 | 38 | 15 | 13 | 9 | 73 | 2022 | 2022 | R16
165226282130 | 166009282130 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-23 | 2022-05-23 | 2022-06-09 | 2022-10-20 | 2022-11-14 | Underground | R16 | 2022-10-20 | 1 | 14 | 96 | 18 | 126 | 2022 | 2022 | R16
160656274693 | 162818274693 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-19 | 2022-01-24 | 2022-04-01 | 2022-07-08 | 2022-07-11 | Underground | R16 | 2022-07-08 | 4 | 50 | 71 | 2 | 124 | 2022 | 2022 | R16
165519259223 | 167406259223 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-22 | 2021-10-20 | 2021-11-30 | 2022-01-19 | 2022-01-21 | Underground | R16 | 2022-01-19 | 21 | 30 | 37 | 3 | 88 | 2021 | 2022 | R16
167271182932 | 164445182932 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-05 | 2020-03-05 | 2020-03-05 |  | 2020-04-16 | Overhead | R16 |  | 1 |  |  |  | 31 | 2020 | 2020 | R16
162374270007 | 162790270007 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-19 | 2022-01-19 | 2022-02-22 | 2022-04-29 | 2022-05-02 | Underground | R16 | 2022-04-29 | 1 | 25 | 49 | 2 | 74 | 2022 | 2022 | R16
163042264483 | 169110264483 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-04 | 2022-01-12 | 2022-01-12 | 2022-03-01 | 2022-04-20 | Overhead | R16 | 2022-03-01 | 7 |  | 35 | 37 | 77 | 2022 | 2022 | R16
162061251163 | 160673251163 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-07 | 2021-10-07 | 2021-10-07 |  | 2023-01-05 | Underground | R16 | 2022-09-28 | 1 |  | 255 | 72 | 326 | 2021 | 2023 | R16
160686256978 | 166978256978 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-03 | 2021-11-17 | 2021-11-17 |  | 2022-01-20 | Overhead | R16 | 2021-12-21 | 11 |  | 25 | 23 | 57 | 2021 | 2022 | R16
166586292811 | 169282292811 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-07-26 | 2022-08-10 | 2022-09-07 | 2023-09-07 | 2023-09-07 | Underground | R16 | 2023-09-07 | 12 | 21 | 262 |  | 293 | 2022 | 2023 | R16
167376181707 | 161973181707 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-24 | 2020-02-24 | 2020-02-24 |  | 2020-06-24 | Overhead | R16 | 2020-04-21 | 1 |  | 42 | 47 | 88 | 2020 | 2020 | R16
165553276283 | 161113276283 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-08 | 2022-04-18 | 2022-04-18 |  | 2023-06-27 | Overhead | R16 | 2023-03-20 | 7 |  | 241 | 72 | 318 | 2022 | 2023 | R16
169188263831 | 160066263831 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2022-01-06 | 2022-01-06 | 2022-01-07 |  | 2022-06-03 | Underground | R16 |  | 1 | 2 |  |  | 107 | 2022 | 2022 | R16
160516259779 | 163630259779 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-03 | 2021-12-03 | 2021-12-03 | 2022-05-09 | 2022-06-08 | Overhead | R16 | 2022-05-09 | 1 |  | 112 | 23 | 134 | 2021 | 2022 | R16
160089260454 | 161656260454 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-12 | 2021-10-28 | 2021-12-09 | 2022-05-11 | 2022-06-08 | Underground | R16 | 2022-05-11 | 13 | 31 | 110 | 21 | 172 | 2021 | 2022 | R16
165343285547 | 166159285547 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-24 | 2022-05-24 | 2022-07-13 |  | 2023-02-17 | Underground | R16 | 2023-01-09 | 1 | 37 | 129 | 30 | 194 | 2022 | 2023 | R16
160488283869 | 161014283869 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-05 | 2022-05-05 | 2022-06-27 |  | 2022-09-30 | Underground | R16 | 2022-08-29 | 1 | 38 | 46 | 25 | 107 | 2022 | 2022 | R16
167578182214 | 162465182214 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-26 | 2020-02-26 | 2020-02-28 |  | 2020-06-09 | Overhead | R16 | 2020-04-06 | 1 | 3 | 27 | 47 | 75 | 2020 | 2020 | R16
162087269106 | 169308269106 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2022-02-15 | 2022-02-15 | 2022-02-15 |  | 2022-08-05 | Overhead | R16 | 2022-08-05 | 1 |  | 124 |  | 124 | 2022 | 2022 | R16
167585184573 | 169637184573 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-12 | 2020-02-12 | 2020-03-18 |  | 2020-07-07 | Underground | R16 | 2020-05-12 | 1 | 26 | 40 | 41 | 105 | 2020 | 2020 | R16
166837283919 | 163134283919 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-27 | 2022-06-27 | 2022-06-27 |  | 2022-08-19 | Overhead | R16 | 2022-08-12 | 1 |  | 35 | 6 | 40 | 2022 | 2022 | R16
166647277537 | 160203277537 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-04-05 | 2022-04-05 | 2022-04-29 |  | 2022-06-06 | Overhead | R16 |  | 1 | 19 |  |  | 45 | 2022 | 2022 | R16
163346280592 | 166121280592 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-24 | 2022-05-24 | 2022-05-24 |  | 2022-08-11 | Overhead | R16 | 2022-06-27 | 1 |  | 25 | 34 | 58 | 2022 | 2022 | R16
165993251644 | 161407251644 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-11 | 2021-10-11 | 2021-10-11 |  | 2022-04-08 | Overhead | R16 | 2022-04-06 | 1 |  | 128 | 3 | 130 | 2021 | 2022 | R16
164442280644 | 163272280644 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-11 | 2022-05-11 | 2022-05-25 |  | 2022-08-24 | Underground | R16 | 2022-08-18 | 1 | 11 | 62 | 5 | 76 | 2022 | 2022 | R16
168665303292 | 167721303292 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2022-07-19 | 2022-12-15 | 2022-12-16 | 2023-07-05 | 2023-07-19 | Underground | R16 | 2023-07-05 | 108 | 2 | 144 | 11 | 262 | 2022 | 2023 | R16
164878265517 | 166309265517 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-16 | 2021-12-16 | 2022-01-20 | 2022-03-08 | 2022-03-09 | Underground | R16 | 2022-03-08 | 1 | 26 | 34 | 2 | 60 | 2021 | 2022 | R16
161726273704 | 167872273704 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-23 | 2022-03-23 | 2022-03-23 | 2022-04-12 | 2022-05-13 | Overhead | R16 | 2022-04-12 | 1 |  | 15 | 24 | 38 | 2022 | 2022 | R16
162940267089 | 162429267089 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-01-18 | 2022-01-18 | 2022-02-01 |  | 2022-03-04 | Overhead | R16 |  | 1 | 11 |  |  | 34 | 2022 | 2022 | R16
160117285690 | 166480285690 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-13 | 2022-07-15 | 2022-07-15 |  | 2022-10-05 | Overhead | R16 | 2022-10-04 | 3 |  | 58 | 2 | 61 | 2022 | 2022 | R16
169298278890 | 162148278890 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2022-04-14 | 2022-05-11 | 2022-05-11 | 2022-06-02 | 2022-06-14 | Overhead | R16 | 2022-06-02 | 20 |  | 17 | 9 | 44 | 2022 | 2022 | R16
160272271769 | 163384271769 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-03 | 2022-03-07 | 2022-03-07 |  | 2022-06-30 | Overhead | R16 | 2022-06-02 | 3 |  | 64 | 21 | 86 | 2022 | 2022 | R16
164902263262 | 166842263262 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-20 | 2021-12-20 | 2022-01-03 | 2022-05-22 | 2022-05-12 | Underground | R16 | 2022-05-22 | 1 | 11 | 100 |  | 104 | 2021 | 2022 | R16
169285251866 | 167661251866 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-09-23 | 2021-09-24 | 2021-10-12 | 2021-10-15 | 2021-10-26 | Overhead | R16 | 2021-10-15 | 2 | 13 | 4 | 8 | 24 | 2021 | 2021 | R16
162815272865 | 167742272865 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-27 | 2021-12-27 | 2022-03-16 | 2022-07-19 | 2022-07-20 | Underground | R16 | 2022-07-19 | 1 | 58 | 90 | 2 | 148 | 2021 | 2022 | R16
160628288602 | 160875288602 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-04-07 | 2022-04-07 | 2022-08-10 |  | 2023-02-17 | Underground | R16 |  | 1 | 90 |  |  | 227 | 2022 | 2023 | R16
161607289822 | 168215289822 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2022-02-10 | 2022-02-11 | 2022-08-22 | 2023-05-03 | 2023-05-24 | Underground | R16 | 2023-05-03 | 2 | 137 | 183 | 16 | 335 | 2022 | 2023 | R16
164759272811 | 166225272811 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-16 | 2022-03-16 | 2022-03-16 | 2022-08-01 | 2022-09-01 | Overhead | R16 | 2022-08-01 | 1 |  | 99 | 24 | 122 | 2022 | 2022 | R16
169232311269 | 168469311269 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2021-09-28 | 2022-02-16 | 2023-03-02 |  | 2023-07-31 | Underground | R16 | 2023-03-31 | 102 | 272 | 22 | 87 | 480 | 2021 | 2023 | R16
169882286848 | 163928286848 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-30 |  | 2022-06-30 | 2022-09-30 | 2022-10-27 | Underground | R16 | 2022-09-30 |  |  | 67 | 20 | 86 | 2022 | 2022 | R16
169706269306 | 167545269306 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-23 | 2021-12-23 | 2022-02-16 | 2022-06-17 | 2022-06-22 | Underground | R16 | 2022-06-17 | 1 | 40 | 88 | 4 | 130 | 2021 | 2022 | R16
166340250420 | 168589250420 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-09-29 | 2021-10-01 | 2021-10-01 | 2022-05-06 | 2022-09-01 | Underground | R16 | 2022-05-06 | 3 |  | 156 | 85 | 242 | 2021 | 2022 | R16
167882180145 | 169256180145 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-11 | 2020-02-11 | 2020-02-11 |  | 2020-06-29 | Overhead | R16 | 2020-04-23 | 1 |  | 53 | 48 | 100 | 2020 | 2020 | R16
163421275905 | 168252275905 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-29 | 2021-12-29 |  | 2022-04-12 | 2022-07-28 | Underground | R16 | 2022-04-12 | 1 |  |  | 78 | 152 | 2021 | 2022 | R16
169093271148 | 162921271148 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-02 | 2022-03-02 | 2022-03-02 |  | 2022-09-11 | Overhead | R16 | 2022-08-10 | 1 |  | 116 | 23 | 138 | 2022 | 2022 | R16
169450264685 | 162360264685 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-28 | 2021-11-28 | 2022-01-13 | 2022-04-22 | 2022-04-25 | Underground | R16 | 2022-04-22 | 0 | 34 | 72 | 2 | 106 | 2021 | 2022 | R16
167916264701 | 167423264701 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-12-22 | 2021-12-27 | 2022-01-13 |  | 2022-06-22 | Underground | R16 |  | 4 | 14 |  |  | 131 | 2021 | 2022 | R16
168092284703 | 164592284703 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-06 | 2022-07-06 | 2022-07-06 |  | 2022-08-24 | Overhead | R16 | 2022-08-15 | 1 |  | 29 | 8 | 36 | 2022 | 2022 | R16
165028273983 | 165749273983 | STREET AND HIGHWAY RELOCATION | R16 ELECTRIC RELOCATION US | Commercial | 2022-03-15 | 2022-03-15 | 2022-03-28 | 2022-04-12 | 2022-05-10 | Underground | R16 | 2022-04-12 | 1 | 10 | 12 | 21 | 41 | 2022 | 2022 | R16
168032239280 | 161021239280 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-07-14 | 2021-07-14 | 2021-07-15 |  | 2022-01-07 | Underground | R16 |  | 1 | 2 |  |  | 128 | 2021 | 2022 | R16
166086279879 | 165117279879 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-19 | 2022-05-19 | 2022-05-19 | 2022-08-04 | 2022-09-14 | Overhead | R16 | 2022-08-04 | 1 |  | 56 | 30 | 85 | 2022 | 2022 | R16
167514267081 | 161012267081 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-11 | 2022-01-11 | 2022-02-01 | 2023-11-15 | 2023-12-07 | Underground | R16 | 2023-11-15 | 1 | 16 | 467 | 17 | 498 | 2022 | 2023 | R16
163027285301 | 167772285301 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-02-08 | 2022-06-17 | 2022-07-11 |  | 2023-03-16 | Underground | R16 |  | 94 | 17 |  |  | 288 | 2022 | 2023 | R16
168132228924 | 160274228924 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-01-27 | 2021-01-27 | 2021-04-30 |  | 2023-07-24 | Underground | R16 |  | 1 | 68 |  |  | 649 | 2021 | 2023 | R16
165392285466 | 166088285466 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-07-12 | 2022-07-12 | 2022-07-12 | 2022-08-18 | 2022-08-19 | Overhead | R16 | 2022-08-18 | 1 |  | 28 | 2 | 29 | 2022 | 2022 | R16
166264249968 | 168832249968 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-29 | 2021-09-29 | 2021-09-29 | 2021-11-18 | 2022-02-02 | Overhead | R16 | 2021-11-18 | 1 |  | 37 | 55 | 91 | 2021 | 2022 | R16
160798273004 | 166590273004 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-17 | 2022-03-17 | 2022-03-17 | 2022-04-20 | 2022-08-03 | Overhead | R16 | 2022-04-20 | 1 |  | 25 | 76 | 100 | 2022 | 2022 | R16
164154254675 | 166627254675 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-02 | 2021-11-02 | 2021-11-02 | 2022-08-04 | 2022-09-12 | Overhead | R16 | 2022-08-04 | 1 |  | 198 | 28 | 225 | 2021 | 2022 | R16
168192181846 | 162354181846 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-25 | 2020-02-25 | 2020-02-25 |  | 2020-06-09 | Overhead | R16 | 2020-03-24 | 1 |  | 21 | 56 | 76 | 2020 | 2020 | R16
160430271850 | 162003271850 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2022-02-25 | 2022-03-03 | 2022-03-07 |  | 2022-07-26 | Overhead | R16 |  | 5 | 3 |  |  | 108 | 2022 | 2022 | R16
168730276310 | 162613276310 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-04-18 | 2022-04-18 | 2022-04-18 | 2022-05-02 | 2022-06-02 | Overhead | R16 | 2022-05-02 | 1 |  | 11 | 24 | 34 | 2022 | 2022 | R16
168081276927 | 168807276927 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-03 | 2022-04-25 | 2022-04-25 |  | 2022-12-13 | Overhead | R16 | 2022-11-14 | 81 |  | 146 | 22 | 247 | 2022 | 2022 | R16
168292188246 | 162649188246 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-20 | 2020-04-20 | 2020-04-20 |  | 2020-08-28 | Overhead | R16 | 2020-07-07 | 1 |  | 57 | 39 | 95 | 2020 | 2020 | R16
166656278080 | 167370278080 | RESIDENTIAL - MOBILE HOME | OH R16 RES NON RES OS | Residential | 2022-02-07 | 2022-05-03 | 2022-05-03 | 2022-05-28 | 2022-05-31 | Overhead | R16 | 2022-05-28 | 62 |  | 19 | 2 | 82 | 2022 | 2022 | R16
168353181652 | 162068181652 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-24 | 2020-02-24 | 2020-02-24 |  | 2020-06-23 | Overhead | R16 | 2020-04-15 | 1 |  | 38 | 50 | 87 | 2020 | 2020 | R16
168357183206 | 169522183206 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-12 | 2020-02-12 | 2020-03-06 |  | 2020-06-23 | Underground | R16 | 2020-04-15 | 1 | 18 | 29 | 50 | 95 | 2020 | 2020 | R16
168106273408 | 160273273408 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-18 | 2022-02-18 | 2022-03-21 | 2022-09-13 | 2022-09-14 | Overhead | R16 | 2022-09-13 | 1 | 22 | 127 | 2 | 149 | 2022 | 2022 | R16
167646285429 | 165531285429 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-10 | 2022-07-13 | 2022-07-13 |  | 2022-08-19 | Overhead | R16 | 2022-08-04 | 3 |  | 17 | 12 | 30 | 2022 | 2022 | R16
164729278073 | 169482278073 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-03 | 2022-05-03 | 2022-05-03 | 2022-07-06 | 2022-08-18 | Underground | R16 | 2022-07-06 | 1 |  | 47 | 32 | 78 | 2022 | 2022 | R16
161821276577 | 163353276577 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-21 | 2022-04-21 | 2022-04-21 |  | 2022-06-12 | Overhead | R16 | 2022-05-23 | 1 |  | 23 | 15 | 37 | 2022 | 2022 | R16
166360275999 | 167021275999 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-03-21 | 2022-04-15 | 2022-04-15 | 2022-06-28 | 2022-08-10 | Overhead | R16 | 2022-06-28 | 20 |  | 53 | 32 | 103 | 2022 | 2022 | R16
166021267171 | 169282267171 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-01-04 | 2022-01-05 | 2022-02-02 | 2022-04-20 | 2022-04-21 | Underground | R16 | 2022-04-20 | 2 | 21 | 56 | 2 | 78 | 2022 | 2022 | R16
162563279960 | 164012279960 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-25 | 2022-01-25 | 2022-05-19 |  | 2023-08-15 | Underground | R16 | 2023-04-18 | 1 | 83 | 239 | 86 | 406 | 2022 | 2023 | R16
168411181746 | 169516181746 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-12 | 2020-02-12 | 2020-02-24 |  | 2020-06-24 | Overhead | R16 | 2020-04-22 | 1 | 9 | 43 | 46 | 96 | 2020 | 2020 | R16
168464216162 | 167332216162 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-11-25 | 2020-12-21 | 2021-01-05 |  | 2022-04-20 | Overhead | R16 |  | 19 | 12 |  |  | 366 | 2020 | 2022 | R16
168526255557 | 168223255557 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-09 | 2021-11-09 | 2021-11-09 | 2022-06-20 | 2022-06-20 | Overhead | R16 | 2022-06-20 | 1 |  | 160 |  | 160 | 2021 | 2022 | R16
169592261673 | 165562261673 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-14 | 2021-10-11 | 2021-12-16 | 2022-07-25 | 2022-08-18 | Underground | R16 | 2022-07-25 | 20 | 49 | 158 | 19 | 243 | 2021 | 2022 | R16
166334259178 | 169453259178 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-12 | 2021-12-01 | 2021-12-01 | 2022-03-04 | 2022-07-30 | Overhead | R16 | 2022-03-04 | 14 |  | 68 | 106 | 186 | 2021 | 2022 | R16
168487192586 | 160348192586 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-04-07 | 2020-04-07 | 2020-05-29 |  | 2021-06-02 | Underground | R16 |  | 1 | 39 |  |  | 302 | 2020 | 2021 | R16
160388267099 | 166110267099 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-01 | 2022-02-01 | 2022-02-01 | 2022-05-02 | 2022-06-02 | Overhead | R16 | 2022-05-02 | 1 |  | 65 | 24 | 88 | 2022 | 2022 | R16
168487187183 | 161227187183 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-04-10 | 2020-04-10 | 2020-04-10 |  | 2020-06-23 | Overhead | R16 |  | 1 |  |  |  | 53 | 2020 | 2020 | R16
162791251214 | 161145251214 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-08 | 2021-10-08 | 2021-10-08 | 2022-07-26 | 2022-09-20 | Overhead | R16 | 2022-07-26 | 1 |  | 208 | 41 | 248 | 2021 | 2022 | R16
168511195645 | 164986195645 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-29 | 2020-06-29 | 2020-06-29 |  | 2020-10-06 | Underground | R16 | 2020-09-02 | 1 |  | 48 | 25 | 72 | 2020 | 2020 | R16
160400251977 | 162404251977 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-14 | 2021-10-14 | 2021-10-14 | 2021-12-28 | 2021-12-28 | Overhead | R16 | 2021-12-28 | 1 |  | 54 |  | 54 | 2021 | 2021 | R16
162298270333 | 161290270333 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-02-23 | 2022-02-23 | 2022-02-23 | 2022-07-19 | 2022-08-08 | Overhead | R16 | 2022-07-19 | 1 |  | 105 | 15 | 119 | 2022 | 2022 | R16
162153268076 | 167932268076 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-03-11 | 2022-05-03 | Overhead | R16 | 2022-03-11 | 1 |  | 23 | 38 | 60 | 2022 | 2022 | R16
163870269382 | 169691269382 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-16 | 2022-02-16 | 2022-02-16 |  | 2022-04-01 | Overhead | R16 | 2022-03-24 | 1 |  | 27 | 7 | 33 | 2022 | 2022 | R16
169448271902 | 163346271902 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-03 | 2022-03-03 | 2022-03-08 | 2022-04-19 | 2022-04-20 | Underground | R16 | 2022-04-19 | 1 | 4 | 31 | 2 | 35 | 2022 | 2022 | R16
168305268322 | 160762268322 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-10 | 2022-01-25 | 2022-02-09 | 2022-07-06 | 2022-08-18 | Overhead | R16 | 2022-07-06 | 12 | 12 | 106 | 32 | 159 | 2022 | 2022 | R16
160491262427 | 163013262427 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-01 | 2021-12-08 | 2021-12-23 | 2022-02-23 | 2022-02-25 | Underground | R16 | 2022-02-23 | 6 | 12 | 45 | 3 | 63 | 2021 | 2022 | R16
165475280402 | 168078280402 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-25 | 2022-03-25 | 2022-05-23 | 2022-07-08 | 2022-08-04 | Underground | R16 | 2022-07-08 | 1 | 42 | 35 | 20 | 95 | 2022 | 2022 | R16
167419266994 | 165955266994 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-01 | 2022-02-01 | 2022-02-01 | 2022-05-22 | 2022-06-20 | Overhead | R16 | 2022-05-22 | 1 |  | 79 | 21 | 100 | 2022 | 2022 | R16
162921259010 | 162473259010 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-29 | 2021-11-29 | 2021-11-29 | 2022-03-25 | 2022-05-19 | Overhead | R16 | 2022-03-25 | 1 |  | 85 | 40 | 124 | 2021 | 2022 | R16
167469279850 | 161873279850 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2021-10-12 | 2021-10-12 | 2022-05-19 | 2022-10-02 | 2022-10-05 | Underground | R16 | 2022-10-02 | 1 | 158 | 97 | 3 | 257 | 2021 | 2022 | R16
168848257025 | 160080257025 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-16 | 2021-11-17 | 2021-11-17 | 2022-01-10 | 2022-03-11 | Overhead | R16 | 2022-01-10 | 2 |  | 39 | 45 | 84 | 2021 | 2022 | R16
168877183673 | 169521183673 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-12 | 2020-02-12 | 2020-03-11 |  | 2020-06-23 | Underground | R16 | 2020-04-15 | 1 | 21 | 26 | 50 | 95 | 2020 | 2020 | R16
163491254913 | 166927254913 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-03 | 2021-11-03 | 2021-11-03 | 2021-12-31 | 2022-01-03 | Overhead | R16 | 2021-12-31 | 1 |  | 43 | 2 | 44 | 2021 | 2022 | R16
163444281302 | 167323281302 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-31 | 2022-06-01 | 2022-06-01 |  | 2022-09-29 | Underground | R16 | 2022-09-22 | 2 |  | 82 | 6 | 88 | 2022 | 2022 | R16
161432265463 | 161492265463 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-13 | 2022-01-20 | 2022-01-20 | 2022-04-22 | 2022-04-25 | Overhead | R16 | 2022-04-22 | 6 |  | 67 | 2 | 73 | 2022 | 2022 | R16
164702251207 | 168991251207 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-29 | 2021-10-08 | 2021-10-08 |  | 2022-01-11 | Overhead | R16 | 2021-12-03 | 8 |  | 41 | 28 | 75 | 2021 | 2022 | R16
165995248412 | 166463248412 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-17 | 2021-09-17 | 2021-09-17 |  | 2021-12-02 | Underground | R16 | 2021-11-02 | 1 |  | 33 | 23 | 55 | 2021 | 2021 | R16
162409278938 | 168829278938 | RESIDENTIAL - SINGLE FAMILY DETACHED | ELEC OH MISC SVC OS | Residential | 2022-03-30 |  | 2022-05-11 | 2022-06-12 | 2022-06-15 | Overhead | R16 | 2022-06-12 |  |  | 23 | 3 | 56 | 2022 | 2022 | R16
162499277669 | 166217277669 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-29 | 2022-04-29 | 2022-04-29 |  | 2022-10-10 | Overhead | R16 | 2022-10-06 | 1 |  | 115 | 3 | 117 | 2022 | 2022 | R16
169022235171 | 162172235171 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2021-06-04 | 2021-06-04 | 2021-06-16 |  | 2023-08-21 | Underground | R16 |  | 1 | 9 |  |  | 577 | 2021 | 2023 | R16
162092262634 | 168041262634 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-28 | 2021-12-28 | 2021-12-28 | 2022-02-11 | 2022-05-03 | Overhead | R16 | 2022-02-11 | 1 |  | 34 | 58 | 91 | 2021 | 2022 | R16
169024184994 | 165274184994 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2020-03-10 | 2020-03-20 | 2020-03-23 |  | 2021-04-15 | Overhead | R16 | 2020-12-23 | 9 | 2 | 198 | 82 | 288 | 2020 | 2021 | R16
167500278626 | 166148278626 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-03-16 | 2022-03-16 | 2022-05-09 | 2022-11-09 | 2022-11-21 | Underground | R16 | 2022-11-09 | 1 | 39 | 133 | 9 | 179 | 2022 | 2022 | R16
165004286229 | 165769286229 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-12 | 2022-07-18 | 2022-07-20 |  | 2022-09-11 | Overhead | R16 | 2022-08-04 | 5 | 3 | 12 | 27 | 44 | 2022 | 2022 | R16
162731258594 | 167208258594 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-04 | 2021-11-23 | 2021-11-23 |  | 2022-02-22 | Overhead | R16 | 2022-01-21 | 14 |  | 44 | 23 | 79 | 2021 | 2022 | R16
160727286772 | 168925286772 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-25 | 2022-07-25 | 2022-07-25 |  | 2023-04-27 | Overhead | R16 | 2023-01-27 | 1 |  | 135 | 65 | 199 | 2022 | 2023 | R16
169038307311 | 163162307311 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-03-03 | 2023-01-24 | 2023-01-27 |  | 2023-08-14 | Overhead | R16 | 2023-04-11 | 234 | 4 | 53 | 90 | 378 | 2022 | 2023 | R16
163149257086 | 165701257086 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-10-28 | 2021-10-28 | 2021-11-17 | 2022-06-09 | 2022-07-26 | Underground | R16 | 2022-06-09 | 1 | 15 | 147 | 34 | 194 | 2021 | 2022 | R16
168150276452 | 161103276452 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-01-11 | 2022-01-18 | 2022-04-20 | 2023-01-30 | 2023-02-02 | Underground | R16 | 2023-01-30 | 6 | 67 | 204 | 4 | 278 | 2022 | 2023 | R16
165034295078 | 163987295078 | INDUSTRIAL | R16 RESD AND NON RESD US | Commercial | 2021-12-06 | 2021-12-06 | 2022-09-27 | 2022-12-21 | 2023-02-22 | Underground | R16 | 2022-12-21 | 1 | 212 | 62 | 46 | 318 | 2021 | 2023 | R16
169199183578 | 165184183578 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-10 | 2020-03-10 | 2020-03-10 |  | 2020-06-09 | Overhead | R16 | 2020-04-09 | 1 |  | 23 | 44 | 66 | 2020 | 2020 | R16
169251186341 | 165443186341 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-10 | 2020-03-10 | 2020-04-03 |  | 2020-08-28 | Underground | R16 | 2020-06-30 | 1 | 19 | 63 | 44 | 124 | 2020 | 2020 | R16
166455273763 | 168037273763 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2023-02-28 | 2023-03-31 | Overhead | R16 | 2023-02-28 | 1 |  | 244 | 24 | 267 | 2022 | 2023 | R16
164379248851 | 167216248851 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2021-10-25 | 2021-11-18 | Overhead | R16 | 2021-10-25 | 1 |  | 24 | 19 | 42 | 2021 | 2021 | R16
162407284648 | 163706284648 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-06-29 | 2022-07-05 | 2022-07-05 | 2022-09-21 | 2023-01-05 | Overhead | R16 | 2022-09-21 | 5 |  | 57 | 77 | 137 | 2022 | 2023 | R16
160477262331 | 167417262331 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2022-02-10 | 2022-03-10 | Overhead | R16 | 2022-02-10 | 1 |  | 37 | 21 | 57 | 2021 | 2022 | R16
169359201142 | 160923201142 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-09 | 2020-04-09 | 2020-08-19 |  | 2020-12-29 | Underground | R16 | 2020-09-24 | 1 | 95 | 27 | 69 | 189 | 2020 | 2020 | R16
160576277356 | 164728277356 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-28 | 2022-04-28 | 2022-04-28 |  | 2022-07-25 | Overhead | R16 | 2022-06-07 | 1 |  | 29 | 35 | 63 | 2022 | 2022 | R16
163968249132 | 167728249132 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-23 | 2021-09-23 | 2021-09-23 | 2021-12-03 | 2022-04-14 | Overhead | R16 | 2021-12-03 | 1 |  | 52 | 95 | 146 | 2021 | 2022 | R16
167914274218 | 168244274218 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-25 | 2022-03-30 | 2022-03-30 |  | 2023-02-03 | Underground | R16 | 2022-12-01 | 4 |  | 177 | 47 | 226 | 2022 | 2023 | R16
162921250487 | 169697250487 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-04 | 2021-10-04 | 2021-10-04 | 2021-10-26 | 2021-12-01 | Overhead | R16 | 2021-10-26 | 1 |  | 17 | 27 | 43 | 2021 | 2021 | R16
163649275662 | 161409275662 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-04-12 | 2022-04-12 | 2022-04-12 |  | 2022-07-22 | Underground | R16 | 2022-07-18 | 1 |  | 70 | 5 | 74 | 2022 | 2022 | R16
165511277182 | 164066277182 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-26 | 2022-04-26 | 2022-04-26 | 2022-08-01 | 2022-08-02 | Overhead | R16 | 2022-08-01 | 1 |  | 70 | 2 | 71 | 2022 | 2022 | R16
167010285229 | 165700285229 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-11 | 2022-07-11 | 2022-07-11 | 2023-04-03 | 2023-07-28 | Overhead | R16 | 2023-04-03 | 1 |  | 191 | 85 | 275 | 2022 | 2023 | R16
160523253882 | 164726253882 | NON-RESIDENTIAL - SUBSEQUENT WORK | R16 ELEC DEVELOPMENT | Commercial | 2021-10-25 | 2021-10-25 | 2021-10-26 |  | 2022-05-05 | Underground | R16 |  | 1 | 2 |  |  | 139 | 2021 | 2022 | R16
160152301215 | 168445301215 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Commercial | 2022-07-21 | 2022-07-21 | 2022-11-23 | 2023-02-21 | 2023-04-18 | Underground | R16 | 2023-02-21 | 1 | 90 | 65 | 41 | 194 | 2022 | 2023 | R16
169532191499 | 167899191499 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2020-05-19 | 2020-05-19 | 2020-05-19 |  | 2020-10-06 | Overhead | R16 | 2020-08-17 | 1 |  | 65 | 37 | 101 | 2020 | 2020 | R16
160015254568 | 161892254568 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-12 | 2021-10-12 | 2021-11-01 | 2022-01-26 | 2022-01-27 | Underground | R16 | 2022-01-26 | 1 | 15 | 63 | 2 | 78 | 2021 | 2022 | R16
167686272100 | 162760272100 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-30 | 2021-11-30 | 2022-03-09 |  | 2022-08-03 | Underground | R16 | 2022-06-16 | 1 | 72 | 72 | 35 | 177 | 2021 | 2022 | R16
168567249811 | 165811249811 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-09-15 | 2021-09-16 | 2021-09-28 |  | 2021-11-13 | Overhead | R16 |  | 2 | 9 |  |  | 43 | 2021 | 2021 | R16
169556185280 | 167893185280 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-24 | 2020-03-24 | 2020-03-24 |  | 2022-10-20 | Overhead | R16 |  | 1 |  |  |  | 673 | 2020 | 2022 | R16
160835249091 | 167612249091 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-23 | 2021-09-23 | 2021-09-23 | 2022-02-07 | 2022-07-21 | Underground | R16 | 2022-02-07 | 1 |  | 98 | 119 | 216 | 2021 | 2022 | R16
164628292972 | 165117292972 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2021-10-27 | 2022-05-03 | 2022-09-08 |  | 2023-05-22 | Underground | R16 |  | 135 | 93 |  |  | 409 | 2021 | 2023 | R16
169610185260 | 167595185260 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-23 | 2020-03-24 | 2020-03-24 |  | 2020-10-06 | Overhead | R16 | 2020-07-16 | 2 |  | 83 | 59 | 142 | 2020 | 2020 | R16
162392281041 | 167033281041 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-27 | 2022-05-27 | 2022-05-27 |  | 2022-07-16 | Overhead | R16 | 2022-07-06 | 1 |  | 29 | 8 | 36 | 2022 | 2022 | R16
169618187292 | 162422187292 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-25 | 2020-02-25 | 2020-04-13 |  | 2020-08-27 | Underground | R16 | 2020-06-25 | 1 | 35 | 54 | 46 | 133 | 2020 | 2020 | R16
167655280580 | 164464280580 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-05-16 | 2022-05-24 | 2022-05-24 |  | 2022-08-18 | Overhead | R16 | 2022-07-13 | 7 |  | 37 | 27 | 69 | 2022 | 2022 | R16
169681182867 | 163691182867 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-02 | 2020-03-03 | 2020-03-03 |  | 2021-07-02 | Underground | R16 | 2020-10-23 | 2 |  | 169 | 181 | 350 | 2020 | 2021 | R16
169690184483 | 166725184483 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-18 | 2020-03-18 | 2020-03-18 |  | 2020-07-01 | Overhead | R16 | 2020-04-29 | 1 |  | 31 | 46 | 76 | 2020 | 2020 | R16
169443294926 | 167501294926 | NON-RESIDENTIAL - SUBSEQUENT WORK | R16 RESD AND NON RESD US | Commercial | 2022-03-22 | 2022-03-22 | 2022-09-26 |  | 2023-06-07 | Underground | R16 |  | 1 | 135 |  |  | 317 | 2022 | 2023 | R16
163767248628 | 166891248628 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-20 | 2021-09-20 | 2021-09-20 |  | 2021-11-30 | Overhead | R16 | 2021-11-03 | 1 |  | 33 | 20 | 52 | 2021 | 2021 | R16
161242249868 | 168354249868 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-28 | 2021-09-28 | 2021-09-28 | 2022-09-01 | 2022-03-08 | Overhead | R16 | 2022-09-01 | 1 |  | 243 |  | 116 | 2021 | 2022 | R16
165604262666 | 167251262666 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-21 | 2021-12-27 | 2021-12-27 | 2022-03-08 | 2022-03-09 | Overhead | R16 | 2022-03-08 | 5 |  | 52 | 2 | 57 | 2021 | 2022 | R16
169718189636 | 166683189636 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-17 | 2020-03-17 | 2020-05-01 |  | 2020-08-28 | Underground | R16 | 2020-07-01 | 1 | 34 | 44 | 43 | 119 | 2020 | 2020 | R16
163022285972 | 167354285972 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-31 | 2022-05-31 | 2022-07-18 |  | 2022-08-24 | Underground | R16 | 2022-08-22 | 1 | 35 | 26 | 3 | 62 | 2022 | 2022 | R16
165038278005 | 169130278005 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-03 |  | 2022-05-03 | 2022-06-28 | 2022-10-21 | Overhead | R16 | 2022-06-28 |  |  | 41 | 84 | 124 | 2022 | 2022 | R16
168820251502 | 161321251502 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-10 | 2021-10-10 | 2021-10-10 |  | 2022-02-17 | Overhead | R16 | 2022-01-19 | 0 |  | 73 | 22 | 94 | 2021 | 2022 | R16
168526263274 | 166135263274 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-16 | 2022-01-04 | 2022-01-04 |  | 2023-04-27 | Overhead | R16 | 2023-01-25 | 14 |  | 277 | 67 | 356 | 2021 | 2023 | R16
165962261660 | 163143261660 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-01 | 2021-12-16 | 2021-12-16 |  | 2022-04-01 | Overhead | R16 | 2022-03-08 | 12 |  | 59 | 19 | 88 | 2021 | 2022 | R16
168922285086 | 165253285086 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-08 | 2022-07-08 | 2022-07-08 |  | 2022-10-05 | Overhead | R16 | 2022-10-05 | 1 |  | 64 |  | 64 | 2022 | 2022 | R16
168622248801 | 166829248801 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-10-19 | 2021-12-02 | Overhead | R16 | 2021-10-19 | 1 |  | 21 | 33 | 53 | 2021 | 2021 | R16
160043266462 | 161320266462 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-01-12 | 2022-01-19 | 2022-01-27 |  | 2023-12-14 | Underground | R16 |  | 6 | 7 |  |  | 502 | 2022 | 2023 | R16
163206297615 | 166112297615 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-24 | 2022-10-19 | 2022-10-20 |  | 2023-05-30 | Overhead | R16 | 2023-02-09 | 107 | 2 | 81 | 79 | 266 | 2022 | 2023 | R16
161592265240 | 162307265240 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-01-18 | 2022-01-18 | 2022-01-18 |  | 2022-02-18 | Overhead | R16 | 2022-01-20 | 1 |  | 3 | 22 | 24 | 2022 | 2022 | R16
161053268445 | 167004268445 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-02-04 | 2022-02-10 | 2022-02-10 |  | 2022-04-22 | Overhead | R16 | 2022-03-25 | 5 |  | 32 | 21 | 56 | 2022 | 2022 | R16
167738281349 | 167739281349 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-02 | 2022-06-02 | 2022-06-02 | 2022-06-28 | 2023-09-12 | Overhead | R16 | 2022-06-28 | 1 |  | 19 | 316 | 334 | 2022 | 2023 | R16
161134284069 | 161367284069 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-06-20 | 2022-06-20 | 2022-06-29 | 2022-08-11 | 2022-08-15 | Underground | R16 | 2022-08-11 | 1 | 8 | 32 | 3 | 41 | 2022 | 2022 | R16
166342259099 | 162775259099 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-30 | 2021-11-30 | 2021-11-30 | 2022-03-17 | 2022-03-18 | Overhead | R16 | 2022-03-17 | 1 |  | 78 | 2 | 79 | 2021 | 2022 | R16
164408249230 | 167736249230 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-23 | 2021-09-23 | 2021-09-23 |  | 2021-11-10 | Overhead | R16 | 2021-10-14 | 1 |  | 16 | 20 | 35 | 2021 | 2021 | R16
166191275679 | 162017275679 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-14 | 2022-04-14 | 2022-04-14 |  | 2022-06-20 | Overhead | R16 | 2022-05-18 | 1 |  | 25 | 24 | 48 | 2022 | 2022 | R16
161021275671 | 161792275671 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-12 | 2022-04-12 | 2022-04-12 |  | 2022-05-31 | Overhead | R16 | 2022-05-02 | 1 |  | 15 | 22 | 36 | 2022 | 2022 | R16
166729279019 | 166775279019 | NON-RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Commercial | 2021-09-20 | 2021-09-20 | 2022-05-13 | 2022-06-14 | 2022-06-27 | Underground | R16 | 2022-06-14 | 1 | 170 | 23 | 10 | 201 | 2021 | 2022 | R16
161446278993 | 165780278993 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-04-29 | 2022-04-29 | 2022-05-11 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 1 | 9 | 172 |  | 180 | 2022 | 2023 | R16
164436285883 | 167170285883 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-16 | 2022-07-16 | 2022-07-16 | 2022-11-05 | 2022-11-06 | Overhead | R16 | 2022-11-05 | 0 |  | 80 | 0 | 80 | 2022 | 2022 | R16
161642254807 | 166866254807 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2021-11-03 | 2021-11-03 | 2021-11-03 | 2022-04-20 | 2022-05-03 | Overhead | R16 | 2022-04-20 | 1 |  | 121 | 10 | 130 | 2021 | 2022 | R16
169867188790 | 163196188790 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-04-23 | 2020-04-23 | 2020-04-23 |  | 2020-07-02 | Overhead | R16 | 2020-04-28 | 1 |  | 4 | 48 | 51 | 2020 | 2020 | R16
162783277845 | 165125277845 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-28 |  | 2022-05-02 | 2022-10-12 | 2022-11-18 | Overhead | R16 | 2022-10-12 |  |  | 118 | 28 | 147 | 2022 | 2022 | R16
160743272913 | 166522272913 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-17 | 2022-03-17 | 2022-03-17 | 2022-03-29 | 2022-06-01 | Overhead | R16 | 2022-03-29 | 1 |  | 9 | 47 | 55 | 2022 | 2022 | R16
169936191660 | 161754191660 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-21 | 2020-02-21 | 2020-05-19 |  | 2020-07-10 | Underground | R16 | 2020-06-10 | 1 | 63 | 17 | 23 | 101 | 2020 | 2020 | R16
164755264426 | 161213264426 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-12 | 2022-01-12 | 2022-01-12 | 2022-02-17 | 2022-03-15 | Overhead | R16 | 2022-02-17 | 1 |  | 27 | 19 | 45 | 2022 | 2022 | R16
169987273374 | 161952273374 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-12 | 2021-10-12 | 2022-03-21 |  | 2022-06-02 | Underground | R16 | 2022-05-06 | 1 | 115 | 35 | 20 | 168 | 2021 | 2022 | R16
162119261580 | 163345261580 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-12-02 | 2021-12-02 | 2021-12-16 | 2022-01-27 | 2022-03-08 | Underground | R16 | 2022-01-27 | 1 | 11 | 31 | 29 | 69 | 2021 | 2022 | R16
169901273412 | 167109273412 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-21 | 2022-03-21 | 2022-03-21 |  | 2022-10-05 | Overhead | R16 | 2022-10-05 | 1 |  | 143 |  | 143 | 2022 | 2022 | R16
164190296800 | 164590296800 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-05-17 | 2022-05-17 | 2022-10-12 | 2022-11-21 | 2022-11-22 | Underground | R16 | 2022-11-21 | 1 | 107 | 29 | 2 | 136 | 2022 | 2022 | R16
160506190444 | 166138190444 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-08 | 2020-05-08 | 2020-05-08 |  | 2021-07-19 | Overhead | R16 | 2020-11-19 | 1 |  | 140 | 173 | 312 | 2020 | 2021 | R16
161054274207 | 164579274207 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-03-08 | 2022-03-09 | 2022-03-29 | 2022-05-23 | 2022-05-26 | Underground | R16 | 2022-05-23 | 2 | 15 | 40 | 4 | 58 | 2022 | 2022 | R16
161110287781 | 164385287781 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-04-27 | 2022-05-09 | 2022-08-03 |  | 2022-10-21 | Overhead | R16 |  | 9 | 63 |  |  | 128 | 2022 | 2022 | R16
162730263244 | 168865263244 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-03 | 2022-01-03 | 2022-01-03 |  | 2022-03-01 | Overhead | R16 | 2022-01-26 | 1 |  | 18 | 25 | 42 | 2022 | 2022 | R16
163389290624 | 169280290624 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-26 | 2022-08-29 | 2022-08-29 | 2023-03-04 | 2023-03-07 | Overhead | R16 | 2023-03-04 | 25 |  | 135 | 2 | 161 | 2022 | 2023 | R16
168506264482 | 161112264482 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-11 | 2022-01-11 | 2022-01-11 | 2022-03-14 | 2022-04-05 | Overhead | R16 | 2022-03-14 | 1 |  | 45 | 17 | 61 | 2022 | 2022 | R16
160673200155 | 160663200155 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-08 | 2020-04-08 | 2020-08-11 |  | 2021-01-07 | Overhead | R16 | 2020-10-04 | 1 | 90 | 39 | 69 | 197 | 2020 | 2021 | R16
164416277178 | 168993277178 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-30 | 2022-04-08 | 2022-04-26 |  | 2022-06-30 | Underground | R16 | 2022-06-08 | 8 | 13 | 32 | 17 | 67 | 2022 | 2022 | R16
164483279757 | 163253279757 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-11 | 2022-05-11 | 2022-05-18 | 2022-06-29 | 2022-06-30 | Underground | R16 | 2022-06-29 | 1 | 6 | 31 | 2 | 37 | 2022 | 2022 | R16
167809257084 | 160261257084 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2022-01-10 | 2022-10-17 | Overhead | R16 | 2022-01-10 | 1 |  | 39 | 201 | 239 | 2021 | 2022 | R16
163070283514 | 162228283514 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-23 | 2022-06-23 | 2022-06-23 |  | 2022-12-11 | Underground | R16 | 2022-12-11 | 1 |  | 122 |  | 122 | 2022 | 2022 | R16
160979255128 | 167461255128 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-04 | 2021-11-04 | 2021-11-04 | 2022-05-11 | 2022-06-08 | Overhead | R16 | 2022-05-11 | 1 |  | 135 | 21 | 155 | 2021 | 2022 | R16
160796185542 | 167846185542 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-24 | 2020-03-24 | 2020-03-26 |  | 2020-07-01 | Overhead | R16 | 2020-04-28 | 1 | 3 | 24 | 47 | 72 | 2020 | 2020 | R16
167465268296 | 162480268296 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-14 | 2021-10-14 | 2022-02-09 | 2022-05-06 | 2022-06-30 | Underground | R16 | 2022-05-06 | 1 | 85 | 63 | 40 | 186 | 2021 | 2022 | R16
160000284154 | 163892284154 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2022-08-08 | 2022-08-09 | Overhead | R16 | 2022-08-08 | 1 |  | 28 | 2 | 29 | 2022 | 2022 | R16
166198274790 | 169996274790 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-04 | 2022-04-04 | 2022-04-04 |  | 2022-06-06 | Overhead | R16 | 2022-05-10 | 1 |  | 27 | 20 | 46 | 2022 | 2022 | R16
160245281283 | 161889281283 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-14 | 2022-01-14 | 2022-06-01 |  | 2022-08-03 | Overhead | R16 | 2022-06-22 | 1 | 99 | 16 | 31 | 144 | 2022 | 2022 | R16
160918185291 | 168178185291 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-03-25 | 2020-03-25 | 2020-03-25 |  | 2020-06-29 | Underground | R16 | 2020-04-24 | 1 |  | 23 | 47 | 69 | 2020 | 2020 | R16
166240300123 | 165313300123 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-08 | 2022-07-08 | 2022-11-09 | 2023-01-19 | 2023-01-23 | Underground | R16 | 2023-01-19 | 1 | 89 | 52 | 3 | 142 | 2022 | 2023 | R16
160016257707 | 162447257707 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-14 | 2021-10-14 | 2021-11-22 |  | 2022-03-03 | Underground | R16 | 2022-02-03 | 1 | 28 | 54 | 21 | 101 | 2021 | 2022 | R16
165505286788 | 165828286788 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-12 | 2022-07-12 | 2022-07-25 |  | 2022-12-04 | Underground | R16 | 2022-08-30 | 1 | 10 | 27 | 69 | 104 | 2022 | 2022 | R16
167755274912 | 163577274912 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-10-19 | 2021-10-19 | 2022-04-05 |  | 2022-05-03 | Overhead | R16 | 2022-04-08 | 1 | 121 | 4 | 18 | 141 | 2021 | 2022 | R16
166301276889 | 163622276889 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-22 | 2022-04-22 | 2022-04-22 | 2022-05-03 | 2022-08-03 | Overhead | R16 | 2022-05-03 | 1 |  | 8 | 67 | 74 | 2022 | 2022 | R16
168099282903 | 160992282903 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-16 | 2022-06-16 | 2022-06-16 |  | 2022-07-29 | Overhead | R16 | 2022-07-25 | 1 |  | 28 | 5 | 32 | 2022 | 2022 | R16
161078185028 | 161124185028 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-02-20 | 2020-02-20 | 2020-03-23 |  | 2023-08-23 | Underground | R16 | 2023-08-07 | 1 | 23 | 881 | 13 | 915 | 2020 | 2023 | R16
166578287874 | 167978287874 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2022-07-21 | 2022-07-21 | 2022-08-05 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 1 | 12 | 110 |  | 121 | 2022 | 2023 | R16
163417269104 | 169168269104 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2022-02-14 | 2022-02-14 | 2022-02-15 |  | 2022-10-21 | Underground | R16 |  | 1 | 2 |  |  | 180 | 2022 | 2022 | R16
161224184160 | 166362184160 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-16 | 2020-03-16 | 2020-03-16 |  | 2020-07-09 | Overhead | R16 | 2020-05-28 | 1 |  | 54 | 31 | 84 | 2020 | 2020 | R16
168682302391 | 168218302391 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-03-25 | 2022-03-28 | 2022-12-05 |  | 2023-10-04 | Underground | R16 |  | 2 | 181 |  |  | 399 | 2022 | 2023 | R16
161548283317 | 161846283317 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-21 | 2022-06-21 | 2022-06-21 | 2022-10-20 | 2023-01-05 | Underground | R16 | 2022-10-20 | 1 |  | 88 | 56 | 143 | 2022 | 2023 | R16
161294274371 | 169244274371 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-30 | 2022-03-30 | 2022-03-30 | 2022-04-26 | 2022-05-31 | Overhead | R16 | 2022-04-26 | 1 |  | 20 | 26 | 45 | 2022 | 2022 | R16
166909280302 | 161039280302 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-08 | 2022-05-16 | 2022-05-23 | 2022-07-06 | 2022-08-11 | Overhead | R16 | 2022-07-06 | 27 | 6 | 33 | 27 | 90 | 2022 | 2022 | R16
164822268475 | 167231268475 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-07 | 2022-02-11 | 2022-02-11 | 2022-04-04 | 2022-08-10 | Overhead | R16 | 2022-04-04 | 5 |  | 37 | 93 | 133 | 2022 | 2022 | R16
164443297025 | 162630297025 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-09 | 2022-05-09 | 2022-10-14 | 2023-02-06 | 2023-02-07 | Underground | R16 | 2023-02-06 | 1 | 115 | 82 | 2 | 197 | 2022 | 2023 | R16
164590271972 | 164783271972 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-09 | 2022-03-09 | 2022-03-09 | 2022-04-05 | 2022-04-26 | Overhead | R16 | 2022-04-05 | 1 |  | 20 | 16 | 35 | 2022 | 2022 | R16
169343255182 | 163123255182 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-18 | 2021-10-18 | 2021-11-04 |  | 2023-08-15 | Underground | R16 | 2023-03-15 | 1 | 14 | 355 | 110 | 477 | 2021 | 2023 | R16
162489269524 | 164665269524 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-27 | 2022-01-27 | 2022-02-17 | 2023-02-15 | 2023-11-17 | Overhead | R16 | 2023-02-15 | 1 | 16 | 260 | 198 | 472 | 2022 | 2023 | R16
161402212252 | 164724212252 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-06-26 | 2020-07-24 | 2020-12-01 |  | 2021-04-23 | Overhead | R16 | 2021-02-05 | 21 | 93 | 49 | 56 | 216 | 2020 | 2021 | R16
162411298840 | 161759298840 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2022-02-25 | 2022-06-10 | 2022-10-31 | 2023-06-20 | 2023-07-25 | Underground | R16 | 2023-06-20 | 76 | 102 | 167 | 26 | 368 | 2022 | 2023 | R16
161522185625 | 168586185625 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-03-27 | 2020-03-27 | 2020-03-27 |  | 2020-07-14 | Overhead | R16 | 2020-06-19 | 1 |  | 61 | 18 | 78 | 2020 | 2020 | R16
161145287219 | 167408287219 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Commercial | 2021-09-22 | 2021-09-22 | 2022-07-28 | 2023-06-26 | 2023-08-16 | Underground | R16 | 2023-06-26 | 1 | 222 | 238 | 38 | 496 | 2021 | 2023 | R16
164016285482 | 164411285482 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-05 | 2022-07-12 | 2022-07-12 | 2022-08-31 | 2022-10-26 | Overhead | R16 | 2022-08-31 | 6 |  | 37 | 41 | 82 | 2022 | 2022 | R16
161566190313 | 166062190313 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-07 | 2020-05-07 | 2020-05-07 |  | 2020-07-10 | Overhead | R16 | 2020-06-11 | 1 |  | 26 | 22 | 47 | 2020 | 2020 | R16
160607251157 | 169791251157 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-04 | 2021-10-04 | 2021-10-08 | 2022-01-02 | 2022-01-05 | Overhead | R16 | 2022-01-02 | 1 | 5 | 61 | 3 | 68 | 2021 | 2022 | R16
168077284409 | 161374284409 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-12 | 2022-06-29 | 2022-07-01 | 2023-03-16 | 2023-07-26 | Overhead | R16 | 2023-03-16 | 121 | 3 | 185 | 95 | 401 | 2022 | 2023 | R16
168888275168 | 160650275168 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-06 | 2022-04-06 | 2022-04-07 |  | 2022-06-01 | Overhead | R16 | 2022-05-02 | 1 | 2 | 18 | 23 | 41 | 2022 | 2022 | R16
161631191754 | 161593191754 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-21 | 2020-02-21 | 2020-05-21 |  | 2022-08-23 | Underground | R16 |  | 1 | 65 |  |  | 653 | 2020 | 2022 | R16
169780275667 | 160661275667 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-07 | 2022-04-07 | 2022-04-12 |  | 2022-07-17 | Underground | R16 | 2022-07-07 | 1 | 4 | 63 | 7 | 72 | 2022 | 2022 | R16
165726282760 | 160518282760 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-15 | 2022-06-15 | 2022-06-15 |  | 2022-12-04 | Overhead | R16 | 2022-10-17 | 1 |  | 89 | 35 | 123 | 2022 | 2022 | R16
167577283711 | 162442283711 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-23 | 2022-06-24 | 2022-06-24 | 2022-08-26 | 2022-10-20 | Overhead | R16 | 2022-08-26 | 2 |  | 46 | 40 | 86 | 2022 | 2022 | R16
168567249808 | 165810249808 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-09-15 | 2021-09-16 | 2021-09-28 |  | 2021-11-13 | Overhead | R16 |  | 2 | 9 |  |  | 43 | 2021 | 2021 | R16
161716182027 | 162712182027 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-26 | 2020-02-26 | 2020-02-26 |  | 2021-04-20 | Underground | R16 | 2021-01-11 | 1 |  | 229 | 72 | 300 | 2020 | 2021 | R16
164186257700 | 160961257700 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-21 | 2021-11-21 | 2021-11-21 |  | 2022-05-12 | Overhead | R16 | 2022-04-20 | 0 |  | 108 | 17 | 124 | 2021 | 2022 | R16
163087261780 | 166570261780 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-17 | 2021-12-17 | 2021-12-17 |  | 2022-03-03 | Underground | R16 | 2022-02-03 | 1 |  | 35 | 21 | 55 | 2021 | 2022 | R16
164879277850 | 168444277850 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-02 | 2022-05-02 | 2022-05-02 | 2022-12-11 | 2022-12-20 | Underground | R16 | 2022-12-11 | 1 |  | 160 | 7 | 167 | 2022 | 2022 | R16
161751198601 | 166477198601 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-16 | 2020-03-16 | 2020-07-27 |  | 2021-04-13 | Underground | R16 | 2020-12-07 | 1 | 96 | 96 | 92 | 282 | 2020 | 2021 | R16
164017278023 | 169150278023 | CUSTOMER UPGRADE IN SERVICE | UG SVC CONVERSION | Residential | 2022-03-30 | 2022-04-01 | 2022-05-03 |  | 2022-10-21 | Underground | R16 | 2022-08-29 | 3 | 23 | 85 | 40 | 148 | 2022 | 2022 | R16
161768184709 | 167120184709 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-19 | 2020-03-19 | 2020-03-19 |  | 2020-07-01 | Overhead | R16 | 2020-04-27 | 1 |  | 28 | 48 | 75 | 2020 | 2020 | R16
161313274902 | 160093274902 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-05 | 2022-04-05 | 2022-04-05 |  | 2022-07-03 | Overhead | R16 | 2022-06-21 | 1 |  | 56 | 9 | 64 | 2022 | 2022 | R16
160849265159 | 162988265159 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-12-01 | 2021-12-13 | 2022-01-19 | 2022-03-29 | 2022-03-29 | Underground | R16 | 2022-03-29 | 9 | 28 | 50 |  | 85 | 2021 | 2022 | R16
161949187541 | 162657187541 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-26 | 2020-02-26 | 2020-04-14 |  | 2020-08-28 | Underground | R16 | 2020-07-02 | 1 | 35 | 58 | 42 | 133 | 2020 | 2020 | R16
164350253782 | 165710253782 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-15 | 2021-09-15 | 2021-10-25 |  | 2022-03-23 | Underground | R16 | 2022-03-01 | 1 | 29 | 92 | 17 | 136 | 2021 | 2022 | R16
162190266451 | 165066266451 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-28 | 2022-01-28 | 2022-01-28 |  | 2022-05-12 | Overhead | R16 | 2022-04-20 | 1 |  | 59 | 17 | 75 | 2022 | 2022 | R16
162016200614 | 168900200614 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-05-26 | 2020-05-26 | 2020-08-14 |  | 2021-04-14 | Underground | R16 | 2020-12-16 | 1 | 59 | 89 | 86 | 232 | 2020 | 2021 | R16
167864280614 | 165128280614 | CUSTOMER UPGRADE IN SERVICE | UG SVC CONVERSION | Residential | 2022-03-10 | 2022-03-10 | 2022-05-25 | 2022-07-14 | 2022-07-25 | Underground | R16 | 2022-07-14 | 1 | 55 | 37 | 8 | 98 | 2022 | 2022 | R16
168329273167 | 166798273167 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-18 | 2022-03-18 | 2022-03-18 | 2023-05-14 | 2023-05-17 | Overhead | R16 | 2023-05-14 | 1 |  | 301 | 3 | 304 | 2022 | 2023 | R16
167071259412 | 163102259412 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-01 | 2021-12-01 | 2021-12-01 |  | 2022-01-24 | Overhead | R16 | 2021-12-28 | 1 |  | 20 | 20 | 39 | 2021 | 2022 | R16
165083249899 | 168659249899 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-29 | 2021-09-29 | 2021-09-29 | 2022-02-10 | 2022-03-11 | Overhead | R16 | 2022-02-10 | 1 |  | 97 | 22 | 118 | 2021 | 2022 | R16
165451253507 | 162933253507 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2021-10-15 | 2021-10-15 | 2021-10-22 | 2022-04-19 | 2022-05-04 | Underground | R16 | 2022-04-19 | 1 | 6 | 128 | 12 | 144 | 2021 | 2022 | R16
167932268014 | 167374268014 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-07 | 2022-02-07 | 2022-02-08 | 2022-03-05 | 2022-03-08 | Overhead | R16 | 2022-03-05 | 1 | 2 | 19 | 2 | 22 | 2022 | 2022 | R16
164546270137 | 160658270137 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-22 | 2022-02-23 | 2022-02-23 | 2022-03-18 | 2022-04-26 | Overhead | R16 | 2022-03-18 | 2 |  | 18 | 28 | 46 | 2022 | 2022 | R16
160920277436 | 162736277436 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-18 | 2022-04-18 | 2022-04-28 | 2022-05-16 | 2022-06-30 | Underground | R16 | 2022-05-16 | 1 | 9 | 13 | 34 | 54 | 2022 | 2022 | R16
162167219123 | 169333219123 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-01-25 | 2021-01-25 | 2021-01-29 |  | 2022-09-15 | Underground | R16 |  | 1 | 5 |  |  | 429 | 2021 | 2022 | R16
160917296682 | 162418296682 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-06-23 | 2022-06-23 | 2022-10-11 |  | 2023-11-02 | Underground | R16 |  | 1 | 79 |  |  | 356 | 2022 | 2023 | R16
163766254470 | 167591254470 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-23 | 2021-09-23 | 2021-11-01 | 2021-11-17 | 2022-01-24 | Underground | R16 | 2021-11-17 | 1 | 28 | 13 | 49 | 88 | 2021 | 2022 | R16
163354281043 | 167121281043 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-05-27 | 2022-05-27 | 2022-05-27 |  | 2022-10-21 | Underground | R16 | 2022-08-02 | 1 |  | 48 | 59 | 106 | 2022 | 2022 | R16
167373250611 | 169958250611 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-05 | 2021-10-05 | 2021-10-05 | 2021-10-26 | 2021-12-17 | Overhead | R16 | 2021-10-26 | 1 |  | 16 | 39 | 54 | 2021 | 2021 | R16
164874262621 | 166052262621 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-15 | 2021-12-15 | 2021-12-27 | 2022-02-28 | 2022-03-22 | Overhead | R16 | 2022-02-28 | 1 | 9 | 46 | 17 | 70 | 2021 | 2022 | R16
162361190169 | 165772190169 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-05-06 | 2020-05-06 | 2020-05-06 |  | 2020-11-02 | Overhead | R16 | 2020-09-04 | 1 |  | 88 | 42 | 129 | 2020 | 2020 | R16
168880283691 | 162839283691 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-24 | 2022-06-24 | 2022-06-24 |  | 2022-07-22 | Overhead | R16 | 2022-07-19 | 1 |  | 18 | 4 | 21 | 2022 | 2022 | R16
165797256109 | 162168256109 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-14 | 2021-10-14 | 2021-11-11 |  | 2022-02-07 | Underground | R16 | 2022-01-10 | 1 | 21 | 43 | 21 | 83 | 2021 | 2022 | R16
163624254174 | 163671254174 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-19 | 2021-10-28 | 2021-10-28 |  | 2022-02-01 | Overhead | R16 | 2021-12-13 | 8 |  | 33 | 37 | 76 | 2021 | 2022 | R16
163612278128 | 163952278128 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2022-04-25 | 2022-04-25 | 2022-05-04 |  | 2023-01-10 | Underground | R16 |  | 1 | 8 |  |  | 187 | 2022 | 2023 | R16
160043265934 | 161318265934 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-01-12 | 2022-01-18 | 2022-01-25 |  | 2023-01-05 | Underground | R16 |  | 5 | 6 |  |  | 257 | 2022 | 2023 | R16
165013272833 | 169400272833 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-15 | 2022-02-22 | 2022-03-16 |  | 2022-04-15 | Underground | R16 | 2022-04-04 | 6 | 17 | 14 | 10 | 44 | 2022 | 2022 | R16
162466184852 | 167228184852 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-20 | 2020-03-20 | 2020-03-20 |  | 2020-07-07 | Overhead | R16 | 2020-05-13 | 1 |  | 39 | 40 | 78 | 2020 | 2020 | R16
164028256003 | 168837256003 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-10 | 2021-11-10 | 2021-11-10 |  | 2022-04-26 | Underground | R16 | 2022-04-07 | 1 |  | 107 | 14 | 120 | 2021 | 2022 | R16
162592190769 | 166760190769 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-12 | 2020-05-12 | 2020-05-12 |  | 2020-07-09 | Overhead | R16 | 2020-06-01 | 1 |  | 15 | 29 | 43 | 2020 | 2020 | R16
160074248402 | 166266248402 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-09-17 | 2021-09-17 | 2021-09-17 | 2021-12-02 | 2021-12-02 | Overhead | R16 | 2021-12-02 | 1 |  | 55 |  | 55 | 2021 | 2021 | R16
162672274726 | 169390274726 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-03-31 | 2022-03-31 | 2022-04-04 |  | 2022-05-03 | Overhead | R16 |  | 1 | 3 |  |  | 24 | 2022 | 2022 | R16
165361253266 | 164227253266 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2021-11-17 | 2022-01-12 | Overhead | R16 | 2021-11-17 | 1 |  | 20 | 41 | 60 | 2021 | 2022 | R16
167919262168 | 169271262168 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-09-30 | 2021-09-30 | 2021-12-21 | 2023-07-26 | 2023-08-21 | Underground | R16 | 2023-07-26 | 1 | 59 | 417 | 19 | 493 | 2021 | 2023 | R16
162667184475 | 163154184475 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-28 | 2020-02-28 | 2020-03-18 |  | 2022-06-28 | Underground | R16 |  | 1 | 14 |  |  | 608 | 2020 | 2022 | R16
162672274723 | 169415274723 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-03-31 | 2022-03-31 | 2022-04-04 |  | 2022-05-03 | Overhead | R16 |  | 1 | 3 |  |  | 24 | 2022 | 2022 | R16
162896249249 | 167822249249 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-23 | 2021-09-23 | 2021-09-23 | 2021-10-14 | 2021-11-09 | Overhead | R16 | 2021-10-14 | 1 |  | 16 | 19 | 34 | 2021 | 2021 | R16
162677190678 | 160843190678 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-09 | 2020-05-12 | 2020-05-12 |  | 2020-08-14 | Overhead | R16 |  | 24 |  |  |  | 92 | 2020 | 2020 | R16
168909277521 | 161071277521 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-08 | 2022-04-28 | 2022-04-28 | 2022-06-02 | 2022-06-03 | Overhead | R16 | 2022-06-02 | 15 |  | 26 | 2 | 41 | 2022 | 2022 | R16
162684182821 | 163850182821 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-03 | 2020-03-03 | 2020-03-03 |  | 2021-04-14 | Underground | R16 | 2020-12-09 | 1 |  | 202 | 91 | 292 | 2020 | 2021 | R16
162723182575 | 163697182575 | GENERAL/OTHER | R16 RESD AND NON RESD US | Commercial | 2020-03-03 | 2020-03-03 | 2020-03-03 |  | 2020-06-09 | Underground | R16 | 2020-03-30 | 1 |  | 20 | 52 | 71 | 2020 | 2020 | R16
168438280184 | 163931280184 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-13 | 2022-05-20 | 2022-05-20 |  | 2022-07-03 | Overhead | R16 | 2022-06-27 | 6 |  | 27 | 5 | 36 | 2022 | 2022 | R16
161308252150 | 162507252150 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-14 | 2021-10-14 | 2021-10-14 | 2022-08-25 | 2022-08-26 | Overhead | R16 | 2022-08-25 | 1 |  | 226 | 2 | 227 | 2021 | 2022 | R16
162835186817 | 163457186817 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-02 | 2020-03-02 | 2020-04-09 |  | 2020-10-06 | Underground | R16 | 2020-08-17 | 1 | 29 | 93 | 37 | 157 | 2020 | 2020 | R16
169214254360 | 165571254360 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-14 | 2021-10-28 | 2021-10-28 | 2021-12-09 | 2022-01-24 | Overhead | R16 | 2021-12-09 | 33 |  | 31 | 33 | 95 | 2021 | 2022 | R16
162883235025 | 165585235025 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2020-03-11 | 2020-03-11 | 2021-06-14 |  | 2022-01-14 | Underground | R16 |  | 1 | 329 |  |  | 483 | 2020 | 2022 | R16
167769270293 | 161466270293 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-24 | 2022-02-24 | 2022-02-24 |  | 2022-05-03 | Overhead | R16 | 2022-04-11 | 1 |  | 33 | 17 | 49 | 2022 | 2022 | R16
162888188614 | 163092188614 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-21 | 2020-04-21 | 2020-04-21 |  | 2020-08-28 | Overhead | R16 | 2020-06-30 | 1 |  | 51 | 44 | 94 | 2020 | 2020 | R16
160236272059 | 164808272059 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2021-12-09 | 2021-12-10 | 2022-03-10 |  | 2022-05-19 | Overhead | R16 |  | 2 | 65 |  |  | 116 | 2021 | 2022 | R16
167969265762 | 161665265762 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-13 | 2022-01-13 | 2022-01-21 | 2022-09-20 | 2022-09-21 | Underground | R16 | 2022-09-20 | 1 | 7 | 173 | 2 | 180 | 2022 | 2022 | R16
165405250856 | 168452250856 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-09-27 | 2021-10-06 | 2021-10-06 |  | 2022-08-03 | Overhead | R16 | 2022-06-17 | 8 |  | 183 | 34 | 223 | 2021 | 2022 | R16
163667273742 | 164829273742 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-09 | 2022-03-09 | 2022-03-24 | 2022-03-29 | 2022-05-19 | Underground | R16 | 2022-03-29 | 1 | 12 | 4 | 38 | 52 | 2022 | 2022 | R16
160558279806 | 164967279806 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-18 | 2022-05-18 | 2022-05-18 | 2022-05-27 | 2022-07-08 | Underground | R16 | 2022-05-27 | 1 |  | 8 | 31 | 38 | 2022 | 2022 | R16
162976191223 | 167290191223 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-14 | 2020-05-14 | 2020-05-15 |  | 2020-11-24 | Overhead | R16 | 2020-07-22 | 1 | 2 | 49 | 90 | 139 | 2020 | 2020 | R16
169417272845 | 165957272845 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-03-16 | 2022-03-16 | 2022-03-16 | 2023-05-03 | 2023-05-09 | Overhead | R16 | 2023-05-03 | 1 |  | 296 | 5 | 300 | 2022 | 2023 | R16
162380251067 | 160103251067 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-10-05 | 2021-10-07 | 2021-10-07 |  | 2022-06-20 | Underground | R16 | 2022-05-25 | 3 |  | 165 | 19 | 185 | 2021 | 2022 | R16
163011185499 | 168703185499 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-27 | 2020-03-27 | 2020-03-27 |  | 2020-07-09 | Overhead | R16 | 2020-06-03 | 1 |  | 49 | 27 | 75 | 2020 | 2020 | R16
164825269495 | 167533269495 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-07 | 2022-02-17 | 2022-02-17 | 2022-10-04 | 2023-01-05 | Overhead | R16 | 2022-10-04 | 9 |  | 164 | 68 | 239 | 2022 | 2023 | R16
167382272257 | 165405272257 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-11 | 2022-03-11 | 2022-03-11 | 2022-03-27 | 2022-03-30 | Overhead | R16 | 2022-03-27 | 1 |  | 11 | 3 | 14 | 2022 | 2022 | R16
160495264110 | 160752264110 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-01-10 | 2022-01-10 | 2022-01-10 |  | 2023-03-13 | Overhead | R16 | 2022-02-18 | 1 |  | 30 | 277 | 306 | 2022 | 2023 | R16
168170249882 | 168601249882 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-09-28 | 2021-09-28 | 2021-09-28 |  | 2023-03-09 | Overhead | R16 | 2021-12-17 | 1 |  | 59 | 320 | 378 | 2021 | 2023 | R16
163093196594 | 160501196594 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-07 | 2020-04-07 | 2020-07-07 |  | 2020-11-24 | Overhead | R16 | 2020-07-22 | 1 | 66 | 12 | 90 | 166 | 2020 | 2020 | R16
161431262147 | 164349262147 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-22 | 2021-10-27 | 2021-12-21 | 2021-12-21 | 2021-12-22 | Overhead | R16 | 2021-12-21 | 4 | 40 |  | 2 | 44 | 2021 | 2021 | R16
163094191024 | 166934191024 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-13 | 2020-05-13 | 2020-05-13 |  | 2020-10-06 | Overhead | R16 | 2020-06-24 | 1 |  | 31 | 75 | 105 | 2020 | 2020 | R16
163095211106 | 164195211106 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-04 | 2020-03-04 | 2020-11-18 |  | 2021-05-05 | Underground | R16 | 2021-02-12 | 1 | 186 | 63 | 59 | 306 | 2020 | 2021 | R16
168571276944 | 160032276944 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-04 | 2022-04-04 | 2022-04-26 | 2022-10-05 | 2023-01-05 | Underground | R16 | 2022-10-05 | 1 | 17 | 117 | 67 | 199 | 2022 | 2023 | R16
164185282661 | 164196282661 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-04-26 | 2022-04-26 | 2022-06-14 | 2023-06-12 | 2023-06-20 | Underground | R16 | 2023-06-12 | 1 | 36 | 260 | 7 | 301 | 2022 | 2023 | R16
166250305118 | 164579305118 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Commercial | 2022-07-06 | 2022-07-06 | 2023-01-30 | 2023-01-06 | 2023-07-31 | Underground | R16 | 2023-01-06 | 1 | 149 |  | 147 | 279 | 2022 | 2023 | R16
163165195700 | 164819195700 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-29 | 2020-06-29 | 2020-06-29 |  | 2023-08-03 | Overhead | R16 | 2023-07-18 | 1 |  | 797 | 13 | 809 | 2020 | 2023 | R16
169722280931 | 166931280931 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-27 | 2022-05-27 | 2022-05-27 | 2023-08-04 | 2023-09-20 | Overhead | R16 | 2023-08-04 | 1 |  | 311 | 34 | 344 | 2022 | 2023 | R16
163928281465 | 166326281465 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-17 | 2022-03-17 | 2022-06-02 | 2023-01-05 | 2023-01-05 | Underground | R16 | 2023-01-05 | 1 | 56 | 156 |  | 211 | 2022 | 2023 | R16
161593271303 | 166274271303 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-02-02 | 2022-02-02 | 2022-03-03 |  | 2022-07-03 | Underground | R16 | 2022-06-20 | 1 | 22 | 78 | 10 | 108 | 2022 | 2022 | R16
167794263167 | 166185263167 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-11-01 | 2021-11-03 | 2022-01-03 |  | 2022-08-16 | Underground | R16 | 2022-07-11 | 3 | 44 | 136 | 27 | 207 | 2021 | 2022 | R16
166679265144 | 166022265144 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-16 | 2021-12-29 | 2022-01-18 |  | 2022-08-18 | Overhead | R16 | 2022-07-01 | 75 | 15 | 119 | 35 | 241 | 2021 | 2022 | R16
162586275961 | 162277275961 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-14 | 2022-04-14 | 2022-04-14 | 2022-05-04 | 2022-06-01 | Overhead | R16 | 2022-05-04 | 1 |  | 15 | 21 | 35 | 2022 | 2022 | R16
165482267404 | 169980267404 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-06 | 2022-01-06 | 2022-02-03 |  | 2022-04-19 | Underground | R16 | 2022-03-02 | 1 | 21 | 20 | 35 | 74 | 2022 | 2022 | R16
163022269494 | 166600269494 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-03 | 2022-02-17 | 2022-02-17 | 2022-03-22 | 2022-04-22 | Overhead | R16 | 2022-03-22 | 11 |  | 24 | 24 | 57 | 2022 | 2022 | R16
160761281193 | 164737281193 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-09 | 2022-03-09 | 2022-06-01 | 2022-06-23 | 2022-07-26 | Underground | R16 | 2022-06-23 | 1 | 61 | 17 | 24 | 100 | 2022 | 2022 | R16
164120284903 | 164725284903 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-06 | 2022-07-07 | 2022-07-07 |  | 2023-02-26 | Overhead | R16 | 2023-01-25 | 2 |  | 145 | 23 | 168 | 2022 | 2023 | R16
161454263172 | 164521263172 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-22 | 2021-10-22 | 2022-01-03 | 2022-08-10 | 2023-08-14 | Underground | R16 | 2022-08-10 | 1 | 52 | 158 | 264 | 472 | 2021 | 2023 | R16
163357183713 | 165836183713 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-12 | 2020-03-12 | 2020-03-12 |  | 2020-07-09 | Overhead | R16 | 2020-06-04 | 1 |  | 61 | 26 | 86 | 2020 | 2020 | R16
167516247835 | 165738247835 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-11-30 | 2022-01-13 | Underground | R16 | 2021-11-30 | 1 |  | 55 | 33 | 87 | 2021 | 2022 | R16
163400187233 | 161763187233 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-14 | 2020-04-14 | 2020-04-14 |  | 2020-09-16 | Overhead | R16 | 2020-07-08 | 1 |  | 62 | 51 | 112 | 2020 | 2020 | R16
163433183874 | 165918183874 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-12 | 2020-03-12 | 2020-03-12 |  | 2020-10-06 | Overhead | R16 | 2020-07-09 | 1 |  | 86 | 64 | 149 | 2020 | 2020 | R16
167507249242 | 167395249242 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-23 | 2021-09-23 | 2021-09-23 | 2021-09-29 | 2021-11-02 | Overhead | R16 | 2021-09-29 | 1 |  | 5 | 25 | 29 | 2021 | 2021 | R16
163469196734 | 167263196734 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-03-20 | 2020-03-20 | 2020-07-08 |  | 2021-01-22 | Underground | R16 | 2020-10-15 | 1 | 79 | 72 | 72 | 221 | 2020 | 2021 | R16
163612256047 | 168206256047 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2021-11-09 | 2021-11-09 | 2022-10-07 |  | 2022-08-11 | Underground | R16 |  | 1 | 239 |  |  | 198 | 2021 | 2022 | R16
163612256047 | 168206256047 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2021-11-09 | 2021-11-09 | 2022-10-07 |  | 2022-08-11 | Underground | R16 |  | 1 | 239 |  |  | 198 | 2021 | 2022 | R16
163504185829 | 163684185829 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-03 | 2020-03-03 | 2020-03-31 |  | 2020-07-08 | Underground | R16 | 2020-05-20 | 1 | 21 | 37 | 36 | 92 | 2020 | 2020 | R16
168816284079 | 163796284079 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-29 | 2022-06-29 | 2022-06-29 |  | 2022-09-29 | Overhead | R16 | 2022-09-22 | 1 |  | 62 | 6 | 67 | 2022 | 2022 | R16
161161282657 | 165000282657 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-18 | 2022-05-18 | 2022-06-16 |  | 2022-08-19 | Underground | R16 | 2022-08-17 | 1 | 22 | 45 | 3 | 68 | 2022 | 2022 | R16
161169281220 | 167217281220 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-31 | 2022-05-31 | 2022-05-31 |  | 2022-09-29 | Overhead | R16 | 2022-09-12 | 1 |  | 75 | 14 | 88 | 2022 | 2022 | R16
167844286155 | 167622286155 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-19 | 2022-07-19 | 2022-07-19 |  | 2023-03-01 | Underground | R16 | 2022-12-15 | 1 |  | 108 | 55 | 162 | 2022 | 2023 | R16
169188285127 | 165353285127 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-08 | 2022-07-08 | 2022-07-08 |  | 2022-09-11 | Overhead | R16 | 2022-09-07 | 1 |  | 44 | 3 | 46 | 2022 | 2022 | R16
163641184406 | 166710184406 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-17 | 2020-03-17 | 2020-03-17 |  | 2021-10-11 | Overhead | R16 | 2021-10-11 | 1 |  | 410 |  | 410 | 2020 | 2021 | R16
161753283415 | 169773283415 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-06-10 | 2022-06-10 | 2022-06-22 |  | 2023-07-23 | Overhead | R16 | 2023-03-08 | 1 | 9 | 186 | 98 | 291 | 2022 | 2023 | R16
160795271289 | 163345271289 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-03 | 2022-03-03 | 2022-03-03 | 2022-03-14 | 2022-04-21 | Overhead | R16 | 2022-03-14 | 1 |  | 8 | 29 | 36 | 2022 | 2022 | R16
163742184404 | 165342184404 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-10 | 2020-03-17 | 2020-03-17 |  | 2020-07-09 | Overhead | R16 | 2020-06-09 | 6 |  | 61 | 23 | 88 | 2020 | 2020 | R16
160612282874 | 160856282874 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-06-16 | 2022-06-16 | 2022-06-16 |  | 2022-08-10 | Underground | R16 | 2022-07-06 | 1 |  | 15 | 26 | 40 | 2022 | 2022 | R16
163776184518 | 166901184518 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-18 | 2020-03-18 | 2020-03-18 |  | 2020-07-07 | Overhead | R16 | 2020-05-13 | 1 |  | 41 | 40 | 80 | 2020 | 2020 | R16
164572264421 | 166942264421 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-20 | 2022-01-11 | 2022-01-11 | 2022-03-14 | 2022-05-03 | Overhead | R16 | 2022-03-14 | 17 |  | 45 | 37 | 97 | 2021 | 2022 | R16
166345275655 | 165757275655 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-01-31 | 2022-02-02 | 2022-04-12 |  | 2022-06-02 | Underground | R16 |  | 3 | 50 |  |  | 89 | 2022 | 2022 | R16
163501267084 | 165981267084 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-02-01 | 2022-02-01 | 2022-02-01 | 2022-09-01 | 2022-10-26 | Overhead | R16 | 2022-09-01 | 1 |  | 153 | 40 | 192 | 2022 | 2022 | R16
163829236504 | 169734236504 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-29 | 2020-08-31 | 2021-06-24 |  | 2021-09-10 | Overhead | R16 |  | 67 | 214 |  |  | 336 | 2020 | 2021 | R16
169252280048 | 160319280048 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-05 | 2022-04-05 | 2022-05-19 |  | 2023-10-04 | Underground | R16 | 2023-06-30 | 1 | 33 | 292 | 69 | 392 | 2022 | 2023 | R16
164714262763 | 168054262763 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-28 | 2021-12-28 | 2021-12-28 |  | 2023-08-01 | Overhead | R16 | 2023-06-16 | 1 |  | 384 | 33 | 416 | 2021 | 2023 | R16
168521256917 | 160233256917 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2022-02-02 | 2022-04-14 | Overhead | R16 | 2022-02-02 | 1 |  | 56 | 52 | 107 | 2021 | 2022 | R16
168388280838 | 168489280838 | NON-RESIDENTIAL - LARGE OFFICE | UG R16 RESD AND NON RESD UD | Commercial | 2021-11-09 | 2021-11-09 | 2022-05-27 | 2022-06-10 | 2022-06-30 | Underground | R16 | 2022-06-10 | 1 | 144 | 11 | 15 | 168 | 2021 | 2022 | R16
163849190385 | 162618190385 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-04-20 | 2020-04-20 | 2020-05-07 |  | 2023-11-08 | Underground | R16 |  | 1 | 14 |  |  | 928 | 2020 | 2023 | R16
163884214224 | 169366214224 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-08 | 2020-12-16 | 2020-12-16 |  | 2021-04-22 | Overhead | R16 | 2021-02-01 | 7 |  | 34 | 59 | 98 | 2020 | 2021 | R16
168155264486 | 161291264486 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-12 | 2022-01-12 | 2022-01-12 | 2022-03-15 | 2022-04-01 | Overhead | R16 | 2022-03-15 | 1 |  | 45 | 14 | 58 | 2022 | 2022 | R16
163991236364 | 166265236364 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-23 | 2021-06-23 | 2021-06-23 |  | 2022-03-31 | Underground | R16 | 2022-03-04 | 1 |  | 183 | 20 | 202 | 2021 | 2022 | R16
166162253634 | 164823253634 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2022-06-18 | 2022-06-20 | Underground | R16 | 2022-06-18 | 1 |  | 170 | 1 | 171 | 2021 | 2022 | R16
161260265079 | 162598265079 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2022-01-19 | 2022-01-19 | 2022-01-19 | 2022-01-25 | 2022-01-26 | Overhead | R16 | 2022-01-25 | 1 |  | 5 | 2 | 6 | 2022 | 2022 | R16
169636294891 | 161099294891 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-23 | 2022-06-06 | 2022-09-26 | 2023-02-07 | 2023-03-06 | Overhead | R16 | 2023-02-07 | 74 | 81 | 97 | 20 | 269 | 2022 | 2023 | R16
160160285167 | 163812285167 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-29 | 2022-06-29 | 2022-07-11 | 2022-09-21 | 2023-01-05 | Overhead | R16 | 2022-09-21 | 1 | 9 | 53 | 77 | 137 | 2022 | 2023 | R16
168466279591 | 164326279591 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-16 | 2022-05-16 | 2022-05-16 |  | 2022-08-03 | Overhead | R16 | 2022-06-22 | 1 |  | 28 | 31 | 58 | 2022 | 2022 | R16
164061185077 | 163932185077 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-04 | 2020-03-04 | 2020-03-24 |  | 2020-07-07 | Underground | R16 | 2020-05-11 | 1 | 15 | 35 | 42 | 90 | 2020 | 2020 | R16
167210277854 | 168249277854 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-05-02 | 2022-05-02 | 2022-05-02 | 2022-08-08 | 2022-08-10 | Underground | R16 | 2022-08-08 | 1 |  | 71 | 3 | 73 | 2022 | 2022 | R16
163316282286 | 165945282286 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-23 | 2022-05-23 | 2022-06-10 |  | 2022-07-17 | Underground | R16 | 2022-08-10 | 1 | 15 | 44 |  | 40 | 2022 | 2022 | R16
164207189148 | 164006189148 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-28 | 2020-04-28 | 2020-04-28 |  | 2020-07-10 | Overhead | R16 | 2020-06-11 | 1 |  | 33 | 22 | 54 | 2020 | 2020 | R16
162978254118 | 162857254118 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-15 | 2021-10-28 | 2021-10-28 |  | 2022-01-07 | Overhead | R16 | 2021-11-30 | 10 |  | 24 | 29 | 61 | 2021 | 2022 | R16
164209190208 | 164824190208 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-09 | 2020-03-09 | 2020-05-06 |  | 2020-10-06 | Underground | R16 | 2020-06-22 | 1 | 43 | 34 | 77 | 152 | 2020 | 2020 | R16
164404250347 | 167007250347 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-21 | 2021-09-21 | 2021-10-01 |  | 2021-11-30 | Underground | R16 | 2021-11-01 | 1 | 9 | 22 | 22 | 51 | 2021 | 2021 | R16
160816283040 | 161172283040 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-17 | 2022-06-17 | 2022-06-17 | 2022-07-27 | 2022-07-28 | Overhead | R16 | 2022-07-27 | 1 |  | 29 | 2 | 30 | 2022 | 2022 | R16
165019275640 | 166217275640 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-16 | 2022-04-11 | 2022-04-11 | 2023-05-04 | 2023-06-12 | Overhead | R16 | 2023-05-04 | 19 |  | 279 | 28 | 324 | 2022 | 2023 | R16
164225185078 | 165604185078 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-11 | 2020-03-11 | 2020-03-24 |  | 2020-07-09 | Underground | R16 | 2020-05-27 | 1 | 10 | 47 | 32 | 87 | 2020 | 2020 | R16
161102268277 | 161480268277 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-12 | 2022-01-12 | 2022-02-09 | 2022-08-28 | 2022-08-31 | Underground | R16 | 2022-08-28 | 1 | 21 | 143 | 3 | 166 | 2022 | 2022 | R16
164226185300 | 168070185300 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-24 | 2020-03-24 | 2020-03-24 |  | 2020-07-08 | Underground | R16 | 2020-04-20 | 1 |  | 20 | 58 | 77 | 2020 | 2020 | R16
164344275006 | 167653275006 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-23 | 2022-03-23 | 2022-04-06 |  | 2022-10-14 | Underground | R16 | 2022-10-13 | 1 | 11 | 137 | 2 | 148 | 2022 | 2022 | R16
164299210368 | 169892210368 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2020-04-02 | 2020-08-14 | 2020-11-11 |  | 2021-04-16 | Underground | R16 |  | 97 | 64 |  |  | 272 | 2020 | 2021 | R16
163610274121 | 164989274121 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-10 | 2022-03-28 | 2022-03-28 |  | 2022-06-08 | Underground | R16 | 2022-05-19 | 13 |  | 39 | 15 | 65 | 2022 | 2022 | R16
164343276830 | 161026276830 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2021-10-08 | 2022-04-11 | 2022-04-22 |  | 2023-01-10 | Underground | R16 |  | 132 | 10 |  |  | 328 | 2021 | 2023 | R16
164390279824 | 166951279824 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-12-20 | 2022-04-26 | 2022-05-18 | 2023-02-15 | 2023-03-04 | Overhead | R16 | 2023-02-15 | 92 | 17 | 196 | 13 | 315 | 2021 | 2023 | R16
163811290288 | 164464290288 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-05 | 2022-07-08 | 2022-08-24 | 2023-04-14 | 2023-08-30 | Underground | R16 | 2023-04-14 | 4 | 34 | 168 | 99 | 302 | 2022 | 2023 | R16
166591263069 | 167811263069 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-27 | 2021-12-30 | 2021-12-30 | 2022-03-22 | 2022-04-22 | Overhead | R16 | 2022-03-22 | 4 |  | 59 | 24 | 85 | 2021 | 2022 | R16
162118286399 | 166511286399 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-13 | 2022-07-13 | 2022-07-22 |  | 2023-11-20 | Overhead | R16 |  | 1 | 8 |  |  | 354 | 2022 | 2023 | R16
163749281264 | 167265281264 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-31 | 2022-05-31 | 2022-05-31 |  | 2022-10-14 | Underground | R16 | 2022-09-27 | 1 |  | 86 | 14 | 99 | 2022 | 2022 | R16
164406186710 | 167099186710 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-19 | 2020-04-07 | 2020-04-07 |  | 2022-09-28 | Overhead | R16 |  | 14 |  |  |  | 660 | 2020 | 2022 | R16
160845285710 | 167533285710 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-06-01 | 2022-06-01 | 2022-07-15 | 2023-05-31 | 2023-07-19 | Underground | R16 | 2023-05-31 | 1 | 33 | 229 | 36 | 296 | 2022 | 2023 | R16
164429188326 | 166834188326 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-18 | 2020-04-20 | 2020-04-20 |  | 2020-10-06 | Underground | R16 | 2020-08-13 | 24 |  | 84 | 39 | 145 | 2020 | 2020 | R16
164580256278 | 163596256278 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-19 | 2021-11-12 | 2021-11-12 | 2021-11-28 | 2022-04-05 | Overhead | R16 | 2021-11-28 | 19 |  | 11 | 92 | 121 | 2021 | 2022 | R16
164431185322 | 165634185322 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-11 | 2020-03-11 | 2020-03-25 |  | 2020-07-10 | Underground | R16 | 2020-06-10 | 1 | 11 | 56 | 23 | 88 | 2020 | 2020 | R16
166528281803 | 166305281803 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-05-25 | 2022-05-25 | 2022-06-06 | 2023-02-12 | 2023-02-15 | Overhead | R16 | 2023-02-12 | 1 | 9 | 180 | 3 | 191 | 2022 | 2023 | R16
164435188874 | 163186188874 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-22 | 2020-04-23 | 2020-04-23 |  | 2020-07-09 | Overhead | R16 | 2020-05-27 | 2 |  | 25 | 32 | 57 | 2020 | 2020 | R16
163722270145 | 166582270145 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-03 | 2022-02-15 | 2022-02-22 | 2022-04-27 | 2022-07-25 | Underground | R16 | 2022-04-27 | 9 | 6 | 47 | 64 | 123 | 2022 | 2022 | R16
164815262233 | 166810262233 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-19 | 2021-12-22 | 2021-12-22 | 2022-02-18 | 2022-03-15 | Overhead | R16 | 2022-02-18 | 3 |  | 43 | 18 | 62 | 2021 | 2022 | R16
160043266460 | 161319266460 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-01-12 | 2022-01-19 | 2022-01-27 |  | 2023-12-14 | Underground | R16 |  | 6 | 7 |  |  | 502 | 2022 | 2023 | R16
164456184641 | 166628184641 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-17 | 2020-03-17 | 2020-03-18 |  | 2020-07-01 | Overhead | R16 | 2020-04-27 | 1 | 2 | 29 | 48 | 77 | 2020 | 2020 | R16
162276274299 | 164828274299 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-09 | 2022-03-09 | 2022-03-31 |  | 2022-05-19 | Overhead | R16 | 2022-04-27 | 1 | 17 | 20 | 17 | 52 | 2022 | 2022 | R16
169803252203 | 161972252203 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-12 | 2021-10-12 | 2021-10-14 | 2021-12-17 | 2021-12-20 | Overhead | R16 | 2021-12-17 | 1 | 3 | 47 | 2 | 50 | 2021 | 2021 | R16
164489191583 | 161411191583 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-13 | 2020-04-13 | 2020-05-19 |  | 2021-07-01 | Underground | R16 | 2020-06-17 | 1 | 27 | 22 | 272 | 319 | 2020 | 2021 | R16
161652267208 | 166344267208 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-02 | 2022-02-02 | 2022-02-02 | 2022-04-27 | 2022-06-01 | Underground | R16 | 2022-04-27 | 1 |  | 61 | 26 | 86 | 2022 | 2022 | R16
169955270425 | 161663270425 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-24 | 2022-02-24 | 2022-02-24 |  | 2022-05-13 | Overhead | R16 | 2022-04-21 | 1 |  | 41 | 17 | 57 | 2022 | 2022 | R16
164524208850 | 165051208850 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-09 | 2020-03-09 | 2020-10-28 |  | 2021-06-02 | Underground | R16 | 2021-03-01 | 1 | 168 | 89 | 68 | 323 | 2020 | 2021 | R16
168811275505 | 160905275505 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-07 | 2022-04-07 | 2022-04-11 |  | 2022-09-30 | Underground | R16 | 2022-09-15 | 1 | 3 | 114 | 12 | 127 | 2022 | 2022 | R16
164569186551 | 165662186551 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-11 | 2020-03-11 | 2020-04-07 |  | 2020-10-06 | Underground | R16 | 2020-10-06 | 1 | 20 | 131 |  | 150 | 2020 | 2020 | R16
161947272474 | 164611272474 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-08 | 2022-03-15 | 2022-03-15 | 2022-05-04 | 2022-06-06 | Overhead | R16 | 2022-05-04 | 6 |  | 37 | 24 | 65 | 2022 | 2022 | R16
167480287218 | 169355287218 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-26 | 2022-07-27 | 2022-07-28 |  | 2022-12-09 | Overhead | R16 |  | 2 | 2 |  |  | 99 | 2022 | 2022 | R16
164085249643 | 168275249643 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-27 | 2021-09-27 | 2021-09-27 |  | 2021-12-08 | Overhead | R16 | 2021-11-10 | 1 |  | 33 | 21 | 53 | 2021 | 2021 | R16
168956288507 | 167092288507 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-03-21 | 2022-03-21 | 2022-08-10 | 2022-12-02 | 2022-12-05 | Underground | R16 | 2022-12-02 | 1 | 103 | 83 | 2 | 186 | 2022 | 2022 | R16
168893293813 | 166434293813 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-25 | 2022-05-25 | 2022-09-15 |  | 2023-03-02 | Overhead | R16 | 2022-12-20 | 1 | 82 | 69 | 53 | 202 | 2022 | 2023 | R16
168256274145 | 168594274145 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-28 | 2022-03-29 | 2022-03-29 | 2022-05-03 | 2022-05-03 | Overhead | R16 | 2022-05-03 | 2 |  | 26 |  | 27 | 2022 | 2022 | R16
169451266900 | 162372266900 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-28 | 2022-01-31 | 2022-01-31 |  | 2023-07-31 | Overhead | R16 | 2023-04-19 | 46 |  | 318 | 74 | 436 | 2021 | 2023 | R16
164656185382 | 165660185382 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-11 | 2020-03-11 | 2020-03-25 |  | 2020-06-24 | Underground | R16 | 2020-04-22 | 1 | 11 | 21 | 46 | 76 | 2020 | 2020 | R16
168369253908 | 160830253908 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-10-07 | 2021-10-19 | 2021-10-26 | 2021-12-17 | 2022-01-05 | Overhead | R16 | 2021-12-17 | 9 | 6 | 39 | 14 | 65 | 2021 | 2022 | R16
163216286942 | 162136286942 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2022-01-18 | 2022-05-09 | 2022-07-26 | 2022-08-04 | 2023-11-17 | Overhead | R16 | 2022-08-04 | 80 | 57 | 8 | 337 | 479 | 2022 | 2023 | R16
163143280117 | 165502280117 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-20 | 2022-05-20 | 2022-05-20 |  | 2022-08-11 | Overhead | R16 | 2022-06-27 | 1 |  | 27 | 34 | 60 | 2022 | 2022 | R16
164678184591 | 167214184591 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-19 | 2020-03-19 | 2020-03-19 |  | 2020-07-08 | Underground | R16 | 2020-04-17 | 1 |  | 22 | 59 | 80 | 2020 | 2020 | R16
162660259405 | 162533259405 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-29 | 2021-11-29 | 2021-12-01 | 2022-02-02 | 2022-03-09 | Overhead | R16 | 2022-02-02 | 1 | 3 | 46 | 26 | 73 | 2021 | 2022 | R16
168021272152 | 164992272152 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-10 | 2022-03-10 | 2022-03-10 | 2022-04-19 | 2022-05-18 | Overhead | R16 | 2022-04-19 | 1 |  | 29 | 22 | 50 | 2022 | 2022 | R16
164703222411 | 166213222411 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2021-01-12 | 2021-01-20 | 2021-03-04 |  | 2022-06-01 | Underground | R16 |  | 7 | 32 |  |  | 362 | 2021 | 2022 | R16
163925281183 | 167310281183 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-31 | 2022-05-31 | 2022-05-31 |  | 2022-09-09 | Overhead | R16 | 2022-09-08 | 1 |  | 73 | 2 | 74 | 2022 | 2022 | R16
169151252208 | 161428252208 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-11 | 2021-10-11 | 2021-10-14 | 2021-11-09 | 2021-11-10 | Underground | R16 | 2021-11-09 | 1 | 4 | 19 | 2 | 23 | 2021 | 2021 | R16
166292251235 | 168894251235 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-09-29 | 2021-10-07 | 2021-10-07 | 2022-01-24 | 2022-01-27 | Underground | R16 | 2022-01-24 | 7 |  | 78 | 4 | 87 | 2021 | 2022 | R16
163530268380 | 165274268380 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-29 | 2022-02-09 | 2022-02-09 |  | 2023-01-10 | Underground | R16 | 2022-11-08 | 8 |  | 195 | 46 | 247 | 2022 | 2023 | R16
168179268646 | 160603268646 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-10 | 2022-02-11 | 2022-02-11 |  | 2022-10-21 | Overhead | R16 | 2022-08-31 | 25 |  | 144 | 38 | 205 | 2022 | 2022 | R16
163450278773 | 162699278773 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-05-10 | 2022-05-10 | 2022-05-10 |  | 2022-10-18 | Underground | R16 |  | 1 |  |  |  | 116 | 2022 | 2022 | R16
165265269688 | 167664269688 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-08 | 2022-02-08 | 2022-02-18 | 2022-08-03 | 2022-10-21 | Underground | R16 | 2022-08-03 | 1 | 9 | 119 | 58 | 184 | 2022 | 2022 | R16
164766185033 | 165772185033 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-11 | 2020-03-11 | 2020-03-23 |  | 2020-07-02 | Underground | R16 | 2020-05-05 | 1 | 9 | 32 | 43 | 82 | 2020 | 2020 | R16
163158263927 | 164092263927 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-07 | 2022-01-07 | 2022-01-07 | 2022-03-02 | 2022-04-05 | Overhead | R16 | 2022-03-02 | 24 |  | 39 | 25 | 86 | 2021 | 2022 | R16
168245286018 | 167568286018 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-07-19 | 2022-07-19 | 2022-07-19 |  | 2022-10-21 | Overhead | R16 | 2022-09-07 | 1 |  | 37 | 33 | 69 | 2022 | 2022 | R16
165396254242 | 165269254242 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-27 | 2021-10-27 | 2021-10-28 |  | 2021-12-17 | Overhead | R16 | 2021-11-17 | 1 | 2 | 15 | 23 | 38 | 2021 | 2021 | R16
168880256587 | 168612256587 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-09 | 2021-11-15 | 2021-11-15 |  | 2023-03-09 | Overhead | R16 | 2022-02-17 | 5 |  | 69 | 276 | 348 | 2021 | 2023 | R16
164694307461 | 165988307461 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2021-12-15 | 2021-12-15 | 2023-01-27 | 2023-07-17 | 2023-06-28 | Underground | R16 | 2023-07-17 | 1 | 293 | 122 |  | 401 | 2021 | 2023 | R16
164926188865 | 163089188865 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-22 | 2020-04-23 | 2020-04-23 |  | 2020-10-06 | Underground | R16 | 2020-05-26 | 2 |  | 24 | 96 | 120 | 2020 | 2020 | R16
163742269664 | 165862269664 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-01 | 2022-02-04 | 2022-02-18 |  | 2022-05-04 | Underground | R16 | 2022-04-12 | 4 | 11 | 38 | 17 | 67 | 2022 | 2022 | R16
166585263749 | 160080263749 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-06 | 2022-01-06 | 2022-01-06 | 2022-09-29 | 2023-01-05 | Overhead | R16 | 2022-09-29 | 1 |  | 191 | 71 | 261 | 2022 | 2023 | R16
167462250595 | 160048250595 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-10-05 | 2021-10-05 | 2021-10-06 | 2021-10-18 | 2021-10-29 | Overhead | R16 | 2021-10-18 | 1 | 2 | 9 | 10 | 19 | 2021 | 2021 | R16
167462250595 | 160048250595 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2021-10-05 | 2021-10-05 | 2021-10-06 | 2021-10-18 | 2021-10-29 | Underground | R16 | 2021-10-18 | 1 | 2 | 9 | 10 | 19 | 2021 | 2021 | R16
165143186268 | 169629186268 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-04-02 | 2020-04-02 | 2020-04-02 |  | 2020-10-06 | Overhead | R16 | 2020-07-16 | 1 |  | 76 | 59 | 134 | 2020 | 2020 | R16
165143186099 | 169725186099 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-04-02 | 2020-04-02 | 2020-04-02 |  | 2020-06-23 | Overhead | R16 | 2020-04-14 | 1 |  | 9 | 51 | 59 | 2020 | 2020 | R16
162474275272 | 161042275272 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-08 | 2022-04-08 | 2022-04-08 |  | 2022-06-06 | Underground | R16 | 2022-05-10 | 1 |  | 23 | 20 | 42 | 2022 | 2022 | R16
164143280325 | 165823280325 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-23 | 2022-05-23 | 2022-05-23 | 2022-06-19 | 2022-06-22 | Overhead | R16 | 2022-06-19 | 1 |  | 20 | 3 | 23 | 2022 | 2022 | R16
161766290359 | 165983290359 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2022-02-01 | 2022-02-03 | 2022-08-26 |  | 2023-09-29 | Underground | R16 |  | 3 | 147 |  |  | 434 | 2022 | 2023 | R16
165350190873 | 166950190873 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-13 | 2020-05-13 | 2020-05-13 |  | 2020-07-09 | Overhead | R16 | 2020-05-28 | 1 |  | 12 | 31 | 42 | 2020 | 2020 | R16
168351272578 | 160005272578 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-17 | 2022-02-17 | 2022-03-15 |  | 2022-10-23 | Underground | R16 | 2022-10-06 | 1 | 19 | 148 | 12 | 177 | 2022 | 2022 | R16
165358191094 | 165512191094 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-10 | 2020-03-10 | 2020-05-15 |  | 2022-10-20 | Underground | R16 |  | 1 | 49 |  |  | 683 | 2020 | 2022 | R16
168882275169 | 160843275169 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-07 | 2022-04-07 | 2022-04-07 | 2022-05-13 | 2022-06-10 | Overhead | R16 | 2022-05-13 | 1 |  | 27 | 21 | 47 | 2022 | 2022 | R16
165425196766 | 166669196766 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-17 | 2020-03-17 | 2020-07-08 |  | 2020-11-24 | Underground | R16 | 2020-07-22 | 1 | 82 | 11 | 90 | 181 | 2020 | 2020 | R16
161593253083 | 163679253083 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-20 | 2021-10-20 | 2021-10-20 |  | 2022-01-07 | Overhead | R16 | 2021-11-29 | 1 |  | 29 | 30 | 58 | 2021 | 2022 | R16
167553319623 | 162877319623 | RESIDENTIAL - MOBILE HOME | R16 RESD AND NON RESD US | Residential | 2022-06-24 | 2022-06-24 | 2023-05-18 | 2023-10-13 | 2023-10-24 | Underground | R16 | 2023-10-13 | 1 | 235 | 107 | 8 | 348 | 2022 | 2023 | R16
165758287560 | 167590287560 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-01 | 2022-07-23 | 2022-08-01 |  | 2022-10-26 | Underground | R16 | 2022-09-22 | 38 | 6 | 39 | 25 | 106 | 2022 | 2022 | R16
169904275135 | 160596275135 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-06 | 2022-04-07 | 2022-04-07 |  | 2022-08-03 | Overhead | R16 | 2022-06-20 | 2 |  | 53 | 33 | 86 | 2022 | 2022 | R16
169025283388 | 161401283388 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-11 | 2022-04-11 | 2022-06-22 | 2022-08-03 | 2023-01-05 | Underground | R16 | 2022-08-03 | 1 | 53 | 31 | 112 | 194 | 2022 | 2023 | R16
165560284297 | 164123284297 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-01 | 2022-07-01 | 2022-07-01 |  | 2023-06-04 | Underground | R16 | 2023-02-01 | 1 |  | 154 | 88 | 241 | 2022 | 2023 | R16
165666188431 | 165738188431 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-03-11 | 2020-03-11 | 2020-04-21 |  | 2022-01-18 | Underground | R16 | 2021-12-22 | 1 | 30 | 437 | 20 | 485 | 2020 | 2022 | R16
165670206912 | 165879206912 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-05-07 | 2020-08-29 | 2020-10-12 |  | 2021-04-14 | Overhead | R16 |  | 82 | 31 |  |  | 245 | 2020 | 2021 | R16
165012276002 | 164462276002 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-08 | 2022-04-15 | 2022-04-15 | 2022-12-09 | 2023-01-12 | Overhead | R16 | 2022-12-09 | 29 |  | 171 | 25 | 223 | 2022 | 2023 | R16
169125249040 | 165834249040 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-15 | 2021-09-15 | 2021-09-22 |  | 2022-08-11 | Overhead | R16 | 2022-06-30 | 1 | 6 | 202 | 31 | 237 | 2021 | 2022 | R16
164918258990 | 162524258990 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-29 | 2021-11-29 | 2021-11-29 | 2021-12-14 | 2022-02-09 | Underground | R16 | 2021-12-14 | 1 |  | 12 | 42 | 53 | 2021 | 2022 | R16
165731287299 | 165746287299 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-03-11 | 2020-03-11 | 2022-07-29 |  | 2023-05-04 | Underground | R16 |  | 1 | 623 |  |  | 822 | 2020 | 2023 | R16
167012281500 | 167885281500 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-02 | 2022-06-02 | 2022-06-02 |  | 2022-12-04 | Overhead | R16 | 2022-10-18 | 1 |  | 99 | 34 | 132 | 2022 | 2022 | R16
160329265978 | 160556265978 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-10 | 2022-01-24 | 2022-01-24 | 2022-04-24 | 2022-04-27 | Overhead | R16 | 2022-04-24 | 11 |  | 65 | 3 | 78 | 2022 | 2022 | R16
161561268244 | 162372268244 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-18 | 2022-01-18 | 2022-02-09 |  | 2022-08-03 | Underground | R16 | 2022-06-16 | 1 | 17 | 92 | 35 | 142 | 2022 | 2022 | R16
169775286136 | 164055286136 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-01 | 2022-07-01 | 2022-07-20 |  | 2022-09-09 | Underground | R16 | 2022-09-08 | 1 | 14 | 37 | 2 | 51 | 2022 | 2022 | R16
165827188588 | 165871188588 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-03-12 | 2020-03-12 | 2020-04-21 |  | 2020-12-18 | Underground | R16 | 2020-09-18 | 1 | 29 | 109 | 66 | 202 | 2020 | 2020 | R16
161741256625 | 169772256625 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2021-11-15 | 2021-11-15 | 2021-11-15 |  | 2022-01-18 | Underground | R16 |  | 1 |  |  |  | 47 | 2021 | 2022 | R16
169355257208 | 169912257208 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-16 | 2021-11-18 | 2021-11-18 | 2022-03-07 | 2022-04-01 | Overhead | R16 | 2022-03-07 | 3 |  | 78 | 20 | 99 | 2021 | 2022 | R16
165845269800 | 160491269800 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-02-18 | 2022-02-18 | 2022-02-18 |  | 2023-07-31 | Underground | R16 |  | 1 |  |  |  | 377 | 2022 | 2023 | R16
169022276562 | 163115276562 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-20 | 2022-04-20 | 2022-04-20 | 2022-06-06 | 2022-08-02 | Overhead | R16 | 2022-06-06 | 1 |  | 34 | 42 | 75 | 2022 | 2022 | R16
167493250521 | 168278250521 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2021-09-27 | 2021-09-28 | 2021-10-04 |  | 2022-07-28 | Underground | R16 |  | 2 | 5 |  |  | 219 | 2021 | 2022 | R16
165894188707 | 165867188707 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-03-12 | 2020-03-12 | 2020-04-22 |  | 2021-07-24 | Underground | R16 | 2020-10-30 | 1 | 30 | 138 | 191 | 357 | 2020 | 2021 | R16
164377259512 | 163334259512 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-12-02 | 2021-12-02 | 2021-12-02 |  | 2022-02-18 | Overhead | R16 | 2022-01-19 | 1 |  | 35 | 23 | 57 | 2021 | 2022 | R16
167573295241 | 162227295241 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-14 | 2022-05-20 | 2022-09-28 |  | 2023-01-10 | Underground | R16 | 2022-11-08 | 27 | 94 | 30 | 46 | 194 | 2022 | 2023 | R16
160718272552 | 164523272552 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-26 | 2022-01-26 | 2022-03-14 | 2022-07-22 | 2022-07-25 | Underground | R16 | 2022-07-22 | 1 | 34 | 95 | 2 | 129 | 2022 | 2022 | R16
165984186574 | 160455186574 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-07 | 2020-04-07 | 2020-04-07 |  | 2020-07-07 | Overhead | R16 | 2020-05-12 | 1 |  | 26 | 41 | 66 | 2020 | 2020 | R16
161776270751 | 166048270751 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-02-02 | 2022-02-02 | 2022-02-28 |  | 2022-08-03 | Underground | R16 |  | 1 | 19 |  |  | 131 | 2022 | 2022 | R16
166021187675 | 162154187675 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-16 | 2020-04-16 | 2020-04-16 |  | 2021-07-01 | Overhead | R16 | 2020-06-16 | 1 |  | 44 | 273 | 316 | 2020 | 2021 | R16
166267253229 | 167952253229 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-24 | 2021-09-24 | 2021-10-21 |  | 2022-10-17 | Underground | R16 |  | 1 | 20 |  |  | 277 | 2021 | 2022 | R16
166092184998 | 166100184998 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-03-13 | 2020-03-13 | 2020-03-23 |  | 2022-10-03 | Underground | R16 | 2022-09-30 | 1 | 7 | 660 | 2 | 667 | 2020 | 2022 | R16
160432289746 | 166739289746 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-14 | 2022-07-14 | 2022-08-19 |  | 2022-12-15 | Underground | R16 | 2022-12-14 | 1 | 27 | 84 | 2 | 111 | 2022 | 2022 | R16
166110190264 | 162982190264 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-21 | 2020-04-21 | 2020-05-06 |  | 2020-10-06 | Underground | R16 | 2020-07-09 | 1 | 12 | 47 | 64 | 121 | 2020 | 2020 | R16
167119256308 | 169238256308 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2022-08-29 | 2023-06-08 | Overhead | R16 | 2022-08-29 | 1 |  | 207 | 204 | 410 | 2021 | 2023 | R16
162064255766 | 162874255766 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-15 | 2021-11-09 | 2021-11-09 | 2022-01-10 | 2022-02-02 | Overhead | R16 | 2022-01-10 | 18 |  | 45 | 18 | 79 | 2021 | 2022 | R16
166119189964 | 165315189964 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-04 | 2020-05-04 | 2020-05-04 |  | 2020-07-14 | Overhead | R16 | 2020-06-17 | 1 |  | 33 | 20 | 52 | 2020 | 2020 | R16
167987259171 | 162738259171 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-30 | 2021-11-30 | 2021-11-30 |  | 2022-02-07 | Overhead | R16 | 2022-01-14 | 1 |  | 34 | 17 | 50 | 2021 | 2022 | R16
166145188500 | 162924188500 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-21 | 2020-04-21 | 2020-04-21 |  | 2020-07-09 | Overhead | R16 | 2020-06-01 | 1 |  | 30 | 29 | 58 | 2020 | 2020 | R16
161192293545 | 160925293545 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-13 | 2022-09-13 | 2022-09-13 |  | 2022-10-10 | Underground | R16 | 2022-10-06 | 1 |  | 18 | 3 | 20 | 2022 | 2022 | R16
160741290651 | 162752290651 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-10 | 2022-08-10 | 2022-08-30 |  | 2022-12-07 | Underground | R16 | 2022-10-31 | 1 | 15 | 45 | 28 | 86 | 2022 | 2022 | R16
160551294451 | 162030294451 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-16 | 2022-09-19 | 2022-09-21 | 2022-12-27 | 2023-02-03 | Underground | R16 | 2022-12-27 | 2 | 3 | 70 | 29 | 101 | 2022 | 2023 | R16
169764290046 | 165511290046 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-23 | 2022-08-23 | 2022-08-23 |  | 2022-09-29 | Overhead | R16 | 2022-09-28 | 1 |  | 27 | 2 | 28 | 2022 | 2022 | R16
161961297122 | 167382297122 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-14 | 2022-10-14 | 2022-10-14 |  | 2023-01-08 | Overhead | R16 | 2022-12-22 | 1 |  | 50 | 12 | 61 | 2022 | 2023 | R16
169580330126 | 167929330126 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-20 | 2023-08-20 | 2023-08-20 | 2023-08-31 | 2023-10-23 | Overhead | R16 | 2023-08-31 | 0 |  | 9 | 38 | 46 | 2023 | 2023 | R16
160320290989 | 162259290989 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-08 | 2022-08-08 | 2022-09-01 |  | 2022-09-30 | Underground | R16 | 2022-09-26 | 1 | 19 | 18 | 5 | 40 | 2022 | 2022 | R16
162347330093 | 169285330093 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-21 | 2023-08-21 | 2023-08-21 | 2023-08-22 | 2023-09-18 | Overhead | R16 | 2023-08-22 | 1 |  | 2 | 20 | 21 | 2023 | 2023 | R16
164323298441 | 165622298441 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential Subdivision | 2022-10-05 | 2022-10-05 | 2022-10-26 | 2022-10-27 | 2022-11-14 | Overhead | R16 | 2022-10-27 | 1 | 16 | 2 | 13 | 29 | 2022 | 2022 | R16
166256295168 | 164030295168 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-27 | 2022-09-28 | 2022-09-28 | 2023-03-13 | 2023-11-07 | Overhead | R16 | 2023-03-13 | 2 |  | 119 | 172 | 291 | 2022 | 2023 | R16
165423328444 | 167064328444 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-15 | 2023-08-15 | 2023-08-15 | 2023-09-19 | 2023-12-11 | Overhead | R16 | 2023-09-19 | 1 |  | 26 | 60 | 85 | 2023 | 2023 | R16
168759331314 | 161059331314 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-08-30 | 2023-08-31 | 2023-08-31 | 2023-09-07 | 2023-09-20 | Overhead | R16 | 2023-09-07 | 2 |  | 6 | 10 | 16 | 2023 | 2023 | R16
166137302495 | 167396302495 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-31 | 2022-08-31 | 2022-12-07 |  | 2023-08-25 | Underground | R16 | 2023-07-20 | 1 | 71 | 162 | 27 | 258 | 2022 | 2023 | R16
165590297534 | 165478297534 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-05 | 2022-10-19 | 2022-10-19 | 2022-12-12 | 2022-12-13 | Overhead | R16 | 2022-12-12 | 11 |  | 39 | 2 | 50 | 2022 | 2022 | R16
167123298919 | 169133298919 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-24 | 2022-10-24 | 2022-11-01 |  | 2023-02-17 | Underground | R16 | 2022-12-21 | 1 | 7 | 37 | 43 | 85 | 2022 | 2023 | R16
163371296180 | 165627296180 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-05 | 2022-10-05 | 2022-10-05 | 2022-10-27 | 2023-02-11 | Overhead | R16 | 2022-10-27 | 1 |  | 17 | 77 | 93 | 2022 | 2023 | R16
167623333726 | 163648333726 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-09-14 | 2023-09-14 | 2023-09-26 | 2023-11-15 | 2023-11-28 | Underground | R16 | 2023-11-15 | 1 | 9 | 37 | 10 | 54 | 2023 | 2023 | R16
166441248446 | 165177248446 | CUSTOMER UPGRADE IN SERVICE | UG SVC CONVERSION | Residential | 2021-09-14 | 2021-09-16 | 2021-09-17 |  | 2021-12-28 | Underground | R16 | 2021-11-29 | 3 | 2 | 52 | 22 | 76 | 2021 | 2021 | R16
161396293342 | 164267293342 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-16 | 2022-08-17 | 2022-09-12 | 2022-11-07 | 2022-11-10 | Underground | R16 | 2022-11-07 | 2 | 19 | 41 | 4 | 63 | 2022 | 2022 | R16
166455185971 | 169469185971 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-01 | 2020-04-01 | 2020-04-01 |  | 2020-07-02 | Overhead | R16 | 2020-05-06 | 1 |  | 26 | 42 | 67 | 2020 | 2020 | R16
169608300925 | 163776300925 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-17 | 2022-11-17 | 2022-11-17 |  | 2023-07-28 | Overhead | R16 | 2023-02-27 | 1 |  | 73 | 110 | 182 | 2022 | 2023 | R16
166457187680 | 161957187680 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-15 | 2020-04-15 | 2020-04-15 |  | 2020-07-09 | Overhead | R16 | 2020-06-01 | 1 |  | 34 | 29 | 62 | 2020 | 2020 | R16
160084303135 | 165040303135 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-08-19 | 2022-08-19 | 2022-12-22 |  | 2023-07-31 | Underground | R16 |  | 1 | 90 |  |  | 247 | 2022 | 2023 | R16
162957301260 | 166937301260 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-12 | 2022-10-12 | 2022-11-21 |  | 2023-01-13 | Underground | R16 | 2023-01-11 | 1 | 29 | 38 | 3 | 68 | 2022 | 2023 | R16
162479297535 | 164622297535 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-17 | 2022-10-19 | 2022-10-19 | 2023-01-11 | 2023-01-11 | Overhead | R16 | 2023-01-11 | 46 |  | 61 |  | 106 | 2022 | 2023 | R16
166600186825 | 167749186825 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-23 | 2020-03-23 | 2020-04-08 |  | 2020-08-28 | Overhead | R16 | 2020-07-06 | 1 | 13 | 64 | 40 | 115 | 2020 | 2020 | R16
168604288757 | 161953288757 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-05 | 2022-08-05 | 2022-08-12 |  | 2022-12-06 | Underground | R16 | 2022-10-12 | 1 | 6 | 44 | 40 | 88 | 2022 | 2022 | R16
166392292763 | 169591292763 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-06 | 2022-09-06 | 2022-09-06 | 2023-07-19 | 2023-08-14 | Overhead | R16 | 2023-07-19 | 1 |  | 227 | 19 | 245 | 2022 | 2023 | R16
163212335545 | 168856335545 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-27 | 2023-11-09 | Underground | R16 | 2023-10-27 | 1 |  | 11 | 10 | 20 | 2023 | 2023 | R16
165989300525 | 163113300525 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-11-14 | 2022-11-14 | 2022-11-14 |  | 2023-02-03 | Overhead | R16 | 2022-11-23 | 1 |  | 8 | 53 | 60 | 2022 | 2023 | R16
166959296651 | 166342296651 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-10-10 | 2022-10-10 | 2022-10-10 |  | 2023-08-18 | Overhead | R16 | 2023-05-15 | 1 |  | 156 | 70 | 225 | 2022 | 2023 | R16
161810302631 | 163844302631 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-17 | 2022-11-17 | 2022-12-07 |  | 2023-02-08 | Underground | R16 |  | 1 | 15 |  |  | 60 | 2022 | 2023 | R16
167700293182 | 169533293182 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-09-06 | 2022-09-06 | 2022-09-09 | 2023-05-05 | 2023-08-16 | Underground | R16 | 2023-05-05 | 1 | 4 | 171 | 74 | 247 | 2022 | 2023 | R16
166486295971 | 165500295971 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-05 | 2022-10-05 | 2022-10-05 | 2023-02-28 | 2023-11-30 | Overhead | R16 | 2023-02-28 | 1 |  | 105 | 198 | 302 | 2022 | 2023 | R16
163419293191 | 167076293191 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-30 | 2022-08-30 | 2022-09-09 |  | 2022-12-15 | Underground | R16 | 2022-11-16 | 1 | 9 | 49 | 22 | 78 | 2022 | 2022 | R16
168673289331 | 164285289331 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-17 | 2022-08-17 | 2022-08-17 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 1 |  | 102 |  | 102 | 2022 | 2023 | R16
166976190878 | 166947190878 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-03-18 | 2020-03-18 | 2020-05-13 |  | 2021-07-24 | Underground | R16 | 2020-10-30 | 1 | 41 | 123 | 191 | 353 | 2020 | 2021 | R16
166977190879 | 166938190879 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-03-18 | 2020-03-18 | 2020-05-13 |  | 2021-04-20 | Underground | R16 | 2020-12-04 | 1 | 41 | 148 | 98 | 285 | 2020 | 2021 | R16
163216294487 | 166171294487 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-25 | 2022-09-01 | 2022-09-21 |  | 2023-08-22 | Underground | R16 | 2023-05-17 | 6 | 15 | 171 | 70 | 259 | 2022 | 2023 | R16
166978191342 | 167575191342 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-18 | 2020-05-18 | 2020-05-18 |  | 2021-07-01 | Overhead | R16 | 2020-06-17 | 1 |  | 23 | 272 | 294 | 2020 | 2021 | R16
165992291101 | 167863291101 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-01 | 2022-09-01 | 2022-09-01 | 2022-10-11 | 2022-10-12 | Overhead | R16 | 2022-10-11 | 1 |  | 29 | 2 | 30 | 2022 | 2022 | R16
163279302329 | 166428302329 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-06 | 2022-12-06 | 2022-12-06 |  | 2023-04-07 | Overhead | R16 | 2023-02-03 | 1 |  | 44 | 46 | 89 | 2022 | 2023 | R16
166389303505 | 166212303505 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OD | Commercial | 2022-12-05 | 2022-12-05 | 2022-12-19 |  | 2023-05-04 | Overhead | R16 |  | 1 | 11 |  |  | 109 | 2022 | 2023 | R16
167116186552 | 167126186552 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-20 | 2020-03-20 | 2020-04-07 |  | 2020-07-08 | Underground | R16 | 2020-05-18 | 1 | 13 | 30 | 38 | 79 | 2020 | 2020 | R16
167117184690 | 166989184690 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-03-19 | 2020-03-19 | 2020-03-19 |  | 2022-04-01 | Underground | R16 | 2022-03-04 | 1 |  | 512 | 21 | 532 | 2020 | 2022 | R16
163528297100 | 167363297100 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-14 | 2022-10-14 | 2022-10-14 | 2023-03-29 | 2023-03-30 | Overhead | R16 | 2023-03-29 | 1 |  | 119 | 2 | 120 | 2022 | 2023 | R16
167134188780 | 161087188780 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-10 | 2020-04-10 | 2020-04-22 |  | 2020-07-09 | Overhead | R16 | 2020-06-04 | 1 | 9 | 32 | 26 | 65 | 2020 | 2020 | R16
162262289998 | 165288289998 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-22 | 2022-08-23 | 2022-08-23 | 2022-10-05 | 2023-01-05 | Overhead | R16 | 2022-10-05 | 2 |  | 32 | 67 | 99 | 2022 | 2023 | R16
167826301021 | 163787301021 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-17 | 2022-11-17 | 2022-11-17 | 2023-09-15 | 2023-09-29 | Overhead | R16 | 2023-09-15 | 1 |  | 217 | 11 | 227 | 2022 | 2023 | R16
168076292369 | 167867292369 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-01 | 2022-09-02 | 2022-09-02 | 2022-10-14 | 2022-10-17 | Overhead | R16 | 2022-10-14 | 2 |  | 31 | 2 | 33 | 2022 | 2022 | R16
167288186343 | 160054186343 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-03 | 2020-04-03 | 2020-04-03 |  | 2020-10-06 | Overhead | R16 | 2020-07-20 | 1 |  | 77 | 57 | 133 | 2020 | 2020 | R16
167156294007 | 160004294007 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2022-09-07 | 2022-09-16 | 2022-09-16 | 2023-09-21 | 2023-09-22 | Overhead | R16 | 2023-09-21 | 8 |  | 265 | 2 | 273 | 2022 | 2023 | R16
167327191036 | 167786191036 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-24 | 2020-03-24 | 2020-05-14 |  | 2020-07-09 | Underground | R16 | 2020-06-09 | 1 | 38 | 19 | 23 | 78 | 2020 | 2020 | R16
161198327865 | 166131327865 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-10 | 2023-08-10 | 2023-08-10 | 2023-08-30 | 2023-09-07 | Overhead | R16 | 2023-08-30 | 1 |  | 15 | 7 | 21 | 2023 | 2023 | R16
163386290802 | 167189290802 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-30 | 2022-08-30 | 2022-08-30 |  | 2023-08-09 | Overhead | R16 | 2023-04-25 | 1 |  | 171 | 77 | 247 | 2022 | 2023 | R16
160440295699 | 163245295699 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-11 | 2022-08-11 | 2022-10-04 | 2023-01-30 | 2023-01-31 | Underground | R16 | 2023-01-30 | 1 | 39 | 85 | 2 | 124 | 2022 | 2023 | R16
164776295725 | 164889295725 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-10-03 | 2022-10-03 | 2022-10-03 |  | 2023-04-11 | Overhead | R16 | 2023-01-27 | 1 |  | 85 | 53 | 137 | 2022 | 2023 | R16
162678300478 | 163329300478 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-15 | 2022-11-15 | 2022-11-15 |  | 2023-04-07 | Underground | R16 | 2023-03-07 | 1 |  | 81 | 24 | 104 | 2022 | 2023 | R16
160657287805 | 161057287805 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-02 | 2022-08-02 | 2022-08-03 |  | 2022-09-11 | Underground | R16 | 2022-08-04 | 1 | 2 | 2 | 27 | 29 | 2022 | 2022 | R16
164111302200 | 162609302200 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-10 | 2022-11-29 | 2022-12-02 | 2023-01-09 | 2023-01-12 | Underground | R16 | 2023-01-09 | 14 | 4 | 27 | 4 | 46 | 2022 | 2023 | R16
165013308011 | 167921308011 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-18 | 2022-10-18 | 2023-02-01 |  | 2023-05-15 | Overhead | R16 | 2023-02-13 | 1 | 77 | 9 | 66 | 150 | 2022 | 2023 | R16
169122303133 | 166310303133 | CUSTOMER UPGRADE IN SERVICE | UG SVC CONVERSION | Residential | 2022-10-09 | 2022-10-09 | 2022-12-16 |  | 2023-04-10 | Underground | R16 | 2023-01-19 | 0 | 50 | 25 | 58 | 131 | 2022 | 2023 | R16
162793327701 | 164523327701 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-08-02 | 2023-08-08 | 2023-08-08 |  | 2023-09-13 | Overhead | R16 |  | 5 |  |  |  | 31 | 2023 | 2023 | R16
167186299034 | 168663299034 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-21 | 2022-10-21 | 2022-11-02 | 2023-02-07 | 2023-02-14 | Underground | R16 | 2023-02-07 | 1 | 9 | 70 | 6 | 83 | 2022 | 2023 | R16
169295299683 | 161663299683 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-07 | 2022-11-07 | 2022-11-07 |  | 2023-03-01 | Overhead | R16 | 2022-12-14 | 1 |  | 28 | 56 | 83 | 2022 | 2023 | R16
165365297065 | 167299297065 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-14 | 2022-10-14 | 2022-10-14 | 2023-01-11 | 2023-01-20 | Overhead | R16 | 2023-01-11 | 1 |  | 64 | 8 | 71 | 2022 | 2023 | R16
165900331679 | 161715331679 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-05 | 2023-09-05 | 2023-09-05 | 2023-10-24 | 2023-12-27 | Overhead | R16 | 2023-10-24 | 1 |  | 36 | 47 | 82 | 2023 | 2023 | R16
168052186193 | 169842186193 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-02 | 2020-04-03 | 2020-04-03 |  | 2020-07-08 | Overhead | R16 | 2020-04-17 | 2 |  | 11 | 59 | 70 | 2020 | 2020 | R16
168055200845 | 164145200845 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-04-28 | 2020-06-23 | 2020-08-18 |  | 2022-02-02 | Underground | R16 |  | 41 | 41 |  |  | 462 | 2020 | 2022 | R16
166907287928 | 160898287928 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-02 | 2022-08-04 | 2022-08-04 |  | 2022-12-04 | Overhead | R16 | 2022-10-10 | 3 |  | 48 | 40 | 89 | 2022 | 2022 | R16
168055200034 | 163958200034 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-06-23 | 2020-07-01 | 2020-08-10 |  | 2022-02-02 | Underground | R16 |  | 7 | 29 |  |  | 422 | 2020 | 2022 | R16
166119299457 | 161224299457 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2022-11-03 | 2022-11-03 | 2022-11-04 | 2023-11-16 | 2023-11-17 | Overhead | R16 | 2023-11-16 | 1 | 2 | 270 | 2 | 272 | 2022 | 2023 | R16
168095191550 | 167853191550 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-19 | 2020-05-19 | 2020-05-19 |  | 2020-10-06 | Overhead | R16 | 2020-07-13 | 1 |  | 40 | 62 | 101 | 2020 | 2020 | R16
168098189306 | 160781189306 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-08 | 2020-04-08 | 2020-04-29 |  | 2020-10-06 | Underground | R16 | 2020-07-30 | 1 | 16 | 67 | 49 | 130 | 2020 | 2020 | R16
161448325684 | 161942325684 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-19 | 2023-07-19 | 2023-07-19 | 2023-07-25 | 2023-07-27 | Overhead | R16 | 2023-07-25 | 1 |  | 5 | 3 | 7 | 2023 | 2023 | R16
169700288217 | 162310288217 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-08 | 2022-08-08 | 2022-08-08 | 2022-09-20 | 2022-09-21 | Overhead | R16 | 2022-09-20 | 1 |  | 32 | 2 | 33 | 2022 | 2022 | R16
169646298948 | 160494298948 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-31 | 2022-10-31 | 2022-11-01 |  | 2023-02-17 | Underground | R16 | 2022-12-15 | 1 | 2 | 33 | 47 | 80 | 2022 | 2023 | R16
161261296758 | 166779296758 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-10-12 | 2022-10-12 | 2022-10-12 |  | 2023-08-04 | Overhead | R16 | 2023-07-28 | 1 |  | 208 | 6 | 213 | 2022 | 2023 | R16
161397293701 | 160243293701 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-08 | 2022-09-14 | 2022-09-14 |  | 2023-01-13 | Overhead | R16 | 2023-01-11 | 5 |  | 86 | 3 | 92 | 2022 | 2023 | R16
169742302607 | 165408302607 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-29 | 2022-12-06 | 2022-12-07 | 2023-08-01 | 2023-08-30 | Underground | R16 | 2023-08-01 | 6 | 2 | 170 | 22 | 197 | 2022 | 2023 | R16
167793333759 | 164255333759 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-18 | 2023-09-18 | 2023-09-26 | 2023-10-12 | 2023-10-27 | Overhead | R16 | 2023-10-12 | 1 | 7 | 13 | 12 | 30 | 2023 | 2023 | R16
168398194633 | 167657194633 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-18 | 2020-05-18 | 2020-06-18 |  | 2020-10-06 | Underground | R16 | 2020-07-29 | 1 | 24 | 30 | 50 | 102 | 2020 | 2020 | R16
160846331311 | 161094331311 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-08-30 | 2023-08-30 | 2023-08-30 | 2023-10-09 | 2023-10-31 | Overhead | R16 | 2023-10-09 | 1 |  | 29 | 17 | 45 | 2023 | 2023 | R16
164343295466 | 160972295466 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-09-13 | 2022-09-13 | 2022-09-30 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 1 | 14 | 70 |  | 83 | 2022 | 2023 | R16
164878299401 | 161106299401 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-03 | 2022-11-03 | 2022-11-03 | 2023-02-01 | 2023-02-03 | Overhead | R16 | 2023-02-01 | 1 |  | 65 | 3 | 67 | 2022 | 2023 | R16
164757302522 | 161449302522 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-14 | 2022-09-14 | 2022-12-06 | 2023-03-22 | 2023-05-18 | Underground | R16 | 2023-03-22 | 1 | 60 | 77 | 42 | 177 | 2022 | 2023 | R16
168697331172 | 160910331172 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-30 | 2023-08-30 | 2023-08-30 | 2023-11-02 | 2023-11-08 | Overhead | R16 | 2023-11-02 | 1 |  | 47 | 5 | 51 | 2023 | 2023 | R16
168490186478 | 160583186478 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-08 | 2020-04-08 | 2020-04-08 |  | 2020-07-09 | Overhead | R16 | 2020-05-27 | 1 |  | 36 | 32 | 67 | 2020 | 2020 | R16
161964305850 | 164279305850 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-21 | 2022-11-21 | 2023-01-25 | 2023-02-28 | 2023-04-07 | Underground | R16 | 2023-02-28 | 1 | 48 | 25 | 29 | 100 | 2022 | 2023 | R16
161919290536 | 165090290536 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-08-19 | 2022-08-19 | 2022-08-29 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 1 | 7 | 94 |  | 100 | 2022 | 2023 | R16
163707301804 | 161552301804 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-15 | 2022-09-15 | 2022-11-29 |  | 2023-03-17 | Underground | R16 | 2023-01-06 | 1 | 54 | 29 | 51 | 132 | 2022 | 2023 | R16
163322295285 | 164195295285 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-28 | 2022-09-28 | 2022-09-28 | 2022-11-22 | 2022-11-30 | Overhead | R16 | 2022-11-22 | 1 |  | 40 | 7 | 46 | 2022 | 2022 | R16
167486302467 | 163159302467 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-22 | 2022-09-22 | 2022-12-06 | 2023-02-13 | 2023-02-14 | Underground | R16 | 2023-02-13 | 1 | 54 | 50 | 2 | 104 | 2022 | 2023 | R16
168595190703 | 166376190703 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-11 | 2020-05-11 | 2020-05-11 |  | 2021-07-26 | Overhead | R16 | 2020-11-04 | 1 |  | 128 | 189 | 316 | 2020 | 2021 | R16
168705187782 | 169969187782 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-03 | 2020-04-03 | 2020-04-16 |  | 2022-05-31 | Underground | R16 | 2022-05-02 | 1 | 10 | 533 | 22 | 563 | 2020 | 2022 | R16
168741194447 | 161860194447 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-15 | 2020-04-15 | 2020-06-15 |  | 2020-10-06 | Underground | R16 | 2020-07-23 | 1 | 44 | 29 | 54 | 125 | 2020 | 2020 | R16
162221333324 | 164933333324 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-21 | 2023-09-21 | 2023-09-21 | 2023-11-01 | 2023-11-28 | Overhead | R16 | 2023-11-01 | 1 |  | 30 | 20 | 49 | 2023 | 2023 | R16
168779185859 | 169162185859 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-31 | 2020-03-31 | 2020-03-31 |  | 2020-06-24 | Underground | R16 | 2020-04-23 | 1 |  | 18 | 45 | 62 | 2020 | 2020 | R16
160899295796 | 164930295796 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-02 | 2022-10-03 | 2022-10-03 |  | 2023-07-26 | Underground | R16 | 2023-02-23 | 1 |  | 104 | 110 | 213 | 2022 | 2023 | R16
166649300153 | 162668300153 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-10 | 2022-11-10 | 2022-11-10 | 2023-04-21 | 2023-05-05 | Overhead | R16 | 2023-04-21 | 1 |  | 117 | 11 | 127 | 2022 | 2023 | R16
161193301169 | 163855301169 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-11-17 | 2022-11-21 | 2022-11-21 | 2023-02-25 | 2023-02-28 | Underground | R16 | 2023-02-25 | 3 |  | 70 | 2 | 74 | 2022 | 2023 | R16
162252335554 | 168957335554 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-11-27 | Overhead | R16 | 2023-10-13 | 1 |  |  | 32 | 32 | 2023 | 2023 | R16
161420302923 | 167236302923 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-09 | 2022-12-09 | 2022-12-09 | 2023-02-27 | 2023-02-27 | Overhead | R16 | 2023-02-27 | 1 |  | 57 |  | 57 | 2022 | 2023 | R16
163610333460 | 169179333460 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-08-21 | 2023-08-21 | 2023-09-22 | 2023-10-27 | 2023-10-30 | Underground | R16 | 2023-10-27 | 1 | 25 | 26 | 2 | 51 | 2023 | 2023 | R16
169503299032 | 160801299032 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-01 | 2022-11-01 | 2022-11-01 |  | 2022-12-06 | Overhead | R16 | 2022-11-14 | 1 |  | 10 | 17 | 26 | 2022 | 2022 | R16
169212326833 | 162711326833 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-24 | 2023-07-24 | 2023-07-31 | 2023-09-25 | 2023-09-28 | Underground | R16 | 2023-09-25 | 1 | 6 | 41 | 4 | 49 | 2023 | 2023 | R16
169109191280 | 167423191280 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-15 | 2020-05-15 | 2020-05-15 |  | 2020-11-06 | Overhead | R16 | 2020-07-10 | 1 |  | 41 | 86 | 126 | 2020 | 2020 | R16
169789299437 | 161403299437 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-04 | 2022-11-04 | 2022-11-04 |  | 2022-12-22 | Overhead | R16 | 2022-12-19 | 1 |  | 32 | 4 | 35 | 2022 | 2022 | R16
162217302906 | 167320302906 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-09 | 2022-12-09 | 2022-12-09 |  | 2023-06-16 | Overhead | R16 | 2023-03-09 | 1 |  | 65 | 72 | 136 | 2022 | 2023 | R16
169151189958 | 163234189958 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-22 | 2020-04-22 | 2020-05-04 |  | 2020-12-14 | Underground | R16 | 2020-09-09 | 1 | 9 | 93 | 69 | 169 | 2020 | 2020 | R16
169188236411 | 166653236411 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2021-06-23 | 2021-06-23 | 2021-06-24 |  | 2022-04-15 | Underground | R16 |  | 1 | 2 |  |  | 213 | 2021 | 2022 | R16
169232306976 | 164239306976 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-11-21 | 2022-11-21 | 2023-01-30 | 2023-01-24 | 2023-11-14 | Underground | R16 | 2023-01-24 | 1 | 51 |  | 211 | 257 | 2022 | 2023 | R16
164150287542 | 160612287542 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2022-08-01 | 2022-08-01 | 2022-08-01 |  | 2022-11-03 | Overhead | R16 | 2022-11-02 | 1 |  | 68 | 2 | 69 | 2022 | 2022 | R16
160749295206 | 166900295206 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-08-29 | 2022-08-29 | 2022-09-28 | 2023-09-22 | 2023-11-14 | Underground | R16 | 2023-09-22 | 1 | 23 | 258 | 38 | 317 | 2022 | 2023 | R16
161545295428 | 162805295428 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-21 | 2022-09-21 | 2022-09-30 | 2023-03-09 | 2023-03-25 | Underground | R16 | 2023-03-09 | 1 | 8 | 115 | 12 | 133 | 2022 | 2023 | R16
169307225750 | 163871225750 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-04-27 | 2020-04-27 | 2021-04-05 |  | 2021-11-03 | Underground | R16 | 2021-06-23 | 1 | 246 | 58 | 96 | 398 | 2020 | 2021 | R16
163822301123 | 160866301123 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2022-11-02 | 2022-11-18 | 2022-11-18 |  | 2023-07-26 | Overhead | R16 | 2023-07-06 | 13 |  | 165 | 15 | 191 | 2022 | 2023 | R16
161429303156 | 166006303156 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-08-24 | 2022-09-07 | 2022-12-22 |  | 2023-09-08 | Underground | R16 |  | 11 | 77 |  |  | 273 | 2022 | 2023 | R16
169314249708 | 160333249708 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC DEVELOPMENT | Residential | 2021-07-12 | 2021-07-15 | 2021-09-27 |  | 2023-08-04 | Underground | R16 |  | 4 | 53 |  |  | 540 | 2021 | 2023 | R16
163695330761 | 169172330761 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-21 | 2023-08-21 | 2023-08-25 |  | 2023-10-13 | Overhead | R16 | 2023-10-12 | 1 | 5 | 35 | 2 | 40 | 2023 | 2023 | R16
163382298776 | 166535298776 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-11 | 2022-10-11 | 2022-11-01 | 2023-06-19 | 2023-06-20 | Underground | R16 | 2023-06-19 | 1 | 16 | 165 | 2 | 181 | 2022 | 2023 | R16
166645297514 | 168043297514 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-10-19 | 2022-10-19 | 2022-10-19 | 2023-07-05 | 2023-07-07 | Underground | R16 | 2023-07-05 | 1 |  | 186 | 3 | 188 | 2022 | 2023 | R16
169365188987 | 163593188987 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-24 | 2020-04-24 | 2020-04-24 |  | 2020-07-07 | Overhead | R16 | 2020-05-07 | 1 |  | 10 | 44 | 53 | 2020 | 2020 | R16
169366186843 | 160725186843 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-08 | 2020-04-08 | 2020-04-08 |  | 2021-09-13 | Underground | R16 | 2021-08-18 | 1 |  | 356 | 19 | 374 | 2020 | 2021 | R16
163327305240 | 165527305240 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-23 | 2022-08-23 | 2023-01-30 | 2023-02-21 | 2023-03-16 | Underground | R16 | 2023-02-21 | 1 | 115 | 17 | 18 | 148 | 2022 | 2023 | R16
166445333948 | 164918333948 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-21 | 2023-09-28 | 2023-09-28 | 2023-10-02 | 2023-10-31 | Overhead | R16 | 2023-10-02 | 6 |  | 3 | 22 | 29 | 2023 | 2023 | R16
161788288508 | 160873288508 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-08-02 | 2022-08-02 | 2022-08-10 | 2022-12-15 | 2022-12-20 | Overhead | R16 | 2022-12-15 | 1 | 7 | 92 | 4 | 101 | 2022 | 2022 | R16
169443191206 | 169445191206 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-04-01 | 2020-04-02 | 2020-05-15 |  | 2021-04-14 | Underground | R16 | 2020-12-14 | 2 | 32 | 152 | 88 | 271 | 2020 | 2021 | R16
166805293648 | 160938293648 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2022-09-12 | 2022-09-12 | 2022-09-14 |  | 2023-04-04 | Overhead | R16 | 2023-01-24 | 1 | 3 | 95 | 51 | 147 | 2022 | 2023 | R16
167506290208 | 165900290208 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-24 | 2022-08-24 | 2022-08-24 |  | 2023-08-18 | Overhead | R16 | 2023-03-24 | 1 |  | 153 | 106 | 258 | 2022 | 2023 | R16
168417287401 | 160206287401 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-29 | 2022-07-29 | 2022-07-29 | 2023-03-21 | 2023-04-08 | Overhead | R16 | 2023-03-21 | 1 |  | 168 | 14 | 181 | 2022 | 2023 | R16
169489190751 | 166462190751 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-11 | 2020-05-11 | 2020-05-11 |  | 2020-07-10 | Overhead | R16 | 2020-06-10 | 1 |  | 23 | 23 | 45 | 2020 | 2020 | R16
164953302678 | 166294302678 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-05 | 2022-12-08 | 2022-12-09 | 2023-03-09 | 2023-04-22 | Overhead | R16 | 2023-03-09 | 4 | 2 | 65 | 32 | 100 | 2022 | 2023 | R16
161591310184 | 163773310184 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-17 | 2023-02-22 | 2023-02-22 |  | 2023-09-13 | Underground | R16 | 2023-05-25 | 70 |  | 67 | 80 | 215 | 2022 | 2023 | R16
169516188301 | 161956188301 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-15 | 2020-04-20 | 2020-04-20 |  | 2020-07-09 | Overhead | R16 | 2020-06-04 | 4 |  | 34 | 26 | 62 | 2020 | 2020 | R16
160977328811 | 165073328811 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-04 | 2023-08-18 | 2023-08-18 | 2023-09-05 | 2023-10-30 | Overhead | R16 | 2023-09-05 | 11 |  | 13 | 40 | 62 | 2023 | 2023 | R16
169566308975 | 164870308975 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-27 | 2023-02-10 | 2023-02-10 |  | 2023-06-16 | Overhead | R16 | 2023-04-06 | 55 |  | 40 | 52 | 145 | 2022 | 2023 | R16
163073295377 | 164672295377 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2022-10-05 | 2022-12-06 | Overhead | R16 | 2022-10-05 | 1 |  | 4 | 45 | 48 | 2022 | 2022 | R16
163094297050 | 167471297050 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-14 | 2022-10-14 | 2022-10-14 |  | 2023-04-01 | Overhead | R16 | 2023-01-04 | 1 |  | 59 | 63 | 121 | 2022 | 2023 | R16
166981287744 | 161167287744 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-03 | 2022-08-03 | 2022-08-03 | 2022-12-05 | 2023-11-07 | Overhead | R16 | 2022-12-05 | 1 |  | 89 | 242 | 330 | 2022 | 2023 | R16
169576289084 | 167155289084 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-05-14 | 2022-08-15 | 2022-08-15 |  | 2023-07-27 | Overhead | R16 | 2023-03-17 | 588 |  | 155 | 95 | 836 | 2020 | 2023 | R16
163770299695 | 161970299695 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-08 | 2022-11-08 | 2022-11-08 | 2022-12-21 | 2023-02-10 | Overhead | R16 | 2022-12-21 | 1 |  | 32 | 38 | 69 | 2022 | 2023 | R16
161710290108 | 165857290108 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-24 | 2022-08-24 | 2022-08-24 | 2022-09-06 | 2022-09-07 | Overhead | R16 | 2022-09-06 | 1 |  | 10 | 2 | 11 | 2022 | 2022 | R16
169782209295 | 167240209295 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-10 | 2020-10-21 | 2020-11-02 |  | 2021-06-02 | Underground | R16 |  | 74 | 9 |  |  | 234 | 2020 | 2021 | R16
169823188382 | 160483188382 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-07 | 2020-04-07 | 2020-04-20 |  | 2020-10-06 | Underground | R16 | 2020-07-16 | 1 | 10 | 64 | 59 | 131 | 2020 | 2020 | R16
160344294602 | 161819294602 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-15 | 2022-09-22 | 2022-09-22 |  | 2022-12-04 | Overhead | R16 | 2022-11-02 | 6 |  | 30 | 23 | 57 | 2022 | 2022 | R16
162985332624 | 163722332624 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-14 | 2023-09-14 | 2023-09-14 | 2023-12-04 | 2023-12-18 | Overhead | R16 | 2023-12-04 | 1 |  | 58 | 11 | 68 | 2023 | 2023 | R16
168976287644 | 160718287644 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-08-02 | 2022-08-02 | 2022-08-02 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 1 |  | 113 |  | 113 | 2022 | 2023 | R16
160017186509 | 160018186509 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-04-03 | 2020-04-03 | 2020-04-06 |  | 2021-10-25 | Underground | R16 | 2021-09-03 | 1 | 2 | 370 | 37 | 407 | 2020 | 2021 | R16
163078306441 | 163736306441 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-26 | 2022-09-26 | 2023-01-30 | 2023-01-18 | 2023-05-17 | Underground | R16 | 2023-01-18 | 1 | 91 |  | 86 | 168 | 2022 | 2023 | R16
161511299687 | 161770299687 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-07 | 2022-11-07 | 2022-11-07 | 2023-06-15 | 2023-07-17 | Overhead | R16 | 2023-06-15 | 1 |  | 159 | 23 | 181 | 2022 | 2023 | R16
164115303861 | 165389303861 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-04 | 2022-10-04 | 2022-12-22 |  | 2023-05-16 | Underground | R16 | 2023-02-16 | 1 | 58 | 41 | 64 | 161 | 2022 | 2023 | R16
160073198869 | 167954198869 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-05-19 | 2020-07-27 | 2020-07-29 |  | 2021-11-11 | Overhead | R16 |  | 50 | 3 |  |  | 388 | 2020 | 2021 | R16
160079192005 | 163482192005 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-23 | 2020-04-23 | 2020-05-22 |  | 2021-07-01 | Underground | R16 | 2020-06-16 | 1 | 22 | 18 | 273 | 311 | 2020 | 2021 | R16
160082190752 | 166437190752 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-11 | 2020-05-11 | 2020-05-11 |  | 2020-07-10 | Overhead | R16 | 2020-06-10 | 1 |  | 23 | 23 | 45 | 2020 | 2020 | R16
163379331196 | 166705331196 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-14 | 2023-08-14 | 2023-08-30 | 2023-10-16 | 2023-10-26 | Overhead | R16 | 2023-10-16 | 1 | 13 | 34 | 9 | 54 | 2023 | 2023 | R16
168485301493 | 164822301493 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-26 | 2022-11-26 | 2022-11-26 | 2023-03-03 | 2023-03-06 | Overhead | R16 | 2023-03-03 | 0 |  | 70 | 2 | 71 | 2022 | 2023 | R16
163876326904 | 163916326904 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-07-31 | 2023-07-31 | 2023-07-31 | 2023-07-31 | 2023-08-01 | Overhead | R16 | 2023-07-31 | 1 |  |  | 2 | 2 | 2023 | 2023 | R16
163214293055 | 160003293055 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-07 | 2022-09-07 | 2022-09-09 | 2022-10-07 | 2022-12-06 | Overhead | R16 | 2022-10-07 | 1 | 3 | 21 | 43 | 65 | 2022 | 2022 | R16
160284189125 | 160852189125 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-09 | 2020-04-09 | 2020-04-27 |  | 2020-08-28 | Underground | R16 | 2020-07-01 | 1 | 13 | 48 | 43 | 102 | 2020 | 2020 | R16
167714295228 | 160404295228 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2022-09-09 | 2022-09-09 | 2022-09-28 | 2023-07-21 | 2023-08-16 | Underground | R16 | 2023-07-21 | 1 | 14 | 213 | 19 | 244 | 2022 | 2023 | R16
163689331777 | 167504331777 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-08-17 | 2023-08-17 | 2023-09-06 | 2023-09-19 | 2023-11-06 | Underground | R16 | 2023-09-19 | 1 | 15 | 10 | 35 | 58 | 2023 | 2023 | R16
163095297746 | 162172297746 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-18 | 2022-09-18 | 2022-10-21 |  | 2023-10-13 | Underground | R16 | 2023-06-28 | 0 | 25 | 179 | 78 | 280 | 2022 | 2023 | R16
160466194799 | 163504194799 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-22 | 2020-06-22 | 2020-06-22 |  | 2021-07-14 | Overhead | R16 | 2020-11-19 | 1 |  | 109 | 170 | 278 | 2020 | 2021 | R16
168872303964 | 161785303964 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2022-09-15 | 2022-12-20 | 2022-12-22 | 2023-09-06 | 2023-09-21 | Overhead | R16 | 2023-09-06 | 69 | 3 | 185 | 12 | 266 | 2022 | 2023 | R16
169728295048 | 162622295048 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-08-09 | 2022-09-01 | 2022-09-26 | 2023-06-18 | 2023-06-21 | Underground | R16 | 2023-06-18 | 18 | 18 | 190 | 3 | 227 | 2022 | 2023 | R16
164296290853 | 167417290853 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-31 | 2022-08-31 | 2022-08-31 |  | 2022-10-23 | Overhead | R16 | 2022-10-13 | 1 |  | 32 | 7 | 38 | 2022 | 2022 | R16
166035302591 | 166931302591 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-10-12 | 2022-11-30 | 2022-12-07 |  | 2023-05-17 | Overhead | R16 |  | 36 | 6 |  |  | 156 | 2022 | 2023 | R16
168544295277 | 164577295277 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-29 | 2022-09-29 | 2022-09-29 |  | 2022-11-28 | Overhead | R16 |  | 1 |  |  |  | 43 | 2022 | 2022 | R16
160556246265 | 161129246265 | NON-RESIDENTIAL - MISCELLANEOUS | UG ELEC MISC SVC US | Residential | 2021-08-25 | 2021-08-25 | 2021-09-01 |  | 2022-07-26 | Underground | R16 |  | 1 | 6 |  |  | 240 | 2021 | 2022 | R16
160557187624 | 161787187624 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-15 | 2020-04-15 | 2020-04-15 |  | 2022-03-03 | Overhead | R16 | 2022-02-04 | 1 |  | 473 | 20 | 492 | 2020 | 2022 | R16
160668295298 | 164414295298 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-29 | 2022-09-29 | 2022-09-29 |  | 2023-08-28 | Overhead | R16 | 2023-08-11 | 1 |  | 227 | 12 | 238 | 2022 | 2023 | R16
162220326328 | 162931326328 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-25 | 2023-07-25 | 2023-07-25 | 2023-08-10 | 2023-09-25 | Overhead | R16 | 2023-08-10 | 1 |  | 13 | 33 | 45 | 2023 | 2023 | R16
162729297023 | 167311297023 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-13 | 2022-10-13 | 2022-10-13 | 2023-01-30 | 2023-01-31 | Underground | R16 | 2023-01-30 | 1 |  | 78 | 2 | 79 | 2022 | 2023 | R16
163962299933 | 164668299933 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-30 | 2022-09-30 | 2022-11-08 | 2023-01-23 | 2023-01-26 | Underground | R16 | 2023-01-23 | 1 | 28 | 55 | 4 | 85 | 2022 | 2023 | R16
162574331944 | 162229331944 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-07 | 2023-09-07 | 2023-09-07 | 2023-11-15 | 2023-12-05 | Overhead | R16 | 2023-11-15 | 1 |  | 50 | 15 | 64 | 2023 | 2023 | R16
168997299354 | 161291299354 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-03 | 2022-11-03 | 2022-11-03 | 2023-01-30 | 2023-01-31 | Overhead | R16 | 2023-01-30 | 1 |  | 63 | 2 | 64 | 2022 | 2023 | R16
160754188928 | 160809188928 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-04-10 | 2020-04-10 | 2020-04-24 |  | 2022-06-06 | Underground | R16 | 2022-05-09 | 1 | 11 | 532 | 21 | 562 | 2020 | 2022 | R16
169889336083 | 165479336083 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-09-26 | 2023-10-17 | 2023-10-17 | 2023-12-05 | 2023-12-08 | Overhead | R16 | 2023-12-05 | 16 |  | 36 | 4 | 54 | 2023 | 2023 | R16
167670298404 | 169754298404 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-26 | 2022-10-26 | 2022-10-26 |  | 2022-12-15 | Overhead | R16 | 2022-12-14 | 1 |  | 36 | 2 | 37 | 2022 | 2022 | R16
166263300825 | 167410300825 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-31 | 2022-08-31 | 2022-11-16 | 2022-11-16 | 2023-02-17 | Underground | R16 | 2022-11-16 | 1 | 56 |  | 68 | 123 | 2022 | 2023 | R16
160174331994 | 162531331994 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-09-18 | 2023-11-29 | Overhead | R16 | 2023-09-18 | 1 |  | 7 | 53 | 59 | 2023 | 2023 | R16
160776198823 | 162404198823 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-06-16 | 2020-06-16 | 2020-07-28 |  | 2021-11-19 | Underground | R16 | 2020-09-17 | 1 | 31 | 38 | 307 | 374 | 2020 | 2021 | R16
164636303972 | 166634303972 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-07 | 2022-12-21 | 2022-12-22 |  | 2023-06-09 | Overhead | R16 | 2023-01-18 | 11 | 2 | 20 | 103 | 133 | 2022 | 2023 | R16
160995305620 | 166071305620 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-02 | 2022-12-02 | 2023-01-30 | 2023-01-10 | 2023-07-24 | Underground | R16 | 2023-01-10 | 1 | 42 |  | 140 | 167 | 2022 | 2023 | R16
167430295744 | 164894295744 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-03 |  | 2022-10-03 |  | 2022-12-15 | Overhead | R16 | 2022-12-13 |  |  | 52 | 3 | 54 | 2022 | 2022 | R16
168734328746 | 165231328746 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-05 | 2023-08-17 | 2023-08-17 | 2023-10-20 | 2023-10-25 | Overhead | R16 | 2023-10-20 | 9 |  | 47 | 4 | 58 | 2023 | 2023 | R16
166109302785 | 166964302785 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-08 | 2022-12-08 | 2022-12-08 |  | 2023-04-04 | Overhead | R16 | 2022-12-29 | 1 |  | 16 | 69 | 84 | 2022 | 2023 | R16
169557327073 | 161830327073 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-19 | 2023-07-19 | 2023-08-01 | 2023-09-26 | 2023-10-25 | Overhead | R16 | 2023-09-26 | 1 | 10 | 41 | 22 | 71 | 2023 | 2023 | R16
166913293913 | 160314293913 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-08 | 2022-09-16 | 2022-09-16 | 2022-11-01 | 2023-01-14 | Overhead | R16 | 2022-11-01 | 7 |  | 33 | 54 | 92 | 2022 | 2023 | R16
160978194668 | 162212194668 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-04-16 | 2020-04-16 | 2020-06-18 |  | 2020-10-29 | Overhead | R16 | 2020-08-31 | 1 | 46 | 53 | 44 | 141 | 2020 | 2020 | R16
160929303083 | 163763303083 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-17 | 2022-11-17 | 2022-12-21 |  | 2023-02-15 | Underground | R16 |  | 1 | 25 |  |  | 65 | 2022 | 2023 | R16
162463297010 | 164773297010 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-30 | 2022-09-30 | 2022-10-14 | 2022-11-24 | 2022-11-30 | Overhead | R16 | 2022-11-24 | 1 | 11 | 30 | 5 | 44 | 2022 | 2022 | R16
161062195054 | 163859195054 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2020-06-24 | 2020-06-24 | 2020-06-24 |  | 2021-04-14 | Overhead | R16 | 2020-12-09 | 1 |  | 121 | 91 | 211 | 2020 | 2021 | R16
166315290686 | 167079290686 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-30 | 2022-08-30 | 2022-08-30 |  | 2022-12-04 | Underground | R16 | 2022-10-19 | 1 |  | 37 | 33 | 69 | 2022 | 2022 | R16
161182196647 | 166625196647 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2020-07-08 | 2020-07-08 | 2020-07-08 |  | 2021-04-16 | Overhead | R16 | 2020-12-30 | 1 |  | 126 | 78 | 203 | 2020 | 2021 | R16
168677328710 | 167124328710 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-15 | 2023-08-15 | 2023-08-17 | 2023-08-24 | 2023-08-31 | Overhead | R16 | 2023-08-24 | 1 | 3 | 6 | 6 | 13 | 2023 | 2023 | R16
163591330990 | 160085330990 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-08-25 | 2023-08-28 | 2023-08-28 | 2023-08-30 | 2023-10-18 | Underground | R16 | 2023-08-30 | 2 |  | 3 | 36 | 39 | 2023 | 2023 | R16
168558288449 | 169604288449 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | R16 RESD AND NON RESD US | Commercial | 2022-07-27 | 2022-07-27 | 2022-08-10 |  | 2023-03-27 | Underground | R16 |  | 1 | 11 |  |  | 174 | 2022 | 2023 | R16
164287294379 | 162663294379 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-10 | 2022-08-10 | 2022-09-21 |  | 2023-06-26 | Underground | R16 | 2023-03-13 | 1 | 31 | 124 | 76 | 229 | 2022 | 2023 | R16
169269325839 | 162457325839 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-22 | 2023-07-22 | 2023-07-22 | 2023-07-31 | 2023-09-07 | Overhead | R16 | 2023-07-31 | 0 |  | 6 | 29 | 34 | 2023 | 2023 | R16
163192302369 | 166208302369 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-05 | 2022-12-05 | 2022-12-05 | 2023-07-05 | 2023-07-20 | Overhead | R16 | 2023-07-05 | 1 |  | 153 | 12 | 164 | 2022 | 2023 | R16
167243297940 | 160246297940 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-09-08 | 2022-10-23 | 2022-10-23 | 2023-03-03 | 2023-03-24 | Overhead | R16 | 2023-03-03 | 32 |  | 95 | 16 | 142 | 2022 | 2023 | R16
167596297623 | 168027297623 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-19 | 2022-10-19 | 2022-10-19 |  | 2022-12-15 | Overhead | R16 | 2022-12-14 | 1 |  | 41 | 2 | 42 | 2022 | 2022 | R16
169564308565 | 161756308565 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-11-07 | 2023-01-06 | 2023-02-06 |  | 2023-10-12 | Overhead | R16 |  | 45 | 22 |  |  | 244 | 2022 | 2023 | R16
161403207388 | 161765207388 | NON-RESIDENTIAL - LODGING | UG R16 RESD AND NON RESD UD | Commercial | 2020-04-14 | 2020-09-09 | 2020-10-15 |  | 2022-10-03 | Underground | R16 |  | 107 | 27 |  |  | 645 | 2020 | 2022 | R16
162991295230 | 164153295230 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2022-09-28 | 2022-09-28 | 2022-09-28 | 2022-10-25 | 2022-10-26 | Overhead | R16 | 2022-10-25 | 1 |  | 20 | 2 | 21 | 2022 | 2022 | R16
161404189389 | 164584189389 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-29 | 2020-04-29 | 2020-04-29 |  | 2020-08-28 | Overhead | R16 | 2020-07-02 | 1 |  | 47 | 42 | 88 | 2020 | 2020 | R16
164275333541 | 165343333541 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-22 | 2023-09-22 | 2023-09-22 | 2023-10-11 | 2023-11-02 | Overhead | R16 | 2023-10-11 | 1 |  | 14 | 17 | 30 | 2023 | 2023 | R16
165278294361 | 162245294361 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-08 |  | 2022-08-08 | 2023-10-11 | 2023-11-06 | Underground | R16 | 2023-10-11 |  |  | 308 | 19 | 326 | 2022 | 2023 | R16
166138290563 | 162214290563 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-08 | 2022-08-08 | 2022-08-29 |  | 2022-09-30 | Underground | R16 | 2022-09-29 | 1 | 16 | 24 | 2 | 40 | 2022 | 2022 | R16
167406292954 | 169974292954 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-09-07 | 2022-09-08 | 2022-09-08 |  | 2023-06-19 | Overhead | R16 | 2023-06-05 | 2 |  | 193 | 11 | 204 | 2022 | 2023 | R16
160689287483 | 160590287483 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-01 | 2022-08-01 | 2022-08-01 |  | 2022-12-05 | Overhead | R16 | 2022-12-01 | 1 |  | 89 | 3 | 91 | 2022 | 2022 | R16
169041295430 | 161426295430 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-14 | 2022-09-30 | 2022-09-30 |  | 2023-03-01 | Overhead | R16 | 2022-12-14 | 13 |  | 54 | 56 | 121 | 2022 | 2023 | R16
167856289595 | 164934289595 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-19 | 2022-08-19 | 2022-08-19 |  | 2022-10-11 | Overhead | R16 | 2022-10-10 | 1 |  | 37 | 2 | 38 | 2022 | 2022 | R16
160769287998 | 161913287998 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-05 | 2022-08-05 | 2022-08-05 | 2022-10-16 | 2023-01-11 | Underground | R16 | 2022-10-16 | 1 |  | 51 | 63 | 114 | 2022 | 2023 | R16
161600190362 | 161920190362 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-15 | 2020-04-15 | 2020-05-07 |  | 2020-08-14 | Underground | R16 | 2020-06-22 | 1 | 17 | 33 | 40 | 88 | 2020 | 2020 | R16
168827294280 | 162294294280 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2022-09-19 | 2022-09-19 | 2022-09-19 |  | 2023-01-10 | Overhead | R16 | 2022-11-14 | 1 |  | 41 | 42 | 82 | 2022 | 2023 | R16
161613199745 | 161747199745 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-06-12 | 2020-06-12 | 2020-08-05 |  | 2021-04-14 | Overhead | R16 | 2020-12-10 | 1 | 39 | 92 | 90 | 219 | 2020 | 2021 | R16
161055289261 | 164114289261 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-16 | 2022-08-16 | 2022-08-16 | 2022-08-22 | 2022-08-25 | Overhead | R16 | 2022-08-22 | 1 |  | 5 | 4 | 8 | 2022 | 2022 | R16
161613194389 | 162081194389 | RESIDENTIAL - SINGLE FAMILY DETACHED | ELEC OH MISC SVC OS | Residential | 2020-06-12 | 2020-06-16 | 2020-06-16 |  | 2021-04-14 | Overhead | R16 | 2020-12-10 | 3 |  | 128 | 90 | 219 | 2020 | 2021 | R16
163434293846 | 164666293846 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-18 | 2022-08-18 | 2022-09-15 | 2023-01-11 | 2023-01-11 | Underground | R16 | 2023-01-11 | 1 | 21 | 85 |  | 105 | 2022 | 2023 | R16
163207298902 | 167232298902 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-13 | 2022-10-31 | 2022-10-31 | 2023-06-29 | 2023-08-24 | Underground | R16 | 2023-06-29 | 13 |  | 174 | 41 | 226 | 2022 | 2023 | R16
164473296446 | 166041296446 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-07 | 2022-10-08 | 2022-10-08 | 2023-08-01 | 2023-08-03 | Overhead | R16 | 2023-08-01 | 1 |  | 212 | 3 | 215 | 2022 | 2023 | R16
161722190677 | 166597190677 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2020-05-12 | 2020-05-12 | 2020-05-12 |  | 2021-04-14 | Overhead | R16 | 2020-12-11 | 1 |  | 154 | 89 | 242 | 2020 | 2021 | R16
169625301374 | 163478301374 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-11-16 | 2022-11-22 | 2022-11-22 | 2023-06-23 | 2023-08-16 | Underground | R16 | 2023-06-23 | 5 |  | 154 | 39 | 196 | 2022 | 2023 | R16
163861294153 | 162326294153 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-20 | 2022-09-20 | 2022-09-20 |  | 2022-11-16 | Overhead | R16 | 2022-11-14 | 1 |  | 40 | 3 | 42 | 2022 | 2022 | R16
163054321233 | 167016321233 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-12-08 | 2023-04-19 | 2023-06-06 | 2023-10-23 | 2023-11-06 | Underground | R16 | 2023-10-23 | 95 | 35 | 100 | 11 | 238 | 2022 | 2023 | R16
163610339066 | 160027339066 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-24 | 2023-08-24 | 2023-11-08 | 2023-12-04 | 2023-12-06 | Overhead | R16 | 2023-12-04 | 1 | 55 | 19 | 3 | 75 | 2023 | 2023 | R16
163880293082 | 160273293082 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-09-08 | 2022-09-08 | 2022-09-08 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 1 |  | 86 |  | 86 | 2022 | 2023 | R16
161802192492 | 169396192492 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-28 | 2020-05-28 | 2020-05-28 |  | 2020-08-28 | Overhead | R16 | 2020-06-29 | 1 |  | 23 | 45 | 67 | 2020 | 2020 | R16
160165301894 | 163655301894 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-17 | 2022-11-17 | 2022-11-30 | 2022-12-12 | 2023-03-24 | Underground | R16 | 2022-12-12 | 1 | 10 | 9 | 75 | 92 | 2022 | 2023 | R16
161764295751 | 164054295751 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-09-28 | 2022-10-03 | 2022-10-04 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 4 | 2 | 68 |  | 72 | 2022 | 2023 | R16
165920333905 | 165981333905 | RESIDENTIAL - MOBILE HOME | OH R16 RES NON RES OS | Residential | 2023-09-27 | 2023-09-27 | 2023-09-27 | 2023-10-03 | 2023-10-03 | Overhead | R16 | 2023-10-03 | 1 |  | 5 |  | 5 | 2023 | 2023 | R16
161829188863 | 163480188863 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-23 | 2020-04-23 | 2020-04-23 |  | 2020-08-28 | Overhead | R16 | 2020-06-30 | 1 |  | 49 | 44 | 92 | 2020 | 2020 | R16
163453331107 | 160209331107 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-25 | 2023-08-29 | 2023-08-29 | 2023-09-11 | 2023-12-11 | Overhead | R16 | 2023-09-11 | 3 |  | 10 | 66 | 77 | 2023 | 2023 | R16
161393289036 | 162591289036 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-09 | 2022-08-10 | 2022-08-15 | 2022-12-12 | 2022-12-15 | Underground | R16 | 2022-12-12 | 2 | 4 | 86 | 4 | 93 | 2022 | 2022 | R16
161869188883 | 163450188883 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-23 | 2020-04-23 | 2020-04-23 |  | 2020-10-06 | Overhead | R16 | 2020-08-21 | 1 |  | 87 | 33 | 119 | 2020 | 2020 | R16
162932335263 | 168265335263 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-10-10 | 2023-10-10 | 2023-10-10 |  | 2023-12-14 | Overhead | R16 |  | 1 |  |  |  | 48 | 2023 | 2023 | R16
163375295994 | 163728295994 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-27 | 2022-10-05 | 2022-10-05 |  | 2022-12-10 | Overhead | R16 | 2022-11-07 | 7 |  | 24 | 25 | 54 | 2022 | 2022 | R16
169728332336 | 163245332336 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-12 | 2023-09-12 | 2023-09-12 | 2023-09-13 | 2023-10-25 | Overhead | R16 | 2023-09-13 | 1 |  | 2 | 31 | 32 | 2023 | 2023 | R16
165939287927 | 161652287927 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-04 | 2022-08-04 | 2022-08-04 |  | 2023-05-02 | Overhead | R16 | 2023-01-31 | 1 |  | 129 | 66 | 194 | 2022 | 2023 | R16
162042191595 | 165267191595 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-04 | 2020-05-19 | 2020-05-19 |  | 2021-07-02 | Overhead | R16 | 2020-10-26 | 12 |  | 115 | 180 | 305 | 2020 | 2021 | R16
168986295847 | 163165295847 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-09-23 | 2022-10-03 | 2022-10-04 |  | 2023-04-27 | Underground | R16 |  | 7 | 2 |  |  | 155 | 2022 | 2023 | R16
162137202535 | 164976202535 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2020-05-01 | 2020-09-02 | 2020-09-03 |  | 2021-04-16 | Overhead | R16 |  | 89 | 2 |  |  | 251 | 2020 | 2021 | R16
160330337105 | 168010337105 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-10-09 | 2023-10-09 | 2023-10-26 | 2023-11-20 | 2023-11-28 | Underground | R16 | 2023-11-20 | 1 | 14 | 18 | 7 | 37 | 2023 | 2023 | R16
162184216133 | 161138216133 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-12-16 | 2020-12-16 | 2021-01-04 |  | 2021-05-07 | Overhead | R16 | 2021-02-24 | 1 | 14 | 38 | 53 | 103 | 2020 | 2021 | R16
160724287298 | 160470287298 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-29 | 2022-07-29 | 2022-07-29 |  | 2022-09-30 | Overhead | R16 | 2022-08-22 | 1 |  | 17 | 30 | 46 | 2022 | 2022 | R16
167947306856 | 165532306856 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-11-30 | 2022-11-30 | 2023-01-30 | 2023-01-24 | 2023-06-01 | Underground | R16 | 2023-01-24 | 1 | 44 |  | 93 | 132 | 2022 | 2023 | R16
162500299580 | 165585299580 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-05 | 2022-11-04 | 2022-11-04 |  | 2023-05-30 | Overhead | R16 | 2023-02-07 | 23 |  | 68 | 81 | 170 | 2022 | 2023 | R16
164550294265 | 165572294265 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-08-23 | 2022-08-23 | 2022-09-19 | 2023-02-21 | 2023-03-07 | Underground | R16 | 2023-02-21 | 1 | 20 | 112 | 11 | 141 | 2022 | 2023 | R16
162394191039 | 162875191039 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-21 | 2020-04-21 | 2020-05-14 |  | 2020-07-09 | Underground | R16 | 2020-06-02 | 1 | 18 | 14 | 28 | 58 | 2020 | 2020 | R16
161818289284 | 163600289284 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-12 | 2022-08-16 | 2022-08-16 |  | 2023-08-04 | Overhead | R16 | 2022-09-29 | 3 |  | 33 | 222 | 256 | 2022 | 2023 | R16
164835330686 | 160270330686 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-25 | 2023-08-25 | 2023-08-25 | 2023-11-15 | 2023-11-20 | Overhead | R16 | 2023-11-15 | 1 |  | 59 | 4 | 62 | 2023 | 2023 | R16
162584301816 | 163996301816 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-16 | 2022-08-16 | 2022-11-30 |  | 2023-07-20 | Underground | R16 | 2023-06-28 | 1 | 77 | 151 | 17 | 243 | 2022 | 2023 | R16
162464189391 | 164436189391 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2020-04-29 | 2020-04-29 | 2020-04-29 |  | 2020-07-14 | Overhead | R16 | 2020-06-18 | 1 |  | 37 | 19 | 55 | 2020 | 2020 | R16
162465193244 | 166184193244 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-09 | 2020-05-09 | 2020-06-04 |  | 2023-06-09 | Overhead | R16 |  | 0 | 19 |  |  | 805 | 2020 | 2023 | R16
164403331997 | 162504331997 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-10-10 | 2023-10-13 | Overhead | R16 | 2023-10-10 | 1 |  | 23 | 4 | 26 | 2023 | 2023 | R16
162468267112 | 166032267112 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2021-12-15 | 2021-12-15 | 2022-02-01 |  | 2022-04-01 | Underground | R16 |  | 1 | 35 |  |  | 78 | 2021 | 2022 | R16
169800325945 | 162432325945 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-22 | 2023-07-22 | 2023-07-22 | 2023-08-28 | 2023-10-12 | Overhead | R16 | 2023-08-28 | 0 |  | 26 | 34 | 59 | 2023 | 2023 | R16
165962333897 | 165517333897 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2023-09-25 | 2023-09-28 | 2023-09-28 | 2023-10-12 | 2023-11-16 | Overhead | R16 | 2023-10-12 | 4 |  | 11 | 26 | 39 | 2023 | 2023 | R16
160326289610 | 165011289610 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-19 | 2022-08-19 | 2022-08-19 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 1 |  | 100 |  | 100 | 2022 | 2023 | R16
169589299938 | 162330299938 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2022-11-09 | 2022-11-09 | 2022-11-09 |  | 2023-07-07 | Overhead | R16 |  | 1 |  |  |  | 173 | 2022 | 2023 | R16
164597307431 | 166305307431 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-05 | 2022-12-05 | 2023-01-28 |  | 2023-08-14 | Underground | R16 | 2023-04-24 | 1 | 40 | 61 | 81 | 181 | 2022 | 2023 | R16
164626294877 | 163702294877 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-26 | 2022-09-26 | 2022-09-26 | 2023-08-23 | 2023-08-24 | Overhead | R16 | 2023-08-23 | 1 |  | 238 | 2 | 239 | 2022 | 2023 | R16
161083325788 | 161382325788 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-17 | 2023-07-20 | 2023-07-20 | 2023-11-14 | 2023-11-17 | Overhead | R16 | 2023-11-14 | 4 |  | 84 | 4 | 90 | 2023 | 2023 | R16
169215333372 | 165191333372 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-04 | 2023-09-21 | 2023-09-21 | 2023-10-13 | 2023-11-15 | Overhead | R16 | 2023-10-13 | 35 |  | 17 | 24 | 74 | 2023 | 2023 | R16
165232297068 | 163247297068 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-11 | 2022-08-16 | 2022-10-14 | 2023-04-23 | 2023-04-26 | Underground | R16 | 2023-04-23 | 4 | 44 | 136 | 3 | 185 | 2022 | 2023 | R16
162024294413 | 163093294413 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-22 | 2022-09-22 | 2022-09-22 | 2022-09-29 | 2022-12-04 | Overhead | R16 | 2022-09-29 | 1 |  | 6 | 47 | 52 | 2022 | 2022 | R16
169275326318 | 161815326318 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-19 | 2023-07-19 | 2023-07-26 | 2023-09-29 | 2023-10-25 | Underground | R16 | 2023-09-29 | 1 | 6 | 48 | 19 | 71 | 2023 | 2023 | R16
162897327234 | 164381327234 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2023-08-02 | 2023-08-03 | 2023-08-03 | 2023-08-07 | 2023-11-09 | Underground | R16 | 2023-08-07 | 2 |  | 3 | 69 | 72 | 2023 | 2023 | R16
162786194920 | 169024194920 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-05-26 | 2020-05-26 | 2020-06-19 |  | 2022-01-25 | Underground | R16 | 2022-01-25 | 1 | 19 | 418 |  | 436 | 2020 | 2022 | R16
169305302089 | 166026302089 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-02 | 2022-12-02 | 2022-12-02 | 2023-01-19 | 2023-01-20 | Overhead | R16 | 2023-01-19 | 1 |  | 35 | 2 | 36 | 2022 | 2023 | R16
168989301197 | 165321301197 | NON-RESIDENTIAL - SMALL RETAIL | R16 RESD AND NON RESD US | Commercial | 2022-10-04 | 2022-11-02 | 2022-11-21 | 2023-08-23 | 2023-09-20 | Underground | R16 | 2023-08-23 | 22 | 14 | 198 | 21 | 252 | 2022 | 2023 | R16
162579330280 | 169229330280 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-21 | 2023-08-21 | 2023-08-21 | 2023-10-11 | 2023-12-04 | Overhead | R16 | 2023-10-11 | 1 |  | 38 | 39 | 76 | 2023 | 2023 | R16
162648327372 | 165097327372 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-04 | 2023-08-04 | 2023-08-04 | 2023-08-17 | 2023-09-22 | Overhead | R16 | 2023-08-17 | 1 |  | 10 | 27 | 36 | 2023 | 2023 | R16
167925298029 | 168614298029 | NON-RESIDENTIAL - LARGE OFFICE | R16 RESD AND NON RESD US | Commercial | 2022-10-20 | 2022-10-20 | 2022-10-24 | 2023-01-24 | 2023-02-06 | Underground | R16 | 2023-01-24 | 1 | 3 | 67 | 10 | 78 | 2022 | 2023 | R16
162271295885 | 163812295885 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-27 | 2022-10-04 | 2022-10-04 | 2022-10-07 | 2023-01-10 | Overhead | R16 | 2022-10-07 | 6 |  | 4 | 68 | 76 | 2022 | 2023 | R16
164647332923 | 164099332923 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-15 | 2023-09-18 | 2023-09-18 | 2023-10-13 | 2023-10-17 | Overhead | R16 | 2023-10-13 | 2 |  | 20 | 3 | 23 | 2023 | 2023 | R16
162957189405 | 164464189405 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-29 | 2020-04-29 | 2020-04-29 |  | 2020-10-06 | Overhead | R16 | 2020-07-27 | 1 |  | 64 | 52 | 115 | 2020 | 2020 | R16
161421297246 | 162576297246 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-09-20 | 2022-09-20 | 2022-10-17 | 2022-12-03 | 2022-12-06 | Underground | R16 | 2022-12-03 | 1 | 20 | 35 | 2 | 56 | 2022 | 2022 | R16
162901290371 | 163709290371 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-15 | 2022-08-15 | 2022-08-26 | 2023-01-26 | 2023-03-04 | Underground | R16 | 2023-01-26 | 1 | 10 | 110 | 27 | 145 | 2022 | 2023 | R16
163306302343 | 164964302343 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-28 | 2022-12-05 | 2022-12-05 |  | 2023-07-24 | Overhead | R16 | 2023-02-21 | 6 |  | 57 | 110 | 171 | 2022 | 2023 | R16
168764287530 | 160603287530 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-01 | 2022-08-01 | 2022-08-01 | 2022-11-14 | 2022-11-14 | Overhead | R16 | 2022-11-14 | 1 |  | 76 |  | 76 | 2022 | 2022 | R16
169349295929 | 165169295929 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-04 | 2022-10-04 | 2022-10-04 |  | 2022-12-20 | Overhead | R16 | 2022-12-15 | 1 |  | 53 | 4 | 56 | 2022 | 2022 | R16
161377306102 | 160675306102 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-01 | 2023-01-13 | 2023-01-25 | 2023-01-17 | 2023-09-29 | Underground | R16 | 2023-01-17 | 120 | 9 |  | 184 | 305 | 2022 | 2023 | R16
161731289670 | 164939289670 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-19 | 2022-08-19 | 2022-08-19 | 2022-10-19 | 2023-01-05 | Overhead | R16 | 2022-10-19 | 1 |  | 44 | 57 | 100 | 2022 | 2023 | R16
163105189310 | 163841189310 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-27 | 2020-04-29 | 2020-04-29 |  | 2020-07-13 | Overhead | R16 | 2020-06-15 | 3 |  | 34 | 21 | 56 | 2020 | 2020 | R16
163107189413 | 164548189413 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-29 | 2020-04-29 | 2020-04-29 |  | 2020-07-09 | Overhead | R16 | 2020-06-08 | 1 |  | 29 | 24 | 52 | 2020 | 2020 | R16
164839334093 | 162325334093 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2023-09-07 | 2023-09-07 | 2023-09-29 | 2023-10-30 | 2023-11-15 | Overhead | R16 | 2023-10-30 | 1 | 17 | 22 | 13 | 50 | 2023 | 2023 | R16
163041302561 | 165806302561 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-01 | 2022-12-06 | 2022-12-06 | 2023-01-11 | 2023-01-23 | Overhead | R16 | 2023-01-11 | 4 |  | 27 | 9 | 38 | 2022 | 2023 | R16
166518287888 | 161492287888 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-04 | 2022-08-04 | 2022-08-04 | 2022-11-13 | 2022-11-16 | Underground | R16 | 2022-11-13 | 1 |  | 72 | 3 | 75 | 2022 | 2022 | R16
164159299466 | 169889299466 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-27 | 2022-10-27 | 2022-11-04 | 2022-11-14 | 2023-04-04 | Underground | R16 | 2022-11-14 | 1 | 7 | 7 | 102 | 114 | 2022 | 2023 | R16
162049332220 | 160249332220 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-25 | 2023-09-09 | 2023-09-09 | 2023-10-06 | 2023-11-03 | Overhead | R16 | 2023-10-06 | 11 |  | 20 | 21 | 51 | 2023 | 2023 | R16
163295190336 | 166086190336 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-08 | 2020-05-08 | 2020-05-08 |  | 2020-08-14 | Underground | R16 | 2020-06-23 | 1 |  | 33 | 39 | 71 | 2020 | 2020 | R16
169127302606 | 166281302606 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-09 | 2022-10-09 | 2022-12-06 |  | 2023-07-31 | Underground | R16 | 2023-03-10 | 0 | 42 | 69 | 102 | 211 | 2022 | 2023 | R16
164097307899 | 165504307899 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-30 | 2022-11-30 | 2023-02-01 |  | 2023-09-29 | Overhead | R16 | 2023-05-31 | 1 | 46 | 86 | 88 | 218 | 2022 | 2023 | R16
163314191051 | 167133191051 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-14 | 2020-05-14 | 2020-05-14 |  | 2021-10-25 | Overhead | R16 | 2021-08-30 | 1 |  | 338 | 41 | 378 | 2020 | 2021 | R16
161487294633 | 163148294633 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-23 | 2022-09-23 | 2022-09-23 | 2022-11-21 | 2022-11-24 | Overhead | R16 | 2022-11-21 | 1 |  | 42 | 4 | 45 | 2022 | 2022 | R16
163324192589 | 163567192589 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-24 |  | 2020-04-24 |  | 2020-08-14 | Underground | R16 | 2020-06-23 |  |  | 43 | 39 | 81 | 2020 | 2020 | R16
168017335086 | 167471335086 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-10-05 | 2023-10-09 | 2023-10-09 | 2023-11-22 | 2023-12-15 | Overhead | R16 | 2023-11-22 | 3 |  | 33 | 18 | 52 | 2023 | 2023 | R16
163560297081 | 160105297081 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-28 | 2022-08-01 | 2022-10-14 | 2022-12-22 | 2022-12-27 | Overhead | R16 | 2022-12-22 | 3 | 55 | 50 | 4 | 109 | 2022 | 2022 | R16
165436297388 | 167956297388 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-18 | 2022-10-18 | 2022-10-18 |  | 2023-03-31 | Overhead | R16 | 2023-02-16 | 1 |  | 88 | 32 | 119 | 2022 | 2023 | R16
165635330487 | 169928330487 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-24 | 2023-08-24 | 2023-08-24 | 2023-09-01 | 2023-10-19 | Overhead | R16 | 2023-09-01 | 1 |  | 7 | 35 | 41 | 2023 | 2023 | R16
169336325844 | 162169325844 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-21 | 2023-07-21 | 2023-07-21 | 2023-08-30 | 2023-10-05 | Underground | R16 | 2023-08-30 | 1 |  | 29 | 27 | 55 | 2023 | 2023 | R16
162788332281 | 162759332281 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-11 | 2023-09-11 | 2023-09-11 | 2023-10-05 | 2023-10-09 | Overhead | R16 | 2023-10-05 | 1 |  | 19 | 3 | 21 | 2023 | 2023 | R16
168150298329 | 169777298329 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-26 | 2022-10-26 | 2022-10-26 |  | 2022-12-06 | Overhead | R16 | 2022-11-14 | 1 |  | 14 | 17 | 30 | 2022 | 2022 | R16
165506289814 | 165842289814 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-24 | 2022-08-24 | 2022-08-24 | 2022-09-22 | 2022-12-16 | Overhead | R16 | 2022-09-22 | 1 |  | 22 | 62 | 83 | 2022 | 2022 | R16
167423305607 | 167000305607 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-12-08 | 2022-12-08 | 2023-01-11 |  | 2023-06-26 | Overhead | R16 |  | 1 | 25 |  |  | 143 | 2022 | 2023 | R16
163635191128 | 167119191128 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-14 | 2020-05-15 | 2020-05-15 |  | 2020-07-09 | Overhead | R16 | 2020-06-08 | 2 |  | 17 | 24 | 41 | 2020 | 2020 | R16
169943301936 | 165673301936 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-01 | 2022-12-01 | 2022-12-01 |  | 2023-08-22 | Overhead | R16 | 2023-05-17 | 1 |  | 120 | 70 | 189 | 2022 | 2023 | R16
164985328798 | 166175328798 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-08-10 | 2023-08-10 | 2023-08-18 | 2023-11-10 | 2023-11-27 | Underground | R16 | 2023-11-10 | 1 | 7 | 61 | 12 | 78 | 2023 | 2023 | R16
162454297682 | 168315297682 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-19 | 2022-10-20 | 2022-10-20 | 2023-01-11 | 2023-01-28 | Overhead | R16 | 2023-01-11 | 2 |  | 60 | 13 | 73 | 2022 | 2023 | R16
162221294354 | 165678294354 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-23 | 2022-08-24 | 2022-09-21 |  | 2022-12-07 | Overhead | R16 | 2022-11-01 | 2 | 21 | 30 | 27 | 77 | 2022 | 2022 | R16
168980307241 | 160137307241 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-29 | 2022-11-22 | 2023-01-25 |  | 2023-06-27 | Overhead | R16 |  | 83 | 47 |  |  | 238 | 2022 | 2023 | R16
163820293543 | 160491293543 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-09 | 2022-09-12 | 2022-09-12 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 2 |  | 84 |  | 85 | 2022 | 2023 | R16
163741190940 | 165305190940 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-04 | 2020-05-13 | 2020-05-13 |  | 2020-08-20 | Overhead | R16 | 2020-06-24 | 8 |  | 31 | 42 | 79 | 2020 | 2020 | R16
163892190025 | 165424190025 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-04 | 2020-05-04 | 2020-05-04 |  | 2020-08-20 | Overhead | R16 | 2020-06-24 | 1 |  | 38 | 42 | 79 | 2020 | 2020 | R16
167349297421 | 163268297421 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2022-09-23 | 2022-09-23 | 2022-10-18 | 2022-11-17 | 2022-12-02 | Underground | R16 | 2022-11-17 | 1 | 18 | 23 | 12 | 51 | 2022 | 2022 | R16
163927288401 | 164147288401 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-07-01 | 2022-07-26 | 2022-08-09 |  | 2023-08-16 | Underground | R16 |  | 18 | 11 |  |  | 294 | 2022 | 2023 | R16
167725302069 | 161704302069 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-07 | 2022-11-07 | 2022-12-01 |  | 2023-08-02 | Underground | R16 | 2023-03-28 | 1 | 19 | 84 | 92 | 193 | 2022 | 2023 | R16
163936190350 | 165944190350 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-07 | 2020-05-07 | 2020-05-07 |  | 2020-07-09 | Overhead | R16 | 2020-05-28 | 1 |  | 16 | 31 | 46 | 2020 | 2020 | R16
164791292450 | 167896292450 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-02 | 2022-09-02 | 2022-09-02 | 2023-11-09 | 2023-11-09 | Underground | R16 | 2023-11-09 | 1 |  | 310 |  | 310 | 2022 | 2023 | R16
168116287804 | 161283287804 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-03 | 2022-08-03 | 2022-08-03 |  | 2022-09-29 | Overhead | R16 | 2022-09-08 | 1 |  | 27 | 16 | 42 | 2022 | 2022 | R16
164124191066 | 164176191066 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-28 | 2020-04-28 | 2020-05-14 |  | 2020-07-10 | Underground | R16 | 2020-06-12 | 1 | 13 | 22 | 21 | 54 | 2020 | 2020 | R16
164131193831 | 161615193831 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-10 | 2020-06-10 | 2020-06-10 |  | 2022-06-01 | Overhead | R16 | 2021-03-30 | 1 |  | 210 | 307 | 516 | 2020 | 2022 | R16
161301290173 | 162859290173 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-10 | 2022-08-10 | 2022-08-26 |  | 2023-01-10 | Underground | R16 | 2022-11-09 | 1 | 13 | 54 | 45 | 110 | 2022 | 2023 | R16
163200330465 | 167620330465 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-17 | 2023-08-23 | 2023-08-23 | 2023-11-03 | 2023-11-13 | Overhead | R16 | 2023-11-03 | 5 |  | 53 | 7 | 63 | 2023 | 2023 | R16
169232289473 | 164689289473 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-18 | 2022-08-18 | 2022-08-18 | 2023-02-14 | 2023-05-02 | Overhead | R16 | 2023-02-14 | 1 |  | 129 | 56 | 184 | 2022 | 2023 | R16
160464335173 | 165994335173 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-27 | 2023-10-10 | 2023-10-10 | 2023-10-17 | 2023-11-20 | Overhead | R16 | 2023-10-17 | 10 |  | 6 | 25 | 39 | 2023 | 2023 | R16
165846288710 | 163278288710 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-11 | 2022-08-11 | 2022-08-11 | 2022-10-14 | 2022-10-17 | Overhead | R16 | 2022-10-14 | 1 |  | 47 | 2 | 48 | 2022 | 2022 | R16
164726297967 | 168512297967 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-20 | 2022-10-20 | 2022-10-24 | 2022-11-06 | 2022-11-09 | Overhead | R16 | 2022-11-06 | 1 | 3 | 10 | 3 | 15 | 2022 | 2022 | R16
168235297549 | 167957297549 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-18 | 2022-10-19 | 2022-10-20 |  | 2022-12-06 | Underground | R16 | 2022-11-07 | 2 | 2 | 13 | 22 | 36 | 2022 | 2022 | R16
169569295030 | 160941295030 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-12 | 2022-09-27 | 2022-09-27 | 2023-07-02 | 2023-07-05 | Overhead | R16 | 2023-07-02 | 12 |  | 199 | 3 | 213 | 2022 | 2023 | R16
164279191070 | 167300191070 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-14 | 2020-05-14 | 2020-05-14 |  | 2020-12-29 | Overhead | R16 | 2020-09-24 | 1 |  | 96 | 69 | 164 | 2020 | 2020 | R16
169994299649 | 164780299649 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-09-30 | 2022-11-07 | 2022-11-07 | 2023-02-12 | 2023-02-15 | Underground | R16 | 2023-02-12 | 27 |  | 70 | 3 | 99 | 2022 | 2023 | R16
166795299008 | 167580299008 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-10-17 | 2022-10-17 | 2022-11-01 |  | 2023-06-13 | Underground | R16 | 2023-02-13 | 1 | 12 | 75 | 87 | 172 | 2022 | 2023 | R16
161203298444 | 168568298444 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-10-20 | 2022-10-21 | 2022-10-27 | 2023-10-24 | 2023-11-30 | Underground | R16 | 2023-10-24 | 2 | 5 | 259 | 28 | 291 | 2022 | 2023 | R16
161387310982 | 164507310982 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-30 | 2022-09-30 | 2023-02-28 | 2023-04-27 | 2023-05-18 | Underground | R16 | 2023-04-27 | 1 | 108 | 43 | 16 | 165 | 2022 | 2023 | R16
161063299005 | 161933299005 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-16 | 2022-10-25 | 2022-11-01 |  | 2023-08-17 | Underground | R16 |  | 28 | 6 |  |  | 240 | 2022 | 2023 | R16
164378191593 | 164394191593 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-29 | 2020-04-29 | 2020-05-19 |  | 2020-07-13 | Underground | R16 | 2020-06-15 | 1 | 15 | 20 | 21 | 54 | 2020 | 2020 | R16
165489301092 | 163471301092 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-15 | 2022-11-18 | 2022-11-18 |  | 2023-04-10 | Overhead | R16 | 2023-01-30 | 4 |  | 52 | 51 | 105 | 2022 | 2023 | R16
164450190750 | 166534190750 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-11 | 2020-05-11 | 2020-05-11 |  | 2020-07-09 | Overhead | R16 | 2020-06-01 | 1 |  | 16 | 29 | 44 | 2020 | 2020 | R16
163053299204 | 160834299204 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-01 | 2022-11-01 | 2022-11-02 | 2022-11-30 | 2022-12-01 | Overhead | R16 | 2022-11-30 | 1 | 2 | 21 | 2 | 23 | 2022 | 2022 | R16
165038301428 | 164659301428 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-23 | 2022-11-23 | 2022-11-23 |  | 2023-01-13 | Overhead | R16 | 2023-01-11 | 1 |  | 36 | 3 | 38 | 2022 | 2023 | R16
163463290135 | 165567290135 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-23 | 2022-08-23 | 2022-08-24 | 2022-10-10 | 2022-10-13 | Underground | R16 | 2022-10-10 | 1 | 2 | 34 | 4 | 38 | 2022 | 2022 | R16
164505190443 | 165807190443 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-06 | 2020-05-08 | 2020-05-08 |  | 2020-07-09 | Overhead | R16 | 2020-06-09 | 3 |  | 23 | 23 | 47 | 2020 | 2020 | R16
169669302880 | 163985302880 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-18 | 2022-11-18 | 2022-12-09 | 2022-12-09 | 2023-04-01 | Overhead | R16 | 2022-12-09 | 1 | 16 |  | 81 | 96 | 2022 | 2023 | R16
163002293533 | 160520293533 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-09 | 2022-09-12 | 2022-09-12 |  | 2023-02-27 | Overhead | R16 | 2022-12-16 | 2 |  | 70 | 52 | 122 | 2022 | 2023 | R16
165042325474 | 168252325474 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-19 | 2022-10-19 | 2023-07-19 | 2023-08-31 | 2023-09-01 | Underground | R16 | 2023-08-31 | 1 | 196 | 32 | 2 | 228 | 2022 | 2023 | R16
164608206364 | 167435206364 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-13 | 2020-07-13 | 2020-10-06 |  | 2021-01-22 | Overhead | R16 | 2020-10-15 | 1 | 62 | 8 | 72 | 140 | 2020 | 2021 | R16
166131302534 | 166735302534 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-07 | 2022-12-07 | 2022-12-07 | 2023-01-12 | 2023-01-17 | Overhead | R16 | 2023-01-12 | 1 |  | 27 | 4 | 30 | 2022 | 2023 | R16
164671194088 | 161823194088 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-11 | 2020-06-11 | 2020-06-11 |  | 2020-08-28 | Overhead | R16 | 2020-06-29 | 1 |  | 13 | 45 | 57 | 2020 | 2020 | R16
162821339567 | 168121339567 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-10-09 | 2023-10-09 | 2023-11-13 | 2023-11-28 | 2023-12-11 | Underground | R16 | 2023-11-28 | 1 | 26 | 12 | 10 | 46 | 2023 | 2023 | R16
167876331881 | 169732331881 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-23 | 2023-09-06 | 2023-09-06 | 2023-09-20 | 2023-11-06 | Overhead | R16 | 2023-09-20 | 11 |  | 11 | 34 | 54 | 2023 | 2023 | R16
164742190393 | 165333190393 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-04 | 2020-05-07 | 2020-05-07 |  | 2022-05-17 | Overhead | R16 | 2020-06-05 | 4 |  | 22 | 508 | 532 | 2020 | 2022 | R16
164758191558 | 167709191558 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-19 | 2020-05-19 | 2020-05-19 |  | 2020-08-28 | Overhead | R16 | 2020-06-30 | 1 |  | 31 | 44 | 74 | 2020 | 2020 | R16
162323294647 | 163983294647 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-16 | 2022-08-16 | 2022-09-23 |  | 2023-03-31 | Underground | R16 | 2023-03-22 | 1 | 29 | 129 | 8 | 164 | 2022 | 2023 | R16
162131309895 | 164311309895 | CUSTOMER UPGRADE IN SERVICE | UG SVC CONVERSION | Commercial | 2022-11-21 | 2022-11-22 | 2023-02-21 |  | 2023-07-05 | Underground | R16 |  | 2 | 66 |  |  | 163 | 2022 | 2023 | R16
169286301586 | 164830301586 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-27 | 2022-11-28 | 2022-11-28 | 2023-01-08 | 2023-01-11 | Overhead | R16 | 2023-01-08 | 1 |  | 30 | 3 | 33 | 2022 | 2023 | R16
166857290708 | 164167290708 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2022-08-16 | 2022-08-16 | 2022-08-31 | 2022-10-03 | 2022-10-12 | Underground | R16 | 2022-10-03 | 1 | 12 | 24 | 8 | 42 | 2022 | 2022 | R16
162226325785 | 161520325785 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-17 | 2023-07-20 | 2023-07-20 | 2023-08-16 | 2023-08-25 | Overhead | R16 | 2023-08-16 | 4 |  | 20 | 8 | 30 | 2023 | 2023 | R16
164743302503 | 166398302503 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-06 | 2022-12-06 | 2022-12-06 | 2023-02-07 | 2023-02-08 | Overhead | R16 | 2023-02-07 | 1 |  | 46 | 2 | 47 | 2022 | 2023 | R16
166600299378 | 162747299378 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2022-08-10 | 2022-08-10 | 2022-11-04 | 2023-07-28 | 2023-08-21 | Underground | R16 | 2023-07-28 | 1 | 63 | 191 | 17 | 269 | 2022 | 2023 | R16
166876300773 | 167628300773 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-17 | 2022-10-17 | 2022-11-17 |  | 2023-03-01 | Underground | R16 | 2023-02-27 | 1 | 24 | 73 | 3 | 98 | 2022 | 2023 | R16
165655289333 | 164358289333 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-17 | 2022-08-17 | 2022-08-17 | 2022-10-07 | 2022-12-06 | Overhead | R16 | 2022-10-07 | 1 |  | 38 | 43 | 80 | 2022 | 2022 | R16
162051325882 | 161798325882 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2023-07-19 | 2023-07-19 | 2023-07-21 | 2023-08-03 | 2023-08-07 | Overhead | R16 | 2023-08-03 | 1 | 3 | 10 | 3 | 14 | 2023 | 2023 | R16
166074305082 | 167163305082 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-13 | 2022-10-13 | 2023-01-30 | 2023-02-07 | 2023-04-01 | Underground | R16 | 2023-02-07 | 1 | 78 | 7 | 39 | 122 | 2022 | 2023 | R16
162368301018 | 164084301018 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-11-18 | 2022-11-18 | 2022-11-18 | 2023-07-06 | 2023-07-25 | Underground | R16 | 2023-07-06 | 1 |  | 165 | 14 | 178 | 2022 | 2023 | R16
163116296881 | 166677296881 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-11 | 2022-10-12 | 2022-10-12 |  | 2022-12-04 | Overhead | R16 | 2022-11-21 | 2 |  | 29 | 10 | 39 | 2022 | 2022 | R16
164947191260 | 165695191260 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-05-06 | 2020-05-06 | 2020-05-15 |  | 2022-09-22 | Underground | R16 | 2022-08-01 | 1 | 8 | 577 | 39 | 622 | 2020 | 2022 | R16
165845326533 | 163298326533 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-27 | 2023-07-27 | 2023-07-27 | 2023-11-13 | 2023-11-13 | Underground | R16 | 2023-11-13 | 1 |  | 78 |  | 78 | 2023 | 2023 | R16
169063300744 | 163475300744 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-16 | 2022-11-16 | 2022-11-16 | 2023-02-24 | 2023-03-17 | Overhead | R16 | 2023-02-24 | 1 |  | 73 | 16 | 88 | 2022 | 2023 | R16
165065189553 | 165089189553 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2020-05-01 | 2020-05-01 | 2020-05-01 |  | 2021-04-07 | Overhead | R16 | 2020-12-02 | 1 |  | 154 | 91 | 244 | 2020 | 2021 | R16
162742334839 | 163328334839 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-12 | 2023-09-12 | 2023-10-06 | 2023-10-23 | 2023-11-08 | Overhead | R16 | 2023-10-23 | 1 | 19 | 12 | 13 | 42 | 2023 | 2023 | R16
169578296165 | 165740296165 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-06 | 2022-10-06 | 2022-10-06 | 2022-10-25 | 2022-10-26 | Overhead | R16 | 2022-10-25 | 1 |  | 14 | 2 | 15 | 2022 | 2022 | R16
161053328147 | 166624328147 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-12 | 2023-08-12 | 2023-08-12 | 2023-10-03 | 2023-10-26 | Overhead | R16 | 2023-10-03 | 0 |  | 37 | 18 | 54 | 2023 | 2023 | R16
169673299581 | 161006299581 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-02 | 2022-11-02 | 2022-11-04 |  | 2023-03-01 | Overhead | R16 | 2023-02-21 | 1 | 3 | 78 | 7 | 86 | 2022 | 2023 | R16
165192204321 | 169054204321 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-05-27 | 2020-08-14 | 2020-09-18 |  | 2021-04-16 | Underground | R16 |  | 58 | 26 |  |  | 233 | 2020 | 2021 | R16
165491331996 | 160993331996 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2023-08-30 | 2023-08-30 | 2023-09-08 | 2023-09-14 | 2023-10-02 | Overhead | R16 | 2023-09-14 | 1 | 8 | 5 | 13 | 24 | 2023 | 2023 | R16
169636294882 | 163174294882 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-09-23 | 2022-09-23 | 2022-09-26 | 2022-11-09 | 2022-12-06 | Overhead | R16 | 2022-11-09 | 1 | 2 | 33 | 20 | 53 | 2022 | 2022 | R16
163406290182 | 162621290182 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-09 | 2022-08-12 | 2022-08-24 |  | 2022-12-21 | Underground | R16 |  | 4 | 9 |  |  | 97 | 2022 | 2022 | R16
163240296885 | 166914296885 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-12 | 2022-10-12 | 2022-10-12 | 2023-01-05 | 2023-01-09 | Overhead | R16 | 2023-01-05 | 1 |  | 62 | 3 | 64 | 2022 | 2023 | R16
163788293542 | 160444293542 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-09 | 2022-09-12 | 2022-09-12 |  | 2023-01-22 | Overhead | R16 | 2023-01-17 | 2 |  | 92 | 4 | 96 | 2022 | 2023 | R16
169728300508 | 161797300508 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-07 | 2022-11-07 | 2022-11-14 | 2022-12-16 | 2023-02-17 | Underground | R16 | 2022-12-16 | 1 | 6 | 25 | 46 | 75 | 2022 | 2023 | R16
163358335280 | 168254335280 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-10-10 | 2023-10-10 | 2023-10-10 | 2023-12-19 | 2023-12-27 | Overhead | R16 | 2023-12-19 | 1 |  | 51 | 7 | 57 | 2023 | 2023 | R16
165317193523 | 160887193523 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-06-08 | 2020-06-08 | 2020-06-08 |  | 2020-08-14 | Overhead | R16 | 2020-06-22 | 1 |  | 11 | 40 | 50 | 2020 | 2020 | R16
161923296704 | 162418296704 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-20 | 2022-09-20 | 2022-10-11 | 2022-12-09 | 2022-12-12 | Underground | R16 | 2022-12-09 | 1 | 16 | 44 | 2 | 60 | 2022 | 2022 | R16
165318193656 | 168068193656 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-05-20 | 2020-06-08 | 2020-06-09 |  | 2020-10-06 | Underground | R16 |  | 14 | 2 |  |  | 100 | 2020 | 2020 | R16
165566295302 | 164266295302 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-28 | 2022-09-28 | 2022-09-28 | 2022-10-11 | 2022-10-25 | Overhead | R16 | 2022-10-11 | 1 |  | 10 | 11 | 20 | 2022 | 2022 | R16
164983294410 | 162974294410 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-22 | 2022-09-22 | 2022-09-22 |  | 2022-12-15 | Overhead | R16 | 2022-12-13 | 1 |  | 59 | 3 | 61 | 2022 | 2022 | R16
164274332965 | 164281332965 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-09-18 | 2023-09-18 | 2023-09-18 | 2023-10-05 | 2023-10-12 | Overhead | R16 | 2023-10-05 | 1 |  | 14 | 6 | 19 | 2023 | 2023 | R16
165235290097 | 163366290097 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-12 | 2022-08-24 | 2022-08-24 |  | 2022-09-27 | Overhead | R16 | 2022-09-26 | 9 |  | 24 | 2 | 33 | 2022 | 2022 | R16
162816330744 | 164760330744 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-03 | 2023-08-25 | 2023-08-25 | 2023-12-14 | 2023-12-20 | Overhead | R16 | 2023-12-14 | 17 |  | 80 | 5 | 100 | 2023 | 2023 | R16
169051293011 | 160014293011 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-09-07 | 2022-09-08 | 2022-09-08 | 2023-05-18 | 2023-05-22 | Underground | R16 | 2023-05-18 | 2 |  | 181 | 3 | 184 | 2022 | 2023 | R16
167502328443 | 166966328443 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-15 | 2023-08-15 | 2023-08-15 | 2023-10-05 | 2023-10-09 | Overhead | R16 | 2023-10-05 | 1 |  | 38 | 3 | 40 | 2023 | 2023 | R16
160115316919 | 160433316919 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-09 | 2022-10-25 | 2023-04-26 |  | 2023-06-05 | Overhead | R16 | 2023-05-24 | 33 | 132 | 21 | 9 | 192 | 2022 | 2023 | R16
162771331336 | 169297331336 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-08-21 | 2023-08-21 | 2023-08-31 | 2023-10-16 | 2023-11-07 | Underground | R16 | 2023-10-16 | 1 | 9 | 33 | 17 | 57 | 2023 | 2023 | R16
165635194557 | 162841194557 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-17 | 2020-06-17 | 2020-06-17 |  | 2021-06-14 | Overhead | R16 | 2020-09-29 | 1 |  | 75 | 185 | 259 | 2020 | 2021 | R16
163445289882 | 165044289882 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-19 | 2022-08-19 | 2022-08-22 | 2022-10-13 | 2023-02-10 | Overhead | R16 | 2022-10-13 | 1 | 2 | 39 | 87 | 126 | 2022 | 2023 | R16
164757292880 | 162187292880 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-08 |  | 2022-08-08 | 2022-12-15 | 2022-12-20 | Underground | R16 | 2022-12-15 |  |  | 94 | 4 | 97 | 2022 | 2022 | R16
165687193988 | 166158193988 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-08 | 2020-05-08 | 2020-06-11 |  | 2020-10-06 | Underground | R16 | 2020-07-23 | 1 | 25 | 31 | 54 | 108 | 2020 | 2020 | R16
162006302642 | 166687302642 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-11 | 2022-10-11 | 2022-12-07 | 2022-12-07 | 2023-03-24 | Underground | R16 | 2022-12-07 | 1 | 42 |  | 78 | 119 | 2022 | 2023 | R16
165744192802 | 160011192802 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-01 | 2020-06-01 | 2020-06-01 |  | 2020-07-14 | Overhead | R16 | 2020-06-18 | 1 |  | 14 | 19 | 32 | 2020 | 2020 | R16
163461307832 | 164042307832 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-16 | 2022-08-16 | 2023-02-01 |  | 2023-05-18 | Underground | R16 | 2023-03-21 | 1 | 122 | 35 | 43 | 198 | 2022 | 2023 | R16
165745195669 | 164199195669 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-24 | 2020-06-29 | 2020-06-29 |  | 2020-10-06 | Overhead | R16 | 2020-07-22 | 4 |  | 18 | 55 | 75 | 2020 | 2020 | R16
165092305370 | 166235305370 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-25 | 2022-08-25 | 2023-01-30 | 2023-01-09 | 2023-05-02 | Underground | R16 | 2023-01-09 | 1 | 113 |  | 82 | 179 | 2022 | 2023 | R16
161019331208 | 164971331208 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-08-03 | 2023-08-03 | 2023-08-30 | 2023-12-01 | 2023-12-04 | Underground | R16 | 2023-12-01 | 1 | 20 | 68 | 2 | 88 | 2023 | 2023 | R16
162408298537 | 164233298537 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-09-28 | 2022-09-28 | 2022-10-28 |  | 2023-02-17 | Underground | R16 | 2023-02-06 | 1 | 23 | 72 | 10 | 103 | 2022 | 2023 | R16
161310335260 | 164460335260 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-02 | 2023-08-02 | 2023-10-10 | 2023-10-10 | 2023-10-19 | Overhead | R16 | 2023-10-10 | 1 | 50 |  | 8 | 57 | 2023 | 2023 | R16
169935301912 | 165438301912 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-11-30 | 2022-11-30 | 2022-12-01 | 2023-03-02 | 2023-03-17 | Overhead | R16 | 2023-03-02 | 1 | 2 | 66 | 12 | 78 | 2022 | 2023 | R16
165941192801 | 166673192801 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-12 | 2020-05-12 | 2020-06-01 |  | 2020-08-14 | Underground | R16 | 2020-06-23 | 1 | 15 | 17 | 39 | 69 | 2020 | 2020 | R16
165949196045 | 164927196045 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-30 | 2020-06-30 | 2020-06-30 |  | 2020-10-06 | Overhead | R16 | 2020-08-07 | 1 |  | 29 | 43 | 71 | 2020 | 2020 | R16
165770302921 | 167227302921 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-09 | 2022-12-09 | 2022-12-09 |  | 2023-03-02 | Underground | R16 | 2022-12-21 | 1 |  | 9 | 52 | 60 | 2022 | 2023 | R16
166047192244 | 168874192244 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-26 | 2020-05-26 | 2020-05-26 |  | 2020-10-06 | Overhead | R16 | 2020-08-13 | 1 |  | 58 | 39 | 96 | 2020 | 2020 | R16
164247307408 | 162632307408 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-20 | 2022-09-20 | 2023-01-27 | 2023-06-07 | 2023-06-08 | Underground | R16 | 2023-06-07 | 1 | 94 | 94 | 2 | 188 | 2022 | 2023 | R16
168167298464 | 169651298464 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-26 | 2022-10-26 | 2022-10-27 | 2023-06-23 | 2023-06-28 | Overhead | R16 | 2023-06-23 | 1 | 2 | 172 | 4 | 176 | 2022 | 2023 | R16
162374304229 | 165953304229 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-02 | 2022-12-02 | 2023-01-30 | 2022-12-28 | 2023-03-31 | Underground | R16 | 2022-12-28 | 1 | 42 |  | 68 | 86 | 2022 | 2023 | R16
166065229963 | 169735229963 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2020-07-23 | 2021-02-25 | 2021-05-07 |  | 2022-04-25 | Overhead | R16 |  | 156 | 52 |  |  | 458 | 2020 | 2022 | R16
161990294803 | 163432294803 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-24 | 2022-09-24 | 2022-09-24 | 2022-11-16 | 2022-11-17 | Overhead | R16 | 2022-11-16 | 0 |  | 38 | 2 | 39 | 2022 | 2022 | R16
164381290213 | 165971290213 | GENERAL/OTHER | OH R16 RES NON RES OS | Residential | 2022-08-24 | 2022-08-24 | 2022-08-24 | 2022-12-15 | 2022-12-21 | Overhead | R16 | 2022-12-15 | 1 |  | 82 | 5 | 86 | 2022 | 2022 | R16
166140193115 | 160456193115 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-04 | 2020-06-04 | 2020-06-04 |  | 2020-08-14 | Overhead | R16 | 2020-06-22 | 1 |  | 13 | 40 | 52 | 2020 | 2020 | R16
162431294881 | 164246294881 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-16 | 2022-08-16 | 2022-09-26 |  | 2023-04-27 | Underground | R16 | 2023-02-02 | 1 | 30 | 94 | 61 | 183 | 2022 | 2023 | R16
166142190973 | 167125190973 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-14 | 2020-05-14 | 2020-05-14 |  | 2021-08-03 | Overhead | R16 | 2021-03-10 | 1 |  | 215 | 105 | 319 | 2020 | 2021 | R16
168011299027 | 169388299027 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-25 | 2022-10-25 | 2022-11-01 | 2022-11-07 | 2023-02-17 | Overhead | R16 | 2022-11-07 | 1 | 6 | 5 | 75 | 84 | 2022 | 2023 | R16
167042297998 | 169390297998 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-25 | 2022-10-25 | 2022-10-25 | 2023-02-08 | 2023-03-03 | Overhead | R16 | 2023-02-08 | 1 |  | 77 | 18 | 94 | 2022 | 2023 | R16
166168222540 | 162347222540 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-06-15 | 2020-11-13 | 2021-03-04 |  | 2021-11-08 | Underground | R16 |  | 110 | 80 |  |  | 366 | 2020 | 2021 | R16
164970287850 | 161558287850 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-08-04 | 2022-08-04 | 2022-08-04 | 2023-09-21 | 2023-10-20 | Overhead | R16 | 2023-09-21 | 1 |  | 296 | 22 | 317 | 2022 | 2023 | R16
163433308473 | 167273308473 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-13 | 2022-10-17 | 2023-02-07 |  | 2023-09-07 | Underground | R16 | 2023-05-02 | 3 | 82 | 61 | 93 | 236 | 2022 | 2023 | R16
167153292427 | 165030292427 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-19 | 2022-08-19 | 2022-09-02 | 2023-07-18 | 2023-07-19 | Overhead | R16 | 2023-07-18 | 1 | 11 | 228 | 2 | 239 | 2022 | 2023 | R16
164112301589 | 165254301589 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-11-29 | 2022-11-29 | 2022-11-29 |  | 2023-06-10 | Underground | R16 | 2022-12-15 | 1 |  | 13 | 127 | 139 | 2022 | 2023 | R16
167655290675 | 166270290675 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2022-08-25 | 2022-08-30 | 2022-08-30 | 2023-03-01 | 2023-03-02 | Overhead | R16 | 2023-03-01 | 4 |  | 132 | 2 | 136 | 2022 | 2023 | R16
166807293810 | 161251293810 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-11-11 | 2022-11-14 | Overhead | R16 | 2022-11-11 | 2 | 2 | 42 | 2 | 45 | 2022 | 2022 | R16
168569308637 | 167664308637 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2022-09-01 | 2022-12-06 | 2023-02-07 |  | 2023-09-13 | Overhead | R16 |  | 69 | 46 |  |  | 270 | 2022 | 2023 | R16
169716332272 | 167406332272 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-08-16 | 2023-08-16 | 2023-09-12 | 2023-11-14 | 2023-11-21 | Underground | R16 | 2023-11-14 | 1 | 20 | 46 | 6 | 70 | 2023 | 2023 | R16
163495332983 | 160240332983 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-25 | 2023-09-18 | 2023-09-18 | 2023-09-20 | 2023-10-31 | Overhead | R16 | 2023-09-20 | 17 |  | 3 | 30 | 48 | 2023 | 2023 | R16
162917295348 | 163462295348 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-26 | 2022-09-27 | 2022-09-29 | 2023-03-23 | 2023-04-18 | Overhead | R16 | 2023-03-23 | 2 | 3 | 126 | 19 | 147 | 2022 | 2023 | R16
165503294982 | 160337294982 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-09 | 2022-09-26 | 2022-09-26 |  | 2023-12-27 | Overhead | R16 | 2023-12-06 | 12 |  | 313 | 16 | 339 | 2022 | 2023 | R16
161692331420 | 161308331420 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-31 | 2023-08-31 | 2023-08-31 | 2023-10-12 | 2023-11-15 | Overhead | R16 | 2023-10-12 | 1 |  | 31 | 25 | 55 | 2023 | 2023 | R16
164132297400 | 165083297400 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-03 | 2022-10-17 | 2022-10-17 | 2023-06-06 | 2023-06-15 | Overhead | R16 | 2023-06-06 | 11 |  | 167 | 8 | 184 | 2022 | 2023 | R16
166430197547 | 168564197547 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-16 | 2020-07-16 | 2020-07-16 |  | 2021-11-10 | Overhead | R16 | 2020-11-12 | 1 |  | 86 | 260 | 345 | 2020 | 2021 | R16
168858287739 | 161635287739 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-04 | 2022-08-04 | 2022-08-04 |  | 2023-04-10 | Overhead | R16 | 2023-01-19 | 1 |  | 121 | 58 | 178 | 2022 | 2023 | R16
165641288004 | 161777288004 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-05 | 2022-08-05 | 2022-08-05 | 2022-09-13 | 2022-12-04 | Overhead | R16 | 2022-09-13 | 1 |  | 28 | 59 | 86 | 2022 | 2022 | R16
161157288106 | 169935288106 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2022-07-28 | 2022-07-29 | 2022-08-05 | 2022-08-11 | 2022-08-22 | Underground | R16 | 2022-08-11 | 2 | 6 | 5 | 8 | 18 | 2022 | 2022 | R16
167499298050 | 161774298050 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-15 | 2022-09-15 | 2022-10-24 | 2022-11-18 | 2023-02-17 | Underground | R16 | 2022-11-18 | 1 | 28 | 20 | 66 | 112 | 2022 | 2023 | R16
168224301654 | 169663301654 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2022-10-26 | 2022-10-26 | 2022-11-29 | 2023-03-09 | 2023-04-20 | Underground | R16 | 2023-03-09 | 1 | 25 | 73 | 31 | 127 | 2022 | 2023 | R16
165735297512 | 167726297512 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-17 | 2022-10-19 | 2022-10-19 |  | 2023-01-24 | Overhead | R16 | 2023-01-13 | 3 |  | 63 | 8 | 72 | 2022 | 2023 | R16
162029289861 | 162636289861 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-09 | 2022-08-09 | 2022-08-22 |  | 2022-09-30 | Overhead | R16 | 2022-09-08 | 1 | 10 | 14 | 17 | 39 | 2022 | 2022 | R16
163720302716 | 167168302716 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-09 | 2022-12-09 | 2022-12-09 | 2023-03-24 | 2023-05-18 | Overhead | R16 | 2023-03-24 | 1 |  | 76 | 40 | 115 | 2022 | 2023 | R16
167294299497 | 165096299497 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-20 | 2022-08-26 | 2022-11-04 |  | 2023-05-10 | Underground | R16 | 2023-02-15 | 5 | 51 | 74 | 61 | 188 | 2022 | 2023 | R16
167391298583 | 169102298583 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-24 | 2022-10-24 | 2022-10-28 |  | 2023-02-17 | Underground | R16 | 2022-12-13 | 1 | 5 | 33 | 49 | 85 | 2022 | 2023 | R16
164779287158 | 169909287158 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-28 | 2022-07-28 | 2022-07-28 | 2022-08-09 | 2022-08-29 | Overhead | R16 | 2022-08-09 | 1 |  | 9 | 15 | 23 | 2022 | 2022 | R16
169293300385 | 160581300385 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-31 | 2022-10-31 | 2022-11-14 |  | 2023-03-01 | Overhead | R16 | 2022-12-13 | 1 | 11 | 22 | 57 | 88 | 2022 | 2023 | R16
169875303493 | 165168303493 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-29 | 2022-12-16 | 2022-12-22 |  | 2023-05-04 | Overhead | R16 | 2023-02-28 | 14 | 5 | 49 | 48 | 113 | 2022 | 2023 | R16
164426301774 | 165705301774 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2022-10-05 | 2022-10-05 | 2022-11-30 | 2023-07-24 | 2023-08-16 | Underground | R16 | 2023-07-24 | 1 | 41 | 169 | 18 | 226 | 2022 | 2023 | R16
168876298512 | 169602298512 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-26 | 2022-10-26 | 2022-10-28 |  | 2023-05-02 | Underground | R16 | 2022-11-22 | 1 | 3 | 18 | 116 | 135 | 2022 | 2023 | R16
166510299304 | 162482299304 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-09-20 | 2022-09-21 | 2022-11-03 | 2023-06-08 | 2023-07-19 | Overhead | R16 | 2023-06-08 | 2 | 32 | 156 | 30 | 217 | 2022 | 2023 | R16
161754309016 | 162562309016 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-08-09 | 2023-02-10 | 2023-02-10 | 2023-05-18 | 2023-08-31 | Overhead | R16 | 2023-05-18 | 134 |  | 70 | 76 | 278 | 2022 | 2023 | R16
163868301040 | 163869301040 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-11-17 | 2022-11-17 | 2022-11-17 |  | 2023-03-02 | Overhead | R16 | 2022-12-21 | 1 |  | 25 | 52 | 76 | 2022 | 2023 | R16
164518296098 | 164235296098 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-17 | 2022-08-17 | 2022-10-05 |  | 2023-07-20 | Overhead | R16 | 2023-03-10 | 1 | 36 | 113 | 95 | 242 | 2022 | 2023 | R16
166113295936 | 165454295936 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-05 | 2022-10-05 | 2022-10-05 | 2023-05-16 | 2023-05-17 | Overhead | R16 | 2023-05-16 | 1 |  | 160 | 2 | 161 | 2022 | 2023 | R16
166655199554 | 166631199554 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-12 | 2020-05-12 | 2020-08-04 |  | 2022-09-15 | Underground | R16 | 2022-07-26 | 1 | 61 | 516 | 38 | 613 | 2020 | 2022 | R16
162340302040 | 165790302040 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-01 | 2022-12-01 | 2022-12-01 |  | 2023-08-18 | Overhead | R16 | 2023-04-21 | 1 |  | 102 | 86 | 187 | 2022 | 2023 | R16
164389299985 | 162012299985 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-16 | 2022-09-16 | 2022-11-09 |  | 2023-03-02 | Underground | R16 | 2022-12-16 | 1 | 39 | 28 | 55 | 120 | 2022 | 2023 | R16
160178287766 | 161313287766 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-03 | 2022-08-03 | 2022-08-03 | 2022-11-21 | 2022-12-06 | Overhead | R16 | 2022-11-21 | 1 |  | 79 | 12 | 90 | 2022 | 2022 | R16
169247288069 | 161838288069 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-05 | 2022-08-05 | 2022-08-05 |  | 2022-09-11 | Overhead | R16 | 2022-08-25 | 1 |  | 15 | 12 | 26 | 2022 | 2022 | R16
166725192242 | 168880192242 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-26 | 2020-05-26 | 2020-05-26 |  | 2020-10-06 | Overhead | R16 | 2020-08-05 | 1 |  | 52 | 45 | 96 | 2020 | 2020 | R16
162589308449 | 165759308449 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-01 | 2022-12-01 | 2023-02-06 | 2023-07-14 | 2023-07-17 | Underground | R16 | 2023-07-14 | 1 | 48 | 115 | 2 | 163 | 2022 | 2023 | R16
167797330272 | 169581330272 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-22 | 2023-08-23 | 2023-08-23 | 2023-09-27 | 2023-10-02 | Overhead | R16 | 2023-09-27 | 2 |  | 26 | 4 | 30 | 2023 | 2023 | R16
169156298971 | 160441298971 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-31 | 2022-10-31 | 2022-11-01 |  | 2023-04-24 | Underground | R16 | 2023-01-18 | 1 | 2 | 57 | 69 | 126 | 2022 | 2023 | R16
165396298250 | 164439298250 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-29 | 2022-09-29 | 2022-10-26 | 2023-12-07 | 2023-12-12 | Underground | R16 | 2023-12-07 | 1 | 20 | 292 | 4 | 314 | 2022 | 2023 | R16
166804193803 | 161244193803 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-06-09 | 2020-06-09 | 2020-06-09 |  | 2021-11-10 | Overhead | R16 | 2020-06-25 | 1 |  | 13 | 360 | 372 | 2020 | 2021 | R16
168496298918 | 160594298918 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2022-12-09 | 2023-01-18 | Overhead | R16 | 2022-12-09 | 1 |  | 29 | 29 | 57 | 2022 | 2023 | R16
160434304889 | 165858304889 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-07 | 2023-01-04 | 2023-01-30 | 2023-01-04 | 2023-06-08 | Overhead | R16 | 2023-01-04 | 64 | 19 |  | 112 | 175 | 2022 | 2023 | R16
166817220752 | 166930220752 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-13 | 2020-05-13 | 2021-02-17 |  | 2021-11-09 | Underground | R16 | 2021-04-28 | 1 | 201 | 51 | 140 | 390 | 2020 | 2021 | R16
167169316829 | 160678316829 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-01 | 2022-11-01 | 2023-04-24 |  | 2023-06-21 | Underground | R16 | 2023-06-02 | 1 | 125 | 30 | 14 | 167 | 2022 | 2023 | R16
165134334142 | 160939334142 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-30 | 2023-09-29 | 2023-09-29 | 2023-11-29 | 2023-12-05 | Overhead | R16 | 2023-11-29 | 23 |  | 44 | 5 | 70 | 2023 | 2023 | R16
166067296772 | 163171296772 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-22 | 2022-09-22 | 2022-10-12 |  | 2022-12-30 | Underground | R16 |  | 1 | 15 |  |  | 72 | 2022 | 2022 | R16
163673336136 | 169755336136 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-10-18 | 2023-10-18 | 2023-10-18 | 2023-11-02 | 2023-12-07 | Overhead | R16 | 2023-11-02 | 1 |  | 12 | 26 | 37 | 2023 | 2023 | R16
166869191651 | 167669191651 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-18 | 2020-05-18 | 2020-05-20 |  | 2020-07-14 | Overhead | R16 | 2020-06-17 | 1 | 3 | 21 | 20 | 42 | 2020 | 2020 | R16
165757290542 | 162189290542 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-08 | 2022-08-08 | 2022-08-29 | 2023-02-14 | 2023-02-15 | Underground | R16 | 2023-02-14 | 1 | 16 | 122 | 2 | 138 | 2022 | 2023 | R16
166886192657 | 169794192657 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-29 | 2020-05-29 | 2020-05-29 |  | 2020-07-13 | Overhead | R16 | 2020-06-15 | 1 |  | 12 | 21 | 32 | 2020 | 2020 | R16
165189290412 | 161720290412 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-04 | 2022-08-05 | 2022-08-26 |  | 2023-05-30 | Underground | R16 | 2023-02-10 | 2 | 16 | 121 | 78 | 214 | 2022 | 2023 | R16
166994192876 | 167198192876 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-15 | 2020-05-15 | 2020-06-03 |  | 2020-08-28 | Underground | R16 | 2020-06-30 | 1 | 14 | 20 | 44 | 76 | 2020 | 2020 | R16
161190302794 | 165459302794 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-30 | 2022-11-30 | 2022-12-09 |  | 2023-12-08 | Underground | R16 | 2023-10-10 | 1 | 8 | 218 | 44 | 268 | 2022 | 2023 | R16
167023194710 | 166933194710 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-13 | 2020-05-13 | 2020-06-19 |  | 2021-11-10 | Underground | R16 | 2020-09-17 | 1 | 28 | 65 | 300 | 391 | 2020 | 2021 | R16
168738307285 | 165082307285 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-28 | 2022-11-28 | 2023-01-26 | 2023-10-24 | 2023-11-01 | Underground | R16 | 2023-10-24 | 1 | 44 | 194 | 7 | 243 | 2022 | 2023 | R16
167089292834 | 169954292834 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2022-09-07 | 2022-09-07 | 2022-09-07 | 2023-09-28 | 2023-09-29 | Overhead | R16 | 2023-09-28 | 1 |  | 277 | 2 | 278 | 2022 | 2023 | R16
165360298770 | 168494298770 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-20 | 2022-10-20 | 2022-10-31 |  | 2023-04-04 | Underground | R16 | 2023-01-26 | 1 | 8 | 64 | 49 | 119 | 2022 | 2023 | R16
165330294779 | 162447294779 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-08-09 | 2022-08-09 | 2022-09-24 |  | 2023-01-23 | Underground | R16 | 2022-12-01 | 1 | 34 | 49 | 38 | 120 | 2022 | 2023 | R16
167059192913 | 160369192913 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-03 | 2020-06-03 | 2020-06-03 |  | 2020-08-28 | Overhead | R16 | 2020-07-06 | 1 |  | 24 | 40 | 63 | 2020 | 2020 | R16
160445290779 | 167449290779 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-31 | 2022-08-31 | 2022-08-31 |  | 2023-04-07 | Overhead | R16 | 2023-03-23 | 1 |  | 147 | 12 | 158 | 2022 | 2023 | R16
161961295844 | 162312295844 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-19 | 2022-09-19 | 2022-10-04 |  | 2022-12-11 | Underground | R16 | 2022-12-06 | 1 | 12 | 46 | 4 | 60 | 2022 | 2022 | R16
166586289657 | 161471289657 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-04 | 2022-08-04 | 2022-08-19 | 2022-10-17 | 2023-01-05 | Underground | R16 | 2022-10-17 | 1 | 12 | 42 | 59 | 111 | 2022 | 2023 | R16
162212305727 | 160181305727 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-07-29 | 2022-12-20 | 2023-01-25 | 2023-01-12 | 2023-04-24 | Overhead | R16 | 2023-01-12 | 103 | 27 |  | 73 | 192 | 2022 | 2023 | R16
165490289358 | 162641289358 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-09 | 2022-08-17 | 2022-08-17 |  | 2022-11-11 | Overhead | R16 | 2022-11-09 | 7 |  | 61 | 3 | 69 | 2022 | 2022 | R16
167124267044 | 165668267044 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-02-01 | 2022-02-01 | 2022-02-01 |  | 2022-03-15 | Overhead | R16 | 2022-02-16 | 1 |  | 12 | 20 | 31 | 2022 | 2022 | R16
163010293411 | 160309293411 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2022-09-09 | 2022-09-09 | 2022-09-12 | 2023-07-17 | 2023-05-31 | Underground | R16 | 2023-07-17 | 1 | 2 | 221 |  | 189 | 2022 | 2023 | R16
161374295319 | 164340295319 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-28 | 2022-09-28 | 2022-09-28 |  | 2023-10-16 | Underground | R16 | 2023-07-21 | 1 |  | 213 | 62 | 274 | 2022 | 2023 | R16
163514290823 | 166240290823 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-25 | 2022-08-30 | 2022-08-30 | 2022-12-21 | 2023-01-04 | Overhead | R16 | 2022-12-21 | 4 |  | 82 | 11 | 95 | 2022 | 2023 | R16
168101295079 | 166745295079 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-29 | 2022-09-27 | 2022-09-27 |  | 2023-04-27 | Underground | R16 | 2023-02-02 | 22 |  | 93 | 61 | 174 | 2022 | 2023 | R16
164219335632 | 169440335632 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2023-08-22 | 2023-09-25 | 2023-10-13 | 2023-11-28 | 2023-12-19 | Overhead | R16 | 2023-11-28 | 25 | 15 | 33 | 16 | 86 | 2023 | 2023 | R16
167228206177 | 167293206177 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-14 | 2020-05-14 | 2020-10-05 |  | 2021-04-20 | Underground | R16 | 2020-11-12 | 1 | 103 | 29 | 114 | 244 | 2020 | 2021 | R16
167132311443 | 164492311443 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2022-11-22 | 2023-03-03 | 2023-03-03 | 2023-07-27 | 2023-07-31 | Overhead | R16 | 2023-07-27 | 74 |  | 105 | 3 | 180 | 2022 | 2023 | R16
169886304031 | 165155304031 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-29 | 2022-12-22 | 2022-12-27 |  | 2023-08-14 | Overhead | R16 | 2023-03-24 | 18 | 4 | 64 | 102 | 185 | 2022 | 2023 | R16
167266207613 | 165871207613 | NON-RESIDENTIAL - LARGE RETAIL | R16 RESD AND NON RESD US | Commercial | 2020-07-01 | 2020-09-03 | 2020-10-20 |  | 2021-08-16 | Underground | R16 |  | 47 | 34 |  |  | 294 | 2020 | 2021 | R16
161755303214 | 166808303214 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-07 | 2022-12-07 | 2022-12-14 | 2022-12-15 | 2023-04-01 | Underground | R16 | 2022-12-15 | 1 | 6 | 2 | 77 | 83 | 2022 | 2023 | R16
167285194825 | 163241194825 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-18 | 2020-06-18 | 2020-06-18 |  | 2020-10-06 | Overhead | R16 | 2020-07-20 | 1 |  | 23 | 57 | 79 | 2020 | 2020 | R16
162972297627 | 163679297627 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-08-15 | 2022-08-16 | 2022-10-19 |  | 2023-11-10 | Underground | R16 |  | 2 | 47 |  |  | 325 | 2022 | 2023 | R16
167393193542 | 160879193542 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-08 | 2020-06-08 | 2020-06-08 |  | 2020-10-06 | Overhead | R16 | 2020-09-24 | 1 |  | 79 | 9 | 87 | 2020 | 2020 | R16
164852289171 | 160643289171 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-01 | 2022-08-16 | 2022-08-16 |  | 2023-02-03 | Overhead | R16 | 2022-12-01 | 12 |  | 78 | 47 | 135 | 2022 | 2023 | R16
162413335035 | 166431335035 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-29 | 2023-10-10 | 2023-10-10 | 2023-10-19 | 2023-10-26 | Overhead | R16 | 2023-10-19 | 8 |  | 8 | 6 | 20 | 2023 | 2023 | R16
167272335875 | 167361335875 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2023-10-04 | 2023-10-04 | 2023-10-17 | 2023-11-09 | 2023-11-10 | Underground | R16 | 2023-11-09 | 1 | 10 | 18 | 2 | 28 | 2023 | 2023 | R16
166206288982 | 163389288982 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-12 | 2022-08-15 | 2022-08-15 |  | 2022-09-30 | Overhead | R16 | 2022-09-29 | 2 |  | 34 | 2 | 36 | 2022 | 2022 | R16
167420192609 | 169561192609 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-28 | 2020-05-28 | 2020-05-28 |  | 2020-10-06 | Overhead | R16 | 2020-07-10 | 1 |  | 32 | 63 | 94 | 2020 | 2020 | R16
162954302798 | 169957302798 | SPECIFIC BUDGET PROJECTS | UG R16 RESD AND NON RESD UD | Commercial | 2022-09-07 | 2022-09-07 | 2022-12-09 |  | 2023-05-10 | Underground | R16 |  | 1 | 68 |  |  | 176 | 2022 | 2023 | R16
167441238228 | 169931238228 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-09 | 2021-07-09 | 2021-07-09 |  | 2021-09-13 | Underground | R16 | 2021-08-18 | 1 |  | 29 | 19 | 47 | 2021 | 2021 | R16
165100296806 | 166881296806 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-12 | 2022-10-12 | 2022-10-12 |  | 2023-01-10 | Overhead | R16 | 2023-01-03 | 1 |  | 60 | 6 | 65 | 2022 | 2023 | R16
164646298487 | 167698298487 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-10-18 | 2022-10-24 | 2022-10-27 |  | 2023-01-10 | Overhead | R16 | 2022-11-04 | 5 | 4 | 7 | 48 | 61 | 2022 | 2023 | R16
167491192608 | 169501192608 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-28 | 2020-05-28 | 2020-05-28 |  | 2020-07-10 | Overhead | R16 | 2020-06-11 | 1 |  | 11 | 22 | 32 | 2020 | 2020 | R16
167360339526 | 162624339526 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-08 | 2023-11-13 | 2023-11-13 | 2023-11-29 | 2023-11-30 | Overhead | R16 | 2023-11-29 | 47 |  | 13 | 2 | 60 | 2023 | 2023 | R16
167493337995 | 166264337995 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-09-28 | 2023-09-28 | 2023-10-31 | 2023-11-15 | 2023-11-30 | Underground | R16 | 2023-11-15 | 1 | 24 | 12 | 12 | 46 | 2023 | 2023 | R16
166112293809 | 161238293809 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-11-03 | 2022-12-02 | Overhead | R16 | 2022-11-03 | 2 | 2 | 36 | 22 | 59 | 2022 | 2022 | R16
167556197217 | 167579197217 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-13 | 2020-07-13 | 2020-07-15 |  | 2020-10-06 | Underground | R16 | 2020-08-21 | 1 | 3 | 28 | 33 | 62 | 2020 | 2020 | R16
165490294223 | 165816294223 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-24 | 2022-08-24 | 2022-09-19 | 2023-03-06 | 2023-03-09 | Underground | R16 | 2023-03-06 | 1 | 19 | 121 | 4 | 142 | 2022 | 2023 | R16
165965295211 | 164246295211 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-09-28 | 2022-09-28 | 2022-09-28 | 2023-04-12 | 2023-04-27 | Overhead | R16 | 2023-04-12 | 1 |  | 141 | 12 | 152 | 2022 | 2023 | R16
160742292984 | 160067292984 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-08 | 2022-09-08 | 2022-09-08 | 2022-11-15 | 2022-11-16 | Overhead | R16 | 2022-11-15 | 1 |  | 49 | 2 | 50 | 2022 | 2022 | R16
165259290654 | 166950290654 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-29 | 2022-08-30 | 2022-08-30 | 2022-11-22 | 2022-11-30 | Overhead | R16 | 2022-11-22 | 2 |  | 61 | 7 | 68 | 2022 | 2022 | R16
161436295780 | 162366295780 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-20 | 2022-10-03 | 2022-10-03 |  | 2023-08-14 | Overhead | R16 | 2023-03-21 | 10 |  | 122 | 105 | 235 | 2022 | 2023 | R16
167681198002 | 167700198002 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-18 | 2020-05-18 | 2020-07-21 |  | 2020-12-15 | Underground | R16 | 2020-09-10 | 1 | 47 | 38 | 69 | 152 | 2020 | 2020 | R16
165788296593 | 165961296593 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-07 | 2022-10-10 | 2022-10-10 |  | 2022-12-04 | Overhead | R16 | 2022-10-17 | 2 |  | 6 | 35 | 41 | 2022 | 2022 | R16
166444301684 | 164867301684 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-28 | 2022-11-28 | 2022-11-28 | 2023-02-16 | 2023-02-17 | Overhead | R16 | 2023-02-16 | 1 |  | 59 | 2 | 60 | 2022 | 2023 | R16
166996290057 | 163995290057 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-16 | 2022-08-24 | 2022-08-24 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 7 |  | 97 |  | 103 | 2022 | 2023 | R16
162856290085 | 165537290085 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-08-23 | 2022-08-23 | 2022-08-23 | 2023-03-30 | 2023-04-03 | Underground | R16 | 2023-03-30 | 1 |  | 158 | 3 | 160 | 2022 | 2023 | R16
164224333808 | 164260333808 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-09-18 | 2023-09-19 | 2023-09-27 | 2023-10-20 | 2023-11-29 | Overhead | R16 | 2023-10-20 | 2 | 7 | 18 | 29 | 53 | 2023 | 2023 | R16
166871300662 | 162546300662 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-10 | 2022-11-15 | 2022-11-15 | 2023-01-10 | 2023-07-28 | Overhead | R16 | 2023-01-10 | 4 |  | 41 | 144 | 187 | 2022 | 2023 | R16
162668332610 | 163695332610 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-14 | 2023-09-14 | 2023-09-14 | 2023-10-10 | 2023-10-13 | Overhead | R16 | 2023-10-10 | 1 |  | 19 | 4 | 22 | 2023 | 2023 | R16
160917307053 | 164884307053 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-11-28 | 2022-11-28 | 2023-01-25 |  | 2023-11-02 | Underground | R16 |  | 1 | 43 |  |  | 244 | 2022 | 2023 | R16
168817328127 | 166526328127 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-08-11 | 2023-08-11 | 2023-08-11 | 2023-11-14 | 2023-11-21 | Underground | R16 | 2023-11-14 | 1 |  | 68 | 6 | 73 | 2023 | 2023 | R16
163824333497 | 165450333497 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-10-02 | 2023-11-28 | Overhead | R16 | 2023-10-02 | 1 |  | 6 | 42 | 47 | 2023 | 2023 | R16
167900297949 | 163317297949 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-06-19 | 2020-09-01 | 2022-10-24 |  | 2023-08-14 | Underground | R16 |  | 53 | 560 |  |  | 822 | 2020 | 2023 | R16
161512289572 | 164971289572 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-19 | 2022-08-19 | 2022-08-19 | 2022-11-02 | 2022-12-01 | Overhead | R16 | 2022-11-02 | 1 |  | 54 | 22 | 75 | 2022 | 2022 | R16
162048289916 | 165373289916 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-22 | 2022-08-22 | 2022-08-22 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 1 |  | 99 |  | 99 | 2022 | 2023 | R16
169886294204 | 162253294204 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-09-19 | 2022-09-19 | 2022-09-19 |  | 2023-08-10 | Overhead | R16 | 2023-05-08 | 1 |  | 166 | 69 | 234 | 2022 | 2023 | R16
160053292896 | 169911292896 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-07 | 2022-09-07 | 2022-09-07 |  | 2022-12-15 | Overhead | R16 | 2022-10-20 | 1 |  | 32 | 41 | 72 | 2022 | 2022 | R16
167681331803 | 169968331803 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-08-24 | 2023-08-24 | 2023-09-06 | 2023-11-29 | 2023-12-19 | Underground | R16 | 2023-11-29 | 1 | 10 | 61 | 15 | 84 | 2023 | 2023 | R16
164537326374 | 163111326374 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-26 | 2023-07-26 | 2023-07-26 | 2023-11-13 | 2023-11-15 | Underground | R16 | 2023-11-13 | 1 |  | 79 | 3 | 81 | 2023 | 2023 | R16
162450289366 | 162494289366 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-09 | 2022-08-09 | 2022-08-17 | 2022-10-18 | 2023-01-05 | Underground | R16 | 2022-10-18 | 1 | 7 | 45 | 58 | 108 | 2022 | 2023 | R16
166360299225 | 167362299225 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-31 | 2022-08-31 | 2022-11-02 | 2023-01-30 | 2023-08-18 | Underground | R16 | 2023-01-30 | 1 | 46 | 64 | 145 | 253 | 2022 | 2023 | R16
166728289318 | 169691289318 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-27 | 2022-08-18 | 2022-08-18 |  | 2022-09-30 | Overhead | R16 | 2022-09-21 | 17 |  | 25 | 8 | 48 | 2022 | 2022 | R16
169865287973 | 161826287973 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-05 | 2022-08-05 | 2022-08-05 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 1 |  | 110 |  | 110 | 2022 | 2023 | R16
166838301034 | 164067301034 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-18 | 2022-11-18 | 2022-11-18 | 2023-02-07 | 2023-02-08 | Overhead | R16 | 2023-02-07 | 1 |  | 58 | 2 | 59 | 2022 | 2023 | R16
164588332712 | 163184332712 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-12 | 2023-09-15 | 2023-09-15 | 2023-10-18 | 2023-11-20 | Overhead | R16 | 2023-10-18 | 4 |  | 24 | 24 | 50 | 2023 | 2023 | R16
166035287215 | 160059287215 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-28 | 2022-07-28 | 2022-07-28 | 2022-08-02 | 2022-10-18 | Overhead | R16 | 2022-08-02 | 1 |  | 4 | 56 | 59 | 2022 | 2022 | R16
168871316849 | 164681316849 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-23 | 2022-12-01 | 2023-04-24 | 2023-07-27 | 2023-08-29 | Underground | R16 | 2023-07-27 | 7 | 103 | 69 | 24 | 200 | 2022 | 2023 | R16
160863292855 | 161255292855 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-08-03 | 2022-08-03 | 2022-09-07 | 2023-03-10 | 2023-03-14 | Underground | R16 | 2023-03-10 | 1 | 26 | 133 | 3 | 160 | 2022 | 2023 | R16
168106192947 | 169997192947 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-01 | 2020-06-01 | 2020-06-01 |  | 2020-08-28 | Overhead | R16 | 2020-06-18 | 1 |  | 14 | 52 | 65 | 2020 | 2020 | R16
161784305865 | 167034305865 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-08 | 2022-12-08 | 2023-01-25 | 2023-01-13 | 2023-06-05 | Underground | R16 | 2023-01-13 | 1 | 35 |  | 102 | 128 | 2022 | 2023 | R16
167634335245 | 163170335245 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-09-12 | 2023-10-10 | 2023-10-10 |  | 2023-12-29 | Underground | R16 | 2023-12-21 | 21 |  | 53 | 7 | 79 | 2023 | 2023 | R16
163699290186 | 165342290186 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-22 | 2022-08-24 | 2022-08-24 | 2022-10-12 | 2023-01-05 | Overhead | R16 | 2022-10-12 | 3 |  | 36 | 62 | 99 | 2022 | 2023 | R16
168157196891 | 161091196891 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-06-08 | 2020-06-08 | 2020-07-10 |  | 2021-08-12 | Underground | R16 | 2021-03-30 | 1 | 25 | 188 | 98 | 309 | 2020 | 2021 | R16
164117305833 | 167174305833 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-13 | 2022-10-13 | 2023-01-13 | 2023-01-27 | 2023-04-04 | Overhead | R16 | 2023-01-27 | 1 | 67 | 11 | 48 | 124 | 2022 | 2023 | R16
169186325834 | 162398325834 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-22 | 2023-07-22 | 2023-07-22 | 2023-07-25 | 2023-11-03 | Overhead | R16 | 2023-07-25 | 0 |  | 2 | 74 | 75 | 2023 | 2023 | R16
162766339484 | 162775339484 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2023-11-01 | 2023-11-01 | 2023-11-13 | 2023-11-13 | 2023-11-15 | Overhead | R16 | 2023-11-13 | 1 | 9 |  | 3 | 11 | 2023 | 2023 | R16
160105300926 | 161998300926 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-08 | 2022-11-17 | 2022-11-17 | 2023-08-24 | 2023-09-13 | Overhead | R16 | 2023-08-24 | 8 |  | 201 | 15 | 222 | 2022 | 2023 | R16
168277290794 | 166982290794 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-08-29 | 2022-08-29 | 2022-08-31 |  | 2022-10-26 | Overhead | R16 | 2022-09-12 | 1 | 3 | 9 | 33 | 43 | 2022 | 2022 | R16
168222226829 | 168242226829 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2021-01-20 | 2021-03-01 | 2021-04-14 |  | 2022-08-01 | Underground | R16 | 2022-08-01 | 29 | 33 | 339 |  | 399 | 2021 | 2022 | R16
164465295981 | 165165295981 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-04 | 2022-10-04 | 2022-10-04 |  | 2023-03-24 | Overhead | R16 | 2023-01-12 | 1 |  | 73 | 52 | 124 | 2022 | 2023 | R16
162619297393 | 164905297393 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2022-10-03 | 2022-10-04 | 2022-10-19 | 2023-05-14 | 2023-05-17 | Overhead | R16 | 2023-05-14 | 2 | 12 | 148 | 3 | 163 | 2022 | 2023 | R16
168342206571 | 160479206571 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-07-28 | 2020-10-07 | 2020-10-08 |  | 2021-08-16 | Underground | R16 |  | 52 | 2 |  |  | 275 | 2020 | 2021 | R16
168888294925 | 167071294925 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-30 | 2022-08-30 | 2022-09-26 | 2023-05-17 | 2023-05-18 | Underground | R16 | 2023-05-17 | 1 | 20 | 168 | 2 | 188 | 2022 | 2023 | R16
166352290107 | 165679290107 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-23 |  | 2022-08-24 | 2022-10-03 | 2023-01-05 | Overhead | R16 | 2022-10-03 |  |  | 29 | 69 | 98 | 2022 | 2023 | R16
161879325568 | 161754325568 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-19 | 2023-07-19 | 2023-07-19 | 2023-09-05 | 2023-09-07 | Overhead | R16 | 2023-09-05 | 1 |  | 35 | 3 | 37 | 2023 | 2023 | R16
168376198480 | 160230198480 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-27 | 2020-07-27 | 2020-07-27 |  | 2021-12-17 | Overhead | R16 | 2021-11-18 | 1 |  | 344 | 22 | 365 | 2020 | 2021 | R16
168417192941 | 169972192941 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-01 | 2020-06-01 | 2020-06-01 |  | 2023-06-27 | Overhead | R16 | 2023-02-08 | 1 |  | 703 | 100 | 802 | 2020 | 2023 | R16
161434296556 | 166606296556 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-11 | 2022-10-11 | 2022-10-11 |  | 2023-05-11 | Overhead | R16 | 2023-02-14 | 1 |  | 91 | 63 | 153 | 2022 | 2023 | R16
165543289829 | 164829289829 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-18 | 2022-08-18 | 2022-08-23 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 1 | 4 | 98 |  | 101 | 2022 | 2023 | R16
168462212481 | 169888212481 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2020-10-23 | 2020-12-01 | 2020-12-01 |  | 2021-05-05 | Underground | R16 |  | 28 |  |  |  | 139 | 2020 | 2021 | R16
164710299530 | 161466299530 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-04 | 2022-11-04 | 2022-11-04 |  | 2023-01-12 | Overhead | R16 |  | 1 |  |  |  | 50 | 2022 | 2023 | R16
164588301624 | 164965301624 | NON-RESIDENTIAL - LARGE OFFICE | R16 RESD AND NON RESD US | Residential | 2022-11-28 | 2022-11-28 | 2022-11-28 | 2022-12-15 | 2023-03-02 | Underground | R16 | 2022-12-15 | 1 |  | 14 | 56 | 69 | 2022 | 2023 | R16
162457295928 | 162887295928 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-09-21 | 2022-09-22 | 2022-10-04 |  | 2023-08-31 | Overhead | R16 |  | 2 | 9 |  |  | 247 | 2022 | 2023 | R16
163010293410 | 160212293410 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2022-09-08 | 2022-09-08 | 2022-09-12 | 2023-08-01 | 2023-04-05 | Underground | R16 | 2023-08-01 | 1 | 3 | 232 |  | 150 | 2022 | 2023 | R16
167118293116 | 160411293116 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2022-09-09 | 2022-09-09 | 2022-09-09 |  | 2023-07-14 | Overhead | R16 | 2023-06-27 | 1 |  | 208 | 14 | 221 | 2022 | 2023 | R16
162114332731 | 161386332731 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-08-31 | 2023-08-31 | 2023-09-15 | 2023-12-19 | 2023-12-20 | Underground | R16 | 2023-12-19 | 1 | 12 | 68 | 2 | 80 | 2023 | 2023 | R16
168625194699 | 169994194699 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-01 | 2020-06-01 | 2020-06-18 |  | 2020-12-15 | Underground | R16 | 2020-09-11 | 1 | 14 | 62 | 68 | 142 | 2020 | 2020 | R16
168549296069 | 165314296069 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-04 | 2022-10-05 | 2022-10-05 |  | 2023-02-11 | Overhead | R16 | 2022-12-07 | 2 |  | 46 | 48 | 94 | 2022 | 2023 | R16
168629195122 | 168545195122 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-22 | 2020-05-22 | 2020-06-23 |  | 2020-12-17 | Underground | R16 | 2020-09-17 | 1 | 23 | 63 | 66 | 150 | 2020 | 2020 | R16
168663204216 | 169266204216 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-28 | 2020-05-28 | 2020-09-18 |  | 2021-05-05 | Underground | R16 | 2021-02-12 | 1 | 82 | 106 | 59 | 245 | 2020 | 2021 | R16
160005325564 | 161708325564 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-07-19 | 2023-07-19 | 2023-07-19 | 2023-08-01 | 2023-10-25 | Overhead | R16 | 2023-08-01 | 1 |  | 10 | 62 | 71 | 2023 | 2023 | R16
165243289420 | 162688289420 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-10 | 2022-08-17 | 2022-08-17 | 2022-12-05 | 2023-02-23 | Overhead | R16 | 2022-12-05 | 6 |  | 79 | 59 | 142 | 2022 | 2023 | R16
169540330994 | 162474330994 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-22 | 2023-07-22 | 2023-08-28 | 2023-10-25 | 2023-10-26 | Underground | R16 | 2023-10-25 | 0 | 26 | 43 | 2 | 69 | 2023 | 2023 | R16
168540297743 | 160037297743 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-28 |  | 2022-10-21 |  | 2023-01-24 | Overhead | R16 | 2023-01-13 |  |  | 61 | 8 | 129 | 2022 | 2023 | R16
168813220048 | 161363220048 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-06-09 | 2020-06-09 | 2021-02-09 |  | 2021-08-23 | Underground | R16 | 2021-07-14 | 1 | 176 | 112 | 29 | 315 | 2020 | 2021 | R16
169435299116 | 160788299116 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-01 | 2022-11-02 | 2022-11-02 |  | 2023-02-11 | Underground | R16 | 2022-12-07 | 2 |  | 26 | 48 | 74 | 2022 | 2023 | R16
164906304734 | 161912304734 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-08 | 2022-11-08 | 2023-01-30 | 2023-05-08 | 2023-05-08 | Underground | R16 | 2023-05-08 | 1 | 60 | 71 |  | 130 | 2022 | 2023 | R16
168830196524 | 166145196524 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-06 | 2020-07-06 | 2020-07-06 |  | 2021-08-10 | Overhead | R16 | 2021-03-23 | 1 |  | 187 | 101 | 287 | 2020 | 2021 | R16
168841193870 | 161051193870 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-08 | 2020-06-10 | 2020-06-10 |  | 2021-07-01 | Overhead | R16 | 2020-10-28 | 3 |  | 101 | 177 | 279 | 2020 | 2021 | R16
164460295508 | 164830295508 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-30 |  | 2022-09-30 |  | 2023-01-28 | Overhead | R16 | 2023-01-18 |  |  | 79 | 8 | 86 | 2022 | 2023 | R16
163795328616 | 167661328616 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-17 | 2023-08-17 | 2023-08-17 | 2023-11-06 | 2023-11-16 | Overhead | R16 | 2023-11-06 | 1 |  | 58 | 9 | 66 | 2023 | 2023 | R16
168981304260 | 165493304260 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-30 | 2022-11-30 | 2022-12-26 |  | 2023-04-19 | Underground | R16 |  | 1 | 19 |  |  | 101 | 2022 | 2023 | R16
160689331489 | 161531331489 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-09-01 | 2023-09-01 | 2023-09-01 | 2023-10-11 | 2023-10-18 | Underground | R16 | 2023-10-11 | 1 |  | 29 | 6 | 34 | 2023 | 2023 | R16
169315300920 | 163688300920 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-17 | 2022-11-17 | 2022-11-17 |  | 2023-02-17 | Overhead | R16 | 2022-12-29 | 1 |  | 31 | 37 | 67 | 2022 | 2023 | R16
161504326545 | 163033326545 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-26 | 2023-07-27 | 2023-07-27 | 2023-08-02 | 2023-11-02 | Overhead | R16 | 2023-08-02 | 2 |  | 5 | 67 | 72 | 2023 | 2023 | R16
167697298026 | 166410298026 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-25 | 2022-08-25 | 2022-10-24 |  | 2023-04-27 | Underground | R16 | 2023-01-18 | 1 | 43 | 63 | 72 | 176 | 2022 | 2023 | R16
167200293091 | 160347293091 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-09-09 | 2022-09-09 | 2022-09-09 | 2022-11-18 | 2022-11-30 | Overhead | R16 | 2022-11-18 | 1 |  | 51 | 9 | 59 | 2022 | 2022 | R16
169623303672 | 160813303672 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-01 | 2022-12-19 | 2022-12-19 | 2022-12-22 | 2023-07-20 | Underground | R16 | 2022-12-22 | 35 |  | 4 | 151 | 188 | 2022 | 2023 | R16
169991308245 | 162697308245 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-10 | 2022-11-13 | 2023-02-03 |  | 2023-07-31 | Underground | R16 | 2023-03-10 | 2 | 60 | 26 | 102 | 188 | 2022 | 2023 | R16
168288297980 | 168155297980 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-10-19 | 2022-10-19 | 2022-10-24 |  | 2023-06-26 | Underground | R16 | 2023-03-14 | 1 | 4 | 102 | 75 | 179 | 2022 | 2023 | R16
163351303982 | 164582303982 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-11-22 | 2022-12-02 | 2022-12-22 | 2023-06-08 | 2023-08-29 | Underground | R16 | 2023-06-08 | 9 | 15 | 121 | 59 | 201 | 2022 | 2023 | R16
169308301485 | 164587301485 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-23 | 2022-11-23 | 2022-11-23 | 2023-01-24 | 2023-01-25 | Overhead | R16 | 2023-01-24 | 1 |  | 45 | 2 | 46 | 2022 | 2023 | R16
163407331622 | 166725331622 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-08-14 | 2023-08-14 | 2023-09-01 | 2023-09-20 | 2023-09-29 | Underground | R16 | 2023-09-20 | 1 | 15 | 14 | 8 | 35 | 2023 | 2023 | R16
160394299922 | 161932299922 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-08 | 2022-11-08 | 2022-11-08 | 2023-06-06 | 2023-06-07 | Overhead | R16 | 2023-06-06 | 1 |  | 151 | 2 | 152 | 2022 | 2023 | R16
169247198506 | 167057198506 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-07-10 | 2020-07-10 | 2020-07-27 |  | 2021-11-05 | Overhead | R16 | 2021-04-09 | 1 | 12 | 185 | 151 | 346 | 2020 | 2021 | R16
169610296766 | 166903296766 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-12 | 2022-10-12 | 2022-10-12 | 2022-11-07 | 2022-11-08 | Overhead | R16 | 2022-11-07 | 1 |  | 19 | 2 | 20 | 2022 | 2022 | R16
165219332735 | 165568332735 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-08-08 | 2023-08-08 | 2023-09-15 | 2023-11-13 | 2023-11-14 | Underground | R16 | 2023-11-13 | 1 | 29 | 42 | 2 | 71 | 2023 | 2023 | R16
163449290380 | 166151290380 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-08-25 | 2022-08-25 | 2022-08-25 | 2022-08-26 | 2022-11-21 | Underground | R16 | 2022-08-26 | 1 |  | 2 | 62 | 63 | 2022 | 2022 | R16
169308196400 | 164738196400 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-26 | 2020-07-02 | 2020-07-02 |  | 2021-11-03 | Underground | R16 | 2021-06-18 | 5 |  | 252 | 99 | 354 | 2020 | 2021 | R16
160360326222 | 162657326222 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-24 | 2023-07-24 | 2023-07-24 | 2023-08-30 | 2023-09-07 | Overhead | R16 | 2023-08-30 | 1 |  | 28 | 7 | 34 | 2023 | 2023 | R16
169329199731 | 162306199731 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-06 | 2020-08-06 | 2020-08-06 |  | 2020-10-29 | Overhead | R16 | 2020-09-01 | 1 |  | 19 | 43 | 61 | 2020 | 2020 | R16
169257301226 | 160746301226 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-01 | 2022-11-21 | 2022-11-21 |  | 2023-06-09 | Overhead | R16 | 2023-02-28 | 15 |  | 72 | 74 | 159 | 2022 | 2023 | R16
169342285971 | 167310285971 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2022-07-18 | 2022-07-18 | 2022-07-18 |  | 2023-10-06 | Underground | R16 |  | 1 |  |  |  | 320 | 2022 | 2023 | R16
169295296079 | 161846296079 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-05 | 2022-08-05 | 2022-10-05 | 2022-10-13 | 2022-12-06 | Underground | R16 | 2022-10-13 | 1 | 44 | 7 | 39 | 88 | 2022 | 2022 | R16
169390196816 | 169372196816 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-28 | 2020-05-28 | 2020-07-10 |  | 2020-10-06 | Underground | R16 | 2020-07-29 | 1 | 32 | 14 | 50 | 94 | 2020 | 2020 | R16
169179289439 | 162361289439 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-08 | 2022-08-08 | 2022-08-18 |  | 2022-12-03 | Underground | R16 | 2022-10-10 | 1 | 9 | 38 | 40 | 85 | 2022 | 2022 | R16
169309290444 | 161091290444 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-08-02 | 2022-08-04 | 2022-08-26 | 2022-10-03 | 2022-10-05 | Underground | R16 | 2022-10-03 | 3 | 17 | 27 | 3 | 47 | 2022 | 2022 | R16
164225302290 | 165978302290 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2022-12-02 | 2022-12-05 | 2022-12-05 | 2022-12-15 | 2023-02-08 | Underground | R16 | 2022-12-15 | 2 |  | 9 | 40 | 49 | 2022 | 2023 | R16
163551330987 | 167564330987 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-08-17 | 2023-08-17 | 2023-08-28 | 2023-09-14 | 2023-09-21 | Underground | R16 | 2023-09-14 | 1 | 8 | 14 | 6 | 26 | 2023 | 2023 | R16
164321301362 | 164361301362 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-29 | 2022-09-29 | 2022-11-21 | 2023-05-26 | 2023-05-26 | Overhead | R16 | 2023-05-26 | 1 | 38 | 135 |  | 172 | 2022 | 2023 | R16
166714312393 | 168545312393 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2022-10-20 | 2022-11-30 | 2023-03-13 | 2023-07-24 | 2023-08-16 | Underground | R16 | 2023-07-24 | 30 | 74 | 96 | 18 | 215 | 2022 | 2023 | R16
169562196962 | 166943196962 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-09 | 2020-07-09 | 2020-07-09 |  | 2021-01-08 | Underground | R16 | 2020-09-28 | 1 |  | 58 | 75 | 132 | 2020 | 2021 | R16
162973299686 | 161706299686 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-07 | 2022-11-07 | 2022-11-07 | 2022-11-08 | 2023-07-25 | Underground | R16 | 2022-11-08 | 1 |  | 2 | 186 | 187 | 2022 | 2023 | R16
163054332130 | 165748332130 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-08-08 | 2023-08-08 | 2023-09-08 | 2023-09-12 | 2023-12-14 | Underground | R16 | 2023-09-12 | 1 | 24 | 3 | 68 | 93 | 2023 | 2023 | R16
160087291030 | 166911291030 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-29 | 2022-08-29 | 2022-09-01 |  | 2023-08-11 | Underground | R16 | 2023-07-13 | 1 | 4 | 226 | 22 | 250 | 2022 | 2023 | R16
169660194643 | 162643194643 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-17 | 2020-06-17 | 2020-06-17 |  | 2021-01-08 | Underground | R16 | 2020-10-06 | 1 |  | 80 | 69 | 148 | 2020 | 2021 | R16
161986300514 | 166582300514 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-11 | 2022-10-11 | 2022-11-15 | 2022-12-12 | 2023-01-04 | Underground | R16 | 2022-12-12 | 1 | 26 | 20 | 18 | 62 | 2022 | 2023 | R16
165686331414 | 161546331414 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-01 | 2023-09-01 | 2023-09-01 | 2023-11-13 | 2023-12-19 | Overhead | R16 | 2023-11-13 | 1 |  | 52 | 27 | 78 | 2023 | 2023 | R16
169625321350 | 168581321350 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-10-20 | 2022-10-20 | 2023-06-06 | 2023-07-11 | 2023-07-25 | Underground | R16 | 2023-07-11 | 1 | 164 | 26 | 11 | 199 | 2022 | 2023 | R16
169304307445 | 161759307445 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-11-07 | 2023-01-12 | 2023-01-27 | 2023-05-23 | 2023-10-24 | Underground | R16 | 2023-05-23 | 49 | 12 | 83 | 111 | 252 | 2022 | 2023 | R16
169685295035 | 163943295035 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-27 | 2022-09-27 | 2022-09-27 | 2023-06-16 | 2023-06-20 | Overhead | R16 | 2023-06-16 | 1 |  | 189 | 3 | 191 | 2022 | 2023 | R16
169680196059 | 163512196059 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-22 | 2020-06-22 | 2020-07-01 |  | 2020-12-15 | Underground | R16 | 2020-09-10 | 1 | 8 | 52 | 69 | 127 | 2020 | 2020 | R16
167627329974 | 169140329974 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-08-20 | 2023-08-20 | 2023-08-20 | 2023-09-25 | 2023-10-06 | Overhead | R16 | 2023-09-25 | 0 |  | 26 | 10 | 35 | 2023 | 2023 | R16
165363302787 | 164853302787 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Commercial | 2022-11-28 | 2022-12-02 | 2022-12-08 |  | 2023-09-27 | Underground | R16 |  | 5 | 5 |  |  | 218 | 2022 | 2023 | R16
160408294452 | 160533294452 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-09 | 2022-09-14 | 2022-09-21 | 2022-09-23 | 2022-09-26 | Underground | R16 | 2022-09-23 | 4 | 6 | 3 | 2 | 12 | 2022 | 2022 | R16
160431307137 | 163016307137 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-22 | 2023-01-25 | 2023-01-25 |  | 2023-06-26 | Overhead | R16 | 2023-02-22 | 90 |  | 21 | 89 | 198 | 2022 | 2023 | R16
162829330575 | 163819330575 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-31 | 2023-07-31 | 2023-08-25 | 2023-08-31 | 2023-09-21 | Underground | R16 | 2023-08-31 | 1 | 20 | 5 | 16 | 39 | 2023 | 2023 | R16
169760195329 | 164258195329 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-25 | 2020-06-25 | 2020-06-25 |  | 2020-10-06 | Overhead | R16 | 2020-07-06 | 1 |  | 8 | 67 | 74 | 2020 | 2020 | R16
160212298851 | 165201298851 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-21 | 2022-09-02 | 2022-10-31 | 2023-01-02 | 2023-01-05 | Underground | R16 | 2023-01-02 | 10 | 42 | 46 | 4 | 99 | 2022 | 2023 | R16
162633295682 | 164769295682 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-30 | 2022-10-02 | 2022-10-02 |  | 2022-12-11 | Overhead | R16 | 2022-12-06 | 1 |  | 47 | 4 | 51 | 2022 | 2022 | R16
161373331725 | 161688331725 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-05 | 2023-09-05 | 2023-09-05 | 2023-10-03 | 2023-10-04 | Overhead | R16 | 2023-10-03 | 1 |  | 21 | 2 | 22 | 2023 | 2023 | R16
163126296322 | 165040296322 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-03 | 2022-10-03 | 2022-10-07 |  | 2022-12-06 | Overhead | R16 | 2022-11-30 | 1 | 5 | 39 | 5 | 47 | 2022 | 2022 | R16
160827296562 | 165857296562 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-07 | 2022-10-10 | 2022-10-10 |  | 2022-11-16 | Overhead | R16 | 2022-11-14 | 2 |  | 26 | 3 | 29 | 2022 | 2022 | R16
166409302037 | 163657302037 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-11-17 | 2022-11-17 | 2022-12-02 | 2023-07-08 | 2023-10-06 | Underground | R16 | 2023-07-08 | 1 | 12 | 156 | 65 | 232 | 2022 | 2023 | R16
169401298947 | 160523298947 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-31 | 2022-11-01 | 2022-11-01 |  | 2023-01-24 | Overhead | R16 | 2023-01-13 | 2 |  | 54 | 8 | 62 | 2022 | 2023 | R16
169501300152 | 162629300152 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-10 | 2022-11-10 | 2022-11-10 | 2023-02-08 | 2023-02-28 | Overhead | R16 | 2023-02-08 | 1 |  | 65 | 15 | 79 | 2022 | 2023 | R16
166142296769 | 163086296769 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-22 | 2022-09-22 | 2022-10-12 | 2023-01-10 | 2023-01-11 | Underground | R16 | 2023-01-10 | 1 | 15 | 65 | 2 | 80 | 2022 | 2023 | R16
163142296301 | 165613296301 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-05 | 2022-10-06 | 2022-10-06 | 2022-11-06 | 2022-11-09 | Overhead | R16 | 2022-11-06 | 2 |  | 22 | 3 | 26 | 2022 | 2022 | R16
160735297191 | 165192297191 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2022-10-04 | 2022-10-14 | 2022-10-17 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 9 | 2 | 59 |  | 68 | 2022 | 2023 | R16
167648304252 | 163112304252 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-14 | 2022-11-14 | 2023-01-30 | 2023-02-10 | 2023-02-13 | Underground | R16 | 2023-02-10 | 1 | 56 | 10 | 2 | 66 | 2022 | 2023 | R16
160020195617 | 162367195617 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-16 | 2020-06-16 | 2020-06-29 |  | 2021-04-21 | Underground | R16 | 2021-01-19 | 1 | 10 | 147 | 67 | 222 | 2020 | 2021 | R16
166307293114 | 167512293114 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-31 | 2022-08-31 | 2022-09-09 | 2023-02-08 | 2023-02-28 | Underground | R16 | 2023-02-08 | 1 | 8 | 109 | 15 | 130 | 2022 | 2023 | R16
160840304410 | 166070304410 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-02 | 2022-12-02 | 2023-01-30 | 2022-12-30 | 2023-07-24 | Underground | R16 | 2022-12-30 | 1 | 42 |  | 147 | 167 | 2022 | 2023 | R16
160024195625 | 164766195625 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-29 | 2020-06-29 | 2020-06-29 |  | 2020-10-06 | Overhead | R16 | 2020-07-13 | 1 |  | 11 | 62 | 72 | 2020 | 2020 | R16
163153300137 | 164925300137 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-10-03 | 2022-10-24 | 2022-11-11 |  | 2023-07-07 | Underground | R16 |  | 16 | 15 |  |  | 200 | 2022 | 2023 | R16
160026229552 | 166086229552 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-23 | 2021-02-23 | 2021-05-05 |  | 2021-10-28 | Underground | R16 | 2021-07-29 | 1 | 52 | 62 | 66 | 178 | 2021 | 2021 | R16
161255337065 | 161374337065 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2023-10-27 | 2023-10-27 | 2023-10-27 | 2023-11-06 | 2023-12-08 | Overhead | R16 | 2023-11-06 | 1 |  | 7 | 25 | 31 | 2023 | 2023 | R16
168570297211 | 166325297211 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-25 | 2022-10-17 | 2022-10-17 |  | 2023-03-24 | Overhead | R16 | 2023-01-12 | 38 |  | 64 | 52 | 152 | 2022 | 2023 | R16
160136200337 | 160387200337 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-06-03 | 2020-07-24 | 2020-08-12 |  | 2021-04-29 | Underground | R16 |  | 38 | 14 |  |  | 237 | 2020 | 2021 | R16
169535313744 | 161758313744 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-05 | 2022-08-05 | 2023-03-27 |  | 2023-08-09 | Underground | R16 | 2023-07-19 | 1 | 167 | 83 | 16 | 264 | 2022 | 2023 | R16
160149195355 | 164528195355 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-26 | 2020-06-26 | 2020-06-26 |  | 2020-10-06 | Overhead | R16 | 2020-07-22 | 1 |  | 19 | 55 | 73 | 2020 | 2020 | R16
160214195001 | 163458195001 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-22 | 2020-06-22 | 2020-06-22 |  | 2022-10-19 | Overhead | R16 |  | 1 |  |  |  | 608 | 2020 | 2022 | R16
166184299418 | 161197299418 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2022-11-03 | 2022-11-03 | 2022-11-04 |  | 2023-12-01 | Overhead | R16 | 2023-10-17 | 1 | 2 | 248 | 34 | 282 | 2022 | 2023 | R16
163222297617 | 167807297617 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-10-18 | 2022-10-18 | 2022-10-20 |  | 2023-06-19 | Underground | R16 | 2023-03-07 | 1 | 3 | 99 | 75 | 175 | 2022 | 2023 | R16
167852336972 | 161254336972 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-10-26 | 2023-10-26 | 2023-10-26 | 2023-11-06 | 2023-11-09 | Overhead | R16 | 2023-11-06 | 1 |  | 8 | 4 | 11 | 2023 | 2023 | R16
169968332701 | 163688332701 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2023-09-14 | 2023-09-14 | 2023-09-14 | 2023-09-28 | 2023-10-03 | Underground | R16 | 2023-09-28 | 1 |  | 11 | 4 | 14 | 2023 | 2023 | R16
160244196255 | 165972196255 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-02 | 2020-07-02 | 2020-07-02 |  | 2021-07-01 | Overhead | R16 | 2020-08-13 | 1 |  | 31 | 231 | 261 | 2020 | 2021 | R16
160073301028 | 164502301028 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-08-17 | 2022-08-17 | 2022-11-18 | 2023-12-03 | 2023-12-06 | Overhead | R16 | 2023-12-03 | 1 | 68 | 271 | 3 | 341 | 2022 | 2023 | R16
164383293766 | 164891293766 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2022-08-19 | 2022-08-19 | 2022-09-14 |  | 2023-06-27 | Overhead | R16 |  | 1 | 19 |  |  | 223 | 2022 | 2023 | R16
162457297519 | 168225297519 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-19 | 2022-10-19 | 2022-10-19 | 2022-12-12 | 2022-12-13 | Overhead | R16 | 2022-12-12 | 1 |  | 39 | 2 | 40 | 2022 | 2022 | R16
160397328371 | 163991328371 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-31 | 2023-07-31 | 2023-08-15 | 2023-11-22 | 2023-11-29 | Underground | R16 | 2023-11-22 | 1 | 12 | 72 | 6 | 88 | 2023 | 2023 | R16
167686329122 | 167846329122 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-08-19 | 2023-08-19 | 2023-08-19 | 2023-08-29 | 2023-08-30 | Overhead | R16 | 2023-08-29 | 0 |  | 7 | 2 | 8 | 2023 | 2023 | R16
164732297979 | 166827297979 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-12 | 2022-10-12 | 2022-10-25 |  | 2023-02-01 | Underground | R16 | 2022-12-05 | 1 | 10 | 30 | 43 | 81 | 2022 | 2023 | R16
168827298762 | 160357298762 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-31 | 2022-10-31 | 2022-10-31 |  | 2023-02-11 | Overhead | R16 | 2022-12-07 | 1 |  | 28 | 48 | 75 | 2022 | 2023 | R16
166650296063 | 165277296063 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-05 |  | 2022-10-05 | 2022-12-20 | 2023-01-14 | Overhead | R16 | 2022-12-20 |  |  | 55 | 19 | 73 | 2022 | 2023 | R16
164609296137 | 165678296137 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-06 | 2022-10-06 | 2022-10-06 | 2023-01-18 | 2023-04-09 | Overhead | R16 | 2023-01-18 | 1 |  | 75 | 58 | 132 | 2022 | 2023 | R16
161049288166 | 162169288166 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-08 | 2022-08-08 | 2022-08-08 | 2022-08-24 | 2022-10-21 | Overhead | R16 | 2022-08-24 | 1 |  | 13 | 43 | 55 | 2022 | 2022 | R16
168028301736 | 160373301736 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-07-29 | 2022-07-29 | 2022-11-29 | 2022-12-11 | 2022-12-14 | Overhead | R16 | 2022-12-11 | 1 | 88 | 9 | 3 | 99 | 2022 | 2022 | R16
164987289949 | 165233289949 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-22 | 2022-08-22 | 2023-03-24 | 2023-03-31 | 2023-01-06 | Overhead | R16 | 2023-03-31 | 1 | 155 | 6 |  | 100 | 2022 | 2023 | R16
162021294512 | 162919294512 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-21 | 2022-09-21 | 2022-09-21 | 2022-10-05 | 2023-01-10 | Overhead | R16 | 2022-10-05 | 1 |  | 11 | 70 | 80 | 2022 | 2023 | R16
160506194586 | 162830194586 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-17 | 2020-06-17 | 2020-06-17 |  | 2020-10-06 | Overhead | R16 | 2020-08-06 | 1 |  | 37 | 44 | 80 | 2020 | 2020 | R16
169429302780 | 166989302780 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-08 | 2022-12-08 | 2022-12-08 |  | 2023-06-28 | Overhead | R16 | 2023-06-06 | 1 |  | 129 | 17 | 145 | 2022 | 2023 | R16
169197330775 | 160354330775 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-26 | 2023-08-26 | 2023-08-26 | 2023-09-29 | 2023-10-03 | Overhead | R16 | 2023-09-29 | 0 |  | 25 | 3 | 27 | 2023 | 2023 | R16
160573201855 | 164561201855 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-25 | 2020-07-06 | 2020-08-27 |  | 2021-04-14 | Underground | R16 | 2020-12-10 | 8 | 39 | 76 | 90 | 210 | 2020 | 2021 | R16
166164296774 | 163162296774 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-22 | 2022-09-22 | 2022-10-12 |  | 2022-11-28 | Underground | R16 |  | 1 | 15 |  |  | 48 | 2022 | 2022 | R16
160590202522 | 160581202522 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-04 | 2020-06-04 | 2020-09-01 |  | 2021-04-16 | Underground | R16 | 2020-12-30 | 1 | 64 | 87 | 78 | 227 | 2020 | 2021 | R16
166215290978 | 167632290978 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-01 | 2022-09-01 | 2022-09-01 | 2022-12-22 | 2022-12-30 | Overhead | R16 | 2022-12-22 | 1 |  | 81 | 7 | 87 | 2022 | 2022 | R16
164571308900 | 167935308900 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-02 | 2022-09-02 | 2023-02-09 |  | 2023-09-05 | Underground | R16 | 2023-05-09 | 1 | 115 | 64 | 86 | 263 | 2022 | 2023 | R16
160631212564 | 166138212564 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-06 | 2020-11-17 | 2020-12-02 |  | 2021-08-16 | Overhead | R16 |  | 97 | 12 |  |  | 291 | 2020 | 2021 | R16
163905289612 | 163322289612 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-11 | 2022-08-11 | 2022-08-19 | 2022-10-26 | 2023-02-17 | Underground | R16 | 2022-10-26 | 1 | 7 | 49 | 83 | 137 | 2022 | 2023 | R16
165390293754 | 161496293754 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-15 | 2022-09-15 | 2022-09-15 | 2022-10-12 | 2023-05-18 | Overhead | R16 | 2022-10-12 | 1 |  | 20 | 157 | 176 | 2022 | 2023 | R16
160917336589 | 160430336589 | NON-RESIDENTIAL - MISCELLANEOUS | UG ELEC MISC SVC US | Commercial | 2022-10-31 | 2022-10-31 | 2023-10-23 |  | 2023-12-11 | Underground | R16 |  | 1 | 256 |  |  | 291 | 2022 | 2023 | R16
160631212570 | 166213212570 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-06 | 2020-11-17 | 2020-12-02 |  | 2021-11-05 | Overhead | R16 |  | 97 | 12 |  |  | 350 | 2020 | 2021 | R16
166904296159 | 165669296159 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-06 | 2022-10-06 | 2022-10-06 |  | 2023-02-11 | Overhead | R16 | 2022-12-19 | 1 |  | 53 | 40 | 92 | 2022 | 2023 | R16
166321296241 | 163490296241 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-09-25 | 2022-10-06 | 2022-10-06 |  | 2023-10-04 | Overhead | R16 | 2023-07-05 | 9 |  | 195 | 66 | 268 | 2022 | 2023 | R16
165623295033 | 160691295033 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-01 | 2022-08-01 | 2022-09-27 |  | 2023-01-10 | Underground | R16 | 2022-11-08 | 1 | 42 | 31 | 46 | 117 | 2022 | 2023 | R16
160631212575 | 161116212575 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-28 | 2020-11-17 | 2020-12-02 |  | 2021-11-13 | Overhead | R16 |  | 15 | 12 |  |  | 273 | 2020 | 2021 | R16
162690293051 | 169531293051 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-04 | 2022-09-08 | 2022-09-08 | 2022-12-05 | 2022-12-06 | Overhead | R16 | 2022-12-05 | 4 |  | 63 | 2 | 67 | 2022 | 2022 | R16
163151296549 | 165778296549 | NON-RESIDENTIAL - SMALL RETAIL | OH R16 RES NON RES OS | Commercial | 2022-10-07 | 2022-10-07 | 2022-10-10 | 2023-02-16 | 2023-03-06 | Overhead | R16 | 2023-02-16 | 1 | 2 | 94 | 13 | 107 | 2022 | 2023 | R16
161016299796 | 161842299796 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-08 | 2022-11-08 | 2022-11-09 |  | 2023-03-01 | Overhead | R16 | 2022-12-13 | 1 | 2 | 25 | 57 | 82 | 2022 | 2023 | R16
160988288790 | 163235288790 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-11 | 2022-08-11 | 2022-08-11 | 2022-11-02 | 2022-11-18 | Overhead | R16 | 2022-11-02 | 1 |  | 60 | 13 | 72 | 2022 | 2022 | R16
163705299765 | 161610299765 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-06 | 2022-11-06 | 2022-11-07 | 2022-11-13 | 2022-11-17 | Overhead | R16 | 2022-11-13 | 0 | 1 | 5 | 4 | 9 | 2022 | 2022 | R16
169764287480 | 160570287480 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-01 | 2022-08-01 | 2022-08-01 | 2022-08-31 | 2022-09-01 | Overhead | R16 | 2022-08-31 | 1 |  | 23 | 2 | 24 | 2022 | 2022 | R16
160757212452 | 168166212452 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-02 | 2020-12-02 | 2020-12-02 |  | 2021-04-16 | Overhead | R16 | 2021-01-06 | 1 |  | 26 | 73 | 98 | 2020 | 2021 | R16
164238330510 | 169989330510 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-24 | 2023-08-24 | 2023-08-24 | 2023-12-06 | 2023-12-12 | Overhead | R16 | 2023-12-06 | 1 |  | 75 | 5 | 79 | 2023 | 2023 | R16
160627300435 | 165290300435 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2022-10-04 | 2022-10-04 | 2022-11-14 | 2022-11-18 | 2023-01-03 | Underground | R16 | 2022-11-18 | 1 | 30 | 5 | 33 | 66 | 2022 | 2023 | R16
162826290032 | 165672290032 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-23 | 2022-08-23 | 2022-08-23 |  | 2023-02-10 | Overhead | R16 | 2023-02-08 | 1 |  | 122 | 3 | 124 | 2022 | 2023 | R16
162602295680 | 164881295680 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-02 | 2022-10-02 | 2022-10-02 |  | 2022-11-16 | Overhead | R16 | 2022-11-15 | 0 |  | 32 | 2 | 33 | 2022 | 2022 | R16
168319294676 | 165173294676 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-22 | 2022-08-22 | 2023-02-15 | 2022-12-16 | 2023-02-06 | Underground | R16 | 2022-12-16 | 1 | 128 |  | 37 | 121 | 2022 | 2023 | R16
166510299307 | 162483299307 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-09-20 | 2022-09-26 | 2022-11-03 | 2023-06-08 | 2023-07-19 | Overhead | R16 | 2023-06-08 | 5 | 29 | 156 | 30 | 217 | 2022 | 2023 | R16
162765334509 | 167088334509 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-10-03 | 2023-10-03 | 2023-10-04 | 2023-12-15 | 2023-12-28 | Underground | R16 | 2023-12-15 | 1 | 2 | 53 | 10 | 63 | 2023 | 2023 | R16
163050333720 | 165578333720 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-10-09 | 2023-11-15 | Overhead | R16 | 2023-10-09 | 1 |  | 11 | 28 | 38 | 2023 | 2023 | R16
160925197477 | 167247197477 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-10 | 2020-07-16 | 2020-07-16 |  | 2020-11-06 | Overhead | R16 | 2020-07-29 | 5 |  | 10 | 73 | 86 | 2020 | 2020 | R16
160952195501 | 164733195501 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-26 | 2020-06-26 | 2020-06-26 |  | 2020-10-06 | Overhead | R16 | 2020-07-23 | 1 |  | 20 | 54 | 73 | 2020 | 2020 | R16
160173299871 | 162161299871 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-11-08 | 2022-11-08 | 2022-11-08 | 2022-11-10 | 2022-11-17 | Overhead | R16 | 2022-11-10 | 1 |  | 3 | 6 | 8 | 2022 | 2022 | R16
166228290884 | 167418290884 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-31 | 2022-08-31 | 2022-08-31 | 2022-09-14 | 2022-09-30 | Overhead | R16 | 2022-09-14 | 1 |  | 11 | 13 | 23 | 2022 | 2022 | R16
161041195269 | 164181195269 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-24 | 2020-06-24 | 2020-06-24 |  | 2020-10-06 | Overhead | R16 | 2020-08-03 | 1 |  | 29 | 47 | 75 | 2020 | 2020 | R16
161044195270 | 163896195270 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-24 | 2020-06-24 | 2020-06-24 |  | 2020-11-02 | Underground | R16 | 2020-09-03 | 1 |  | 52 | 43 | 94 | 2020 | 2020 | R16
165505298895 | 160417298895 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-31 | 2022-10-31 | 2022-10-31 |  | 2022-12-15 | Overhead | R16 | 2022-12-06 | 1 |  | 27 | 8 | 34 | 2022 | 2022 | R16
160464309992 | 161491309992 | NON-RESIDENTIAL - LARGE OFFICE | R16 RESD AND NON RESD US | Commercial | 2022-08-04 | 2022-08-04 | 2023-02-21 |  | 2023-08-17 | Underground | R16 |  | 1 | 144 |  |  | 271 | 2022 | 2023 | R16
161049195311 | 163895195311 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-24 | 2020-06-24 | 2020-06-25 |  | 2020-08-28 | Overhead | R16 | 2020-07-07 | 1 | 2 | 9 | 39 | 48 | 2020 | 2020 | R16
160012305369 | 166886305369 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-29 | 2022-08-29 | 2023-01-30 | 2023-01-09 | 2023-08-28 | Underground | R16 | 2023-01-09 | 1 | 111 |  | 166 | 261 | 2022 | 2023 | R16
162527305514 | 165026305514 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-03 | 2022-10-03 | 2023-01-25 | 2023-01-11 | 2023-05-11 | Underground | R16 | 2023-01-11 | 1 | 83 |  | 87 | 159 | 2022 | 2023 | R16
162795304190 | 163155304190 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2022-11-15 | 2022-11-15 | 2023-01-30 | 2023-05-04 | 2023-09-19 | Underground | R16 | 2023-05-04 | 1 | 55 | 69 | 99 | 221 | 2022 | 2023 | R16
161182196053 | 165527196053 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-01 | 2020-07-01 | 2020-07-01 |  | 2021-04-21 | Overhead | R16 | 2021-01-27 | 1 |  | 151 | 61 | 211 | 2020 | 2021 | R16
166318296921 | 165048296921 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-20 | 2022-10-12 | 2022-10-12 |  | 2023-03-20 | Underground | R16 | 2023-01-06 | 38 |  | 63 | 52 | 151 | 2022 | 2023 | R16
161967294567 | 162505294567 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-20 | 2022-09-22 | 2022-09-22 | 2023-01-11 | 2023-01-12 | Overhead | R16 | 2023-01-11 | 3 |  | 80 | 2 | 83 | 2022 | 2023 | R16
161187195267 | 164074195267 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-24 | 2020-06-24 | 2020-06-24 |  | 2020-10-06 | Overhead | R16 | 2020-07-15 | 1 |  | 16 | 60 | 75 | 2020 | 2020 | R16
162582306409 | 166475306409 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-06 | 2022-12-06 | 2023-01-30 | 2023-08-10 | 2023-08-15 | Underground | R16 | 2023-08-10 | 1 | 40 | 139 | 4 | 181 | 2022 | 2023 | R16
167375292337 | 164540292337 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-08-17 | 2022-08-17 | 2022-09-02 | 2022-09-12 | 2022-09-15 | Overhead | R16 | 2022-09-12 | 1 | 13 | 7 | 4 | 22 | 2022 | 2022 | R16
161331198205 | 169729198205 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-23 | 2020-07-23 | 2020-07-23 |  | 2021-04-23 | Overhead | R16 | 2021-02-04 | 1 |  | 141 | 57 | 197 | 2020 | 2021 | R16
163125329979 | 166575329979 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-08-11 | 2023-08-21 | 2023-08-21 | 2023-10-30 | 2023-11-07 | Underground | R16 | 2023-10-30 | 7 |  | 51 | 7 | 63 | 2023 | 2023 | R16
163524297543 | 165437297543 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-05 | 2022-10-05 | 2022-10-19 | 2022-11-17 | 2022-12-22 | Underground | R16 | 2022-11-17 | 1 | 11 | 22 | 26 | 57 | 2022 | 2022 | R16
160970333384 | 165157333384 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-22 | 2023-09-22 | 2023-09-22 |  | 2023-11-08 | Overhead | R16 | 2023-10-13 | 1 |  | 16 | 19 | 34 | 2023 | 2023 | R16
161366209324 | 166815209324 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2020-07-09 | 2020-11-02 | 2020-11-02 |  | 2021-11-05 | Underground | R16 | 2021-04-09 | 83 |  | 115 | 151 | 347 | 2020 | 2021 | R16
165187321254 | 166264321254 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-05 | 2023-06-05 | 2023-06-05 | 2023-12-01 | 2023-12-05 | Underground | R16 | 2023-12-01 | 131 |  | 130 | 3 | 262 | 2022 | 2023 | R16
161185330019 | 165201330019 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-05 | 2023-08-20 | 2023-08-20 | 2023-08-21 | 2023-10-03 | Overhead | R16 | 2023-08-21 | 10 |  | 1 | 32 | 42 | 2023 | 2023 | R16
162527299127 | 168820299127 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-10-21 | 2022-10-21 | 2022-11-01 |  | 2023-02-23 | Overhead | R16 | 2022-12-09 | 1 | 8 | 29 | 55 | 90 | 2022 | 2023 | R16
166527289160 | 169744289160 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-27 | 2022-08-15 | 2022-08-15 |  | 2022-11-17 | Overhead | R16 | 2022-11-15 | 14 |  | 67 | 3 | 82 | 2022 | 2022 | R16
163666297182 | 166913297182 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-12 | 2022-10-12 | 2022-10-17 | 2022-10-27 | 2023-02-17 | Overhead | R16 | 2022-10-27 | 1 | 4 | 9 | 82 | 93 | 2022 | 2023 | R16
160953335650 | 166464335650 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-29 | 2023-10-13 | 2023-10-13 | 2023-10-19 | 2023-11-03 | Overhead | R16 | 2023-10-19 | 11 |  | 5 | 12 | 26 | 2023 | 2023 | R16
162065326155 | 162789326155 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-25 | 2023-07-25 | 2023-07-25 | 2023-09-20 | 2023-10-02 | Underground | R16 | 2023-09-20 | 1 |  | 42 | 9 | 50 | 2023 | 2023 | R16
161440195701 | 164940195701 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-29 | 2020-06-29 | 2020-06-29 |  | 2020-10-06 | Overhead | R16 | 2020-07-30 | 1 |  | 24 | 49 | 72 | 2020 | 2020 | R16
163150332474 | 161584332474 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2023-09-01 | 2023-09-01 | 2023-09-13 | 2023-10-10 | 2023-10-24 | Underground | R16 | 2023-10-10 | 1 | 9 | 20 | 11 | 38 | 2023 | 2023 | R16
161135302650 | 166940302650 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-08 | 2022-12-08 | 2022-12-08 | 2023-08-01 | 2023-08-02 | Overhead | R16 | 2023-08-01 | 1 |  | 169 | 2 | 170 | 2022 | 2023 | R16
163679330672 | 169173330672 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-21 | 2023-08-21 | 2023-08-25 | 2023-11-15 | 2023-11-21 | Overhead | R16 | 2023-11-15 | 1 | 5 | 59 | 5 | 67 | 2023 | 2023 | R16
161525195103 | 163669195103 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-23 | 2020-06-23 | 2020-06-23 |  | 2020-12-15 | Overhead | R16 | 2020-09-15 | 1 |  | 61 | 66 | 126 | 2020 | 2020 | R16
160829303046 | 162696303046 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-10 | 2022-11-13 | 2022-12-16 |  | 2023-03-24 | Underground | R16 | 2023-01-11 | 2 | 25 | 19 | 53 | 97 | 2022 | 2023 | R16
163546296390 | 166040296390 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-07 | 2022-10-07 | 2022-10-07 |  | 2023-05-18 | Overhead | R16 | 2023-03-06 | 1 |  | 107 | 54 | 160 | 2022 | 2023 | R16
166805298567 | 169016298567 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-24 | 2022-10-28 | 2022-10-28 | 2023-07-11 | 2023-10-23 | Overhead | R16 | 2023-07-11 | 5 |  | 183 | 75 | 261 | 2022 | 2023 | R16
161560196014 | 165437196014 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-30 | 2020-06-30 | 2020-06-30 |  | 2020-12-18 | Overhead | R16 | 2020-09-17 | 1 |  | 58 | 67 | 124 | 2020 | 2020 | R16
169039328436 | 167213328436 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-16 | 2023-08-16 | 2023-08-16 | 2023-09-12 | 2023-10-23 | Overhead | R16 | 2023-09-12 | 1 |  | 20 | 30 | 49 | 2023 | 2023 | R16
161724295687 | 164951295687 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-03 | 2022-10-03 | 2022-10-03 | 2022-11-29 | 2022-11-30 | Overhead | R16 | 2022-11-29 | 1 |  | 42 | 2 | 43 | 2022 | 2022 | R16
163221334050 | 166543334050 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-29 | 2023-09-29 | 2023-09-29 | 2023-11-14 | 2023-12-08 | Overhead | R16 | 2023-11-14 | 1 |  | 33 | 19 | 51 | 2023 | 2023 | R16
169721328331 | 166920328331 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-14 | 2023-08-14 | 2023-08-14 | 2023-12-06 | 2023-12-12 | Overhead | R16 | 2023-12-06 | 1 |  | 83 | 5 | 87 | 2023 | 2023 | R16
161620207689 | 168737207689 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-19 | 2020-10-19 | 2020-10-19 |  | 2022-11-11 | Overhead | R16 | 2022-11-10 | 1 |  | 539 | 2 | 540 | 2020 | 2022 | R16
165242287293 | 160299287293 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-29 | 2022-07-29 | 2022-07-29 | 2023-04-29 | 2023-08-18 | Overhead | R16 | 2023-04-29 | 1 |  | 196 | 80 | 276 | 2022 | 2023 | R16
161684200780 | 164155200780 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-17 | 2020-08-17 | 2020-08-17 |  | 2021-04-14 | Overhead | R16 | 2020-10-29 | 1 |  | 54 | 120 | 173 | 2020 | 2021 | R16
161402336412 | 167305336412 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-10-05 | 2023-10-20 | 2023-10-20 | 2023-11-22 | 2023-11-28 | Overhead | R16 | 2023-11-22 | 12 |  | 24 | 5 | 39 | 2023 | 2023 | R16
163065297297 | 164415297297 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-29 | 2022-09-29 | 2022-10-17 | 2022-11-16 | 2022-11-17 | Underground | R16 | 2022-11-16 | 1 | 13 | 23 | 2 | 36 | 2022 | 2022 | R16
165125328192 | 166740328192 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-14 | 2023-08-14 | 2023-08-14 | 2023-08-31 | 2023-09-14 | Overhead | R16 | 2023-08-31 | 1 |  | 14 | 11 | 24 | 2023 | 2023 | R16
169188326830 | 162559326830 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-24 | 2023-07-24 | 2023-07-31 | 2023-11-23 | 2023-11-27 | Underground | R16 | 2023-11-23 | 1 | 6 | 84 | 3 | 91 | 2023 | 2023 | R16
162867333317 | 164997333317 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2023-09-21 | 2023-09-21 | 2023-09-21 | 2023-09-22 | 2023-09-28 | Overhead | R16 | 2023-09-22 | 1 |  | 2 | 5 | 6 | 2023 | 2023 | R16
163110294572 | 163115294572 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-22 | 2022-09-22 | 2022-09-22 | 2022-11-18 | 2022-11-18 | Overhead | R16 | 2022-11-18 | 1 |  | 42 |  | 42 | 2022 | 2022 | R16
161925202767 | 164256202767 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-18 | 2020-08-18 | 2020-09-04 |  | 2021-01-07 | Underground | R16 | 2020-11-03 | 1 | 14 | 43 | 48 | 103 | 2020 | 2021 | R16
161929198028 | 169315198028 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-21 | 2020-07-21 | 2020-07-21 |  | 2021-04-29 | Overhead | R16 | 2021-02-11 | 1 |  | 148 | 56 | 203 | 2020 | 2021 | R16
167111301857 | 161158301857 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-14 | 2022-09-14 | 2022-11-30 | 2023-05-23 | 2023-05-24 | Underground | R16 | 2023-05-23 | 1 | 56 | 125 | 2 | 181 | 2022 | 2023 | R16
164615296689 | 166398296689 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-11 | 2022-10-11 | 2022-10-11 | 2023-07-13 | 2023-07-26 | Overhead | R16 | 2023-07-13 | 1 |  | 198 | 10 | 207 | 2022 | 2023 | R16
160846294856 | 162241294856 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-19 | 2022-09-26 | 2022-09-26 |  | 2023-06-16 | Overhead | R16 | 2023-01-20 | 6 |  | 85 | 106 | 195 | 2022 | 2023 | R16
161995212383 | 163792212383 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-06-23 | 2020-06-23 | 2020-12-01 |  | 2021-11-08 | Underground | R16 | 2021-04-20 | 1 | 116 | 101 | 145 | 360 | 2020 | 2021 | R16
166991287422 | 160408287422 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-07-29 | 2022-07-29 | 2022-07-29 |  | 2022-10-21 | Overhead | R16 | 2022-09-07 | 1 |  | 29 | 33 | 61 | 2022 | 2022 | R16
161997201672 | 162834201672 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-17 | 2020-06-17 | 2020-08-25 |  | 2021-04-29 | Underground | R16 | 2021-02-09 | 1 | 50 | 121 | 58 | 227 | 2020 | 2021 | R16
162012197294 | 165014197294 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-30 | 2020-06-30 | 2020-07-14 |  | 2021-02-17 | Underground | R16 | 2020-10-19 | 1 | 11 | 70 | 88 | 167 | 2020 | 2021 | R16
164395293721 | 160479293721 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-09 | 2022-09-13 | 2022-09-13 |  | 2022-10-18 | Overhead | R16 | 2022-10-17 | 3 |  | 25 | 2 | 28 | 2022 | 2022 | R16
161427326520 | 163210326520 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-26 | 2023-07-26 | 2023-07-26 |  | 2023-08-16 | Overhead | R16 | 2023-07-27 | 1 |  | 2 | 15 | 16 | 2023 | 2023 | R16
162043194744 | 163148194744 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-18 | 2020-06-18 | 2020-06-18 |  | 2020-08-28 | Overhead | R16 | 2020-07-06 | 1 |  | 13 | 40 | 52 | 2020 | 2020 | R16
160121296686 | 166533296686 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-11 | 2022-10-11 | 2022-10-11 |  | 2023-05-11 | Overhead | R16 | 2023-02-17 | 1 |  | 94 | 60 | 153 | 2022 | 2023 | R16
165945303267 | 166992303267 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-08 | 2022-12-14 | 2023-01-30 | 2023-02-21 | 2023-03-04 | Overhead | R16 | 2023-02-21 | 5 | 34 | 17 | 9 | 62 | 2022 | 2023 | R16
168369307974 | 162172307974 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-08 | 2022-11-08 | 2023-02-02 | 2023-05-04 | 2023-08-18 | Underground | R16 | 2023-05-04 | 1 | 63 | 66 | 77 | 204 | 2022 | 2023 | R16
162240196218 | 164316196218 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-25 | 2020-06-26 | 2020-07-02 |  | 2021-07-24 | Underground | R16 | 2020-11-09 | 2 | 5 | 93 | 185 | 282 | 2020 | 2021 | R16
169625320958 | 168439320958 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-10-20 | 2022-10-20 | 2023-06-02 | 2023-07-11 | 2023-08-16 | Underground | R16 | 2023-07-11 | 1 | 162 | 28 | 27 | 215 | 2022 | 2023 | R16
162601289555 | 164564289555 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-17 | 2022-08-19 | 2022-08-19 | 2022-10-12 | 2023-01-05 | Overhead | R16 | 2022-10-12 | 3 |  | 39 | 62 | 102 | 2022 | 2023 | R16
168746302645 | 160029302645 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-27 | 2022-10-27 | 2022-12-07 |  | 2023-06-14 | Underground | R16 | 2023-04-27 | 1 | 30 | 102 | 35 | 165 | 2022 | 2023 | R16
162263196409 | 165857196409 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-02 | 2020-07-06 | 2020-07-06 |  | 2020-10-06 | Overhead | R16 | 2020-07-27 | 3 |  | 16 | 52 | 69 | 2020 | 2020 | R16
166993294622 | 163055294622 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-22 | 2022-09-22 | 2022-09-22 |  | 2022-11-11 | Overhead | R16 | 2022-11-09 | 1 |  | 35 | 3 | 37 | 2022 | 2022 | R16
162264196543 | 166144196543 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-06 | 2020-07-06 | 2020-07-06 |  | 2021-08-12 | Overhead | R16 | 2021-07-06 | 1 |  | 262 | 28 | 289 | 2020 | 2021 | R16
166114298447 | 169013298447 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-24 | 2022-10-27 | 2022-10-27 |  | 2023-02-03 | Overhead | R16 | 2022-11-28 | 4 |  | 23 | 50 | 75 | 2022 | 2023 | R16
161744290928 | 164634290928 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-18 | 2022-08-18 | 2022-09-01 |  | 2022-10-27 | Underground | R16 | 2022-10-25 | 1 | 11 | 39 | 3 | 51 | 2022 | 2022 | R16
163461330518 | 160108330518 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-24 | 2023-08-24 | 2023-08-24 | 2023-11-08 | 2023-11-15 | Overhead | R16 | 2023-11-08 | 1 |  | 55 | 6 | 60 | 2023 | 2023 | R16
160921300034 | 160285300034 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-10-28 | 2022-11-09 | 2022-11-09 |  | 2023-04-12 | Underground | R16 | 2023-01-20 | 9 |  | 53 | 59 | 119 | 2022 | 2023 | R16
164428297014 | 167437297014 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-10-14 | 2022-10-14 | 2022-10-14 | 2023-01-09 | 2023-01-12 | Overhead | R16 | 2023-01-09 | 1 |  | 62 | 4 | 65 | 2022 | 2023 | R16
164428297014 | 167437297014 | AGRICULTURAL | R16 RESD AND NON RESD US | Residential | 2022-10-14 | 2022-10-14 | 2022-10-14 | 2023-01-09 | 2023-01-12 | Underground | R16 | 2023-01-09 | 1 |  | 62 | 4 | 65 | 2022 | 2023 | R16
162363196277 | 165924196277 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-02 | 2020-07-02 | 2020-07-02 |  | 2020-10-06 | Underground | R16 | 2020-08-26 | 1 |  | 40 | 30 | 69 | 2020 | 2020 | R16
161878318682 | 162672318682 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-20 | 2023-02-09 | 2023-05-10 | 2023-06-16 | 2023-06-28 | Overhead | R16 | 2023-06-16 | 103 | 65 | 28 | 9 | 202 | 2022 | 2023 | R16
162414196655 | 166242196655 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-06 | 2020-07-08 | 2020-07-08 |  | 2020-10-06 | Overhead | R16 | 2020-07-23 | 3 |  | 12 | 54 | 67 | 2020 | 2020 | R16
168781288010 | 161972288010 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-05 | 2022-08-05 | 2022-08-05 | 2022-10-03 | 2022-10-19 | Overhead | R16 | 2022-10-03 | 1 |  | 42 | 13 | 54 | 2022 | 2022 | R16
168508297370 | 167920297370 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2022-10-18 | 2022-10-18 | 2022-10-18 |  | 2023-08-16 | Underground | R16 |  | 1 |  |  |  | 217 | 2022 | 2023 | R16
162466250041 | 167138250041 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2020-07-10 | 2021-06-07 | 2021-09-29 |  | 2022-10-21 | Overhead | R16 |  | 237 | 83 |  |  | 596 | 2020 | 2022 | R16
163217335520 | 168636335520 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-10-12 | 2023-10-12 | 2023-10-12 | 2023-11-30 | 2023-12-29 | Overhead | R16 | 2023-11-30 | 1 |  | 36 | 22 | 57 | 2023 | 2023 | R16
160747335166 | 163686335166 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-09-14 | 2023-09-14 | 2023-10-10 | 2023-11-08 | 2023-11-14 | Underground | R16 | 2023-11-08 | 1 | 19 | 22 | 5 | 44 | 2023 | 2023 | R16
162497196704 | 166621196704 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-08 | 2020-07-08 | 2020-07-08 |  | 2020-10-06 | Overhead | R16 | 2020-07-23 | 1 |  | 12 | 54 | 65 | 2020 | 2020 | R16
161623289371 | 162355289371 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-08 | 2022-08-08 | 2022-08-17 | 2023-04-27 | 2023-06-19 | Underground | R16 | 2023-04-27 | 1 | 8 | 182 | 38 | 226 | 2022 | 2023 | R16
162785332402 | 163143332402 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-12 | 2023-09-12 | 2023-09-12 | 2023-10-25 | 2023-11-21 | Overhead | R16 | 2023-10-25 | 1 |  | 32 | 20 | 51 | 2023 | 2023 | R16
160560296461 | 166162296461 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-08 | 2022-10-08 | 2022-10-08 | 2023-01-04 | 2023-01-05 | Overhead | R16 | 2023-01-04 | 0 |  | 63 | 2 | 64 | 2022 | 2023 | R16
169696293864 | 161538293864 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-15 | 2022-09-15 | 2022-09-15 | 2023-03-17 | 2023-04-08 | Underground | R16 | 2023-03-17 | 1 |  | 132 | 16 | 147 | 2022 | 2023 | R16
168982289869 | 161037289869 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-02 | 2022-08-02 | 2022-08-22 | 2022-08-31 | 2022-10-26 | Underground | R16 | 2022-08-31 | 1 | 15 | 8 | 41 | 62 | 2022 | 2022 | R16
168352328589 | 167216328589 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-16 | 2023-08-16 | 2023-08-16 | 2023-10-09 | 2023-11-15 | Overhead | R16 | 2023-10-09 | 1 |  | 39 | 28 | 66 | 2023 | 2023 | R16
162893197391 | 162529197391 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-17 | 2020-06-17 | 2020-07-15 |  | 2021-11-08 | Underground | R16 | 2021-05-19 | 1 | 21 | 221 | 124 | 364 | 2020 | 2021 | R16
166719338384 | 160218338384 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-07 | 2023-12-11 | Overhead | R16 | 2023-11-07 | 1 |  | 4 | 25 | 28 | 2023 | 2023 | R16
162965196982 | 166897196982 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-09 | 2020-07-09 | 2020-07-09 |  | 2020-12-15 | Overhead | R16 | 2020-09-15 | 1 |  | 49 | 66 | 114 | 2020 | 2020 | R16
160784294985 | 163343294985 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-23 | 2022-09-26 | 2022-09-26 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 2 |  | 74 |  | 75 | 2022 | 2023 | R16
166877304325 | 161997304325 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-08 | 2022-12-27 | 2022-12-27 |  | 2023-03-31 | Overhead | R16 | 2023-01-20 | 36 |  | 19 | 51 | 104 | 2022 | 2023 | R16
163015200922 | 164469200922 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-18 | 2020-08-18 | 2020-08-18 |  | 2021-04-16 | Overhead | R16 | 2020-11-10 | 1 |  | 61 | 114 | 174 | 2020 | 2021 | R16
167304287885 | 161135287885 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2022-08-03 | 2022-08-03 | 2022-08-03 | 2022-10-23 | 2022-10-25 | Underground | R16 | 2022-10-23 | 1 |  | 58 | 2 | 60 | 2022 | 2022 | R16
160669312636 | 167504312636 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential Subdivision | 2022-08-31 | 2022-09-06 | 2023-03-16 | 2023-10-30 | 2023-11-09 | Underground | R16 | 2023-10-30 | 5 | 138 | 163 | 9 | 312 | 2022 | 2023 | R16
165203309050 | 161295309050 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-14 | 2022-09-14 | 2023-02-10 | 2023-08-23 | 2023-09-28 | Overhead | R16 | 2023-08-23 | 1 | 108 | 139 | 27 | 272 | 2022 | 2023 | R16
161025288273 | 162217288273 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-08 | 2022-08-08 | 2022-08-08 |  | 2022-10-23 | Overhead | R16 | 2022-10-11 | 1 |  | 47 | 9 | 55 | 2022 | 2022 | R16
162349297160 | 167533297160 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-15 | 2022-10-15 | 2022-10-15 |  | 2023-03-31 | Overhead | R16 | 2023-03-05 | 0 |  | 100 | 20 | 120 | 2022 | 2023 | R16
163575288584 | 161653288584 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-04 | 2022-08-04 | 2022-08-10 |  | 2023-03-20 | Overhead | R16 | 2023-01-06 | 1 | 5 | 108 | 52 | 163 | 2022 | 2023 | R16
163113204681 | 167613204681 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-08-29 | 2020-09-22 | 2020-09-22 |  | 2021-01-08 | Overhead | R16 |  | 17 |  |  |  | 95 | 2020 | 2021 | R16
166710317561 | 162255317561 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-09 | 2023-05-01 | 2023-05-01 | 2023-08-29 | 2023-09-07 | Overhead | R16 | 2023-08-29 | 124 |  | 87 | 8 | 217 | 2022 | 2023 | R16
163606298821 | 165388298821 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-04 | 2022-10-04 | 2022-10-31 | 2022-12-12 | 2022-12-22 | Underground | R16 | 2022-12-12 | 1 | 20 | 31 | 9 | 58 | 2022 | 2022 | R16
162303325555 | 161842325555 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-19 | 2023-07-19 | 2023-07-19 | 2023-07-20 | 2023-07-25 | Overhead | R16 | 2023-07-20 | 1 |  | 2 | 4 | 5 | 2023 | 2023 | R16
161837290555 | 166825290555 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-29 | 2022-08-29 | 2022-08-29 |  | 2023-06-09 | Overhead | R16 | 2023-06-02 | 1 |  | 200 | 6 | 205 | 2022 | 2023 | R16
162301331123 | 162787331123 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-25 | 2023-07-25 | 2023-08-29 | 2023-08-30 | 2023-10-02 | Underground | R16 | 2023-08-30 | 1 | 26 | 2 | 24 | 50 | 2023 | 2023 | R16
163327198759 | 160392198759 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-07-28 | 2020-07-28 | 2020-07-28 |  | 2022-04-05 | Underground | R16 | 2022-03-15 | 1 |  | 426 | 16 | 441 | 2020 | 2022 | R16
168632334071 | 165590334071 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-25 | 2023-09-28 | 2023-09-28 | 2023-10-04 | 2023-11-17 | Overhead | R16 | 2023-10-04 | 4 |  | 5 | 33 | 40 | 2023 | 2023 | R16
164972303430 | 167074303430 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-08 | 2022-12-12 | 2022-12-22 |  | 2023-08-11 | Underground | R16 | 2023-03-17 | 3 | 9 | 62 | 106 | 177 | 2022 | 2023 | R16
163449290448 | 166205290448 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-25 | 2022-08-29 | 2022-08-29 |  | 2022-12-04 | Overhead | R16 | 2022-11-02 | 3 |  | 48 | 23 | 72 | 2022 | 2022 | R16
163691332660 | 169174332660 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-08-21 | 2023-08-21 | 2023-09-14 | 2023-10-17 | 2023-10-25 | Underground | R16 | 2023-10-17 | 1 | 19 | 24 | 7 | 48 | 2023 | 2023 | R16
162995334766 | 167199334766 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-10-04 | 2023-10-04 | 2023-10-05 | 2023-10-11 | 2023-11-15 | Underground | R16 | 2023-10-11 | 1 | 2 | 5 | 26 | 31 | 2023 | 2023 | R16
162328311219 | 165084311219 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-04 | 2022-10-04 | 2023-03-03 | 2023-05-09 | 2023-05-10 | Underground | R16 | 2023-05-09 | 1 | 109 | 48 | 2 | 157 | 2022 | 2023 | R16
164912302660 | 166258302660 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-05 | 2022-12-07 | 2022-12-07 | 2023-03-02 | 2023-03-07 | Overhead | R16 | 2023-03-02 | 3 |  | 62 | 4 | 67 | 2022 | 2023 | R16
165017298433 | 160052298433 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-10-27 | 2022-10-27 | 2022-10-27 | 2022-12-02 | 2022-12-05 | Overhead | R16 | 2022-12-02 | 1 |  | 27 | 2 | 28 | 2022 | 2022 | R16
163689332795 | 164220332795 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-17 | 2023-09-17 | 2023-09-17 | 2023-11-06 | 2023-12-13 | Overhead | R16 | 2023-11-06 | 0 |  | 36 | 28 | 63 | 2023 | 2023 | R16
163430202573 | 168219202573 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-02 | 2020-09-02 | 2020-09-02 |  | 2021-01-08 | Overhead | R16 | 2020-09-22 | 1 |  | 15 | 79 | 93 | 2020 | 2021 | R16
163434200636 | 163237200636 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-19 | 2020-06-19 | 2020-08-17 |  | 2021-04-16 | Underground | R16 | 2021-01-04 | 1 | 42 | 101 | 75 | 216 | 2020 | 2021 | R16
163440196775 | 166778196775 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-07-09 | 2020-07-09 | 2020-07-09 |  | 2020-10-06 | Overhead | R16 | 2020-07-20 | 1 |  | 8 | 57 | 64 | 2020 | 2020 | R16
164475331330 | 166856331330 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2023-08-15 | 2023-08-15 | 2023-08-31 | 2023-10-13 | 2023-10-18 | Underground | R16 | 2023-10-13 | 1 | 13 | 32 | 4 | 47 | 2023 | 2023 | R16
166488295584 | 162898295584 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-22 | 2022-09-22 | 2022-09-30 |  | 2022-12-04 | Overhead | R16 | 2022-11-21 | 1 | 7 | 37 | 10 | 52 | 2022 | 2022 | R16
168441330532 | 163205330532 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-26 | 2023-08-24 | 2023-08-24 | 2023-09-14 | 2023-12-28 | Overhead | R16 | 2023-09-14 | 22 |  | 16 | 76 | 112 | 2023 | 2023 | R16
165996326724 | 163134326724 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-07-26 | 2023-07-28 | 2023-07-28 | 2023-08-28 | 2023-09-05 | Overhead | R16 | 2023-08-28 | 3 |  | 22 | 7 | 30 | 2023 | 2023 | R16
163519203314 | 162363203314 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-06 | 2020-08-06 | 2020-09-10 |  | 2021-04-14 | Underground | R16 | 2020-12-10 | 1 | 26 | 66 | 90 | 180 | 2020 | 2021 | R16
163872301766 | 165393301766 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-30 | 2022-11-30 | 2022-11-30 |  | 2023-05-30 | Overhead | R16 | 2023-02-10 | 1 |  | 53 | 78 | 130 | 2022 | 2023 | R16
167326301380 | 169971301380 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-27 | 2022-10-27 | 2022-11-22 |  | 2023-02-17 | Underground | R16 | 2022-12-21 | 1 | 19 | 22 | 43 | 82 | 2022 | 2023 | R16
160774301161 | 164261301161 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-21 | 2022-11-21 | 2022-11-21 |  | 2023-06-19 | Overhead | R16 | 2023-06-19 | 1 |  | 151 |  | 151 | 2022 | 2023 | R16
164634299699 | 161993299699 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-08 | 2022-11-08 | 2022-11-08 | 2023-04-24 | 2023-08-14 | Overhead | R16 | 2023-04-24 | 1 |  | 120 | 81 | 200 | 2022 | 2023 | R16
166212298162 | 169289298162 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2022-10-24 | 2022-10-24 | 2022-10-24 |  | 2023-11-29 | Overhead | R16 | 2023-11-02 | 1 |  | 269 | 20 | 288 | 2022 | 2023 | R16
163654202600 | 165842202600 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-21 | 2020-08-21 | 2020-09-02 |  | 2021-10-25 | Underground | R16 | 2021-08-23 | 1 | 9 | 254 | 46 | 307 | 2020 | 2021 | R16
161541289691 | 164937289691 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-19 | 2022-08-19 | 2022-08-19 |  | 2023-03-20 | Underground | R16 | 2023-02-14 | 1 |  | 128 | 25 | 152 | 2022 | 2023 | R16
163847331512 | 165559331512 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-08-08 | 2023-08-08 | 2023-09-01 | 2023-09-06 | 2023-09-21 | Underground | R16 | 2023-09-06 | 1 | 19 | 4 | 12 | 33 | 2023 | 2023 | R16
167385320603 | 163891320603 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-11-17 | 2022-11-17 | 2023-05-30 | 2023-10-17 | 2023-10-23 | Underground | R16 | 2023-10-17 | 1 | 139 | 101 | 5 | 243 | 2022 | 2023 | R16
166863298301 | 169593298301 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-26 | 2022-10-26 | 2022-10-26 | 2023-01-11 | 2023-01-28 | Overhead | R16 | 2023-01-11 | 1 |  | 56 | 13 | 68 | 2022 | 2023 | R16
163762197568 | 168601197568 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-16 | 2020-07-16 | 2020-07-16 |  | 2021-11-08 | Overhead | R16 | 2021-05-17 | 1 |  | 218 | 126 | 343 | 2020 | 2021 | R16
165589303488 | 169159303488 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-24 | 2022-10-24 | 2022-12-22 | 2023-03-21 | 2023-03-22 | Underground | R16 | 2023-03-21 | 1 | 44 | 64 | 2 | 108 | 2022 | 2023 | R16
160077300896 | 163764300896 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-11-17 | 2022-11-17 | 2022-11-17 |  | 2023-02-15 | Underground | R16 |  | 1 |  |  |  | 65 | 2022 | 2023 | R16
163794201659 | 166730201659 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-26 | 2020-08-26 | 2020-08-26 |  | 2021-07-14 | Overhead | R16 | 2020-11-23 | 1 |  | 64 | 168 | 231 | 2020 | 2021 | R16
161170303953 | 163015303953 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-14 | 2022-11-16 | 2022-12-22 | 2023-10-17 | 2023-10-18 | Underground | R16 | 2023-10-17 | 3 | 27 | 214 | 2 | 243 | 2022 | 2023 | R16
165877328454 | 166916328454 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-15 | 2023-08-16 | 2023-08-16 | 2023-10-27 | 2023-10-30 | Overhead | R16 | 2023-10-27 | 2 |  | 53 | 2 | 55 | 2023 | 2023 | R16
168600298409 | 169144298409 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-24 | 2022-10-27 | 2022-10-27 | 2023-03-22 | 2023-04-08 | Overhead | R16 | 2023-03-22 | 4 |  | 105 | 13 | 120 | 2022 | 2023 | R16
166213303893 | 165330303893 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-29 | 2022-12-01 | 2022-12-22 |  | 2023-08-14 | Underground | R16 | 2023-04-14 | 3 | 16 | 82 | 87 | 185 | 2022 | 2023 | R16
162201299271 | 161312299271 | NON-RESIDENTIAL - SUBSEQUENT WORK | R16 RESD AND NON RESD US | Commercial | 2022-11-03 | 2022-11-03 | 2022-11-03 | 2022-11-28 | 2022-12-06 | Underground | R16 | 2022-11-28 | 1 |  | 18 | 7 | 24 | 2022 | 2022 | R16
163031302671 | 164945302671 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-11-28 | 2022-12-08 | 2022-12-08 |  | 2023-08-09 | Overhead | R16 | 2023-04-24 | 9 |  | 98 | 78 | 183 | 2022 | 2023 | R16
162229298588 | 165853298588 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-06 | 2022-10-06 | 2022-10-28 | 2022-12-11 | 2022-12-14 | Underground | R16 | 2022-12-11 | 1 | 17 | 31 | 3 | 50 | 2022 | 2022 | R16
167202298311 | 169896298311 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-10-27 | 2022-10-27 | 2022-10-27 | 2023-01-11 | 2023-02-10 | Overhead | R16 | 2023-01-11 | 1 |  | 55 | 23 | 77 | 2022 | 2023 | R16
163907200785 | 167569200785 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-13 | 2020-07-13 | 2020-08-17 |  | 2021-01-20 | Underground | R16 | 2020-10-08 | 1 | 26 | 39 | 75 | 138 | 2020 | 2021 | R16
163908197404 | 168280197404 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-07-15 | 2020-07-15 | 2020-07-15 |  | 2021-04-14 | Underground | R16 | 2020-12-10 | 1 |  | 107 | 90 | 196 | 2020 | 2021 | R16
168985293345 | 161090293345 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-02 | 2022-08-04 | 2022-09-12 | 2022-11-05 | 2022-11-15 | Underground | R16 | 2022-11-05 | 3 | 28 | 40 | 7 | 76 | 2022 | 2022 | R16
163920202009 | 163854202009 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-23 | 2020-06-23 | 2020-08-27 |  | 2021-01-21 | Underground | R16 | 2020-10-14 | 1 | 48 | 35 | 72 | 153 | 2020 | 2021 | R16
162819295683 | 164840295683 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-30 | 2022-10-02 | 2022-10-02 | 2023-02-06 | 2023-03-17 | Overhead | R16 | 2023-02-06 | 1 |  | 91 | 30 | 121 | 2022 | 2023 | R16
169143338086 | 162388338086 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-10-30 | 2023-10-30 | 2023-10-30 | 2023-11-20 | 2023-11-28 | Overhead | R16 | 2023-11-20 | 1 |  | 16 | 7 | 22 | 2023 | 2023 | R16
163989197500 | 167699197500 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-13 | 2020-07-13 | 2020-07-15 |  | 2020-10-06 | Overhead | R16 | 2020-08-10 | 1 | 3 | 19 | 42 | 62 | 2020 | 2020 | R16
167258299228 | 160453299228 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-31 | 2022-10-31 | 2022-11-02 |  | 2023-04-04 | Overhead | R16 | 2023-01-12 | 1 | 3 | 52 | 59 | 112 | 2022 | 2023 | R16
164050197348 | 167766197348 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-14 | 2020-07-14 | 2020-07-14 |  | 2020-10-06 | Overhead | R16 | 2020-07-28 | 1 |  | 11 | 51 | 61 | 2020 | 2020 | R16
160637333359 | 165267333359 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-09-22 | 2023-09-22 | 2023-09-22 | 2023-11-27 | 2023-12-04 | Overhead | R16 | 2023-11-27 | 1 |  | 47 | 6 | 52 | 2023 | 2023 | R16
164055197670 | 168740197670 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-07-17 | 2020-07-17 | 2020-07-17 |  | 2020-12-29 | Overhead | R16 | 2020-09-24 | 1 |  | 50 | 69 | 118 | 2020 | 2020 | R16
167002290145 | 165621290145 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2022-08-23 | 2022-08-24 | 2022-08-24 | 2023-02-24 | 2022-12-07 | Underground | R16 | 2023-02-24 | 2 |  | 133 |  | 77 | 2022 | 2022 | R16
167077300887 | 163636300887 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-16 | 2022-11-16 | 2022-11-17 | 2023-09-01 | 2023-09-05 | Overhead | R16 | 2023-09-01 | 1 | 2 | 207 | 3 | 210 | 2022 | 2023 | R16
166721288860 | 163358288860 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-08-12 | 2022-08-12 | 2022-08-12 | 2023-05-23 | 2023-06-14 | Overhead | R16 | 2023-05-23 | 1 |  | 203 | 17 | 219 | 2022 | 2023 | R16
169475328557 | 167511328557 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-17 | 2023-08-17 | 2023-08-17 | 2023-10-20 | 2023-11-21 | Overhead | R16 | 2023-10-20 | 1 |  | 47 | 23 | 69 | 2023 | 2023 | R16
162023304645 | 164653304645 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-30 | 2022-09-30 | 2023-01-30 | 2023-01-03 | 2023-03-31 | Underground | R16 | 2023-01-03 | 1 | 87 |  | 64 | 131 | 2022 | 2023 | R16
162912295084 | 163970295084 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-27 | 2022-09-27 | 2022-09-27 |  | 2023-10-27 | Underground | R16 | 2023-10-23 | 1 |  | 280 | 5 | 284 | 2022 | 2023 | R16
167724295760 | 164940295760 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-02 | 2022-10-03 | 2022-10-03 | 2023-11-01 | 2023-12-01 | Overhead | R16 | 2023-11-01 | 1 |  | 283 | 23 | 305 | 2022 | 2023 | R16
164141199758 | 162267199758 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-06 | 2020-08-06 | 2020-08-06 |  | 2021-11-09 | Overhead | R16 | 2020-10-09 | 1 |  | 47 | 283 | 329 | 2020 | 2021 | R16
169354300738 | 163685300738 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-16 | 2022-11-16 | 2022-11-16 |  | 2023-04-19 | Overhead | R16 | 2023-01-18 | 1 |  | 46 | 66 | 111 | 2022 | 2023 | R16
167915301511 | 164636301511 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-23 | 2022-11-23 | 2022-11-23 |  | 2023-03-24 | Overhead | R16 | 2023-01-12 | 1 |  | 37 | 52 | 88 | 2022 | 2023 | R16
164147195608 | 164796195608 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2020-06-27 | 2020-06-27 | 2020-06-29 |  | 2021-06-16 | Overhead | R16 | 2020-11-13 | 0 | 1 | 100 | 154 | 253 | 2020 | 2021 | R16
161714328348 | 167015328348 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-15 | 2023-08-15 | 2023-08-15 | 2023-09-11 | 2023-09-14 | Overhead | R16 | 2023-09-11 | 1 |  | 20 | 4 | 23 | 2023 | 2023 | R16
169518300678 | 163460300678 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-15 | 2022-11-15 | 2022-11-15 |  | 2023-02-01 | Overhead | R16 | 2022-12-05 | 1 |  | 15 | 43 | 57 | 2022 | 2023 | R16
164203197350 | 168076197350 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-14 | 2020-07-14 | 2020-07-14 |  | 2020-10-06 | Overhead | R16 | 2020-07-29 | 1 |  | 12 | 50 | 61 | 2020 | 2020 | R16
169835298238 | 169679298238 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-26 | 2022-10-26 | 2022-10-26 | 2023-03-06 | 2023-03-07 | Overhead | R16 | 2023-03-06 | 1 |  | 94 | 2 | 95 | 2022 | 2023 | R16
164205198461 | 168503198461 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-16 | 2020-07-27 | 2020-07-27 |  | 2020-10-06 | Overhead | R16 | 2020-08-06 | 8 |  | 9 | 44 | 59 | 2020 | 2020 | R16
168694321751 | 163421321751 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG R16 RESD AND NON RESD UD | Commercial | 2022-11-15 | 2022-12-07 | 2023-06-09 | 2023-08-18 | 2023-09-21 | Underground | R16 | 2023-08-18 | 17 | 133 | 51 | 25 | 223 | 2022 | 2023 | R16
164213197855 | 169246197855 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-21 | 2020-07-21 | 2020-07-21 |  | 2021-07-02 | Underground | R16 | 2020-10-23 | 1 |  | 69 | 181 | 249 | 2020 | 2021 | R16
164919292833 | 165608292833 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-23 | 2022-09-07 | 2022-09-07 | 2022-09-12 | 2023-02-17 | Overhead | R16 | 2022-09-12 | 12 |  | 4 | 115 | 129 | 2022 | 2023 | R16
163241298157 | 165880298157 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-08-24 | 2022-09-19 | 2022-10-26 | 2022-12-08 | 2023-01-19 | Underground | R16 | 2022-12-08 | 19 | 28 | 32 | 31 | 107 | 2022 | 2023 | R16
166231298799 | 160414298799 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-10-31 | 2022-11-01 | 2022-11-01 | 2023-11-09 | 2023-11-10 | Underground | R16 | 2023-11-09 | 2 |  | 268 | 2 | 270 | 2022 | 2023 | R16
162888299026 | 160713299026 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2023-01-11 | 2023-01-28 | Overhead | R16 | 2023-01-11 | 1 |  | 52 | 13 | 64 | 2022 | 2023 | R16
163655327837 | 166158327837 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-10 | 2023-08-10 | 2023-08-10 | 2023-09-20 | 2023-12-07 | Overhead | R16 | 2023-09-20 | 1 |  | 30 | 57 | 86 | 2023 | 2023 | R16
160107292914 | 160142292914 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-08 | 2022-09-08 | 2022-09-08 |  | 2022-11-01 | Overhead | R16 | 2022-10-31 | 1 |  | 38 | 2 | 39 | 2022 | 2022 | R16
164283198481 | 169969198481 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-25 | 2020-07-25 | 2020-07-27 |  | 2020-10-29 | Overhead | R16 | 2020-09-01 | 0 | 1 | 27 | 43 | 69 | 2020 | 2020 | R16
162913300872 | 165584300872 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-05 | 2022-10-05 | 2022-11-17 | 2022-12-27 | 2022-12-29 | Underground | R16 | 2022-12-27 | 1 | 32 | 29 | 3 | 62 | 2022 | 2022 | R16
167129297823 | 168745297823 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-21 | 2022-10-21 | 2022-10-21 | 2022-12-22 | 2023-02-11 | Overhead | R16 | 2022-12-22 | 1 |  | 45 | 37 | 81 | 2022 | 2023 | R16
161803301187 | 165305301187 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-08-22 | 2022-08-22 | 2022-11-21 |  | 2023-11-14 | Underground | R16 |  | 1 | 66 |  |  | 322 | 2022 | 2023 | R16
169385290927 | 165400290927 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-22 | 2022-08-22 | 2022-09-01 |  | 2022-10-05 | Underground | R16 | 2022-10-05 | 1 | 9 | 25 |  | 33 | 2022 | 2022 | R16
165690302903 | 167311302903 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-09 | 2022-12-09 | 2022-12-09 | 2023-05-23 | 2023-11-21 | Overhead | R16 | 2023-05-23 | 1 |  | 118 | 131 | 248 | 2022 | 2023 | R16
166601297715 | 164606297715 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-29 | 2022-09-29 | 2022-10-21 |  | 2023-02-27 | Underground | R16 | 2023-01-03 | 1 | 17 | 53 | 40 | 108 | 2022 | 2023 | R16
164399197020 | 166387197020 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-07 | 2020-07-07 | 2020-07-10 |  | 2021-04-14 | Underground | R16 | 2020-12-15 | 1 | 4 | 113 | 87 | 202 | 2020 | 2021 | R16
161548332222 | 162527332222 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-09 | 2023-09-09 | 2023-09-09 | 2023-09-12 | 2023-09-19 | Overhead | R16 | 2023-09-12 | 0 |  | 2 | 6 | 7 | 2023 | 2023 | R16
164425203731 | 164314203731 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-25 | 2020-06-25 | 2020-09-14 |  | 2021-06-14 | Underground | R16 | 2020-10-12 | 1 | 58 | 21 | 176 | 253 | 2020 | 2021 | R16
164464197194 | 166658197194 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-07-08 | 2020-07-13 | 2020-07-14 |  | 2020-10-06 | Underground | R16 |  | 4 | 2 |  |  | 65 | 2020 | 2020 | R16
167715293017 | 160244293017 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-08 | 2022-09-08 | 2022-09-08 | 2022-11-02 | 2022-11-17 | Overhead | R16 | 2022-11-02 | 1 |  | 40 | 12 | 51 | 2022 | 2022 | R16
164384298826 | 160410298826 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-12-04 | 2022-12-07 | Overhead | R16 | 2022-12-04 | 1 |  | 25 | 3 | 28 | 2022 | 2022 | R16
167124298164 | 169114298164 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-24 | 2022-10-25 | 2022-10-25 | 2022-10-31 | 2023-02-17 | Overhead | R16 | 2022-10-31 | 2 |  | 5 | 80 | 85 | 2022 | 2023 | R16
165670332195 | 162305332195 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-07 | 2023-09-11 | 2023-09-11 | 2023-09-19 | 2023-10-06 | Overhead | R16 | 2023-09-19 | 3 |  | 7 | 14 | 22 | 2023 | 2023 | R16
162218327561 | 161466327561 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-17 | 2023-08-07 | 2023-08-07 | 2023-09-26 | 2023-10-04 | Overhead | R16 | 2023-09-26 | 16 |  | 37 | 7 | 58 | 2023 | 2023 | R16
164679197969 | 164772197969 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-26 | 2020-06-26 | 2020-07-22 |  | 2021-11-13 | Underground | R16 |  | 1 | 19 |  |  | 361 | 2020 | 2021 | R16
162864332641 | 163344332641 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-13 | 2023-09-14 | 2023-09-14 |  | 2023-10-25 | Overhead | R16 | 2023-09-15 | 2 |  | 2 | 29 | 31 | 2023 | 2023 | R16
166068317779 | 162545317779 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-20 | 2022-09-20 | 2023-05-03 |  | 2023-07-06 | Underground | R16 | 2023-06-27 | 1 | 162 | 40 | 8 | 208 | 2022 | 2023 | R16
167358298342 | 169678298342 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-26 | 2022-10-26 | 2022-10-26 |  | 2023-04-01 | Overhead | R16 | 2023-01-19 | 1 |  | 62 | 52 | 113 | 2022 | 2023 | R16
164834197347 | 168004197347 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-14 | 2020-07-14 | 2020-07-14 |  | 2020-10-06 | Overhead | R16 | 2020-08-06 | 1 |  | 18 | 44 | 61 | 2020 | 2020 | R16
165730295124 | 163966295124 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-27 | 2022-09-27 | 2022-09-27 | 2022-11-30 | 2022-12-01 | Overhead | R16 | 2022-11-30 | 1 |  | 47 | 2 | 48 | 2022 | 2022 | R16
165401290015 | 165402290015 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-22 |  | 2022-08-23 | 2022-08-23 | 2022-10-21 | Underground | R16 | 2022-08-23 |  |  |  | 44 | 45 | 2022 | 2022 | R16
169625301376 | 163590301376 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-11-16 | 2022-11-22 | 2022-11-22 | 2023-07-12 | 2023-08-16 | Underground | R16 | 2023-07-12 | 5 |  | 167 | 26 | 196 | 2022 | 2023 | R16
165296327523 | 165348327523 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2023-08-07 | 2023-08-07 | 2023-08-07 | 2023-08-28 | 2023-08-30 | Underground | R16 | 2023-08-28 | 1 |  | 16 | 3 | 18 | 2023 | 2023 | R16
169659299242 | 160939299242 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2022-11-02 | 2022-11-02 | 2022-11-02 |  | 2022-12-13 | Overhead | R16 | 2022-12-08 | 1 |  | 27 | 4 | 30 | 2022 | 2022 | R16
167949287405 | 160471287405 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2022-07-29 | 2022-07-29 | 2022-07-29 | 2022-08-31 | 2022-10-26 | Overhead | R16 | 2022-08-31 | 1 |  | 24 | 41 | 64 | 2022 | 2022 | R16
164972203462 | 161648203462 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-08-03 | 2020-08-03 | 2020-09-10 |  | 2021-01-20 | Overhead | R16 | 2020-10-09 | 1 | 29 | 22 | 74 | 123 | 2020 | 2021 | R16
163850330558 | 163871330558 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-31 | 2023-07-31 | 2023-08-25 | 2023-09-18 | 2023-09-19 | Underground | R16 | 2023-09-18 | 1 | 20 | 17 | 2 | 37 | 2023 | 2023 | R16
162668296101 | 164138296101 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-09-28 | 2022-09-28 | 2022-10-05 | 2023-01-17 | 2023-01-18 | Underground | R16 | 2023-01-17 | 1 | 6 | 75 | 2 | 81 | 2022 | 2023 | R16
164336333047 | 164462333047 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-09-19 | 2023-09-19 | 2023-09-19 | 2023-09-19 | 2023-09-22 | Overhead | R16 | 2023-09-19 | 1 |  |  | 4 | 4 | 2023 | 2023 | R16
163383307679 | 161921307679 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-08 | 2022-11-08 | 2023-01-31 | 2023-03-31 | 2023-04-10 | Underground | R16 | 2023-03-31 | 1 | 61 | 44 | 7 | 110 | 2022 | 2023 | R16
165059197288 | 166415197288 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-07 | 2020-07-07 | 2020-07-14 |  | 2020-10-06 | Underground | R16 | 2020-08-20 | 1 | 6 | 28 | 34 | 66 | 2020 | 2020 | R16
164871290617 | 162175290617 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-08 |  | 2022-08-08 | 2023-11-14 | 2023-12-08 | Underground | R16 | 2023-11-14 |  |  | 332 | 19 | 350 | 2022 | 2023 | R16
165466200107 | 161967200107 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-04 | 2020-08-04 | 2020-08-10 |  | 2022-10-17 | Overhead | R16 |  | 1 | 5 |  |  | 575 | 2020 | 2022 | R16
165506196126 | 165439196126 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-06-30 | 2020-06-30 | 2020-06-30 |  | 2020-10-08 | Underground | R16 | 2020-08-14 | 1 |  | 34 | 40 | 73 | 2020 | 2020 | R16
165532217948 | 165916217948 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-19 | 2020-12-22 | 2021-01-21 |  | 2021-11-08 | Overhead | R16 |  | 24 | 23 |  |  | 253 | 2020 | 2021 | R16
165533200534 | 163624200534 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-08-14 | 2020-08-14 | 2020-08-14 |  | 2021-07-26 | Overhead | R16 | 2020-11-09 | 1 |  | 62 | 186 | 247 | 2020 | 2021 | R16
165533200529 | 163813200529 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-08-14 | 2020-08-14 | 2020-08-14 |  | 2021-06-14 | Overhead | R16 | 2020-09-22 | 1 |  | 28 | 190 | 217 | 2020 | 2021 | R16
165550220682 | 167011220682 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 ELEC DEVELOPMENT | Residential | 2021-01-14 | 2021-01-14 | 2021-02-16 |  | 2022-03-25 | Underground | R16 |  | 1 | 24 |  |  | 312 | 2021 | 2022 | R16
165594196162 | 165613196162 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-06-30 | 2020-07-01 | 2020-07-01 |  | 2020-10-08 | Underground | R16 | 2020-08-14 | 2 |  | 33 | 40 | 73 | 2020 | 2020 | R16
165722201895 | 167081201895 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-27 | 2020-08-27 | 2020-08-27 |  | 2021-04-15 | Overhead | R16 | 2020-09-15 | 1 |  | 14 | 153 | 166 | 2020 | 2021 | R16
166037276336 | 160019276336 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-12-10 | 2020-12-10 | 2022-04-19 |  | 2022-05-19 | Overhead | R16 |  | 1 | 354 |  |  | 376 | 2020 | 2022 | R16
166075265545 | 165008265545 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-26 | 2021-11-04 | 2022-01-26 |  | 2022-03-07 | Overhead | R16 | 2022-02-08 | 8 | 60 | 10 | 20 | 95 | 2021 | 2022 | R16
166109247932 | 165734247932 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-09-15 | 2021-09-15 | 2021-09-15 |  | 2021-11-02 | Overhead | R16 | 2021-09-22 | 1 |  | 6 | 30 | 35 | 2021 | 2021 | R16
166411198309 | 168807198309 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-17 | 2020-07-17 | 2020-07-24 |  | 2020-12-29 | Overhead | R16 | 2020-12-29 | 1 | 6 | 113 |  | 118 | 2020 | 2020 | R16
166459202760 | 164849202760 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-19 | 2020-08-19 | 2020-09-03 |  | 2021-01-20 | Overhead | R16 | 2020-10-08 | 1 | 12 | 26 | 75 | 111 | 2020 | 2021 | R16
166518202591 | 168366202591 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-03 | 2020-09-03 | 2020-09-03 |  | 2021-11-05 | Underground | R16 | 2021-04-07 | 1 |  | 155 | 153 | 307 | 2020 | 2021 | R16
166750202985 | 168996202985 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-04 | 2020-09-04 | 2020-09-04 |  | 2023-06-08 | Overhead | R16 |  | 1 |  |  |  | 720 | 2020 | 2023 | R16
165830243459 | 162807243459 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-22 | 2021-07-22 | 2021-08-13 |  | 2022-01-04 | Underground | R16 | 2021-11-22 | 1 | 17 | 72 | 32 | 119 | 2021 | 2022 | R16
161956235291 | 164294235291 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-06-14 | 2021-06-14 | 2021-06-17 |  | 2021-08-23 | Overhead | R16 | 2021-08-06 | 1 | 4 | 37 | 12 | 51 | 2021 | 2021 | R16
163579239022 | 168989239022 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-06 | 2021-07-06 | 2021-07-14 | 2021-08-26 | 2021-10-25 | Underground | R16 | 2021-08-26 | 1 | 7 | 32 | 43 | 80 | 2021 | 2021 | R16
165191256661 | 163703256661 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-06-10 | 2021-11-15 | 2021-11-15 | 2022-01-25 | 2022-03-01 | Overhead | R16 | 2022-01-25 | 113 |  | 52 | 26 | 189 | 2021 | 2022 | R16
169819235001 | 164303235001 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-08-26 | 2021-10-07 | Overhead | R16 | 2021-08-26 | 1 |  | 54 | 31 | 84 | 2021 | 2021 | R16
162653233486 | 162141233486 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-04 | 2021-06-04 | 2021-06-04 | 2021-06-07 | 2021-08-23 | Overhead | R16 | 2021-06-07 | 1 |  | 2 | 56 | 57 | 2021 | 2021 | R16
161494244485 | 165018244485 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-06-16 | 2021-06-16 | 2021-08-19 |  | 2021-11-15 | Underground | R16 |  | 1 | 47 |  |  | 109 | 2021 | 2021 | R16
165333237313 | 167749237313 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-28 | 2021-07-01 | 2021-07-01 |  | 2022-03-04 | Overhead | R16 | 2022-02-08 | 4 |  | 159 | 19 | 180 | 2021 | 2022 | R16
163399237027 | 165414237027 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-18 | 2021-06-28 | 2021-06-28 | 2021-08-16 | 2021-10-25 | Overhead | R16 | 2021-08-16 | 7 |  | 36 | 51 | 92 | 2021 | 2021 | R16
163366242327 | 165926242327 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-21 | 2021-06-21 | 2021-08-05 |  | 2021-10-25 | Underground | R16 | 2021-08-31 | 1 | 34 | 19 | 40 | 91 | 2021 | 2021 | R16
164804239618 | 162141239618 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2022-01-25 | 2022-02-28 | Overhead | R16 | 2022-01-25 | 1 |  | 136 | 25 | 160 | 2021 | 2022 | R16
160522235441 | 165352235441 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-17 | 2021-06-17 | 2021-06-17 | 2021-09-17 | 2021-09-20 | Overhead | R16 | 2021-09-17 | 1 |  | 67 | 2 | 68 | 2021 | 2021 | R16
160411235006 | 164353235006 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-10-20 | 2021-10-21 | Overhead | R16 | 2021-10-20 | 1 |  | 93 | 2 | 94 | 2021 | 2021 | R16
166991197127 | 166948197127 | MOBILE HOMES PARK AB622 | ELEC SVC FOR MOBILE HOMES | Residential | 2020-07-09 | 2020-07-10 | 2020-07-13 |  | 2022-05-19 | Underground | R16 |  | 2 | 2 |  |  | 486 | 2020 | 2022 | R16
163828236068 | 165888236068 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-21 | 2021-06-21 | 2021-06-21 | 2021-08-31 | 2021-11-09 | Underground | R16 | 2021-08-31 | 1 |  | 52 | 51 | 102 | 2021 | 2021 | R16
168575233392 | 161923233392 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-03 | 2021-06-03 | 2021-06-03 | 2021-06-08 | 2021-08-11 | Overhead | R16 | 2021-06-08 | 1 |  | 4 | 47 | 50 | 2021 | 2021 | R16
169818250382 | 166812250382 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-24 | 2021-09-20 | 2021-10-01 | 2021-11-18 | 2022-01-07 | Underground | R16 | 2021-11-18 | 63 | 10 | 35 | 37 | 142 | 2021 | 2022 | R16
165436239815 | 160352239815 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-12 | 2021-07-21 | 2021-07-21 |  | 2022-03-08 | Underground | R16 | 2022-02-10 | 8 |  | 147 | 19 | 172 | 2021 | 2022 | R16
167609238172 | 169647238172 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-08 | 2021-07-08 | 2021-07-08 | 2022-03-04 | 2022-03-28 | Overhead | R16 | 2022-03-04 | 1 |  | 172 | 17 | 188 | 2021 | 2022 | R16
164340238578 | 166079238578 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-22 | 2021-07-13 | 2021-07-13 | 2021-08-13 | 2021-08-16 | Overhead | R16 | 2021-08-13 | 16 |  | 24 | 2 | 40 | 2021 | 2021 | R16
161741274182 | 166708274182 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-24 | 2021-06-24 | 2022-03-29 | 2022-10-21 | 2022-10-24 | Underground | R16 | 2022-10-21 | 1 | 199 | 149 | 2 | 348 | 2021 | 2022 | R16
161151259014 | 166781259014 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-24 | 2021-06-24 | 2021-11-29 | 2022-01-07 | 2022-02-07 | Underground | R16 | 2022-01-07 | 1 | 113 | 30 | 22 | 163 | 2021 | 2022 | R16
166960234228 | 163235234228 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-09 | 2021-06-09 | 2021-06-09 | 2021-06-23 | 2021-10-27 | Overhead | R16 | 2021-06-23 | 1 |  | 11 | 91 | 101 | 2021 | 2021 | R16
167857242206 | 169242242206 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-07 | 2021-07-07 | 2021-08-05 |  | 2021-10-25 | Underground | R16 | 2021-09-16 | 1 | 22 | 31 | 28 | 79 | 2021 | 2021 | R16
160013264348 | 167407264348 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-06-29 | 2021-06-29 | 2022-01-11 | 2022-05-18 | 2022-07-18 | Underground | R16 | 2022-05-18 | 1 | 141 | 92 | 44 | 275 | 2021 | 2022 | R16
168544253906 | 162357253906 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2021-07-21 | 2021-07-21 | 2021-10-26 | 2022-05-19 | 2022-06-13 | Underground | R16 | 2022-05-19 | 1 | 70 | 148 | 18 | 234 | 2021 | 2022 | R16
166953241135 | 162450241135 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-20 | 2021-07-29 | 2021-07-29 | 2023-03-15 | 2023-07-28 | Overhead | R16 | 2023-03-15 | 8 |  | 425 | 98 | 529 | 2021 | 2023 | R16
160026241665 | 162770241665 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-07 | 2021-06-11 | 2021-08-02 | 2021-08-26 | 2021-09-02 | Underground | R16 | 2021-08-26 | 5 | 37 | 19 | 6 | 64 | 2021 | 2021 | R16
160010233489 | 162042233489 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-04 | 2021-06-04 | 2021-06-04 | 2022-03-14 | 2022-04-21 | Overhead | R16 | 2022-03-14 | 1 |  | 202 | 29 | 230 | 2021 | 2022 | R16
164004236438 | 166786236438 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-24 | 2021-06-24 | 2021-06-24 |  | 2021-10-25 | Overhead | R16 | 2021-08-25 | 1 |  | 45 | 44 | 88 | 2021 | 2021 | R16
166878237322 | 167745237322 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-28 | 2021-06-30 | 2021-06-30 | 2021-10-08 | 2022-03-03 | Overhead | R16 | 2021-10-08 | 3 |  | 73 | 105 | 179 | 2021 | 2022 | R16
161729235137 | 165158235137 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-17 | 2021-06-17 | 2021-06-17 | 2021-10-01 | 2021-10-04 | Overhead | R16 | 2021-10-01 | 1 |  | 77 | 2 | 78 | 2021 | 2021 | R16
161277245171 | 162361245171 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-20 | 2021-07-23 | 2021-08-25 | 2022-02-01 | 2022-02-01 | Underground | R16 | 2022-02-01 | 4 | 24 | 115 |  | 141 | 2021 | 2022 | R16
168633247143 | 161996247143 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2021-07-19 | 2021-08-29 | 2021-09-09 |  | 2022-05-13 | Underground | R16 | 2022-03-28 | 30 | 9 | 143 | 35 | 215 | 2021 | 2022 | R16
164790236052 | 165956236052 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-21 | 2021-06-21 | 2021-06-21 | 2021-08-30 | 2021-08-16 | Overhead | R16 | 2021-08-30 | 1 |  | 51 |  | 41 | 2021 | 2021 | R16
163942253822 | 163381253822 | SPECIFIC BUDGET PROJECTS | OH R16 RES NON RES OD | Commercial | 2021-06-09 | 2021-06-09 | 2021-10-25 |  | 2022-08-26 | Overhead | R16 |  | 1 | 99 |  |  | 318 | 2021 | 2022 | R16
164663240222 | 162863240222 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-22 | 2021-07-22 | 2021-07-22 | 2021-12-07 | 2021-12-08 | Overhead | R16 | 2021-12-07 | 1 |  | 99 | 2 | 100 | 2021 | 2021 | R16
167995202660 | 168304202660 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-02 | 2020-09-02 | 2020-09-03 |  | 2021-04-14 | Underground | R16 | 2020-12-16 | 1 | 2 | 75 | 86 | 161 | 2020 | 2021 | R16
163236240944 | 169725240944 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-08 | 2021-07-27 | 2021-07-27 |  | 2021-10-11 | Overhead | R16 | 2021-09-13 | 14 |  | 35 | 21 | 68 | 2021 | 2021 | R16
162858236371 | 166555236371 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-23 | 2021-06-23 | 2021-06-23 |  | 2021-08-13 | Overhead | R16 | 2021-07-19 | 1 |  | 19 | 20 | 38 | 2021 | 2021 | R16
168032296590 | 168277296590 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-07-15 | 2020-08-27 | 2022-10-10 |  | 2023-10-05 | Underground | R16 |  | 32 | 553 |  |  | 842 | 2020 | 2023 | R16
160578235092 | 164388235092 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-14 | 2021-06-16 | 2021-06-16 | 2021-08-06 | 2021-09-03 | Overhead | R16 | 2021-08-06 | 3 |  | 38 | 21 | 60 | 2021 | 2021 | R16
167350239305 | 164663239305 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-15 | 2021-06-17 | 2021-07-16 |  | 2021-10-25 | Underground | R16 | 2021-09-08 | 3 | 22 | 39 | 34 | 95 | 2021 | 2021 | R16
161097267065 | 168893267065 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-05 | 2021-07-06 | 2022-02-01 | 2022-03-22 | 2022-03-23 | Underground | R16 | 2022-03-22 | 2 | 151 | 36 | 2 | 188 | 2021 | 2022 | R16
165121275513 | 166477275513 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2021-06-23 | 2021-10-12 | 2022-04-11 |  | 2023-02-22 | Underground | R16 | 2023-01-25 | 80 | 130 | 208 | 21 | 436 | 2021 | 2023 | R16
167785242457 | 162205242457 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-20 | 2021-08-06 | 2021-08-06 | 2022-04-11 | 2022-05-12 | Overhead | R16 | 2022-04-11 | 14 |  | 177 | 24 | 213 | 2021 | 2022 | R16
168240235020 | 164183235020 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-08-09 | 2021-10-27 | Overhead | R16 | 2021-08-09 | 1 |  | 41 | 58 | 98 | 2021 | 2021 | R16
169259240099 | 162892240099 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-07-22 | 2021-07-22 | 2021-07-22 |  | 2021-08-23 | Overhead | R16 | 2021-08-06 | 1 |  | 12 | 12 | 23 | 2021 | 2021 | R16
161146309412 | 166496309412 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2021-06-23 | 2022-01-28 | 2023-02-14 | 2023-03-30 | 2023-03-31 | Underground | R16 | 2023-03-30 | 158 | 273 | 33 | 2 | 463 | 2021 | 2023 | R16
163312237866 | 168884237866 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-06 | 2021-07-06 | 2021-07-06 |  | 2021-08-23 | Overhead | R16 | 2021-08-04 | 1 |  | 22 | 14 | 35 | 2021 | 2021 | R16
160635237932 | 169296237932 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-07 | 2021-07-07 | 2021-07-07 | 2021-10-11 | 2021-11-09 | Overhead | R16 | 2021-10-11 | 1 |  | 69 | 22 | 90 | 2021 | 2021 | R16
165162241031 | 160374241031 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-12 | 2021-07-27 | 2021-07-28 |  | 2021-10-25 | Overhead | R16 | 2021-09-17 | 12 | 2 | 38 | 27 | 76 | 2021 | 2021 | R16
168140198826 | 160560198826 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-28 | 2020-07-28 | 2020-07-28 |  | 2020-10-06 | Overhead | R16 | 2020-08-11 | 1 |  | 11 | 41 | 51 | 2020 | 2020 | R16
168658237163 | 162816237163 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-08 | 2021-06-08 | 2021-06-29 |  | 2023-06-08 | Underground | R16 | 2023-05-04 | 1 | 16 | 483 | 26 | 523 | 2021 | 2023 | R16
169420234227 | 163280234227 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-09 | 2021-06-09 | 2021-06-09 | 2021-07-16 | 2021-10-25 | Underground | R16 | 2021-07-16 | 1 |  | 28 | 72 | 99 | 2021 | 2021 | R16
166176241726 | 167747241726 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-28 | 2021-06-29 | 2021-08-02 | 2022-11-29 | 2022-10-17 | Underground | R16 | 2022-11-29 | 2 | 25 | 347 |  | 341 | 2021 | 2022 | R16
168162209848 | 168219209848 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-14 | 2020-07-14 | 2020-11-05 |  | 2021-04-22 | Underground | R16 | 2021-02-01 | 1 | 83 | 63 | 59 | 203 | 2020 | 2021 | R16
163406243560 | 166832243560 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-06-24 | 2021-06-24 | 2021-08-13 | 2023-08-22 | 2023-08-25 | Underground | R16 | 2023-08-22 | 1 | 37 | 528 | 4 | 567 | 2021 | 2023 | R16
169024239907 | 161781239907 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-18 | 2021-07-21 | 2021-07-21 |  | 2021-09-14 | Overhead | R16 | 2021-08-20 | 3 |  | 23 | 18 | 42 | 2021 | 2021 | R16
168230204460 | 168231204460 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-15 | 2020-07-15 | 2020-09-21 |  | 2021-07-26 | Underground | R16 | 2020-10-29 | 1 | 49 | 29 | 193 | 269 | 2020 | 2021 | R16
160829275934 | 168387275934 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2021-07-01 | 2021-09-14 | 2022-04-14 | 2022-10-25 | 2022-11-23 | Underground | R16 | 2022-10-25 | 54 | 153 | 139 | 22 | 365 | 2021 | 2022 | R16
168193249258 | 164693249258 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-15 | 2021-09-24 | 2021-09-24 | 2022-01-28 | 2022-02-02 | Overhead | R16 | 2022-01-28 | 74 |  | 91 | 4 | 167 | 2021 | 2022 | R16
168247199360 | 161370199360 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-31 | 2020-07-31 | 2020-07-31 |  | 2021-07-02 | Overhead | R16 | 2020-10-21 | 1 |  | 59 | 183 | 241 | 2020 | 2021 | R16
167916238358 | 169897238358 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2021-07-09 | 2021-07-09 | 2021-07-09 | 2022-03-08 | 2022-01-18 | Underground | R16 | 2022-03-08 | 1 |  | 173 |  | 138 | 2021 | 2022 | R16
160495240705 | 162630240705 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-21 | 2021-07-21 | 2021-07-26 | 2021-12-27 | 2021-12-28 | Underground | R16 | 2021-12-27 | 1 | 4 | 111 | 2 | 115 | 2021 | 2021 | R16
168927237346 | 166838237346 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2021-06-25 | 2021-06-25 | 2021-06-30 |  | 2023-10-02 | Overhead | R16 |  | 1 | 4 |  |  | 592 | 2021 | 2023 | R16
169729243513 | 167594243513 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-06-28 | 2021-06-28 | 2021-08-13 | 2021-09-27 | 2021-11-09 | Overhead | R16 | 2021-09-27 | 1 | 35 | 32 | 32 | 97 | 2021 | 2021 | R16
165294242020 | 161358242020 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-07-16 | 2021-08-03 | 2021-08-03 |  | 2021-11-18 | Overhead | R16 | 2021-10-26 | 13 |  | 61 | 18 | 90 | 2021 | 2021 | R16
166069287947 | 162475287947 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Commercial | 2021-06-07 | 2021-10-05 | 2022-08-04 | 2023-08-21 | 2023-09-15 | Underground | R16 | 2023-08-21 | 87 | 218 | 273 | 20 | 595 | 2021 | 2023 | R16
167919240352 | 160169240352 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2021-07-12 | 2021-07-12 | 2021-07-23 | 2023-07-26 | 2023-12-26 | Underground | R16 | 2023-07-26 | 1 | 10 | 524 | 110 | 642 | 2021 | 2023 | R16
168399244305 | 162597244305 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-21 | 2021-08-18 | 2021-08-18 |  | 2021-11-08 | Underground | R16 | 2021-11-03 | 21 |  | 56 | 4 | 79 | 2021 | 2021 | R16
168432203117 | 168434203117 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-15 | 2020-07-15 | 2020-09-08 |  | 2021-01-22 | Underground | R16 | 2020-10-15 | 1 | 40 | 28 | 72 | 138 | 2020 | 2021 | R16
161096237569 | 164211237569 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-14 | 2021-07-02 | 2021-07-02 | 2021-11-07 | 2021-12-08 | Overhead | R16 | 2021-11-07 | 15 |  | 91 | 23 | 128 | 2021 | 2021 | R16
163373254034 | 169710254034 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-08 | 2021-07-08 | 2021-10-28 |  | 2022-02-15 | Underground | R16 | 2022-01-18 | 1 | 81 | 59 | 21 | 159 | 2021 | 2022 | R16
168449207036 | 168490207036 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-15 | 2020-07-15 | 2020-10-13 |  | 2021-04-16 | Underground | R16 | 2021-03-22 | 1 | 65 | 115 | 20 | 198 | 2020 | 2021 | R16
166649234496 | 162943234496 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-08 | 2021-06-11 | 2021-06-11 | 2021-06-29 | 2021-09-08 | Overhead | R16 | 2021-06-29 | 4 |  | 13 | 52 | 67 | 2021 | 2021 | R16
160638235434 | 163296235434 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-06-09 | 2021-06-18 | 2021-06-18 | 2021-07-03 | 2022-01-31 | Overhead | R16 | 2021-07-03 | 8 |  | 11 | 151 | 169 | 2021 | 2022 | R16
169387257522 | 162123257522 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-04 | 2021-06-04 | 2021-11-19 | 2022-01-27 | 2022-03-11 | Underground | R16 | 2022-01-27 | 1 | 121 | 50 | 32 | 201 | 2021 | 2022 | R16
164357237154 | 166962237154 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-24 | 2021-06-24 | 2021-06-30 | 2021-07-13 | 2021-07-16 | Overhead | R16 | 2021-07-13 | 1 | 5 | 10 | 4 | 17 | 2021 | 2021 | R16
160922234891 | 163363234891 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-09 | 2021-06-11 | 2021-06-13 | 2021-07-22 | 2021-10-11 | Overhead | R16 | 2021-07-22 | 3 | 1 | 29 | 58 | 89 | 2021 | 2021 | R16
160310234073 | 162701234073 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-06-07 | 2021-06-09 | 2021-06-09 |  | 2021-10-25 | Underground | R16 | 2021-08-30 | 3 |  | 59 | 41 | 101 | 2021 | 2021 | R16
168294243090 | 167058243090 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-25 | 2021-06-25 | 2021-08-11 |  | 2021-11-08 | Overhead | R16 | 2021-08-17 | 1 | 34 | 5 | 60 | 97 | 2021 | 2021 | R16
164208236967 | 166428236967 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-22 | 2021-06-22 | 2021-06-28 | 2021-11-04 | 2021-12-03 | Underground | R16 | 2021-11-04 | 1 | 5 | 94 | 22 | 119 | 2021 | 2021 | R16
165491235473 | 165572235473 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-18 | 2021-06-18 | 2021-06-18 | 2021-09-10 | 2021-10-11 | Overhead | R16 | 2021-09-10 | 1 |  | 61 | 22 | 82 | 2021 | 2021 | R16
162360234272 | 163388234272 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-10 | 2021-06-10 | 2021-06-10 |  | 2021-09-07 | Overhead | R16 | 2021-08-10 | 1 |  | 44 | 21 | 64 | 2021 | 2021 | R16
168644228489 | 169777228489 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-04-22 | 2021-04-22 | 2021-04-28 |  | 2021-10-25 | Underground | R16 |  | 1 | 5 |  |  | 133 | 2021 | 2021 | R16
165034239716 | 167742239716 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-28 | 2021-07-20 | 2021-07-20 |  | 2022-04-21 | Overhead | R16 | 2022-03-23 | 17 |  | 177 | 22 | 214 | 2021 | 2022 | R16
164335255502 | 168462255502 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-07-01 | 2021-07-07 | 2021-11-08 |  | 2023-01-05 | Underground | R16 | 2022-09-28 | 5 | 89 | 233 | 72 | 396 | 2021 | 2023 | R16
165103240349 | 166505240349 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-23 | 2021-06-23 | 2021-07-23 | 2022-11-14 | 2022-11-17 | Underground | R16 | 2022-11-14 | 1 | 23 | 342 | 4 | 367 | 2021 | 2022 | R16
168394242952 | 161661242952 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-16 | 2021-07-19 | 2021-08-10 | 2021-10-27 | 2021-10-27 | Underground | R16 | 2021-10-27 | 2 | 17 | 57 |  | 74 | 2021 | 2021 | R16
163990239281 | 168228239281 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-30 | 2021-06-30 | 2021-07-15 | 2021-10-29 | 2021-12-17 | Underground | R16 | 2021-10-29 | 1 | 12 | 77 | 36 | 123 | 2021 | 2021 | R16
168870203685 | 169656203685 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-09 | 2020-09-09 | 2020-09-11 |  | 2021-04-21 | Overhead | R16 |  | 1 | 3 |  |  | 161 | 2020 | 2021 | R16
168873202374 | 167880202374 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-31 | 2020-08-31 | 2020-08-31 |  | 2021-11-05 | Overhead | R16 | 2021-04-27 | 1 |  | 172 | 139 | 310 | 2020 | 2021 | R16
168785239762 | 162194239762 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2021-11-09 | 2021-12-03 | Overhead | R16 | 2021-11-09 | 1 |  | 81 | 19 | 99 | 2021 | 2021 | R16
163431234154 | 162487234154 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-07 | 2021-06-09 | 2021-06-09 | 2021-07-14 | 2021-08-13 | Overhead | R16 | 2021-07-14 | 3 |  | 26 | 23 | 50 | 2021 | 2021 | R16
169333240661 | 169648240661 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-08 | 2021-07-08 | 2021-07-25 | 2021-09-09 | 2022-01-12 | Underground | R16 | 2021-09-09 | 1 | 12 | 34 | 90 | 135 | 2021 | 2022 | R16
163089236310 | 166180236310 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-22 | 2021-06-23 | 2021-06-23 | 2021-10-11 | 2021-10-12 | Overhead | R16 | 2021-10-11 | 2 |  | 79 | 2 | 81 | 2021 | 2021 | R16
162430236392 | 166666236392 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-23 | 2021-06-23 | 2021-06-23 | 2021-08-11 | 2021-09-10 | Overhead | R16 | 2021-08-11 | 1 |  | 36 | 23 | 58 | 2021 | 2021 | R16
166296237425 | 167766237425 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-29 | 2021-06-29 | 2021-07-01 |  | 2021-10-27 | Underground | R16 | 2021-08-11 | 1 | 3 | 30 | 56 | 87 | 2021 | 2021 | R16
162048239363 | 161604239363 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-16 | 2021-07-16 | 2021-07-16 |  | 2022-11-15 | Overhead | R16 | 2022-11-14 | 1 |  | 347 | 2 | 348 | 2021 | 2022 | R16
161826236979 | 166319236979 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-22 | 2021-06-22 | 2021-06-28 | 2021-06-29 | 2021-09-10 | Underground | R16 | 2021-06-29 | 1 | 5 | 2 | 54 | 59 | 2021 | 2021 | R16
161097236864 | 167243236864 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-26 | 2021-06-26 | 2021-06-26 | 2021-08-11 | 2021-09-10 | Overhead | R16 | 2021-08-11 | 0 |  | 33 | 23 | 55 | 2021 | 2021 | R16
161812233458 | 162152233458 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-04 | 2021-06-04 | 2021-06-04 | 2022-03-31 | 2022-04-01 | Overhead | R16 | 2022-03-31 | 1 |  | 215 | 2 | 216 | 2021 | 2022 | R16
169650236172 | 162768236172 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-08 | 2021-06-08 | 2021-06-22 |  | 2021-10-27 | Overhead | R16 |  | 1 | 11 |  |  | 102 | 2021 | 2021 | R16
162617265155 | 164841265155 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-15 | 2021-06-15 | 2022-01-19 |  | 2022-03-08 | Underground | R16 | 2022-01-19 | 1 | 157 |  | 35 | 191 | 2021 | 2022 | R16
160201237418 | 162009237418 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-06-03 | 2021-06-03 | 2021-06-30 | 2021-08-12 | 2021-08-12 | Underground | R16 | 2021-08-12 | 1 | 20 | 32 |  | 51 | 2021 | 2021 | R16
169003308987 | 167507308987 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-06-28 | 2023-02-09 | 2023-02-09 |  | 2023-07-31 | Overhead | R16 | 2023-04-05 | 424 |  | 40 | 84 | 546 | 2021 | 2023 | R16
161340237119 | 164232237119 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-14 | 2021-06-30 | 2021-06-30 |  | 2021-08-23 | Overhead | R16 | 2021-08-03 | 13 |  | 25 | 15 | 51 | 2021 | 2021 | R16
160486237192 | 168062237192 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2021-06-30 | 2021-06-30 | 2021-06-30 | 2021-07-07 | 2021-07-09 | Overhead | R16 | 2021-07-07 | 1 |  | 6 | 3 | 8 | 2021 | 2021 | R16
165619237609 | 167548237609 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-28 | 2021-07-03 | 2021-07-03 | 2021-10-06 | 2021-10-07 | Overhead | R16 | 2021-10-06 | 5 |  | 68 | 2 | 74 | 2021 | 2021 | R16
162220237820 | 168860237820 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-05 | 2021-07-05 | 2021-07-05 | 2021-09-27 | 2023-04-13 | Overhead | R16 | 2021-09-27 | 1 |  | 61 | 404 | 464 | 2021 | 2023 | R16
169120202134 | 160665202134 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-29 | 2020-07-29 | 2020-08-31 |  | 2021-11-08 | Underground | R16 | 2021-05-24 | 1 | 24 | 191 | 121 | 334 | 2020 | 2021 | R16
161444236919 | 167754236919 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-29 | 2021-06-29 | 2021-06-29 | 2021-08-16 | 2021-08-18 | Overhead | R16 | 2021-08-16 | 1 |  | 35 | 3 | 37 | 2021 | 2021 | R16
169169204169 | 161438204169 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-17 | 2020-09-17 | 2020-09-17 |  | 2021-09-13 | Overhead | R16 | 2021-08-16 | 1 |  | 238 | 21 | 258 | 2020 | 2021 | R16
164156236914 | 162633236914 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-07 | 2021-06-28 | 2021-06-28 | 2022-02-10 | 2022-03-09 | Overhead | R16 | 2022-02-10 | 16 |  | 164 | 20 | 198 | 2021 | 2022 | R16
161038240271 | 165875240271 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-21 | 2021-07-22 | 2021-07-22 | 2021-09-29 | 2021-11-09 | Overhead | R16 | 2021-09-29 | 24 |  | 50 | 30 | 102 | 2021 | 2021 | R16
169814234644 | 163969234644 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-11 | 2021-06-11 | 2021-06-11 |  | 2021-08-23 | Overhead | R16 | 2021-07-14 | 1 |  | 24 | 29 | 52 | 2021 | 2021 | R16
169776241207 | 166679241207 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-24 | 2021-07-29 | 2021-07-29 | 2021-09-09 | 2021-10-11 | Overhead | R16 | 2021-09-09 | 26 |  | 31 | 23 | 78 | 2021 | 2021 | R16
166705234124 | 162698234124 | RESIDENTIAL - SINGLE FAMILY DETACHED | ELEC OH MISC SVC OS | Residential | 2021-06-08 | 2021-06-09 | 2021-06-09 | 2021-06-09 | 2021-08-31 | Overhead | R16 | 2021-06-09 | 2 |  |  | 60 | 61 | 2021 | 2021 | R16
163971245901 | 165883245901 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-21 | 2021-06-21 | 2021-08-30 |  | 2021-10-14 | Underground | R16 | 2021-09-20 | 1 | 51 | 16 | 19 | 84 | 2021 | 2021 | R16
162103241404 | 167477241404 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-28 | 2021-07-12 | 2021-07-30 | 2021-11-18 | 2022-01-07 | Underground | R16 | 2021-11-18 | 11 | 15 | 80 | 37 | 140 | 2021 | 2022 | R16
160134244440 | 163790244440 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2021-06-10 | 2021-06-10 | 2021-08-19 |  | 2021-10-25 | Overhead | R16 |  | 1 | 51 |  |  | 98 | 2021 | 2021 | R16
167478239411 | 161629239411 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-16 | 2021-07-16 | 2021-07-16 | 2021-08-09 | 2021-08-10 | Overhead | R16 | 2021-08-09 | 1 |  | 17 | 2 | 18 | 2021 | 2021 | R16
160914236272 | 164191236272 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-13 | 2021-06-13 | 2021-06-23 |  | 2022-01-12 | Overhead | R16 | 2021-12-03 | 0 | 8 | 118 | 29 | 153 | 2021 | 2022 | R16
161907237040 | 167503237040 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-28 | 2021-06-28 | 2021-06-28 | 2021-08-26 | 2021-10-25 | Overhead | R16 | 2021-08-26 | 1 |  | 44 | 43 | 86 | 2021 | 2021 | R16
162849239045 | 166275239045 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-22 | 2021-06-23 | 2021-07-14 |  | 2021-10-25 | Underground | R16 | 2021-08-24 | 2 | 16 | 30 | 45 | 90 | 2021 | 2021 | R16
168653240054 | 161272240054 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-15 | 2021-07-15 | 2021-07-22 |  | 2021-10-25 | Underground | R16 | 2021-08-26 | 1 | 6 | 26 | 43 | 73 | 2021 | 2021 | R16
167094238553 | 167894238553 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-06-29 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-12-09 | Underground | R16 | 2021-07-14 | 10 | 2 | 2 | 107 | 118 | 2021 | 2021 | R16
162711259509 | 162712259509 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-21 | 2021-07-21 | 2021-12-02 |  | 2023-01-08 | Underground | R16 | 2022-12-22 | 1 | 97 | 276 | 12 | 383 | 2021 | 2023 | R16
160420234974 | 164573234974 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-15 | 2021-06-15 | 2021-06-15 |  | 2021-10-11 | Overhead | R16 | 2021-09-13 | 1 |  | 65 | 21 | 85 | 2021 | 2021 | R16
163605237978 | 162699237978 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-08 | 2021-07-08 | 2021-07-08 |  | 2021-10-25 | Overhead | R16 | 2021-10-25 | 23 |  | 78 |  | 100 | 2021 | 2021 | R16
168917241970 | 162675241970 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-22 | 2021-08-04 | 2021-08-04 | 2021-10-27 | 2021-10-28 | Overhead | R16 | 2021-10-27 | 10 |  | 61 | 2 | 71 | 2021 | 2021 | R16
160324250540 | 168642250540 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2021-07-02 | 2021-08-10 | 2021-10-04 | 2021-10-18 | 2022-01-24 | Underground | R16 | 2021-10-18 | 28 | 40 | 11 | 71 | 147 | 2021 | 2022 | R16
169552210521 | 161410210521 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-31 | 2020-07-31 | 2020-11-12 |  | 2021-11-08 | Underground | R16 | 2021-05-25 | 1 | 75 | 139 | 120 | 332 | 2020 | 2021 | R16
167670237992 | 164965237992 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-16 | 2021-06-16 | 2021-07-07 |  | 2021-12-02 | Underground | R16 | 2021-11-02 | 1 | 16 | 85 | 23 | 122 | 2021 | 2021 | R16
166059262722 | 167402262722 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-28 | 2021-12-27 | 2021-12-27 | 2022-02-11 | 2022-03-11 | Underground | R16 | 2022-02-11 | 131 |  | 35 | 21 | 185 | 2021 | 2022 | R16
160966244803 | 168895244803 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-05 | 2021-07-06 | 2021-08-23 | 2021-10-04 | 2021-10-04 | Underground | R16 | 2021-10-04 | 2 | 35 | 31 |  | 66 | 2021 | 2021 | R16
160901260923 | 163060260923 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-06-08 | 2021-06-22 | 2021-12-13 |  | 2022-05-03 | Underground | R16 | 2022-04-11 | 11 | 125 | 86 | 17 | 236 | 2021 | 2022 | R16
168188246261 | 161785246261 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-18 | 2021-07-18 | 2021-09-01 |  | 2021-11-13 | Underground | R16 | 2021-10-19 | 0 | 33 | 35 | 19 | 85 | 2021 | 2021 | R16
166371236487 | 166864236487 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-06-24 | 2021-06-24 | 2021-06-24 | 2022-03-05 | 2022-03-08 | Overhead | R16 | 2022-03-05 | 1 |  | 182 | 2 | 184 | 2021 | 2022 | R16
169590235435 | 167117235435 | CUSTOMER UPGRADE IN SERVICE | UG SVC CONVERSION | Residential | 2021-02-27 | 2021-02-27 | 2021-06-18 |  | 2022-02-02 | Underground | R16 | 2021-12-16 | 0 | 80 | 130 | 35 | 243 | 2021 | 2022 | R16
161101239202 | 161243239202 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-15 | 2021-07-15 | 2021-07-15 |  | 2022-03-14 | Underground | R16 | 2022-02-24 | 1 |  | 161 | 13 | 173 | 2021 | 2022 | R16
164549237000 | 166429237000 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-23 | 2021-06-28 | 2021-06-28 |  | 2021-11-18 | Overhead | R16 | 2021-10-28 | 4 |  | 89 | 16 | 107 | 2021 | 2021 | R16
169810236672 | 163950236672 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-06-11 | 2021-06-11 | 2021-06-25 | 2022-04-29 | 2022-05-12 | Overhead | R16 | 2022-04-29 | 1 | 11 | 221 | 10 | 240 | 2021 | 2022 | R16
169618203997 | 169771203997 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-23 | 2020-07-23 | 2020-09-16 |  | 2021-06-14 | Underground | R16 | 2020-10-28 | 1 | 40 | 31 | 164 | 233 | 2020 | 2021 | R16
169645202435 | 168130202435 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-01 | 2020-09-01 | 2020-09-01 |  | 2021-11-05 | Overhead | R16 | 2021-04-15 | 1 |  | 163 | 147 | 309 | 2020 | 2021 | R16
169647200019 | 162637200019 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-08-07 | 2020-08-07 | 2020-08-07 |  | 2020-10-06 | Overhead | R16 | 2020-08-27 | 1 |  | 15 | 29 | 43 | 2020 | 2020 | R16
165529240215 | 160197240215 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-12 | 2021-07-23 | 2021-07-23 |  | 2021-08-23 | Overhead | R16 | 2021-08-06 | 10 |  | 11 | 12 | 31 | 2021 | 2021 | R16
165896235477 | 165639235477 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-18 | 2021-06-18 | 2021-06-18 | 2021-12-29 | 2022-02-10 | Overhead | R16 | 2021-12-29 | 1 |  | 139 | 32 | 170 | 2021 | 2022 | R16
164810235254 | 165231235254 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-06-17 | 2021-06-17 | 2021-06-17 |  | 2023-04-07 | Underground | R16 |  | 1 |  |  |  | 472 | 2021 | 2023 | R16
163732238005 | 161949238005 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-04 | 2021-06-04 | 2021-07-07 |  | 2021-10-27 | Overhead | R16 | 2021-08-12 | 1 | 24 | 27 | 55 | 104 | 2021 | 2021 | R16
169219238045 | 169176238045 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-07 | 2021-07-07 | 2021-07-07 | 2021-10-21 | 2023-07-14 | Overhead | R16 | 2021-10-21 | 1 |  | 77 | 452 | 528 | 2021 | 2023 | R16
160578235402 | 162847235402 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-06-08 | 2021-06-08 | 2021-06-17 |  | 2021-08-23 | Underground | R16 | 2021-08-04 | 1 | 8 | 35 | 14 | 55 | 2021 | 2021 | R16
160526240021 | 162445240021 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-09-20 | 2022-03-15 | Underground | R16 | 2021-09-20 | 1 |  | 44 | 127 | 170 | 2021 | 2022 | R16
169054244543 | 167182244543 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-25 | 2021-06-25 | 2021-08-20 | 2021-11-01 | 2021-12-02 | Underground | R16 | 2021-11-01 | 1 | 41 | 52 | 24 | 115 | 2021 | 2021 | R16
161891236012 | 165664236012 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2021-06-18 | 2021-06-18 | 2021-06-22 | 2023-09-04 | 2023-09-07 | Overhead | R16 | 2023-09-04 | 1 | 3 | 575 | 4 | 580 | 2021 | 2023 | R16
161921246837 | 167401246837 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-28 | 2021-07-26 | 2021-09-08 | 2021-11-10 | 2021-12-29 | Underground | R16 | 2021-11-10 | 21 | 33 | 46 | 36 | 133 | 2021 | 2021 | R16
162730274417 | 164753274417 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-15 | 2022-03-11 | 2022-03-31 | 2022-07-19 | 2023-07-03 | Overhead | R16 | 2022-07-19 | 194 | 15 | 79 | 250 | 535 | 2021 | 2023 | R16
160383235172 | 165093235172 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2022-02-19 | 2022-06-06 | Overhead | R16 | 2022-02-19 | 1 |  | 178 | 76 | 254 | 2021 | 2022 | R16
162815236070 | 165855236070 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-21 | 2021-06-21 | 2021-06-21 |  | 2021-10-25 | Underground | R16 | 2021-09-14 | 1 |  | 62 | 30 | 91 | 2021 | 2021 | R16
167368239483 | 161843239483 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-19 | 2021-07-19 | 2021-07-19 | 2021-09-09 | 2021-10-25 | Overhead | R16 | 2021-09-09 | 1 |  | 39 | 33 | 71 | 2021 | 2021 | R16
162092242994 | 166439242994 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-06-23 | 2021-08-11 | 2021-08-11 |  | 2021-12-17 | Overhead | R16 | 2021-11-18 | 36 |  | 72 | 22 | 128 | 2021 | 2021 | R16
163678234310 | 163580234310 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Commercial | 2021-06-10 | 2021-06-10 | 2021-06-10 |  | 2021-11-18 | Underground | R16 | 2021-10-27 | 1 |  | 100 | 17 | 116 | 2021 | 2021 | R16
164076234834 | 164766234834 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-15 | 2021-06-15 | 2021-06-15 | 2021-07-27 | 2021-08-23 | Overhead | R16 | 2021-07-27 | 1 |  | 31 | 20 | 50 | 2021 | 2021 | R16
165712239623 | 161925239623 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-19 | 2021-07-19 | 2021-07-19 | 2021-09-21 | 2021-10-28 | Overhead | R16 | 2021-09-21 | 1 |  | 47 | 28 | 74 | 2021 | 2021 | R16
160907235231 | 165240235231 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-17 | 2021-06-17 | 2021-06-17 | 2021-08-12 | 2021-08-12 | Overhead | R16 | 2021-08-12 | 1 |  | 41 |  | 41 | 2021 | 2021 | R16
166190260151 | 168452260151 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-01 | 2021-07-01 | 2021-12-07 |  | 2022-02-28 | Underground | R16 | 2022-01-26 | 1 | 114 | 37 | 24 | 173 | 2021 | 2022 | R16
165186237710 | 168715237710 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-02 | 2021-07-02 | 2021-07-02 | 2023-03-17 | 2023-04-18 | Overhead | R16 | 2023-03-17 | 1 |  | 446 | 23 | 468 | 2021 | 2023 | R16
162915239198 | 161131239198 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-14 | 2021-07-16 | 2021-07-16 | 2021-12-22 | 2022-01-24 | Overhead | R16 | 2021-12-22 | 3 |  | 114 | 24 | 139 | 2021 | 2022 | R16
162291234101 | 162795234101 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-08 | 2021-06-08 | 2021-06-08 |  | 2022-02-02 | Underground | R16 | 2021-01-12 | 1 |  |  | 277 | 172 | 2021 | 2022 | R16
166302241586 | 169134241586 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-06 | 2021-07-30 | 2021-07-30 |  | 2021-11-09 | Underground | R16 | 2021-10-12 | 19 |  | 53 | 21 | 91 | 2021 | 2021 | R16
167464246736 | 169140246736 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-06 | 2021-07-15 | 2021-09-08 |  | 2021-12-03 | Underground | R16 | 2021-11-09 | 8 | 40 | 45 | 19 | 109 | 2021 | 2021 | R16
161069237323 | 163064237323 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-09 | 2021-06-09 | 2021-06-30 |  | 2023-02-08 | Underground | R16 | 2023-01-24 | 1 | 16 | 410 | 12 | 436 | 2021 | 2023 | R16
169437305572 | 161691305572 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-06-02 | 2021-06-02 | 2023-01-30 | 2023-01-10 | 2023-03-25 | Overhead | R16 | 2023-01-10 | 1 | 434 |  | 54 | 473 | 2021 | 2023 | R16
163180235994 | 166291235994 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-22 | 2021-06-22 | 2021-06-22 |  | 2021-10-25 | Overhead | R16 | 2021-08-09 | 1 |  | 35 | 56 | 90 | 2021 | 2021 | R16
167919239113 | 161248239113 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-15 | 2021-07-15 | 2021-07-15 | 2021-11-05 | 2021-12-02 | Overhead | R16 | 2021-11-05 | 1 |  | 82 | 20 | 101 | 2021 | 2021 | R16
160119264594 | 160064264594 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-11-16 | 2021-11-16 | 2022-01-13 |  | 2023-03-01 | Underground | R16 |  | 1 | 43 |  |  | 337 | 2021 | 2023 | R16
161146266583 | 166467266583 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-06-23 | 2022-01-28 | 2022-01-28 | 2023-03-30 | 2023-03-31 | Overhead | R16 | 2023-03-30 | 158 |  | 305 | 2 | 463 | 2021 | 2023 | R16
163381238036 | 164883238036 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2021-06-16 | 2021-06-23 | 2021-07-08 |  | 2021-11-10 | Overhead | R16 |  | 6 | 12 |  |  | 106 | 2021 | 2021 | R16
163255240274 | 162905240274 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-22 | 2021-07-22 | 2021-07-22 | 2021-09-30 | 2021-11-09 | Overhead | R16 | 2021-09-30 | 1 |  | 51 | 29 | 79 | 2021 | 2021 | R16
161827242399 | 169712242399 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-08 | 2021-07-08 | 2021-08-07 | 2022-03-07 | 2022-04-01 | Underground | R16 | 2022-03-07 | 1 | 22 | 151 | 20 | 192 | 2021 | 2022 | R16
160128199696 | 162145199696 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-05 | 2020-08-05 | 2020-08-05 |  | 2021-01-21 | Overhead | R16 | 2020-10-13 | 1 |  | 50 | 73 | 122 | 2020 | 2021 | R16
168377241412 | 161275241412 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-15 | 2021-07-15 | 2021-07-30 |  | 2021-12-18 | Underground | R16 | 2021-12-15 | 1 | 12 | 99 | 3 | 112 | 2021 | 2021 | R16
164284239103 | 162656239103 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-07 | 2021-07-15 | 2021-07-15 | 2021-08-13 | 2021-10-25 | Overhead | R16 | 2021-08-13 | 29 |  | 22 | 52 | 101 | 2021 | 2021 | R16
165715238214 | 169336238214 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-07-08 | 2021-07-08 | 2021-07-09 |  | 2021-08-23 | Overhead | R16 | 2021-07-28 | 1 | 2 | 14 | 19 | 33 | 2021 | 2021 | R16
167160237184 | 164528237184 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-14 | 2021-06-29 | 2021-06-29 | 2021-08-05 | 2021-10-27 | Overhead | R16 | 2021-08-05 | 12 |  | 28 | 60 | 98 | 2021 | 2021 | R16
163184241845 | 162019241845 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-04 | 2021-08-02 | 2021-08-02 | 2021-09-13 | 2021-10-25 | Overhead | R16 | 2021-09-13 | 42 |  | 31 | 31 | 102 | 2021 | 2021 | R16
168932242396 | 161784242396 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-18 | 2021-08-06 | 2021-08-06 | 2021-09-20 | 2021-09-21 | Overhead | R16 | 2021-09-20 | 15 |  | 32 | 2 | 47 | 2021 | 2021 | R16
167176236655 | 167204236655 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-25 | 2021-06-25 | 2021-06-25 |  | 2021-11-16 | Overhead | R16 | 2021-11-15 | 1 |  | 102 | 2 | 103 | 2021 | 2021 | R16
166288239550 | 161891239550 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-19 | 2021-07-19 | 2021-07-19 |  | 2022-04-01 | Overhead | R16 |  | 1 |  |  |  | 185 | 2021 | 2022 | R16
167341236706 | 163206236706 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-09 | 2021-06-09 | 2021-06-25 |  | 2021-10-26 | Underground | R16 | 2021-09-01 | 1 | 13 | 49 | 40 | 100 | 2021 | 2021 | R16
160912236141 | 165921236141 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-21 |  | 2021-06-21 | 2022-01-23 | 2022-01-24 | Overhead | R16 | 2022-01-23 |  |  | 155 | 1 | 156 | 2021 | 2022 | R16
164670237031 | 167107237031 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-25 | 2021-06-29 | 2021-06-29 |  | 2021-11-08 | Overhead | R16 | 2021-11-08 | 3 |  | 95 |  | 97 | 2021 | 2021 | R16
162918243177 | 169920243177 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-09 | 2021-08-12 | 2021-08-12 | 2021-09-10 | 2021-10-25 | Overhead | R16 | 2021-09-10 | 25 |  | 22 | 32 | 77 | 2021 | 2021 | R16
160017236160 | 164822236160 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-06-15 | 2021-06-21 | 2021-06-21 |  | 2022-05-19 | Overhead | R16 | 2022-04-29 | 5 |  | 225 | 15 | 243 | 2021 | 2022 | R16
160294204888 | 163045204888 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-24 | 2020-09-24 | 2020-09-24 |  | 2021-07-26 | Overhead | R16 | 2021-05-13 | 1 |  | 166 | 53 | 218 | 2020 | 2021 | R16
169370240230 | 163037240230 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-23 | 2021-07-23 | 2021-07-23 |  | 2021-10-25 | Overhead | R16 | 2021-09-16 | 1 |  | 40 | 28 | 67 | 2021 | 2021 | R16
164440293093 | 167133293093 | NON-RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Commercial | 2021-06-25 | 2021-06-28 | 2022-09-09 | 2023-03-29 | 2023-07-14 | Underground | R16 | 2023-03-29 | 2 | 315 | 144 | 78 | 536 | 2021 | 2023 | R16
160310211959 | 165860211959 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-21 | 2020-08-21 | 2020-11-25 |  | 2021-08-03 | Underground | R16 | 2021-03-17 | 1 | 69 | 81 | 100 | 248 | 2020 | 2021 | R16
167848247235 | 163208247235 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-23 | 2021-07-26 | 2021-09-10 | 2021-10-26 | 2021-10-28 | Underground | R16 | 2021-10-26 | 2 | 35 | 33 | 3 | 70 | 2021 | 2021 | R16
168659263289 | 168664263289 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2021-07-02 | 2021-07-02 | 2022-01-03 | 2022-06-09 | 2022-06-22 | Underground | R16 | 2022-06-09 | 1 | 132 | 114 | 10 | 254 | 2021 | 2022 | R16
166015234070 | 163053234070 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-06-08 | 2021-06-08 | 2021-06-08 | 2021-06-12 | 2021-09-28 | Overhead | R16 | 2021-06-12 | 1 |  | 4 | 77 | 81 | 2021 | 2021 | R16
162636247142 | 163044247142 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-08 | 2021-09-09 | 2021-09-09 |  | 2023-03-09 | Overhead | R16 | 2021-12-17 | 68 |  | 72 | 320 | 458 | 2021 | 2023 | R16
169792237765 | 163223237765 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-09 | 2021-06-09 | 2021-07-06 |  | 2021-09-14 | Underground | R16 | 2021-08-19 | 1 | 20 | 33 | 19 | 70 | 2021 | 2021 | R16
161137236652 | 167130236652 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-25 | 2021-06-25 | 2021-06-25 | 2021-09-10 | 2021-10-25 | Overhead | R16 | 2021-09-10 | 1 |  | 56 | 32 | 87 | 2021 | 2021 | R16
165198236414 | 161835236414 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-03 | 2021-06-24 | 2021-06-24 |  | 2021-08-13 | Overhead | R16 | 2021-07-19 | 16 |  | 18 | 20 | 52 | 2021 | 2021 | R16
169025277654 | 165215277654 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-06-16 | 2022-04-18 | 2022-04-29 |  | 2022-06-09 | Overhead | R16 |  | 219 | 10 |  |  | 257 | 2021 | 2022 | R16
160623239913 | 162311239913 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-20 | 2021-07-20 | 2021-07-21 | 2021-09-29 | 2021-10-25 | Overhead | R16 | 2021-09-29 | 1 | 2 | 51 | 19 | 70 | 2021 | 2021 | R16
162917237125 | 166714237125 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-23 | 2021-06-25 | 2021-06-29 | 2021-08-24 | 2021-08-25 | Overhead | R16 | 2021-08-24 | 3 | 3 | 41 | 2 | 46 | 2021 | 2021 | R16
165894235400 | 165342235400 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-17 | 2021-06-17 | 2021-06-17 | 2021-11-04 | 2021-12-02 | Overhead | R16 | 2021-11-04 | 1 |  | 101 | 21 | 121 | 2021 | 2021 | R16
169025238485 | 160250238485 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-12 | 2021-07-12 | 2021-07-12 |  | 2021-08-23 | Overhead | R16 | 2021-08-06 | 1 |  | 20 | 12 | 31 | 2021 | 2021 | R16
164182239700 | 161445239700 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-07-16 | 2021-07-16 | 2021-07-19 |  | 2021-08-23 | Overhead | R16 |  | 1 | 2 |  |  | 27 | 2021 | 2021 | R16
167149269454 | 168469269454 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-07-02 | 2021-07-15 | 2022-02-17 |  | 2022-03-21 | Underground | R16 | 2022-03-17 | 10 | 156 | 21 | 3 | 187 | 2021 | 2022 | R16
164009237317 | 166580237317 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-06-23 | 2021-07-01 | 2021-07-01 | 2021-09-04 | 2021-09-10 | Underground | R16 | 2021-09-04 | 7 |  | 47 | 5 | 58 | 2021 | 2021 | R16
160787236543 | 163176236543 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-09 | 2021-06-09 | 2021-06-24 |  | 2021-10-27 | Underground | R16 | 2021-08-11 | 1 | 12 | 35 | 56 | 101 | 2021 | 2021 | R16
165048237709 | 168720237709 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-02 | 2021-07-02 | 2021-07-02 | 2021-08-05 | 2021-09-01 | Underground | R16 | 2021-08-05 | 1 |  | 25 | 20 | 44 | 2021 | 2021 | R16
167046234054 | 163034234054 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-09 | 2021-06-09 | 2021-06-09 | 2021-07-21 | 2021-08-23 | Overhead | R16 | 2021-07-21 | 1 |  | 31 | 24 | 54 | 2021 | 2021 | R16
166208237172 | 167904237172 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-29 | 2021-06-29 | 2021-06-29 |  | 2021-08-23 | Overhead | R16 | 2021-08-05 | 1 |  | 28 | 13 | 40 | 2021 | 2021 | R16
165256236947 | 167588236947 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-28 | 2021-06-28 | 2021-06-28 | 2021-08-23 | 2021-08-25 | Overhead | R16 | 2021-08-23 | 1 |  | 41 | 3 | 43 | 2021 | 2021 | R16
161157280859 | 166454280859 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-06-23 | 2021-08-24 | 2022-05-27 |  | 2022-07-26 | Underground | R16 |  | 45 | 199 |  |  | 285 | 2021 | 2022 | R16
168391243875 | 162909243875 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-23 | 2021-07-23 | 2021-08-16 | 2021-12-29 | 2021-12-30 | Overhead | R16 | 2021-12-29 | 1 | 17 | 98 | 2 | 115 | 2021 | 2021 | R16
169940239180 | 161157239180 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-14 | 2021-07-14 | 2021-07-15 |  | 2021-11-13 | Overhead | R16 | 2021-10-20 | 1 | 2 | 70 | 18 | 88 | 2021 | 2021 | R16
165333236381 | 166455236381 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-06-23 | 2021-06-23 | 2021-06-23 | 2021-08-18 | 2021-12-09 | Underground | R16 | 2021-08-18 | 1 |  | 41 | 82 | 122 | 2021 | 2021 | R16
161998243534 | 162868243534 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-07-23 | 2021-07-23 | 2021-08-13 |  | 2021-10-25 | Underground | R16 | 2021-08-31 | 1 | 16 | 13 | 40 | 67 | 2021 | 2021 | R16
165920247647 | 164442247647 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-14 | 2021-09-13 | 2021-09-13 | 2021-11-18 | 2022-01-07 | Underground | R16 | 2021-11-18 | 66 |  | 49 | 37 | 150 | 2021 | 2022 | R16
168119240783 | 160181240783 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2021-07-11 | 2021-07-14 | 2021-07-26 |  | 2021-08-23 | Overhead | R16 |  | 3 | 9 |  |  | 31 | 2021 | 2021 | R16
168412243424 | 164227243424 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-06-13 | 2021-07-07 | 2021-08-12 |  | 2023-08-02 | Overhead | R16 |  | 18 | 27 |  |  | 558 | 2021 | 2023 | R16
169631243882 | 162362243882 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-20 | 2021-07-30 | 2021-08-16 | 2021-12-07 | 2021-12-08 | Overhead | R16 | 2021-12-07 | 9 | 12 | 82 | 2 | 102 | 2021 | 2021 | R16
165557240662 | 169120240662 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-06 | 2021-07-06 | 2021-07-25 | 2021-10-26 | 2021-11-30 | Underground | R16 | 2021-10-26 | 1 | 14 | 67 | 26 | 106 | 2021 | 2021 | R16
160158243871 | 163066243871 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-23 | 2021-08-16 | 2021-08-16 |  | 2021-11-13 | Overhead | R16 | 2021-10-21 | 17 |  | 49 | 17 | 81 | 2021 | 2021 | R16
160088276185 | 162787276185 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-07-22 | 2021-08-26 | 2022-04-18 | 2023-07-14 | 2023-08-16 | Underground | R16 | 2023-07-14 | 26 | 168 | 325 | 24 | 540 | 2021 | 2023 | R16
160752200586 | 163843200586 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-08-14 | 2020-08-14 | 2020-08-14 |  | 2021-07-15 | Overhead | R16 |  | 1 |  |  |  | 240 | 2020 | 2021 | R16
168494235410 | 165149235410 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-06-18 | 2021-06-18 | 2021-06-18 |  | 2021-11-13 | Overhead | R16 | 2021-10-21 | 1 |  | 90 | 17 | 106 | 2021 | 2021 | R16
167596249890 | 169316249890 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-07 | 2021-07-07 | 2021-09-29 | 2021-10-27 | 2021-10-28 | Underground | R16 | 2021-10-27 | 1 | 61 | 21 | 2 | 82 | 2021 | 2021 | R16
164996243106 | 168716243106 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-03 | 2021-07-03 | 2021-08-11 |  | 2021-10-25 | Underground | R16 | 2021-09-20 | 0 | 28 | 29 | 26 | 81 | 2021 | 2021 | R16
160419237899 | 166811237899 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-24 | 2021-06-24 | 2021-07-07 | 2021-09-27 | 2021-11-08 | Underground | R16 | 2021-09-27 | 1 | 10 | 59 | 31 | 98 | 2021 | 2021 | R16
168031250345 | 169221250345 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2021-07-07 | 2021-07-07 | 2021-10-01 | 2021-11-18 | 2022-03-07 | Underground | R16 | 2021-11-18 | 1 | 63 | 35 | 78 | 174 | 2021 | 2022 | R16
163980242816 | 161314242816 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-15 | 2021-07-15 | 2021-08-10 |  | 2021-10-25 | Underground | R16 | 2021-09-15 | 1 | 19 | 27 | 29 | 73 | 2021 | 2021 | R16
161048240287 | 162973240287 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-22 | 2021-07-22 | 2021-07-22 | 2022-03-29 | 2022-04-26 | Overhead | R16 | 2022-03-29 | 1 |  | 179 | 21 | 199 | 2021 | 2022 | R16
169593233287 | 161486233287 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-02 | 2021-06-02 | 2021-06-02 | 2021-06-04 | 2021-08-12 | Overhead | R16 | 2021-06-04 | 1 |  | 3 | 50 | 52 | 2021 | 2021 | R16
160912210655 | 164769210655 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-13 | 2020-11-13 | 2020-11-13 |  | 2021-04-15 | Overhead | R16 | 2020-12-21 | 1 |  | 27 | 84 | 110 | 2020 | 2021 | R16
165050238225 | 169728238225 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-09 | 2021-07-09 | 2021-07-09 | 2021-08-25 | 2021-10-25 | Underground | R16 | 2021-08-25 | 1 |  | 34 | 44 | 77 | 2021 | 2021 | R16
166480240023 | 168331240023 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-30 | 2021-06-30 | 2021-07-21 |  | 2021-10-25 | Underground | R16 | 2021-08-25 | 1 | 16 | 26 | 44 | 84 | 2021 | 2021 | R16
168894234271 | 163671234271 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-10 | 2021-06-10 | 2021-06-10 |  | 2022-09-15 | Overhead | R16 |  | 1 |  |  |  | 331 | 2021 | 2022 | R16
167354244981 | 167645244981 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-28 | 2021-06-28 | 2021-08-23 |  | 2022-01-14 | Underground | R16 | 2021-12-09 | 1 | 41 | 79 | 27 | 145 | 2021 | 2022 | R16
163686236234 | 166280236234 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-22 | 2021-06-23 | 2021-06-23 | 2021-09-23 | 2021-09-23 | Overhead | R16 | 2021-09-23 | 2 |  | 67 |  | 68 | 2021 | 2021 | R16
162923271204 | 162470271204 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2021-06-06 | 2021-08-20 | 2022-03-02 | 2022-06-10 | 2022-06-27 | Underground | R16 | 2022-06-10 | 55 | 139 | 73 | 12 | 276 | 2021 | 2022 | R16
167301235208 | 165058235208 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-16 | 2021-06-16 | 2021-06-16 |  | 2021-09-07 | Overhead | R16 | 2021-08-10 | 1 |  | 40 | 21 | 60 | 2021 | 2021 | R16
169635235411 | 165535235411 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-18 | 2021-06-18 | 2021-06-18 |  | 2022-02-10 | Underground | R16 | 2022-01-03 | 1 |  | 142 | 29 | 170 | 2021 | 2022 | R16
163475253863 | 163218253863 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-09 | 2021-06-09 | 2021-10-26 | 2022-04-06 | 2022-04-07 | Underground | R16 | 2022-04-06 | 1 | 100 | 117 | 2 | 217 | 2021 | 2022 | R16
160543241232 | 162317241232 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-20 | 2021-07-29 | 2021-07-29 | 2022-02-02 | 2022-03-03 | Overhead | R16 | 2022-02-02 | 8 |  | 135 | 22 | 163 | 2021 | 2022 | R16
161060204826 | 161767204826 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-18 | 2020-09-18 | 2020-09-23 |  | 2021-01-21 | Overhead | R16 | 2020-10-13 | 1 | 4 | 15 | 73 | 90 | 2020 | 2021 | R16
161264204964 | 163315204964 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-25 | 2020-09-25 | 2020-09-25 |  | 2021-01-20 | Underground | R16 | 2020-10-08 | 1 |  | 10 | 75 | 84 | 2020 | 2021 | R16
162234201616 | 166453201616 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-25 | 2020-08-25 | 2020-08-25 |  | 2020-12-18 | Overhead | R16 | 2020-09-22 | 1 |  | 21 | 64 | 84 | 2020 | 2020 | R16
162348203137 | 169600203137 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-09 | 2020-09-09 | 2020-09-09 |  | 2020-12-18 | Overhead | R16 | 2020-09-21 | 1 |  | 9 | 65 | 73 | 2020 | 2020 | R16
162550204931 | 161590204931 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-17 | 2020-09-17 | 2020-09-25 |  | 2021-11-09 | Overhead | R16 | 2021-10-12 | 1 | 7 | 273 | 21 | 299 | 2020 | 2021 | R16
162603209165 | 160821209165 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-27 | 2020-10-27 | 2020-10-30 |  | 2021-04-07 | Underground | R16 | 2020-11-30 | 1 | 4 | 22 | 93 | 117 | 2020 | 2021 | R16
162792206080 | 165309206080 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-01 | 2020-10-01 | 2020-10-01 |  | 2021-07-26 | Overhead | R16 | 2020-10-29 | 1 |  | 21 | 193 | 213 | 2020 | 2021 | R16
162875204916 | 163200204916 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-24 | 2020-09-24 | 2020-09-24 |  | 2022-10-19 | Overhead | R16 |  | 1 |  |  |  | 540 | 2020 | 2022 | R16
163006206964 | 167204206964 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-12 | 2020-10-12 | 2020-10-12 |  | 2021-04-16 | Overhead | R16 | 2020-12-30 | 1 |  | 58 | 78 | 135 | 2020 | 2021 | R16
163162286588 | 168121286588 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2022-07-21 | 2022-07-21 | 2022-07-22 |  | 2023-03-24 | Underground | R16 |  | 1 | 2 |  |  | 177 | 2022 | 2023 | R16
163190202364 | 167678202364 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-31 | 2020-08-31 | 2020-08-31 |  | 2021-04-23 | Overhead | R16 | 2021-02-03 | 1 |  | 113 | 58 | 170 | 2020 | 2021 | R16
163231212226 | 167424212226 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-30 | 2020-11-30 | 2020-11-30 |  | 2021-04-29 | Overhead | R16 | 2021-02-08 | 1 |  | 51 | 59 | 109 | 2020 | 2021 | R16
163306283847 | 161446283847 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-06-20 | 2022-06-23 | 2022-06-27 |  | 2023-08-16 | Underground | R16 |  | 4 | 3 |  |  | 303 | 2022 | 2023 | R16
164926182684 | 168111182684 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2020-02-05 | 2020-02-05 | 2020-03-02 | 2021-10-12 | 2021-10-28 | Underground | R16 | 2021-10-12 | 1 | 19 | 422 | 13 | 452 | 2020 | 2021 | R16
163173202291 | 165343202291 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-10 | 2020-08-29 | 2020-08-29 | 2020-12-09 | 2021-04-14 | Overhead | R16 | 2020-12-09 | 124 |  | 73 | 91 | 287 | 2020 | 2021 | R16
163339212037 | 167313212037 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-25 | 2020-11-25 | 2020-11-25 |  | 2021-04-15 | Overhead | R16 | 2021-02-11 | 1 |  | 57 | 46 | 102 | 2020 | 2021 | R16
169289185372 | 168269185372 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-26 | 2020-03-26 | 2020-03-26 | 2020-09-21 | 2020-09-23 | Overhead | R16 | 2020-09-21 | 1 |  | 128 | 3 | 130 | 2020 | 2020 | R16
160169181996 | 162838181996 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-27 | 2020-02-27 | 2020-02-27 | 2020-04-08 | 2020-04-09 | Overhead | R16 | 2020-04-08 | 1 |  | 30 | 2 | 31 | 2020 | 2020 | R16
168834214288 | 160759214288 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-06-05 | 2020-06-05 | 2020-12-17 | 2021-01-21 | 2021-02-12 | Underground | R16 | 2021-01-21 | 1 | 140 | 26 | 17 | 181 | 2020 | 2021 | R16
163420204607 | 161896204607 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-18 | 2020-09-18 | 2020-09-22 |  | 2021-01-08 | Overhead | R16 | 2020-10-05 | 1 | 3 | 10 | 70 | 81 | 2020 | 2021 | R16
163427205964 | 165185205964 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-01 | 2020-10-01 | 2020-10-01 |  | 2021-07-24 | Overhead | R16 | 2020-11-09 | 1 |  | 28 | 185 | 212 | 2020 | 2021 | R16
169415193842 | 161398193842 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-09 | 2020-06-09 | 2020-06-09 | 2020-06-24 | 2020-06-26 | Overhead | R16 | 2020-06-24 | 1 |  | 12 | 3 | 14 | 2020 | 2020 | R16
165437192630 | 169812192630 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-29 | 2020-05-29 | 2020-05-29 | 2020-08-27 | 2020-10-29 | Overhead | R16 | 2020-08-27 | 1 |  | 65 | 46 | 110 | 2020 | 2020 | R16
166543182097 | 162875182097 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-27 | 2020-02-27 | 2020-02-27 | 2020-05-23 | 2020-05-26 | Overhead | R16 | 2020-05-23 | 1 |  | 62 | 2 | 64 | 2020 | 2020 | R16
163449247801 | 164308247801 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-05-11 | 2021-07-09 | 2021-09-13 |  | 2021-11-09 | Overhead | R16 |  | 44 | 47 |  |  | 131 | 2021 | 2021 | R16
163466249859 | 162919249859 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2021-09-02 | 2021-09-09 | 2021-09-29 |  | 2022-04-21 | Overhead | R16 |  | 6 | 15 |  |  | 166 | 2021 | 2022 | R16
165322182090 | 162829182090 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-27 | 2020-02-27 | 2020-02-27 | 2021-08-10 | 2021-09-10 | Overhead | R16 | 2021-08-10 | 1 |  | 379 | 24 | 402 | 2020 | 2021 | R16
162754183735 | 165575183735 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-11 | 2020-03-11 | 2020-03-11 | 2020-04-30 | 2020-05-01 | Overhead | R16 | 2020-04-30 | 1 |  | 37 | 2 | 38 | 2020 | 2020 | R16
167185175473 | 160884175473 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-02 | 2020-01-02 | 2020-01-03 | 2020-02-11 | 2020-02-12 | Overhead | R16 | 2020-02-11 | 1 | 2 | 28 | 2 | 30 | 2020 | 2020 | R16
163578204168 | 165697204168 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG R16 ELECTRIC RELOCATION UD | Residential | 2020-01-24 | 2020-01-24 | 2020-09-17 | 2021-06-08 | 2021-03-26 | Underground | R16 | 2021-06-08 | 1 | 170 | 189 |  | 306 | 2020 | 2021 | R16
164538178265 | 161141178265 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-03 | 2020-01-06 | 2020-01-27 | 2020-02-06 | 2020-02-12 | Underground | R16 | 2020-02-06 | 2 | 16 | 9 | 5 | 29 | 2020 | 2020 | R16
164957202611 | 167534202611 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-02-03 | 2020-02-03 | 2020-09-03 | 2020-10-30 | 2021-04-06 | Underground | R16 | 2020-10-30 | 1 | 154 | 42 | 113 | 307 | 2020 | 2021 | R16
161155177828 | 164780177828 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-21 | 2020-01-21 | 2020-01-23 | 2020-03-04 | 2020-03-09 | Overhead | R16 | 2020-03-04 | 1 | 3 | 30 | 4 | 35 | 2020 | 2020 | R16
167787182807 | 163995182807 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-04 | 2020-03-04 | 2020-03-04 | 2020-05-05 | 2020-07-08 | Overhead | R16 | 2020-05-05 | 1 |  | 45 | 47 | 91 | 2020 | 2020 | R16
163693207603 | 168419207603 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-19 | 2020-10-19 | 2020-10-19 |  | 2021-11-10 | Overhead | R16 | 2020-11-16 | 1 |  | 21 | 258 | 278 | 2020 | 2021 | R16
165648202350 | 168681202350 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-27 | 2020-03-27 | 2020-08-31 | 2020-11-21 | 2021-02-12 | Underground | R16 | 2020-11-21 | 1 | 112 | 60 | 60 | 231 | 2020 | 2021 | R16
169119178818 | 166967178818 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-31 | 2020-01-31 | 2020-01-31 | 2020-03-21 | 2020-03-30 | Overhead | R16 | 2020-03-21 | 1 |  | 36 | 6 | 42 | 2020 | 2020 | R16
169444186786 | 160629186786 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-08 | 2020-04-08 | 2020-04-08 | 2020-06-01 | 2020-06-02 | Overhead | R16 | 2020-06-01 | 1 |  | 39 | 2 | 40 | 2020 | 2020 | R16
165128199041 | 165009199041 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-01-22 | 2020-01-22 | 2020-07-30 | 2021-01-20 | 2021-02-27 | Underground | R16 | 2021-01-20 | 1 | 137 | 125 | 28 | 288 | 2020 | 2021 | R16
160447178598 | 161943178598 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-08 | 2020-01-31 | 2020-01-31 | 2020-02-28 | 2020-06-09 | Overhead | R16 | 2020-02-28 | 18 |  | 21 | 73 | 110 | 2020 | 2020 | R16
163785283131 | 165103283131 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-05-01 | 2020-05-26 | 2022-06-20 | 2022-08-04 | 2022-08-04 | Underground | R16 | 2022-08-04 | 18 | 540 | 34 |  | 590 | 2020 | 2022 | R16
167828186895 | 167852186895 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-02-04 | 2020-02-04 | 2020-04-09 | 2023-01-14 | 2023-01-17 | Underground | R16 | 2023-01-14 | 1 | 48 | 722 | 2 | 771 | 2020 | 2023 | R16
163965206677 | 167033206677 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-09 | 2020-10-09 | 2020-10-09 |  | 2021-04-13 | Overhead | R16 | 2020-12-07 | 1 |  | 42 | 92 | 133 | 2020 | 2021 | R16
163977208700 | 167762208700 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2020-10-14 | 2020-10-14 | 2020-10-27 |  | 2023-08-02 | Underground | R16 |  | 1 | 10 |  |  | 731 | 2020 | 2023 | R16
162106183678 | 165761183678 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-11 | 2020-03-11 | 2020-03-11 | 2020-03-25 | 2023-06-07 | Overhead | R16 | 2020-03-25 | 1 |  | 11 | 836 | 846 | 2020 | 2023 | R16
164008205868 | 163611205868 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-25 | 2020-09-25 | 2020-09-30 |  | 2021-04-07 | Overhead | R16 | 2020-11-30 | 1 | 4 | 44 | 93 | 139 | 2020 | 2021 | R16
165285216709 | 166794216709 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2020-05-12 | 2020-08-29 | 2021-01-11 | 2022-03-24 | 2022-04-15 | Underground | R16 | 2022-03-24 | 79 | 96 | 314 | 17 | 504 | 2020 | 2022 | R16
164204202646 | 168261202646 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-02 | 2020-09-02 | 2020-09-02 |  | 2022-06-01 | Overhead | R16 | 2020-10-30 | 1 |  | 43 | 414 | 456 | 2020 | 2022 | R16
166811256254 | 169007256254 | RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Residential | 2020-05-26 | 2020-09-08 | 2021-11-12 | 2023-06-26 | 2023-10-03 | Underground | R16 | 2023-06-26 | 76 | 309 | 422 | 72 | 876 | 2020 | 2023 | R16
162054202619 | 162024202619 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-06-12 | 2020-08-20 | 2020-09-04 | 2020-10-19 | 2021-02-24 | Underground | R16 | 2020-10-19 | 50 | 12 | 32 | 93 | 184 | 2020 | 2021 | R16
163070188244 | 164145188244 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-04 | 2020-03-04 | 2020-04-20 | 2021-06-29 | 2022-08-03 | Underground | R16 | 2021-06-29 | 1 | 34 | 312 | 287 | 631 | 2020 | 2022 | R16
164476203993 | 161261203993 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-16 | 2020-09-16 | 2020-09-16 |  | 2021-01-20 | Overhead | R16 | 2020-10-08 | 1 |  | 17 | 75 | 91 | 2020 | 2021 | R16
166597200616 | 166598200616 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-08 | 2020-07-08 | 2020-08-16 | 2020-09-15 | 2020-09-16 | Underground | R16 | 2020-09-15 | 1 | 28 | 22 | 2 | 51 | 2020 | 2020 | R16
164486206493 | 166335206493 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-07 | 2020-10-07 | 2020-10-07 |  | 2021-07-26 | Overhead | R16 | 2020-10-29 | 1 |  | 17 | 193 | 209 | 2020 | 2021 | R16
166971175145 | 169956175145 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-26 | 2019-12-26 | 2019-12-26 | 2020-03-26 | 2020-06-09 | Overhead | R16 | 2020-03-26 | 1 |  | 66 | 54 | 119 | 2019 | 2020 | R16
167229189509 | 164495189509 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-29 | 2020-04-29 | 2020-04-30 | 2020-05-18 | 2020-05-21 | Overhead | R16 | 2020-05-18 | 1 | 2 | 13 | 4 | 17 | 2020 | 2020 | R16
165789233597 | 166245233597 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-06 | 2020-07-16 | 2021-06-05 | 2021-07-27 | 2021-07-29 | Underground | R16 | 2021-07-27 | 9 | 232 | 37 | 3 | 279 | 2020 | 2021 | R16
165106201890 | 167005201890 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-08-27 | 2020-08-27 | 2020-08-27 |  | 2020-11-06 | Overhead | R16 | 2020-08-31 | 1 |  | 3 | 50 | 52 | 2020 | 2020 | R16
167246200618 | 167119200618 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-10 | 2020-07-10 | 2020-08-16 | 2020-09-15 | 2020-09-16 | Underground | R16 | 2020-09-15 | 1 | 26 | 22 | 2 | 49 | 2020 | 2020 | R16
163958175304 | 160325175304 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-12-30 | 2019-12-30 | 2019-12-30 | 2020-02-17 | 2020-02-19 | Underground | R16 | 2020-02-17 | 1 |  | 36 | 3 | 38 | 2019 | 2020 | R16
162543179001 | 167242179001 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-01 | 2020-02-01 | 2020-02-01 | 2020-05-27 | 2020-05-28 | Overhead | R16 | 2020-05-27 | 0 |  | 83 | 2 | 84 | 2020 | 2020 | R16
160701204984 | 160639204984 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-04-08 | 2020-06-29 | 2020-09-24 | 2020-12-16 | 2021-03-27 | Underground | R16 | 2020-12-16 | 59 | 64 | 60 | 73 | 253 | 2020 | 2021 | R16
169536184360 | 166196184360 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-13 | 2020-03-17 | 2020-03-17 | 2020-05-29 | 2020-06-01 | Underground | R16 | 2020-05-29 | 3 |  | 54 | 2 | 57 | 2020 | 2020 | R16
160754180356 | 163289180356 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-01-14 | 2020-01-14 | 2020-02-13 | 2021-11-05 | 2021-12-08 | Underground | R16 | 2021-11-05 | 1 | 23 | 452 | 24 | 497 | 2020 | 2021 | R16
165326193277 | 160843193277 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-18 | 2020-02-18 | 2020-06-05 | 2020-07-28 | 2020-07-29 | Overhead | R16 | 2020-07-28 | 1 | 79 | 38 | 2 | 117 | 2020 | 2020 | R16
168767192980 | 169979192980 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2021-02-14 | 2021-02-17 | Underground | R16 | 2021-02-14 | 1 |  | 185 | 3 | 188 | 2020 | 2021 | R16
160509194573 | 162622194573 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-17 | 2020-06-17 | 2020-06-17 | 2020-10-06 | 2021-01-20 | Overhead | R16 | 2020-10-06 | 1 |  | 80 | 77 | 156 | 2020 | 2021 | R16
169026184368 | 163843184368 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-16 | 2020-01-16 | 2020-03-17 | 2020-06-03 | 2020-06-03 | Underground | R16 | 2020-06-03 | 1 | 44 | 57 |  | 100 | 2020 | 2020 | R16
165526184623 | 166914184623 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-18 | 2020-03-18 | 2020-03-18 | 2020-05-15 | 2020-05-19 | Overhead | R16 | 2020-05-15 | 1 |  | 43 | 3 | 45 | 2020 | 2020 | R16
169789189862 | 164131189862 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-01-16 | 2020-03-23 | 2020-05-04 | 2021-04-19 | 2021-05-24 | Underground | R16 | 2021-04-19 | 48 | 31 | 251 | 26 | 353 | 2020 | 2021 | R16
165907197897 | 168016197897 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-07-14 | 2020-07-15 | 2020-07-21 | 2020-11-24 | 2022-01-31 | Overhead | R16 | 2020-11-24 | 2 | 5 | 91 | 310 | 405 | 2020 | 2022 | R16
165353203843 | 160512203843 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-11 | 2020-09-11 | 2020-09-14 |  | 2021-02-17 | Overhead | R16 | 2020-10-19 | 1 | 2 | 26 | 88 | 114 | 2020 | 2021 | R16
165016192450 | 169248192450 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-27 | 2020-05-27 | 2020-05-27 | 2020-05-28 | 2020-08-28 | Overhead | R16 | 2020-05-28 | 1 |  | 2 | 67 | 68 | 2020 | 2020 | R16
165531184343 | 169874184343 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-02-13 | 2020-02-13 | 2020-03-17 | 2021-06-18 | 2021-11-04 | Underground | R16 | 2021-06-18 | 1 | 24 | 329 | 100 | 451 | 2020 | 2021 | R16
164388184251 | 167930184251 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-02-04 | 2020-03-16 | 2020-03-16 | 2020-12-16 | 2020-12-18 | Underground | R16 | 2020-12-16 | 30 |  | 198 | 3 | 229 | 2020 | 2020 | R16
169188198321 | 161138198321 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-08 | 2020-07-23 | 2020-07-23 | 2020-09-30 | 2021-01-08 | Overhead | R16 | 2020-09-30 | 34 |  | 50 | 73 | 155 | 2020 | 2021 | R16
162289196238 | 165950196238 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-02 | 2020-07-02 | 2020-07-02 | 2020-07-14 | 2020-10-06 | Overhead | R16 | 2020-07-14 | 1 |  | 9 | 61 | 69 | 2020 | 2020 | R16
165620184971 | 165674184971 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-23 | 2020-01-23 | 2020-03-23 | 2020-03-27 | 2020-03-30 | Underground | R16 | 2020-03-27 | 1 | 43 | 5 | 2 | 48 | 2020 | 2020 | R16
166294210407 | 166239210407 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-24 | 2020-08-24 | 2020-11-11 |  | 2021-04-20 | Overhead | R16 | 2021-01-11 | 1 | 58 | 44 | 72 | 172 | 2020 | 2021 | R16
166364204112 | 161584204112 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-17 | 2020-09-17 | 2020-09-17 |  | 2021-08-03 | Overhead | R16 | 2021-03-29 | 1 |  | 138 | 92 | 229 | 2020 | 2021 | R16
164325225387 | 164314225387 | Electric Vehicle | UG R16 RESD AND NON RESD UD | Commercial | 2020-03-05 | 2020-09-24 | 2021-03-31 | 2021-07-15 | 2023-09-17 | Underground | R16 | 2021-07-15 | 146 | 135 | 77 | 567 | 922 | 2020 | 2023 | R16
164479179865 | 166876179865 | INDUSTRIAL | R16 RESD AND NON RESD US | Residential | 2020-01-30 | 2020-01-30 | 2020-02-10 | 2020-02-12 | 2021-03-10 | Underground | R16 | 2020-02-12 | 1 | 8 | 3 | 281 | 290 | 2020 | 2021 | R16
169341214463 | 163046214463 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-02-28 | 2020-02-28 | 2020-12-18 | 2023-01-11 | 2022-12-01 | Underground | R16 | 2023-01-11 | 1 | 211 | 539 |  | 720 | 2020 | 2022 | R16
169554195308 | 164267195308 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-25 | 2020-06-25 | 2020-06-25 | 2020-07-20 | 2023-06-08 | Overhead | R16 | 2020-07-20 | 1 |  | 18 | 754 | 771 | 2020 | 2023 | R16
166498205416 | 164068205416 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-28 | 2020-09-28 | 2020-09-28 |  | 2021-06-03 | Overhead | R16 | 2021-03-11 | 1 |  | 119 | 61 | 179 | 2020 | 2021 | R16
166527203084 | 169340203084 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-08 | 2020-09-08 | 2020-09-08 |  | 2020-12-18 | Overhead | R16 | 2020-09-16 | 1 |  | 7 | 68 | 74 | 2020 | 2020 | R16
166528206288 | 165932206288 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-05 | 2020-10-06 | 2020-10-06 |  | 2021-07-24 | Underground | R16 | 2020-11-10 | 2 |  | 26 | 184 | 210 | 2020 | 2021 | R16
168686183751 | 169973183751 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-14 | 2020-02-14 | 2020-03-10 | 2020-05-05 | 2020-07-07 | Underground | R16 | 2020-05-05 | 1 | 18 | 41 | 46 | 103 | 2020 | 2020 | R16
166625207390 | 167273207390 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-12 | 2020-10-15 | 2020-10-15 |  | 2021-11-05 | Underground | R16 | 2021-04-09 | 4 |  | 127 | 151 | 280 | 2020 | 2021 | R16
167710192563 | 169490192563 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-28 | 2020-05-28 | 2020-05-28 | 2020-09-10 | 2020-09-17 | Underground | R16 | 2020-09-10 | 1 |  | 76 | 6 | 81 | 2020 | 2020 | R16
160719189435 | 168211189435 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-03-25 | 2020-03-25 | 2020-04-30 | 2021-05-25 | 2021-10-05 | Underground | R16 | 2021-05-25 | 1 | 27 | 279 | 96 | 400 | 2020 | 2021 | R16
169185197336 | 162870197336 | NON-RESIDENTIAL - LARGE OFFICE | R16 RESD AND NON RESD US | Commercial | 2020-02-27 | 2020-03-30 | 2020-07-16 | 2020-12-27 | 2021-10-18 | Underground | R16 | 2020-12-27 | 23 | 79 | 117 | 211 | 428 | 2020 | 2021 | R16
160876187311 | 160945187311 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-09 | 2020-04-09 | 2020-04-13 | 2021-01-05 | 2021-01-08 | Overhead | R16 | 2021-01-05 | 1 | 3 | 192 | 4 | 197 | 2020 | 2021 | R16
166620181886 | 162414181886 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-25 | 2020-02-25 | 2020-02-25 | 2020-04-27 | 2020-07-02 | Overhead | R16 | 2020-04-27 | 1 |  | 45 | 49 | 93 | 2020 | 2020 | R16
167346188426 | 168948188426 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-30 | 2020-03-30 | 2020-04-20 | 2020-07-30 | 2020-08-11 | Underground | R16 | 2020-07-30 | 1 | 16 | 74 | 9 | 97 | 2020 | 2020 | R16
166782215941 | 164033215941 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-30 | 2020-12-30 | 2020-12-30 |  | 2021-08-10 | Overhead | R16 | 2021-03-19 | 1 |  | 58 | 103 | 160 | 2020 | 2021 | R16
166852201817 | 166853201817 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-26 | 2020-08-26 | 2020-08-26 |  | 2021-08-23 | Overhead | R16 | 2021-08-04 | 1 |  | 246 | 14 | 259 | 2020 | 2021 | R16
163834179946 | 161142179946 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-03 | 2020-01-06 | 2020-02-10 | 2020-04-02 | 2020-04-03 | Underground | R16 | 2020-04-02 | 2 | 26 | 39 | 2 | 66 | 2020 | 2020 | R16
164197197141 | 167297197141 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-13 | 2020-07-13 | 2020-07-13 | 2020-09-03 | 2020-09-04 | Overhead | R16 | 2020-09-03 | 1 |  | 39 | 2 | 40 | 2020 | 2020 | R16
169539191340 | 160786191340 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-09 | 2020-04-09 | 2020-05-17 | 2020-06-08 | 2020-08-28 | Overhead | R16 | 2020-06-08 | 1 | 27 | 16 | 60 | 102 | 2020 | 2020 | R16
163309178560 | 166420178560 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-28 | 2020-01-28 | 2020-01-29 | 2020-03-06 | 2020-03-09 | Overhead | R16 | 2020-03-06 | 1 | 2 | 28 | 2 | 30 | 2020 | 2020 | R16
163672193184 | 164460193184 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-28 | 2020-04-29 | 2020-06-03 | 2020-07-10 | 2020-07-10 | Underground | R16 | 2020-07-10 | 2 | 26 | 28 |  | 54 | 2020 | 2020 | R16
163057184383 | 166651184383 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-17 | 2020-03-17 | 2020-03-17 | 2021-04-23 | 2021-04-26 | Overhead | R16 | 2021-04-23 | 1 |  | 289 | 2 | 290 | 2020 | 2021 | R16
167823174917 | 169425174917 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-19 | 2019-12-19 | 2019-12-19 | 2020-03-01 | 2020-03-05 | Overhead | R16 | 2020-03-01 | 1 |  | 52 | 4 | 56 | 2019 | 2020 | R16
164830199075 | 167764199075 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-13 | 2020-07-23 | 2020-07-30 | 2020-10-06 | 2021-01-21 | Overhead | R16 | 2020-10-06 | 9 | 6 | 49 | 78 | 139 | 2020 | 2021 | R16
163101193323 | 164359193323 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-28 | 2020-06-05 | 2020-06-05 | 2021-03-22 | 2021-05-18 | Overhead | R16 | 2021-03-22 | 29 |  | 207 | 42 | 276 | 2020 | 2021 | R16
167138213986 | 160636213986 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-14 | 2020-12-14 | 2020-12-14 |  | 2021-11-08 | Overhead | R16 | 2021-05-28 | 1 |  | 120 | 117 | 236 | 2020 | 2021 | R16
162062195447 | 164802195447 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-26 | 2020-06-26 | 2020-06-26 | 2020-07-30 | 2020-10-06 | Overhead | R16 | 2020-07-30 | 1 |  | 25 | 49 | 73 | 2020 | 2020 | R16
167169207235 | 167370207235 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-12 | 2020-10-12 | 2020-10-15 |  | 2021-11-08 | Overhead | R16 | 2021-05-19 | 1 | 4 | 155 | 124 | 281 | 2020 | 2021 | R16
169318212807 | 165316212807 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-01-22 | 2020-01-22 | 2020-12-04 | 2021-01-22 | 2021-04-01 | Underground | R16 | 2021-01-22 | 1 | 228 | 36 | 50 | 312 | 2020 | 2021 | R16
167195246331 | 162013246331 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2021-08-30 | 2021-08-30 | 2021-09-02 |  | 2023-08-02 | Underground | R16 |  | 1 | 4 |  |  | 503 | 2021 | 2023 | R16
165863224401 | 165864224401 | Electric Vehicle | UG R16 RESD AND NON RESD UD | Commercial | 2020-03-12 | 2020-11-11 | 2021-03-22 | 2022-02-18 | 2022-03-17 | Underground | R16 | 2022-02-18 | 175 | 94 | 240 | 20 | 526 | 2020 | 2022 | R16
163346197970 | 167146197970 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-07-10 | 2020-07-13 | 2020-07-22 | 2022-02-08 | 2022-03-01 | Overhead | R16 | 2022-02-08 | 2 | 8 | 405 | 16 | 428 | 2020 | 2022 | R16
167269207292 | 167383207292 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-12 | 2020-10-12 | 2020-10-15 |  | 2021-04-15 | Overhead | R16 | 2020-12-23 | 1 | 4 | 50 | 82 | 134 | 2020 | 2021 | R16
165454181338 | 160889181338 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-03 | 2020-01-06 | 2020-02-22 | 2020-04-21 | 2020-04-22 | Underground | R16 | 2020-04-21 | 2 | 35 | 42 | 2 | 79 | 2020 | 2020 | R16
167380204614 | 161850204614 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-18 | 2020-09-22 | 2020-09-22 |  | 2021-07-26 | Underground | R16 | 2020-11-05 | 3 |  | 33 | 188 | 222 | 2020 | 2021 | R16
168276230696 | 160327230696 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-06-03 | 2021-05-13 | 2021-05-13 | 2021-08-05 | 2022-03-03 | Overhead | R16 | 2021-08-05 | 247 |  | 61 | 151 | 457 | 2020 | 2022 | R16
167382221386 | 165946221386 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-23 | 2021-02-23 | 2021-02-23 |  | 2021-11-04 | Overhead | R16 | 2021-04-01 | 1 |  | 28 | 156 | 183 | 2021 | 2021 | R16
169792199496 | 169768199496 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-29 | 2020-05-29 | 2020-08-04 | 2020-08-06 | 2020-10-06 | Underground | R16 | 2020-08-06 | 1 | 48 | 3 | 44 | 93 | 2020 | 2020 | R16
167464207119 | 167867207119 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-14 | 2020-10-14 | 2020-10-14 |  | 2022-10-19 | Overhead | R16 |  | 1 |  |  |  | 526 | 2020 | 2022 | R16
163445193987 | 164384193987 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-29 | 2020-04-29 | 2020-06-11 | 2020-06-11 | 2020-08-28 | Overhead | R16 | 2020-06-11 | 1 | 32 |  | 57 | 88 | 2020 | 2020 | R16
165529190086 | 169165190086 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-31 | 2020-03-31 | 2020-05-05 | 2021-05-05 | 2021-10-25 | Underground | R16 | 2021-05-05 | 1 | 26 | 262 | 124 | 410 | 2020 | 2021 | R16
160421200601 | 161633200601 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-10 | 2020-06-11 | 2020-08-13 | 2021-02-26 | 2021-03-01 | Underground | R16 | 2021-02-26 | 2 | 46 | 142 | 2 | 189 | 2020 | 2021 | R16
165992181411 | 160353181411 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-30 | 2020-01-06 | 2020-02-21 | 2020-03-06 | 2020-09-15 | Underground | R16 | 2020-03-06 | 6 | 35 | 11 | 138 | 187 | 2019 | 2020 | R16
167534209240 | 160749209240 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-10-27 | 2020-10-28 | 2020-10-30 |  | 2021-07-26 | Overhead | R16 |  | 2 | 3 |  |  | 195 | 2020 | 2021 | R16
163258195274 | 160877195274 | NON-RESIDENTIAL - WAREHOUSE | UG R16 RESD AND NON RESD UD | Commercial | 2020-02-19 | 2020-05-18 | 2020-06-24 | 2020-11-10 | 2020-12-16 | Underground | R16 | 2020-11-10 | 64 | 28 | 100 | 27 | 216 | 2020 | 2020 | R16
167631210117 | 164523210117 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-29 | 2020-09-29 | 2020-11-10 |  | 2021-04-14 | Overhead | R16 | 2020-12-16 | 1 | 31 | 27 | 86 | 142 | 2020 | 2021 | R16
162758186555 | 160481186555 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-07 | 2020-04-07 | 2020-04-07 | 2020-05-05 | 2020-05-06 | Overhead | R16 | 2020-05-05 | 1 |  | 21 | 2 | 22 | 2020 | 2020 | R16
160729187667 | 161821187667 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-14 | 2020-04-15 | 2020-04-15 | 2020-06-03 | 2020-06-05 | Overhead | R16 | 2020-06-03 | 2 |  | 36 | 3 | 39 | 2020 | 2020 | R16
160924177503 | 168913177503 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-17 | 2019-12-17 | 2020-01-21 |  | 2020-06-09 | Overhead | R16 |  | 1 | 26 |  |  | 126 | 2019 | 2020 | R16
166932190652 | 161104190652 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-19 | 2020-02-19 | 2020-05-12 | 2020-07-02 | 2020-07-29 | Underground | R16 | 2020-07-02 | 1 | 60 | 38 | 20 | 116 | 2020 | 2020 | R16
163693178451 | 164540178451 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-18 | 2020-01-18 | 2020-01-28 | 2020-03-04 | 2020-03-09 | Underground | R16 | 2020-03-04 | 0 | 7 | 27 | 4 | 36 | 2020 | 2020 | R16
162597182877 | 162610182877 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-02-26 | 2020-02-26 | 2020-03-04 | 2021-08-19 | 2023-10-04 | Overhead | R16 | 2021-08-19 | 1 | 6 | 382 | 555 | 941 | 2020 | 2023 | R16
163590186123 | 169415186123 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-04-01 | 2020-04-01 | 2020-04-01 | 2020-08-13 | 2021-01-07 | Underground | R16 | 2020-08-13 | 1 |  | 97 | 106 | 202 | 2020 | 2021 | R16
169819186031 | 169438186031 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-01 | 2020-04-01 | 2020-04-01 | 2022-06-22 | 2022-06-23 | Overhead | R16 | 2022-06-22 | 1 |  | 581 | 2 | 582 | 2020 | 2022 | R16
167960206586 | 169726206586 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-09 | 2020-09-09 | 2020-10-08 |  | 2022-06-28 | Underground | R16 |  | 1 | 22 |  |  | 470 | 2020 | 2022 | R16
160164176980 | 163133176980 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-13 | 2020-01-13 | 2020-01-14 | 2020-05-21 | 2020-05-22 | Overhead | R16 | 2020-05-21 | 1 | 2 | 93 | 2 | 95 | 2020 | 2020 | R16
160737188867 | 162421188867 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-17 | 2020-04-21 | 2020-04-23 | 2020-05-19 | 2020-08-14 | Underground | R16 | 2020-05-19 | 3 | 3 | 19 | 64 | 86 | 2020 | 2020 | R16
161397197119 | 163003197119 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-17 | 2020-06-30 | 2020-07-15 | 2020-08-31 | 2020-09-04 | Underground | R16 | 2020-08-31 | 10 | 12 | 34 | 5 | 58 | 2020 | 2020 | R16
168090208766 | 169608208766 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-09 | 2020-09-09 | 2020-10-28 |  | 2021-08-18 | Underground | R16 | 2021-03-24 | 1 | 36 | 106 | 106 | 246 | 2020 | 2021 | R16
168129214033 | 160976214033 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-15 | 2020-12-15 | 2020-12-15 |  | 2021-11-08 | Overhead | R16 | 2021-05-19 | 1 |  | 112 | 124 | 235 | 2020 | 2021 | R16
163179177988 | 165717177988 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-24 | 2020-01-24 | 2020-01-24 | 2020-03-04 | 2020-03-05 | Overhead | R16 | 2020-03-04 | 1 |  | 29 | 2 | 30 | 2020 | 2020 | R16
164418190185 | 169109190185 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-12-18 | 2020-04-07 | 2020-05-06 | 2020-07-07 | 2020-07-08 | Underground | R16 | 2020-07-07 | 80 | 22 | 45 | 2 | 146 | 2019 | 2020 | R16
166324180912 | 160831180912 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-18 | 2020-02-18 | 2020-02-18 | 2020-03-06 | 2020-06-09 | Overhead | R16 | 2020-03-06 | 1 |  | 14 | 68 | 81 | 2020 | 2020 | R16
169175174899 | 169183174899 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-18 | 2019-12-18 | 2019-12-20 | 2020-01-19 | 2020-01-23 | Overhead | R16 | 2020-01-19 | 1 | 3 | 21 | 4 | 27 | 2019 | 2020 | R16
167729189443 | 163968189443 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-01-16 | 2020-01-16 | 2020-04-29 | 2020-10-21 | 2021-01-26 | Overhead | R16 | 2020-10-21 | 1 | 75 | 126 | 70 | 269 | 2020 | 2021 | R16
169472191864 | 169800191864 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-04-02 | 2020-04-02 | 2020-05-21 | 2023-04-21 | 2023-04-27 | Underground | R16 | 2023-04-21 | 1 | 36 | 762 | 5 | 801 | 2020 | 2023 | R16
169235238584 | 166919238584 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2020-01-30 | 2020-10-02 | 2022-06-24 | 2022-07-18 | 2022-08-02 | Underground | R16 | 2022-07-18 | 177 | 451 | 17 | 12 | 654 | 2020 | 2022 | R16
168396208780 | 160843208780 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-27 | 2020-10-27 | 2020-10-27 |  | 2021-06-03 | Overhead | R16 | 2021-03-08 | 1 |  | 95 | 64 | 158 | 2020 | 2021 | R16
168465216970 | 168759216970 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-09-04 | 2020-09-04 | 2021-01-13 |  | 2021-08-11 | Underground | R16 | 2021-03-24 | 1 | 94 | 51 | 101 | 244 | 2020 | 2021 | R16
169342243964 | 163058243964 | NON-RESIDENTIAL - LODGING | UG R16 RESD AND NON RESD UD | Commercial | 2020-06-18 | 2020-07-30 | 2021-08-16 | 2022-12-06 | 2022-12-21 | Underground | R16 | 2022-12-06 | 31 | 273 | 342 | 12 | 655 | 2020 | 2022 | R16
161132196118 | 166033196118 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-07-02 | 2020-07-02 | 2020-07-02 | 2020-07-21 | 2020-10-06 | Overhead | R16 | 2020-07-21 | 1 |  | 14 | 56 | 69 | 2020 | 2020 | R16
166563196497 | 164184196497 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-06-24 | 2020-06-24 | 2020-07-07 | 2020-07-30 | 2020-11-19 | Underground | R16 | 2020-07-30 | 1 | 10 | 18 | 81 | 107 | 2020 | 2020 | R16
162752211376 | 162648211376 | SPECIFIC BUDGET PROJECTS | UG R16 RESD AND NON RESD UD | Commercial | 2020-04-20 | 2020-08-28 | 2020-11-20 |  | 2021-03-03 | Underground | R16 |  | 95 | 61 |  |  | 228 | 2020 | 2021 | R16
168602213025 | 168648213025 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-03 | 2020-09-03 | 2020-12-07 |  | 2021-10-27 | Underground | R16 | 2021-08-12 | 1 | 68 | 179 | 55 | 300 | 2020 | 2021 | R16
163055178741 | 166675178741 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-30 | 2020-01-30 | 2020-01-30 | 2020-04-17 | 2020-06-09 | Overhead | R16 | 2020-04-17 | 1 |  | 57 | 38 | 94 | 2020 | 2020 | R16
168639214243 | 161255214243 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-16 | 2020-12-16 | 2020-12-16 |  | 2021-04-23 | Overhead | R16 | 2021-02-04 | 1 |  | 37 | 57 | 93 | 2020 | 2021 | R16
167917174993 | 169926174993 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-23 | 2019-12-23 | 2019-12-26 | 2020-01-02 | 2021-11-10 | Overhead | R16 | 2020-01-02 | 1 | 4 | 6 | 485 | 493 | 2019 | 2021 | R16
169426196224 | 161181196224 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-08 | 2020-06-30 | 2020-06-30 | 2020-09-03 | 2020-12-18 | Overhead | R16 | 2020-09-03 | 17 |  | 48 | 77 | 140 | 2020 | 2020 | R16
160847192041 | 168667192041 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-22 | 2020-05-22 | 2020-05-22 | 2020-05-28 | 2020-06-12 | Overhead | R16 | 2020-05-28 | 1 |  | 5 | 12 | 16 | 2020 | 2020 | R16
162234197417 | 165784197417 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OD | Commercial | 2020-07-01 | 2020-07-01 | 2020-07-16 | 2020-12-31 | 2023-06-07 | Overhead | R16 | 2020-12-31 | 1 | 12 | 121 | 635 | 766 | 2020 | 2023 | R16
168888215268 | 161955215268 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-21 | 2020-12-21 | 2020-12-21 |  | 2021-08-23 | Underground | R16 | 2021-07-27 | 1 |  | 157 | 20 | 176 | 2020 | 2021 | R16
168932179045 | 167358179045 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-03 | 2020-02-03 | 2020-02-03 | 2020-03-06 | 2020-03-09 | Overhead | R16 | 2020-03-06 | 1 |  | 25 | 2 | 26 | 2020 | 2020 | R16
166137178882 | 169511178882 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-12-19 | 2019-12-19 | 2020-01-31 | 2021-12-28 | 2021-12-30 | Underground | R16 | 2021-12-28 | 1 | 32 | 498 | 3 | 531 | 2019 | 2021 | R16
168630191437 | 160514191437 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OD | Commercial | 2020-02-14 | 2020-02-14 | 2020-05-19 |  | 2020-12-21 | Overhead | R16 |  | 1 | 68 |  |  | 222 | 2020 | 2020 | R16
164371187573 | 161921187573 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-15 | 2020-04-15 | 2020-04-15 | 2020-06-03 | 2020-06-03 | Overhead | R16 | 2020-06-03 | 1 |  | 36 |  | 36 | 2020 | 2020 | R16
166051283885 | 166017283885 | SPECIFIC BUDGET PROJECTS | UG R16 RESD AND NON RESD UD | Commercial | 2020-05-07 | 2020-10-23 | 2022-06-27 | 2023-09-15 | 2023-09-15 | Underground | R16 | 2023-09-15 | 122 | 437 | 320 |  | 877 | 2020 | 2023 | R16
169370206250 | 166083206250 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-06 | 2020-10-06 | 2020-10-06 |  | 2021-07-19 | Overhead | R16 | 2020-11-18 | 1 |  | 32 | 174 | 205 | 2020 | 2021 | R16
166768181833 | 162273181833 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-25 | 2020-02-25 | 2020-02-25 | 2020-04-30 | 2020-04-30 | Overhead | R16 | 2020-04-30 | 1 |  | 48 |  | 48 | 2020 | 2020 | R16
166558190259 | 166031190259 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-07 | 2020-05-07 | 2020-05-07 | 2020-06-18 | 2021-05-19 | Overhead | R16 | 2020-06-18 | 1 |  | 31 | 240 | 270 | 2020 | 2021 | R16
169698174497 | 168968174497 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-17 | 2019-12-17 | 2019-12-17 | 2020-02-04 | 2020-02-05 | Overhead | R16 | 2020-02-04 | 1 |  | 36 | 2 | 37 | 2019 | 2020 | R16
161595188970 | 163166188970 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-22 | 2020-04-24 | 2020-04-24 | 2020-07-14 | 2020-07-17 | Overhead | R16 | 2020-07-14 | 3 |  | 58 | 4 | 63 | 2020 | 2020 | R16
169837215718 | 168258215718 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-10-15 | 2020-10-20 | 2020-12-30 |  | 2021-11-08 | Underground | R16 | 2021-04-23 | 4 | 52 | 83 | 142 | 278 | 2020 | 2021 | R16
169985215411 | 161202215411 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-16 | 2020-12-16 | 2020-12-23 |  | 2021-09-02 | Overhead | R16 | 2021-08-10 | 1 | 6 | 165 | 18 | 187 | 2020 | 2021 | R16
166407219205 | 163774219205 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Commercial | 2020-01-16 | 2020-01-16 | 2021-02-01 | 2021-12-27 | 2021-11-12 | Underground | R16 | 2021-12-27 | 1 | 273 | 236 |  | 477 | 2020 | 2021 | R16
163194196386 | 166031196386 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-02 | 2020-07-02 | 2020-07-02 | 2020-07-13 | 2020-10-06 | Overhead | R16 | 2020-07-13 | 1 |  | 8 | 62 | 69 | 2020 | 2020 | R16
160445207737 | 166352207737 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-07 | 2020-10-07 | 2020-10-21 |  | 2021-07-24 | Underground | R16 | 2020-11-04 | 1 | 11 | 11 | 188 | 208 | 2020 | 2021 | R16
161569199480 | 164286199480 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-25 | 2020-06-25 | 2020-08-03 | 2020-08-11 | 2020-10-06 | Overhead | R16 | 2020-08-11 | 1 | 28 | 7 | 41 | 74 | 2020 | 2020 | R16
161355179166 | 167478179166 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-03 | 2020-02-03 | 2020-02-03 | 2020-03-20 | 2020-06-01 | Overhead | R16 | 2020-03-20 | 1 |  | 35 | 52 | 86 | 2020 | 2020 | R16
160475222742 | 167851222742 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-03-02 | 2021-03-05 | 2021-03-05 |  | 2021-08-16 | Overhead | R16 | 2021-03-26 | 4 |  | 16 | 102 | 120 | 2021 | 2021 | R16
167712193344 | 160716193344 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-05 | 2020-06-05 | 2020-06-05 | 2020-06-12 | 2021-04-23 | Overhead | R16 | 2020-06-12 | 1 |  | 6 | 226 | 231 | 2020 | 2021 | R16
161727188779 | 163442188779 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-23 | 2020-04-23 | 2020-04-23 | 2020-05-07 | 2020-05-12 | Underground | R16 | 2020-05-07 | 1 |  | 11 | 4 | 14 | 2020 | 2020 | R16
167940192862 | 168297192862 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-06 | 2020-02-06 | 2020-06-01 | 2020-07-13 | 2020-07-14 | Underground | R16 | 2020-07-13 | 1 | 83 | 31 | 2 | 114 | 2020 | 2020 | R16
169551181895 | 162328181895 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-02-25 | 2020-02-25 | 2020-02-26 | 2020-11-04 | 2020-12-16 | Underground | R16 | 2020-11-04 | 1 | 2 | 181 | 31 | 212 | 2020 | 2020 | R16
163178286123 | 161222286123 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-06-08 | 2022-03-15 | 2022-07-19 | 2022-10-24 | 2022-11-15 | Underground | R16 | 2022-10-24 | 462 | 91 | 70 | 17 | 637 | 2020 | 2022 | R16
160912195391 | 162338195391 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-15 | 2020-06-15 | 2020-06-26 | 2020-07-31 | 2021-07-01 | Underground | R16 | 2020-07-31 | 1 | 10 | 26 | 240 | 274 | 2020 | 2021 | R16
166637188135 | 160856188135 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-19 | 2020-02-19 | 2020-04-18 | 2020-07-15 | 2020-07-16 | Underground | R16 | 2020-07-15 | 1 | 43 | 63 | 2 | 107 | 2020 | 2020 | R16
162243180350 | 169809180350 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-13 | 2020-02-13 | 2020-02-13 | 2020-03-09 | 2020-06-09 | Overhead | R16 | 2020-03-09 | 1 |  | 18 | 67 | 84 | 2020 | 2020 | R16
160777209245 | 161588209245 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-30 | 2020-10-30 | 2020-10-30 |  | 2022-06-01 | Overhead | R16 | 2020-12-22 | 1 |  | 38 | 377 | 414 | 2020 | 2022 | R16
166248191997 | 168668191997 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-22 | 2020-05-22 | 2020-05-22 | 2021-02-25 | 2021-06-02 | Overhead | R16 | 2021-02-25 | 1 |  | 200 | 70 | 269 | 2020 | 2021 | R16
167080193952 | 167736193952 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-18 | 2020-06-01 | 2020-06-12 | 2020-07-20 | 2020-10-06 | Overhead | R16 | 2020-07-20 | 11 | 10 | 27 | 57 | 102 | 2020 | 2020 | R16
165980194077 | 167020194077 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-13 | 2020-05-29 | 2020-06-12 | 2020-07-29 | 2020-07-30 | Underground | R16 | 2020-07-29 | 13 | 11 | 34 | 2 | 57 | 2020 | 2020 | R16
160506182853 | 163852182853 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-03 | 2020-03-03 | 2020-03-04 | 2020-05-04 | 2020-05-06 | Overhead | R16 | 2020-05-04 | 1 | 2 | 44 | 3 | 47 | 2020 | 2020 | R16
165712180185 | 169404180185 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-11 | 2020-02-11 | 2020-02-11 | 2020-03-25 | 2020-03-26 | Overhead | R16 | 2020-03-25 | 1 |  | 32 | 2 | 33 | 2020 | 2020 | R16
168486186497 | 160500186497 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-07 | 2020-04-07 | 2020-04-07 | 2020-04-22 | 2020-04-24 | Overhead | R16 | 2020-04-22 | 1 |  | 12 | 3 | 14 | 2020 | 2020 | R16
161028208901 | 160962208901 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-10-28 | 2020-10-28 | 2020-10-28 |  | 2021-11-13 | Underground | R16 | 2021-04-30 | 1 |  | 133 | 141 | 273 | 2020 | 2021 | R16
166457177252 | 164349177252 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-17 | 2020-01-17 | 2020-01-17 | 2020-02-18 | 2020-02-19 | Overhead | R16 | 2020-02-18 | 1 |  | 23 | 2 | 24 | 2020 | 2020 | R16
161120215686 | 163314215686 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-28 | 2020-12-28 | 2020-12-28 |  | 2021-04-16 | Overhead | R16 | 2021-01-07 | 1 |  | 9 | 72 | 80 | 2020 | 2021 | R16
163747273688 | 162977273688 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG R16 RESD AND NON RESD UD | Commercial | 2020-04-21 | 2021-09-10 | 2022-03-23 | 2022-11-02 | 2022-12-08 | Underground | R16 | 2022-11-02 | 364 | 139 | 161 | 27 | 688 | 2020 | 2022 | R16
166212177820 | 163514177820 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-15 | 2020-01-17 | 2020-01-22 | 2020-07-30 | 2020-10-06 | Overhead | R16 | 2020-07-30 | 3 | 4 | 137 | 49 | 190 | 2020 | 2020 | R16
165280210935 | 166537210935 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-01-29 | 2020-04-17 | 2020-11-18 | 2021-08-20 | 2021-11-02 | Underground | R16 | 2021-08-20 | 58 | 154 | 198 | 53 | 460 | 2020 | 2021 | R16
161355276319 | 163001276319 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-06-17 | 2022-04-19 | 2022-04-19 | 2022-04-21 | 2022-05-16 | Overhead | R16 | 2022-04-21 | 480 |  | 3 | 18 | 499 | 2020 | 2022 | R16
161255262820 | 167422262820 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-11-04 | 2021-11-10 | 2021-12-28 |  | 2022-03-04 | Underground | R16 |  | 5 | 35 |  |  | 87 | 2021 | 2022 | R16
161904181691 | 162041181691 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-02-24 | 2020-02-24 | 2020-02-24 | 2021-07-15 | 2022-07-29 | Underground | R16 | 2021-07-15 | 1 |  | 364 | 272 | 635 | 2020 | 2022 | R16
162225214524 | 162305214524 | Electric Vehicle | UG R16 RESD AND NON RESD UD | Commercial | 2020-02-25 | 2020-03-03 | 2020-12-18 | 2022-04-12 | 2022-06-03 | Underground | R16 | 2022-04-12 | 6 | 209 | 343 | 39 | 594 | 2020 | 2022 | R16
164168219938 | 164278219938 | MOBILE HOMES PARK AB622 | ELEC SVC FOR MOBILE HOMES | Residential | 2020-06-24 | 2021-02-09 | 2021-02-09 |  | 2022-02-07 | Underground | R16 |  | 165 |  |  |  | 424 | 2020 | 2022 | R16
163067212521 | 167197212521 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC DEVELOPMENT | Residential | 2020-05-14 | 2020-09-29 | 2020-12-02 | 2021-05-23 | 2021-06-18 | Underground | R16 | 2021-05-23 | 99 | 47 | 123 | 20 | 287 | 2020 | 2021 | R16
160991177906 | 165078177906 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-22 | 2020-01-22 | 2020-01-23 | 2020-02-18 | 2020-02-19 | Overhead | R16 | 2020-02-18 | 1 | 2 | 19 | 2 | 21 | 2020 | 2020 | R16
161346174702 | 168969174702 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-17 | 2019-12-17 | 2019-12-17 | 2020-03-04 | 2020-03-05 | Overhead | R16 | 2020-03-04 | 1 |  | 57 | 2 | 58 | 2019 | 2020 | R16
163161208102 | 168112208102 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH CP R16 WORK RELO TO UG | Residential | 2020-03-25 | 2020-03-25 | 2020-10-23 | 2020-11-06 | 2022-03-22 | Overhead | R16 | 2020-11-06 | 1 | 153 | 11 | 358 | 520 | 2020 | 2022 | R16
163161208102 | 168112208102 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OD | Residential | 2020-03-25 | 2020-03-25 | 2020-10-23 | 2020-11-06 | 2022-03-22 | Overhead | R16 | 2020-11-06 | 1 | 153 | 11 | 358 | 520 | 2020 | 2022 | R16
161717245451 | 161528245451 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Commercial | 2020-04-14 | 2020-10-14 | 2021-08-26 | 2021-09-08 | 2023-02-07 | Underground | R16 | 2021-09-08 | 132 | 227 | 10 | 370 | 736 | 2020 | 2023 | R16
161505209269 | 161678209269 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-30 | 2020-10-30 | 2020-10-30 |  | 2021-04-07 | Overhead | R16 | 2020-12-01 | 1 |  | 23 | 92 | 114 | 2020 | 2021 | R16
161513210469 | 167324210469 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-12 | 2020-10-12 | 2020-11-12 |  | 2021-04-15 | Underground | R16 | 2020-12-22 | 1 | 24 | 29 | 83 | 134 | 2020 | 2021 | R16
163346197972 | 160141197972 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-06-02 | 2020-06-17 | 2020-07-22 | 2022-02-08 | 2022-03-01 | Underground | R16 | 2022-02-08 | 12 | 26 | 405 | 16 | 456 | 2020 | 2022 | R16
165771185281 | 167983185281 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-24 | 2020-03-24 | 2020-03-24 | 2020-09-01 | 2020-12-15 | Overhead | R16 | 2020-09-01 | 1 |  | 116 | 76 | 191 | 2020 | 2020 | R16
161592216701 | 161184216701 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-12-16 | 2020-12-16 | 2021-01-08 |  | 2021-04-29 | Overhead | R16 | 2021-02-11 | 1 | 18 | 25 | 56 | 97 | 2020 | 2021 | R16
163554174399 | 169110174399 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-17 | 2019-12-17 | 2019-12-17 | 2020-01-22 | 2020-01-23 | Overhead | R16 | 2020-01-22 | 1 |  | 27 | 2 | 28 | 2019 | 2020 | R16
168600188240 | 163135188240 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-28 | 2020-04-20 | 2020-04-20 | 2020-06-24 | 2020-08-28 | Overhead | R16 | 2020-06-24 | 37 |  | 48 | 48 | 131 | 2020 | 2020 | R16
169638176732 | 160298176732 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-01-02 | 2020-01-02 | 2020-01-13 | 2020-10-09 | 2022-02-07 | Underground | R16 | 2020-10-09 | 1 | 8 | 195 | 347 | 548 | 2020 | 2022 | R16
163764200551 | 165970200551 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-02 | 2020-07-16 | 2020-08-14 | 2021-06-22 | 2021-06-25 | Underground | R16 | 2021-06-22 | 11 | 22 | 223 | 4 | 257 | 2020 | 2021 | R16
166070200127 | 168060200127 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-14 | 2020-07-14 | 2020-08-08 | 2020-09-28 | 2020-09-30 | Underground | R16 | 2020-09-28 | 1 | 19 | 36 | 3 | 57 | 2020 | 2020 | R16
164316215504 | 161066215504 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Commercial | 2020-02-19 | 2020-10-05 | 2020-12-23 | 2021-11-18 | 2022-01-11 | Underground | R16 | 2021-11-18 | 164 | 58 | 237 | 39 | 495 | 2020 | 2022 | R16
169357191556 | 167796191556 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-19 | 2020-05-19 | 2020-05-19 | 2020-07-31 | 2020-08-03 | Overhead | R16 | 2020-07-31 | 1 |  | 54 | 2 | 55 | 2020 | 2020 | R16
168015176973 | 163574176973 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-15 | 2020-01-15 | 2020-01-15 | 2020-03-12 | 2020-03-13 | Overhead | R16 | 2020-03-12 | 1 |  | 42 | 2 | 43 | 2020 | 2020 | R16
162507195916 | 165482195916 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-30 | 2020-06-30 | 2020-06-30 | 2020-07-01 | 2020-10-06 | Overhead | R16 | 2020-07-01 | 1 |  | 2 | 70 | 71 | 2020 | 2020 | R16
169788197349 | 161930197349 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-11 | 2020-06-11 | 2020-07-14 | 2020-11-20 | 2021-04-15 | Underground | R16 | 2020-11-20 | 1 | 24 | 94 | 105 | 221 | 2020 | 2021 | R16
161101204234 | 163322204234 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-19 | 2020-06-19 | 2020-09-18 | 2020-10-30 | 2023-10-12 | Underground | R16 | 2020-10-30 | 1 | 66 | 31 | 770 | 865 | 2020 | 2023 | R16
169284193675 | 161370193675 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-09 | 2020-06-09 | 2020-06-09 | 2020-07-01 | 2020-08-05 | Overhead | R16 | 2020-07-01 | 1 |  | 17 | 26 | 42 | 2020 | 2020 | R16
168346195511 | 169439195511 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-28 | 2020-05-28 | 2020-06-26 | 2020-08-17 | 2020-08-18 | Underground | R16 | 2020-08-17 | 1 | 22 | 37 | 2 | 59 | 2020 | 2020 | R16
164067189683 | 164927189683 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-01 | 2020-05-01 | 2020-05-01 | 2020-06-03 | 2020-06-05 | Overhead | R16 | 2020-06-03 | 1 |  | 24 | 3 | 26 | 2020 | 2020 | R16
160090188873 | 161852188873 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-14 | 2020-04-23 | 2020-04-23 | 2020-05-12 | 2020-06-16 | Overhead | R16 | 2020-05-12 | 8 |  | 14 | 26 | 46 | 2020 | 2020 | R16
166466178895 | 166511178895 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-29 | 2020-01-29 | 2020-01-31 | 2020-02-23 | 2020-04-15 | Overhead | R16 | 2020-02-23 | 1 | 3 | 16 | 38 | 56 | 2020 | 2020 | R16
160846200699 | 166257200699 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-03-14 | 2020-03-14 | 2020-08-17 | 2022-12-19 | 2022-12-19 | Underground | R16 | 2022-12-19 | 0 | 111 | 611 |  | 721 | 2020 | 2022 | R16
163016185350 | 165211185350 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-03-10 | 2020-03-10 | 2020-03-25 | 2020-07-30 | 2020-08-05 | Underground | R16 | 2020-07-30 | 1 | 12 | 92 | 5 | 107 | 2020 | 2020 | R16
162207207108 | 166772207108 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-08 | 2020-10-13 | 2020-10-13 |  | 2021-07-06 | Overhead | R16 | 2020-10-26 | 4 |  | 10 | 182 | 194 | 2020 | 2021 | R16
162252222923 | 168824222923 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-03-08 | 2021-03-08 | 2021-03-08 |  | 2021-08-16 | Underground | R16 |  | 1 |  |  |  | 116 | 2021 | 2021 | R16
168392187673 | 162162187673 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-04-16 | 2020-04-16 | 2020-04-16 | 2020-04-28 | 2020-04-29 | Overhead | R16 | 2020-04-28 | 1 |  | 9 | 2 | 10 | 2020 | 2020 | R16
167848175413 | 160334175413 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-31 | 2019-12-31 | 2019-12-31 | 2020-04-23 | 2020-06-30 | Overhead | R16 | 2020-04-23 | 1 |  | 83 | 49 | 131 | 2019 | 2020 | R16
163761197251 | 168005197251 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-14 | 2020-07-14 | 2020-07-14 | 2020-07-28 | 2020-10-06 | Overhead | R16 | 2020-07-28 | 1 |  | 11 | 51 | 61 | 2020 | 2020 | R16
160012200390 | 165675200390 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-23 | 2020-01-23 | 2020-08-12 | 2020-09-24 | 2020-12-23 | Underground | R16 | 2020-09-24 | 1 | 145 | 32 | 65 | 240 | 2020 | 2020 | R16
167900276467 | 160494276467 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-06-04 | 2020-07-02 | 2022-04-20 | 2023-01-05 | 2023-01-05 | Underground | R16 | 2023-01-05 | 21 | 470 | 187 |  | 676 | 2020 | 2023 | R16
160520192274 | 168402192274 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-05-21 | 2020-05-21 | 2020-05-27 | 2020-07-22 | 2020-12-09 | Underground | R16 | 2020-07-22 | 1 | 5 | 41 | 101 | 145 | 2020 | 2020 | R16
161246222384 | 161313222384 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-06-09 | 2020-06-09 | 2021-03-03 | 2021-10-31 | 2021-11-09 | Overhead | R16 | 2021-10-31 | 1 | 192 | 173 | 7 | 371 | 2020 | 2021 | R16
162588248444 | 168403248444 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-16 | 2021-04-16 | 2021-09-17 |  | 2022-01-04 | Overhead | R16 | 2021-11-22 | 1 | 111 | 47 | 32 | 188 | 2021 | 2022 | R16
161953192280 | 161878192280 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-08 | 2020-01-08 | 2020-05-26 | 2020-08-10 | 2020-10-05 | Underground | R16 | 2020-08-10 | 1 | 100 | 55 | 41 | 194 | 2020 | 2020 | R16
169786195377 | 164621195377 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-26 | 2020-06-26 | 2020-06-26 | 2020-09-24 | 2020-12-29 | Overhead | R16 | 2020-09-24 | 1 |  | 65 | 69 | 133 | 2020 | 2020 | R16
160093203324 | 160081203324 | NON-RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Commercial | 2020-04-03 | 2020-05-19 | 2020-09-09 | 2021-09-14 | 2022-03-01 | Underground | R16 | 2021-09-14 | 33 | 82 | 265 | 121 | 498 | 2020 | 2022 | R16
162243190889 | 166909190889 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-13 | 2020-05-13 | 2020-05-13 | 2020-08-04 | 2020-07-08 | Overhead | R16 | 2020-08-04 | 1 |  | 60 |  | 41 | 2020 | 2020 | R16
168172192661 | 169419192661 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-05-28 | 2020-05-29 | 2020-05-29 | 2020-07-09 | 2020-07-09 | Overhead | R16 | 2020-07-09 | 2 |  | 30 |  | 31 | 2020 | 2020 | R16
169253191745 | 169340191745 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-03-31 | 2020-03-31 | 2020-05-20 | 2022-06-10 | 2023-01-25 | Underground | R16 | 2022-06-10 | 1 | 37 | 538 | 164 | 737 | 2020 | 2023 | R16
162863209545 | 162508209545 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-04 | 2020-11-04 | 2020-11-04 |  | 2021-10-25 | Overhead | R16 | 2021-05-13 | 1 |  | 137 | 118 | 254 | 2020 | 2021 | R16
167605193177 | 162060193177 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-24 | 2020-02-26 | 2020-06-05 | 2020-06-18 | 2020-06-19 | Underground | R16 | 2020-06-18 | 3 | 73 | 10 | 2 | 85 | 2020 | 2020 | R16
167958192392 | 169379192392 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-28 | 2020-05-28 | 2020-05-28 | 2020-07-13 | 2020-07-15 | Overhead | R16 | 2020-07-13 | 1 |  | 33 | 3 | 35 | 2020 | 2020 | R16
166297315125 | 162206315125 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-07 | 2023-04-07 | 2023-04-07 | 2023-09-07 | 2023-12-11 | Overhead | R16 | 2023-09-07 | 1 |  | 110 | 68 | 177 | 2023 | 2023 | R16
168795247860 | 165335247860 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-09-14 | 2021-09-14 | 2021-09-14 | 2021-11-24 | 2021-11-24 | Underground | R16 | 2021-11-24 | 1 |  | 52 |  | 52 | 2021 | 2021 | R16
167926335537 | 164722335537 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-06-12 | 2023-10-13 | 2023-10-13 | 2023-11-20 | 2023-11-30 | Overhead | R16 | 2023-11-20 | 90 |  | 27 | 9 | 124 | 2023 | 2023 | R16
165944316862 | 168400316862 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-22 | 2023-04-03 | 2023-04-24 |  | 2023-09-13 | Underground | R16 | 2023-06-08 | 9 | 16 | 34 | 70 | 126 | 2023 | 2023 | R16
168053245408 | 161585245408 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-09-14 | 2021-11-09 | Overhead | R16 | 2021-09-14 | 1 |  | 14 | 41 | 54 | 2021 | 2021 | R16
168280306858 | 165190306858 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-01-20 | 2023-01-20 | 2023-01-30 | 2023-01-24 | 2023-04-27 | Overhead | R16 | 2023-01-24 | 1 | 7 |  | 68 | 70 | 2023 | 2023 | R16
164139316235 | 167140316235 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-17 | 2023-04-18 | 2023-04-18 |  | 2023-06-27 | Underground | R16 | 2023-06-27 | 23 |  | 51 |  | 73 | 2023 | 2023 | R16
160987317816 | 167516317816 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-03 |  | 2023-05-03 | 2023-11-09 | 2023-12-13 | Overhead | R16 | 2023-11-09 |  |  | 137 | 25 | 161 | 2023 | 2023 | R16
169654318970 | 169319318970 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-12 | 2023-05-12 | 2023-05-12 | 2023-07-03 | 2023-07-05 | Overhead | R16 | 2023-07-03 | 1 |  | 37 | 3 | 39 | 2023 | 2023 | R16
165716303926 | 169058303926 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-20 | 2022-12-20 | 2022-12-22 |  | 2023-03-31 | Overhead | R16 | 2023-03-17 | 1 | 3 | 62 | 11 | 74 | 2022 | 2023 | R16
165929305622 | 162826305622 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-10 | 2023-01-10 | 2023-01-30 | 2023-08-08 | 2023-08-10 | Overhead | R16 | 2023-08-08 | 1 | 15 | 137 | 3 | 153 | 2023 | 2023 | R16
167617318838 | 169268318838 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-11 | 2023-05-11 | 2023-05-11 | 2023-07-31 | 2023-09-11 | Overhead | R16 | 2023-07-31 | 1 |  | 58 | 31 | 88 | 2023 | 2023 | R16
163208213134 | 169393213134 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-08 | 2020-12-08 | 2020-12-08 |  | 2022-10-17 | Underground | R16 |  | 1 |  |  |  | 485 | 2020 | 2022 | R16
166923248093 | 165324248093 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-14 | 2021-09-16 | 2021-09-16 | 2021-11-29 | 2021-12-17 | Overhead | R16 | 2021-11-29 | 3 |  | 53 | 15 | 69 | 2021 | 2021 | R16
168019242813 | 167141242813 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-08-09 | 2021-08-09 | 2021-08-09 | 2021-11-04 | 2021-11-05 | Overhead | R16 | 2021-11-04 | 1 |  | 64 | 2 | 65 | 2021 | 2021 | R16
161998245193 | 167139245193 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-10 | 2021-08-10 | 2021-08-25 | 2022-08-12 | 2022-10-21 | Underground | R16 | 2022-08-12 | 1 | 12 | 253 | 51 | 314 | 2021 | 2022 | R16
164766303472 | 168500303472 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-16 | 2022-12-16 | 2022-12-22 |  | 2023-04-27 | Overhead | R16 | 2023-01-30 | 1 | 5 | 28 | 64 | 95 | 2022 | 2023 | R16
163798274568 | 164218274568 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2021-07-28 | 2021-07-30 | 2022-04-01 | 2023-07-28 | 2022-12-01 | Underground | R16 | 2023-07-28 | 3 | 176 | 346 |  | 352 | 2021 | 2022 | R16
166841244462 | 169973244462 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-19 | 2021-08-19 | 2021-08-19 | 2021-09-27 | 2021-11-09 | Overhead | R16 | 2021-09-27 | 1 |  | 28 | 32 | 59 | 2021 | 2021 | R16
167821249256 | 164754249256 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-29 | 2021-07-29 | 2021-09-24 |  | 2022-02-28 | Overhead | R16 | 2022-01-28 | 1 | 42 | 91 | 22 | 153 | 2021 | 2022 | R16
161785247586 | 165008247586 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-13 | 2021-09-13 | 2021-09-13 |  | 2022-04-15 | Underground | R16 | 2022-04-14 | 1 |  | 154 | 2 | 155 | 2021 | 2022 | R16
163984322074 | 165135322074 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-13 | 2023-06-13 | 2023-06-13 | 2023-07-26 | 2023-07-26 | Overhead | R16 | 2023-07-26 | 1 |  | 32 |  | 32 | 2023 | 2023 | R16
163502210720 | 166298210720 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-07 | 2020-10-07 | 2020-11-13 |  | 2021-10-14 | Underground | R16 | 2021-08-23 | 1 | 28 | 202 | 39 | 267 | 2020 | 2021 | R16
166202246382 | 163127246382 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-09-02 | 2021-09-02 | 2021-09-02 | 2021-11-15 | 2021-12-02 | Overhead | R16 | 2021-11-15 | 1 |  | 53 | 14 | 66 | 2021 | 2021 | R16
166209305228 | 162093305228 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-01-06 | 2023-01-06 | 2023-01-06 | 2023-01-06 | 2023-01-20 | Overhead | R16 | 2023-01-06 | 1 |  |  | 11 | 11 | 2023 | 2023 | R16
165604320660 | 166058320660 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-26 | 2023-05-16 | 2023-05-30 | 2023-07-31 | 2023-07-31 | Overhead | R16 | 2023-07-31 | 15 | 11 | 45 |  | 69 | 2023 | 2023 | R16
169158326238 | 166651326238 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-21 | 2023-07-26 | 2023-07-26 | 2023-10-12 | 2023-10-17 | Overhead | R16 | 2023-10-12 | 26 |  | 57 | 4 | 85 | 2023 | 2023 | R16
168337307128 | 165404307128 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-01-23 | 2023-01-23 | 2023-01-25 | 2023-09-28 | 2023-10-03 | Underground | R16 | 2023-09-28 | 1 | 3 | 177 | 4 | 182 | 2023 | 2023 | R16
164022310820 | 165825310820 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2023-01-24 | 2023-01-24 | 2023-02-26 |  | 2023-09-28 | Underground | R16 | 2023-06-19 | 1 | 24 | 81 | 74 | 178 | 2023 | 2023 | R16
161298315220 | 161957315220 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-06 | 2023-04-07 | 2023-04-07 | 2023-08-15 | 2023-08-16 | Overhead | R16 | 2023-08-15 | 2 |  | 93 | 2 | 95 | 2023 | 2023 | R16
169367312316 | 162319312316 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-23 | 2023-02-23 | 2023-03-13 | 2023-05-04 | 2023-05-16 | Underground | R16 | 2023-05-04 | 1 | 13 | 39 | 9 | 59 | 2023 | 2023 | R16
169356244214 | 169875244214 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-19 | 2021-08-19 | 2021-08-19 |  | 2022-05-17 | Overhead | R16 | 2022-05-16 | 1 |  | 193 | 2 | 194 | 2021 | 2022 | R16
163663228167 | 163636228167 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-09 | 2020-11-09 | 2021-04-23 |  | 2022-10-27 | Underground | R16 | 2022-10-26 | 1 | 120 | 394 | 2 | 514 | 2020 | 2022 | R16
165723312051 | 165877312051 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2023-03-10 | 2023-03-10 | 2023-03-10 | 2023-10-11 | 2023-10-12 | Underground | R16 | 2023-10-11 | 1 |  | 154 | 2 | 155 | 2023 | 2023 | R16
160791245807 | 162078245807 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-30 | 2021-08-30 | 2021-08-30 | 2021-09-09 | 2021-11-09 | Overhead | R16 | 2021-09-09 | 1 |  | 9 | 44 | 52 | 2021 | 2021 | R16
164532324541 | 166618324541 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-21 | 2023-07-07 | 2023-07-07 | 2023-08-16 | 2023-09-29 | Overhead | R16 | 2023-08-16 | 13 |  | 29 | 33 | 73 | 2023 | 2023 | R16
168044308304 | 168241308304 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-03 | 2023-02-03 | 2023-02-03 |  | 2023-05-18 | Overhead | R16 | 2023-03-21 | 1 |  | 33 | 43 | 75 | 2023 | 2023 | R16
165580326753 | 160677326753 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-12 | 2023-07-29 | 2023-07-29 | 2023-09-05 | 2023-09-20 | Overhead | R16 | 2023-09-05 | 13 |  | 27 | 12 | 51 | 2023 | 2023 | R16
164512241121 | 164150241121 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-28 | 2021-07-28 | 2021-07-28 |  | 2023-10-12 | Overhead | R16 | 2023-08-31 | 1 |  | 547 | 31 | 577 | 2021 | 2023 | R16
165941307566 | 166937307566 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-01-30 | 2023-01-30 | 2023-01-30 |  | 2023-02-22 | Overhead | R16 |  | 1 |  |  |  | 18 | 2023 | 2023 | R16
162160323707 | 168402323707 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2023-06-29 | 2023-06-29 | 2023-06-29 | 2023-12-04 | 2023-12-08 | Overhead | R16 | 2023-12-04 | 1 |  | 113 | 5 | 117 | 2023 | 2023 | R16
163384318638 | 167442318638 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-02 | 2023-05-09 | 2023-05-09 | 2023-10-23 | 2023-11-06 | Overhead | R16 | 2023-10-23 | 6 |  | 120 | 11 | 135 | 2023 | 2023 | R16
160825313928 | 168081313928 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-22 | 2023-03-22 | 2023-03-28 |  | 2023-05-18 | Underground | R16 | 2023-03-31 | 1 | 5 | 4 | 35 | 42 | 2023 | 2023 | R16
160731324146 | 167414324146 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-26 | 2023-06-26 | 2023-07-05 | 2023-08-10 | 2023-08-23 | Overhead | R16 | 2023-08-10 | 1 | 8 | 27 | 10 | 43 | 2023 | 2023 | R16
165027303888 | 169009303888 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-20 | 2022-12-20 | 2022-12-22 | 2023-02-09 | 2023-04-08 | Overhead | R16 | 2023-02-09 | 1 | 3 | 36 | 42 | 79 | 2022 | 2023 | R16
164512303512 | 167924303512 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-14 | 2022-12-14 | 2022-12-22 | 2023-03-16 | 2023-03-25 | Underground | R16 | 2023-03-16 | 1 | 7 | 61 | 7 | 73 | 2022 | 2023 | R16
162794242664 | 166844242664 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-09 | 2021-08-09 | 2021-08-09 | 2021-10-20 | 2021-11-18 | Overhead | R16 | 2021-10-20 | 1 |  | 53 | 22 | 74 | 2021 | 2021 | R16
164363319198 | 169857319198 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-07-19 | 2023-07-20 | Overhead | R16 | 2023-07-19 | 1 |  | 48 | 2 | 49 | 2023 | 2023 | R16
167350323826 | 161484323826 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-24 | 2023-06-30 | 2023-06-30 | 2023-08-30 | 2023-09-20 | Underground | R16 | 2023-08-30 | 28 |  | 44 | 16 | 86 | 2023 | 2023 | R16
166990318144 | 168140318144 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-05 | 2023-05-05 | 2023-05-05 | 2023-06-20 | 2023-06-21 | Overhead | R16 | 2023-06-20 | 1 |  | 33 | 2 | 34 | 2023 | 2023 | R16
165083304268 | 167984304268 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-14 | 2022-12-14 | 2023-01-30 | 2022-12-28 | 2023-03-31 | Underground | R16 | 2022-12-28 | 1 | 34 |  | 68 | 78 | 2022 | 2023 | R16
168924323584 | 166480323584 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-14 | 2023-03-14 | 2023-06-28 | 2023-10-19 | 2023-11-13 | Underground | R16 | 2023-10-19 | 1 | 77 | 82 | 18 | 175 | 2023 | 2023 | R16
168547317548 | 169405317548 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-27 | 2023-03-27 | 2023-05-01 |  | 2023-06-21 | Underground | R16 | 2023-05-02 | 1 | 26 | 2 | 37 | 63 | 2023 | 2023 | R16
164387231374 | 163274231374 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-06 | 2020-11-06 | 2021-05-19 |  | 2021-11-08 | Overhead | R16 | 2021-10-04 | 1 | 139 | 99 | 26 | 262 | 2020 | 2021 | R16
165235243902 | 168764243902 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-08-16 | 2021-08-16 | 2021-08-16 |  | 2023-07-07 | Overhead | R16 | 2023-03-17 | 1 |  | 415 | 81 | 495 | 2021 | 2023 | R16
164392210241 | 163918210241 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-10 | 2020-11-10 | 2020-11-10 |  | 2021-04-07 | Overhead | R16 | 2020-11-30 | 1 |  | 15 | 93 | 107 | 2020 | 2021 | R16
162267308735 | 166698308735 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-27 | 2023-01-27 | 2023-02-08 |  | 2023-05-16 | Underground | R16 | 2023-02-22 | 1 | 9 | 11 | 60 | 78 | 2023 | 2023 | R16
163583307822 | 160221307822 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-29 | 2022-12-29 | 2023-01-31 |  | 2023-08-16 | Underground | R16 | 2023-05-08 | 1 | 24 | 70 | 73 | 165 | 2022 | 2023 | R16
169164266922 | 163825266922 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-08 | 2021-12-27 | 2022-01-31 |  | 2022-03-15 | Overhead | R16 |  | 79 | 26 |  |  | 135 | 2021 | 2022 | R16
162487241386 | 164768241386 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-30 | 2021-07-30 | 2021-07-30 | 2021-08-20 | 2021-10-25 | Overhead | R16 | 2021-08-20 | 1 |  | 16 | 47 | 62 | 2021 | 2021 | R16
169916324891 | 160566324891 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-12 | 2023-07-12 | 2023-07-12 | 2023-09-06 | 2023-09-11 | Overhead | R16 | 2023-09-06 | 1 |  | 41 | 4 | 44 | 2023 | 2023 | R16
168920316494 | 161335316494 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-04 | 2023-04-04 | 2023-04-20 |  | 2023-08-18 | Underground | R16 | 2023-05-02 | 1 | 13 | 9 | 79 | 99 | 2023 | 2023 | R16
162161331888 | 167820331888 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-27 | 2023-06-27 | 2023-09-07 | 2023-09-25 | 2023-10-06 | Underground | R16 | 2023-09-25 | 1 | 53 | 13 | 10 | 74 | 2023 | 2023 | R16
165572307575 | 165489307575 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2023-01-24 | 2023-01-24 | 2023-01-30 |  | 2023-08-14 | Underground | R16 | 2023-04-27 | 1 | 5 | 64 | 78 | 145 | 2023 | 2023 | R16
160422310396 | 168662310396 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-06 | 2023-02-06 | 2023-02-23 | 2023-04-02 | 2023-04-06 | Underground | R16 | 2023-04-02 | 1 | 14 | 27 | 4 | 44 | 2023 | 2023 | R16
160026246128 | 162676246128 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-01 | 2021-09-01 | 2021-09-01 |  | 2022-02-07 | Overhead | R16 | 2022-01-11 | 1 |  | 95 | 20 | 114 | 2021 | 2022 | R16
168035317175 | 164793317175 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-19 | 2023-04-27 | 2023-04-27 | 2023-07-25 | 2023-07-25 | Overhead | R16 | 2023-07-25 | 7 |  | 64 |  | 70 | 2023 | 2023 | R16
165616244963 | 160712244963 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-23 | 2021-08-23 | 2021-08-23 | 2021-08-31 | 2021-11-01 | Overhead | R16 | 2021-08-31 | 1 |  | 7 | 45 | 51 | 2021 | 2021 | R16
160172323255 | 167494323255 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-27 | 2023-06-27 | 2023-06-27 | 2023-07-03 | 2023-08-01 | Underground | R16 | 2023-07-03 | 1 |  | 5 | 22 | 26 | 2023 | 2023 | R16
163366261283 | 165175261283 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-13 | 2021-12-14 | 2021-12-14 | 2022-03-29 | 2022-04-26 | Overhead | R16 | 2022-03-29 | 67 |  | 76 | 21 | 162 | 2021 | 2022 | R16
168526312785 | 166352312785 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-04-05 | 2023-06-13 | Overhead | R16 | 2023-04-05 | 2 | 2 | 15 | 50 | 66 | 2023 | 2023 | R16
161370319527 | 161082319527 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-03 | 2023-04-03 | 2023-05-19 | 2023-07-28 | 2023-08-02 | Underground | R16 | 2023-07-28 | 1 | 35 | 51 | 4 | 88 | 2023 | 2023 | R16
168443246523 | 163137246523 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-09-02 | 2021-09-02 | 2021-09-02 | 2022-03-06 | 2022-04-26 | Underground | R16 | 2022-03-06 | 1 |  | 132 | 37 | 169 | 2021 | 2022 | R16
164838304006 | 169412304006 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-22 | 2022-12-22 | 2022-12-27 | 2023-02-22 | 2023-02-23 | Overhead | R16 | 2023-02-22 | 1 | 4 | 42 | 2 | 46 | 2022 | 2023 | R16
161820320613 | 160874320613 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-20 | 2023-05-30 | 2023-05-30 | 2023-07-08 | 2023-07-11 | Overhead | R16 | 2023-07-08 | 7 |  | 29 | 2 | 37 | 2023 | 2023 | R16
163122313503 | 168560313503 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-23 | 2023-03-23 | 2023-03-23 | 2023-05-17 | 2023-11-27 | Overhead | R16 | 2023-05-17 | 1 |  | 40 | 139 | 178 | 2023 | 2023 | R16
160930325688 | 167599325688 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-27 | 2023-06-27 | 2023-07-20 | 2023-07-20 | 2023-08-29 | Overhead | R16 | 2023-07-20 | 1 | 18 |  | 29 | 46 | 2023 | 2023 | R16
168045322728 | 162257322728 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-30 | 2023-06-19 | 2023-06-19 | 2023-08-18 | 2023-08-18 | Overhead | R16 | 2023-08-18 | 15 |  | 45 |  | 59 | 2023 | 2023 | R16
164876213023 | 165393213023 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-11-17 | 2020-11-17 | 2020-12-07 |  | 2022-01-18 | Underground | R16 | 2021-12-22 | 1 | 15 | 273 | 20 | 306 | 2020 | 2022 | R16
164878299103 | 169263299103 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-08-17 | 2021-08-25 | 2022-11-01 |  | 2023-03-02 | Overhead | R16 |  | 7 | 310 |  |  | 403 | 2021 | 2023 | R16
160764313582 | 168707313582 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-24 | 2023-03-24 | 2023-03-24 |  | 2023-08-08 | Underground | R16 | 2023-04-21 | 1 |  | 21 | 78 | 98 | 2023 | 2023 | R16
169772307932 | 161068307932 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-04 | 2023-01-04 | 2023-02-01 |  | 2023-09-28 | Underground | R16 | 2023-06-15 | 1 | 21 | 97 | 76 | 192 | 2023 | 2023 | R16
160634313919 | 169649313919 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-28 | 2023-03-28 | 2023-03-28 | 2023-05-09 | 2023-05-10 | Overhead | R16 | 2023-05-09 | 1 |  | 31 | 2 | 32 | 2023 | 2023 | R16
161299250359 | 165529250359 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2021-09-14 | 2021-10-01 | 2021-10-01 | 2021-10-12 | 2021-10-14 | Overhead | R16 | 2021-10-12 | 14 |  | 8 | 3 | 23 | 2021 | 2021 | R16
169432314354 | 164501314354 | RESIDENTIAL - MOBILE HOME | OH R16 RES NON RES OS | Residential | 2023-03-03 | 2023-03-31 | 2023-03-31 |  | 2023-08-18 | Overhead | R16 | 2023-05-05 | 21 |  | 26 | 76 | 121 | 2023 | 2023 | R16
168829326862 | 169559326862 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-07 | 2023-07-31 | 2023-07-31 | 2023-07-31 | 2023-08-17 | Overhead | R16 | 2023-07-31 | 17 |  |  | 14 | 30 | 2023 | 2023 | R16
160431308883 | 169332308883 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-08 | 2023-02-08 | 2023-02-08 |  | 2023-03-31 | Overhead | R16 | 2023-02-21 | 1 |  | 10 | 29 | 38 | 2023 | 2023 | R16
167501323978 | 165306323978 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-14 | 2023-06-14 | 2023-07-06 | 2023-07-17 | 2023-08-07 | Underground | R16 | 2023-07-17 | 1 | 17 | 8 | 16 | 39 | 2023 | 2023 | R16
160593324029 | 169674324029 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-15 | 2023-07-03 | 2023-07-03 | 2023-08-22 | 2023-09-25 | Overhead | R16 | 2023-08-22 | 36 |  | 37 | 25 | 96 | 2023 | 2023 | R16
164041247195 | 164548247195 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-11-17 | 2021-11-18 | Overhead | R16 | 2021-11-17 | 1 |  | 49 | 2 | 50 | 2021 | 2021 | R16
161346321647 | 164278321647 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-08 | 2023-06-08 | 2023-06-08 | 2023-07-05 | 2023-08-02 | Overhead | R16 | 2023-07-05 | 1 |  | 20 | 21 | 40 | 2023 | 2023 | R16
162993242189 | 166245242189 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-05 | 2021-08-05 | 2021-08-05 | 2021-09-21 | 2021-10-28 | Overhead | R16 | 2021-09-21 | 1 |  | 34 | 28 | 61 | 2021 | 2021 | R16
160469243305 | 168040243305 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-12 | 2021-08-12 | 2021-08-12 | 2021-09-20 | 2021-09-22 | Overhead | R16 | 2021-09-20 | 1 |  | 28 | 3 | 30 | 2021 | 2021 | R16
162807248378 | 163815248378 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-07 | 2021-09-07 | 2021-09-17 | 2021-12-28 | 2022-02-07 | Underground | R16 | 2021-12-28 | 1 | 9 | 73 | 30 | 110 | 2021 | 2022 | R16
165290212155 | 169467212155 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-21 | 2020-10-21 | 2020-12-01 |  | 2021-04-20 | Underground | R16 | 2021-01-14 | 1 | 30 | 33 | 69 | 130 | 2020 | 2021 | R16
162833311822 | 163488311822 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-02-28 | 2023-03-07 | 2023-03-07 |  | 2023-08-15 | Overhead | R16 | 2023-05-08 | 6 |  | 45 | 72 | 121 | 2023 | 2023 | R16
165306216745 | 160910216745 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-27 | 2021-01-08 | 2021-01-08 |  | 2021-11-02 | Underground | R16 | 2021-06-15 | 54 |  | 113 | 101 | 266 | 2020 | 2021 | R16
169636314483 | 160811314483 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-31 | 2023-04-03 | 2023-04-03 |  | 2023-06-06 | Overhead | R16 | 2023-04-26 | 2 |  | 18 | 30 | 48 | 2023 | 2023 | R16
160358314791 | 161357314791 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-05 | 2023-01-05 | 2023-04-04 | 2023-12-25 | 2023-12-28 | Underground | R16 | 2023-12-25 | 1 | 64 | 190 | 4 | 256 | 2023 | 2023 | R16
162419316874 | 164692316874 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-06 | 2023-03-06 | 2023-04-25 | 2023-05-22 | 2023-05-25 | Underground | R16 | 2023-05-22 | 1 | 37 | 20 | 4 | 59 | 2023 | 2023 | R16
164369312777 | 165653312777 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-03-09 | 2023-03-14 | 2023-03-17 |  | 2023-10-04 | Underground | R16 |  | 4 | 4 |  |  | 150 | 2023 | 2023 | R16
165448209339 | 167399209339 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-12 | 2020-10-13 | 2020-11-03 |  | 2021-04-07 | Underground | R16 | 2020-12-03 | 2 | 16 | 23 | 90 | 128 | 2020 | 2021 | R16
164566313077 | 161961313077 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-22 | 2023-02-22 | 2023-03-21 | 2023-05-11 | 2023-05-12 | Underground | R16 | 2023-05-11 | 1 | 20 | 38 | 2 | 58 | 2023 | 2023 | R16
166513305029 | 160741305029 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-03 | 2023-01-05 | 2023-01-30 | 2023-03-07 | 2023-03-31 | Overhead | R16 | 2023-03-07 | 3 | 18 | 27 | 19 | 64 | 2023 | 2023 | R16
161003307681 | 166648307681 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-27 | 2023-01-27 | 2023-01-30 | 2023-02-27 | 2023-03-20 | Overhead | R16 | 2023-02-27 | 1 | 2 | 21 | 16 | 37 | 2023 | 2023 | R16
166342319637 | 167626319637 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-03 | 2023-05-03 | 2023-05-19 |  | 2023-09-05 | Underground | R16 | 2023-05-22 | 1 | 13 | 2 | 77 | 90 | 2023 | 2023 | R16
161003309542 | 160635309542 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-15 | 2023-02-15 | 2023-02-15 | 2023-04-21 | 2023-06-13 | Overhead | R16 | 2023-04-21 | 1 |  | 48 | 38 | 85 | 2023 | 2023 | R16
168235327751 | 165039327751 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-06-13 | 2023-07-07 | 2023-08-09 | 2023-10-13 | 2023-10-20 | Overhead | R16 | 2023-10-13 | 19 | 24 | 48 | 6 | 94 | 2023 | 2023 | R16
165630292780 | 161776292780 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-11-02 | 2021-10-28 | 2022-09-06 |  | 2023-08-09 | Underground | R16 | 2023-04-17 | 259 | 224 | 160 | 83 | 723 | 2020 | 2023 | R16
167709249049 | 163885249049 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-07 | 2021-09-07 | 2021-09-22 | 2022-03-11 | 2022-04-04 | Underground | R16 | 2022-03-11 | 1 | 12 | 123 | 17 | 150 | 2021 | 2022 | R16
164584311187 | 169456311187 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-09 | 2023-03-02 | 2023-03-02 | 2023-09-13 | 2023-09-14 | Overhead | R16 | 2023-09-13 | 16 |  | 140 | 2 | 156 | 2023 | 2023 | R16
166431318391 | 167089318391 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-02 | 2023-05-08 | 2023-05-08 | 2023-08-11 | 2023-10-05 | Overhead | R16 | 2023-08-11 | 5 |  | 70 | 40 | 113 | 2023 | 2023 | R16
161490310948 | 163638310948 | NON-RESIDENTIAL - MISCELLANEOUS | UG ELEC MISC SVC US | Residential | 2023-03-01 | 2023-03-01 | 2023-03-01 | 2023-03-03 | 2023-03-08 | Underground | R16 | 2023-03-03 | 1 |  | 3 | 4 | 6 | 2023 | 2023 | R16
160350315429 | 164004315429 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-02 | 2023-03-08 | 2023-04-11 |  | 2023-07-14 | Underground | R16 | 2023-07-12 | 5 | 25 | 67 | 3 | 97 | 2023 | 2023 | R16
161709306962 | 165515306962 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-23 | 2023-01-23 | 2023-01-30 | 2023-01-23 | 2023-09-11 | Overhead | R16 | 2023-01-23 | 1 | 6 |  | 166 | 166 | 2023 | 2023 | R16
167627321230 | 160411321230 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-17 | 2023-05-17 | 2023-06-06 | 2023-09-06 | 2023-09-07 | Underground | R16 | 2023-09-06 | 1 | 15 | 67 | 2 | 82 | 2023 | 2023 | R16
164616247880 | 165180247880 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-13 | 2021-09-14 | 2021-09-14 | 2021-10-29 | 2021-11-30 | Overhead | R16 | 2021-10-29 | 2 |  | 34 | 23 | 57 | 2021 | 2021 | R16
160181309032 | 162602309032 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-01-10 |  | 2023-02-11 | 2023-10-24 | 2023-10-25 | Overhead | R16 | 2023-10-24 |  |  | 182 | 2 | 207 | 2023 | 2023 | R16
166482303269 | 167996303269 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-14 | 2022-12-14 | 2022-12-14 | 2023-01-12 | 2023-03-17 | Overhead | R16 | 2023-01-12 | 1 |  | 22 | 47 | 68 | 2022 | 2023 | R16
168086311770 | 163877311770 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-17 | 2023-03-08 | 2023-03-08 | 2023-09-07 | 2023-10-18 | Overhead | R16 | 2023-09-07 | 37 |  | 132 | 30 | 197 | 2023 | 2023 | R16
163445320223 | 163641320223 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-13 | 2023-04-13 | 2023-05-24 | 2023-07-19 | 2023-07-14 | Underground | R16 | 2023-07-19 | 1 | 30 | 41 |  | 67 | 2023 | 2023 | R16
160986319616 | 163323319616 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-12 | 2023-05-19 | 2023-05-19 | 2023-10-13 | 2023-10-23 | Overhead | R16 | 2023-10-13 | 28 |  | 106 | 7 | 139 | 2023 | 2023 | R16
161389324281 | 161953324281 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-26 | 2023-07-06 | 2023-07-06 | 2023-07-25 | 2023-08-25 | Overhead | R16 | 2023-07-25 | 30 |  | 14 | 24 | 66 | 2023 | 2023 | R16
167943314582 | 166645314582 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-15 | 2023-03-15 | 2023-04-03 | 2023-12-14 | 2023-12-14 | Underground | R16 | 2023-12-14 | 1 | 14 | 184 |  | 197 | 2023 | 2023 | R16
169155245837 | 162218245837 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-08-30 | 2021-08-30 | 2021-08-30 | 2022-02-11 | 2022-02-11 | Overhead | R16 | 2022-02-11 | 1 |  | 120 |  | 120 | 2021 | 2022 | R16
162285321414 | 162356321414 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-30 | 2023-05-30 | 2023-06-07 | 2023-08-22 | 2023-09-01 | Underground | R16 | 2023-08-22 | 1 | 7 | 55 | 9 | 69 | 2023 | 2023 | R16
169889241889 | 165437241889 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-03 | 2021-08-03 | 2021-08-03 | 2021-08-12 | 2021-10-25 | Overhead | R16 | 2021-08-12 | 1 |  | 8 | 53 | 60 | 2021 | 2021 | R16
166088214561 | 161661214561 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-18 | 2020-12-18 | 2020-12-18 |  | 2021-05-06 | Overhead | R16 | 2021-02-22 | 1 |  | 47 | 54 | 100 | 2020 | 2021 | R16
169819251700 | 166171251700 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-08-05 | 2021-08-05 | 2021-10-11 |  | 2021-12-29 | Overhead | R16 |  | 1 | 48 |  |  | 105 | 2021 | 2021 | R16
168941244217 | 166034244217 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-08-04 | 2021-08-19 | 2021-08-19 |  | 2023-10-10 | Underground | R16 | 2023-10-04 | 12 |  | 555 | 5 | 570 | 2021 | 2023 | R16
163854315609 | 163637315609 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-01 | 2023-04-13 | 2023-04-13 | 2023-06-05 | 2023-06-07 | Overhead | R16 | 2023-06-05 | 32 |  | 38 | 3 | 71 | 2023 | 2023 | R16
161946320614 | 169023320614 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-10 | 2023-05-30 | 2023-05-30 | 2023-06-24 | 2023-06-27 | Overhead | R16 | 2023-06-24 | 15 |  | 19 | 2 | 35 | 2023 | 2023 | R16
166997304391 | 160355304391 | RESIDENTIAL - SINGLE FAMILY ATTACHED | OH R16 RES NON RES OS | Residential | 2022-12-30 | 2022-12-30 | 2023-01-30 | 2023-02-17 | 2023-06-01 | Overhead | R16 | 2023-02-17 | 1 | 22 | 15 | 75 | 110 | 2022 | 2023 | R16
169422304083 | 169405304083 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-22 | 2022-12-22 | 2022-12-22 |  | 2023-08-02 | Overhead | R16 | 2023-03-27 | 1 |  | 68 | 93 | 160 | 2022 | 2023 | R16
169289312106 | 166633312106 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-27 | 2023-01-27 | 2023-03-10 | 2023-05-12 | 2023-05-15 | Underground | R16 | 2023-05-12 | 1 | 31 | 46 | 2 | 77 | 2023 | 2023 | R16
162941247865 | 166327247865 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Commercial | 2021-08-05 | 2021-09-13 | 2021-09-14 | 2021-10-25 | 2021-11-18 | Underground | R16 | 2021-10-25 | 28 | 2 | 30 | 19 | 76 | 2021 | 2021 | R16
164194321712 | 168268321712 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-05 | 2023-05-05 | 2023-06-09 | 2023-09-25 | 2023-09-28 | Underground | R16 | 2023-09-25 | 1 | 26 | 77 | 4 | 105 | 2023 | 2023 | R16
160762308152 | 168026308152 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2023-02-02 | 2023-02-02 | 2023-02-02 |  | 2023-06-26 | Overhead | R16 | 2023-03-08 | 1 |  | 25 | 79 | 103 | 2023 | 2023 | R16
163562311332 | 164185311332 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-03 | 2023-03-03 | 2023-03-03 | 2023-07-17 | 2023-06-21 | Overhead | R16 | 2023-07-17 | 1 |  | 97 |  | 79 | 2023 | 2023 | R16
162523245474 | 169283245474 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-08-17 | 2021-08-27 | 2021-08-27 | 2021-10-05 | 2021-10-05 | Underground | R16 | 2021-10-05 | 9 |  | 28 |  | 36 | 2021 | 2021 | R16
160749241322 | 164056241322 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-28 | 2021-07-29 | 2021-07-29 |  | 2021-08-23 | Overhead | R16 | 2021-08-06 | 2 |  | 7 | 12 | 19 | 2021 | 2021 | R16
168853244114 | 165439244114 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-03 | 2021-08-17 | 2021-08-17 |  | 2021-10-25 | Overhead | R16 | 2021-09-15 | 11 |  | 22 | 29 | 60 | 2021 | 2021 | R16
166428220552 | 168614220552 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-19 | 2020-10-19 | 2021-02-16 |  | 2021-11-02 | Underground | R16 | 2021-06-15 | 1 | 87 | 86 | 101 | 272 | 2020 | 2021 | R16
166196326870 | 160559326870 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-12 | 2023-07-29 | 2023-08-01 | 2023-09-11 | 2023-09-14 | Overhead | R16 | 2023-09-11 | 13 | 2 | 30 | 4 | 47 | 2023 | 2023 | R16
160422322822 | 166484322822 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-28 | 2023-06-20 | 2023-06-20 | 2023-08-17 | 2023-08-17 | Overhead | R16 | 2023-08-17 | 38 |  | 43 |  | 80 | 2023 | 2023 | R16
168205304326 | 169892304326 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-27 |  | 2022-12-27 |  | 2023-03-01 | Overhead | R16 | 2023-01-26 |  |  | 23 | 25 | 47 | 2022 | 2023 | R16
168602305129 | 161378305129 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-05 | 2023-01-05 | 2023-01-30 | 2023-02-27 | 2023-02-27 | Overhead | R16 | 2023-02-27 | 1 | 18 | 21 |  | 38 | 2023 | 2023 | R16
164410321639 | 163725321639 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-06 | 2023-06-09 | 2023-06-09 | 2023-06-09 | 2023-07-06 | Overhead | R16 | 2023-06-09 | 4 |  |  | 20 | 23 | 2023 | 2023 | R16
167075338500 | 160623338500 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-12 | 2023-07-12 | 2023-11-03 | 2023-12-05 | 2023-12-21 | Underground | R16 | 2023-12-05 | 1 | 83 | 23 | 13 | 117 | 2023 | 2023 | R16
164732321446 | 163515321446 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-05 | 2023-06-06 | 2023-06-07 | 2023-08-03 | 2023-08-08 | Overhead | R16 | 2023-08-03 | 2 | 2 | 42 | 4 | 47 | 2023 | 2023 | R16
162185321463 | 162777321463 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-01 | 2023-06-07 | 2023-06-07 | 2023-08-17 | 2023-08-17 | Overhead | R16 | 2023-08-17 | 5 |  | 52 |  | 56 | 2023 | 2023 | R16
166829208909 | 167796208909 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-10-14 | 2020-10-14 | 2020-10-28 |  | 2021-07-24 | Underground | R16 |  | 1 | 11 |  |  | 203 | 2020 | 2021 | R16
160288322787 | 165047322787 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-13 | 2023-06-13 | 2023-06-20 | 2023-08-16 | 2023-09-08 | Overhead | R16 | 2023-08-16 | 1 | 6 | 42 | 18 | 64 | 2023 | 2023 | R16
160039249812 | 164403249812 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-09 | 2021-09-09 | 2021-09-28 | 2022-02-23 | 2023-07-13 | Underground | R16 | 2022-02-23 | 1 | 14 | 107 | 362 | 481 | 2021 | 2023 | R16
169530315311 | 161338315311 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-04 | 2023-04-06 | 2023-04-10 |  | 2023-08-18 | Overhead | R16 | 2023-04-19 | 3 | 3 | 8 | 88 | 99 | 2023 | 2023 | R16
169365306960 | 165573306960 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-23 | 2023-01-23 | 2023-01-30 | 2023-01-23 | 2023-03-31 | Overhead | R16 | 2023-01-23 | 1 | 6 |  | 50 | 50 | 2023 | 2023 | R16
161825325047 | 161036325047 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-14 | 2023-07-14 | 2023-07-14 | 2023-08-07 | 2023-09-13 | Overhead | R16 | 2023-08-07 | 1 |  | 17 | 28 | 44 | 2023 | 2023 | R16
166935216912 | 165625216912 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-01-07 | 2021-01-07 | 2021-01-12 |  | 2021-04-29 | Overhead | R16 |  | 1 | 4 |  |  | 81 | 2021 | 2021 | R16
162812320998 | 167862320998 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-03-21 | 2023-03-21 | 2023-06-02 | 2023-06-03 | 2023-07-19 | Overhead | R16 | 2023-06-03 | 1 | 54 | 1 | 33 | 87 | 2023 | 2023 | R16
160172246444 | 163084246444 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-02 | 2021-09-03 | 2021-09-03 | 2023-03-14 | 2023-07-26 | Overhead | R16 | 2023-03-14 | 2 |  | 398 | 97 | 495 | 2021 | 2023 | R16
169715250459 | 165036250459 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-13 | 2021-09-13 | 2021-10-04 | 2022-01-04 | 2022-07-29 | Underground | R16 | 2022-01-04 | 1 | 16 | 67 | 149 | 230 | 2021 | 2022 | R16
164801303833 | 169059303833 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-20 | 2022-12-20 | 2022-12-22 |  | 2023-02-27 | Overhead | R16 | 2023-01-04 | 1 | 3 | 10 | 39 | 50 | 2022 | 2023 | R16
166618305133 | 167499305133 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-12 | 2022-12-12 | 2023-01-30 | 2023-03-23 | 2023-04-08 | Underground | R16 | 2023-03-23 | 1 | 36 | 39 | 12 | 85 | 2022 | 2023 | R16
166746318748 | 169092318748 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-10 | 2023-05-10 | 2023-05-10 |  | 2023-06-12 | Overhead | R16 | 2023-06-08 | 1 |  | 22 | 3 | 24 | 2023 | 2023 | R16
165603310648 | 161123310648 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-16 | 2023-02-25 | 2023-02-25 | 2023-07-18 | 2023-07-19 | Overhead | R16 | 2023-07-18 | 7 |  | 102 | 2 | 110 | 2023 | 2023 | R16
169007330265 | 163969330265 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-07 | 2023-06-08 | 2023-08-22 | 2023-09-28 | 2023-10-12 | Underground | R16 | 2023-09-28 | 2 | 54 | 28 | 11 | 92 | 2023 | 2023 | R16
166333319700 | 165512319700 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-24 | 2023-04-24 | 2023-05-19 |  | 2023-07-12 | Underground | R16 | 2023-07-12 | 1 | 20 | 39 |  | 58 | 2023 | 2023 | R16
168460304008 | 169198304008 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-21 | 2022-12-22 | 2022-12-27 | 2023-04-17 | 2023-06-12 | Overhead | R16 | 2023-04-17 | 2 | 4 | 80 | 41 | 124 | 2022 | 2023 | R16
161530304122 | 169526304122 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-22 |  | 2022-12-27 | 2023-01-26 | 2023-02-18 | Overhead | R16 | 2023-01-26 |  |  | 23 | 17 | 42 | 2022 | 2023 | R16
168326241629 | 165376241629 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-02 | 2021-08-02 | 2021-08-02 |  | 2021-10-11 | Overhead | R16 | 2021-09-13 | 1 |  | 31 | 21 | 51 | 2021 | 2021 | R16
160147306417 | 164935306417 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2023-01-19 | 2023-01-19 | 2023-01-30 | 2023-07-24 | 2023-08-24 | Underground | R16 | 2023-07-24 | 1 | 8 | 126 | 24 | 156 | 2023 | 2023 | R16
164660327025 | 164752327025 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-19 | 2023-04-19 | 2023-08-01 |  | 2023-12-05 | Underground | R16 | 2023-12-01 | 1 | 75 | 89 | 3 | 165 | 2023 | 2023 | R16
161360321778 | 161480321778 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-24 | 2023-06-09 | 2023-06-09 | 2023-08-03 | 2023-09-12 | Overhead | R16 | 2023-08-03 | 13 |  | 40 | 29 | 80 | 2023 | 2023 | R16
162124242242 | 166114242242 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-04 | 2021-08-04 | 2021-08-04 | 2021-12-22 | 2022-01-24 | Underground | R16 | 2021-12-22 | 1 |  | 101 | 24 | 124 | 2021 | 2022 | R16
166380318133 | 160811318133 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-03 | 2023-01-04 | 2023-05-05 |  | 2023-10-13 | Underground | R16 | 2023-07-13 | 2 | 88 | 50 | 67 | 204 | 2023 | 2023 | R16
167851322601 | 161323322601 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-23 | 2023-05-23 | 2023-06-18 | 2023-11-07 | 2023-11-10 | Underground | R16 | 2023-11-07 | 1 | 19 | 102 | 4 | 124 | 2023 | 2023 | R16
167624249200 | 165791249200 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-03 | 2021-09-22 | 2021-09-22 |  | 2022-01-12 | Underground | R16 | 2021-12-03 | 37 |  | 53 | 29 | 117 | 2021 | 2022 | R16
164931302975 | 167662302975 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-12 | 2022-12-12 | 2022-12-21 | 2023-04-24 | 2023-05-18 | Overhead | R16 | 2023-04-24 | 1 | 8 | 89 | 19 | 114 | 2022 | 2023 | R16
167333211385 | 165433211385 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-11-17 | 2020-11-19 | 2020-11-19 |  | 2021-04-15 | Underground | R16 | 2021-01-18 | 3 |  | 43 | 64 | 108 | 2020 | 2021 | R16
160996307582 | 161529307582 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-05 | 2023-01-29 | 2023-01-29 |  | 2023-05-05 | Overhead | R16 | 2023-03-30 | 17 |  | 44 | 27 | 87 | 2023 | 2023 | R16
166782322920 | 166749322920 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-21 | 2023-06-21 | 2023-06-21 | 2023-07-20 | 2023-07-20 | Overhead | R16 | 2023-07-20 | 1 |  | 22 |  | 22 | 2023 | 2023 | R16
165934307097 | 166414307097 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-26 | 2023-01-26 | 2023-01-26 |  | 2023-03-31 | Overhead | R16 | 2023-01-26 | 1 |  |  | 47 | 47 | 2023 | 2023 | R16
161606307573 | 161841307573 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-05 | 2023-01-06 | 2023-01-30 |  | 2023-07-31 | Underground | R16 | 2023-03-14 | 2 | 17 | 32 | 100 | 148 | 2023 | 2023 | R16
168315315650 | 161856315650 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-06 | 2023-04-13 | 2023-04-13 |  | 2023-08-15 | Overhead | R16 | 2023-04-27 | 6 |  | 11 | 79 | 94 | 2023 | 2023 | R16
167562238872 | 166992238872 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-11-24 | 2021-07-06 | 2021-07-14 |  | 2021-11-01 | Overhead | R16 |  | 161 | 7 |  |  | 245 | 2020 | 2021 | R16
161835323243 | 163120323243 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-02 | 2023-06-14 | 2023-06-26 | 2023-09-26 | 2023-11-08 | Underground | R16 | 2023-09-26 | 9 | 9 | 67 | 32 | 114 | 2023 | 2023 | R16
167567270047 | 160706270047 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2022-02-22 | 2022-02-22 | 2022-02-22 |  | 2023-11-20 | Underground | R16 |  | 1 |  |  |  | 455 | 2022 | 2023 | R16
164796307640 | 162632307640 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-01-10 | 2023-01-17 | 2023-01-29 |  | 2023-06-16 | Overhead | R16 |  | 6 | 9 |  |  | 114 | 2023 | 2023 | R16
168340247069 | 162751247069 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-01 | 2021-09-01 | 2021-09-09 | 2022-01-20 | 2022-03-01 | Underground | R16 | 2022-01-20 | 1 | 7 | 96 | 29 | 130 | 2021 | 2022 | R16
161607316276 | 165053316276 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-20 | 2023-04-20 | 2023-04-20 | 2023-07-20 | 2023-08-04 | Overhead | R16 | 2023-07-20 | 1 |  | 66 | 12 | 77 | 2023 | 2023 | R16
166427244822 | 160545244822 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-23 | 2021-08-23 | 2021-08-23 | 2021-10-07 | 2021-11-13 | Overhead | R16 | 2021-10-07 | 1 |  | 34 | 27 | 60 | 2021 | 2021 | R16
167602219542 | 160120219542 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-10 | 2020-12-10 | 2021-02-03 |  | 2021-06-03 | Underground | R16 | 2021-03-09 | 1 | 40 | 25 | 63 | 126 | 2020 | 2021 | R16
167562313621 | 168492313621 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-23 | 2023-03-23 | 2023-03-24 | 2023-03-31 | 2023-03-31 | Overhead | R16 | 2023-03-31 | 1 | 2 | 6 |  | 7 | 2023 | 2023 | R16
167732215870 | 164053215870 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-30 | 2020-12-30 | 2020-12-30 |  | 2021-11-02 | Overhead | R16 | 2021-06-15 | 1 |  | 120 | 101 | 220 | 2020 | 2021 | R16
163545308984 | 169604308984 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-09 | 2023-02-09 | 2023-02-09 | 2023-04-04 | 2023-04-18 | Overhead | R16 | 2023-04-04 | 1 |  | 39 | 11 | 49 | 2023 | 2023 | R16
169277322667 | 164543322667 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-18 | 2023-03-11 | 2023-06-19 | 2023-07-26 | 2023-08-24 | Underground | R16 | 2023-07-26 | 38 | 71 | 28 | 22 | 157 | 2023 | 2023 | R16
164603309928 | 160790309928 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-15 | 2023-02-15 | 2023-02-21 | 2023-04-02 | 2023-04-05 | Underground | R16 | 2023-04-02 | 1 | 5 | 29 | 3 | 36 | 2023 | 2023 | R16
169929245228 | 169270245228 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-17 | 2021-08-17 | 2021-08-25 |  | 2022-01-12 | Underground | R16 | 2021-12-02 | 1 | 7 | 72 | 30 | 107 | 2021 | 2022 | R16
165612316089 | 163199316089 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-28 | 2023-02-28 | 2023-04-17 | 2023-06-07 | 2023-07-20 | Underground | R16 | 2023-06-07 | 1 | 35 | 38 | 32 | 103 | 2023 | 2023 | R16
168980312033 | 165860312033 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-10 | 2023-03-10 | 2023-03-10 | 2023-04-12 | 2023-04-13 | Overhead | R16 | 2023-04-12 | 1 |  | 24 | 2 | 25 | 2023 | 2023 | R16
161957307463 | 166683307463 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-27 | 2023-01-27 | 2023-01-27 |  | 2023-05-18 | Underground | R16 | 2023-03-06 | 1 |  | 27 | 54 | 80 | 2023 | 2023 | R16
166347309658 | 161386309658 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-17 | 2023-02-17 | 2023-02-17 | 2023-03-25 | 2023-04-20 | Overhead | R16 | 2023-03-25 | 1 |  | 26 | 19 | 45 | 2023 | 2023 | R16
162740310960 | 163270310960 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-28 | 2023-02-28 | 2023-02-28 | 2023-03-09 | 2023-03-13 | Overhead | R16 | 2023-03-09 | 1 |  | 8 | 3 | 10 | 2023 | 2023 | R16
164365322507 | 160576322507 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-05-18 | 2023-06-16 | 2023-06-16 | 2023-08-28 | 2023-11-10 | Underground | R16 | 2023-08-28 | 22 |  | 52 | 55 | 127 | 2023 | 2023 | R16
169491324991 | 168553324991 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-29 | 2023-07-13 | 2023-07-14 | 2023-09-14 | 2023-09-19 | Overhead | R16 | 2023-09-14 | 11 | 2 | 45 | 4 | 59 | 2023 | 2023 | R16
168701242427 | 164266242427 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-07-28 | 2021-07-28 | 2021-08-06 | 2021-10-26 | 2021-10-28 | Underground | R16 | 2021-10-26 | 1 | 8 | 58 | 3 | 67 | 2021 | 2021 | R16
166905245906 | 169944245906 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-19 | 2021-08-19 | 2021-08-30 | 2021-12-13 | 2022-01-19 | Underground | R16 | 2021-12-13 | 1 | 8 | 76 | 28 | 110 | 2021 | 2022 | R16
168264268484 | 161643268484 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 ELEC DEVELOPMENT | Residential | 2022-01-13 | 2022-02-01 | 2022-02-10 |  | 2023-06-28 | Underground | R16 |  | 14 | 8 |  |  | 380 | 2022 | 2023 | R16
168232314610 | 163198314610 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-28 | 2023-02-28 | 2023-04-03 |  | 2023-05-18 | Underground | R16 | 2023-04-05 | 1 | 25 | 3 | 32 | 58 | 2023 | 2023 | R16
161236317187 | 166299317187 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-27 | 2023-04-27 | 2023-04-27 | 2023-09-13 | 2023-12-01 | Overhead | R16 | 2023-09-13 | 1 |  | 100 | 58 | 157 | 2023 | 2023 | R16
164763306944 | 165581306944 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-23 | 2023-01-23 | 2023-01-30 | 2023-01-23 | 2023-05-16 | Overhead | R16 | 2023-01-23 | 1 | 6 |  | 82 | 82 | 2023 | 2023 | R16
166546325897 | 169757325897 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-07 | 2023-07-07 | 2023-07-22 |  | 2023-08-25 | Underground | R16 | 2023-07-24 | 1 | 11 | 1 | 25 | 36 | 2023 | 2023 | R16
160667243861 | 166183243861 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2021-08-05 | 2021-08-05 | 2021-08-16 | 2021-09-24 | 2021-10-11 | Overhead | R16 | 2021-09-24 | 1 | 8 | 30 | 12 | 48 | 2021 | 2021 | R16
162389320810 | 168650320810 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-23 | 2023-03-23 | 2023-06-01 | 2023-09-19 | 2023-09-29 | Overhead | R16 | 2023-09-19 | 1 | 51 | 79 | 9 | 137 | 2023 | 2023 | R16
160931314366 | 164684314366 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-18 | 2023-02-02 | 2023-03-31 |  | 2023-08-18 | Underground | R16 | 2023-05-09 | 12 | 42 | 28 | 74 | 153 | 2023 | 2023 | R16
165454242901 | 167140242901 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-08-09 | 2021-08-09 | 2021-08-09 | 2023-03-03 | 2023-06-08 | Underground | R16 | 2023-03-03 | 1 |  | 410 | 70 | 479 | 2021 | 2023 | R16
168843311685 | 165790311685 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-24 | 2023-01-24 | 2023-03-07 | 2023-07-07 | 2023-07-07 | Underground | R16 | 2023-07-07 | 1 | 31 | 89 |  | 119 | 2023 | 2023 | R16
167203310418 | 162297310418 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2023-02-23 | 2023-02-23 | 2023-02-24 |  | 2023-06-16 | Overhead | R16 |  | 1 | 2 |  |  | 82 | 2023 | 2023 | R16
167895318296 | 163055318296 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-04-11 | 2023-05-08 | 2023-05-08 |  | 2023-12-08 | Overhead | R16 | 2023-12-08 | 20 |  | 155 |  | 174 | 2023 | 2023 | R16
166638314186 | 160553314186 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-03-31 | 2023-03-31 | 2023-03-31 |  | 2023-08-16 | Overhead | R16 | 2023-05-30 | 1 |  | 43 | 57 | 99 | 2023 | 2023 | R16
166119312799 | 162303312799 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-23 | 2023-02-23 | 2023-03-17 | 2023-05-24 | 2023-05-25 | Underground | R16 | 2023-05-24 | 1 | 17 | 49 | 2 | 66 | 2023 | 2023 | R16
168514221639 | 169586221639 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-01-25 | 2021-02-26 | 2021-02-26 |  | 2023-08-22 | Overhead | R16 | 2023-05-23 | 25 |  | 583 | 66 | 672 | 2021 | 2023 | R16
168254307891 | 160825307891 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-04 | 2023-02-01 | 2023-02-01 |  | 2023-07-24 | Overhead | R16 | 2023-02-22 | 21 |  | 16 | 109 | 144 | 2023 | 2023 | R16
168052312723 | 166764312723 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-04-18 | 2023-05-14 | Overhead | R16 | 2023-04-18 | 1 |  | 24 | 19 | 42 | 2023 | 2023 | R16
165876317801 | 166026317801 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-26 | 2023-05-02 | 2023-05-02 | 2023-08-09 | 2023-08-11 | Overhead | R16 | 2023-08-09 | 5 |  | 72 | 3 | 78 | 2023 | 2023 | R16
160647327704 | 166782327704 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-06-21 | 2023-07-07 | 2023-08-08 | 2023-09-11 | 2023-09-15 | Overhead | R16 | 2023-09-11 | 13 | 23 | 25 | 5 | 63 | 2023 | 2023 | R16
166636332522 | 169128332522 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-05 | 2023-07-05 | 2023-09-13 | 2023-09-13 | 2023-10-05 | Overhead | R16 | 2023-09-13 | 1 | 51 |  | 17 | 67 | 2023 | 2023 | R16
169466315533 | 160736315533 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-31 | 2023-04-05 | 2023-04-13 |  | 2023-08-14 | Overhead | R16 | 2023-05-01 | 4 | 7 | 13 | 76 | 97 | 2023 | 2023 | R16
167288323340 | 167038323340 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-22 | 2023-06-22 | 2023-06-26 | 2023-06-30 | 2023-07-24 | Overhead | R16 | 2023-06-30 | 1 | 3 | 5 | 17 | 23 | 2023 | 2023 | R16
166391335878 | 169384335878 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-12 |  | 2023-05-12 | 2023-12-05 | 2023-12-15 | Underground | R16 | 2023-12-05 |  |  | 148 | 9 | 156 | 2023 | 2023 | R16
168052246430 | 161600246430 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-26 |  | 2021-08-26 | 2021-11-18 | 2022-01-07 | Underground | R16 | 2021-11-18 |  |  | 61 | 37 | 97 | 2021 | 2022 | R16
168834210645 | 160790210645 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-27 | 2020-10-27 | 2020-11-13 |  | 2021-04-16 | Underground | R16 | 2021-01-04 | 1 | 14 | 37 | 75 | 124 | 2020 | 2021 | R16
164403245913 | 161206245913 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-08-25 | 2021-08-25 | 2021-08-31 | 2022-02-25 | 2022-02-25 | Underground | R16 | 2022-02-25 | 1 | 5 | 129 |  | 133 | 2021 | 2022 | R16
160652251708 | 163648251708 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-07 | 2021-09-07 | 2021-10-11 |  | 2021-12-02 | Underground | R16 | 2021-11-08 | 1 | 25 | 21 | 19 | 63 | 2021 | 2021 | R16
160464313646 | 168982313646 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-24 | 2023-03-24 | 2023-03-24 | 2023-07-17 | 2023-07-17 | Underground | R16 | 2023-07-17 | 1 |  | 82 |  | 82 | 2023 | 2023 | R16
163993242004 | 165748242004 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-08-03 | 2021-08-03 | 2021-08-03 |  | 2021-10-25 | Underground | R16 | 2021-09-15 | 1 |  | 32 | 29 | 60 | 2021 | 2021 | R16
168943241953 | 165989241953 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Commercial | 2021-08-04 | 2021-08-04 | 2021-08-04 | 2022-01-19 | 2022-02-08 | Underground | R16 | 2022-01-19 | 1 |  | 121 | 15 | 135 | 2021 | 2022 | R16
162776310849 | 163059310849 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-27 | 2023-02-27 | 2023-02-27 |  | 2023-08-08 | Overhead | R16 | 2023-04-20 | 1 |  | 39 | 79 | 117 | 2023 | 2023 | R16
169171255076 | 168555255076 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-08-13 | 2021-08-16 | 2021-11-04 |  | 2022-02-18 | Underground | R16 |  | 2 | 59 |  |  | 136 | 2021 | 2022 | R16
167570322197 | 168587322197 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-23 | 2023-03-23 | 2023-06-15 | 2023-07-20 | 2023-07-20 | Underground | R16 | 2023-07-20 | 1 | 61 | 26 |  | 86 | 2023 | 2023 | R16
169182259071 | 164303259071 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-21 | 2021-11-29 | 2021-11-29 |  | 2022-03-23 | Overhead | R16 | 2022-02-28 | 28 |  | 66 | 18 | 110 | 2021 | 2022 | R16
169373325550 | 166257325550 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-20 | 2023-06-20 | 2023-07-19 | 2023-09-06 | 2023-09-14 | Underground | R16 | 2023-09-06 | 1 | 22 | 36 | 7 | 63 | 2023 | 2023 | R16
163487242941 | 167213242941 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2021-09-09 | 2021-10-25 | Overhead | R16 | 2021-09-09 | 1 |  | 23 | 33 | 55 | 2021 | 2021 | R16
167169323633 | 168527323633 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-29 | 2023-06-29 | 2023-06-29 | 2023-08-16 | 2023-09-25 | Overhead | R16 | 2023-08-16 | 1 |  | 35 | 29 | 63 | 2023 | 2023 | R16
169541308174 | 161057308174 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-04 | 2023-01-04 | 2023-02-03 | 2023-03-27 | 2023-03-28 | Underground | R16 | 2023-03-27 | 1 | 23 | 37 | 2 | 60 | 2023 | 2023 | R16
168160322995 | 163432322995 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-06-05 | 2023-06-23 | 2023-06-23 |  | 2023-06-29 | Overhead | R16 | 2023-06-23 | 15 |  |  | 5 | 19 | 2023 | 2023 | R16
168927324136 | 164134324136 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-08 | 2023-06-08 | 2023-07-06 | 2023-08-03 | 2023-09-11 | Overhead | R16 | 2023-08-03 | 1 | 21 | 21 | 28 | 68 | 2023 | 2023 | R16
167138324791 | 165506324791 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2023-06-15 | 2023-06-15 | 2023-07-12 | 2023-08-16 | 2023-08-31 | Overhead | R16 | 2023-08-16 | 1 | 20 | 26 | 12 | 56 | 2023 | 2023 | R16
160925307460 | 164067307460 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-17 | 2023-01-17 | 2023-01-27 |  | 2023-07-31 | Underground | R16 | 2023-03-07 | 1 | 9 | 28 | 105 | 140 | 2023 | 2023 | R16
169491226687 | 162818226687 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2021-03-23 | 2021-03-26 | 2021-04-13 |  | 2021-11-05 | Overhead | R16 |  | 4 | 13 |  |  | 164 | 2021 | 2021 | R16
161968325664 | 160701325664 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-12 | 2023-07-19 | 2023-07-19 | 2023-12-07 | 2023-12-14 | Overhead | R16 | 2023-12-07 | 6 |  | 102 | 6 | 112 | 2023 | 2023 | R16
169571212666 | 165762212666 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-19 | 2020-12-03 | 2020-12-03 |  | 2021-04-20 | Underground | R16 | 2021-01-12 | 11 |  | 29 | 71 | 109 | 2020 | 2021 | R16
165785307077 | 163138307077 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2023-01-11 | 2023-01-12 | 2023-01-25 | 2023-06-28 | 2023-06-29 | Underground | R16 | 2023-06-28 | 2 | 10 | 111 | 2 | 122 | 2023 | 2023 | R16
168963249081 | 165027249081 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-13 | 2021-09-13 | 2021-09-22 |  | 2022-03-25 | Underground | R16 | 2022-03-02 | 1 | 8 | 116 | 18 | 140 | 2021 | 2022 | R16
169689210154 | 161003210154 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-28 | 2020-11-10 | 2020-11-10 |  | 2021-08-16 | Underground | R16 | 2021-03-19 | 10 |  | 94 | 107 | 209 | 2020 | 2021 | R16
165281309856 | 161623309856 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-20 | 2023-02-22 | 2023-02-22 | 2023-10-12 | 2023-11-15 | Overhead | R16 | 2023-10-12 | 3 |  | 167 | 25 | 193 | 2023 | 2023 | R16
163373309555 | 160312309555 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-13 | 2023-02-13 | 2023-02-16 |  | 2023-05-18 | Underground | R16 | 2023-03-21 | 1 | 4 | 24 | 43 | 69 | 2023 | 2023 | R16
166460320634 | 160270320634 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2023-05-17 | 2023-05-17 | 2023-05-31 | 2023-06-07 | 2023-08-23 | Overhead | R16 | 2023-06-07 | 1 | 11 | 6 | 56 | 71 | 2023 | 2023 | R16
167004315317 | 167630315317 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-20 |  | 2023-03-20 | 2023-10-20 | 2023-11-03 | Underground | R16 | 2023-10-20 |  |  | 155 | 11 | 165 | 2023 | 2023 | R16
169819251494 | 165418251494 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-08-02 | 2021-08-03 | 2021-10-11 |  | 2021-12-29 | Overhead | R16 |  | 2 | 50 |  |  | 108 | 2021 | 2021 | R16
169819251496 | 165651251496 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-08-03 | 2021-08-03 | 2021-10-11 |  | 2021-12-29 | Overhead | R16 |  | 1 | 50 |  |  | 107 | 2021 | 2021 | R16
167985317537 | 160357317537 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-30 | 2023-05-01 | 2023-05-01 | 2023-11-17 | 2023-12-14 | Underground | R16 | 2023-11-17 | 23 |  | 145 | 20 | 186 | 2023 | 2023 | R16
169819251703 | 165812251703 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-08-04 | 2021-08-04 | 2021-10-11 |  | 2021-12-29 | Overhead | R16 |  | 1 | 49 |  |  | 106 | 2021 | 2021 | R16
160397310244 | 169103310244 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-08 | 2023-02-23 | 2023-02-23 |  | 2023-08-14 | Overhead | R16 | 2023-03-23 | 12 |  | 21 | 103 | 134 | 2023 | 2023 | R16
160109305527 | 160627305527 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-03 | 2023-01-03 | 2023-01-30 | 2023-01-10 | 2023-05-31 | Underground | R16 | 2023-01-10 | 1 | 20 |  | 102 | 107 | 2023 | 2023 | R16
163533321559 | 161292321559 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-23 | 2023-05-25 | 2023-06-08 | 2023-07-21 | 2023-07-24 | Underground | R16 | 2023-07-21 | 3 | 11 | 32 | 2 | 45 | 2023 | 2023 | R16
160330250522 | 165139250522 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-09-13 | 2021-09-14 | 2021-10-04 | 2022-10-07 | 2022-11-14 | Underground | R16 | 2022-10-07 | 2 | 15 | 265 | 27 | 306 | 2021 | 2022 | R16
161734319904 | 160887319904 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-22 | 2023-05-22 | 2023-05-22 | 2023-07-18 | 2023-07-20 | Overhead | R16 | 2023-07-18 | 1 |  | 42 | 3 | 44 | 2023 | 2023 | R16
168867327241 | 165187327241 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-14 | 2023-06-16 | 2023-08-03 | 2023-10-10 | 2023-10-12 | Overhead | R16 | 2023-10-10 | 3 | 35 | 49 | 3 | 87 | 2023 | 2023 | R16
165300313247 | 167885313247 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-21 | 2023-03-21 | 2023-03-21 | 2023-05-11 | 2023-08-22 | Overhead | R16 | 2023-05-11 | 1 |  | 38 | 74 | 111 | 2023 | 2023 | R16
162692319941 | 164345319941 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-04-18 | 2023-05-02 | 2023-05-22 | 2023-10-31 | 2023-11-02 | Underground | R16 | 2023-10-31 | 11 | 15 | 117 | 3 | 143 | 2023 | 2023 | R16
161274313603 | 163032313603 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-27 | 2023-03-20 | 2023-03-24 |  | 2023-08-14 | Overhead | R16 | 2023-05-05 | 16 | 5 | 31 | 72 | 121 | 2023 | 2023 | R16
169301244907 | 160659244907 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-08-23 | 2021-08-23 | 2021-08-23 |  | 2021-12-02 | Overhead | R16 | 2021-11-08 | 1 |  | 56 | 19 | 74 | 2021 | 2021 | R16
167502322921 | 166147322921 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-19 | 2023-06-21 | 2023-06-21 | 2023-09-14 | 2023-11-08 | Overhead | R16 | 2023-09-14 | 3 |  | 62 | 40 | 103 | 2023 | 2023 | R16
166455251783 | 164939251783 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-13 | 2021-09-13 | 2021-10-12 |  | 2022-01-07 | Underground | R16 | 2021-12-01 | 1 | 22 | 37 | 28 | 85 | 2021 | 2022 | R16
165812313056 | 163381313056 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2023-02-28 | 2023-02-28 | 2023-03-20 |  | 2023-03-31 | Overhead | R16 | 2023-03-23 | 1 | 15 | 4 | 7 | 24 | 2023 | 2023 | R16
164439319937 | 169841319937 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-15 | 2023-05-15 | 2023-05-23 |  | 2023-06-27 | Overhead | R16 | 2023-05-23 | 1 | 7 |  | 26 | 32 | 2023 | 2023 | R16
166455290723 | 161854290723 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-27 | 2021-08-27 | 2022-08-30 |  | 2023-05-30 | Underground | R16 | 2023-02-09 | 1 | 263 | 118 | 79 | 458 | 2021 | 2023 | R16
167111318764 | 166495318764 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-01-26 | 2023-01-26 | 2023-05-10 |  | 2023-09-27 | Overhead | R16 |  | 1 | 75 |  |  | 175 | 2023 | 2023 | R16
161913253607 | 160217253607 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-20 | 2021-08-30 | 2021-10-25 |  | 2022-05-03 | Underground | R16 | 2022-04-11 | 7 | 41 | 121 | 17 | 183 | 2021 | 2022 | R16
160793324705 | 167416324705 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-26 | 2023-06-26 | 2023-07-10 | 2023-07-19 | 2023-08-03 | Overhead | R16 | 2023-07-19 | 1 | 11 | 8 | 12 | 29 | 2023 | 2023 | R16
163744327284 | 167744327284 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-02 | 2023-02-02 | 2023-08-03 | 2023-08-16 | 2023-09-20 | Underground | R16 | 2023-08-16 | 1 | 131 | 10 | 26 | 165 | 2023 | 2023 | R16
162412249125 | 163666249125 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-07 | 2021-09-07 | 2021-09-23 | 2022-03-09 | 2022-03-10 | Underground | R16 | 2022-03-09 | 1 | 13 | 120 | 2 | 133 | 2021 | 2022 | R16
160563231541 | 162326231541 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2021-05-03 | 2021-05-03 | 2021-05-19 |  | 2022-03-31 | Underground | R16 | 2022-03-11 | 1 | 13 | 213 | 15 | 239 | 2021 | 2022 | R16
167841323258 | 167593323258 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-27 | 2023-06-27 | 2023-06-27 | 2023-11-13 | 2023-12-11 | Overhead | R16 | 2023-11-13 | 1 |  | 100 | 21 | 120 | 2023 | 2023 | R16
161387315095 | 160774315095 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-31 | 2023-03-31 | 2023-04-07 |  | 2023-08-09 | Underground | R16 | 2023-04-19 | 1 | 6 | 9 | 81 | 94 | 2023 | 2023 | R16
163686317635 | 166700317635 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-30 | 2023-05-01 | 2023-05-01 | 2023-05-22 | 2023-06-13 | Overhead | R16 | 2023-05-22 | 1 |  | 16 | 17 | 32 | 2023 | 2023 | R16
168676308833 | 162380308833 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-09 | 2023-02-08 | 2023-02-08 | 2023-05-11 | 2023-05-17 | Overhead | R16 | 2023-05-11 | 23 |  | 67 | 5 | 93 | 2023 | 2023 | R16
167769244047 | 169278244047 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-17 | 2021-08-17 | 2021-08-17 | 2022-10-12 | 2023-06-08 | Underground | R16 | 2022-10-12 | 1 |  | 302 | 172 | 473 | 2021 | 2023 | R16
164770321646 | 164276321646 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-08 | 2023-06-08 | 2023-06-08 | 2023-06-14 | 2023-06-28 | Overhead | R16 | 2023-06-14 | 1 |  | 5 | 11 | 15 | 2023 | 2023 | R16
160826323468 | 163859323468 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-07 | 2023-06-07 | 2023-06-28 | 2023-11-27 | 2023-12-04 | Underground | R16 | 2023-11-27 | 1 | 16 | 109 | 6 | 129 | 2023 | 2023 | R16
164671242122 | 165817242122 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-04 | 2021-08-04 | 2021-08-04 | 2021-10-07 | 2021-11-18 | Overhead | R16 | 2021-10-07 | 1 |  | 47 | 31 | 77 | 2021 | 2021 | R16
160714313467 | 168376313467 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-22 | 2023-03-23 | 2023-03-23 | 2023-05-08 | 2023-06-13 | Overhead | R16 | 2023-05-08 | 2 |  | 33 | 27 | 60 | 2023 | 2023 | R16
161193323337 | 167611323337 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-27 | 2023-06-27 | 2023-06-27 | 2023-09-26 | 2023-12-07 | Overhead | R16 | 2023-09-26 | 1 |  | 66 | 53 | 118 | 2023 | 2023 | R16
162318320609 | 162267320609 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-05-30 | 2023-05-30 | 2023-05-30 | 2023-05-30 | 2023-06-12 | Overhead | R16 | 2023-05-30 | 1 |  |  | 10 | 10 | 2023 | 2023 | R16
160838213959 | 166311213959 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-20 | 2020-12-15 | 2020-12-15 |  | 2021-08-12 | Underground | R16 | 2021-03-22 | 18 |  | 70 | 104 | 190 | 2020 | 2021 | R16
169877323319 | 167325323319 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-26 | 2023-06-26 | 2023-06-27 | 2023-07-27 | 2023-08-08 | Overhead | R16 | 2023-07-27 | 1 | 2 | 23 | 9 | 32 | 2023 | 2023 | R16
161264319295 | 160239319295 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-17 | 2023-05-17 | 2023-05-17 | 2023-11-15 | 2023-11-20 | Overhead | R16 | 2023-11-15 | 1 |  | 131 | 4 | 134 | 2023 | 2023 | R16
167068313861 | 168487313861 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-03-23 | 2023-03-27 | 2023-03-27 |  | 2023-07-31 | Overhead | R16 | 2023-04-06 | 3 |  | 9 | 83 | 93 | 2023 | 2023 | R16
164120306129 | 164121306129 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2023-01-17 | 2023-01-17 | 2023-01-25 | 2023-01-17 | 2023-06-04 | Underground | R16 | 2023-01-17 | 1 | 7 |  | 99 | 99 | 2023 | 2023 | R16
161421309015 | 166695309015 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2023-01-27 | 2023-01-27 | 2023-02-10 | 2023-08-08 | 2023-08-14 | Underground | R16 | 2023-08-08 | 1 | 11 | 128 | 5 | 142 | 2023 | 2023 | R16
165271317751 | 162525317751 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-10 | 2023-04-10 | 2023-05-02 | 2023-08-17 | 2023-09-18 | Underground | R16 | 2023-08-17 | 1 | 17 | 78 | 23 | 116 | 2023 | 2023 | R16
165662316179 | 162748316179 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-11 | 2023-04-18 | 2023-04-18 | 2023-04-27 | 2023-08-09 | Overhead | R16 | 2023-04-27 | 6 |  | 8 | 75 | 87 | 2023 | 2023 | R16
169823308810 | 169044308810 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-08 | 2023-02-08 | 2023-02-08 | 2023-04-12 | 2023-04-13 | Overhead | R16 | 2023-04-12 | 1 |  | 46 | 2 | 47 | 2023 | 2023 | R16
161078216316 | 165344216316 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-06 | 2021-01-06 | 2021-01-06 |  | 2021-04-23 | Underground | R16 | 2021-02-02 | 1 |  | 20 | 59 | 78 | 2021 | 2021 | R16
162684246106 | 166990246106 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-09 | 2021-08-09 | 2021-09-01 | 2021-12-27 | 2021-12-28 | Underground | R16 | 2021-12-27 | 1 | 18 | 84 | 2 | 102 | 2021 | 2021 | R16
166358258576 | 163683258576 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-06 | 2021-09-06 | 2021-11-24 | 2022-02-11 | 2022-02-25 | Underground | R16 | 2022-02-11 | 1 | 58 | 58 | 11 | 125 | 2021 | 2022 | R16
166799243454 | 168461243454 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-13 | 2021-08-13 | 2021-08-13 | 2021-10-05 | 2021-11-10 | Overhead | R16 | 2021-10-05 | 1 |  | 38 | 27 | 64 | 2021 | 2021 | R16
161103212766 | 168653212766 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-04 | 2020-12-04 | 2020-12-04 |  | 2021-04-14 | Overhead | R16 | 2020-12-16 | 1 |  | 9 | 86 | 94 | 2020 | 2021 | R16
165450250574 | 168836250574 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-16 | 2021-08-16 | 2021-10-05 |  | 2021-12-29 | Underground | R16 | 2021-11-19 | 1 | 37 | 34 | 29 | 98 | 2021 | 2021 | R16
166709247270 | 166770247270 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OD | Commercial | 2021-08-06 | 2021-08-13 | 2021-09-09 |  | 2021-10-19 | Overhead | R16 | 2021-09-08 | 6 | 20 |  | 30 | 53 | 2021 | 2021 | R16
166941322224 | 165206322224 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-14 | 2023-06-14 | 2023-06-14 | 2023-09-29 | 2023-11-15 | Overhead | R16 | 2023-09-29 | 1 |  | 78 | 34 | 111 | 2023 | 2023 | R16
166445308583 | 166127308583 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-01-25 | 2023-02-06 | 2023-02-06 | 2023-02-19 | 2023-08-23 | Overhead | R16 | 2023-02-19 | 9 |  | 10 | 133 | 151 | 2023 | 2023 | R16
161841314030 | 160074314030 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-03-29 |  | 2023-03-29 | 2023-04-13 | 2023-06-13 | Overhead | R16 | 2023-04-13 |  |  | 12 | 44 | 55 | 2023 | 2023 | R16
164276321563 | 163727321563 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-06 | 2023-06-06 | 2023-06-07 | 2023-07-31 | 2023-09-07 | Overhead | R16 | 2023-07-31 | 1 | 2 | 39 | 29 | 68 | 2023 | 2023 | R16
169055314285 | 160443314285 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-30 | 2023-03-30 | 2023-03-30 | 2023-06-26 | 2023-07-06 | Overhead | R16 | 2023-06-26 | 1 |  | 63 | 9 | 71 | 2023 | 2023 | R16
160083246951 | 164110246951 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-08 | 2021-09-08 | 2021-09-08 | 2022-02-04 | 2022-02-07 | Overhead | R16 | 2022-02-04 | 1 |  | 108 | 2 | 109 | 2021 | 2022 | R16
167363335373 | 169802335373 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-07 | 2023-07-07 | 2023-10-12 |  | 2023-12-14 | Underground | R16 | 2023-12-06 | 1 | 70 | 40 | 7 | 115 | 2023 | 2023 | R16
166420311325 | 162699311325 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2023-02-24 | 2023-02-24 | 2023-03-03 |  | 2023-08-30 | Underground | R16 |  | 1 | 6 |  |  | 134 | 2023 | 2023 | R16
166993315717 | 163281315717 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-28 | 2023-02-28 | 2023-04-13 | 2023-06-28 | 2023-06-29 | Underground | R16 | 2023-06-28 | 1 | 33 | 55 | 2 | 88 | 2023 | 2023 | R16
166416322292 | 160571322292 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-18 | 2023-05-18 | 2023-06-15 | 2023-12-05 | 2023-12-06 | Underground | R16 | 2023-12-05 | 1 | 21 | 124 | 2 | 145 | 2023 | 2023 | R16
165943308371 | 165751308371 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-24 | 2023-02-04 | 2023-02-04 | 2023-07-17 | 2023-07-26 | Overhead | R16 | 2023-07-17 | 9 |  | 116 | 8 | 132 | 2023 | 2023 | R16
162513318005 | 167859318005 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-04 | 2023-05-04 | 2023-05-04 | 2023-07-06 | 2023-07-06 | Overhead | R16 | 2023-07-06 | 1 |  | 46 |  | 46 | 2023 | 2023 | R16
165665246962 | 160553246962 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-23 | 2021-08-23 | 2021-09-08 | 2021-10-20 | 2021-10-21 | Overhead | R16 | 2021-10-20 | 1 | 13 | 31 | 2 | 44 | 2021 | 2021 | R16
160424319556 | 165851319556 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-25 | 2023-04-25 | 2023-05-18 | 2023-06-27 | 2023-08-21 | Underground | R16 | 2023-06-27 | 1 | 18 | 29 | 40 | 85 | 2023 | 2023 | R16
164355247978 | 160604247978 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-23 | 2021-08-23 | 2021-09-16 |  | 2021-12-17 | Underground | R16 | 2021-11-18 | 1 | 19 | 46 | 22 | 85 | 2021 | 2021 | R16
168038245147 | 161126245147 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-10-07 | 2021-11-13 | Overhead | R16 | 2021-10-07 | 1 |  | 32 | 27 | 58 | 2021 | 2021 | R16
169660241104 | 164142241104 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-07-28 | 2021-07-28 | 2021-07-28 | 2022-03-29 | 2022-04-25 | Overhead | R16 | 2022-03-29 | 1 |  | 175 | 20 | 194 | 2021 | 2022 | R16
166444307672 | 166908307672 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-30 | 2023-01-30 | 2023-01-30 |  | 2023-08-14 | Overhead | R16 | 2023-04-26 | 1 |  | 63 | 79 | 141 | 2023 | 2023 | R16
165573281702 | 165394281702 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-14 | 2022-06-06 | 2022-06-06 | 2022-07-19 | 2022-07-20 | Overhead | R16 | 2022-07-19 | 190 |  | 32 | 2 | 222 | 2021 | 2022 | R16
164308249024 | 165203249024 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-13 | 2021-09-14 | 2021-09-22 | 2021-12-29 | 2022-02-10 | Overhead | R16 | 2021-12-29 | 2 | 7 | 71 | 32 | 109 | 2021 | 2022 | R16
169679245388 | 161478245388 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-10-04 | 2021-11-18 | Overhead | R16 | 2021-10-04 | 1 |  | 28 | 34 | 61 | 2021 | 2021 | R16
163477315908 | 163242315908 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-28 | 2023-02-28 | 2023-04-14 | 2023-08-11 | 2023-09-20 | Underground | R16 | 2023-08-11 | 1 | 34 | 86 | 29 | 147 | 2023 | 2023 | R16
161057317465 | 166382317465 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-04-27 | 2023-05-01 | 2023-05-01 |  | 2023-08-31 | Overhead | R16 | 2023-05-26 | 3 |  | 20 | 70 | 91 | 2023 | 2023 | R16
161453315248 | 169138315248 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-27 | 2023-03-27 | 2023-04-10 |  | 2023-08-17 | Underground | R16 | 2023-05-04 | 1 | 11 | 19 | 76 | 104 | 2023 | 2023 | R16
164072321299 | 163900321299 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-07 | 2023-06-07 | 2023-06-07 | 2023-07-12 | 2023-08-16 | Overhead | R16 | 2023-07-12 | 1 |  | 26 | 26 | 51 | 2023 | 2023 | R16
165046318912 | 165728318912 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-25 | 2023-05-12 | 2023-05-12 | 2023-10-03 | 2023-10-27 | Overhead | R16 | 2023-10-03 | 14 |  | 103 | 19 | 134 | 2023 | 2023 | R16
167602317159 | 166510317159 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-28 | 2023-04-28 | 2023-04-28 | 2023-07-17 | 2023-07-31 | Overhead | R16 | 2023-07-17 | 1 |  | 57 | 11 | 67 | 2023 | 2023 | R16
166445317699 | 167192317699 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-02 | 2023-05-02 | 2023-05-02 | 2023-05-09 | 2023-06-13 | Overhead | R16 | 2023-05-09 | 1 |  | 6 | 26 | 31 | 2023 | 2023 | R16
165138309479 | 161855309479 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-05 | 2023-01-05 | 2023-02-16 |  | 2023-08-16 | Underground | R16 | 2023-05-01 | 1 | 31 | 53 | 78 | 160 | 2023 | 2023 | R16
163263269205 | 162124269205 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-08-30 | 2021-08-30 | 2022-02-15 |  | 2023-04-25 | Underground | R16 |  | 1 | 122 |  |  | 432 | 2021 | 2023 | R16
169727305403 | 162338305403 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-01-09 |  | 2023-01-09 | 2023-01-09 | 2023-01-13 | Overhead | R16 | 2023-01-09 |  |  |  | 5 | 5 | 2023 | 2023 | R16
161255305696 | 168286305696 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-12-15 | 2023-01-03 | 2023-01-25 | 2023-02-08 | 2023-05-17 | Overhead | R16 | 2023-02-08 | 14 | 17 | 11 | 71 | 110 | 2022 | 2023 | R16
164811303824 | 169001303824 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-20 | 2022-12-20 | 2022-12-22 |  | 2023-06-12 | Overhead | R16 | 2023-04-25 | 1 | 3 | 89 | 35 | 125 | 2022 | 2023 | R16
169632319272 | 167330319272 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-02 | 2023-05-16 | 2023-05-16 | 2023-09-19 | 2023-09-25 | Overhead | R16 | 2023-09-19 | 11 |  | 91 | 5 | 105 | 2023 | 2023 | R16
166553313069 | 167680313069 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2023-03-20 | 2023-03-20 | 2023-03-20 | 2023-05-26 | 2023-05-30 | Overhead | R16 | 2023-05-26 | 1 |  | 50 | 3 | 52 | 2023 | 2023 | R16
163060318130 | 168138318130 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-05-05 | 2023-05-05 | 2023-05-05 | 2023-10-23 | 2023-11-08 | Underground | R16 | 2023-10-23 | 1 |  | 122 | 13 | 134 | 2023 | 2023 | R16
169491248918 | 165069248918 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-13 | 2021-09-22 | 2021-09-22 |  | 2021-12-17 | Underground | R16 | 2021-12-13 | 8 |  | 59 | 5 | 70 | 2021 | 2021 | R16
165859249031 | 165140249031 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-13 | 2021-09-22 | 2021-09-22 |  | 2022-02-02 | Overhead | R16 | 2022-01-13 | 8 |  | 82 | 15 | 103 | 2021 | 2022 | R16
163729304061 | 169285304061 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-21 | 2022-12-21 | 2022-12-22 | 2023-03-21 | 2023-05-18 | Overhead | R16 | 2023-03-21 | 1 | 2 | 64 | 43 | 107 | 2022 | 2023 | R16
161922213392 | 160066213392 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-10 | 2020-12-10 | 2020-12-10 |  | 2021-04-29 | Overhead | R16 | 2021-02-11 | 1 |  | 46 | 56 | 101 | 2020 | 2021 | R16
165564320390 | 161322320390 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2023-05-23 | 2023-05-26 | 2023-05-26 | 2023-09-11 | 2023-09-14 | Underground | R16 | 2023-09-11 | 4 |  | 77 | 4 | 83 | 2023 | 2023 | R16
162002211692 | 166880211692 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-24 | 2020-11-24 | 2020-11-24 |  | 2021-11-08 | Overhead | R16 | 2021-05-12 | 1 |  | 122 | 129 | 250 | 2020 | 2021 | R16
166715313432 | 168797313432 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-03-24 | 2023-03-24 | 2023-03-24 | 2023-05-26 | 2023-05-26 | Overhead | R16 | 2023-05-26 | 1 |  | 46 |  | 46 | 2023 | 2023 | R16
160605246335 | 163176246335 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-02 | 2021-09-02 | 2021-09-02 |  | 2022-04-01 | Overhead | R16 | 2022-03-16 | 1 |  | 140 | 13 | 152 | 2021 | 2022 | R16
162018216796 | 169492216796 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-08 | 2020-12-08 | 2021-01-12 |  | 2021-05-06 | Underground | R16 | 2021-02-18 | 1 | 26 | 28 | 56 | 108 | 2020 | 2021 | R16
164228316008 | 163697316008 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2023-04-14 | 2023-04-14 | 2023-04-17 | 2023-11-14 | 2023-07-21 | Underground | R16 | 2023-11-14 | 1 | 2 | 152 |  | 71 | 2023 | 2023 | R16
164915321418 | 163514321418 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-05 | 2023-06-07 | 2023-06-07 | 2023-08-18 | 2023-10-03 | Overhead | R16 | 2023-08-18 | 3 |  | 53 | 33 | 87 | 2023 | 2023 | R16
168230309471 | 160565309471 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-15 | 2023-02-15 | 2023-02-15 |  | 2023-03-31 | Overhead | R16 | 2023-03-09 | 1 |  | 17 | 17 | 33 | 2023 | 2023 | R16
166660317182 | 165092317182 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-04-20 | 2023-04-27 | 2023-04-27 | 2023-07-25 | 2023-07-28 | Overhead | R16 | 2023-07-25 | 6 |  | 64 | 4 | 72 | 2023 | 2023 | R16
162354210617 | 165079210617 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-16 | 2020-11-16 | 2020-11-16 |  | 2021-04-16 | Overhead | R16 | 2021-01-04 | 1 |  | 36 | 75 | 110 | 2020 | 2021 | R16
166590325481 | 163326325481 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-04 | 2023-06-04 | 2023-07-18 | 2023-10-03 | 2023-12-05 | Underground | R16 | 2023-10-03 | 0 | 32 | 56 | 46 | 132 | 2023 | 2023 | R16
165753309503 | 167295309503 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2023-01-31 | 2023-01-31 | 2023-02-15 | 2023-07-17 | 2023-07-26 | Underground | R16 | 2023-07-17 | 1 | 12 | 109 | 8 | 127 | 2023 | 2023 | R16
168720333624 | 166347333624 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-14 | 2023-03-14 | 2023-09-26 | 2023-11-27 | 2023-11-28 | Underground | R16 | 2023-11-27 | 1 | 141 | 45 | 2 | 186 | 2023 | 2023 | R16
167264244398 | 169219244398 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-17 | 2021-08-19 | 2021-08-19 | 2021-10-07 | 2021-11-18 | Overhead | R16 | 2021-10-07 | 3 |  | 36 | 31 | 68 | 2021 | 2021 | R16
162415265630 | 168942265630 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-04 | 2020-12-14 | 2022-01-21 |  | 2022-04-21 | Underground | R16 | 2022-03-23 | 7 | 290 | 44 | 22 | 360 | 2020 | 2022 | R16
166840307659 | 167279307659 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-31 | 2023-01-31 | 2023-01-31 | 2023-08-02 | 2023-08-28 | Overhead | R16 | 2023-08-02 | 1 |  | 132 | 19 | 150 | 2023 | 2023 | R16
160942324238 | 167650324238 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2023-05-03 | 2023-05-04 | 2023-07-07 | 2023-11-15 | 2023-12-12 | Overhead | R16 | 2023-11-15 | 2 | 47 | 94 | 20 | 160 | 2023 | 2023 | R16
162497221246 | 168142221246 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-02 | 2021-02-08 | 2021-02-22 |  | 2021-12-28 | Underground | R16 | 2021-11-23 | 49 | 11 | 197 | 26 | 280 | 2020 | 2021 | R16
161445314987 | 168676314987 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-24 | 2023-03-24 | 2023-04-06 | 2023-04-27 | 2023-08-08 | Underground | R16 | 2023-04-27 | 1 | 10 | 16 | 74 | 98 | 2023 | 2023 | R16
161905313918 | 163229313918 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-28 | 2023-03-28 | 2023-03-28 |  | 2023-08-14 | Overhead | R16 | 2023-05-04 | 21 |  | 28 | 73 | 120 | 2023 | 2023 | R16
160873324421 | 169749324421 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-15 | 2023-07-07 | 2023-07-07 | 2023-11-09 | 2023-12-14 | Overhead | R16 | 2023-11-09 | 40 |  | 90 | 26 | 154 | 2023 | 2023 | R16
162645231264 | 168767231264 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-12-04 | 2021-04-20 | 2021-05-18 |  | 2021-10-25 | Underground | R16 | 2021-07-22 | 98 | 21 | 48 | 68 | 232 | 2020 | 2021 | R16
160687246892 | 164073246892 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-08 | 2021-09-08 | 2021-09-08 | 2021-09-28 | 2021-12-02 | Underground | R16 | 2021-09-28 | 1 |  | 15 | 48 | 62 | 2021 | 2021 | R16
160854319109 | 169725319109 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-15 | 2023-05-15 | 2023-05-15 |  | 2023-06-29 | Overhead | R16 | 2023-06-05 | 1 |  | 16 | 19 | 34 | 2023 | 2023 | R16
164789306293 | 164591306293 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-18 | 2023-01-18 | 2023-01-30 | 2023-07-31 | 2023-08-01 | Overhead | R16 | 2023-07-31 | 1 | 9 | 131 | 2 | 140 | 2023 | 2023 | R16
166644259020 | 166277259020 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-05 | 2021-08-05 | 2021-11-29 | 2022-05-06 | 2022-05-25 | Underground | R16 | 2022-05-06 | 1 | 83 | 115 | 14 | 210 | 2021 | 2022 | R16
165134323635 | 168467323635 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-29 | 2023-06-29 | 2023-06-29 | 2023-08-10 | 2023-08-30 | Overhead | R16 | 2023-08-10 | 1 |  | 31 | 15 | 45 | 2023 | 2023 | R16
166493307269 | 166485307269 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-26 | 2023-01-26 | 2023-01-26 | 2023-07-20 | 2023-08-08 | Underground | R16 | 2023-07-20 | 1 |  | 126 | 14 | 139 | 2023 | 2023 | R16
164787314206 | 169345314206 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-27 | 2023-03-27 | 2023-03-30 | 2023-08-17 | 2023-10-03 | Underground | R16 | 2023-08-17 | 1 | 4 | 101 | 34 | 137 | 2023 | 2023 | R16
167827307005 | 165738307005 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-24 | 2023-01-24 | 2023-01-30 | 2023-01-24 | 2023-04-18 | Overhead | R16 | 2023-01-24 | 1 | 5 |  | 61 | 61 | 2023 | 2023 | R16
161890316938 | 164270316938 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-18 | 2023-04-27 | 2023-04-27 | 2023-06-22 | 2023-06-27 | Overhead | R16 | 2023-06-22 | 8 |  | 41 | 4 | 51 | 2023 | 2023 | R16
168614241230 | 164505241230 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-09-29 | 2023-04-13 | Underground | R16 | 2021-09-29 | 1 |  | 45 | 402 | 446 | 2021 | 2023 | R16
161646313934 | 168014313934 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-22 | 2023-03-22 | 2023-03-28 |  | 2023-05-18 | Underground | R16 | 2023-04-10 | 1 | 5 | 10 | 29 | 42 | 2023 | 2023 | R16
168933311073 | 169229311073 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2023-02-08 | 2023-03-01 | 2023-03-01 |  | 2023-08-11 | Overhead | R16 | 2023-03-23 | 16 |  | 17 | 102 | 133 | 2023 | 2023 | R16
162990226342 | 168906226342 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-04 | 2020-12-09 | 2021-04-09 |  | 2021-11-02 | Underground | R16 | 2021-06-25 | 4 | 88 | 56 | 93 | 238 | 2020 | 2021 | R16
164126321777 | 161093321777 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-22 | 2023-06-09 | 2023-06-09 |  | 2023-07-14 | Overhead | R16 | 2023-06-15 | 15 |  | 5 | 22 | 40 | 2023 | 2023 | R16
169568317195 | 166423317195 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-28 | 2023-04-28 | 2023-04-28 |  | 2023-08-14 | Overhead | R16 | 2023-04-28 | 1 |  |  | 77 | 77 | 2023 | 2023 | R16
163048213171 | 169409213171 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-08 | 2020-12-08 | 2020-12-08 |  | 2022-07-19 | Overhead | R16 |  | 1 |  |  |  | 421 | 2020 | 2022 | R16
169195244881 | 160660244881 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-23 | 2021-08-23 | 2021-08-23 |  | 2021-11-16 | Overhead | R16 | 2021-10-04 | 1 |  | 31 | 32 | 62 | 2021 | 2021 | R16
163709321306 | 163541321306 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-08-22 | 2023-09-15 | Overhead | R16 | 2023-08-22 | 1 |  | 57 | 19 | 75 | 2023 | 2023 | R16
168992241066 | 164020241066 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-27 | 2021-07-27 | 2021-07-27 |  | 2021-11-01 | Overhead | R16 | 2021-09-28 | 1 |  | 46 | 25 | 70 | 2021 | 2021 | R16
163317220553 | 160659220553 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-12-14 | 2021-01-26 | 2022-12-02 |  | 2023-06-07 | Overhead | R16 |  | 32 | 484 |  |  | 648 | 2020 | 2023 | R16
169485317523 | 166632317523 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-15 | 2023-03-15 | 2023-05-01 | 2023-10-11 | 2023-10-23 | Underground | R16 | 2023-10-11 | 1 | 34 | 118 | 9 | 159 | 2023 | 2023 | R16
163320217125 | 163939217125 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-30 | 2021-01-14 | 2021-01-14 |  | 2021-10-25 | Underground | R16 | 2021-09-08 | 12 |  | 170 | 34 | 214 | 2020 | 2021 | R16
165942320370 | 161761320370 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-25 | 2023-05-26 | 2023-05-26 | 2023-11-03 | 2023-11-09 | Overhead | R16 | 2023-11-03 | 2 |  | 116 | 5 | 121 | 2023 | 2023 | R16
167412323637 | 168505323637 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-29 | 2023-06-29 | 2023-06-29 | 2023-08-14 | 2023-10-02 | Overhead | R16 | 2023-08-14 | 1 |  | 33 | 36 | 68 | 2023 | 2023 | R16
163204314644 | 161263314644 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-04-04 | 2023-04-04 | 2023-04-04 | 2023-06-23 | 2023-06-26 | Overhead | R16 | 2023-06-23 | 1 |  | 59 | 2 | 60 | 2023 | 2023 | R16
166015305013 | 160529305013 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2023-01-03 | 2023-01-03 | 2023-07-24 | 2023-01-05 | 2023-01-07 | Underground | R16 | 2023-01-05 | 1 | 145 |  | 2 | 4 | 2023 | 2023 | R16
169702316258 | 162619316258 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-10 | 2023-04-18 | 2023-04-18 |  | 2023-06-01 | Overhead | R16 | 2023-04-26 | 7 |  | 7 | 27 | 39 | 2023 | 2023 | R16
162548315544 | 166203315544 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-13 | 2023-03-13 | 2023-04-11 | 2023-08-10 | 2023-09-13 | Overhead | R16 | 2023-08-10 | 1 | 22 | 88 | 25 | 133 | 2023 | 2023 | R16
163385213232 | 169108213232 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-07 | 2020-12-09 | 2020-12-09 |  | 2021-04-21 | Underground | R16 | 2021-03-16 | 3 |  | 70 | 27 | 98 | 2020 | 2021 | R16
164032317930 | 165205317930 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-01-20 | 2023-01-20 | 2023-05-03 |  | 2023-06-01 | Overhead | R16 | 2023-05-03 | 1 | 74 |  | 22 | 95 | 2023 | 2023 | R16
162601248344 | 168986248344 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-17 | 2021-08-17 | 2021-09-17 | 2022-02-23 | 2022-02-15 | Underground | R16 | 2022-02-23 | 1 | 24 | 114 |  | 131 | 2021 | 2022 | R16
161611320254 | 161901320254 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-25 | 2023-05-25 | 2023-05-25 | 2023-08-11 | 2023-11-15 | Overhead | R16 | 2023-08-11 | 1 |  | 57 | 69 | 125 | 2023 | 2023 | R16
164821303685 | 168758303685 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-19 | 2022-12-19 | 2022-12-19 | 2022-12-22 | 2023-04-01 | Overhead | R16 | 2022-12-22 | 1 |  | 4 | 72 | 75 | 2022 | 2023 | R16
164446308457 | 165263308457 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-20 | 2023-01-23 | 2023-02-06 | 2023-08-07 | 2023-08-30 | Underground | R16 | 2023-08-07 | 2 | 11 | 131 | 18 | 159 | 2023 | 2023 | R16
161857248861 | 164538248861 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-10 | 2021-09-21 | 2022-02-14 |  | 2021-12-17 | Overhead | R16 | 2021-11-17 | 8 | 105 |  | 23 | 71 | 2021 | 2021 | R16
163017246909 | 164233246909 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-28 | 2021-08-12 | 2021-09-08 |  | 2022-01-25 | Underground | R16 | 2022-01-24 | 12 | 20 | 99 | 2 | 130 | 2021 | 2022 | R16
163897315916 | 160068315916 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-29 | 2023-04-14 | 2023-04-14 | 2023-09-20 | 2023-09-21 | Overhead | R16 | 2023-09-20 | 13 |  | 114 | 2 | 127 | 2023 | 2023 | R16
163504242945 | 167219242945 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2021-09-27 | 2021-11-09 | Overhead | R16 | 2021-09-27 | 1 |  | 35 | 32 | 66 | 2021 | 2021 | R16
166808243122 | 167037243122 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2021-11-30 | 2022-01-13 | Overhead | R16 | 2021-11-30 | 1 |  | 81 | 33 | 113 | 2021 | 2022 | R16
165732317016 | 166293317016 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-27 | 2023-04-27 | 2023-04-27 | 2023-04-27 | 2023-06-13 | Overhead | R16 | 2023-04-27 | 1 |  |  | 34 | 34 | 2023 | 2023 | R16
168341312505 | 164625312505 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-06 |  | 2023-03-06 | 2023-05-02 | 2023-06-12 | Underground | R16 | 2023-05-02 |  |  | 42 | 30 | 71 | 2023 | 2023 | R16
167737308904 | 169482308904 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-02-09 | 2023-02-09 | 2023-02-09 | 2023-04-18 | 2023-08-11 | Underground | R16 | 2023-04-18 | 1 |  | 49 | 84 | 132 | 2023 | 2023 | R16
164369312880 | 165439312880 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-03-09 | 2023-03-13 | 2023-03-17 |  | 2023-10-05 | Underground | R16 |  | 3 | 5 |  |  | 151 | 2023 | 2023 | R16
161366254467 | 165717254467 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-03 | 2021-08-03 | 2021-11-01 |  | 2021-12-28 | Underground | R16 | 2021-12-28 | 1 | 65 | 42 |  | 106 | 2021 | 2021 | R16
166696319892 | 168722319892 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-09 | 2023-05-22 | 2023-05-22 | 2023-10-04 | 2023-10-17 | Underground | R16 | 2023-10-04 | 10 |  | 98 | 10 | 116 | 2023 | 2023 | R16
160633319631 | 160712319631 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-19 | 2023-05-19 | 2023-05-19 | 2023-05-22 | 2023-06-14 | Underground | R16 | 2023-05-22 | 1 |  | 2 | 18 | 19 | 2023 | 2023 | R16
169723314525 | 165203314525 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2023-03-08 | 2023-03-08 | 2023-04-03 |  | 2023-08-16 | Overhead | R16 |  | 1 | 19 |  |  | 116 | 2023 | 2023 | R16
160035251981 | 160642251981 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-23 | 2021-10-13 | 2021-10-13 | 2021-12-09 | 2022-01-20 | Overhead | R16 | 2021-12-09 | 38 |  | 42 | 31 | 109 | 2021 | 2022 | R16
169651245081 | 167316245081 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-11 | 2021-08-13 | 2021-08-24 |  | 2021-11-09 | Underground | R16 | 2021-10-13 | 3 | 8 | 37 | 20 | 65 | 2021 | 2021 | R16
161522321209 | 168592321209 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-23 | 2023-03-23 | 2023-06-05 | 2023-06-05 | 2023-06-29 | Underground | R16 | 2023-06-05 | 1 | 53 |  | 19 | 71 | 2023 | 2023 | R16
165728312049 | 163913312049 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2023-03-02 | 2023-03-02 | 2023-03-10 |  | 2023-12-18 | Underground | R16 | 2023-10-17 | 1 | 7 | 158 | 45 | 208 | 2023 | 2023 | R16
164800303377 | 168036303377 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-14 | 2022-12-16 | 2022-12-22 |  | 2023-08-18 | Overhead | R16 | 2023-04-13 | 3 | 5 | 81 | 92 | 178 | 2022 | 2023 | R16
160706316771 | 168840316771 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-24 | 2023-03-24 | 2023-04-24 | 2023-06-15 | 2023-08-24 | Underground | R16 | 2023-06-15 | 1 | 22 | 39 | 51 | 110 | 2023 | 2023 | R16
169297245067 | 169417245067 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-18 | 2021-08-18 | 2021-08-24 | 2021-09-07 | 2021-09-10 | Overhead | R16 | 2021-09-07 | 1 | 5 | 11 | 4 | 18 | 2021 | 2021 | R16
165572303484 | 167710303484 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-12 | 2022-12-12 | 2022-12-21 | 2023-03-07 | 2023-03-24 | Underground | R16 | 2023-03-07 | 1 | 8 | 55 | 14 | 75 | 2022 | 2023 | R16
160415315274 | 162751315274 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-11 | 2023-04-11 | 2023-04-11 |  | 2023-08-14 | Overhead | R16 | 2023-04-21 | 1 |  | 9 | 82 | 90 | 2023 | 2023 | R16
161913320206 | 163781320206 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-14 | 2023-04-14 | 2023-05-24 | 2023-08-24 | 2023-10-04 | Underground | R16 | 2023-08-24 | 1 | 29 | 67 | 30 | 124 | 2023 | 2023 | R16
162017308880 | 169189308880 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-08 | 2023-02-08 | 2023-02-08 | 2023-04-05 | 2023-04-06 | Overhead | R16 | 2023-04-05 | 1 |  | 41 | 2 | 42 | 2023 | 2023 | R16
161257256364 | 167508256364 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-11 | 2021-08-11 | 2021-11-12 |  | 2022-01-11 | Underground | R16 |  | 1 | 68 |  |  | 110 | 2021 | 2022 | R16
168094314105 | 162648314105 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-24 | 2023-03-29 | 2023-03-29 |  | 2023-10-06 | Overhead | R16 | 2023-07-06 | 24 |  | 72 | 67 | 161 | 2023 | 2023 | R16
168216249307 | 165230249307 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-01 | 2021-08-05 | 2021-09-24 | 2021-09-27 | 2021-10-12 | Overhead | R16 | 2021-09-27 | 4 | 37 | 2 | 12 | 52 | 2021 | 2021 | R16
168796246054 | 162549246054 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2021-09-08 | 2021-11-01 | Overhead | R16 | 2021-09-08 | 1 |  | 7 | 39 | 45 | 2021 | 2021 | R16
164413216087 | 164056216087 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-30 | 2021-01-04 | 2021-01-04 |  | 2021-08-23 | Overhead | R16 | 2021-04-01 | 4 |  | 64 | 103 | 169 | 2020 | 2021 | R16
164416216052 | 164112216052 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-30 | 2021-01-05 | 2021-01-05 |  | 2021-11-04 | Overhead | R16 | 2021-06-24 | 5 |  | 123 | 96 | 222 | 2020 | 2021 | R16
165450310414 | 161644310414 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-20 | 2023-02-21 | 2023-02-24 | 2023-03-16 | 2023-04-22 | Underground | R16 | 2023-03-16 | 2 | 4 | 15 | 27 | 45 | 2023 | 2023 | R16
169953248039 | 166376248039 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-05 | 2021-08-05 | 2021-09-16 |  | 2021-12-17 | Underground | R16 | 2021-12-15 | 1 | 31 | 65 | 3 | 97 | 2021 | 2021 | R16
164488223390 | 164388223390 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-16 | 2021-02-16 | 2021-03-12 |  | 2022-08-18 | Underground | R16 |  | 1 | 19 |  |  | 393 | 2021 | 2022 | R16
165678328290 | 166233328290 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-27 | 2023-05-15 | 2023-08-14 | 2023-08-14 | 2023-09-20 | Overhead | R16 | 2023-08-14 | 13 | 66 |  | 28 | 105 | 2023 | 2023 | R16
161786242377 | 166786242377 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-07 | 2021-08-07 | 2021-08-07 | 2021-10-07 | 2021-11-18 | Overhead | R16 | 2021-10-07 | 0 |  | 44 | 31 | 74 | 2021 | 2021 | R16
168589315456 | 161336315456 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2023-04-04 | 2023-04-04 | 2023-04-11 | 2023-08-31 | 2023-10-05 | Overhead | R16 | 2023-08-31 | 1 | 6 | 103 | 26 | 133 | 2023 | 2023 | R16
167264306465 | 164660306465 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-18 | 2023-01-19 | 2023-01-30 | 2023-03-31 | 2023-08-09 | Overhead | R16 | 2023-03-31 | 2 | 8 | 45 | 94 | 146 | 2023 | 2023 | R16
163631307144 | 165844307144 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-24 | 2023-01-25 | 2023-01-25 | 2023-04-04 | 2023-04-10 | Overhead | R16 | 2023-04-04 | 2 |  | 50 | 5 | 55 | 2023 | 2023 | R16
165197319688 | 160704319688 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-19 | 2023-05-19 | 2023-05-19 | 2023-05-31 | 2023-06-08 | Overhead | R16 | 2023-05-31 | 1 |  | 9 | 7 | 15 | 2023 | 2023 | R16
168531324951 | 163017324951 | CUSTOMER UPGRADE IN SERVICE | UG SVC CONVERSION | Residential | 2023-04-11 | 2023-05-08 | 2023-07-12 |  | 2023-12-12 | Underground | R16 | 2023-12-08 | 20 | 48 | 108 | 3 | 176 | 2023 | 2023 | R16
160594248127 | 164946248127 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-13 | 2021-09-15 | 2021-09-15 | 2021-10-22 | 2021-11-13 | Overhead | R16 | 2021-10-22 | 3 |  | 28 | 16 | 45 | 2021 | 2021 | R16
160310321363 | 163600321363 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-10-04 | 2023-10-09 | Overhead | R16 | 2023-10-04 | 1 |  | 88 | 4 | 91 | 2023 | 2023 | R16
164588311989 | 163150311989 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-02-27 | 2023-03-09 | 2023-03-09 | 2023-08-09 | 2023-08-24 | Overhead | R16 | 2023-08-09 | 9 |  | 110 | 12 | 129 | 2023 | 2023 | R16
167704320462 | 162004320462 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-26 | 2023-05-26 | 2023-05-26 | 2023-06-02 | 2023-06-28 | Overhead | R16 | 2023-06-02 | 1 |  | 6 | 19 | 24 | 2023 | 2023 | R16
163147303851 | 169105303851 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-20 | 2022-12-20 | 2022-12-22 | 2023-02-12 | 2023-02-17 | Overhead | R16 | 2023-02-12 | 1 | 3 | 37 | 5 | 44 | 2022 | 2023 | R16
161872242334 | 166335242334 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-05 | 2021-08-05 | 2021-08-06 | 2021-09-30 | 2021-11-02 | Overhead | R16 | 2021-09-30 | 1 | 2 | 40 | 24 | 64 | 2021 | 2021 | R16
166852327827 | 160531327827 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2023-07-12 | 2023-07-12 | 2023-08-09 | 2023-09-11 | 2023-09-14 | Underground | R16 | 2023-09-11 | 1 | 21 | 24 | 4 | 47 | 2023 | 2023 | R16
166903323147 | 167102323147 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-23 | 2023-06-23 | 2023-06-23 | 2023-07-06 | 2023-07-24 | Overhead | R16 | 2023-07-06 | 1 |  | 10 | 13 | 22 | 2023 | 2023 | R16
168402309544 | 160663309544 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-15 | 2023-02-15 | 2023-02-15 | 2023-02-21 | 2023-05-18 | Overhead | R16 | 2023-02-21 | 1 |  | 5 | 63 | 67 | 2023 | 2023 | R16
167675312110 | 165897312110 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-10 | 2023-03-10 | 2023-03-10 |  | 2023-06-27 | Overhead | R16 | 2023-05-12 | 1 |  | 46 | 33 | 78 | 2023 | 2023 | R16
163441321770 | 165881321770 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-10 | 2023-03-10 | 2023-06-09 | 2023-07-19 | 2023-07-24 | Underground | R16 | 2023-07-19 | 1 | 66 | 29 | 4 | 97 | 2023 | 2023 | R16
167422304387 | 169704304387 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-27 | 2022-12-29 | 2022-12-29 |  | 2023-08-10 | Overhead | R16 | 2023-05-03 | 3 |  | 90 | 72 | 163 | 2022 | 2023 | R16
168393308149 | 160979308149 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-04 | 2023-02-02 | 2023-02-02 | 2023-10-18 | 2023-11-07 | Overhead | R16 | 2023-10-18 | 22 |  | 185 | 15 | 220 | 2023 | 2023 | R16
164135310420 | 160282310420 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-13 | 2023-02-23 | 2023-02-23 | 2023-04-28 | 2023-06-16 | Overhead | R16 | 2023-04-28 | 9 |  | 47 | 36 | 90 | 2023 | 2023 | R16
165188215839 | 161030215839 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-15 | 2020-12-30 | 2020-12-30 |  | 2021-05-06 | Overhead | R16 | 2021-02-18 | 12 |  | 37 | 56 | 103 | 2020 | 2021 | R16
169883310823 | 162980310823 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-26 | 2023-02-26 | 2023-02-26 |  | 2023-07-11 | Overhead | R16 | 2023-05-04 | 0 |  | 49 | 49 | 97 | 2023 | 2023 | R16
165304213694 | 165650213694 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-18 | 2020-11-18 | 2020-12-12 |  | 2021-04-14 | Overhead | R16 | 2020-12-15 | 1 | 18 | 2 | 87 | 106 | 2020 | 2021 | R16
165308218543 | 169454218543 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-26 | 2021-01-26 | 2021-01-26 |  | 2021-12-02 | Overhead | R16 |  | 1 |  |  |  | 223 | 2021 | 2021 | R16
160086320928 | 161751320928 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-05 | 2023-04-05 | 2023-06-01 | 2023-10-05 | 2023-10-10 | Underground | R16 | 2023-10-05 | 1 | 42 | 91 | 4 | 135 | 2023 | 2023 | R16
165318214465 | 166638214465 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-11-23 | 2020-11-25 | 2020-12-18 |  | 2021-08-16 | Overhead | R16 | 2021-03-25 | 3 | 18 | 70 | 103 | 191 | 2020 | 2021 | R16
160738313746 | 168594313746 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-23 | 2023-03-23 | 2023-03-27 |  | 2023-08-09 | Underground | R16 | 2023-03-31 | 1 | 3 | 5 | 94 | 100 | 2023 | 2023 | R16
169053303297 | 167998303297 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-14 | 2022-12-14 | 2022-12-14 | 2023-02-27 | 2023-03-31 | Overhead | R16 | 2023-02-27 | 1 |  | 54 | 25 | 78 | 2022 | 2023 | R16
166557327107 | 169620327107 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-07 | 2023-07-07 | 2023-08-02 | 2023-11-09 | 2023-12-14 | Underground | R16 | 2023-11-09 | 1 | 19 | 72 | 26 | 115 | 2023 | 2023 | R16
163055318295 | 168436318295 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-08 |  | 2023-05-08 | 2023-08-08 | 2023-09-05 | Underground | R16 | 2023-08-08 |  |  | 67 | 21 | 87 | 2023 | 2023 | R16
165450310448 | 162576310448 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-24 | 2023-02-24 | 2023-02-24 | 2023-03-14 | 2023-06-27 | Overhead | R16 | 2023-03-14 | 1 |  | 13 | 76 | 88 | 2023 | 2023 | R16
161180320735 | 161193320735 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-23 | 2023-05-23 | 2023-06-01 | 2023-09-28 | 2023-12-21 | Underground | R16 | 2023-09-28 | 1 | 8 | 86 | 61 | 153 | 2023 | 2023 | R16
163610311866 | 165145311866 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-07-17 | 2023-07-19 | Overhead | R16 | 2023-07-17 | 1 |  | 94 | 3 | 96 | 2023 | 2023 | R16
163738322112 | 163973322112 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-07 | 2023-06-07 | 2023-06-14 | 2023-07-19 | 2023-07-20 | Underground | R16 | 2023-07-19 | 1 | 6 | 26 | 2 | 32 | 2023 | 2023 | R16
167622251045 | 168259251045 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-13 | 2021-08-13 | 2021-10-08 |  | 2021-12-02 | Underground | R16 | 2021-11-08 | 1 | 41 | 22 | 19 | 80 | 2021 | 2021 | R16
167447318980 | 169518318980 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-05-12 | 2023-05-12 | 2023-05-12 |  | 2023-08-14 | Overhead | R16 | 2023-05-12 | 1 |  |  | 67 | 67 | 2023 | 2023 | R16
165622257750 | 160927257750 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-15 | 2020-12-15 | 2021-11-22 |  | 2022-02-15 | Underground | R16 | 2022-01-18 | 1 | 245 | 42 | 21 | 306 | 2020 | 2022 | R16
167078313595 | 169003313595 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-24 | 2023-03-24 | 2023-03-24 |  | 2023-08-18 | Overhead | R16 | 2023-04-18 | 1 |  | 18 | 89 | 106 | 2023 | 2023 | R16
163569246380 | 163052246380 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-02 | 2021-09-02 | 2021-09-02 | 2021-09-08 | 2022-02-02 | Overhead | R16 | 2021-09-08 | 1 |  | 5 | 106 | 110 | 2021 | 2022 | R16
169954311991 | 164731311991 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-06 | 2023-03-06 | 2023-03-10 | 2023-06-06 | 2023-09-28 | Overhead | R16 | 2023-06-06 | 1 | 5 | 63 | 83 | 149 | 2023 | 2023 | R16
168953309047 | 162981309047 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-11 | 2023-01-11 | 2023-02-10 | 2023-08-16 | 2023-08-29 | Underground | R16 | 2023-08-16 | 1 | 23 | 134 | 10 | 165 | 2023 | 2023 | R16
165363315048 | 165868315048 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-24 | 2023-01-24 | 2023-04-07 | 2023-09-05 | 2023-09-13 | Underground | R16 | 2023-09-05 | 1 | 54 | 108 | 7 | 167 | 2023 | 2023 | R16
168973306438 | 162443306438 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-10 | 2023-01-19 | 2023-01-30 | 2023-02-26 | 2023-06-13 | Overhead | R16 | 2023-02-26 | 8 | 8 | 20 | 77 | 111 | 2023 | 2023 | R16
169036241153 | 164264241153 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-28 | 2021-07-28 | 2021-07-29 |  | 2021-09-07 | Underground | R16 | 2021-08-10 | 1 | 2 | 9 | 21 | 30 | 2021 | 2021 | R16
162129247180 | 164328247180 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-09 | 2021-09-09 | 2021-09-09 | 2021-11-29 | 2022-03-04 | Overhead | R16 | 2021-11-29 | 1 |  | 58 | 70 | 127 | 2021 | 2022 | R16
169264330129 | 164900330129 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-12 | 2023-06-12 | 2023-08-21 | 2023-10-27 | 2023-11-13 | Underground | R16 | 2023-10-27 | 1 | 51 | 50 | 12 | 111 | 2023 | 2023 | R16
165932216574 | 165855216574 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-08 | 2021-01-08 | 2021-01-08 |  | 2021-11-08 | Overhead | R16 | 2021-05-27 | 1 |  | 100 | 118 | 217 | 2021 | 2021 | R16
168813303054 | 167670303054 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-12 | 2022-12-12 | 2022-12-21 | 2023-01-29 | 2023-02-01 | Overhead | R16 | 2023-01-29 | 1 | 8 | 28 | 3 | 38 | 2022 | 2023 | R16
165946218380 | 165130218380 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-05 | 2021-01-05 | 2021-01-25 |  | 2021-11-05 | Underground | R16 | 2021-04-15 | 1 | 15 | 59 | 147 | 219 | 2021 | 2021 | R16
168028244497 | 160224244497 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2022-06-07 | 2022-08-03 | Overhead | R16 | 2022-06-07 | 1 |  | 208 | 42 | 249 | 2021 | 2022 | R16
163396255555 | 160626255555 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-08-23 | 2021-08-23 | 2021-11-09 |  | 2022-07-26 | Underground | R16 |  | 1 | 57 |  |  | 242 | 2021 | 2022 | R16
162981322734 | 163113322734 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-02 | 2023-06-19 | 2023-06-19 | 2023-07-11 | 2023-08-16 | Overhead | R16 | 2023-07-11 | 12 |  | 17 | 27 | 54 | 2023 | 2023 | R16
165552243103 | 167506243103 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-11 | 2021-08-11 | 2021-08-11 |  | 2022-07-27 | Overhead | R16 |  | 1 |  |  |  | 251 | 2021 | 2022 | R16
163879323725 | 164956323725 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-13 | 2023-06-29 | 2023-06-29 | 2023-08-29 | 2023-10-20 | Overhead | R16 | 2023-08-29 | 13 |  | 44 | 39 | 94 | 2023 | 2023 | R16
167543310223 | 168912310223 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-07 | 2023-02-08 | 2023-02-23 | 2023-04-14 | 2023-04-17 | Underground | R16 | 2023-04-14 | 2 | 12 | 37 | 2 | 50 | 2023 | 2023 | R16
166560308557 | 167588308557 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-01 | 2023-02-06 | 2023-02-06 |  | 2023-07-31 | Underground | R16 | 2023-04-10 | 4 |  | 46 | 81 | 129 | 2023 | 2023 | R16
162968335782 | 167787335782 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-27 | 2023-06-29 | 2023-10-16 | 2023-11-14 | 2023-11-21 | Underground | R16 | 2023-11-14 | 3 | 78 | 22 | 6 | 106 | 2023 | 2023 | R16
162298317920 | 167530317920 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-03 |  | 2023-05-03 | 2023-07-31 | 2023-08-14 | Overhead | R16 | 2023-07-31 |  |  | 64 | 11 | 74 | 2023 | 2023 | R16
162434247345 | 164707247345 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-10 | 2021-09-10 | 2021-09-10 |  | 2021-11-30 | Overhead | R16 |  | 1 |  |  |  | 58 | 2021 | 2021 | R16
166824318911 | 169348318911 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-05-12 | 2023-05-12 | 2023-05-12 | 2023-06-27 | 2023-07-05 | Overhead | R16 | 2023-06-27 | 1 |  | 33 | 7 | 39 | 2023 | 2023 | R16
166219217588 | 166777217588 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-13 | 2021-01-19 | 2021-01-19 |  | 2022-02-10 | Overhead | R16 | 2022-01-05 | 5 |  | 252 | 27 | 282 | 2021 | 2022 | R16
167710323995 | 169215323995 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-05 | 2023-07-05 | 2023-07-05 | 2023-07-19 | 2023-08-03 | Overhead | R16 | 2023-07-19 | 1 |  | 11 | 12 | 22 | 2023 | 2023 | R16
166488308582 | 168562308582 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-06 | 2023-02-06 | 2023-02-06 |  | 2023-07-31 | Overhead | R16 | 2023-04-03 | 1 |  | 41 | 86 | 126 | 2023 | 2023 | R16
165026317263 | 162964317263 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-04-11 | 2023-04-11 | 2023-04-28 | 2023-09-22 | 2023-09-29 | Underground | R16 | 2023-09-22 | 1 | 14 | 106 | 6 | 124 | 2023 | 2023 | R16
160540309069 | 169806309069 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-10 | 2023-02-10 | 2023-02-10 | 2023-03-28 | 2023-04-08 | Overhead | R16 | 2023-03-28 | 1 |  | 33 | 9 | 41 | 2023 | 2023 | R16
167006320835 | 161615320835 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-05-25 | 2023-05-25 | 2023-06-01 | 2023-07-05 | 2023-07-19 | Underground | R16 | 2023-07-05 | 1 | 6 | 25 | 11 | 40 | 2023 | 2023 | R16
166907314235 | 169721314235 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-04-17 | 2023-07-10 | Underground | R16 | 2023-04-17 | 2 | 2 | 13 | 61 | 75 | 2023 | 2023 | R16
168138316392 | 166793316392 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-15 | 2023-03-15 | 2023-04-20 | 2023-07-24 | 2023-07-25 | Overhead | R16 | 2023-07-24 | 1 | 27 | 68 | 2 | 95 | 2023 | 2023 | R16
160366316376 | 164714316376 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-04-19 |  | 2023-04-19 | 2023-07-02 | 2023-07-05 | Overhead | R16 | 2023-07-02 |  |  | 53 | 3 | 56 | 2023 | 2023 | R16
162103319267 | 160123319267 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-05-16 | 2023-05-16 | 2023-05-16 | 2023-05-31 | 2023-06-01 | Overhead | R16 | 2023-05-31 | 1 |  | 12 | 2 | 13 | 2023 | 2023 | R16
165672324813 | 167557324813 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-27 | 2023-07-13 | 2023-07-13 |  | 2023-08-07 | Overhead | R16 | 2023-07-13 | 13 |  |  | 18 | 30 | 2023 | 2023 | R16
166575215848 | 163495215848 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-28 | 2020-12-28 | 2020-12-30 |  | 2021-05-05 | Overhead | R16 | 2021-02-16 | 1 | 3 | 35 | 57 | 93 | 2020 | 2021 | R16
163165319298 | 163746319298 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-14 | 2023-04-14 | 2023-05-17 |  | 2023-10-16 | Overhead | R16 |  | 1 | 24 |  |  | 132 | 2023 | 2023 | R16
164673278034 | 165452278034 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-02 | 2021-08-27 | 2022-05-04 | 2022-06-06 | 2022-08-02 | Underground | R16 | 2022-06-06 | 20 | 179 | 24 | 42 | 262 | 2021 | 2022 | R16
169707328026 | 161337328026 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-04 | 2023-04-04 | 2023-08-11 | 2023-10-16 | 2023-11-03 | Underground | R16 | 2023-10-16 | 1 | 94 | 47 | 15 | 154 | 2023 | 2023 | R16
160997308942 | 169369308942 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-09 | 2023-02-09 | 2023-02-09 | 2023-03-31 | 2023-06-13 | Overhead | R16 | 2023-03-31 | 1 |  | 37 | 53 | 89 | 2023 | 2023 | R16
161546323290 | 164183323290 | NON-RESIDENTIAL - SMALL RETAIL | R16 RESD AND NON RESD US | Commercial | 2023-06-08 | 2023-06-08 | 2023-06-26 | 2023-09-27 | 2023-10-03 | Underground | R16 | 2023-09-27 | 1 | 13 | 68 | 5 | 84 | 2023 | 2023 | R16
166777216593 | 161031216593 | CUSTOMER UPGRADE IN SERVICE | UG SVC CONVERSION | Commercial | 2020-12-15 | 2021-01-04 | 2021-01-08 |  | 2021-04-21 | Underground | R16 | 2021-01-19 | 15 | 5 | 8 | 67 | 92 | 2020 | 2021 | R16
169279245856 | 162247245856 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-30 | 2021-08-30 | 2021-08-30 | 2021-10-25 | 2021-10-25 | Overhead | R16 | 2021-10-25 | 1 |  | 41 |  | 41 | 2021 | 2021 | R16
166823215711 | 163521215711 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-28 | 2020-12-28 | 2020-12-28 |  | 2021-06-03 | Overhead | R16 | 2021-03-11 | 1 |  | 54 | 61 | 114 | 2020 | 2021 | R16
161954309107 | 169804309107 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-10 | 2023-02-10 | 2023-02-10 | 2023-06-13 | 2023-09-27 | Overhead | R16 | 2023-06-13 | 1 |  | 88 | 77 | 164 | 2023 | 2023 | R16
166832236153 | 165746236153 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-04-05 | 2021-06-21 | 2021-06-21 |  | 2021-10-26 | Underground | R16 | 2021-06-22 | 56 |  | 2 | 91 | 147 | 2021 | 2021 | R16
168580316767 | 165496316767 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-24 | 2023-04-24 | 2023-04-24 |  | 2023-06-14 | Overhead | R16 | 2023-05-15 | 1 |  | 16 | 23 | 38 | 2023 | 2023 | R16
166103323680 | 164189323680 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-17 | 2023-05-01 | 2023-06-28 | 2023-06-28 | 2023-08-14 | Overhead | R16 | 2023-06-28 | 11 | 43 |  | 34 | 86 | 2023 | 2023 | R16
169626310224 | 161724310224 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-21 | 2023-02-23 | 2023-02-23 | 2023-04-06 | 2023-04-07 | Overhead | R16 | 2023-04-06 | 3 |  | 31 | 2 | 34 | 2023 | 2023 | R16
166909222734 | 167648222734 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-02 | 2021-03-02 | 2021-03-08 |  | 2022-12-13 | Underground | R16 |  | 1 | 5 |  |  | 466 | 2021 | 2022 | R16
168888245204 | 161256245204 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-25 | 2021-08-25 | 2021-08-25 |  | 2021-12-02 | Overhead | R16 | 2021-11-08 | 1 |  | 54 | 19 | 72 | 2021 | 2021 | R16
160523250109 | 165022250109 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-13 | 2021-09-13 | 2021-09-30 |  | 2022-01-04 | Underground | R16 | 2021-11-22 | 1 | 14 | 38 | 32 | 82 | 2021 | 2022 | R16
168992246224 | 161667246224 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-27 | 2021-08-27 | 2021-09-01 | 2021-09-30 | 2021-11-18 | Underground | R16 | 2021-09-30 | 1 | 4 | 22 | 36 | 60 | 2021 | 2021 | R16
161338315341 | 161007315341 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-03 | 2023-04-03 | 2023-04-10 | 2023-04-29 | 2023-06-12 | Underground | R16 | 2023-04-29 | 1 | 6 | 15 | 31 | 51 | 2023 | 2023 | R16
164151323027 | 166237323027 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-03-14 | 2023-04-26 | 2023-06-22 | 2023-08-30 | 2023-09-08 | Underground | R16 | 2023-08-30 | 32 | 42 | 50 | 8 | 129 | 2023 | 2023 | R16
160716314342 | 167651314342 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-20 | 2023-03-20 | 2023-03-31 | 2023-04-10 | 2023-06-12 | Underground | R16 | 2023-04-10 | 1 | 10 | 7 | 46 | 61 | 2023 | 2023 | R16
169778317781 | 161810317781 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-06 | 2023-05-02 | 2023-05-02 | 2023-08-25 | 2023-09-05 | Underground | R16 | 2023-08-25 | 19 |  | 84 | 8 | 109 | 2023 | 2023 | R16
161997314440 | 168669314440 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-23 | 2023-03-23 | 2023-03-31 |  | 2023-09-19 | Underground | R16 | 2023-04-27 | 1 | 7 | 20 | 104 | 129 | 2023 | 2023 | R16
167203215829 | 161042215829 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-15 | 2020-12-30 | 2020-12-30 |  | 2023-10-27 | Underground | R16 | 2023-10-13 | 12 |  | 728 | 11 | 749 | 2020 | 2023 | R16
160281330545 | 163902330545 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-07 | 2023-06-07 | 2023-08-24 | 2023-11-01 | 2023-11-09 | Underground | R16 | 2023-11-01 | 1 | 57 | 50 | 7 | 112 | 2023 | 2023 | R16
161040249062 | 161649249062 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-27 | 2021-08-27 | 2021-09-22 | 2021-11-10 | 2021-12-17 | Underground | R16 | 2021-11-10 | 1 | 19 | 36 | 28 | 81 | 2021 | 2021 | R16
168771246258 | 162979246258 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-09-02 | 2021-09-02 | 2021-09-02 | 2021-10-13 | 2021-11-09 | Overhead | R16 | 2021-10-13 | 1 |  | 30 | 20 | 49 | 2021 | 2021 | R16
168192244880 | 160592244880 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-23 | 2021-08-23 | 2021-08-23 |  | 2021-11-01 | Overhead | R16 | 2021-09-29 | 1 |  | 28 | 24 | 51 | 2021 | 2021 | R16
168692319510 | 169962319510 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-05-16 | 2023-05-16 | 2023-05-19 |  | 2023-09-13 | Overhead | R16 |  | 1 | 4 |  |  | 87 | 2023 | 2023 | R16
160078325240 | 164759325240 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-12 | 2023-06-12 | 2023-07-16 | 2023-09-27 | 2023-10-03 | Underground | R16 | 2023-09-27 | 1 | 25 | 53 | 5 | 82 | 2023 | 2023 | R16
166136304407 | 168030304407 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-14 | 2022-12-14 | 2023-01-30 | 2022-12-30 | 2023-04-01 | Underground | R16 | 2022-12-30 | 1 | 34 |  | 66 | 78 | 2022 | 2023 | R16
167251307791 | 167263307791 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-31 | 2023-01-31 | 2023-01-31 | 2023-02-21 | 2023-02-22 | Overhead | R16 | 2023-02-21 | 1 |  | 16 | 2 | 17 | 2023 | 2023 | R16
164872311826 | 163622311826 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-26 | 2021-07-26 | 2023-03-08 |  | 2023-07-20 | Underground | R16 | 2023-06-20 | 1 | 423 | 75 | 23 | 519 | 2021 | 2023 | R16
167346224774 | 167390224774 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-28 | 2020-11-28 | 2021-03-25 |  | 2021-11-05 | Underground | R16 | 2021-05-07 | 0 | 84 | 32 | 131 | 245 | 2020 | 2021 | R16
164984245214 | 161481245214 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-26 | 2021-08-26 | 2021-08-26 |  | 2022-01-24 | Underground | R16 | 2021-12-30 | 1 |  | 91 | 18 | 108 | 2021 | 2022 | R16
168002305305 | 161124305305 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-04 | 2023-01-09 | 2023-01-30 | 2023-03-30 | 2023-04-05 | Underground | R16 | 2023-03-30 | 4 | 16 | 44 | 5 | 66 | 2023 | 2023 | R16
161849321653 | 168015321653 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-22 | 2023-03-22 | 2023-06-09 |  | 2023-08-23 | Underground | R16 | 2023-07-31 | 1 | 58 | 37 | 18 | 111 | 2023 | 2023 | R16
167456229716 | 164890229716 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-17 | 2021-02-17 | 2021-05-06 |  | 2021-11-02 | Underground | R16 | 2021-06-17 | 1 | 57 | 31 | 99 | 185 | 2021 | 2021 | R16
168692308242 | 167885308242 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-02 | 2023-02-02 | 2023-02-03 | 2023-03-30 | 2023-04-18 | Overhead | R16 | 2023-03-30 | 1 | 2 | 40 | 14 | 54 | 2023 | 2023 | R16
167855336029 | 162251336029 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-05-30 | 2023-06-05 | 2023-10-18 | 2023-12-11 | 2023-12-13 | Overhead | R16 | 2023-12-11 | 5 | 98 | 39 | 3 | 142 | 2023 | 2023 | R16
162653245762 | 162040245762 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-29 | 2021-08-29 | 2021-08-29 | 2022-04-07 | 2022-04-11 | Overhead | R16 | 2022-04-07 | 0 |  | 159 | 3 | 161 | 2021 | 2022 | R16
165301310939 | 163543310939 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-01 | 2023-03-01 | 2023-03-01 |  | 2023-05-18 | Overhead | R16 | 2023-03-15 | 1 |  | 11 | 47 | 57 | 2023 | 2023 | R16
164188242303 | 166089242303 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-05 | 2021-08-05 | 2021-08-05 | 2021-09-15 | 2021-11-08 | Overhead | R16 | 2021-09-15 | 1 |  | 30 | 39 | 68 | 2021 | 2021 | R16
160738320888 | 169812320888 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-15 | 2023-05-15 | 2023-06-01 | 2023-09-25 | 2023-11-14 | Underground | R16 | 2023-09-25 | 1 | 14 | 83 | 37 | 132 | 2023 | 2023 | R16
162894309427 | 167891309427 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-02 | 2023-02-02 | 2023-02-15 |  | 2023-05-31 | Underground | R16 | 2023-05-18 | 1 | 10 | 67 | 10 | 85 | 2023 | 2023 | R16
164691318665 | 165248318665 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-21 | 2023-05-09 | 2023-05-09 |  | 2023-06-22 | Overhead | R16 | 2023-06-16 | 13 |  | 29 | 5 | 45 | 2023 | 2023 | R16
165827305512 | 160371305512 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2022-12-30 | 2023-01-06 | 2023-01-25 | 2023-01-17 | 2023-01-30 | Overhead | R16 | 2023-01-17 | 6 | 14 |  | 10 | 22 | 2022 | 2023 | R16
167915322402 | 161230322402 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-23 | 2023-05-23 | 2023-06-16 | 2023-10-16 | 2023-10-26 | Underground | R16 | 2023-10-16 | 1 | 19 | 87 | 9 | 113 | 2023 | 2023 | R16
168174241388 | 164757241388 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-30 | 2021-07-30 | 2021-07-30 | 2021-10-21 | 2021-12-03 | Overhead | R16 | 2021-10-21 | 1 |  | 60 | 32 | 91 | 2021 | 2021 | R16
167982315406 | 166679315406 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-15 | 2023-04-07 | 2023-04-11 | 2023-07-05 | 2023-07-06 | Overhead | R16 | 2023-07-05 | 18 | 3 | 62 | 2 | 82 | 2023 | 2023 | R16
165063337788 | 169214337788 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-05 | 2023-07-05 | 2023-10-27 | 2023-11-07 | 2023-12-14 | Underground | R16 | 2023-11-07 | 1 | 83 | 8 | 28 | 117 | 2023 | 2023 | R16
165285323822 | 169912323822 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-05-15 | 2023-06-17 | 2023-06-30 | 2023-10-24 | 2023-11-01 | Underground | R16 | 2023-10-24 | 25 | 10 | 83 | 7 | 123 | 2023 | 2023 | R16
167701217408 | 167229217408 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-14 | 2021-01-14 | 2021-01-14 |  | 2021-08-16 | Overhead | R16 | 2021-03-17 | 1 |  | 45 | 109 | 153 | 2021 | 2021 | R16
168051308516 | 168548308516 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-06 | 2023-02-06 | 2023-02-06 |  | 2023-07-07 | Overhead | R16 | 2023-03-14 | 1 |  | 27 | 84 | 110 | 2023 | 2023 | R16
167728218333 | 166373218333 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-12 | 2021-01-25 | 2021-01-25 |  | 2022-03-28 | Overhead | R16 | 2022-03-09 | 10 |  | 293 | 14 | 315 | 2021 | 2022 | R16
168220317102 | 167559317102 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-20 | 2023-03-20 | 2023-04-26 | 2023-06-12 | 2023-06-13 | Underground | R16 | 2023-06-12 | 1 | 28 | 34 | 2 | 62 | 2023 | 2023 | R16
160119255648 | 168740255648 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2021-08-15 | 2021-08-15 | 2021-11-08 | 2022-10-11 | 2022-10-24 | Underground | R16 | 2022-10-11 | 0 | 61 | 242 | 10 | 311 | 2021 | 2022 | R16
168917308976 | 164649308976 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-18 | 2023-02-10 | 2023-02-10 |  | 2023-08-11 | Overhead | R16 | 2023-03-31 | 18 |  | 36 | 96 | 148 | 2023 | 2023 | R16
162683259846 | 163660259846 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-07-26 | 2021-12-03 | 2021-12-03 | 2021-12-07 | 2022-01-18 | Overhead | R16 | 2021-12-07 | 95 |  | 3 | 31 | 127 | 2021 | 2022 | R16
161037319270 | 160007319270 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-16 | 2023-05-16 | 2023-05-16 | 2023-11-27 | 2023-12-21 | Overhead | R16 | 2023-11-27 | 1 |  | 140 | 19 | 158 | 2023 | 2023 | R16
166336242999 | 166973242999 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-09 | 2021-08-11 | 2021-08-11 | 2021-11-10 | 2021-12-28 | Overhead | R16 | 2021-11-10 | 3 |  | 66 | 35 | 102 | 2021 | 2021 | R16
160270241918 | 165813241918 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-04 | 2021-08-04 | 2021-08-04 | 2021-10-01 | 2022-03-25 | Overhead | R16 | 2021-10-01 | 1 |  | 43 | 126 | 168 | 2021 | 2022 | R16
165563308237 | 168215308237 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-03 | 2023-02-03 | 2023-02-03 |  | 2023-08-03 | Overhead | R16 | 2023-03-20 | 1 |  | 32 | 99 | 130 | 2023 | 2023 | R16
168149218890 | 160679218890 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-29 | 2021-01-29 | 2021-01-29 |  | 2021-11-04 | Overhead | R16 | 2021-04-05 | 1 |  | 47 | 154 | 200 | 2021 | 2021 | R16
165740326122 | 164245326122 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-09 | 2023-07-23 | 2023-07-24 | 2023-08-02 | 2023-08-25 | Overhead | R16 | 2023-08-02 | 31 | 1 | 8 | 18 | 56 | 2023 | 2023 | R16
160497316287 | 163284316287 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-04-12 | 2023-04-19 | 2023-04-19 | 2023-10-31 | 2023-11-02 | Overhead | R16 | 2023-10-31 | 6 |  | 140 | 3 | 147 | 2023 | 2023 | R16
165121241804 | 165331241804 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-02 | 2021-08-02 | 2021-08-02 | 2021-10-07 | 2021-11-18 | Overhead | R16 | 2021-10-07 | 1 |  | 49 | 31 | 79 | 2021 | 2021 | R16
166251244894 | 160709244894 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-23 | 2021-08-23 | 2021-08-23 | 2021-10-05 | 2022-02-02 | Overhead | R16 | 2021-10-05 | 1 |  | 32 | 87 | 118 | 2021 | 2022 | R16
162266247131 | 162104247131 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-30 | 2021-09-10 | 2021-09-10 |  | 2021-11-13 | Overhead | R16 | 2021-11-05 | 10 |  | 41 | 6 | 55 | 2021 | 2021 | R16
162586313443 | 168044313443 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2023-03-21 | 2023-03-21 | 2023-03-22 | 2023-09-19 | 2023-10-25 | Overhead | R16 | 2023-09-19 | 1 | 2 | 130 | 27 | 157 | 2023 | 2023 | R16
168428249117 | 163675249117 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-07 | 2021-09-08 | 2021-09-24 | 2021-12-03 | 2022-01-05 | Underground | R16 | 2021-12-03 | 2 | 13 | 51 | 24 | 87 | 2021 | 2022 | R16
166441247606 | 165130247606 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-13 | 2021-09-13 | 2021-09-13 |  | 2022-02-10 | Overhead | R16 | 2021-10-18 | 1 |  | 26 | 84 | 109 | 2021 | 2022 | R16
162328308581 | 166237308581 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-25 | 2023-02-06 | 2023-02-06 |  | 2023-06-26 | Overhead | R16 |  | 9 |  |  |  | 109 | 2023 | 2023 | R16
168312259620 | 169483259620 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-10-01 | 2021-11-04 | 2021-12-02 |  | 2023-07-31 | Underground | R16 |  | 25 | 21 |  |  | 477 | 2021 | 2023 | R16
167319318913 | 169323318913 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-05-12 | 2023-05-12 | 2023-05-12 | 2023-08-29 | 2023-09-01 | Underground | R16 | 2023-08-29 | 1 |  | 78 | 4 | 81 | 2023 | 2023 | R16
164916321478 | 164173321478 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-08 | 2023-06-08 | 2023-06-08 | 2023-06-13 | 2023-06-30 | Overhead | R16 | 2023-06-13 | 1 |  | 4 | 14 | 17 | 2023 | 2023 | R16
162793318795 | 165017318795 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-08 | 2023-03-08 | 2023-05-11 | 2023-08-22 | 2023-10-24 | Underground | R16 | 2023-08-22 | 1 | 47 | 74 | 46 | 165 | 2023 | 2023 | R16
168530216969 | 165476216969 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-07 | 2021-01-13 | 2021-01-13 |  | 2021-11-08 | Underground | R16 | 2021-05-27 | 5 |  | 97 | 118 | 218 | 2021 | 2021 | R16
161956311309 | 161177311309 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-05 | 2023-01-05 | 2023-03-03 |  | 2023-08-18 | Underground | R16 | 2023-04-27 | 1 | 42 | 40 | 82 | 162 | 2023 | 2023 | R16
161064307905 | 167451307905 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-31 | 2023-01-31 | 2023-01-31 | 2023-11-26 | 2023-11-30 | Underground | R16 | 2023-11-26 | 1 |  | 214 | 4 | 218 | 2023 | 2023 | R16
168667227899 | 169426227899 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-21 | 2021-04-21 | 2021-04-21 |  | 2021-11-08 | Overhead | R16 | 2021-05-28 | 1 |  | 28 | 117 | 144 | 2021 | 2021 | R16
164038311014 | 163760311014 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-01 | 2023-03-01 | 2023-03-01 |  | 2023-07-31 | Overhead | R16 | 2023-03-24 | 1 |  | 18 | 92 | 109 | 2023 | 2023 | R16
166217314796 | 168399314796 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-23 | 2023-04-04 | 2023-04-04 | 2023-09-08 | 2023-09-25 | Overhead | R16 | 2023-09-08 | 9 |  | 114 | 12 | 133 | 2023 | 2023 | R16
163113314391 | 160763314391 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-31 | 2023-03-31 | 2023-03-31 | 2023-04-18 | 2023-06-12 | Overhead | R16 | 2023-04-18 | 1 |  | 13 | 40 | 52 | 2023 | 2023 | R16
164699342494 | 164811342494 | MOBILE HOMES PARK AB622 | ELEC SVC FOR MOBILE HOMES | Residential | 2021-09-10 | 2021-09-10 | 2023-12-13 |  | 2023-12-15 | Underground | R16 |  | 1 | 589 |  |  | 591 | 2021 | 2023 | R16
161614247043 | 163810247043 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-07 | 2021-09-08 | 2021-09-08 | 2021-11-04 | 2021-12-02 | Overhead | R16 | 2021-11-04 | 2 |  | 42 | 21 | 63 | 2021 | 2021 | R16
168794219667 | 162237219667 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-04 | 2021-02-04 | 2021-02-04 |  | 2021-08-12 | Underground | R16 | 2021-07-07 | 1 |  | 110 | 27 | 136 | 2021 | 2021 | R16
165195311147 | 163193311147 | CUSTOMER UPGRADE IN SERVICE | UG SVC CONVERSION | Residential | 2023-02-27 | 2023-02-28 | 2023-03-02 | 2023-08-04 | 2023-08-28 | Underground | R16 | 2023-08-04 | 2 | 3 | 112 | 17 | 131 | 2023 | 2023 | R16
164567325401 | 167555325401 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-27 | 2023-06-27 | 2023-07-17 | 2023-10-20 | 2023-10-30 | Underground | R16 | 2023-10-20 | 1 | 15 | 70 | 7 | 90 | 2023 | 2023 | R16
164720307108 | 169974307108 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-28 | 2022-12-28 | 2023-01-25 | 2023-02-08 | 2023-04-01 | Overhead | R16 | 2023-02-08 | 1 | 21 | 11 | 38 | 68 | 2022 | 2023 | R16
168903216405 | 165172216405 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-06 | 2021-01-06 | 2021-01-06 |  | 2021-08-12 | Overhead | R16 | 2021-03-17 | 1 |  | 51 | 107 | 157 | 2021 | 2021 | R16
164121304053 | 169520304053 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-22 | 2022-12-22 | 2022-12-27 |  | 2023-02-12 | Overhead | R16 | 2023-01-25 | 1 | 4 | 22 | 13 | 37 | 2022 | 2023 | R16
168180309283 | 165989309283 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-24 | 2023-01-24 | 2023-02-13 |  | 2023-06-16 | Overhead | R16 | 2023-02-13 | 1 | 15 |  | 90 | 104 | 2023 | 2023 | R16
164803243161 | 167367243161 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-08-10 | 2021-08-10 | 2021-08-11 |  | 2022-08-03 | Underground | R16 |  | 1 | 2 |  |  | 257 | 2021 | 2022 | R16
169011219296 | 161929219296 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-03 | 2021-02-03 | 2021-02-03 |  | 2022-08-03 | Overhead | R16 |  | 1 |  |  |  | 391 | 2021 | 2022 | R16
162364306784 | 165401306784 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-23 | 2023-01-23 | 2023-01-30 | 2023-01-23 | 2023-12-04 | Overhead | R16 | 2023-01-23 | 1 | 6 |  | 226 | 226 | 2023 | 2023 | R16
163289250019 | 163633250019 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-06 | 2021-09-29 | 2021-09-30 |  | 2022-02-07 | Overhead | R16 | 2022-01-10 | 18 | 2 | 73 | 21 | 111 | 2021 | 2022 | R16
164622313936 | 167035313936 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-30 | 2023-01-30 | 2023-03-29 |  | 2023-08-17 | Underground | R16 | 2023-04-05 | 1 | 43 | 6 | 97 | 144 | 2023 | 2023 | R16
166180304448 | 168063304448 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-14 | 2022-12-14 | 2023-01-30 | 2023-03-09 | 2023-03-31 | Underground | R16 | 2023-03-09 | 1 | 34 | 29 | 17 | 78 | 2022 | 2023 | R16
168430325475 | 164446325475 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-19 | 2023-06-20 | 2023-07-19 | 2023-07-19 | 2023-09-27 | Overhead | R16 | 2023-07-19 | 45 | 22 |  | 51 | 116 | 2023 | 2023 | R16
163007307197 | 166054307197 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-25 | 2023-01-25 | 2023-01-26 | 2023-06-01 | 2023-06-13 | Overhead | R16 | 2023-06-01 | 1 | 2 | 91 | 9 | 100 | 2023 | 2023 | R16
164680325423 | 165334325423 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-14 | 2023-06-14 | 2023-07-18 | 2023-08-28 | 2023-09-13 | Underground | R16 | 2023-08-28 | 1 | 25 | 30 | 13 | 66 | 2023 | 2023 | R16
166800313050 | 167459313050 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-20 | 2023-03-20 | 2023-03-20 |  | 2023-05-18 | Overhead | R16 | 2023-03-27 | 1 |  | 6 | 39 | 44 | 2023 | 2023 | R16
166707243741 | 168573243741 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-13 | 2021-08-13 | 2021-08-13 | 2021-11-05 | 2021-12-08 | Overhead | R16 | 2021-11-05 | 1 |  | 61 | 24 | 84 | 2021 | 2021 | R16
167189307861 | 167373307861 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-31 | 2023-01-31 | 2023-01-31 | 2023-05-19 | 2023-06-19 | Overhead | R16 | 2023-05-19 | 1 |  | 79 | 22 | 100 | 2023 | 2023 | R16
168985252052 | 161339252052 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-26 | 2021-10-13 | 2021-10-13 | 2022-01-07 | 2022-02-07 | Overhead | R16 | 2022-01-07 | 35 |  | 63 | 22 | 118 | 2021 | 2022 | R16
169350218720 | 166375218720 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-12 | 2021-01-27 | 2021-01-27 |  | 2021-11-08 | Overhead | R16 | 2021-04-20 | 12 |  | 60 | 145 | 215 | 2021 | 2021 | R16
168330316181 | 164186316181 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-17 | 2023-04-17 | 2023-04-17 | 2023-06-07 | 2023-06-08 | Overhead | R16 | 2023-06-07 | 1 |  | 38 | 2 | 39 | 2023 | 2023 | R16
161153244530 | 160361244530 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-11-29 | 2021-11-30 | Overhead | R16 | 2021-11-29 | 1 |  | 72 | 2 | 73 | 2021 | 2021 | R16
162556240924 | 163638240924 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-27 | 2021-07-27 | 2021-07-27 |  | 2021-11-09 | Overhead | R16 | 2021-10-13 | 1 |  | 57 | 20 | 76 | 2021 | 2021 | R16
165470309972 | 167678309972 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-01 | 2023-02-03 | 2023-02-22 |  | 2023-08-18 | Underground | R16 | 2023-04-19 | 3 | 14 | 41 | 88 | 143 | 2023 | 2023 | R16
163880319227 | 169867319227 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-07-06 | 2023-07-06 | Overhead | R16 | 2023-07-06 | 1 |  | 39 |  | 39 | 2023 | 2023 | R16
160631243360 | 168050243360 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-08-12 | 2021-08-12 | 2021-08-12 | 2022-09-20 | 2022-09-21 | Overhead | R16 | 2022-09-20 | 1 |  | 289 | 2 | 290 | 2021 | 2022 | R16
163656315579 | 163033315579 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-11 | 2023-04-13 | 2023-04-13 | 2023-04-19 | 2023-06-13 | Overhead | R16 | 2023-04-19 | 3 |  | 5 | 40 | 46 | 2023 | 2023 | R16
165741314765 | 167693314765 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-01 | 2023-03-13 | 2023-04-04 |  | 2023-09-13 | Underground | R16 | 2023-05-30 | 29 | 17 | 41 | 77 | 161 | 2023 | 2023 | R16
160250322010 | 161307322010 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2023-05-23 | 2023-05-24 | 2023-06-12 | 2023-10-12 | 2023-10-20 | Underground | R16 | 2023-10-12 | 2 | 14 | 89 | 7 | 109 | 2023 | 2023 | R16
165864317899 | 169892317899 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-03-29 | 2023-05-03 | 2023-05-04 | 2023-07-17 | 2023-08-18 | Overhead | R16 | 2023-07-17 | 26 | 2 | 53 | 25 | 103 | 2023 | 2023 | R16
160948309223 | 160070309223 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-12 | 2023-02-12 | 2023-02-12 |  | 2023-07-31 | Overhead | R16 | 2023-04-07 | 0 |  | 40 | 82 | 121 | 2023 | 2023 | R16
162339307804 | 166732307804 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-01-27 | 2023-01-31 | 2023-01-31 | 2023-07-31 | 2023-08-09 | Overhead | R16 | 2023-07-31 | 3 |  | 130 | 8 | 139 | 2023 | 2023 | R16
160791332312 | 166303332312 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-20 | 2023-06-20 | 2023-09-13 | 2023-10-31 | 2023-11-06 | Underground | R16 | 2023-10-31 | 1 | 62 | 35 | 5 | 100 | 2023 | 2023 | R16
169755218343 | 168960218343 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH REWIRE OS | Commercial | 2021-01-22 | 2021-01-22 | 2021-01-25 |  | 2021-04-29 | Overhead | R16 | 2021-02-16 | 1 | 2 | 17 | 53 | 70 | 2021 | 2021 | R16
168974282100 | 163597282100 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2021-09-07 | 2022-04-05 | 2022-06-08 | 2022-07-20 | 2022-07-22 | Underground | R16 | 2022-07-20 | 151 | 47 | 31 | 3 | 229 | 2021 | 2022 | R16
168767247036 | 160849247036 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-24 | 2021-08-24 | 2021-09-08 | 2022-02-01 | 2022-03-03 | Underground | R16 | 2022-02-01 | 1 | 12 | 105 | 23 | 138 | 2021 | 2022 | R16
162295311723 | 163296311723 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-28 | 2023-03-07 | 2023-03-07 |  | 2023-07-31 | Overhead | R16 | 2023-03-10 | 6 |  | 4 | 102 | 110 | 2023 | 2023 | R16
166219322668 | 168707322668 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-09 | 2023-05-09 | 2023-09-08 | 2023-09-08 | 2023-09-18 | Underground | R16 | 2023-09-08 | 1 | 89 |  | 7 | 95 | 2023 | 2023 | R16
164605243354 | 168177243354 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-12 | 2021-08-12 | 2021-08-12 |  | 2022-07-27 | Overhead | R16 | 2022-07-26 | 1 |  | 249 | 2 | 250 | 2021 | 2022 | R16
167060317222 | 166393317222 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-28 | 2023-04-28 | 2023-04-28 | 2023-05-22 | 2023-06-15 | Overhead | R16 | 2023-05-22 | 1 |  | 17 | 19 | 35 | 2023 | 2023 | R16
168707306307 | 164359306307 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-18 | 2023-01-18 | 2023-01-30 | 2023-01-18 | 2023-03-31 | Overhead | R16 | 2023-01-18 | 1 | 9 |  | 53 | 53 | 2023 | 2023 | R16
162839242948 | 167262242948 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2021-09-01 | 2023-04-14 | Overhead | R16 | 2021-09-01 | 1 |  | 17 | 423 | 439 | 2021 | 2023 | R16
162398303684 | 168742303684 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-19 | 2022-12-19 | 2022-12-22 | 2023-02-06 | 2023-02-07 | Overhead | R16 | 2023-02-06 | 1 | 4 | 33 | 2 | 37 | 2022 | 2023 | R16
165352306472 | 165071306472 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-19 | 2023-01-19 | 2023-01-30 | 2023-02-03 | 2023-02-08 | Overhead | R16 | 2023-02-03 | 1 | 8 | 5 | 4 | 15 | 2023 | 2023 | R16
167593302977 | 167784302977 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-12-13 | 2022-12-13 | 2022-12-16 |  | 2023-03-02 | Underground | R16 | 2022-12-22 | 1 | 4 | 5 | 51 | 58 | 2022 | 2023 | R16
160189253171 | 164170253171 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2021-10-21 | 2021-10-21 | 2021-10-21 |  | 2022-10-25 | Underground | R16 |  | 1 |  |  |  | 264 | 2021 | 2022 | R16
165738320123 | 161388320123 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-23 | 2023-05-24 | 2023-05-24 | 2023-07-27 | 2023-08-02 | Overhead | R16 | 2023-07-27 | 2 |  | 47 | 5 | 52 | 2023 | 2023 | R16
166743318116 | 167335318116 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-03 | 2023-05-03 | 2023-05-05 |  | 2023-06-05 | Overhead | R16 | 2023-05-30 | 1 | 3 | 18 | 5 | 24 | 2023 | 2023 | R16
164659311828 | 165295311828 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-08 | 2023-03-08 | 2023-03-08 | 2023-08-10 | 2023-08-10 | Overhead | R16 | 2023-08-10 | 1 |  | 112 |  | 112 | 2023 | 2023 | R16
161632307800 | 167195307800 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-31 | 2023-01-31 | 2023-01-31 |  | 2023-06-26 | Overhead | R16 | 2023-04-05 | 1 |  | 47 | 59 | 105 | 2023 | 2023 | R16
160273219525 | 161950219525 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-03 | 2021-02-03 | 2021-02-03 |  | 2021-08-26 | Overhead | R16 | 2021-06-07 | 1 |  | 89 | 59 | 147 | 2021 | 2021 | R16
169019310243 | 161179310243 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-16 | 2023-02-21 | 2023-02-23 | 2023-03-29 | 2023-05-26 | Overhead | R16 | 2023-03-29 | 4 | 3 | 25 | 43 | 72 | 2023 | 2023 | R16
160313224485 | 162430224485 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-22 | 2021-03-23 | 2021-03-23 |  | 2021-11-08 | Underground | R16 | 2021-05-24 | 2 |  | 45 | 121 | 166 | 2021 | 2021 | R16
161660307094 | 166301307094 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-26 | 2023-01-26 | 2023-01-26 | 2023-07-27 | 2023-10-04 | Overhead | R16 | 2023-07-27 | 1 |  | 131 | 50 | 180 | 2023 | 2023 | R16
162692241834 | 165695241834 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-03 | 2021-08-03 | 2021-08-03 |  | 2021-09-01 | Overhead | R16 | 2021-08-09 | 1 |  | 5 | 18 | 22 | 2021 | 2021 | R16
167491320544 | 160000320544 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-16 | 2023-05-30 | 2023-05-30 | 2023-07-17 | 2023-08-07 | Overhead | R16 | 2023-07-17 | 11 |  | 35 | 16 | 60 | 2023 | 2023 | R16
168850317502 | 161821317502 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-06 | 2023-05-01 | 2023-05-01 | 2023-08-17 | 2023-08-29 | Overhead | R16 | 2023-08-17 | 18 |  | 79 | 9 | 104 | 2023 | 2023 | R16
167523241637 | 165015241637 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-30 | 2021-08-03 | 2021-08-03 | 2022-08-25 | 2022-08-29 | Overhead | R16 | 2022-08-25 | 3 |  | 278 | 3 | 282 | 2021 | 2022 | R16
163209243341 | 168090243341 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-12 | 2021-08-12 | 2021-08-12 | 2021-11-04 | 2021-12-08 | Overhead | R16 | 2021-11-04 | 1 |  | 61 | 25 | 85 | 2021 | 2021 | R16
164511241123 | 164136241123 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-28 | 2021-07-28 | 2021-07-28 |  | 2021-09-14 | Overhead | R16 | 2021-08-20 | 1 |  | 18 | 18 | 35 | 2021 | 2021 | R16
163685240521 | 163430240521 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-24 | 2021-07-24 | 2021-07-24 | 2021-09-08 | 2021-09-14 | Overhead | R16 | 2021-09-08 | 0 |  | 33 | 5 | 37 | 2021 | 2021 | R16
167045244824 | 169322244824 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-17 | 2021-08-19 | 2021-08-23 | 2021-10-07 | 2021-11-18 | Overhead | R16 | 2021-10-07 | 3 | 3 | 34 | 31 | 68 | 2021 | 2021 | R16
160710233209 | 165095233209 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-13 | 2021-05-18 | 2021-06-02 |  | 2021-11-03 | Overhead | R16 |  | 4 | 12 |  |  | 125 | 2021 | 2021 | R16
168797319085 | 165696319085 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-25 | 2023-05-15 | 2023-05-15 | 2023-06-06 | 2023-06-15 | Overhead | R16 | 2023-06-06 | 15 |  | 17 | 8 | 38 | 2023 | 2023 | R16
168926323673 | 168315323673 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-29 | 2023-06-29 | 2023-06-29 | 2023-08-02 | 2023-08-30 | Overhead | R16 | 2023-08-02 | 1 |  | 25 | 21 | 45 | 2023 | 2023 | R16
166371308297 | 168419308297 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-04 | 2023-02-04 | 2023-02-04 | 2023-06-27 | 2023-08-02 | Overhead | R16 | 2023-06-27 | 0 |  | 102 | 27 | 128 | 2023 | 2023 | R16
161000220750 | 164833220750 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-17 | 2021-02-17 | 2021-02-17 |  | 2021-08-12 | Overhead | R16 | 2021-04-07 | 1 |  | 36 | 92 | 127 | 2021 | 2021 | R16
169421313342 | 167779313342 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-21 | 2023-03-22 | 2023-03-22 | 2023-09-19 | 2023-10-10 | Overhead | R16 | 2023-09-19 | 2 |  | 130 | 16 | 146 | 2023 | 2023 | R16
160536321883 | 166501321883 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-28 | 2023-06-12 | 2023-06-12 | 2023-07-21 | 2023-07-24 | Overhead | R16 | 2023-07-21 | 32 |  | 30 | 2 | 62 | 2023 | 2023 | R16
165388309066 | 169796309066 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-02-10 | 2023-02-10 | 2023-02-10 | 2023-02-23 | 2023-02-24 | Overhead | R16 | 2023-02-23 | 1 |  | 10 | 2 | 11 | 2023 | 2023 | R16
166802316480 | 167541316480 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2023-03-20 | 2023-03-21 | 2023-04-20 | 2023-09-21 | 2023-10-04 | Underground | R16 | 2023-09-21 | 2 | 23 | 111 | 10 | 143 | 2023 | 2023 | R16
161242220539 | 164332220539 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-16 | 2021-02-16 | 2021-02-16 |  | 2021-11-13 | Overhead | R16 | 2021-04-19 | 1 |  | 45 | 150 | 194 | 2021 | 2021 | R16
160504314981 | 161881314981 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-06 | 2023-04-06 | 2023-04-06 |  | 2023-06-29 | Overhead | R16 | 2023-05-31 | 1 |  | 40 | 22 | 61 | 2023 | 2023 | R16
166614303065 | 167641303065 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-12 | 2022-12-16 | 2022-12-21 |  | 2023-02-26 | Overhead | R16 | 2023-02-14 | 5 | 4 | 40 | 9 | 55 | 2022 | 2023 | R16
162546334522 | 163393334522 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-05 | 2023-06-05 | 2023-10-03 | 2023-10-16 | 2023-11-03 | Underground | R16 | 2023-10-16 | 1 | 87 | 10 | 15 | 110 | 2023 | 2023 | R16
165065318148 | 168065318148 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-05 | 2023-05-05 | 2023-05-05 |  | 2023-06-06 | Overhead | R16 | 2023-05-05 | 1 |  |  | 23 | 23 | 2023 | 2023 | R16
164904268090 | 167549268090 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-11 | 2021-08-12 | 2022-02-08 |  | 2022-08-23 | Underground | R16 |  | 2 | 129 |  |  | 270 | 2021 | 2022 | R16
162159336156 | 167810336156 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-27 | 2023-06-27 | 2023-10-19 | 2023-10-23 | 2023-11-09 | Underground | R16 | 2023-10-23 | 1 | 83 | 3 | 14 | 98 | 2023 | 2023 | R16
161589246256 | 162859246256 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-01 | 2021-09-02 | 2021-09-02 | 2021-10-06 | 2021-12-17 | Overhead | R16 | 2021-10-06 | 2 |  | 25 | 53 | 78 | 2021 | 2021 | R16
160599316651 | 162847316651 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-11 | 2023-04-11 | 2023-04-21 |  | 2023-08-30 | Underground | R16 | 2023-04-24 | 1 | 9 | 2 | 93 | 102 | 2023 | 2023 | R16
161377309101 | 164928309101 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-19 | 2023-02-10 | 2023-02-10 | 2023-05-04 | 2023-07-10 | Overhead | R16 | 2023-05-04 | 17 |  | 60 | 48 | 123 | 2023 | 2023 | R16
167485317512 | 166798317512 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-01 | 2023-05-01 | 2023-05-01 | 2023-08-24 | 2023-10-05 | Overhead | R16 | 2023-08-24 | 1 |  | 84 | 31 | 114 | 2023 | 2023 | R16
161487251181 | 160465251181 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-07 | 2021-10-07 | 2021-10-07 |  | 2022-02-10 | Underground | R16 | 2022-01-05 | 1 |  | 65 | 27 | 91 | 2021 | 2022 | R16
161150247428 | 164813247428 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-11-30 | 2022-01-18 | Overhead | R16 | 2021-11-30 | 1 |  | 58 | 36 | 93 | 2021 | 2022 | R16
164687321948 | 161261321948 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-23 | 2023-06-12 | 2023-06-12 | 2023-10-12 | 2023-10-26 | Overhead | R16 | 2023-10-12 | 15 |  | 89 | 11 | 113 | 2023 | 2023 | R16
165421319516 | 168902319516 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-05-10 | 2023-05-19 | 2023-05-19 | 2023-10-27 | 2023-11-01 | Underground | R16 | 2023-10-27 | 8 |  | 116 | 4 | 126 | 2023 | 2023 | R16
161574222366 | 167287222366 | CUSTOMER UPGRADE IN SERVICE | UG SVC CONVERSION | Residential | 2021-01-15 | 2021-02-22 | 2021-03-03 |  | 2021-11-04 | Underground | R16 | 2021-04-05 | 27 | 8 | 24 | 154 | 210 | 2021 | 2021 | R16
167270315308 | 168520315308 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-23 | 2023-04-10 | 2023-04-10 |  | 2023-08-30 | Underground | R16 | 2023-04-14 | 13 |  | 5 | 99 | 115 | 2023 | 2023 | R16
167490323794 | 167830323794 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-27 | 2023-06-30 | 2023-06-30 | 2023-08-02 | 2023-08-18 | Overhead | R16 | 2023-08-02 | 4 |  | 24 | 13 | 39 | 2023 | 2023 | R16
164076321686 | 163434321686 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-05 | 2023-06-05 | 2023-06-09 | 2023-06-28 | 2023-09-12 | Underground | R16 | 2023-06-28 | 1 | 5 | 14 | 55 | 72 | 2023 | 2023 | R16
167832244426 | 169873244426 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-19 | 2021-08-19 | 2021-08-19 |  | 2021-11-02 | Underground | R16 | 2021-10-28 | 1 |  | 51 | 4 | 54 | 2021 | 2021 | R16
168112322997 | 166868322997 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-23 | 2023-06-23 | 2023-06-23 | 2023-06-27 | 2023-07-19 | Underground | R16 | 2023-06-27 | 1 |  | 3 | 17 | 19 | 2023 | 2023 | R16
162185246717 | 163886246717 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-07 | 2021-09-07 | 2021-09-07 | 2021-11-16 | 2022-01-04 | Overhead | R16 | 2021-11-16 | 1 |  | 51 | 36 | 86 | 2021 | 2022 | R16
162222249938 | 165240249938 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-13 | 2021-09-14 | 2021-09-29 | 2021-11-17 | 2021-11-18 | Underground | R16 | 2021-11-17 | 2 | 12 | 36 | 2 | 49 | 2021 | 2021 | R16
168807321887 | 164071321887 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-07 | 2023-06-12 | 2023-06-12 | 2023-07-17 | 2023-07-20 | Overhead | R16 | 2023-07-17 | 4 |  | 26 | 4 | 32 | 2023 | 2023 | R16
162220247228 | 164698247228 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-10 | 2021-09-10 | 2021-09-10 |  | 2021-11-09 | Overhead | R16 | 2021-09-30 | 1 |  | 15 | 29 | 43 | 2021 | 2021 | R16
167913316515 | 162229316515 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-07 | 2023-04-10 | 2023-04-21 |  | 2023-06-21 | Underground | R16 | 2023-06-12 | 2 | 10 | 37 | 8 | 54 | 2023 | 2023 | R16
161779305609 | 167965305609 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-13 | 2022-12-13 | 2023-01-25 | 2023-02-21 | 2023-02-22 | Overhead | R16 | 2023-02-21 | 1 | 32 | 20 | 2 | 52 | 2022 | 2023 | R16
168314314045 | 169796314045 | RESIDENTIAL - SINGLE FAMILY DETACHED | ELEC OH MISC SVC OS | Residential | 2023-03-28 | 2023-03-28 | 2023-03-29 |  | 2023-07-28 | Overhead | R16 | 2023-03-29 | 1 | 2 |  | 88 | 89 | 2023 | 2023 | R16
163496322893 | 165555322893 | RESIDENTIAL - MOBILE HOME | OH R16 RES NON RES OS | Residential | 2023-06-15 | 2023-06-22 | 2023-06-22 | 2023-12-08 | 2023-12-15 | Overhead | R16 | 2023-12-08 | 6 |  | 122 | 6 | 132 | 2023 | 2023 | R16
169869303860 | 168954303860 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-20 | 2022-12-20 | 2022-12-22 |  | 2023-02-26 | Overhead | R16 | 2022-12-29 | 1 | 3 | 6 | 42 | 49 | 2022 | 2023 | R16
162713216723 | 165638216723 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-08 | 2021-01-08 | 2021-01-08 |  | 2023-06-19 | Overhead | R16 | 2023-03-10 | 1 |  | 566 | 72 | 637 | 2021 | 2023 | R16
166392326924 | 165501326924 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-24 | 2023-04-24 | 2023-07-31 |  | 2023-08-28 | Underground | R16 | 2023-08-17 | 1 | 71 | 14 | 8 | 91 | 2023 | 2023 | R16
168973246930 | 163883246930 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-07 | 2021-09-07 | 2021-09-08 | 2021-10-20 | 2021-12-09 | Overhead | R16 | 2021-10-20 | 1 | 2 | 31 | 37 | 68 | 2021 | 2021 | R16
161180247876 | 165037247876 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-13 | 2021-09-13 | 2021-09-15 | 2022-03-30 | 2022-04-18 | Overhead | R16 | 2022-03-30 | 1 | 3 | 141 | 14 | 156 | 2021 | 2022 | R16
160082294022 | 169924294022 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2021-08-19 | 2022-04-13 | 2022-09-16 | 2023-04-26 | 2023-05-10 | Underground | R16 | 2023-04-26 | 170 | 113 | 159 | 11 | 450 | 2021 | 2023 | R16
160134315324 | 160028315324 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-29 |  | 2023-04-10 | 2023-07-10 | 2023-07-24 | Overhead | R16 | 2023-07-10 |  |  | 66 | 11 | 84 | 2023 | 2023 | R16
161390244419 | 160424244419 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-10-15 | 2021-10-18 | Overhead | R16 | 2021-10-15 | 1 |  | 41 | 2 | 42 | 2021 | 2021 | R16
166737314828 | 162643314828 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-01-10 | 2023-01-10 | 2023-04-05 |  | 2023-06-19 | Overhead | R16 | 2023-04-05 | 1 | 62 |  | 54 | 115 | 2023 | 2023 | R16
163791316072 | 163261316072 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-12 | 2023-04-12 | 2023-04-17 |  | 2023-09-13 | Overhead | R16 |  | 1 | 4 |  |  | 111 | 2023 | 2023 | R16
168491323717 | 168610323717 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-30 | 2023-06-30 | 2023-06-30 | 2023-07-24 | 2023-08-07 | Overhead | R16 | 2023-07-24 | 1 |  | 17 | 11 | 27 | 2023 | 2023 | R16
162967219317 | 169185219317 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-25 | 2021-02-04 | 2021-02-04 |  | 2021-11-08 | Overhead | R16 | 2021-05-14 | 9 |  | 72 | 127 | 206 | 2021 | 2021 | R16
163251321121 | 160948321121 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-05-22 | 2023-05-22 | 2023-06-02 | 2023-10-13 | 2023-11-03 | Underground | R16 | 2023-10-13 | 1 | 10 | 96 | 16 | 120 | 2023 | 2023 | R16
161645247797 | 165239247797 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-14 | 2021-09-14 | 2021-09-14 |  | 2021-11-30 | Overhead | R16 | 2021-11-03 | 1 |  | 37 | 20 | 56 | 2021 | 2021 | R16
160897324027 | 169694324027 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-15 | 2023-07-03 | 2023-07-03 | 2023-09-12 | 2023-09-12 | Overhead | R16 | 2023-09-12 | 36 |  | 52 |  | 87 | 2023 | 2023 | R16
167074240925 | 163913240925 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-27 | 2021-07-27 | 2021-07-27 | 2021-09-01 | 2021-10-26 | Overhead | R16 | 2021-09-01 | 1 |  | 27 | 40 | 66 | 2021 | 2021 | R16
160733260293 | 161539260293 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-27 | 2021-08-27 | 2021-12-08 |  | 2022-03-08 | Underground | R16 | 2022-01-18 | 1 | 74 | 30 | 36 | 138 | 2021 | 2022 | R16
165634312555 | 166817312555 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-06-05 | 2023-09-26 | Overhead | R16 | 2023-06-05 | 1 |  | 58 | 82 | 139 | 2023 | 2023 | R16
167437318016 | 169366318016 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-03-27 | 2023-04-04 | 2023-05-05 |  | 2023-08-18 | Overhead | R16 | 2023-05-11 | 7 | 24 | 5 | 72 | 105 | 2023 | 2023 | R16
165904311655 | 164317311655 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-03-03 | 2023-03-03 | 2023-03-06 | 2023-03-08 | 2023-05-17 | Overhead | R16 | 2023-03-08 | 1 | 2 | 3 | 51 | 54 | 2023 | 2023 | R16
168734317887 | 167565317887 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-03 | 2023-05-03 | 2023-05-03 | 2023-09-28 | 2023-10-06 | Overhead | R16 | 2023-09-28 | 1 |  | 107 | 7 | 113 | 2023 | 2023 | R16
160796307354 | 166611307354 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-27 | 2023-01-27 | 2023-01-27 |  | 2023-05-17 | Overhead | R16 | 2023-02-27 | 1 |  | 22 | 58 | 79 | 2023 | 2023 | R16
161333315023 | 161857315023 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-06 | 2023-04-06 | 2023-04-06 | 2023-08-18 | 2023-10-02 | Overhead | R16 | 2023-08-18 | 1 |  | 97 | 32 | 128 | 2023 | 2023 | R16
165887241390 | 164804241390 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-30 | 2021-07-30 | 2021-07-30 | 2021-11-12 | 2021-12-01 | Overhead | R16 | 2021-11-12 | 1 |  | 76 | 14 | 89 | 2021 | 2021 | R16
162846316733 | 165651316733 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-24 | 2023-04-24 | 2023-04-24 | 2023-07-12 | 2023-07-13 | Overhead | R16 | 2023-07-12 | 1 |  | 58 | 2 | 59 | 2023 | 2023 | R16
164284258662 | 165111258662 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-13 | 2021-09-13 | 2021-11-24 | 2022-01-20 | 2022-02-28 | Underground | R16 | 2022-01-20 | 1 | 53 | 42 | 28 | 121 | 2021 | 2022 | R16
163275251304 | 162977251304 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-02 | 2021-09-02 | 2021-10-08 |  | 2022-02-15 | Underground | R16 | 2022-01-18 | 1 | 27 | 73 | 21 | 119 | 2021 | 2022 | R16
167761308107 | 167639308107 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-02 | 2023-02-02 | 2023-02-02 | 2023-02-02 | 2023-05-30 | Overhead | R16 | 2023-02-02 | 1 |  |  | 84 | 84 | 2023 | 2023 | R16
161183320203 | 168208320203 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-22 | 2023-03-22 | 2023-05-24 | 2023-06-09 | 2023-07-24 | Underground | R16 | 2023-06-09 | 1 | 46 | 13 | 32 | 89 | 2023 | 2023 | R16
168210324104 | 162258324104 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-30 | 2023-07-03 | 2023-07-03 | 2023-07-26 | 2023-11-16 | Overhead | R16 | 2023-07-26 | 25 |  | 18 | 82 | 123 | 2023 | 2023 | R16
160984322789 | 162849322789 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-11 | 2023-04-11 | 2023-06-20 | 2023-10-13 | 2023-10-25 | Underground | R16 | 2023-10-13 | 1 | 51 | 84 | 9 | 142 | 2023 | 2023 | R16
162745313901 | 167880313901 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-02 | 2023-02-02 | 2023-03-27 |  | 2023-08-22 | Underground | R16 | 2023-05-09 | 1 | 38 | 32 | 76 | 144 | 2023 | 2023 | R16
164499308700 | 165156308700 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-20 | 2023-01-23 | 2023-02-07 |  | 2023-10-02 | Underground | R16 | 2023-06-22 | 2 | 12 | 98 | 73 | 182 | 2023 | 2023 | R16
161976321497 | 162764321497 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-01 | 2023-06-08 | 2023-06-08 | 2023-09-25 | 2023-11-15 | Overhead | R16 | 2023-09-25 | 6 |  | 78 | 38 | 120 | 2023 | 2023 | R16
163400219324 | 169202219324 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-25 | 2021-02-02 | 2021-02-02 |  | 2021-08-03 | Overhead | R16 | 2021-03-17 | 7 |  | 32 | 100 | 137 | 2021 | 2021 | R16
168939257033 | 169044257033 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2021-08-16 | 2021-11-02 | 2021-11-17 | 2022-01-10 | 2022-01-26 | Underground | R16 | 2022-01-10 | 57 | 12 | 39 | 13 | 118 | 2021 | 2022 | R16
164760303710 | 168725303710 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-19 | 2022-12-19 | 2022-12-22 |  | 2023-07-26 | Overhead | R16 | 2023-03-28 | 1 | 4 | 69 | 87 | 158 | 2022 | 2023 | R16
168220311683 | 164619311683 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-03-06 | 2023-03-06 | 2023-03-07 | 2023-05-15 | 2023-08-31 | Underground | R16 | 2023-05-15 | 1 | 2 | 50 | 79 | 129 | 2023 | 2023 | R16
163065308302 | 168197308302 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-03 | 2023-02-03 | 2023-02-03 | 2023-02-13 | 2023-03-31 | Overhead | R16 | 2023-02-13 | 1 |  | 7 | 35 | 41 | 2023 | 2023 | R16
163940315676 | 162995315676 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-11 | 2023-04-13 | 2023-04-13 | 2023-04-14 | 2023-06-13 | Overhead | R16 | 2023-04-14 | 3 |  | 2 | 43 | 46 | 2023 | 2023 | R16
168989256514 | 163541256514 | RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Residential | 2021-07-26 | 2021-11-02 | 2021-11-15 | 2022-01-19 | 2022-01-26 | Underground | R16 | 2022-01-19 | 72 | 10 | 48 | 6 | 133 | 2021 | 2022 | R16
161777246980 | 163966246980 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-08 | 2021-09-08 | 2021-09-08 |  | 2023-02-17 | Overhead | R16 | 2022-12-15 | 1 |  | 332 | 47 | 378 | 2021 | 2023 | R16
163581220959 | 165241220959 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-18 | 2021-02-18 | 2021-02-19 |  | 2021-11-05 | Overhead | R16 | 2021-04-27 | 1 | 2 | 48 | 139 | 187 | 2021 | 2021 | R16
165618311360 | 163549311360 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-13 | 2023-03-03 | 2023-03-03 |  | 2023-07-26 | Overhead | R16 | 2023-03-27 | 36 |  | 17 | 88 | 139 | 2023 | 2023 | R16
162683245038 | 161151245038 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2022-03-22 | 2022-03-23 | Overhead | R16 | 2022-03-22 | 1 |  | 150 | 2 | 151 | 2021 | 2022 | R16
165574310537 | 162776310537 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-24 | 2023-02-24 | 2023-02-24 | 2023-08-07 | 2023-08-15 | Overhead | R16 | 2023-08-07 | 1 |  | 117 | 7 | 123 | 2023 | 2023 | R16
164759303320 | 168032303320 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-14 | 2022-12-14 | 2022-12-21 |  | 2023-06-29 | Overhead | R16 | 2023-06-19 | 1 | 6 | 129 | 9 | 142 | 2022 | 2023 | R16
163030246754 | 163852246754 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-09-07 | 2021-09-08 | 2021-09-08 |  | 2023-03-31 | Underground | R16 | 2023-03-02 | 2 |  | 387 | 22 | 409 | 2021 | 2023 | R16
163756223239 | 162228223239 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-04 | 2021-02-04 | 2021-03-11 |  | 2021-11-02 | Underground | R16 | 2021-06-15 | 1 | 26 | 69 | 101 | 194 | 2021 | 2021 | R16
163808222331 | 169125222331 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-25 | 2021-02-12 | 2021-03-03 |  | 2021-08-12 | Underground | R16 | 2021-03-18 | 15 | 14 | 12 | 106 | 144 | 2021 | 2021 | R16
166084321062 | 160989321062 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-22 | 2023-05-22 | 2023-06-02 | 2023-10-30 | 2023-11-02 | Underground | R16 | 2023-10-30 | 1 | 10 | 107 | 4 | 119 | 2023 | 2023 | R16
162664305054 | 161756305054 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-05 | 2023-01-05 | 2023-01-05 | 2023-03-14 | 2023-03-15 | Overhead | R16 | 2023-03-14 | 1 |  | 49 | 2 | 50 | 2023 | 2023 | R16
160907252046 | 162546252046 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-31 | 2021-08-31 | 2021-10-13 | 2022-01-27 | 2022-03-02 | Underground | R16 | 2022-01-27 | 1 | 32 | 77 | 25 | 132 | 2021 | 2022 | R16
164478305407 | 162378305407 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-09 |  | 2023-01-30 | 2023-04-13 | 2023-04-14 | Overhead | R16 | 2023-04-13 |  |  | 54 | 2 | 70 | 2023 | 2023 | R16
160082305139 | 166401305139 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-08-05 | 2021-09-03 | 2023-01-06 |  | 2023-10-12 | Overhead | R16 |  | 22 | 351 |  |  | 571 | 2021 | 2023 | R16
164103228614 | 162979228614 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-03-24 | 2021-03-24 | 2021-04-28 |  | 2021-10-27 | Underground | R16 |  | 1 | 26 |  |  | 156 | 2021 | 2021 | R16
164140218106 | 168865218106 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-22 | 2021-01-22 | 2021-01-22 |  | 2021-08-05 | Overhead | R16 | 2021-03-29 | 1 |  | 47 | 94 | 140 | 2021 | 2021 | R16
167594320823 | 167285320823 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-17 | 2023-05-31 | 2023-05-31 | 2023-11-27 | 2023-12-06 | Overhead | R16 | 2023-11-27 | 54 |  | 129 | 8 | 189 | 2023 | 2023 | R16
164252220610 | 164307220610 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-16 | 2021-02-16 | 2021-02-16 |  | 2021-11-08 | Overhead | R16 | 2021-04-20 | 1 |  | 46 | 145 | 190 | 2021 | 2021 | R16
163899322648 | 164342322648 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-18 | 2023-04-18 | 2023-06-19 |  | 2023-10-04 | Underground | R16 | 2023-06-23 | 1 | 45 | 5 | 74 | 122 | 2023 | 2023 | R16
161343320637 | 162541320637 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-31 | 2023-05-31 | 2023-05-31 | 2023-05-31 | 2023-06-28 | Overhead | R16 | 2023-05-31 | 1 |  |  | 21 | 21 | 2023 | 2023 | R16
164151324460 | 169702324460 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-07 | 2023-07-07 | 2023-07-07 | 2023-07-17 | 2023-08-10 | Overhead | R16 | 2023-07-17 | 1 |  | 7 | 19 | 25 | 2023 | 2023 | R16
160674319429 | 169371319429 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-05-11 | 2023-05-12 | 2023-05-17 |  | 2023-09-13 | Overhead | R16 |  | 2 | 4 |  |  | 90 | 2023 | 2023 | R16
164679321300 | 168201321300 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-05 | 2023-06-05 | 2023-06-05 | 2023-07-20 | 2023-08-04 | Overhead | R16 | 2023-07-20 | 22 |  | 34 | 12 | 66 | 2023 | 2023 | R16
161160241413 | 164902241413 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-30 | 2021-07-30 | 2021-07-30 |  | 2021-10-25 | Overhead | R16 | 2021-09-08 | 1 |  | 29 | 34 | 62 | 2021 | 2021 | R16
168779325634 | 169897325634 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-10 | 2023-07-10 | 2023-07-20 | 2023-07-25 | 2023-08-28 | Underground | R16 | 2023-07-25 | 1 | 9 | 4 | 25 | 36 | 2023 | 2023 | R16
164274319663 | 164319319663 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-18 | 2023-04-18 | 2023-05-19 | 2023-09-18 | 2023-09-25 | Underground | R16 | 2023-09-18 | 1 | 24 | 87 | 6 | 115 | 2023 | 2023 | R16
161826327105 | 167353327105 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-26 | 2023-06-26 | 2023-08-02 | 2023-12-07 | 2023-12-08 | Underground | R16 | 2023-12-07 | 1 | 28 | 92 | 2 | 120 | 2023 | 2023 | R16
169153314535 | 160619314535 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-31 | 2023-04-03 | 2023-04-03 |  | 2023-08-14 | Overhead | R16 | 2023-04-04 | 2 |  | 2 | 95 | 97 | 2023 | 2023 | R16
167230312782 | 166266312782 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-06-26 | 2023-07-21 | Overhead | R16 | 2023-06-26 | 2 | 2 | 73 | 20 | 94 | 2023 | 2023 | R16
164515221529 | 166423221529 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-24 | 2021-02-25 | 2021-02-25 |  | 2021-11-08 | Overhead | R16 | 2021-05-27 | 2 |  | 66 | 118 | 184 | 2021 | 2021 | R16
160635320028 | 161283320028 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-23 | 2023-05-23 | 2023-05-23 | 2023-05-31 | 2023-06-28 | Overhead | R16 | 2023-05-31 | 1 |  | 7 | 21 | 27 | 2023 | 2023 | R16
161520318511 | 168877318511 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-24 | 2023-03-24 | 2023-05-09 |  | 2023-08-22 | Underground | R16 | 2023-05-10 | 1 | 33 | 2 | 75 | 108 | 2023 | 2023 | R16
166519317718 | 167205317718 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-02 | 2023-05-02 | 2023-05-02 | 2023-07-27 | 2023-08-25 | Overhead | R16 | 2023-07-27 | 1 |  | 63 | 22 | 84 | 2023 | 2023 | R16
164620222685 | 162244222685 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-02-04 | 2021-02-17 | 2021-03-05 |  | 2022-04-25 | Underground | R16 | 2022-04-04 | 10 | 13 | 282 | 16 | 318 | 2021 | 2022 | R16
169180315894 | 163285315894 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-04-12 | 2023-04-14 | 2023-04-14 |  | 2023-07-05 | Overhead | R16 | 2023-06-27 | 3 |  | 53 | 7 | 61 | 2023 | 2023 | R16
167665312018 | 165611312018 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-09 | 2023-03-10 | 2023-03-10 | 2023-03-14 | 2023-06-12 | Overhead | R16 | 2023-03-14 | 2 |  | 3 | 65 | 68 | 2023 | 2023 | R16
167073315306 | 168479315306 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-23 | 2023-04-10 | 2023-04-10 | 2023-05-31 | 2023-06-07 | Underground | R16 | 2023-05-31 | 13 |  | 38 | 6 | 55 | 2023 | 2023 | R16
167862323619 | 167792323619 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-27 | 2023-06-29 | 2023-06-29 | 2023-07-12 | 2023-08-16 | Overhead | R16 | 2023-07-12 | 3 |  | 10 | 26 | 37 | 2023 | 2023 | R16
160769315405 | 162354315405 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2023-04-08 | 2023-04-10 | 2023-04-10 |  | 2023-06-09 | Underground | R16 | 2023-05-30 | 1 |  | 37 | 9 | 45 | 2023 | 2023 | R16
160704315246 | 162615315246 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-04-10 | 2023-04-10 | 2023-04-10 |  | 2023-08-09 | Overhead | R16 | 2023-05-02 | 1 |  | 17 | 72 | 88 | 2023 | 2023 | R16
162366303422 | 168293303422 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-15 | 2022-12-15 | 2022-12-15 | 2022-12-21 | 2023-02-28 | Overhead | R16 | 2022-12-21 | 1 |  | 5 | 50 | 54 | 2022 | 2023 | R16
165296246772 | 163750246772 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-07 | 2021-09-07 | 2021-09-07 | 2022-03-17 | 2022-04-20 | Underground | R16 | 2022-03-17 | 1 |  | 138 | 25 | 162 | 2021 | 2022 | R16
163541312109 | 166696312109 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-27 | 2023-01-27 | 2023-03-10 |  | 2023-07-28 | Underground | R16 | 2023-03-13 | 1 | 31 | 2 | 100 | 131 | 2023 | 2023 | R16
163657309489 | 160853309489 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-15 | 2023-02-15 | 2023-02-15 | 2023-03-22 | 2023-05-18 | Overhead | R16 | 2023-03-22 | 1 |  | 26 | 42 | 67 | 2023 | 2023 | R16
165964312089 | 165752312089 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-10 | 2023-03-10 | 2023-03-10 | 2023-04-20 | 2023-06-12 | Overhead | R16 | 2023-04-20 | 1 |  | 30 | 38 | 67 | 2023 | 2023 | R16
164353340760 | 166938340760 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-22 | 2023-06-22 | 2023-11-27 | 2023-12-08 | 2023-12-28 | Underground | R16 | 2023-12-08 | 1 | 113 | 10 | 15 | 136 | 2023 | 2023 | R16
165045321170 | 163792321170 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-06 | 2023-06-06 | 2023-06-06 | 2023-06-29 | 2023-09-21 | Overhead | R16 | 2023-06-29 | 1 |  | 18 | 61 | 78 | 2023 | 2023 | R16
166528309543 | 160495309543 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-14 | 2023-02-14 | 2023-02-15 | 2023-02-24 | 2023-05-17 | Overhead | R16 | 2023-02-24 | 1 | 2 | 8 | 59 | 67 | 2023 | 2023 | R16
165448303408 | 167632303408 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-12-12 | 2022-12-14 | 2022-12-16 |  | 2023-01-12 | Overhead | R16 | 2023-01-10 | 3 | 3 | 18 | 3 | 24 | 2022 | 2023 | R16
165280319324 | 165380319324 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-21 | 2023-05-17 | 2023-05-17 |  | 2023-09-28 | Overhead | R16 | 2023-06-16 | 19 |  | 23 | 75 | 115 | 2023 | 2023 | R16
168655325647 | 169251325647 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-05 | 2023-07-05 | 2023-07-20 | 2023-09-01 | 2023-10-25 | Underground | R16 | 2023-09-01 | 1 | 12 | 32 | 39 | 81 | 2023 | 2023 | R16
160852314071 | 167955314071 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-22 | 2023-03-22 | 2023-03-29 |  | 2023-06-09 | Underground | R16 | 2023-05-25 | 1 | 6 | 42 | 12 | 58 | 2023 | 2023 | R16
166031303981 | 168825303981 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-21 | 2022-12-21 | 2022-12-22 | 2023-03-08 | 2023-06-13 | Overhead | R16 | 2023-03-08 | 1 | 2 | 55 | 70 | 125 | 2022 | 2023 | R16
165908303656 | 167557303656 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-12 | 2022-12-22 | 2022-12-27 |  | 2023-07-31 | Underground | R16 | 2023-02-16 | 9 | 4 | 38 | 118 | 166 | 2022 | 2023 | R16
169529241648 | 165366241648 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-02 | 2021-08-02 | 2021-08-02 | 2021-09-15 | 2021-11-08 | Overhead | R16 | 2021-09-15 | 1 |  | 33 | 39 | 71 | 2021 | 2021 | R16
164082316569 | 164252316569 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2023-04-18 | 2023-04-19 | 2023-04-21 | 2023-08-08 | 2023-09-06 | Underground | R16 | 2023-08-08 | 2 | 3 | 78 | 22 | 102 | 2023 | 2023 | R16
169340245222 | 161224245222 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-31 | 2021-11-02 | Overhead | R16 | 2021-08-31 | 1 |  | 5 | 46 | 50 | 2021 | 2021 | R16
161484319301 | 163280319301 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Commercial | 2023-04-12 | 2023-04-12 | 2023-05-16 | 2023-12-08 | 2023-12-19 | Overhead | R16 | 2023-12-08 | 1 | 25 | 149 | 8 | 180 | 2023 | 2023 | R16
162836245499 | 161915245499 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-27 | 2021-08-27 | 2021-08-27 | 2022-01-19 | 2022-03-01 | Overhead | R16 | 2022-01-19 | 1 |  | 104 | 30 | 133 | 2021 | 2022 | R16
169713248975 | 165166248975 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-13 | 2021-09-13 | 2021-09-23 | 2022-02-24 | 2022-03-25 | Underground | R16 | 2022-02-24 | 1 | 9 | 111 | 22 | 140 | 2021 | 2022 | R16
165221303221 | 167714303221 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-13 | 2022-12-13 | 2022-12-21 | 2023-03-22 | 2023-04-08 | Overhead | R16 | 2023-03-22 | 1 | 7 | 66 | 13 | 84 | 2022 | 2023 | R16
165145224858 | 162888224858 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-08 | 2021-03-26 | 2021-03-26 |  | 2021-08-31 | Overhead | R16 | 2021-06-11 | 35 |  | 56 | 58 | 147 | 2021 | 2021 | R16
169363312422 | 162708312422 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-24 | 2023-03-14 | 2023-03-14 |  | 2023-07-26 | Overhead | R16 | 2023-03-22 | 13 |  | 7 | 91 | 109 | 2023 | 2023 | R16
162432272992 | 167558272992 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-08-11 | 2021-08-11 | 2022-03-18 |  | 2023-05-04 | Underground | R16 |  | 1 | 158 |  |  | 452 | 2021 | 2023 | R16
163149249055 | 168737249055 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-16 | 2021-08-16 | 2021-09-22 |  | 2021-12-28 | Overhead | R16 | 2021-11-16 | 1 | 28 | 40 | 31 | 97 | 2021 | 2021 | R16
168766311803 | 165432311803 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-23 | 2023-01-23 | 2023-03-08 | 2023-03-28 | 2023-03-29 | Underground | R16 | 2023-03-28 | 1 | 33 | 15 | 2 | 48 | 2023 | 2023 | R16
165455316050 | 166096316050 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-13 | 2023-04-17 | 2023-04-17 |  | 2023-09-28 | Underground | R16 | 2023-06-22 | 26 |  | 49 | 71 | 144 | 2023 | 2023 | R16
169373243988 | 169213243988 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-17 | 2021-08-17 | 2021-08-17 |  | 2023-07-07 | Overhead | R16 | 2021-09-23 | 1 |  | 28 | 467 | 494 | 2021 | 2023 | R16
162131319194 | 169870319194 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-07-27 | 2023-08-01 | Overhead | R16 | 2023-07-27 | 1 |  | 54 | 4 | 57 | 2023 | 2023 | R16
166062263714 | 169412263714 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-18 | 2021-08-18 | 2022-01-06 | 2022-03-08 | 2022-03-09 | Underground | R16 | 2022-03-08 | 1 | 102 | 44 | 2 | 146 | 2021 | 2022 | R16
162585323161 | 167080323161 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-06-23 | 2023-06-23 | 2023-06-23 | 2023-07-25 | 2023-07-25 | Overhead | R16 | 2023-07-25 | 1 |  | 23 |  | 23 | 2023 | 2023 | R16
167241307586 | 166969307586 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-30 | 2023-01-30 | 2023-01-30 |  | 2023-08-16 | Overhead | R16 | 2023-05-02 | 1 |  | 67 | 77 | 143 | 2023 | 2023 | R16
165498219783 | 162471219783 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-05 | 2021-02-05 | 2021-02-05 |  | 2021-11-09 | Underground | R16 | 2021-04-28 | 1 |  | 59 | 140 | 198 | 2021 | 2021 | R16
163049306995 | 168821306995 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2022-12-19 | 2022-12-19 | 2023-01-25 | 2023-05-17 | 2023-08-04 | Underground | R16 | 2023-05-17 | 1 | 28 | 81 | 58 | 165 | 2022 | 2023 | R16
168427309642 | 161064309642 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-16 | 2023-02-16 | 2023-02-16 | 2023-08-08 | 2023-09-28 | Overhead | R16 | 2023-08-08 | 1 |  | 124 | 38 | 161 | 2023 | 2023 | R16
168982305130 | 161760305130 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-05 | 2023-01-05 | 2023-01-05 | 2023-05-12 | 2023-05-16 | Overhead | R16 | 2023-05-12 | 1 |  | 92 | 3 | 94 | 2023 | 2023 | R16
167864245801 | 163977245801 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-27 | 2021-07-27 | 2021-08-29 | 2021-11-04 | 2021-12-03 | Overhead | R16 | 2021-11-04 | 1 | 24 | 49 | 22 | 94 | 2021 | 2021 | R16
168991332400 | 160315332400 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-11 | 2023-07-11 | 2023-09-12 | 2023-09-12 | 2023-09-29 | Overhead | R16 | 2023-09-12 | 1 | 46 |  | 14 | 59 | 2023 | 2023 | R16
160939321656 | 164718321656 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2023-04-19 | 2023-04-21 | 2023-06-09 |  | 2023-09-29 | Overhead | R16 |  | 3 | 36 |  |  | 118 | 2023 | 2023 | R16
165642224555 | 160501224555 | CUSTOMER UPGRADE IN SERVICE | UG SVC CONVERSION | Residential | 2021-03-13 | 2021-03-16 | 2021-03-24 |  | 2023-07-17 | Underground | R16 |  | 2 | 7 |  |  | 611 | 2021 | 2023 | R16
162663321888 | 168635321888 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-23 | 2023-03-23 | 2023-06-12 | 2023-06-16 | 2023-06-29 | Overhead | R16 | 2023-06-16 | 1 | 58 | 5 | 10 | 71 | 2023 | 2023 | R16
160157246048 | 169729246048 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-18 | 2021-08-18 | 2021-08-31 | 2023-02-07 | 2023-03-08 | Underground | R16 | 2023-02-07 | 1 | 10 | 376 | 22 | 406 | 2021 | 2023 | R16
165872308153 | 166477308153 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-26 | 2023-01-26 | 2023-02-02 | 2023-08-23 | 2023-09-19 | Underground | R16 | 2023-08-23 | 1 | 6 | 145 | 20 | 169 | 2023 | 2023 | R16
167333312065 | 165383312065 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-23 | 2023-01-23 | 2023-03-10 |  | 2023-08-09 | Underground | R16 | 2023-04-20 | 1 | 35 | 30 | 80 | 143 | 2023 | 2023 | R16
166782285705 | 165206285705 | AGRICULTURAL | OH R16 RES NON RES OS | Commercial | 2021-08-01 | 2022-07-12 | 2022-07-15 |  | 2022-10-21 | Overhead | R16 |  | 247 | 4 |  |  | 320 | 2021 | 2022 | R16
165888266964 | 165120266964 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-12-10 | 2021-12-10 | 2022-01-31 |  | 2022-05-05 | Overhead | R16 |  | 1 | 37 |  |  | 105 | 2021 | 2022 | R16
165981265242 | 163875265242 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-12-06 | 2021-12-06 | 2022-01-19 |  | 2022-02-18 | Overhead | R16 | 2022-01-20 | 1 | 33 | 2 | 22 | 55 | 2021 | 2022 | R16
168248244000 | 168806244000 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2021-08-16 | 2021-08-16 | 2021-08-16 |  | 2021-09-10 | Overhead | R16 | 2021-08-17 | 1 |  | 2 | 19 | 20 | 2021 | 2021 | R16
165550313645 | 168845313645 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-03-24 | 2023-03-24 | 2023-03-24 |  | 2023-07-28 | Overhead | R16 | 2023-03-28 | 1 |  | 3 | 89 | 91 | 2023 | 2023 | R16
168791310002 | 169765310002 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-10 | 2023-02-13 | 2023-02-22 |  | 2023-08-14 | Underground | R16 | 2023-03-23 | 2 | 8 | 22 | 103 | 132 | 2023 | 2023 | R16
166083226092 | 168484226092 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-04 | 2021-03-04 | 2021-04-08 |  | 2021-11-05 | Underground | R16 | 2021-05-10 | 1 | 26 | 23 | 130 | 177 | 2021 | 2021 | R16
169603242029 | 165872242029 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-04 | 2021-08-04 | 2021-08-04 | 2021-09-15 | 2021-11-09 | Overhead | R16 | 2021-09-15 | 1 |  | 31 | 40 | 70 | 2021 | 2021 | R16
162047315982 | 168932315982 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-24 | 2023-03-24 | 2023-04-15 |  | 2023-08-18 | Overhead | R16 | 2023-05-02 | 1 | 16 | 12 | 79 | 106 | 2023 | 2023 | R16
162445312011 | 160320312011 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-13 | 2023-02-13 | 2023-03-10 | 2023-05-04 | 2023-08-17 | Underground | R16 | 2023-05-04 | 1 | 20 | 40 | 76 | 134 | 2023 | 2023 | R16
168586310106 | 160755310106 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-15 | 2023-02-22 | 2023-02-22 |  | 2023-09-05 | Underground | R16 | 2023-05-01 | 6 |  | 49 | 92 | 145 | 2023 | 2023 | R16
163565317719 | 161805317719 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-21 | 2023-02-21 | 2023-05-02 |  | 2023-06-07 | Underground | R16 | 2023-05-10 | 1 | 51 | 7 | 21 | 77 | 2023 | 2023 | R16
163315316138 | 164334316138 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-18 | 2023-04-18 | 2023-04-18 | 2023-05-04 | 2023-06-13 | Overhead | R16 | 2023-05-04 | 1 |  | 13 | 29 | 41 | 2023 | 2023 | R16
166129219061 | 160912219061 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-29 | 2021-01-29 | 2021-01-29 |  | 2021-05-06 | Overhead | R16 | 2021-02-18 | 1 |  | 15 | 56 | 70 | 2021 | 2021 | R16
165425251944 | 165429251944 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2021-09-14 | 2021-10-13 | 2021-10-13 |  | 2021-11-10 | Underground | R16 | 2021-10-14 | 22 |  | 2 | 20 | 42 | 2021 | 2021 | R16
165081304344 | 169977304344 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-28 | 2022-12-28 | 2023-01-30 | 2022-12-28 | 2023-03-31 | Overhead | R16 | 2022-12-28 | 1 | 24 |  | 68 | 68 | 2022 | 2023 | R16
167180333555 | 169091333555 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-05 | 2023-07-05 | 2023-09-25 | 2023-11-21 | 2023-11-28 | Underground | R16 | 2023-11-21 | 1 | 59 | 42 | 6 | 105 | 2023 | 2023 | R16
160779317588 | 161024317588 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-03 | 2023-04-03 | 2023-05-01 | 2023-06-23 | 2023-06-29 | Underground | R16 | 2023-06-23 | 1 | 21 | 40 | 5 | 64 | 2023 | 2023 | R16
166390252639 | 160752252639 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2021-10-07 | 2021-10-07 | 2021-10-18 |  | 2022-02-22 | Underground | R16 |  | 1 | 8 |  |  | 99 | 2021 | 2022 | R16
160993247007 | 164183247007 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-09-09 | 2021-09-09 | 2021-09-09 | 2023-02-23 | 2023-03-17 | Overhead | R16 | 2023-02-23 | 1 |  | 381 | 17 | 397 | 2021 | 2023 | R16
165622324856 | 166973324856 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-22 | 2023-06-22 | 2023-07-13 | 2023-07-18 | 2023-08-23 | Overhead | R16 | 2023-07-18 | 1 | 16 | 4 | 27 | 45 | 2023 | 2023 | R16
166544309598 | 168233309598 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-03 | 2023-02-17 | 2023-02-17 |  | 2023-07-12 | Overhead | R16 | 2023-07-12 | 11 |  | 104 |  | 114 | 2023 | 2023 | R16
160697313835 | 162721313835 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-02-24 | 2023-03-28 | 2023-03-28 |  | 2023-08-14 | Overhead | R16 | 2023-04-24 | 23 |  | 20 | 81 | 122 | 2023 | 2023 | R16
165463305485 | 162423305485 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-10 | 2023-01-10 | 2023-01-30 | 2023-01-10 | 2023-08-15 | Overhead | R16 | 2023-01-10 | 1 | 15 |  | 156 | 156 | 2023 | 2023 | R16
168584314305 | 160473314305 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-30 | 2023-03-30 | 2023-03-30 | 2023-04-12 | 2023-04-13 | Overhead | R16 | 2023-04-12 | 1 |  | 10 | 2 | 11 | 2023 | 2023 | R16
160197312728 | 164176312728 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-03 | 2023-03-16 | 2023-03-16 |  | 2023-08-14 | Overhead | R16 | 2023-04-05 | 10 |  | 15 | 94 | 117 | 2023 | 2023 | R16
161476307768 | 167260307768 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-01-31 | 2023-01-31 | 2023-01-31 | 2023-03-30 | 2023-03-31 | Overhead | R16 | 2023-03-30 | 1 |  | 43 | 2 | 44 | 2023 | 2023 | R16
166057333362 | 167369333362 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2023-06-26 | 2023-06-26 | 2023-09-21 | 2023-12-06 | 2023-12-11 | Underground | R16 | 2023-12-06 | 1 | 64 | 55 | 4 | 121 | 2023 | 2023 | R16
164063247557 | 164160247557 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-07-28 | 2021-07-28 | 2021-09-14 | 2021-10-17 | 2021-10-19 | Underground | R16 | 2021-10-17 | 1 | 35 | 24 | 2 | 60 | 2021 | 2021 | R16
166748221547 | 163272221547 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-09 | 2021-02-24 | 2021-02-24 |  | 2021-11-04 | Overhead | R16 | 2021-04-06 | 12 |  | 30 | 153 | 193 | 2021 | 2021 | R16
166591245720 | 160560245720 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-08-22 | 2021-08-22 | 2021-08-27 |  | 2022-01-18 | Underground | R16 | 2021-12-08 | 0 | 5 | 74 | 30 | 107 | 2021 | 2022 | R16
160310321362 | 169567321362 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-03-28 | 2023-04-10 | 2023-06-05 | 2023-08-10 | 2023-06-14 | Overhead | R16 | 2023-08-10 | 10 | 41 | 49 |  | 57 | 2023 | 2023 | R16
169009246053 | 169733246053 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-18 | 2021-08-18 | 2021-08-31 | 2023-02-23 | 2023-03-17 | Underground | R16 | 2023-02-23 | 1 | 10 | 388 | 17 | 413 | 2021 | 2023 | R16
169288312432 | 166940312432 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-30 | 2023-03-14 | 2023-03-14 | 2023-05-23 | 2023-07-18 | Overhead | R16 | 2023-05-23 | 32 |  | 51 | 41 | 122 | 2023 | 2023 | R16
161999314332 | 169154314332 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-27 | 2023-03-27 | 2023-03-31 | 2023-07-10 | 2023-09-11 | Overhead | R16 | 2023-07-10 | 1 | 5 | 72 | 46 | 121 | 2023 | 2023 | R16
166885222119 | 167664222119 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-02 | 2021-03-02 | 2021-03-02 |  | 2021-11-09 | Overhead | R16 | 2021-04-28 | 1 |  | 42 | 140 | 181 | 2021 | 2021 | R16
163102309653 | 161357309653 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-17 | 2023-02-17 | 2023-02-17 |  | 2023-05-16 | Overhead | R16 | 2023-03-07 | 1 |  | 13 | 51 | 63 | 2023 | 2023 | R16
165432303200 | 167640303200 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-12 | 2022-12-13 | 2022-12-21 | 2023-02-21 | 2023-03-03 | Overhead | R16 | 2023-02-21 | 2 | 7 | 45 | 9 | 60 | 2022 | 2023 | R16
166312307618 | 165480307618 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-23 | 2023-01-31 | 2023-01-31 | 2023-02-14 | 2023-07-28 | Overhead | R16 | 2023-02-14 | 7 |  | 11 | 119 | 135 | 2023 | 2023 | R16
163319313080 | 163607313080 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-01 | 2023-03-01 | 2023-03-20 | 2023-09-21 | 2023-10-09 | Overhead | R16 | 2023-09-21 | 1 | 14 | 134 | 13 | 159 | 2023 | 2023 | R16
167178317387 | 163731317387 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-14 | 2023-04-29 | 2023-04-29 |  | 2023-07-12 | Overhead | R16 | 2023-05-26 | 11 |  | 20 | 34 | 64 | 2023 | 2023 | R16
164013310971 | 163368310971 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-28 | 2023-02-28 | 2023-02-28 | 2023-04-12 | 2023-04-20 | Overhead | R16 | 2023-04-12 | 1 |  | 32 | 7 | 38 | 2023 | 2023 | R16
161245333861 | 161121333861 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-16 | 2023-02-16 | 2023-09-27 | 2023-10-29 | 2023-11-01 | Overhead | R16 | 2023-10-29 | 1 | 160 | 23 | 3 | 185 | 2023 | 2023 | R16
161496304598 | 160820304598 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-03 |  | 2023-01-30 | 2023-02-15 | 2023-03-24 | Overhead | R16 | 2023-02-15 |  |  | 13 | 28 | 59 | 2023 | 2023 | R16
166520317827 | 166037317827 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-04-26 | 2023-04-26 | 2023-05-03 |  | 2023-10-13 | Overhead | R16 |  | 1 | 6 |  |  | 123 | 2023 | 2023 | R16
168122306807 | 160823306807 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-04 | 2023-01-23 | 2023-01-30 | 2023-01-23 | 2023-06-19 | Overhead | R16 | 2023-01-23 | 14 | 6 |  | 106 | 119 | 2023 | 2023 | R16
162638312683 | 164943312683 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-03-06 | 2023-03-16 | 2023-03-16 | 2023-08-01 | 2023-08-10 | Underground | R16 | 2023-08-01 | 9 |  | 99 | 8 | 114 | 2023 | 2023 | R16
161906242275 | 166379242275 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-05 | 2021-08-05 | 2021-08-05 | 2021-09-28 | 2021-11-09 | Overhead | R16 | 2021-09-28 | 1 |  | 39 | 31 | 69 | 2021 | 2021 | R16
168670318878 | 162570318878 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-10 | 2023-01-19 | 2023-05-12 |  | 2023-12-08 | Overhead | R16 | 2023-11-30 | 8 | 82 | 145 | 7 | 239 | 2023 | 2023 | R16
165636321314 | 160209321314 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-30 | 2023-06-06 | 2023-06-06 | 2023-07-13 | 2023-07-14 | Overhead | R16 | 2023-07-13 | 49 |  | 28 | 2 | 77 | 2023 | 2023 | R16
166248247070 | 164285247070 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-09 | 2021-09-09 | 2021-09-09 | 2021-09-15 | 2021-11-17 | Underground | R16 | 2021-09-15 | 1 |  | 5 | 46 | 50 | 2021 | 2021 | R16
162331308451 | 164066308451 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-17 | 2023-01-17 | 2023-02-06 | 2023-03-10 | 2023-08-02 | Underground | R16 | 2023-03-10 | 1 | 15 | 25 | 104 | 142 | 2023 | 2023 | R16
166758319919 | 161171319919 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-23 | 2023-05-23 | 2023-05-23 | 2023-09-11 | 2023-10-12 | Overhead | R16 | 2023-09-11 | 1 |  | 80 | 24 | 103 | 2023 | 2023 | R16
167331221373 | 165796221373 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-22 | 2021-02-23 | 2021-02-23 |  | 2021-08-11 | Overhead | R16 | 2021-06-30 | 2 |  | 92 | 31 | 123 | 2021 | 2021 | R16
166669245054 | 161288245054 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-09-20 | 2021-11-13 | Overhead | R16 | 2021-09-20 | 1 |  | 19 | 40 | 58 | 2021 | 2021 | R16
165127311198 | 164169311198 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-02 | 2023-03-02 | 2023-03-02 |  | 2023-08-08 | Overhead | R16 | 2023-04-20 | 1 |  | 36 | 79 | 114 | 2023 | 2023 | R16
169983318292 | 165875318292 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-26 | 2023-04-26 | 2023-05-08 |  | 2023-10-02 | Underground | R16 | 2023-06-22 | 1 | 9 | 34 | 73 | 114 | 2023 | 2023 | R16
164809313181 | 167311313181 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-18 | 2023-03-21 | 2023-03-21 |  | 2023-08-09 | Overhead | R16 | 2023-04-06 | 2 |  | 13 | 90 | 103 | 2023 | 2023 | R16
166090307256 | 165447307256 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-23 | 2023-01-23 | 2023-01-26 |  | 2023-05-17 | Underground | R16 | 2023-02-21 | 1 | 4 | 19 | 62 | 83 | 2023 | 2023 | R16
166407246803 | 163642246803 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-07 | 2021-09-07 | 2021-09-07 |  | 2022-01-04 | Overhead | R16 | 2021-11-22 | 1 |  | 55 | 32 | 86 | 2021 | 2022 | R16
163900251956 | 161535251956 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-08-27 | 2021-09-22 | 2021-10-14 | 2021-11-03 | 2022-03-03 | Underground | R16 | 2021-11-03 | 19 | 17 | 15 | 87 | 135 | 2021 | 2022 | R16
160119255809 | 168086255809 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2021-08-12 | 2021-08-12 | 2021-11-09 | 2022-10-11 | 2022-10-24 | Underground | R16 | 2022-10-11 | 1 | 64 | 241 | 10 | 313 | 2021 | 2022 | R16
169142241644 | 165426241644 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-02 | 2021-08-02 | 2021-08-02 | 2021-10-07 | 2021-11-18 | Overhead | R16 | 2021-10-07 | 1 |  | 49 | 31 | 79 | 2021 | 2021 | R16
162603309373 | 169201309373 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-08 | 2023-02-08 | 2023-02-14 |  | 2023-05-16 | Overhead | R16 | 2023-02-28 | 1 | 5 | 11 | 56 | 70 | 2023 | 2023 | R16
167580225234 | 167054225234 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-02-26 | 2021-02-26 | 2021-03-30 |  | 2021-11-03 | Underground | R16 | 2021-06-18 | 1 | 23 | 59 | 99 | 179 | 2021 | 2021 | R16
166702308186 | 163212308186 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-11 | 2023-01-11 | 2023-02-02 |  | 2023-05-18 | Underground | R16 | 2023-04-18 | 1 | 17 | 54 | 23 | 92 | 2023 | 2023 | R16
166295246401 | 162974246401 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-02 | 2021-09-02 | 2021-09-02 | 2022-05-08 | 2022-05-11 | Underground | R16 | 2022-05-08 | 1 |  | 177 | 3 | 180 | 2021 | 2022 | R16
168755324712 | 167297324712 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2023-06-26 | 2023-06-27 | 2023-07-10 | 2023-12-01 | 2023-12-19 | Underground | R16 | 2023-12-01 | 2 | 10 | 105 | 13 | 127 | 2023 | 2023 | R16
160010312601 | 166670312601 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-15 | 2023-03-15 | 2023-03-15 |  | 2023-08-22 | Overhead | R16 | 2023-04-17 | 1 |  | 24 | 92 | 115 | 2023 | 2023 | R16
161969314287 | 160491314287 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-30 | 2023-03-30 | 2023-03-30 |  | 2023-06-01 | Overhead | R16 | 2023-04-04 | 1 |  | 4 | 43 | 46 | 2023 | 2023 | R16
167605320433 | 169635320433 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-28 | 2023-03-28 | 2023-05-26 | 2023-07-26 | 2023-08-15 | Underground | R16 | 2023-07-26 | 1 | 44 | 44 | 15 | 101 | 2023 | 2023 | R16
161119321041 | 162949321041 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-02 | 2023-06-02 | 2023-06-02 | 2023-12-08 | 2023-12-11 | Underground | R16 | 2023-12-08 | 1 |  | 136 | 2 | 137 | 2023 | 2023 | R16
165898246060 | 166843246060 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-09 | 2021-08-31 | 2021-08-31 |  | 2021-10-25 | Overhead | R16 | 2021-09-15 | 17 |  | 12 | 29 | 56 | 2021 | 2021 | R16
161969315587 | 168746315587 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-02-06 | 2023-02-14 | 2023-04-12 | 2023-06-16 | 2023-07-25 | Underground | R16 | 2023-06-16 | 7 | 42 | 48 | 28 | 122 | 2023 | 2023 | R16
165791333231 | 163883333231 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-06-07 | 2023-06-07 | 2023-09-21 | 2023-10-11 | 2023-10-13 | Underground | R16 | 2023-10-11 | 1 | 77 | 15 | 3 | 93 | 2023 | 2023 | R16
165645245103 | 161020245103 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-24 | 2021-08-24 | 2021-08-24 |  | 2021-11-18 | Overhead | R16 | 2021-10-27 | 1 |  | 47 | 17 | 63 | 2021 | 2021 | R16
169937317883 | 167580317883 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-03 | 2023-05-03 | 2023-05-03 | 2023-07-11 | 2023-07-31 | Overhead | R16 | 2023-07-11 | 1 |  | 50 | 15 | 64 | 2023 | 2023 | R16
165345241741 | 164648241741 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Residential | 2021-07-29 | 2021-07-29 | 2021-08-02 | 2021-09-20 | 2021-10-06 | Overhead | R16 | 2021-09-20 | 1 | 3 | 36 | 13 | 50 | 2021 | 2021 | R16
166919312558 | 166855312558 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-07-24 | 2023-07-25 | Overhead | R16 | 2023-07-24 | 1 |  | 93 | 2 | 94 | 2023 | 2023 | R16
168265218532 | 169644218532 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-01-26 | 2021-01-26 | 2021-01-26 |  | 2021-08-03 | Overhead | R16 | 2021-03-29 | 1 |  | 45 | 92 | 136 | 2021 | 2021 | R16
169929319002 | 169327319002 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-12 | 2023-05-12 | 2023-05-12 | 2023-05-17 | 2023-06-14 | Overhead | R16 | 2023-05-17 | 1 |  | 4 | 21 | 24 | 2023 | 2023 | R16
168277220059 | 163259220059 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-10 | 2021-02-10 | 2021-02-10 |  | 2022-10-18 | Overhead | R16 |  | 1 |  |  |  | 440 | 2021 | 2022 | R16
165430241399 | 164508241399 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-29 | 2021-07-30 | 2021-07-30 |  | 2021-11-08 | Underground | R16 | 2021-09-20 | 2 |  | 37 | 36 | 73 | 2021 | 2021 | R16
168575255157 | 160834255157 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2021-08-23 | 2021-10-07 | 2021-11-05 | 2022-04-22 | 2022-05-16 | Underground | R16 | 2022-04-22 | 34 | 22 | 121 | 17 | 191 | 2021 | 2022 | R16
162137339937 | 166035339937 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-04-26 | 2023-04-26 | 2023-11-16 | 2023-12-11 | 2023-12-15 | Underground | R16 | 2023-12-11 | 1 | 147 | 18 | 5 | 168 | 2023 | 2023 | R16
161012316418 | 160202316418 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-13 | 2023-02-13 | 2023-04-20 | 2023-09-19 | 2023-10-03 | Underground | R16 | 2023-09-19 | 1 | 49 | 109 | 11 | 167 | 2023 | 2023 | R16
163841328480 | 165451328480 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-14 | 2023-06-14 | 2023-08-15 | 2023-10-26 | 2023-11-01 | Underground | R16 | 2023-10-26 | 1 | 45 | 53 | 5 | 101 | 2023 | 2023 | R16
162996312228 | 166038312228 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-13 | 2023-03-13 | 2023-03-13 | 2023-04-27 | 2023-05-08 | Overhead | R16 | 2023-04-27 | 1 |  | 34 | 8 | 41 | 2023 | 2023 | R16
168438235209 | 165044235209 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-04-01 | 2021-04-15 | 2021-06-16 |  | 2021-11-30 | Underground | R16 | 2021-11-03 | 11 | 45 | 101 | 20 | 174 | 2021 | 2021 | R16
164892244647 | 160438244647 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-30 | 2021-10-25 | Overhead | R16 | 2021-08-30 | 1 |  | 7 | 41 | 47 | 2021 | 2021 | R16
164296244896 | 160760244896 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-23 | 2021-08-23 | 2021-08-23 | 2021-10-07 | 2021-11-15 | Overhead | R16 | 2021-10-07 | 1 |  | 34 | 28 | 61 | 2021 | 2021 | R16
167737304907 | 169719304907 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-12-27 | 2022-12-27 | 2023-01-04 |  | 2023-03-24 | Overhead | R16 |  | 1 | 7 |  |  | 64 | 2022 | 2023 | R16
167436323411 | 165104323411 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2023-06-13 | 2023-06-14 | 2023-06-28 | 2023-07-28 | 2023-08-21 | Overhead | R16 | 2023-07-28 | 2 | 11 | 23 | 17 | 50 | 2023 | 2023 | R16
167619314171 | 167576314171 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-03-20 | 2023-03-20 | 2023-03-30 | 2023-04-24 | 2023-05-17 | Underground | R16 | 2023-04-24 | 1 | 9 | 18 | 18 | 43 | 2023 | 2023 | R16
168633247144 | 162071247144 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-08-29 | 2021-08-29 | 2021-09-09 |  | 2023-01-05 | Underground | R16 | 2022-10-12 | 0 | 9 | 285 | 62 | 354 | 2021 | 2023 | R16
164067322239 | 165553322239 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-15 | 2023-06-15 | 2023-06-15 | 2023-08-04 | 2023-10-26 | Overhead | R16 | 2023-08-04 | 1 |  | 37 | 60 | 96 | 2023 | 2023 | R16
162515247024 | 164063247024 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-08 | 2021-09-08 | 2021-09-08 | 2021-11-08 | 2022-02-01 | Overhead | R16 | 2021-11-08 | 1 |  | 44 | 62 | 105 | 2021 | 2022 | R16
167996320913 | 162264320913 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-05-30 | 2023-06-02 | 2023-06-02 |  | 2023-06-29 | Overhead | R16 | 2023-06-23 | 4 |  | 16 | 5 | 23 | 2023 | 2023 | R16
168670245031 | 166712245031 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-25 | 2021-02-25 | 2021-08-25 |  | 2023-02-06 | Underground | R16 | 2022-12-08 | 1 | 130 | 337 | 43 | 508 | 2021 | 2023 | R16
160967254884 | 167059254884 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-08-10 | 2021-10-22 | 2021-11-03 |  | 2022-07-25 | Overhead | R16 |  | 54 | 9 |  |  | 250 | 2021 | 2022 | R16
164150316869 | 165259316869 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-21 | 2023-04-24 | 2023-04-25 | 2023-06-23 | 2023-06-26 | Overhead | R16 | 2023-06-23 | 2 | 2 | 44 | 2 | 47 | 2023 | 2023 | R16
167225322339 | 165747322339 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-16 | 2023-06-16 | 2023-06-16 | 2023-09-27 | 2023-10-20 | Overhead | R16 | 2023-09-27 | 1 |  | 74 | 18 | 91 | 2023 | 2023 | R16
161812247583 | 164968247583 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-13 | 2021-09-13 | 2021-09-13 |  | 2021-12-02 | Underground | R16 | 2021-11-09 | 1 |  | 42 | 18 | 59 | 2021 | 2021 | R16
162890247813 | 165428247813 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-14 | 2021-09-14 | 2021-09-14 |  | 2021-11-02 | Overhead | R16 | 2021-10-12 | 1 |  | 21 | 16 | 36 | 2021 | 2021 | R16
160137315847 | 167647315847 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-20 | 2023-04-14 | 2023-04-14 | 2023-05-17 | 2023-06-12 | Overhead | R16 | 2023-05-17 | 20 |  | 24 | 19 | 61 | 2023 | 2023 | R16
160720314364 | 167667314364 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-20 | 2023-03-31 | 2023-03-31 | 2023-04-24 | 2023-06-12 | Overhead | R16 | 2023-04-24 | 10 |  | 17 | 36 | 61 | 2023 | 2023 | R16
164993320012 | 161421320012 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-23 | 2023-05-23 | 2023-05-23 | 2023-07-16 | 2023-07-20 | Overhead | R16 | 2023-07-16 | 1 |  | 39 | 4 | 43 | 2023 | 2023 | R16
163332325962 | 163897325962 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-07 | 2023-06-07 | 2023-07-22 | 2023-07-26 | 2023-08-02 | Underground | R16 | 2023-07-26 | 1 | 33 | 3 | 6 | 41 | 2023 | 2023 | R16
168538313078 | 167764313078 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-21 | 2023-03-21 | 2023-03-21 | 2023-06-21 | 2023-07-06 | Underground | R16 | 2023-06-21 | 1 |  | 67 | 12 | 78 | 2023 | 2023 | R16
163516317453 | 164540317453 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-18 | 2023-05-01 | 2023-05-01 | 2023-05-03 | 2023-06-13 | Overhead | R16 | 2023-05-03 | 10 |  | 3 | 30 | 41 | 2023 | 2023 | R16
162566245472 | 169658245472 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-18 | 2021-08-19 | 2021-08-27 | 2021-10-07 | 2021-10-07 | Underground | R16 | 2021-10-07 | 2 | 7 | 30 |  | 37 | 2021 | 2021 | R16
161740332401 | 167774332401 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-27 | 2023-06-27 | 2023-09-12 | 2023-11-17 | 2023-11-22 | Overhead | R16 | 2023-11-17 | 1 | 56 | 49 | 4 | 107 | 2023 | 2023 | R16
168027309884 | 168914309884 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-07 | 2023-02-08 | 2023-02-21 | 2023-03-28 | 2023-04-05 | Overhead | R16 | 2023-03-28 | 2 | 10 | 26 | 7 | 42 | 2023 | 2023 | R16
165740312271 | 166149312271 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2023-03-13 | 2023-03-13 | 2023-03-13 | 2023-08-02 | 2023-08-09 | Underground | R16 | 2023-08-02 | 1 |  | 103 | 6 | 108 | 2023 | 2023 | R16
162527248784 | 167258248784 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-10 | 2021-08-10 | 2021-09-21 |  | 2023-06-28 | Underground | R16 | 2023-06-05 | 1 | 31 | 445 | 18 | 492 | 2021 | 2023 | R16
168975318306 | 165900318306 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Commercial | 2023-04-25 | 2023-05-04 | 2023-05-08 | 2023-06-05 | 2023-07-03 | Overhead | R16 | 2023-06-05 | 8 | 3 | 21 | 21 | 50 | 2023 | 2023 | R16
166905322104 | 165077322104 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-13 | 2023-06-13 | 2023-06-13 | 2023-06-14 | 2023-07-19 | Underground | R16 | 2023-06-14 | 1 |  | 2 | 26 | 27 | 2023 | 2023 | R16
169591242110 | 165811242110 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-03 | 2021-08-04 | 2021-08-04 |  | 2021-10-25 | Overhead | R16 | 2021-08-26 | 2 |  | 17 | 43 | 60 | 2021 | 2021 | R16
167495317715 | 167119317715 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-02 | 2023-05-02 | 2023-05-02 | 2023-06-29 | 2023-07-14 | Overhead | R16 | 2023-06-29 | 1 |  | 43 | 12 | 54 | 2023 | 2023 | R16
161302321426 | 161657321426 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-25 | 2023-05-25 | 2023-06-06 | 2023-08-09 | 2023-08-09 | Underground | R16 | 2023-08-09 | 1 | 9 | 47 |  | 55 | 2023 | 2023 | R16
168175310641 | 169236310641 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-09 | 2023-02-24 | 2023-02-24 | 2023-04-30 | 2023-05-09 | Underground | R16 | 2023-04-30 | 12 |  | 46 | 7 | 64 | 2023 | 2023 | R16
162161309517 | 160975309517 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-16 | 2023-02-16 | 2023-02-16 | 2023-04-28 | 2023-06-12 | Overhead | R16 | 2023-04-28 | 1 |  | 52 | 32 | 83 | 2023 | 2023 | R16
162650243722 | 166840243722 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-08 | 2021-08-08 | 2021-08-13 | 2021-11-30 | 2022-01-13 | Underground | R16 | 2021-11-30 | 0 | 5 | 78 | 33 | 114 | 2021 | 2022 | R16
163922244076 | 166701244076 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-06 | 2021-08-06 | 2021-08-18 |  | 2021-11-10 | Underground | R16 | 2021-10-14 | 1 | 9 | 42 | 20 | 69 | 2021 | 2021 | R16
169387224067 | 163073224067 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-09 | 2021-02-09 | 2021-03-17 |  | 2021-09-13 | Overhead | R16 | 2021-08-18 | 1 | 27 | 111 | 19 | 155 | 2021 | 2021 | R16
166914246566 | 160593246566 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-23 | 2021-08-23 | 2021-09-03 |  | 2022-03-01 | Underground | R16 | 2022-01-27 | 1 | 10 | 105 | 24 | 137 | 2021 | 2022 | R16
167728308656 | 161285308656 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-05 | 2023-01-05 | 2023-02-07 | 2023-07-17 | 2023-07-19 | Underground | R16 | 2023-07-17 | 1 | 24 | 115 | 3 | 140 | 2023 | 2023 | R16
162223242946 | 167225242946 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2021-09-10 | 2021-10-28 | Underground | R16 | 2021-09-10 | 1 |  | 24 | 35 | 58 | 2021 | 2021 | R16
164562325021 | 168704325021 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-30 | 2023-07-13 | 2023-07-13 |  | 2023-09-27 | Overhead | R16 | 2023-08-17 | 10 |  | 26 | 30 | 64 | 2023 | 2023 | R16
164864315462 | 163841315462 | NON-RESIDENTIAL - MISCELLANEOUS | UG ELEC MISC SVC US | Commercial | 2023-03-01 | 2023-04-07 | 2023-04-11 |  | 2023-10-02 | Underground | R16 |  | 28 | 3 |  |  | 154 | 2023 | 2023 | R16
160574247380 | 164684247380 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-10 | 2021-09-10 | 2021-09-10 | 2021-11-04 | 2021-12-02 | Overhead | R16 | 2021-11-04 | 1 |  | 40 | 21 | 60 | 2021 | 2021 | R16
168543317803 | 169706317803 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-28 |  | 2023-03-28 | 2023-07-10 | 2023-08-02 | Underground | R16 | 2023-07-10 |  |  | 75 | 18 | 92 | 2023 | 2023 | R16
168184312609 | 166669312609 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-15 | 2023-03-15 | 2023-03-15 |  | 2023-07-24 | Overhead | R16 | 2023-03-28 | 1 |  | 10 | 85 | 94 | 2023 | 2023 | R16
169598308141 | 167923308141 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-02 | 2023-02-02 | 2023-02-02 | 2023-03-09 | 2023-03-10 | Overhead | R16 | 2023-03-09 | 1 |  | 26 | 2 | 27 | 2023 | 2023 | R16
169429317976 | 161598317976 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-21 | 2023-02-21 | 2023-05-04 | 2023-06-18 | 2023-06-21 | Overhead | R16 | 2023-06-18 | 1 | 53 | 32 | 3 | 87 | 2023 | 2023 | R16
161358253597 | 164356253597 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-09 | 2021-10-26 | 2021-10-26 | 2022-03-02 | 2022-03-04 | Overhead | R16 | 2022-03-02 | 34 |  | 92 | 3 | 127 | 2021 | 2022 | R16
161284322503 | 165787322503 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-16 | 2023-06-16 | 2023-06-16 | 2023-08-07 | 2023-08-08 | Overhead | R16 | 2023-08-07 | 1 |  | 37 | 2 | 38 | 2023 | 2023 | R16
160439314929 | 167806314929 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2023-03-21 | 2023-03-21 | 2023-04-06 |  | 2023-06-06 | Underground | R16 | 2023-05-25 | 1 | 13 | 36 | 9 | 56 | 2023 | 2023 | R16
160170221888 | 165388221888 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-19 | 2021-02-27 | 2021-02-27 |  | 2021-11-11 | Overhead | R16 | 2021-04-19 | 6 |  | 36 | 149 | 190 | 2021 | 2021 | R16
166418331261 | 160323331261 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-11 | 2023-07-11 | 2023-08-30 | 2023-10-09 | 2023-10-16 | Underground | R16 | 2023-10-09 | 1 | 37 | 29 | 6 | 70 | 2023 | 2023 | R16
167157319943 | 169158319943 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-11 | 2023-05-22 | 2023-05-22 | 2023-08-01 | 2023-08-21 | Overhead | R16 | 2023-08-01 | 8 |  | 52 | 15 | 73 | 2023 | 2023 | R16
169261259804 | 166851259804 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-09 | 2021-10-12 | 2021-12-03 | 2022-09-07 | 2022-11-15 | Underground | R16 | 2022-09-07 | 47 | 39 | 199 | 50 | 332 | 2021 | 2022 | R16
164036247649 | 164639247649 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-09-10 | 2021-09-13 | 2021-09-13 | 2021-12-03 | 2021-12-06 | Underground | R16 | 2021-12-03 | 2 |  | 60 | 2 | 62 | 2021 | 2021 | R16
161800304286 | 169990304286 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-28 |  | 2023-01-30 | 2023-04-04 | 2023-04-18 | Underground | R16 | 2023-04-04 |  |  | 47 | 11 | 80 | 2022 | 2023 | R16
167738318760 | 169022318760 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-10 | 2023-05-10 | 2023-05-10 |  | 2023-10-02 | Overhead | R16 | 2023-06-14 | 1 |  | 26 | 79 | 104 | 2023 | 2023 | R16
164724242909 | 167165242909 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-10 | 2021-08-10 | 2021-08-10 |  | 2021-10-25 | Overhead | R16 | 2021-09-08 | 1 |  | 22 | 34 | 55 | 2021 | 2021 | R16
162650316023 | 163423316023 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-13 | 2023-04-17 | 2023-04-17 | 2023-05-16 | 2023-05-17 | Overhead | R16 | 2023-05-16 | 3 |  | 22 | 2 | 25 | 2023 | 2023 | R16
167438313644 | 164695313644 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-06 | 2023-03-06 | 2023-03-24 |  | 2023-08-22 | Underground | R16 | 2023-05-24 | 1 | 15 | 44 | 65 | 122 | 2023 | 2023 | R16
162717323505 | 166925323505 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-22 | 2023-06-22 | 2023-06-27 | 2023-07-24 | 2023-07-25 | Overhead | R16 | 2023-07-24 | 1 | 4 | 20 | 2 | 24 | 2023 | 2023 | R16
166997248553 | 168784248553 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-16 | 2021-08-16 | 2021-09-20 | 2021-11-17 | 2021-11-18 | Underground | R16 | 2021-11-17 | 1 | 26 | 43 | 2 | 69 | 2021 | 2021 | R16
168549311380 | 160798311380 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-15 | 2023-02-16 | 2023-03-03 | 2023-07-28 | 2023-09-14 | Underground | R16 | 2023-07-28 | 2 | 12 | 106 | 35 | 152 | 2023 | 2023 | R16
166382305510 | 162936305510 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-11 | 2023-01-11 | 2023-01-11 | 2023-03-08 | 2023-03-09 | Overhead | R16 | 2023-03-08 | 1 |  | 41 | 2 | 42 | 2023 | 2023 | R16
164462267384 | 163967267384 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2021-07-27 | 2021-07-27 | 2022-02-03 | 2023-05-25 | 2023-07-03 | Underground | R16 | 2023-05-25 | 1 | 138 | 341 | 28 | 505 | 2021 | 2023 | R16
163821317690 | 166430317690 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-28 | 2023-04-28 | 2023-05-02 | 2023-05-08 | 2023-10-09 | Overhead | R16 | 2023-05-08 | 1 | 3 | 5 | 111 | 117 | 2023 | 2023 | R16
162341242671 | 166958242671 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-09 | 2021-08-09 | 2021-08-09 | 2021-10-07 | 2021-11-13 | Overhead | R16 | 2021-10-07 | 1 |  | 44 | 27 | 70 | 2021 | 2021 | R16
168787312421 | 161225312421 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-17 | 2023-03-14 | 2023-03-14 |  | 2023-08-18 | Overhead | R16 | 2023-04-12 | 18 |  | 22 | 93 | 131 | 2023 | 2023 | R16
168423317533 | 160112317533 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-29 | 2023-03-31 | 2023-05-01 | 2023-08-01 | 2023-09-07 | Underground | R16 | 2023-08-01 | 3 | 22 | 67 | 28 | 117 | 2023 | 2023 | R16
161206320042 | 161048320042 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2023-05-23 | 2023-05-23 | 2023-05-23 | 2023-06-13 | 2023-08-31 | Overhead | R16 | 2023-06-13 | 1 |  | 16 | 58 | 73 | 2023 | 2023 | R16
160709222821 | 160833222821 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-29 | 2021-01-29 | 2021-03-07 |  | 2021-11-08 | Underground | R16 | 2021-05-12 | 1 | 26 | 48 | 129 | 202 | 2021 | 2021 | R16
160037304421 | 160182304421 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-29 | 2022-12-29 | 2022-12-29 | 2022-12-29 | 2023-01-11 | Overhead | R16 | 2022-12-29 | 1 |  |  | 10 | 10 | 2022 | 2023 | R16
166478318529 | 167563318529 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-03 | 2023-05-10 | 2023-05-10 |  | 2023-07-13 | Underground | R16 | 2023-07-07 | 6 |  | 43 | 5 | 52 | 2023 | 2023 | R16
164519321505 | 163488321505 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-05 | 2023-06-06 | 2023-06-07 | 2023-10-17 | 2023-11-21 | Overhead | R16 | 2023-10-17 | 2 | 2 | 95 | 26 | 122 | 2023 | 2023 | R16
164048318049 | 167788318049 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-05-04 | 2023-05-04 | 2023-05-04 | 2023-05-24 | 2023-05-25 | Overhead | R16 | 2023-05-24 | 1 |  | 15 | 2 | 16 | 2023 | 2023 | R16
169212312406 | 165109312406 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2023-03-07 | 2023-03-07 | 2023-03-14 | 2023-10-10 | 2023-07-03 | Underground | R16 | 2023-10-10 | 1 | 6 | 151 |  | 85 | 2023 | 2023 | R16
167060242486 | 163974242486 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-27 | 2021-07-27 | 2021-08-06 |  | 2021-10-27 | Overhead | R16 | 2021-08-11 | 1 | 9 | 4 | 56 | 67 | 2021 | 2021 | R16
166746315034 | 163945315034 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-02 | 2023-03-02 | 2023-04-07 | 2023-06-07 | 2023-07-07 | Underground | R16 | 2023-06-07 | 1 | 27 | 44 | 23 | 92 | 2023 | 2023 | R16
168676323803 | 169673323803 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-02-10 | 2023-02-10 | 2023-06-30 | 2023-09-21 | 2023-09-22 | Underground | R16 | 2023-09-21 | 1 | 101 | 60 | 2 | 161 | 2023 | 2023 | R16
160584243846 | 165687243846 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-03 |  | 2021-08-16 | 2021-10-07 | 2021-11-15 | Overhead | R16 | 2021-10-07 |  |  | 39 | 28 | 75 | 2021 | 2021 | R16
166420308324 | 168320308324 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-03 | 2023-02-03 | 2023-02-03 |  | 2023-08-09 | Overhead | R16 | 2023-04-11 | 1 |  | 48 | 87 | 134 | 2023 | 2023 | R16
166395311948 | 165534311948 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-03-09 | 2023-03-09 | 2023-03-09 | 2023-04-28 | 2023-06-12 | Overhead | R16 | 2023-04-28 | 1 |  | 37 | 32 | 68 | 2023 | 2023 | R16
161725314512 | 161028314512 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-03 | 2023-04-03 | 2023-04-03 | 2023-04-04 | 2023-08-09 | Overhead | R16 | 2023-04-04 | 1 |  | 2 | 92 | 93 | 2023 | 2023 | R16
169442319356 | 166637319356 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-27 | 2023-01-27 | 2023-05-18 | 2023-08-01 | 2023-08-07 | Underground | R16 | 2023-08-01 | 1 | 80 | 54 | 5 | 137 | 2023 | 2023 | R16
161554221637 | 166977221637 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-26 | 2021-02-26 | 2021-02-26 |  | 2021-11-04 | Overhead | R16 | 2021-04-06 | 1 |  | 28 | 153 | 180 | 2021 | 2021 | R16
160394247202 | 163155247202 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-02 | 2021-09-09 | 2021-09-09 |  | 2021-11-10 | Overhead | R16 | 2021-10-18 | 6 |  | 28 | 18 | 50 | 2021 | 2021 | R16
166315319647 | 167117319647 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-02 | 2023-05-02 | 2023-05-19 |  | 2023-07-10 | Underground | R16 | 2023-06-08 | 1 | 14 | 15 | 23 | 50 | 2023 | 2023 | R16
164167242321 | 165283242321 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-02 | 2021-08-05 | 2021-08-05 |  | 2021-11-02 | Overhead | R16 | 2021-10-12 | 4 |  | 49 | 16 | 67 | 2021 | 2021 | R16
160423323141 | 164749323141 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-13 | 2023-06-20 | 2023-06-23 | 2023-07-27 | 2023-08-08 | Overhead | R16 | 2023-07-27 | 6 | 4 | 25 | 9 | 41 | 2023 | 2023 | R16
161080315608 | 168626315608 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-24 | 2023-03-24 | 2023-04-13 |  | 2023-08-22 | Overhead | R16 | 2023-04-14 | 1 | 15 | 2 | 93 | 108 | 2023 | 2023 | R16
161592258553 | 163296258553 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-10-18 | 2021-10-22 | 2021-11-23 |  | 2022-02-24 | Underground | R16 | 2022-02-04 | 5 | 23 | 54 | 15 | 94 | 2021 | 2022 | R16
161125305160 | 168553305160 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-16 | 2023-01-05 | 2023-01-30 | 2023-01-05 | 2023-03-31 | Overhead | R16 | 2023-01-05 | 15 | 18 |  | 62 | 76 | 2022 | 2023 | R16
161787316497 | 164954316497 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-20 | 2023-04-20 | 2023-04-20 |  | 2023-07-13 | Overhead | R16 | 2023-07-05 | 1 |  | 55 | 7 | 61 | 2023 | 2023 | R16
165415240840 | 163683240840 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-26 | 2021-07-26 | 2021-07-26 | 2021-10-26 | 2021-12-01 | Overhead | R16 | 2021-10-26 | 1 |  | 67 | 27 | 93 | 2021 | 2021 | R16
161617219824 | 162466219824 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-05 | 2021-02-05 | 2021-02-05 |  | 2021-11-05 | Underground | R16 | 2021-05-06 | 1 |  | 65 | 132 | 196 | 2021 | 2021 | R16
163995316260 | 164423316260 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-18 | 2023-04-18 | 2023-04-18 | 2023-05-30 | 2023-06-14 | Overhead | R16 | 2023-05-30 | 1 |  | 31 | 12 | 42 | 2023 | 2023 | R16
162796313468 | 169181313468 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-08 | 2023-02-08 | 2023-03-23 | 2023-09-13 | 2023-09-14 | Underground | R16 | 2023-09-13 | 1 | 32 | 125 | 2 | 157 | 2023 | 2023 | R16
166749323015 | 165963323015 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-19 | 2023-06-22 | 2023-06-22 | 2023-09-07 | 2023-11-29 | Overhead | R16 | 2023-09-07 | 4 |  | 56 | 60 | 118 | 2023 | 2023 | R16
161683221857 | 161638221857 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-02 | 2021-02-02 | 2021-02-27 |  | 2021-08-12 | Overhead | R16 | 2021-07-07 | 1 | 19 | 93 | 27 | 138 | 2021 | 2021 | R16
168104324509 | 169813324509 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2023-08-31 | 2023-10-12 | Overhead | R16 | 2023-08-31 | 0 |  | 39 | 31 | 69 | 2023 | 2023 | R16
168547305385 | 161171305385 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2023-01-04 | 2023-01-09 | 2023-01-30 | 2023-01-09 | 2023-03-27 | Overhead | R16 | 2023-01-09 | 4 | 16 |  | 56 | 59 | 2023 | 2023 | R16
165359307602 | 165425307602 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-23 | 2023-01-30 | 2023-01-30 |  | 2023-07-24 | Overhead | R16 | 2023-01-31 | 6 |  | 2 | 125 | 131 | 2023 | 2023 | R16
162654318962 | 169431318962 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-12 | 2023-05-12 | 2023-05-12 |  | 2023-07-14 | Overhead | R16 | 2023-06-22 | 1 |  | 30 | 17 | 46 | 2023 | 2023 | R16
161494309210 | 160121309210 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-13 |  | 2023-02-13 | 2023-04-03 | 2023-04-06 | Overhead | R16 | 2023-04-03 |  |  | 36 | 4 | 39 | 2023 | 2023 | R16
162202243527 | 166321243527 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-05 |  | 2021-08-13 | 2021-10-05 | 2021-11-09 | Overhead | R16 | 2021-10-05 |  |  | 38 | 26 | 69 | 2021 | 2021 | R16
167551318972 | 169329318972 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-12 | 2023-05-12 | 2023-05-12 | 2023-06-09 | 2023-07-17 | Overhead | R16 | 2023-06-09 | 1 |  | 21 | 27 | 47 | 2023 | 2023 | R16
168456330803 | 165642330803 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-24 | 2023-04-24 | 2023-08-25 | 2023-10-27 | 2023-11-06 | Underground | R16 | 2023-10-27 | 1 | 90 | 46 | 7 | 141 | 2023 | 2023 | R16
163825336204 | 163638336204 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-06 | 2023-06-09 | 2023-10-18 | 2023-10-30 | 2023-12-11 | Underground | R16 | 2023-10-30 | 4 | 94 | 9 | 31 | 135 | 2023 | 2023 | R16
161777223967 | 167247223967 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-01 | 2021-03-01 | 2021-03-17 |  | 2021-10-26 | Underground | R16 | 2021-04-08 | 1 | 13 | 17 | 144 | 172 | 2021 | 2021 | R16
162469317811 | 166458317811 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-28 | 2023-04-28 | 2023-05-03 | 2023-09-07 | 2023-09-15 | Overhead | R16 | 2023-09-07 | 1 | 4 | 92 | 7 | 101 | 2023 | 2023 | R16
161820221903 | 167153221903 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-26 | 2021-02-26 | 2021-02-26 |  | 2021-08-23 | Overhead | R16 | 2021-07-26 | 1 |  | 107 | 21 | 127 | 2021 | 2021 | R16
165845305862 | 161172305862 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-01-05 | 2023-01-05 | 2023-01-25 | 2023-01-13 | 2023-06-22 | Overhead | R16 | 2023-01-13 | 1 | 15 |  | 115 | 121 | 2023 | 2023 | R16
168292316873 | 167645316873 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-20 | 2023-03-20 | 2023-04-25 | 2023-06-14 | 2023-06-15 | Underground | R16 | 2023-06-14 | 1 | 27 | 37 | 2 | 64 | 2023 | 2023 | R16
166102305412 | 162361305412 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-09 | 2023-01-10 | 2023-01-30 | 2023-05-09 | 2023-06-09 | Underground | R16 | 2023-05-09 | 2 | 15 | 72 | 24 | 110 | 2023 | 2023 | R16
160660316879 | 163746316879 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-01 | 2023-04-26 | 2023-04-26 | 2023-05-04 | 2023-07-12 | Overhead | R16 | 2023-05-04 | 41 |  | 7 | 50 | 96 | 2023 | 2023 | R16
165211242856 | 167138242856 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2021-11-18 | 2022-09-29 | Overhead | R16 | 2021-11-18 | 1 |  | 73 | 226 | 298 | 2021 | 2022 | R16
164738323516 | 166546323516 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2023-06-21 | 2023-06-21 | 2023-06-28 |  | 2023-10-13 | Overhead | R16 |  | 1 | 6 |  |  | 83 | 2023 | 2023 | R16
160794303965 | 168831303965 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-19 | 2022-12-21 | 2022-12-22 | 2023-02-27 | 2023-03-07 | Underground | R16 | 2023-02-27 | 3 | 2 | 48 | 7 | 57 | 2022 | 2023 | R16
162040233063 | 169854233063 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-05-25 | 2021-06-01 | 2021-06-01 |  | 2021-10-27 | Overhead | R16 | 2021-08-11 | 6 |  | 52 | 56 | 112 | 2021 | 2021 | R16
162356324061 | 161803324061 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-21 | 2023-07-03 | 2023-07-03 | 2023-08-02 | 2023-08-17 | Overhead | R16 | 2023-08-02 | 95 |  | 23 | 12 | 128 | 2023 | 2023 | R16
165893320299 | 165386320299 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-01-23 | 2023-01-23 | 2023-05-25 | 2023-06-13 | 2023-08-16 | Overhead | R16 | 2023-06-13 | 1 | 89 | 14 | 47 | 148 | 2023 | 2023 | R16
162213221544 | 165863221544 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-22 | 2021-02-24 | 2021-02-24 |  | 2021-08-23 | Overhead | R16 | 2021-07-27 | 3 |  | 110 | 20 | 131 | 2021 | 2021 | R16
162742314623 | 161060314623 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-03 | 2023-04-03 | 2023-04-03 |  | 2023-08-09 | Overhead | R16 | 2023-04-03 | 1 |  |  | 93 | 93 | 2023 | 2023 | R16
169116305134 | 161795305134 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-05 | 2023-01-05 | 2023-01-05 | 2023-03-29 | 2023-12-07 | Overhead | R16 | 2023-03-29 | 1 |  | 60 | 182 | 241 | 2023 | 2023 | R16
166310325088 | 169310325088 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-07-05 | 2023-07-14 | 2023-07-14 | 2023-07-20 | 2023-08-25 | Overhead | R16 | 2023-07-20 | 8 |  | 5 | 27 | 38 | 2023 | 2023 | R16
161789249937 | 165233249937 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-13 | 2021-09-14 | 2021-09-29 | 2021-10-05 | 2021-11-30 | Underground | R16 | 2021-10-05 | 2 | 12 | 5 | 41 | 57 | 2021 | 2021 | R16
169140313015 | 162106313015 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2023-02-22 | 2023-02-27 | 2023-03-20 |  | 2023-07-26 | Overhead | R16 | 2023-03-21 | 4 | 16 | 2 | 92 | 111 | 2023 | 2023 | R16
167515308360 | 168219308360 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-03 | 2023-02-03 | 2023-02-03 |  | 2023-05-02 | Overhead | R16 | 2023-02-13 | 1 |  | 7 | 57 | 63 | 2023 | 2023 | R16
168814246233 | 162712246233 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-01 | 2021-09-01 | 2021-09-01 |  | 2021-11-09 | Overhead | R16 | 2021-09-30 | 1 |  | 22 | 29 | 50 | 2021 | 2021 | R16
164063324378 | 169718324378 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-07 | 2023-07-07 | 2023-07-07 | 2023-10-23 | 2023-10-27 | Overhead | R16 | 2023-10-23 | 1 |  | 77 | 5 | 81 | 2023 | 2023 | R16
164368311610 | 163192311610 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-27 | 2023-02-27 | 2023-03-06 |  | 2023-04-12 | Underground | R16 | 2023-03-27 | 1 | 6 | 16 | 13 | 33 | 2023 | 2023 | R16
165636314255 | 160576314255 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-03-31 | 2023-03-31 | 2023-03-31 | 2023-05-04 | 2023-05-05 | Overhead | R16 | 2023-05-04 | 1 |  | 25 | 2 | 26 | 2023 | 2023 | R16
161684314502 | 160995314502 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-04-03 | 2023-04-03 | 2023-04-03 | 2023-09-25 | 2023-10-24 | Overhead | R16 | 2023-09-25 | 1 |  | 126 | 22 | 147 | 2023 | 2023 | R16
160483309230 | 169761309230 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-10 | 2023-02-14 | 2023-02-14 | 2023-04-12 | 2023-04-13 | Overhead | R16 | 2023-04-12 | 3 |  | 42 | 2 | 45 | 2023 | 2023 | R16
169347246751 | 163887246751 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-08 | 2021-09-08 | 2021-09-08 |  | 2022-08-25 | Overhead | R16 | 2022-08-17 | 1 |  | 246 | 7 | 252 | 2021 | 2022 | R16
164994248974 | 164936248974 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-09-13 | 2021-09-13 | 2021-09-23 |  | 2021-11-18 | Overhead | R16 | 2021-10-29 | 1 | 9 | 27 | 15 | 49 | 2021 | 2021 | R16
166816248080 | 160609248080 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-23 | 2021-08-23 | 2021-09-15 |  | 2022-05-18 | Underground | R16 | 2022-04-26 | 1 | 18 | 160 | 17 | 193 | 2021 | 2022 | R16
160939247640 | 163639247640 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-07 | 2021-09-12 | 2021-09-12 | 2021-11-08 | 2021-11-09 | Overhead | R16 | 2021-11-08 | 4 |  | 41 | 2 | 46 | 2021 | 2021 | R16
166436319539 | 167536319539 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-03 | 2023-05-04 | 2023-05-19 | 2023-10-02 | 2023-10-26 | Underground | R16 | 2023-10-02 | 2 | 12 | 97 | 19 | 127 | 2023 | 2023 | R16
169698240707 | 163724240707 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-07-26 | 2021-07-26 | 2021-07-26 |  | 2021-10-27 | Overhead | R16 | 2021-08-13 | 1 |  | 15 | 54 | 68 | 2021 | 2021 | R16
163523322961 | 166764322961 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-06-21 | 2023-06-21 | 2023-06-21 | 2023-07-24 | 2023-08-02 | Underground | R16 | 2023-07-24 | 1 |  | 24 | 8 | 31 | 2023 | 2023 | R16
166802322267 | 165152322267 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-13 | 2023-06-15 | 2023-06-15 | 2023-06-21 | 2023-08-30 | Overhead | R16 | 2023-06-21 | 3 |  | 5 | 51 | 57 | 2023 | 2023 | R16
165970318360 | 169854318360 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-27 | 2023-01-30 | 2023-05-08 | 2023-07-17 | 2023-08-14 | Underground | R16 | 2023-07-17 | 25 | 71 | 51 | 21 | 165 | 2022 | 2023 | R16
166956326501 | 168468326501 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-29 | 2023-07-26 | 2023-07-26 | 2023-08-18 | 2023-09-19 | Overhead | R16 | 2023-08-18 | 20 |  | 18 | 23 | 59 | 2023 | 2023 | R16
166881320999 | 165623320999 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-24 | 2023-05-15 | 2023-06-02 | 2023-06-03 | 2023-06-12 | Overhead | R16 | 2023-06-03 | 16 | 15 | 1 | 6 | 36 | 2023 | 2023 | R16
168126323731 | 164542323731 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-19 | 2023-06-29 | 2023-06-29 |  | 2023-08-02 | Overhead | R16 | 2023-06-30 | 52 |  | 2 | 24 | 76 | 2023 | 2023 | R16
161685324349 | 169791324349 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-02-10 | 2023-06-17 | 2023-07-06 |  | 2023-10-13 | Overhead | R16 |  | 91 | 14 |  |  | 176 | 2023 | 2023 | R16
160709327908 | 160703327908 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-13 | 2023-07-13 | 2023-08-10 | 2023-10-11 | 2023-11-08 | Underground | R16 | 2023-10-11 | 1 | 21 | 45 | 21 | 85 | 2023 | 2023 | R16
169658314904 | 161539314904 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-05 | 2023-01-05 | 2023-04-06 |  | 2023-08-18 | Underground | R16 | 2023-05-09 | 1 | 66 | 24 | 74 | 162 | 2023 | 2023 | R16
168126326146 | 169929326146 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-10 | 2023-07-10 | 2023-07-24 | 2023-11-27 | 2023-12-12 | Overhead | R16 | 2023-11-27 | 1 | 11 | 91 | 12 | 112 | 2023 | 2023 | R16
164083313914 | 169694313914 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-03-28 | 2023-03-28 | 2023-03-28 |  | 2023-04-20 | Overhead | R16 | 2023-03-28 | 1 |  |  | 18 | 18 | 2023 | 2023 | R16
162714247900 | 163656247900 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-07 | 2021-09-14 | 2021-09-14 | 2021-11-08 | 2022-09-02 | Overhead | R16 | 2021-11-08 | 6 |  | 40 | 215 | 259 | 2021 | 2022 | R16
160674319436 | 169374319436 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2023-05-11 | 2023-05-12 | 2023-05-17 |  | 2023-09-13 | Overhead | R16 |  | 2 | 4 |  |  | 90 | 2023 | 2023 | R16
169444321218 | 164445321218 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-19 | 2023-06-05 | 2023-06-05 |  | 2023-09-22 | Overhead | R16 | 2023-06-05 | 34 |  |  | 80 | 113 | 2023 | 2023 | R16
161362250628 | 163500250628 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-03 | 2021-09-03 | 2021-10-05 |  | 2021-11-15 | Overhead | R16 | 2021-10-28 | 1 | 23 | 18 | 13 | 52 | 2021 | 2021 | R16
166527317790 | 167200317790 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-17 | 2023-05-02 | 2023-05-02 | 2023-07-19 | 2023-07-19 | Overhead | R16 | 2023-07-19 | 33 |  | 57 |  | 89 | 2023 | 2023 | R16
168693307935 | 167604307935 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-01 | 2023-02-02 | 2023-02-02 |  | 2023-08-09 | Overhead | R16 | 2023-03-28 | 2 |  | 39 | 97 | 136 | 2023 | 2023 | R16
163327223036 | 167804223036 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-02 | 2021-03-10 | 2021-03-10 |  | 2021-11-04 | Overhead | R16 | 2021-04-05 | 7 |  | 19 | 154 | 178 | 2021 | 2021 | R16
163840247150 | 162069247150 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-08-30 | 2021-08-30 | 2021-09-09 | 2021-10-28 | 2021-10-28 | Underground | R16 | 2021-10-28 | 1 | 9 | 36 |  | 44 | 2021 | 2021 | R16
164036247531 | 164637247531 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-09-10 | 2021-09-14 | 2021-09-14 | 2021-11-10 | 2022-04-29 | Underground | R16 | 2021-11-10 | 3 |  | 42 | 123 | 166 | 2021 | 2022 | R16
164299308559 | 168017308559 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-14 | 2022-12-20 | 2023-02-07 | 2023-08-02 | 2023-08-14 | Underground | R16 | 2023-08-02 | 5 | 36 | 127 | 9 | 174 | 2022 | 2023 | R16
163426227534 | 161561227534 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2021-03-18 | 2021-03-18 | 2021-04-19 |  | 2023-08-23 | Underground | R16 |  | 1 | 23 |  |  | 635 | 2021 | 2023 | R16
160473314754 | 161459314754 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-05 | 2023-04-05 | 2023-04-05 | 2023-05-05 | 2023-06-01 | Overhead | R16 | 2023-05-05 | 1 |  | 23 | 20 | 42 | 2023 | 2023 | R16
163028244293 | 169577244293 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-19 | 2021-08-19 | 2021-08-19 | 2022-09-27 | 2022-09-28 | Overhead | R16 | 2022-09-27 | 1 |  | 289 | 2 | 290 | 2021 | 2022 | R16
164845323699 | 168444323699 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-29 | 2023-06-29 | 2023-06-29 | 2023-08-03 | 2023-08-21 | Overhead | R16 | 2023-08-03 | 1 |  | 26 | 13 | 38 | 2023 | 2023 | R16
162891171921 | 162655171921 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Commercial | 2019-11-12 | 2019-11-12 | 2019-11-14 | 2021-07-08 | 2021-10-05 | Overhead | R16 | 2021-07-08 | 1 | 3 | 431 | 64 | 496 | 2019 | 2021 | R16
163754159540 | 168776159540 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-08 | 2019-07-10 | 2019-07-29 | 2019-08-14 | 2019-08-14 | Underground | R16 | 2019-08-14 | 3 | 14 | 13 |  | 28 | 2019 | 2019 | R16
163675226327 | 169377226327 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-03-09 | 2021-03-18 | 2021-04-08 |  | 2021-11-03 | Underground | R16 | 2021-06-18 | 8 | 16 | 52 | 99 | 172 | 2021 | 2021 | R16
163374157027 | 167680157027 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-01 | 2019-07-03 | 2019-07-03 | 2019-07-05 | 2023-11-21 | Overhead | R16 | 2019-07-05 | 3 |  | 3 | 1143 | 1147 | 2019 | 2023 | R16
160160163232 | 160849163232 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-07-18 | 2019-07-18 | 2019-09-03 | 2020-06-30 | 2020-08-28 | Underground | R16 | 2020-06-30 | 1 | 34 | 216 | 44 | 292 | 2019 | 2020 | R16
163704225606 | 162959225606 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-24 | 2021-03-24 | 2021-04-02 |  | 2022-10-21 | Underground | R16 | 2022-08-23 | 1 | 8 | 363 | 44 | 413 | 2021 | 2022 | R16
169047172088 | 160134172088 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-30 | 2019-10-30 | 2019-11-18 | 2020-02-03 | 2020-06-09 | Underground | R16 | 2020-02-03 | 1 | 14 | 56 | 92 | 160 | 2019 | 2020 | R16
160460190946 | 162401190946 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE FOR UPGRADE UD | Commercial | 2019-09-23 | 2019-11-14 | 2020-05-13 | 2021-06-13 | 2021-06-22 | Underground | R16 | 2021-06-13 | 39 | 130 | 283 | 7 | 457 | 2019 | 2021 | R16
160940165662 | 163652165662 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-05 | 2019-09-24 | 2019-09-24 | 2019-11-15 | 2019-12-06 | Overhead | R16 | 2019-11-15 | 37 |  | 39 | 16 | 90 | 2019 | 2019 | R16
165449168367 | 163961168367 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-10-01 | 2019-10-02 | 2019-10-16 | 2019-11-18 | 2020-04-21 | Overhead | R16 | 2019-11-18 | 2 | 11 | 24 | 112 | 146 | 2019 | 2020 | R16
168065211160 | 168240211160 | RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Residential | 2019-10-22 | 2019-10-22 | 2020-11-18 | 2021-03-09 | 2021-07-26 | Underground | R16 | 2021-03-09 | 1 | 282 | 80 | 100 | 460 | 2019 | 2021 | R16
164348224033 | 161303224033 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-17 | 2021-03-17 | 2021-03-18 |  | 2021-11-05 | Overhead | R16 | 2021-04-14 | 1 | 2 | 20 | 148 | 168 | 2021 | 2021 | R16
168599165603 | 162514165603 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-23 | 2019-09-23 | 2019-09-23 | 2019-09-30 | 2019-10-01 | Overhead | R16 | 2019-09-30 | 1 |  | 6 | 2 | 7 | 2019 | 2019 | R16
164413225191 | 169425225191 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-09 | 2021-03-30 | 2021-03-30 |  | 2021-11-08 | Underground | R16 | 2021-05-13 | 16 |  | 33 | 128 | 175 | 2021 | 2021 | R16
161745180749 | 163209180749 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-14 | 2019-11-19 | 2020-02-14 |  | 2020-04-03 | Underground | R16 |  | 4 | 64 |  |  | 102 | 2019 | 2020 | R16
162747162315 | 167469162315 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-26 | 2019-08-26 | 2019-08-27 | 2019-09-20 | 2019-09-24 | Overhead | R16 | 2019-09-20 | 1 | 2 | 19 | 3 | 22 | 2019 | 2019 | R16
164352165707 | 162832165707 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-24 | 2019-09-25 | 2019-09-25 | 2019-11-21 | 2023-06-09 | Overhead | R16 | 2019-11-21 | 2 |  | 42 | 927 | 969 | 2019 | 2023 | R16
164710225144 | 164078225144 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-29 | 2021-03-29 | 2021-03-29 |  | 2022-10-17 | Overhead | R16 |  | 1 |  |  |  | 406 | 2021 | 2022 | R16
160392158144 | 160354158144 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-07-17 | 2019-07-17 | 2019-07-17 | 2022-07-19 | 2022-07-19 | Underground | R16 | 2022-07-19 | 1 |  | 785 |  | 785 | 2019 | 2022 | R16
168837164569 | 166535164569 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-20 | 2019-08-20 | 2019-09-16 | 2019-11-06 | 2020-04-30 | Underground | R16 | 2019-11-06 | 1 | 20 | 38 | 127 | 183 | 2019 | 2020 | R16
166813164955 | 169080164955 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-04 | 2019-09-19 | 2019-09-19 | 2019-09-20 | 2019-12-04 | Overhead | R16 | 2019-09-20 | 12 |  | 2 | 54 | 66 | 2019 | 2019 | R16
161687168557 | 163680168557 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-30 | 2019-10-17 | 2019-10-17 | 2019-12-10 | 2020-01-03 | Overhead | R16 | 2019-12-10 | 14 |  | 39 | 19 | 70 | 2019 | 2020 | R16
164831253155 | 162623253155 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-23 | 2021-03-23 | 2021-10-21 |  | 2022-08-18 | Overhead | R16 | 2022-08-15 | 1 | 153 | 213 | 4 | 368 | 2021 | 2022 | R16
164849223394 | 168909223394 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-08 | 2021-03-12 | 2021-03-12 |  | 2021-11-09 | Overhead | R16 | 2021-04-27 | 5 |  | 33 | 141 | 177 | 2021 | 2021 | R16
168117170818 | 161493170818 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-06 | 2019-11-06 | 2019-11-06 | 2020-03-13 | 2020-06-09 | Overhead | R16 | 2020-03-13 | 1 |  | 93 | 63 | 155 | 2019 | 2020 | R16
160822162549 | 163345162549 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-02 | 2019-08-28 | 2019-08-28 | 2020-09-23 | 2023-06-08 | Overhead | R16 | 2020-09-23 | 19 |  | 281 | 707 | 1005 | 2019 | 2023 | R16
166852175053 | 163141175053 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-14 | 2019-11-14 | 2019-12-23 |  | 2022-10-20 | Underground | R16 |  | 1 | 28 |  |  | 766 | 2019 | 2022 | R16
166777169150 | 168469169150 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-22 | 2019-10-22 | 2019-10-23 | 2019-11-15 | 2019-11-26 | Overhead | R16 | 2019-11-15 | 1 | 2 | 18 | 8 | 26 | 2019 | 2019 | R16
165126273147 | 168677273147 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-03-08 | 2022-03-18 | 2022-03-18 |  | 2022-06-03 | Overhead | R16 | 2022-05-13 | 270 |  | 41 | 16 | 325 | 2021 | 2022 | R16
162966171872 | 163234171872 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-14 | 2019-11-14 | 2019-11-14 | 2020-08-11 | 2020-08-20 | Overhead | R16 | 2020-08-11 | 1 |  | 194 | 8 | 201 | 2019 | 2020 | R16
167239173070 | 169929173070 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-29 | 2019-10-31 | 2019-11-27 | 2020-06-10 | 2020-06-11 | Overhead | R16 | 2020-06-10 | 3 | 20 | 141 | 2 | 163 | 2019 | 2020 | R16
169254155696 | 165096155696 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-19 | 2019-06-19 | 2019-06-19 | 2019-07-17 | 2019-07-17 | Overhead | R16 | 2019-07-17 | 1 |  | 21 |  | 21 | 2019 | 2019 | R16
163061176546 | 167826176546 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-11 | 2019-12-11 | 2020-01-10 | 2020-04-17 | 2020-04-20 | Underground | R16 | 2020-04-17 | 1 | 23 | 71 | 2 | 94 | 2019 | 2020 | R16
162351156982 | 167753156982 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-02 | 2019-07-02 | 2019-07-02 | 2019-07-17 | 2019-11-25 | Overhead | R16 | 2019-07-17 | 1 |  | 12 | 94 | 105 | 2019 | 2019 | R16
163988194570 | 166314194570 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-11 | 2020-06-17 | 2020-06-17 | 2020-08-27 | 2020-11-02 | Overhead | R16 | 2020-08-27 | 179 |  | 52 | 48 | 277 | 2019 | 2020 | R16
161059184409 | 162621184409 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2019-09-24 | 2020-01-27 | 2020-03-17 |  | 2021-04-05 | Overhead | R16 | 2020-03-26 | 90 | 37 | 8 | 268 | 400 | 2019 | 2021 | R16
164488159324 | 162454159324 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-29 | 2019-07-29 | 2019-07-29 | 2019-09-25 | 2022-05-17 | Overhead | R16 | 2019-09-25 | 1 |  | 43 | 690 | 732 | 2019 | 2022 | R16
165384222607 | 167671222607 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-02 | 2021-03-02 | 2021-03-05 |  | 2021-08-18 | Overhead | R16 | 2021-06-16 | 1 | 4 | 74 | 46 | 122 | 2021 | 2021 | R16
166401174503 | 168795174503 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-16 | 2019-12-16 | 2019-12-16 | 2020-03-09 | 2020-04-01 | Overhead | R16 | 2020-03-09 | 1 |  | 61 | 18 | 78 | 2019 | 2020 | R16
161023163820 | 169881163820 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-09-09 | 2019-09-09 | 2019-09-09 | 2020-05-07 | 2020-05-11 | Overhead | R16 | 2020-05-07 | 1 |  | 174 | 3 | 176 | 2019 | 2020 | R16
165515161576 | 166411161576 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-20 | 2019-08-20 | 2019-08-20 | 2020-02-26 | 2020-02-27 | Overhead | R16 | 2020-02-26 | 1 |  | 137 | 2 | 138 | 2019 | 2020 | R16
161230304188 | 169865304188 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-27 | 2022-12-27 | 2022-12-28 |  | 2023-10-24 | Overhead | R16 | 2023-09-27 | 1 | 2 | 196 | 20 | 216 | 2022 | 2023 | R16
160788164351 | 166378164351 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-20 | 2019-09-13 | 2019-09-13 | 2019-11-12 | 2019-11-13 | Overhead | R16 | 2019-11-12 | 19 |  | 43 | 2 | 62 | 2019 | 2019 | R16
165982236547 | 165827236547 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2021-04-06 | 2021-04-06 | 2021-06-25 |  | 2022-08-10 | Overhead | R16 |  | 1 | 59 |  |  | 352 | 2021 | 2022 | R16
162704190177 | 164856190177 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-25 | 2020-05-07 | 2020-05-07 | 2020-06-24 | 2020-08-28 | Overhead | R16 | 2020-06-24 | 119 |  | 35 | 48 | 200 | 2019 | 2020 | R16
168188161842 | 166367161842 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-20 | 2019-08-20 | 2019-08-20 | 2019-09-27 | 2019-09-30 | Overhead | R16 | 2019-09-27 | 1 |  | 29 | 2 | 30 | 2019 | 2019 | R16
161270173644 | 166365173644 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-05 | 2019-12-05 | 2019-12-05 | 2020-01-28 | 2020-01-29 | Overhead | R16 | 2020-01-28 | 1 |  | 39 | 2 | 40 | 2019 | 2020 | R16
161678165731 | 162764165731 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-25 | 2019-09-25 | 2019-09-25 | 2019-10-04 | 2019-10-07 | Overhead | R16 | 2019-10-04 | 1 |  | 8 | 2 | 9 | 2019 | 2019 | R16
164089192612 | 167926192612 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-19 | 2019-10-19 | 2020-05-29 | 2021-08-10 | 2021-12-03 | Underground | R16 | 2021-08-10 | 0 | 160 | 313 | 84 | 555 | 2019 | 2021 | R16
166419225602 | 165139225602 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-01 | 2021-04-01 | 2021-04-01 |  | 2021-10-26 | Overhead | R16 | 2021-04-21 | 1 |  | 15 | 135 | 149 | 2021 | 2021 | R16
167188165717 | 162921165717 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-25 | 2019-09-25 | 2019-09-25 | 2019-10-25 | 2019-11-14 | Overhead | R16 | 2019-10-25 | 1 |  | 23 | 15 | 37 | 2019 | 2019 | R16
167549164773 | 169689164773 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-12 | 2019-07-12 | 2019-09-16 | 2019-11-22 | 2019-12-03 | Underground | R16 | 2019-11-22 | 1 | 47 | 50 | 8 | 103 | 2019 | 2019 | R16
168202170962 | 161498170962 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-06 | 2019-11-06 | 2019-11-06 | 2020-02-06 | 2020-06-09 | Overhead | R16 | 2020-02-06 | 1 |  | 67 | 89 | 155 | 2019 | 2020 | R16
161771161719 | 166358161719 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-20 | 2019-08-20 | 2019-08-20 | 2019-08-29 | 2023-06-08 | Overhead | R16 | 2019-08-29 | 1 |  | 8 | 986 | 993 | 2019 | 2023 | R16
169423159412 | 169286159412 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-07-10 | 2019-07-10 | 2019-07-29 | 2019-08-23 | 2021-12-16 | Underground | R16 | 2019-08-23 | 1 | 14 | 20 | 605 | 637 | 2019 | 2021 | R16
166490222692 | 168845222692 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-08 | 2021-03-08 | 2021-03-08 |  | 2021-10-27 | Overhead | R16 | 2021-09-07 | 1 |  | 132 | 37 | 168 | 2021 | 2021 | R16
163754164408 | 164395164408 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-08 | 2019-08-09 | 2019-09-13 | 2019-10-22 | 2019-10-24 | Underground | R16 | 2019-10-22 | 2 | 26 | 28 | 3 | 56 | 2019 | 2019 | R16
166575223177 | 167675223177 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-03-02 | 2021-03-02 | 2021-03-11 |  | 2021-08-11 | Underground | R16 | 2021-07-01 | 1 | 8 | 81 | 30 | 117 | 2021 | 2021 | R16
168592170132 | 168692170132 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-23 | 2019-10-23 | 2019-10-30 | 2021-10-21 | 2021-10-26 | Underground | R16 | 2021-10-21 | 1 | 6 | 517 | 4 | 525 | 2019 | 2021 | R16
165098163922 | 169948163922 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-09 | 2019-09-09 | 2019-09-09 | 2019-10-07 | 2019-10-07 | Overhead | R16 | 2019-10-07 | 1 |  | 21 |  | 21 | 2019 | 2019 | R16
169323166717 | 161641166717 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-18 | 2019-09-30 | 2019-10-04 | 2019-12-10 | 2020-01-06 | Overhead | R16 | 2019-12-10 | 9 | 5 | 48 | 20 | 79 | 2019 | 2020 | R16
166819223458 | 160302223458 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-03-12 | 2021-03-12 | 2021-03-12 |  | 2021-11-09 | Overhead | R16 | 2021-09-24 | 1 |  | 141 | 33 | 173 | 2021 | 2021 | R16
163434155176 | 163428155176 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-06-12 | 2019-06-12 | 2019-06-13 | 2019-08-02 | 2020-01-08 | Underground | R16 | 2019-08-02 | 1 | 2 | 37 | 114 | 151 | 2019 | 2020 | R16
161517166825 | 164541166825 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-10-03 | 2019-10-03 | 2019-10-03 | 2019-10-03 | 2019-10-10 | Overhead | R16 | 2019-10-03 | 1 |  |  | 6 | 6 | 2019 | 2019 | R16
168796171683 | 162584171683 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-11-12 | 2019-11-13 | 2019-11-13 | 2019-11-20 | 2021-11-13 | Overhead | R16 | 2019-11-20 | 2 |  | 6 | 518 | 524 | 2019 | 2021 | R16
166873230502 | 163340230502 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-05 | 2021-05-05 | 2021-05-12 |  | 2021-09-14 | Overhead | R16 | 2021-08-20 | 1 | 6 | 73 | 18 | 95 | 2021 | 2021 | R16
167751155689 | 165002155689 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-18 | 2019-06-18 | 2019-06-18 | 2020-04-29 | 2020-07-08 | Overhead | R16 | 2020-04-29 | 1 |  | 227 | 51 | 277 | 2019 | 2020 | R16
168471172888 | 162239172888 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-08 | 2019-11-25 | 2019-11-25 | 2020-02-24 | 2020-06-09 | Overhead | R16 | 2020-02-24 | 12 |  | 66 | 77 | 153 | 2019 | 2020 | R16
169565330117 | 168968330117 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-05 | 2023-08-21 | 2023-08-21 | 2023-09-19 | 2023-10-24 | Overhead | R16 | 2023-09-19 | 34 |  | 22 | 26 | 80 | 2023 | 2023 | R16
162107169957 | 169551169957 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-28 | 2019-10-28 | 2019-10-29 | 2019-12-06 | 2019-12-09 | Overhead | R16 | 2019-12-06 | 1 | 2 | 29 | 2 | 31 | 2019 | 2019 | R16
160354170133 | 165055170133 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-08-13 | 2019-08-13 | 2019-10-30 | 2019-10-31 | 2020-01-09 | Overhead | R16 | 2019-10-31 | 1 | 57 | 2 | 51 | 108 | 2019 | 2020 | R16
160217169038 | 161683169038 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-09-18 | 2019-09-18 | 2019-10-22 | 2019-11-21 | 2020-09-18 | Underground | R16 | 2019-11-21 | 1 | 25 | 23 | 217 | 263 | 2019 | 2020 | R16
162975173787 | 162928173787 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-11-13 | 2019-11-13 | 2019-12-06 | 2020-11-18 | 2020-11-18 | Overhead | R16 | 2020-11-18 | 1 | 18 | 249 |  | 266 | 2019 | 2020 | R16
165516161507 | 160626161507 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-07-17 | 2019-07-19 | 2019-08-19 | 2019-10-22 | 2022-12-13 | Underground | R16 | 2019-10-22 | 3 | 22 | 47 | 821 | 890 | 2019 | 2022 | R16
167181224879 | 160532224879 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-15 | 2021-03-15 | 2021-03-29 |  | 2021-11-08 | Underground | R16 | 2021-05-12 | 1 | 11 | 33 | 129 | 171 | 2021 | 2021 | R16
167732168944 | 168493168944 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-30 | 2019-08-30 | 2019-10-21 | 2019-12-06 | 2019-12-11 | Underground | R16 | 2019-12-06 | 1 | 37 | 35 | 4 | 74 | 2019 | 2019 | R16
160781165845 | 162868165845 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-09-25 | 2019-09-25 | 2019-09-25 | 2020-03-02 | 2020-03-04 | Overhead | R16 | 2020-03-02 | 1 |  | 114 | 3 | 116 | 2019 | 2020 | R16
166224188964 | 165596188964 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-15 | 2019-08-15 | 2020-04-24 | 2020-04-29 | 2020-07-07 | Underground | R16 | 2020-04-29 | 1 | 182 | 4 | 50 | 234 | 2019 | 2020 | R16
165053160077 | 164116160077 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-06 | 2019-08-06 | 2019-08-06 | 2019-09-05 | 2019-11-06 | Overhead | R16 | 2019-09-05 | 1 |  | 23 | 45 | 67 | 2019 | 2019 | R16
162768175393 | 165300175393 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-10-07 | 2019-10-07 | 2020-01-03 | 2020-01-21 | 2020-01-24 | Underground | R16 | 2020-01-21 | 1 | 65 | 13 | 4 | 80 | 2019 | 2020 | R16
167292228426 | 167310228426 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-28 | 2021-02-28 | 2021-04-26 |  | 2021-11-09 | Underground | R16 | 2021-08-05 | 0 | 41 | 74 | 69 | 182 | 2021 | 2021 | R16
167697154992 | 163360154992 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-11 | 2019-06-11 | 2019-06-11 | 2019-11-05 | 2019-11-06 | Overhead | R16 | 2019-11-05 | 1 |  | 106 | 2 | 107 | 2019 | 2019 | R16
163437175681 | 166362175681 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-04 | 2019-12-04 | 2020-01-02 | 2020-03-06 | 2020-03-09 | Underground | R16 | 2020-03-06 | 1 | 22 | 47 | 2 | 69 | 2019 | 2020 | R16
167721162820 | 168026162820 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-29 | 2019-08-29 | 2019-08-29 | 2019-08-31 | 2019-09-03 | Underground | R16 | 2019-08-31 | 1 |  | 2 | 2 | 4 | 2019 | 2019 | R16
167327223462 | 160387223462 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-12 | 2021-03-12 | 2021-03-12 |  | 2021-11-08 | Overhead | R16 | 2021-05-19 | 1 |  | 49 | 124 | 172 | 2021 | 2021 | R16
165258160404 | 165619160404 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-22 | 2019-06-22 | 2019-08-06 | 2019-09-20 | 2019-09-24 | Underground | R16 | 2019-09-20 | 0 | 32 | 34 | 3 | 67 | 2019 | 2019 | R16
167445233404 | 163208233404 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-05 | 2021-05-05 | 2021-06-03 |  | 2022-03-21 | Underground | R16 | 2022-03-17 | 1 | 22 | 206 | 3 | 229 | 2021 | 2022 | R16
165755162691 | 168681162691 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-30 | 2019-08-30 | 2019-08-30 | 2019-12-06 | 2019-12-17 | Overhead | R16 | 2019-12-06 | 1 |  | 71 | 8 | 78 | 2019 | 2019 | R16
161301178188 | 161283178188 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-22 | 2019-07-29 | 2020-01-27 | 2020-06-29 | 2020-09-03 | Overhead | R16 | 2020-06-29 | 6 | 131 | 111 | 49 | 294 | 2019 | 2020 | R16
169919174311 | 168070174311 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2019-12-12 | 2019-12-12 | 2019-12-12 | 2020-04-24 | 2020-07-02 | Overhead | R16 | 2020-04-24 | 1 |  | 97 | 50 | 146 | 2019 | 2020 | R16
169172162653 | 168164162653 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-29 | 2019-08-29 | 2019-08-29 | 2019-09-18 | 2019-09-18 | Overhead | R16 | 2019-09-18 | 1 |  | 15 |  | 15 | 2019 | 2019 | R16
162407155474 | 164874155474 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-18 | 2019-06-18 | 2019-06-18 | 2019-08-26 | 2019-09-04 | Overhead | R16 | 2019-08-26 | 1 |  | 50 | 8 | 57 | 2019 | 2019 | R16
164902159160 | 168249159160 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-05 | 2019-07-26 | 2019-07-26 | 2019-09-09 | 2019-09-26 | Overhead | R16 | 2019-09-09 | 16 |  | 32 | 14 | 60 | 2019 | 2019 | R16
162641179467 | 162889179467 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-13 | 2019-11-13 | 2020-02-05 | 2020-04-22 | 2020-07-01 | Underground | R16 | 2020-04-22 | 1 | 61 | 56 | 51 | 166 | 2019 | 2020 | R16
165495164217 | 166966164217 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-23 | 2019-09-12 | 2019-09-12 | 2020-01-02 | 2021-11-13 | Overhead | R16 | 2020-01-02 | 15 |  | 81 | 487 | 581 | 2019 | 2021 | R16
165443174094 | 162519174094 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-12 | 2019-11-12 | 2019-12-11 | 2019-12-23 | 2020-01-14 | Underground | R16 | 2019-12-23 | 1 | 22 | 9 | 17 | 46 | 2019 | 2020 | R16
162821157596 | 169582157596 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-12 | 2019-07-12 | 2019-07-12 | 2019-12-05 | 2019-12-06 | Overhead | R16 | 2019-12-05 | 1 |  | 105 | 2 | 106 | 2019 | 2019 | R16
167786233124 | 161043233124 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-03-16 | 2021-04-23 | 2021-06-01 |  | 2021-12-17 | Overhead | R16 | 2021-11-10 | 29 | 28 | 117 | 28 | 199 | 2021 | 2021 | R16
169529198022 | 169649198022 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2019-07-12 | 2019-07-12 | 2020-07-21 | 2021-10-13 | 2021-10-28 | Underground | R16 | 2021-10-13 | 1 | 268 | 322 | 12 | 600 | 2019 | 2021 | R16
163020173061 | 164913173061 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-24 | 2019-11-26 | 2019-11-26 | 2020-02-21 | 2020-06-09 | Overhead | R16 | 2020-02-21 | 2 |  | 64 | 78 | 142 | 2019 | 2020 | R16
168768169098 | 168319169098 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-22 | 2019-10-22 | 2019-10-22 | 2019-11-04 | 2019-11-04 | Overhead | R16 | 2019-11-04 | 1 |  | 10 |  | 10 | 2019 | 2019 | R16
167918175383 | 168662175383 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-30 | 2019-08-30 | 2019-12-30 | 2020-04-23 | 2021-07-15 | Underground | R16 | 2020-04-23 | 1 | 87 | 84 | 321 | 490 | 2019 | 2021 | R16
163926158452 | 168790158452 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-08 | 2019-07-10 | 2019-07-19 | 2019-09-11 | 2019-09-16 | Underground | R16 | 2019-09-11 | 3 | 8 | 39 | 4 | 51 | 2019 | 2019 | R16
166431164073 | 166806164073 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-22 | 2019-08-23 | 2019-09-11 | 2020-09-28 | 2020-09-30 | Underground | R16 | 2020-09-28 | 2 | 14 | 274 | 3 | 290 | 2019 | 2020 | R16
161762161777 | 169086161777 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-07-09 | 2019-07-09 | 2019-08-22 | 2019-10-31 | 2020-02-06 | Underground | R16 | 2019-10-31 | 1 | 33 | 51 | 71 | 153 | 2019 | 2020 | R16
161898170658 | 165435170658 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-08 | 2019-10-08 | 2019-11-06 | 2019-11-20 | 2022-12-01 | Underground | R16 | 2019-11-20 | 1 | 22 | 11 | 792 | 823 | 2019 | 2022 | R16
165793158866 | 161593158866 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-23 | 2019-07-24 | 2019-07-24 | 2019-08-20 | 2019-08-20 | Overhead | R16 | 2019-08-20 | 2 |  | 20 |  | 21 | 2019 | 2019 | R16
162532220659 | 164547220659 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-21 | 2019-12-23 | 2021-02-18 | 2021-12-08 | 2023-06-07 | Underground | R16 | 2021-12-08 | 23 | 304 | 210 | 391 | 925 | 2019 | 2023 | R16
161409172703 | 164568172703 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-21 | 2019-11-21 | 2019-11-21 | 2020-02-03 | 2020-06-09 | Overhead | R16 | 2020-02-03 | 1 |  | 53 | 92 | 144 | 2019 | 2020 | R16
163374157321 | 168229157321 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-03 | 2019-07-08 | 2019-07-08 | 2019-09-12 | 2019-09-16 | Overhead | R16 | 2019-09-12 | 4 |  | 49 | 3 | 54 | 2019 | 2019 | R16
166199205455 | 166231205455 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Commercial | 2019-08-19 | 2020-07-07 | 2020-09-28 | 2022-06-16 | 2022-07-05 | Underground | R16 | 2022-06-16 | 232 | 60 | 449 | 14 | 752 | 2019 | 2022 | R16
166042169070 | 160333169070 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-09-11 | 2019-09-11 | 2019-10-21 | 2020-06-03 | 2020-06-05 | Underground | R16 | 2020-06-03 | 1 | 29 | 163 | 3 | 193 | 2019 | 2020 | R16
166063164040 | 161345164040 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-22 | 2019-07-25 | 2019-09-10 | 2019-10-15 | 2019-10-17 | Underground | R16 | 2019-10-15 | 4 | 34 | 26 | 3 | 64 | 2019 | 2019 | R16
168801159941 | 163480159941 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-02 | 2019-08-02 | 2019-08-02 | 2019-09-13 | 2019-09-19 | Overhead | R16 | 2019-09-13 | 1 |  | 31 | 5 | 35 | 2019 | 2019 | R16
161319170886 | 161075170886 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-11-05 | 2019-11-05 | 2019-11-06 | 2020-03-17 | 2020-03-21 | Overhead | R16 | 2020-03-17 | 1 | 2 | 95 | 4 | 99 | 2019 | 2020 | R16
168567249807 | 165769249807 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-09-15 | 2021-09-16 | 2021-09-28 |  | 2021-11-13 | Overhead | R16 |  | 2 | 9 |  |  | 43 | 2021 | 2021 | R16
167832180712 | 166482180712 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-12-05 | 2019-12-05 | 2020-02-14 | 2022-03-30 | 2022-03-31 | Underground | R16 | 2022-03-30 | 1 | 52 | 554 | 2 | 606 | 2019 | 2022 | R16
166148210114 | 165541210114 | NON-RESIDENTIAL - HEALTH CARE | UG R16 RESD AND NON RESD UD | Commercial | 2019-12-02 | 2020-05-07 | 2020-11-10 | 2022-04-04 | 2022-04-26 | Underground | R16 | 2022-04-04 | 114 | 134 | 365 | 17 | 627 | 2019 | 2022 | R16
167769310353 | 167345310353 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-31 | 2023-02-24 | 2023-02-24 | 2023-08-15 | 2023-08-22 | Overhead | R16 | 2023-08-15 | 19 |  | 123 | 6 | 146 | 2023 | 2023 | R16
162331155471 | 164529155471 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-18 | 2019-06-18 | 2019-06-18 | 2019-08-20 | 2019-08-28 | Overhead | R16 | 2019-08-20 | 1 |  | 46 | 7 | 52 | 2019 | 2019 | R16
160569161123 | 163400161123 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-02 | 2019-08-13 | 2019-08-13 | 2019-12-23 | 2020-03-02 | Overhead | R16 | 2019-12-23 | 8 |  | 95 | 51 | 152 | 2019 | 2020 | R16
167793173974 | 167097173974 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-10 | 2019-12-10 | 2019-12-10 | 2020-03-09 | 2020-06-09 | Overhead | R16 | 2020-03-09 | 1 |  | 65 | 67 | 131 | 2019 | 2020 | R16
169178156843 | 166647156843 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-28 | 2019-06-28 | 2019-07-01 | 2019-07-17 | 2019-07-17 | Overhead | R16 | 2019-07-17 | 1 | 2 | 13 |  | 14 | 2019 | 2019 | R16
162587159472 | 162397159472 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-29 | 2019-07-29 | 2019-07-29 | 2019-08-16 | 2019-08-19 | Overhead | R16 | 2019-08-16 | 1 |  | 15 | 2 | 16 | 2019 | 2019 | R16
168744225307 | 164421225307 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-30 | 2021-03-30 | 2021-03-30 |  | 2021-11-16 | Overhead | R16 | 2021-05-26 | 1 |  | 42 | 125 | 166 | 2021 | 2021 | R16
168745226124 | 166381226124 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-07 | 2021-04-07 | 2021-04-07 |  | 2021-11-09 | Overhead | R16 | 2021-10-01 | 1 |  | 128 | 28 | 155 | 2021 | 2021 | R16
165542158215 | 167415158215 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-01 | 2019-07-01 | 2019-07-18 | 2019-08-06 | 2022-10-17 | Underground | R16 | 2019-08-06 | 1 | 14 | 14 | 835 | 861 | 2019 | 2022 | R16
162978161216 | 165926161216 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-16 | 2019-08-16 | 2019-08-16 | 2019-09-02 | 2019-09-05 | Overhead | R16 | 2019-09-02 | 1 |  | 12 | 4 | 15 | 2019 | 2019 | R16
161908167159 | 165539167159 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-08 | 2019-10-08 | 2019-10-08 | 2020-03-03 | 2020-06-09 | Overhead | R16 | 2020-03-03 | 1 |  | 106 | 71 | 176 | 2019 | 2020 | R16
169228160397 | 162322160397 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-07-26 | 2019-07-26 | 2019-08-07 | 2019-08-14 | 2019-09-25 | Overhead | R16 | 2019-08-14 | 1 | 9 | 6 | 31 | 44 | 2019 | 2019 | R16
163984165960 | 163034165960 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-26 | 2019-09-26 | 2019-09-26 | 2019-10-30 | 2019-10-31 | Overhead | R16 | 2019-10-30 | 1 |  | 25 | 2 | 26 | 2019 | 2019 | R16
168807224662 | 163008224662 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-24 | 2021-03-24 | 2021-03-24 |  | 2021-10-25 | Overhead | R16 | 2021-08-31 | 1 |  | 115 | 40 | 154 | 2021 | 2021 | R16
161477170552 | 160610170552 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-31 | 2019-11-04 | 2019-11-04 | 2020-10-28 | 2021-06-30 | Underground | R16 | 2020-10-28 | 3 |  | 258 | 176 | 435 | 2019 | 2021 | R16
163060200565 | 161459200565 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-09-17 | 2020-05-28 | 2020-08-13 | 2020-10-01 | 2020-11-09 | Underground | R16 | 2020-10-01 | 183 | 56 | 36 | 28 | 300 | 2019 | 2020 | R16
165824158391 | 160963158391 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-19 | 2019-07-19 | 2019-07-19 | 2019-07-25 | 2019-12-03 | Overhead | R16 | 2019-07-25 | 1 |  | 5 | 94 | 98 | 2019 | 2019 | R16
162417173066 | 165002173066 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-24 | 2019-11-26 | 2019-11-26 | 2020-01-03 | 2020-06-09 | Overhead | R16 | 2020-01-03 | 2 |  | 29 | 113 | 142 | 2019 | 2020 | R16
164080173890 | 166831173890 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-09 | 2019-12-09 | 2019-12-09 | 2020-03-09 | 2020-06-09 | Overhead | R16 | 2020-03-09 | 1 |  | 66 | 67 | 132 | 2019 | 2020 | R16
169017225811 | 165761225811 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-04-05 | 2021-04-05 | 2021-04-05 |  | 2021-09-14 | Overhead | R16 | 2021-08-20 | 1 |  | 100 | 18 | 117 | 2021 | 2021 | R16
166307164366 | 160778164366 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-13 | 2019-09-13 | 2019-09-13 | 2019-11-27 | 2019-12-09 | Overhead | R16 | 2019-11-27 | 1 |  | 54 | 9 | 62 | 2019 | 2019 | R16
167222171899 | 167171171899 | NON-RESIDENTIAL - SMALL RETAIL | UG R16 RESD AND NON RESD UD | Commercial | 2019-10-16 | 2019-10-18 | 2019-11-15 | 2020-02-13 | 2020-06-22 | Underground | R16 | 2020-02-13 | 3 | 21 | 65 | 93 | 179 | 2019 | 2020 | R16
161092177063 | 167300177063 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-10 | 2019-12-10 | 2020-01-15 | 2020-02-11 | 2020-02-12 | Underground | R16 | 2020-02-11 | 1 | 27 | 20 | 2 | 47 | 2019 | 2020 | R16
168130161610 | 160825161610 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-18 | 2019-08-19 | 2019-08-19 | 2020-05-07 | 2021-07-08 | Overhead | R16 | 2020-05-07 | 23 |  | 189 | 306 | 516 | 2019 | 2021 | R16
169330246260 | 167034246260 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-09 | 2021-08-09 | 2021-09-01 |  | 2021-12-28 | Underground | R16 | 2021-11-16 | 1 | 18 | 55 | 31 | 102 | 2021 | 2021 | R16
166311163343 | 166794163343 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-21 | 2019-08-21 | 2019-09-04 | 2019-12-12 | 2019-12-23 | Underground | R16 | 2019-12-12 | 1 | 11 | 72 | 8 | 89 | 2019 | 2019 | R16
169383233783 | 165859233783 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-17 | 2021-05-17 | 2021-06-07 |  | 2021-10-27 | Underground | R16 | 2021-08-12 | 1 | 16 | 49 | 55 | 118 | 2021 | 2021 | R16
161059184412 | 162625184412 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2019-09-24 | 2020-01-28 | 2020-03-17 | 2020-05-08 | 2020-07-29 | Overhead | R16 | 2020-05-08 | 91 | 36 | 39 | 59 | 222 | 2019 | 2020 | R16
169783168697 | 169698168697 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-07 | 2019-09-07 | 2019-10-18 | 2020-03-12 | 2020-03-13 | Underground | R16 | 2020-03-12 | 0 | 30 | 105 | 2 | 135 | 2019 | 2020 | R16
163750170884 | 165577170884 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-09 | 2019-11-06 | 2019-11-06 | 2020-01-22 | 2021-11-10 | Overhead | R16 | 2020-01-22 | 21 |  | 56 | 471 | 546 | 2019 | 2021 | R16
167824170123 | 169986170123 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-29 | 2019-10-29 | 2019-10-29 | 2019-12-09 | 2019-12-10 | Overhead | R16 | 2019-12-09 | 1 |  | 30 | 2 | 31 | 2019 | 2019 | R16
168845172909 | 163262172909 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-14 | 2019-11-18 | 2019-11-26 | 2020-02-12 | 2020-06-09 | Overhead | R16 | 2020-02-12 | 3 | 7 | 57 | 85 | 149 | 2019 | 2020 | R16
165499193522 | 168877193522 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-09-03 | 2020-04-17 | 2020-06-08 | 2021-09-24 | 2021-10-11 | Underground | R16 | 2021-09-24 | 164 | 37 | 340 | 12 | 550 | 2019 | 2021 | R16
163268197836 | 163350197836 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-15 | 2019-11-15 | 2020-07-21 | 2020-09-17 | 2020-09-18 | Underground | R16 | 2020-09-17 | 1 | 178 | 43 | 2 | 221 | 2019 | 2020 | R16
163703160959 | 160984160959 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-19 | 2019-07-19 | 2019-08-14 | 2019-09-11 | 2019-09-12 | Underground | R16 | 2019-09-11 | 1 | 19 | 21 | 2 | 40 | 2019 | 2019 | R16
164208165427 | 162349165427 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-23 | 2019-09-23 | 2019-09-23 | 2019-10-16 | 2019-10-29 | Overhead | R16 | 2019-10-16 | 1 |  | 18 | 10 | 27 | 2019 | 2019 | R16
166548204486 | 169269204486 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-09-05 | 2019-09-05 | 2020-09-21 | 2021-03-15 | 2021-05-12 | Underground | R16 | 2021-03-15 | 1 | 273 | 126 | 43 | 440 | 2019 | 2021 | R16
161915171586 | 163563171586 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-30 | 2019-09-30 | 2019-11-12 | 2020-01-28 | 2020-01-30 | Underground | R16 | 2020-01-28 | 1 | 32 | 56 | 3 | 89 | 2019 | 2020 | R16
166130159948 | 161412159948 | NON-RESIDENTIAL - LODGING | R16 RESD AND NON RESD US | Commercial | 2019-07-22 | 2019-07-22 | 2019-08-02 | 2020-01-25 | 2020-03-06 | Underground | R16 | 2020-01-25 | 1 | 10 | 126 | 30 | 165 | 2019 | 2020 | R16
169743224963 | 160799224963 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-16 | 2021-03-16 | 2021-03-26 |  | 2021-11-08 | Underground | R16 | 2021-05-27 | 1 | 9 | 45 | 118 | 170 | 2021 | 2021 | R16
169766225031 | 164077225031 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-29 | 2021-03-29 | 2021-03-29 |  | 2023-03-31 | Overhead | R16 | 2023-01-26 | 1 |  | 479 | 47 | 525 | 2021 | 2023 | R16
169067165518 | 162754165518 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-24 | 2019-09-24 | 2019-09-24 | 2019-12-10 | 2020-01-03 | Overhead | R16 | 2019-12-10 | 1 |  | 56 | 19 | 74 | 2019 | 2020 | R16
161876178905 | 161162178905 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-16 | 2019-09-16 | 2020-01-31 | 2021-01-13 | 2021-01-14 | Underground | R16 | 2021-01-13 | 1 | 100 | 249 | 2 | 349 | 2019 | 2021 | R16
162740163835 | 167865163835 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-02 | 2019-07-02 | 2019-09-10 | 2019-11-21 | 2019-11-22 | Underground | R16 | 2019-11-21 | 1 | 51 | 53 | 2 | 104 | 2019 | 2019 | R16
161996163509 | 169436163509 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-05 | 2019-09-06 | 2019-09-06 | 2019-10-16 | 2019-10-17 | Overhead | R16 | 2019-10-16 | 2 |  | 29 | 2 | 31 | 2019 | 2019 | R16
168695176672 | 162969176672 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-07-31 | 2019-07-31 | 2020-01-14 | 2020-04-02 | 2020-04-03 | Underground | R16 | 2020-04-02 | 1 | 120 | 58 | 2 | 178 | 2019 | 2020 | R16
162128167156 | 165447167156 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-08 | 2019-10-08 | 2019-10-08 | 2019-11-25 | 2023-06-08 | Overhead | R16 | 2019-11-25 | 1 |  | 35 | 924 | 958 | 2019 | 2023 | R16
169042172621 | 160940172621 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-04 | 2019-11-21 | 2019-11-21 | 2020-02-21 | 2020-07-08 | Overhead | R16 | 2020-02-21 | 14 |  | 67 | 99 | 178 | 2019 | 2020 | R16
166894221757 | 169911221757 | NON-RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Commercial | 2019-09-09 | 2019-09-09 | 2021-02-26 | 2021-07-01 | 2022-01-04 | Underground | R16 | 2021-07-01 | 1 | 385 | 90 | 134 | 607 | 2019 | 2022 | R16
162631163976 | 160208163976 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-10 | 2019-09-10 | 2019-09-10 | 2020-06-25 | 2020-06-26 | Overhead | R16 | 2020-06-25 | 1 |  | 208 | 2 | 209 | 2019 | 2020 | R16
160079224501 | 162631224501 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-23 | 2021-03-23 | 2021-03-23 |  | 2021-11-05 | Underground | R16 | 2021-05-05 | 1 |  | 32 | 133 | 164 | 2021 | 2021 | R16
160102160366 | 163956160366 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-06 | 2019-08-06 | 2019-08-06 | 2020-01-22 | 2021-11-10 | Overhead | R16 | 2020-01-22 | 1 |  | 122 | 471 | 592 | 2019 | 2021 | R16
163063164365 | 165548164365 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-15 | 2019-08-15 | 2019-09-13 | 2019-11-15 | 2019-11-26 | Underground | R16 | 2019-11-15 | 1 | 22 | 46 | 8 | 74 | 2019 | 2019 | R16
168297180259 | 168915180259 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-03 | 2019-09-03 | 2020-02-13 | 2020-08-12 | 2020-10-06 | Underground | R16 | 2020-08-12 | 1 | 118 | 130 | 40 | 286 | 2019 | 2020 | R16
164279170455 | 160839170455 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-02 | 2019-11-02 | 2019-11-02 | 2019-12-17 | 2019-12-18 | Overhead | R16 | 2019-12-17 | 0 |  | 32 | 2 | 33 | 2019 | 2019 | R16
165081158469 | 164954158469 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-19 | 2019-06-19 | 2019-07-20 | 2020-06-05 | 2021-01-14 | Underground | R16 | 2020-06-05 | 1 | 23 | 230 | 160 | 412 | 2019 | 2021 | R16
160433225286 | 162777225286 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-03-23 | 2021-03-29 | 2021-03-30 |  | 2022-02-01 | Overhead | R16 | 2021-12-13 | 5 | 2 | 185 | 37 | 226 | 2021 | 2022 | R16
163922170210 | 166412170210 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-11 | 2019-10-30 | 2019-10-30 | 2020-01-22 | 2021-11-10 | Overhead | R16 | 2020-01-22 | 14 |  | 61 | 471 | 544 | 2019 | 2021 | R16
161901185026 | 163800185026 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-19 | 2019-11-27 | 2020-03-23 | 2021-10-11 | 2021-10-14 | Underground | R16 | 2021-10-11 | 7 | 84 | 406 | 4 | 498 | 2019 | 2021 | R16
160590165042 | 161433165042 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-09-17 | 2019-09-17 | 2019-09-18 | 2019-12-20 | 2019-12-18 | Underground | R16 | 2019-12-20 | 1 | 2 | 68 |  | 67 | 2019 | 2019 | R16
162518167668 | 165810167668 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-09 | 2019-10-09 | 2019-10-10 | 2020-02-12 | 2020-06-09 | Overhead | R16 | 2020-02-12 | 1 | 2 | 90 | 85 | 175 | 2019 | 2020 | R16
160504250796 | 166741250796 | NON-RESIDENTIAL - SMALL RETAIL | OH R16 RES NON RES OS | Commercial | 2021-04-08 | 2021-06-25 | 2021-10-06 |  | 2023-01-05 | Overhead | R16 |  | 57 | 74 |  |  | 456 | 2021 | 2023 | R16
161160175183 | 164988175183 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OD | Commercial | 2019-06-18 | 2019-07-12 | 2019-12-26 | 2019-12-30 | 2021-04-05 | Overhead | R16 | 2019-12-30 | 19 | 120 | 3 | 331 | 470 | 2019 | 2021 | R16
164409169116 | 166118169116 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-19 | 2019-10-22 | 2019-10-22 | 2019-11-22 | 2020-01-03 | Overhead | R16 | 2019-11-22 | 47 |  | 24 | 31 | 100 | 2019 | 2020 | R16
162550171904 | 163178171904 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-14 | 2019-11-14 | 2019-11-14 | 2020-02-21 | 2020-06-09 | Overhead | R16 | 2020-02-21 | 1 |  | 72 | 78 | 149 | 2019 | 2020 | R16
160670244110 | 165146244110 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-01 | 2021-04-01 | 2021-08-17 |  | 2021-11-09 | Underground | R16 | 2021-09-23 | 1 | 99 | 28 | 34 | 159 | 2021 | 2021 | R16
164255207544 | 165229207544 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-07 | 2019-10-07 | 2020-10-16 | 2021-04-28 | 2021-05-03 | Underground | R16 | 2021-04-28 | 1 | 270 | 139 | 4 | 411 | 2019 | 2021 | R16
164311164081 | 160384164081 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-11 | 2019-09-11 | 2019-09-11 | 2019-11-04 | 2019-11-04 | Overhead | R16 | 2019-11-04 | 1 |  | 39 |  | 39 | 2019 | 2019 | R16
164905171355 | 162367171355 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-11 | 2019-11-11 | 2019-11-11 | 2019-12-18 | 2019-12-19 | Overhead | R16 | 2019-12-18 | 1 |  | 28 | 2 | 29 | 2019 | 2019 | R16
168448159575 | 161163159575 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-22 | 2019-07-30 | 2019-07-30 | 2019-10-08 | 2019-10-16 | Overhead | R16 | 2019-10-08 | 7 |  | 51 | 7 | 63 | 2019 | 2019 | R16
168141165756 | 168734165756 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-03 | 2019-09-03 | 2019-09-25 | 2020-05-06 | 2020-07-08 | Underground | R16 | 2020-05-06 | 1 | 17 | 161 | 46 | 222 | 2019 | 2020 | R16
163293156232 | 165881156232 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-24 | 2019-06-24 | 2019-06-24 | 2019-07-25 | 2019-08-26 | Underground | R16 | 2019-07-25 | 1 |  | 24 | 23 | 46 | 2019 | 2019 | R16
160948227913 | 168129227913 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-15 | 2021-04-15 | 2021-04-22 |  | 2021-11-08 | Underground | R16 | 2021-05-25 | 1 | 6 | 24 | 120 | 148 | 2021 | 2021 | R16
165153159754 | 168720159754 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-08 | 2019-07-08 | 2019-08-01 | 2019-09-05 | 2019-09-05 | Underground | R16 | 2019-09-05 | 1 | 19 | 26 |  | 44 | 2019 | 2019 | R16
166019157630 | 169580157630 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-11 | 2019-07-11 | 2019-07-11 | 2019-09-25 | 2019-09-26 | Overhead | R16 | 2019-09-25 | 1 |  | 55 | 2 | 56 | 2019 | 2019 | R16
166263161606 | 169881161606 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-15 | 2019-07-15 | 2019-08-19 | 2020-07-20 | 2020-08-28 | Underground | R16 | 2020-07-20 | 1 | 26 | 241 | 30 | 295 | 2019 | 2020 | R16
162701175618 | 165579175618 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-02 | 2019-12-02 | 2020-01-02 | 2020-03-16 | 2020-03-18 | Underground | R16 | 2020-03-16 | 1 | 24 | 53 | 3 | 78 | 2019 | 2020 | R16
164407162343 | 167386162343 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-26 | 2019-08-26 | 2019-08-26 | 2019-09-30 | 2019-12-04 | Overhead | R16 | 2019-09-30 | 1 |  | 26 | 48 | 73 | 2019 | 2019 | R16
169663164927 | 160608164927 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-12 | 2019-09-17 | 2019-09-17 | 2019-10-22 | 2020-04-01 | Overhead | R16 | 2019-10-22 | 4 |  | 26 | 117 | 145 | 2019 | 2020 | R16
161125226069 | 166229226069 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-07 | 2021-04-07 | 2021-04-07 |  | 2021-08-11 | Overhead | R16 | 2021-06-30 | 1 |  | 61 | 31 | 91 | 2021 | 2021 | R16
163463175246 | 165312175246 | FOREIGN UTILITY | OH R16 RES NON RES OD | Commercial | 2019-08-13 | 2019-09-11 | 2019-12-27 | 2020-07-08 | 2020-10-05 | Overhead | R16 | 2020-07-08 | 22 | 78 | 139 | 64 | 300 | 2019 | 2020 | R16
169017165702 | 162757165702 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-24 | 2019-09-24 | 2019-09-24 | 2019-11-27 | 2020-03-25 | Overhead | R16 | 2019-11-27 | 1 |  | 47 | 86 | 132 | 2019 | 2020 | R16
169429171200 | 169596171200 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-06 | 2019-09-06 | 2019-11-08 | 2020-06-24 | 2020-08-28 | Underground | R16 | 2020-06-24 | 1 | 46 | 164 | 48 | 256 | 2019 | 2020 | R16
162419170042 | 163674170042 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-30 | 2019-09-30 | 2019-10-29 | 2020-02-10 | 2020-02-11 | Underground | R16 | 2020-02-10 | 1 | 22 | 75 | 2 | 97 | 2019 | 2020 | R16
166826170708 | 161208170708 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-05 | 2019-11-05 | 2019-11-05 | 2020-01-10 | 2021-11-10 | Overhead | R16 | 2020-01-10 | 1 |  | 49 | 479 | 527 | 2019 | 2021 | R16
160468179604 | 161430179604 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-17 | 2019-09-17 | 2020-02-06 | 2021-08-13 | 2021-08-17 | Underground | R16 | 2021-08-13 | 1 | 103 | 397 | 3 | 501 | 2019 | 2021 | R16
165051156212 | 165886156212 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-25 | 2019-06-25 | 2019-06-25 | 2019-09-11 | 2019-09-12 | Overhead | R16 | 2019-09-11 | 1 |  | 57 | 2 | 58 | 2019 | 2019 | R16
161407226436 | 167078226436 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-12 | 2021-04-12 | 2021-04-12 |  | 2021-11-05 | Overhead | R16 | 2021-05-04 | 1 |  | 17 | 134 | 150 | 2021 | 2021 | R16
169840174680 | 163411174680 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-15 | 2019-11-15 | 2019-12-17 | 2020-01-06 | 2020-01-07 | Underground | R16 | 2020-01-06 | 1 | 23 | 15 | 2 | 38 | 2019 | 2020 | R16
167742165771 | 163033165771 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-25 | 2019-09-25 | 2019-09-25 | 2019-12-19 | 2022-05-17 | Overhead | R16 | 2019-12-19 | 1 |  | 62 | 629 | 690 | 2019 | 2022 | R16
161368167454 | 165755167454 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-09 | 2019-10-09 | 2019-10-09 | 2020-05-18 | 2020-05-19 | Overhead | R16 | 2020-05-18 | 1 |  | 159 | 2 | 160 | 2019 | 2020 | R16
163173159894 | 163496159894 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-02 | 2019-08-02 | 2019-08-02 | 2019-08-26 | 2019-08-27 | Overhead | R16 | 2019-08-26 | 1 |  | 17 | 2 | 18 | 2019 | 2019 | R16
165335158027 | 160128158027 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-16 | 2019-07-16 | 2019-07-16 | 2019-11-19 | 2019-11-26 | Underground | R16 | 2019-11-19 | 1 |  | 91 | 6 | 96 | 2019 | 2019 | R16
169136159617 | 163023159617 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-31 | 2019-07-31 | 2019-07-31 | 2020-01-02 | 2021-11-13 | Overhead | R16 | 2020-01-02 | 1 |  | 112 | 487 | 598 | 2019 | 2021 | R16
162501160968 | 165200160968 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-08-13 | 2019-08-13 | 2019-08-13 | 2019-10-11 | 2019-10-16 | Underground | R16 | 2019-10-11 | 1 |  | 44 | 4 | 47 | 2019 | 2019 | R16
166052155679 | 164232155679 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-15 | 2019-06-15 | 2019-06-19 | 2020-07-09 | 2020-07-13 | Overhead | R16 | 2020-07-09 | 0 | 3 | 277 | 3 | 281 | 2019 | 2020 | R16
167955163413 | 169383163413 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-05 | 2019-09-05 | 2019-09-05 | 2019-09-30 | 2022-07-19 | Overhead | R16 | 2019-09-30 | 1 |  | 18 | 732 | 749 | 2019 | 2022 | R16
168416174605 | 168213174605 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2019-12-13 | 2019-12-16 | 2019-12-16 | 2020-07-02 | 2020-07-06 | Overhead | R16 | 2020-07-02 | 2 |  | 144 | 3 | 147 | 2019 | 2020 | R16
161064172306 | 163821172306 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-19 | 2019-11-19 | 2019-11-19 | 2020-01-10 | 2020-01-13 | Overhead | R16 | 2020-01-10 | 1 |  | 39 | 2 | 40 | 2019 | 2020 | R16
168547167297 | 165465167297 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-08 | 2019-10-08 | 2019-10-08 | 2020-01-24 | 2020-01-28 | Overhead | R16 | 2020-01-24 | 1 |  | 79 | 3 | 81 | 2019 | 2020 | R16
162420160127 | 163735160127 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-05 | 2019-08-05 | 2019-08-05 | 2019-08-20 | 2019-08-21 | Overhead | R16 | 2019-08-20 | 1 |  | 12 | 2 | 13 | 2019 | 2019 | R16
162401228698 | 161178228698 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-29 | 2021-04-30 | 2021-04-30 |  | 2022-08-03 | Overhead | R16 | 2022-06-08 | 2 |  | 289 | 41 | 330 | 2021 | 2022 | R16
162403224870 | 163744224870 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-26 | 2021-03-26 | 2021-03-26 |  | 2021-11-02 | Overhead | R16 | 2021-06-15 | 1 |  | 58 | 101 | 158 | 2021 | 2021 | R16
168170164062 | 160148164062 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-09-10 | 2019-09-10 | 2019-09-10 |  | 2020-02-04 | Underground | R16 |  | 1 |  |  |  | 106 | 2019 | 2020 | R16
167964162678 | 168426162678 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-29 | 2019-08-29 | 2019-08-29 | 2019-09-18 | 2019-09-18 | Overhead | R16 | 2019-09-18 | 1 |  | 15 |  | 15 | 2019 | 2019 | R16
166438158935 | 160118158935 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-15 | 2019-07-18 | 2019-07-25 | 2019-08-21 | 2019-08-22 | Underground | R16 | 2019-08-21 | 4 | 6 | 20 | 2 | 29 | 2019 | 2019 | R16
166008158540 | 169087158540 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-10 | 2019-07-21 | 2019-07-21 | 2019-11-12 | 2019-11-21 | Overhead | R16 | 2019-11-12 | 8 |  | 82 | 8 | 97 | 2019 | 2019 | R16
162697161157 | 165676161157 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2019-08-15 | 2019-08-15 | 2019-08-15 | 2019-12-30 | 2020-01-02 | Overhead | R16 | 2019-12-30 | 1 |  | 98 | 4 | 101 | 2019 | 2020 | R16
169385158454 | 169460158454 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-11 | 2019-07-12 | 2019-07-19 | 2019-10-28 | 2019-10-30 | Underground | R16 | 2019-10-28 | 2 | 6 | 72 | 3 | 80 | 2019 | 2019 | R16
162781226153 | 166433226153 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-07 | 2021-04-07 | 2021-04-07 |  | 2021-10-11 | Overhead | R16 | 2021-09-13 | 1 |  | 114 | 21 | 134 | 2021 | 2021 | R16
162989227891 | 166948227891 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-09 | 2021-04-20 | 2021-04-21 |  | 2021-08-18 | Overhead | R16 | 2021-06-16 | 8 | 2 | 41 | 46 | 94 | 2021 | 2021 | R16
164765173923 | 166523173923 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-06 | 2019-12-06 | 2019-12-09 | 2020-03-03 | 2020-06-09 | Overhead | R16 | 2020-03-03 | 1 | 2 | 62 | 71 | 133 | 2019 | 2020 | R16
163061249772 | 168486249772 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-09-28 | 2021-09-28 | 2021-09-28 |  | 2021-11-09 | Overhead | R16 |  | 1 |  |  |  | 31 | 2021 | 2021 | R16
163814157996 | 160393157996 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-17 | 2019-07-17 | 2019-07-17 | 2020-08-12 | 2021-01-21 | Overhead | R16 | 2020-08-12 | 1 |  | 281 | 117 | 397 | 2019 | 2021 | R16
163918167217 | 165403167217 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-08 | 2019-10-08 | 2019-10-08 | 2020-01-19 | 2020-01-21 | Overhead | R16 | 2020-01-19 | 1 |  | 74 | 2 | 76 | 2019 | 2020 | R16
168006197222 | 168435197222 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-30 | 2020-05-12 | 2020-07-13 | 2022-10-04 | 2022-10-11 | Underground | R16 | 2022-10-04 | 183 | 45 | 582 | 6 | 813 | 2019 | 2022 | R16
165233157669 | 164856157669 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-18 | 2019-06-18 | 2019-07-12 | 2019-11-29 | 2019-12-02 | Underground | R16 | 2019-11-29 | 1 | 19 | 101 | 2 | 120 | 2019 | 2019 | R16
163214260555 | 164712260555 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-12-09 | 2021-12-09 | 2021-12-09 |  | 2022-08-01 | Underground | R16 | 2022-07-28 | 1 |  | 166 | 3 | 168 | 2021 | 2022 | R16
160413157821 | 169724157821 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-08-28 | 2019-09-18 | Overhead | R16 | 2019-08-28 | 0 |  | 33 | 16 | 48 | 2019 | 2019 | R16
165155157611 | 169441157611 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-11 | 2019-07-11 | 2019-07-11 | 2019-08-28 | 2019-09-18 | Overhead | R16 | 2019-08-28 | 1 |  | 35 | 16 | 50 | 2019 | 2019 | R16
167184174912 | 168086174912 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-12-13 | 2019-12-13 | 2019-12-19 | 2020-07-30 | 2020-10-06 | Underground | R16 | 2020-07-30 | 1 | 5 | 161 | 49 | 213 | 2019 | 2020 | R16
165747161190 | 165763161190 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC DEVELOPMENT | Residential | 2019-08-15 | 2019-08-15 | 2019-08-15 | 2021-06-01 | 2021-04-01 | Underground | R16 | 2021-06-01 | 1 |  | 469 |  | 426 | 2019 | 2021 | R16
165876173762 | 166725173762 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-06 | 2019-12-06 | 2019-12-06 | 2019-12-23 | 2019-12-18 | Underground | R16 | 2019-12-23 | 1 |  | 12 |  | 9 | 2019 | 2019 | R16
160771163319 | 160588163319 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH CP R16 WORK RELO TO UG | Commercial | 2019-07-18 | 2019-07-29 | 2019-09-04 | 2019-10-31 | 2020-04-29 | Overhead | R16 | 2019-10-31 | 8 | 28 | 42 | 130 | 205 | 2019 | 2020 | R16
163383231369 | 164528231369 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-03-30 | 2021-04-21 | 2021-05-19 |  | 2021-08-23 | Underground | R16 |  | 17 | 21 |  |  | 105 | 2021 | 2021 | R16
168867174916 | 161904174916 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-09-19 | 2019-09-19 | 2019-12-19 | 2019-12-31 | 2020-03-02 | Overhead | R16 | 2019-12-31 | 1 | 66 | 9 | 45 | 118 | 2019 | 2020 | R16
160669166003 | 162955166003 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-25 | 2019-09-26 | 2019-09-27 | 2019-11-27 | 2020-06-09 | Overhead | R16 | 2019-11-27 | 2 | 2 | 44 | 140 | 185 | 2019 | 2020 | R16
160723173856 | 166614173856 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-09 | 2019-12-09 | 2019-12-09 | 2020-01-09 | 2020-01-10 | Overhead | R16 | 2020-01-09 | 1 |  | 24 | 2 | 25 | 2019 | 2020 | R16
166426156486 | 166433156486 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-27 | 2019-06-27 | 2019-06-27 | 2019-08-07 | 2021-10-20 | Overhead | R16 | 2019-08-07 | 1 |  | 30 | 576 | 605 | 2019 | 2021 | R16
168875198966 | 167573198966 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG ELEC MISC SVC US | Residential | 2019-07-01 | 2019-07-02 | 2020-07-29 | 2020-08-13 | 2022-08-29 | Underground | R16 | 2020-08-13 | 2 | 282 | 12 | 533 | 826 | 2019 | 2022 | R16
168511166673 | 167484166673 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-26 | 2019-08-26 | 2019-10-02 | 2020-10-01 | 2021-01-02 | Underground | R16 | 2020-10-01 | 1 | 28 | 262 | 67 | 355 | 2019 | 2021 | R16
162696168314 | 165180168314 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-07 | 2019-10-07 | 2019-10-16 | 2020-07-13 | 2020-12-15 | Underground | R16 | 2020-07-13 | 1 | 8 | 194 | 112 | 312 | 2019 | 2020 | R16
163278163142 | 168776163142 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-03 | 2019-09-03 | 2019-09-03 | 2019-09-18 | 2019-09-19 | Overhead | R16 | 2019-09-18 | 1 |  | 12 | 2 | 13 | 2019 | 2019 | R16
162762169584 | 165952169584 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-16 | 2019-08-16 | 2019-10-25 | 2019-12-23 | 2020-02-06 | Underground | R16 | 2019-12-23 | 1 | 51 | 42 | 34 | 125 | 2019 | 2020 | R16
162736161214 | 164871161214 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-09 | 2019-08-09 | 2019-08-15 | 2019-08-22 | 2019-09-05 | Underground | R16 | 2019-08-22 | 1 | 5 | 6 | 11 | 20 | 2019 | 2019 | R16
160620166768 | 160830166768 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-12 | 2019-09-12 | 2019-10-03 | 2022-02-16 | 2022-02-17 | Underground | R16 | 2022-02-16 | 1 | 16 | 620 | 2 | 636 | 2019 | 2022 | R16
166012158441 | 160971158441 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-19 | 2019-07-19 | 2019-07-19 | 2019-08-28 | 2019-08-29 | Overhead | R16 | 2019-08-28 | 1 |  | 29 | 2 | 30 | 2019 | 2019 | R16
168027178272 | 169285178272 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-26 | 2020-01-16 | 2020-01-27 | 2020-07-21 | 2020-09-23 | Underground | R16 | 2020-07-21 | 59 | 8 | 127 | 47 | 238 | 2019 | 2020 | R16
160598174458 | 161806174458 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-07 | 2019-11-07 | 2019-12-13 | 2020-04-14 | 2020-04-15 | Underground | R16 | 2020-04-14 | 1 | 27 | 88 | 2 | 115 | 2019 | 2020 | R16
162108174362 | 161027174362 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-04 | 2019-11-04 | 2019-12-13 | 2020-01-14 | 2020-01-15 | Overhead | R16 | 2020-01-14 | 1 | 30 | 23 | 2 | 53 | 2019 | 2020 | R16
160816224909 | 166350224909 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OD | Residential | 2019-12-04 | 2020-10-19 | 2021-03-26 | 2021-05-26 | 2021-06-29 | Overhead | R16 | 2021-05-26 | 229 | 115 | 44 | 25 | 410 | 2019 | 2021 | R16
160617161776 | 163448161776 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-03 | 2019-08-03 | 2019-08-22 | 2020-02-12 | 2020-06-09 | Underground | R16 | 2020-02-12 | 0 | 14 | 125 | 85 | 222 | 2019 | 2020 | R16
162409162328 | 167527162328 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-26 | 2019-08-26 | 2019-08-27 | 2019-11-12 | 2019-11-21 | Overhead | R16 | 2019-11-12 | 1 | 2 | 56 | 8 | 64 | 2019 | 2019 | R16
169567175203 | 168425175203 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-07-06 | 2019-12-26 | 2019-12-26 | 2020-03-19 | 2020-03-21 | Overhead | R16 | 2020-03-19 | 124 |  | 61 | 2 | 185 | 2019 | 2020 | R16
164724231299 | 168490231299 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-19 | 2021-05-19 | 2021-05-19 |  | 2022-11-22 | Overhead | R16 | 2022-11-21 | 1 |  | 394 | 2 | 395 | 2021 | 2022 | R16
162156173350 | 165672173350 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-02 | 2019-12-02 | 2019-12-02 | 2020-02-14 | 2020-06-09 | Overhead | R16 | 2020-02-14 | 1 |  | 55 | 83 | 137 | 2019 | 2020 | R16
165212170265 | 165434170265 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-08 | 2019-10-08 | 2019-10-30 | 2019-11-19 | 2019-12-30 | Underground | R16 | 2019-11-19 | 1 | 17 | 15 | 30 | 60 | 2019 | 2019 | R16
168376175533 | 169618175533 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-28 | 2019-10-28 | 2020-01-02 | 2020-06-08 | 2020-10-26 | Underground | R16 | 2020-06-08 | 1 | 49 | 113 | 101 | 261 | 2019 | 2020 | R16
164783241125 | 166969241125 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2021-04-09 | 2021-07-19 | 2021-07-28 |  | 2023-01-05 | Overhead | R16 |  | 72 | 8 |  |  | 455 | 2021 | 2023 | R16
166177157569 | 169232157569 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-10 | 2019-07-10 | 2019-07-10 | 2019-10-01 | 2019-10-16 | Overhead | R16 | 2019-10-01 | 1 |  | 60 | 12 | 71 | 2019 | 2019 | R16
163841167504 | 165579167504 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2019-10-09 | 2019-10-09 | 2019-10-09 | 2020-06-04 | 2020-06-05 | Overhead | R16 | 2020-06-04 | 1 |  | 172 | 2 | 173 | 2019 | 2020 | R16
161520170464 | 162812170464 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-25 | 2019-10-31 | 2019-11-01 | 2020-01-02 | 2021-11-13 | Overhead | R16 | 2020-01-02 | 27 | 2 | 45 | 487 | 558 | 2019 | 2021 | R16
164280196771 | 162515196771 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-11-11 | 2019-11-27 | 2020-07-09 | 2020-12-17 | 2021-01-21 | Underground | R16 | 2020-12-17 | 13 | 162 | 116 | 26 | 314 | 2019 | 2021 | R16
168006197221 | 168572197221 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-08-30 | 2020-02-13 | 2020-07-13 | 2022-04-20 | 2022-05-17 | Underground | R16 | 2022-04-20 | 120 | 108 | 463 | 20 | 708 | 2019 | 2022 | R16
162219169442 | 168915169442 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-24 | 2019-10-24 | 2019-10-24 | 2020-01-10 | 2020-01-29 | Overhead | R16 | 2020-01-10 | 1 |  | 57 | 14 | 70 | 2019 | 2020 | R16
161028157332 | 163592157332 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-12 | 2019-06-12 | 2019-07-09 | 2019-12-05 | 2019-12-06 | Underground | R16 | 2019-12-05 | 1 | 20 | 108 | 2 | 128 | 2019 | 2019 | R16
163720165513 | 163742165513 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-05 | 2019-08-05 | 2019-09-24 | 2019-10-22 | 2019-10-23 | Underground | R16 | 2019-10-22 | 1 | 37 | 21 | 2 | 58 | 2019 | 2019 | R16
161467168384 | 167163168384 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-16 | 2019-10-16 | 2019-10-16 | 2020-10-02 | 2020-10-05 | Overhead | R16 | 2020-10-02 | 1 |  | 253 | 2 | 254 | 2019 | 2020 | R16
168183171767 | 162909171767 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-13 | 2019-11-13 | 2019-11-13 | 2020-01-08 | 2021-10-28 | Overhead | R16 | 2020-01-08 | 1 |  | 41 | 472 | 512 | 2019 | 2021 | R16
168180166573 | 161833166573 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-24 | 2019-07-24 | 2019-10-02 | 2019-11-27 | 2020-01-02 | Underground | R16 | 2019-11-27 | 1 | 51 | 41 | 27 | 117 | 2019 | 2020 | R16
160635176704 | 165996176704 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE FOR UPGRADE UD | Commercial | 2019-12-04 | 2019-12-11 | 2020-01-13 | 2020-01-28 | 2020-07-07 | Underground | R16 | 2020-01-28 | 6 | 24 | 12 | 116 | 155 | 2019 | 2020 | R16
166195171684 | 168782171684 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-23 | 2019-11-13 | 2019-11-13 | 2020-01-23 | 2021-11-10 | Overhead | R16 | 2020-01-23 | 16 |  | 52 | 470 | 536 | 2019 | 2021 | R16
164124156479 | 166357156479 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-06-26 | 2019-06-26 | 2019-06-26 | 2019-08-09 | 2019-12-06 | Overhead | R16 | 2019-08-09 | 1 |  | 33 | 86 | 118 | 2019 | 2019 | R16
165575158217 | 167397158217 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-01 | 2019-07-01 | 2019-07-18 | 2019-08-14 | 2019-08-15 | Underground | R16 | 2019-08-14 | 1 | 14 | 20 | 2 | 34 | 2019 | 2019 | R16
165945226956 | 167648226956 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-13 | 2021-04-13 | 2021-04-15 |  | 2021-11-01 | Overhead | R16 | 2021-09-28 | 1 | 3 | 119 | 25 | 145 | 2021 | 2021 | R16
165932159693 | 162829159693 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-07-30 | 2019-08-01 | 2019-08-01 | 2020-02-25 | 2020-02-26 | Underground | R16 | 2020-02-25 | 3 |  | 149 | 2 | 152 | 2019 | 2020 | R16
169228172620 | 161352172620 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-06 | 2019-11-06 | 2019-11-21 | 2020-04-13 | 2020-06-29 | Underground | R16 | 2020-04-13 | 1 | 12 | 103 | 56 | 169 | 2019 | 2020 | R16
167977261083 | 167979261083 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-10-21 | 2019-10-21 | 2021-12-13 | 2022-03-25 | 2022-04-13 | Underground | R16 | 2022-03-25 | 1 | 561 | 75 | 14 | 648 | 2019 | 2022 | R16
164960175341 | 165042175341 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-10-05 | 2019-10-05 | 2019-12-30 | 2021-02-17 | 2021-04-01 | Underground | R16 | 2021-02-17 | 0 | 61 | 298 | 32 | 389 | 2019 | 2021 | R16
163920177538 | 163808177538 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-01 | 2019-10-01 | 2020-01-21 | 2020-03-24 | 2020-03-24 | Underground | R16 | 2020-03-24 | 1 | 81 | 46 |  | 126 | 2019 | 2020 | R16
164862163953 | 160181163953 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-10 | 2019-09-10 | 2019-09-10 | 2019-12-26 | 2020-01-08 | Overhead | R16 | 2019-12-26 | 1 |  | 78 | 10 | 87 | 2019 | 2020 | R16
169348162654 | 168234162654 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-29 | 2019-08-29 | 2019-08-29 | 2020-07-29 | 2020-10-02 | Overhead | R16 | 2020-07-29 | 1 |  | 240 | 48 | 287 | 2019 | 2020 | R16
160098157173 | 167798157173 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-07-02 | 2019-07-03 | 2019-07-08 | 2019-08-21 | 2020-04-01 | Underground | R16 | 2019-08-21 | 2 | 4 | 33 | 161 | 197 | 2019 | 2020 | R16
163433162616 | 165369162616 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-14 | 2019-08-29 | 2019-08-29 | 2020-03-20 | 2020-06-09 | Overhead | R16 | 2020-03-20 | 12 |  | 147 | 58 | 215 | 2019 | 2020 | R16
168149169175 | 168351169175 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-10-22 | 2019-10-22 | 2019-10-22 | 2020-05-08 | 2020-05-11 | Overhead | R16 | 2020-05-08 | 1 |  | 144 | 2 | 145 | 2019 | 2020 | R16
166331282730 | 165423282730 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2022-05-20 | 2022-05-31 | 2022-06-15 |  | 2023-06-23 | Underground | R16 |  | 8 | 12 |  |  | 286 | 2022 | 2023 | R16
165151157405 | 169213157405 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-10 | 2019-07-10 | 2019-07-10 | 2019-08-28 | 2019-09-10 | Overhead | R16 | 2019-08-28 | 1 |  | 36 | 10 | 45 | 2019 | 2019 | R16
166331282576 | 165424282576 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2022-05-20 | 2022-05-25 | 2022-06-15 |  | 2023-06-23 | Underground | R16 |  | 4 | 16 |  |  | 286 | 2022 | 2023 | R16
163168162318 | 167620162318 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-26 | 2019-08-27 | 2019-08-27 | 2019-11-12 | 2019-11-21 | Overhead | R16 | 2019-11-12 | 2 |  | 56 | 8 | 64 | 2019 | 2019 | R16
166341228967 | 161922228967 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-30 | 2021-04-30 | 2021-04-30 |  | 2021-10-11 | Overhead | R16 | 2021-09-13 | 1 |  | 97 | 21 | 117 | 2021 | 2021 | R16
162989175619 | 165640175619 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-02 | 2019-12-02 | 2020-01-02 | 2020-01-09 | 2021-03-11 | Underground | R16 | 2020-01-09 | 1 | 24 | 6 | 306 | 334 | 2019 | 2021 | R16
161620172752 | 164996172752 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-25 | 2019-11-25 | 2019-11-25 | 2020-02-12 | 2020-06-09 | Overhead | R16 | 2020-02-12 | 1 |  | 58 | 85 | 142 | 2019 | 2020 | R16
169351263855 | 169852263855 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-09 | 2019-09-09 | 2022-01-07 | 2022-01-10 | 2022-01-26 | Overhead | R16 | 2022-01-10 | 1 | 610 | 2 | 13 | 623 | 2019 | 2022 | R16
164094321667 | 163838321667 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-06 | 2023-06-06 | 2023-06-09 | 2023-07-28 | 2023-07-28 | Overhead | R16 | 2023-07-28 | 1 | 4 | 36 |  | 39 | 2023 | 2023 | R16
164946165036 | 165140165036 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-12 | 2019-08-12 | 2019-09-18 | 2019-10-16 | 2019-11-13 | Underground | R16 | 2019-10-16 | 1 | 28 | 21 | 21 | 68 | 2019 | 2019 | R16
166518254824 | 163121254824 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-10-17 | 2021-10-17 | 2021-11-02 |  | 2021-12-29 | Overhead | R16 |  | 0 | 12 |  |  | 53 | 2021 | 2021 | R16
168325187509 | 169432187509 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-10-26 | 2020-01-28 | 2020-04-14 | 2020-12-11 | 2021-04-01 | Underground | R16 | 2020-12-11 | 67 | 56 | 174 | 80 | 374 | 2019 | 2021 | R16
164633172246 | 169415172246 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-09-05 | 2019-09-05 | 2019-11-19 | 2020-01-28 | 2020-06-18 | Overhead | R16 | 2020-01-28 | 1 | 54 | 51 | 103 | 206 | 2019 | 2020 | R16
162702173343 | 165621173343 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-12-02 | 2019-12-02 | 2019-12-02 | 2019-12-03 | 2020-04-29 | Overhead | R16 | 2019-12-03 | 1 |  | 2 | 107 | 108 | 2019 | 2020 | R16
163350167442 | 165405167442 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-08 | 2019-10-08 | 2019-10-08 | 2019-11-12 | 2019-11-21 | Overhead | R16 | 2019-11-12 | 1 |  | 26 | 8 | 33 | 2019 | 2019 | R16
166672227110 | 168405227110 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-16 | 2021-04-16 | 2021-04-16 |  | 2021-08-18 | Overhead | R16 | 2021-06-16 | 1 |  | 44 | 46 | 89 | 2021 | 2021 | R16
165756158096 | 160750158096 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-17 | 2019-07-17 | 2019-07-17 | 2019-08-28 | 2023-06-08 | Overhead | R16 | 2019-08-28 | 1 |  | 31 | 987 | 1017 | 2019 | 2023 | R16
165369155666 | 163770155666 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-13 | 2019-06-13 | 2019-06-18 | 2019-07-30 | 2019-09-03 | Overhead | R16 | 2019-07-30 | 1 | 4 | 31 | 26 | 59 | 2019 | 2019 | R16
169710164875 | 160227164875 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-09-10 | 2019-09-10 | 2019-09-18 | 2019-10-01 | 2019-10-03 | Underground | R16 | 2019-10-01 | 1 | 7 | 10 | 3 | 18 | 2019 | 2019 | R16
160100158637 | 161553158637 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-23 | 2019-07-23 | 2019-07-23 | 2019-08-20 | 2019-08-21 | Overhead | R16 | 2019-08-20 | 1 |  | 21 | 2 | 22 | 2019 | 2019 | R16
163739161851 | 166767161851 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-21 | 2019-08-21 | 2019-08-21 | 2019-10-11 | 2019-10-28 | Overhead | R16 | 2019-10-11 | 1 |  | 38 | 12 | 49 | 2019 | 2019 | R16
166236167473 | 161131167473 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-14 | 2019-09-14 | 2019-10-09 | 2019-11-19 | 2019-11-20 | Underground | R16 | 2019-11-19 | 0 | 18 | 30 | 2 | 48 | 2019 | 2019 | R16
164798163452 | 169384163452 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-05 | 2019-09-05 | 2019-09-05 | 2019-12-19 | 2020-06-09 | Overhead | R16 | 2019-12-19 | 1 |  | 76 | 124 | 199 | 2019 | 2020 | R16
161648193647 | 163428193647 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-11-15 | 2020-04-17 | 2020-06-08 | 2020-10-12 | 2021-01-07 | Underground | R16 | 2020-10-12 | 111 | 37 | 91 | 64 | 300 | 2019 | 2021 | R16
166522159566 | 160032159566 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-15 | 2019-07-17 | 2019-07-30 | 2019-10-01 | 2019-10-01 | Underground | R16 | 2019-10-01 | 3 | 10 | 46 |  | 57 | 2019 | 2019 | R16
161904163103 | 168827163103 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-09-03 | 2019-09-03 | 2019-09-03 | 2021-07-15 | 2022-03-22 | Underground | R16 | 2021-07-15 | 1 |  | 488 | 179 | 666 | 2019 | 2022 | R16
167412170468 | 160789170468 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-01 | 2019-11-01 | 2019-11-01 | 2020-01-28 | 2020-01-29 | Overhead | R16 | 2020-01-28 | 1 |  | 63 | 2 | 64 | 2019 | 2020 | R16
160911162173 | 167105162173 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-08-24 | 2019-08-24 | 2019-08-24 | 2020-01-30 | 2020-01-31 | Underground | R16 | 2020-01-30 | 0 |  | 114 | 2 | 115 | 2019 | 2020 | R16
167416229715 | 163502229715 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-06 | 2021-05-06 | 2021-05-06 |  | 2021-10-27 | Overhead | R16 | 2021-06-21 | 1 |  | 33 | 93 | 125 | 2021 | 2021 | R16
167204165408 | 162568165408 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-24 | 2019-09-24 | 2019-09-24 | 2020-01-02 | 2021-11-13 | Overhead | R16 | 2020-01-02 | 1 |  | 73 | 487 | 559 | 2019 | 2021 | R16
167195165888 | 162939165888 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-26 | 2019-09-26 | 2019-09-26 | 2019-10-15 | 2019-11-04 | Overhead | R16 | 2019-10-15 | 1 |  | 14 | 15 | 28 | 2019 | 2019 | R16
163608188569 | 168796188569 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-09-02 | 2020-01-24 | 2020-04-21 | 2021-03-18 | 2021-05-03 | Underground | R16 | 2021-03-18 | 105 | 63 | 238 | 33 | 436 | 2019 | 2021 | R16
160815166787 | 164601166787 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-10-03 | 2019-10-03 | 2019-10-03 | 2020-01-14 | 2020-01-17 | Overhead | R16 | 2020-01-14 | 1 |  | 74 | 4 | 77 | 2019 | 2020 | R16
162521175609 | 163763175609 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-30 | 2019-09-30 | 2020-01-02 | 2020-06-08 | 2020-12-16 | Underground | R16 | 2020-06-08 | 1 | 69 | 113 | 138 | 318 | 2019 | 2020 | R16
168255225547 | 160165225547 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-30 | 2021-03-03 | 2021-04-01 | 2022-03-21 | 2022-05-03 | Underground | R16 | 2022-03-21 | 351 | 22 | 253 | 32 | 655 | 2019 | 2022 | R16
168683172533 | 161454172533 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-11-05 | 2019-11-06 | 2019-11-21 | 2019-11-25 | 2020-02-04 | Overhead | R16 | 2019-11-25 | 2 | 12 | 3 | 52 | 66 | 2019 | 2020 | R16
165538159158 | 162199159158 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-26 | 2019-07-26 | 2019-07-26 | 2019-08-27 | 2019-08-28 | Overhead | R16 | 2019-08-27 | 1 |  | 23 | 2 | 24 | 2019 | 2019 | R16
161059184415 | 162628184415 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2019-09-24 | 2020-01-28 | 2020-03-17 | 2020-03-26 | 2020-07-13 | Overhead | R16 | 2020-03-26 | 91 | 36 | 8 | 78 | 210 | 2019 | 2020 | R16
163247179601 | 167408179601 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-01 | 2019-07-02 | 2020-02-06 | 2020-04-01 | 2020-04-03 | Underground | R16 | 2020-04-01 | 2 | 158 | 40 | 3 | 200 | 2019 | 2020 | R16
161503160880 | 163641160880 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-05 | 2019-08-12 | 2019-08-12 | 2019-08-30 | 2019-11-13 | Overhead | R16 | 2019-08-30 | 6 |  | 15 | 54 | 73 | 2019 | 2019 | R16
166671161195 | 166068161195 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-17 | 2019-08-17 | 2019-08-17 | 2019-09-26 | 2021-12-16 | Overhead | R16 | 2019-09-26 | 0 |  | 29 | 581 | 609 | 2019 | 2021 | R16
168407158728 | 161419158728 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-23 | 2019-07-23 | 2019-07-23 | 2019-09-10 | 2019-09-11 | Overhead | R16 | 2019-09-10 | 1 |  | 36 | 2 | 37 | 2019 | 2019 | R16
166241171730 | 163037171730 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-13 | 2019-11-13 | 2019-11-13 | 2019-12-30 | 2020-01-02 | Overhead | R16 | 2019-12-30 | 1 |  | 34 | 4 | 37 | 2019 | 2020 | R16
161579178546 | 164563178546 | NON-RESIDENTIAL - HEALTH CARE | R16 RESD AND NON RESD US | Commercial | 2019-11-21 | 2019-11-21 | 2020-01-29 | 2020-09-02 | 2020-10-21 | Underground | R16 | 2020-09-02 | 1 | 50 | 156 | 36 | 240 | 2019 | 2020 | R16
168282316741 | 166988316741 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-09-21 | 2023-04-05 | 2023-04-23 |  | 2023-09-13 | Underground | R16 |  | 402 | 13 |  |  | 517 | 2021 | 2023 | R16
165522160395 | 168967160395 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-07-09 | 2019-07-09 | 2019-08-07 | 2020-06-09 | 2020-09-18 | Overhead | R16 | 2020-06-09 | 1 | 22 | 220 | 74 | 314 | 2019 | 2020 | R16
165522160395 | 168967160395 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-07-09 | 2019-07-09 | 2019-08-07 | 2020-06-09 | 2020-09-18 | Underground | R16 | 2020-06-09 | 1 | 22 | 220 | 74 | 314 | 2019 | 2020 | R16
165673167887 | 165727167887 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-09 | 2019-10-09 | 2019-10-12 | 2021-02-03 | 2021-02-04 | Overhead | R16 | 2021-02-03 | 1 | 3 | 343 | 2 | 347 | 2019 | 2021 | R16
161396183170 | 166267183170 | NON-RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Residential Subdivision | 2019-06-27 | 2019-06-27 | 2020-03-06 | 2020-08-05 | 2021-03-11 | Underground | R16 | 2020-08-05 | 1 | 182 | 109 | 157 | 446 | 2019 | 2021 | R16
168298227768 | 169497227768 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-21 | 2021-04-21 | 2021-04-21 |  | 2021-11-13 | Overhead | R16 | 2021-10-21 | 1 |  | 132 | 17 | 148 | 2021 | 2021 | R16
168310229512 | 169101229512 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-04-20 | 2021-04-20 | 2021-05-05 |  | 2021-08-18 | Underground | R16 | 2021-06-16 | 1 | 12 | 31 | 46 | 87 | 2021 | 2021 | R16
169405164322 | 160828164322 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-13 | 2019-09-13 | 2019-09-13 | 2019-10-09 | 2019-11-11 | Overhead | R16 | 2019-10-09 | 1 |  | 19 | 24 | 42 | 2019 | 2019 | R16
166698156521 | 166128156521 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-06-26 | 2019-06-27 | 2019-06-27 | 2019-10-29 | 2019-10-30 | Overhead | R16 | 2019-10-29 | 2 |  | 89 | 2 | 91 | 2019 | 2019 | R16
169679173448 | 165696173448 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-03 | 2019-12-03 | 2019-12-03 | 2020-01-19 | 2020-01-21 | Overhead | R16 | 2020-01-19 | 1 |  | 34 | 2 | 36 | 2019 | 2020 | R16
168295156253 | 165882156253 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-24 | 2019-06-25 | 2019-06-25 | 2020-01-23 | 2020-01-24 | Overhead | R16 | 2020-01-23 | 2 |  | 153 | 2 | 155 | 2019 | 2020 | R16
160635176703 | 161399176703 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-11-06 | 2019-12-11 | 2020-01-13 | 2020-01-28 | 2020-07-07 | Underground | R16 | 2020-01-28 | 26 | 24 | 12 | 116 | 175 | 2019 | 2020 | R16
163366172038 | 163872172038 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-19 | 2019-11-19 | 2019-11-19 | 2019-12-27 | 2021-11-13 | Overhead | R16 | 2019-12-27 | 1 |  | 29 | 491 | 519 | 2019 | 2021 | R16
166883173564 | 166168173564 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-12-04 | 2019-12-04 | 2019-12-04 | 2020-01-13 | 2020-01-14 | Overhead | R16 | 2020-01-13 | 1 |  | 29 | 2 | 30 | 2019 | 2020 | R16
160784170961 | 161149170961 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-22 | 2019-07-22 | 2019-11-06 | 2020-04-24 | 2020-04-24 | Underground | R16 | 2020-04-24 | 1 | 78 | 123 |  | 200 | 2019 | 2020 | R16
162773232342 | 165623232342 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-02-22 | 2021-02-22 | 2021-05-25 | 2022-08-02 | 2022-08-11 | Overhead | R16 | 2022-08-02 | 1 | 67 | 311 | 8 | 384 | 2021 | 2022 | R16
164161165120 | 161842165120 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-19 | 2019-09-19 | 2019-09-19 | 2019-10-15 | 2019-10-16 | Overhead | R16 | 2019-10-15 | 1 |  | 19 | 2 | 20 | 2019 | 2019 | R16
169240160339 | 161295160339 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-22 | 2019-07-22 | 2019-08-07 | 2019-09-12 | 2020-02-20 | Underground | R16 | 2019-09-12 | 1 | 13 | 27 | 116 | 154 | 2019 | 2020 | R16
167510166384 | 163831166384 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-30 | 2019-09-30 | 2019-09-30 | 2020-03-13 | 2020-06-09 | Overhead | R16 | 2020-03-13 | 1 |  | 120 | 63 | 182 | 2019 | 2020 | R16
161802163263 | 164055163263 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-07 | 2019-08-07 | 2019-09-03 | 2019-09-25 | 2022-05-17 | Underground | R16 | 2019-09-25 | 1 | 20 | 17 | 690 | 725 | 2019 | 2022 | R16
164356174430 | 168327174430 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-13 | 2019-12-13 | 2019-12-13 | 2020-04-08 | 2020-06-23 | Overhead | R16 | 2020-04-08 | 1 |  | 84 | 55 | 138 | 2019 | 2020 | R16
169384158802 | 161368158802 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-23 | 2019-07-23 | 2019-07-23 | 2020-08-14 | 2020-10-06 | Overhead | R16 | 2020-08-14 | 1 |  | 279 | 38 | 316 | 2019 | 2020 | R16
168879229463 | 162508229463 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-04 | 2021-05-04 | 2021-05-04 |  | 2021-11-04 | Overhead | R16 | 2021-10-27 | 1 |  | 127 | 7 | 133 | 2021 | 2021 | R16
160914164198 | 161023164198 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-13 | 2019-09-13 | 2019-09-13 | 2019-10-02 | 2019-11-25 | Overhead | R16 | 2019-10-02 | 1 |  | 14 | 39 | 52 | 2019 | 2019 | R16
161749176997 | 163206176997 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-14 | 2019-11-19 | 2020-01-14 | 2020-06-17 | 2020-06-18 | Underground | R16 | 2020-06-17 | 4 | 41 | 112 | 2 | 156 | 2019 | 2020 | R16
168145173488 | 163731173488 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-05 | 2019-08-05 | 2019-12-03 | 2020-03-17 | 2020-04-02 | Underground | R16 | 2020-03-17 | 1 | 87 | 76 | 13 | 174 | 2019 | 2020 | R16
167322175493 | 168459175493 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-12-16 | 2019-12-30 | 2020-01-02 | 2021-08-11 | 2023-06-07 | Overhead | R16 | 2021-08-11 | 11 | 4 | 420 | 476 | 908 | 2019 | 2023 | R16
168976280010 | 165181280010 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-05-19 | 2022-05-19 | 2022-05-19 |  | 2022-07-17 | Overhead | R16 | 2022-06-27 | 1 |  | 28 | 15 | 42 | 2022 | 2022 | R16
165280157491 | 169031157491 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-09 | 2019-07-09 | 2019-07-09 | 2019-07-31 | 2019-07-31 | Overhead | R16 | 2019-07-31 | 1 |  | 17 |  | 17 | 2019 | 2019 | R16
168135170965 | 161622170965 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-06 | 2019-11-06 | 2019-11-06 | 2019-12-26 | 2020-01-08 | Overhead | R16 | 2019-12-26 | 1 |  | 37 | 10 | 46 | 2019 | 2020 | R16
169003308956 | 168154308956 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-19 | 2023-02-09 | 2023-02-09 |  | 2023-07-31 | Overhead | R16 | 2023-04-05 | 452 |  | 40 | 84 | 574 | 2021 | 2023 | R16
166528172013 | 167962172013 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-21 | 2019-11-15 | 2019-11-15 | 2019-12-04 | 2020-06-09 | Overhead | R16 | 2019-12-04 | 20 |  | 14 | 135 | 167 | 2019 | 2020 | R16
160327178589 | 169929178589 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-09-09 | 2019-12-26 | 2020-01-30 | 2020-08-25 | 2020-11-16 | Underground | R16 | 2020-08-25 | 79 | 26 | 149 | 60 | 311 | 2019 | 2020 | R16
169967156400 | 163832156400 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-13 | 2019-06-13 | 2019-06-25 | 2019-09-16 | 2019-09-19 | Underground | R16 | 2019-09-16 | 1 | 9 | 60 | 4 | 71 | 2019 | 2019 | R16
161028170823 | 161117170823 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-05 | 2019-11-05 | 2019-11-05 | 2020-02-03 | 2020-06-09 | Overhead | R16 | 2020-02-03 | 1 |  | 65 | 92 | 156 | 2019 | 2020 | R16
163441168526 | 167479168526 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-17 | 2019-10-17 | 2019-10-17 | 2020-01-10 | 2020-06-09 | Overhead | R16 | 2020-01-10 | 1 |  | 62 | 108 | 169 | 2019 | 2020 | R16
163613156929 | 167623156929 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2019-07-19 | 2019-07-19 | Overhead | R16 | 2019-07-19 | 1 |  | 15 |  | 15 | 2019 | 2019 | R16
169264160245 | 161622160245 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-24 | 2019-07-24 | 2019-08-05 | 2019-12-10 | 2020-06-09 | Underground | R16 | 2019-12-10 | 1 | 9 | 92 | 131 | 230 | 2019 | 2020 | R16
166317170091 | 166976170091 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-15 | 2019-10-15 | 2019-10-29 | 2019-12-18 | 2019-12-19 | Underground | R16 | 2019-12-18 | 1 | 11 | 37 | 2 | 48 | 2019 | 2019 | R16
169307235220 | 162864235220 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES UD | Residential | 2021-05-04 | 2021-06-16 | 2021-06-16 |  | 2021-11-08 | Underground | R16 | 2021-09-20 | 32 |  | 69 | 36 | 135 | 2021 | 2021 | R16
162502162172 | 163010162172 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-31 | 2019-07-31 | 2019-08-24 | 2019-09-05 | 2019-10-04 | Underground | R16 | 2019-09-05 | 1 | 18 | 9 | 22 | 48 | 2019 | 2019 | R16
162163155643 | 163454155643 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-12 | 2019-06-17 | 2019-06-17 | 2019-06-19 | 2019-11-18 | Overhead | R16 | 2019-06-19 | 4 |  | 3 | 109 | 114 | 2019 | 2019 | R16
166537204456 | 166702204456 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-10-13 | 2020-07-09 | 2020-09-22 | 2021-05-01 | 2021-06-21 | Underground | R16 | 2021-05-01 | 194 | 54 | 159 | 36 | 441 | 2019 | 2021 | R16
169400231020 | 165780231020 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-16 | 2021-05-16 | 2021-05-16 |  | 2021-11-09 | Overhead | R16 | 2021-09-30 | 0 |  | 99 | 29 | 127 | 2021 | 2021 | R16
160436162061 | 164153162061 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-07 | 2019-08-07 | 2019-08-22 |  | 2022-10-17 | Underground | R16 |  | 1 | 12 |  |  | 834 | 2019 | 2022 | R16
161590155284 | 163776155284 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-13 | 2019-06-13 | 2019-06-13 | 2019-07-20 | 2019-07-23 | Underground | R16 | 2019-07-20 | 1 |  | 27 | 2 | 29 | 2019 | 2019 | R16
169436233112 | 161790233112 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-30 | 2021-04-30 | 2021-06-02 |  | 2021-08-11 | Overhead | R16 | 2021-07-01 | 1 | 24 | 22 | 30 | 74 | 2021 | 2021 | R16
163668189588 | 165155189588 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OD | Residential | 2019-11-25 | 2020-01-07 | 2020-04-30 | 2020-06-09 | 2020-12-21 | Overhead | R16 | 2020-06-09 | 32 | 83 | 29 | 140 | 281 | 2019 | 2020 | R16
169515238107 | 161309238107 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-28 | 2021-04-28 | 2021-07-07 |  | 2021-10-25 | Overhead | R16 | 2021-08-25 | 1 | 51 | 36 | 44 | 129 | 2021 | 2021 | R16
164290157012 | 166442157012 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-06-27 | 2019-06-27 | 2019-07-05 | 2019-08-06 | 2019-08-07 | Overhead | R16 | 2019-08-06 | 1 | 7 | 23 | 2 | 30 | 2019 | 2019 | R16
162064173159 | 163443173159 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-18 | 2019-11-27 | 2019-12-02 | 2019-12-04 | 2020-06-09 | Overhead | R16 | 2019-12-04 | 8 | 4 | 3 | 135 | 147 | 2019 | 2020 | R16
166085159042 | 161944159042 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-07-25 | 2019-07-25 | 2019-07-25 | 2019-11-25 | 2021-12-16 | Overhead | R16 | 2019-11-25 | 1 |  | 88 | 539 | 626 | 2019 | 2021 | R16
169259156800 | 167451156800 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2019-07-15 | 2019-08-26 | Overhead | R16 | 2019-07-15 | 1 |  | 11 | 31 | 41 | 2019 | 2019 | R16
169586250007 | 167399250007 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-23 | 2021-09-29 | 2021-09-29 |  | 2022-02-18 | Underground | R16 | 2022-01-19 | 5 |  | 81 | 23 | 107 | 2021 | 2022 | R16
163176170829 | 164038170829 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-01 | 2019-10-01 | 2019-11-05 | 2020-01-08 | 2020-01-09 | Underground | R16 | 2020-01-08 | 1 | 26 | 47 | 2 | 73 | 2019 | 2020 | R16
169958163161 | 162868163161 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-31 | 2019-08-30 | 2019-09-03 | 2019-12-10 | 2020-01-03 | Overhead | R16 | 2019-12-10 | 23 | 3 | 71 | 19 | 113 | 2019 | 2020 | R16
163099156463 | 166315156463 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-26 | 2019-06-26 | 2019-06-26 | 2019-08-15 | 2019-11-08 | Overhead | R16 | 2019-08-15 | 1 |  | 37 | 62 | 98 | 2019 | 2019 | R16
167109156830 | 167509156830 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-02 | 2019-07-02 | 2019-07-02 | 2019-11-26 | 2019-11-27 | Overhead | R16 | 2019-11-26 | 1 |  | 106 | 2 | 107 | 2019 | 2019 | R16
163760207617 | 163850207617 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-30 | 2019-09-30 | 2020-10-20 | 2020-12-23 | 2021-04-29 | Underground | R16 | 2020-12-23 | 1 | 277 | 47 | 92 | 414 | 2019 | 2021 | R16
163631189314 | 166620189314 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Residential | 2019-12-06 | 2019-12-06 | 2020-04-29 | 2020-07-14 | 2021-01-04 | Underground | R16 | 2020-07-14 | 1 | 104 | 55 | 125 | 282 | 2019 | 2021 | R16
167097165571 | 169561165571 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-06 | 2019-09-24 | 2019-09-24 | 2019-09-27 | 2020-06-09 | Overhead | R16 | 2019-09-27 | 13 |  | 4 | 183 | 198 | 2019 | 2020 | R16
166756170381 | 160601170381 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-31 | 2019-10-31 | 2019-10-31 | 2022-07-26 | 2022-10-21 | Overhead | R16 | 2022-07-26 | 1 |  | 714 | 64 | 777 | 2019 | 2022 | R16
167715163347 | 168152163347 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-08-28 | 2019-09-04 | 2019-09-04 | 2019-09-26 | 2019-09-27 | Overhead | R16 | 2019-09-26 | 6 |  | 17 | 2 | 23 | 2019 | 2019 | R16
167588192893 | 164563192893 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-10-03 | 2019-10-08 | 2020-06-01 | 2020-08-26 | 2020-11-12 | Underground | R16 | 2020-08-26 | 4 | 170 | 63 | 57 | 291 | 2019 | 2020 | R16
160392169317 | 160406169317 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential Subdivision | 2019-09-11 | 2019-09-11 | 2019-10-24 | 2019-11-12 | 2020-04-01 | Underground | R16 | 2019-11-12 | 1 | 32 | 14 | 102 | 146 | 2019 | 2020 | R16
160059165880 | 162977165880 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-25 | 2019-09-25 | 2019-09-25 | 2020-07-09 | 2020-10-06 | Overhead | R16 | 2020-07-09 | 1 |  | 207 | 64 | 270 | 2019 | 2020 | R16
167351268148 | 167622268148 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2022-02-08 | 2022-02-08 | 2022-02-08 | 2022-05-13 | 2023-05-23 | Underground | R16 | 2022-05-13 | 1 |  | 69 | 268 | 336 | 2022 | 2023 | R16
168722170859 | 161762170859 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-07 | 2019-11-07 | 2019-11-07 | 2020-02-06 | 2020-06-09 | Overhead | R16 | 2020-02-06 | 1 |  | 66 | 89 | 154 | 2019 | 2020 | R16
168172170946 | 161505170946 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-06 | 2019-11-06 | 2019-11-06 | 2020-01-22 | 2021-11-10 | Overhead | R16 | 2020-01-22 | 1 |  | 56 | 471 | 526 | 2019 | 2021 | R16
160492231960 | 163016231960 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-05-05 | 2021-05-05 | 2021-05-21 |  | 2021-08-23 | Underground | R16 | 2021-07-27 | 1 | 13 | 48 | 20 | 79 | 2021 | 2021 | R16
167008165512 | 168929165512 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-04 | 2019-09-17 | 2019-09-24 | 2019-12-10 | 2020-01-02 | Overhead | R16 | 2019-12-10 | 10 | 6 | 56 | 18 | 87 | 2019 | 2020 | R16
161664168386 | 167243168386 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-16 | 2019-10-16 | 2019-10-16 | 2019-12-04 | 2020-06-09 | Overhead | R16 | 2019-12-04 | 1 |  | 36 | 135 | 170 | 2019 | 2020 | R16
164472157069 | 168005157069 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-03 | 2019-07-03 | 2019-07-03 | 2019-08-28 | 2019-09-11 | Overhead | R16 | 2019-08-28 | 1 |  | 41 | 11 | 51 | 2019 | 2019 | R16
160790231001 | 164595231001 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-11 | 2021-05-11 | 2021-05-17 |  | 2021-10-25 | Underground | R16 | 2021-09-02 | 1 | 5 | 79 | 38 | 120 | 2021 | 2021 | R16
163833170578 | 165771170578 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-09 | 2019-11-05 | 2019-11-05 | 2020-01-14 | 2021-11-10 | Underground | R16 | 2020-01-14 | 20 |  | 51 | 477 | 546 | 2019 | 2021 | R16
162759265678 | 163412265678 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-01-21 | 2022-01-21 | 2022-01-21 |  | 2022-02-28 | Overhead | R16 | 2022-01-28 | 1 |  | 6 | 22 | 27 | 2022 | 2022 | R16
167605277047 | 163835277047 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2022-04-25 | 2022-04-25 | 2022-04-25 |  | 2022-08-03 | Overhead | R16 | 2022-06-15 | 1 |  | 38 | 36 | 73 | 2022 | 2022 | R16
163730296029 | 163964296029 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2022-05-13 | 2022-05-24 | 2022-10-05 |  | 2023-09-27 | Underground | R16 |  | 8 | 97 |  |  | 359 | 2022 | 2023 | R16
166000255237 | 167691255237 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-05 | 2021-11-05 | 2021-11-05 | 2022-04-15 | 2022-05-03 | Overhead | R16 | 2022-04-15 | 1 |  | 116 | 13 | 128 | 2021 | 2022 | R16
168961285781 | 165564285781 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-11 | 2022-07-15 | 2022-07-15 |  | 2023-08-07 | Overhead | R16 | 2023-07-25 | 5 |  | 268 | 10 | 281 | 2022 | 2023 | R16
167489293025 | 166630293025 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-14 | 2022-07-14 | 2022-09-08 | 2022-12-11 | 2022-12-20 | Underground | R16 | 2022-12-11 | 1 | 41 | 67 | 7 | 114 | 2022 | 2022 | R16
162649280871 | 166473280871 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-05-25 | 2022-05-26 | 2022-05-26 | 2022-06-08 | 2022-07-25 | Overhead | R16 | 2022-06-08 | 2 |  | 10 | 34 | 44 | 2022 | 2022 | R16
161031250670 | 166581250670 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-18 | 2021-10-05 | 2021-10-05 |  | 2022-04-13 | Underground | R16 | 2022-03-29 | 101 |  | 126 | 12 | 237 | 2021 | 2022 | R16
169162247834 | 165731247834 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-11-04 | 2021-12-03 | Overhead | R16 | 2021-11-04 | 1 |  | 37 | 22 | 58 | 2021 | 2021 | R16
161136253064 | 163971253064 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-20 | 2021-10-20 | 2021-10-20 | 2022-01-13 | 2023-03-31 | Overhead | R16 | 2022-01-13 | 1 |  | 62 | 317 | 378 | 2021 | 2023 | R16
163738280313 | 163016280313 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-11 | 2022-05-11 | 2022-05-23 |  | 2022-08-11 | Underground | R16 | 2022-06-29 | 1 | 9 | 28 | 32 | 67 | 2022 | 2022 | R16
168019275005 | 169297275005 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-31 | 2022-04-06 | 2022-04-06 | 2022-08-12 | 2022-10-21 | Overhead | R16 | 2022-08-12 | 5 |  | 93 | 51 | 147 | 2022 | 2022 | R16
161190256560 | 167737256560 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-11-05 | 2021-11-14 | 2021-11-14 |  | 2023-03-09 | Overhead | R16 | 2022-01-07 | 6 |  | 40 | 305 | 350 | 2021 | 2023 | R16
161146239162 | 168181239162 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-05-19 | 2021-07-14 | 2021-07-14 |  | 2021-11-09 | Overhead | R16 | 2021-09-30 | 41 |  | 57 | 29 | 125 | 2021 | 2021 | R16
166151279868 | 162261279868 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-28 | 2022-02-28 | 2022-05-18 | 2022-06-14 | 2022-06-20 | Underground | R16 | 2022-06-14 | 1 | 58 | 20 | 5 | 81 | 2022 | 2022 | R16
164344259781 | 165432259781 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-27 | 2021-10-29 | 2021-12-03 | 2022-02-01 | 2022-02-02 | Underground | R16 | 2022-02-01 | 3 | 26 | 43 | 2 | 71 | 2021 | 2022 | R16
162903273658 | 168050273658 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-24 | 2022-03-24 | 2022-03-24 | 2022-05-19 | 2022-07-05 | Overhead | R16 | 2022-05-19 | 1 |  | 41 | 34 | 74 | 2022 | 2022 | R16
161597289030 | 163671289030 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-23 | 2022-01-23 | 2022-08-15 |  | 2022-08-29 | Overhead | R16 | 2022-08-26 | 0 | 146 | 10 | 2 | 156 | 2022 | 2022 | R16
164359285398 | 166317285398 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-13 | 2022-07-13 | 2022-07-13 |  | 2023-11-15 | Overhead | R16 | 2023-10-30 | 1 |  | 339 | 13 | 351 | 2022 | 2023 | R16
165215305386 | 168937305386 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-14 | 2022-03-15 | 2023-01-30 | 2023-01-09 | 2023-05-30 | Overhead | R16 | 2023-01-09 | 22 | 230 |  | 102 | 337 | 2022 | 2023 | R16
161130293875 | 168045293875 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-07-20 | 2022-07-20 | 2022-09-15 |  | 2023-04-03 | Underground | R16 | 2023-02-21 | 1 | 42 | 114 | 30 | 184 | 2022 | 2023 | R16
169783285455 | 166069285455 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-29 | 2022-04-29 | 2022-07-13 |  | 2022-11-01 | Underground | R16 | 2022-10-31 | 1 | 54 | 79 | 2 | 133 | 2022 | 2022 | R16
165533277934 | 168010277934 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2022-02-09 | 2022-02-11 | 2022-05-02 | 2023-04-24 | 2023-04-28 | Underground | R16 | 2023-04-24 | 3 | 57 | 256 | 5 | 318 | 2022 | 2023 | R16
164460289032 | 165871289032 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-23 | 2022-05-23 | 2022-08-15 | 2022-10-10 | 2022-10-14 | Underground | R16 | 2022-10-10 | 1 | 61 | 41 | 5 | 105 | 2022 | 2022 | R16
169726251616 | 168944251616 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2021-09-29 | 2021-10-01 | 2021-10-11 |  | 2022-01-07 | Overhead | R16 |  | 3 | 7 |  |  | 73 | 2021 | 2022 | R16
166546281631 | 167928281631 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-03 | 2022-06-03 | 2022-06-03 | 2022-10-29 | 2022-11-01 | Underground | R16 | 2022-10-29 | 1 |  | 106 | 2 | 108 | 2022 | 2022 | R16
164728269341 | 166577269341 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-02-03 | 2022-02-03 | 2022-02-16 | 2022-04-11 | 2023-06-07 | Overhead | R16 | 2022-04-11 | 1 | 10 | 39 | 303 | 350 | 2022 | 2023 | R16
161437234555 | 168726234555 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-20 | 2021-05-27 | 2021-06-11 |  | 2022-08-10 | Overhead | R16 |  | 6 | 12 |  |  | 320 | 2021 | 2022 | R16
163831290393 | 165840290393 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-12 | 2022-08-10 | 2022-08-26 |  | 2022-12-06 | Underground | R16 | 2022-11-09 | 22 | 13 | 54 | 20 | 106 | 2022 | 2022 | R16
164471255521 | 166182255521 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-01 | 2021-11-01 | 2021-11-08 |  | 2022-06-20 | Underground | R16 | 2022-05-24 | 1 | 6 | 142 | 20 | 166 | 2021 | 2022 | R16
161478232400 | 169282232400 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-05-24 | 2021-05-25 | 2021-05-25 |  | 2022-08-02 | Underground | R16 | 2022-06-13 | 2 |  | 275 | 37 | 312 | 2021 | 2022 | R16
168921254921 | 166759254921 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-03 | 2021-11-03 | 2021-11-03 | 2021-12-28 | 2022-03-15 | Underground | R16 | 2021-12-28 | 1 |  | 40 | 56 | 95 | 2021 | 2022 | R16
161510265306 | 169097265306 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-17 | 2021-08-17 | 2022-01-19 |  | 2022-03-28 | Underground | R16 | 2022-03-28 | 1 | 112 | 49 |  | 160 | 2021 | 2022 | R16
162954278412 | 162215278412 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-06 | 2022-05-06 | 2022-05-06 | 2022-08-10 | 2022-08-11 | Overhead | R16 | 2022-08-10 | 1 |  | 69 | 2 | 70 | 2022 | 2022 | R16
165596300663 | 169179300663 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-02-15 | 2022-11-08 | 2022-11-15 |  | 2023-10-02 | Underground | R16 |  | 191 | 6 |  |  | 425 | 2022 | 2023 | R16
167964262175 | 162786262175 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-30 | 2021-11-30 | 2021-12-22 | 2022-04-06 | 2022-05-03 | Underground | R16 | 2022-04-06 | 1 | 17 | 76 | 20 | 111 | 2021 | 2022 | R16
165459274457 | 169462274457 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-31 | 2022-04-01 | 2022-04-01 |  | 2022-06-20 | Overhead | R16 | 2022-05-25 | 2 |  | 39 | 19 | 58 | 2022 | 2022 | R16
165827303241 | 168549303241 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-11 | 2022-02-11 | 2022-12-21 |  | 2023-09-19 | Underground | R16 | 2023-06-06 | 1 | 224 | 120 | 76 | 418 | 2022 | 2023 | R16
169681251251 | 168228251251 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-09-27 | 2021-10-08 | 2021-10-08 |  | 2022-01-18 | Underground | R16 | 2021-12-22 | 10 |  | 54 | 20 | 82 | 2021 | 2022 | R16
169658287038 | 164023287038 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-30 |  | 2022-06-30 | 2022-09-15 | 2023-03-03 | Underground | R16 | 2022-09-15 |  |  | 56 | 122 | 177 | 2022 | 2023 | R16
165195276610 | 169186276610 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-03-30 | 2022-04-12 | 2022-04-21 |  | 2023-06-13 | Overhead | R16 | 2023-03-01 | 10 | 8 | 225 | 75 | 315 | 2022 | 2023 | R16
161800232530 | 169817232530 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-25 | 2021-05-26 | 2021-05-26 |  | 2021-11-09 | Overhead | R16 | 2021-10-12 | 2 |  | 100 | 21 | 121 | 2021 | 2021 | R16
168370280812 | 165440280812 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-05-20 | 2022-05-20 | 2022-05-26 | 2022-10-07 | 2022-10-11 | Underground | R16 | 2022-10-07 | 1 | 5 | 97 | 3 | 103 | 2022 | 2022 | R16
164048297207 | 164213297207 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-03-07 | 2022-03-07 | 2022-10-17 | 2023-08-16 | 2023-09-12 | Underground | R16 | 2023-08-16 | 1 | 161 | 218 | 20 | 397 | 2022 | 2023 | R16
165563273334 | 167168273334 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-03-22 | 2022-03-22 | 2022-03-22 |  | 2022-06-20 | Overhead | R16 | 2022-05-27 | 1 |  | 49 | 17 | 65 | 2022 | 2022 | R16
163095284161 | 163680284161 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-29 | 2022-06-29 | 2022-06-29 |  | 2022-08-05 | Overhead | R16 | 2022-08-05 | 1 |  | 28 |  | 28 | 2022 | 2022 | R16
165675251036 | 160593251036 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-07 | 2021-10-07 | 2021-10-07 |  | 2021-11-09 | Overhead | R16 | 2021-11-04 | 1 |  | 21 | 4 | 24 | 2021 | 2021 | R16
162198230255 | 164510230255 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-11 | 2021-05-11 | 2021-05-11 |  | 2022-03-08 | Overhead | R16 | 2022-01-19 | 1 |  | 182 | 35 | 216 | 2021 | 2022 | R16
163449272919 | 165188272919 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-11 | 2022-03-18 | 2022-03-18 | 2022-05-12 | 2022-05-13 | Overhead | R16 | 2022-05-12 | 6 |  | 40 | 2 | 46 | 2022 | 2022 | R16
161736271996 | 162220271996 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-18 | 2022-01-21 | 2022-03-09 |  | 2022-09-29 | Underground | R16 | 2022-08-15 | 4 | 34 | 114 | 34 | 183 | 2022 | 2022 | R16
161433282261 | 162392282261 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-14 | 2022-04-14 | 2022-06-10 | 2022-11-03 | 2022-11-07 | Underground | R16 | 2022-11-03 | 1 | 42 | 105 | 3 | 148 | 2022 | 2022 | R16
167612261381 | 166089261381 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-12-15 | 2021-12-15 | 2021-12-15 | 2022-06-21 | 2022-08-03 | Underground | R16 | 2022-06-21 | 1 |  | 135 | 32 | 166 | 2021 | 2022 | R16
162209293617 | 167337293617 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-05-31 | 2022-05-31 | 2022-09-13 | 2023-01-10 | 2023-01-30 | Underground | R16 | 2023-01-10 | 1 | 76 | 86 | 15 | 175 | 2022 | 2023 | R16
162374229442 | 162704229442 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-04 | 2021-05-04 | 2021-05-04 |  | 2021-11-08 | Overhead | R16 | 2021-05-20 | 1 |  | 13 | 123 | 135 | 2021 | 2021 | R16
167045260669 | 168022260669 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-24 | 2021-09-27 | 2021-12-10 | 2021-12-14 | 2022-01-11 | Overhead | R16 | 2021-12-14 | 2 | 55 | 3 | 21 | 78 | 2021 | 2022 | R16
163457307881 | 161806307881 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2022-06-21 | 2022-09-24 | 2023-01-31 | 2023-05-19 | 2023-08-21 | Overhead | R16 | 2023-05-19 | 69 | 92 | 79 | 67 | 305 | 2022 | 2023 | R16
163459280564 | 166026280564 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-24 | 2022-05-24 | 2022-05-24 |  | 2023-08-18 | Overhead | R16 | 2023-05-16 | 1 |  | 256 | 69 | 324 | 2022 | 2023 | R16
166237278827 | 168330278827 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-25 | 2022-03-25 | 2022-05-10 |  | 2022-08-23 | Underground | R16 | 2022-07-18 | 1 | 33 | 50 | 27 | 108 | 2022 | 2022 | R16
163778252213 | 166869252213 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-21 | 2021-09-21 | 2021-10-15 | 2023-09-28 | 2023-11-08 | Underground | R16 | 2023-09-28 | 1 | 19 | 510 | 30 | 557 | 2021 | 2023 | R16
169986281219 | 166106281219 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-02-02 | 2022-03-18 | 2022-06-01 | 2023-03-17 | 2023-05-26 | Overhead | R16 | 2023-03-17 | 33 | 54 | 208 | 51 | 343 | 2022 | 2023 | R16
166306295050 | 167838295050 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-20 | 2022-07-20 | 2022-09-27 |  | 2022-12-07 | Underground | R16 | 2022-11-14 | 1 | 50 | 35 | 18 | 101 | 2022 | 2022 | R16
163089267855 | 163528267855 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-10-19 | 2021-10-26 | 2022-02-07 | 2022-04-08 | 2022-04-28 | Underground | R16 | 2022-04-08 | 6 | 75 | 45 | 15 | 138 | 2021 | 2022 | R16
161569276986 | 163283276986 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-20 | 2022-01-20 | 2022-04-25 |  | 2022-06-21 | Overhead | R16 | 2022-05-24 | 1 | 68 | 22 | 21 | 109 | 2022 | 2022 | R16
165267274453 | 162004274453 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-25 |  | 2022-03-31 | 2022-06-21 | 2022-08-11 | Overhead | R16 | 2022-06-21 |  |  | 59 | 38 | 120 | 2022 | 2022 | R16
169420296130 | 163399296130 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-03 | 2022-03-08 | 2022-10-06 | 2023-01-29 | 2023-02-01 | Underground | R16 | 2023-01-29 | 4 | 153 | 82 | 3 | 240 | 2022 | 2023 | R16
162890244598 | 167690244598 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-08-11 | 2021-08-11 | 2021-08-20 |  | 2023-08-09 | Overhead | R16 | 2023-04-24 | 1 | 8 | 437 | 78 | 521 | 2021 | 2023 | R16
163230286582 | 161958286582 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-04-13 | 2022-04-13 | 2022-07-22 |  | 2023-10-02 | Underground | R16 |  | 1 | 73 |  |  | 384 | 2022 | 2023 | R16
166598265940 | 169965265940 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-06 | 2022-01-06 | 2022-01-24 |  | 2022-03-03 | Underground | R16 | 2022-02-02 | 1 | 13 | 8 | 22 | 41 | 2022 | 2022 | R16
162909281798 | 168636281798 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-06 | 2022-06-06 | 2022-06-06 |  | 2022-12-04 | Overhead | R16 | 2022-10-05 | 1 |  | 88 | 43 | 130 | 2022 | 2022 | R16
166647277021 | 160202277021 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-04-05 | 2022-04-05 | 2022-04-25 |  | 2022-06-06 | Overhead | R16 |  | 1 | 15 |  |  | 45 | 2022 | 2022 | R16
163405295179 | 165940295179 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-05-23 | 2022-09-28 | 2022-09-28 |  | 2023-08-23 | Underground | R16 | 2023-08-10 | 93 |  | 227 | 10 | 328 | 2022 | 2023 | R16
161557269181 | 162202269181 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-18 | 2022-02-04 | 2022-02-15 | 2022-12-12 | 2022-12-31 | Underground | R16 | 2022-12-12 | 14 | 8 | 215 | 15 | 249 | 2022 | 2022 | R16
165003286266 | 166024286266 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-12 | 2022-07-12 | 2022-07-20 |  | 2022-09-11 | Underground | R16 | 2022-09-01 | 1 | 7 | 32 | 7 | 44 | 2022 | 2022 | R16
161033273047 | 165210273047 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-10 | 2022-03-17 | 2022-03-17 |  | 2023-01-05 | Overhead | R16 | 2022-10-11 | 6 |  | 149 | 63 | 216 | 2022 | 2023 | R16
169233267050 | 169908267050 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-16 | 2022-02-01 | 2022-02-01 | 2022-08-24 | 2022-10-21 | Overhead | R16 | 2022-08-24 | 56 |  | 147 | 43 | 244 | 2021 | 2022 | R16
163280278120 | 165058278120 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-28 | 2022-05-03 | 2022-05-03 |  | 2022-08-11 | Overhead | R16 | 2022-06-30 | 68 |  | 43 | 31 | 140 | 2022 | 2022 | R16
165728277052 | 163923277052 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-25 | 2022-04-25 | 2022-04-25 |  | 2022-07-17 | Overhead | R16 | 2022-07-07 | 1 |  | 54 | 7 | 60 | 2022 | 2022 | R16
160384253798 | 162317253798 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-13 | 2021-10-13 | 2021-10-27 | 2023-08-10 | 2023-08-11 | Underground | R16 | 2023-08-10 | 1 | 11 | 467 | 2 | 478 | 2021 | 2023 | R16
164460290146 | 168040290146 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-20 | 2022-07-21 | 2022-08-24 | 2022-11-29 | 2022-12-20 | Underground | R16 | 2022-11-29 | 2 | 25 | 70 | 16 | 110 | 2022 | 2022 | R16
164655273563 | 169947273563 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-17 | 2022-02-17 | 2022-03-22 |  | 2022-05-18 | Underground | R16 | 2022-04-25 | 1 | 24 | 25 | 18 | 65 | 2022 | 2022 | R16
161157251187 | 167510251187 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2021-09-22 | 2021-09-28 | 2022-09-09 | 2023-08-17 | 2022-02-07 | Underground | R16 | 2023-08-17 | 5 | 249 | 245 |  | 99 | 2021 | 2022 | R16
162269281445 | 163044281445 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-11 | 2022-06-02 | 2022-06-02 |  | 2022-08-10 | Overhead | R16 | 2022-07-08 | 17 |  | 27 | 24 | 66 | 2022 | 2022 | R16
163337280632 | 164185280632 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-16 | 2022-05-24 | 2022-05-24 | 2022-07-06 | 2022-08-18 | Overhead | R16 | 2022-07-06 | 7 |  | 32 | 32 | 69 | 2022 | 2022 | R16
162811279282 | 163963279282 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-13 | 2022-05-13 | 2022-05-13 |  | 2022-07-28 | Overhead | R16 | 2022-07-28 | 1 |  | 55 |  | 55 | 2022 | 2022 | R16
165731277430 | 164012277430 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2022-04-25 | 2022-04-27 | 2022-04-27 | 2023-10-19 | 2023-10-20 | Overhead | R16 | 2023-10-19 | 3 |  | 387 | 2 | 390 | 2022 | 2023 | R16
161833281362 | 163197281362 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-11 | 2022-05-11 | 2022-06-01 |  | 2022-07-29 | Underground | R16 | 2022-07-26 | 1 | 16 | 40 | 4 | 58 | 2022 | 2022 | R16
167329281552 | 169389281552 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-15 | 2022-02-15 | 2022-06-03 |  | 2023-08-08 | Underground | R16 | 2023-04-21 | 1 | 79 | 231 | 78 | 386 | 2022 | 2023 | R16
167001270384 | 161497270384 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-02-24 | 2022-02-24 | 2022-02-24 |  | 2022-03-25 | Overhead | R16 | 2022-03-07 | 1 |  | 8 | 15 | 22 | 2022 | 2022 | R16
161588273242 | 164471273242 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-08 | 2022-03-08 | 2022-03-18 | 2023-06-13 | 2023-06-22 | Underground | R16 | 2023-06-13 | 1 | 9 | 323 | 8 | 338 | 2022 | 2023 | R16
162139257322 | 161164257322 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2021-10-08 | 2021-11-18 | 2021-11-18 |  | 2022-06-01 | Underground | R16 | 2022-05-17 | 30 |  | 129 | 12 | 169 | 2021 | 2022 | R16
167934275260 | 160853275260 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-07 | 2022-04-07 | 2022-04-07 | 2022-06-28 | 2022-08-24 | Underground | R16 | 2022-06-28 | 1 |  | 59 | 42 | 100 | 2022 | 2022 | R16
165929274360 | 168929274360 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-30 | 2022-03-30 | 2022-03-30 | 2022-06-01 | 2022-12-15 | Overhead | R16 | 2022-06-01 | 1 |  | 46 | 142 | 187 | 2022 | 2022 | R16
161559273113 | 166888273113 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-18 | 2022-03-18 | 2022-03-18 |  | 2022-07-03 | Underground | R16 | 2022-06-16 | 1 |  | 65 | 12 | 76 | 2022 | 2022 | R16
161467280930 | 166916280930 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-27 | 2022-05-27 | 2022-05-27 |  | 2022-07-16 | Overhead | R16 | 2022-07-14 | 1 |  | 35 | 2 | 36 | 2022 | 2022 | R16
166647277538 | 160207277538 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-04-05 | 2022-04-06 | 2022-04-29 |  | 2022-06-06 | Overhead | R16 |  | 2 | 18 |  |  | 45 | 2022 | 2022 | R16
168532275781 | 167651275781 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-23 | 2021-12-23 | 2022-04-13 |  | 2022-10-26 | Underground | R16 | 2022-09-15 | 1 | 80 | 112 | 30 | 220 | 2021 | 2022 | R16
164184231681 | 168672231681 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-20 | 2021-05-20 | 2021-05-20 |  | 2022-09-11 | Overhead | R16 | 2022-08-30 | 1 |  | 334 | 9 | 342 | 2021 | 2022 | R16
165682255503 | 165100255503 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-26 | 2021-11-08 | 2021-11-08 | 2023-08-02 | 2023-08-17 | Overhead | R16 | 2023-08-02 | 10 |  | 453 | 12 | 473 | 2021 | 2023 | R16
164983275099 | 169110275099 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-30 | 2021-09-30 | 2022-04-07 | 2022-04-07 | 2022-07-17 | Underground | R16 | 2022-04-07 | 1 | 136 |  | 72 | 207 | 2021 | 2022 | R16
163402278242 | 160433278242 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-04 | 2022-05-04 | 2022-05-04 | 2022-06-21 | 2022-08-11 | Overhead | R16 | 2022-06-21 | 1 |  | 35 | 38 | 72 | 2022 | 2022 | R16
165317285958 | 164688285958 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2022-01-27 | 2022-01-31 | 2022-07-19 | 2022-08-25 | 2022-09-13 | Underground | R16 | 2022-08-25 | 3 | 122 | 28 | 14 | 164 | 2022 | 2022 | R16
166905271150 | 162699271150 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-03-01 | 2022-03-02 | 2022-03-02 | 2022-07-25 | 2022-07-25 | Overhead | R16 | 2022-07-25 | 2 |  | 104 |  | 105 | 2022 | 2022 | R16
166013263170 | 168843263170 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-01-03 | 2022-01-03 | 2022-01-03 |  | 2022-05-09 | Overhead | R16 | 2022-04-15 | 1 |  | 75 | 17 | 91 | 2022 | 2022 | R16
162316266633 | 164888266633 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-27 | 2022-01-28 | 2022-01-28 | 2022-05-24 | 2022-06-20 | Overhead | R16 | 2022-05-24 | 2 |  | 83 | 20 | 103 | 2022 | 2022 | R16
162482274298 | 168606274298 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2022-03-28 | 2022-03-29 | 2022-03-31 |  | 2022-05-12 | Overhead | R16 |  | 2 | 3 |  |  | 34 | 2022 | 2022 | R16
167111287093 | 167457287093 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-07-18 | 2022-07-18 | 2022-07-27 | 2022-09-26 | 2022-12-16 | Underground | R16 | 2022-09-26 | 1 | 8 | 44 | 60 | 110 | 2022 | 2022 | R16
168238280041 | 165200280041 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-19 | 2022-05-19 | 2022-05-19 |  | 2022-07-03 | Overhead | R16 | 2022-06-21 | 1 |  | 24 | 9 | 32 | 2022 | 2022 | R16
164516277227 | 169762277227 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-16 | 2022-02-22 | 2022-04-26 | 2022-05-17 | 2022-05-19 | Underground | R16 | 2022-05-17 | 5 | 46 | 16 | 3 | 67 | 2022 | 2022 | R16
169204261330 | 169561261330 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-14 | 2021-12-14 | 2021-12-14 | 2022-03-07 | 2022-03-28 | Overhead | R16 | 2022-03-07 | 22 |  | 60 | 16 | 96 | 2021 | 2022 | R16
167623266211 | 164610266211 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-12-08 | 2021-12-09 | 2022-01-26 | 2022-04-21 | 2022-04-26 | Underground | R16 | 2022-04-21 | 2 | 35 | 62 | 4 | 100 | 2021 | 2022 | R16
161453297233 | 165127297233 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-28 | 2022-04-28 | 2022-10-18 | 2023-01-31 | 2023-02-07 | Underground | R16 | 2023-01-31 | 1 | 124 | 76 | 6 | 204 | 2022 | 2023 | R16
168927263876 | 166322263876 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-16 | 2022-01-07 | 2022-01-07 |  | 2022-06-03 | Underground | R16 | 2022-05-13 | 17 |  | 91 | 16 | 122 | 2021 | 2022 | R16
164971299377 | 160740299377 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2021-11-19 | 2022-03-14 | 2022-11-04 | 2023-07-14 | 2023-10-26 | Underground | R16 | 2023-07-14 | 82 | 170 | 181 | 75 | 505 | 2021 | 2023 | R16
169402264181 | 160574264181 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-01-10 | 2022-01-10 | 2022-01-10 | 2022-03-24 | 2022-03-31 | Overhead | R16 | 2022-03-24 | 1 |  | 54 | 6 | 59 | 2022 | 2022 | R16
168425281003 | 166927281003 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2022-03-18 | 2022-03-18 | 2022-05-26 | 2022-11-29 | 2022-12-20 | Underground | R16 | 2022-11-29 | 1 | 50 | 134 | 16 | 198 | 2022 | 2022 | R16
165225279954 | 165452279954 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-20 | 2022-05-20 | 2022-05-20 |  | 2022-07-15 | Overhead | R16 | 2022-07-13 | 1 |  | 39 | 3 | 41 | 2022 | 2022 | R16
162935283641 | 161925283641 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-21 | 2022-06-21 | 2022-06-23 | 2022-10-31 | 2022-11-03 | Underground | R16 | 2022-10-31 | 1 | 3 | 93 | 4 | 98 | 2022 | 2022 | R16
164110288121 | 161612288121 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-05 | 2022-05-05 | 2022-08-05 |  | 2022-11-22 | Underground | R16 | 2022-11-21 | 1 | 67 | 77 | 2 | 144 | 2022 | 2022 | R16
165033285840 | 164389285840 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-05 | 2022-07-15 | 2022-07-15 | 2023-01-05 | 2023-01-05 | Underground | R16 | 2023-01-05 | 9 |  | 125 |  | 133 | 2022 | 2023 | R16
168621272149 | 161115272149 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-11 | 2022-01-11 | 2022-03-10 |  | 2022-05-12 | Underground | R16 | 2022-04-20 | 1 | 43 | 30 | 17 | 88 | 2022 | 2022 | R16
168567262917 | 167967262917 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2021-09-24 | 2021-09-24 | 2021-12-30 | 2023-12-01 | 2023-12-28 | Underground | R16 | 2023-12-01 | 1 | 70 | 502 | 20 | 590 | 2021 | 2023 | R16
169444264657 | 161618264657 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-13 | 2022-01-13 | 2022-01-13 |  | 2022-05-19 | Underground | R16 | 2022-04-28 | 1 |  | 76 | 16 | 91 | 2022 | 2022 | R16
163779286351 | 168252286351 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-07-21 | 2022-07-21 | 2022-07-21 |  | 2022-10-21 | Overhead | R16 | 2022-09-06 | 1 |  | 34 | 34 | 67 | 2022 | 2022 | R16
165256251241 | 160020251241 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-08-19 | 2021-08-19 | 2021-10-07 |  | 2022-07-15 | Underground | R16 | 2022-06-06 | 1 | 36 | 173 | 30 | 237 | 2021 | 2022 | R16
165333270809 | 160308270809 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-02-18 | 2022-02-18 | 2022-02-28 | 2023-08-04 | 2023-07-06 | Underground | R16 | 2023-08-04 | 1 | 7 | 375 |  | 360 | 2022 | 2023 | R16
167516263764 | 169915263764 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-06 | 2022-01-06 | 2022-01-06 | 2022-03-04 | 2022-03-25 | Overhead | R16 | 2022-03-04 | 1 |  | 42 | 16 | 57 | 2022 | 2022 | R16
165705300407 | 162670300407 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-05-09 | 2022-05-31 | 2022-11-14 |  | 2023-03-17 | Overhead | R16 |  | 17 | 120 |  |  | 225 | 2022 | 2023 | R16
169672271288 | 163296271288 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-03 | 2022-03-03 | 2022-03-03 |  | 2022-10-19 | Overhead | R16 |  | 1 |  |  |  | 165 | 2022 | 2022 | R16
160915276000 | 160644276000 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-07 | 2022-04-07 | 2022-04-15 | 2022-10-27 | 2022-12-11 | Underground | R16 | 2022-10-27 | 1 | 7 | 140 | 32 | 177 | 2022 | 2022 | R16
162471288825 | 162187288825 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-06 | 2022-05-06 | 2022-08-12 | 2022-09-22 | 2023-05-15 | Underground | R16 | 2022-09-22 | 1 | 71 | 30 | 168 | 267 | 2022 | 2023 | R16
164588278972 | 163317278972 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-11 | 2022-05-11 | 2022-05-12 |  | 2022-06-18 | Overhead | R16 | 2022-06-14 | 1 | 2 | 24 | 4 | 28 | 2022 | 2022 | R16
167832284882 | 160265284882 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-13 | 2022-06-20 | 2022-07-07 | 2022-09-24 | 2022-09-27 | Underground | R16 | 2022-09-24 | 6 | 14 | 57 | 2 | 77 | 2022 | 2022 | R16
165494231738 | 168793231738 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-21 | 2021-05-21 | 2021-05-21 |  | 2021-10-25 | Underground | R16 | 2021-09-08 | 1 |  | 79 | 34 | 112 | 2021 | 2021 | R16
167904267136 | 164765267136 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-09 | 2022-02-01 | 2022-02-01 |  | 2022-08-11 | Underground | R16 | 2022-07-01 | 39 |  | 109 | 30 | 176 | 2021 | 2022 | R16
168682284598 | 163279284598 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-03-03 | 2022-03-11 | 2022-07-07 |  | 2023-08-09 | Underground | R16 |  | 7 | 85 |  |  | 375 | 2022 | 2023 | R16
169564342495 | 169908342495 | MOBILE HOMES PARK AB622 | ELEC SVC FOR MOBILE HOMES | Residential | 2021-10-04 | 2021-10-05 | 2023-12-13 |  | 2023-12-14 | Underground | R16 |  | 2 | 572 |  |  | 574 | 2021 | 2023 | R16
163219278401 | 161254278401 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-05 | 2022-05-05 | 2022-05-05 | 2022-07-06 | 2022-08-18 | Overhead | R16 | 2022-07-06 | 1 |  | 45 | 32 | 76 | 2022 | 2022 | R16
168336268637 | 160091268637 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-17 | 2021-11-17 | 2022-02-11 | 2022-08-03 | 2022-10-21 | Underground | R16 | 2022-08-03 | 1 | 63 | 124 | 58 | 243 | 2021 | 2022 | R16
160407257142 | 160291257142 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2022-01-30 | 2022-02-02 | Overhead | R16 | 2022-01-30 | 1 |  | 53 | 3 | 56 | 2021 | 2022 | R16
163789280477 | 169468280477 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-03 | 2022-05-03 | 2022-05-24 |  | 2022-08-11 | Underground | R16 | 2022-06-29 | 1 | 16 | 27 | 32 | 73 | 2022 | 2022 | R16
161804274325 | 167278274325 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-04 | 2021-11-18 | 2022-03-30 |  | 2022-06-06 | Underground | R16 | 2022-05-09 | 11 | 95 | 29 | 21 | 153 | 2021 | 2022 | R16
164132269710 | 160329269710 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2022-02-18 | 2022-02-18 | 2022-02-18 |  | 2023-05-05 | Overhead | R16 | 2023-03-30 | 1 |  | 290 | 27 | 316 | 2022 | 2023 | R16
169987271036 | 162421271036 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-28 | 2022-02-28 | 2022-03-02 |  | 2022-06-06 | Underground | R16 | 2022-05-11 | 1 | 3 | 51 | 19 | 71 | 2022 | 2022 | R16
165167250094 | 167024250094 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-09-21 | 2021-09-27 | 2021-09-30 | 2021-10-05 | 2021-11-03 | Overhead | R16 | 2021-10-05 | 5 | 4 | 4 | 22 | 32 | 2021 | 2021 | R16
162052288585 | 169207288585 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-02-14 | 2022-06-15 | 2022-08-10 | 2023-01-05 | 2023-01-05 | Underground | R16 | 2023-01-05 | 88 | 41 | 107 |  | 234 | 2022 | 2023 | R16
168095275004 | 160308275004 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-05 | 2022-04-06 | 2022-04-06 | 2022-07-12 | 2022-08-23 | Overhead | R16 | 2022-07-12 | 2 |  | 70 | 31 | 101 | 2022 | 2022 | R16
165109274525 | 160374274525 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-18 | 2022-02-18 | 2022-04-01 | 2022-10-14 | 2022-10-17 | Underground | R16 | 2022-10-14 | 1 | 31 | 141 | 2 | 172 | 2022 | 2022 | R16
167008267502 | 166653267502 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-03 | 2022-02-03 | 2022-02-03 |  | 2022-05-31 | Overhead | R16 | 2022-05-02 | 1 |  | 63 | 22 | 84 | 2022 | 2022 | R16
162304272103 | 164565272103 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-08 | 2022-03-09 | 2022-03-09 | 2022-04-07 | 2022-05-03 | Overhead | R16 | 2022-04-07 | 2 |  | 22 | 19 | 41 | 2022 | 2022 | R16
161573272139 | 162957272139 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-02 | 2022-03-02 | 2022-03-11 |  | 2022-06-22 | Underground | R16 | 2022-06-13 | 1 | 8 | 67 | 8 | 81 | 2022 | 2022 | R16
162439285801 | 167061285801 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-07-15 | 2022-07-15 | 2022-07-15 | 2022-10-16 | 2022-10-19 | Underground | R16 | 2022-10-16 | 1 |  | 66 | 3 | 69 | 2022 | 2022 | R16
168871276338 | 162745276338 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-04-19 | 2022-04-19 | 2022-04-19 | 2022-04-24 | 2023-02-06 | Underground | R16 | 2022-04-24 | 1 |  | 4 | 206 | 210 | 2022 | 2023 | R16
168890264562 | 161331264562 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-12 | 2022-01-12 | 2022-01-12 |  | 2022-05-19 | Underground | R16 | 2022-04-27 | 1 |  | 76 | 17 | 92 | 2022 | 2022 | R16
165247274058 | 167568274058 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-23 | 2022-03-23 | 2022-03-29 |  | 2022-05-04 | Overhead | R16 |  | 1 | 5 |  |  | 31 | 2022 | 2022 | R16
162967277133 | 165323277133 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-11 | 2022-04-27 | 2022-04-27 |  | 2022-06-30 | Overhead | R16 | 2022-06-01 | 34 |  | 26 | 22 | 80 | 2022 | 2022 | R16
167965277060 | 163773277060 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-04-25 | 2022-04-25 | 2022-04-25 |  | 2022-08-11 | Underground | R16 | 2022-07-01 | 1 |  | 50 | 30 | 79 | 2022 | 2022 | R16
163202268080 | 164824268080 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-25 | 2021-10-26 | 2022-02-08 | 2022-11-01 | 2022-11-04 | Underground | R16 | 2022-11-01 | 2 | 76 | 191 | 4 | 270 | 2021 | 2022 | R16
168104233365 | 168146233365 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2021-05-19 | 2021-05-19 | 2021-06-03 |  | 2023-08-23 | Underground | R16 |  | 1 | 12 |  |  | 591 | 2021 | 2023 | R16
163003279229 | 162973279229 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-11 | 2022-05-13 | 2022-05-13 | 2022-05-16 | 2022-06-30 | Underground | R16 | 2022-05-16 | 3 |  | 2 | 34 | 37 | 2022 | 2022 | R16
168544285203 | 162267285203 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-23 | 2022-06-23 | 2022-07-11 |  | 2022-08-05 | Underground | R16 | 2022-08-01 | 1 | 13 | 16 | 5 | 32 | 2022 | 2022 | R16
163870285920 | 167059285920 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-15 | 2022-07-15 | 2022-07-18 |  | 2022-09-29 | Underground | R16 | 2022-08-15 | 1 | 2 | 21 | 34 | 55 | 2022 | 2022 | R16
164850266197 | 166612266197 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-02 | 2021-11-03 | 2022-01-26 | 2022-03-24 | 2022-05-10 | Underground | R16 | 2022-03-24 | 2 | 61 | 42 | 34 | 136 | 2021 | 2022 | R16
169409264713 | 169264264713 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-04 | 2022-01-04 | 2022-01-13 | 2022-03-07 | 2023-06-08 | Underground | R16 | 2022-03-07 | 1 | 8 | 38 | 329 | 373 | 2022 | 2023 | R16
166740287026 | 169323287026 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-26 | 2022-07-26 | 2022-07-26 | 2022-09-28 | 2023-01-05 | Overhead | R16 | 2022-09-28 | 1 |  | 47 | 72 | 118 | 2022 | 2023 | R16
167589270749 | 162335270749 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-28 | 2022-02-28 | 2022-02-28 | 2022-03-03 | 2022-06-30 | Overhead | R16 | 2022-03-03 | 1 |  | 4 | 86 | 89 | 2022 | 2022 | R16
161854284166 | 161949284166 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-02-25 | 2022-02-25 | 2022-06-29 | 2023-06-01 | 2023-08-11 | Underground | R16 | 2023-06-01 | 1 | 89 | 242 | 52 | 381 | 2022 | 2023 | R16
167037276636 | 163117276636 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-20 | 2022-04-21 | 2022-04-21 | 2022-05-16 | 2022-06-20 | Overhead | R16 | 2022-05-16 | 2 |  | 18 | 26 | 44 | 2022 | 2022 | R16
162511277639 | 164418277639 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-27 | 2022-04-27 | 2022-04-29 | 2022-05-09 | 2022-06-12 | Underground | R16 | 2022-05-09 | 1 | 3 | 7 | 25 | 33 | 2022 | 2022 | R16
166230273284 | 167130273284 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-21 | 2022-03-21 | 2022-03-21 |  | 2022-05-19 | Overhead | R16 | 2022-04-28 | 1 |  | 29 | 16 | 44 | 2022 | 2022 | R16
166038285461 | 166042285461 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-12 | 2022-07-12 | 2022-07-12 |  | 2022-08-19 | Overhead | R16 | 2022-08-17 | 1 |  | 27 | 3 | 29 | 2022 | 2022 | R16
161119272777 | 166136272777 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-16 | 2022-03-16 | 2022-03-16 |  | 2022-11-16 | Overhead | R16 | 2022-11-14 | 1 |  | 174 | 3 | 176 | 2022 | 2022 | R16
165418252064 | 162213252064 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-13 | 2021-10-13 | 2021-10-13 | 2022-04-13 | 2022-04-14 | Overhead | R16 | 2022-04-13 | 1 |  | 131 | 2 | 132 | 2021 | 2022 | R16
160639248032 | 165832248032 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-15 | 2021-09-15 | 2021-09-15 |  | 2022-02-02 | Overhead | R16 | 2021-12-16 | 1 |  | 67 | 35 | 101 | 2021 | 2022 | R16
161724272990 | 165829272990 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-15 | 2022-03-15 | 2022-03-18 | 2022-05-09 | 2022-08-16 | Underground | R16 | 2022-05-09 | 1 | 4 | 37 | 72 | 111 | 2022 | 2022 | R16
168803250978 | 160475250978 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-10-06 | 2021-10-07 | 2021-10-07 |  | 2022-06-06 | Underground | R16 | 2022-06-01 | 2 |  | 170 | 4 | 174 | 2021 | 2022 | R16
168961260332 | 168940260332 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-10 | 2021-11-10 | 2021-12-08 |  | 2022-04-14 | Underground | R16 | 2022-04-14 | 1 | 21 | 92 |  | 112 | 2021 | 2022 | R16
164545267790 | 167323267790 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-07 | 2022-02-07 | 2022-02-07 | 2022-07-27 | 2022-07-28 | Overhead | R16 | 2022-07-27 | 1 |  | 123 | 2 | 124 | 2022 | 2022 | R16
162556254442 | 163487254442 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-19 | 2021-10-29 | 2021-10-29 | 2021-11-19 | 2022-01-11 | Overhead | R16 | 2021-11-19 | 9 |  | 16 | 38 | 61 | 2021 | 2022 | R16
163802248978 | 167567248978 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-23 | 2021-09-23 | 2021-09-23 |  | 2021-11-09 | Overhead | R16 | 2021-11-02 | 1 |  | 29 | 6 | 34 | 2021 | 2021 | R16
168682321179 | 162851321179 | NON-RESIDENTIAL - MISCELLANEOUS | UG ELEC MISC SVC US | Commercial | 2022-04-19 | 2022-04-21 | 2023-06-07 |  | 2023-12-11 | Underground | R16 |  | 3 | 295 |  |  | 430 | 2022 | 2023 | R16
165466258722 | 162156258722 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-24 | 2021-11-24 | 2021-11-24 | 2022-02-04 | 2022-02-07 | Overhead | R16 | 2022-02-04 | 1 |  | 53 | 2 | 54 | 2021 | 2022 | R16
165143253796 | 165372253796 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-27 | 2021-10-27 | 2021-10-27 |  | 2021-11-18 | Overhead | R16 | 2021-10-29 | 1 |  | 3 | 15 | 17 | 2021 | 2021 | R16
168304271025 | 169116271025 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-14 | 2022-02-14 | 2022-03-01 | 2023-04-25 | 2023-06-12 | Overhead | R16 | 2023-04-25 | 1 | 12 | 301 | 35 | 346 | 2022 | 2023 | R16
163431252870 | 161327252870 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-10 | 2021-10-20 | 2021-10-20 | 2022-04-07 | 2022-06-03 | Underground | R16 | 2022-04-07 | 8 |  | 122 | 42 | 170 | 2021 | 2022 | R16
169308249305 | 167917249305 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-24 | 2021-09-24 | 2021-09-24 |  | 2021-12-02 | Overhead | R16 | 2021-11-05 | 1 |  | 31 | 20 | 50 | 2021 | 2021 | R16
160521254827 | 166152254827 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-16 | 2021-09-16 | 2021-11-03 | 2021-12-21 | 2021-12-22 | Overhead | R16 | 2021-12-21 | 1 | 35 | 35 | 2 | 70 | 2021 | 2021 | R16
169969264349 | 160951264349 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-01-11 | 2022-01-11 | 2022-01-11 |  | 2022-03-08 | Underground | R16 | 2022-01-18 | 1 |  | 6 | 36 | 41 | 2022 | 2022 | R16
161007278423 | 163819278423 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-25 | 2022-05-05 | 2022-05-05 |  | 2022-08-03 | Overhead | R16 | 2022-06-22 | 9 |  | 35 | 31 | 73 | 2022 | 2022 | R16
163734277896 | 165794277896 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE FOR UPGRADE UD | Residential | 2021-10-28 | 2022-04-22 | 2022-05-03 |  | 2022-08-02 | Underground | R16 |  | 127 | 8 |  |  | 199 | 2021 | 2022 | R16
163963289299 | 164609289299 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2022-07-06 | 2022-07-06 | 2023-01-27 | 2023-08-04 | 2023-08-16 | Underground | R16 | 2023-08-04 | 1 | 148 | 136 | 9 | 291 | 2022 | 2023 | R16
168704322978 | 166525322978 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-05-25 | 2023-03-15 | 2023-06-22 | 2023-11-15 | 2023-12-12 | Underground | R16 | 2023-11-15 | 211 | 72 | 105 | 20 | 405 | 2022 | 2023 | R16
169933282168 | 160187282168 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-05-04 | 2022-06-09 | 2022-06-09 | 2023-06-12 | 2023-06-15 | Underground | R16 | 2023-06-12 | 27 |  | 263 | 4 | 292 | 2022 | 2023 | R16
168583277578 | 167660277578 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-23 | 2022-04-29 | 2022-04-29 |  | 2022-07-02 | Overhead | R16 | 2022-06-29 | 28 |  | 44 | 3 | 73 | 2022 | 2022 | R16
163159277727 | 164335277727 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-27 | 2022-04-27 | 2022-04-30 |  | 2022-07-15 | Overhead | R16 | 2022-07-14 | 1 | 3 | 54 | 2 | 58 | 2022 | 2022 | R16
168960271419 | 165527271419 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-13 | 2021-12-13 | 2022-03-04 | 2022-05-29 | 2022-06-01 | Underground | R16 | 2022-05-29 | 1 | 60 | 61 | 3 | 123 | 2021 | 2022 | R16
169189284325 | 160084284325 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-06-13 | 2022-06-30 | 2022-06-30 |  | 2023-04-25 | Underground | R16 | 2023-01-23 | 14 |  | 148 | 67 | 227 | 2022 | 2023 | R16
163059248094 | 165990248094 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-16 | 2021-09-16 | 2021-09-16 | 2021-11-16 | 2021-12-10 | Overhead | R16 | 2021-11-16 | 1 |  | 44 | 19 | 62 | 2021 | 2021 | R16
165319258583 | 164696258583 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-26 | 2021-11-23 | 2021-11-23 |  | 2022-09-20 | Underground | R16 | 2022-08-05 | 21 |  | 184 | 33 | 236 | 2021 | 2022 | R16
163338267781 | 167213267781 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2022-02-06 | 2022-02-06 | 2022-02-06 |  | 2022-04-27 | Overhead | R16 | 2022-03-31 | 0 |  | 39 | 20 | 58 | 2022 | 2022 | R16
166758274011 | 168493274011 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-28 | 2022-03-28 | 2022-03-28 |  | 2022-06-20 | Underground | R16 | 2022-05-26 | 1 |  | 44 | 18 | 61 | 2022 | 2022 | R16
166183258772 | 166178258772 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-01 | 2021-11-26 | 2021-11-26 | 2022-02-10 | 2022-02-15 | Underground | R16 | 2022-02-10 | 20 |  | 55 | 4 | 77 | 2021 | 2022 | R16
161271285752 | 166861285752 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-14 | 2022-07-15 | 2022-07-15 | 2022-10-05 | 2022-12-04 | Overhead | R16 | 2022-10-05 | 2 |  | 59 | 43 | 102 | 2022 | 2022 | R16
162991251918 | 160681251918 | NON-RESIDENTIAL - SUBSEQUENT WORK | R16 ELEC DEVELOPMENT | Commercial | 2021-10-07 | 2021-10-07 | 2021-10-13 | 2021-12-30 | 2023-10-12 | Underground | R16 | 2021-12-30 | 1 | 5 | 57 | 466 | 526 | 2021 | 2023 | R16
163175254282 | 165733254282 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-28 | 2021-10-28 | 2021-10-28 | 2022-04-15 | 2022-04-16 | Overhead | R16 | 2022-04-15 | 1 |  | 122 | 1 | 122 | 2021 | 2022 | R16
165052289878 | 163745289878 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-05-13 | 2022-06-03 | 2022-08-22 | 2022-11-18 | 2022-12-29 | Underground | R16 | 2022-11-18 | 16 | 57 | 65 | 30 | 165 | 2022 | 2022 | R16
162183260708 | 167734260708 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-05 | 2021-12-10 | 2021-12-10 |  | 2023-02-17 | Overhead | R16 | 2022-10-27 | 26 |  | 230 | 82 | 336 | 2021 | 2023 | R16
160960269272 | 163637269272 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-01-24 | 2022-01-24 | 2022-02-16 |  | 2022-04-26 | Underground | R16 | 2022-04-06 | 1 | 18 | 36 | 15 | 67 | 2022 | 2022 | R16
160202279679 | 169948279679 | NON-RESIDENTIAL - SMALL RETAIL | R16 RESD AND NON RESD US | Commercial | 2022-04-04 | 2022-04-04 | 2022-05-18 |  | 2023-04-20 | Underground | R16 | 2023-03-23 | 1 | 33 | 222 | 21 | 274 | 2022 | 2023 | R16
163969309960 | 164212309960 | GENERAL/OTHER | UG R16 RESD AND NON RESD UD | Commercial | 2021-10-21 | 2021-10-21 | 2023-02-21 | 2023-07-14 | 2023-08-24 | Underground | R16 | 2023-07-14 | 1 | 349 | 104 | 30 | 481 | 2021 | 2023 | R16
167608276567 | 162793276567 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-01 | 2022-04-20 | 2022-04-20 |  | 2022-09-15 | Underground | R16 | 2022-07-26 | 37 |  | 70 | 38 | 143 | 2022 | 2022 | R16
160270247480 | 160432247480 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-20 | 2021-09-10 | 2021-09-10 |  | 2022-01-07 | Underground | R16 | 2021-11-30 | 16 |  | 58 | 29 | 101 | 2021 | 2022 | R16
163033275785 | 163580275785 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-10-19 | 2021-10-19 | 2022-04-13 | 2023-05-18 | 2023-08-18 | Overhead | R16 | 2023-05-18 | 1 | 127 | 287 | 67 | 479 | 2021 | 2023 | R16
163628289354 | 167448289354 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-18 | 2022-07-18 | 2022-08-17 |  | 2023-08-09 | Underground | R16 | 2023-07-21 | 1 | 23 | 243 | 14 | 278 | 2022 | 2023 | R16
167544264218 | 160997264218 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-11 | 2022-01-11 | 2022-01-11 | 2022-03-22 | 2022-04-21 | Overhead | R16 | 2022-03-22 | 1 |  | 51 | 23 | 73 | 2022 | 2022 | R16
166025270178 | 161496270178 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-02-24 | 2022-02-24 | 2022-02-24 | 2022-05-19 | 2022-05-11 | Underground | R16 | 2022-05-19 | 1 |  | 61 |  | 55 | 2022 | 2022 | R16
166424266264 | 163788266264 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-24 | 2022-01-26 | 2022-01-26 | 2022-01-27 | 2022-04-01 | Overhead | R16 | 2022-01-27 | 3 |  | 2 | 47 | 50 | 2022 | 2022 | R16
165669282301 | 169642282301 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-10 | 2022-06-10 | 2022-06-10 | 2022-07-20 | 2022-09-20 | Overhead | R16 | 2022-07-20 | 1 |  | 29 | 45 | 73 | 2022 | 2022 | R16
164731281867 | 168426281867 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-06 | 2022-06-07 | 2022-06-07 | 2022-07-03 | 2022-07-06 | Overhead | R16 | 2022-07-03 | 2 |  | 19 | 3 | 23 | 2022 | 2022 | R16
168926278110 | 169934278110 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-04 | 2022-04-04 | 2022-05-04 | 2022-08-22 | 2022-08-23 | Underground | R16 | 2022-08-22 | 1 | 23 | 79 | 2 | 102 | 2022 | 2022 | R16
162650310076 | 165582310076 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-11 | 2022-07-11 | 2023-02-22 | 2023-05-11 | 2023-06-12 | Underground | R16 | 2023-05-11 | 1 | 163 | 57 | 23 | 241 | 2022 | 2023 | R16
165644284641 | 164391284641 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-05 | 2022-07-05 | 2022-07-05 |  | 2022-08-24 | Overhead | R16 | 2022-08-15 | 1 |  | 30 | 8 | 37 | 2022 | 2022 | R16
163365279462 | 169197279462 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-03 | 2022-05-04 | 2022-05-16 |  | 2023-05-04 | Overhead | R16 |  | 2 | 9 |  |  | 263 | 2022 | 2023 | R16
161039286258 | 164984286258 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2022-07-07 | 2022-07-07 | 2022-07-20 |  | 2022-10-21 | Overhead | R16 |  | 1 | 10 |  |  | 77 | 2022 | 2022 | R16
165031274130 | 168436274130 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-28 | 2022-03-29 | 2022-03-29 | 2022-04-22 | 2022-04-25 | Overhead | R16 | 2022-04-22 | 2 |  | 19 | 2 | 21 | 2022 | 2022 | R16
160669283888 | 163076283888 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-27 | 2022-06-27 | 2022-06-27 |  | 2022-07-29 | Overhead | R16 | 2022-07-21 | 1 |  | 19 | 7 | 25 | 2022 | 2022 | R16
160204285695 | 166438285695 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-13 | 2022-07-15 | 2022-07-15 |  | 2022-08-24 | Overhead | R16 | 2022-08-22 | 3 |  | 27 | 3 | 31 | 2022 | 2022 | R16
164729285761 | 165926285761 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-12 | 2022-07-12 | 2022-07-14 | 2023-04-27 | 2023-05-12 | Underground | R16 | 2023-04-27 | 1 | 3 | 206 | 12 | 219 | 2022 | 2023 | R16
169229252777 | 160975252777 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-10-08 | 2021-10-19 | 2021-10-19 |  | 2022-02-02 | Overhead | R16 | 2022-02-02 | 8 |  | 77 |  | 84 | 2021 | 2022 | R16
160013253133 | 164187253133 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2023-05-24 | 2023-06-14 | Overhead | R16 | 2023-05-24 | 1 |  | 415 | 16 | 430 | 2021 | 2023 | R16
166733255785 | 168096255785 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-08 | 2021-11-09 | 2021-11-09 |  | 2022-09-19 | Overhead | R16 | 2022-09-16 | 2 |  | 224 | 2 | 226 | 2021 | 2022 | R16
161033276471 | 163044276471 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2022-04-20 | 2022-04-20 | 2022-04-20 | 2023-05-30 | 2023-08-17 | Underground | R16 | 2023-05-30 | 1 |  | 290 | 58 | 347 | 2022 | 2023 | R16
167700284935 | 164924284935 | RESIDENTIAL - MOBILE HOME | OH R16 RES NON RES OS | Residential | 2022-07-07 | 2022-07-07 | 2022-07-07 | 2022-12-11 | 2022-12-20 | Overhead | R16 | 2022-12-11 | 1 |  | 112 | 7 | 119 | 2022 | 2022 | R16
165893249068 | 167294249068 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2022-03-24 | 2022-04-13 | Overhead | R16 | 2022-03-24 | 1 |  | 132 | 15 | 146 | 2021 | 2022 | R16
166401286511 | 164942286511 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-07 | 2022-07-22 | 2022-07-22 |  | 2023-02-03 | Underground | R16 | 2022-11-21 | 12 |  | 87 | 55 | 152 | 2022 | 2023 | R16
169331283162 | 167186283162 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-21 | 2022-06-20 | 2022-06-20 |  | 2022-10-21 | Overhead | R16 | 2022-08-16 | 66 |  | 42 | 49 | 155 | 2022 | 2022 | R16
164678248864 | 167156248864 | RESIDENTIAL - SINGLE FAMILY ATTACHED | OH R16 RES NON RES OS | Residential | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-10-21 | 2021-11-18 | Overhead | R16 | 2021-10-21 | 1 |  | 23 | 21 | 43 | 2021 | 2021 | R16
166175310077 | 160801310077 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-02-22 | 2022-02-22 | 2023-02-22 | 2023-07-17 | 2023-08-24 | Underground | R16 | 2023-07-17 | 1 | 262 | 104 | 29 | 393 | 2022 | 2023 | R16
164742253027 | 164023253027 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-20 | 2021-10-20 | 2021-10-20 |  | 2022-01-11 | Overhead | R16 | 2021-12-01 | 1 |  | 31 | 30 | 60 | 2021 | 2022 | R16
162006263427 | 168888263427 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-01-04 | 2022-01-04 | 2022-01-04 |  | 2022-02-11 | Overhead | R16 | 2022-01-07 | 1 |  | 4 | 26 | 29 | 2022 | 2022 | R16
167685270173 | 169084270173 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-14 | 2022-02-23 | 2022-02-23 | 2022-06-28 | 2022-08-10 | Overhead | R16 | 2022-06-28 | 8 |  | 90 | 32 | 128 | 2022 | 2022 | R16
166387273288 | 161108273288 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-02-23 | 2022-02-23 | 2022-03-21 | 2022-10-29 | 2022-11-01 | Underground | R16 | 2022-10-29 | 1 | 19 | 160 | 2 | 180 | 2022 | 2022 | R16
167690269694 | 160051269694 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-17 | 2022-02-18 | 2022-02-18 | 2022-03-30 | 2022-04-27 | Overhead | R16 | 2022-03-30 | 2 |  | 29 | 21 | 50 | 2022 | 2022 | R16
166920281542 | 162072281542 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-02-25 | 2022-02-25 | 2022-06-03 | 2022-11-15 | 2022-12-06 | Underground | R16 | 2022-11-15 | 1 | 71 | 118 | 16 | 203 | 2022 | 2022 | R16
169555290115 | 165101290115 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-26 | 2022-08-25 | 2022-08-25 |  | 2023-02-26 | Overhead | R16 | 2023-01-26 | 218 |  | 111 | 22 | 349 | 2021 | 2023 | R16
167123276456 | 161678276456 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-13 | 2022-01-14 | 2022-04-20 | 2022-05-17 | 2022-06-10 | Overhead | R16 | 2022-05-17 | 2 | 69 | 20 | 19 | 107 | 2022 | 2022 | R16
162245279209 | 163041279209 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-11 | 2022-05-12 | 2022-05-12 | 2022-07-12 | 2022-08-23 | Overhead | R16 | 2022-07-12 | 2 |  | 44 | 31 | 75 | 2022 | 2022 | R16
166902272809 | 169064272809 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-14 | 2022-02-14 | 2022-03-16 |  | 2022-06-30 | Underground | R16 | 2022-06-21 | 1 | 23 | 70 | 8 | 99 | 2022 | 2022 | R16
163669284520 | 167912284520 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-02 | 2022-06-02 | 2022-07-05 |  | 2022-08-24 | Underground | R16 | 2022-08-09 | 1 | 24 | 26 | 12 | 60 | 2022 | 2022 | R16
161063285673 | 166837285673 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-07-15 | 2022-07-15 | 2022-07-15 | 2022-07-16 | 2022-07-29 | Overhead | R16 | 2022-07-16 | 1 |  | 1 | 10 | 11 | 2022 | 2022 | R16
167557287598 | 168624287598 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-07 | 2022-08-02 | 2022-08-02 | 2022-12-22 | 2023-01-24 | Overhead | R16 | 2022-12-22 | 41 |  | 103 | 24 | 166 | 2022 | 2023 | R16
164083264119 | 165542264119 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-13 | 2021-12-13 | 2022-01-11 | 2022-03-25 | 2022-06-03 | Underground | R16 | 2022-03-25 | 1 | 22 | 54 | 51 | 125 | 2021 | 2022 | R16
169088275861 | 165207275861 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-10 | 2022-03-15 | 2022-04-14 |  | 2022-07-07 | Underground | R16 | 2022-05-13 | 4 | 23 | 22 | 40 | 86 | 2022 | 2022 | R16
161079293300 | 168579293300 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-22 | 2022-09-10 | 2022-09-10 | 2022-12-15 | 2022-12-19 | Underground | R16 | 2022-12-15 | 36 |  | 69 | 3 | 107 | 2022 | 2022 | R16
167060250729 | 160005250729 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-05 | 2021-10-05 | 2021-10-05 | 2021-10-14 | 2021-12-16 | Overhead | R16 | 2021-10-14 | 1 |  | 8 | 46 | 53 | 2021 | 2021 | R16
161809267504 | 166627267504 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-03 | 2022-02-03 | 2022-02-03 | 2022-08-09 | 2022-10-21 | Overhead | R16 | 2022-08-09 | 1 |  | 134 | 54 | 187 | 2022 | 2022 | R16
160339257024 | 160053257024 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-16 | 2021-11-16 | 2021-11-17 |  | 2022-03-15 | Overhead | R16 | 2022-02-16 | 1 | 2 | 66 | 20 | 86 | 2021 | 2022 | R16
169950251374 | 161264251374 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-08 | 2021-10-08 | 2021-10-08 | 2021-10-26 | 2021-11-30 | Overhead | R16 | 2021-10-26 | 1 |  | 13 | 26 | 38 | 2021 | 2021 | R16
167366261536 | 166391261536 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2022-03-24 | 2022-04-20 | Underground | R16 | 2022-03-24 | 1 |  | 71 | 20 | 90 | 2021 | 2022 | R16
168270289225 | 168888289225 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-25 | 2022-07-25 | 2022-08-16 | 2022-09-29 | 2022-12-15 | Underground | R16 | 2022-09-29 | 1 | 17 | 33 | 56 | 104 | 2022 | 2022 | R16
164628292974 | 166929292974 | NON-RESIDENTIAL - WAREHOUSE | R16 RESD AND NON RESD US | Commercial | 2022-07-15 | 2022-07-15 | 2022-09-08 | 2023-04-10 | 2023-05-08 | Underground | R16 | 2023-04-10 | 1 | 40 | 153 | 21 | 212 | 2022 | 2023 | R16
166243327364 | 162812327364 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-06-24 | 2023-08-04 | 2023-08-04 | 2023-12-11 | 2023-12-28 | Overhead | R16 | 2023-12-11 | 291 |  | 92 | 14 | 395 | 2022 | 2023 | R16
169241284527 | 164453284527 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-05 | 2022-07-05 | 2022-07-05 | 2022-09-09 | 2023-07-26 | Overhead | R16 | 2022-09-09 | 1 |  | 49 | 229 | 277 | 2022 | 2023 | R16
161101253633 | 164473253633 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-22 | 2021-10-25 | 2021-10-25 | 2022-01-05 | 2022-01-06 | Overhead | R16 | 2022-01-05 | 2 |  | 53 | 2 | 55 | 2021 | 2022 | R16
163458255143 | 167392255143 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-04 | 2021-11-04 | 2021-11-04 | 2021-11-05 | 2022-01-20 | Overhead | R16 | 2021-11-05 | 1 |  | 2 | 55 | 56 | 2021 | 2022 | R16
163551289223 | 167383289223 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-18 | 2022-07-18 | 2022-08-16 |  | 2022-12-01 | Underground | R16 | 2022-11-28 | 1 | 22 | 75 | 4 | 99 | 2022 | 2022 | R16
164576298382 | 167870298382 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-06-02 | 2022-06-02 | 2022-10-26 | 2023-04-18 | 2023-01-27 | Underground | R16 | 2023-04-18 | 1 | 105 | 125 |  | 172 | 2022 | 2023 | R16
162913270475 | 165158270475 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-28 | 2022-01-28 | 2022-02-25 | 2022-05-12 | 2022-08-03 | Underground | R16 | 2022-05-12 | 1 | 21 | 55 | 60 | 134 | 2022 | 2022 | R16
163569263925 | 164103263925 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-12-07 | 2022-01-07 | 2022-01-07 | 2022-01-19 | 2022-02-28 | Overhead | R16 | 2022-01-19 | 24 |  | 9 | 29 | 60 | 2021 | 2022 | R16
168892276196 | 169958276196 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-04 | 2022-04-04 | 2022-04-19 | 2023-01-25 | 2023-11-07 | Underground | R16 | 2023-01-25 | 1 | 12 | 202 | 205 | 417 | 2022 | 2023 | R16
163194244962 | 163670244962 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-26 | 2021-07-26 | 2021-08-23 |  | 2021-11-10 | Underground | R16 | 2021-10-14 | 1 | 21 | 39 | 20 | 78 | 2021 | 2021 | R16
164298276282 | 167382276282 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-03-22 | 2022-03-22 | 2022-04-18 | 2023-09-08 | 2023-09-25 | Underground | R16 | 2023-09-08 | 1 | 20 | 365 | 12 | 395 | 2022 | 2023 | R16
160784281783 | 168405281783 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-06 | 2022-06-06 | 2022-06-06 |  | 2023-07-18 | Overhead | R16 | 2023-07-10 | 1 |  | 286 | 7 | 292 | 2022 | 2023 | R16
169068256217 | 169463256217 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2022-03-22 | 2022-04-21 | Overhead | R16 | 2022-03-22 | 1 |  | 93 | 23 | 115 | 2021 | 2022 | R16
168938259005 | 162391259005 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-29 | 2021-11-29 | 2021-11-29 | 2022-03-15 | 2022-04-01 | Overhead | R16 | 2022-03-15 | 1 |  | 77 | 14 | 90 | 2021 | 2022 | R16
163214244179 | 169626244179 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-18 | 2021-08-18 | 2021-08-18 |  | 2021-10-25 | Overhead | R16 | 2021-09-16 | 1 |  | 22 | 28 | 49 | 2021 | 2021 | R16
165085253482 | 167953253482 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-24 | 2021-09-24 | 2021-10-22 | 2021-12-13 | 2021-12-14 | Underground | R16 | 2021-12-13 | 1 | 21 | 37 | 2 | 58 | 2021 | 2021 | R16
163075324348 | 167544324348 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2022-03-22 | 2022-11-28 | 2023-07-06 | 2023-11-10 | 2023-12-12 | Underground | R16 | 2023-11-10 | 180 | 159 | 92 | 23 | 451 | 2022 | 2023 | R16
167662299102 | 166685299102 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-07-14 | 2022-09-13 | 2022-11-01 | 2023-01-10 | 2023-01-25 | Overhead | R16 | 2023-01-10 | 44 | 36 | 51 | 12 | 140 | 2022 | 2023 | R16
160504253070 | 162873253070 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-15 | 2021-10-20 | 2021-10-20 | 2022-01-31 | 2023-06-08 | Overhead | R16 | 2022-01-31 | 4 |  | 74 | 354 | 430 | 2021 | 2023 | R16
162509251580 | 161166251580 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-09 | 2021-10-09 | 2021-10-11 | 2022-03-14 | 2022-04-01 | Overhead | R16 | 2022-03-14 | 0 | 1 | 111 | 15 | 125 | 2021 | 2022 | R16
164751261105 | 167482261105 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-04 | 2021-11-04 | 2021-12-14 |  | 2022-06-30 | Underground | R16 | 2022-05-31 | 1 | 29 | 121 | 23 | 171 | 2021 | 2022 | R16
160167252317 | 162803252317 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-15 | 2021-10-15 | 2021-10-15 | 2022-10-13 | 2023-06-08 | Overhead | R16 | 2022-10-13 | 1 |  | 260 | 171 | 430 | 2021 | 2023 | R16
166026274518 | 168981274518 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-30 | 2022-04-01 | 2022-04-01 | 2022-05-16 | 2022-06-20 | Overhead | R16 | 2022-05-16 | 3 |  | 32 | 26 | 59 | 2022 | 2022 | R16
168274251767 | 161795251767 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-12 | 2021-10-12 | 2021-10-12 | 2022-02-24 | 2022-03-15 | Overhead | R16 | 2022-02-24 | 1 |  | 98 | 14 | 111 | 2021 | 2022 | R16
167430281361 | 163172281361 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-04-20 | 2022-06-01 | 2022-06-01 | 2023-01-05 | 2023-01-05 | Underground | R16 | 2023-01-05 | 31 |  | 157 |  | 187 | 2022 | 2023 | R16
163063285593 | 164160285593 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2022-04-26 | 2022-04-27 | 2022-07-14 |  | 2023-10-02 | Overhead | R16 |  | 2 | 57 |  |  | 375 | 2022 | 2023 | R16
163063285593 | 164160285593 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2022-04-26 | 2022-04-27 | 2022-07-14 |  | 2023-10-02 | Underground | R16 |  | 2 | 57 |  |  | 375 | 2022 | 2023 | R16
168604264803 | 168050264803 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-12-28 | 2021-12-28 | 2022-01-13 |  | 2022-10-21 | Underground | R16 | 2022-08-17 | 1 | 13 | 155 | 48 | 214 | 2021 | 2022 | R16
166809250533 | 169822250533 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-04 | 2021-10-05 | 2021-10-05 | 2022-07-13 | 2023-06-08 | Overhead | R16 | 2022-07-13 | 2 |  | 202 | 237 | 439 | 2021 | 2023 | R16
160985265154 | 162431265154 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-05-12 | 2022-05-13 | Overhead | R16 | 2022-05-12 | 1 |  | 83 | 2 | 84 | 2022 | 2022 | R16
164671255480 | 167850255480 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-07 | 2021-11-07 | 2021-11-07 |  | 2022-04-01 | Overhead | R16 | 2022-03-08 | 0 |  | 87 | 19 | 105 | 2021 | 2022 | R16
164966270127 | 161599270127 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-01-13 | 2022-01-13 | 2022-02-23 |  | 2022-06-20 | Overhead | R16 |  | 1 | 30 |  |  | 113 | 2022 | 2022 | R16
167403273517 | 167789273517 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-23 | 2022-03-23 | 2022-03-23 | 2022-03-25 | 2022-03-28 | Overhead | R16 | 2022-03-25 | 1 |  | 3 | 2 | 4 | 2022 | 2022 | R16
166984273799 | 160855273799 | NON-RESIDENTIAL - LARGE RETAIL | UG R16 RESD AND NON RESD UD | Commercial | 2022-01-11 | 2022-03-22 | 2022-03-25 | 2022-10-12 | 2022-10-14 | Underground | R16 | 2022-10-12 | 51 | 4 | 144 | 3 | 199 | 2022 | 2022 | R16
169227264100 | 169776264100 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-04 | 2021-10-04 | 2022-01-09 |  | 2022-04-19 | Underground | R16 | 2022-03-02 | 1 | 70 | 38 | 35 | 142 | 2021 | 2022 | R16
166320282642 | 166876282642 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-26 | 2022-05-27 | 2022-06-14 | 2022-09-28 | 2022-09-28 | Underground | R16 | 2022-09-28 | 2 | 13 | 77 |  | 90 | 2022 | 2022 | R16
161541293655 | 164275293655 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-04-26 | 2022-09-12 | 2022-09-14 |  | 2023-03-03 | Overhead | R16 |  | 100 | 3 |  |  | 224 | 2022 | 2023 | R16
165718282038 | 166562282038 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-25 | 2022-05-25 | 2022-06-09 |  | 2022-09-11 | Underground | R16 | 2022-08-15 | 1 | 12 | 48 | 20 | 78 | 2022 | 2022 | R16
164689251840 | 161645251840 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-10-12 | 2021-10-12 | 2021-10-12 |  | 2023-08-18 | Overhead | R16 | 2023-05-05 | 1 |  | 409 | 76 | 484 | 2021 | 2023 | R16
166987269386 | 169664269386 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-16 | 2022-02-16 | 2022-02-16 |  | 2022-12-04 | Overhead | R16 | 2022-11-01 | 1 |  | 185 | 24 | 208 | 2022 | 2022 | R16
163323272924 | 166275272924 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-16 | 2022-03-16 | 2022-03-16 |  | 2022-04-26 | Overhead | R16 | 2022-04-06 | 1 |  | 16 | 15 | 30 | 2022 | 2022 | R16
167114252032 | 168150252032 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-09-26 | 2021-09-26 | 2021-10-14 |  | 2021-12-02 | Overhead | R16 | 2021-11-02 | 0 | 14 | 14 | 23 | 49 | 2021 | 2021 | R16
161748271119 | 162625271119 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-19 | 2022-01-19 | 2022-03-03 |  | 2022-04-15 | Underground | R16 | 2022-04-15 | 1 | 32 | 32 |  | 63 | 2022 | 2022 | R16
160185271793 | 162239271793 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-28 | 2022-02-28 | 2022-03-08 | 2022-11-10 | 2023-07-27 | Underground | R16 | 2022-11-10 | 1 | 7 | 178 | 186 | 369 | 2022 | 2023 | R16
164906284829 | 162734284829 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2022-06-24 | 2022-06-24 | 2022-07-07 | 2022-12-30 | 2023-01-19 | Underground | R16 | 2022-12-30 | 1 | 10 | 127 | 15 | 150 | 2022 | 2023 | R16
165976262918 | 162013262918 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2021-11-24 | 2021-12-28 | 2021-12-30 |  | 2022-06-06 | Overhead | R16 |  | 25 | 3 |  |  | 139 | 2021 | 2022 | R16
164157266962 | 163622266962 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-23 | 2022-01-23 | 2022-01-31 | 2022-06-25 | 2022-06-28 | Underground | R16 | 2022-06-25 | 0 | 6 | 105 | 2 | 112 | 2022 | 2022 | R16
165109265523 | 163001265523 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-20 | 2022-01-20 | 2022-01-20 | 2022-02-15 | 2022-04-05 | Overhead | R16 | 2022-02-15 | 1 |  | 19 | 36 | 54 | 2022 | 2022 | R16
168493283299 | 161799283299 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-21 | 2022-06-21 | 2022-06-21 |  | 2022-12-04 | Overhead | R16 | 2022-10-05 | 1 |  | 77 | 43 | 119 | 2022 | 2022 | R16
165844260611 | 166189260611 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-01 | 2021-12-09 | 2021-12-09 | 2022-03-14 | 2022-04-01 | Overhead | R16 | 2022-03-14 | 29 |  | 68 | 15 | 110 | 2021 | 2022 | R16
160041251942 | 161669251942 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-12 | 2021-10-12 | 2021-10-13 | 2021-12-09 | 2022-01-20 | Overhead | R16 | 2021-12-09 | 1 | 2 | 42 | 31 | 73 | 2021 | 2022 | R16
167267274487 | 169276274487 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-31 | 2022-03-31 | 2022-03-31 | 2022-11-21 | 2022-12-06 | Overhead | R16 | 2022-11-21 | 1 |  | 168 | 12 | 179 | 2022 | 2022 | R16
162212281470 | 164483281470 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-03-08 | 2022-03-08 | 2022-06-03 |  | 2022-12-14 | Underground | R16 | 2022-10-21 | 1 | 64 | 101 | 39 | 202 | 2022 | 2022 | R16
167976263337 | 162242263337 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-11-24 | 2022-01-04 | 2022-01-04 | 2022-06-02 | 2022-06-20 | Underground | R16 | 2022-06-02 | 30 |  | 108 | 13 | 149 | 2021 | 2022 | R16
164706255163 | 163074255163 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-18 | 2021-10-18 | 2021-11-04 |  | 2022-02-09 | Underground | R16 | 2022-01-06 | 1 | 14 | 46 | 25 | 83 | 2021 | 2022 | R16
163358265717 | 168369265717 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-30 | 2022-01-21 | 2022-01-21 | 2022-03-17 | 2022-04-21 | Overhead | R16 | 2022-03-17 | 17 |  | 40 | 26 | 81 | 2021 | 2022 | R16
161907266532 | 165219266532 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-28 | 2022-01-28 | 2022-01-28 |  | 2022-04-26 | Overhead | R16 | 2022-04-06 | 1 |  | 49 | 15 | 63 | 2022 | 2022 | R16
168098275078 | 160925275078 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-08 | 2022-04-08 | 2022-04-08 | 2022-08-29 | 2022-10-21 | Underground | R16 | 2022-08-29 | 1 |  | 102 | 40 | 141 | 2022 | 2022 | R16
168497305625 | 168581305625 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2022-06-06 | 2022-07-21 | 2023-01-25 | 2023-10-05 | 2023-10-23 | Underground | R16 | 2023-10-05 | 34 | 135 | 182 | 13 | 361 | 2022 | 2023 | R16
163087263237 | 169121263237 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2022-01-04 | 2022-01-04 | 2022-01-04 | 2022-01-27 | 2022-03-28 | Overhead | R16 | 2022-01-27 | 1 |  | 18 | 43 | 60 | 2022 | 2022 | R16
167985263533 | 164845263533 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-09 | 2021-12-09 | 2022-01-04 |  | 2023-01-10 | Underground | R16 | 2022-11-02 | 1 | 19 | 217 | 50 | 284 | 2021 | 2023 | R16
160060277290 | 164491277290 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-27 | 2022-04-27 | 2022-04-27 |  | 2023-03-01 | Overhead | R16 | 2022-12-15 | 1 |  | 167 | 55 | 221 | 2022 | 2023 | R16
163648264574 | 161444264574 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-12 | 2022-01-12 | 2022-01-12 | 2022-02-11 | 2022-02-15 | Underground | R16 | 2022-02-11 | 1 |  | 23 | 3 | 25 | 2022 | 2022 | R16
165006240708 | 163672240708 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-26 | 2021-07-26 | 2021-07-26 |  | 2021-11-09 | Overhead | R16 | 2021-10-06 | 1 |  | 53 | 25 | 77 | 2021 | 2021 | R16
168487277059 | 161400277059 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-11 | 2022-04-13 | 2022-04-25 | 2022-06-02 | 2022-06-30 | Underground | R16 | 2022-06-02 | 3 | 9 | 29 | 21 | 59 | 2022 | 2022 | R16
162352297060 | 164337297060 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-27 | 2022-04-27 | 2022-10-14 |  | 2022-12-31 | Overhead | R16 | 2022-12-28 | 1 | 123 | 54 | 3 | 178 | 2022 | 2022 | R16
168321273982 | 168430273982 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-03-27 | 2022-03-27 | 2022-03-27 |  | 2022-05-02 | Overhead | R16 | 2022-04-29 | 0 |  | 25 | 2 | 26 | 2022 | 2022 | R16
168554283554 | 162820283554 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-06-24 | 2022-06-24 | 2022-06-24 |  | 2022-09-13 | Overhead | R16 |  | 1 |  |  |  | 58 | 2022 | 2022 | R16
165019249718 | 168264249718 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-09-28 | 2021-09-28 | 2021-09-28 |  | 2023-06-08 | Underground | R16 | 2023-04-10 | 1 |  | 400 | 44 | 443 | 2021 | 2023 | R16
163822280658 | 164359280658 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-16 | 2022-05-16 | 2022-05-26 | 2022-11-15 | 2023-03-03 | Underground | R16 | 2022-11-15 | 1 | 9 | 124 | 79 | 210 | 2022 | 2023 | R16
160071277344 | 161317277344 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-11 | 2022-04-11 | 2022-04-27 |  | 2023-01-10 | Underground | R16 | 2023-01-06 | 1 | 13 | 183 | 3 | 197 | 2022 | 2023 | R16
160016269978 | 162816269978 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-30 | 2021-11-30 | 2022-02-22 |  | 2022-06-01 | Overhead | R16 | 2022-05-05 | 1 | 61 | 53 | 20 | 132 | 2021 | 2022 | R16
163293279956 | 163230279956 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-04-20 | 2022-04-20 | 2022-05-20 | 2022-06-29 | 2022-07-14 | Overhead | R16 | 2022-06-29 | 1 | 23 | 29 | 12 | 62 | 2022 | 2022 | R16
165650281945 | 168906281945 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-07 | 2022-06-07 | 2022-06-07 |  | 2022-12-16 | Underground | R16 | 2022-10-06 | 1 |  | 88 | 52 | 139 | 2022 | 2022 | R16
168285270300 | 161321270300 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-23 | 2022-02-23 | 2022-02-23 |  | 2022-12-07 | Overhead | R16 | 2022-10-26 | 1 |  | 176 | 31 | 206 | 2022 | 2022 | R16
163614261923 | 166859261923 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-22 | 2022-03-02 | Overhead | R16 | 2021-12-22 | 1 |  | 3 | 51 | 53 | 2021 | 2022 | R16
163969285251 | 164198285251 | NON-RESIDENTIAL - LARGE OFFICE | UG R16 RESD AND NON RESD UD | Commercial | 2021-10-21 | 2021-10-21 | 2022-07-11 | 2022-07-25 | 2022-08-08 | Underground | R16 | 2022-07-25 | 1 | 188 | 11 | 11 | 208 | 2021 | 2022 | R16
168219275182 | 160752275182 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-07 | 2022-04-07 | 2022-04-07 | 2022-05-05 | 2022-08-03 | Overhead | R16 | 2022-05-05 | 1 |  | 21 | 65 | 85 | 2022 | 2022 | R16
162413288211 | 168056288211 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-28 | 2021-12-29 | 2022-08-08 |  | 2022-10-21 | Overhead | R16 | 2022-08-15 | 2 | 159 | 6 | 50 | 214 | 2021 | 2022 | R16
166647279564 | 160029279564 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-04-04 | 2022-05-11 | 2022-05-16 |  | 2022-07-25 | Overhead | R16 |  | 28 | 4 |  |  | 81 | 2022 | 2022 | R16
163562262607 | 164090262607 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-07 | 2021-12-27 | 2021-12-27 | 2022-01-14 | 2022-03-03 | Overhead | R16 | 2022-01-14 | 15 |  | 15 | 35 | 63 | 2021 | 2022 | R16
160109286194 | 166244286194 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-05-24 | 2022-05-24 | 2022-07-20 | 2022-12-25 | 2023-06-06 | Underground | R16 | 2022-12-25 | 1 | 42 | 113 | 117 | 271 | 2022 | 2023 | R16
162800257823 | 167302257823 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-22 | 2021-11-22 | 2021-11-22 | 2022-03-02 | 2022-03-03 | Underground | R16 | 2022-03-02 | 44 |  | 73 | 2 | 117 | 2021 | 2022 | R16
160726253394 | 164333253394 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-22 | 2021-10-22 | 2021-10-22 | 2021-11-12 | 2022-02-09 | Overhead | R16 | 2021-11-12 | 1 |  | 16 | 64 | 79 | 2021 | 2022 | R16
161343268307 | 166949268307 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-04 | 2022-02-09 | 2022-02-09 |  | 2022-04-01 | Overhead | R16 | 2022-03-30 | 4 |  | 36 | 3 | 41 | 2022 | 2022 | R16
165434246807 | 163266246807 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-23 | 2021-07-23 | 2021-09-07 |  | 2023-04-19 | Underground | R16 | 2023-01-25 | 1 | 33 | 362 | 61 | 454 | 2021 | 2023 | R16
162144251382 | 167592251382 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-23 | 2021-09-23 | 2021-10-08 | 2022-02-19 | 2022-03-28 | Underground | R16 | 2022-02-19 | 1 | 12 | 96 | 26 | 133 | 2021 | 2022 | R16
164621274441 | 169335274441 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-31 | 2022-03-31 | 2022-03-31 | 2022-04-05 | 2022-06-01 | Overhead | R16 | 2022-04-05 | 1 |  | 4 | 42 | 45 | 2022 | 2022 | R16
162502275627 | 166848275627 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-18 | 2022-04-12 | 2022-04-12 |  | 2023-03-16 | Overhead | R16 | 2023-03-07 | 18 |  | 236 | 8 | 260 | 2022 | 2023 | R16
167766282287 | 169569282287 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-10 | 2022-06-10 | 2022-06-10 | 2023-04-05 | 2023-12-04 | Overhead | R16 | 2023-04-05 | 1 |  | 214 | 174 | 387 | 2022 | 2023 | R16
160885276886 | 163620276886 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2022-04-22 | 2022-04-22 | 2022-04-22 | 2023-11-22 | 2023-12-08 | Overhead | R16 | 2023-11-22 | 1 |  | 414 | 13 | 426 | 2022 | 2023 | R16
167042287035 | 167472287035 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-18 | 2022-07-18 | 2022-07-27 | 2022-10-12 | 2022-12-15 | Underground | R16 | 2022-10-12 | 1 | 8 | 56 | 47 | 109 | 2022 | 2022 | R16
167265260388 | 166393260388 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-17 | 2021-09-17 | 2021-12-08 | 2023-08-01 | 2023-07-14 | Underground | R16 | 2023-08-01 | 1 | 59 | 430 |  | 476 | 2021 | 2023 | R16
167098281114 | 167491281114 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-01 | 2022-06-01 | 2022-06-01 | 2022-09-15 | 2023-01-05 | Underground | R16 | 2022-09-15 | 1 |  | 77 | 81 | 157 | 2022 | 2023 | R16
164729257702 | 167336257702 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-04 | 2021-11-04 | 2021-11-21 | 2021-12-31 | 2022-01-03 | Overhead | R16 | 2021-12-31 | 1 | 12 | 30 | 2 | 43 | 2021 | 2022 | R16
163738252567 | 165651252567 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-15 | 2021-09-15 | 2021-10-18 | 2022-02-18 | 2022-03-07 | Underground | R16 | 2022-02-18 | 1 | 24 | 90 | 12 | 124 | 2021 | 2022 | R16
166889250070 | 168909250070 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-29 | 2021-09-30 | 2021-09-30 | 2022-02-10 | 2022-03-11 | Overhead | R16 | 2022-02-10 | 2 |  | 96 | 22 | 118 | 2021 | 2022 | R16
167418275021 | 166258275021 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-02 | 2022-04-05 | 2022-04-05 | 2022-06-18 | 2022-06-21 | Underground | R16 | 2022-06-18 | 45 |  | 54 | 2 | 100 | 2022 | 2022 | R16
161007275773 | 167148275773 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2022-03-22 | 2022-03-22 | 2022-04-14 | 2023-09-27 | 2023-10-25 | Underground | R16 | 2023-09-27 | 1 | 18 | 380 | 21 | 417 | 2022 | 2023 | R16
163298281794 | 167911281794 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-08 | 2021-11-08 | 2022-06-06 | 2022-12-15 | 2022-12-22 | Underground | R16 | 2022-12-15 | 1 | 151 | 139 | 6 | 294 | 2021 | 2022 | R16
161848274547 | 169528274547 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-31 | 2022-03-31 | 2022-04-01 |  | 2022-05-03 | Underground | R16 | 2022-04-28 | 1 | 2 | 20 | 4 | 24 | 2022 | 2022 | R16
169652286345 | 161225286345 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-17 |  | 2022-07-20 | 2022-07-26 | 2022-09-20 | Overhead | R16 | 2022-07-26 |  |  | 5 | 41 | 68 | 2022 | 2022 | R16
167051312402 | 169491312402 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-01 | 2021-10-01 | 2023-03-14 |  | 2023-11-21 | Underground | R16 | 2023-03-16 | 1 | 378 | 3 | 179 | 558 | 2021 | 2023 | R16
164966256075 | 162138256075 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-10-13 | 2021-10-13 | 2021-11-11 |  | 2022-01-12 | Overhead | R16 |  | 1 | 22 |  |  | 66 | 2021 | 2022 | R16
168755285515 | 165664285515 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-05-21 | 2022-05-21 | 2022-07-13 | 2022-11-16 | 2022-12-06 | Underground | R16 | 2022-11-16 | 0 | 38 | 91 | 15 | 142 | 2022 | 2022 | R16
161451284896 | 164977284896 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-07 | 2022-07-07 | 2022-07-07 |  | 2022-09-11 | Overhead | R16 | 2022-08-04 | 1 |  | 21 | 27 | 47 | 2022 | 2022 | R16
168160283601 | 162525283601 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-23 | 2022-06-23 | 2022-06-23 |  | 2022-08-03 | Overhead | R16 | 2022-08-03 | 1 |  | 30 |  | 30 | 2022 | 2022 | R16
168139276022 | 160615276022 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-10-07 | 2022-04-13 | 2022-04-15 |  | 2022-08-10 | Overhead | R16 |  | 135 | 3 |  |  | 220 | 2021 | 2022 | R16
167049306356 | 166678306356 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-03-18 | 2022-08-10 | 2023-01-30 | 2023-05-25 | 2023-08-30 | Overhead | R16 | 2023-05-25 | 104 | 124 | 84 | 70 | 379 | 2022 | 2023 | R16
165046273465 | 166390273465 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-16 | 2022-03-18 | 2022-03-21 | 2022-06-06 | 2023-06-08 | Underground | R16 | 2022-06-06 | 3 | 2 | 56 | 264 | 322 | 2022 | 2023 | R16
168247283951 | 163215283951 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-06-28 | 2022-06-28 | 2022-06-28 |  | 2022-09-20 | Underground | R16 | 2022-08-04 | 1 |  | 28 | 34 | 61 | 2022 | 2022 | R16
161123254397 | 163546254397 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-10-19 | 2021-10-19 | 2021-10-29 | 2022-02-10 | 2022-03-10 | Underground | R16 | 2022-02-10 | 1 | 9 | 75 | 21 | 103 | 2021 | 2022 | R16
160252264292 | 161108264292 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-11 | 2022-01-11 | 2022-01-11 |  | 2023-01-25 | Overhead | R16 | 2023-01-18 | 1 |  | 267 | 6 | 272 | 2022 | 2023 | R16
168487276147 | 168438276147 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-10 | 2022-02-10 | 2022-04-15 | 2022-07-19 | 2022-07-20 | Underground | R16 | 2022-07-19 | 1 | 47 | 68 | 2 | 115 | 2022 | 2022 | R16
162245272575 | 165840272575 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-15 | 2022-03-15 | 2022-03-15 | 2022-08-26 | 2022-08-29 | Overhead | R16 | 2022-08-26 | 1 |  | 119 | 2 | 120 | 2022 | 2022 | R16
167100281914 | 162340281914 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-28 | 2021-11-28 | 2022-06-08 | 2022-09-13 | 2022-09-14 | Underground | R16 | 2022-09-13 | 0 | 138 | 70 | 2 | 208 | 2021 | 2022 | R16
161127285121 | 165252285121 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-08 | 2022-07-08 | 2022-07-08 | 2023-06-15 | 2023-09-19 | Overhead | R16 | 2023-06-15 | 1 |  | 245 | 69 | 313 | 2022 | 2023 | R16
168882253391 | 164295253391 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-22 | 2021-10-22 | 2021-10-22 | 2022-01-25 | 2022-06-12 | Overhead | R16 | 2022-01-25 | 1 |  | 68 | 99 | 166 | 2021 | 2022 | R16
163877285064 | 165275285064 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-08 | 2022-07-08 | 2022-07-08 |  | 2022-09-11 | Overhead | R16 | 2022-09-01 | 1 |  | 40 | 7 | 46 | 2022 | 2022 | R16
168769275838 | 169191275838 | NON-RESIDENTIAL - LARGE RETAIL | R16 RESD AND NON RESD US | Commercial | 2021-09-30 | 2022-03-04 | 2022-04-13 | 2022-10-12 | 2022-10-25 | Underground | R16 | 2022-10-12 | 112 | 29 | 131 | 10 | 279 | 2021 | 2022 | R16
165565266845 | 169961266845 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-06 | 2022-01-06 | 2022-01-31 |  | 2022-03-28 | Underground | R16 | 2022-03-10 | 1 | 18 | 29 | 13 | 58 | 2022 | 2022 | R16
165024281917 | 168538281917 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-28 | 2022-03-28 | 2022-06-08 |  | 2022-09-01 | Underground | R16 | 2022-08-31 | 1 | 53 | 61 | 2 | 114 | 2022 | 2022 | R16
167432251961 | 161869251961 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-13 | 2021-10-13 | 2021-10-13 | 2022-01-31 | 2022-03-03 | Overhead | R16 | 2022-01-31 | 1 |  | 79 | 24 | 102 | 2021 | 2022 | R16
166189274901 | 160157274901 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-05 | 2022-04-05 | 2022-04-05 | 2022-11-15 | 2023-01-10 | Overhead | R16 | 2022-11-15 | 1 |  | 161 | 41 | 201 | 2022 | 2023 | R16
166647277024 | 160205277024 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-04-05 | 2022-04-06 | 2022-04-25 |  | 2022-06-06 | Overhead | R16 |  | 2 | 14 |  |  | 45 | 2022 | 2022 | R16
161140264245 | 166006264245 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-12-14 | 2021-12-21 | 2022-01-10 |  | 2022-04-27 | Underground | R16 |  | 6 | 15 |  |  | 97 | 2021 | 2022 | R16
160083266877 | 164144266877 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-25 | 2022-01-31 | 2022-01-31 | 2022-03-08 | 2022-03-31 | Overhead | R16 | 2022-03-08 | 5 |  | 27 | 18 | 48 | 2022 | 2022 | R16
161170280783 | 166518280783 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-25 | 2022-05-25 | 2022-05-25 | 2022-06-28 | 2022-08-11 | Overhead | R16 | 2022-06-28 | 1 |  | 25 | 33 | 57 | 2022 | 2022 | R16
166647280110 | 161862280110 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-04-12 | 2022-04-12 | 2022-05-20 |  | 2022-07-25 | Overhead | R16 |  | 1 | 29 |  |  | 75 | 2022 | 2022 | R16
160376273625 | 166794273625 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-18 | 2022-03-23 | 2022-03-23 | 2022-04-20 | 2022-05-18 | Overhead | R16 | 2022-04-20 | 4 |  | 21 | 21 | 44 | 2022 | 2022 | R16
166893316096 | 160620316096 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-02-20 | 2022-02-20 | 2023-04-18 | 2023-09-11 | 2023-09-11 | Underground | R16 | 2023-09-11 | 0 | 302 | 105 |  | 406 | 2022 | 2023 | R16
163655287602 | 166083287602 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-12 | 2022-07-12 | 2022-08-01 | 2023-09-08 | 2023-09-12 | Underground | R16 | 2023-09-08 | 1 | 15 | 290 | 3 | 306 | 2022 | 2023 | R16
164474282183 | 167610282183 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-01 | 2022-06-01 | 2022-06-09 | 2022-08-14 | 2022-08-19 | Underground | R16 | 2022-08-14 | 1 | 7 | 47 | 5 | 58 | 2022 | 2022 | R16
161846267042 | 164485267042 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-26 | 2022-01-26 | 2022-02-01 | 2022-02-02 | 2022-04-25 | Underground | R16 | 2022-02-02 | 1 | 5 | 2 | 59 | 64 | 2022 | 2022 | R16
166410294940 | 165448294940 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2021-12-13 | 2022-07-08 | 2022-09-26 | 2023-06-09 | 2023-07-07 | Underground | R16 | 2023-06-09 | 150 | 57 | 185 | 21 | 410 | 2021 | 2023 | R16
167522267649 | 161104267649 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-01-11 | 2022-01-18 | 2022-02-04 | 2022-03-08 | 2022-03-14 | Underground | R16 | 2022-03-08 | 6 | 14 | 23 | 5 | 45 | 2022 | 2022 | R16
162005265541 | 163026265541 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-20 | 2022-01-20 | 2022-01-20 |  | 2022-08-03 | Overhead | R16 | 2022-06-21 | 1 |  | 109 | 32 | 140 | 2022 | 2022 | R16
166002269381 | 169692269381 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-16 | 2022-02-16 | 2022-02-16 | 2022-03-29 | 2022-04-25 | Underground | R16 | 2022-03-29 | 1 |  | 30 | 20 | 49 | 2022 | 2022 | R16
160863273440 | 165136273440 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-10-26 | 2022-03-21 | 2022-03-21 | 2022-07-20 | 2022-07-21 | Overhead | R16 | 2022-07-20 | 105 |  | 88 | 2 | 193 | 2021 | 2022 | R16
165273275221 | 167553275221 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2022-03-22 | 2022-04-07 | 2022-04-07 | 2022-06-10 | 2022-06-28 | Overhead | R16 | 2022-06-10 | 13 |  | 47 | 13 | 71 | 2022 | 2022 | R16
164460249016 | 167446249016 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-22 | 2021-09-23 | 2021-09-23 |  | 2021-11-02 | Overhead | R16 | 2021-10-18 | 2 |  | 18 | 12 | 30 | 2021 | 2021 | R16
167797275003 | 160470275003 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-06 | 2022-04-06 | 2022-04-06 | 2022-07-22 | 2022-07-25 | Overhead | R16 | 2022-07-22 | 1 |  | 78 | 2 | 79 | 2022 | 2022 | R16
167743257784 | 161050257784 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-11-22 | 2021-11-22 | 2021-11-22 |  | 2022-01-20 | Overhead | R16 |  | 1 |  |  |  | 44 | 2021 | 2022 | R16
160735276818 | 163725276818 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-22 | 2022-04-22 | 2022-04-22 | 2022-05-22 | 2022-05-31 | Overhead | R16 | 2022-05-22 | 1 |  | 21 | 7 | 28 | 2022 | 2022 | R16
168763286868 | 168886286868 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-25 | 2022-07-25 | 2022-07-25 |  | 2023-03-31 | Overhead | R16 | 2023-02-14 | 1 |  | 147 | 34 | 180 | 2022 | 2023 | R16
165846277198 | 162355277198 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-14 | 2022-04-27 | 2022-04-27 |  | 2022-08-11 | Overhead | R16 | 2022-06-29 | 10 |  | 46 | 32 | 86 | 2022 | 2022 | R16
162555284144 | 163841284144 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-29 | 2022-06-29 | 2022-06-29 |  | 2023-02-26 | Overhead | R16 | 2023-01-10 | 1 |  | 140 | 34 | 173 | 2022 | 2023 | R16
166415285047 | 163061285047 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-01-20 | 2022-07-08 | 2022-07-08 |  | 2023-02-03 | Underground | R16 | 2022-11-22 | 122 |  | 98 | 54 | 272 | 2022 | 2023 | R16
161802277604 | 164718277604 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-28 | 2022-04-29 | 2022-04-29 | 2022-07-12 | 2022-07-13 | Overhead | R16 | 2022-07-12 | 2 |  | 53 | 2 | 55 | 2022 | 2022 | R16
169784283983 | 162846283983 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-24 | 2022-06-27 | 2022-06-27 | 2023-07-09 | 2023-07-12 | Overhead | R16 | 2023-07-09 | 2 |  | 270 | 3 | 274 | 2022 | 2023 | R16
161265281160 | 164652281160 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-05-17 | 2022-05-20 | 2022-05-31 |  | 2022-09-20 | Underground | R16 |  | 4 | 8 |  |  | 91 | 2022 | 2022 | R16
165032270821 | 165838270821 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-01 | 2022-02-01 | 2022-02-28 |  | 2023-04-24 | Underground | R16 | 2023-01-06 | 1 | 20 | 225 | 77 | 320 | 2022 | 2023 | R16
165490306917 | 169469306917 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-31 | 2023-01-13 | 2023-01-30 | 2023-07-17 | 2023-09-05 | Underground | R16 | 2023-07-17 | 207 | 12 | 121 | 37 | 374 | 2022 | 2023 | R16
160174257067 | 168351257067 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Commercial | 2021-11-09 | 2021-11-09 | 2021-11-17 | 2023-01-18 | 2023-02-06 | Underground | R16 | 2023-01-18 | 1 | 7 | 306 | 14 | 325 | 2021 | 2023 | R16
161399278992 | 165359278992 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-04-29 | 2022-04-29 | 2022-05-11 |  | 2022-06-10 | Overhead | R16 |  | 1 | 9 |  |  | 31 | 2022 | 2022 | R16
167747283466 | 162215283466 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-22 | 2022-06-22 | 2022-06-22 |  | 2022-09-29 | Overhead | R16 | 2022-08-18 | 1 |  | 42 | 31 | 72 | 2022 | 2022 | R16
160817278762 | 161719278762 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-12 | 2022-04-12 | 2022-05-09 | 2022-12-19 | 2023-06-10 | Underground | R16 | 2022-12-19 | 1 | 20 | 161 | 125 | 304 | 2022 | 2023 | R16
163737279751 | 161414279751 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2021-10-11 | 2021-10-25 | 2022-05-18 |  | 2022-08-16 | Underground | R16 | 2022-07-11 | 11 | 148 | 39 | 27 | 222 | 2021 | 2022 | R16
168185281801 | 164838281801 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2022-04-28 | 2022-04-28 | 2022-06-06 |  | 2022-10-21 | Overhead | R16 |  | 1 | 28 |  |  | 127 | 2022 | 2022 | R16
166932268644 | 168422268644 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-10 | 2022-02-10 | 2022-02-10 |  | 2022-07-22 | Overhead | R16 | 2022-07-18 | 1 |  | 113 | 5 | 117 | 2022 | 2022 | R16
165757280545 | 166100280545 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-24 | 2022-05-24 | 2022-05-24 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 1 |  | 163 |  | 163 | 2022 | 2023 | R16
163141254518 | 166504254518 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-11-02 | 2021-11-02 | 2021-11-02 |  | 2022-05-13 | Overhead | R16 | 2022-04-21 | 1 |  | 123 | 17 | 139 | 2021 | 2022 | R16
163194281166 | 161760281166 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-05-05 | 2022-05-05 | 2022-05-31 |  | 2022-09-16 | Underground | R16 | 2022-09-15 | 1 | 19 | 78 | 2 | 97 | 2022 | 2022 | R16
164955281765 | 168411281765 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-06-06 | 2022-06-06 | 2022-06-06 | 2022-07-11 | 2022-07-27 | Overhead | R16 | 2022-07-11 | 1 |  | 26 | 13 | 38 | 2022 | 2022 | R16
169038282834 | 169391282834 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-09 | 2022-06-16 | 2022-06-16 | 2022-07-27 | 2022-08-03 | Overhead | R16 | 2022-07-27 | 6 |  | 30 | 6 | 40 | 2022 | 2022 | R16
167731263678 | 163457263678 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-02 | 2021-12-02 | 2022-01-06 | 2022-08-11 | 2022-08-24 | Underground | R16 | 2022-08-11 | 1 | 26 | 156 | 10 | 190 | 2021 | 2022 | R16
167969271588 | 162646271588 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-01 | 2022-03-04 | 2022-03-04 |  | 2022-07-25 | Overhead | R16 | 2022-07-05 | 4 |  | 88 | 15 | 105 | 2022 | 2022 | R16
168485257070 | 160004257070 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-16 | 2021-11-17 | 2021-11-17 | 2022-03-04 | 2022-03-25 | Overhead | R16 | 2022-03-04 | 2 |  | 78 | 16 | 94 | 2021 | 2022 | R16
166223256253 | 169236256253 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2022-10-24 | 2023-01-10 | Overhead | R16 | 2022-10-24 | 1 |  | 247 | 57 | 303 | 2021 | 2023 | R16
168467259973 | 163886259973 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-12-06 | 2021-12-06 | 2021-12-06 | 2022-06-01 | 2022-08-16 | Underground | R16 | 2022-06-01 | 1 |  | 128 | 55 | 182 | 2021 | 2022 | R16
165376269325 | 164238269325 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2022-01-26 | 2022-01-26 | 2022-02-16 | 2023-04-25 | 2023-08-11 | Underground | R16 | 2023-04-25 | 1 | 16 | 310 | 79 | 403 | 2022 | 2023 | R16
165014270820 | 165880270820 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-01 | 2022-02-01 | 2022-02-28 | 2022-04-12 | 2022-04-13 | Underground | R16 | 2022-04-12 | 1 | 20 | 32 | 2 | 52 | 2022 | 2022 | R16
161044269987 | 160715269987 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-22 | 2022-02-22 | 2022-02-22 |  | 2022-04-22 | Underground | R16 | 2022-04-22 | 1 |  | 44 |  | 44 | 2022 | 2022 | R16
164139255548 | 168086255548 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2021-11-08 | 2021-11-08 | 2021-11-08 | 2023-08-15 | 2023-08-16 | Overhead | R16 | 2023-08-15 | 1 |  | 462 | 2 | 463 | 2021 | 2023 | R16
164131271058 | 166634271058 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-12-17 | 2021-12-17 | 2022-03-01 | 2023-01-30 | 2023-02-14 | Underground | R16 | 2023-01-30 | 1 | 53 | 240 | 12 | 303 | 2021 | 2023 | R16
167143263763 | 168812263763 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-03 | 2022-01-03 | 2022-01-06 | 2022-01-24 | 2022-03-03 | Overhead | R16 | 2022-01-24 | 1 | 4 | 13 | 29 | 44 | 2022 | 2022 | R16
166321261544 | 162367261544 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-11-29 | 2021-12-14 | 2021-12-16 |  | 2022-06-20 | Underground | R16 | 2022-05-24 | 12 | 3 | 114 | 20 | 146 | 2021 | 2022 | R16
166995275647 | 160186275647 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-05 | 2022-04-05 | 2022-04-12 | 2022-05-17 | 2023-05-04 | Underground | R16 | 2022-05-17 | 1 | 6 | 26 | 253 | 283 | 2022 | 2023 | R16
168114283284 | 161521283284 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-06-20 | 2022-06-20 | 2022-06-20 |  | 2022-08-24 | Overhead | R16 | 2022-08-10 | 1 |  | 38 | 11 | 48 | 2022 | 2022 | R16
168453256294 | 169171256294 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-11-11 | 2021-11-12 | 2021-11-12 |  | 2022-06-08 | Underground | R16 | 2022-05-20 | 2 |  | 136 | 14 | 150 | 2021 | 2022 | R16
168460243214 | 164926243214 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-07-30 | 2021-08-12 | 2021-08-12 |  | 2023-03-09 | Underground | R16 | 2021-12-17 | 10 |  | 92 | 320 | 420 | 2021 | 2023 | R16
160360282202 | 164245282202 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-16 | 2022-05-16 | 2022-06-09 |  | 2022-09-26 | Underground | R16 | 2022-09-23 | 1 | 19 | 77 | 2 | 96 | 2022 | 2022 | R16
164687281676 | 168398281676 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-06 | 2022-06-07 | 2022-06-07 | 2023-01-22 | 2023-01-25 | Overhead | R16 | 2023-01-22 | 2 |  | 164 | 3 | 168 | 2022 | 2023 | R16
162169283949 | 161590283949 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-05 | 2022-05-31 | 2022-06-28 |  | 2023-12-15 | Underground | R16 | 2023-12-14 | 19 | 21 | 383 | 2 | 422 | 2022 | 2023 | R16
168589244207 | 169573244207 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-18 | 2021-08-18 | 2021-08-18 |  | 2021-11-09 | Overhead | R16 | 2021-09-30 | 1 |  | 32 | 29 | 60 | 2021 | 2021 | R16
164723282987 | 162311282987 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-06 | 2022-05-06 | 2022-06-17 |  | 2022-11-14 | Underground | R16 |  | 1 | 31 |  |  | 137 | 2022 | 2022 | R16
161633270311 | 168375270311 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2022-02-10 | 2022-02-10 | 2022-02-24 |  | 2022-04-01 | Overhead | R16 |  | 1 | 11 |  |  | 37 | 2022 | 2022 | R16
167114259833 | 166207259833 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-01 | 2021-12-03 | 2021-12-03 |  | 2022-06-20 | Underground | R16 | 2022-05-25 | 25 |  | 124 | 19 | 166 | 2021 | 2022 | R16
166009263209 | 168172263209 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-28 | 2022-01-03 | 2022-01-03 |  | 2022-04-26 | Overhead | R16 | 2022-04-06 | 5 |  | 68 | 15 | 86 | 2021 | 2022 | R16
160495255972 | 161933255972 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-12 | 2021-11-10 | 2021-11-10 |  | 2022-10-21 | Overhead | R16 | 2022-08-16 | 22 |  | 200 | 49 | 269 | 2021 | 2022 | R16
169906273379 | 163902273379 | NON-RESIDENTIAL - LARGE RETAIL | R16 RESD AND NON RESD US | Commercial | 2022-03-07 | 2022-03-07 | 2022-03-22 | 2022-08-28 | 2023-01-25 | Underground | R16 | 2022-08-28 | 1 | 12 | 114 | 108 | 233 | 2022 | 2023 | R16
168095265483 | 162709265483 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-20 | 2022-01-20 | 2022-01-20 | 2022-04-11 | 2022-05-12 | Overhead | R16 | 2022-04-11 | 1 |  | 58 | 24 | 81 | 2022 | 2022 | R16
164971319852 | 160743319852 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2021-11-19 | 2023-04-27 | 2023-05-23 | 2023-07-14 | 2023-10-26 | Underground | R16 | 2023-07-14 | 375 | 19 | 39 | 75 | 505 | 2021 | 2023 | R16
161182259679 | 164238259679 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-10-21 | 2021-10-21 | 2021-12-02 | 2022-03-18 | 2022-08-04 | Underground | R16 | 2022-03-18 | 1 | 31 | 77 | 100 | 206 | 2021 | 2022 | R16
165358285353 | 166086285353 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-07-12 | 2022-07-12 | 2022-07-12 |  | 2022-07-19 | Overhead | R16 |  | 1 |  |  |  | 6 | 2022 | 2022 | R16
164837289045 | 169670289045 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-10 | 2022-08-15 | 2023-01-30 | 2023-01-10 | 2023-03-31 | Overhead | R16 | 2023-01-10 | 47 | 121 |  | 59 | 211 | 2022 | 2023 | R16
162175253663 | 164783253663 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2022-02-09 | 2022-02-10 | Overhead | R16 | 2022-02-09 | 1 |  | 78 | 2 | 79 | 2021 | 2022 | R16
166271266519 | 164437266519 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2021-12-08 | 2021-12-27 | 2022-01-28 | 2022-02-02 | 2022-02-03 | Overhead | R16 | 2022-02-02 | 14 | 25 | 4 | 2 | 42 | 2021 | 2022 | R16
165734268661 | 162352268661 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-29 | 2021-11-29 | 2022-02-11 |  | 2022-08-25 | Overhead | R16 | 2022-08-24 | 1 | 55 | 139 | 2 | 194 | 2021 | 2022 | R16
161915269560 | 168366269560 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2022-02-10 | 2022-02-14 | 2022-02-17 |  | 2022-08-18 | Overhead | R16 |  | 3 | 4 |  |  | 136 | 2022 | 2022 | R16
166502293922 | 165407293922 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2022-05-20 | 2022-05-20 | 2022-09-15 |  | 2023-10-24 | Underground | R16 | 2023-10-09 | 1 | 85 | 278 | 12 | 373 | 2022 | 2023 | R16
161470274509 | 162839274509 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-15 | 2021-11-16 | 2022-03-31 | 2022-04-01 | 2022-04-25 | Overhead | R16 | 2022-04-01 | 23 | 98 | 2 | 17 | 137 | 2021 | 2022 | R16
161283259201 | 162713259201 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-30 | 2021-11-30 | 2021-11-30 | 2022-05-22 | 2022-05-27 | Overhead | R16 | 2022-05-22 | 1 |  | 124 | 5 | 129 | 2021 | 2022 | R16
160111253727 | 161988253727 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-13 | 2021-10-13 | 2021-10-26 | 2021-11-16 | 2021-12-17 | Underground | R16 | 2021-11-16 | 1 | 10 | 16 | 24 | 48 | 2021 | 2021 | R16
163872277579 | 169164277579 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-30 | 2022-03-30 | 2022-04-29 | 2022-12-19 | 2023-01-11 | Underground | R16 | 2022-12-19 | 1 | 23 | 167 | 18 | 206 | 2022 | 2023 | R16
162961278012 | 163445278012 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-22 | 2022-05-03 | 2022-05-03 |  | 2023-02-02 | Overhead | R16 | 2022-09-12 | 8 |  | 95 | 104 | 205 | 2022 | 2023 | R16
161118266136 | 166323266136 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-12-16 | 2021-12-16 | 2022-01-26 |  | 2022-03-21 | Underground | R16 | 2022-03-17 | 1 | 30 | 37 | 3 | 68 | 2021 | 2022 | R16
162218273640 | 164183273640 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-21 | 2021-10-21 | 2022-03-23 |  | 2022-06-01 | Underground | R16 | 2022-05-04 | 1 | 110 | 31 | 21 | 160 | 2021 | 2022 | R16
168546274154 | 162348274154 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-02-28 | 2022-02-28 | 2022-03-29 |  | 2023-07-22 | Underground | R16 |  | 1 | 22 |  |  | 365 | 2022 | 2023 | R16
167950281641 | 168083281641 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2022-06-03 | 2022-06-05 | 2022-06-06 |  | 2022-08-16 | Overhead | R16 |  | 1 | 1 |  |  | 53 | 2022 | 2022 | R16
164182288754 | 168091288754 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2022-06-03 | 2022-06-06 | 2022-08-12 | 2022-11-09 | 2022-12-13 | Underground | R16 | 2022-11-09 | 2 | 50 | 64 | 25 | 138 | 2022 | 2022 | R16
164864272092 | 160829272092 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-02-22 | 2022-02-22 | 2022-03-09 | 2022-04-13 | 2022-04-19 | Underground | R16 | 2022-04-13 | 1 | 12 | 26 | 5 | 41 | 2022 | 2022 | R16
168211275531 | 161522275531 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-12 | 2022-04-12 | 2022-04-12 | 2023-04-11 | 2023-08-14 | Overhead | R16 | 2023-04-11 | 1 |  | 261 | 90 | 350 | 2022 | 2023 | R16
164249261679 | 166524261679 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-12-17 | 2021-12-17 | 2021-12-17 | 2023-08-02 | 2023-10-16 | Underground | R16 | 2023-08-02 | 1 |  | 424 | 54 | 477 | 2021 | 2023 | R16
162095313316 | 164397313316 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-08 | 2021-12-08 | 2023-03-23 | 2023-10-10 | 2023-10-30 | Underground | R16 | 2023-10-10 | 1 | 337 | 144 | 15 | 494 | 2021 | 2023 | R16
169698265405 | 169426265405 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-08-17 | 2022-01-19 | 2022-01-20 |  | 2022-10-17 | Overhead | R16 |  | 112 | 2 |  |  | 305 | 2021 | 2022 | R16
169833266432 | 168658266432 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-09-29 | 2021-09-29 | 2022-01-27 |  | 2022-09-14 | Underground | R16 |  | 1 | 87 |  |  | 251 | 2021 | 2022 | R16
163877301168 | 167059301168 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-05-28 | 2022-05-28 | 2022-11-21 |  | 2023-12-19 | Overhead | R16 | 2023-12-18 | 0 | 126 | 281 | 2 | 407 | 2022 | 2023 | R16
162427279158 | 167271279158 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-07 | 2022-02-07 | 2022-05-13 |  | 2022-09-30 | Underground | R16 | 2022-09-20 | 1 | 70 | 93 | 9 | 170 | 2022 | 2022 | R16
160300266260 | 164324266260 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-26 | 2022-01-26 | 2022-01-26 | 2022-03-14 | 2022-04-01 | Overhead | R16 | 2022-03-14 | 1 |  | 34 | 15 | 48 | 2022 | 2022 | R16
165790255934 | 166200255934 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-01 | 2021-11-01 | 2021-11-10 | 2022-01-13 | 2022-03-08 | Underground | R16 | 2022-01-13 | 1 | 8 | 47 | 39 | 92 | 2021 | 2022 | R16
167580274760 | 168842274760 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-29 | 2022-03-29 | 2022-04-04 |  | 2022-06-09 | Underground | R16 | 2022-05-16 | 1 | 5 | 31 | 19 | 53 | 2022 | 2022 | R16
169245283710 | 162047283710 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-22 | 2022-06-24 | 2022-06-24 | 2022-08-18 | 2022-10-21 | Overhead | R16 | 2022-08-18 | 3 |  | 40 | 47 | 88 | 2022 | 2022 | R16
164206277353 | 160098277353 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2022-02-18 | 2022-02-25 | 2022-04-27 | 2022-07-18 | 2022-10-06 | Underground | R16 | 2022-07-18 | 6 | 44 | 59 | 59 | 165 | 2022 | 2022 | R16
161935262911 | 168364262911 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-30 | 2021-12-30 | 2021-12-30 | 2022-04-20 | 2022-04-21 | Overhead | R16 | 2022-04-20 | 1 |  | 80 | 2 | 81 | 2021 | 2022 | R16
164640274830 | 166674274830 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-03 | 2022-02-03 | 2022-04-05 | 2022-09-27 | 2022-10-11 | Underground | R16 | 2022-09-27 | 1 | 44 | 126 | 11 | 179 | 2022 | 2022 | R16
166813251998 | 162228251998 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-13 | 2021-10-13 | 2021-10-13 |  | 2021-12-17 | Overhead | R16 | 2021-12-16 | 1 |  | 47 | 2 | 48 | 2021 | 2021 | R16
163265284065 | 163268284065 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-28 | 2022-06-28 | 2022-06-28 |  | 2022-08-31 | Overhead | R16 | 2022-08-30 | 1 |  | 46 | 2 | 47 | 2022 | 2022 | R16
164984251066 | 166778251066 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-20 | 2021-09-20 | 2021-10-06 |  | 2022-04-01 | Underground | R16 | 2022-03-09 | 1 | 13 | 111 | 18 | 140 | 2021 | 2022 | R16
163101265210 | 162439265210 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-01-19 | 2022-01-19 | 2022-01-19 |  | 2022-03-01 | Overhead | R16 | 2022-01-28 | 1 |  | 8 | 23 | 30 | 2022 | 2022 | R16
169980259000 | 162417259000 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-14 | 2021-11-29 | 2021-11-29 | 2022-01-06 | 2022-03-08 | Overhead | R16 | 2022-01-06 | 33 |  | 29 | 44 | 104 | 2021 | 2022 | R16
165659282665 | 160275282665 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-14 | 2022-06-14 | 2022-06-14 |  | 2022-09-11 | Overhead | R16 | 2022-08-25 | 1 |  | 53 | 12 | 64 | 2022 | 2022 | R16
162627273201 | 166894273201 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-18 | 2022-03-18 | 2022-03-18 | 2022-04-13 | 2022-05-05 | Overhead | R16 | 2022-04-13 | 1 |  | 19 | 17 | 35 | 2022 | 2022 | R16
169504282095 | 164799282095 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-18 | 2022-05-18 | 2022-06-09 | 2022-08-01 | 2022-08-02 | Underground | R16 | 2022-08-01 | 1 | 17 | 38 | 2 | 55 | 2022 | 2022 | R16
167387289830 | 169567289830 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-06-10 | 2022-08-19 | 2022-08-23 | 2022-10-13 | 2022-10-14 | Overhead | R16 | 2022-10-13 | 51 | 3 | 38 | 2 | 91 | 2022 | 2022 | R16
166849252673 | 169146252673 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-30 | 2021-09-30 | 2021-10-19 | 2022-01-31 | 2022-03-03 | Underground | R16 | 2022-01-31 | 1 | 14 | 75 | 24 | 111 | 2021 | 2022 | R16
168814277902 | 161543277902 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-12 | 2022-04-12 | 2022-05-02 |  | 2022-07-03 | Overhead | R16 | 2022-06-28 | 1 | 15 | 42 | 4 | 59 | 2022 | 2022 | R16
163463270298 | 161484270298 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-24 | 2022-02-24 | 2022-02-24 |  | 2022-04-27 | Overhead | R16 | 2022-04-01 | 1 |  | 27 | 19 | 45 | 2022 | 2022 | R16
166817254372 | 166295254372 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-01 | 2021-11-01 | 2021-11-01 | 2021-12-29 | 2022-03-08 | Overhead | R16 | 2021-12-29 | 1 |  | 43 | 50 | 92 | 2021 | 2022 | R16
160591260766 | 165086260766 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-10 | 2021-12-10 | 2021-12-10 |  | 2022-12-16 | Overhead | R16 | 2022-10-26 | 1 |  | 229 | 38 | 266 | 2021 | 2022 | R16
163456267482 | 166277267482 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-02-02 | 2022-02-02 | 2022-02-03 |  | 2022-08-10 | Overhead | R16 | 2022-07-06 | 1 | 2 | 110 | 26 | 136 | 2022 | 2022 | R16
160545242727 | 163750242727 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-26 | 2021-07-26 | 2021-08-09 |  | 2021-10-26 | Underground | R16 | 2021-09-01 | 1 | 11 | 18 | 40 | 67 | 2021 | 2021 | R16
160546246079 | 167033246079 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-09 | 2021-08-09 | 2021-09-01 |  | 2021-11-30 | Underground | R16 | 2021-11-03 | 1 | 18 | 46 | 20 | 82 | 2021 | 2021 | R16
168298302742 | 166847302742 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-15 | 2022-08-05 | 2022-12-08 |  | 2023-04-27 | Underground | R16 | 2023-02-03 | 16 | 90 | 42 | 60 | 205 | 2022 | 2023 | R16
160558250361 | 168845250361 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-29 | 2021-09-29 | 2021-10-01 |  | 2022-04-20 | Underground | R16 | 2022-04-19 | 1 | 3 | 143 | 2 | 146 | 2021 | 2022 | R16
165078275012 | 168310275012 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-03-25 | 2022-03-30 | 2022-04-06 | 2022-07-07 | 2022-08-18 | Overhead | R16 | 2022-07-07 | 4 | 6 | 67 | 31 | 105 | 2022 | 2022 | R16
160575243198 | 164929243198 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-30 | 2021-07-30 | 2021-08-12 |  | 2021-11-02 | Underground | R16 | 2021-10-14 | 1 | 10 | 46 | 14 | 68 | 2021 | 2021 | R16
166251285268 | 165651285268 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-11 | 2022-07-11 | 2022-07-11 |  | 2022-09-11 | Overhead | R16 | 2022-08-11 | 1 |  | 24 | 22 | 45 | 2022 | 2022 | R16
164906283122 | 161956283122 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-11-23 | 2021-11-23 | 2022-06-20 |  | 2023-10-03 | Underground | R16 | 2023-09-20 | 1 | 150 | 328 | 10 | 486 | 2021 | 2023 | R16
164226275872 | 162315275872 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-15 | 2022-04-15 | 2022-04-15 | 2022-09-19 | 2023-01-05 | Overhead | R16 | 2022-09-19 | 1 |  | 112 | 79 | 190 | 2022 | 2023 | R16
161580272185 | 164782272185 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-09 | 2022-03-10 | 2022-03-10 |  | 2022-05-05 | Overhead | R16 | 2022-05-05 | 2 |  | 41 |  | 42 | 2022 | 2022 | R16
165191285343 | 164425285343 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-07-05 | 2022-07-05 | 2022-07-12 |  | 2023-03-01 | Overhead | R16 |  | 1 | 6 |  |  | 172 | 2022 | 2023 | R16
161264284200 | 163261284200 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-03 | 2022-03-09 | 2022-06-29 |  | 2023-01-10 | Underground | R16 | 2022-10-31 | 5 | 81 | 89 | 52 | 224 | 2022 | 2023 | R16
162531269189 | 169177269189 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-01-04 | 2022-01-04 | 2022-02-16 | 2022-04-06 | 2022-04-13 | Underground | R16 | 2022-04-06 | 1 | 32 | 36 | 6 | 72 | 2022 | 2022 | R16
160993277929 | 163982277929 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-10-20 | 2021-12-09 | 2022-05-02 |  | 2022-06-20 | Overhead | R16 |  | 37 | 103 |  |  | 174 | 2021 | 2022 | R16
168727250777 | 160382250777 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-06 | 2021-10-06 | 2021-10-06 | 2021-11-18 | 2022-01-07 | Overhead | R16 | 2021-11-18 | 1 |  | 32 | 37 | 68 | 2021 | 2022 | R16
162408318886 | 167538318886 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG R16 RESD AND NON RESD UD | Commercial | 2022-06-01 | 2022-06-15 | 2023-05-12 | 2023-10-13 | 2023-11-09 | Underground | R16 | 2023-10-13 | 11 | 238 | 111 | 20 | 377 | 2022 | 2023 | R16
166072262075 | 166974262075 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-03 | 2021-12-20 | 2021-12-20 |  | 2022-05-04 | Overhead | R16 | 2022-04-28 | 34 |  | 94 | 5 | 131 | 2021 | 2022 | R16
161476279582 | 162885279582 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-05-10 | 2022-05-16 | 2022-05-16 | 2022-08-03 | 2022-08-05 | Overhead | R16 | 2022-08-03 | 5 |  | 58 | 3 | 64 | 2022 | 2022 | R16
168682320288 | 161614320288 | NON-RESIDENTIAL - MISCELLANEOUS | UG ELEC MISC SVC US | Commercial | 2022-04-12 | 2022-09-06 | 2023-05-25 |  | 2023-12-11 | Underground | R16 |  | 106 | 188 |  |  | 435 | 2022 | 2023 | R16
162501275257 | 161060275257 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-08 | 2022-04-08 | 2022-04-08 | 2022-05-16 | 2022-06-20 | Overhead | R16 | 2022-05-16 | 1 |  | 27 | 26 | 52 | 2022 | 2022 | R16
162295278917 | 163048278917 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2023-01-19 | 2023-01-24 | Overhead | R16 | 2023-01-19 | 1 |  | 182 | 4 | 185 | 2022 | 2023 | R16
163034248732 | 166782248732 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-09-20 | 2021-09-21 | 2021-09-21 | 2021-11-02 | 2021-12-02 | Overhead | R16 | 2021-11-02 | 2 |  | 31 | 23 | 54 | 2021 | 2021 | R16
166054298321 | 162906298321 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG R16 RESD AND NON RESD UD | Commercial | 2021-10-15 | 2022-05-09 | 2022-10-26 | 2023-06-21 | 2023-07-20 | Underground | R16 | 2023-06-21 | 147 | 123 | 171 | 22 | 460 | 2021 | 2023 | R16
167187256343 | 161025256343 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-10-08 | 2021-10-08 | 2021-11-12 |  | 2022-02-22 | Underground | R16 | 2022-01-19 | 1 | 26 | 49 | 25 | 98 | 2021 | 2022 | R16
161132315549 | 160971315549 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-04-08 | 2022-04-08 | 2023-04-12 | 2023-08-07 | 2023-09-05 | Underground | R16 | 2023-08-07 | 1 | 264 | 84 | 22 | 368 | 2022 | 2023 | R16
164478296361 | 167252296361 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-07-18 | 2022-07-18 | 2022-10-07 | 2023-04-24 | 2023-06-02 | Underground | R16 | 2023-04-24 | 1 | 60 | 142 | 30 | 230 | 2022 | 2023 | R16
169142257460 | 161529257460 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-12 | 2021-10-12 | 2021-11-18 | 2022-01-10 | 2022-04-12 | Underground | R16 | 2022-01-10 | 1 | 28 | 38 | 67 | 131 | 2021 | 2022 | R16
160642278973 | 162792278973 | NON-RESIDENTIAL - LARGE OFFICE | R16 RESD AND NON RESD US | Commercial | 2022-05-10 | 2022-05-10 | 2022-05-12 |  | 2022-06-27 | Underground | R16 | 2022-05-31 | 1 | 3 | 14 | 20 | 35 | 2022 | 2022 | R16
160025262011 | 166779262011 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-20 | 2021-12-20 | 2021-12-20 |  | 2023-07-20 | Overhead | R16 | 2023-06-15 | 1 |  | 389 | 26 | 414 | 2021 | 2023 | R16
169972283124 | 167030283124 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-27 | 2022-06-17 | 2022-06-20 |  | 2023-08-03 | Overhead | R16 | 2023-08-02 | 16 | 2 | 293 | 2 | 310 | 2022 | 2023 | R16
162405286791 | 168954286791 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-25 | 2022-07-25 | 2022-07-25 | 2022-09-16 | 2022-09-19 | Overhead | R16 | 2022-09-16 | 1 |  | 40 | 2 | 41 | 2022 | 2022 | R16
165589286913 | 169044286913 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-08 | 2022-06-08 | 2022-07-26 |  | 2023-12-11 | Underground | R16 | 2023-12-01 | 1 | 35 | 354 | 7 | 394 | 2022 | 2023 | R16
167056255955 | 168530255955 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-09 | 2021-11-10 | 2021-11-10 | 2022-01-19 | 2023-06-08 | Overhead | R16 | 2022-01-19 | 2 |  | 51 | 362 | 413 | 2021 | 2023 | R16
168713262169 | 168305262169 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-09-27 | 2021-09-27 | 2021-12-21 | 2022-03-24 | 2022-04-13 | Overhead | R16 | 2022-03-24 | 1 | 62 | 68 | 15 | 143 | 2021 | 2022 | R16
160408288405 | 165192288405 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-08 | 2022-07-18 | 2022-08-09 |  | 2023-03-24 | Underground | R16 | 2023-01-05 | 7 | 17 | 108 | 57 | 186 | 2022 | 2023 | R16
168338257013 | 169929257013 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-16 | 2021-11-17 | 2021-11-17 | 2022-07-06 | 2022-08-16 | Overhead | R16 | 2022-07-06 | 2 |  | 166 | 30 | 196 | 2021 | 2022 | R16
163532280543 | 164314280543 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-16 | 2022-05-16 | 2022-05-24 | 2022-07-13 | 2022-08-23 | Underground | R16 | 2022-07-13 | 1 | 7 | 37 | 30 | 72 | 2022 | 2022 | R16
165214268560 | 168261268560 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-10 | 2022-02-10 | 2022-02-10 |  | 2022-06-10 | Overhead | R16 | 2022-05-18 | 1 |  | 70 | 18 | 87 | 2022 | 2022 | R16
164552266313 | 167439266313 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-04 | 2021-11-04 | 2022-01-27 | 2022-04-19 | 2022-04-20 | Underground | R16 | 2022-04-19 | 1 | 61 | 59 | 2 | 120 | 2021 | 2022 | R16
160049254531 | 161654254531 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-10-12 | 2021-11-01 | 2021-11-01 | 2022-01-20 | 2022-02-28 | Overhead | R16 | 2022-01-20 | 15 |  | 59 | 28 | 100 | 2021 | 2022 | R16
167901268578 | 168534268578 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-11 | 2022-02-11 | 2022-02-11 |  | 2022-05-31 | Overhead | R16 | 2022-05-02 | 1 |  | 57 | 22 | 78 | 2022 | 2022 | R16
165737259425 | 166282259425 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-01 | 2021-11-09 | 2021-12-01 | 2022-01-27 | 2022-03-02 | Underground | R16 | 2022-01-27 | 7 | 17 | 42 | 25 | 88 | 2021 | 2022 | R16
169762270931 | 160234270931 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-17 | 2022-02-17 | 2022-03-01 | 2022-06-08 | 2022-07-25 | Underground | R16 | 2022-06-08 | 1 | 9 | 72 | 34 | 113 | 2022 | 2022 | R16
168817275048 | 160504275048 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-06 | 2022-04-06 | 2022-04-06 |  | 2023-01-10 | Overhead | R16 | 2022-11-02 | 1 |  | 151 | 50 | 200 | 2022 | 2023 | R16
161956263241 | 166232263241 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-05 | 2021-08-05 | 2022-01-03 |  | 2022-04-26 | Underground | R16 | 2022-04-07 | 1 | 108 | 69 | 14 | 189 | 2021 | 2022 | R16
166538258544 | 168417258544 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-09 | 2021-11-09 | 2021-11-23 | 2022-02-28 | 2022-02-28 | Underground | R16 | 2022-02-28 | 1 | 11 | 70 |  | 80 | 2021 | 2022 | R16
163000260979 | 165758260979 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-14 | 2021-12-14 | 2021-12-14 |  | 2022-04-15 | Overhead | R16 | 2022-04-13 | 1 |  | 87 | 3 | 89 | 2021 | 2022 | R16
161557272058 | 164856272058 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-10 | 2022-03-10 | 2022-03-10 | 2022-05-16 | 2023-04-08 | Overhead | R16 | 2022-05-16 | 1 |  | 48 | 235 | 282 | 2022 | 2023 | R16
165404287053 | 164763287053 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH CP R16 WORK RELO TO UG | Residential | 2021-10-25 | 2022-02-07 | 2022-07-27 | 2022-08-22 | 2022-10-03 | Overhead | R16 | 2022-08-22 | 76 | 123 | 19 | 31 | 246 | 2021 | 2022 | R16
167517269862 | 169694269862 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-16 |  | 2022-02-18 | 2022-03-29 | 2022-04-25 | Overhead | R16 | 2022-03-29 |  |  | 28 | 20 | 49 | 2022 | 2022 | R16
161044285479 | 168558285479 | NON-RESIDENTIAL - WAREHOUSE | UG R16 RESD AND NON RESD UD | Commercial | 2022-02-11 | 2022-02-11 | 2022-07-14 | 2023-05-31 | 2023-08-16 | Underground | R16 | 2023-05-31 | 1 | 110 | 230 | 56 | 394 | 2022 | 2023 | R16
162241248244 | 165986248244 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2021-09-16 | 2021-09-16 | 2021-09-16 |  | 2022-02-23 | Overhead | R16 | 2022-02-22 | 1 |  | 114 | 2 | 115 | 2021 | 2022 | R16
163083268680 | 164225268680 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-07 | 2021-12-07 | 2022-02-10 |  | 2022-05-05 | Underground | R16 |  | 1 | 48 |  |  | 108 | 2021 | 2022 | R16
168682318013 | 168310318013 | NON-RESIDENTIAL - MISCELLANEOUS | UG ELEC MISC SVC US | Commercial | 2022-02-10 | 2022-02-24 | 2023-05-05 | 2023-07-23 | 2023-12-11 | Underground | R16 | 2023-07-23 | 11 | 312 | 56 | 101 | 478 | 2022 | 2023 | R16
169133259043 | 160001259043 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-16 | 2021-11-16 | 2021-11-29 | 2022-05-09 | 2022-06-10 | Underground | R16 | 2022-05-09 | 1 | 10 | 116 | 25 | 149 | 2021 | 2022 | R16
163364274878 | 168003274878 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-09 | 2022-02-17 | 2022-04-05 |  | 2022-08-11 | Underground | R16 | 2022-06-28 | 7 | 34 | 61 | 33 | 132 | 2022 | 2022 | R16
164830279684 | 161834279684 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-06 | 2022-05-06 | 2022-05-17 |  | 2022-09-11 | Underground | R16 | 2022-08-24 | 1 | 8 | 72 | 13 | 91 | 2022 | 2022 | R16
160737253881 | 163545253881 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-19 | 2021-10-19 | 2021-10-26 | 2022-02-08 | 2022-03-08 | Underground | R16 | 2022-02-08 | 1 | 6 | 76 | 21 | 101 | 2021 | 2022 | R16
166643278021 | 164712278021 | RESIDENTIAL - SUBSEQUENT WORK | OH R16 RES NON RES OD | Residential | 2022-04-28 | 2022-04-28 | 2022-05-03 | 2022-05-11 | 2022-05-25 | Overhead | R16 | 2022-05-11 | 1 | 4 | 7 | 11 | 20 | 2022 | 2022 | R16
163435265967 | 163619265967 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-01-24 | 2022-01-24 | 2022-01-24 |  | 2022-04-01 | Underground | R16 | 2022-02-17 | 1 |  | 19 | 32 | 50 | 2022 | 2022 | R16
162637253726 | 163539253726 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-19 | 2021-10-19 | 2021-10-26 | 2021-10-28 | 2021-12-02 | Underground | R16 | 2021-10-28 | 1 | 6 | 3 | 26 | 33 | 2021 | 2021 | R16
162690247200 | 163105247200 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-02 | 2021-09-02 | 2021-09-09 |  | 2022-02-02 | Underground | R16 | 2022-01-13 | 1 | 6 | 91 | 15 | 110 | 2021 | 2022 | R16
161694264922 | 161894264922 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-14 | 2022-01-14 | 2022-01-14 | 2022-02-08 | 2022-02-10 | Overhead | R16 | 2022-02-08 | 1 |  | 18 | 3 | 20 | 2022 | 2022 | R16
165682275506 | 167422275506 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-22 | 2022-03-22 | 2022-04-11 | 2023-07-19 | 2023-08-11 | Underground | R16 | 2023-07-19 | 1 | 15 | 333 | 18 | 364 | 2022 | 2023 | R16
163877255560 | 167710255560 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-05 | 2021-11-05 | 2021-11-07 | 2022-01-03 | 2022-01-04 | Overhead | R16 | 2022-01-03 | 1 | 1 | 41 | 2 | 43 | 2021 | 2022 | R16
168253275798 | 161670275798 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-02-24 | 2022-04-04 | 2022-04-15 |  | 2023-02-03 | Underground | R16 |  | 28 | 10 |  |  | 247 | 2022 | 2023 | R16
165685275894 | 162644275894 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2022-03-01 | 2022-03-01 | 2022-04-15 | 2022-12-20 | 2022-12-22 | Underground | R16 | 2022-12-20 | 1 | 34 | 178 | 3 | 213 | 2022 | 2022 | R16
161560267462 | 162339267462 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-18 | 2022-01-18 | 2022-02-03 | 2022-03-18 | 2022-03-21 | Underground | R16 | 2022-03-18 | 1 | 13 | 32 | 2 | 45 | 2022 | 2022 | R16
166091284203 | 163715284203 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-29 | 2022-06-29 | 2022-06-29 | 2022-12-05 | 2022-12-20 | Overhead | R16 | 2022-12-05 | 1 |  | 114 | 12 | 125 | 2022 | 2022 | R16
160847277120 | 163968277120 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-25 | 2022-04-25 | 2022-04-25 | 2022-08-24 | 2022-10-21 | Overhead | R16 | 2022-08-24 | 1 |  | 88 | 43 | 130 | 2022 | 2022 | R16
160052268910 | 162647268910 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-19 | 2022-01-19 | 2022-02-14 | 2022-04-20 | 2022-04-21 | Overhead | R16 | 2022-04-20 | 1 | 19 | 48 | 2 | 67 | 2022 | 2022 | R16
166098281939 | 169084281939 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-08 | 2022-06-08 | 2022-06-08 |  | 2022-07-20 | Overhead | R16 | 2022-07-18 | 1 |  | 29 | 3 | 31 | 2022 | 2022 | R16
166269271162 | 169322271162 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-15 | 2022-02-15 | 2022-03-02 | 2022-08-24 | 2022-10-21 | Underground | R16 | 2022-08-24 | 1 | 12 | 126 | 43 | 179 | 2022 | 2022 | R16
162409284778 | 163216284778 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-28 | 2022-07-07 | 2022-07-07 | 2022-08-18 | 2022-10-21 | Overhead | R16 | 2022-08-18 | 8 |  | 31 | 47 | 84 | 2022 | 2022 | R16
166063249971 | 168892249971 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-29 | 2021-09-29 | 2021-09-29 | 2021-10-07 | 2021-11-18 | Overhead | R16 | 2021-10-07 | 1 |  | 7 | 31 | 37 | 2021 | 2021 | R16
162430279522 | 163014279522 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-11 | 2022-05-16 | 2022-05-16 | 2022-07-06 | 2022-08-16 | Overhead | R16 | 2022-07-06 | 4 |  | 38 | 30 | 70 | 2022 | 2022 | R16
160914254403 | 165757254403 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-28 | 2021-10-28 | 2021-10-29 | 2022-02-09 | 2022-03-09 | Overhead | R16 | 2022-02-09 | 1 | 2 | 74 | 21 | 95 | 2021 | 2022 | R16
169198283333 | 164242283333 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-16 | 2022-05-16 | 2022-06-22 | 2022-11-14 | 2022-11-15 | Underground | R16 | 2022-11-14 | 1 | 28 | 104 | 2 | 132 | 2022 | 2022 | R16
166052268523 | 166101268523 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2021-12-15 | 2021-12-15 | 2022-02-10 | 2022-02-28 | 2022-03-21 | Overhead | R16 | 2022-02-28 | 1 | 42 | 13 | 16 | 69 | 2021 | 2022 | R16
163219243297 | 168249243297 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-12 | 2021-08-13 | 2021-08-13 |  | 2021-10-11 | Overhead | R16 | 2021-09-13 | 2 |  | 22 | 21 | 43 | 2021 | 2021 | R16
167915255623 | 163959255623 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-20 | 2021-10-20 | 2021-11-08 | 2022-05-22 | 2022-06-06 | Underground | R16 | 2022-05-22 | 1 | 14 | 140 | 11 | 164 | 2021 | 2022 | R16
167112283843 | 163073283843 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-27 | 2022-06-27 | 2022-06-27 |  | 2023-01-05 | Overhead | R16 | 2022-09-09 | 1 |  | 55 | 85 | 139 | 2022 | 2023 | R16
164607276964 | 166819276964 | NON-RESIDENTIAL - WAREHOUSE | OH R16 RES NON RES OS | Commercial | 2021-12-20 | 2021-12-20 | 2022-04-25 |  | 2022-05-06 | Overhead | R16 | 2022-05-06 | 1 | 91 | 10 |  | 100 | 2021 | 2022 | R16
160302277364 | 160729277364 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-22 | 2022-02-22 | 2022-04-27 |  | 2022-09-30 | Underground | R16 | 2022-09-01 | 1 | 47 | 92 | 22 | 159 | 2022 | 2022 | R16
163659245784 | 165696245784 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-03 | 2021-08-03 | 2021-08-30 |  | 2021-11-02 | Underground | R16 | 2021-10-13 | 1 | 20 | 33 | 15 | 66 | 2021 | 2021 | R16
161880311034 | 160590311034 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2022-02-18 | 2023-01-06 | 2023-03-01 | 2023-07-25 | 2023-08-16 | Underground | R16 | 2023-07-25 | 231 | 39 | 105 | 17 | 389 | 2022 | 2023 | R16
163721248956 | 163848248956 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-09-07 | 2021-09-22 | 2021-09-22 |  | 2023-02-03 | Underground | R16 | 2022-12-02 | 12 |  | 313 | 46 | 369 | 2021 | 2023 | R16
163178255286 | 167618255286 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-05 | 2021-11-05 | 2021-11-05 |  | 2022-04-21 | Overhead | R16 | 2022-03-22 | 1 |  | 98 | 23 | 120 | 2021 | 2022 | R16
166013269007 | 167599269007 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-08 | 2022-02-15 | 2022-02-15 |  | 2022-12-06 | Overhead | R16 | 2022-10-27 | 6 |  | 183 | 29 | 216 | 2022 | 2022 | R16
162350277188 | 164296277188 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2022-04-26 | 2022-04-27 | 2022-04-27 |  | 2022-06-20 | Overhead | R16 | 2022-05-25 | 2 |  | 21 | 19 | 40 | 2022 | 2022 | R16
160999269202 | 169470269202 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-15 | 2022-02-15 | 2022-02-15 |  | 2022-03-25 | Overhead | R16 | 2022-03-09 | 1 |  | 17 | 13 | 29 | 2022 | 2022 | R16
166342258890 | 162250258890 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-10-13 | 2021-10-18 | 2021-11-29 | 2022-02-24 | 2022-09-26 | Underground | R16 | 2022-02-24 | 4 | 31 | 64 | 153 | 249 | 2021 | 2022 | R16
161106253021 | 163841253021 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-20 | 2021-10-20 | 2021-10-20 |  | 2021-12-28 | Underground | R16 | 2021-11-24 | 1 |  | 26 | 25 | 50 | 2021 | 2021 | R16
169085267475 | 161971267475 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-11-23 | 2021-11-24 | 2022-02-04 |  | 2022-08-11 | Underground | R16 |  | 2 | 53 |  |  | 188 | 2021 | 2022 | R16
162829262603 | 163889262603 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-07 | 2021-12-27 | 2021-12-27 |  | 2022-03-07 | Overhead | R16 | 2022-02-09 | 15 |  | 33 | 19 | 65 | 2021 | 2022 | R16
169560275835 | 162771275835 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-03-01 | 2022-03-01 | 2022-04-13 |  | 2022-12-14 | Underground | R16 | 2022-11-17 | 1 | 32 | 157 | 20 | 207 | 2022 | 2022 | R16
163661263734 | 160026263734 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-06 | 2022-01-06 | 2022-01-06 |  | 2023-01-05 | Overhead | R16 | 2022-10-13 | 1 |  | 201 | 61 | 261 | 2022 | 2023 | R16
163287272562 | 165575272562 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-14 | 2022-03-14 | 2022-03-14 |  | 2022-05-05 | Overhead | R16 | 2022-04-13 | 1 |  | 23 | 17 | 39 | 2022 | 2022 | R16
160427299397 | 160389299397 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG R16 RESD AND NON RESD UD | Commercial | 2022-04-06 | 2022-04-06 | 2022-11-04 | 2023-07-21 | 2023-08-24 | Underground | R16 | 2023-07-21 | 1 | 153 | 186 | 25 | 362 | 2022 | 2023 | R16
161085278960 | 162748278960 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2022-05-10 | 2022-05-10 | 2022-05-10 | 2022-06-27 | 2022-08-25 | Underground | R16 | 2022-06-27 | 1 |  | 35 | 44 | 78 | 2022 | 2022 | R16
168574275997 | 160955275997 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-08 | 2022-04-08 | 2022-04-15 | 2022-06-06 | 2022-08-03 | Overhead | R16 | 2022-06-06 | 1 | 6 | 37 | 43 | 84 | 2022 | 2022 | R16
163291269326 | 164007269326 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-25 | 2022-01-25 | 2022-02-16 | 2022-02-28 | 2022-04-20 | Underground | R16 | 2022-02-28 | 1 | 17 | 9 | 38 | 62 | 2022 | 2022 | R16
160307280877 | 162581280877 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2022-05-09 | 2022-05-09 | 2022-05-26 | 2023-02-10 | 2023-02-16 | Underground | R16 | 2023-02-10 | 1 | 14 | 187 | 5 | 204 | 2022 | 2023 | R16
169722280766 | 161477280766 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-12 | 2022-01-12 | 2022-05-25 | 2022-10-09 | 2022-10-25 | Underground | R16 | 2022-10-09 | 1 | 96 | 98 | 12 | 205 | 2022 | 2022 | R16
165403247817 | 165564247817 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-14 | 2021-09-14 | 2021-09-14 |  | 2021-12-01 | Overhead | R16 | 2021-11-01 | 1 |  | 35 | 23 | 57 | 2021 | 2021 | R16
165930259001 | 168143259001 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-08 | 2021-11-29 | 2021-11-29 | 2022-02-15 | 2022-03-15 | Overhead | R16 | 2022-02-15 | 16 |  | 57 | 21 | 92 | 2021 | 2022 | R16
162986278314 | 166039278314 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-16 | 2022-03-16 | 2022-05-06 |  | 2022-06-20 | Overhead | R16 | 2022-05-25 | 1 | 38 | 14 | 19 | 69 | 2022 | 2022 | R16
164613249423 | 164685249423 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-10 | 2021-09-10 | 2021-09-24 |  | 2023-02-17 | Underground | R16 | 2022-12-15 | 1 | 11 | 320 | 47 | 376 | 2021 | 2023 | R16
168131297607 | 161888297607 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-14 | 2022-07-08 | 2022-10-19 | 2023-05-24 | 2023-05-30 | Underground | R16 | 2023-05-24 | 126 | 74 | 156 | 5 | 358 | 2022 | 2023 | R16
162658280410 | 166216280410 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2022-05-24 | 2022-05-24 | 2022-05-24 |  | 2023-08-14 | Overhead | R16 |  | 1 |  |  |  | 320 | 2022 | 2023 | R16
161341265381 | 162701265381 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-19 | 2022-01-19 | 2022-01-19 |  | 2022-07-03 | Overhead | R16 | 2022-06-20 | 1 |  | 109 | 10 | 118 | 2022 | 2022 | R16
163065255657 | 168494255657 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-09 | 2021-11-09 | 2021-11-09 | 2021-11-15 | 2022-03-08 | Overhead | R16 | 2021-11-15 | 1 |  | 5 | 82 | 86 | 2021 | 2022 | R16
169783284185 | 160066284185 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2022-06-13 | 2022-06-13 | 2022-06-29 | 2023-02-09 | 2023-02-10 | Underground | R16 | 2023-02-09 | 1 | 13 | 162 | 2 | 175 | 2022 | 2023 | R16
163635279635 | 162500279635 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-09 | 2022-05-09 | 2022-05-17 |  | 2022-12-11 | Underground | R16 | 2022-12-08 | 1 | 7 | 148 | 2 | 155 | 2022 | 2022 | R16
166128297987 | 162156297987 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-06-22 | 2022-06-22 | 2022-10-24 |  | 2023-08-28 | Underground | R16 |  | 1 | 89 |  |  | 309 | 2022 | 2023 | R16
167737268397 | 167872268397 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2021-12-28 | 2022-02-02 | 2022-02-09 |  | 2022-08-03 | Overhead | R16 |  | 27 | 6 |  |  | 157 | 2021 | 2022 | R16
163857277249 | 160943277249 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OD | Residential | 2022-04-08 | 2022-04-08 | 2022-04-27 | 2022-08-04 | 2022-09-13 | Overhead | R16 | 2022-08-04 | 1 | 14 | 72 | 29 | 113 | 2022 | 2022 | R16
168361266848 | 162080266848 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-16 | 2022-01-16 | 2022-01-31 |  | 2022-07-18 | Overhead | R16 | 2022-07-14 | 0 | 11 | 119 | 3 | 131 | 2022 | 2022 | R16
169615276083 | 162572276083 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-16 | 2022-04-16 | 2022-04-16 |  | 2022-06-10 | Overhead | R16 | 2022-05-18 | 0 |  | 23 | 18 | 40 | 2022 | 2022 | R16
165462261413 | 166321261413 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2021-12-20 | 2021-12-20 | Underground | R16 | 2021-12-20 | 1 |  | 3 |  | 3 | 2021 | 2021 | R16
160673251781 | 161655251781 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-12 | 2021-10-12 | 2021-10-12 | 2021-12-01 | 2021-12-14 | Overhead | R16 | 2021-12-01 | 1 |  | 37 | 10 | 46 | 2021 | 2021 | R16
163971253845 | 164835253845 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2021-10-25 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-12-02 | Overhead | R16 | 2021-10-27 | 1 | 2 | 2 | 27 | 29 | 2021 | 2021 | R16
169003260303 | 168582260303 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-09 | 2021-12-07 | 2021-12-07 |  | 2022-10-21 | Overhead | R16 | 2022-08-19 | 21 |  | 184 | 46 | 249 | 2021 | 2022 | R16
168545260581 | 164789260581 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-09 | 2021-12-09 | 2021-12-09 | 2022-11-21 | 2023-02-11 | Overhead | R16 | 2022-11-21 | 1 |  | 248 | 60 | 307 | 2021 | 2023 | R16
167564284103 | 168053284103 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-03 | 2022-06-03 | 2022-06-28 | 2022-10-04 | 2022-10-05 | Underground | R16 | 2022-10-04 | 1 | 18 | 71 | 2 | 89 | 2022 | 2022 | R16
166933275569 | 160969275569 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-08 | 2022-04-11 | 2022-04-11 | 2022-05-05 | 2022-08-03 | Underground | R16 | 2022-05-05 | 2 |  | 19 | 65 | 84 | 2022 | 2022 | R16
168049290480 | 169701290480 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-06-10 | 2022-06-10 | 2022-08-26 |  | 2023-02-08 | Underground | R16 | 2023-01-20 | 1 | 56 | 106 | 14 | 174 | 2022 | 2023 | R16
166425250291 | 169383250291 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-01 | 2021-10-01 | 2021-10-01 | 2021-11-10 | 2021-12-29 | Overhead | R16 | 2021-11-10 | 1 |  | 29 | 36 | 64 | 2021 | 2021 | R16
160803312444 | 160582312444 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-05-05 | 2022-08-02 | 2023-03-14 | 2023-06-16 | 2023-09-05 | Overhead | R16 | 2023-06-16 | 64 | 161 | 69 | 58 | 349 | 2022 | 2023 | R16
165930288246 | 163328288246 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-21 | 2022-04-21 | 2022-08-08 | 2022-10-03 | 2022-10-06 | Underground | R16 | 2022-10-03 | 1 | 78 | 41 | 4 | 121 | 2022 | 2022 | R16
164542293984 | 165843293984 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-23 | 2022-06-13 | 2022-09-16 | 2022-10-13 | 2022-10-13 | Overhead | R16 | 2022-10-13 | 16 | 70 | 20 |  | 104 | 2022 | 2022 | R16
165860278029 | 165940278029 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-29 | 2022-05-03 | 2022-05-03 |  | 2022-06-20 | Overhead | R16 |  | 3 |  |  |  | 37 | 2022 | 2022 | R16
163268269283 | 167547269283 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-08 | 2022-02-08 | 2022-02-16 | 2022-04-12 | 2022-06-12 | Underground | R16 | 2022-04-12 | 1 | 7 | 40 | 44 | 89 | 2022 | 2022 | R16
160721300042 | 166806300042 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-18 | 2022-03-18 | 2022-11-09 | 2023-03-29 | 2023-05-18 | Underground | R16 | 2023-03-29 | 1 | 169 | 101 | 37 | 305 | 2022 | 2023 | R16
168577276041 | 162516276041 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-15 | 2022-04-15 | 2022-04-15 | 2022-05-16 | 2022-10-21 | Overhead | R16 | 2022-05-16 | 1 |  | 22 | 115 | 136 | 2022 | 2022 | R16
160878270541 | 164218270541 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-26 | 2022-01-31 | 2022-02-25 |  | 2022-08-23 | Underground | R16 | 2022-07-18 | 4 | 20 | 102 | 27 | 150 | 2022 | 2022 | R16
166024292408 | 167991292408 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-03 | 2022-06-03 | 2022-09-02 |  | 2023-03-27 | Underground | R16 | 2023-01-10 | 1 | 66 | 93 | 55 | 212 | 2022 | 2023 | R16
166093254640 | 166741254640 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-09-20 | 2021-11-01 | 2021-11-01 |  | 2023-05-30 | Underground | R16 | 2023-02-03 | 31 |  | 330 | 83 | 442 | 2021 | 2023 | R16
162203260385 | 164251260385 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-07 | 2021-12-08 | 2021-12-08 | 2022-03-17 | 2023-06-12 | Overhead | R16 | 2022-03-17 | 2 |  | 72 | 323 | 395 | 2021 | 2023 | R16
166110242872 | 167058242872 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-10 | 2021-08-10 | 2021-08-10 |  | 2021-10-27 | Overhead | R16 | 2021-09-07 | 1 |  | 21 | 37 | 57 | 2021 | 2021 | R16
168188282020 | 169578282020 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-03-31 | 2022-04-14 | 2022-06-08 | 2023-06-29 | 2023-10-26 | Underground | R16 | 2023-06-29 | 11 | 40 | 277 | 86 | 411 | 2022 | 2023 | R16
161027267159 | 166235267159 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-02-02 | 2022-02-02 | 2022-02-02 | 2022-06-27 | 2022-08-09 | Underground | R16 | 2022-06-27 | 1 |  | 104 | 32 | 135 | 2022 | 2022 | R16
169144283512 | 161251283512 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-23 | 2022-03-29 | 2022-06-23 |  | 2022-09-15 | Overhead | R16 | 2022-06-28 | 25 | 63 | 4 | 58 | 147 | 2022 | 2022 | R16
161592269159 | 169665269159 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-16 | 2022-02-16 | 2022-02-16 |  | 2022-05-12 | Overhead | R16 | 2022-04-19 | 1 |  | 45 | 18 | 62 | 2022 | 2022 | R16
160533277118 | 161357277118 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-01-12 | 2022-01-13 | 2022-04-26 |  | 2022-07-26 | Overhead | R16 |  | 2 | 74 |  |  | 140 | 2022 | 2022 | R16
164850262201 | 166137262201 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-16 | 2021-12-21 | 2021-12-21 |  | 2022-12-11 | Overhead | R16 | 2022-12-08 | 4 |  | 253 | 2 | 257 | 2021 | 2022 | R16
166305251938 | 160669251938 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-23 | 2021-08-23 | 2021-10-14 |  | 2022-06-03 | Underground | R16 | 2022-05-12 | 1 | 39 | 151 | 17 | 205 | 2021 | 2022 | R16
169728261210 | 165549261210 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-14 | 2021-12-14 | 2021-12-14 | 2022-05-16 | 2022-06-20 | Overhead | R16 | 2022-05-16 | 1 |  | 110 | 26 | 135 | 2021 | 2022 | R16
162084280709 | 161392280709 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-05 | 2022-05-25 | 2022-05-25 |  | 2022-10-26 | Overhead | R16 | 2022-08-15 | 15 |  | 59 | 53 | 125 | 2022 | 2022 | R16
163208279918 | 165073279918 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-18 | 2022-05-19 | 2022-05-19 | 2023-01-05 | 2023-01-05 | Underground | R16 | 2023-01-05 | 2 |  | 166 |  | 167 | 2022 | 2023 | R16
165943287312 | 166490287312 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-25 | 2022-05-25 | 2022-07-29 |  | 2023-01-10 | Underground | R16 | 2022-11-17 | 1 | 48 | 80 | 39 | 165 | 2022 | 2023 | R16
169681284817 | 164615284817 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2022-07-06 | 2022-07-06 | 2022-07-06 | 2023-07-19 | 2023-09-20 | Underground | R16 | 2023-07-19 | 1 |  | 271 | 46 | 316 | 2022 | 2023 | R16
166635274904 | 160232274904 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-05 | 2022-04-05 | 2022-04-05 | 2022-06-19 | 2022-07-11 | Overhead | R16 | 2022-06-19 | 1 |  | 54 | 16 | 70 | 2022 | 2022 | R16
166551265212 | 165527265212 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-14 | 2021-09-14 | 2022-01-19 |  | 2022-04-27 | Underground | R16 | 2022-03-28 | 1 | 92 | 49 | 23 | 162 | 2021 | 2022 | R16
167250265684 | 165727265684 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2021-10-28 | 2021-12-01 | 2022-01-21 |  | 2023-03-09 | Overhead | R16 |  | 25 | 38 |  |  | 356 | 2021 | 2023 | R16
162436259399 | 164794259399 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2021-10-25 | 2021-10-25 | 2021-12-02 |  | 2022-03-07 | Underground | R16 | 2022-02-09 | 1 | 29 | 50 | 19 | 96 | 2021 | 2022 | R16
166782242695 | 166654242695 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2021-08-07 | 2021-08-07 | 2021-08-10 |  | 2021-11-09 | Underground | R16 | 2021-10-01 | 0 | 2 | 39 | 28 | 67 | 2021 | 2021 | R16
166798259364 | 169445259364 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-11-12 | 2021-12-01 | 2021-12-01 |  | 2022-08-16 | Overhead | R16 | 2022-07-11 | 14 |  | 159 | 27 | 198 | 2021 | 2022 | R16
164795268383 | 168043268383 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-02-09 | 2022-02-09 | 2022-02-09 |  | 2022-08-16 | Overhead | R16 | 2022-07-12 | 1 |  | 110 | 26 | 135 | 2022 | 2022 | R16
162918294027 | 160104294027 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-06-13 | 2022-06-20 | 2022-09-16 |  | 2023-02-03 | Overhead | R16 | 2022-11-22 | 6 | 65 | 48 | 54 | 170 | 2022 | 2023 | R16
162647265252 | 161258265252 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-01-12 | 2022-01-13 | 2022-01-19 | 2023-03-02 | 2023-03-29 | Overhead | R16 | 2023-03-02 | 2 | 5 | 292 | 20 | 316 | 2022 | 2023 | R16
162245252722 | 162558252722 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-14 | 2021-10-18 | 2021-10-18 | 2021-10-27 | 2021-12-02 | Overhead | R16 | 2021-10-27 | 3 |  | 8 | 27 | 36 | 2021 | 2021 | R16
167937283374 | 163297283374 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2022-05-11 | 2022-05-24 | 2022-06-22 |  | 2023-04-01 | Underground | R16 | 2023-01-23 | 10 | 22 | 154 | 50 | 233 | 2022 | 2023 | R16
166348261187 | 165446261187 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-28 | 2021-10-28 | 2021-12-14 | 2022-01-06 | 2022-03-02 | Overhead | R16 | 2022-01-06 | 1 | 34 | 18 | 40 | 90 | 2021 | 2022 | R16
168330284015 | 162432284015 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-23 | 2022-06-28 | 2022-06-28 | 2022-08-26 | 2023-08-15 | Overhead | R16 | 2022-08-26 | 4 |  | 44 | 253 | 299 | 2022 | 2023 | R16
167886265227 | 160939265227 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-11 | 2022-01-11 | 2022-01-19 | 2022-02-23 | 2022-04-27 | Underground | R16 | 2022-02-23 | 1 | 7 | 26 | 46 | 77 | 2022 | 2022 | R16
168879286725 | 168820286725 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-25 | 2022-07-25 | 2022-07-25 | 2022-09-23 | 2022-09-26 | Overhead | R16 | 2022-09-23 | 1 |  | 45 | 2 | 46 | 2022 | 2022 | R16
167012278965 | 163117278965 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-11-14 | 2022-11-17 | Underground | R16 | 2022-11-14 | 1 |  | 134 | 4 | 137 | 2022 | 2022 | R16
165904288203 | 165042288203 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-07 | 2022-08-05 | 2022-08-08 |  | 2022-10-21 | Overhead | R16 | 2022-09-08 | 22 | 2 | 24 | 32 | 77 | 2022 | 2022 | R16
165012295825 | 160943295825 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-20 | 2021-11-20 | 2022-10-03 |  | 2022-12-22 | Underground | R16 | 2022-12-21 | 0 | 226 | 58 | 2 | 284 | 2021 | 2022 | R16
164695307462 | 166065307462 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2021-12-15 | 2021-12-15 | 2023-01-27 | 2023-07-11 | 2023-07-07 | Underground | R16 | 2023-07-11 | 1 | 293 | 118 |  | 408 | 2021 | 2023 | R16
169130256846 | 169924256846 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-16 | 2021-11-16 | 2021-11-16 | 2021-11-17 | 2022-01-20 | Overhead | R16 | 2021-11-17 | 1 |  | 2 | 47 | 48 | 2021 | 2022 | R16
160968283920 | 161928283920 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-06-22 | 2022-06-22 | 2022-06-27 |  | 2022-10-27 | Underground | R16 | 2022-10-24 | 1 | 4 | 86 | 4 | 92 | 2022 | 2022 | R16
169333287013 | 169426287013 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-27 | 2022-07-27 | 2022-07-27 | 2022-12-13 | 2023-03-17 | Overhead | R16 | 2022-12-13 | 1 |  | 100 | 69 | 168 | 2022 | 2023 | R16
167230284355 | 164271284355 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-01 | 2022-07-01 | 2022-07-01 |  | 2022-09-11 | Overhead | R16 | 2022-08-11 | 1 |  | 30 | 22 | 51 | 2022 | 2022 | R16
161705274175 | 164290274175 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-03-07 | 2022-03-07 | 2022-03-30 | 2022-11-14 | 2022-11-14 | Underground | R16 | 2022-11-14 | 1 | 18 | 164 |  | 181 | 2022 | 2022 | R16
166577286904 | 167279286904 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-18 | 2022-07-18 | 2022-07-26 | 2022-09-28 | 2023-01-05 | Underground | R16 | 2022-09-28 | 1 | 7 | 47 | 72 | 124 | 2022 | 2023 | R16
165847285198 | 162822285198 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Commercial | 2022-05-10 | 2022-05-10 | 2022-07-12 |  | 2022-08-16 | Underground | R16 |  | 1 | 46 |  |  | 71 | 2022 | 2022 | R16
167877244414 | 168763244414 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-16 | 2021-08-16 | 2021-08-20 |  | 2021-12-02 | Underground | R16 | 2021-11-22 | 1 | 5 | 67 | 9 | 79 | 2021 | 2021 | R16
164547285026 | 164334285026 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-05 | 2022-07-08 | 2022-07-08 |  | 2022-10-21 | Overhead | R16 | 2022-09-07 | 4 |  | 44 | 33 | 79 | 2022 | 2022 | R16
166096299330 | 166329299330 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-13 | 2022-07-13 | 2022-11-03 | 2023-02-08 | 2023-02-08 | Underground | R16 | 2023-02-08 | 1 | 82 | 70 |  | 151 | 2022 | 2023 | R16
166976295147 | 166880295147 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2022-05-26 | 2022-08-01 | 2022-09-28 | 2023-08-07 | 2023-09-06 | Underground | R16 | 2023-08-07 | 48 | 43 | 224 | 23 | 335 | 2022 | 2023 | R16
169373259218 | 162834259218 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-30 | 2021-12-01 | 2021-12-01 | 2022-01-25 | 2022-02-28 | Overhead | R16 | 2022-01-25 | 2 |  | 40 | 25 | 65 | 2021 | 2022 | R16
163152278740 | 162535278740 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-09 | 2022-05-09 | 2022-05-09 |  | 2022-07-25 | Overhead | R16 | 2022-06-08 | 1 |  | 23 | 34 | 56 | 2022 | 2022 | R16
163602313431 | 163700313431 | NON-RESIDENTIAL - SMALL RETAIL | UG R16 RESD AND NON RESD UD | Commercial | 2022-04-22 | 2022-04-22 | 2023-03-24 | 2023-10-16 | 2023-10-30 | Underground | R16 | 2023-10-16 | 1 | 241 | 147 | 11 | 397 | 2022 | 2023 | R16
168817275041 | 160503275041 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-06 | 2022-04-06 | 2022-04-06 |  | 2023-01-10 | Overhead | R16 | 2022-11-02 | 1 |  | 151 | 50 | 200 | 2022 | 2023 | R16
163388275038 | 166339275038 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-17 | 2022-03-17 | 2022-04-06 | 2022-05-01 | 2022-05-04 | Underground | R16 | 2022-05-01 | 1 | 15 | 18 | 3 | 35 | 2022 | 2022 | R16
166980276421 | 162822276421 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-19 | 2022-04-19 | 2022-04-19 |  | 2022-06-09 | Overhead | R16 | 2022-05-17 | 1 |  | 21 | 18 | 38 | 2022 | 2022 | R16
163457307880 | 160113307880 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-13 | 2022-06-16 | 2023-01-31 | 2023-05-19 | 2023-08-17 | Overhead | R16 | 2023-05-19 | 4 | 164 | 79 | 65 | 309 | 2022 | 2023 | R16
165487262299 | 167398262299 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2022-04-26 | 2022-05-31 | Overhead | R16 | 2022-04-26 | 1 |  | 90 | 26 | 115 | 2021 | 2022 | R16
161286287421 | 169184287421 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-26 | 2022-07-29 | 2022-07-29 | 2022-09-01 | 2022-09-20 | Overhead | R16 | 2022-09-01 | 4 |  | 25 | 14 | 41 | 2022 | 2022 | R16
162847280600 | 165824280600 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-23 | 2022-05-24 | 2022-05-24 |  | 2022-07-02 | Overhead | R16 | 2022-06-29 | 2 |  | 27 | 3 | 30 | 2022 | 2022 | R16
164211269722 | 160353269722 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-18 | 2022-02-18 | 2022-02-18 |  | 2022-06-03 | Overhead | R16 | 2022-05-12 | 1 |  | 60 | 17 | 76 | 2022 | 2022 | R16
167737268398 | 168001268398 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2021-12-28 | 2022-01-31 | 2022-02-09 |  | 2023-01-05 | Overhead | R16 |  | 25 | 8 |  |  | 268 | 2021 | 2023 | R16
168393264410 | 160977264410 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-11 | 2022-01-11 | 2022-01-11 | 2022-03-07 | 2022-04-01 | Overhead | R16 | 2022-03-07 | 1 |  | 40 | 20 | 59 | 2022 | 2022 | R16
166139271499 | 169135271499 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-14 | 2022-02-14 | 2022-03-04 | 2023-08-22 | 2023-08-23 | Underground | R16 | 2023-08-22 | 1 | 15 | 383 | 2 | 398 | 2022 | 2023 | R16
164548273757 | 167796273757 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-03-23 | 2022-03-25 | 2022-03-25 | 2023-01-04 | 2023-01-18 | Underground | R16 | 2023-01-04 | 3 |  | 204 | 11 | 216 | 2022 | 2023 | R16
167426276556 | 169868276556 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-04 | 2022-04-04 | 2022-04-21 | 2022-09-15 | 2023-01-05 | Underground | R16 | 2022-09-15 | 1 | 14 | 106 | 81 | 199 | 2022 | 2023 | R16
168922287005 | 169188287005 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-26 | 2022-07-26 | 2022-07-26 | 2022-11-14 | 2022-11-30 | Overhead | R16 | 2022-11-14 | 1 |  | 80 | 13 | 92 | 2022 | 2022 | R16
168930250775 | 163474250775 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-03 | 2021-09-03 | 2021-10-06 |  | 2022-04-04 | Underground | R16 | 2022-03-14 | 1 | 24 | 114 | 16 | 152 | 2021 | 2022 | R16
169070246700 | 163489246700 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-09-03 | 2021-09-05 | 2021-09-05 |  | 2023-03-13 | Overhead | R16 | 2022-02-18 | 1 |  | 120 | 277 | 397 | 2021 | 2023 | R16
163809284730 | 165248284730 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-20 | 2022-05-23 | 2022-07-06 | 2022-08-29 | 2022-09-01 | Underground | R16 | 2022-08-29 | 2 | 33 | 39 | 4 | 75 | 2022 | 2022 | R16
167131274294 | 167828274294 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-27 | 2021-12-27 | 2022-03-31 |  | 2022-06-03 | Underground | R16 | 2022-05-13 | 1 | 69 | 32 | 16 | 115 | 2021 | 2022 | R16
165145330913 | 167226330913 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-07 | 2022-04-13 | 2023-08-28 | 2023-11-15 | 2023-11-20 | Underground | R16 | 2023-11-15 | 48 | 359 | 58 | 4 | 466 | 2022 | 2023 | R16
162473279666 | 164507279666 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-07-27 | 2022-07-28 | Overhead | R16 | 2022-07-27 | 1 |  | 52 | 2 | 53 | 2022 | 2022 | R16
162463293080 | 160752293080 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-19 | 2021-11-23 | 2022-09-08 |  | 2023-08-21 | Underground | R16 | 2023-08-18 | 3 | 208 | 247 | 2 | 457 | 2021 | 2023 | R16
166212279320 | 163979279320 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-13 | 2022-05-13 | 2022-05-13 |  | 2022-06-30 | Overhead | R16 | 2022-06-06 | 1 |  | 17 | 19 | 35 | 2022 | 2022 | R16
164815276870 | 167012276870 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-21 | 2022-04-22 | 2022-04-22 | 2022-05-09 | 2022-06-03 | Overhead | R16 | 2022-05-09 | 25 |  | 12 | 20 | 55 | 2022 | 2022 | R16
161921289665 | 166196289665 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-13 | 2022-07-13 | 2022-08-19 | 2022-09-21 | 2022-09-22 | Underground | R16 | 2022-09-21 | 1 | 28 | 24 | 2 | 52 | 2022 | 2022 | R16
163431287767 | 163167287767 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-27 | 2022-06-27 | 2022-08-03 |  | 2023-05-17 | Underground | R16 | 2023-03-22 | 1 | 28 | 166 | 41 | 233 | 2022 | 2023 | R16
168734275002 | 160404275002 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-05 | 2022-04-05 | 2022-04-05 | 2022-04-21 | 2022-06-06 | Overhead | R16 | 2022-04-21 | 1 |  | 13 | 33 | 45 | 2022 | 2022 | R16
169988276346 | 162819276346 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-19 | 2022-04-19 | 2022-04-19 |  | 2022-07-15 | Overhead | R16 | 2022-06-09 | 1 |  | 38 | 27 | 64 | 2022 | 2022 | R16
167092250364 | 169257250364 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-01 | 2021-10-01 | 2021-10-01 | 2021-11-10 | 2021-12-29 | Overhead | R16 | 2021-11-10 | 1 |  | 29 | 36 | 64 | 2021 | 2021 | R16
169513246559 | 163423246559 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-03 | 2021-09-03 | 2021-09-03 |  | 2021-11-18 | Overhead | R16 | 2021-10-28 | 1 |  | 40 | 16 | 55 | 2021 | 2021 | R16
164672323964 | 167269323964 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-04 | 2021-11-04 | 2023-07-03 | 2023-08-08 | 2023-08-09 | Overhead | R16 | 2023-08-08 | 1 | 433 | 27 | 2 | 460 | 2021 | 2023 | R16
169553245390 | 161530245390 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-26 | 2021-08-26 | 2021-08-26 |  | 2022-09-11 | Overhead | R16 | 2022-09-07 | 1 |  | 270 | 3 | 272 | 2021 | 2022 | R16
167119268029 | 166739268029 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-05 | 2022-02-05 | 2022-02-08 | 2022-04-09 | 2022-04-18 | Overhead | R16 | 2022-04-09 | 0 | 2 | 44 | 6 | 51 | 2022 | 2022 | R16
162705260988 | 165573260988 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-13 | 2021-12-13 | 2021-12-13 | 2022-03-23 | 2022-04-08 | Overhead | R16 | 2022-03-23 | 1 |  | 73 | 13 | 85 | 2021 | 2022 | R16
166544282304 | 167908282304 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-03 | 2022-06-03 | 2022-06-10 | 2022-10-21 | 2022-11-28 | Underground | R16 | 2022-10-21 | 1 | 6 | 96 | 27 | 127 | 2022 | 2022 | R16
166457277248 | 163481277248 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-21 | 2022-04-27 | 2022-04-27 |  | 2023-09-07 | Overhead | R16 | 2023-08-28 | 5 |  | 349 | 9 | 361 | 2022 | 2023 | R16
165602284254 | 162527284254 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-09 | 2022-05-09 | 2022-07-01 |  | 2023-09-29 | Underground | R16 | 2023-06-14 | 1 | 40 | 249 | 78 | 365 | 2022 | 2023 | R16
163536264184 | 167808264184 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-27 | 2022-01-10 | 2022-01-10 |  | 2023-05-30 | Overhead | R16 | 2023-02-15 | 11 |  | 288 | 75 | 372 | 2021 | 2023 | R16
167958273976 | 163318273976 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-03 | 2022-03-03 | 2022-03-28 | 2022-06-17 | 2022-06-23 | Underground | R16 | 2022-06-17 | 1 | 18 | 60 | 5 | 81 | 2022 | 2022 | R16
164002285158 | 162271285158 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-22 | 2022-07-12 | 2022-07-12 |  | 2023-08-14 | Underground | R16 | 2023-04-27 | 15 |  | 208 | 78 | 299 | 2022 | 2023 | R16
160442275726 | 161926275726 | NON-RESIDENTIAL - SMALL RETAIL | UG R16 RESD AND NON RESD UD | Commercial | 2022-04-13 | 2022-04-13 | 2022-04-13 | 2022-12-22 | 2023-01-18 | Underground | R16 | 2022-12-22 | 1 |  | 182 | 20 | 201 | 2022 | 2023 | R16
160082274843 | 169865274843 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-04-04 | 2022-04-04 | 2022-04-04 |  | 2023-08-04 | Underground | R16 | 2023-03-30 | 1 |  | 259 | 92 | 350 | 2022 | 2023 | R16
169933281760 | 160186281760 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-05-04 | 2022-05-04 | 2022-06-06 | 2022-07-11 | 2022-07-27 | Underground | R16 | 2022-07-11 | 1 | 24 | 26 | 13 | 61 | 2022 | 2022 | R16
160985277636 | 165767277636 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-29 | 2022-04-29 | 2022-04-29 | 2022-08-11 | 2022-08-12 | Overhead | R16 | 2022-08-11 | 1 |  | 75 | 2 | 76 | 2022 | 2022 | R16
160233244538 | 160434244538 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2021-08-20 | 2021-08-20 | 2021-08-20 |  | 2021-12-14 | Overhead | R16 | 2021-12-06 | 1 |  | 77 | 7 | 83 | 2021 | 2021 | R16
165037274561 | 168908274561 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-29 | 2022-03-31 | 2022-04-01 | 2022-05-22 | 2022-05-27 | Overhead | R16 | 2022-05-22 | 3 | 2 | 36 | 5 | 44 | 2022 | 2022 | R16
160242246419 | 163446246419 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-03 | 2021-09-03 | 2021-09-03 |  | 2023-05-18 | Overhead | R16 | 2023-03-17 | 1 |  | 401 | 45 | 445 | 2021 | 2023 | R16
160286284080 | 161450284080 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-20 | 2022-06-20 | 2022-06-28 |  | 2022-12-20 | Underground | R16 |  | 1 | 7 |  |  | 132 | 2022 | 2022 | R16
169307289582 | 164029289582 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-01 | 2022-08-18 | 2022-08-18 |  | 2022-09-26 | Overhead | R16 | 2022-09-22 | 35 |  | 26 | 3 | 62 | 2022 | 2022 | R16
160544284030 | 167286284030 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-31 | 2022-06-27 | 2022-06-28 |  | 2023-03-23 | Underground | R16 | 2023-01-09 | 20 | 2 | 140 | 54 | 213 | 2022 | 2023 | R16
168591312358 | 162576312358 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-09 | 2022-05-09 | 2023-03-14 | 2023-04-26 | 2023-08-23 | Underground | R16 | 2023-04-26 | 1 | 222 | 32 | 86 | 338 | 2022 | 2023 | R16
162506260985 | 165529260985 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-13 | 2021-12-13 | 2021-12-13 |  | 2022-02-07 | Overhead | R16 | 2022-01-05 | 1 |  | 18 | 24 | 41 | 2021 | 2022 | R16
167008250018 | 168576250018 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-28 | 2021-09-30 | 2021-09-30 | 2022-01-25 | 2022-02-28 | Overhead | R16 | 2022-01-25 | 3 |  | 84 | 25 | 110 | 2021 | 2022 | R16
160061263474 | 169323263474 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-01-05 | 2022-01-05 | 2022-01-05 |  | 2022-03-08 | Overhead | R16 | 2022-02-10 | 1 |  | 27 | 19 | 45 | 2022 | 2022 | R16
160393247204 | 164410247204 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-09 | 2021-09-09 | 2021-09-09 |  | 2022-03-03 | Overhead | R16 | 2022-02-02 | 1 |  | 105 | 22 | 126 | 2021 | 2022 | R16
161190256562 | 167739256562 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-11-05 | 2021-11-14 | 2021-11-14 |  | 2023-09-29 | Overhead | R16 | 2023-09-22 | 6 |  | 485 | 6 | 496 | 2021 | 2023 | R16
162379248882 | 167117248882 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-21 | 2021-09-21 | 2021-09-21 |  | 2022-01-12 | Underground | R16 | 2021-12-02 | 1 |  | 53 | 30 | 82 | 2021 | 2022 | R16
165991250329 | 169518250329 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-02 | 2021-10-04 | 2021-10-04 | 2022-03-03 | 2022-05-04 | Overhead | R16 | 2022-03-03 | 1 |  | 109 | 45 | 153 | 2021 | 2022 | R16
166252287742 | 166342287742 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-13 | 2022-08-03 | 2022-08-03 |  | 2022-09-22 | Overhead | R16 | 2022-09-13 | 16 |  | 30 | 8 | 52 | 2022 | 2022 | R16
166794259041 | 162475259041 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-29 | 2021-11-29 | 2021-11-29 | 2022-02-14 | 2022-03-14 | Overhead | R16 | 2022-02-14 | 1 |  | 56 | 21 | 76 | 2021 | 2022 | R16
160246277862 | 161785277862 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-14 | 2022-01-14 | 2022-05-02 |  | 2022-08-30 | Underground | R16 | 2022-08-29 | 1 | 77 | 86 | 2 | 163 | 2022 | 2022 | R16
162201261554 | 166315261554 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2022-02-11 | 2023-03-09 | Overhead | R16 | 2022-02-11 | 1 |  | 42 | 280 | 321 | 2021 | 2023 | R16
168337267280 | 169645267280 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-15 | 2021-11-15 | 2022-02-02 | 2023-07-13 | 2023-07-25 | Underground | R16 | 2023-07-13 | 1 | 58 | 377 | 9 | 442 | 2021 | 2023 | R16
163451252894 | 163801252894 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-20 | 2021-10-20 | 2021-10-20 |  | 2021-11-18 | Overhead | R16 | 2021-10-28 | 1 |  | 7 | 16 | 22 | 2021 | 2021 | R16
169456267414 | 162817267414 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-01-19 | 2022-01-24 | 2022-02-03 | 2022-04-20 | 2022-04-25 | Underground | R16 | 2022-04-20 | 4 | 9 | 55 | 4 | 69 | 2022 | 2022 | R16
163388270822 | 160412270822 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-18 | 2022-02-18 | 2022-02-28 |  | 2022-08-03 | Underground | R16 | 2022-06-24 | 1 | 7 | 85 | 29 | 119 | 2022 | 2022 | R16
164503290507 | 161870290507 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-04-12 | 2022-08-29 | 2022-08-29 |  | 2023-08-30 | Underground | R16 |  | 100 |  |  |  | 362 | 2022 | 2023 | R16
165270318576 | 161924318576 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2022-04-13 | 2022-06-13 | 2023-05-09 | 2023-05-22 | 2023-06-27 | Underground | R16 | 2023-05-22 | 44 | 237 | 10 | 27 | 315 | 2022 | 2023 | R16
165299281789 | 167524281789 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-01 | 2022-06-06 | 2022-06-06 | 2022-08-03 | 2022-10-21 | Overhead | R16 | 2022-08-03 | 4 |  | 43 | 58 | 103 | 2022 | 2022 | R16
161109249175 | 167727249175 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-23 | 2021-09-23 | 2021-09-23 |  | 2021-11-17 | Overhead | R16 |  | 1 |  |  |  | 40 | 2021 | 2021 | R16
164751279633 | 164653279633 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-10-27 | 2023-01-10 | Overhead | R16 | 2022-10-27 | 1 |  | 118 | 54 | 171 | 2022 | 2023 | R16
167627274915 | 167493274915 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-22 | 2022-03-22 | 2022-04-05 |  | 2022-05-03 | Underground | R16 | 2022-05-03 | 1 | 11 | 21 |  | 31 | 2022 | 2022 | R16
167186269518 | 160420269518 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-18 |  | 2022-02-18 | 2022-05-04 | 2022-06-06 | Overhead | R16 | 2022-05-04 |  |  | 54 | 24 | 77 | 2022 | 2022 | R16
166202269220 | 169374269220 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-02-15 | 2022-02-15 | 2022-02-15 | 2022-11-15 | 2022-11-16 | Overhead | R16 | 2022-11-15 | 1 |  | 196 | 2 | 197 | 2022 | 2022 | R16
160133270264 | 165327270264 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-28 | 2022-02-23 | 2022-02-23 |  | 2022-08-10 | Overhead | R16 | 2022-07-06 | 19 |  | 96 | 26 | 139 | 2022 | 2022 | R16
167021263802 | 167874263802 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-08 | 2021-11-08 | 2022-01-06 |  | 2022-04-27 | Underground | R16 | 2022-04-01 | 1 | 44 | 62 | 19 | 123 | 2021 | 2022 | R16
162843290477 | 163451290477 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-28 | 2022-07-08 | 2022-08-29 |  | 2022-12-13 | Underground | R16 | 2022-12-09 | 9 | 37 | 75 | 3 | 121 | 2022 | 2022 | R16
161575267441 | 166529267441 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-03 | 2022-02-03 | 2022-02-03 |  | 2022-03-25 | Overhead | R16 | 2022-03-14 | 1 |  | 28 | 10 | 37 | 2022 | 2022 | R16
163053284712 | 163247284712 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-02 | 2021-12-02 | 2022-07-06 | 2023-08-02 | 2023-09-29 | Underground | R16 | 2023-08-02 | 1 | 155 | 281 | 43 | 477 | 2021 | 2023 | R16
166827250583 | 169845250583 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-05 | 2021-10-05 | 2021-10-05 | 2021-10-08 | 2021-12-02 | Overhead | R16 | 2021-10-08 | 1 |  | 4 | 40 | 43 | 2021 | 2021 | R16
160321286792 | 163355286792 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-06-28 | 2022-06-28 | 2022-07-25 | 2023-04-03 | 2023-04-10 | Underground | R16 | 2023-04-03 | 1 | 20 | 181 | 6 | 205 | 2022 | 2023 | R16
160871264563 | 163246264563 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-12-02 | 2021-12-02 | 2022-01-12 | 2023-09-11 | 2023-09-22 | Underground | R16 | 2023-09-11 | 1 | 30 | 434 | 10 | 472 | 2021 | 2023 | R16
166203288656 | 166108288656 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-02-02 | 2022-07-12 | 2022-08-12 | 2022-11-22 | 2022-12-14 | Underground | R16 | 2022-11-22 | 115 | 24 | 73 | 17 | 226 | 2022 | 2022 | R16
164678262015 | 166982262015 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-20 | 2021-12-20 | 2021-12-20 |  | 2022-03-11 | Overhead | R16 | 2022-02-15 | 1 |  | 42 | 19 | 60 | 2021 | 2022 | R16
168682303699 | 168754303699 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-03-29 | 2022-04-01 | 2022-12-21 |  | 2023-11-30 | Underground | R16 | 2023-10-26 | 4 | 189 | 222 | 26 | 438 | 2022 | 2023 | R16
168416274304 | 167937274304 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-24 | 2022-03-30 | 2022-03-30 |  | 2023-06-22 | Overhead | R16 | 2023-05-25 | 5 |  | 302 | 21 | 326 | 2022 | 2023 | R16
163448265163 | 162229265163 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-18 | 2022-01-18 | 2022-01-18 |  | 2022-08-24 | Overhead | R16 | 2022-08-10 | 1 |  | 147 | 11 | 157 | 2022 | 2022 | R16
161105270146 | 163030270146 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-15 | 2021-11-30 | 2022-02-22 | 2022-02-23 | 2022-04-19 | Overhead | R16 | 2022-02-23 | 33 | 61 | 2 | 40 | 133 | 2021 | 2022 | R16
169362275830 | 162007275830 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-13 | 2022-04-13 | 2022-04-13 |  | 2022-06-06 | Underground | R16 | 2022-05-11 | 1 |  | 21 | 19 | 39 | 2022 | 2022 | R16
168260275897 | 162483275897 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-04-15 | 2022-04-15 | 2022-04-15 | 2023-10-22 | 2023-10-25 | Underground | R16 | 2023-10-22 | 1 |  | 396 | 3 | 399 | 2022 | 2023 | R16
168296290861 | 167222290861 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-18 | 2022-07-21 | 2022-08-31 |  | 2023-01-10 | Underground | R16 | 2022-11-18 | 4 | 30 | 58 | 38 | 127 | 2022 | 2023 | R16
162207261193 | 165862261193 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-14 | 2021-12-14 | 2021-12-14 | 2021-12-16 | 2022-02-28 | Overhead | R16 | 2021-12-16 | 1 |  | 3 | 53 | 55 | 2021 | 2022 | R16
163047268579 | 168649268579 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-11 | 2022-02-11 | 2022-02-11 | 2022-08-24 | 2022-10-21 | Overhead | R16 | 2022-08-24 | 1 |  | 139 | 43 | 181 | 2022 | 2022 | R16
169619281374 | 164210281374 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-04-26 | 2022-04-26 | 2022-06-03 |  | 2022-09-20 | Underground | R16 | 2022-08-05 | 1 | 29 | 46 | 33 | 106 | 2022 | 2022 | R16
161516290310 | 163044290310 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2022-06-27 | 2022-06-27 | 2022-08-26 |  | 2023-01-10 | Underground | R16 |  | 1 | 45 |  |  | 142 | 2022 | 2023 | R16
164759264629 | 161455264629 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-13 | 2022-01-13 | 2022-01-13 | 2022-03-11 | 2022-04-04 | Overhead | R16 | 2022-03-11 | 1 |  | 42 | 17 | 58 | 2022 | 2022 | R16
160086252306 | 162324252306 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-14 | 2021-10-15 | 2021-10-15 | 2022-03-21 | 2022-04-21 | Overhead | R16 | 2022-03-21 | 2 |  | 112 | 24 | 136 | 2021 | 2022 | R16
160050259902 | 163604259902 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-03 | 2021-12-03 | 2021-12-03 | 2022-02-03 | 2022-03-04 | Overhead | R16 | 2022-02-03 | 1 |  | 45 | 22 | 66 | 2021 | 2022 | R16
169349250672 | 169839250672 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-05 | 2021-10-05 | 2021-10-05 | 2022-02-09 | 2022-02-10 | Overhead | R16 | 2022-02-09 | 1 |  | 92 | 2 | 93 | 2021 | 2022 | R16
160314278165 | 169458278165 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-03 | 2022-05-03 | 2022-05-03 | 2022-05-19 | 2022-05-23 | Overhead | R16 | 2022-05-19 | 1 |  | 13 | 3 | 15 | 2022 | 2022 | R16
162734262312 | 167512262312 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-22 | 2021-12-22 | 2021-12-22 |  | 2022-03-01 | Overhead | R16 | 2022-01-27 | 1 |  | 27 | 24 | 50 | 2021 | 2022 | R16
165680266020 | 162648266020 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-01-19 | 2022-01-19 | 2022-01-24 | 2022-06-15 | 2022-06-16 | Overhead | R16 | 2022-06-15 | 1 | 4 | 103 | 2 | 107 | 2022 | 2022 | R16
161738267262 | 164400267262 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-26 | 2022-02-01 | 2022-02-02 |  | 2022-10-01 | Overhead | R16 | 2022-09-20 | 5 | 2 | 165 | 9 | 178 | 2022 | 2022 | R16
166008263387 | 168999263387 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-03 | 2022-01-03 | 2022-01-04 | 2023-03-06 | 2023-03-07 | Overhead | R16 | 2023-03-06 | 1 | 2 | 305 | 2 | 307 | 2022 | 2023 | R16
161176256821 | 164800256821 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-25 | 2021-10-25 | 2021-11-16 | 2022-01-10 | 2022-02-07 | Underground | R16 | 2022-01-10 | 1 | 17 | 40 | 21 | 76 | 2021 | 2022 | R16
163170259191 | 162674259191 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-30 | 2021-11-30 | 2021-11-30 | 2022-03-22 | 2022-03-23 | Overhead | R16 | 2022-03-22 | 1 |  | 81 | 2 | 82 | 2021 | 2022 | R16
164687274276 | 167373274276 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-22 | 2022-03-22 | 2022-03-31 | 2022-07-20 | 2022-09-20 | Underground | R16 | 2022-07-20 | 1 | 8 | 80 | 45 | 131 | 2022 | 2022 | R16
161555266390 | 163125266390 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-20 | 2022-01-27 | 2022-01-27 |  | 2022-04-25 | Overhead | R16 | 2022-04-04 | 6 |  | 48 | 16 | 68 | 2022 | 2022 | R16
162308253715 | 165066253715 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-26 | 2021-10-26 | 2021-10-26 | 2022-03-29 | 2022-03-30 | Overhead | R16 | 2022-03-29 | 1 |  | 111 | 2 | 112 | 2021 | 2022 | R16
163034280359 | 166073280359 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-24 | 2022-05-24 | 2022-05-24 |  | 2022-09-28 | Overhead | R16 | 2022-09-27 | 1 |  | 91 | 2 | 92 | 2022 | 2022 | R16
164717254268 | 165334254268 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2021-10-27 | 2021-10-27 | 2021-10-29 | 2021-11-28 | 2023-10-04 | Overhead | R16 | 2021-11-28 | 1 | 3 | 21 | 483 | 506 | 2021 | 2023 | R16
163404261299 | 163976261299 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-07 | 2021-12-15 | 2021-12-15 | 2022-01-27 | 2022-03-02 | Overhead | R16 | 2022-01-27 | 7 |  | 32 | 25 | 62 | 2021 | 2022 | R16
169124253586 | 164706253586 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-25 | 2021-10-25 | 2021-10-25 | 2021-12-03 | 2021-12-06 | Overhead | R16 | 2021-12-03 | 1 |  | 30 | 2 | 31 | 2021 | 2021 | R16
168228294665 | 169021294665 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-25 | 2022-07-25 | 2022-09-23 |  | 2023-01-24 | Underground | R16 | 2023-01-13 | 1 | 45 | 81 | 8 | 132 | 2022 | 2023 | R16
161304278521 | 162342278521 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-05-06 | 2022-05-06 | 2022-05-06 | 2022-05-16 | 2022-05-17 | Overhead | R16 | 2022-05-16 | 1 |  | 7 | 2 | 8 | 2022 | 2022 | R16
163021283616 | 162733283616 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2023-03-07 | 2023-03-08 | Overhead | R16 | 2023-03-07 | 1 |  | 183 | 2 | 184 | 2022 | 2023 | R16
164060253716 | 162318253716 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-10-13 | 2021-10-26 | 2021-10-26 | 2022-07-07 | 2023-08-02 | Overhead | R16 | 2022-07-07 | 10 |  | 183 | 280 | 471 | 2021 | 2023 | R16
162752280735 | 166633280735 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-26 | 2022-05-26 | 2022-05-26 |  | 2022-07-03 | Overhead | R16 | 2022-06-30 | 1 |  | 26 | 2 | 27 | 2022 | 2022 | R16
162347290405 | 162720290405 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2022-01-19 | 2022-02-11 | 2022-08-26 | 2023-05-03 | 2023-06-09 | Underground | R16 | 2023-05-03 | 18 | 141 | 179 | 28 | 363 | 2022 | 2023 | R16
167733285964 | 164053285964 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-01 | 2022-07-01 | 2022-07-18 | 2022-08-12 | 2022-08-17 | Underground | R16 | 2022-08-12 | 1 | 12 | 20 | 4 | 34 | 2022 | 2022 | R16
168999254777 | 166062254777 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-29 | 2021-10-29 | 2021-11-03 | 2023-05-11 | 2023-08-31 | Overhead | R16 | 2023-05-11 | 1 | 4 | 397 | 81 | 480 | 2021 | 2023 | R16
162876273005 | 166515273005 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-17 | 2022-03-17 | 2022-03-17 | 2022-04-25 | 2022-06-03 | Overhead | R16 | 2022-04-25 | 1 |  | 28 | 30 | 57 | 2022 | 2022 | R16
162696271976 | 164851271976 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-09 | 2022-03-09 | 2022-03-09 |  | 2022-04-26 | Overhead | R16 | 2022-04-07 | 1 |  | 22 | 14 | 35 | 2022 | 2022 | R16
160523257049 | 168750257049 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2021-11-10 | 2021-11-10 | 2021-11-17 |  | 2022-06-09 | Underground | R16 |  | 1 | 6 |  |  | 152 | 2021 | 2022 | R16
165802265951 | 161638265951 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-12 | 2021-10-12 | 2022-01-25 |  | 2022-07-17 | Overhead | R16 | 2022-06-14 | 1 | 76 | 101 | 24 | 199 | 2021 | 2022 | R16
168877280756 | 166459280756 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-25 | 2022-05-25 | 2022-05-25 |  | 2022-07-03 | Underground | R16 | 2022-06-22 | 1 |  | 21 | 8 | 28 | 2022 | 2022 | R16
168327249582 | 168177249582 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-09-27 | 2021-09-27 | 2021-09-27 | 2021-09-29 | 2021-11-09 | Overhead | R16 | 2021-09-29 | 1 |  | 3 | 30 | 32 | 2021 | 2021 | R16
163702252168 | 161343252168 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-11 | 2021-10-14 | 2021-10-14 |  | 2022-02-10 | Overhead | R16 | 2022-01-05 | 4 |  | 60 | 27 | 89 | 2021 | 2022 | R16
169145250575 | 169847250575 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-05 | 2021-10-05 | 2021-10-05 | 2021-12-13 | 2021-12-15 | Overhead | R16 | 2021-12-13 | 1 |  | 50 | 3 | 52 | 2021 | 2021 | R16
169224317074 | 163917317074 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2022-06-30 | 2022-06-30 | 2023-04-27 |  | 2023-08-18 | Overhead | R16 |  | 1 | 216 |  |  | 297 | 2022 | 2023 | R16
160242264346 | 161030264346 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-11 | 2022-01-11 | 2022-01-11 | 2022-03-23 | 2022-04-13 | Overhead | R16 | 2022-03-23 | 1 |  | 52 | 16 | 67 | 2022 | 2022 | R16
161704272991 | 168518272991 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-11 | 2022-02-11 | 2022-03-18 |  | 2022-07-16 | Underground | R16 | 2022-07-12 | 1 | 26 | 83 | 4 | 111 | 2022 | 2022 | R16
163814270254 | 166601270254 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-03 | 2022-02-17 | 2022-02-23 | 2022-09-28 | 2023-01-05 | Overhead | R16 | 2022-09-28 | 11 | 5 | 156 | 72 | 241 | 2022 | 2023 | R16
166699274890 | 168327274890 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-10 | 2022-02-10 | 2022-04-05 |  | 2022-06-30 | Underground | R16 | 2022-06-01 | 1 | 39 | 42 | 22 | 101 | 2022 | 2022 | R16
165799254798 | 166721254798 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-02 | 2021-11-03 | 2021-11-03 | 2022-05-03 | 2022-06-06 | Overhead | R16 | 2022-05-03 | 2 |  | 130 | 25 | 155 | 2021 | 2022 | R16
164591282037 | 169390282037 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-09 | 2022-06-09 | 2022-06-09 |  | 2022-08-26 | Overhead | R16 |  | 1 |  |  |  | 57 | 2022 | 2022 | R16
165428284771 | 164743284771 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-06 | 2022-07-06 | 2022-07-07 |  | 2022-09-11 | Overhead | R16 | 2022-08-31 | 1 | 2 | 40 | 8 | 48 | 2022 | 2022 | R16
166559260114 | 164265260114 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-12-07 | 2021-12-07 | 2021-12-07 | 2022-01-21 | 2022-03-03 | Overhead | R16 | 2022-01-21 | 1 |  | 34 | 30 | 63 | 2021 | 2022 | R16
161364278991 | 165719278991 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-04-29 | 2022-04-29 | 2022-05-11 |  | 2022-06-08 | Overhead | R16 |  | 1 | 9 |  |  | 29 | 2022 | 2022 | R16
166012255947 | 168522255947 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-09 | 2021-11-09 | 2021-11-10 |  | 2022-06-06 | Overhead | R16 | 2022-05-10 | 1 | 2 | 130 | 20 | 150 | 2021 | 2022 | R16
163175256668 | 166834256668 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-20 | 2021-11-15 | 2021-11-15 |  | 2022-03-11 | Overhead | R16 | 2022-02-16 | 41 |  | 68 | 18 | 125 | 2021 | 2022 | R16
160984286354 | 168452286354 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-21 | 2022-07-21 | 2022-07-21 |  | 2022-09-29 | Overhead | R16 | 2022-08-18 | 1 |  | 21 | 31 | 51 | 2022 | 2022 | R16
166920259268 | 162609259268 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-10-14 | 2021-10-14 | 2021-11-30 | 2022-03-26 | 2022-04-28 | Underground | R16 | 2022-03-26 | 1 | 34 | 84 | 24 | 141 | 2021 | 2022 | R16
164345286946 | 169086286946 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-26 | 2022-07-26 | 2022-07-26 | 2022-08-17 | 2022-08-18 | Overhead | R16 | 2022-08-17 | 1 |  | 17 | 2 | 18 | 2022 | 2022 | R16
162341286549 | 168626286549 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-23 | 2022-07-23 | 2022-07-23 |  | 2022-09-15 | Overhead | R16 | 2022-07-29 | 0 |  | 5 | 35 | 39 | 2022 | 2022 | R16
160129265359 | 164822265359 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-09 | 2021-12-09 | 2022-01-20 |  | 2022-06-20 | Underground | R16 | 2022-05-26 | 1 | 31 | 91 | 18 | 138 | 2021 | 2022 | R16
161020284770 | 164740284770 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-06 | 2022-07-06 | 2022-07-07 |  | 2023-03-14 | Overhead | R16 | 2023-02-22 | 1 | 2 | 165 | 15 | 180 | 2022 | 2023 | R16
163746272012 | 164811272012 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-09 | 2022-03-09 | 2022-03-09 | 2022-08-09 | 2022-11-16 | Overhead | R16 | 2022-08-09 | 1 |  | 110 | 72 | 181 | 2022 | 2022 | R16
168682290409 | 165083290409 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-03-10 | 2022-03-16 | 2022-08-26 |  | 2023-10-06 | Underground | R16 |  | 5 | 118 |  |  | 412 | 2022 | 2023 | R16
162435266389 | 163787266389 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-07 | 2021-12-07 | 2022-01-27 |  | 2022-03-10 | Underground | R16 | 2022-02-14 | 1 | 38 | 13 | 19 | 68 | 2021 | 2022 | R16
164182263236 | 169091263236 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-04 | 2022-01-04 | 2022-01-04 | 2022-03-10 | 2022-03-11 | Overhead | R16 | 2022-03-10 | 1 |  | 48 | 2 | 49 | 2022 | 2022 | R16
161525251629 | 169997251629 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-05 | 2021-10-05 | 2021-10-11 | 2021-11-11 | 2021-11-15 | Overhead | R16 | 2021-11-11 | 1 | 5 | 24 | 3 | 30 | 2021 | 2021 | R16
160751268911 | 169078268911 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-14 | 2022-02-14 | 2022-02-14 | 2022-03-03 | 2022-03-25 | Overhead | R16 | 2022-03-03 | 1 |  | 14 | 17 | 30 | 2022 | 2022 | R16
169323282519 | 163112282519 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-11 | 2022-05-11 | 2022-06-14 | 2022-08-11 | 2022-08-16 | Underground | R16 | 2022-08-11 | 1 | 25 | 43 | 4 | 70 | 2022 | 2022 | R16
167111270694 | 169190270694 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-02-14 | 2022-02-14 | 2022-02-25 |  | 2022-03-28 | Overhead | R16 |  | 1 | 10 |  |  | 31 | 2022 | 2022 | R16
165867281418 | 166457281418 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-25 | 2022-05-25 | 2022-06-02 |  | 2022-10-26 | Overhead | R16 |  | 1 | 7 |  |  | 111 | 2022 | 2022 | R16
163658256187 | 167507256187 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-23 | 2021-09-23 | 2022-04-05 |  | 2022-03-25 | Underground | R16 | 2022-04-07 | 1 | 139 | 3 |  | 132 | 2021 | 2022 | R16
164273254006 | 166805254006 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-21 | 2021-09-21 | 2021-10-27 |  | 2022-01-07 | Underground | R16 | 2021-11-29 | 1 | 27 | 24 | 30 | 79 | 2021 | 2022 | R16
169617274290 | 160746274290 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-22 | 2022-02-22 | 2022-03-31 |  | 2022-11-06 | Underground | R16 | 2022-10-19 | 1 | 28 | 145 | 13 | 184 | 2022 | 2022 | R16
163997253111 | 166851253111 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-20 | 2021-10-20 | 2021-10-20 |  | 2022-02-18 | Overhead | R16 | 2022-01-20 | 23 |  | 67 | 22 | 110 | 2021 | 2022 | R16
161179282944 | 163040282944 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-11 | 2022-06-17 | 2022-06-17 | 2022-07-19 | 2022-09-15 | Overhead | R16 | 2022-07-19 | 28 |  | 23 | 43 | 92 | 2022 | 2022 | R16
162895273050 | 166657273050 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-18 | 2022-03-18 | 2022-03-18 | 2022-08-18 | 2022-10-21 | Overhead | R16 | 2022-08-18 | 1 |  | 110 | 47 | 156 | 2022 | 2022 | R16
160139271253 | 163183271253 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-03 | 2022-03-03 | 2022-03-03 |  | 2022-08-24 | Overhead | R16 | 2022-08-17 | 1 |  | 120 | 6 | 125 | 2022 | 2022 | R16
167320259665 | 162523259665 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-11-29 | 2021-11-29 | 2021-12-02 |  | 2023-03-13 | Overhead | R16 |  | 1 | 4 |  |  | 336 | 2021 | 2023 | R16
163772261933 | 166805261933 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-20 | 2021-12-20 | 2021-12-20 |  | 2022-03-10 | Overhead | R16 | 2022-03-08 | 1 |  | 57 | 3 | 59 | 2021 | 2022 | R16
163089267856 | 163529267856 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-10-19 | 2021-10-26 | 2022-02-07 | 2022-04-08 | 2022-04-28 | Underground | R16 | 2022-04-08 | 6 | 75 | 45 | 15 | 138 | 2021 | 2022 | R16
161321309307 | 165478309307 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-07-11 | 2023-02-07 | 2023-02-14 |  | 2023-09-13 | Underground | R16 |  | 152 | 6 |  |  | 308 | 2022 | 2023 | R16
162463260496 | 163910260496 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-12-06 | 2021-12-06 | 2021-12-09 | 2022-04-06 | 2022-05-12 | Overhead | R16 | 2022-04-06 | 1 | 4 | 85 | 27 | 114 | 2021 | 2022 | R16
168682297528 | 165087297528 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-03-10 | 2022-03-16 | 2022-10-19 |  | 2023-08-04 | Underground | R16 |  | 5 | 156 |  |  | 367 | 2022 | 2023 | R16
164978297447 | 166215297447 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-13 | 2022-07-13 | 2022-10-18 | 2023-04-09 | 2023-04-12 | Underground | R16 | 2023-04-09 | 1 | 70 | 124 | 3 | 196 | 2022 | 2023 | R16
168862248136 | 165854248136 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-11-02 | 2021-12-01 | Overhead | R16 | 2021-11-02 | 1 |  | 35 | 22 | 56 | 2021 | 2021 | R16
168120286274 | 162458286274 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-06-23 | 2022-06-23 | 2022-07-20 | 2023-07-24 | 2023-08-14 | Underground | R16 | 2023-07-24 | 1 | 20 | 264 | 16 | 298 | 2022 | 2023 | R16
162799259787 | 163047259787 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-12-01 | 2021-12-01 | 2021-12-03 | 2021-12-17 | 2021-12-17 | Underground | R16 | 2021-12-17 | 1 | 3 | 11 |  | 13 | 2021 | 2021 | R16
161314271943 | 164309271943 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-08 | 2022-03-08 | 2022-03-08 |  | 2022-09-29 | Overhead | R16 | 2022-09-13 | 1 |  | 136 | 13 | 148 | 2022 | 2022 | R16
167272294353 | 164793294353 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2022-05-18 | 2022-05-18 | 2022-09-21 | 2023-03-22 | 2023-04-21 | Underground | R16 | 2023-03-22 | 1 | 91 | 131 | 23 | 243 | 2022 | 2023 | R16
168971286730 | 168842286730 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-25 |  | 2022-07-25 |  | 2022-11-30 | Underground | R16 | 2022-11-18 |  |  | 85 | 9 | 93 | 2022 | 2022 | R16
162861279805 | 164944279805 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-18 | 2022-05-18 | 2022-05-18 | 2022-05-27 | 2023-06-07 | Underground | R16 | 2022-05-27 | 1 |  | 8 | 269 | 276 | 2022 | 2023 | R16
169425274361 | 164913274361 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-09 | 2022-03-30 | 2022-03-30 | 2022-05-03 | 2022-06-06 | Overhead | R16 | 2022-05-03 | 16 |  | 25 | 25 | 64 | 2022 | 2022 | R16
169958249191 | 167369249191 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-23 | 2021-09-23 | 2021-09-23 | 2021-11-29 | 2021-11-30 | Overhead | R16 | 2021-11-29 | 1 |  | 48 | 2 | 49 | 2021 | 2021 | R16
169180277287 | 163742277287 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-04 | 2022-04-11 | 2022-04-27 | 2023-01-05 | 2023-01-05 | Underground | R16 | 2023-01-05 | 27 | 13 | 182 |  | 220 | 2022 | 2023 | R16
161370288429 | 166228288429 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-13 | 2022-07-13 | 2022-08-10 | 2023-07-25 | 2023-07-26 | Underground | R16 | 2023-07-25 | 1 | 21 | 250 | 2 | 271 | 2022 | 2023 | R16
163781282946 | 164272282946 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-05-16 | 2022-06-17 | 2022-06-17 | 2023-12-04 | 2023-12-12 | Underground | R16 | 2023-12-04 | 25 |  | 382 | 7 | 412 | 2022 | 2023 | R16
161670287110 | 163801287110 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-29 | 2022-06-29 | 2022-07-27 | 2023-02-21 | 2023-02-21 | Underground | R16 | 2023-02-21 | 1 | 21 | 150 |  | 170 | 2022 | 2023 | R16
169678273900 | 165208273900 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-10 | 2022-03-25 | 2022-03-25 |  | 2023-01-05 | Overhead | R16 | 2022-10-06 | 12 |  | 140 | 66 | 216 | 2022 | 2023 | R16
169902281188 | 163111281188 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-11 | 2022-05-11 | 2022-06-01 | 2022-08-03 | 2022-08-08 | Underground | R16 | 2022-08-03 | 1 | 16 | 46 | 4 | 64 | 2022 | 2022 | R16
164431276466 | 162965276466 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-04-20 | 2022-04-20 | 2022-04-20 |  | 2022-05-04 | Overhead | R16 | 2022-04-28 | 1 |  | 7 | 5 | 11 | 2022 | 2022 | R16
169032277568 | 165793277568 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-29 | 2022-04-29 | 2022-04-29 |  | 2022-07-17 | Overhead | R16 | 2022-07-06 | 1 |  | 49 | 8 | 56 | 2022 | 2022 | R16
162652270967 | 162685270967 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-01 | 2022-03-01 | 2022-03-01 | 2022-03-28 | 2022-03-29 | Underground | R16 | 2022-03-28 | 1 |  | 20 | 2 | 21 | 2022 | 2022 | R16
166685257162 | 169792257162 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-04 | 2021-10-04 | 2021-11-17 | 2022-04-19 | 2022-04-20 | Underground | R16 | 2022-04-19 | 1 | 33 | 110 | 2 | 143 | 2021 | 2022 | R16
167530269387 | 169770269387 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-16 | 2022-02-16 | 2022-02-16 | 2022-03-22 | 2022-04-22 | Overhead | R16 | 2022-03-22 | 1 |  | 25 | 24 | 48 | 2022 | 2022 | R16
163040264068 | 160379264068 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-08 | 2022-01-08 | 2022-01-08 |  | 2022-04-21 | Overhead | R16 | 2022-03-04 | 0 |  | 40 | 35 | 74 | 2022 | 2022 | R16
166976277243 | 169747277243 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-04-01 | 2022-04-08 | 2022-04-26 |  | 2022-05-31 | Overhead | R16 |  | 6 | 13 |  |  | 43 | 2022 | 2022 | R16
161735292907 | 166752292907 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-14 | 2022-07-14 | 2022-09-07 |  | 2022-12-15 | Underground | R16 | 2022-12-07 | 1 | 40 | 66 | 7 | 111 | 2022 | 2022 | R16
160333263585 | 166372263585 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-16 | 2022-01-05 | 2022-01-05 |  | 2022-06-06 | Underground | R16 | 2022-05-10 | 15 |  | 90 | 20 | 123 | 2021 | 2022 | R16
163348278245 | 160438278245 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-04 | 2022-05-04 | 2022-05-04 | 2022-06-06 | 2022-08-02 | Overhead | R16 | 2022-06-06 | 1 |  | 24 | 42 | 65 | 2022 | 2022 | R16
165741248856 | 167218248856 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2022-08-29 | 2022-08-30 | Overhead | R16 | 2022-08-29 | 1 |  | 244 | 2 | 245 | 2021 | 2022 | R16
164206280464 | 168387280464 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-05-02 | 2022-05-03 | 2022-05-23 | 2022-08-23 | 2022-10-04 | Underground | R16 | 2022-08-23 | 2 | 15 | 67 | 31 | 112 | 2022 | 2022 | R16
164599308847 | 161781308847 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-04-12 | 2022-04-12 | 2023-02-08 | 2023-05-02 | 2023-06-07 | Overhead | R16 | 2023-05-02 | 1 | 217 | 60 | 27 | 302 | 2022 | 2023 | R16
165817279174 | 167091279174 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-21 | 2022-04-07 | 2022-05-13 | 2022-05-16 | 2023-06-08 | Overhead | R16 | 2022-05-16 | 14 | 27 | 2 | 279 | 319 | 2022 | 2023 | R16
168334259773 | 163524259773 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-03 | 2021-12-03 | 2021-12-03 | 2022-03-04 | 2022-03-25 | Overhead | R16 | 2022-03-04 | 1 |  | 66 | 16 | 81 | 2021 | 2022 | R16
168912270750 | 162338270750 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-02-28 | 2022-02-28 | 2022-02-28 |  | 2023-02-03 | Underground | R16 | 2022-11-29 | 1 |  | 197 | 49 | 245 | 2022 | 2023 | R16
160107271432 | 163319271432 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-03 | 2022-03-03 | 2022-03-04 | 2022-03-10 | 2022-04-25 | Underground | R16 | 2022-03-10 | 1 | 2 | 5 | 33 | 38 | 2022 | 2022 | R16
162263267607 | 166913267607 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-04 | 2022-02-04 | 2022-02-04 | 2022-03-04 | 2022-03-07 | Overhead | R16 | 2022-03-04 | 1 |  | 21 | 2 | 22 | 2022 | 2022 | R16
165724278344 | 168642278344 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-03-28 | 2022-03-30 | 2022-05-05 |  | 2022-06-17 | Overhead | R16 |  | 3 | 27 |  |  | 60 | 2022 | 2022 | R16
163070286163 | 164922286163 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-07 | 2022-07-07 | 2022-07-19 | 2022-09-12 | 2022-09-13 | Underground | R16 | 2022-09-12 | 1 | 9 | 40 | 2 | 49 | 2022 | 2022 | R16
169112278666 | 160455278666 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-04 | 2022-05-06 | 2022-05-09 |  | 2022-07-26 | Overhead | R16 |  | 3 | 2 |  |  | 60 | 2022 | 2022 | R16
166016275727 | 161395275727 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-11 | 2022-04-13 | 2022-04-13 |  | 2022-07-15 | Overhead | R16 | 2022-06-27 | 3 |  | 54 | 15 | 70 | 2022 | 2022 | R16
168308263921 | 169954263921 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-06 | 2022-01-06 | 2022-01-07 | 2022-02-14 | 2022-03-23 | Overhead | R16 | 2022-02-14 | 1 | 2 | 27 | 28 | 55 | 2022 | 2022 | R16
166495275503 | 161245275503 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-11 | 2022-04-11 | 2022-04-11 |  | 2022-06-30 | Overhead | R16 | 2022-06-07 | 1 |  | 42 | 18 | 59 | 2022 | 2022 | R16
167134257116 | 168923257116 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-10 | 2021-11-18 | 2021-11-18 |  | 2022-03-25 | Overhead | R16 | 2022-02-17 | 7 |  | 66 | 27 | 98 | 2021 | 2022 | R16
166890266869 | 168329266869 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-28 | 2021-12-01 | 2022-01-31 | 2022-07-26 | 2022-09-20 | Underground | R16 | 2022-07-26 | 47 | 44 | 127 | 41 | 256 | 2021 | 2022 | R16
168673283658 | 160973283658 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-06-16 | 2022-06-16 | 2022-06-24 |  | 2022-12-06 | Underground | R16 | 2022-11-28 | 1 | 7 | 112 | 7 | 124 | 2022 | 2022 | R16
160013277449 | 166515277449 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-02 | 2022-02-23 | 2022-04-28 |  | 2022-08-03 | Underground | R16 | 2022-06-21 | 16 | 47 | 39 | 32 | 131 | 2022 | 2022 | R16
163076286162 | 165584286162 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-11 | 2022-07-11 | 2022-07-19 | 2022-11-21 | 2022-11-22 | Underground | R16 | 2022-11-21 | 1 | 7 | 90 | 2 | 97 | 2022 | 2022 | R16
166908281312 | 167745281312 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-23 | 2022-03-23 | 2022-06-01 |  | 2023-03-24 | Underground | R16 | 2023-01-11 | 1 | 51 | 161 | 53 | 263 | 2022 | 2023 | R16
163567263481 | 165731263481 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-12-14 | 2021-12-14 | 2022-01-04 |  | 2022-03-04 | Underground | R16 | 2022-02-07 | 1 | 16 | 25 | 20 | 59 | 2021 | 2022 | R16
167625260202 | 163743260202 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-10-20 | 2021-10-20 | 2021-12-07 |  | 2022-02-28 | Underground | R16 |  | 1 | 35 |  |  | 94 | 2021 | 2022 | R16
161203297575 | 163848297575 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-04-25 | 2022-09-15 | 2022-10-21 | 2023-10-24 | 2023-11-30 | Overhead | R16 | 2023-10-24 | 104 | 27 | 263 | 28 | 419 | 2022 | 2023 | R16
166361275687 | 167384275687 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-22 | 2022-03-22 | 2022-04-12 | 2022-06-28 | 2022-06-29 | Underground | R16 | 2022-06-28 | 1 | 16 | 56 | 2 | 72 | 2022 | 2022 | R16
167110251869 | 168497251869 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-28 | 2021-10-12 | 2021-10-12 | 2022-11-02 | 2022-11-18 | Overhead | R16 | 2022-11-02 | 11 |  | 277 | 13 | 299 | 2021 | 2022 | R16
163439286181 | 167546286181 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-19 | 2022-07-19 | 2022-07-19 | 2022-08-25 | 2022-08-26 | Overhead | R16 | 2022-08-25 | 1 |  | 28 | 2 | 29 | 2022 | 2022 | R16
164946275119 | 165835275119 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-03-15 | 2022-03-15 | 2022-04-07 | 2022-06-07 | 2022-06-09 | Underground | R16 | 2022-06-07 | 1 | 18 | 44 | 3 | 63 | 2022 | 2022 | R16
166575250945 | 168640250945 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-28 | 2021-09-28 | 2021-10-06 | 2022-01-10 | 2022-02-07 | Underground | R16 | 2022-01-10 | 1 | 7 | 69 | 21 | 95 | 2021 | 2022 | R16
162484265361 | 162328265361 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-19 | 2022-01-19 | 2022-01-19 | 2022-08-09 | 2022-08-12 | Overhead | R16 | 2022-08-09 | 1 |  | 145 | 4 | 148 | 2022 | 2022 | R16
169717270426 | 161638270426 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-24 | 2022-02-24 | 2022-02-24 | 2022-03-03 | 2022-03-28 | Overhead | R16 | 2022-03-03 | 1 |  | 6 | 18 | 23 | 2022 | 2022 | R16
167277282482 | 164866282482 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2022-01-27 | 2022-02-02 | 2022-06-13 | 2022-06-15 | 2022-06-29 | Overhead | R16 | 2022-06-15 | 5 | 94 | 3 | 11 | 110 | 2022 | 2022 | R16
169660264541 | 168115264541 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-08 | 2021-11-08 | 2022-01-12 |  | 2022-07-25 | Underground | R16 | 2022-06-06 | 1 | 48 | 104 | 36 | 186 | 2021 | 2022 | R16
162513277565 | 166074277565 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-29 | 2022-04-29 | 2022-04-29 | 2022-06-20 | 2022-06-21 | Overhead | R16 | 2022-06-20 | 1 |  | 37 | 2 | 38 | 2022 | 2022 | R16
167738251697 | 161637251697 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-12 | 2021-10-12 | 2021-10-12 | 2021-10-26 | 2022-01-18 | Overhead | R16 | 2021-10-26 | 1 |  | 11 | 61 | 71 | 2021 | 2022 | R16
167212272197 | 165433272197 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-03-11 | 2022-03-11 | 2022-03-11 | 2022-04-12 | 2022-05-19 | Overhead | R16 | 2022-04-12 | 1 |  | 23 | 28 | 50 | 2022 | 2022 | R16
166027265117 | 162658265117 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-01-19 | 2022-01-19 | 2022-01-19 | 2022-05-16 | 2022-06-20 | Underground | R16 | 2022-05-16 | 1 |  | 84 | 26 | 109 | 2022 | 2022 | R16
164890262012 | 166807262012 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2022-07-29 | 2022-09-08 | Overhead | R16 | 2022-07-29 | 1 |  | 160 | 30 | 189 | 2021 | 2022 | R16
162893273590 | 167838273590 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2022-03-23 | 2022-03-24 | 2022-03-24 |  | 2023-02-03 | Overhead | R16 | 2022-11-30 | 2 |  | 180 | 48 | 228 | 2022 | 2023 | R16
166263288179 | 161001288179 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-04-08 | 2022-04-08 | 2023-02-28 | 2022-12-29 | 2023-02-06 | Underground | R16 | 2022-12-29 | 1 | 233 |  | 28 | 217 | 2022 | 2023 | R16
167613255899 | 168219255899 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-09 | 2021-11-10 | 2021-11-10 | 2021-12-16 | 2022-01-19 | Overhead | R16 | 2021-12-16 | 2 |  | 27 | 25 | 52 | 2021 | 2022 | R16
161031252991 | 164027252991 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-10-20 | 2021-10-20 | 2021-10-20 | 2021-10-27 | 2021-12-02 | Overhead | R16 | 2021-10-27 | 1 |  | 6 | 27 | 32 | 2021 | 2021 | R16
165118251914 | 162200251914 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-13 | 2021-10-13 | 2021-10-13 | 2021-12-13 | 2022-01-20 | Overhead | R16 | 2021-12-13 | 1 |  | 44 | 29 | 72 | 2021 | 2022 | R16
160592290561 | 166730290561 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-07-14 | 2022-08-29 | 2022-08-29 | 2023-09-07 | 2023-07-12 | Underground | R16 | 2023-09-07 | 33 |  | 269 |  | 260 | 2022 | 2023 | R16
164804272883 | 167275272883 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-07 | 2022-02-07 | 2022-03-16 |  | 2022-09-15 | Underground | R16 | 2022-07-27 | 1 | 28 | 96 | 37 | 159 | 2022 | 2022 | R16
165761284298 | 164059284298 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-01 | 2022-07-01 | 2022-07-01 | 2022-09-19 | 2022-12-04 | Overhead | R16 | 2022-09-19 | 1 |  | 57 | 55 | 111 | 2022 | 2022 | R16
163264285902 | 167709285902 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-08 | 2022-02-08 | 2022-07-18 | 2022-09-06 | 2022-09-07 | Underground | R16 | 2022-09-06 | 1 | 115 | 37 | 2 | 152 | 2022 | 2022 | R16
169645272360 | 161934272360 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-25 | 2022-03-11 | 2022-03-11 |  | 2023-07-17 | Overhead | R16 | 2023-06-06 | 11 |  | 323 | 30 | 362 | 2022 | 2023 | R16
163407289928 | 160888289928 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-04-07 | 2022-04-07 | 2022-08-22 |  | 2023-02-17 | Underground | R16 | 2022-10-14 | 1 | 98 | 40 | 91 | 227 | 2022 | 2023 | R16
168757275661 | 161408275661 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-04-12 | 2022-04-12 | 2022-04-12 | 2022-04-15 | 2022-06-10 | Overhead | R16 | 2022-04-15 | 1 |  | 4 | 41 | 44 | 2022 | 2022 | R16
160606252699 | 163636252699 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-19 | 2021-10-19 | 2021-10-19 | 2021-11-02 | 2021-12-07 | Overhead | R16 | 2021-11-02 | 1 |  | 11 | 26 | 36 | 2021 | 2021 | R16
167669276198 | 162796276198 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-03-01 | 2022-04-19 | 2022-04-19 | 2023-02-01 | 2023-02-09 | Underground | R16 | 2023-02-01 | 36 |  | 207 | 7 | 248 | 2022 | 2023 | R16
167148286388 | 169946286388 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-02-17 | 2022-07-15 | 2022-07-21 |  | 2023-06-13 | Underground | R16 |  | 107 | 5 |  |  | 344 | 2022 | 2023 | R16
161612252005 | 161471252005 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-10-11 | 2021-10-11 | 2021-10-13 | 2022-01-20 | 2022-02-22 | Underground | R16 | 2022-01-20 | 1 | 3 | 72 | 24 | 97 | 2021 | 2022 | R16
167737268551 | 168010268551 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-12-28 | 2022-02-10 | 2022-02-10 |  | 2022-04-21 | Overhead | R16 |  | 33 |  |  |  | 83 | 2021 | 2022 | R16
160570276983 | 163804276983 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-04-25 | 2022-04-25 | 2022-04-25 | 2022-12-08 | 2022-12-12 | Underground | R16 | 2022-12-08 | 1 |  | 164 | 3 | 166 | 2022 | 2022 | R16
160523253922 | 164768253922 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2021-10-25 | 2021-10-26 | 2021-10-26 |  | 2022-06-21 | Underground | R16 |  | 2 |  |  |  | 172 | 2021 | 2022 | R16
167153284294 | 164051284294 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-01 | 2022-07-01 | 2022-07-01 |  | 2022-08-26 | Overhead | R16 | 2022-08-25 | 1 |  | 40 | 2 | 41 | 2022 | 2022 | R16
166935274508 | 169298274508 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2022-03-31 | 2022-03-31 | 2022-03-31 | 2023-11-06 | 2023-09-28 | Underground | R16 | 2023-11-06 | 1 |  | 418 |  | 391 | 2022 | 2023 | R16
166729319226 | 166771319226 | NON-RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Commercial | 2021-09-20 | 2021-09-20 | 2023-05-15 | 2023-08-23 | 2023-11-07 | Underground | R16 | 2023-08-23 | 1 | 431 | 73 | 55 | 557 | 2021 | 2023 | R16
169520282536 | 163671282536 | INDUSTRIAL | R16 RESD AND NON RESD US | Commercial | 2022-04-22 | 2022-05-10 | 2022-06-14 | 2022-12-05 | 2022-12-19 | Underground | R16 | 2022-12-05 | 13 | 26 | 125 | 11 | 172 | 2022 | 2022 | R16
165763265464 | 161417265464 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-13 | 2022-01-20 | 2022-01-20 |  | 2022-02-11 | Overhead | R16 | 2022-02-10 | 6 |  | 16 | 2 | 22 | 2022 | 2022 | R16
168186290334 | 169133290334 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-02-14 | 2022-05-18 | 2022-08-26 | 2022-09-20 | 2022-10-03 | Underground | R16 | 2022-09-20 | 68 | 73 | 18 | 10 | 166 | 2022 | 2022 | R16
169778258954 | 162559258954 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-11-29 | 2021-11-29 | 2021-11-29 | 2022-03-15 | 2022-04-01 | Overhead | R16 | 2022-03-15 | 1 |  | 77 | 14 | 90 | 2021 | 2022 | R16
164480282540 | 160037282540 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-13 | 2022-06-13 | 2022-06-13 | 2022-07-15 | 2022-07-18 | Overhead | R16 | 2022-07-15 | 1 |  | 25 | 2 | 26 | 2022 | 2022 | R16
167756298192 | 165806298192 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Commercial | 2022-03-15 | 2022-03-15 | 2022-10-25 | 2023-07-25 | 2023-08-18 | Underground | R16 | 2023-07-25 | 1 | 161 | 196 | 19 | 374 | 2022 | 2023 | R16
160438263184 | 168806263184 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-03 | 2022-01-03 | 2022-01-03 | 2022-02-18 | 2022-03-25 | Overhead | R16 | 2022-02-18 | 1 |  | 35 | 26 | 60 | 2022 | 2022 | R16
160523274775 | 160109274775 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2022-04-05 | 2022-04-05 | 2022-04-05 |  | 2022-10-26 | Underground | R16 |  | 1 |  |  |  | 147 | 2022 | 2022 | R16
162262263840 | 167502263840 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-22 | 2022-01-06 | 2022-01-06 | 2022-01-11 | 2022-03-25 | Overhead | R16 | 2022-01-11 | 12 |  | 4 | 54 | 68 | 2021 | 2022 | R16
163966284303 | 163754284303 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2023-01-17 | 2023-01-18 | Overhead | R16 | 2023-01-17 | 1 |  | 144 | 2 | 145 | 2022 | 2023 | R16
160730278631 | 162621278631 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-09 | 2022-05-09 | 2022-05-09 | 2022-06-29 | 2022-08-11 | Overhead | R16 | 2022-06-29 | 1 |  | 38 | 32 | 69 | 2022 | 2022 | R16
160010282586 | 161853282586 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2022-01-14 | 2022-01-14 | 2022-06-13 | 2023-07-06 | 2023-07-25 | Underground | R16 | 2023-07-06 | 1 | 107 | 279 | 14 | 398 | 2022 | 2023 | R16
163916263681 | 169760263681 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-14 | 2022-04-01 | Overhead | R16 | 2022-01-14 | 1 |  | 8 | 56 | 63 | 2022 | 2022 | R16
165012269703 | 160048269703 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-02-18 | 2022-02-18 | 2022-02-18 | 2022-02-28 | 2022-03-23 | Overhead | R16 | 2022-02-28 | 1 |  | 7 | 18 | 24 | 2022 | 2022 | R16
162696279673 | 164787279673 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-07-18 | 2022-07-19 | Overhead | R16 | 2022-07-18 | 1 |  | 45 | 2 | 46 | 2022 | 2022 | R16
166055249070 | 167345249070 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-22 | 2021-09-22 | 2021-09-22 | 2022-01-07 | 2022-02-07 | Overhead | R16 | 2022-01-07 | 1 |  | 78 | 22 | 99 | 2021 | 2022 | R16
169510282243 | 169175282243 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2022-06-08 | 2022-06-09 | 2022-06-10 | 2022-06-13 | 2022-07-05 | Overhead | R16 | 2022-06-13 | 2 | 2 | 2 | 17 | 20 | 2022 | 2022 | R16
160021266923 | 164534266923 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-01-26 | 2022-01-26 | 2022-01-31 |  | 2023-08-14 | Overhead | R16 | 2023-04-27 | 1 | 4 | 324 | 78 | 404 | 2022 | 2023 | R16
160725265305 | 169152265305 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-11-11 | 2021-11-11 | 2022-01-19 | 2022-02-15 | 2022-04-02 | Underground | R16 | 2022-02-15 | 1 | 50 | 20 | 34 | 102 | 2021 | 2022 | R16
160513260429 | 164630260429 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-08 | 2021-12-08 | 2021-12-08 | 2022-07-26 | 2022-07-27 | Overhead | R16 | 2022-07-26 | 1 |  | 165 | 2 | 166 | 2021 | 2022 | R16
160146254524 | 166180254524 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-30 | 2021-10-30 | 2021-10-30 |  | 2022-04-12 | Overhead | R16 | 2022-03-28 | 0 |  | 106 | 12 | 117 | 2021 | 2022 | R16
169415270136 | 161300270136 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-23 | 2022-02-23 | 2022-02-23 | 2022-03-17 | 2022-04-21 | Overhead | R16 | 2022-03-17 | 1 |  | 17 | 26 | 42 | 2022 | 2022 | R16
163163283523 | 160865283523 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-06-16 | 2022-06-23 | 2022-06-23 |  | 2022-10-26 | Overhead | R16 | 2022-09-14 | 6 |  | 60 | 31 | 95 | 2022 | 2022 | R16
169081278196 | 166604278196 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-03 | 2022-02-03 | 2022-05-04 |  | 2022-10-21 | Underground | R16 | 2022-08-29 | 1 | 65 | 84 | 40 | 187 | 2022 | 2022 | R16
161186261303 | 165905261303 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-14 | 2021-12-14 | 2021-12-14 | 2023-07-19 | 2023-07-26 | Overhead | R16 | 2023-07-19 | 1 |  | 417 | 6 | 422 | 2021 | 2023 | R16
166324286935 | 169097286935 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-26 | 2022-07-26 | 2022-07-26 |  | 2023-02-14 | Overhead | R16 | 2023-02-13 | 1 |  | 145 | 2 | 146 | 2022 | 2023 | R16
161459253923 | 165071253923 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-10-26 | 2021-10-26 | 2021-10-26 |  | 2022-03-08 | Overhead | R16 | 2022-02-10 | 1 |  | 78 | 19 | 96 | 2021 | 2022 | R16
166898262246 | 167281262246 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2022-02-01 | 2022-03-03 | Overhead | R16 | 2022-02-01 | 1 |  | 30 | 23 | 52 | 2021 | 2022 | R16
167962260614 | 164848260614 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-12-10 | 2021-12-10 | 2021-12-10 | 2022-09-26 | 2023-01-05 | Underground | R16 | 2022-09-26 | 1 |  | 207 | 74 | 280 | 2021 | 2023 | R16
169443263808 | 160144263808 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-01-06 | 2022-01-06 | 2022-01-06 |  | 2022-03-04 | Overhead | R16 | 2022-02-08 | 1 |  | 24 | 19 | 42 | 2022 | 2022 | R16
163575266317 | 166596266317 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-12-17 | 2022-01-27 | 2022-01-27 |  | 2023-01-05 | Overhead | R16 | 2022-10-18 | 30 |  | 189 | 58 | 275 | 2021 | 2023 | R16
168686275013 | 160717275013 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-02-22 | 2022-04-06 | 2022-04-06 | 2022-06-06 | 2022-08-03 | Overhead | R16 | 2022-06-06 | 32 |  | 44 | 43 | 117 | 2022 | 2022 | R16
162620269303 | 168024269303 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-02-09 | 2022-02-09 | 2022-02-16 |  | 2022-03-25 | Underground | R16 | 2022-03-21 | 1 | 6 | 24 | 5 | 33 | 2022 | 2022 | R16
164407282457 | 165971282457 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-05-23 | 2022-05-23 | 2022-06-14 |  | 2022-10-21 | Underground | R16 | 2022-08-16 | 1 | 17 | 46 | 49 | 110 | 2022 | 2022 | R16
160282260057 | 163951260057 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-12-06 | 2021-12-07 | 2021-12-07 | 2023-07-17 | 2023-09-19 | Overhead | R16 | 2023-07-17 | 2 |  | 420 | 47 | 467 | 2021 | 2023 | R16
163728297385 | 166372297385 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2022-07-13 | 2022-08-31 | 2022-10-18 | 2023-05-24 | 2023-06-28 | Underground | R16 | 2023-05-24 | 36 | 35 | 157 | 26 | 251 | 2022 | 2023 | R16
167737300191 | 169951300191 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-10-27 | 2022-10-27 | 2022-11-10 |  | 2023-05-04 | Overhead | R16 |  | 1 | 11 |  |  | 136 | 2022 | 2023 | R16
162003263249 | 169410263249 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2021-10-01 | 2021-10-01 | 2022-01-03 | 2022-01-27 | 2022-01-28 | Underground | R16 | 2022-01-27 | 1 | 67 | 19 | 2 | 86 | 2021 | 2022 | R16
168342334480 | 161618334480 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-18 | 2023-07-18 | 2023-10-03 | 2023-12-18 | 2023-12-26 | Overhead | R16 | 2023-12-18 | 1 | 56 | 55 | 7 | 116 | 2023 | 2023 | R16
160577309844 | 160093309844 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-07-28 | 2023-02-21 | 2023-02-21 |  | 2023-06-13 | Overhead | R16 | 2023-02-24 | 149 |  | 4 | 78 | 229 | 2022 | 2023 | R16
162759327730 | 165736327730 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-08 | 2023-08-08 | 2023-08-08 | 2023-08-15 | 2023-09-25 | Overhead | R16 | 2023-08-15 | 1 |  | 6 | 30 | 35 | 2023 | 2023 | R16
163363290699 | 167165290699 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-30 | 2022-08-30 | 2022-08-30 |  | 2022-12-04 | Overhead | R16 | 2022-10-10 | 1 |  | 30 | 40 | 69 | 2022 | 2022 | R16
162607295901 | 164409295901 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-17 | 2022-08-17 | 2022-10-04 | 2022-11-14 | 2022-11-28 | Underground | R16 | 2022-11-14 | 1 | 35 | 30 | 11 | 74 | 2022 | 2022 | R16
169211338350 | 162575338350 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-10-31 | 2023-11-02 | 2023-11-02 | 2023-11-14 | 2023-11-27 | Overhead | R16 | 2023-11-14 | 3 |  | 9 | 10 | 20 | 2023 | 2023 | R16
166939294623 | 162942294623 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-22 | 2022-09-22 | 2022-09-22 | 2022-10-12 | 2022-10-13 | Overhead | R16 | 2022-10-12 | 1 |  | 15 | 2 | 16 | 2022 | 2022 | R16
167307290224 | 165890290224 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-24 | 2022-08-24 | 2022-08-24 |  | 2022-10-23 | Overhead | R16 | 2022-10-05 | 1 |  | 31 | 13 | 43 | 2022 | 2022 | R16
164218287327 | 160339287327 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-07-29 | 2022-07-29 | 2022-07-29 |  | 2023-08-11 | Underground | R16 | 2023-03-15 | 1 |  | 164 | 108 | 271 | 2022 | 2023 | R16
169626298349 | 169803298349 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-27 | 2022-10-27 | 2022-10-27 | 2022-12-31 | 2023-03-31 | Overhead | R16 | 2022-12-31 | 1 |  | 47 | 65 | 112 | 2022 | 2023 | R16
165235304222 | 167739304222 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-10-17 | 2022-10-17 | 2023-01-30 | 2022-12-27 | 2023-07-07 | Overhead | R16 | 2022-12-27 | 1 | 76 |  | 139 | 190 | 2022 | 2023 | R16
161733326277 | 162881326277 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-25 | 2023-07-25 | 2023-07-25 | 2023-11-13 | 2023-12-01 | Underground | R16 | 2023-11-13 | 1 |  | 80 | 15 | 94 | 2023 | 2023 | R16
162816294370 | 162671294370 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-20 | 2022-09-21 | 2022-09-21 | 2023-02-14 | 2023-02-15 | Overhead | R16 | 2023-02-14 | 2 |  | 105 | 2 | 107 | 2022 | 2023 | R16
166819304396 | 166258304396 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-25 | 2022-08-25 | 2023-01-30 | 2022-12-30 | 2023-03-31 | Underground | R16 | 2022-12-30 | 1 | 113 |  | 66 | 157 | 2022 | 2023 | R16
163688299412 | 169137299412 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-24 | 2022-10-26 | 2022-11-04 |  | 2023-04-12 | Underground | R16 | 2023-01-13 | 3 | 8 | 51 | 64 | 123 | 2022 | 2023 | R16
165780292762 | 169604292762 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-06 | 2022-09-06 | 2022-09-06 | 2022-11-02 | 2023-07-25 | Overhead | R16 | 2022-11-02 | 1 |  | 42 | 190 | 231 | 2022 | 2023 | R16
164132297401 | 167707297401 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-17 | 2022-10-17 | 2022-10-17 | 2023-06-14 | 2023-06-15 | Overhead | R16 | 2023-06-14 | 1 |  | 173 | 2 | 174 | 2022 | 2023 | R16
163935288239 | 162489288239 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-09 | 2022-08-09 | 2022-08-09 |  | 2023-06-07 | Underground | R16 |  | 1 |  |  |  | 217 | 2022 | 2023 | R16
167727330568 | 169708330568 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2022-09-07 | 2022-09-26 | 2023-08-24 |  | 2023-11-17 | Underground | R16 | 2023-10-30 | 14 | 239 | 48 | 15 | 313 | 2022 | 2023 | R16
169137296089 | 165484296089 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-05 | 2022-10-05 | 2022-10-05 | 2022-10-18 | 2023-05-18 | Overhead | R16 | 2022-10-18 | 1 |  | 10 | 153 | 162 | 2022 | 2023 | R16
167127298322 | 162615298322 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-20 | 2022-09-20 | 2022-10-26 |  | 2023-02-03 | Underground | R16 | 2022-12-02 | 1 | 27 | 28 | 46 | 99 | 2022 | 2023 | R16
165937289347 | 164353289347 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-17 | 2022-08-17 | 2022-08-17 | 2023-05-03 | 2023-06-12 | Overhead | R16 | 2023-05-03 | 1 |  | 186 | 29 | 214 | 2022 | 2023 | R16
163705289444 | 160069289444 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-28 | 2022-07-28 | 2022-08-18 | 2022-09-26 | 2022-09-27 | Underground | R16 | 2022-09-26 | 1 | 16 | 28 | 2 | 44 | 2022 | 2022 | R16
169532295300 | 161329295300 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-14 | 2022-09-28 | 2022-09-28 | 2022-12-07 | 2023-03-01 | Overhead | R16 | 2022-12-07 | 11 |  | 51 | 61 | 121 | 2022 | 2023 | R16
166120299267 | 166824299267 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-12 | 2022-10-12 | 2022-11-03 | 2022-11-29 | 2022-12-31 | Underground | R16 | 2022-11-29 | 1 | 17 | 19 | 24 | 58 | 2022 | 2022 | R16
164938332050 | 162583332050 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2023-10-31 | 2023-12-07 | Overhead | R16 | 2023-10-31 | 1 |  | 38 | 28 | 65 | 2023 | 2023 | R16
163150333663 | 163599333663 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | R16 RESD AND NON RESD US | Commercial | 2023-09-13 | 2023-09-13 | 2023-09-25 | 2023-10-17 | 2023-10-24 | Underground | R16 | 2023-10-17 | 1 | 9 | 17 | 6 | 30 | 2023 | 2023 | R16
162763297496 | 164999297496 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-04 | 2022-10-04 | 2022-10-18 |  | 2023-02-28 | Overhead | R16 | 2023-01-03 | 1 | 11 | 56 | 41 | 106 | 2022 | 2023 | R16
167500301199 | 169452301199 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-25 | 2022-10-25 | 2022-11-21 | 2023-03-23 | 2023-04-08 | Underground | R16 | 2023-03-23 | 1 | 20 | 89 | 12 | 119 | 2022 | 2023 | R16
163267333958 | 160988333958 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-08-30 | 2023-08-30 | 2023-09-29 |  | 2023-10-25 | Underground | R16 | 2023-10-02 | 1 | 23 | 2 | 18 | 41 | 2023 | 2023 | R16
168489292370 | 167868292370 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-01 | 2022-09-02 | 2022-09-02 | 2022-09-28 | 2022-09-29 | Overhead | R16 | 2022-09-28 | 2 |  | 19 | 2 | 21 | 2022 | 2022 | R16
164221313415 | 160461313415 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-07-29 | 2022-07-29 | 2023-03-23 | 2023-04-25 | 2023-04-27 | Underground | R16 | 2023-04-25 | 1 | 170 | 24 | 3 | 195 | 2022 | 2023 | R16
169666301047 | 163983301047 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-17 | 2022-11-17 | 2022-11-17 |  | 2022-12-22 | Overhead | R16 | 2022-12-19 | 1 |  | 23 | 4 | 26 | 2022 | 2022 | R16
169035294465 | 160124294465 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-07-28 | 2022-08-01 | 2022-09-21 | 2022-11-13 | 2022-11-16 | Underground | R16 | 2022-11-13 | 3 | 38 | 38 | 3 | 80 | 2022 | 2022 | R16
168347313313 | 169994313313 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-27 | 2022-10-27 | 2023-03-23 | 2023-04-18 | 2023-07-12 | Underground | R16 | 2023-04-18 | 1 | 106 | 19 | 62 | 185 | 2022 | 2023 | R16
160650335647 | 166503335647 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-29 | 2023-10-13 | 2023-10-13 | 2023-10-13 | 2023-10-26 | Overhead | R16 | 2023-10-13 | 11 |  |  | 10 | 20 | 2023 | 2023 | R16
165915304028 | 165322304028 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-29 | 2022-11-29 | 2022-12-27 | 2023-04-07 | 2023-04-10 | Underground | R16 | 2023-04-07 | 1 | 21 | 74 | 2 | 95 | 2022 | 2023 | R16
169793304251 | 163865304251 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-17 | 2022-12-15 | 2023-01-30 | 2022-12-28 | 2023-04-27 | Underground | R16 | 2022-12-28 | 21 | 33 |  | 87 | 116 | 2022 | 2023 | R16
165028293771 | 161216293771 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-26 | 2022-10-25 | Underground | R16 | 2022-09-26 | 2 | 2 | 8 | 22 | 31 | 2022 | 2022 | R16
165384301263 | 164285301263 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-11-21 | 2022-11-21 | 2022-11-21 |  | 2023-03-01 | Overhead | R16 | 2022-12-15 | 1 |  | 19 | 55 | 73 | 2022 | 2023 | R16
167172288319 | 162608288319 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-09 | 2022-08-09 | 2022-08-09 | 2022-09-27 | 2022-09-28 | Overhead | R16 | 2022-09-27 | 1 |  | 36 | 2 | 37 | 2022 | 2022 | R16
168286335930 | 169415335930 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-10-31 | 2023-11-01 | Underground | R16 | 2023-10-31 | 1 |  | 11 | 2 | 12 | 2023 | 2023 | R16
165239288718 | 162984288718 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-11 | 2022-08-12 | 2022-08-12 |  | 2023-05-30 | Overhead | R16 | 2022-10-20 | 2 |  | 50 | 159 | 209 | 2022 | 2023 | R16
160965305826 | 165153305826 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-29 | 2023-01-13 | 2023-01-25 | 2023-03-24 | 2023-07-26 | Underground | R16 | 2023-03-24 | 34 | 9 | 43 | 89 | 172 | 2022 | 2023 | R16
167689292956 | 169558292956 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-06 | 2022-09-06 | 2022-09-08 | 2022-11-21 | 2022-12-01 | Underground | R16 | 2022-11-21 | 1 | 3 | 53 | 9 | 63 | 2022 | 2022 | R16
164459300526 | 167285300526 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-13 | 2022-10-13 | 2022-11-14 | 2022-11-14 | 2023-02-17 | Overhead | R16 | 2022-11-14 | 1 | 23 |  | 70 | 92 | 2022 | 2023 | R16
162767296113 | 164921296113 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-03 | 2022-10-05 | 2022-10-05 |  | 2023-03-31 | Overhead | R16 | 2023-01-18 | 3 |  | 76 | 53 | 130 | 2022 | 2023 | R16
164666290854 | 167546290854 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-31 | 2022-08-31 | 2022-08-31 |  | 2022-10-23 | Overhead | R16 | 2022-10-11 | 1 |  | 30 | 9 | 38 | 2022 | 2022 | R16
166163306484 | 167480306484 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-31 | 2022-08-31 | 2023-01-30 | 2023-06-13 | 2023-06-16 | Underground | R16 | 2023-06-13 | 1 | 109 | 97 | 4 | 208 | 2022 | 2023 | R16
166525301011 | 160512301011 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-09 | 2022-09-09 | 2022-11-18 | 2022-12-08 | 2023-02-11 | Underground | R16 | 2022-12-08 | 1 | 51 | 15 | 47 | 111 | 2022 | 2023 | R16
160425287599 | 160969287599 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-02 | 2022-08-02 | 2022-08-02 | 2022-10-18 | 2022-12-07 | Overhead | R16 | 2022-10-18 | 1 |  | 56 | 37 | 92 | 2022 | 2022 | R16
168154301780 | 169760301780 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-26 | 2022-10-26 | 2022-11-29 |  | 2023-05-18 | Underground | R16 | 2023-03-29 | 1 | 25 | 87 | 37 | 147 | 2022 | 2023 | R16
161405334127 | 166449334127 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2023-09-29 | 2023-09-29 | 2023-09-29 | 2023-10-05 | 2023-11-09 | Overhead | R16 | 2023-10-05 | 1 |  | 5 | 26 | 30 | 2023 | 2023 | R16
165198297389 | 167837297389 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-18 | 2022-10-18 | 2022-10-18 |  | 2023-06-26 | Overhead | R16 | 2023-05-19 | 1 |  | 154 | 27 | 180 | 2022 | 2023 | R16
168012288293 | 161962288293 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-08-05 | 2022-08-05 | 2022-08-08 |  | 2023-07-28 | Overhead | R16 | 2023-04-05 | 1 | 2 | 173 | 83 | 256 | 2022 | 2023 | R16
168018331716 | 161832331716 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2023-09-05 | 2023-09-05 | 2023-09-05 | 2023-11-20 | 2023-11-21 | Underground | R16 | 2023-11-20 | 1 |  | 55 | 2 | 56 | 2023 | 2023 | R16
161852327960 | 166191327960 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-10 | 2023-08-10 | 2023-08-10 | 2023-11-16 | 2023-11-21 | Overhead | R16 | 2023-11-16 | 1 |  | 71 | 4 | 74 | 2023 | 2023 | R16
169686325946 | 162412325946 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-22 | 2023-07-22 | 2023-07-22 | 2023-08-07 | 2023-09-01 | Overhead | R16 | 2023-08-07 | 0 |  | 11 | 20 | 30 | 2023 | 2023 | R16
162844295389 | 164509295389 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2023-02-21 | 2023-03-31 | Overhead | R16 | 2023-02-21 | 1 |  | 103 | 29 | 131 | 2022 | 2023 | R16
162833327256 | 165080327256 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-08-04 | 2023-08-04 | 2023-08-04 | 2023-08-28 | 2023-09-08 | Overhead | R16 | 2023-08-28 | 1 |  | 17 | 10 | 26 | 2023 | 2023 | R16
161699296242 | 165800296242 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-10-06 | 2022-10-06 | 2022-10-06 |  | 2023-03-01 | Overhead | R16 | 2022-12-15 | 1 |  | 51 | 55 | 105 | 2022 | 2023 | R16
166109338644 | 163834338644 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-11-02 | 2023-11-06 | 2023-11-06 | 2023-11-16 | 2023-12-14 | Overhead | R16 | 2023-11-16 | 3 |  | 9 | 21 | 31 | 2023 | 2023 | R16
163210289584 | 164820289584 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-18 | 2022-08-18 | 2022-08-18 | 2022-11-04 | 2022-12-19 | Overhead | R16 | 2022-11-04 | 1 |  | 57 | 32 | 88 | 2022 | 2022 | R16
169551294896 | 160869294896 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-12 | 2022-09-14 | 2022-09-27 | 2022-10-27 | 2022-11-01 | Underground | R16 | 2022-10-27 | 3 | 10 | 23 | 4 | 37 | 2022 | 2022 | R16
163150332475 | 161717332475 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2023-09-05 | 2023-09-05 | 2023-09-13 | 2023-10-10 | 2023-10-24 | Underground | R16 | 2023-10-10 | 1 | 7 | 20 | 11 | 36 | 2023 | 2023 | R16
167242292445 | 164493292445 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-17 | 2022-09-02 | 2022-09-02 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 13 |  | 90 |  | 102 | 2022 | 2023 | R16
169167298318 | 161679298318 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-09-15 | 2022-09-19 | 2022-10-27 |  | 2023-08-14 | Underground | R16 | 2023-04-17 | 3 | 29 | 123 | 86 | 238 | 2022 | 2023 | R16
161331302036 | 165920302036 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-02 | 2022-12-02 | 2022-12-02 | 2023-07-18 | 2023-07-19 | Overhead | R16 | 2023-07-18 | 1 |  | 163 | 2 | 164 | 2022 | 2023 | R16
169598295371 | 163284295371 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-23 | 2022-09-29 | 2022-09-29 |  | 2023-01-10 | Overhead | R16 | 2022-11-04 | 5 |  | 27 | 48 | 78 | 2022 | 2023 | R16
165456327955 | 165687327955 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-08-08 | 2023-08-08 | 2023-08-10 | 2023-08-10 | 2023-08-14 | Overhead | R16 | 2023-08-10 | 1 | 3 |  | 3 | 5 | 2023 | 2023 | R16
164106305163 | 166831305163 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-07 | 2023-01-06 | 2023-01-30 | 2023-01-06 | 2023-06-16 | Overhead | R16 | 2023-01-06 | 23 | 17 |  | 116 | 138 | 2022 | 2023 | R16
169597306171 | 162551306171 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-09 |  | 2023-01-25 | 2023-01-31 | 2023-02-08 | Overhead | R16 | 2023-01-31 |  |  | 5 | 7 | 132 | 2022 | 2023 | R16
169412328629 | 163272328629 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-27 | 2023-07-27 | 2023-08-17 | 2023-09-12 | 2023-10-31 | Underground | R16 | 2023-09-12 | 1 | 16 | 19 | 36 | 69 | 2023 | 2023 | R16
164413294621 | 164700294621 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-18 | 2022-08-18 | 2022-09-22 | 2023-06-14 | 2023-06-15 | Underground | R16 | 2023-06-14 | 1 | 26 | 190 | 2 | 216 | 2022 | 2023 | R16
164992287147 | 169654287147 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-07-27 | 2022-07-27 | 2022-07-27 | 2022-12-28 | 2023-03-17 | Overhead | R16 | 2022-12-28 | 1 |  | 111 | 58 | 168 | 2022 | 2023 | R16
169373302485 | 160947302485 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-02 | 2022-11-02 | 2022-12-06 |  | 2023-05-18 | Underground | R16 | 2023-04-07 | 1 | 25 | 89 | 30 | 142 | 2022 | 2023 | R16
164331333557 | 165320333557 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-09-22 | 2023-09-22 | 2023-09-25 | 2023-11-26 | 2023-11-29 | Underground | R16 | 2023-11-26 | 1 | 2 | 45 | 3 | 49 | 2023 | 2023 | R16
163435297663 | 166488297663 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-11 | 2022-10-20 | 2022-10-20 |  | 2023-03-02 | Overhead | R16 | 2022-12-19 | 8 |  | 43 | 54 | 103 | 2022 | 2023 | R16
162150330017 | 165338330017 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-07 | 2023-08-20 | 2023-08-20 | 2023-08-29 | 2023-10-04 | Overhead | R16 | 2023-08-29 | 10 |  | 7 | 27 | 43 | 2023 | 2023 | R16
166332307810 | 165807307810 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-02 | 2023-01-31 | 2023-01-31 |  | 2023-10-25 | Overhead | R16 | 2023-10-24 | 43 |  | 191 | 2 | 234 | 2022 | 2023 | R16
160557301665 | 167949301665 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-10-18 | 2022-10-18 | 2022-11-28 | 2023-03-08 | 2023-03-09 | Underground | R16 | 2023-03-08 | 1 | 30 | 73 | 2 | 103 | 2022 | 2023 | R16
161696289113 | 163789289113 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-15 | 2022-08-15 | 2022-08-15 |  | 2022-12-04 | Overhead | R16 | 2022-10-19 | 1 |  | 48 | 33 | 80 | 2022 | 2022 | R16
164378297414 | 166742297414 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-10-11 |  | 2022-10-11 | 2023-01-18 | 2023-02-08 | Underground | R16 | 2023-01-18 |  |  | 72 | 16 | 87 | 2022 | 2023 | R16
161781327326 | 164355327326 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-02 | 2023-08-04 | 2023-08-04 | 2023-09-18 | 2023-09-19 | Overhead | R16 | 2023-09-18 | 3 |  | 32 | 2 | 35 | 2023 | 2023 | R16
168442298334 | 169761298334 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-26 | 2022-10-26 | 2022-10-26 |  | 2023-04-04 | Overhead | R16 | 2022-12-20 | 1 |  | 40 | 76 | 115 | 2022 | 2023 | R16
167646294471 | 162893294471 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-21 | 2022-09-21 | 2022-09-21 |  | 2022-12-31 | Overhead | R16 | 2022-12-28 | 1 |  | 71 | 3 | 73 | 2022 | 2022 | R16
166853327653 | 165454327653 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-07 | 2023-08-07 | 2023-08-07 | 2023-09-13 | 2023-09-18 | Overhead | R16 | 2023-09-13 | 1 |  | 28 | 4 | 31 | 2023 | 2023 | R16
163541333612 | 165723333612 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-26 | 2023-09-26 | 2023-09-26 | 2023-10-04 | 2023-11-29 | Overhead | R16 | 2023-10-04 | 1 |  | 7 | 41 | 47 | 2023 | 2023 | R16
166508295976 | 165624295976 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-05 | 2022-10-05 | 2022-10-05 |  | 2023-04-04 | Overhead | R16 | 2023-02-02 | 1 |  | 87 | 44 | 130 | 2022 | 2023 | R16
162006303103 | 163492303103 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2022-09-26 | 2022-09-26 | 2022-12-21 | 2023-01-30 | 2023-01-31 | Underground | R16 | 2023-01-30 | 1 | 63 | 29 | 2 | 92 | 2022 | 2023 | R16
165265294655 | 163336294655 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-23 | 2022-09-23 | 2022-09-23 | 2022-10-17 | 2022-10-21 | Overhead | R16 | 2022-10-17 | 1 |  | 17 | 5 | 21 | 2022 | 2022 | R16
166158293482 | 164275293482 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-16 | 2022-09-12 | 2022-09-12 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 20 |  | 84 |  | 103 | 2022 | 2023 | R16
168283330750 | 160312330750 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-08-25 | 2023-08-26 | 2023-08-26 | 2023-09-18 | 2023-09-22 | Overhead | R16 | 2023-09-18 | 1 |  | 16 | 5 | 21 | 2023 | 2023 | R16
166106289146 | 163300289146 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-11 | 2022-08-16 | 2022-08-16 |  | 2023-02-03 | Underground | R16 | 2022-11-22 | 4 |  | 71 | 54 | 127 | 2022 | 2023 | R16
163352294770 | 163288294770 | NON-RESIDENTIAL - MISCELLANEOUS | UG ELEC MISC SVC US | Commercial | 2022-09-23 | 2022-09-23 | 2022-09-23 | 2022-10-11 | 2022-12-06 | Underground | R16 | 2022-10-11 | 1 |  | 13 | 41 | 53 | 2022 | 2022 | R16
164534327769 | 165834327769 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-09 | 2023-08-09 | 2023-08-09 | 2023-09-11 | 2023-09-27 | Overhead | R16 | 2023-09-11 | 1 |  | 24 | 13 | 36 | 2023 | 2023 | R16
169772339209 | 162482339209 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2023-10-30 | 2023-10-30 | 2023-11-09 | 2023-11-28 | 2023-11-30 | Underground | R16 | 2023-11-28 | 1 | 9 | 14 | 3 | 24 | 2023 | 2023 | R16
169307300630 | 161715300630 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-07 | 2022-11-07 | 2022-11-15 |  | 2023-05-18 | Underground | R16 | 2023-03-27 | 1 | 7 | 95 | 39 | 139 | 2022 | 2023 | R16
165947331400 | 160731331400 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Commercial | 2023-08-29 | 2023-08-29 | 2023-08-31 | 2023-09-25 | 2023-12-29 | Overhead | R16 | 2023-09-25 | 1 | 3 | 18 | 70 | 89 | 2023 | 2023 | R16
162278297704 | 166569297704 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-11 | 2022-10-11 | 2022-10-20 | 2023-06-21 | 2023-07-03 | Underground | R16 | 2023-06-21 | 1 | 8 | 175 | 9 | 190 | 2022 | 2023 | R16
161085333892 | 166175333892 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-28 | 2023-09-28 | 2023-09-28 | 2023-10-02 | 2023-11-01 | Overhead | R16 | 2023-10-02 | 1 |  | 3 | 23 | 25 | 2023 | 2023 | R16
160821299436 | 163810299436 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-09-27 | 2022-11-04 | 2022-11-04 | 2023-08-01 | 2023-07-10 | Underground | R16 | 2023-08-01 | 29 |  | 193 |  | 205 | 2022 | 2023 | R16
169507300675 | 163450300675 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-15 | 2022-11-15 | 2022-11-15 |  | 2023-02-17 | Overhead | R16 | 2023-01-04 | 1 |  | 37 | 33 | 69 | 2022 | 2023 | R16
167925298028 | 168615298028 | NON-RESIDENTIAL - LARGE OFFICE | R16 RESD AND NON RESD US | Commercial | 2022-10-20 | 2022-10-20 | 2022-10-24 | 2023-01-12 | 2023-01-30 | Underground | R16 | 2023-01-12 | 1 | 3 | 59 | 13 | 73 | 2022 | 2023 | R16
161214334550 | 167039334550 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-10-03 | 2023-10-03 | 2023-10-03 | 2023-11-14 | 2023-12-07 | Overhead | R16 | 2023-11-14 | 1 |  | 31 | 18 | 48 | 2023 | 2023 | R16
164339310864 | 168263310864 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-19 | 2022-11-01 | 2023-02-27 |  | 2023-06-26 | Underground | R16 | 2023-03-17 | 10 | 85 | 15 | 72 | 179 | 2022 | 2023 | R16
164674318297 | 165397318297 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-11-30 |  | 2023-03-01 | 2023-11-03 | 2023-11-09 | Underground | R16 | 2023-11-03 |  |  | 178 | 5 | 247 | 2022 | 2023 | R16
161634293646 | 162467293646 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-09 |  | 2022-09-14 | 2023-02-23 | 2023-03-07 | Overhead | R16 | 2023-02-23 |  |  | 117 | 9 | 151 | 2022 | 2023 | R16
163250294938 | 163639294938 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-26 | 2022-09-27 | 2022-09-27 | 2023-01-26 | 2023-02-10 | Overhead | R16 | 2023-01-26 | 2 |  | 88 | 12 | 100 | 2022 | 2023 | R16
163816301822 | 165356301822 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-29 | 2022-11-29 | 2022-11-29 |  | 2023-02-27 | Overhead | R16 | 2023-01-25 | 1 |  | 42 | 24 | 65 | 2022 | 2023 | R16
163662301214 | 164672301214 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-23 | 2022-11-23 | 2022-11-23 | 2022-12-12 | 2022-12-16 | Overhead | R16 | 2022-12-12 | 1 |  | 14 | 5 | 18 | 2022 | 2022 | R16
167589297430 | 167852297430 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2022-10-18 | 2022-10-18 | 2022-10-18 | 2022-11-16 | 2022-11-17 | Underground | R16 | 2022-11-16 | 1 |  | 22 | 2 | 23 | 2022 | 2022 | R16
164342297560 | 161154297560 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-13 | 2022-09-15 | 2022-10-19 |  | 2023-07-07 | Overhead | R16 | 2023-01-24 | 3 | 25 | 70 | 119 | 214 | 2022 | 2023 | R16
169941300716 | 161317300716 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-11-03 | 2022-11-03 | 2022-11-16 |  | 2023-08-18 | Underground | R16 | 2023-04-13 | 1 | 10 | 107 | 92 | 207 | 2022 | 2023 | R16
161309320094 | 167880320094 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2022-09-01 | 2022-09-09 | 2023-05-24 |  | 2023-10-04 | Underground | R16 |  | 7 | 184 |  |  | 285 | 2022 | 2023 | R16
163195333036 | 164559333036 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-19 | 2023-09-19 | 2023-09-19 | 2023-11-22 | 2023-12-04 | Overhead | R16 | 2023-11-22 | 1 |  | 47 | 9 | 55 | 2023 | 2023 | R16
168981290502 | 166681290502 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-26 | 2022-08-26 | 2022-08-26 |  | 2023-12-28 | Underground | R16 | 2024-01-22 | 1 |  | 367 |  | 350 | 2022 | 2023 | R16
165355294345 | 167248294345 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2022-08-30 | 2022-08-30 | 2022-09-20 |  | 2023-07-12 | Underground | R16 | 2023-06-12 | 1 | 16 | 190 | 23 | 227 | 2022 | 2023 | R16
164037299459 | 167941299459 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-18 | 2022-10-19 | 2022-11-04 |  | 2023-06-22 | Overhead | R16 |  | 2 | 13 |  |  | 178 | 2022 | 2023 | R16
163120304945 | 161571304945 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-06 | 2022-11-06 | 2023-01-30 | 2023-02-19 | 2023-04-12 | Overhead | R16 | 2023-02-19 | 0 | 61 | 15 | 38 | 113 | 2022 | 2023 | R16
167109287773 | 161336287773 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-03 | 2022-08-03 | 2022-08-03 |  | 2022-12-04 | Overhead | R16 | 2022-10-31 | 1 |  | 64 | 25 | 88 | 2022 | 2022 | R16
166248295017 | 162530295017 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-20 | 2022-09-26 | 2022-09-26 |  | 2022-12-22 | Overhead | R16 | 2022-11-16 | 5 |  | 38 | 27 | 68 | 2022 | 2022 | R16
164619299400 | 169561299400 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-26 | 2022-10-26 | 2022-11-03 |  | 2023-05-11 | Underground | R16 | 2023-02-10 | 1 | 7 | 72 | 65 | 142 | 2022 | 2023 | R16
165247272526 | 167941272526 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-03-24 | 2020-03-24 | 2022-03-14 | 2023-03-30 | 2023-07-06 | Underground | R16 | 2023-03-30 | 1 | 515 | 274 | 71 | 858 | 2020 | 2023 | R16
163203255263 | 167750255263 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-07-13 | 2020-10-23 | 2021-11-04 |  | 2022-09-07 | Underground | R16 |  | 75 | 270 |  |  | 563 | 2020 | 2022 | R16
164229193983 | 166175193983 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-08 | 2020-05-08 | 2020-06-11 | 2020-07-29 | 2020-10-02 | Underground | R16 | 2020-07-29 | 1 | 25 | 35 | 48 | 106 | 2020 | 2020 | R16
160018177578 | 160065177578 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-12-26 | 2019-12-26 | 2020-01-22 | 2020-07-22 | 2020-10-06 | Underground | R16 | 2020-07-22 | 1 | 20 | 131 | 55 | 204 | 2019 | 2020 | R16
168967184121 | 163450184121 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-02 | 2020-03-15 | 2020-03-15 | 2020-04-14 | 2020-07-01 | Overhead | R16 | 2020-04-14 | 10 |  | 22 | 57 | 88 | 2020 | 2020 | R16
167970221614 | 168913221614 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-05-26 | 2020-10-28 | 2021-02-26 | 2022-09-26 | 2022-09-30 | Underground | R16 | 2022-09-26 | 112 | 88 | 412 | 5 | 614 | 2020 | 2022 | R16
168223190175 | 168238190175 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-02-05 | 2020-02-05 | 2020-05-07 | 2023-04-21 | 2023-12-11 | Underground | R16 | 2023-04-21 | 1 | 67 | 772 | 167 | 1004 | 2020 | 2023 | R16
160801181217 | 161158181217 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-20 | 2020-02-20 | 2020-02-20 | 2020-04-27 | 2020-04-29 | Underground | R16 | 2020-04-27 | 1 |  | 48 | 3 | 50 | 2020 | 2020 | R16
169776202442 | 166909202442 | NON-RESIDENTIAL - SMALL RETAIL | R16 RESD AND NON RESD US | Commercial | 2020-07-09 | 2020-08-31 | 2020-09-01 | 2021-05-14 | 2021-09-19 | Underground | R16 | 2021-05-14 | 38 | 2 | 184 | 91 | 312 | 2020 | 2021 | R16
166563194057 | 168149194057 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-20 | 2020-05-29 | 2020-06-12 | 2020-08-05 | 2020-08-06 | Underground | R16 | 2020-08-05 | 8 | 11 | 39 | 2 | 57 | 2020 | 2020 | R16
162954273035 | 166456273035 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-07-07 | 2021-04-19 | 2022-03-17 | 2022-04-01 | 2023-01-27 | Underground | R16 | 2022-04-01 | 205 | 239 | 12 | 216 | 669 | 2020 | 2023 | R16
168876186537 | 160296186537 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-06 | 2020-04-06 | 2020-04-06 | 2020-09-22 | 2020-12-29 | Overhead | R16 | 2020-09-22 | 1 |  | 122 | 71 | 192 | 2020 | 2020 | R16
165462180153 | 169278180153 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-02-11 | 2020-02-11 | 2020-02-11 | 2020-02-20 | 2020-02-21 | Overhead | R16 | 2020-02-20 | 1 |  | 8 | 2 | 9 | 2020 | 2020 | R16
160804184062 | 164670184062 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-06 | 2020-03-06 | 2020-03-13 | 2020-09-23 | 2020-09-24 | Underground | R16 | 2020-09-23 | 1 | 6 | 139 | 2 | 145 | 2020 | 2020 | R16
160365192488 | 161624192488 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-13 | 2020-04-13 | 2020-05-28 | 2020-06-22 | 2020-07-10 | Underground | R16 | 2020-06-22 | 1 | 34 | 18 | 15 | 65 | 2020 | 2020 | R16
165907190229 | 166520190229 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-16 | 2020-03-16 | 2020-05-06 | 2020-09-30 | 2020-12-29 | Underground | R16 | 2020-09-30 | 1 | 38 | 106 | 65 | 207 | 2020 | 2020 | R16
168799213592 | 163364213592 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-02 | 2020-03-02 | 2020-12-11 | 2021-08-05 | 2021-09-02 | Underground | R16 | 2021-08-05 | 1 | 205 | 170 | 21 | 394 | 2020 | 2021 | R16
168660209176 | 165356209176 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-10 | 2020-03-10 | 2020-10-30 | 2021-01-14 | 2021-06-02 | Underground | R16 | 2021-01-14 | 1 | 169 | 55 | 100 | 322 | 2020 | 2021 | R16
167756182521 | 161741182521 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-07 | 2020-01-07 | 2020-03-01 | 2020-07-22 | 2021-10-21 | Underground | R16 | 2020-07-22 | 1 | 39 | 103 | 327 | 468 | 2020 | 2021 | R16
165309177340 | 164124177340 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-01-17 | 2020-01-17 | 2020-01-17 | 2020-02-21 | 2020-06-09 | Overhead | R16 | 2020-02-21 | 1 |  | 26 | 78 | 103 | 2020 | 2020 | R16
169322176334 | 169519176334 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-20 | 2019-12-20 | 2020-01-09 | 2020-01-10 | 2020-06-09 | Underground | R16 | 2020-01-10 | 1 | 15 | 2 | 108 | 123 | 2019 | 2020 | R16
160079177905 | 161345177905 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-06 | 2020-01-23 | 2020-01-23 | 2020-02-03 | 2020-06-09 | Overhead | R16 | 2020-02-03 | 14 |  | 8 | 92 | 112 | 2020 | 2020 | R16
169246178757 | 167002178757 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-31 | 2020-01-31 | 2020-01-31 | 2020-02-11 | 2020-02-12 | Overhead | R16 | 2020-02-11 | 1 |  | 8 | 2 | 9 | 2020 | 2020 | R16
162341191143 | 166882191143 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-05-12 | 2020-05-12 | 2020-05-14 | 2021-09-13 | 2021-11-08 | Underground | R16 | 2021-09-13 | 1 | 3 | 348 | 41 | 390 | 2020 | 2021 | R16
166997176290 | 161633176290 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-07 | 2020-01-07 | 2020-01-07 | 2020-02-12 | 2020-06-09 | Overhead | R16 | 2020-02-12 | 1 |  | 27 | 85 | 111 | 2020 | 2020 | R16
160983196035 | 164750196035 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-30 | 2020-04-30 | 2020-06-30 | 2020-09-02 | 2021-01-21 | Overhead | R16 | 2020-09-02 | 1 | 44 | 47 | 102 | 191 | 2020 | 2021 | R16
162254227233 | 161440227233 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2020-04-13 | 2021-04-03 | 2021-04-16 | 2022-12-09 | 2022-04-26 | Overhead | R16 | 2022-12-09 | 255 | 10 | 431 |  | 532 | 2020 | 2022 | R16
166129190643 | 167772190643 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-23 | 2020-03-23 | 2020-05-11 | 2020-06-01 | 2020-07-10 | Underground | R16 | 2020-06-01 | 1 | 36 | 16 | 30 | 80 | 2020 | 2020 | R16
168108193170 | 169930193170 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-31 | 2020-05-31 | 2020-06-05 | 2020-07-09 | 2020-10-06 | Overhead | R16 | 2020-07-09 | 0 | 5 | 25 | 64 | 92 | 2020 | 2020 | R16
168595223487 | 167598223487 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-23 | 2020-03-23 | 2021-03-12 | 2021-05-15 | 2021-05-19 | Underground | R16 | 2021-05-15 | 1 | 255 | 46 | 3 | 303 | 2020 | 2021 | R16
164987189802 | 165012189802 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-01 | 2020-05-01 | 2020-05-01 | 2020-05-18 | 2020-05-21 | Underground | R16 | 2020-05-18 | 1 |  | 12 | 4 | 15 | 2020 | 2020 | R16
161727195229 | 164463195229 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-25 | 2020-06-25 | 2020-06-25 | 2020-07-24 | 2020-10-06 | Overhead | R16 | 2020-07-24 | 1 |  | 22 | 53 | 74 | 2020 | 2020 | R16
163800189113 | 166025189113 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-12 | 2020-03-13 | 2020-04-28 | 2020-05-27 | 2020-05-27 | Underground | R16 | 2020-05-27 | 2 | 33 | 22 |  | 55 | 2020 | 2020 | R16
161622197544 | 166988197544 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-09 | 2020-07-10 | 2020-07-16 | 2020-07-17 | 2020-10-06 | Overhead | R16 | 2020-07-17 | 2 | 5 | 2 | 58 | 64 | 2020 | 2020 | R16
166351196430 | 161371196430 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-06-09 | 2020-06-09 | 2020-07-04 | 2020-10-02 | 2022-11-14 | Underground | R16 | 2020-10-02 | 1 | 19 | 65 | 552 | 635 | 2020 | 2022 | R16
164829191889 | 168439191889 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-21 | 2020-05-21 | 2020-05-21 | 2020-06-08 | 2020-06-09 | Overhead | R16 | 2020-06-08 | 1 |  | 13 | 2 | 14 | 2020 | 2020 | R16
163351190373 | 160491190373 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-14 | 2020-02-18 | 2020-05-08 | 2020-08-13 | 2021-02-09 | Underground | R16 | 2020-08-13 | 3 | 59 | 70 | 129 | 258 | 2020 | 2021 | R16
161990195483 | 162840195483 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-17 | 2020-06-17 | 2020-06-26 | 2020-08-10 | 2020-10-06 | Underground | R16 | 2020-08-10 | 1 | 8 | 32 | 42 | 80 | 2020 | 2020 | R16
165458184607 | 160905184607 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-18 | 2020-02-18 | 2020-03-18 |  | 2020-04-08 | Underground | R16 |  | 1 | 22 |  |  | 37 | 2020 | 2020 | R16
163643187334 | 161572187334 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-04-13 | 2020-04-13 | 2020-04-14 | 2020-04-29 | 2020-04-30 | Overhead | R16 | 2020-04-29 | 1 | 2 | 12 | 2 | 14 | 2020 | 2020 | R16
160585191546 | 167424191546 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-15 | 2020-05-15 | 2020-05-18 | 2020-05-27 | 2020-12-21 | Overhead | R16 | 2020-05-27 | 1 | 2 | 8 | 149 | 157 | 2020 | 2020 | R16
162073210974 | 167067210974 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-10 | 2020-07-10 | 2020-11-17 | 2021-01-20 | 2021-04-21 | Underground | R16 | 2021-01-20 | 1 | 93 | 47 | 66 | 204 | 2020 | 2021 | R16
166817182168 | 161923182168 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-24 | 2020-02-24 | 2020-02-27 | 2020-04-10 | 2020-06-24 | Underground | R16 | 2020-04-10 | 1 | 4 | 32 | 54 | 88 | 2020 | 2020 | R16
168477191512 | 166796191512 | GENERAL/OTHER | R16 RESD AND NON RESD US | Commercial | 2020-05-12 | 2020-05-12 | 2020-05-19 | 2021-03-04 | 2021-05-22 | Underground | R16 | 2021-03-04 | 1 | 6 | 208 | 57 | 269 | 2020 | 2021 | R16
162006189470 | 164890189470 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-03-09 | 2020-03-09 | 2020-04-30 | 2020-07-30 | 2020-10-06 | Underground | R16 | 2020-07-30 | 1 | 39 | 66 | 49 | 152 | 2020 | 2020 | R16
167295266996 | 163653266996 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Commercial | 2020-03-02 | 2020-11-19 | 2022-02-01 | 2022-06-03 | 2022-06-22 | Underground | R16 | 2022-06-03 | 189 | 314 | 89 | 14 | 603 | 2020 | 2022 | R16
162823195137 | 164240195137 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-24 | 2020-06-26 | 2020-06-26 | 2020-07-13 | 2020-07-14 | Overhead | R16 | 2020-07-13 | 3 |  | 12 | 2 | 15 | 2020 | 2020 | R16
166447185818 | 162200185818 | RESIDENTIAL - SUBSEQUENT WORK | OH R16 RES NON RES OD | Residential | 2020-02-24 | 2020-03-07 | 2020-03-31 | 2020-03-31 | 2020-05-27 | Overhead | R16 | 2020-03-31 | 10 | 17 |  | 42 | 68 | 2020 | 2020 | R16
160243195190 | 164069195190 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-24 | 2020-06-24 | 2020-06-24 | 2020-09-10 | 2020-12-17 | Overhead | R16 | 2020-09-10 | 1 |  | 57 | 71 | 127 | 2020 | 2020 | R16
168463189661 | 164899189661 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-01 | 2020-05-01 | 2020-05-01 | 2020-06-03 | 2020-06-05 | Overhead | R16 | 2020-06-03 | 1 |  | 24 | 3 | 26 | 2020 | 2020 | R16
168460183911 | 163125183911 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-28 | 2020-03-13 | 2020-03-13 | 2020-03-27 | 2020-07-07 | Overhead | R16 | 2020-03-27 | 11 |  | 11 | 73 | 93 | 2020 | 2020 | R16
168291194653 | 162864194653 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-17 | 2020-06-17 | 2020-06-17 | 2020-06-18 | 2020-07-14 | Overhead | R16 | 2020-06-18 | 1 |  | 2 | 19 | 20 | 2020 | 2020 | R16
167403175358 | 169064175358 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-17 | 2019-12-31 | 2019-12-31 | 2020-03-10 | 2020-03-11 | Overhead | R16 | 2020-03-10 | 11 |  | 51 | 2 | 62 | 2019 | 2020 | R16
169033193328 | 160770193328 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-05 | 2020-06-05 | 2020-06-05 | 2020-07-07 | 2020-10-06 | Overhead | R16 | 2020-07-07 | 1 |  | 23 | 66 | 88 | 2020 | 2020 | R16
168429193194 | 168006193194 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-19 | 2020-06-04 | 2020-06-04 | 2020-07-01 | 2020-10-06 | Overhead | R16 | 2020-07-01 | 13 |  | 20 | 70 | 101 | 2020 | 2020 | R16
160243195189 | 162548195189 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-16 | 2020-06-24 | 2020-06-24 | 2021-04-08 | 2023-06-07 | Overhead | R16 | 2021-04-08 | 7 |  | 207 | 565 | 777 | 2020 | 2023 | R16
161223185049 | 167788185049 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-24 | 2020-03-24 | 2020-03-24 | 2020-04-27 | 2020-07-07 | Overhead | R16 | 2020-04-27 | 1 |  | 25 | 52 | 76 | 2020 | 2020 | R16
168755184980 | 167470184980 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-22 | 2020-03-22 | 2020-03-22 | 2020-05-26 | 2020-05-27 | Overhead | R16 | 2020-05-26 | 0 |  | 47 | 2 | 48 | 2020 | 2020 | R16
162032210098 | 169592210098 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential Subdivision | 2020-02-12 | 2020-02-19 | 2020-11-10 | 2021-11-29 | 2021-12-27 | Underground | R16 | 2021-11-29 | 6 | 190 | 275 | 21 | 489 | 2020 | 2021 | R16
164483195105 | 163688195105 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-23 | 2020-06-23 | 2020-06-23 | 2020-07-08 | 2020-07-09 | Overhead | R16 | 2020-07-08 | 1 |  | 12 | 2 | 13 | 2020 | 2020 | R16
169103188972 | 163502188972 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-23 | 2020-04-24 | 2020-04-24 | 2020-12-11 | 2021-11-11 | Overhead | R16 | 2020-12-11 | 2 |  | 166 | 240 | 406 | 2020 | 2021 | R16
168265209178 | 168253209178 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-15 | 2020-07-15 | 2020-10-30 | 2021-03-17 | 2021-03-18 | Underground | R16 | 2021-03-17 | 1 | 78 | 99 | 2 | 177 | 2020 | 2021 | R16
164745213276 | 161343213276 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG R16 ELECTRIC RELOCATION UD | Residential | 2020-06-09 | 2020-11-13 | 2020-12-09 | 2021-03-22 | 2022-10-03 | Underground | R16 | 2021-03-22 | 114 | 19 | 74 | 401 | 605 | 2020 | 2022 | R16
161993181844 | 162026181844 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-24 | 2020-02-24 | 2020-02-25 | 2020-03-23 | 2020-03-26 | Underground | R16 | 2020-03-23 | 1 | 2 | 20 | 4 | 24 | 2020 | 2020 | R16
166138178489 | 169433178489 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-12-19 | 2019-12-19 | 2020-01-28 | 2021-12-28 | 2021-12-29 | Underground | R16 | 2021-12-28 | 1 | 29 | 501 | 2 | 530 | 2019 | 2021 | R16
161273196227 | 163945196227 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-23 | 2020-06-30 | 2020-07-01 | 2020-09-24 | 2021-01-07 | Overhead | R16 | 2020-09-24 | 6 | 2 | 62 | 76 | 143 | 2020 | 2021 | R16
164567182003 | 169702182003 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2020-02-13 | 2020-02-13 | 2020-02-26 | 2022-01-28 | 2023-08-02 | Underground | R16 | 2022-01-28 | 1 | 10 | 503 | 394 | 905 | 2020 | 2023 | R16
160465190091 | 161830190091 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-14 | 2020-04-14 | 2020-05-05 | 2020-07-23 | 2020-10-06 | Underground | R16 | 2020-07-23 | 1 | 16 | 58 | 54 | 126 | 2020 | 2020 | R16
166116185441 | 161104185441 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-01-03 | 2020-01-03 | 2020-03-25 | 2020-05-15 | 2020-08-25 | Underground | R16 | 2020-05-15 | 1 | 59 | 38 | 73 | 168 | 2020 | 2020 | R16
169226175540 | 160302175540 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-30 | 2019-12-31 | 2019-12-31 | 2020-01-02 | 2020-06-09 | Overhead | R16 | 2020-01-02 | 2 |  | 3 | 114 | 117 | 2019 | 2020 | R16
162187192785 | 160042192785 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2020-07-30 | 2020-07-31 | Overhead | R16 | 2020-07-30 | 1 |  | 44 | 2 | 45 | 2020 | 2020 | R16
164338178720 | 166664178720 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-29 | 2020-01-29 | 2020-01-29 | 2020-02-28 | 2020-06-09 | Overhead | R16 | 2020-02-28 | 1 |  | 23 | 73 | 95 | 2020 | 2020 | R16
169996176332 | 162303176332 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-09 | 2020-01-09 | 2020-01-09 | 2021-01-08 | 2021-07-28 | Overhead | R16 | 2021-01-08 | 1 |  | 262 | 144 | 405 | 2020 | 2021 | R16
165171231139 | 166900231139 | NON-RESIDENTIAL - WAREHOUSE | UG R16 RESD AND NON RESD UD | Commercial | 2020-05-13 | 2020-09-24 | 2021-05-18 | 2021-12-06 | 2022-02-09 | Underground | R16 | 2021-12-06 | 97 | 169 | 145 | 48 | 456 | 2020 | 2022 | R16
165687207052 | 165689207052 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-01-24 | 2020-01-24 | 2020-10-13 | 2020-12-16 | 2021-01-21 | Underground | R16 | 2020-12-16 | 1 | 188 | 47 | 27 | 260 | 2020 | 2021 | R16
166392188900 | 160855188900 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-19 | 2020-02-19 | 2020-04-23 | 2020-06-08 | 2020-06-09 | Underground | R16 | 2020-06-08 | 1 | 47 | 33 | 2 | 80 | 2020 | 2020 | R16
168443180887 | 160649180887 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-01-02 | 2020-01-02 | 2020-02-18 | 2021-05-06 | 2021-05-07 | Underground | R16 | 2021-05-06 | 1 | 34 | 318 | 2 | 352 | 2020 | 2021 | R16
165723177001 | 163447177001 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-14 | 2020-01-14 | 2020-01-14 | 2020-03-24 | 2020-06-09 | Overhead | R16 | 2020-03-24 | 1 |  | 51 | 56 | 106 | 2020 | 2020 | R16
163158184863 | 165393184863 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-10 | 2020-03-19 | 2020-03-19 | 2020-03-27 | 2020-07-07 | Overhead | R16 | 2020-03-27 | 8 |  | 7 | 73 | 86 | 2020 | 2020 | R16
165587186153 | 167360186153 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-20 | 2020-03-20 | 2020-04-02 | 2020-04-09 | 2023-06-07 | Overhead | R16 | 2020-04-09 | 1 | 10 | 6 | 825 | 839 | 2020 | 2023 | R16
164902188626 | 169153188626 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-31 | 2020-03-31 | 2020-04-21 | 2020-06-24 | 2020-08-28 | Underground | R16 | 2020-06-24 | 1 | 16 | 47 | 48 | 109 | 2020 | 2020 | R16
163951250154 | 166589250154 | NON-RESIDENTIAL - HEALTH CARE | UG R16 RESD AND NON RESD UD | Commercial | 2020-05-12 | 2020-07-08 | 2021-09-30 | 2021-11-06 | 2022-04-21 | Underground | R16 | 2021-11-06 | 42 | 322 | 27 | 119 | 508 | 2020 | 2022 | R16
165913177149 | 163736177149 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-01-16 | 2020-01-16 | 2020-01-16 | 2020-07-01 | 2020-07-09 | Overhead | R16 | 2020-07-01 | 1 |  | 120 | 7 | 126 | 2020 | 2020 | R16
161386195420 | 164661195420 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-26 | 2020-06-26 | 2020-06-26 | 2020-07-23 | 2020-07-24 | Overhead | R16 | 2020-07-23 | 1 |  | 20 | 2 | 21 | 2020 | 2020 | R16
160527183938 | 162491183938 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-26 | 2020-03-12 | 2020-03-12 | 2020-03-17 | 2020-07-01 | Overhead | R16 | 2020-03-17 | 12 |  | 4 | 77 | 91 | 2020 | 2020 | R16
169759193274 | 160717193274 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-08 | 2020-04-10 | 2020-06-05 | 2020-06-08 | 2021-02-08 | Underground | R16 | 2020-06-08 | 3 | 41 | 2 | 176 | 219 | 2020 | 2021 | R16
165571182096 | 162920182096 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-27 | 2020-02-27 | 2020-02-27 | 2022-07-08 | 2022-08-16 | Overhead | R16 | 2022-07-08 | 1 |  | 617 | 28 | 644 | 2020 | 2022 | R16
160858217688 | 163677217688 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-03-02 | 2020-03-06 | 2021-01-19 | 2022-01-04 | 2022-01-26 | Overhead | R16 | 2022-01-04 | 5 | 228 | 251 | 17 | 498 | 2020 | 2022 | R16
165948204923 | 161870204923 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-04-15 | 2020-04-16 | 2020-09-24 | 2021-05-03 | 2021-06-28 | Underground | R16 | 2021-05-03 | 2 | 116 | 158 | 41 | 314 | 2020 | 2021 | R16
162202179229 | 165307179229 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-22 | 2020-02-03 | 2020-02-03 | 2021-11-05 | 2021-12-08 | Overhead | R16 | 2021-11-05 | 9 |  | 460 | 24 | 491 | 2020 | 2021 | R16
167416185337 | 168198185337 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-26 | 2020-03-26 | 2020-03-26 | 2021-02-10 | 2022-02-07 | Overhead | R16 | 2021-02-10 | 1 |  | 230 | 259 | 488 | 2020 | 2022 | R16
161561202196 | 163942202196 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-23 | 2020-06-23 | 2020-08-30 | 2020-10-06 | 2021-01-22 | Underground | R16 | 2020-10-06 | 1 | 49 | 27 | 79 | 154 | 2020 | 2021 | R16
163770271379 | 161004271379 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-04-09 | 2021-04-09 | 2022-03-04 |  | 2022-03-22 | Underground | R16 |  | 262 | 236 |  |  | 509 | 2020 | 2022 | R16
163428189327 | 164350189327 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2020-04-28 | 2020-04-29 | 2020-04-29 | 2020-05-14 | 2020-07-09 | Overhead | R16 | 2020-05-14 | 2 |  | 12 | 41 | 53 | 2020 | 2020 | R16
166645191619 | 168059191619 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-20 | 2020-05-20 | 2020-05-20 | 2020-07-07 | 2020-09-01 | Overhead | R16 | 2020-07-07 | 1 |  | 35 | 41 | 75 | 2020 | 2020 | R16
167900276469 | 160495276469 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-06-04 | 2020-08-18 | 2022-04-20 | 2023-01-05 | 2023-01-05 | Underground | R16 | 2023-01-05 | 54 | 437 | 187 |  | 676 | 2020 | 2023 | R16
165726192808 | 160002192808 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2020-07-07 | 2020-10-06 | Overhead | R16 | 2020-07-07 | 1 |  | 27 | 66 | 92 | 2020 | 2020 | R16
164841197663 | 167567197663 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-13 | 2020-07-13 | 2020-07-17 | 2021-01-08 | 2021-04-20 | Underground | R16 | 2021-01-08 | 1 | 5 | 126 | 73 | 202 | 2020 | 2021 | R16
168237186883 | 168827186883 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-27 | 2020-03-30 | 2020-04-08 | 2020-05-20 | 2020-05-21 | Underground | R16 | 2020-05-20 | 2 | 8 | 31 | 2 | 40 | 2020 | 2020 | R16
166429195668 | 162511195668 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-16 | 2020-06-16 | 2020-06-29 | 2020-07-13 | 2020-10-06 | Underground | R16 | 2020-07-13 | 1 | 10 | 11 | 62 | 81 | 2020 | 2020 | R16
167627192311 | 169317192311 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-28 | 2020-05-28 | 2020-05-28 | 2020-07-09 | 2020-10-06 | Overhead | R16 | 2020-07-09 | 1 |  | 31 | 64 | 94 | 2020 | 2020 | R16
163339200188 | 165727200188 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-06 | 2020-06-19 | 2020-08-11 | 2021-05-25 | 2023-06-07 | Underground | R16 | 2021-05-25 | 33 | 38 | 206 | 532 | 806 | 2020 | 2023 | R16
160176176389 | 162365176389 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-09 | 2020-01-09 | 2020-01-09 | 2020-01-30 | 2020-02-03 | Overhead | R16 | 2020-01-30 | 1 |  | 16 | 3 | 18 | 2020 | 2020 | R16
168066194681 | 162817194681 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-17 | 2020-06-17 | 2020-06-17 | 2020-09-22 | 2020-12-18 | Overhead | R16 | 2020-09-22 | 1 |  | 70 | 64 | 133 | 2020 | 2020 | R16
168915194136 | 162090194136 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-12 | 2020-06-12 | 2020-06-12 | 2020-07-07 | 2020-10-06 | Overhead | R16 | 2020-07-07 | 1 |  | 18 | 66 | 83 | 2020 | 2020 | R16
168097187190 | 161371187190 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-04-11 | 2020-04-11 | 2020-04-11 | 2022-01-18 | 2022-02-22 | Underground | R16 | 2022-01-18 | 0 |  | 462 | 26 | 487 | 2020 | 2022 | R16
163398189459 | 164760189459 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-30 | 2020-04-30 | 2020-04-30 | 2020-06-01 | 2020-06-03 | Overhead | R16 | 2020-06-01 | 1 |  | 23 | 3 | 25 | 2020 | 2020 | R16
167670192044 | 162436192044 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-17 | 2020-04-20 | 2020-05-22 | 2020-06-16 | 2020-10-26 | Overhead | R16 | 2020-06-16 | 2 | 25 | 18 | 95 | 137 | 2020 | 2020 | R16
169314195350 | 164107195350 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-25 | 2020-06-25 | 2020-06-25 | 2020-07-27 | 2020-07-28 | Overhead | R16 | 2020-07-27 | 1 |  | 23 | 2 | 24 | 2020 | 2020 | R16
164359181298 | 161229181298 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-20 | 2020-02-20 | 2020-02-20 | 2020-04-07 | 2020-07-07 | Overhead | R16 | 2020-04-07 | 1 |  | 34 | 66 | 99 | 2020 | 2020 | R16
161710186136 | 169569186136 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-02 | 2020-04-02 | 2020-04-02 | 2020-04-09 | 2020-07-01 | Overhead | R16 | 2020-04-09 | 1 |  | 6 | 60 | 65 | 2020 | 2020 | R16
166823184232 | 161782184232 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-07 | 2020-01-07 | 2020-03-16 | 2020-06-16 | 2020-06-18 | Underground | R16 | 2020-06-16 | 1 | 50 | 67 | 3 | 118 | 2020 | 2020 | R16
167066198794 | 166965198794 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-13 | 2020-05-13 | 2020-07-28 | 2020-09-05 | 2020-09-08 | Underground | R16 | 2020-09-05 | 1 | 55 | 29 | 2 | 85 | 2020 | 2020 | R16
169546190674 | 166503190674 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-12 | 2020-05-12 | 2020-05-12 | 2020-07-15 | 2020-07-20 | Overhead | R16 | 2020-07-15 | 1 |  | 47 | 4 | 50 | 2020 | 2020 | R16
169876178888 | 169881178888 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-12-23 | 2019-12-23 | 2020-01-31 | 2020-10-01 | 2020-10-02 | Underground | R16 | 2020-10-01 | 1 | 30 | 175 | 2 | 205 | 2019 | 2020 | R16
166150195013 | 168050195013 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Commercial | 2020-03-24 | 2020-04-27 | 2020-06-23 | 2021-07-26 | 2021-12-10 | Underground | R16 | 2021-07-26 | 25 | 42 | 285 | 100 | 449 | 2020 | 2021 | R16
166492188682 | 161416188682 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-04-13 | 2020-04-13 | 2020-04-22 | 2021-10-26 | 2021-11-08 | Underground | R16 | 2021-10-26 | 1 | 8 | 395 | 10 | 411 | 2020 | 2021 | R16
166294175467 | 160620175467 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-31 | 2019-12-31 | 2019-12-31 | 2020-02-14 | 2020-06-09 | Overhead | R16 | 2020-02-14 | 1 |  | 34 | 83 | 116 | 2019 | 2020 | R16
168187175606 | 169862175606 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-23 | 2019-12-31 | 2020-01-02 | 2020-01-10 | 2020-06-09 | Overhead | R16 | 2020-01-10 | 7 | 3 | 7 | 108 | 122 | 2019 | 2020 | R16
162143188041 | 162123188041 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-16 | 2020-04-16 | 2020-04-17 | 2020-05-24 | 2023-12-08 | Overhead | R16 | 2020-05-24 | 1 | 2 | 26 | 925 | 952 | 2020 | 2023 | R16
169575190897 | 163457190897 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-23 | 2020-04-23 | 2020-05-14 | 2020-05-21 | 2020-05-22 | Underground | R16 | 2020-05-21 | 1 | 16 | 6 | 2 | 22 | 2020 | 2020 | R16
162080225360 | 162328225360 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-06-16 | 2020-06-16 | 2021-03-30 | 2023-01-05 | 2023-01-06 | Underground | R16 | 2023-01-05 | 1 | 206 | 463 | 2 | 669 | 2020 | 2023 | R16
165187176505 | 162590176505 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-10 | 2020-01-10 | 2020-01-10 | 2020-02-04 | 2020-02-05 | Overhead | R16 | 2020-02-04 | 1 |  | 18 | 2 | 19 | 2020 | 2020 | R16
165521186428 | 160907186428 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-18 | 2020-02-18 | 2020-04-06 | 2020-05-29 | 2020-06-01 | Underground | R16 | 2020-05-29 | 1 | 35 | 40 | 2 | 75 | 2020 | 2020 | R16
162399178461 | 165454178461 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-23 | 2020-01-23 | 2020-01-28 | 2020-03-24 | 2020-06-09 | Overhead | R16 | 2020-03-24 | 1 | 4 | 41 | 56 | 99 | 2020 | 2020 | R16
161396193644 | 163621193644 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential Subdivision | 2020-04-24 | 2020-04-24 | 2020-06-08 | 2021-08-05 | 2022-01-11 | Underground | R16 | 2021-08-05 | 1 | 32 | 304 | 114 | 448 | 2020 | 2022 | R16
169330181379 | 163103181379 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-13 | 2020-01-13 | 2020-02-22 | 2020-04-13 | 2020-04-13 | Underground | R16 | 2020-04-13 | 1 | 30 | 36 |  | 66 | 2020 | 2020 | R16
164931247689 | 164888247689 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-04-30 | 2020-05-01 | 2021-09-13 | 2022-07-18 | 2022-08-02 | Underground | R16 | 2022-07-18 | 2 | 357 | 221 | 12 | 589 | 2020 | 2022 | R16
168635193660 | 160931193660 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-08 | 2020-06-08 | 2020-06-08 | 2020-06-22 | 2020-06-23 | Overhead | R16 | 2020-06-22 | 1 |  | 11 | 2 | 12 | 2020 | 2020 | R16
165647180067 | 169026180067 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-02-10 | 2020-02-10 | 2020-02-10 | 2020-10-07 | 2021-01-20 | Overhead | R16 | 2020-10-07 | 1 |  | 173 | 76 | 248 | 2020 | 2021 | R16
165063190241 | 165627190241 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-05-05 | 2020-05-05 | 2020-05-06 | 2020-05-13 | 2021-07-08 | Underground | R16 | 2020-05-13 | 1 | 2 | 6 | 302 | 308 | 2020 | 2021 | R16
165151200213 | 161140200213 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-03 | 2020-01-06 | 2020-08-11 | 2022-01-06 | 2022-01-19 | Underground | R16 | 2022-01-06 | 2 | 157 | 368 | 10 | 534 | 2020 | 2022 | R16
164840183397 | 169779183397 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-13 | 2020-02-13 | 2020-03-10 | 2020-04-27 | 2020-06-30 | Underground | R16 | 2020-04-27 | 1 | 19 | 35 | 47 | 99 | 2020 | 2020 | R16
168750197735 | 160344197735 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-03 | 2020-06-03 | 2020-07-20 | 2020-11-10 | 2021-07-19 | Underground | R16 | 2020-11-10 | 1 | 34 | 82 | 180 | 294 | 2020 | 2021 | R16
169477195018 | 161151195018 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-08 | 2020-06-24 | 2020-06-24 | 2020-07-21 | 2020-10-06 | Overhead | R16 | 2020-07-21 | 13 |  | 20 | 56 | 87 | 2020 | 2020 | R16
164434191495 | 167913191495 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-19 | 2020-05-19 | 2020-05-19 | 2020-05-27 | 2020-07-14 | Overhead | R16 | 2020-05-27 | 1 |  | 7 | 35 | 41 | 2020 | 2020 | R16
161246249026 | 161248249026 | RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Residential | 2020-04-10 | 2020-09-03 | 2021-09-22 | 2022-04-08 | 2022-04-27 | Underground | R16 | 2022-04-08 | 105 | 275 | 143 | 14 | 534 | 2020 | 2022 | R16
164194196067 | 165304196067 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-04 | 2020-06-29 | 2020-06-29 | 2020-09-24 | 2020-12-29 | Overhead | R16 | 2020-09-24 | 41 |  | 64 | 69 | 172 | 2020 | 2020 | R16
163258195276 | 160875195276 | NON-RESIDENTIAL - WAREHOUSE | UG R16 RESD AND NON RESD UD | Commercial | 2020-02-19 | 2020-02-26 | 2020-06-24 | 2020-11-10 | 2021-04-06 | Underground | R16 | 2020-11-10 | 6 | 86 | 100 | 106 | 295 | 2020 | 2021 | R16
161318199681 | 166184199681 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-07-06 | 2020-07-27 | 2020-08-04 | 2021-03-16 | 2021-05-24 | Underground | R16 | 2021-03-16 | 16 | 7 | 161 | 50 | 231 | 2020 | 2021 | R16
166080233958 | 166532233958 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-07-07 | 2020-09-05 | 2021-06-08 | 2023-10-20 | 2023-11-07 | Underground | R16 | 2023-10-20 | 44 | 197 | 619 | 13 | 871 | 2020 | 2023 | R16
169581205740 | 163749205740 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-01-16 | 2020-01-16 | 2020-09-29 | 2020-12-15 | 2021-04-14 | Underground | R16 | 2020-12-15 | 1 | 184 | 56 | 87 | 325 | 2020 | 2021 | R16
161452195356 | 164685195356 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-26 | 2020-06-26 | 2020-06-26 | 2020-08-03 | 2020-10-06 | Overhead | R16 | 2020-08-03 | 1 |  | 27 | 47 | 73 | 2020 | 2020 | R16
166418197718 | 164061197718 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-04-27 | 2020-07-18 | 2020-07-18 | 2020-12-22 | 2021-02-26 | Overhead | R16 | 2020-12-22 | 60 |  | 112 | 49 | 220 | 2020 | 2021 | R16
164147204387 | 160655204387 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-18 | 2020-02-18 | 2020-09-19 | 2020-12-16 | 2020-12-18 | Underground | R16 | 2020-12-16 | 1 | 154 | 63 | 3 | 219 | 2020 | 2020 | R16
162089190662 | 163093190662 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-21 | 2020-04-21 | 2020-05-11 | 2020-06-04 | 2020-06-05 | Underground | R16 | 2020-06-04 | 1 | 15 | 19 | 2 | 34 | 2020 | 2020 | R16
162209280301 | 167620280301 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-05-18 | 2020-05-18 | 2022-05-23 | 2023-01-09 | 2023-01-19 | Overhead | R16 | 2023-01-09 | 1 | 526 | 166 | 9 | 699 | 2020 | 2023 | R16
165250181919 | 162410181919 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-25 | 2020-02-25 | 2020-02-25 | 2020-04-28 | 2020-07-01 | Overhead | R16 | 2020-04-28 | 1 |  | 46 | 47 | 92 | 2020 | 2020 | R16
169935176642 | 161520176642 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-06 | 2020-01-09 | 2020-01-13 | 2020-05-05 | 2020-07-08 | Overhead | R16 | 2020-05-05 | 4 | 3 | 82 | 47 | 133 | 2020 | 2020 | R16
160845184833 | 167178184833 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-20 | 2020-03-20 | 2020-03-20 | 2020-08-20 | 2020-08-21 | Overhead | R16 | 2020-08-20 | 1 |  | 110 | 2 | 111 | 2020 | 2020 | R16
166117248385 | 166127248385 | SPECIFIC BUDGET PROJECTS | UG R16 RESD AND NON RESD UD | Commercial | 2020-03-13 | 2020-10-14 | 2021-09-17 |  | 2022-06-20 | Underground | R16 |  | 154 | 243 |  |  | 592 | 2020 | 2022 | R16
167588193145 | 169456193145 | NON-RESIDENTIAL - LARGE RETAIL | R16 RESD AND NON RESD US | Commercial | 2020-04-01 | 2020-05-21 | 2020-06-03 | 2020-10-12 | 2020-11-12 | Underground | R16 | 2020-10-12 | 37 | 10 | 94 | 24 | 162 | 2020 | 2020 | R16
161655196747 | 166972196747 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-01-30 | 2020-05-29 | 2020-07-09 | 2021-04-29 | 2021-06-29 | Underground | R16 | 2021-04-29 | 87 | 30 | 211 | 44 | 369 | 2020 | 2021 | R16
160016195019 | 161075195019 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-08 | 2020-06-19 | 2020-06-24 | 2020-07-24 | 2020-10-06 | Overhead | R16 | 2020-07-24 | 10 | 4 | 23 | 53 | 87 | 2020 | 2020 | R16
162648181102 | 160698181102 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-18 | 2020-02-18 | 2020-02-18 | 2020-06-04 | 2020-07-15 | Overhead | R16 | 2020-06-04 | 1 |  | 78 | 30 | 107 | 2020 | 2020 | R16
163464195078 | 167001195078 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-05-13 | 2020-05-13 | 2020-06-23 | 2021-02-14 | 2021-02-17 | Overhead | R16 | 2021-02-14 | 1 | 30 | 169 | 3 | 201 | 2020 | 2021 | R16
161341183731 | 164031183731 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-04 | 2020-03-10 | 2020-03-10 | 2020-04-27 | 2020-06-02 | Overhead | R16 | 2020-04-27 | 5 |  | 35 | 27 | 65 | 2020 | 2020 | R16
169306201071 | 164004201071 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-04-27 | 2020-04-27 | 2020-08-19 | 2020-11-05 | 2021-02-04 | Underground | R16 | 2020-11-05 | 1 | 83 | 57 | 66 | 204 | 2020 | 2021 | R16
169817186756 | 167452186756 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-02-03 | 2020-02-03 | 2020-04-09 | 2021-11-06 | 2021-11-23 | Underground | R16 | 2021-11-06 | 1 | 49 | 412 | 12 | 472 | 2020 | 2021 | R16
162000253820 | 160003253820 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OD | Commercial | 2020-06-01 | 2020-10-14 | 2021-10-25 | 2022-10-27 | 2023-03-02 | Overhead | R16 | 2022-10-27 | 98 | 269 | 264 | 91 | 719 | 2020 | 2023 | R16
162919179612 | 168457179612 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-06 | 2020-02-06 | 2020-02-06 | 2021-02-01 | 2021-04-23 | Overhead | R16 | 2021-02-01 | 1 |  | 258 | 60 | 317 | 2020 | 2021 | R16
161012195975 | 163979195975 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-23 | 2020-06-30 | 2020-06-30 | 2020-07-13 | 2020-10-06 | Overhead | R16 | 2020-07-13 | 6 |  | 10 | 62 | 76 | 2020 | 2020 | R16
160526175356 | 160338175356 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-12-31 | 2019-12-31 | 2019-12-31 | 2020-01-10 | 2020-01-13 | Overhead | R16 | 2020-01-10 | 1 |  | 9 | 2 | 10 | 2019 | 2020 | R16
163439185838 | 169212185838 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-31 | 2020-03-31 | 2020-03-31 | 2020-04-08 | 2020-10-06 | Overhead | R16 | 2020-04-08 | 1 |  | 7 | 130 | 136 | 2020 | 2020 | R16
164520197113 | 165957197113 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-02 | 2020-07-14 | 2020-07-14 | 2020-07-20 | 2021-03-11 | Overhead | R16 | 2020-07-20 | 9 |  | 5 | 169 | 181 | 2020 | 2021 | R16
169494184219 | 166660184219 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-17 | 2020-03-17 | 2020-03-17 | 2020-07-30 | 2020-07-31 | Overhead | R16 | 2020-07-30 | 1 |  | 98 | 2 | 99 | 2020 | 2020 | R16
169025184562 | 163862184562 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-03-03 | 2020-03-03 | 2020-03-18 | 2020-05-01 | 2020-10-13 | Underground | R16 | 2020-05-01 | 1 | 12 | 33 | 118 | 161 | 2020 | 2020 | R16
164964179289 | 167583179289 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-03 | 2020-02-03 | 2020-02-03 | 2022-12-13 | 2023-06-07 | Overhead | R16 | 2022-12-13 | 1 |  | 747 | 127 | 873 | 2020 | 2023 | R16
162002177898 | 164265177898 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-17 | 2020-01-17 | 2020-01-23 | 2020-02-09 | 2020-02-12 | Underground | R16 | 2020-02-09 | 1 | 5 | 12 | 3 | 19 | 2020 | 2020 | R16
163332191873 | 163883191873 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-27 | 2020-05-21 | 2020-05-21 | 2020-08-19 | 2020-12-18 | Overhead | R16 | 2020-08-19 | 19 |  | 65 | 88 | 170 | 2020 | 2020 | R16
161444195359 | 164692195359 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-26 | 2020-06-26 | 2020-06-26 | 2020-06-30 | 2020-10-06 | Overhead | R16 | 2020-06-30 | 1 |  | 3 | 71 | 73 | 2020 | 2020 | R16
165350213116 | 162422213116 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-06-16 | 2020-11-18 | 2020-12-08 | 2020-12-09 | 2020-12-16 | Overhead | R16 | 2020-12-09 | 112 | 15 | 2 | 6 | 132 | 2020 | 2020 | R16
161980190483 | 166192190483 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-08 | 2020-05-08 | 2020-05-08 | 2020-10-13 | 2021-02-17 | Overhead | R16 | 2020-10-13 | 1 |  | 113 | 92 | 204 | 2020 | 2021 | R16
166644184175 | 166689184175 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-17 | 2020-03-17 | 2020-03-17 | 2020-03-18 | 2020-03-18 | Underground | R16 | 2020-03-18 | 1 |  | 2 |  | 2 | 2020 | 2020 | R16
165624228699 | 167333228699 | NON-RESIDENTIAL - WAREHOUSE | UG R16 RESD AND NON RESD UD | Commercial | 2020-03-20 | 2020-11-14 | 2021-04-30 | 2022-05-26 | 2022-10-29 | Underground | R16 | 2022-05-26 | 171 | 120 | 280 | 112 | 681 | 2020 | 2022 | R16
168174188757 | 168931188757 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-12-16 | 2020-04-14 | 2020-04-22 | 2020-11-06 | 2020-11-16 | Underground | R16 | 2020-11-06 | 87 | 7 | 143 | 7 | 241 | 2019 | 2020 | R16
160719189432 | 160905189432 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Commercial | 2020-04-09 | 2020-04-09 | 2020-04-30 | 2020-05-19 | 2022-08-22 | Overhead | R16 | 2020-05-19 | 1 | 16 | 14 | 590 | 618 | 2020 | 2022 | R16
165810185777 | 163562185777 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-03-02 | 2020-03-02 | 2020-03-31 | 2020-06-12 | 2020-06-24 | Overhead | R16 | 2020-06-12 | 1 | 22 | 54 | 9 | 83 | 2020 | 2020 | R16
162476180968 | 160629180968 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-18 | 2020-02-18 | 2020-02-18 | 2020-03-11 | 2020-03-12 | Overhead | R16 | 2020-03-11 | 1 |  | 17 | 2 | 18 | 2020 | 2020 | R16
168879175882 | 168935175882 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-17 | 2019-12-17 | 2020-01-06 | 2020-01-06 | 2020-06-09 | Underground | R16 | 2020-01-06 | 1 | 15 |  | 112 | 126 | 2019 | 2020 | R16
163682176583 | 162679176583 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-01-10 | 2020-01-10 | 2020-01-10 | 2020-01-31 | 2023-06-07 | Underground | R16 | 2020-01-31 | 1 |  | 16 | 874 | 889 | 2020 | 2023 | R16
161854199272 | 163946199272 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-23 | 2020-07-31 | 2020-07-31 | 2020-08-04 | 2020-10-29 | Overhead | R16 | 2020-08-04 | 29 |  | 3 | 63 | 93 | 2020 | 2020 | R16
160292196034 | 161495196034 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-04-13 | 2020-06-23 | 2020-06-30 | 2020-11-13 | 2021-02-24 | Underground | R16 | 2020-11-13 | 52 | 6 | 99 | 74 | 228 | 2020 | 2021 | R16
166463194579 | 162484194579 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-17 | 2020-04-17 | 2020-06-17 | 2020-07-20 | 2020-07-22 | Underground | R16 | 2020-07-20 | 1 | 44 | 24 | 3 | 69 | 2020 | 2020 | R16
169978187592 | 162751187592 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-10 | 2020-01-10 | 2020-04-15 | 2020-07-20 | 2020-07-22 | Underground | R16 | 2020-07-20 | 1 | 69 | 69 | 3 | 139 | 2020 | 2020 | R16
163108190699 | 163881190699 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-27 | 2020-05-13 | 2020-05-13 | 2020-06-25 | 2020-07-09 | Overhead | R16 | 2020-06-25 | 13 |  | 32 | 11 | 54 | 2020 | 2020 | R16
161770183727 | 165298183727 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-10 | 2020-03-10 | 2020-03-10 | 2020-03-12 | 2020-07-01 | Overhead | R16 | 2020-03-12 | 1 |  | 3 | 80 | 82 | 2020 | 2020 | R16
162233184633 | 167074184633 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-19 | 2020-03-19 | 2020-03-19 | 2022-02-23 | 2022-03-23 | Overhead | R16 | 2022-02-23 | 1 |  | 505 | 21 | 525 | 2020 | 2022 | R16
162112179747 | 168656179747 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-07 | 2020-02-07 | 2020-02-07 | 2020-03-06 | 2020-06-09 | Overhead | R16 | 2020-03-06 | 1 |  | 21 | 68 | 88 | 2020 | 2020 | R16
162168189985 | 164215189985 | MOBILE HOMES PARK AB622 | ELEC SVC FOR MOBILE HOMES | Residential | 2020-04-28 | 2020-04-28 | 2020-05-05 |  | 2022-04-04 | Underground | R16 |  | 1 | 6 |  |  | 505 | 2020 | 2022 | R16
169127193242 | 160484193242 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-04 | 2020-06-04 | 2020-06-04 | 2020-06-05 | 2020-08-20 | Overhead | R16 | 2020-06-05 | 1 |  | 2 | 55 | 56 | 2020 | 2020 | R16
162762188930 | 163604188930 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-24 | 2020-04-24 | 2020-04-24 | 2020-09-14 | 2020-12-17 | Overhead | R16 | 2020-09-14 | 1 |  | 102 | 69 | 170 | 2020 | 2020 | R16
169481195504 | 164704195504 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-26 | 2020-06-26 | 2020-06-26 | 2020-08-14 | 2020-10-06 | Overhead | R16 | 2020-08-14 | 1 |  | 36 | 38 | 73 | 2020 | 2020 | R16
163203238112 | 160834238112 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-06-05 | 2020-10-23 | 2021-07-08 | 2021-08-10 | 2022-02-09 | Underground | R16 | 2021-08-10 | 101 | 185 | 24 | 132 | 439 | 2020 | 2022 | R16
168080184230 | 161983184230 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-08 | 2020-01-09 | 2020-03-16 | 2020-05-12 | 2020-05-13 | Underground | R16 | 2020-05-12 | 2 | 48 | 42 | 2 | 91 | 2020 | 2020 | R16
161929233880 | 164918233880 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-05-01 | 2020-05-01 | 2021-06-06 | 2023-05-16 | 2023-09-05 | Underground | R16 | 2023-05-16 | 1 | 286 | 507 | 81 | 873 | 2020 | 2023 | R16
166570182050 | 162438182050 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-26 | 2020-02-26 | 2020-02-26 | 2020-03-24 | 2020-06-09 | Overhead | R16 | 2020-03-24 | 1 |  | 20 | 56 | 75 | 2020 | 2020 | R16
164085191057 | 166028191057 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-12 | 2020-03-13 | 2020-05-14 | 2020-10-30 | 2020-10-30 | Underground | R16 | 2020-10-30 | 2 | 45 | 122 |  | 167 | 2020 | 2020 | R16
165551250594 | 168024250594 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-07-14 | 2021-10-06 | 2021-10-06 | 2022-07-14 | 2022-08-01 | Underground | R16 | 2022-07-14 | 322 |  | 202 | 13 | 535 | 2020 | 2022 | R16
168063186238 | 160030186238 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-03 | 2020-04-03 | 2020-04-03 | 2020-07-08 | 2020-10-06 | Overhead | R16 | 2020-07-08 | 1 |  | 69 | 65 | 133 | 2020 | 2020 | R16
168863211671 | 167150211671 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2020-07-10 | 2020-07-19 | 2020-11-24 | 2022-03-09 | 2022-04-01 | Underground | R16 | 2022-03-09 | 6 | 92 | 337 | 18 | 451 | 2020 | 2022 | R16
162597189622 | 164629189622 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential | 2020-04-29 | 2020-04-29 | 2020-04-30 | 2021-04-06 | 2021-04-01 | Underground | R16 | 2021-04-06 | 1 | 2 | 244 |  | 242 | 2020 | 2021 | R16
160791188087 | 162386188087 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-17 | 2020-04-17 | 2020-04-17 | 2020-04-30 | 2020-05-01 | Overhead | R16 | 2020-04-30 | 1 |  | 10 | 2 | 11 | 2020 | 2020 | R16
167885184583 | 166884184583 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-18 | 2020-03-18 | 2020-03-18 | 2020-07-20 | 2020-10-06 | Overhead | R16 | 2020-07-20 | 1 |  | 89 | 57 | 145 | 2020 | 2020 | R16
164593226138 | 164613226138 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-04-29 | 2020-04-29 | 2021-04-08 | 2022-08-31 | 2022-09-15 | Underground | R16 | 2022-08-31 | 1 | 247 | 365 | 12 | 622 | 2020 | 2022 | R16
164544185383 | 165576185383 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-11 | 2020-03-11 | 2020-03-25 | 2020-04-13 | 2020-06-24 | Underground | R16 | 2020-04-13 | 1 | 11 | 14 | 53 | 76 | 2020 | 2020 | R16
161089183825 | 164020183825 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-04 | 2020-03-11 | 2020-03-11 | 2020-05-05 | 2020-07-07 | Overhead | R16 | 2020-05-05 | 6 |  | 40 | 46 | 90 | 2020 | 2020 | R16
163743185525 | 168254185525 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-26 | 2020-03-26 | 2020-03-26 | 2020-06-08 | 2020-06-09 | Overhead | R16 | 2020-06-08 | 1 |  | 53 | 2 | 54 | 2020 | 2020 | R16
166709179299 | 162979179299 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-13 | 2020-01-13 | 2020-02-04 | 2020-09-22 | 2020-09-23 | Overhead | R16 | 2020-09-22 | 1 | 17 | 166 | 2 | 183 | 2020 | 2020 | R16
169465194183 | 162071194183 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-12 | 2020-06-12 | 2020-06-12 | 2020-06-15 | 2020-08-28 | Overhead | R16 | 2020-06-15 | 1 |  | 2 | 55 | 56 | 2020 | 2020 | R16
165048180374 | 169748180374 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-13 | 2020-02-13 | 2020-02-13 | 2020-03-13 | 2020-03-17 | Overhead | R16 | 2020-03-13 | 1 |  | 22 | 3 | 24 | 2020 | 2020 | R16
165374184100 | 165577184100 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-03-11 | 2020-03-11 | 2020-03-15 | 2020-12-28 | 2020-12-28 | Underground | R16 | 2020-12-28 | 1 | 3 | 206 |  | 209 | 2020 | 2020 | R16
167002225152 | 163155225152 | NON-RESIDENTIAL - SMALL RETAIL | R16 RESD AND NON RESD US | Commercial | 2020-06-18 | 2020-06-23 | 2021-03-29 | 2021-04-27 | 2021-06-25 | Underground | R16 | 2021-04-27 | 4 | 200 | 22 | 44 | 267 | 2020 | 2021 | R16
169168185250 | 167936185250 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2020-03-24 | 2020-03-24 | 2020-03-24 | 2021-10-22 | 2021-11-09 | Underground | R16 | 2021-10-22 | 1 |  | 414 | 13 | 426 | 2020 | 2021 | R16
168275186191 | 160036186191 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-03 | 2020-04-03 | 2020-04-03 | 2020-04-08 | 2020-06-16 | Overhead | R16 | 2020-04-08 | 1 |  | 4 | 50 | 53 | 2020 | 2020 | R16
162502182269 | 162575182269 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-01-10 | 2020-01-10 | 2020-02-27 | 2021-11-30 | 2021-12-01 | Underground | R16 | 2021-11-30 | 1 | 35 | 459 | 2 | 494 | 2020 | 2021 | R16
169686195017 | 160905195017 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-08 | 2020-06-23 | 2020-06-24 | 2020-06-24 | 2021-07-26 | Overhead | R16 | 2020-06-24 | 12 | 2 |  | 284 | 296 | 2020 | 2021 | R16
161816188008 | 167302188008 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-20 | 2020-04-17 | 2020-04-17 | 2020-05-24 | 2020-05-27 | Overhead | R16 | 2020-05-24 | 21 |  | 26 | 3 | 49 | 2020 | 2020 | R16
165864186735 | 160096186735 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-03 | 2020-04-08 | 2020-04-08 | 2020-05-23 | 2020-05-26 | Overhead | R16 | 2020-05-23 | 4 |  | 33 | 2 | 38 | 2020 | 2020 | R16
165629195297 | 160885195297 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-03 | 2020-01-03 | 2020-06-26 | 2020-09-04 | 2020-09-15 | Underground | R16 | 2020-09-04 | 1 | 126 | 51 | 8 | 183 | 2020 | 2020 | R16
160196200182 | 160084200182 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-02 | 2020-06-02 | 2020-08-10 |  | 2022-07-25 | Underground | R16 |  | 1 | 50 |  |  | 560 | 2020 | 2022 | R16
168096186381 | 163570186381 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-15 | 2020-01-15 | 2020-04-03 | 2020-06-16 | 2020-06-18 | Underground | R16 | 2020-06-16 | 1 | 58 | 53 | 3 | 112 | 2020 | 2020 | R16
169901191083 | 160276191083 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-04-06 | 2020-04-14 | 2020-05-14 | 2022-10-24 | 2022-10-25 | Underground | R16 | 2022-10-24 | 7 | 23 | 638 | 2 | 667 | 2020 | 2022 | R16
164117198117 | 167802198117 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-13 | 2020-07-22 | 2020-07-22 | 2020-07-30 | 2020-10-06 | Overhead | R16 | 2020-07-30 | 8 |  | 7 | 49 | 62 | 2020 | 2020 | R16
166346214523 | 166348214523 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-01-28 | 2020-01-28 | 2020-12-18 | 2021-05-21 | 2021-08-02 | Underground | R16 | 2021-05-21 | 1 | 234 | 111 | 52 | 395 | 2020 | 2021 | R16
160061189831 | 160719189831 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-08 | 2020-04-10 | 2020-05-04 | 2020-05-07 | 2021-07-08 | Overhead | R16 | 2020-05-07 | 3 | 17 | 4 | 306 | 327 | 2020 | 2021 | R16
169964190775 | 167822190775 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-03-24 | 2020-03-24 | 2020-05-12 | 2021-12-16 | 2021-12-17 | Underground | R16 | 2021-12-16 | 1 | 36 | 418 | 2 | 454 | 2020 | 2021 | R16
169495190675 | 166368190675 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-12 | 2020-05-12 | 2020-05-12 | 2020-05-27 | 2020-05-28 | Overhead | R16 | 2020-05-27 | 1 |  | 12 | 2 | 13 | 2020 | 2020 | R16
169525196153 | 160215196153 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-02 | 2020-06-02 | 2020-07-01 | 2020-08-19 | 2020-08-20 | Underground | R16 | 2020-08-19 | 1 | 22 | 36 | 2 | 58 | 2020 | 2020 | R16
160185179608 | 168412179608 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-06 | 2020-02-06 | 2020-02-06 | 2020-03-21 | 2020-05-19 | Overhead | R16 | 2020-03-21 | 1 |  | 32 | 42 | 74 | 2020 | 2020 | R16
162786196427 | 168922196427 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG R16 RESD AND NON RESD UD | Commercial | 2020-02-10 | 2020-06-19 | 2020-07-02 | 2020-07-31 | 2021-03-11 | Underground | R16 | 2020-07-31 | 95 | 10 | 22 | 160 | 284 | 2020 | 2021 | R16
162349184505 | 166799184505 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-03-17 | 2020-03-17 | 2020-03-17 | 2020-04-14 | 2020-04-15 | Underground | R16 | 2020-04-14 | 1 |  | 21 | 2 | 22 | 2020 | 2020 | R16
164463184862 | 166342184862 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-16 | 2020-03-19 | 2020-03-19 | 2020-04-10 | 2020-06-24 | Overhead | R16 | 2020-04-10 | 4 |  | 17 | 54 | 73 | 2020 | 2020 | R16
163846193997 | 168188193997 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-21 | 2020-05-21 | 2020-06-12 | 2020-09-15 | 2020-12-18 | Underground | R16 | 2020-09-15 | 1 | 17 | 68 | 69 | 152 | 2020 | 2020 | R16
160161179259 | 167915179259 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-04 | 2020-02-04 | 2020-02-04 | 2020-03-01 | 2020-03-02 | Overhead | R16 | 2020-03-01 | 1 |  | 19 | 1 | 20 | 2020 | 2020 | R16
166979192004 | 168825192004 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-27 | 2020-03-31 | 2020-05-22 | 2020-08-17 | 2020-08-17 | Underground | R16 | 2020-08-17 | 3 | 39 | 62 |  | 102 | 2020 | 2020 | R16
161925188320 | 162422188320 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-04-17 | 2020-04-20 | 2020-04-20 | 2020-07-15 | 2020-10-06 | Overhead | R16 | 2020-07-15 | 2 |  | 63 | 60 | 123 | 2020 | 2020 | R16
165762205055 | 166249205055 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OD | Residential | 2020-05-08 | 2020-05-28 | 2020-09-25 | 2020-10-08 | 2020-11-16 | Overhead | R16 | 2020-10-08 | 15 | 87 | 10 | 28 | 137 | 2020 | 2020 | R16
163194189161 | 163824189161 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2020-11-19 | 2021-07-13 | Overhead | R16 | 2020-11-19 | 1 |  | 149 | 169 | 317 | 2020 | 2021 | R16
164238178301 | 165927178301 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-27 | 2020-01-27 | 2020-01-27 | 2020-01-27 | 2020-03-09 | Overhead | R16 | 2020-01-27 | 1 |  |  | 31 | 31 | 2020 | 2020 | R16
167062222063 | 166914222063 | NON-RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Commercial | 2020-05-13 | 2020-05-14 | 2021-03-01 | 2021-09-30 | 2021-10-15 | Underground | R16 | 2021-09-30 | 2 | 208 | 154 | 12 | 373 | 2020 | 2021 | R16
165982202409 | 167924202409 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2020-02-04 | 2020-02-05 | 2020-08-31 | 2021-03-02 | 2021-05-06 | Underground | R16 | 2021-03-02 | 2 | 149 | 132 | 48 | 328 | 2020 | 2021 | R16
164084186864 | 160752186864 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-08 | 2020-04-08 | 2020-04-08 | 2020-04-16 | 2020-07-07 | Overhead | R16 | 2020-04-16 | 1 |  | 7 | 59 | 65 | 2020 | 2020 | R16
167153191782 | 168182191782 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-20 | 2020-05-20 | 2020-05-20 | 2020-06-28 | 2020-07-02 | Overhead | R16 | 2020-06-28 | 1 |  | 28 | 4 | 32 | 2020 | 2020 | R16
162785196257 | 165905196257 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-02 | 2020-07-02 | 2020-07-02 | 2021-03-17 | 2021-03-18 | Overhead | R16 | 2021-03-17 | 1 |  | 185 | 2 | 186 | 2020 | 2021 | R16
162072195482 | 164719195482 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-26 | 2020-06-26 | 2020-06-26 | 2020-06-30 | 2020-10-06 | Overhead | R16 | 2020-06-30 | 1 |  | 3 | 71 | 73 | 2020 | 2020 | R16
163388189135 | 163461189135 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-23 | 2020-04-23 | 2020-04-28 | 2020-04-28 | 2020-04-29 | Overhead | R16 | 2020-04-28 | 1 | 4 |  | 2 | 5 | 2020 | 2020 | R16
168529193402 | 160792193402 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-05 | 2020-06-05 | 2020-06-05 | 2020-09-15 | 2020-12-18 | Overhead | R16 | 2020-09-15 | 1 |  | 73 | 69 | 141 | 2020 | 2020 | R16
162585178825 | 166884178825 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-30 | 2020-01-30 | 2020-01-31 | 2022-04-12 | 2022-04-13 | Overhead | R16 | 2022-04-12 | 1 | 2 | 573 | 2 | 575 | 2020 | 2022 | R16
168057192513 | 168069192513 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-05-20 | 2020-05-20 | 2020-05-29 | 2020-06-09 | 2020-07-10 | Underground | R16 | 2020-06-09 | 1 | 8 | 8 | 24 | 38 | 2020 | 2020 | R16
160793196892 | 161227196892 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-09 | 2020-06-09 | 2020-07-10 | 2020-08-27 | 2020-08-27 | Underground | R16 | 2020-08-27 | 1 | 24 | 35 |  | 58 | 2020 | 2020 | R16
165723182144 | 162933182144 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-27 | 2020-02-27 | 2020-02-27 | 2020-02-27 | 2020-05-15 | Overhead | R16 | 2020-02-27 | 1 |  |  | 57 | 57 | 2020 | 2020 | R16
164638196645 | 166484196645 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-07 | 2020-07-07 | 2020-07-08 | 2020-07-27 | 2020-07-28 | Overhead | R16 | 2020-07-27 | 1 | 2 | 14 | 2 | 16 | 2020 | 2020 | R16
160235181984 | 162437181984 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-26 | 2020-02-26 | 2020-02-26 | 2020-04-02 | 2020-04-02 | Overhead | R16 | 2020-04-02 | 1 |  | 27 |  | 27 | 2020 | 2020 | R16
165253220563 | 169804220563 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-02 | 2020-04-02 | 2021-02-14 | 2021-08-02 | 2021-08-05 | Underground | R16 | 2021-08-02 | 1 | 227 | 121 | 4 | 351 | 2020 | 2021 | R16
164939177847 | 161779177847 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2020-01-07 | 2020-01-07 | 2020-01-23 | 2020-07-14 | 2020-07-15 | Underground | R16 | 2020-07-14 | 1 | 13 | 124 | 2 | 137 | 2020 | 2020 | R16
162450184259 | 169464184259 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-02-12 | 2020-03-03 | 2020-03-17 | 2020-05-21 | 2020-08-12 | Underground | R16 | 2020-05-21 | 15 | 11 | 48 | 60 | 131 | 2020 | 2020 | R16
168242212238 | 163014212238 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-04-21 | 2020-08-31 | 2020-11-30 | 2021-03-16 | 2021-04-07 | Underground | R16 | 2021-03-16 | 95 | 66 | 77 | 17 | 252 | 2020 | 2021 | R16
169358190669 | 166573190669 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-11 | 2020-05-11 | 2020-05-11 | 2020-07-20 | 2020-07-21 | Overhead | R16 | 2020-07-20 | 1 |  | 51 | 2 | 52 | 2020 | 2020 | R16
164396200181 | 165857200181 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-05-07 | 2020-06-03 | 2020-08-10 | 2020-08-27 | 2021-02-08 | Underground | R16 | 2020-08-27 | 20 | 49 | 14 | 118 | 198 | 2020 | 2021 | R16
169329182349 | 161184182349 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-20 | 2020-02-20 | 2020-02-28 | 2020-04-09 | 2020-07-08 | Underground | R16 | 2020-04-09 | 1 | 7 | 30 | 65 | 100 | 2020 | 2020 | R16
164129195047 | 162435195047 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-16 | 2020-06-17 | 2020-06-23 | 2020-07-06 | 2020-07-07 | Overhead | R16 | 2020-07-06 | 2 | 5 | 10 | 2 | 16 | 2020 | 2020 | R16
166216179084 | 166222179084 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-01-28 | 2020-01-28 | 2020-02-03 | 2021-01-19 | 2021-01-22 | Underground | R16 | 2021-01-19 | 1 | 5 | 252 | 4 | 259 | 2020 | 2021 | R16
162954255738 | 166219255738 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-07-07 | 2021-05-07 | 2021-11-09 | 2022-06-22 | 2023-01-27 | Underground | R16 | 2022-06-22 | 219 | 133 | 162 | 158 | 669 | 2020 | 2023 | R16
167268177996 | 165508177996 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-24 | 2020-01-24 | 2020-01-24 | 2020-03-01 | 2020-03-02 | Overhead | R16 | 2020-03-01 | 1 |  | 26 | 1 | 27 | 2020 | 2020 | R16
162761189529 | 164880189529 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-30 | 2020-04-30 | 2020-04-30 | 2020-08-03 | 2020-10-06 | Overhead | R16 | 2020-08-03 | 1 |  | 68 | 47 | 114 | 2020 | 2020 | R16
167563278490 | 165832278490 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-01-24 | 2020-04-23 | 2022-05-06 | 2022-08-10 | 2022-08-26 | Underground | R16 | 2022-08-10 | 65 | 532 | 69 | 13 | 676 | 2020 | 2022 | R16
168428191766 | 168348191766 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-21 | 2020-05-21 | 2020-05-21 | 2020-09-10 | 2020-12-17 | Overhead | R16 | 2020-09-10 | 1 |  | 81 | 71 | 151 | 2020 | 2020 | R16
161699177552 | 164870177552 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-21 | 2020-01-21 | 2020-01-21 | 2020-02-14 | 2020-06-09 | Overhead | R16 | 2020-02-14 | 1 |  | 19 | 83 | 101 | 2020 | 2020 | R16
160614194578 | 162839194578 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-17 | 2020-06-17 | 2020-06-17 | 2020-07-20 | 2020-10-06 | Overhead | R16 | 2020-07-20 | 1 |  | 24 | 57 | 80 | 2020 | 2020 | R16
165422187418 | 166037187418 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-13 | 2020-03-13 | 2020-04-14 | 2020-04-15 | 2020-07-07 | Underground | R16 | 2020-04-15 | 1 | 23 | 2 | 60 | 83 | 2020 | 2020 | R16
166645192175 | 163410192175 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2020-03-01 | 2020-03-01 | 2020-05-26 | 2020-05-27 | 2020-09-18 | Overhead | R16 | 2020-05-27 | 0 | 62 | 2 | 83 | 145 | 2020 | 2020 | R16
160614197851 | 162462197851 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-01-10 | 2020-07-21 | 2020-07-21 | 2020-07-22 | 2022-07-06 | Overhead | R16 | 2020-07-22 | 138 |  | 2 | 511 | 649 | 2020 | 2022 | R16
169498188628 | 163043188628 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-21 | 2020-04-21 | 2020-04-21 | 2020-06-02 | 2020-06-03 | Overhead | R16 | 2020-06-02 | 1 |  | 31 | 2 | 32 | 2020 | 2020 | R16
160727190112 | 162364190112 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-04-17 | 2020-04-21 | 2020-05-05 | 2020-05-05 | 2020-05-29 | Underground | R16 | 2020-05-05 | 3 | 11 |  | 19 | 31 | 2020 | 2020 | R16
161996182933 | 164452182933 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-05 | 2020-03-05 | 2020-03-05 | 2020-04-15 | 2020-04-16 | Overhead | R16 | 2020-04-15 | 1 |  | 30 | 2 | 31 | 2020 | 2020 | R16
169347194818 | 162959194818 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-18 | 2020-06-22 | 2020-06-22 | 2020-06-24 | 2020-07-07 | Overhead | R16 | 2020-06-24 | 3 |  | 3 | 10 | 14 | 2020 | 2020 | R16
160993183723 | 161792183723 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-21 | 2020-02-21 | 2020-03-10 | 2020-03-17 | 2020-06-23 | Underground | R16 | 2020-03-17 | 1 | 13 | 6 | 71 | 88 | 2020 | 2020 | R16
162900213492 | 165448213492 | NON-RESIDENTIAL - SMALL RETAIL | R16 RESD AND NON RESD US | Commercial | 2020-01-24 | 2020-04-28 | 2020-12-10 | 2021-11-24 | 2021-12-27 | Underground | R16 | 2021-11-24 | 68 | 163 | 250 | 24 | 502 | 2020 | 2021 | R16
168122193138 | 160579193138 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-04 | 2020-06-04 | 2020-06-04 | 2020-06-18 | 2020-06-18 | Overhead | R16 | 2020-06-18 | 1 |  | 11 |  | 11 | 2020 | 2020 | R16
168934193124 | 160245193124 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-06-03 | 2020-06-03 | 2020-06-03 | 2020-08-10 | 2020-10-06 | Underground | R16 | 2020-08-10 | 1 |  | 49 | 42 | 90 | 2020 | 2020 | R16
166265193290 | 162162193290 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-02-25 | 2020-02-25 | 2020-06-04 | 2021-04-30 | 2021-11-05 | Underground | R16 | 2021-04-30 | 1 | 73 | 237 | 136 | 444 | 2020 | 2021 | R16
160941253719 | 160777253719 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-02-18 | 2020-08-13 | 2021-10-26 | 2021-12-15 | 2022-01-05 | Underground | R16 | 2021-12-15 | 128 | 314 | 37 | 16 | 492 | 2020 | 2022 | R16
163840260380 | 164350260380 | NON-RESIDENTIAL - SMALL RETAIL | UG R16 RESD AND NON RESD UD | Commercial | 2020-06-25 | 2020-08-15 | 2021-12-08 | 2022-03-11 | 2022-04-01 | Underground | R16 | 2022-03-11 | 37 | 343 | 68 | 16 | 462 | 2020 | 2022 | R16
166292182151 | 163020182151 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-02-27 | 2020-02-27 | 2020-02-27 | 2020-05-05 | 2020-05-06 | Underground | R16 | 2020-05-05 | 1 |  | 49 | 2 | 50 | 2020 | 2020 | R16
164521191451 | 167670191451 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-18 | 2020-05-18 | 2020-05-18 | 2022-04-25 | 2022-04-26 | Overhead | R16 | 2022-04-25 | 1 |  | 506 | 2 | 507 | 2020 | 2022 | R16
167623193163 | 169960193163 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-31 | 2020-05-31 | 2020-06-03 | 2020-06-24 | 2020-10-06 | Overhead | R16 | 2020-06-24 | 0 | 3 | 16 | 75 | 92 | 2020 | 2020 | R16
168051186256 | 169868186256 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-02 | 2020-04-02 | 2020-04-02 | 2020-08-19 | 2021-08-16 | Overhead | R16 | 2020-08-19 | 1 |  | 100 | 259 | 358 | 2020 | 2021 | R16
165463200323 | 167994200323 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-14 | 2020-07-14 | 2020-08-11 | 2020-10-28 | 2021-07-26 | Underground | R16 | 2020-10-28 | 1 | 21 | 57 | 194 | 270 | 2020 | 2021 | R16
160199195273 | 164077195273 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-24 | 2020-06-24 | 2020-06-24 | 2020-06-25 | 2020-10-06 | Overhead | R16 | 2020-06-25 | 1 |  | 2 | 74 | 75 | 2020 | 2020 | R16
165236179003 | 167260179003 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-01 | 2020-02-01 | 2020-02-01 | 2021-04-05 | 2021-06-07 | Overhead | R16 | 2021-04-05 | 0 |  | 306 | 46 | 351 | 2020 | 2021 | R16
166431193032 | 160076193032 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-03 | 2020-06-03 | 2020-06-03 | 2020-10-22 | 2021-07-07 | Overhead | R16 | 2020-10-22 | 1 |  | 102 | 185 | 286 | 2020 | 2021 | R16
162783193587 | 164746193587 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-01-21 | 2020-01-29 | 2020-06-08 | 2020-09-22 | 2020-11-09 | Underground | R16 | 2020-09-22 | 7 | 94 | 77 | 35 | 210 | 2020 | 2020 | R16
168392192920 | 169911192920 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2020-11-04 | 2021-07-19 | Overhead | R16 | 2020-11-04 | 1 |  | 113 | 184 | 296 | 2020 | 2021 | R16
166859216179 | 162909216179 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-02-27 | 2020-02-27 | 2021-01-05 | 2021-01-25 | 2021-04-20 | Underground | R16 | 2021-01-25 | 1 | 224 | 15 | 62 | 299 | 2020 | 2021 | R16
164548185312 | 168173185312 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-25 | 2020-03-25 | 2020-03-25 | 2020-05-24 | 2020-05-27 | Overhead | R16 | 2020-05-24 | 1 |  | 43 | 3 | 46 | 2020 | 2020 | R16
164263175044 | 169792175044 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-12-20 | 2019-12-20 | 2019-12-20 | 2020-01-02 | 2020-01-08 | Underground | R16 | 2020-01-02 | 1 |  | 10 | 5 | 14 | 2019 | 2020 | R16
162201213252 | 166373213252 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-03-16 | 2020-03-17 | 2020-12-09 | 2021-04-13 | 2021-06-08 | Underground | R16 | 2021-04-13 | 2 | 192 | 90 | 41 | 322 | 2020 | 2021 | R16
169107190936 | 167115190936 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-05-14 | 2020-05-14 | 2020-05-14 | 2020-07-01 | 2020-10-06 | Underground | R16 | 2020-07-01 | 1 |  | 35 | 70 | 104 | 2020 | 2020 | R16
166447176111 | 160528176111 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-12-31 | 2019-12-31 | 2020-01-08 | 2020-03-06 | 2020-06-09 | Underground | R16 | 2020-03-06 | 1 | 7 | 43 | 68 | 116 | 2019 | 2020 | R16
169499212701 | 161861212701 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-01-07 | 2020-07-08 | 2020-12-03 | 2021-11-03 | 2021-11-12 | Underground | R16 | 2021-11-03 | 132 | 107 | 240 | 8 | 484 | 2020 | 2021 | R16
167782186506 | 169660186506 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-02-12 | 2020-02-12 | 2020-04-06 | 2020-08-06 | 2021-03-11 | Underground | R16 | 2020-08-06 | 1 | 39 | 89 | 156 | 282 | 2020 | 2021 | R16
167413220265 | 161929220265 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-04-15 | 2021-01-21 | 2021-02-10 | 2021-07-12 | 2022-01-07 | Overhead | R16 | 2021-07-12 | 202 | 15 | 109 | 130 | 453 | 2020 | 2022 | R16
162224194774 | 162191194774 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-15 | 2020-06-15 | 2020-06-22 | 2020-07-16 | 2023-10-04 | Overhead | R16 | 2020-07-16 | 1 | 6 | 19 | 840 | 863 | 2020 | 2023 | R16
162352240948 | 165839240948 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-03-12 | 2020-07-29 | 2021-07-27 | 2021-11-02 | 2021-11-02 | Underground | R16 | 2021-11-02 | 100 | 260 | 71 |  | 429 | 2020 | 2021 | R16
169133196088 | 163982196088 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2020-04-27 | 2020-06-16 | 2020-06-30 | 2021-06-30 | 2021-07-22 | Underground | R16 | 2021-06-30 | 37 | 11 | 262 | 17 | 324 | 2020 | 2021 | R16
167262196539 | 166530196539 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-07 | 2020-07-07 | 2020-07-07 | 2020-09-23 | 2020-09-24 | Overhead | R16 | 2020-09-23 | 1 |  | 57 | 2 | 58 | 2020 | 2020 | R16
168221212431 | 163377212431 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-06-19 | 2020-06-19 | 2020-12-02 | 2021-02-23 | 2021-04-01 | Underground | R16 | 2021-02-23 | 1 | 119 | 60 | 28 | 205 | 2020 | 2021 | R16
169635214087 | 164104214087 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-03-04 | 2020-03-30 | 2020-12-15 | 2021-03-19 | 2021-05-06 | Underground | R16 | 2021-03-19 | 19 | 187 | 69 | 35 | 307 | 2020 | 2021 | R16
165829247601 | 164581247601 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2020-03-06 | 2020-04-07 | 2021-09-13 | 2021-09-30 | 2021-10-20 | Overhead | R16 | 2021-09-30 | 23 | 375 | 14 | 15 | 424 | 2020 | 2021 | R16
161659183660 | 164813183660 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-09 | 2020-03-09 | 2020-03-10 | 2020-04-14 | 2020-07-01 | Overhead | R16 | 2020-04-14 | 1 | 2 | 26 | 57 | 83 | 2020 | 2020 | R16
162617193545 | 167286193545 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-20 | 2020-03-20 | 2020-06-08 | 2020-09-25 | 2021-11-08 | Overhead | R16 | 2020-09-25 | 1 | 57 | 80 | 292 | 427 | 2020 | 2021 | R16
163260228802 | 169738228802 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Commercial | 2020-04-02 | 2020-08-07 | 2022-06-17 | 2023-05-25 | 2023-07-25 | Underground | R16 | 2023-05-25 | 92 | 486 | 245 | 44 | 864 | 2020 | 2023 | R16
166128185431 | 168454185431 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-26 | 2020-03-26 | 2020-03-26 | 2020-04-14 | 2020-07-01 | Overhead | R16 | 2020-04-14 | 1 |  | 14 | 57 | 70 | 2020 | 2020 | R16
160762187517 | 161735187517 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-14 | 2020-04-15 | 2020-04-15 | 2020-07-09 | 2020-10-06 | Overhead | R16 | 2020-07-09 | 2 |  | 62 | 64 | 126 | 2020 | 2020 | R16
168467185207 | 161260185207 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-01-03 | 2020-01-03 | 2020-03-24 | 2021-06-09 | 2021-06-29 | Underground | R16 | 2021-06-09 | 1 | 58 | 317 | 15 | 388 | 2020 | 2021 | R16
169897194369 | 162407194369 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-16 | 2020-06-16 | 2020-06-16 | 2020-07-30 | 2020-10-06 | Overhead | R16 | 2020-07-30 | 1 |  | 33 | 49 | 81 | 2020 | 2020 | R16
162953194137 | 165663194137 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-06 | 2020-05-06 | 2020-06-12 | 2020-08-05 | 2020-08-07 | Overhead | R16 | 2020-08-05 | 1 | 28 | 39 | 3 | 68 | 2020 | 2020 | R16
166390197482 | 168283197482 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-15 | 2020-07-15 | 2020-07-15 | 2021-06-28 | 2021-06-29 | Overhead | R16 | 2021-06-28 | 1 |  | 249 | 2 | 250 | 2020 | 2021 | R16
163253193294 | 163361193294 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-03-01 | 2020-03-01 | 2020-06-04 | 2020-07-03 | 2020-07-06 | Underground | R16 | 2020-07-03 | 0 | 69 | 22 | 2 | 91 | 2020 | 2020 | R16
167219191898 | 168544191898 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-05-22 | 2020-05-22 | 2020-05-22 | 2020-06-10 | 2020-06-11 | Overhead | R16 | 2020-06-10 | 1 |  | 14 | 2 | 15 | 2020 | 2020 | R16
165064179288 | 167538179288 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-02-03 | 2020-02-03 | 2020-02-03 | 2020-03-13 | 2020-03-17 | Overhead | R16 | 2020-03-13 | 1 |  | 30 | 3 | 32 | 2020 | 2020 | R16
166250210595 | 169454210595 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OD | Residential | 2020-02-12 | 2020-02-26 | 2020-11-13 | 2021-09-21 | 2021-10-11 | Overhead | R16 | 2021-09-21 | 11 | 188 | 223 | 15 | 434 | 2020 | 2021 | R16
161529196244 | 163941196244 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-23 | 2020-06-30 | 2020-07-01 | 2020-07-20 | 2020-07-22 | Overhead | R16 | 2020-07-20 | 6 | 2 | 14 | 3 | 22 | 2020 | 2020 | R16
164036202126 | 165973202126 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2020-05-07 | 2020-05-08 | 2020-08-28 | 2021-09-15 | 2021-09-30 | Underground | R16 | 2021-09-15 | 2 | 81 | 274 | 12 | 366 | 2020 | 2021 | R16
161994195238 | 164740195238 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-06-26 | 2020-06-26 | 2020-06-26 | 2020-06-30 | 2020-10-06 | Overhead | R16 | 2020-06-30 | 1 |  | 3 | 71 | 73 | 2020 | 2020 | R16
168134186477 | 160553186477 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-07 | 2020-04-07 | 2020-04-08 | 2022-05-10 | 2022-06-03 | Overhead | R16 | 2022-05-10 | 1 | 2 | 545 | 19 | 564 | 2020 | 2022 | R16
163420182099 | 162886182099 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-02-27 | 2020-02-27 | 2020-02-27 | 2020-11-03 | 2021-07-23 | Overhead | R16 | 2020-11-03 | 1 |  | 179 | 189 | 367 | 2020 | 2021 | R16
163050183962 | 165945183962 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-03-12 | 2020-03-12 | 2020-03-12 | 2020-05-06 | 2020-05-20 | Overhead | R16 | 2020-05-06 | 1 |  | 40 | 11 | 50 | 2020 | 2020 | R16
166005160978 | 166261160978 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-26 | 2019-06-26 | 2019-08-13 | 2019-09-11 | 2019-09-12 | Underground | R16 | 2019-09-11 | 1 | 35 | 22 | 2 | 57 | 2019 | 2019 | R16
168844171155 | 162109171155 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-08 | 2019-11-08 | 2019-11-08 | 2020-02-05 | 2023-06-08 | Overhead | R16 | 2020-02-05 | 1 |  | 64 | 872 | 935 | 2019 | 2023 | R16
160969167581 | 161331167581 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-16 | 2019-09-16 | 2019-10-09 | 2020-02-04 | 2020-02-06 | Underground | R16 | 2020-02-04 | 1 | 18 | 85 | 3 | 104 | 2019 | 2020 | R16
161362174592 | 165132174592 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-07 | 2019-10-07 | 2019-12-17 | 2020-01-14 | 2020-01-14 | Underground | R16 | 2020-01-14 | 1 | 52 | 21 |  | 72 | 2019 | 2020 | R16
163498319398 | 160263319398 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2022-10-28 | 2022-10-28 | 2023-05-18 | 2023-07-27 | 2023-09-27 | Overhead | R16 | 2023-07-27 | 1 | 145 | 51 | 45 | 239 | 2022 | 2023 | R16
163372162430 | 165402162430 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-14 | 2019-08-22 | 2019-08-27 | 2019-08-29 | 2023-06-07 | Overhead | R16 | 2019-08-29 | 7 | 4 | 3 | 985 | 996 | 2019 | 2023 | R16
165328172078 | 168406172078 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-08 | 2019-10-14 | 2019-11-18 | 2020-04-03 | 2023-06-07 | Underground | R16 | 2020-04-03 | 71 | 26 | 100 | 829 | 1023 | 2019 | 2023 | R16
165241155064 | 163422155064 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-11 | 2019-06-11 | 2019-06-11 | 2019-08-06 | 2019-08-07 | Overhead | R16 | 2019-08-06 | 1 |  | 41 | 2 | 42 | 2019 | 2019 | R16
163882173737 | 165156173737 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-25 | 2019-11-25 | 2019-12-09 | 2020-01-10 | 2021-11-10 | Underground | R16 | 2020-01-10 | 1 | 11 | 25 | 479 | 513 | 2019 | 2021 | R16
166673156641 | 166567156641 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-10-28 | 2019-10-29 | Underground | R16 | 2019-10-28 | 1 |  | 87 | 2 | 88 | 2019 | 2019 | R16
165105174746 | 165715174746 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-12-03 | 2019-12-03 | 2019-12-18 | 2020-02-21 | 2020-12-18 | Underground | R16 | 2020-02-21 | 1 | 12 | 48 | 216 | 274 | 2019 | 2020 | R16
164035175015 | 165307175015 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-11-26 | 2019-12-20 | 2019-12-23 | 2020-01-14 | 2020-04-21 | Underground | R16 | 2020-01-14 | 19 | 2 | 17 | 71 | 106 | 2019 | 2020 | R16
165776157455 | 169299157455 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-10 | 2019-07-10 | 2019-07-10 | 2019-08-28 | 2019-11-25 | Overhead | R16 | 2019-08-28 | 1 |  | 36 | 64 | 99 | 2019 | 2019 | R16
169170200646 | 164507200646 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-11-21 | 2019-11-21 | 2020-08-14 | 2020-08-26 | 2021-02-16 | Overhead | R16 | 2020-08-26 | 1 | 192 | 9 | 125 | 324 | 2019 | 2021 | R16
164802169084 | 167885169084 | INDUSTRIAL | OH R16 RES NON RES OS | Commercial | 2019-10-19 | 2019-10-19 | 2019-10-21 | 2020-01-06 | 2020-11-18 | Overhead | R16 | 2020-01-06 | 0 | 1 | 56 | 228 | 283 | 2019 | 2020 | R16
162067182977 | 163832182977 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-19 | 2019-12-19 | 2020-03-05 | 2020-05-27 | 2023-06-07 | Underground | R16 | 2020-05-27 | 23 | 56 | 60 | 791 | 927 | 2019 | 2023 | R16
166046168252 | 165090168252 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-08-12 | 2019-08-12 | 2019-10-15 | 2020-01-21 | 2020-04-21 | Underground | R16 | 2020-01-21 | 1 | 47 | 71 | 66 | 182 | 2019 | 2020 | R16
162679172582 | 162809172582 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-12 | 2019-11-12 | 2019-11-21 | 2020-01-14 | 2020-01-17 | Underground | R16 | 2020-01-14 | 1 | 8 | 39 | 4 | 49 | 2019 | 2020 | R16
166879168124 | 160748168124 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Commercial | 2019-09-12 | 2019-09-24 | 2019-10-14 | 2019-10-15 | 2020-05-05 | Overhead | R16 | 2019-10-15 | 9 | 15 | 2 | 146 | 169 | 2019 | 2020 | R16
163043176853 | 163821176853 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-05 | 2019-08-05 | 2020-01-14 | 2020-04-15 | 2020-04-17 | Underground | R16 | 2020-04-15 | 1 | 117 | 67 | 3 | 185 | 2019 | 2020 | R16
163115162521 | 167617162521 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-27 | 2019-08-27 | 2019-08-27 | 2019-09-09 | 2019-10-16 | Overhead | R16 | 2019-09-09 | 1 |  | 10 | 28 | 37 | 2019 | 2019 | R16
165325166499 | 164029166499 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-10-02 | 2019-10-02 | 2019-10-02 | 2019-10-17 | 2019-10-18 | Overhead | R16 | 2019-10-17 | 1 |  | 12 | 2 | 13 | 2019 | 2019 | R16
163510174026 | 163521174026 | NON-RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Residential Subdivision | 2019-06-12 | 2019-06-12 | 2019-12-10 | 2020-08-07 | 2020-11-06 | Underground | R16 | 2020-08-07 | 1 | 130 | 174 | 66 | 368 | 2019 | 2020 | R16
167952170084 | 163068170084 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-26 | 2019-09-26 | 2019-10-29 | 2019-11-29 | 2019-12-02 | Underground | R16 | 2019-11-29 | 1 | 24 | 24 | 2 | 48 | 2019 | 2019 | R16
164883172900 | 169715172900 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-10-28 | 2019-11-12 | 2019-11-25 | 2019-11-25 | 2020-02-05 | Overhead | R16 | 2019-11-25 | 12 | 10 |  | 53 | 73 | 2019 | 2020 | R16
161221284049 | 163153284049 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-10-18 | 2021-10-18 | 2022-06-28 | 2023-09-15 | 2023-10-10 | Underground | R16 | 2023-09-15 | 1 | 182 | 319 | 18 | 517 | 2021 | 2023 | R16
166430166775 | 168353166775 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-29 | 2019-08-29 | 2019-10-03 | 2019-10-30 | 2019-11-05 | Underground | R16 | 2019-10-30 | 1 | 26 | 20 | 5 | 49 | 2019 | 2019 | R16
162257176426 | 164072176426 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-08-06 | 2019-08-06 | 2020-01-09 | 2021-06-25 | 2021-12-09 | Underground | R16 | 2021-06-25 | 1 | 113 | 382 | 120 | 613 | 2019 | 2021 | R16
169179155364 | 164159155364 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-15 | 2019-06-15 | 2019-06-15 | 2019-07-17 | 2019-11-14 | Overhead | R16 | 2019-07-17 | 0 |  | 23 | 87 | 109 | 2019 | 2019 | R16
163753168490 | 167379168490 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-18 | 2019-10-18 | 2019-10-18 | 2019-11-01 | 2021-11-13 | Overhead | R16 | 2019-11-01 | 1 |  | 11 | 531 | 541 | 2019 | 2021 | R16
166209161593 | 169970161593 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-15 | 2019-07-15 | 2019-08-19 | 2019-09-18 | 2019-09-19 | Underground | R16 | 2019-09-18 | 1 | 26 | 23 | 2 | 49 | 2019 | 2019 | R16
168620175593 | 164480175593 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-11-21 | 2019-11-21 | 2020-01-02 | 2020-04-16 | 2020-09-30 | Underground | R16 | 2020-04-16 | 1 | 31 | 76 | 120 | 225 | 2019 | 2020 | R16
161266162335 | 161308162335 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-07-23 | 2019-07-23 | 2019-08-27 | 2019-09-05 | 2019-12-04 | Underground | R16 | 2019-09-05 | 1 | 26 | 8 | 65 | 97 | 2019 | 2019 | R16
163788173049 | 165792173049 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-09 | 2019-10-29 | 2019-11-27 | 2020-02-13 | 2023-06-07 | Underground | R16 | 2020-02-13 | 15 | 22 | 57 | 865 | 956 | 2019 | 2023 | R16
166583170591 | 161211170591 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-04 | 2019-11-04 | 2019-11-04 | 2019-12-13 | 2019-12-17 | Overhead | R16 | 2019-12-13 | 1 |  | 30 | 3 | 32 | 2019 | 2019 | R16
160735168816 | 162519168816 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-23 | 2019-09-23 | 2019-10-19 | 2020-01-23 | 2021-11-10 | Underground | R16 | 2020-01-23 | 1 | 20 | 69 | 470 | 558 | 2019 | 2021 | R16
163744158279 | 166100158279 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-06-25 | 2019-06-25 | 2019-07-19 | 2019-08-22 | 2019-08-28 | Underground | R16 | 2019-08-22 | 1 | 19 | 25 | 5 | 47 | 2019 | 2019 | R16
169569165876 | 163175165876 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-26 | 2019-09-26 | 2019-09-26 | 2019-10-04 | 2019-10-16 | Overhead | R16 | 2019-10-04 | 1 |  | 7 | 9 | 15 | 2019 | 2019 | R16
162950172618 | 164619172618 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-22 | 2019-11-22 | 2019-11-22 | 2020-02-10 | 2020-06-09 | Overhead | R16 | 2020-02-10 | 1 |  | 57 | 87 | 143 | 2019 | 2020 | R16
160529164023 | 161764164023 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-24 | 2019-07-24 | 2019-09-10 |  | 2023-06-07 | Underground | R16 |  | 1 | 35 |  |  | 1011 | 2019 | 2023 | R16
160733191914 | 164540191914 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-10-03 | 2019-10-03 | 2020-05-22 | 2020-10-01 | 2021-01-14 | Underground | R16 | 2020-10-01 | 1 | 167 | 95 | 76 | 336 | 2019 | 2021 | R16
162207159642 | 162950159642 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-30 | 2019-07-30 | 2019-07-30 | 2019-08-05 | 2019-08-16 | Overhead | R16 | 2019-08-05 | 1 |  | 5 | 10 | 14 | 2019 | 2019 | R16
167715193631 | 167811193631 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2019-12-11 | 2020-04-15 | 2020-06-09 | 2021-03-09 | 2021-03-18 | Underground | R16 | 2021-03-09 | 91 | 40 | 196 | 8 | 332 | 2019 | 2021 | R16
162255161855 | 166507161855 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-20 | 2019-08-22 | 2019-08-22 | 2019-11-15 | 2019-11-26 | Overhead | R16 | 2019-11-15 | 3 |  | 62 | 8 | 71 | 2019 | 2019 | R16
168401169898 | 160026169898 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-29 | 2019-10-29 | 2019-10-29 | 2020-01-03 | 2020-01-17 | Overhead | R16 | 2020-01-03 | 1 |  | 49 | 11 | 59 | 2019 | 2020 | R16
162981168044 | 162934168044 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-25 | 2019-09-25 | 2019-10-13 | 2022-11-17 | 2022-11-18 | Underground | R16 | 2022-11-17 | 1 | 13 | 809 | 2 | 823 | 2019 | 2022 | R16
166763165972 | 169012165972 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-03 | 2019-09-03 | 2019-09-26 | 2021-01-20 | 2021-01-21 | Underground | R16 | 2021-01-20 | 1 | 18 | 345 | 2 | 363 | 2019 | 2021 | R16
166690158936 | 160119158936 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-15 | 2019-07-18 | 2019-07-25 | 2019-12-11 | 2019-12-12 | Underground | R16 | 2019-12-11 | 4 | 6 | 100 | 2 | 109 | 2019 | 2019 | R16
167878170382 | 160527170382 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-31 | 2019-10-31 | 2019-10-31 | 2020-03-03 | 2020-06-09 | Underground | R16 | 2020-03-03 | 1 |  | 89 | 71 | 159 | 2019 | 2020 | R16
169471158918 | 163404158918 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-06-11 | 2019-06-11 | 2019-07-25 | 2020-01-09 | 2021-11-11 | Underground | R16 | 2020-01-09 | 1 | 33 | 121 | 481 | 633 | 2019 | 2021 | R16
169289162833 | 168654162833 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-30 | 2019-08-30 | 2019-08-30 |  | 2022-10-19 | Overhead | R16 |  | 1 |  |  |  | 819 | 2019 | 2022 | R16
162380179552 | 160085179552 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-09-10 | 2019-09-10 | 2020-02-06 | 2021-07-21 | 2023-11-17 | Underground | R16 | 2021-07-21 | 1 | 108 | 380 | 608 | 1094 | 2019 | 2023 | R16
166814164886 | 168995164886 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-04 | 2019-09-17 | 2019-09-17 | 2019-09-18 | 2019-11-26 | Overhead | R16 | 2019-09-18 | 10 |  | 2 | 50 | 60 | 2019 | 2019 | R16
161101155963 | 165442155963 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-06-20 | 2019-06-20 | 2019-06-20 | 2019-07-17 | 2019-07-18 | Overhead | R16 | 2019-07-17 | 1 |  | 20 | 2 | 21 | 2019 | 2019 | R16
161816167941 | 166449167941 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-11 | 2019-10-11 | 2019-10-11 | 2019-12-26 | 2020-02-19 | Overhead | R16 | 2019-12-26 | 1 |  | 55 | 40 | 94 | 2019 | 2020 | R16
165030290434 | 165507290434 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-14 | 2019-08-14 | 2022-08-29 | 2023-02-04 | 2023-02-07 | Underground | R16 | 2023-02-04 | 1 | 794 | 115 | 2 | 910 | 2019 | 2023 | R16
166882173563 | 165814173563 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-12-03 | 2019-12-04 | 2019-12-04 | 2020-01-13 | 2020-02-11 | Overhead | R16 | 2020-01-13 | 2 |  | 29 | 22 | 51 | 2019 | 2020 | R16
161948163154 | 163086163154 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-31 | 2019-07-31 | 2019-09-03 | 2019-10-22 | 2019-10-24 | Underground | R16 | 2019-10-22 | 1 | 25 | 36 | 3 | 62 | 2019 | 2019 | R16
162019169158 | 169060169158 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-24 | 2019-10-24 | 2019-10-24 | 2019-10-31 | 2020-06-09 | Overhead | R16 | 2019-10-31 | 1 |  | 6 | 159 | 164 | 2019 | 2020 | R16
167105175008 | 168108175008 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-13 | 2019-12-13 | 2019-12-20 | 2019-12-30 | 2020-02-19 | Underground | R16 | 2019-12-30 | 1 | 6 | 7 | 38 | 49 | 2019 | 2020 | R16
169615154997 | 163409154997 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-12 | 2019-06-12 | 2019-06-12 | 2019-10-02 | 2019-10-03 | Overhead | R16 | 2019-10-02 | 1 |  | 81 | 2 | 82 | 2019 | 2019 | R16
161081164348 | 160962164348 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-13 | 2019-09-13 | 2019-09-13 | 2019-12-19 | 2019-12-20 | Underground | R16 | 2019-12-19 | 1 |  | 70 | 2 | 71 | 2019 | 2019 | R16
165602162555 | 167872162555 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-28 | 2019-08-30 | 2019-08-30 | 2019-09-20 | 2019-12-09 | Overhead | R16 | 2019-09-20 | 3 |  | 16 | 57 | 74 | 2019 | 2019 | R16
161270167582 | 168800167582 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-03 | 2019-09-03 | 2019-10-09 | 2019-11-15 | 2019-11-18 | Underground | R16 | 2019-11-15 | 1 | 27 | 28 | 2 | 55 | 2019 | 2019 | R16
169458287169 | 165186287169 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2022-03-11 | 2022-03-11 | 2022-07-28 | 2022-08-02 | 2022-08-29 | Underground | R16 | 2022-08-02 | 1 | 100 | 4 | 20 | 122 | 2022 | 2022 | R16
167563293672 | 169985293672 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-10-29 | 2021-12-22 | 2022-09-14 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 562 | 191 | 82 |  | 833 | 2019 | 2023 | R16
165124171925 | 163250171925 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-14 | 2019-11-14 | 2019-11-14 | 2019-12-05 | 2019-12-06 | Overhead | R16 | 2019-12-05 | 1 |  | 16 | 2 | 17 | 2019 | 2019 | R16
166432316516 | 162317316516 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-07 | 2023-04-10 | 2023-04-21 | 2023-08-15 | 2023-10-24 | Underground | R16 | 2023-08-15 | 2 | 10 | 83 | 51 | 143 | 2023 | 2023 | R16
169043171981 | 160093171981 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-30 | 2019-11-15 | 2019-11-15 | 2020-04-03 | 2021-11-10 | Overhead | R16 | 2020-04-03 | 13 |  | 101 | 419 | 531 | 2019 | 2021 | R16
163650173021 | 165238173021 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-26 | 2019-11-26 | 2019-11-26 | 2020-01-22 | 2020-01-23 | Overhead | R16 | 2020-01-22 | 1 |  | 42 | 2 | 43 | 2019 | 2020 | R16
164945230460 | 165053230460 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-11-25 | 2019-11-25 | 2021-05-12 | 2022-10-20 | 2023-04-17 | Underground | R16 | 2022-10-20 | 1 | 383 | 377 | 128 | 886 | 2019 | 2023 | R16
163630313295 | 168057313295 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2023-03-22 | 2023-03-22 | 2023-03-22 |  | 2023-07-26 | Overhead | R16 | 2023-03-29 | 1 |  | 6 | 86 | 91 | 2023 | 2023 | R16
161488160918 | 162471160918 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-29 | 2019-07-29 | 2019-08-12 | 2019-09-26 | 2019-09-26 | Overhead | R16 | 2019-09-26 | 1 | 11 | 34 |  | 44 | 2019 | 2019 | R16
161833172209 | 163643172209 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-18 | 2019-11-18 | 2019-11-18 | 2019-11-19 | 2020-02-05 | Overhead | R16 | 2019-11-19 | 1 |  | 2 | 57 | 58 | 2019 | 2020 | R16
164089169856 | 169668169856 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2019-10-28 | 2019-10-28 | 2019-10-28 | 2021-08-10 | 2021-12-03 | Overhead | R16 | 2021-08-10 | 1 |  | 467 | 84 | 550 | 2019 | 2021 | R16
169995159672 | 161168159672 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-22 | 2019-07-22 | 2019-08-01 | 2019-10-04 | 2019-10-07 | Underground | R16 | 2019-10-04 | 1 | 9 | 47 | 2 | 56 | 2019 | 2019 | R16
168715175113 | 167257175113 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-11 | 2019-12-11 | 2019-12-23 | 2020-01-27 | 2020-01-28 | Overhead | R16 | 2020-01-27 | 1 | 9 | 26 | 2 | 35 | 2019 | 2020 | R16
166698156522 | 166372156522 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-06-26 | 2019-06-27 | 2019-06-27 | 2019-10-29 | 2019-10-30 | Overhead | R16 | 2019-10-29 | 2 |  | 89 | 2 | 91 | 2019 | 2019 | R16
161059184416 | 162623184416 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2019-09-24 | 2020-01-28 | 2020-03-17 | 2020-04-17 | 2020-07-13 | Overhead | R16 | 2020-04-17 | 91 | 36 | 24 | 62 | 210 | 2019 | 2020 | R16
161521157066 | 167962157066 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-03 | 2019-07-03 | 2019-07-03 | 2019-07-19 | 2019-07-23 | Overhead | R16 | 2019-07-19 | 1 |  | 13 | 3 | 15 | 2019 | 2019 | R16
165922181976 | 166581181976 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-06 | 2019-12-06 | 2020-02-26 | 2020-03-05 | 2020-03-30 | Underground | R16 | 2020-03-05 | 1 | 59 | 7 | 18 | 82 | 2019 | 2020 | R16
166257202621 | 161909202621 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-11-07 | 2019-11-21 | 2020-09-02 | 2021-06-22 | 2022-08-03 | Underground | R16 | 2021-06-22 | 11 | 205 | 210 | 292 | 715 | 2019 | 2022 | R16
164324174112 | 169942174112 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-29 | 2019-12-12 | 2019-12-12 | 2019-12-26 | 2020-01-08 | Underground | R16 | 2019-12-26 | 33 |  | 11 | 10 | 52 | 2019 | 2020 | R16
162224160611 | 164056160611 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-07 | 2019-08-09 | 2019-08-09 | 2019-08-09 | 2019-12-06 | Overhead | R16 | 2019-08-09 | 3 |  |  | 86 | 88 | 2019 | 2019 | R16
169913176971 | 167166176971 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-10-16 | 2019-10-26 | 2020-01-15 | 2020-01-17 | 2020-05-19 | Overhead | R16 | 2020-01-17 | 8 | 58 | 3 | 88 | 155 | 2019 | 2020 | R16
163816164038 | 168535164038 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-30 | 2019-08-30 | 2019-09-11 | 2020-05-27 | 2020-05-28 | Underground | R16 | 2020-05-27 | 1 | 9 | 186 | 2 | 195 | 2019 | 2020 | R16
161083176469 | 164165176469 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2019-10-02 | 2019-10-02 | 2020-01-10 | 2020-03-12 | 2020-11-10 | Overhead | R16 | 2020-03-12 | 1 | 73 | 45 | 174 | 290 | 2019 | 2020 | R16
161813174885 | 163672174885 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-09-30 | 2019-10-22 | 2019-12-19 | 2020-06-10 | 2020-08-14 | Overhead | R16 | 2020-06-10 | 17 | 43 | 125 | 48 | 230 | 2019 | 2020 | R16
169126164095 | 169321164095 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-05 | 2019-09-12 | 2019-09-12 | 2019-10-05 | 2020-03-31 | Overhead | R16 | 2019-10-05 | 6 |  | 17 | 127 | 149 | 2019 | 2020 | R16
162322178846 | 161861178846 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-07-25 | 2019-07-25 | 2020-01-31 | 2022-01-31 | 2022-03-02 | Underground | R16 | 2022-01-31 | 1 | 137 | 522 | 23 | 680 | 2019 | 2022 | R16
161493170576 | 163288170576 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-27 | 2019-11-05 | 2019-11-05 | 2019-11-20 | 2019-11-26 | Underground | R16 | 2019-11-20 | 28 |  | 12 | 5 | 43 | 2019 | 2019 | R16
168836199917 | 164332199917 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-11-20 | 2020-07-21 | 2020-08-10 | 2021-10-25 | 2021-11-16 | Underground | R16 | 2021-10-25 | 175 | 15 | 316 | 17 | 520 | 2019 | 2021 | R16
163412163167 | 168774163167 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-03 | 2019-09-03 | 2019-09-03 | 2019-10-03 | 2019-10-03 | Overhead | R16 | 2019-10-03 | 1 |  | 23 |  | 23 | 2019 | 2019 | R16
164630169103 | 165092169103 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-12 | 2019-08-12 | 2019-10-21 | 2019-12-09 | 2019-12-11 | Underground | R16 | 2019-12-09 | 1 | 51 | 36 | 3 | 88 | 2019 | 2019 | R16
164280281970 | 164291281970 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2019-06-16 | 2020-04-03 | 2022-06-08 | 2023-06-12 | 2023-07-21 | Underground | R16 | 2023-06-12 | 210 | 569 | 264 | 30 | 1070 | 2019 | 2023 | R16
161034168231 | 166937168231 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-10-15 | 2019-10-15 | 2019-10-15 | 2020-12-03 | 2021-11-11 | Underground | R16 | 2020-12-03 | 1 |  | 298 | 246 | 543 | 2019 | 2021 | R16
166738170908 | 167512170908 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-26 | 2019-08-26 | 2019-11-06 | 2020-01-21 | 2020-01-27 | Overhead | R16 | 2020-01-21 | 1 | 53 | 55 | 5 | 111 | 2019 | 2020 | R16
169263162575 | 167205162575 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-08-23 | 2019-08-23 | 2019-08-28 | 2021-04-13 | 2021-04-20 | Underground | R16 | 2021-04-13 | 1 | 4 | 425 | 6 | 433 | 2019 | 2021 | R16
169330294551 | 163067294551 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-22 | 2022-09-22 | 2022-09-22 |  | 2023-10-30 | Overhead | R16 | 2023-09-08 | 1 |  | 252 | 37 | 288 | 2022 | 2023 | R16
166491163530 | 166773163530 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-21 | 2019-08-21 | 2019-09-06 | 2019-10-15 | 2019-10-16 | Underground | R16 | 2019-10-15 | 1 | 13 | 28 | 2 | 41 | 2019 | 2019 | R16
167903155088 | 163591155088 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-12 | 2019-06-12 | 2019-06-12 | 2019-07-29 | 2019-07-30 | Overhead | R16 | 2019-07-29 | 1 |  | 34 | 2 | 35 | 2019 | 2019 | R16
164604174092 | 167082174092 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-10 | 2019-12-11 | 2019-12-11 | 2020-01-30 | 2020-02-03 | Overhead | R16 | 2020-01-30 | 2 |  | 37 | 3 | 40 | 2019 | 2020 | R16
165300173133 | 165591173133 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-02 | 2019-12-02 | 2019-12-02 | 2020-03-25 | 2020-05-27 | Overhead | R16 | 2020-03-25 | 1 |  | 83 | 46 | 128 | 2019 | 2020 | R16
161359172503 | 164355172503 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-11-20 | 2019-11-20 | 2019-11-21 | 2021-03-18 | 2021-03-19 | Underground | R16 | 2021-03-18 | 1 | 2 | 346 | 2 | 348 | 2019 | 2021 | R16
163080155897 | 165520155897 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-21 | 2019-06-21 | 2019-06-21 | 2019-07-30 | 2019-09-03 | Overhead | R16 | 2019-07-30 | 1 |  | 28 | 26 | 53 | 2019 | 2019 | R16
165730166828 | 164593166828 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-03 | 2019-10-03 | 2019-10-03 | 2020-03-01 | 2020-03-02 | Overhead | R16 | 2020-03-01 | 1 |  | 107 | 1 | 108 | 2019 | 2020 | R16
160760174097 | 162769174097 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-12 | 2019-11-13 | 2019-12-11 | 2020-02-21 | 2020-02-26 | Underground | R16 | 2020-02-21 | 2 | 21 | 53 | 4 | 77 | 2019 | 2020 | R16
168956172743 | 169025172743 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-09-04 | 2019-09-04 | 2019-11-22 | 2020-02-12 | 2020-03-06 | Underground | R16 | 2020-02-12 | 1 | 58 | 59 | 18 | 133 | 2019 | 2020 | R16
165884160460 | 164251160460 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-07 | 2019-08-07 | 2019-08-07 | 2019-09-04 | 2019-09-05 | Underground | R16 | 2019-09-04 | 1 |  | 21 | 2 | 22 | 2019 | 2019 | R16
161361166642 | 164147166642 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-02 | 2019-10-02 | 2019-10-02 | 2019-10-23 | 2019-10-24 | Overhead | R16 | 2019-10-23 | 1 |  | 16 | 2 | 17 | 2019 | 2019 | R16
162914162776 | 168442162776 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-30 | 2019-08-30 | 2019-08-30 | 2019-09-18 | 2019-09-18 | Overhead | R16 | 2019-09-18 | 1 |  | 14 |  | 14 | 2019 | 2019 | R16
165430170769 | 168494170769 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-22 | 2019-11-05 | 2019-11-05 | 2020-02-11 | 2021-11-08 | Overhead | R16 | 2020-02-11 | 11 |  | 71 | 455 | 535 | 2019 | 2021 | R16
164568164034 | 165377164034 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-14 | 2019-08-16 | 2019-09-10 | 2019-11-12 | 2019-12-09 | Underground | R16 | 2019-11-12 | 3 | 18 | 46 | 20 | 84 | 2019 | 2019 | R16
164145158841 | 161373158841 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-07-23 | 2019-07-23 | 2019-07-24 | 2020-04-21 | 2020-06-24 | Overhead | R16 | 2020-04-21 | 1 | 2 | 195 | 47 | 242 | 2019 | 2020 | R16
163828157259 | 168537157259 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-18 | 2019-07-23 | Overhead | R16 | 2019-07-18 | 1 |  | 9 | 4 | 12 | 2019 | 2019 | R16
169617161791 | 166610161791 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-20 | 2019-08-20 | 2019-08-20 | 2019-10-08 | 2019-10-09 | Overhead | R16 | 2019-10-08 | 1 |  | 36 | 2 | 37 | 2019 | 2019 | R16
162024168053 | 164319168053 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-02 | 2019-10-02 | 2019-10-15 | 2020-01-22 | 2021-11-10 | Underground | R16 | 2020-01-22 | 1 | 10 | 72 | 471 | 551 | 2019 | 2021 | R16
167451167206 | 168418167206 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-29 | 2019-09-03 | 2019-10-07 | 2019-11-21 | 2019-11-20 | Underground | R16 | 2019-11-21 | 4 | 25 | 34 |  | 60 | 2019 | 2019 | R16
168252320392 | 169817320392 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-15 | 2023-05-26 | 2023-05-26 | 2023-07-03 | 2023-07-27 | Overhead | R16 | 2023-07-03 | 10 |  | 27 | 19 | 54 | 2023 | 2023 | R16
167829168404 | 168291168404 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-05 | 2019-07-05 | 2019-10-16 | 2020-02-21 | 2021-05-19 | Underground | R16 | 2020-02-21 | 1 | 74 | 93 | 324 | 489 | 2019 | 2021 | R16
167317174989 | 167127174989 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-08-23 | 2019-10-26 | 2019-12-23 | 2020-03-02 | 2020-06-18 | Underground | R16 | 2020-03-02 | 46 | 41 | 51 | 79 | 215 | 2019 | 2020 | R16
168166173136 | 165356173136 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-12-02 | 2019-12-02 | 2019-12-02 | 2019-12-05 | 2019-12-06 | Overhead | R16 | 2019-12-05 | 1 |  | 4 | 2 | 5 | 2019 | 2019 | R16
165140160614 | 164629160614 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Commercial | 2019-08-09 | 2019-08-09 | 2019-08-09 | 2019-08-13 | 2020-01-08 | Overhead | R16 | 2019-08-13 | 1 |  | 3 | 107 | 109 | 2019 | 2020 | R16
160954163175 | 168909163175 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-03 | 2019-09-03 | 2019-09-03 | 2020-08-26 | 2020-08-28 | Overhead | R16 | 2020-08-26 | 1 |  | 257 | 3 | 259 | 2019 | 2020 | R16
169661163119 | 167711163119 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-08-27 | 2019-08-27 | 2019-09-05 | 2019-10-10 | 2020-02-05 | Overhead | R16 | 2019-10-10 | 1 | 8 | 26 | 85 | 117 | 2019 | 2020 | R16
160845172499 | 163510172499 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-16 | 2019-11-21 | 2019-11-21 | 2020-04-27 | 2020-07-02 | Overhead | R16 | 2020-04-27 | 4 |  | 113 | 49 | 164 | 2019 | 2020 | R16
165415163162 | 167013163162 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-23 | 2019-08-30 | 2019-09-03 | 2020-01-02 | 2021-11-13 | Overhead | R16 | 2020-01-02 | 6 | 3 | 88 | 487 | 581 | 2019 | 2021 | R16
160530169938 | 168970169938 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-03 | 2019-09-03 | 2019-10-29 | 2020-02-18 | 2020-02-19 | Underground | R16 | 2020-02-18 | 1 | 41 | 81 | 2 | 122 | 2019 | 2020 | R16
169735180780 | 165152180780 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-11-25 | 2019-11-25 | 2020-02-14 | 2020-12-21 | 2021-01-21 | Underground | R16 | 2020-12-21 | 1 | 60 | 222 | 24 | 304 | 2019 | 2021 | R16
169232169142 | 169853169142 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-09 | 2019-09-09 | 2019-10-21 | 2019-10-24 | 2019-11-05 | Overhead | R16 | 2019-10-24 | 1 | 31 | 4 | 9 | 42 | 2019 | 2019 | R16
169563165868 | 160273165868 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-09-10 | 2019-09-24 | 2019-09-26 | 2019-10-24 | 2020-04-27 | Underground | R16 | 2019-10-24 | 11 | 3 | 21 | 133 | 165 | 2019 | 2020 | R16
166639176102 | 161775176102 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-11-07 | 2019-11-07 | 2020-01-07 | 2022-01-26 | 2022-03-04 | Underground | R16 | 2022-01-26 | 1 | 44 | 537 | 28 | 607 | 2019 | 2022 | R16
168766159539 | 161814159539 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-24 | 2019-07-24 | 2019-07-31 | 2019-08-14 | 2019-08-14 | Underground | R16 | 2019-08-14 | 1 | 6 | 11 |  | 16 | 2019 | 2019 | R16
168849162613 | 168138162613 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-28 | 2019-08-28 | 2019-08-28 | 2019-10-29 | 2019-10-30 | Overhead | R16 | 2019-10-29 | 1 |  | 45 | 2 | 46 | 2019 | 2019 | R16
161091180049 | 161272180049 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-05 | 2019-11-05 | 2020-02-10 | 2020-03-17 | 2020-04-02 | Underground | R16 | 2020-03-17 | 1 | 70 | 27 | 13 | 108 | 2019 | 2020 | R16
167711156514 | 166575156514 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-27 | 2019-06-27 | 2019-06-27 | 2019-07-18 | 2019-07-18 | Overhead | R16 | 2019-07-18 | 1 |  | 16 |  | 16 | 2019 | 2019 | R16
162569155472 | 164912155472 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-18 | 2019-06-18 | 2019-06-18 | 2019-08-15 | 2019-08-28 | Overhead | R16 | 2019-08-15 | 1 |  | 43 | 10 | 52 | 2019 | 2019 | R16
169972162540 | 163006162540 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-01 | 2019-08-01 | 2019-08-27 | 2019-10-21 | 2019-10-30 | Underground | R16 | 2019-10-21 | 1 | 19 | 40 | 8 | 65 | 2019 | 2019 | R16
164248170925 | 169020170925 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-09-03 | 2019-10-02 | 2019-11-06 | 2022-05-05 | 2022-05-24 | Underground | R16 | 2022-05-05 | 22 | 26 | 652 | 14 | 711 | 2019 | 2022 | R16
169939164973 | 161303164973 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-22 | 2019-07-22 | 2019-09-19 | 2020-02-25 | 2020-02-26 | Underground | R16 | 2020-02-25 | 1 | 44 | 114 | 2 | 158 | 2019 | 2020 | R16
166320168596 | 163998168596 | RESIDENTIAL - SINGLE FAMILY DETACHED | ELEC OH MISC SVC OD | Commercial | 2019-10-01 | 2019-10-01 | 2019-10-18 | 2019-11-08 | 2021-04-05 | Overhead | R16 | 2019-11-08 | 1 | 14 | 16 | 367 | 395 | 2019 | 2021 | R16
160204160984 | 164992160984 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-12 | 2019-08-12 | 2019-08-12 | 2020-08-13 | 2020-08-21 | Overhead | R16 | 2020-08-13 | 1 |  | 264 | 7 | 270 | 2019 | 2020 | R16
163692225009 | 164744225009 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-08-09 | 2019-08-09 | 2021-03-29 | 2021-08-12 | 2021-09-14 | Underground | R16 | 2021-08-12 | 1 | 427 | 99 | 24 | 548 | 2019 | 2021 | R16
162347155473 | 164873155473 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-18 | 2019-06-18 | 2019-06-18 | 2019-07-30 | 2019-09-03 | Overhead | R16 | 2019-07-30 | 1 |  | 31 | 26 | 56 | 2019 | 2019 | R16
163091167694 | 169358167694 | NON-RESIDENTIAL - SMALL RETAIL | UG R16 RESD AND NON RESD UD | Commercial | 2019-07-11 | 2019-09-09 | 2019-10-10 | 2020-10-14 | 2021-11-12 | Underground | R16 | 2020-10-14 | 43 | 24 | 265 | 283 | 612 | 2019 | 2021 | R16
169555172885 | 164838172885 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-25 | 2019-11-25 | 2019-11-25 | 2020-01-02 | 2020-01-03 | Overhead | R16 | 2020-01-02 | 1 |  | 29 | 2 | 30 | 2019 | 2020 | R16
167814158545 | 161160158545 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-21 | 2019-07-21 | 2019-07-21 | 2022-12-08 | 2023-06-07 | Overhead | R16 | 2022-12-08 | 0 |  | 884 | 130 | 1013 | 2019 | 2023 | R16
165775157667 | 169415157667 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-12 | 2019-07-12 | 2019-07-12 | 2019-09-06 | 2019-09-19 | Overhead | R16 | 2019-09-06 | 1 |  | 41 | 10 | 50 | 2019 | 2019 | R16
163446156828 | 167655156828 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2019-10-20 | 2019-10-23 | Overhead | R16 | 2019-10-20 | 1 |  | 80 | 3 | 83 | 2019 | 2019 | R16
163807160328 | 164090160328 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-06 | 2019-08-06 | 2019-08-06 | 2019-09-04 | 2019-09-05 | Overhead | R16 | 2019-09-04 | 1 |  | 22 | 2 | 23 | 2019 | 2019 | R16
162344158046 | 163394158046 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-12 | 2019-06-12 | 2019-07-15 | 2019-08-16 | 2019-08-19 | Underground | R16 | 2019-08-16 | 1 | 24 | 25 | 2 | 49 | 2019 | 2019 | R16
169057160108 | 161473160108 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-23 | 2019-07-26 | 2019-08-05 | 2019-08-28 | 2019-09-04 | Underground | R16 | 2019-08-28 | 4 | 7 | 18 | 6 | 32 | 2019 | 2019 | R16
169517156928 | 167661156928 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2019-08-01 | 2019-08-19 | Overhead | R16 | 2019-08-01 | 1 |  | 24 | 13 | 36 | 2019 | 2019 | R16
164394159018 | 167620159018 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-01 | 2019-07-22 | 2019-07-26 | 2019-09-25 | 2019-10-09 | Overhead | R16 | 2019-09-25 | 16 | 5 | 44 | 11 | 73 | 2019 | 2019 | R16
160709181893 | 162805181893 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-12 | 2019-11-13 | 2020-02-26 | 2020-05-27 | 2020-05-29 | Underground | R16 | 2020-05-27 | 2 | 76 | 66 | 3 | 144 | 2019 | 2020 | R16
164067162746 | 165800162746 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-24 | 2019-08-29 | 2019-08-29 | 2019-09-18 | 2019-10-30 | Overhead | R16 | 2019-09-18 | 49 |  | 15 | 31 | 93 | 2019 | 2019 | R16
164490162122 | 167207162122 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-23 | 2019-08-23 | 2019-08-23 | 2019-12-11 | 2021-11-13 | Overhead | R16 | 2019-12-11 | 1 |  | 79 | 503 | 581 | 2019 | 2021 | R16
161468156527 | 163318156527 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-11 | 2019-06-27 | 2019-06-27 | 2019-08-20 | 2019-08-28 | Overhead | R16 | 2019-08-20 | 13 |  | 39 | 7 | 57 | 2019 | 2019 | R16
165992207250 | 160322207250 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-07-16 | 2019-10-30 | 2019-11-15 | 2021-01-07 | 2021-04-01 | Underground | R16 | 2021-01-07 | 77 | 13 | 300 | 61 | 448 | 2019 | 2021 | R16
161176170921 | 165129170921 | INDUSTRIAL | R16 RESD AND NON RESD US | Commercial | 2019-08-12 | 2019-08-22 | 2019-11-06 | 2020-05-28 | 2020-09-01 | Underground | R16 | 2020-05-28 | 9 | 55 | 147 | 69 | 277 | 2019 | 2020 | R16
162368172679 | 164923172679 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-25 | 2019-11-25 | 2019-11-25 | 2019-11-26 | 2020-06-09 | Overhead | R16 | 2019-11-26 | 1 |  | 2 | 141 | 142 | 2019 | 2020 | R16
161814157324 | 163251157324 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-06-10 | 2019-06-10 | 2019-07-08 | 2020-09-18 | 2020-12-18 | Underground | R16 | 2020-09-18 | 1 | 21 | 315 | 66 | 400 | 2019 | 2020 | R16
162423164560 | 169950164560 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-09 | 2019-09-09 | 2019-09-15 | 2019-12-27 | 2019-12-30 | Overhead | R16 | 2019-12-27 | 1 | 5 | 75 | 2 | 81 | 2019 | 2019 | R16
169049173401 | 165519173401 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-02 | 2019-12-02 | 2019-12-02 | 2020-01-22 | 2020-01-23 | Overhead | R16 | 2020-01-22 | 1 |  | 38 | 2 | 39 | 2019 | 2020 | R16
169109166032 | 163504166032 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-28 | 2019-09-28 | 2019-09-28 | 2019-10-23 | 2019-10-24 | Overhead | R16 | 2019-10-23 | 0 |  | 18 | 2 | 19 | 2019 | 2019 | R16
165551176099 | 165930176099 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-12-03 | 2019-12-03 | 2020-01-09 | 2021-01-08 | 2021-01-11 | Underground | R16 | 2021-01-08 | 1 | 28 | 262 | 2 | 290 | 2019 | 2021 | R16
160161196016 | 160154196016 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2019-10-30 | 2020-02-21 | 2020-06-30 | 2022-05-23 | 2023-01-18 | Underground | R16 | 2022-05-23 | 83 | 93 | 495 | 173 | 841 | 2019 | 2023 | R16
169216171086 | 161983171086 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-07 | 2019-11-07 | 2019-11-07 | 2019-12-13 | 2019-12-17 | Overhead | R16 | 2019-12-13 | 1 |  | 27 | 3 | 29 | 2019 | 2019 | R16
160730156471 | 166332156471 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2019-06-26 | 2019-06-26 | 2019-06-26 | 2019-08-20 | 2021-04-05 | Overhead | R16 | 2019-08-20 | 1 |  | 40 | 425 | 464 | 2019 | 2021 | R16
163867163089 | 165892163089 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-16 | 2019-09-04 | 2019-09-04 | 2019-09-09 | 2019-11-21 | Overhead | R16 | 2019-09-09 | 14 |  | 4 | 54 | 70 | 2019 | 2019 | R16
163770163274 | 164330163274 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-07 | 2019-08-07 | 2019-09-04 | 2019-11-21 | 2019-11-19 | Underground | R16 | 2019-11-21 | 1 | 21 | 57 |  | 75 | 2019 | 2019 | R16
167981172692 | 164566172692 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-03 | 2019-10-03 | 2019-11-22 | 2020-02-24 | 2020-06-09 | Overhead | R16 | 2020-02-24 | 1 | 37 | 67 | 77 | 179 | 2019 | 2020 | R16
168792172742 | 169848172742 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-29 | 2019-10-31 | 2019-11-22 | 2020-01-28 | 2020-01-29 | Underground | R16 | 2020-01-28 | 3 | 17 | 48 | 2 | 67 | 2019 | 2020 | R16
168793201246 | 166845201246 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-10-14 | 2020-01-26 | 2020-08-20 | 2021-10-13 | 2021-10-28 | Underground | R16 | 2021-10-13 | 75 | 149 | 300 | 12 | 534 | 2019 | 2021 | R16
165150328074 | 161044328074 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-03 | 2023-04-03 | 2023-08-12 |  | 2023-10-24 | Underground | R16 | 2023-09-22 | 1 | 95 | 30 | 23 | 147 | 2023 | 2023 | R16
168725189938 | 169750189938 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-10-28 | 2020-01-24 | 2020-05-05 | 2020-09-10 | 2021-02-16 | Underground | R16 | 2020-09-10 | 65 | 73 | 93 | 114 | 342 | 2019 | 2021 | R16
169803155367 | 164221155367 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-15 | 2019-06-15 | 2019-06-15 | 2019-07-29 | 2019-08-26 | Overhead | R16 | 2019-07-29 | 0 |  | 31 | 21 | 51 | 2019 | 2019 | R16
167797172841 | 160219172841 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH CP R16 WORK RELO TO UG | Residential | 2019-10-30 | 2019-10-30 | 2019-11-22 | 2020-04-14 | 2020-07-29 | Overhead | R16 | 2020-04-14 | 1 | 18 | 103 | 77 | 196 | 2019 | 2020 | R16
160075186571 | 167334186571 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-08-26 | 2019-08-26 | 2020-04-06 | 2023-02-09 | 2023-02-22 | Underground | R16 | 2023-02-09 | 1 | 161 | 744 | 10 | 913 | 2019 | 2023 | R16
169676170713 | 161163170713 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-16 | 2019-09-16 | 2019-11-05 | 2020-02-20 | 2020-02-21 | Underground | R16 | 2020-02-20 | 1 | 37 | 78 | 2 | 115 | 2019 | 2020 | R16
161428168556 | 163207168556 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-27 | 2019-10-17 | 2019-10-17 | 2020-01-09 | 2021-11-10 | Overhead | R16 | 2020-01-09 | 15 |  | 61 | 480 | 554 | 2019 | 2021 | R16
163195168334 | 166390168334 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-10-10 | 2019-10-10 | 2019-10-16 | 2021-08-30 | 2021-10-25 | Underground | R16 | 2021-08-30 | 1 | 5 | 489 | 41 | 533 | 2019 | 2021 | R16
161855184658 | 162666184658 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-24 | 2019-09-24 | 2020-03-19 |  | 2021-10-29 | Underground | R16 |  | 1 | 128 |  |  | 549 | 2019 | 2021 | R16
169577156925 | 167576156925 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2019-07-23 | 2019-07-24 | Overhead | R16 | 2019-07-23 | 1 |  | 17 | 2 | 18 | 2019 | 2019 | R16
164977158860 | 161347158860 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-23 | 2019-07-23 | 2019-07-24 | 2019-09-09 | 2019-09-25 | Overhead | R16 | 2019-09-09 | 1 | 2 | 34 | 13 | 47 | 2019 | 2019 | R16
165781167502 | 162467167502 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-23 | 2019-09-23 | 2019-10-09 | 2019-12-20 | 2020-01-23 | Underground | R16 | 2019-12-20 | 1 | 13 | 53 | 25 | 89 | 2019 | 2020 | R16
164792165417 | 162740165417 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-24 | 2019-09-24 | 2019-09-24 | 2019-12-10 | 2020-01-02 | Overhead | R16 | 2019-12-10 | 1 |  | 56 | 18 | 73 | 2019 | 2020 | R16
160420157423 | 168976157423 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-09 | 2019-07-09 | 2019-07-09 | 2020-07-13 | 2020-10-06 | Overhead | R16 | 2020-07-13 | 1 |  | 265 | 62 | 326 | 2019 | 2020 | R16
169405164171 | 160886164171 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-13 | 2019-09-13 | 2019-09-13 | 2019-12-20 | 2019-12-30 | Underground | R16 | 2019-12-20 | 1 |  | 71 | 7 | 77 | 2019 | 2019 | R16
162162177195 | 163617177195 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-18 | 2019-11-18 | 2020-01-16 | 2020-03-17 | 2020-03-18 | Underground | R16 | 2020-03-17 | 1 | 44 | 44 | 2 | 88 | 2019 | 2020 | R16
169537174143 | 160750174143 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-01 | 2019-11-01 | 2019-12-10 |  | 2020-02-19 | Underground | R16 |  | 1 | 28 |  |  | 79 | 2019 | 2020 | R16
163067158474 | 161062158474 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-20 | 2019-07-20 | 2019-07-20 | 2019-09-09 | 2019-09-25 | Overhead | R16 | 2019-09-09 | 0 |  | 36 | 13 | 48 | 2019 | 2019 | R16
160982165854 | 163306165854 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-27 | 2019-09-27 | 2019-09-27 | 2020-01-22 | 2021-11-10 | Overhead | R16 | 2020-01-22 | 1 |  | 84 | 471 | 554 | 2019 | 2021 | R16
163365172896 | 165158172896 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-25 | 2019-11-25 | 2019-11-25 | 2020-03-03 | 2020-06-09 | Overhead | R16 | 2020-03-03 | 1 |  | 72 | 71 | 142 | 2019 | 2020 | R16
166866174215 | 168271174215 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-13 | 2019-12-13 | 2019-12-13 | 2020-04-22 | 2020-04-24 | Overhead | R16 | 2020-04-22 | 1 |  | 94 | 3 | 96 | 2019 | 2020 | R16
169064172235 | 161451172235 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-11-05 | 2019-11-05 | 2019-11-19 | 2019-11-19 | 2020-03-02 | Underground | R16 | 2019-11-19 | 1 | 11 |  | 75 | 85 | 2019 | 2020 | R16
169989164669 | 160606164669 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-09-12 | 2019-09-16 | 2019-09-16 | 2019-10-30 | 2019-11-05 | Underground | R16 | 2019-10-30 | 3 |  | 33 | 5 | 39 | 2019 | 2019 | R16
164854163870 | 160140163870 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-09 | 2019-09-09 | 2019-09-09 | 2019-11-19 | 2019-12-03 | Overhead | R16 | 2019-11-19 | 1 |  | 52 | 11 | 62 | 2019 | 2019 | R16
160777169106 | 168095169106 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-10-21 | 2019-10-21 | 2019-10-21 | 2023-10-02 | 2023-10-02 | Underground | R16 | 2023-10-02 | 1 |  | 1031 |  | 1031 | 2019 | 2023 | R16
167936165466 | 168167165466 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-29 | 2019-08-29 | 2019-09-23 | 2019-11-06 | 2019-11-07 | Underground | R16 | 2019-11-06 | 1 | 18 | 33 | 2 | 51 | 2019 | 2019 | R16
166125163970 | 166268163970 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-19 | 2019-08-19 | 2019-09-10 | 2019-11-06 | 2019-11-08 | Underground | R16 | 2019-11-06 | 1 | 17 | 42 | 3 | 60 | 2019 | 2019 | R16
166101160969 | 165197160969 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2019-08-13 | 2019-08-13 | 2019-08-13 | 2019-08-14 | 2021-10-04 | Overhead | R16 | 2019-08-14 | 1 |  | 2 | 559 | 560 | 2019 | 2021 | R16
163301210372 | 163116210372 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG R16 RESD AND NON RESD UD | Commercial | 2019-06-11 | 2019-06-11 | 2020-11-12 | 2021-03-09 | 2021-04-26 | Underground | R16 | 2021-03-09 | 1 | 373 | 84 | 35 | 490 | 2019 | 2021 | R16
166534173654 | 164497173654 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-08-08 | 2019-12-05 | 2019-12-05 | 2020-01-23 | 2021-10-21 | Overhead | R16 | 2020-01-23 | 86 |  | 36 | 456 | 576 | 2019 | 2021 | R16
167000169701 | 167379169701 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-26 | 2019-08-26 | 2019-10-25 | 2020-02-03 | 2020-02-05 | Underground | R16 | 2020-02-03 | 1 | 45 | 72 | 3 | 118 | 2019 | 2020 | R16
160979163414 | 169319163414 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-05 | 2019-09-05 | 2019-09-05 | 2019-09-24 | 2019-09-25 | Overhead | R16 | 2019-09-24 | 1 |  | 14 | 2 | 15 | 2019 | 2019 | R16
161717170654 | 166454170654 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-10-11 | 2019-10-11 | 2019-11-05 | 2020-11-18 | 2021-07-14 | Overhead | R16 | 2020-11-18 | 1 | 18 | 272 | 171 | 459 | 2019 | 2021 | R16
166694155198 | 164061155198 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-14 | 2019-06-14 | 2019-06-14 | 2019-11-05 | 2019-11-06 | Overhead | R16 | 2019-11-05 | 1 |  | 103 | 2 | 104 | 2019 | 2019 | R16
166227169152 | 168358169152 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-23 | 2019-10-23 | 2019-10-23 | 2019-12-11 | 2020-07-08 | Overhead | R16 | 2019-12-11 | 1 |  | 36 | 151 | 186 | 2019 | 2020 | R16
161275175401 | 167361175401 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-12-11 | 2019-12-11 | 2019-12-30 | 2020-03-10 | 2020-09-15 | Underground | R16 | 2020-03-10 | 1 | 14 | 52 | 136 | 200 | 2019 | 2020 | R16
168709162741 | 168235162741 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-29 | 2019-08-29 | 2019-08-29 | 2019-11-27 | 2019-12-09 | Overhead | R16 | 2019-11-27 | 1 |  | 65 | 9 | 73 | 2019 | 2019 | R16
166447166885 | 164891166885 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-10-04 | 2019-10-04 | 2019-10-04 | 2019-11-08 | 2019-11-08 | Overhead | R16 | 2019-11-08 | 1 |  | 26 |  | 26 | 2019 | 2019 | R16
167373174451 | 168293174451 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-22 | 2019-10-23 | 2019-12-13 | 2020-05-29 | 2020-06-01 | Underground | R16 | 2020-05-29 | 2 | 38 | 121 | 2 | 160 | 2019 | 2020 | R16
168142167628 | 168806167628 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-03 | 2019-09-03 | 2019-10-09 | 2020-04-20 | 2020-07-01 | Underground | R16 | 2020-04-20 | 1 | 27 | 139 | 53 | 217 | 2019 | 2020 | R16
164045182908 | 166157182908 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-19 | 2020-03-04 | 2020-03-04 | 2020-04-09 | 2020-04-13 | Overhead | R16 | 2020-04-09 | 143 |  | 27 | 3 | 171 | 2019 | 2020 | R16
169007162960 | 168711162960 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-31 | 2019-08-31 | 2019-08-31 | 2020-01-19 | 2020-01-24 | Overhead | R16 | 2020-01-19 | 0 |  | 100 | 5 | 105 | 2019 | 2020 | R16
162015170185 | 162150170185 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-20 | 2019-09-20 | 2019-10-30 | 2020-02-05 | 2021-11-09 | Underground | R16 | 2020-02-05 | 1 | 29 | 71 | 460 | 558 | 2019 | 2021 | R16
167744166020 | 163300166020 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-26 | 2019-09-26 | 2019-09-26 | 2020-01-10 | 2021-11-10 | Overhead | R16 | 2020-01-10 | 1 |  | 77 | 479 | 555 | 2019 | 2021 | R16
166716208637 | 166892208637 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-12-09 | 2020-04-08 | 2020-10-27 |  | 2021-02-23 | Underground | R16 |  | 88 | 145 |  |  | 317 | 2019 | 2021 | R16
169285155365 | 164162155365 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-15 | 2019-06-15 | 2019-06-15 | 2019-07-29 | 2019-08-26 | Overhead | R16 | 2019-07-29 | 0 |  | 31 | 21 | 51 | 2019 | 2019 | R16
168202165811 | 160453165811 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-09-11 | 2019-09-24 | 2019-09-26 | 2020-02-20 | 2020-11-18 | Underground | R16 | 2020-02-20 | 10 | 3 | 106 | 195 | 311 | 2019 | 2020 | R16
166072167489 | 166168167489 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-10-10 | 2019-10-10 | 2019-10-10 | 2020-04-08 | 2020-06-09 | Overhead | R16 | 2020-04-08 | 1 |  | 130 | 45 | 174 | 2019 | 2020 | R16
164530158148 | 165898158148 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-06-25 | 2019-06-25 | 2019-07-17 | 2020-05-18 | 2020-07-29 | Underground | R16 | 2020-05-18 | 1 | 17 | 219 | 53 | 287 | 2019 | 2020 | R16
168045165029 | 161676165029 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-18 | 2019-09-18 | 2019-09-18 | 2019-09-23 | 2019-11-21 | Overhead | R16 | 2019-09-23 | 1 |  | 4 | 44 | 47 | 2019 | 2019 | R16
163556172984 | 165231172984 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-26 | 2019-11-26 | 2019-11-26 | 2020-01-10 | 2020-06-09 | Overhead | R16 | 2020-01-10 | 1 |  | 34 | 108 | 141 | 2019 | 2020 | R16
166834170465 | 168992170465 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-03 | 2019-09-03 | 2019-11-01 | 2019-12-04 | 2020-06-09 | Underground | R16 | 2019-12-04 | 1 | 44 | 24 | 135 | 201 | 2019 | 2020 | R16
165206161898 | 169527161898 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-12 | 2019-07-12 | 2019-08-22 | 2020-01-09 | 2020-01-10 | Underground | R16 | 2020-01-09 | 1 | 30 | 101 | 2 | 131 | 2019 | 2020 | R16
163308173780 | 166535173780 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-05 | 2019-12-05 | 2019-12-05 | 2020-02-05 | 2020-02-06 | Overhead | R16 | 2020-02-05 | 1 |  | 45 | 2 | 46 | 2019 | 2020 | R16
164617169880 | 169349169880 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-25 | 2019-10-25 | 2019-10-28 | 2019-12-09 | 2021-12-16 | Overhead | R16 | 2019-12-09 | 1 | 2 | 31 | 529 | 560 | 2019 | 2021 | R16
161523166356 | 163954166356 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-01 | 2019-10-01 | 2019-10-01 | 2019-11-05 | 2019-11-06 | Overhead | R16 | 2019-11-05 | 1 |  | 26 | 2 | 27 | 2019 | 2019 | R16
161760168967 | 162884168967 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-25 | 2019-09-25 | 2019-10-21 | 2019-12-10 | 2019-12-11 | Underground | R16 | 2019-12-10 | 1 | 19 | 37 | 2 | 56 | 2019 | 2019 | R16
167193165511 | 169513165511 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-06 | 2019-09-19 | 2019-09-24 | 2019-12-10 | 2020-01-02 | Overhead | R16 | 2019-12-10 | 10 | 4 | 56 | 18 | 85 | 2019 | 2020 | R16
168963166250 | 168956166250 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE FOR UPGRADE UD | Commercial | 2019-07-09 | 2019-07-09 | 2019-09-30 | 2019-11-13 | 2020-02-06 | Underground | R16 | 2019-11-13 | 1 | 60 | 33 | 62 | 153 | 2019 | 2020 | R16
160550170049 | 161161170049 | NON-RESIDENTIAL - LODGING | R16 RESD AND NON RESD US | Commercial | 2019-07-22 | 2019-07-22 | 2019-10-30 | 2020-03-18 | 2020-10-13 | Underground | R16 | 2020-03-18 | 1 | 73 | 101 | 150 | 322 | 2019 | 2020 | R16
165099163164 | 167071163164 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-23 | 2019-09-03 | 2019-09-03 | 2019-12-20 | 2020-06-09 | Overhead | R16 | 2019-12-20 | 8 |  | 79 | 123 | 208 | 2019 | 2020 | R16
160033173872 | 169955173872 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-29 | 2019-10-29 | 2019-12-09 | 2022-07-21 | 2022-07-22 | Underground | R16 | 2022-07-21 | 1 | 30 | 684 | 2 | 714 | 2019 | 2022 | R16
160058163166 | 168643163166 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-30 | 2019-09-03 | 2019-09-03 | 2020-02-14 | 2020-06-09 | Underground | R16 | 2020-02-14 | 3 |  | 119 | 83 | 203 | 2019 | 2020 | R16
164778168947 | 168063168947 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-21 | 2019-10-21 | 2019-10-21 | 2020-03-03 | 2020-06-09 | Overhead | R16 | 2020-03-03 | 1 |  | 97 | 71 | 167 | 2019 | 2020 | R16
164086155159 | 164146155159 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-14 | 2019-06-14 | 2019-06-14 | 2019-07-19 | 2019-07-23 | Overhead | R16 | 2019-07-19 | 1 |  | 26 | 3 | 28 | 2019 | 2019 | R16
163009156225 | 165734156225 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-24 | 2019-06-24 | 2019-06-24 | 2019-08-04 | 2019-12-06 | Overhead | R16 | 2019-08-04 | 1 |  | 30 | 90 | 120 | 2019 | 2019 | R16
165560173692 | 168362173692 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-07-05 | 2019-07-05 | 2019-12-06 | 2021-04-02 | 2021-06-02 | Underground | R16 | 2021-04-02 | 1 | 111 | 346 | 44 | 499 | 2019 | 2021 | R16
168517161870 | 162429161870 | SDG&E | UG ELEC MISC SVC US | Commercial | 2019-07-29 | 2019-07-29 | 2019-08-21 | 2020-04-15 | 2022-08-29 | Underground | R16 | 2020-04-15 | 1 | 18 | 171 | 619 | 806 | 2019 | 2022 | R16
165099156382 | 165546156382 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC DEVELOPMENT | Residential | 2019-06-21 | 2019-06-21 | 2019-06-25 | 2021-02-04 | 2020-10-29 | Underground | R16 | 2021-02-04 | 1 | 3 | 423 |  | 355 | 2019 | 2020 | R16
169231173975 | 161607173975 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-09-18 | 2019-10-15 | 2019-12-10 | 2020-02-18 | 2023-06-07 | Underground | R16 | 2020-02-18 | 20 | 41 | 51 | 862 | 971 | 2019 | 2023 | R16
162280158548 | 161191158548 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-22 | 2019-07-22 | 2019-07-22 | 2019-07-22 | 2019-12-06 | Overhead | R16 | 2019-07-22 | 1 |  |  | 100 | 100 | 2019 | 2019 | R16
167885166628 | 165174166628 | NON-RESIDENTIAL - SMALL OFFICE | R16 RESD AND NON RESD US | Commercial | 2019-06-19 | 2019-09-09 | 2019-10-03 | 2020-10-15 | 2021-02-24 | Underground | R16 | 2020-10-15 | 59 | 19 | 271 | 95 | 441 | 2019 | 2021 | R16
165530159164 | 168357159164 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-05 | 2019-07-25 | 2019-07-26 | 2019-09-25 | 2019-10-10 | Overhead | R16 | 2019-09-25 | 15 | 2 | 44 | 12 | 70 | 2019 | 2019 | R16
169483159348 | 162475159348 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-29 | 2019-07-29 | 2019-07-29 | 2022-06-15 | 2022-10-20 | Overhead | R16 | 2022-06-15 | 1 |  | 753 | 92 | 844 | 2019 | 2022 | R16
160857162169 | 167176162169 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-24 | 2019-08-24 | 2019-08-24 | 2019-10-01 | 2019-10-02 | Overhead | R16 | 2019-10-01 | 0 |  | 27 | 2 | 28 | 2019 | 2019 | R16
168862168648 | 167567168648 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-17 | 2019-10-17 | 2019-10-17 | 2019-12-04 | 2020-01-02 | Overhead | R16 | 2019-12-04 | 1 |  | 35 | 22 | 56 | 2019 | 2020 | R16
168537165111 | 168496165111 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-30 | 2019-08-30 | 2019-09-20 | 2019-10-22 | 2019-11-08 | Overhead | R16 | 2019-10-22 | 1 | 16 | 23 | 14 | 51 | 2019 | 2019 | R16
168112162961 | 168664162961 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-31 | 2019-08-31 | 2019-08-31 | 2020-01-10 | 2020-01-13 | Overhead | R16 | 2020-01-10 | 0 |  | 95 | 2 | 96 | 2019 | 2020 | R16
164030162351 | 164175162351 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-07 | 2019-08-07 | 2019-08-26 | 2019-10-24 | 2019-10-25 | Underground | R16 | 2019-10-24 | 1 | 14 | 44 | 2 | 58 | 2019 | 2019 | R16
164461172152 | 165193172152 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-13 | 2019-08-13 | 2019-11-18 | 2020-03-06 | 2020-06-09 | Underground | R16 | 2020-03-06 | 1 | 70 | 80 | 68 | 216 | 2019 | 2020 | R16
165516164916 | 161926164916 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-19 | 2019-09-19 | 2019-09-19 | 2019-11-20 | 2020-01-15 | Overhead | R16 | 2019-11-20 | 1 |  | 45 | 41 | 85 | 2019 | 2020 | R16
165935159675 | 163354159675 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-08-01 | 2019-08-01 | 2019-08-01 | 2020-02-27 | 2020-02-28 | Underground | R16 | 2020-02-27 | 1 |  | 151 | 2 | 152 | 2019 | 2020 | R16
163702178833 | 161143178833 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH CP R16 WORK RELO TO UG | Commercial | 2019-09-16 | 2019-10-14 | 2020-01-31 | 2020-05-20 | 2020-09-18 | Overhead | R16 | 2020-05-20 | 21 | 80 | 79 | 88 | 265 | 2019 | 2020 | R16
166735158583 | 160851158583 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-18 | 2019-07-22 | 2019-07-22 | 2019-08-29 | 2020-02-19 | Overhead | R16 | 2019-08-29 | 3 |  | 29 | 125 | 155 | 2019 | 2020 | R16
161291172838 | 164839172838 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-25 | 2019-11-25 | 2019-11-25 | 2020-12-10 | 2021-04-14 | Overhead | R16 | 2020-12-10 | 1 |  | 274 | 90 | 363 | 2019 | 2021 | R16
162666173993 | 164369173993 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-21 | 2019-11-21 | 2019-12-10 | 2019-12-12 | 2020-06-09 | Underground | R16 | 2019-12-12 | 1 | 14 | 3 | 129 | 144 | 2019 | 2020 | R16
166882172761 | 165070172761 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-05 | 2019-10-05 | 2019-11-22 | 2020-02-20 | 2020-02-25 | Underground | R16 | 2020-02-20 | 0 | 35 | 65 | 4 | 102 | 2019 | 2020 | R16
169761166841 | 161832166841 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-07-24 | 2019-07-24 | 2019-10-03 | 2020-08-27 | 2020-08-28 | Underground | R16 | 2020-08-27 | 1 | 52 | 236 | 2 | 288 | 2019 | 2020 | R16
168548169837 | 160027169837 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-29 | 2019-10-29 | 2019-10-29 | 2020-01-03 | 2020-01-17 | Overhead | R16 | 2020-01-03 | 1 |  | 49 | 11 | 59 | 2019 | 2020 | R16
163762158621 | 165717158621 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-24 | 2019-06-24 | 2019-07-22 | 2019-08-15 | 2019-09-24 | Underground | R16 | 2019-08-15 | 1 | 21 | 19 | 29 | 67 | 2019 | 2019 | R16
166269160133 | 163800160133 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-05 | 2019-08-05 | 2019-08-05 | 2019-10-09 | 2019-10-10 | Overhead | R16 | 2019-10-09 | 1 |  | 48 | 2 | 49 | 2019 | 2019 | R16
168090170291 | 169156170291 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-25 | 2019-10-31 | 2019-10-31 | 2020-01-09 | 2021-11-10 | Overhead | R16 | 2020-01-09 | 5 |  | 51 | 480 | 534 | 2019 | 2021 | R16
164312162478 | 166481162478 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-20 | 2019-08-26 | 2019-08-28 | 2019-10-17 | 2019-10-21 | Overhead | R16 | 2019-10-17 | 5 | 3 | 37 | 3 | 45 | 2019 | 2019 | R16
160771163317 | 160772163317 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-07-18 | 2019-07-29 | 2019-09-04 | 2020-10-20 | 2021-02-04 | Underground | R16 | 2020-10-20 | 8 | 28 | 295 | 78 | 406 | 2019 | 2021 | R16
168044173999 | 169214173999 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-25 | 2019-12-10 | 2019-12-10 | 2020-03-09 | 2020-06-24 | Overhead | R16 | 2020-03-09 | 33 |  | 65 | 78 | 174 | 2019 | 2020 | R16
167254164799 | 169492164799 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-06 | 2019-09-19 | 2019-09-19 | 2020-01-02 | 2021-11-13 | Overhead | R16 | 2020-01-02 | 10 |  | 76 | 487 | 571 | 2019 | 2021 | R16
166849169594 | 169431169594 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-26 | 2019-10-26 | 2019-10-26 | 2020-03-01 | 2021-10-14 | Underground | R16 | 2020-03-01 | 0 |  | 90 | 424 | 514 | 2019 | 2021 | R16
162427178060 | 164548178060 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-21 | 2020-01-24 | 2020-01-24 | 2020-04-24 | 2020-04-24 | Overhead | R16 | 2020-04-24 | 47 |  | 66 |  | 112 | 2019 | 2020 | R16
161495167339 | 165690167339 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-08 | 2019-10-08 | 2019-10-08 | 2019-11-13 | 2019-11-21 | Overhead | R16 | 2019-11-13 | 1 |  | 27 | 7 | 33 | 2019 | 2019 | R16
161377174393 | 165365174393 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-27 | 2019-11-27 | 2019-12-17 | 2020-03-12 | 2020-03-13 | Underground | R16 | 2020-03-12 | 1 | 15 | 63 | 2 | 78 | 2019 | 2020 | R16
169233168641 | 169248168641 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-04 | 2019-09-04 | 2019-10-17 | 2020-05-23 | 2020-05-26 | Underground | R16 | 2020-05-23 | 1 | 32 | 157 | 2 | 190 | 2019 | 2020 | R16
163502163172 | 168553163172 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-30 | 2019-08-30 | 2019-09-03 | 2019-12-15 | 2019-12-18 | Overhead | R16 | 2019-12-15 | 1 | 3 | 74 | 3 | 79 | 2019 | 2019 | R16
166347164090 | 166781164090 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-21 | 2019-08-21 | 2019-09-11 | 2019-11-05 | 2019-11-06 | Underground | R16 | 2019-11-05 | 1 | 16 | 40 | 2 | 56 | 2019 | 2019 | R16
167871165461 | 162380165461 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-23 | 2019-09-23 | 2019-09-23 | 2019-09-24 | 2019-10-30 | Overhead | R16 | 2019-09-24 | 1 |  | 2 | 27 | 28 | 2019 | 2019 | R16
163996164033 | 164434164033 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-08 | 2019-08-16 | 2019-09-10 | 2019-10-14 | 2019-10-23 | Underground | R16 | 2019-10-14 | 7 | 18 | 25 | 8 | 55 | 2019 | 2019 | R16
166342166651 | 164248166651 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-02 | 2019-10-02 | 2019-10-02 | 2019-10-17 | 2019-10-18 | Overhead | R16 | 2019-10-17 | 1 |  | 12 | 2 | 13 | 2019 | 2019 | R16
160595175120 | 161797175120 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-07 | 2019-11-07 | 2019-12-20 | 2020-04-02 | 2020-04-02 | Underground | R16 | 2020-04-02 | 1 | 32 | 75 |  | 106 | 2019 | 2020 | R16
168564165058 | 162139165058 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-20 | 2019-09-20 | 2019-09-20 | 2019-11-08 | 2019-11-21 | Overhead | R16 | 2019-11-08 | 1 |  | 36 | 10 | 45 | 2019 | 2019 | R16
168354161960 | 164743161960 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-08-09 | 2019-08-09 | 2019-08-21 | 2020-01-28 | 2020-01-29 | Underground | R16 | 2020-01-28 | 1 | 9 | 115 | 2 | 124 | 2019 | 2020 | R16
162823169282 | 168318169282 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-22 | 2019-10-22 | 2019-10-22 | 2020-01-10 | 2021-11-10 | Overhead | R16 | 2020-01-10 | 1 |  | 59 | 479 | 537 | 2019 | 2021 | R16
168717172086 | 162882172086 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-13 | 2019-11-17 | 2019-11-18 | 2019-11-20 | 2020-06-09 | Overhead | R16 | 2019-11-20 | 3 | 1 | 3 | 145 | 150 | 2019 | 2020 | R16
169941174125 | 169960174125 | NON-RESIDENTIAL - SMALL RETAIL | UG R16 RESD AND NON RESD UD | Residential | 2019-07-15 | 2019-07-15 | 2019-12-10 | 2020-02-26 | 2021-04-05 | Underground | R16 | 2020-02-26 | 1 | 107 | 57 | 289 | 451 | 2019 | 2021 | R16
167715324719 | 160222324719 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-07-11 | 2023-08-07 | Overhead | R16 | 2023-07-11 | 1 |  |  | 20 | 20 | 2023 | 2023 | R16
164108159014 | 164134159014 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-06-15 | 2019-06-15 | 2019-07-25 | 2019-08-09 | 2019-08-12 | Overhead | R16 | 2019-08-09 | 0 | 29 | 12 | 2 | 41 | 2019 | 2019 | R16
162489182578 | 162821182578 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-30 | 2020-03-03 | 2020-03-03 | 2020-03-06 | 2020-03-09 | Overhead | R16 | 2020-03-06 | 156 |  | 4 | 2 | 160 | 2019 | 2020 | R16
161180158002 | 165995158002 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | R16 RESD AND NON RESD US | Commercial | 2019-06-25 | 2019-07-02 | 2019-07-15 | 2019-08-06 | 2019-12-03 | Underground | R16 | 2019-08-06 | 6 | 10 | 17 | 86 | 116 | 2019 | 2019 | R16
160181170628 | 161017170628 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-04 | 2019-11-04 | 2019-11-04 | 2019-12-01 | 2019-12-10 | Overhead | R16 | 2019-12-01 | 1 |  | 20 | 7 | 27 | 2019 | 2019 | R16
168563170949 | 160325170949 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-30 | 2019-10-30 | 2019-11-06 | 2020-01-08 | 2020-04-21 | Underground | R16 | 2020-01-08 | 1 | 6 | 46 | 75 | 125 | 2019 | 2020 | R16
168160164880 | 161478164880 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-09-17 | 2019-09-17 | 2019-09-17 | 2019-10-01 | 2019-11-14 | Underground | R16 | 2019-10-01 | 1 |  | 11 | 33 | 43 | 2019 | 2019 | R16
166820170092 | 160051170092 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-30 | 2019-10-30 | 2019-10-30 | 2019-12-13 | 2019-12-17 | Underground | R16 | 2019-12-13 | 1 |  | 33 | 3 | 35 | 2019 | 2019 | R16
167012166786 | 164464166786 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-03 | 2019-10-03 | 2019-10-03 | 2019-12-10 | 2020-01-02 | Overhead | R16 | 2019-12-10 | 1 |  | 49 | 18 | 66 | 2019 | 2020 | R16
164121168529 | 168713168529 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-07-08 | 2019-07-09 | 2019-10-18 | 2020-04-10 | 2021-04-05 | Underground | R16 | 2020-04-10 | 2 | 74 | 126 | 257 | 456 | 2019 | 2021 | R16
166817184143 | 164821184143 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-11-22 | 2019-11-22 | 2020-03-16 | 2020-03-29 | 2020-09-02 | Overhead | R16 | 2020-03-29 | 1 | 82 | 10 | 113 | 204 | 2019 | 2020 | R16
162103174317 | 162131174317 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-20 | 2019-09-20 | 2019-12-12 | 2020-01-21 | 2020-01-22 | Underground | R16 | 2020-01-21 | 1 | 60 | 29 | 2 | 89 | 2019 | 2020 | R16
166152175319 | 167375175319 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2019-08-26 | 2019-08-27 | 2020-01-02 | 2020-01-16 | 2020-11-10 | Overhead | R16 | 2020-01-16 | 2 | 93 | 11 | 214 | 317 | 2019 | 2020 | R16
161347179749 | 163069179749 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-13 | 2019-11-13 | 2020-02-07 | 2023-01-11 | 2022-11-30 | Overhead | R16 | 2023-01-11 | 1 | 63 | 764 |  | 796 | 2019 | 2022 | R16
169620171135 | 162074171135 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-08 | 2019-11-08 | 2019-11-08 | 2020-02-14 | 2020-06-17 | Overhead | R16 | 2020-02-14 | 1 |  | 71 | 89 | 159 | 2019 | 2020 | R16
167935176816 | 164465176816 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-08 | 2019-12-31 | 2020-01-14 | 2022-06-09 | 2022-07-26 | Underground | R16 | 2022-06-09 | 104 | 11 | 628 | 34 | 774 | 2019 | 2022 | R16
163710157472 | 169151157472 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-10 | 2019-07-10 | 2019-07-10 | 2019-08-26 | 2019-08-27 | Overhead | R16 | 2019-08-26 | 1 |  | 34 | 2 | 35 | 2019 | 2019 | R16
162891172481 | 162819172481 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-07-30 | 2019-09-23 | 2019-11-20 | 2020-12-22 | 2022-03-09 | Underground | R16 | 2020-12-22 | 40 | 43 | 285 | 317 | 682 | 2019 | 2022 | R16
160896160495 | 163864160495 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-05 | 2019-08-05 | 2019-08-08 | 2019-10-23 | 2019-10-30 | Underground | R16 | 2019-10-23 | 1 | 4 | 55 | 6 | 63 | 2019 | 2019 | R16
166375167885 | 163312167885 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-26 | 2019-09-26 | 2019-10-11 | 2019-10-30 | 2019-10-31 | Underground | R16 | 2019-10-30 | 1 | 12 | 14 | 2 | 26 | 2019 | 2019 | R16
166348160961 | 160073160961 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-15 | 2019-07-15 | 2019-08-12 | 2020-07-01 | 2019-10-16 | Underground | R16 | 2020-07-01 | 1 | 21 | 233 |  | 68 | 2019 | 2019 | R16
169793165044 | 169643165044 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-06 | 2019-09-06 | 2019-09-18 | 2020-08-12 | 2020-08-20 | Underground | R16 | 2020-08-12 | 1 | 9 | 236 | 7 | 250 | 2019 | 2020 | R16
160855162142 | 167244162142 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-23 | 2019-08-23 | 2019-08-23 | 2019-09-30 | 2019-09-30 | Overhead | R16 | 2019-09-30 | 1 |  | 27 |  | 27 | 2019 | 2019 | R16
162702174793 | 165622174793 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-12-02 | 2019-12-02 | 2019-12-18 | 2019-12-20 | 2020-06-16 | Overhead | R16 | 2019-12-20 | 1 | 13 | 3 | 128 | 142 | 2019 | 2020 | R16
167046181212 | 167157181212 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-15 | 2019-10-15 | 2020-02-19 | 2020-10-05 | 2020-10-06 | Underground | R16 | 2020-10-05 | 1 | 92 | 164 | 2 | 256 | 2019 | 2020 | R16
167997168501 | 167376168501 | GENERAL/OTHER | R16 RESD AND NON RESD US | Commercial | 2019-10-17 | 2019-10-17 | 2019-10-17 | 2020-04-14 | 2020-07-01 | Underground | R16 | 2020-04-14 | 1 |  | 129 | 57 | 185 | 2019 | 2020 | R16
163799158282 | 160672158282 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-17 | 2019-07-17 | 2019-07-17 | 2019-10-11 | 2020-01-08 | Overhead | R16 | 2019-10-11 | 1 |  | 63 | 64 | 126 | 2019 | 2020 | R16
168001160246 | 161700160246 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-24 | 2019-07-24 | 2019-08-05 | 2019-10-01 | 2019-10-14 | Underground | R16 | 2019-10-01 | 1 | 9 | 42 | 10 | 59 | 2019 | 2019 | R16
163450177546 | 165818177546 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-12-03 | 2020-01-08 | 2020-01-21 | 2020-02-04 | 2020-02-04 | Overhead | R16 | 2020-02-04 | 27 | 10 | 11 |  | 46 | 2019 | 2020 | R16
164896207431 | 164932207431 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-11-22 | 2019-11-22 | 2020-10-16 | 2021-02-18 | 2021-03-25 | Underground | R16 | 2021-02-18 | 1 | 236 | 90 | 26 | 350 | 2019 | 2021 | R16
167817170710 | 161268170710 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-05 | 2019-11-05 | 2019-11-05 | 2020-03-13 | 2020-08-28 | Overhead | R16 | 2020-03-13 | 1 |  | 94 | 121 | 214 | 2019 | 2020 | R16
164850162751 | 167043162751 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-23 | 2019-08-29 | 2019-08-29 | 2019-11-12 | 2019-11-21 | Overhead | R16 | 2019-11-12 | 5 |  | 54 | 8 | 65 | 2019 | 2019 | R16
162104203102 | 162897203102 | NON-RESIDENTIAL - HEALTH CARE | UG R16 RESD AND NON RESD UD | Residential | 2019-11-13 | 2020-03-25 | 2020-09-08 | 2021-08-13 | 2021-10-18 | Underground | R16 | 2021-08-13 | 96 | 120 | 244 | 47 | 504 | 2019 | 2021 | R16
164084174289 | 168001174289 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-12 | 2019-12-12 | 2019-12-12 | 2020-01-06 | 2020-06-09 | Overhead | R16 | 2020-01-06 | 1 |  | 18 | 112 | 129 | 2019 | 2020 | R16
169609174683 | 160918174683 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-04 | 2019-11-04 | 2019-12-18 | 2020-01-29 | 2020-06-22 | Overhead | R16 | 2020-01-29 | 1 | 33 | 31 | 104 | 166 | 2019 | 2020 | R16
169463174308 | 160189174308 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-10 | 2019-09-10 | 2019-12-12 | 2020-03-03 | 2020-04-28 | Underground | R16 | 2020-03-03 | 1 | 68 | 59 | 41 | 166 | 2019 | 2020 | R16
166512162536 | 168072162536 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-28 | 2019-08-28 | 2019-08-28 | 2019-10-11 | 2019-10-23 | Overhead | R16 | 2019-10-11 | 1 |  | 33 | 9 | 41 | 2019 | 2019 | R16
163807183685 | 166789183685 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-09 | 2019-12-09 | 2020-03-10 | 2020-06-29 | 2020-06-30 | Underground | R16 | 2020-06-29 | 1 | 67 | 80 | 2 | 147 | 2019 | 2020 | R16
162556167738 | 161009167738 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-14 | 2019-09-14 | 2019-10-11 | 2019-11-12 | 2019-11-13 | Underground | R16 | 2019-11-12 | 0 | 20 | 23 | 2 | 43 | 2019 | 2019 | R16
160525172930 | 164689172930 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-10-04 | 2019-10-04 | 2019-11-25 | 2020-01-08 | 2020-03-06 | Underground | R16 | 2020-01-08 | 1 | 37 | 33 | 43 | 111 | 2019 | 2020 | R16
162639167529 | 165681167529 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-10-09 | 2019-10-09 | 2019-10-09 | 2019-11-05 | 2019-11-05 | Underground | R16 | 2019-11-05 | 1 |  | 20 |  | 20 | 2019 | 2019 | R16
165393219628 | 165425219628 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-08-14 | 2019-08-14 | 2021-02-04 | 2022-01-10 | 2022-01-21 | Underground | R16 | 2022-01-10 | 1 | 387 | 243 | 10 | 638 | 2019 | 2022 | R16
163114170883 | 167170170883 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-15 | 2019-11-06 | 2019-11-06 | 2020-01-03 | 2020-06-09 | Overhead | R16 | 2020-01-03 | 17 |  | 43 | 113 | 171 | 2019 | 2020 | R16
163612217776 | 165286217776 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-11-26 | 2019-11-26 | 2021-01-21 | 2021-03-23 | 2021-08-06 | Underground | R16 | 2021-03-23 | 1 | 303 | 44 | 99 | 444 | 2019 | 2021 | R16
163990172429 | 164536172429 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-03 | 2019-10-03 | 2019-11-20 | 2019-12-18 | 2019-12-19 | Underground | R16 | 2019-12-18 | 1 | 35 | 21 | 2 | 56 | 2019 | 2019 | R16
168080166969 | 160082166969 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-09 | 2019-09-09 | 2019-10-05 | 2020-06-25 | 2020-06-26 | Underground | R16 | 2020-06-25 | 1 | 20 | 189 | 2 | 210 | 2019 | 2020 | R16
166790159551 | 162609159551 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-07-29 | 2019-07-29 | 2019-07-29 | 2019-08-13 | 2019-08-27 | Underground | R16 | 2019-08-13 | 1 |  | 12 | 11 | 22 | 2019 | 2019 | R16
165410163385 | 168917163385 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-03 | 2019-09-04 | 2019-09-04 | 2019-09-13 | 2019-09-24 | Overhead | R16 | 2019-09-13 | 2 |  | 8 | 8 | 16 | 2019 | 2019 | R16
167967206139 | 169480206139 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-05 | 2019-09-05 | 2020-10-05 | 2023-07-07 | 2023-07-10 | Underground | R16 | 2023-07-07 | 1 | 283 | 720 | 2 | 1003 | 2019 | 2023 | R16
161587155286 | 163729155286 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-13 | 2019-06-13 | 2019-06-13 | 2019-07-29 | 2019-08-26 | Overhead | R16 | 2019-07-29 | 1 |  | 33 | 21 | 53 | 2019 | 2019 | R16
169544181055 | 165556181055 | NON-RESIDENTIAL - MISCELLANEOUS | UG ELEC MISC SVC US | Commercial | 2019-08-14 | 2019-10-07 | 2020-02-19 | 2020-10-29 | 2022-09-28 | Underground | R16 | 2020-10-29 | 39 | 98 | 182 | 500 | 816 | 2019 | 2022 | R16
166296157067 | 164250157067 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-06-15 | 2019-06-15 | 2019-07-03 | 2020-10-02 | 2020-10-05 | Overhead | R16 | 2020-10-02 | 0 | 13 | 328 | 2 | 341 | 2019 | 2020 | R16
161010160914 | 162719160914 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-30 | 2019-07-30 | 2019-08-12 | 2019-09-25 | 2019-09-26 | Underground | R16 | 2019-09-25 | 1 | 10 | 33 | 2 | 43 | 2019 | 2019 | R16
162140174093 | 163509174093 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-18 | 2019-12-11 | 2019-12-11 | 2020-02-14 | 2020-06-09 | Overhead | R16 | 2020-02-14 | 18 |  | 48 | 83 | 147 | 2019 | 2020 | R16
167187166006 | 169547166006 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-06 | 2019-09-26 | 2019-09-27 | 2019-11-27 | 2020-06-09 | Overhead | R16 | 2019-11-27 | 15 | 2 | 44 | 140 | 198 | 2019 | 2020 | R16
162230198135 | 162443198135 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-09-23 | 2020-04-14 | 2020-07-23 | 2021-02-17 | 2021-05-05 | Underground | R16 | 2021-02-17 | 147 | 73 | 150 | 56 | 423 | 2019 | 2021 | R16
166069159241 | 162177159241 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-26 | 2019-07-26 | 2019-07-26 | 2020-01-14 | 2020-01-17 | Overhead | R16 | 2020-01-14 | 1 |  | 123 | 4 | 126 | 2019 | 2020 | R16
165980200395 | 161345200395 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-09-16 | 2019-09-17 | 2020-08-13 | 2021-04-16 | 2021-04-19 | Underground | R16 | 2021-04-16 | 2 | 238 | 177 | 2 | 416 | 2019 | 2021 | R16
163182181335 | 166380181335 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-04 | 2019-12-09 | 2020-02-22 | 2020-04-13 | 2020-04-13 | Underground | R16 | 2020-04-13 | 4 | 55 | 36 |  | 94 | 2019 | 2020 | R16
165889154934 | 163238154934 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-11 | 2019-06-11 | 2019-06-11 | 2020-02-26 | 2020-02-27 | Overhead | R16 | 2020-02-26 | 1 |  | 187 | 2 | 188 | 2019 | 2020 | R16
160400175061 | 161748175061 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-07 | 2019-11-07 | 2019-12-20 | 2020-03-13 | 2020-03-12 | Underground | R16 | 2020-03-13 | 1 | 32 | 61 |  | 91 | 2019 | 2020 | R16
165513173139 | 163187173139 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-06-11 | 2019-06-11 | 2019-12-02 | 2020-10-14 | 2020-11-13 | Underground | R16 | 2020-10-14 | 1 | 125 | 228 | 23 | 374 | 2019 | 2020 | R16
160398165481 | 166783165481 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-08-21 | 2019-08-26 | 2019-09-23 | 2022-05-18 | 2022-05-18 | Overhead | R16 | 2022-05-18 | 4 | 21 | 693 |  | 716 | 2019 | 2022 | R16
162642172948 | 164024172948 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-20 | 2019-11-20 | 2019-11-26 | 2020-03-03 | 2020-12-18 | Underground | R16 | 2020-03-03 | 1 | 5 | 71 | 209 | 283 | 2019 | 2020 | R16
165222169684 | 169281169684 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-25 | 2019-10-25 | 2019-10-25 | 2019-12-09 | 2019-12-11 | Overhead | R16 | 2019-12-09 | 1 |  | 32 | 3 | 34 | 2019 | 2019 | R16
169180155240 | 163648155240 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-12 | 2019-06-12 | 2019-06-13 | 2019-07-15 | 2019-07-16 | Overhead | R16 | 2019-07-15 | 1 | 2 | 23 | 2 | 25 | 2019 | 2019 | R16
166196170460 | 168010170460 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-21 | 2019-10-31 | 2019-11-01 | 2020-01-02 | 2021-11-13 | Overhead | R16 | 2020-01-02 | 9 | 2 | 45 | 487 | 540 | 2019 | 2021 | R16
161352168455 | 162644168455 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-09-24 | 2019-09-24 | 2019-10-17 | 2019-11-19 | 2019-11-27 | Underground | R16 | 2019-11-19 | 1 | 18 | 24 | 7 | 47 | 2019 | 2019 | R16
163654168681 | 167465168681 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2019-10-17 | 2019-10-17 | 2019-10-17 | 2020-01-28 | 2020-03-17 | Underground | R16 | 2020-01-28 | 1 |  | 74 | 36 | 109 | 2019 | 2020 | R16
165411312760 | 166958312760 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-08-30 | 2023-09-14 | Overhead | R16 | 2023-08-30 | 1 |  | 120 | 12 | 131 | 2023 | 2023 | R16
169572165986 | 163343165986 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-09-27 | 2019-09-27 | 2019-09-27 | 2020-10-29 | 2021-01-29 | Underground | R16 | 2020-10-29 | 1 |  | 285 | 67 | 351 | 2019 | 2021 | R16
164781162753 | 166527162753 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-21 | 2019-08-29 | 2019-08-29 | 2019-11-19 | 2019-11-26 | Underground | R16 | 2019-11-19 | 7 |  | 59 | 6 | 70 | 2019 | 2019 | R16
162748173337 | 162903173337 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-13 | 2019-11-13 | 2019-12-04 | 2020-01-24 | 2020-01-27 | Underground | R16 | 2020-01-24 | 1 | 16 | 38 | 2 | 54 | 2019 | 2020 | R16
168176156756 | 167770156756 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-02 | 2019-07-02 | 2019-07-02 | 2019-10-21 | 2019-10-21 | Overhead | R16 | 2019-10-21 | 1 |  | 80 |  | 80 | 2019 | 2019 | R16
162539171870 | 162957171870 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-26 | 2019-09-26 | 2019-11-14 | 2020-02-03 | 2020-06-09 | Underground | R16 | 2020-02-03 | 1 | 36 | 58 | 92 | 184 | 2019 | 2020 | R16
163707158603 | 161275158603 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-22 | 2019-07-22 | 2019-07-22 | 2019-07-25 | 2019-08-28 | Overhead | R16 | 2019-07-25 | 1 |  | 4 | 25 | 28 | 2019 | 2019 | R16
163221158550 | 165119158550 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-20 | 2019-06-27 | 2019-07-22 | 2019-09-27 | 2019-10-11 | Overhead | R16 | 2019-09-27 | 6 | 18 | 50 | 11 | 82 | 2019 | 2019 | R16
160570169380 | 160886169380 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-18 | 2019-07-18 | 2019-10-23 | 2020-03-23 | 2020-03-31 | Underground | R16 | 2020-03-23 | 1 | 70 | 109 | 7 | 184 | 2019 | 2020 | R16
166331272122 | 168373272122 | Affordable Housing | R16 RESD AND NON RESD US | Residential | 2022-02-10 | 2022-02-10 | 2022-03-09 | 2023-10-12 | 2023-10-10 | Underground | R16 | 2023-10-12 | 1 | 20 | 417 |  | 434 | 2022 | 2023 | R16
165679164362 | 166799164362 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-22 | 2019-09-13 | 2019-09-13 | 2019-11-13 | 2019-11-14 | Overhead | R16 | 2019-11-13 | 17 |  | 44 | 2 | 61 | 2019 | 2019 | R16
161521176245 | 168799176245 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-23 | 2019-11-05 | 2020-01-07 | 2021-01-13 | 2021-04-20 | Underground | R16 | 2021-01-13 | 10 | 46 | 267 | 70 | 390 | 2019 | 2021 | R16
161881174834 | 167676174834 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-12-11 | 2019-12-12 | 2019-12-19 | 2020-01-02 | 2020-03-10 | Overhead | R16 | 2020-01-02 | 2 | 6 | 11 | 49 | 65 | 2019 | 2020 | R16
161076157639 | 169733157639 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-07-12 | 2019-07-12 | 2019-07-12 | 2019-07-18 | 2019-09-03 | Overhead | R16 | 2019-07-18 | 1 |  | 5 | 34 | 38 | 2019 | 2019 | R16
163695168887 | 167927168887 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-19 | 2019-10-19 | 2019-10-19 | 2019-12-04 | 2020-01-02 | Overhead | R16 | 2019-12-04 | 0 |  | 33 | 22 | 54 | 2019 | 2020 | R16
167937165573 | 160354165573 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-11 | 2019-09-24 | 2019-09-24 | 2020-03-03 | 2020-06-09 | Overhead | R16 | 2020-03-03 | 10 |  | 116 | 71 | 195 | 2019 | 2020 | R16
169004166238 | 163261166238 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-09-26 | 2019-09-26 | 2019-10-01 | 2020-02-10 | 2020-06-09 | Underground | R16 | 2020-02-10 | 1 | 4 | 95 | 87 | 184 | 2019 | 2020 | R16
163443155811 | 163718155811 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-13 | 2019-06-13 | 2019-06-20 | 2019-10-28 | 2019-10-29 | Overhead | R16 | 2019-10-28 | 1 | 6 | 93 | 2 | 99 | 2019 | 2019 | R16
168133284881 | 164299284881 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-09-09 | 2021-09-24 | 2022-07-07 | 2022-07-25 | 2022-08-08 | Underground | R16 | 2022-07-25 | 12 | 205 | 13 | 11 | 238 | 2021 | 2022 | R16
165504161591 | 166123161591 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-19 | 2019-08-19 | 2019-08-19 | 2019-10-15 | 2019-10-16 | Overhead | R16 | 2019-10-15 | 1 |  | 42 | 2 | 43 | 2019 | 2019 | R16
168167159464 | 161893159464 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-25 | 2019-07-29 | 2019-07-29 | 2019-08-20 | 2019-08-22 | Underground | R16 | 2019-08-20 | 3 |  | 17 | 3 | 21 | 2019 | 2019 | R16
169723174751 | 163323174751 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-26 | 2019-09-26 | 2019-12-19 |  | 2022-10-19 | Underground | R16 |  | 1 | 61 |  |  | 800 | 2019 | 2022 | R16
160037167224 | 165147167224 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-07 | 2019-10-07 | 2019-10-07 | 2020-12-31 | 2021-04-16 | Overhead | R16 | 2020-12-31 | 1 |  | 324 | 77 | 400 | 2019 | 2021 | R16
164324175002 | 165355175002 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-02 | 2019-12-15 | 2019-12-20 | 2020-03-03 | 2020-06-09 | Overhead | R16 | 2020-03-03 | 10 | 5 | 53 | 71 | 137 | 2019 | 2020 | R16
166389157032 | 166175157032 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-26 | 2019-06-26 | 2019-07-03 | 2019-08-20 | 2019-08-21 | Underground | R16 | 2019-08-20 | 1 | 6 | 35 | 2 | 41 | 2019 | 2019 | R16
165041253919 | 164292253919 | CUSTOMER UPGRADE IN SERVICE | UG SVC CONVERSION | Commercial | 2019-06-17 | 2019-06-17 | 2021-10-27 | 2021-12-10 | 2021-12-10 | Underground | R16 | 2021-12-10 | 1 | 618 | 33 |  | 650 | 2019 | 2021 | R16
160177162530 | 167823162530 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-28 | 2019-08-28 | 2019-08-28 | 2019-09-20 | 2019-10-30 | Overhead | R16 | 2019-09-20 | 1 |  | 18 | 29 | 46 | 2019 | 2019 | R16
165810160881 | 169224160881 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-10 | 2019-07-10 | 2019-08-12 | 2019-09-16 | 2019-09-27 | Overhead | R16 | 2019-09-16 | 1 | 24 | 26 | 10 | 58 | 2019 | 2019 | R16
168624161016 | 166039161016 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-06-25 | 2019-06-25 | 2019-08-14 | 2020-06-03 | 2021-06-09 | Underground | R16 | 2020-06-03 | 1 | 37 | 211 | 266 | 512 | 2019 | 2021 | R16
163695158885 | 161799158885 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-25 | 2019-07-25 | 2019-07-25 | 2019-10-22 | 2019-10-23 | Overhead | R16 | 2019-10-22 | 1 |  | 64 | 2 | 65 | 2019 | 2019 | R16
169045171980 | 160087171980 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-30 | 2019-11-15 | 2019-11-15 | 2020-05-05 | 2020-05-14 | Overhead | R16 | 2020-05-05 | 13 |  | 123 | 8 | 142 | 2019 | 2020 | R16
163351228207 | 164347228207 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-11-20 | 2020-03-13 | 2021-04-23 | 2022-12-14 | 2023-07-03 | Underground | R16 | 2022-12-14 | 83 | 291 | 429 | 144 | 944 | 2019 | 2023 | R16
168503166672 | 164168166672 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-02 | 2019-10-02 | 2019-10-02 | 2020-01-15 | 2021-10-20 | Overhead | R16 | 2020-01-15 | 1 |  | 76 | 461 | 536 | 2019 | 2021 | R16
164992159200 | 162128159200 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-26 | 2019-07-26 | 2019-07-26 | 2019-08-16 | 2019-08-19 | Overhead | R16 | 2019-08-16 | 1 |  | 16 | 2 | 17 | 2019 | 2019 | R16
169511185675 | 165038185675 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-08-12 | 2020-03-31 | 2020-03-31 | 2020-04-10 | 2020-06-24 | Overhead | R16 | 2020-04-10 | 167 |  | 9 | 54 | 228 | 2019 | 2020 | R16
169322172002 | 161923172002 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-19 | 2019-09-19 | 2019-11-15 | 2020-02-28 | 2022-05-17 | Underground | R16 | 2020-02-28 | 1 | 42 | 76 | 578 | 694 | 2019 | 2022 | R16
164761166907 | 164647166907 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-04 | 2019-10-04 | 2019-10-04 | 2019-11-13 | 2019-11-15 | Underground | R16 | 2019-11-13 | 1 |  | 29 | 3 | 31 | 2019 | 2019 | R16
163108157624 | 165264157624 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-20 | 2019-07-11 | 2019-07-11 | 2019-08-20 | 2019-12-16 | Overhead | R16 | 2019-08-20 | 16 |  | 29 | 85 | 128 | 2019 | 2019 | R16
168683156047 | 165484156047 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-21 | 2019-06-21 | 2019-06-21 | 2020-02-21 | 2021-12-16 | Overhead | R16 | 2020-02-21 | 1 |  | 176 | 475 | 650 | 2019 | 2021 | R16
162077162903 | 162039162903 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-25 | 2019-07-25 | 2019-08-30 | 2020-03-31 | 2020-06-09 | Underground | R16 | 2020-03-31 | 1 | 27 | 153 | 51 | 229 | 2019 | 2020 | R16
166118163268 | 167824163268 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE FOR UPGRADE UD | Commercial | 2019-07-02 | 2019-07-09 | 2019-09-04 | 2020-09-15 | 2023-09-26 | Underground | R16 | 2020-09-15 | 6 | 42 | 270 | 791 | 1106 | 2019 | 2023 | R16
168680169400 | 168689169400 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-23 | 2019-10-23 | 2019-10-23 | 2019-12-04 | 2020-01-02 | Overhead | R16 | 2019-12-04 | 1 |  | 31 | 22 | 52 | 2019 | 2020 | R16
167179174798 | 168131174798 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-21 | 2019-10-21 | 2019-12-18 | 2020-03-13 | 2020-03-16 | Underground | R16 | 2020-03-13 | 1 | 43 | 63 | 2 | 106 | 2019 | 2020 | R16
169910181708 | 169863181708 | NON-RESIDENTIAL - LODGING | UG R16 RESD AND NON RESD UD | Commercial | 2019-07-15 | 2019-07-15 | 2020-02-24 |  | 2021-11-04 | Underground | R16 |  | 1 | 161 |  |  | 604 | 2019 | 2021 | R16
160292336174 | 166465336174 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-29 | 2023-10-16 | 2023-10-20 | 2023-10-24 | 2023-11-03 | Overhead | R16 | 2023-10-24 | 12 | 5 | 3 | 9 | 26 | 2023 | 2023 | R16
167940163453 | 167361163453 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-26 | 2019-08-26 | 2019-09-05 | 2019-12-02 | 2019-12-03 | Underground | R16 | 2019-12-02 | 1 | 9 | 63 | 2 | 72 | 2019 | 2019 | R16
161209214310 | 161532214310 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-11-06 | 2019-11-12 | 2020-12-18 | 2021-11-22 | 2021-12-21 | Underground | R16 | 2021-11-22 | 5 | 289 | 242 | 22 | 555 | 2019 | 2021 | R16
163795172264 | 165578172264 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-09 | 2019-10-31 | 2019-11-19 | 2019-11-20 | 2021-11-10 | Overhead | R16 | 2019-11-20 | 17 | 14 | 2 | 516 | 546 | 2019 | 2021 | R16
162552175339 | 165178175339 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-11-26 | 2019-11-26 | 2019-12-31 | 2020-07-01 | 2020-07-09 | Underground | R16 | 2020-07-01 | 1 | 26 | 132 | 7 | 163 | 2019 | 2020 | R16
161040158561 | 163881158561 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-06-13 | 2019-06-14 | 2019-07-22 | 2019-10-01 | 2020-04-24 | Underground | R16 | 2019-10-01 | 2 | 27 | 52 | 149 | 227 | 2019 | 2020 | R16
162727175422 | 168061175422 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-12 | 2019-12-12 | 2019-12-30 | 2020-01-23 | 2020-01-24 | Underground | R16 | 2020-01-23 | 1 | 13 | 19 | 2 | 32 | 2019 | 2020 | R16
162644163068 | 168809163068 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-03 | 2019-09-03 | 2019-09-03 | 2019-09-09 | 2019-11-13 | Overhead | R16 | 2019-09-09 | 1 |  | 5 | 48 | 52 | 2019 | 2019 | R16
160030188909 | 166479188909 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Commercial | 2019-10-12 | 2020-03-31 | 2020-04-24 | 2020-05-15 | 2020-08-12 | Overhead | R16 | 2020-05-15 | 122 | 19 | 16 | 64 | 218 | 2019 | 2020 | R16
165277162752 | 167070162752 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-23 | 2019-08-29 | 2019-08-29 | 2020-05-20 | 2020-07-22 | Overhead | R16 | 2020-05-20 | 5 |  | 190 | 46 | 239 | 2019 | 2020 | R16
169566165035 | 161155165035 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-16 | 2019-09-16 | 2019-09-18 | 2019-10-22 | 2019-10-23 | Underground | R16 | 2019-10-22 | 1 | 3 | 25 | 2 | 28 | 2019 | 2019 | R16
165658164724 | 166216164724 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-19 | 2019-08-19 | 2019-09-16 | 2019-10-16 | 2019-10-17 | Underground | R16 | 2019-10-16 | 1 | 21 | 23 | 2 | 44 | 2019 | 2019 | R16
166885155708 | 164192155708 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-06-14 | 2019-06-18 | 2019-06-18 | 2022-12-16 | 2023-06-07 | Overhead | R16 | 2022-12-16 | 3 |  | 914 | 124 | 1039 | 2019 | 2023 | R16
167371172265 | 168130172265 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-21 | 2019-10-21 | 2019-11-19 | 2020-01-28 | 2020-01-29 | Underground | R16 | 2020-01-28 | 1 | 22 | 51 | 2 | 73 | 2019 | 2020 | R16
164883172903 | 169718172903 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-10-28 | 2019-11-12 | 2019-11-25 | 2019-11-26 | 2020-02-06 | Overhead | R16 | 2019-11-26 | 12 | 10 | 2 | 53 | 74 | 2019 | 2020 | R16
167450173588 | 166265173588 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-05 | 2019-12-05 | 2019-12-05 | 2020-01-30 | 2020-01-31 | Overhead | R16 | 2020-01-30 | 1 |  | 41 | 2 | 42 | 2019 | 2020 | R16
169505159709 | 160449159709 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-07-17 | 2019-07-17 | 2019-08-01 | 2020-01-28 | 2022-08-24 | Underground | R16 | 2020-01-28 | 1 | 12 | 129 | 672 | 811 | 2019 | 2022 | R16
166072169528 | 160846169528 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-12 | 2019-09-12 | 2019-10-24 | 2019-11-19 | 2019-11-20 | Underground | R16 | 2019-11-19 | 1 | 31 | 19 | 2 | 50 | 2019 | 2019 | R16
162597170907 | 166237170907 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-06-26 | 2019-10-15 | 2019-11-06 | 2020-02-10 | 2020-10-21 | Underground | R16 | 2020-02-10 | 80 | 17 | 69 | 183 | 346 | 2019 | 2020 | R16
162786155080 | 163358155080 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-06-11 | 2019-06-11 | 2019-06-11 | 2019-06-14 | 2019-06-14 | Underground | R16 | 2019-06-14 | 1 |  | 4 |  | 4 | 2019 | 2019 | R16
160173173882 | 166791173882 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-07 | 2019-12-07 | 2019-12-07 | 2020-02-24 | 2020-06-09 | Overhead | R16 | 2020-02-24 | 0 |  | 56 | 77 | 132 | 2019 | 2020 | R16
166041162364 | 167454162364 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-08-26 | 2019-08-26 | 2019-08-26 | 2019-11-25 | 2019-11-27 | Overhead | R16 | 2019-11-25 | 1 |  | 66 | 3 | 68 | 2019 | 2019 | R16
160635169067 | 165692169067 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-06-24 | 2019-06-24 | 2019-10-21 | 2021-02-24 | 2021-03-31 | Underground | R16 | 2021-02-24 | 1 | 86 | 353 | 26 | 463 | 2019 | 2021 | R16
167194157079 | 168149157079 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-05 | 2019-07-05 | 2019-07-05 | 2019-08-09 | 2019-08-09 | Overhead | R16 | 2019-08-09 | 1 |  | 26 |  | 26 | 2019 | 2019 | R16
166326175321 | 166389175321 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-06 | 2019-12-30 | 2019-12-30 | 2020-03-20 | 2020-06-09 | Overhead | R16 | 2020-03-20 | 17 |  | 60 | 58 | 133 | 2019 | 2020 | R16
169547160230 | 163756160230 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-05 | 2019-08-05 | 2019-08-05 | 2020-02-18 | 2020-02-19 | Overhead | R16 | 2020-02-18 | 1 |  | 142 | 2 | 143 | 2019 | 2020 | R16
162247179134 | 167245179134 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-10 | 2020-02-04 | 2020-02-04 | 2020-02-14 | 2020-06-09 | Overhead | R16 | 2020-02-14 | 41 |  | 9 | 83 | 131 | 2019 | 2020 | R16
162592159125 | 162242159125 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-26 | 2019-07-26 | 2019-07-26 | 2019-08-20 | 2019-08-21 | Overhead | R16 | 2019-08-20 | 1 |  | 18 | 2 | 19 | 2019 | 2019 | R16
160888167607 | 166142167607 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-10 | 2019-10-10 | 2019-10-10 | 2019-10-15 | 2019-10-21 | Overhead | R16 | 2019-10-15 | 1 |  | 4 | 5 | 8 | 2019 | 2019 | R16
160572174266 | 164012174266 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-01 | 2019-10-01 | 2019-12-12 | 2020-08-14 | 2020-08-17 | Underground | R16 | 2020-08-14 | 1 | 53 | 177 | 2 | 230 | 2019 | 2020 | R16
164746182089 | 165371182089 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-08-13 | 2019-08-14 | 2020-02-27 | 2020-11-30 | 2020-12-28 | Underground | R16 | 2020-11-30 | 2 | 142 | 198 | 21 | 360 | 2019 | 2020 | R16
161131213872 | 165411213872 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | R16 RESD AND NON RESD US | Commercial | 2019-11-27 | 2020-11-04 | 2020-12-14 | 2021-05-19 | 2021-07-29 | Underground | R16 | 2021-05-19 | 246 | 29 | 113 | 52 | 437 | 2019 | 2021 | R16
162468176903 | 163762176903 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-30 | 2019-09-30 | 2020-01-14 | 2020-03-26 | 2023-06-07 | Underground | R16 | 2020-03-26 | 1 | 77 | 53 | 835 | 963 | 2019 | 2023 | R16
169306202780 | 160240202780 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-30 | 2019-10-30 | 2020-09-04 | 2020-11-25 | 2020-12-07 | Underground | R16 | 2020-11-25 | 1 | 223 | 59 | 9 | 289 | 2019 | 2020 | R16
165815164220 | 167757164220 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-28 | 2019-09-12 | 2019-09-12 | 2019-12-31 | 2020-01-08 | Underground | R16 | 2019-12-31 | 12 |  | 79 | 7 | 96 | 2019 | 2020 | R16
169800170454 | 169155170454 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-24 | 2019-10-24 | 2019-11-01 | 2020-02-11 | 2020-10-28 | Underground | R16 | 2020-02-11 | 1 | 7 | 73 | 187 | 265 | 2019 | 2020 | R16
168712171202 | 169720171202 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-28 | 2019-10-28 | 2019-11-08 | 2020-01-15 | 2020-01-15 | Underground | R16 | 2020-01-15 | 1 | 10 | 49 |  | 58 | 2019 | 2020 | R16
165357174409 | 168234174409 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-12-13 | 2019-12-13 | 2019-12-13 | 2020-02-24 | 2020-06-09 | Overhead | R16 | 2020-02-24 | 1 |  | 52 | 77 | 128 | 2019 | 2020 | R16
169449155659 | 164286155659 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-17 | 2019-06-17 | 2019-06-18 | 2019-06-28 | 2019-07-01 | Overhead | R16 | 2019-06-28 | 1 | 2 | 9 | 2 | 11 | 2019 | 2019 | R16
162133161553 | 166363161553 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-19 | 2019-08-19 | 2019-08-19 | 2019-09-04 | 2019-09-05 | Overhead | R16 | 2019-09-04 | 1 |  | 13 | 2 | 14 | 2019 | 2019 | R16
164552168536 | 167456168536 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-18 | 2019-10-18 | 2019-10-18 | 2019-12-03 | 2020-01-02 | Overhead | R16 | 2019-12-03 | 1 |  | 33 | 23 | 55 | 2019 | 2020 | R16
168549169402 | 168880169402 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-23 | 2019-10-23 | 2019-10-23 | 2019-12-06 | 2019-12-09 | Overhead | R16 | 2019-12-06 | 1 |  | 33 | 2 | 34 | 2019 | 2019 | R16
161556162068 | 167118162068 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-24 | 2019-08-24 | 2019-08-24 | 2019-09-20 | 2019-09-24 | Overhead | R16 | 2019-09-20 | 0 |  | 20 | 3 | 22 | 2019 | 2019 | R16
163689169273 | 164343169273 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-07 | 2019-08-07 | 2019-10-24 | 2019-12-10 | 2020-02-05 | Underground | R16 | 2019-12-10 | 1 | 57 | 34 | 42 | 131 | 2019 | 2020 | R16
167958168808 | 169832168808 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-15 | 2019-07-15 | 2019-10-18 | 2019-12-09 | 2019-12-10 | Overhead | R16 | 2019-12-09 | 1 | 70 | 37 | 2 | 107 | 2019 | 2019 | R16
165250167712 | 166486167712 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2019-10-11 | 2019-10-11 | 2019-10-11 | 2019-11-03 | 2021-11-10 | Overhead | R16 | 2019-11-03 | 1 |  | 16 | 528 | 544 | 2019 | 2021 | R16
162150173156 | 163477173156 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-18 | 2019-11-27 | 2019-12-02 | 2020-02-14 | 2020-06-17 | Overhead | R16 | 2020-02-14 | 8 | 4 | 55 | 89 | 153 | 2019 | 2020 | R16
166193169440 | 168706169440 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-23 | 2019-10-23 | 2019-10-24 | 2019-11-29 | 2019-12-02 | Overhead | R16 | 2019-11-29 | 1 | 2 | 27 | 2 | 29 | 2019 | 2019 | R16
163657305091 | 168253305091 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-12-13 | 2019-12-13 | 2023-01-30 | 2023-01-05 | 2023-03-24 | Underground | R16 | 2023-01-05 | 1 | 817 |  | 57 | 856 | 2019 | 2023 | R16
164428304587 | 165856304587 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2019-10-09 | 2020-05-16 | 2023-01-10 | 2023-10-12 | 2023-11-21 | Underground | R16 | 2023-10-12 | 158 | 692 | 198 | 29 | 1075 | 2019 | 2023 | R16
161177162773 | 166110162773 | NON-RESIDENTIAL - LARGE OFFICE | R16 RESD AND NON RESD US | Commercial | 2019-06-25 | 2019-06-28 | 2019-08-30 | 2020-05-27 | 2020-09-30 | Underground | R16 | 2020-05-27 | 4 | 46 | 194 | 91 | 332 | 2019 | 2020 | R16
164046158575 | 161293158575 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2019-07-22 | 2019-07-22 | 2019-07-22 | 2020-01-22 | 2020-01-23 | Overhead | R16 | 2020-01-22 | 1 |  | 133 | 2 | 134 | 2019 | 2020 | R16
161920168312 | 167143168312 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-15 | 2019-10-15 | 2019-10-16 | 2020-09-23 | 2020-12-29 | Underground | R16 | 2020-09-23 | 1 | 2 | 246 | 70 | 316 | 2019 | 2020 | R16
160022309380 | 160249309380 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-02-13 | 2023-02-13 | 2023-02-13 |  | 2023-08-04 | Underground | R16 | 2023-04-13 | 1 |  | 44 | 82 | 125 | 2023 | 2023 | R16
162145167150 | 165106167150 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-08 | 2019-10-08 | 2019-10-08 | 2019-12-06 | 2019-12-17 | Overhead | R16 | 2019-12-06 | 1 |  | 44 | 8 | 51 | 2019 | 2019 | R16
167095170369 | 160666170369 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-01 | 2019-11-01 | 2019-11-01 | 2019-11-25 | 2021-12-16 | Overhead | R16 | 2019-11-25 | 1 |  | 17 | 539 | 555 | 2019 | 2021 | R16
163791180371 | 169440180371 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-25 | 2019-10-25 | 2020-02-13 | 2020-10-06 | 2021-01-20 | Underground | R16 | 2020-10-06 | 1 | 80 | 169 | 77 | 324 | 2019 | 2021 | R16
160245172411 | 164370172411 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-20 | 2019-11-20 | 2019-11-20 | 2020-02-12 | 2020-06-09 | Overhead | R16 | 2020-02-12 | 1 |  | 61 | 85 | 145 | 2019 | 2020 | R16
160159318861 | 169209318861 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-11 | 2023-05-11 | 2023-05-11 | 2023-06-23 | 2023-08-09 | Overhead | R16 | 2023-06-23 | 1 |  | 32 | 34 | 65 | 2023 | 2023 | R16
166810171690 | 167020171690 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-22 | 2019-08-22 | 2019-11-13 | 2020-01-03 | 2020-01-07 | Underground | R16 | 2020-01-03 | 1 | 60 | 38 | 3 | 99 | 2019 | 2020 | R16
165935168072 | 168454168072 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-30 | 2019-09-06 | 2019-10-14 | 2020-01-02 | 2023-06-07 | Underground | R16 | 2020-01-02 | 6 | 27 | 59 | 895 | 984 | 2019 | 2023 | R16
168282167705 | 160826167705 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-13 | 2019-10-10 | 2019-10-10 | 2019-11-19 | 2019-11-27 | Overhead | R16 | 2019-11-19 | 20 |  | 29 | 7 | 54 | 2019 | 2019 | R16
161495173456 | 163406173456 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-11 | 2019-06-11 | 2019-12-03 | 2020-05-20 | 2020-06-04 | Underground | R16 | 2020-05-20 | 1 | 126 | 122 | 12 | 258 | 2019 | 2020 | R16
165536174356 | 168248174356 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-13 | 2019-12-13 | 2019-12-13 | 2020-01-08 | 2020-01-09 | Overhead | R16 | 2020-01-08 | 1 |  | 19 | 2 | 20 | 2019 | 2020 | R16
161137163912 | 169958163912 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2019-09-09 | 2019-09-09 | 2019-09-09 | 2022-06-10 | 2022-06-28 | Overhead | R16 | 2022-06-10 | 1 |  | 720 | 13 | 732 | 2019 | 2022 | R16
163176167539 | 165680167539 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-08 | 2019-10-08 | 2019-10-09 | 2020-07-09 | 2020-07-10 | Overhead | R16 | 2020-07-09 | 1 | 2 | 197 | 2 | 199 | 2019 | 2020 | R16
164831188593 | 167387188593 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE FOR UPGRADE UD | Residential | 2019-10-16 | 2020-04-01 | 2020-04-22 | 2020-08-14 | 2022-02-01 | Underground | R16 | 2020-08-14 | 121 | 16 | 83 | 383 | 600 | 2019 | 2022 | R16
162571158403 | 163452158403 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-11 | 2019-06-11 | 2019-07-18 | 2019-08-05 | 2019-08-05 | Underground | R16 | 2019-08-05 | 1 | 28 | 13 |  | 40 | 2019 | 2019 | R16
162785166650 | 160192166650 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-10 | 2019-09-10 | 2019-10-02 | 2021-08-13 | 2021-08-13 | Underground | R16 | 2021-08-13 | 1 | 17 | 488 |  | 504 | 2019 | 2021 | R16
162141170636 | 166704170636 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-08-21 | 2019-10-12 | 2019-11-05 | 2020-02-12 | 2020-04-27 | Underground | R16 | 2020-02-12 | 38 | 17 | 72 | 54 | 179 | 2019 | 2020 | R16
161785171745 | 161826171745 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-09-19 | 2019-09-19 | 2019-11-13 | 2020-06-10 | 2020-09-30 | Underground | R16 | 2020-06-10 | 1 | 40 | 151 | 81 | 270 | 2019 | 2020 | R16
160587163152 | 161713163152 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-24 | 2019-07-25 | 2019-09-03 | 2019-10-08 | 2019-10-09 | Underground | R16 | 2019-10-08 | 2 | 29 | 26 | 2 | 56 | 2019 | 2019 | R16
167205174387 | 166949174387 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-09 | 2019-12-09 | 2019-12-16 | 2020-01-21 | 2020-01-22 | Underground | R16 | 2020-01-21 | 1 | 6 | 27 | 2 | 33 | 2019 | 2020 | R16
167103182922 | 162598182922 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-09-24 | 2019-11-20 | 2020-03-04 | 2020-11-17 | 2021-01-28 | Underground | R16 | 2020-11-17 | 42 | 76 | 185 | 53 | 353 | 2019 | 2021 | R16
167528171879 | 161739171879 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-11-07 | 2019-11-07 | 2019-11-15 | 2021-09-28 | 2021-11-09 | Underground | R16 | 2021-09-28 | 1 | 7 | 488 | 31 | 524 | 2019 | 2021 | R16
167598163441 | 169016163441 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-09-04 | 2019-09-04 | 2019-09-05 | 2020-06-22 | 2021-12-16 | Underground | R16 | 2020-06-22 | 1 | 2 | 208 | 389 | 597 | 2019 | 2021 | R16
164790163336 | 169391163336 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-05 | 2019-09-05 | 2019-09-05 | 2020-07-15 | 2020-07-17 | Overhead | R16 | 2020-07-15 | 1 |  | 225 | 3 | 227 | 2019 | 2020 | R16
165720159962 | 163456159962 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-02 | 2019-08-02 | 2019-08-02 | 2019-09-06 | 2019-09-09 | Overhead | R16 | 2019-09-06 | 1 |  | 26 | 2 | 27 | 2019 | 2019 | R16
162073159524 | 162007159524 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-07-25 | 2019-07-25 | 2019-07-29 | 2019-09-13 | 2019-09-16 | Underground | R16 | 2019-09-13 | 1 | 3 | 35 | 2 | 38 | 2019 | 2019 | R16
161579178502 | 168693178502 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH CP R16 WORK RELO TO UG | Commercial | 2019-10-23 | 2019-10-23 | 2020-01-28 | 2020-03-23 | 2023-02-10 | Overhead | R16 | 2020-03-23 | 1 | 70 | 40 | 755 | 863 | 2019 | 2023 | R16
162882156844 | 167582156844 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2019-09-13 | 2019-09-19 | Overhead | R16 | 2019-09-13 | 1 |  | 55 | 5 | 59 | 2019 | 2019 | R16
167223187344 | 168471187344 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-16 | 2020-04-13 | 2020-04-13 | 2020-04-23 | 2020-05-27 | Underground | R16 | 2020-04-23 | 86 |  | 9 | 25 | 118 | 2019 | 2020 | R16
165513162307 | 165728162307 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-06-25 | 2019-07-02 | 2019-08-26 | 2020-01-09 | 2020-01-10 | Underground | R16 | 2020-01-09 | 6 | 40 | 99 | 2 | 144 | 2019 | 2020 | R16
162526166875 | 164753166875 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-10-04 | 2019-10-04 | 2019-10-04 | 2019-11-11 | 2019-11-13 | Overhead | R16 | 2019-11-11 | 1 |  | 27 | 3 | 29 | 2019 | 2019 | R16
169299199318 | 167258199318 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE FOR UPGRADE UD | Commercial | 2019-10-16 | 2020-05-28 | 2020-08-03 | 2020-09-23 | 2020-11-10 | Underground | R16 | 2020-09-23 | 162 | 48 | 38 | 35 | 280 | 2019 | 2020 | R16
162201201013 | 165790201013 | NON-RESIDENTIAL - HEALTH CARE | UG R16 RESD AND NON RESD UD | Commercial | 2019-06-24 | 2019-06-24 | 2020-08-19 | 2021-12-02 | 2022-01-06 | Underground | R16 | 2021-12-02 | 1 | 303 | 337 | 26 | 664 | 2019 | 2022 | R16
165394159594 | 165839159594 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-06-25 | 2019-06-25 | 2019-07-31 | 2019-09-24 | 2019-10-28 | Underground | R16 | 2019-09-24 | 1 | 27 | 40 | 25 | 90 | 2019 | 2019 | R16
162180212890 | 168251212890 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-07-03 | 2020-09-25 | 2020-12-07 | 2022-01-19 | 2022-02-08 | Underground | R16 | 2022-01-19 | 323 | 52 | 293 | 15 | 680 | 2019 | 2022 | R16
161265175567 | 163203175567 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-14 | 2019-11-22 | 2020-01-02 | 2020-04-02 | 2020-04-03 | Overhead | R16 | 2020-04-02 | 7 | 30 | 66 | 2 | 102 | 2019 | 2020 | R16
163423173155 | 164982173155 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-24 | 2019-11-27 | 2019-12-02 | 2020-02-24 | 2020-07-08 | Overhead | R16 | 2020-02-24 | 3 | 4 | 61 | 98 | 163 | 2019 | 2020 | R16
164037155401 | 164196155401 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-06-14 | 2019-06-14 | 2019-06-14 | 2019-12-19 | 2019-12-20 | Underground | R16 | 2019-12-19 | 1 |  | 135 | 2 | 136 | 2019 | 2019 | R16
161856167627 | 162826167627 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-25 | 2019-09-25 | 2019-10-09 | 2019-11-25 | 2019-11-27 | Underground | R16 | 2019-11-25 | 1 | 11 | 34 | 3 | 46 | 2019 | 2019 | R16
167975175303 | 163283175303 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-26 | 2019-12-30 | 2019-12-30 | 2020-01-02 | 2020-03-25 | Underground | R16 | 2020-01-02 | 68 |  | 4 | 60 | 130 | 2019 | 2020 | R16
169245170254 | 169165170254 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-25 | 2019-10-25 | 2019-10-31 | 2020-02-15 | 2020-02-18 | Underground | R16 | 2020-02-15 | 1 | 5 | 77 | 2 | 83 | 2019 | 2020 | R16
167247174457 | 168268174457 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-22 | 2019-10-25 | 2019-12-13 | 2020-04-30 | 2020-05-01 | Overhead | R16 | 2020-04-30 | 4 | 36 | 100 | 2 | 139 | 2019 | 2020 | R16
161843168338 | 167223168338 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-10-16 | 2019-10-16 | 2019-10-17 | 2019-10-17 | 2022-03-28 | Overhead | R16 | 2019-10-17 | 1 | 2 |  | 638 | 639 | 2019 | 2022 | R16
164883172901 | 169716172901 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-10-28 | 2019-11-12 | 2019-11-25 | 2019-11-25 | 2020-02-05 | Overhead | R16 | 2019-11-25 | 12 | 10 |  | 53 | 73 | 2019 | 2020 | R16
168111177077 | 168472177077 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-22 | 2019-10-22 | 2020-01-17 | 2020-02-27 | 2020-02-28 | Underground | R16 | 2020-02-27 | 1 | 64 | 30 | 2 | 94 | 2019 | 2020 | R16
169449154874 | 163305154874 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-11 | 2019-06-11 | 2019-06-11 | 2019-07-17 | 2019-07-17 | Overhead | R16 | 2019-07-17 | 1 |  | 27 |  | 27 | 2019 | 2019 | R16
169342191527 | 169734191527 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH CP R16 WORK RELO TO UG | Commercial | 2019-10-28 | 2019-10-31 | 2020-05-19 | 2020-06-09 | 2020-06-12 | Overhead | R16 | 2020-06-09 | 4 | 144 | 16 | 4 | 165 | 2019 | 2020 | R16
167987171955 | 161107171955 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-14 | 2019-09-14 | 2019-11-18 | 2020-03-13 | 2020-03-17 | Underground | R16 | 2020-03-13 | 0 | 46 | 85 | 3 | 132 | 2019 | 2020 | R16
165016165134 | 164933165134 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-12 | 2019-08-12 | 2019-09-19 | 2020-02-18 | 2020-06-09 | Underground | R16 | 2020-02-18 | 1 | 29 | 109 | 81 | 217 | 2019 | 2020 | R16
164243171901 | 162549171901 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-11-12 | 2019-11-12 | 2019-11-14 | 2019-11-19 | 2020-02-05 | Overhead | R16 | 2019-11-19 | 1 | 3 | 4 | 57 | 62 | 2019 | 2020 | R16
167892181914 | 168753181914 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-07-08 | 2019-08-14 | 2020-02-25 | 2020-11-23 | 2021-01-12 | Underground | R16 | 2020-11-23 | 28 | 140 | 195 | 37 | 397 | 2019 | 2021 | R16
167849162824 | 168421162824 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-29 | 2019-08-29 | 2019-08-29 | 2019-10-04 | 2019-10-07 | Overhead | R16 | 2019-10-04 | 1 |  | 27 | 2 | 28 | 2019 | 2019 | R16
166230154984 | 163110154984 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-06-10 | 2019-06-10 | 2019-06-10 | 2020-01-09 | 2021-11-10 | Underground | R16 | 2020-01-09 | 1 |  | 154 | 480 | 633 | 2019 | 2021 | R16
168094201992 | 168095201992 | Electric Vehicle | UG R16 RESD AND NON RESD UD | Commercial | 2019-12-12 | 2020-06-15 | 2020-08-28 | 2021-01-26 | 2021-03-30 | Underground | R16 | 2021-01-26 | 133 | 55 | 108 | 46 | 339 | 2019 | 2021 | R16
161132160143 | 161220160143 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-07-22 | 2019-07-22 | 2019-08-05 | 2020-01-23 | 2020-01-24 | Underground | R16 | 2020-01-23 | 1 | 11 | 124 | 2 | 135 | 2019 | 2020 | R16
163329168237 | 163703168237 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OD | Residential | 2019-08-05 | 2019-08-05 | 2019-10-16 | 2019-10-17 | 2020-02-05 | Overhead | R16 | 2019-10-17 | 1 | 53 | 2 | 80 | 133 | 2019 | 2020 | R16
166694158851 | 160826158851 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-18 | 2019-07-22 | 2019-07-24 | 2019-08-21 | 2020-02-19 | Overhead | R16 | 2019-08-21 | 3 | 3 | 21 | 131 | 155 | 2019 | 2020 | R16
162918167160 | 169930167160 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-09 | 2019-09-09 | 2019-10-06 |  | 2022-10-19 | Underground | R16 |  | 1 | 20 |  |  | 813 | 2019 | 2022 | R16
165553161830 | 166733161830 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-21 | 2019-08-21 | 2019-08-21 |  | 2022-10-20 | Overhead | R16 |  | 1 |  |  |  | 827 | 2019 | 2022 | R16
163573161179 | 167442161179 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-01 | 2019-07-01 | 2019-08-15 | 2019-12-20 | 2019-12-18 | Underground | R16 | 2019-12-20 | 1 | 34 | 92 |  | 123 | 2019 | 2019 | R16
169250161308 | 160751161308 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-18 | 2019-07-18 | 2019-08-16 | 2020-01-30 | 2020-02-03 | Underground | R16 | 2020-01-30 | 1 | 22 | 120 | 3 | 143 | 2019 | 2020 | R16
169985173810 | 160379173810 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-10 | 2019-09-10 | 2019-12-07 | 2020-03-05 | 2020-03-06 | Underground | R16 | 2020-03-05 | 1 | 64 | 64 | 2 | 129 | 2019 | 2020 | R16
169028165776 | 161866165776 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-19 | 2019-09-19 | 2019-09-26 | 2021-05-20 | 2021-05-21 | Underground | R16 | 2021-05-20 | 1 | 6 | 431 | 2 | 437 | 2019 | 2021 | R16
162143163743 | 165261163743 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-19 | 2019-06-19 | 2019-09-07 | 2019-11-12 | 2019-11-21 | Underground | R16 | 2019-11-12 | 1 | 58 | 47 | 8 | 112 | 2019 | 2019 | R16
164325169914 | 169761169914 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-28 | 2019-10-28 | 2019-10-28 | 2020-01-30 | 2020-02-03 | Overhead | R16 | 2020-01-30 | 1 |  | 69 | 3 | 71 | 2019 | 2020 | R16
166089159576 | 169295159576 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-10 | 2019-07-10 | 2019-07-30 | 2019-09-27 | 2019-10-11 | Underground | R16 | 2019-09-27 | 1 | 15 | 44 | 11 | 68 | 2019 | 2019 | R16
167991162566 | 167968162566 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-08-28 | 2019-08-28 | 2019-08-28 | 2019-08-31 | 2019-09-03 | Overhead | R16 | 2019-08-31 | 1 |  | 3 | 2 | 5 | 2019 | 2019 | R16
164025319669 | 163411319669 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-13 | 2023-04-13 | 2023-05-19 | 2023-07-19 | 2023-08-09 | Underground | R16 | 2023-07-19 | 1 | 27 | 44 | 16 | 85 | 2023 | 2023 | R16
161666169561 | 169130169561 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-24 | 2019-10-24 | 2019-10-24 | 2019-11-06 | 2019-11-07 | Overhead | R16 | 2019-11-06 | 1 |  | 10 | 2 | 11 | 2019 | 2019 | R16
168565166700 | 169043166700 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-03 | 2019-09-03 | 2019-10-02 | 2020-04-29 | 2020-07-10 | Underground | R16 | 2020-04-29 | 1 | 22 | 151 | 53 | 224 | 2019 | 2020 | R16
169511155548 | 164415155548 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-17 | 2019-06-17 | 2019-06-17 | 2019-08-27 | 2019-09-04 | Overhead | R16 | 2019-08-27 | 1 |  | 52 | 7 | 58 | 2019 | 2019 | R16
168289173546 | 169671173546 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-28 | 2019-10-28 | 2019-12-04 | 2020-02-25 | 2020-02-26 | Underground | R16 | 2020-02-25 | 1 | 28 | 60 | 2 | 88 | 2019 | 2020 | R16
163640163425 | 169304163425 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-05 | 2019-09-05 | 2019-09-05 | 2019-11-27 | 2019-12-16 | Overhead | R16 | 2019-11-27 | 1 |  | 60 | 14 | 73 | 2019 | 2019 | R16
163790158268 | 165791158268 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-24 | 2019-06-24 | 2019-07-19 | 2019-07-23 | 2019-11-14 | Underground | R16 | 2019-07-23 | 1 | 20 | 3 | 83 | 104 | 2019 | 2019 | R16
168711165856 | 163294165856 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-27 | 2019-09-27 | 2019-09-27 | 2019-10-02 | 2021-11-13 | Overhead | R16 | 2019-10-02 | 1 |  | 4 | 553 | 556 | 2019 | 2021 | R16
163993192334 | 164915192334 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-04 | 2019-10-04 | 2020-05-28 | 2020-07-24 | 2020-07-29 | Underground | R16 | 2020-07-24 | 1 | 170 | 42 | 4 | 214 | 2019 | 2020 | R16
164756295000 | 163287295000 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2022-09-23 | 2022-09-26 | 2022-09-26 | 2023-07-25 | 2023-10-06 | Underground | R16 | 2023-07-25 | 2 |  | 217 | 54 | 271 | 2022 | 2023 | R16
165753168806 | 166267168806 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-19 | 2019-08-19 | 2019-10-18 | 2020-01-21 | 2020-01-29 | Underground | R16 | 2020-01-21 | 1 | 45 | 68 | 7 | 118 | 2019 | 2020 | R16
163028174301 | 168019174301 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-12 | 2019-12-12 | 2019-12-12 | 2020-03-03 | 2020-06-09 | Overhead | R16 | 2020-03-03 | 1 |  | 59 | 71 | 129 | 2019 | 2020 | R16
167407158280 | 160609158280 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-17 | 2019-07-17 | 2019-07-17 | 2019-08-09 | 2019-08-12 | Overhead | R16 | 2019-08-09 | 1 |  | 18 | 2 | 19 | 2019 | 2019 | R16
165119163388 | 169079163388 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-04 | 2019-09-04 | 2019-09-04 | 2020-02-14 | 2020-06-09 | Overhead | R16 | 2020-02-14 | 1 |  | 118 | 83 | 200 | 2019 | 2020 | R16
169390173634 | 163196173634 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-15 | 2019-11-15 | 2019-12-06 | 2020-03-16 | 2020-07-09 | Underground | R16 | 2020-03-16 | 1 | 16 | 72 | 84 | 170 | 2019 | 2020 | R16
165084165654 | 162648165654 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-24 | 2019-09-24 | 2019-09-24 | 2020-03-13 | 2020-03-17 | Overhead | R16 | 2020-03-13 | 1 |  | 124 | 3 | 126 | 2019 | 2020 | R16
168717161601 | 164942161601 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-12 | 2019-08-19 | 2019-08-19 | 2019-09-06 | 2019-11-06 | Overhead | R16 | 2019-09-06 | 6 |  | 15 | 44 | 63 | 2019 | 2019 | R16
165820161269 | 169894161269 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-15 | 2019-07-25 | 2019-08-15 |  | 2019-09-19 | Underground | R16 |  | 9 | 16 |  |  | 49 | 2019 | 2019 | R16
163452164843 | 160880164843 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-09-12 | 2019-09-12 | 2019-09-17 | 2021-05-12 | 2022-08-01 | Underground | R16 | 2021-05-12 | 1 | 4 | 432 | 319 | 753 | 2019 | 2022 | R16
166588174421 | 168242174421 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-12-13 | 2019-12-13 | 2019-12-13 | 2020-06-03 | 2020-06-04 | Overhead | R16 | 2020-06-03 | 1 |  | 124 | 2 | 125 | 2019 | 2020 | R16
165166158889 | 165654158889 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-22 | 2019-06-22 | 2019-07-25 | 2019-12-27 | 2019-12-30 | Underground | R16 | 2019-12-27 | 0 | 24 | 112 | 2 | 136 | 2019 | 2019 | R16
167754171982 | 169164171982 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-25 | 2019-11-15 | 2019-11-15 | 2020-03-13 | 2020-06-09 | Overhead | R16 | 2020-03-13 | 16 |  | 86 | 63 | 163 | 2019 | 2020 | R16
164036158600 | 169076158600 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-07-09 | 2019-07-09 | 2019-07-22 | 2019-08-21 | 2019-09-12 | Underground | R16 | 2019-08-21 | 1 | 10 | 23 | 17 | 48 | 2019 | 2019 | R16
163919169269 | 168754169269 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-23 | 2019-10-23 | 2019-10-23 | 2019-11-21 | 2019-11-21 | Overhead | R16 | 2019-11-21 | 1 |  | 22 |  | 22 | 2019 | 2019 | R16
168532169578 | 168554169578 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-30 | 2019-08-30 | 2019-10-25 | 2019-12-03 | 2020-01-28 | Overhead | R16 | 2019-12-03 | 1 | 41 | 28 | 41 | 108 | 2019 | 2020 | R16
169607163450 | 162391163450 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-29 | 2019-08-06 | 2019-09-05 | 2019-09-06 | 2019-11-21 | Underground | R16 | 2019-09-06 | 7 | 23 | 2 | 55 | 84 | 2019 | 2019 | R16
167250165661 | 162545165661 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-24 | 2019-09-24 | 2019-09-24 | 2020-03-25 | 2020-03-25 | Overhead | R16 | 2020-03-25 | 1 |  | 132 |  | 132 | 2019 | 2020 | R16
164664170279 | 167969170279 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-22 | 2019-10-22 | 2019-11-01 | 2020-01-10 | 2023-04-22 | Overhead | R16 | 2020-01-10 | 1 | 9 | 51 | 856 | 914 | 2019 | 2023 | R16
163049164744 | 163758164744 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-05 | 2019-08-05 | 2019-09-16 | 2019-11-08 | 2019-11-14 | Underground | R16 | 2019-11-08 | 1 | 31 | 40 | 5 | 74 | 2019 | 2019 | R16
167190164102 | 160357164102 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-11 | 2019-09-11 | 2019-09-11 | 2019-11-15 | 2020-06-09 | Overhead | R16 | 2019-11-15 | 1 |  | 48 | 148 | 195 | 2019 | 2020 | R16
162148166399 | 163051166399 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-09-25 | 2019-09-25 | 2019-10-02 | 2019-10-07 | 2019-10-08 | Overhead | R16 | 2019-10-07 | 1 | 6 | 4 | 2 | 10 | 2019 | 2019 | R16
167864162806 | 168510162806 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-30 | 2019-08-30 | 2019-08-30 | 2019-10-04 | 2019-10-07 | Overhead | R16 | 2019-10-04 | 1 |  | 26 | 2 | 27 | 2019 | 2019 | R16
165210341650 | 168562341650 | RESIDENTIAL - SINGLE FAMILY ATTACHED | OH R16 RES NON RES OS | Residential | 2023-12-05 | 2023-12-05 | 2023-12-05 | 2023-12-12 | 2023-12-20 | Overhead | R16 | 2023-12-12 | 1 |  | 6 | 7 | 12 | 2023 | 2023 | R16
166846341237 | 164451341237 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-11-07 | 2023-11-13 | 2023-12-01 | 2023-12-01 | 2023-12-08 | Overhead | R16 | 2023-12-01 | 5 | 15 |  | 6 | 24 | 2023 | 2023 | R16
165691340526 | 164818340526 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2023-11-09 | 2023-11-17 | 2023-11-21 | 2023-12-15 | 2023-12-27 | Underground | R16 | 2023-12-15 | 7 | 3 | 19 | 9 | 35 | 2023 | 2023 | R16
164326339153 | 164458339153 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-11-08 | 2023-11-09 | 2023-11-09 | 2023-11-10 | 2023-11-10 | Overhead | R16 | 2023-11-10 | 2 |  | 2 |  | 3 | 2023 | 2023 | R16
165330308807 | 165267308807 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-21 | 2023-01-21 | 2023-02-08 |  | 2023-06-23 | Underground | R16 | 2023-03-14 | 0 | 13 | 25 | 74 | 110 | 2023 | 2023 | R16
169443338987 | 164435338987 | NON-RESIDENTIAL - SUBSEQUENT WORK | R16 RESD AND NON RESD US | Commercial | 2023-11-08 | 2023-11-08 | 2023-11-08 | 2023-11-29 | 2023-12-12 | Underground | R16 | 2023-11-29 | 1 |  | 16 | 10 | 25 | 2023 | 2023 | R16
167496338876 | 164183338876 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-13 | 2023-12-11 | Overhead | R16 | 2023-11-13 | 2 |  | 5 | 21 | 26 | 2023 | 2023 | R16
165056207153 | 167757207153 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-14 | 2020-10-14 | 2020-10-14 | 2022-08-30 | 2022-08-31 | Overhead | R16 | 2022-08-30 | 1 |  | 490 | 2 | 491 | 2020 | 2022 | R16
169880149532 | 164225149532 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-18 | 2019-04-18 | 2019-04-18 | 2019-05-09 | 2019-05-09 | Overhead | R16 | 2019-05-09 | 1 |  | 16 |  | 16 | 2019 | 2019 | R16
168084198485 | 160213198485 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-27 | 2020-07-27 | 2020-07-27 | 2021-01-22 | 2023-03-06 | Overhead | R16 | 2021-01-22 | 1 |  | 130 | 552 | 681 | 2020 | 2023 | R16
169817187476 | 161079187476 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-05-28 | 2019-05-30 | 2020-04-15 | 2021-11-06 | 2021-11-23 | Underground | R16 | 2021-11-06 | 3 | 230 | 408 | 12 | 651 | 2019 | 2021 | R16
164364141893 | 160780141893 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-31 | 2019-02-01 | 2019-02-01 | 2019-11-27 | 2019-12-30 | Overhead | R16 | 2019-11-27 | 2 |  | 214 | 24 | 238 | 2019 | 2019 | R16
161702145286 | 167017145286 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-07 | 2019-03-07 | 2019-03-07 | 2019-03-27 | 2019-03-27 | Overhead | R16 | 2019-03-27 | 1 |  | 15 |  | 15 | 2019 | 2019 | R16
169481141763 | 169556141763 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-29 | 2019-01-29 | 2019-01-29 | 2019-02-19 | 2019-02-20 | Overhead | R16 | 2019-02-19 | 1 |  | 16 | 2 | 17 | 2019 | 2019 | R16
160320277450 | 168531277450 | CUSTOMER UPGRADE IN SERVICE | UG SVC CONVERSION | Residential | 2021-01-20 | 2021-01-26 | 2023-01-27 | 2023-01-17 | 2023-10-20 | Underground | R16 | 2023-01-17 | 5 | 524 |  | 199 | 718 | 2021 | 2023 | R16
167456206401 | 166014206401 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-06 | 2020-10-06 | 2020-10-06 | 2020-10-25 | 2020-10-28 | Overhead | R16 | 2020-10-25 | 1 |  | 14 | 3 | 17 | 2020 | 2020 | R16
169911142479 | 169009142479 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-25 | 2019-01-25 | 2019-02-07 | 2019-07-02 | 2019-08-26 | Underground | R16 | 2019-07-02 | 1 | 10 | 104 | 40 | 152 | 2019 | 2019 | R16
162404239017 | 164775239017 | INDUSTRIAL | UG R16 RESD AND NON RESD UD | Commercial | 2021-03-31 | 2021-06-07 | 2021-07-15 | 2021-08-21 | 2021-09-21 | Underground | R16 | 2021-08-21 | 49 | 29 | 27 | 22 | 125 | 2021 | 2021 | R16
169889231077 | 166077231077 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-18 | 2021-05-18 | 2021-05-18 | 2021-09-28 | 2021-11-02 | Underground | R16 | 2021-09-28 | 1 |  | 96 | 26 | 121 | 2021 | 2021 | R16
165908206257 | 166280206257 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-07 | 2020-10-07 | 2020-10-07 | 2020-10-08 | 2020-10-16 | Overhead | R16 | 2020-10-08 | 1 |  | 2 | 7 | 8 | 2020 | 2020 | R16
165663141468 | 169397141468 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-01-28 | 2019-01-28 | 2019-01-28 | 2019-06-18 | 2019-06-18 | Overhead | R16 | 2019-06-18 | 1 |  | 102 |  | 102 | 2019 | 2019 | R16
167481198854 | 160908198854 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-07-29 | 2020-07-29 | 2020-07-29 | 2020-08-26 | 2021-03-11 | Overhead | R16 | 2020-08-26 | 1 |  | 21 | 142 | 162 | 2020 | 2021 | R16
165840203375 | 161105203375 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-30 | 2020-09-04 | 2020-09-10 | 2020-10-09 | 2021-07-02 | Overhead | R16 | 2020-10-09 | 27 | 5 | 22 | 191 | 242 | 2020 | 2021 | R16
164935155986 | 166152155986 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-30 | 2019-04-30 | 2019-06-21 | 2019-08-09 | 2019-08-12 | Underground | R16 | 2019-08-09 | 1 | 39 | 36 | 2 | 75 | 2019 | 2019 | R16
166978142551 | 162148142551 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-07 | 2019-02-07 | 2019-02-07 | 2020-02-21 | 2020-06-09 | Underground | R16 | 2020-02-21 | 1 |  | 272 | 78 | 349 | 2019 | 2020 | R16
160593229225 | 161397229225 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-04-29 | 2021-05-03 | 2021-05-03 | 2021-05-15 | 2021-10-05 | Overhead | R16 | 2021-05-15 | 3 |  | 10 | 102 | 114 | 2021 | 2021 | R16
164508216391 | 160612216391 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-13 | 2020-12-15 | 2021-01-07 | 2021-02-02 | 2021-04-29 | Underground | R16 | 2021-02-02 | 2 | 18 | 19 | 63 | 99 | 2020 | 2021 | R16
169240201846 | 166989201846 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-27 | 2020-08-27 | 2020-08-27 | 2020-09-24 | 2021-01-07 | Overhead | R16 | 2020-09-24 | 1 |  | 21 | 76 | 96 | 2020 | 2021 | R16
168085182667 | 161116182667 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-05-28 | 2019-06-05 | 2020-03-02 | 2020-12-07 | 2021-02-27 | Underground | R16 | 2020-12-07 | 7 | 194 | 201 | 60 | 459 | 2019 | 2021 | R16
164082145457 | 167376145457 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-09 | 2019-03-09 | 2019-03-09 | 2019-03-21 | 2019-03-21 | Overhead | R16 | 2019-03-21 | 0 |  | 9 |  | 9 | 2019 | 2019 | R16
160897202172 | 167530202172 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-28 | 2020-08-28 | 2020-08-28 | 2020-10-02 | 2020-10-05 | Underground | R16 | 2020-10-02 | 1 |  | 26 | 2 | 27 | 2020 | 2020 | R16
161539205818 | 167867205818 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-31 | 2020-08-31 | 2020-10-01 | 2023-01-19 | 2023-04-19 | Underground | R16 | 2023-01-19 | 1 | 24 | 601 | 65 | 688 | 2020 | 2023 | R16
161114156876 | 161857156876 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-03 | 2019-06-03 | 2019-07-03 | 2019-09-30 | 2019-10-03 | Underground | R16 | 2019-09-30 | 1 | 23 | 64 | 4 | 89 | 2019 | 2019 | R16
166615233960 | 160288233960 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-03-12 | 2021-03-12 | 2021-06-06 | 2022-06-20 | 2022-07-05 | Underground | R16 | 2022-06-20 | 1 | 61 | 271 | 12 | 343 | 2021 | 2022 | R16
168318144452 | 166460144452 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-09 | 2019-01-09 | 2019-02-28 | 2019-05-22 | 2019-05-21 | Underground | R16 | 2019-05-22 | 1 | 37 | 60 |  | 95 | 2019 | 2019 | R16
160883151440 | 167380151440 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-06 | 2019-05-06 | 2019-05-06 | 2019-07-11 | 2019-07-11 | Overhead | R16 | 2019-07-11 | 1 |  | 49 |  | 49 | 2019 | 2019 | R16
166827202635 | 168481202635 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-09-03 | 2020-09-03 | 2020-09-03 | 2020-11-03 | 2021-07-24 | Underground | R16 | 2020-11-03 | 1 |  | 44 | 189 | 232 | 2020 | 2021 | R16
160700204181 | 165881204181 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-21 | 2020-08-21 | 2020-09-16 | 2020-10-02 | 2020-10-19 | Underground | R16 | 2020-10-02 | 1 | 19 | 13 | 12 | 42 | 2020 | 2020 | R16
167910275936 | 168475275936 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-04-16 | 2021-04-17 | 2022-04-14 | 2023-05-04 | 2023-07-14 | Underground | R16 | 2023-05-04 | 1 | 259 | 276 | 52 | 586 | 2021 | 2023 | R16
164537201534 | 166564201534 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-25 | 2020-08-25 | 2020-08-25 | 2020-09-14 | 2020-12-17 | Overhead | R16 | 2020-09-14 | 1 |  | 15 | 69 | 83 | 2020 | 2020 | R16
164634145810 | 167923145810 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2019-03-13 | 2019-03-13 | 2019-03-13 | 2019-03-21 | 2019-05-26 | Overhead | R16 | 2019-03-21 | 1 |  | 7 | 47 | 53 | 2019 | 2019 | R16
169385148446 | 169553148446 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-23 | 2019-03-23 | 2019-04-06 | 2019-04-24 | 2019-04-24 | Overhead | R16 | 2019-04-24 | 0 | 10 | 13 |  | 23 | 2019 | 2019 | R16
160404225755 | 164616225755 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-31 | 2021-04-05 | 2021-04-05 | 2021-07-20 | 2021-07-22 | Overhead | R16 | 2021-07-20 | 4 |  | 77 | 3 | 82 | 2021 | 2021 | R16
161247232770 | 165342232770 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-05-14 | 2021-05-28 | 2021-05-28 | 2021-10-08 | 2021-11-10 | Underground | R16 | 2021-10-08 | 11 |  | 96 | 24 | 129 | 2021 | 2021 | R16
166647228594 | 161606228594 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-03-18 | 2021-04-19 | 2021-04-28 | 2021-08-30 | 2021-10-26 | Underground | R16 | 2021-08-30 | 23 | 8 | 89 | 42 | 159 | 2021 | 2021 | R16
163077149444 | 163632149444 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2019-04-15 | 2019-04-15 | 2019-04-17 | 2019-05-28 | 2019-10-28 | Underground | R16 | 2019-05-28 | 1 | 3 | 30 | 110 | 141 | 2019 | 2019 | R16
167400226886 | 161658226886 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-18 | 2021-04-14 | 2021-04-14 | 2021-06-10 | 2021-08-18 | Overhead | R16 | 2021-06-10 | 20 |  | 42 | 50 | 110 | 2021 | 2021 | R16
160728218245 | 166952218245 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-11-24 | 2020-12-02 | 2021-01-25 | 2021-03-11 | 2021-08-16 | Overhead | R16 | 2021-03-11 | 7 | 39 | 34 | 113 | 190 | 2020 | 2021 | R16
161148140898 | 168745140898 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-24 | 2019-01-24 | 2019-01-24 | 2019-02-28 | 2019-03-25 | Overhead | R16 | 2019-02-28 | 1 |  | 26 | 18 | 43 | 2019 | 2019 | R16
169197201619 | 166333201619 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-25 | 2020-08-25 | 2020-08-25 | 2021-01-08 | 2021-06-02 | Overhead | R16 | 2021-01-08 | 1 |  | 99 | 104 | 202 | 2020 | 2021 | R16
166611228041 | 169871228041 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-05-18 | 2021-08-26 | Overhead | R16 | 2021-05-18 | 1 |  | 19 | 73 | 91 | 2021 | 2021 | R16
169474204869 | 162884204869 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-23 | 2020-09-23 | 2020-09-23 | 2021-03-23 | 2021-08-02 | Overhead | R16 | 2021-03-23 | 1 |  | 130 | 95 | 224 | 2020 | 2021 | R16
164658211503 | 162402211503 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-03 | 2020-11-03 | 2020-11-20 | 2021-02-17 | 2021-05-06 | Underground | R16 | 2021-02-17 | 1 | 14 | 64 | 57 | 133 | 2020 | 2021 | R16
161800163465 | 161523163465 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-02-05 | 2019-02-05 | 2019-09-05 | 2023-01-11 | 2022-12-07 | Underground | R16 | 2023-01-11 | 1 | 153 | 875 |  | 1002 | 2019 | 2022 | R16
165557203253 | 169603203253 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-09 | 2020-09-09 | 2020-09-09 | 2021-07-20 | 2021-07-22 | Underground | R16 | 2021-07-20 | 1 |  | 225 | 3 | 227 | 2020 | 2021 | R16
166571225117 | 164287225117 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2022-02-23 | 2022-03-15 | Overhead | R16 | 2022-02-23 | 1 |  | 238 | 15 | 252 | 2021 | 2022 | R16
168421147330 | 160850147330 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-01 | 2019-02-01 | 2019-03-26 | 2019-05-02 | 2019-05-02 | Overhead | R16 | 2019-05-02 | 1 | 38 | 28 |  | 65 | 2019 | 2019 | R16
168279143888 | 164482143888 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-21 | 2019-02-21 | 2019-02-21 | 2019-03-28 | 2019-05-20 | Overhead | R16 | 2019-03-28 | 1 |  | 26 | 38 | 63 | 2019 | 2019 | R16
168591304321 | 169753304321 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-27 | 2022-12-27 | 2022-12-27 |  | 2023-03-01 | Overhead | R16 | 2023-01-26 | 1 |  | 23 | 25 | 47 | 2022 | 2023 | R16
168876227483 | 164279227483 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-03-29 | 2021-03-29 | 2021-04-19 |  | 2022-11-30 | Overhead | R16 |  | 1 | 16 |  |  | 438 | 2021 | 2022 | R16
160384152665 | 166644152665 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2019-01-10 | 2019-01-10 | 2019-05-16 | 2019-07-11 | 2019-07-12 | Underground | R16 | 2019-07-11 | 1 | 91 | 41 | 2 | 132 | 2019 | 2019 | R16
165678212756 | 163296212756 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Commercial | 2020-08-12 | 2020-08-13 | 2020-12-04 | 2023-07-31 | 2023-09-01 | Underground | R16 | 2023-07-31 | 2 | 82 | 692 | 25 | 798 | 2020 | 2023 | R16
161222148635 | 169773148635 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-03-25 | 2019-03-28 | 2019-04-09 | 2020-08-06 | 2020-11-06 | Underground | R16 | 2020-08-06 | 4 | 9 | 348 | 67 | 425 | 2019 | 2020 | R16
164555229350 | 161838229350 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-04-30 | 2021-05-01 | 2021-05-03 | 2022-12-13 | 2023-06-07 | Underground | R16 | 2022-12-13 | 1 | 1 | 422 | 127 | 549 | 2021 | 2023 | R16
163941226239 | 163932226239 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE FOR UPGRADE UD | Commercial | 2020-11-10 | 2020-11-10 | 2021-04-08 | 2023-07-25 | 2023-07-07 | Underground | R16 | 2023-07-25 | 1 | 108 | 599 |  | 694 | 2020 | 2023 | R16
168839211827 | 163709211827 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-09 | 2020-11-24 | 2020-11-24 | 2021-03-04 | 2021-06-03 | Overhead | R16 | 2021-03-04 | 12 |  | 73 | 66 | 149 | 2020 | 2021 | R16
160567223488 | 160196223488 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-12 | 2021-03-12 | 2021-03-12 | 2021-04-01 | 2021-11-05 | Overhead | R16 | 2021-04-01 | 1 |  | 15 | 157 | 171 | 2021 | 2021 | R16
160706211033 | 167362211033 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-08-28 | 2020-08-28 | 2020-11-18 | 2021-02-23 | 2022-08-03 | Underground | R16 | 2021-02-23 | 1 | 59 | 70 | 377 | 504 | 2020 | 2022 | R16
164197214265 | 161251214265 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-16 | 2020-12-16 | 2020-12-16 | 2021-03-17 | 2021-08-11 | Overhead | R16 | 2021-03-17 | 1 |  | 66 | 106 | 171 | 2020 | 2021 | R16
165874224198 | 165861224198 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-02-22 | 2021-02-22 | 2021-03-22 | 2022-04-28 | 2022-05-02 | Underground | R16 | 2022-04-28 | 1 | 21 | 289 | 3 | 311 | 2021 | 2022 | R16
164007263173 | 167851263173 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-12-01 | 2021-07-21 | 2022-01-03 | 2022-04-13 | 2022-10-29 | Underground | R16 | 2022-04-13 | 167 | 119 | 73 | 143 | 499 | 2020 | 2022 | R16
161219222896 | 169416222896 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-09 | 2021-03-09 | 2021-03-09 | 2021-12-02 | 2022-01-11 | Overhead | R16 | 2021-12-02 | 1 |  | 193 | 29 | 221 | 2021 | 2022 | R16
161897217871 | 163628217871 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-11 | 2020-11-13 | 2021-01-22 | 2021-04-10 | 2021-04-22 | Underground | R16 | 2021-04-10 | 3 | 51 | 56 | 9 | 117 | 2020 | 2021 | R16
162637269516 | 164443269516 | CUSTOMER UPGRADE IN SERVICE | UG SVC CONVERSION | Residential | 2021-05-10 | 2021-05-10 | 2022-02-18 | 2022-08-25 | 2022-09-14 | Underground | R16 | 2022-08-25 | 1 | 205 | 135 | 15 | 353 | 2021 | 2022 | R16
162805203742 | 160484203742 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-11 | 2020-09-11 | 2020-09-11 | 2020-10-06 | 2021-02-17 | Overhead | R16 | 2020-10-06 | 1 |  | 18 | 97 | 114 | 2020 | 2021 | R16
161518155885 | 162772155885 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-06-07 | 2019-06-07 | 2019-06-20 | 2019-11-18 | 2019-12-09 | Underground | R16 | 2019-11-18 | 1 | 10 | 108 | 16 | 132 | 2019 | 2019 | R16
161688152281 | 168528152281 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-13 | 2019-05-13 | 2019-05-13 | 2020-10-16 | 2021-02-20 | Underground | R16 | 2020-10-16 | 1 |  | 375 | 91 | 465 | 2019 | 2021 | R16
167320141180 | 168539141180 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-03-07 | 2019-03-07 | Overhead | R16 | 2019-03-07 | 1 |  | 32 |  | 32 | 2019 | 2019 | R16
160825222851 | 166046222851 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-11 | 2021-01-11 | 2021-03-08 | 2021-11-18 | 2021-12-07 | Overhead | R16 | 2021-11-18 | 1 | 41 | 184 | 14 | 237 | 2021 | 2021 | R16
167241222588 | 168561222588 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-05-27 | 2021-11-04 | Overhead | R16 | 2021-05-27 | 1 |  | 60 | 116 | 175 | 2021 | 2021 | R16
168042269472 | 162429269472 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-03-22 | 2021-10-18 | 2022-02-17 | 2023-01-23 | 2023-02-06 | Underground | R16 | 2023-01-23 | 151 | 89 | 243 | 11 | 491 | 2021 | 2023 | R16
165114230736 | 164641230736 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-11 | 2021-05-14 | 2021-05-14 | 2022-04-11 | 2022-05-12 | Overhead | R16 | 2022-04-11 | 4 |  | 237 | 24 | 263 | 2021 | 2022 | R16
164250147781 | 160940147781 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-31 | 2019-03-31 | 2019-03-31 | 2019-08-04 | 2019-09-06 | Overhead | R16 | 2019-08-04 | 0 |  | 90 | 25 | 115 | 2019 | 2019 | R16
169274153805 | 161910153805 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2019-04-05 | 2019-04-05 | 2019-05-30 | 2019-11-02 | 2020-03-31 | Underground | R16 | 2019-11-02 | 1 | 40 | 112 | 107 | 258 | 2019 | 2020 | R16
160339153208 | 160394153208 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-05-22 | 2019-05-22 | 2019-05-22 | 2019-05-26 | 2019-05-29 | Overhead | R16 | 2019-05-26 | 1 |  | 3 | 3 | 6 | 2019 | 2019 | R16
162623236664 | 164491236664 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-11 | 2021-05-11 | 2021-06-24 | 2021-08-16 | 2021-11-13 | Underground | R16 | 2021-08-16 | 1 | 33 | 38 | 65 | 134 | 2021 | 2021 | R16
167603146781 | 167446146781 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-16 | 2019-01-16 | 2019-03-21 | 2019-04-05 | 2019-05-15 | Overhead | R16 | 2019-04-05 | 1 | 47 | 12 | 29 | 86 | 2019 | 2019 | R16
164560144824 | 165505144824 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-28 | 2019-02-28 | 2019-03-04 | 2019-03-07 | 2019-10-06 | Underground | R16 | 2019-03-07 | 1 | 3 | 4 | 152 | 157 | 2019 | 2019 | R16
169363220766 | 162292220766 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-02-04 | 2021-02-04 | 2021-02-17 | 2021-05-18 | 2021-05-19 | Overhead | R16 | 2021-05-18 | 1 | 10 | 65 | 2 | 75 | 2021 | 2021 | R16
168074217457 | 160527217457 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-10-26 | 2020-11-16 | 2021-01-15 | 2021-01-19 | 2021-02-04 | Overhead | R16 | 2021-01-19 | 16 | 45 | 3 | 13 | 74 | 2020 | 2021 | R16
161420150202 | 164940150202 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-22 | 2019-04-24 | 2019-04-24 | 2019-11-13 | 2019-11-21 | Overhead | R16 | 2019-11-13 | 3 |  | 146 | 7 | 154 | 2019 | 2019 | R16
160221150127 | 163597150127 | NON-RESIDENTIAL - LARGE OFFICE | R16 RESD AND NON RESD US | Commercial | 2019-02-15 | 2019-02-15 | 2019-04-24 | 2020-01-13 | 2020-04-23 | Underground | R16 | 2020-01-13 | 1 | 49 | 189 | 74 | 310 | 2019 | 2020 | R16
162352200634 | 163945200634 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-15 | 2020-08-17 | 2020-08-17 | 2020-08-26 | 2020-08-28 | Overhead | R16 | 2020-08-26 | 1 |  | 8 | 3 | 10 | 2020 | 2020 | R16
164207206589 | 166805206589 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-08 | 2020-10-08 | 2020-10-08 | 2020-11-23 | 2021-04-07 | Overhead | R16 | 2020-11-23 | 1 |  | 33 | 98 | 130 | 2020 | 2021 | R16
164159140144 | 166377140144 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-09 | 2019-01-09 | 2019-01-14 | 2019-02-26 | 2019-02-27 | Overhead | R16 | 2019-02-26 | 1 | 4 | 32 | 2 | 36 | 2019 | 2019 | R16
162793212456 | 167507212456 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-30 | 2020-12-02 | 2020-12-02 | 2020-12-10 | 2021-04-21 | Overhead | R16 | 2020-12-10 | 3 |  | 7 | 95 | 103 | 2020 | 2021 | R16
169681226838 | 167981226838 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-01-19 | 2021-01-19 | 2021-04-14 | 2021-04-30 | 2021-11-08 | Overhead | R16 | 2021-04-30 | 1 | 62 | 13 | 137 | 210 | 2021 | 2021 | R16
168585214085 | 168350214085 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-15 | 2020-10-15 | 2020-12-15 | 2021-01-14 | 2021-05-06 | Overhead | R16 | 2021-01-14 | 1 | 44 | 23 | 81 | 146 | 2020 | 2021 | R16
166385249545 | 166965249545 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-02-26 | 2021-09-27 | 2021-09-27 | 2022-02-25 | 2022-03-22 | Overhead | R16 | 2022-02-25 | 152 |  | 110 | 18 | 278 | 2021 | 2022 | R16
161089230667 | 165379230667 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-06 | 2021-04-30 | 2021-05-13 | 2021-05-28 | 2021-08-23 | Overhead | R16 | 2021-05-28 | 19 | 10 | 12 | 62 | 100 | 2021 | 2021 | R16
166328227166 | 167316227166 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-12 | 2021-04-12 | 2021-04-16 | 2021-07-10 | 2021-07-12 | Underground | R16 | 2021-07-10 | 1 | 5 | 61 | 1 | 66 | 2021 | 2021 | R16
164547230373 | 164603230373 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-05-18 | 2021-08-26 | Overhead | R16 | 2021-05-18 | 1 |  | 6 | 73 | 78 | 2021 | 2021 | R16
166312214506 | 169972214506 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-09-10 | 2020-10-21 | 2020-12-20 | 2022-03-04 | 2022-03-21 | Underground | R16 | 2022-03-04 | 30 | 43 | 315 | 12 | 398 | 2020 | 2022 | R16
166365147739 | 168098147739 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-03-13 | 2019-03-13 | 2019-04-02 | 2020-06-22 | 2022-03-29 | Underground | R16 | 2020-06-22 | 1 | 15 | 320 | 462 | 795 | 2019 | 2022 | R16
163971227529 | 165084227529 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2021-04-01 | 2021-04-07 | 2021-04-19 | 2021-05-06 | 2021-06-24 | Underground | R16 | 2021-05-06 | 5 | 9 | 14 | 36 | 61 | 2021 | 2021 | R16
161809214433 | 164665214433 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-13 | 2020-11-13 | 2020-12-21 | 2021-01-22 | 2021-06-02 | Overhead | R16 | 2021-01-22 | 1 | 27 | 25 | 94 | 144 | 2020 | 2021 | R16
161618228869 | 160491228869 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-26 | 2021-04-26 | 2021-04-30 | 2021-07-27 | 2021-08-23 | Underground | R16 | 2021-07-27 | 1 | 5 | 63 | 20 | 86 | 2021 | 2021 | R16
166954213588 | 160148213588 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-10 | 2020-12-10 | 2020-12-10 | 2020-12-15 | 2021-04-22 | Overhead | R16 | 2020-12-15 | 1 |  | 4 | 93 | 96 | 2020 | 2021 | R16
168610209450 | 162491209450 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-03 | 2020-11-03 | 2020-11-04 | 2020-11-06 | 2021-04-07 | Overhead | R16 | 2020-11-06 | 1 | 2 | 3 | 109 | 112 | 2020 | 2021 | R16
168411297483 | 162869297483 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-05 | 2021-10-06 | 2022-10-18 | 2023-09-21 | 2023-09-22 | Underground | R16 | 2023-09-21 | 111 | 270 | 243 | 2 | 623 | 2021 | 2023 | R16
164651252037 | 164724252037 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2021-01-05 | 2021-04-13 | 2021-10-14 | 2022-05-23 | 2022-06-07 | Underground | R16 | 2022-05-23 | 71 | 133 | 158 | 12 | 371 | 2021 | 2022 | R16
160232145324 | 166976145324 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-07 | 2019-03-07 | 2019-03-07 | 2019-03-24 | 2019-03-27 | Overhead | R16 | 2019-03-24 | 1 |  | 12 | 3 | 15 | 2019 | 2019 | R16
162363230423 | 167051230423 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-10 | 2021-05-11 | 2021-05-11 | 2021-06-09 | 2021-08-17 | Overhead | R16 | 2021-06-09 | 22 |  | 22 | 50 | 92 | 2021 | 2021 | R16
168002235193 | 162219235193 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential Subdivision | 2021-02-04 | 2021-02-04 | 2021-06-17 | 2021-08-31 | 2022-02-02 | Underground | R16 | 2021-08-31 | 1 | 96 | 54 | 112 | 260 | 2021 | 2022 | R16
166492139503 | 164834139503 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-01-03 | 2019-01-03 | 2019-01-07 | 2020-04-08 | 2020-06-23 | Underground | R16 | 2020-04-08 | 1 | 3 | 328 | 55 | 384 | 2019 | 2020 | R16
162651143754 | 162189143754 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-08 | 2019-02-08 | 2019-02-20 | 2019-02-28 | 2019-02-28 | Underground | R16 | 2019-02-28 | 1 | 9 | 7 |  | 15 | 2019 | 2019 | R16
163834203889 | 160977203889 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-15 | 2020-09-15 | 2020-09-15 | 2020-10-20 | 2020-10-22 | Overhead | R16 | 2020-10-20 | 1 |  | 26 | 3 | 28 | 2020 | 2020 | R16
161336212932 | 169010212932 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-05 | 2020-12-05 | 2020-12-05 | 2021-02-02 | 2021-02-03 | Overhead | R16 | 2021-02-02 | 0 |  | 42 | 2 | 43 | 2020 | 2021 | R16
167410221550 | 166414221550 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-02-24 | 2021-02-24 | 2021-02-24 | 2021-03-30 | 2021-03-31 | Overhead | R16 | 2021-03-30 | 1 |  | 25 | 2 | 26 | 2021 | 2021 | R16
168551219781 | 162246219781 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2021-02-04 | 2021-02-04 | 2021-02-04 | 2021-02-08 | 2021-02-09 | Overhead | R16 | 2021-02-08 | 1 |  | 3 | 2 | 4 | 2021 | 2021 | R16
164460156160 | 165624156160 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-04-26 | 2019-04-26 | 2019-06-24 |  | 2019-09-24 | Underground | R16 | 2019-09-01 | 1 | 42 | 50 | 17 | 108 | 2019 | 2019 | R16
168167230490 | 162318230490 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-11-03 | 2020-11-03 | 2021-05-13 |  | 2022-03-09 | Underground | R16 |  | 1 | 138 |  |  | 352 | 2020 | 2022 | R16
169500153853 | 161604153853 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-31 | 2019-05-31 | 2019-05-31 | 2019-08-09 | 2019-08-09 | Overhead | R16 | 2019-08-09 | 1 |  | 51 |  | 51 | 2019 | 2019 | R16
166489220537 | 160689220537 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-14 | 2020-12-14 | 2021-02-16 | 2021-04-26 | 2021-04-27 | Underground | R16 | 2021-04-26 | 1 | 47 | 50 | 2 | 97 | 2020 | 2021 | R16
161713200072 | 162913200072 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2020-08-11 | 2020-08-11 | 2020-08-11 | 2021-02-01 | 2021-05-03 | Overhead | R16 | 2021-02-01 | 1 |  | 125 | 66 | 190 | 2020 | 2021 | R16
160223155090 | 161269155090 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-30 | 2019-05-30 | 2019-06-12 | 2019-07-19 | 2019-07-22 | Underground | R16 | 2019-07-19 | 1 | 10 | 28 | 2 | 38 | 2019 | 2019 | R16
161429205615 | 164365205615 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-29 | 2020-09-29 | 2020-09-29 | 2020-10-22 | 2021-11-10 | Overhead | R16 | 2020-10-22 | 1 |  | 18 | 275 | 292 | 2020 | 2021 | R16
163075244802 | 165795244802 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-16 | 2021-08-23 | 2021-08-23 | 2021-09-09 | 2021-09-09 | Underground | R16 | 2021-09-09 | 71 |  | 14 |  | 84 | 2021 | 2021 | R16
161263230646 | 167238230646 | NON-RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Commercial | 2020-10-12 | 2020-10-12 | 2021-05-14 | 2021-10-27 | 2021-11-15 | Underground | R16 | 2021-10-27 | 1 | 155 | 119 | 14 | 286 | 2020 | 2021 | R16
169487231180 | 161524231180 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2021-02-01 | 2021-03-08 | 2021-05-17 | 2022-07-14 | 2022-08-01 | Underground | R16 | 2022-07-14 | 26 | 51 | 304 | 13 | 391 | 2021 | 2022 | R16
168744229691 | 160008229691 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-04-23 | 2021-04-23 | 2021-05-06 | 2021-05-07 | 2021-11-02 | Overhead | R16 | 2021-05-07 | 1 | 10 | 2 | 128 | 138 | 2021 | 2021 | R16
164464231569 | 167999231569 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-05-19 | 2021-05-20 | 2021-05-20 | 2021-10-27 | 2021-11-18 | Overhead | R16 | 2021-10-27 | 2 |  | 115 | 17 | 132 | 2021 | 2021 | R16
168646225308 | 164417225308 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-30 | 2021-03-30 | 2021-03-30 | 2022-02-24 | 2022-02-24 | Overhead | R16 | 2022-02-24 | 1 |  | 238 |  | 238 | 2021 | 2022 | R16
165809226076 | 166134226076 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-06 | 2021-04-07 | 2021-04-07 | 2022-12-20 | 2022-12-19 | Overhead | R16 | 2022-12-20 | 2 |  | 445 |  | 445 | 2021 | 2022 | R16
167538215716 | 160643215716 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-09-12 | 2020-09-14 | 2020-12-29 | 2021-02-17 | 2022-02-01 | Underground | R16 | 2021-02-17 | 1 | 77 | 37 | 250 | 362 | 2020 | 2022 | R16
169585207206 | 161506207206 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-09-17 | 2020-09-17 | 2020-10-14 | 2021-11-10 | 2021-12-17 | Overhead | R16 | 2021-11-10 | 1 | 20 | 281 | 28 | 327 | 2020 | 2021 | R16
164515214228 | 161376214228 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-16 | 2020-12-17 | 2020-12-17 | 2020-12-21 | 2021-04-29 | Overhead | R16 | 2020-12-21 | 2 |  | 3 | 94 | 97 | 2020 | 2021 | R16
168108207209 | 168091207209 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-14 | 2020-10-14 | 2020-10-14 | 2020-10-29 | 2021-04-13 | Overhead | R16 | 2020-10-29 | 1 |  | 12 | 119 | 130 | 2020 | 2021 | R16
166594143812 | 164197143812 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-20 | 2019-02-20 | 2019-02-21 | 2019-03-10 | 2019-03-13 | Underground | R16 | 2019-03-10 | 1 | 2 | 12 | 3 | 16 | 2019 | 2019 | R16
165356214321 | 161395214321 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-17 | 2020-12-17 | 2020-12-17 | 2020-12-31 | 2021-04-23 | Overhead | R16 | 2020-12-31 | 1 |  | 11 | 82 | 92 | 2020 | 2021 | R16
167012220720 | 164503220720 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-03-15 | 2021-03-16 | Overhead | R16 | 2021-03-15 | 1 |  | 20 | 2 | 21 | 2021 | 2021 | R16
165859141032 | 168531141032 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-03-12 | 2019-03-13 | Overhead | R16 | 2019-03-12 | 1 |  | 35 | 2 | 36 | 2019 | 2019 | R16
169801219362 | 161618219362 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-02 | 2021-02-02 | 2021-02-02 | 2021-03-23 | 2021-08-06 | Overhead | R16 | 2021-03-23 | 1 |  | 36 | 99 | 134 | 2021 | 2021 | R16
165298148844 | 162770148844 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-09-26 | 2019-09-27 | Underground | R16 | 2019-09-26 | 1 |  | 122 | 2 | 123 | 2019 | 2019 | R16
165187229245 | 161557229245 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-30 | 2021-05-03 | 2021-05-03 | 2021-06-24 | 2021-08-11 | Overhead | R16 | 2021-06-24 | 2 |  | 39 | 35 | 74 | 2021 | 2021 | R16
168401225024 | 161377225024 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-17 | 2021-03-26 | 2021-03-26 | 2022-08-25 | 2022-08-30 | Overhead | R16 | 2022-08-25 | 8 |  | 370 | 4 | 380 | 2021 | 2022 | R16
169716152578 | 168861152578 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-14 | 2019-05-17 | 2019-05-17 | 2019-07-08 | 2019-07-08 | Overhead | R16 | 2019-07-08 | 4 |  | 37 |  | 40 | 2019 | 2019 | R16
160212208053 | 168988208053 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-20 | 2020-10-23 | 2020-10-23 | 2021-03-08 | 2021-11-05 | Overhead | R16 | 2021-03-08 | 4 |  | 97 | 175 | 274 | 2020 | 2021 | R16
160290225450 | 164856225450 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-06-08 | 2021-06-09 | Overhead | R16 | 2021-06-08 | 1 |  | 50 | 2 | 51 | 2021 | 2021 | R16
169810224735 | 166545224735 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-13 | 2021-01-13 | 2021-03-25 | 2021-05-18 | 2023-06-07 | Underground | R16 | 2021-05-18 | 1 | 52 | 39 | 537 | 626 | 2021 | 2023 | R16
169746226596 | 167661226596 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-13 | 2021-04-13 | 2021-04-13 | 2022-01-23 | 2022-01-24 | Overhead | R16 | 2022-01-23 | 1 |  | 204 | 1 | 205 | 2021 | 2022 | R16
164503253058 | 160442253058 | NON-RESIDENTIAL - SUBSEQUENT WORK | R16 RESD AND NON RESD US | Commercial | 2020-09-11 | 2021-07-01 | 2021-10-21 | 2023-06-16 | 2023-08-23 | Underground | R16 | 2023-06-16 | 210 | 81 | 432 | 49 | 769 | 2020 | 2023 | R16
168142201380 | 164857201380 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-18 | 2020-08-20 | 2020-08-20 | 2020-10-06 | 2021-07-19 | Overhead | R16 | 2020-10-06 | 3 |  | 34 | 205 | 240 | 2020 | 2021 | R16
169718211661 | 164956211661 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-15 | 2020-11-23 | 2020-11-23 | 2021-01-27 | 2021-04-23 | Overhead | R16 | 2021-01-27 | 6 |  | 48 | 63 | 115 | 2020 | 2021 | R16
160225219851 | 162775219851 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-08 | 2021-02-08 | 2021-02-08 | 2021-04-14 | 2021-04-16 | Overhead | R16 | 2021-04-14 | 1 |  | 48 | 3 | 50 | 2021 | 2021 | R16
169465199535 | 169116199535 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-07-21 | 2020-07-21 | 2020-08-04 | 2021-03-25 | 2021-08-16 | Overhead | R16 | 2021-03-25 | 1 | 11 | 168 | 103 | 280 | 2020 | 2021 | R16
168096212759 | 166630212759 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-23 | 2020-12-03 | 2020-12-04 | 2022-10-20 | 2022-09-08 | Overhead | R16 | 2022-10-20 | 9 | 2 | 490 |  | 469 | 2020 | 2022 | R16
162474222231 | 164839222231 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-17 | 2021-02-17 | 2021-03-03 | 2021-11-10 | 2022-07-16 | Underground | R16 | 2021-11-10 | 1 | 11 | 181 | 178 | 368 | 2021 | 2022 | R16
165129224197 | 161774224197 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-03-18 | 2021-03-18 | 2021-03-22 | 2021-10-17 | 2021-10-20 | Underground | R16 | 2021-10-17 | 1 | 3 | 150 | 3 | 155 | 2021 | 2021 | R16
162007140554 | 167935140554 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-18 | 2019-01-18 | 2019-01-18 | 2019-04-09 | 2019-04-09 | Overhead | R16 | 2019-04-09 | 1 |  | 58 |  | 58 | 2019 | 2019 | R16
167709205878 | 169755205878 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-09 | 2020-10-01 | 2020-10-01 | 2021-01-06 | 2021-01-07 | Overhead | R16 | 2021-01-06 | 17 |  | 70 | 2 | 87 | 2020 | 2021 | R16
167078201399 | 165876201399 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-21 | 2020-08-21 | 2020-08-21 | 2020-09-23 | 2021-05-06 | Overhead | R16 | 2020-09-23 | 1 |  | 24 | 162 | 185 | 2020 | 2021 | R16
166635158039 | 163865158039 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-17 | 2019-04-17 | 2019-07-18 | 2019-08-12 | 2019-08-16 | Underground | R16 | 2019-08-12 | 1 | 67 | 18 | 5 | 88 | 2019 | 2019 | R16
169266223945 | 161587223945 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-18 | 2021-03-18 | 2021-03-18 | 2021-03-25 | 2021-08-23 | Overhead | R16 | 2021-03-25 | 1 |  | 6 | 108 | 113 | 2021 | 2021 | R16
169191203267 | 169139203267 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-09 | 2020-09-09 | 2020-09-09 | 2020-09-16 | 2021-07-07 | Overhead | R16 | 2020-09-16 | 1 |  | 6 | 211 | 216 | 2020 | 2021 | R16
162200206922 | 166810206922 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-08 | 2020-10-12 | 2020-10-12 | 2020-11-17 | 2021-04-29 | Overhead | R16 | 2020-11-17 | 3 |  | 27 | 118 | 146 | 2020 | 2021 | R16
162228200707 | 164124200707 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-17 | 2020-08-17 | 2020-08-17 | 2020-10-07 | 2020-10-15 | Underground | R16 | 2020-10-07 | 1 |  | 38 | 7 | 44 | 2020 | 2020 | R16
160582150361 | 165571150361 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-25 | 2019-04-25 | 2019-04-25 | 2019-08-12 | 2019-12-06 | Underground | R16 | 2019-08-12 | 1 |  | 78 | 85 | 162 | 2019 | 2019 | R16
167616188517 | 163272188517 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-13 | 2019-02-13 | 2020-04-23 | 2020-04-30 | 2020-07-08 | Underground | R16 | 2020-04-30 | 1 | 312 | 6 | 50 | 366 | 2019 | 2020 | R16
162439143837 | 164764143837 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-22 | 2019-02-22 | 2019-02-22 | 2019-03-07 | 2019-03-07 | Overhead | R16 | 2019-03-07 | 1 |  | 10 |  | 10 | 2019 | 2019 | R16
168796226975 | 164837226975 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-31 | 2021-04-13 | 2021-04-16 | 2021-06-02 | 2021-08-26 | Underground | R16 | 2021-06-02 | 10 | 4 | 34 | 62 | 107 | 2021 | 2021 | R16
166146154108 | 163663154108 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-04-15 | 2019-04-15 | 2019-06-03 | 2020-01-02 | 2020-01-03 | Underground | R16 | 2020-01-02 | 1 | 36 | 154 | 2 | 190 | 2019 | 2020 | R16
160489208702 | 160558208702 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-27 | 2020-10-27 | 2020-10-27 | 2020-10-29 | 2021-04-20 | Overhead | R16 | 2020-10-29 | 1 |  | 3 | 124 | 126 | 2020 | 2021 | R16
164498222999 | 166689222999 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2021-02-25 | 2021-02-25 | 2021-03-10 | 2022-04-07 | 2021-12-12 | Underground | R16 | 2022-04-07 | 1 | 10 | 282 |  | 207 | 2021 | 2021 | R16
161729156553 | 162972156553 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-10 | 2019-06-27 | 2019-06-28 | 2019-08-12 | 2019-12-06 | Overhead | R16 | 2019-08-12 | 14 | 2 | 32 | 85 | 130 | 2019 | 2019 | R16
162001238075 | 167859238075 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-04-13 | 2021-06-29 | 2021-07-08 | 2021-10-04 | 2021-12-29 | Underground | R16 | 2021-10-04 | 56 | 8 | 63 | 63 | 187 | 2021 | 2021 | R16
169940202283 | 167306202283 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-28 | 2020-08-29 | 2020-08-29 | 2020-10-06 | 2021-02-17 | Overhead | R16 | 2020-10-06 | 1 |  | 27 | 97 | 124 | 2020 | 2021 | R16
162274231954 | 169026231954 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2021-05-21 | 2021-05-21 | 2021-05-21 | 2021-08-26 | 2021-10-26 | Overhead | R16 | 2021-08-26 | 1 |  | 70 | 44 | 113 | 2021 | 2021 | R16
162574157008 | 162378157008 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-05 | 2019-06-05 | 2019-07-02 | 2019-08-02 | 2019-08-02 | Underground | R16 | 2019-08-02 | 1 | 20 | 24 |  | 43 | 2019 | 2019 | R16
166046151724 | 167757151724 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-05-07 | 2019-05-07 | 2019-05-07 | 2019-05-30 | 2019-10-28 | Underground | R16 | 2019-05-30 | 1 |  | 18 | 108 | 125 | 2019 | 2019 | R16
166449248201 | 165842248201 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | R16 RESD AND NON RESD US | Commercial | 2021-05-17 | 2021-06-03 | 2021-09-16 | 2022-09-16 | 2023-02-07 | Underground | R16 | 2022-09-16 | 14 | 76 | 262 | 103 | 452 | 2021 | 2023 | R16
161692222086 | 167463222086 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-01 | 2021-03-01 | 2021-03-01 | 2021-07-07 | 2021-07-08 | Underground | R16 | 2021-07-07 | 1 |  | 93 | 2 | 94 | 2021 | 2021 | R16
161600152668 | 161850152668 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-04 | 2019-04-04 | 2019-05-16 | 2019-07-12 | 2019-07-12 | Underground | R16 | 2019-07-12 | 1 | 31 | 42 |  | 72 | 2019 | 2019 | R16
169102233333 | 169342233333 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-05-24 | 2021-05-27 | 2021-06-03 | 2021-06-09 | 2022-03-14 | Underground | R16 | 2021-06-09 | 4 | 6 | 5 | 199 | 211 | 2021 | 2022 | R16
164955192200 | 160113192200 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-05-21 | 2020-05-22 | 2020-05-26 | 2021-07-12 | 2022-02-04 | Underground | R16 | 2021-07-12 | 264 | 3 | 295 | 150 | 709 | 2019 | 2022 | R16
162058149805 | 164611149805 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-20 | 2019-04-20 | 2019-04-20 | 2019-05-06 | 2019-05-06 | Overhead | R16 | 2019-05-06 | 0 |  | 11 |  | 11 | 2019 | 2019 | R16
168338227889 | 163300227889 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-25 | 2021-04-21 | 2021-04-21 | 2021-07-16 | 2021-10-25 | Overhead | R16 | 2021-07-16 | 20 |  | 63 | 72 | 153 | 2021 | 2021 | R16
167802208999 | 169030208999 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-20 | 2020-10-22 | 2020-10-30 | 2021-02-09 | 2021-02-08 | Underground | R16 | 2021-02-09 | 3 | 7 | 73 |  | 80 | 2020 | 2021 | R16
164799146204 | 168268146204 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-15 | 2019-03-15 | 2019-03-15 | 2019-04-29 | 2019-04-29 | Overhead | R16 | 2019-04-29 | 1 |  | 32 |  | 32 | 2019 | 2019 | R16
169490210448 | 164612210448 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-12 | 2020-11-12 | 2020-11-12 | 2020-11-13 | 2021-04-14 | Underground | R16 | 2020-11-13 | 1 |  | 2 | 109 | 110 | 2020 | 2021 | R16
169292232175 | 169249232175 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Residential | 2019-01-28 | 2019-10-17 | 2021-05-25 | 2021-12-02 | 2022-01-06 | Underground | R16 | 2021-12-02 | 189 | 419 | 138 | 26 | 769 | 2019 | 2022 | R16
163887200883 | 162286200883 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-06 | 2020-08-06 | 2020-08-18 | 2020-08-24 | 2020-08-27 | Overhead | R16 | 2020-08-24 | 1 | 9 | 5 | 4 | 16 | 2020 | 2020 | R16
167011145135 | 166991145135 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-14 | 2019-01-14 | 2019-03-07 | 2019-03-11 | 2019-07-01 | Overhead | R16 | 2019-03-11 | 1 | 39 | 3 | 81 | 121 | 2019 | 2019 | R16
166436229293 | 168401229293 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-20 | 2021-01-20 | 2021-05-03 | 2021-05-07 | 2021-05-10 | Underground | R16 | 2021-05-07 | 1 | 74 | 5 | 2 | 79 | 2021 | 2021 | R16
166596141696 | 160551141696 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-01-31 | 2019-01-31 | 2019-01-31 | 2019-02-28 | 2019-04-15 | Overhead | R16 | 2019-02-28 | 1 |  | 21 | 33 | 53 | 2019 | 2019 | R16
164624150394 | 165589150394 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2019-04-26 | 2019-04-26 | 2019-04-26 | 2019-05-21 | 2019-05-22 | Overhead | R16 | 2019-05-21 | 1 |  | 18 | 2 | 19 | 2019 | 2019 | R16
168420279920 | 164431279920 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2021-03-30 | 2021-11-05 | 2022-05-18 | 2023-07-17 | 2023-08-16 | Underground | R16 | 2023-07-17 | 159 | 139 | 304 | 23 | 622 | 2021 | 2023 | R16
163018233092 | 166260233092 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-05-18 | 2021-05-28 | 2021-06-01 | 2021-11-18 | 2021-12-17 | Overhead | R16 | 2021-11-18 | 9 | 3 | 123 | 22 | 154 | 2021 | 2021 | R16
165773226869 | 167619226869 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-13 | 2021-04-13 | 2021-04-14 | 2021-05-24 | 2021-11-03 | Overhead | R16 | 2021-05-24 | 1 | 2 | 29 | 118 | 147 | 2021 | 2021 | R16
160941222642 | 166201222642 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2021-01-11 | 2021-03-04 | 2021-03-05 | 2021-03-09 | 2021-03-31 | Overhead | R16 | 2021-03-09 | 39 | 2 | 3 | 17 | 58 | 2021 | 2021 | R16
166131227864 | 169267227864 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-20 | 2021-04-20 | 2021-04-20 | 2021-07-08 | 2021-08-23 | Overhead | R16 | 2021-07-08 | 1 |  | 58 | 33 | 90 | 2021 | 2021 | R16
164675219987 | 164492219987 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | UG R16 ELECTRIC RELOCATION UD | Commercial | 2020-09-29 | 2020-11-30 | 2021-02-09 | 2021-11-24 | 2022-01-06 | Underground | R16 | 2021-11-24 | 45 | 52 | 207 | 32 | 333 | 2020 | 2022 | R16
163042222481 | 167664222481 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-30 | 2020-12-13 | 2021-03-04 | 2021-03-04 | 2021-06-03 | Overhead | R16 | 2021-03-04 | 10 | 59 |  | 66 | 134 | 2020 | 2021 | R16
160390159911 | 165354159911 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Residential Subdivision | 2019-04-25 | 2019-04-25 | 2019-08-02 |  | 2021-03-30 | Underground | R16 |  | 1 | 72 |  |  | 504 | 2019 | 2021 | R16
162233207338 | 168528207338 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-17 | 2020-10-17 | 2020-10-17 | 2021-02-11 | 2021-02-18 | Underground | R16 | 2021-02-11 | 0 |  | 84 | 6 | 89 | 2020 | 2021 | R16
166155280621 | 162681280621 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-07 | 2022-05-24 | 2022-05-24 | 2022-09-15 | 2023-06-08 | Overhead | R16 | 2022-09-15 | 337 |  | 83 | 191 | 609 | 2021 | 2023 | R16
165586215968 | 164254215968 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-31 | 2020-12-31 | 2020-12-31 | 2021-03-01 | 2023-06-07 | Underground | R16 | 2021-03-01 | 1 |  | 43 | 593 | 635 | 2020 | 2023 | R16
169899222148 | 167296222148 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-28 | 2021-03-01 | 2021-03-01 | 2021-07-12 | 2021-07-14 | Overhead | R16 | 2021-07-12 | 1 |  | 96 | 3 | 98 | 2021 | 2021 | R16
163651145134 | 164726145134 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-03 | 2019-01-03 | 2019-03-07 | 2019-11-04 | 2019-11-05 | Underground | R16 | 2019-11-04 | 1 | 46 | 173 | 2 | 219 | 2019 | 2019 | R16
165339157741 | 164925157741 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-04-23 | 2019-04-23 | 2019-07-12 | 2020-12-18 | 2022-05-06 | Underground | R16 | 2020-12-18 | 1 | 59 | 376 | 361 | 794 | 2019 | 2022 | R16
167095237021 | 168071237021 | NON-RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Commercial | 2020-10-14 | 2021-01-04 | 2021-06-28 | 2022-01-27 | 2022-02-11 | Underground | R16 | 2022-01-27 | 59 | 126 | 154 | 12 | 348 | 2020 | 2022 | R16
161128146129 | 168324146129 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-15 | 2019-03-15 | 2019-03-15 | 2019-04-11 | 2019-04-11 | Overhead | R16 | 2019-04-11 | 1 |  | 20 |  | 20 | 2019 | 2019 | R16
161576198076 | 169764198076 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-23 | 2020-07-24 | 2020-07-24 | 2021-01-26 | 2021-04-21 | Overhead | R16 | 2021-01-26 | 2 |  | 133 | 62 | 195 | 2020 | 2021 | R16
161460216285 | 160716216285 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-12-14 | 2020-12-15 | 2021-01-06 | 2021-08-06 | 2021-08-31 | Underground | R16 | 2021-08-06 | 2 | 17 | 153 | 18 | 187 | 2020 | 2021 | R16
161666154213 | 161773154213 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-31 | 2019-05-31 | 2019-06-04 | 2019-06-20 | 2019-06-20 | Overhead | R16 | 2019-06-20 | 1 | 3 | 13 |  | 15 | 2019 | 2019 | R16
162943217892 | 169948217892 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-10 | 2021-01-22 | 2021-01-22 | 2021-05-12 | 2022-09-12 | Overhead | R16 | 2021-05-12 | 32 |  | 79 | 349 | 458 | 2020 | 2022 | R16
168562229287 | 162413229287 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-03 | 2021-05-03 | 2021-05-03 | 2021-05-10 | 2021-08-11 | Overhead | R16 | 2021-05-10 | 1 |  | 6 | 68 | 73 | 2021 | 2021 | R16
161575212699 | 168610212699 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-12-03 | 2020-12-03 | 2020-12-03 | 2021-03-25 | 2021-11-04 | Underground | R16 | 2021-03-25 | 1 |  | 81 | 161 | 241 | 2020 | 2021 | R16
162144140171 | 166850140171 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-11 | 2019-01-11 | 2019-01-14 | 2019-02-12 | 2019-02-13 | Overhead | R16 | 2019-02-12 | 1 | 2 | 22 | 2 | 24 | 2019 | 2019 | R16
169743215868 | 169807215868 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2020-12-09 | 2020-12-10 | 2020-12-30 | 2021-01-06 | 2021-02-04 | Overhead | R16 | 2021-01-06 | 2 | 15 | 6 | 22 | 42 | 2020 | 2021 | R16
160143311249 | 164218311249 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-03-02 | 2023-03-02 | 2023-03-02 |  | 2023-10-06 | Overhead | R16 | 2023-07-10 | 1 |  | 93 | 65 | 157 | 2023 | 2023 | R16
162897151605 | 163348151605 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-13 | 2019-02-13 | 2019-05-07 | 2019-09-25 | 2019-10-16 | Underground | R16 | 2019-09-25 | 1 | 60 | 102 | 16 | 176 | 2019 | 2019 | R16
161657202276 | 166872202276 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-26 | 2020-09-01 | 2020-09-01 | 2020-10-21 | 2021-07-07 | Overhead | R16 | 2020-10-21 | 5 |  | 37 | 186 | 226 | 2020 | 2021 | R16
161304152204 | 168556152204 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-05-13 | 2019-05-13 | 2019-05-13 | 2019-10-01 | 2019-11-14 | Underground | R16 | 2019-10-01 | 1 |  | 102 | 33 | 134 | 2019 | 2019 | R16
163973144390 | 161459144390 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-02-05 | 2019-02-05 | 2019-02-27 | 2020-10-05 | 2019-12-13 | Underground | R16 | 2020-10-05 | 1 | 17 | 419 |  | 224 | 2019 | 2019 | R16
165275148097 | 160951148097 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-01 | 2019-04-04 | 2019-04-04 | 2019-06-18 | 2019-06-19 | Underground | R16 | 2019-06-18 | 4 |  | 54 | 2 | 58 | 2019 | 2019 | R16
161552254915 | 163430254915 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-10 | 2021-02-10 | 2021-11-03 | 2022-01-13 | 2022-01-19 | Underground | R16 | 2022-01-13 | 1 | 191 | 52 | 5 | 246 | 2021 | 2022 | R16
166639234843 | 160461234843 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-26 | 2021-04-27 | 2021-06-14 | 2021-07-31 | 2021-08-03 | Underground | R16 | 2021-07-31 | 2 | 35 | 35 | 2 | 72 | 2021 | 2021 | R16
160505308983 | 169645308983 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-02-09 | 2023-02-09 | 2023-02-09 |  | 2023-03-03 | Overhead | R16 | 2023-02-10 | 1 |  | 2 | 16 | 17 | 2023 | 2023 | R16
166971256036 | 166886256036 | FOREIGN UTILITY | UG R16 RESD AND NON RESD UD | Commercial | 2021-02-26 | 2021-05-20 | 2021-11-11 | 2023-06-22 | 2023-11-30 | Underground | R16 | 2023-06-22 | 60 | 126 | 421 | 116 | 720 | 2021 | 2023 | R16
169653245672 | 162474245672 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-22 | 2021-03-22 | 2021-08-28 | 2021-09-01 | 2021-09-02 | Underground | R16 | 2021-09-01 | 1 | 115 | 3 | 2 | 119 | 2021 | 2021 | R16
167545224094 | 164987224094 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-17 | 2021-03-08 | 2021-03-18 | 2021-05-17 | 2021-11-08 | Underground | R16 | 2021-05-17 | 14 | 9 | 43 | 126 | 189 | 2021 | 2021 | R16
165212221029 | 164132221029 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-12 | 2021-02-12 | 2021-02-19 | 2021-04-15 | 2021-11-08 | Underground | R16 | 2021-04-15 | 1 | 6 | 40 | 148 | 192 | 2021 | 2021 | R16
162361216148 | 160973216148 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-28 | 2020-10-28 | 2021-01-05 | 2021-03-01 | 2021-03-01 | Overhead | R16 | 2021-03-01 | 1 | 50 | 40 |  | 89 | 2020 | 2021 | R16
162726152238 | 160306152238 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-27 | 2019-03-27 | 2019-05-13 | 2019-08-15 | 2019-12-06 | Underground | R16 | 2019-08-15 | 1 | 34 | 69 | 82 | 183 | 2019 | 2019 | R16
160277223135 | 160188223135 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-12 | 2021-03-12 | 2021-03-12 | 2021-03-19 | 2021-11-02 | Underground | R16 | 2021-03-19 | 1 |  | 6 | 163 | 168 | 2021 | 2021 | R16
165749206936 | 167229206936 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-13 | 2020-10-13 | 2020-10-13 | 2020-10-20 | 2021-07-07 | Overhead | R16 | 2020-10-20 | 1 |  | 6 | 187 | 192 | 2020 | 2021 | R16
168341229289 | 162459229289 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-03 | 2021-05-03 | 2021-05-03 | 2021-05-17 | 2021-10-07 | Underground | R16 | 2021-05-17 | 1 |  | 11 | 104 | 114 | 2021 | 2021 | R16
165899152727 | 169894152727 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-20 | 2019-05-20 | 2019-05-20 | 2019-07-24 | 2019-08-26 | Overhead | R16 | 2019-07-24 | 1 |  | 48 | 24 | 71 | 2019 | 2019 | R16
169783139361 | 165369139361 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-05 | 2019-01-05 | 2019-01-05 | 2019-02-16 | 2019-02-19 | Overhead | R16 | 2019-02-16 | 0 |  | 30 | 2 | 32 | 2019 | 2019 | R16
166947206902 | 163545206902 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-25 | 2020-09-25 | 2020-10-12 | 2021-01-20 | 2021-05-06 | Underground | R16 | 2021-01-20 | 1 | 12 | 73 | 77 | 160 | 2020 | 2021 | R16
162143207547 | 164293207547 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-28 | 2020-10-06 | 2020-10-16 | 2020-10-30 | 2021-02-24 | Overhead | R16 | 2020-10-30 | 7 | 9 | 11 | 84 | 108 | 2020 | 2021 | R16
161450148507 | 162282148507 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-08 | 2019-04-08 | 2019-04-08 | 2019-05-13 | 2019-06-20 | Overhead | R16 | 2019-05-13 | 1 |  | 26 | 29 | 54 | 2019 | 2019 | R16
166813205715 | 163301205715 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-24 | 2020-09-30 | 2020-09-30 | 2020-11-10 | 2021-07-19 | Overhead | R16 | 2020-11-10 | 5 |  | 30 | 180 | 213 | 2020 | 2021 | R16
161656139770 | 165741139770 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-07 | 2019-01-10 | 2019-01-10 | 2019-01-17 | 2019-01-29 | Overhead | R16 | 2019-01-17 | 4 |  | 6 | 9 | 17 | 2019 | 2019 | R16
162202140701 | 167778140701 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-17 | 2019-01-17 | 2019-01-17 | 2019-02-12 | 2019-02-13 | Overhead | R16 | 2019-02-12 | 1 |  | 19 | 2 | 20 | 2019 | 2019 | R16
162954255810 | 166703255810 | SPECIFIC BUDGET PROJECTS | OH R16 RES NON RES OD | Commercial | 2021-05-18 | 2021-08-06 | 2021-11-09 | 2022-06-06 | 2022-06-07 | Overhead | R16 | 2022-06-06 | 59 | 68 | 150 | 2 | 276 | 2021 | 2022 | R16
168547234326 | 163321234326 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-25 | 2021-06-09 | 2021-06-10 | 2021-09-14 | 2021-11-08 | Overhead | R16 | 2021-09-14 | 55 | 2 | 69 | 40 | 163 | 2021 | 2021 | R16
166062202195 | 160493202195 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-28 | 2020-07-28 | 2020-08-30 | 2020-09-30 | 2021-07-24 | Underground | R16 | 2020-09-30 | 1 | 24 | 23 | 213 | 259 | 2020 | 2021 | R16
160505229342 | 162316229342 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-03 | 2021-05-03 | 2021-05-03 | 2022-06-08 | 2022-06-09 | Overhead | R16 | 2022-06-08 | 1 |  | 288 | 2 | 289 | 2021 | 2022 | R16
160357206423 | 164135206423 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-08-17 | 2020-08-19 | 2020-10-06 | 2020-11-04 | 2021-01-29 | Underground | R16 | 2020-11-04 | 3 | 35 | 22 | 63 | 120 | 2020 | 2021 | R16
167540217409 | 167264217409 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-14 | 2021-01-14 | 2021-01-14 | 2021-01-29 | 2021-11-11 | Overhead | R16 | 2021-01-29 | 1 |  | 12 | 205 | 216 | 2021 | 2021 | R16
163438238803 | 168888238803 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-04-19 | 2021-04-27 | 2021-07-12 | 2022-06-13 | 2022-07-15 | Underground | R16 | 2022-06-13 | 7 | 55 | 241 | 25 | 325 | 2021 | 2022 | R16
169982212598 | 169936212598 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-09-10 | 2020-09-10 | 2020-12-03 | 2021-04-06 | 2021-04-07 | Overhead | R16 | 2021-04-06 | 1 | 61 | 89 | 2 | 150 | 2020 | 2021 | R16
169423216411 | 165362216411 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-06 | 2021-01-06 | 2021-01-06 | 2021-01-26 | 2021-05-07 | Overhead | R16 | 2021-01-26 | 1 |  | 15 | 74 | 88 | 2021 | 2021 | R16
163914220418 | 164032220418 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-12 | 2021-02-12 | 2021-02-12 | 2022-12-12 | 2022-12-12 | Overhead | R16 | 2022-12-12 | 1 |  | 477 |  | 477 | 2021 | 2022 | R16
160449139856 | 166639139856 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-11 | 2019-01-11 | 2019-01-11 | 2019-02-11 | 2019-02-13 | Overhead | R16 | 2019-02-11 | 1 |  | 22 | 3 | 24 | 2019 | 2019 | R16
160335210646 | 164646210646 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-13 | 2020-11-13 | 2020-11-13 | 2021-06-10 | 2021-08-23 | Overhead | R16 | 2021-06-10 | 1 |  | 150 | 53 | 202 | 2020 | 2021 | R16
165872148110 | 161732148110 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-04 | 2019-04-04 | 2019-04-04 | 2019-05-01 | 2019-05-01 | Overhead | R16 | 2019-05-01 | 1 |  | 20 |  | 20 | 2019 | 2019 | R16
168099203345 | 169661203345 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-09 | 2020-09-09 | 2020-09-09 | 2020-09-16 | 2021-07-07 | Overhead | R16 | 2020-09-16 | 1 |  | 6 | 211 | 216 | 2020 | 2021 | R16
160856210810 | 162543210810 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-03 | 2020-11-03 | 2020-11-14 | 2021-01-13 | 2021-01-13 | Underground | R16 | 2021-01-13 | 1 | 9 | 43 |  | 52 | 2020 | 2021 | R16
164039231715 | 168692231715 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-20 | 2021-05-20 | 2021-05-20 | 2021-07-22 | 2021-10-25 | Overhead | R16 | 2021-07-22 | 1 |  | 46 | 68 | 113 | 2021 | 2021 | R16
169276221832 | 165597221832 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-21 | 2021-02-26 | 2021-02-26 | 2021-04-30 | 2021-10-28 | Overhead | R16 | 2021-04-30 | 5 |  | 46 | 130 | 179 | 2021 | 2021 | R16
168689151632 | 167699151632 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-07 | 2019-05-07 | 2019-05-07 | 2021-03-16 | 2021-03-17 | Overhead | R16 | 2021-03-16 | 1 |  | 486 | 2 | 487 | 2019 | 2021 | R16
166961142906 | 162793142906 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-11 | 2019-02-11 | 2019-02-11 | 2019-03-08 | 2019-03-11 | Overhead | R16 | 2019-03-08 | 1 |  | 20 | 2 | 21 | 2019 | 2019 | R16
164837159152 | 161395159152 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-05-30 | 2019-06-27 | 2019-07-26 | 2019-10-03 | 2020-04-06 | Underground | R16 | 2019-10-03 | 21 | 22 | 50 | 133 | 223 | 2019 | 2020 | R16
161009217991 | 167626217991 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-30 | 2020-12-08 | 2021-01-22 | 2021-09-01 | 2023-04-12 | Underground | R16 | 2021-09-01 | 7 | 34 | 159 | 421 | 618 | 2020 | 2023 | R16
166386197729 | 168893197729 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-17 | 2020-07-17 | 2020-07-20 | 2020-08-26 | 2020-08-28 | Overhead | R16 | 2020-08-26 | 1 | 2 | 28 | 3 | 31 | 2020 | 2020 | R16
161199153467 | 168766153467 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-14 | 2019-05-29 | 2019-05-29 | 2019-06-13 | 2019-06-13 | Overhead | R16 | 2019-06-13 | 12 |  | 12 |  | 23 | 2019 | 2019 | R16
168029207500 | 160707207500 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-09-14 | 2020-09-14 | 2020-10-16 | 2021-01-11 | 2021-03-30 | Underground | R16 | 2021-01-11 | 1 | 25 | 62 | 57 | 142 | 2020 | 2021 | R16
161901143976 | 164836143976 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-22 | 2019-02-22 | 2019-02-22 | 2019-03-15 | 2019-03-19 | Overhead | R16 | 2019-03-15 | 1 |  | 16 | 3 | 18 | 2019 | 2019 | R16
169477200709 | 160993200709 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-30 | 2020-07-30 | 2020-08-17 | 2020-08-28 | 2020-09-02 | Underground | R16 | 2020-08-28 | 1 | 13 | 10 | 4 | 25 | 2020 | 2020 | R16
169624206145 | 162160206145 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-05 | 2020-10-05 | 2020-10-05 | 2020-12-03 | 2021-02-27 | Overhead | R16 | 2020-12-03 | 44 |  | 44 | 62 | 148 | 2020 | 2021 | R16
167533209562 | 162428209562 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-03 | 2020-11-03 | 2020-11-03 | 2020-11-06 | 2021-04-13 | Overhead | R16 | 2020-11-06 | 1 |  | 4 | 113 | 116 | 2020 | 2021 | R16
164004307344 | 166474307344 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-26 | 2023-01-26 | 2023-01-26 |  | 2023-06-26 | Overhead | R16 | 2023-02-01 | 1 |  | 5 | 104 | 108 | 2023 | 2023 | R16
164006309040 | 169690309040 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-09 | 2023-02-10 | 2023-02-10 |  | 2023-03-03 | Overhead | R16 | 2023-02-21 | 2 |  | 8 | 9 | 17 | 2023 | 2023 | R16
165098206195 | 163216206195 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-09-24 | 2020-10-06 | 2020-10-06 | 2020-10-28 | 2021-07-26 | Overhead | R16 | 2020-10-28 | 9 |  | 17 | 194 | 218 | 2020 | 2021 | R16
168042269475 | 162428269475 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2021-03-22 | 2021-11-12 | 2022-02-17 | 2023-01-23 | 2023-02-06 | Underground | R16 | 2023-01-23 | 170 | 70 | 243 | 11 | 491 | 2021 | 2023 | R16
164867153068 | 166574153068 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-01 | 2019-05-01 | 2019-05-21 | 2019-10-09 | 2019-10-10 | Underground | R16 | 2019-10-09 | 1 | 15 | 102 | 2 | 117 | 2019 | 2019 | R16
164122207650 | 167629207650 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-10-14 | 2020-10-14 | 2020-10-19 | 2020-11-09 | 2021-07-19 | Overhead | R16 | 2020-11-09 | 1 | 4 | 16 | 181 | 199 | 2020 | 2021 | R16
160709165196 | 166710165196 | NON-RESIDENTIAL - LODGING | UG R16 RESD AND NON RESD UD | Commercial | 2019-05-01 | 2019-05-01 | 2019-09-20 | 2019-10-30 | 2020-02-06 | Underground | R16 | 2019-10-30 | 1 | 103 | 29 | 72 | 202 | 2019 | 2020 | R16
166789217880 | 168025217880 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-20 | 2021-01-20 | 2021-01-20 | 2021-04-26 | 2021-10-25 | Overhead | R16 | 2021-04-26 | 1 |  | 69 | 131 | 199 | 2021 | 2021 | R16
162312203294 | 167685203294 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-31 | 2020-09-09 | 2020-09-09 | 2020-10-23 | 2020-10-29 | Overhead | R16 | 2020-10-23 | 8 |  | 33 | 5 | 44 | 2020 | 2020 | R16
163971231857 | 165093231857 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2021-05-13 | 2021-05-13 | 2021-05-21 | 2021-08-11 | 2022-03-29 | Underground | R16 | 2021-08-11 | 1 | 7 | 59 | 165 | 229 | 2021 | 2022 | R16
163844148169 | 163851148169 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-15 | 2019-02-15 | 2019-04-05 | 2019-04-05 | 2019-06-03 | Underground | R16 | 2019-04-05 | 1 | 36 |  | 42 | 77 | 2019 | 2019 | R16
160611142587 | 162116142587 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-07 | 2019-02-07 | 2019-02-07 | 2019-03-12 | 2019-03-13 | Underground | R16 | 2019-03-12 | 1 |  | 24 | 2 | 25 | 2019 | 2019 | R16
164807222346 | 169694222346 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-26 | 2021-01-29 | 2021-03-03 | 2021-03-22 | 2023-06-07 | Overhead | R16 | 2021-03-22 | 4 | 24 | 14 | 578 | 617 | 2021 | 2023 | R16
167272199508 | 161770199508 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-08-03 | 2020-08-03 | 2020-08-03 | 2020-08-14 | 2020-12-22 | Overhead | R16 | 2020-08-14 | 1 |  | 10 | 93 | 102 | 2020 | 2020 | R16
160728224399 | 162760224399 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-23 | 2021-03-23 | 2021-03-23 | 2021-07-22 | 2021-07-22 | Overhead | R16 | 2021-07-22 | 1 |  | 88 |  | 88 | 2021 | 2021 | R16
162868146636 | 169016146636 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-03-20 | 2019-03-20 | 2019-03-20 | 2019-09-16 | 2019-09-17 | Overhead | R16 | 2019-09-16 | 1 |  | 129 | 2 | 130 | 2019 | 2019 | R16
169133151200 | 160659151200 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-29 | 2019-03-29 | 2019-05-03 | 2019-08-14 | 2019-08-15 | Underground | R16 | 2019-08-14 | 1 | 26 | 74 | 2 | 100 | 2019 | 2019 | R16
166519200351 | 161798200351 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-03 | 2020-08-11 | 2020-08-11 | 2020-08-28 | 2020-12-17 | Overhead | R16 | 2020-08-28 | 7 |  | 14 | 80 | 99 | 2020 | 2020 | R16
162051154883 | 168201154883 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-05-09 | 2019-05-09 | 2019-06-10 | 2020-08-28 | 2021-03-11 | Underground | R16 | 2020-08-28 | 1 | 23 | 320 | 140 | 481 | 2019 | 2021 | R16
169220237104 | 164181237104 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-10 | 2021-06-10 | 2021-06-29 | 2021-06-29 | 2021-09-13 | Overhead | R16 | 2021-06-29 | 24 | 14 |  | 55 | 91 | 2021 | 2021 | R16
167867149333 | 169152149333 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-20 | 2019-03-20 | 2019-04-16 | 2019-05-02 | 2019-05-02 | Underground | R16 | 2019-05-02 | 1 | 20 | 13 |  | 32 | 2019 | 2019 | R16
164799303641 | 168090303641 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-14 | 2022-12-19 | 2022-12-22 |  | 2023-04-27 | Overhead | R16 | 2023-01-24 | 4 | 4 | 24 | 68 | 97 | 2022 | 2023 | R16
165771225566 | 165201225566 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-01 | 2021-04-01 | 2021-04-01 | 2022-01-14 | 2022-03-08 | Overhead | R16 | 2022-01-14 | 1 |  | 207 | 38 | 244 | 2021 | 2022 | R16
166537204545 | 160718204545 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-07-29 | 2020-07-29 | 2020-09-21 | 2021-05-03 | 2021-06-21 | Underground | R16 | 2021-05-03 | 1 | 39 | 161 | 36 | 234 | 2020 | 2021 | R16
168357157429 | 162417157429 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-06-05 | 2019-06-05 | 2019-07-09 | 2019-12-20 | 2020-06-11 | Underground | R16 | 2019-12-20 | 1 | 25 | 119 | 125 | 267 | 2019 | 2020 | R16
166843207662 | 167589207662 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-13 | 2020-10-19 | 2020-10-19 | 2020-12-11 | 2020-12-16 | Underground | R16 | 2020-12-11 | 5 |  | 40 | 4 | 47 | 2020 | 2020 | R16
167401233466 | 161307233466 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-17 | 2021-06-04 | 2021-06-04 | 2021-12-01 | 2022-01-18 | Overhead | R16 | 2021-12-01 | 58 |  | 129 | 35 | 220 | 2021 | 2022 | R16
169535151283 | 167260151283 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-05-20 | 2019-05-21 | Overhead | R16 | 2019-05-20 | 1 |  | 12 | 2 | 13 | 2019 | 2019 | R16
166903150071 | 164846150071 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-23 | 2019-04-23 | 2019-04-23 | 2019-11-11 | 2019-11-14 | Overhead | R16 | 2019-11-11 | 1 |  | 145 | 4 | 148 | 2019 | 2019 | R16
169028209281 | 160395209281 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-01-30 | 2020-08-26 | 2020-10-30 | 2021-05-07 | 2021-06-02 | Underground | R16 | 2021-05-07 | 411 | 48 | 136 | 19 | 611 | 2019 | 2021 | R16
169002214159 | 160546214159 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-26 | 2020-11-04 | 2020-12-16 | 2021-02-10 | 2021-02-11 | Underground | R16 | 2021-02-10 | 8 | 31 | 41 | 2 | 79 | 2020 | 2021 | R16
161318233509 | 163665233509 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-11-09 | 2020-11-13 | 2021-06-04 | 2021-07-21 | 2021-12-29 | Underground | R16 | 2021-07-21 | 5 | 146 | 34 | 116 | 298 | 2020 | 2021 | R16
166729230360 | 168478230360 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2021-03-05 | 2021-03-05 | 2021-05-11 | 2022-04-07 | 2022-05-02 | Underground | R16 | 2022-04-07 | 1 | 48 | 238 | 18 | 302 | 2021 | 2022 | R16
160798210578 | 162144210578 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-02 | 2020-11-02 | 2020-11-13 | 2020-11-19 | 2021-04-29 | Overhead | R16 | 2020-11-19 | 1 | 10 | 5 | 116 | 129 | 2020 | 2021 | R16
169278242863 | 165617242863 | NON-RESIDENTIAL - WAREHOUSE | UG R16 RESD AND NON RESD UD | Commercial | 2020-11-18 | 2020-11-18 | 2021-08-09 | 2022-09-21 | 2022-12-08 | Underground | R16 | 2022-09-21 | 1 | 189 | 293 | 57 | 537 | 2020 | 2022 | R16
162629153250 | 165953153250 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-29 | 2019-05-23 | 2019-05-23 | 2019-05-30 | 2019-07-10 | Overhead | R16 | 2019-05-30 | 19 |  | 6 | 30 | 53 | 2019 | 2019 | R16
166660220561 | 165551220561 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-20 | 2021-02-12 | 2021-02-12 | 2021-10-06 | 2021-11-09 | Overhead | R16 | 2021-10-06 | 127 |  | 169 | 25 | 319 | 2020 | 2021 | R16
169571212933 | 164616212933 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH R16 SVC RELOCATION OD | Commercial | 2020-11-12 | 2020-11-14 | 2020-12-07 | 2021-04-22 | 2021-05-12 | Overhead | R16 | 2021-04-22 | 2 | 16 | 99 | 15 | 130 | 2020 | 2021 | R16
165438307801 | 168100307801 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-14 | 2023-01-31 | 2023-01-31 |  | 2023-07-20 | Overhead | R16 | 2023-03-15 | 35 |  | 32 | 92 | 157 | 2022 | 2023 | R16
161849148072 | 161337148072 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-04-03 | 2019-04-03 | 2019-04-03 | 2019-06-13 | 2019-06-14 | Underground | R16 | 2019-06-13 | 1 |  | 52 | 2 | 53 | 2019 | 2019 | R16
168867207001 | 166225207001 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-06 | 2020-10-06 | 2020-10-12 | 2021-05-10 | 2021-11-04 | Underground | R16 | 2021-05-10 | 1 | 5 | 151 | 129 | 283 | 2020 | 2021 | R16
165501303908 | 167978303908 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-14 | 2022-12-15 | 2023-01-03 |  | 2023-05-30 | Underground | R16 | 2023-02-08 | 2 | 14 | 27 | 80 | 120 | 2022 | 2023 | R16
168924249721 | 164782249721 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-12 | 2021-05-12 | 2021-09-27 | 2022-01-20 | 2022-03-03 | Underground | R16 | 2022-01-20 | 1 | 99 | 84 | 31 | 212 | 2021 | 2022 | R16
168405218324 | 165630218324 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-07 | 2021-01-14 | 2021-01-25 | 2021-02-25 | 2021-03-15 | Underground | R16 | 2021-02-25 | 6 | 8 | 24 | 13 | 48 | 2021 | 2021 | R16
163348228925 | 163708228925 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-28 | 2021-04-30 | 2021-04-30 | 2021-04-30 | 2021-08-11 | Overhead | R16 | 2021-04-30 | 25 |  |  | 74 | 98 | 2021 | 2021 | R16
167561217905 | 168692217905 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-21 | 2021-01-21 | 2021-01-21 | 2021-03-23 | 2021-11-04 | Overhead | R16 | 2021-03-23 | 1 |  | 44 | 163 | 206 | 2021 | 2021 | R16
160875206020 | 162778206020 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-09-23 | 2020-09-23 | 2020-10-01 | 2021-01-13 | 2023-09-15 | Overhead | R16 | 2021-01-13 | 1 | 7 | 75 | 698 | 778 | 2020 | 2023 | R16
169373207958 | 168859207958 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-20 | 2020-10-23 | 2020-10-23 | 2020-12-09 | 2021-06-03 | Overhead | R16 | 2020-12-09 | 4 |  | 34 | 127 | 163 | 2020 | 2021 | R16
160847213842 | 162546213842 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-03 | 2020-11-03 | 2020-12-14 | 2021-02-16 | 2021-03-01 | Underground | R16 | 2021-02-16 | 1 | 30 | 47 | 10 | 85 | 2020 | 2021 | R16
165899245611 | 164201245611 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-09-28 | 2020-09-28 | 2021-08-27 | 2021-12-20 | 2022-01-11 | Underground | R16 | 2021-12-20 | 1 | 240 | 82 | 17 | 337 | 2020 | 2022 | R16
161614210324 | 164285210324 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-11 | 2020-11-11 | 2020-11-11 | 2020-12-15 | 2022-09-01 | Overhead | R16 | 2020-12-15 | 1 |  | 25 | 448 | 472 | 2020 | 2022 | R16
168942240289 | 161240240289 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-28 | 2021-05-04 | 2021-07-23 | 2021-08-24 | 2021-09-02 | Underground | R16 | 2021-08-24 | 5 | 59 | 23 | 8 | 92 | 2021 | 2021 | R16
163552148797 | 168753148797 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-19 | 2019-03-19 | 2019-04-11 | 2019-06-14 | 2019-06-14 | Underground | R16 | 2019-06-14 | 1 | 18 | 47 |  | 64 | 2019 | 2019 | R16
169978216576 | 168874216576 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2020-12-04 | 2020-12-10 | 2021-01-08 | 2021-08-04 | 2021-12-09 | Underground | R16 | 2021-08-04 | 5 | 22 | 149 | 92 | 265 | 2020 | 2021 | R16
164812243157 | 160234243157 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE FOR UPGRADE UD | Commercial | 2021-03-12 | 2021-05-15 | 2021-08-12 | 2021-11-16 | 2021-12-02 | Underground | R16 | 2021-11-16 | 46 | 64 | 69 | 13 | 190 | 2021 | 2021 | R16
160962200747 | 164283200747 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-17 | 2020-08-17 | 2020-08-17 | 2020-09-01 | 2020-11-02 | Overhead | R16 | 2020-09-01 | 1 |  | 12 | 45 | 56 | 2020 | 2020 | R16
169002140483 | 167610140483 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-16 | 2019-01-16 | 2019-01-16 | 2019-05-30 | 2019-05-31 | Overhead | R16 | 2019-05-30 | 1 |  | 97 | 2 | 98 | 2019 | 2019 | R16
167341219832 | 162573219832 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-02-06 | 2021-02-06 | 2021-02-06 | 2022-10-20 | 2022-10-21 | Overhead | R16 | 2022-10-20 | 0 |  | 444 | 2 | 445 | 2021 | 2022 | R16
161741221758 | 166831221758 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-26 | 2021-02-26 | 2021-02-26 | 2021-06-15 | 2021-06-16 | Overhead | R16 | 2021-06-15 | 1 |  | 78 | 2 | 79 | 2021 | 2021 | R16
166972296307 | 161683296307 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-18 | 2021-04-20 | 2022-10-06 | 2023-04-08 | 2023-04-22 | Underground | R16 | 2023-04-08 | 24 | 383 | 132 | 10 | 547 | 2021 | 2023 | R16
166713304438 | 160219304438 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-29 | 2022-12-29 | 2022-12-29 |  | 2023-10-30 | Overhead | R16 | 2023-09-18 | 1 |  | 188 | 31 | 218 | 2022 | 2023 | R16
169638204225 | 161651204225 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-17 | 2020-09-17 | 2020-09-17 | 2020-11-02 | 2021-07-26 | Overhead | R16 | 2020-11-02 | 1 |  | 33 | 191 | 223 | 2020 | 2021 | R16
167972149780 | 168051149780 | NON-RESIDENTIAL - SMALL RETAIL | UG R16 RESD AND NON RESD UD | Commercial | 2019-03-13 | 2019-03-19 | 2019-04-19 | 2020-12-08 | 2021-02-27 | Underground | R16 | 2020-12-08 | 5 | 24 | 428 | 59 | 513 | 2019 | 2021 | R16
163132152008 | 168459152008 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-11 | 2019-05-11 | 2019-05-11 | 2019-05-13 | 2019-08-12 | Overhead | R16 | 2019-05-13 | 0 |  | 1 | 66 | 66 | 2019 | 2019 | R16
167856227932 | 169715227932 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-10 | 2021-03-17 | 2021-04-21 | 2021-08-30 | 2021-08-30 | Overhead | R16 | 2021-08-30 | 6 | 26 | 94 |  | 124 | 2021 | 2021 | R16
165017150859 | 166934150859 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-02 | 2019-05-02 | 2019-05-02 | 2021-08-27 | 2022-08-03 | Overhead | R16 | 2021-08-27 | 1 |  | 607 | 244 | 850 | 2019 | 2022 | R16
165309148157 | 161980148157 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-05 | 2019-04-05 | 2019-04-05 | 2019-04-24 | 2019-04-24 | Overhead | R16 | 2019-04-24 | 1 |  | 14 |  | 14 | 2019 | 2019 | R16
164859139932 | 166179139932 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-09 | 2019-01-09 | 2019-01-11 | 2019-02-25 | 2019-02-25 | Underground | R16 | 2019-02-25 | 1 | 3 | 32 |  | 34 | 2019 | 2019 | R16
160031221535 | 169450221535 | NON-RESIDENTIAL - LARGE RETAIL | R16 RESD AND NON RESD US | Commercial | 2020-09-08 | 2021-02-02 | 2021-02-25 | 2021-06-17 | 2021-07-02 | Underground | R16 | 2021-06-17 | 106 | 18 | 81 | 12 | 214 | 2020 | 2021 | R16
162989246528 | 169125246528 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-22 | 2021-05-22 | 2021-09-02 | 2022-03-08 | 2022-04-01 | Underground | R16 | 2022-03-08 | 0 | 74 | 134 | 19 | 225 | 2021 | 2022 | R16
166990227646 | 161821227646 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-01 | 2020-12-20 | 2021-04-19 | 2021-05-11 | 2021-06-10 | Overhead | R16 | 2021-05-11 | 35 | 86 | 17 | 23 | 159 | 2020 | 2021 | R16
168808280068 | 168689280068 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2021-05-20 | 2021-05-20 | 2022-05-19 |  | 2023-01-25 | Underground | R16 |  | 1 | 261 |  |  | 440 | 2021 | 2023 | R16
169726150862 | 165919150862 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-30 | 2019-04-30 | 2019-04-30 | 2019-07-30 | 2019-09-03 | Overhead | R16 | 2019-07-30 | 1 |  | 66 | 26 | 91 | 2019 | 2019 | R16
161913203025 | 168572203025 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-03 | 2020-09-04 | 2020-09-04 | 2020-09-24 | 2021-06-17 | Overhead | R16 | 2020-09-24 | 2 |  | 15 | 191 | 206 | 2020 | 2021 | R16
161977216697 | 164879216697 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-05 | 2021-01-08 | 2021-01-08 | 2021-06-01 | 2021-06-01 | Underground | R16 | 2021-06-01 | 4 |  | 103 |  | 106 | 2021 | 2021 | R16
166206198979 | 168650198979 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-07-16 | 2020-07-16 | 2020-07-30 | 2020-09-14 | 2020-09-15 | Underground | R16 | 2020-09-14 | 1 | 11 | 33 | 2 | 44 | 2020 | 2020 | R16
167749313067 | 166873313067 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-16 | 2023-03-20 | 2023-03-20 |  | 2023-08-30 | Overhead | R16 | 2023-05-15 | 3 |  | 41 | 78 | 120 | 2023 | 2023 | R16
162902202988 | 167764202988 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-31 | 2020-08-31 | 2020-09-04 | 2020-10-21 | 2020-10-22 | Underground | R16 | 2020-10-21 | 1 | 5 | 34 | 2 | 39 | 2020 | 2020 | R16
161613218916 | 169328218916 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-25 | 2021-01-29 | 2021-01-29 | 2021-03-25 | 2021-08-06 | Overhead | R16 | 2021-03-25 | 5 |  | 40 | 97 | 140 | 2021 | 2021 | R16
162920230755 | 165387230755 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-14 | 2021-05-14 | 2021-05-14 | 2022-12-14 | 2023-06-07 | Overhead | R16 | 2022-12-14 | 1 |  | 414 | 126 | 539 | 2021 | 2023 | R16
163123224325 | 169342224325 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-09 | 2021-03-09 | 2021-03-22 | 2021-07-02 | 2021-08-12 | Underground | R16 | 2021-07-02 | 1 | 10 | 75 | 30 | 113 | 2021 | 2021 | R16
168620207006 | 167285207006 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-12 | 2020-10-12 | 2020-10-12 | 2020-12-10 | 2022-06-01 | Overhead | R16 | 2020-12-10 | 1 |  | 44 | 385 | 428 | 2020 | 2022 | R16
163977226227 | 165757226227 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-05 | 2021-04-05 | 2021-04-08 | 2021-07-26 | 2023-04-13 | Underground | R16 | 2021-07-26 | 1 | 4 | 78 | 449 | 529 | 2021 | 2023 | R16
168351207055 | 167475207055 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-13 | 2020-10-13 | 2020-10-13 | 2020-10-16 | 2021-07-02 | Overhead | R16 | 2020-10-16 | 1 |  | 4 | 186 | 189 | 2020 | 2021 | R16
162730157947 | 167766157947 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH CP R16 WORK RELO TO UG | Commercial | 2019-03-12 | 2019-03-27 | 2019-07-16 | 2019-08-21 | 2021-11-30 | Overhead | R16 | 2019-08-21 | 12 | 80 | 27 | 595 | 711 | 2019 | 2021 | R16
167972199081 | 160909199081 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-30 | 2020-07-30 | 2020-07-30 | 2020-09-02 | 2020-09-03 | Overhead | R16 | 2020-09-02 | 1 |  | 25 | 2 | 26 | 2020 | 2020 | R16
161482210686 | 164813210686 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-13 | 2020-11-13 | 2020-11-13 | 2020-12-31 | 2021-04-16 | Overhead | R16 | 2020-12-31 | 1 |  | 35 | 77 | 111 | 2020 | 2021 | R16
166024209826 | 163033209826 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-11-05 | 2020-11-05 | 2020-11-05 | 2021-01-12 | 2021-04-20 | Overhead | R16 | 2021-01-12 | 1 |  | 49 | 71 | 119 | 2020 | 2021 | R16
167544146371 | 167442146371 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential Subdivision | 2019-03-11 | 2019-03-11 | 2019-03-19 | 2021-03-18 | 2021-02-24 | Underground | R16 | 2021-03-18 | 1 | 7 | 523 |  | 513 | 2019 | 2021 | R16
168667308929 | 166950308929 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-30 | 2023-01-30 | 2023-02-09 |  | 2023-08-04 | Underground | R16 | 2023-03-24 | 1 | 9 | 32 | 96 | 135 | 2023 | 2023 | R16
166961228658 | 161407228658 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-29 | 2021-04-29 | 2021-04-29 | 2021-07-26 | 2021-08-23 | Overhead | R16 | 2021-07-26 | 1 |  | 63 | 21 | 83 | 2021 | 2021 | R16
168050148214 | 161698148214 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-04 | 2019-04-04 | 2019-04-04 | 2019-05-22 | 2019-05-22 | Overhead | R16 | 2019-05-22 | 1 |  | 35 |  | 35 | 2019 | 2019 | R16
166250292895 | 162925292895 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2019-02-12 | 2020-10-23 | 2023-01-30 | 2023-02-08 | 2023-03-01 | Underground | R16 | 2023-02-08 | 444 | 592 | 8 | 16 | 1057 | 2019 | 2023 | R16
162753154695 | 162892154695 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-07 | 2019-06-07 | 2019-06-07 | 2019-07-23 | 2019-07-23 | Overhead | R16 | 2019-07-23 | 1 |  | 33 |  | 33 | 2019 | 2019 | R16
163622199645 | 162008199645 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-04 | 2020-08-04 | 2020-08-04 | 2020-09-24 | 2020-12-29 | Overhead | R16 | 2020-09-24 | 1 |  | 38 | 69 | 106 | 2020 | 2020 | R16
162732227835 | 165844227835 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-06 | 2021-04-21 | 2021-04-21 | 2021-04-30 | 2021-10-25 | Underground | R16 | 2021-04-30 | 12 |  | 8 | 127 | 145 | 2021 | 2021 | R16
164416216886 | 166808216886 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-09 | 2020-10-09 | 2021-01-11 | 2022-11-30 | 2022-12-13 | Underground | R16 | 2022-11-30 | 1 | 67 | 493 | 10 | 568 | 2020 | 2022 | R16
166415209022 | 169721209022 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-10-22 | 2020-10-29 | 2020-10-29 | 2020-11-02 | 2021-07-26 | Overhead | R16 | 2020-11-02 | 6 |  | 3 | 191 | 198 | 2020 | 2021 | R16
169587212781 | 165757212781 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-19 | 2020-12-03 | 2020-12-03 | 2021-01-12 | 2021-08-11 | Overhead | R16 | 2021-01-12 | 11 |  | 29 | 152 | 190 | 2020 | 2021 | R16
169367233081 | 161206233081 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-28 | 2021-05-04 | 2021-06-01 | 2021-06-11 | 2023-06-07 | Overhead | R16 | 2021-06-11 | 5 | 21 | 9 | 519 | 551 | 2021 | 2023 | R16
167108152918 | 160466152918 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-22 | 2019-05-23 | 2019-05-23 | 2019-08-12 | 2019-12-06 | Overhead | R16 | 2019-08-12 | 2 |  | 58 | 85 | 143 | 2019 | 2019 | R16
160523153405 | 160532153405 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-01-31 | 2019-01-31 | 2019-05-23 | 2019-12-15 | 2020-02-19 | Underground | R16 | 2019-12-15 | 1 | 81 | 147 | 48 | 275 | 2019 | 2020 | R16
168346212730 | 168697212730 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-04 | 2020-12-04 | 2020-12-04 | 2020-12-17 | 2021-04-22 | Overhead | R16 | 2020-12-17 | 1 |  | 10 | 91 | 100 | 2020 | 2021 | R16
163704153735 | 168433153735 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-10 | 2019-05-10 | 2019-05-30 | 2019-08-28 | 2019-09-11 | Underground | R16 | 2019-08-28 | 1 | 15 | 65 | 11 | 89 | 2019 | 2019 | R16
162697145083 | 166469145083 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-10 | 2019-01-11 | 2019-03-05 | 2019-06-24 | 2019-11-11 | Overhead | R16 | 2019-06-24 | 2 | 38 | 80 | 101 | 218 | 2019 | 2019 | R16
160409229592 | 163006229592 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-05 | 2021-05-05 | 2021-05-05 | 2022-10-14 | 2022-10-17 | Overhead | R16 | 2022-10-14 | 1 |  | 378 | 2 | 379 | 2021 | 2022 | R16
163259198359 | 160164198359 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-25 | 2020-07-25 | 2020-07-25 | 2020-08-07 | 2020-10-06 | Overhead | R16 | 2020-08-07 | 0 |  | 10 | 43 | 52 | 2020 | 2020 | R16
169820160313 | 162012160313 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-03 | 2019-06-03 | 2019-08-06 | 2020-10-02 | 2021-01-08 | Underground | R16 | 2020-10-02 | 1 | 47 | 304 | 71 | 420 | 2019 | 2021 | R16
161590152898 | 160461152898 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-22 | 2019-05-22 | 2019-05-22 | 2019-06-18 | 2019-06-18 | Overhead | R16 | 2019-06-18 | 1 |  | 20 |  | 20 | 2019 | 2019 | R16
169159258886 | 161207258886 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-28 | 2021-05-04 | 2021-11-29 | 2022-07-27 | 2022-07-29 | Underground | R16 | 2022-07-27 | 5 | 150 | 173 | 3 | 328 | 2021 | 2022 | R16
163649150096 | 165174150096 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-24 | 2019-04-24 | 2019-04-24 | 2019-05-15 | 2019-05-15 | Overhead | R16 | 2019-05-15 | 1 |  | 16 |  | 16 | 2019 | 2019 | R16
161452146642 | 168857146642 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-19 | 2019-03-19 | 2019-03-19 | 2019-04-24 | 2019-04-25 | Overhead | R16 | 2019-04-24 | 1 |  | 27 | 2 | 28 | 2019 | 2019 | R16
169411226294 | 166699226294 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2021-04-09 | 2021-04-09 | 2021-04-09 | 2021-04-12 | 2021-05-22 | Overhead | R16 | 2021-04-12 | 1 |  | 2 | 30 | 31 | 2021 | 2021 | R16
161690202381 | 167734202381 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2021-01-21 | 2021-04-21 | Overhead | R16 | 2021-01-21 | 1 |  | 104 | 65 | 168 | 2020 | 2021 | R16
160896215582 | 161942215582 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-02 | 2020-11-05 | 2020-12-28 | 2021-03-16 | 2021-03-17 | Underground | R16 | 2021-03-16 | 4 | 38 | 57 | 2 | 98 | 2020 | 2021 | R16
166130253969 | 166031253969 | SPECIFIC BUDGET PROJECTS | UG R16 RESD AND NON RESD UD | Commercial | 2021-01-11 | 2021-04-12 | 2021-10-27 |  | 2023-04-05 | Underground | R16 |  | 66 | 143 |  |  | 583 | 2021 | 2023 | R16
167743216458 | 167725216458 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-14 | 2020-10-14 | 2021-01-07 | 2021-08-31 | 2021-09-01 | Underground | R16 | 2021-08-31 | 1 | 62 | 169 | 2 | 231 | 2020 | 2021 | R16
164842226163 | 165989226163 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-06 | 2021-04-07 | 2021-04-07 | 2021-06-28 | 2022-08-03 | Overhead | R16 | 2021-06-28 | 2 |  | 59 | 288 | 347 | 2021 | 2022 | R16
167564143169 | 160492143169 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-31 | 2019-01-31 | 2019-02-14 | 2019-05-08 | 2019-05-09 | Underground | R16 | 2019-05-08 | 1 | 11 | 60 | 2 | 71 | 2019 | 2019 | R16
164150268267 | 163998268267 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2021-03-29 | 2021-03-31 | 2022-02-09 | 2022-07-22 | 2022-08-04 | Underground | R16 | 2022-07-22 | 3 | 226 | 118 | 10 | 354 | 2021 | 2022 | R16
163104226362 | 169401226362 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-09 | 2021-04-09 | 2021-04-09 | 2021-06-11 | 2021-11-03 | Overhead | R16 | 2021-06-11 | 24 |  | 46 | 104 | 172 | 2021 | 2021 | R16
168659150592 | 162126150592 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-02-07 | 2019-03-22 | 2019-04-29 | 2020-03-23 | 2020-11-11 | Underground | R16 | 2020-03-23 | 32 | 27 | 236 | 168 | 460 | 2019 | 2020 | R16
166841207422 | 167540207422 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-10-13 | 2020-10-14 | 2020-10-15 | 2021-02-26 | 2021-04-06 | Underground | R16 | 2021-02-26 | 2 | 2 | 97 | 28 | 126 | 2020 | 2021 | R16
164365146145 | 168249146145 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-15 | 2019-03-15 | 2019-03-15 | 2019-04-01 | 2019-04-02 | Overhead | R16 | 2019-04-01 | 1 |  | 12 | 2 | 13 | 2019 | 2019 | R16
168652207391 | 169682207391 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-17 | 2019-05-17 | 2020-10-15 | 2021-02-19 | 2021-06-03 | Underground | R16 | 2021-02-19 | 1 | 370 | 92 | 75 | 535 | 2019 | 2021 | R16
165810202456 | 168370202456 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-02 | 2020-09-02 | 2020-09-02 | 2022-03-06 | 2022-04-14 | Overhead | R16 | 2022-03-06 | 1 |  | 393 | 29 | 422 | 2020 | 2022 | R16
165241210671 | 164737210671 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-13 | 2020-11-13 | 2020-11-13 | 2020-12-18 | 2021-05-06 | Overhead | R16 | 2020-12-18 | 1 |  | 26 | 100 | 125 | 2020 | 2021 | R16
162871149907 | 164822149907 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-22 | 2019-04-22 | 2019-04-22 | 2019-05-06 | 2019-05-07 | Overhead | R16 | 2019-05-06 | 1 |  | 11 | 2 | 12 | 2019 | 2019 | R16
165775224490 | 162850224490 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-23 | 2021-03-23 | 2021-03-23 | 2021-09-21 | 2021-11-09 | Overhead | R16 | 2021-09-21 | 1 |  | 131 | 36 | 166 | 2021 | 2021 | R16
168032243087 | 169693243087 | Electric Vehicle | UG R16 RESD AND NON RESD UD | Commercial | 2021-03-10 | 2021-05-27 | 2021-08-11 | 2022-03-21 | 2022-11-01 | Underground | R16 | 2022-03-21 | 57 | 55 | 159 | 162 | 430 | 2021 | 2022 | R16
163808147021 | 167529147021 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-11 | 2019-03-11 | 2019-03-23 | 2019-05-16 | 2019-05-16 | Underground | R16 | 2019-05-16 | 1 | 10 | 39 |  | 49 | 2019 | 2019 | R16
167920216395 | 165113216395 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2020-08-19 | 2020-08-31 | 2021-01-07 | 2021-10-05 | 2021-10-27 | Underground | R16 | 2021-10-05 | 9 | 94 | 194 | 17 | 311 | 2020 | 2021 | R16
169782232388 | 166115232388 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-18 | 2021-05-26 | 2021-05-26 | 2021-07-28 | 2021-07-30 | Overhead | R16 | 2021-07-28 | 7 |  | 46 | 3 | 54 | 2021 | 2021 | R16
165498151062 | 166224151062 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-04-30 | 2019-04-30 | 2019-05-01 | 2019-10-22 | 2019-10-23 | Underground | R16 | 2019-10-22 | 1 | 2 | 125 | 2 | 127 | 2019 | 2019 | R16
169980278494 | 164118278494 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-05-10 | 2022-05-06 | 2022-05-06 | 2022-07-19 | 2022-08-23 | Overhead | R16 | 2022-07-19 | 260 |  | 53 | 26 | 337 | 2021 | 2022 | R16
162558222890 | 169345222890 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-09 | 2021-03-09 | 2021-03-09 | 2021-05-17 | 2021-05-18 | Overhead | R16 | 2021-05-17 | 1 |  | 50 | 2 | 51 | 2021 | 2021 | R16
168043211014 | 163539211014 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-11-09 | 2020-11-09 | 2020-11-17 | 2021-07-26 | 2021-07-27 | Underground | R16 | 2021-07-26 | 1 | 7 | 180 | 2 | 187 | 2020 | 2021 | R16
167825211598 | 168620211598 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-18 | 2020-10-18 | 2020-11-24 | 2021-01-29 | 2021-05-19 | Underground | R16 | 2021-01-29 | 0 | 27 | 49 | 79 | 153 | 2020 | 2021 | R16
164489212794 | 165590212794 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-18 | 2020-11-18 | 2020-12-04 | 2021-02-08 | 2021-08-12 | Underground | R16 | 2021-02-08 | 1 | 13 | 47 | 134 | 192 | 2020 | 2021 | R16
161775319299 | 163372319299 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-13 | 2023-05-03 | 2023-05-17 |  | 2023-09-13 | Overhead | R16 |  | 15 | 11 |  |  | 110 | 2023 | 2023 | R16
166980204407 | 161909204407 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-19 | 2020-09-19 | 2020-09-19 | 2021-05-26 | 2021-11-03 | Overhead | R16 | 2021-05-26 | 0 |  | 178 | 116 | 293 | 2020 | 2021 | R16
167638234535 | 168462234535 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-05-19 | 2021-05-19 | 2021-06-11 | 2021-09-28 | 2021-10-26 | Underground | R16 | 2021-09-28 | 1 | 18 | 78 | 21 | 115 | 2021 | 2021 | R16
165070199077 | 168923199077 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-20 | 2020-07-30 | 2020-07-30 | 2020-08-19 | 2020-10-06 | Overhead | R16 | 2020-08-19 | 9 |  | 15 | 35 | 57 | 2020 | 2020 | R16
169204226062 | 166723226062 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-02-25 | 2021-04-07 | 2021-04-07 | 2022-01-05 | 2022-02-07 | Overhead | R16 | 2022-01-05 | 30 |  | 196 | 24 | 248 | 2021 | 2022 | R16
165464153871 | 166226153871 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-30 | 2019-04-30 | 2019-05-30 | 2019-07-31 | 2019-07-31 | Underground | R16 | 2019-07-31 | 1 | 23 | 45 |  | 67 | 2019 | 2019 | R16
164063154404 | 162174154404 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-05 | 2019-06-05 | 2019-06-05 | 2019-06-18 | 2019-06-18 | Overhead | R16 | 2019-06-18 | 1 |  | 10 |  | 10 | 2019 | 2019 | R16
160669230340 | 161772230340 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential Subdivision | 2021-04-30 | 2021-04-30 | 2021-05-11 | 2023-06-15 | 2023-09-06 | Underground | R16 | 2023-06-15 | 1 | 8 | 548 | 60 | 614 | 2021 | 2023 | R16
162349304851 | 168271304851 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-15 | 2022-12-15 | 2023-01-04 |  | 2023-05-04 | Overhead | R16 | 2023-03-01 | 1 | 15 | 41 | 47 | 101 | 2022 | 2023 | R16
168140207631 | 168691207631 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-19 | 2020-10-20 | 2020-10-20 | 2020-11-03 | 2021-07-19 | Overhead | R16 | 2020-11-03 | 2 |  | 11 | 185 | 196 | 2020 | 2021 | R16
162602308787 | 169204308787 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-08 | 2023-02-08 | 2023-02-08 |  | 2023-08-08 | Overhead | R16 | 2023-04-12 | 1 |  | 46 | 85 | 130 | 2023 | 2023 | R16
168832146407 | 168598146407 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-18 | 2019-03-18 | 2019-03-18 | 2019-04-12 | 2019-04-17 | Overhead | R16 | 2019-04-12 | 1 |  | 20 | 4 | 23 | 2019 | 2019 | R16
168981283387 | 161320283387 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-10-29 | 2020-12-08 | 2022-06-22 | 2022-07-01 | 2023-06-07 | Underground | R16 | 2022-07-01 | 29 | 402 | 8 | 244 | 680 | 2020 | 2023 | R16
161673205746 | 163830205746 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-14 | 2020-08-14 | 2020-09-29 | 2020-11-17 | 2020-12-16 | Underground | R16 | 2020-11-17 | 1 | 33 | 36 | 22 | 89 | 2020 | 2020 | R16
162778299641 | 165024299641 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH CP R16 WORK RELO TO UG | Commercial | 2021-02-18 | 2021-04-30 | 2022-11-07 | 2023-06-19 | 2023-07-25 | Overhead | R16 | 2023-06-19 | 52 | 397 | 161 | 27 | 634 | 2021 | 2023 | R16
162746150035 | 162694150035 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-10 | 2019-04-10 | 2019-04-25 | 2019-04-29 | 2019-05-08 | Overhead | R16 | 2019-04-29 | 1 | 12 | 3 | 8 | 21 | 2019 | 2019 | R16
161424142900 | 162641142900 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-02-11 | 2019-02-11 | 2019-02-11 | 2019-06-04 | 2019-06-04 | Overhead | R16 | 2019-06-04 | 1 |  | 82 |  | 82 | 2019 | 2019 | R16
163357311385 | 162709311385 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-24 | 2023-03-02 | 2023-03-03 |  | 2023-07-11 | Underground | R16 | 2023-05-24 | 5 | 2 | 59 | 35 | 98 | 2023 | 2023 | R16
164274229181 | 160986229181 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-31 | 2021-04-30 | 2021-05-02 | 2022-01-14 | 2022-02-17 | Overhead | R16 | 2022-01-14 | 65 | 1 | 185 | 25 | 274 | 2021 | 2022 | R16
167102152704 | 168910152704 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-14 | 2019-05-17 | 2019-05-17 | 2020-01-22 | 2020-06-23 | Overhead | R16 | 2020-01-22 | 4 |  | 179 | 110 | 291 | 2019 | 2020 | R16
161689220288 | 163568220288 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2021-02-11 | 2021-02-11 | 2021-02-11 | 2021-02-23 | 2021-06-02 | Overhead | R16 | 2021-02-23 | 1 |  | 9 | 72 | 80 | 2021 | 2021 | R16
163321143521 | 162745143521 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-11 | 2019-02-15 | 2019-02-15 | 2019-04-05 | 2019-04-23 | Overhead | R16 | 2019-04-05 | 5 |  | 36 | 13 | 52 | 2019 | 2019 | R16
166977218778 | 160673218778 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-28 | 2021-01-28 | 2021-01-29 | 2021-08-23 | 2022-08-03 | Overhead | R16 | 2021-08-23 | 1 | 2 | 147 | 248 | 395 | 2021 | 2022 | R16
164041153248 | 167252153248 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-03 | 2019-05-23 | 2019-05-23 | 2019-05-30 | 2019-07-08 | Overhead | R16 | 2019-05-30 | 15 |  | 6 | 28 | 47 | 2019 | 2019 | R16
168595234946 | 169595234946 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-05-25 | 2021-05-25 | 2021-06-14 | 2022-05-16 | 2022-06-09 | Underground | R16 | 2022-05-16 | 1 | 15 | 241 | 19 | 273 | 2021 | 2022 | R16
168570213680 | 160121213680 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-11 | 2020-12-11 | 2020-12-11 | 2020-12-14 | 2021-07-28 | Overhead | R16 | 2020-12-14 | 1 |  | 2 | 163 | 164 | 2020 | 2021 | R16
162413272446 | 166344272446 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Commercial | 2021-04-07 | 2021-04-07 | 2022-03-14 | 2022-12-28 | 2023-01-06 | Underground | R16 | 2022-12-28 | 1 | 244 | 208 | 8 | 458 | 2021 | 2023 | R16
161681150190 | 162705150190 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-10 | 2019-04-25 | 2019-04-25 | 2019-05-25 | 2019-05-28 | Overhead | R16 | 2019-05-25 | 12 |  | 22 | 2 | 35 | 2019 | 2019 | R16
168383229291 | 162417229291 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-03 | 2021-05-03 | 2021-05-03 | 2021-05-06 | 2021-08-12 | Overhead | R16 | 2021-05-06 | 1 |  | 4 | 71 | 74 | 2021 | 2021 | R16
165884231832 | 165755231832 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2020-11-19 | 2020-11-19 | 2021-05-21 | 2023-08-10 | 2022-11-01 | Underground | R16 | 2023-08-10 | 1 | 132 | 580 |  | 509 | 2020 | 2022 | R16
167909153464 | 162300153464 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-04-08 | 2019-04-08 | 2019-05-28 | 2019-06-03 | 2019-06-05 | Underground | R16 | 2019-06-03 | 1 | 37 | 5 | 3 | 43 | 2019 | 2019 | R16
164039307481 | 166183307481 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-01-25 | 2023-01-25 | 2023-01-27 |  | 2023-06-16 | Overhead | R16 | 2023-02-22 | 1 | 3 | 19 | 83 | 103 | 2023 | 2023 | R16
160125225805 | 160932225805 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-16 | 2021-03-24 | 2021-04-05 | 2021-07-13 | 2021-07-13 | Underground | R16 | 2021-07-13 | 7 | 9 | 72 |  | 86 | 2021 | 2021 | R16
165890150341 | 165480150341 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-25 | 2019-04-25 | 2019-04-25 | 2019-09-06 | 2019-10-16 | Overhead | R16 | 2019-09-06 | 1 |  | 97 | 29 | 125 | 2019 | 2019 | R16
166863147967 | 161129147967 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-02 | 2019-04-03 | 2019-04-03 | 2019-04-19 | 2019-04-23 | Overhead | R16 | 2019-04-19 | 2 |  | 13 | 3 | 16 | 2019 | 2019 | R16
165106226466 | 166354226466 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-04-07 | 2021-04-12 | 2021-04-12 | 2021-05-16 | 2021-05-20 | Underground | R16 | 2021-05-16 | 4 |  | 25 | 4 | 32 | 2021 | 2021 | R16
165579221405 | 165623221405 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2021-01-07 | 2021-01-07 | 2021-02-23 | 2021-05-26 | 2022-08-25 | Underground | R16 | 2021-05-26 | 1 | 34 | 67 | 327 | 426 | 2021 | 2022 | R16
160559226487 | 167120226487 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-10 | 2021-04-10 | 2021-04-10 | 2022-03-07 | 2022-04-01 | Overhead | R16 | 2022-03-07 | 0 |  | 236 | 20 | 255 | 2021 | 2022 | R16
160717142480 | 161336142480 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-05 | 2019-02-05 | 2019-02-05 | 2019-06-13 | 2019-06-13 | Overhead | R16 | 2019-06-13 | 1 |  | 93 |  | 93 | 2019 | 2019 | R16
168374198598 | 160453198598 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-28 | 2020-07-28 | 2020-07-28 | 2021-10-14 | 2021-10-15 | Overhead | R16 | 2021-10-14 | 1 |  | 318 | 2 | 319 | 2020 | 2021 | R16
162413205599 | 161027205599 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-16 | 2020-09-16 | 2020-09-29 | 2020-10-02 | 2021-01-20 | Underground | R16 | 2020-10-02 | 1 | 10 | 4 | 79 | 91 | 2020 | 2021 | R16
165500225947 | 165901225947 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-06 | 2021-04-06 | 2021-04-06 | 2021-04-07 | 2021-10-14 | Overhead | R16 | 2021-04-07 | 1 |  | 2 | 137 | 138 | 2021 | 2021 | R16
166460201958 | 167007201958 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-27 | 2020-08-27 | 2020-08-27 | 2020-09-14 | 2021-01-08 | Underground | R16 | 2020-09-14 | 1 |  | 13 | 85 | 97 | 2020 | 2021 | R16
160402276162 | 169083276162 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-12-07 | 2020-12-12 | 2022-04-18 | 2022-12-01 | 2022-12-20 | Underground | R16 | 2022-12-01 | 5 | 351 | 164 | 14 | 532 | 2020 | 2022 | R16
167999219294 | 160075219294 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-01-27 | 2021-01-27 | 2021-02-03 | 2021-02-05 | 2021-08-11 | Underground | R16 | 2021-02-05 | 1 | 6 | 3 | 134 | 141 | 2021 | 2021 | R16
169003200345 | 163183200345 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-11 | 2020-08-11 | 2020-08-11 | 2021-03-04 | 2021-08-16 | Overhead | R16 | 2021-03-04 | 1 |  | 148 | 118 | 265 | 2020 | 2021 | R16
165290146925 | 169389146925 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2019-03-22 | 2019-03-22 | 2019-03-22 | 2020-01-29 | 2020-01-30 | Overhead | R16 | 2020-01-29 | 1 |  | 224 | 2 | 225 | 2019 | 2020 | R16
161980211220 | 168220211220 | AGRICULTURAL | OH R16 RES NON RES OD | Residential | 2020-09-02 | 2020-09-02 | 2020-11-18 | 2022-02-08 | 2022-02-24 | Overhead | R16 | 2022-02-08 | 1 | 56 | 320 | 13 | 387 | 2020 | 2022 | R16
161359222224 | 169417222224 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-25 | 2021-01-30 | 2021-03-02 | 2021-03-10 | 2021-08-06 | Overhead | R16 | 2021-03-10 | 5 | 22 | 7 | 108 | 140 | 2021 | 2021 | R16
160083226253 | 161526226253 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2021-02-01 | 2021-03-25 | 2021-04-09 | 2021-08-04 | 2021-12-17 | Underground | R16 | 2021-08-04 | 39 | 12 | 84 | 98 | 230 | 2021 | 2021 | R16
165257304007 | 167987304007 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-12-14 | 2022-12-14 | 2022-12-27 |  | 2023-03-24 | Overhead | R16 | 2023-01-09 | 1 | 10 | 10 | 55 | 73 | 2022 | 2023 | R16
168344207058 | 167549207058 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-13 | 2020-10-13 | 2020-10-13 | 2020-10-16 | 2021-04-21 | Overhead | R16 | 2020-10-16 | 1 |  | 4 | 134 | 137 | 2020 | 2021 | R16
167405157853 | 165297157853 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-26 | 2019-02-27 | 2019-07-16 | 2019-07-29 | 2019-08-01 | Overhead | R16 | 2019-07-29 | 2 | 100 | 10 | 4 | 113 | 2019 | 2019 | R16
163000190933 | 160069190933 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-03-27 | 2019-03-27 | 2020-05-14 | 2020-10-29 | 2021-07-26 | Underground | R16 | 2020-10-29 | 1 | 297 | 121 | 193 | 609 | 2019 | 2021 | R16
162583226280 | 168821226280 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-07 | 2021-04-08 | 2021-04-08 | 2021-04-16 | 2021-11-02 | Overhead | R16 | 2021-04-16 | 24 |  | 7 | 143 | 172 | 2021 | 2021 | R16
169469154640 | 169306154640 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-16 | 2019-05-16 | 2019-06-06 | 2019-07-26 | 2019-07-31 | Underground | R16 | 2019-07-26 | 1 | 16 | 37 | 4 | 55 | 2019 | 2019 | R16
168584146510 | 168959146510 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-19 | 2019-03-19 | 2019-03-19 | 2019-05-01 | 2019-05-01 | Overhead | R16 | 2019-05-01 | 1 |  | 32 |  | 32 | 2019 | 2019 | R16
168916149466 | 164068149466 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-17 | 2019-04-17 | 2019-04-17 | 2019-05-13 | 2019-05-13 | Overhead | R16 | 2019-05-13 | 1 |  | 19 |  | 19 | 2019 | 2019 | R16
169499231851 | 162272231851 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-03 | 2021-05-20 | 2021-05-20 | 2021-07-21 | 2021-08-23 | Overhead | R16 | 2021-07-21 | 14 |  | 45 | 24 | 81 | 2021 | 2021 | R16
164229259788 | 164291259788 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2021-03-29 | 2021-03-29 | 2021-12-03 | 2022-06-06 | 2022-06-22 | Underground | R16 | 2022-06-06 | 1 | 180 | 132 | 13 | 323 | 2021 | 2022 | R16
164726151908 | 164753151908 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-04-22 | 2019-04-22 | 2019-05-09 | 2019-07-26 | 2019-07-29 | Underground | R16 | 2019-07-26 | 1 | 14 | 57 | 2 | 71 | 2019 | 2019 | R16
160806233905 | 160997233905 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-12-15 | 2021-05-12 | 2021-06-07 | 2021-08-26 | 2021-08-27 | Underground | R16 | 2021-08-26 | 107 | 19 | 59 | 2 | 184 | 2020 | 2021 | R16
165357206190 | 165450206190 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-02 | 2020-10-02 | 2020-10-06 | 2020-12-17 | 2023-10-16 | Overhead | R16 | 2020-12-17 | 1 | 3 | 53 | 738 | 792 | 2020 | 2023 | R16
161607226742 | 167741226742 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-13 | 2021-04-13 | 2021-04-13 | 2021-07-28 | 2021-08-23 | Overhead | R16 | 2021-07-28 | 1 |  | 77 | 19 | 95 | 2021 | 2021 | R16
166460227278 | 168661227278 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-16 | 2021-04-16 | 2021-04-16 | 2021-12-03 | 2022-10-17 | Overhead | R16 | 2021-12-03 | 1 |  | 166 | 227 | 392 | 2021 | 2022 | R16
169440213448 | 160601213448 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-26 | 2020-11-04 | 2020-12-10 | 2021-03-29 | 2021-04-01 | Underground | R16 | 2021-03-29 | 8 | 27 | 78 | 4 | 114 | 2020 | 2021 | R16
166195207579 | 169162207579 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-20 | 2020-10-20 | 2020-10-20 | 2020-12-28 | 2020-12-28 | Underground | R16 | 2020-12-28 | 1 |  | 50 |  | 50 | 2020 | 2020 | R16
161777220185 | 163256220185 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-09 | 2021-02-09 | 2021-02-09 | 2021-03-10 | 2021-11-04 | Overhead | R16 | 2021-03-10 | 1 |  | 22 | 172 | 193 | 2021 | 2021 | R16
166780221110 | 168104221110 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-01 | 2020-09-08 | 2021-02-19 | 2021-04-11 | 2021-04-20 | Underground | R16 | 2021-04-11 | 6 | 119 | 36 | 7 | 166 | 2020 | 2021 | R16
167118225137 | 162787225137 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-23 | 2021-03-29 | 2021-03-29 | 2021-07-19 | 2021-11-09 | Overhead | R16 | 2021-07-19 | 5 |  | 81 | 82 | 166 | 2021 | 2021 | R16
162212207549 | 163764207549 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-14 | 2020-08-14 | 2020-10-16 | 2020-12-10 | 2020-12-16 | Underground | R16 | 2020-12-10 | 1 | 46 | 40 | 5 | 89 | 2020 | 2020 | R16
165674219876 | 165527219876 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-01-07 | 2021-01-08 | 2021-02-09 | 2021-02-26 | 2021-03-25 | Overhead | R16 | 2021-02-26 | 2 | 23 | 14 | 20 | 56 | 2021 | 2021 | R16
160970249063 | 167264249063 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-28 | 2021-03-02 | 2021-09-22 | 2022-02-14 | 2023-06-08 | Underground | R16 | 2022-02-14 | 2 | 147 | 104 | 344 | 594 | 2021 | 2023 | R16
160043225015 | 164240225015 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-06-14 | 2021-06-15 | Overhead | R16 | 2021-06-14 | 1 |  | 56 | 2 | 57 | 2021 | 2021 | R16
160328198589 | 160207198589 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-27 | 2020-07-27 | 2020-07-27 |  | 2022-10-20 | Overhead | R16 |  | 1 |  |  |  | 584 | 2020 | 2022 | R16
167543150273 | 168167150273 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2019-01-22 | 2019-01-22 | 2019-04-26 | 2021-04-06 | 2021-11-12 | Underground | R16 | 2021-04-06 | 1 | 69 | 508 | 159 | 734 | 2019 | 2021 | R16
167722198767 | 160248198767 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-28 | 2020-07-28 | 2020-07-28 | 2020-08-21 | 2021-01-08 | Overhead | R16 | 2020-08-21 | 1 |  | 19 | 101 | 119 | 2020 | 2021 | R16
165051146202 | 165866146202 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-01 | 2019-03-01 | 2019-03-15 | 2019-05-01 | 2019-05-01 | Underground | R16 | 2019-05-01 | 1 | 11 | 34 |  | 44 | 2019 | 2019 | R16
166738322702 | 162622322702 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-01-10 | 2023-01-10 | 2023-06-19 |  | 2023-09-28 | Overhead | R16 | 2023-06-19 | 1 | 115 |  | 74 | 188 | 2023 | 2023 | R16
166823307717 | 167083307717 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-30 | 2023-01-30 | 2023-01-30 |  | 2023-06-16 | Overhead | R16 | 2023-01-31 | 1 |  | 2 | 99 | 100 | 2023 | 2023 | R16
167228309509 | 167294309509 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-31 | 2023-01-31 | 2023-02-15 |  | 2023-07-07 | Underground | R16 | 2023-02-21 | 1 | 12 | 5 | 99 | 114 | 2023 | 2023 | R16
163692221271 | 165038221271 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-18 | 2021-02-22 | 2021-02-22 | 2021-04-28 | 2021-04-29 | Overhead | R16 | 2021-04-28 | 3 |  | 48 | 2 | 51 | 2021 | 2021 | R16
165786223464 | 160352223464 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-12 | 2021-03-12 | 2021-03-12 | 2021-05-14 | 2021-12-29 | Underground | R16 | 2021-05-14 | 1 |  | 46 | 164 | 209 | 2021 | 2021 | R16
166193199087 | 160594199087 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-29 | 2020-07-29 | 2020-07-30 | 2020-09-04 | 2020-12-15 | Overhead | R16 | 2020-09-04 | 1 | 2 | 27 | 73 | 100 | 2020 | 2020 | R16
164143223736 | 161460223736 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-17 | 2021-03-16 | 2021-03-16 | 2021-03-16 | 2021-08-02 | Overhead | R16 | 2021-03-16 | 64 |  |  | 100 | 163 | 2020 | 2021 | R16
163203234510 | 169836234510 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2021-05-25 | 2021-06-08 | 2021-06-10 | 2021-07-06 | 2021-08-12 | Overhead | R16 | 2021-07-06 | 11 | 3 | 19 | 28 | 58 | 2021 | 2021 | R16
166999220614 | 162826220614 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-08 | 2021-02-16 | 2021-02-16 | 2021-03-09 | 2021-11-05 | Underground | R16 | 2021-03-09 | 7 |  | 16 | 174 | 195 | 2021 | 2021 | R16
169358208502 | 169003208502 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-20 | 2020-10-26 | 2020-10-26 | 2020-10-28 | 2021-04-15 | Overhead | R16 | 2020-10-28 | 5 |  | 3 | 122 | 128 | 2020 | 2021 | R16
167569307456 | 166855307456 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-28 | 2023-01-28 | 2023-01-28 |  | 2023-05-05 | Overhead | R16 | 2023-03-15 | 0 |  | 33 | 38 | 70 | 2023 | 2023 | R16
162529224013 | 161209224013 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-17 | 2021-03-17 | 2021-03-17 | 2021-05-27 | 2021-11-04 | Overhead | R16 | 2021-05-27 | 1 |  | 52 | 116 | 167 | 2021 | 2021 | R16
162967146396 | 168843146396 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-19 | 2019-03-19 | 2019-03-19 | 2019-05-09 | 2019-05-09 | Overhead | R16 | 2019-05-09 | 1 |  | 38 |  | 38 | 2019 | 2019 | R16
163374203160 | 168647203160 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-09-03 | 2020-09-03 | 2020-09-08 | 2022-10-20 | 2022-10-21 | Overhead | R16 | 2022-10-20 | 1 | 4 | 553 | 2 | 557 | 2020 | 2022 | R16
167230227897 | 169610227897 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-21 | 2021-04-21 | 2021-04-21 | 2021-07-08 | 2021-07-09 | Overhead | R16 | 2021-07-08 | 1 |  | 57 | 2 | 58 | 2021 | 2021 | R16
164387147407 | 160248147407 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-27 | 2019-03-27 | 2019-03-27 | 2019-04-29 | 2019-04-29 | Overhead | R16 | 2019-04-29 | 1 |  | 24 |  | 24 | 2019 | 2019 | R16
162673141333 | 169174141333 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-26 | 2019-01-26 | 2019-01-26 | 2019-02-21 | 2019-04-01 | Underground | R16 | 2019-02-21 | 0 |  | 19 | 28 | 46 | 2019 | 2019 | R16
169420208736 | 161141208736 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-28 | 2020-10-29 | 2020-10-29 | 2020-11-03 | 2021-04-14 | Underground | R16 | 2020-11-03 | 2 |  | 4 | 117 | 121 | 2020 | 2021 | R16
169108198006 | 169201198006 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-07-21 | 2020-07-21 | 2020-07-21 | 2021-02-04 | 2021-02-04 | Overhead | R16 | 2021-02-04 | 1 |  | 143 |  | 143 | 2020 | 2021 | R16
168541143594 | 168535143594 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-01-23 | 2019-01-31 | 2019-02-21 | 2019-09-24 | 2020-04-10 | Underground | R16 | 2019-09-24 | 7 | 16 | 154 | 144 | 318 | 2019 | 2020 | R16
167001236054 | 169726236054 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-12-09 | 2021-01-20 | 2021-06-21 | 2021-10-12 | 2021-10-28 | Underground | R16 | 2021-10-12 | 31 | 109 | 82 | 13 | 232 | 2020 | 2021 | R16
162853203662 | 160199203662 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-11 | 2020-09-11 | 2020-09-11 | 2020-12-31 | 2021-04-16 | Overhead | R16 | 2020-12-31 | 1 |  | 80 | 77 | 156 | 2020 | 2021 | R16
164209211933 | 160433211933 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-25 | 2020-11-25 | 2020-11-25 | 2021-03-18 | 2021-08-11 | Overhead | R16 | 2021-03-18 | 23 |  | 82 | 105 | 208 | 2020 | 2021 | R16
168620311875 | 165424311875 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-09 | 2023-03-09 | 2023-03-09 |  | 2023-06-26 | Overhead | R16 | 2023-03-17 | 1 |  | 7 | 72 | 78 | 2023 | 2023 | R16
166703149954 | 165347149954 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-02-28 | 2019-02-28 | 2019-04-23 | 2019-05-24 | 2019-11-12 | Overhead | R16 | 2019-05-24 | 1 | 39 | 24 | 123 | 184 | 2019 | 2019 | R16
163639151750 | 166939151750 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-03 | 2019-05-08 | 2019-05-08 | 2019-06-04 | 2019-08-12 | Overhead | R16 | 2019-06-04 | 4 |  | 20 | 50 | 72 | 2019 | 2019 | R16
169069309572 | 160978309572 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-16 | 2023-02-16 | 2023-02-16 |  | 2023-07-12 | Overhead | R16 | 2023-06-05 | 1 |  | 78 | 28 | 105 | 2023 | 2023 | R16
163152151703 | 167657151703 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-07 | 2019-05-07 | 2019-05-07 | 2020-02-03 | 2022-05-17 | Overhead | R16 | 2020-02-03 | 1 |  | 195 | 597 | 791 | 2019 | 2022 | R16
169208307950 | 167662307950 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-02-01 | 2023-02-01 | 2023-02-01 |  | 2023-03-31 | Overhead | R16 | 2023-03-07 | 1 |  | 25 | 19 | 43 | 2023 | 2023 | R16
164867206236 | 165307206236 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-20 | 2020-08-20 | 2020-10-06 |  | 2022-10-20 | Underground | R16 |  | 1 | 34 |  |  | 566 | 2020 | 2022 | R16
164885205912 | 165273205912 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-10-01 | 2020-10-01 | 2020-10-01 | 2020-10-05 | 2021-01-14 | Underground | R16 | 2020-10-05 | 1 |  | 3 | 74 | 76 | 2020 | 2021 | R16
169306316063 | 161593316063 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-21 | 2023-04-17 | 2023-04-17 |  | 2023-08-18 | Overhead | R16 | 2023-05-19 | 40 |  | 25 | 66 | 129 | 2023 | 2023 | R16
168757224733 | 163369224733 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-25 | 2021-03-25 | 2023-06-14 | 2023-07-18 | 2022-10-17 | Overhead | R16 | 2023-07-18 | 1 | 580 | 25 |  | 408 | 2021 | 2022 | R16
166714228700 | 167754228700 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2021-04-13 | 2021-04-13 | 2021-04-28 | 2023-09-08 | 2023-11-17 | Underground | R16 | 2023-09-08 | 1 | 12 | 618 | 51 | 679 | 2021 | 2023 | R16
164007217715 | 169209217715 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2020-09-08 | 2020-11-21 | 2021-01-20 | 2021-04-21 | 2021-05-04 | Underground | R16 | 2021-04-21 | 54 | 43 | 66 | 10 | 171 | 2020 | 2021 | R16
168438206089 | 164104206089 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2020-09-28 | 2020-10-02 | 2020-10-02 | 2020-10-08 | 2021-04-15 | Overhead | R16 | 2020-10-08 | 5 |  | 5 | 136 | 144 | 2020 | 2021 | R16
168461148069 | 161083148069 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-01 | 2019-04-01 | 2019-04-03 | 2021-12-29 | 2022-01-12 | Underground | R16 | 2021-12-29 | 1 | 3 | 716 | 11 | 728 | 2019 | 2022 | R16
167130271718 | 163263271718 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-05-05 | 2022-02-24 | 2022-03-08 | 2022-07-20 | 2022-09-13 | Underground | R16 | 2022-07-20 | 212 | 9 | 97 | 40 | 355 | 2021 | 2022 | R16
160257149567 | 164085149567 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-17 | 2019-04-17 | 2019-04-17 | 2019-05-28 | 2019-05-30 | Overhead | R16 | 2019-05-28 | 1 |  | 30 | 3 | 32 | 2019 | 2019 | R16
167626141963 | 167627141963 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-01-16 | 2019-01-16 | 2019-01-31 | 2021-04-21 | 2021-05-20 | Underground | R16 | 2021-04-21 | 1 | 12 | 580 | 22 | 612 | 2019 | 2021 | R16
169625307938 | 167867307938 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-02 | 2023-02-02 | 2023-02-02 |  | 2023-03-31 | Overhead | R16 | 2023-02-02 | 1 |  |  | 42 | 42 | 2023 | 2023 | R16
169630309328 | 160118309328 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-13 | 2023-02-13 | 2023-02-13 |  | 2023-07-28 | Overhead | R16 | 2023-02-23 | 1 |  | 9 | 112 | 120 | 2023 | 2023 | R16
162678255285 | 160405255285 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2021-05-27 | 2021-06-18 | 2021-11-05 | 2022-02-14 | 2022-03-11 | Underground | R16 | 2022-02-14 | 17 | 101 | 72 | 20 | 207 | 2021 | 2022 | R16
162293143106 | 162667143106 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-11 | 2019-02-12 | 2019-02-12 | 2019-03-03 | 2019-03-06 | Overhead | R16 | 2019-03-03 | 2 |  | 14 | 3 | 18 | 2019 | 2019 | R16
161431208991 | 161534208991 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-30 | 2020-10-30 | 2020-10-30 | 2020-10-30 | 2021-07-26 | Underground | R16 | 2020-10-30 | 1 |  |  | 192 | 192 | 2020 | 2021 | R16
164805220065 | 162918220065 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-09 | 2021-02-09 | 2021-02-09 | 2021-05-11 | 2021-11-08 | Overhead | R16 | 2021-05-11 | 1 |  | 66 | 130 | 195 | 2021 | 2021 | R16
164410210806 | 166326210806 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-07 | 2020-10-13 | 2020-11-14 | 2021-07-15 | 2021-07-20 | Underground | R16 | 2021-07-15 | 5 | 24 | 174 | 4 | 205 | 2020 | 2021 | R16
169822317004 | 166141317004 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-01-25 | 2023-01-31 | 2023-04-26 |  | 2023-08-18 | Overhead | R16 |  | 5 | 62 |  |  | 148 | 2023 | 2023 | R16
161029220110 | 167607220110 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-30 | 2020-12-29 |  | 2021-02-10 | 2021-05-05 | Overhead | R16 | 2021-02-10 | 22 |  |  | 61 | 113 | 2020 | 2021 | R16
167698149353 | 163793149353 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-16 | 2019-04-16 | 2019-04-16 | 2019-05-21 | 2019-05-23 | Overhead | R16 | 2019-05-21 | 1 |  | 26 | 3 | 28 | 2019 | 2019 | R16
169974214129 | 168242214129 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-12-03 | 2020-12-07 | 2020-12-15 | 2020-12-16 | 2021-02-26 | Overhead | R16 | 2020-12-16 | 3 | 7 | 2 | 53 | 62 | 2020 | 2021 | R16
167738215585 | 162070215585 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-09-21 | 2020-09-30 | 2020-12-28 | 2021-02-18 | 2021-03-19 | Underground | R16 | 2021-02-18 | 8 | 64 | 39 | 22 | 130 | 2020 | 2021 | R16
166325230598 | 164749230598 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-12 | 2021-05-13 | 2021-05-13 | 2021-05-25 | 2021-08-23 | Overhead | R16 | 2021-05-25 | 2 |  | 9 | 65 | 74 | 2021 | 2021 | R16
164145221881 | 166814221881 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-02-26 | 2021-02-26 | 2021-02-26 | 2021-04-08 | 2021-04-09 | Overhead | R16 | 2021-04-08 | 1 |  | 30 | 2 | 31 | 2021 | 2021 | R16
164148201191 | 165167201191 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-19 | 2020-08-19 | 2020-08-19 | 2020-10-01 | 2020-10-02 | Overhead | R16 | 2020-10-01 | 1 |  | 32 | 2 | 33 | 2020 | 2020 | R16
160062267105 | 160989267105 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH CP R16 WORK RELO TO UG | Residential | 2021-03-16 | 2021-03-23 | 2022-02-01 | 2022-02-15 | 2022-03-08 | Overhead | R16 | 2022-02-15 | 6 | 226 | 11 | 16 | 256 | 2021 | 2022 | R16
169206172809 | 163098172809 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Residential | 2019-02-12 | 2019-03-29 | 2019-11-25 | 2021-11-04 | 2021-11-23 | Underground | R16 | 2021-11-04 | 34 | 172 | 509 | 14 | 726 | 2019 | 2021 | R16
168203211820 | 163618211820 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-09 | 2020-11-24 | 2020-11-24 | 2020-12-31 | 2021-04-16 | Overhead | R16 | 2020-12-31 | 12 |  | 28 | 77 | 115 | 2020 | 2021 | R16
160695309668 | 161172309668 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-02-16 | 2023-02-17 | 2023-02-17 |  | 2023-12-01 | Overhead | R16 | 2023-11-07 | 2 |  | 188 | 19 | 207 | 2023 | 2023 | R16
167434149634 | 162245149634 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-08 | 2019-04-18 | 2019-04-18 | 2019-07-02 | 2019-07-23 | Overhead | R16 | 2019-07-02 | 9 |  | 54 | 16 | 77 | 2019 | 2019 | R16
168603232711 | 165547232711 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-14 | 2021-05-14 | 2021-05-28 | 2021-11-04 | 2021-11-05 | Underground | R16 | 2021-11-04 | 1 | 11 | 115 | 2 | 126 | 2021 | 2021 | R16
163443151693 | 161822151693 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-04-05 | 2019-04-05 | 2019-05-08 | 2020-05-01 | 2021-03-05 | Underground | R16 | 2020-05-01 | 1 | 24 | 258 | 221 | 501 | 2019 | 2021 | R16
164420197603 | 168591197603 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-16 | 2020-07-16 | 2020-07-16 | 2020-08-27 | 2020-11-02 | Overhead | R16 | 2020-08-27 | 1 |  | 31 | 48 | 78 | 2020 | 2020 | R16
161522141487 | 169341141487 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-28 | 2019-01-28 | 2019-01-28 | 2019-02-20 | 2019-02-25 | Overhead | R16 | 2019-02-20 | 1 |  | 18 | 4 | 21 | 2019 | 2019 | R16
161293314794 | 163293314794 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-28 | 2023-04-04 | 2023-04-04 |  | 2023-06-05 | Overhead | R16 | 2023-05-05 | 26 |  | 24 | 22 | 70 | 2023 | 2023 | R16
162371213398 | 167525213398 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-30 | 2020-12-11 | 2020-12-11 | 2021-02-01 | 2021-11-08 | Overhead | R16 | 2021-02-01 | 10 |  | 37 | 201 | 246 | 2020 | 2021 | R16
163433201126 | 164845201126 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-19 | 2020-08-19 | 2020-08-19 | 2021-01-11 | 2021-01-12 | Overhead | R16 | 2021-01-11 | 1 |  | 104 | 2 | 105 | 2020 | 2021 | R16
163723222404 | 168070222404 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-03 | 2021-03-03 | 2021-03-03 | 2021-03-04 | 2021-11-13 | Overhead | R16 | 2021-03-04 | 1 |  | 2 | 182 | 183 | 2021 | 2021 | R16
160379218453 | 167809218453 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-01-19 | 2021-01-21 | 2021-01-26 | 2021-02-26 | 2021-06-03 | Overhead | R16 | 2021-02-26 | 3 | 4 | 24 | 70 | 98 | 2021 | 2021 | R16
162138201073 | 162343201073 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-06 | 2020-08-06 | 2020-08-19 | 2020-10-08 | 2020-10-16 | Overhead | R16 | 2020-10-08 | 1 | 10 | 37 | 7 | 52 | 2020 | 2020 | R16
160617297484 | 165378297484 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-04-06 | 2022-10-18 | 2022-10-18 | 2023-05-19 | 2023-06-12 | Overhead | R16 | 2023-05-19 | 401 |  | 154 | 17 | 570 | 2021 | 2023 | R16
161426152973 | 164859152973 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-24 | 2019-05-20 | 2019-05-20 | 2019-05-30 | 2023-06-08 | Overhead | R16 | 2019-05-30 | 19 |  | 9 | 1051 | 1077 | 2019 | 2023 | R16
167479228896 | 168577228896 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-07 | 2021-04-29 | 2021-04-30 | 2021-06-17 | 2021-11-03 | Overhead | R16 | 2021-06-17 | 39 | 2 | 35 | 100 | 173 | 2021 | 2021 | R16
162263313353 | 168647313353 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-23 | 2023-03-23 | 2023-03-23 |  | 2023-10-26 | Overhead | R16 | 2023-09-12 | 1 |  | 124 | 33 | 156 | 2023 | 2023 | R16
162400215992 | 163506215992 | SDG&E | R16 REWIRE FOR UPGRADE UD | Commercial | 2020-11-07 | 2020-12-28 | 2020-12-31 | 2021-11-11 | 2022-01-21 | Underground | R16 | 2021-11-11 | 36 | 4 | 226 | 52 | 315 | 2020 | 2022 | R16
163811220442 | 163875220442 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-12 | 2021-02-12 | 2021-02-12 | 2021-02-12 | 2023-06-07 | Overhead | R16 | 2021-02-12 | 1 |  |  | 604 | 604 | 2021 | 2023 | R16
164228274702 | 167508274702 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2020-10-13 | 2020-10-13 | 2022-04-04 | 2023-01-05 | 2023-01-05 | Underground | R16 | 2023-01-05 | 1 | 385 | 199 |  | 583 | 2020 | 2023 | R16
162623210975 | 163956210975 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-10 | 2020-11-10 | 2020-11-17 | 2021-01-11 | 2021-04-21 | Overhead | R16 | 2021-01-11 | 1 | 6 | 40 | 73 | 117 | 2020 | 2021 | R16
166972146961 | 160322146961 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-01-30 | 2019-02-12 | 2019-03-22 | 2019-09-13 | 2020-04-11 | Underground | R16 | 2019-09-13 | 10 | 29 | 126 | 151 | 313 | 2019 | 2020 | R16
163198249019 | 164114249019 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-10 | 2021-05-10 | 2021-09-23 | 2021-10-11 | 2021-10-12 | Overhead | R16 | 2021-10-11 | 1 | 99 | 13 | 2 | 112 | 2021 | 2021 | R16
166940219131 | 163336219131 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2020-11-06 | 2020-11-24 | 2021-02-01 | 2021-02-26 | 2021-04-01 | Underground | R16 | 2021-02-26 | 13 | 50 | 20 | 25 | 105 | 2020 | 2021 | R16
164534203083 | 167021203083 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-27 | 2020-08-27 | 2020-09-08 | 2020-10-02 | 2021-01-08 | Underground | R16 | 2020-10-02 | 1 | 9 | 19 | 71 | 97 | 2020 | 2021 | R16
163308224011 | 161616224011 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-02 | 2021-02-02 | 2021-03-17 | 2021-04-23 | 2021-11-08 | Underground | R16 | 2021-04-23 | 1 | 32 | 28 | 142 | 200 | 2021 | 2021 | R16
165962216780 | 165880216780 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-08 | 2021-01-08 | 2021-01-08 | 2021-01-29 | 2021-08-11 | Overhead | R16 | 2021-01-29 | 1 |  | 16 | 139 | 154 | 2021 | 2021 | R16
167437208084 | 168679208084 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-04 | 2020-09-04 | 2020-10-22 | 2021-02-08 | 2021-02-09 | Underground | R16 | 2021-02-08 | 1 | 35 | 78 | 2 | 113 | 2020 | 2021 | R16
162935309484 | 160771309484 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-15 | 2023-02-15 | 2023-02-15 |  | 2023-08-09 | Overhead | R16 | 2023-02-27 | 1 |  | 9 | 118 | 126 | 2023 | 2023 | R16
162995310501 | 162556310501 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-23 | 2023-02-24 | 2023-02-24 |  | 2023-06-22 | Overhead | R16 | 2023-02-27 | 2 |  | 2 | 84 | 86 | 2023 | 2023 | R16
164322209560 | 168281209560 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-10-15 | 2020-10-15 | 2020-11-03 | 2020-12-16 | 2021-04-14 | Underground | R16 | 2020-12-16 | 1 | 14 | 32 | 86 | 130 | 2020 | 2021 | R16
166176197577 | 168649197577 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-16 | 2020-07-16 | 2020-07-17 | 2020-08-21 | 2020-10-06 | Overhead | R16 | 2020-08-21 | 1 | 2 | 26 | 33 | 59 | 2020 | 2020 | R16
169449222388 | 168079222388 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-03-03 | 2021-03-03 | 2021-03-03 | 2022-04-04 | 2022-05-09 | Underground | R16 | 2022-04-04 | 1 |  | 284 | 26 | 309 | 2021 | 2022 | R16
167697148001 | 161251148001 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-02 | 2019-04-02 | 2019-04-02 | 2019-04-21 | 2019-04-24 | Underground | R16 | 2019-04-21 | 1 |  | 14 | 3 | 17 | 2019 | 2019 | R16
162342139033 | 165056139033 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-04 | 2019-01-04 | 2019-01-04 | 2019-03-04 | 2019-03-05 | Overhead | R16 | 2019-03-04 | 1 |  | 42 | 2 | 43 | 2019 | 2019 | R16
165184216388 | 164358216388 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-31 | 2020-12-31 | 2021-01-07 | 2021-11-04 | 2021-12-03 | Overhead | R16 | 2021-11-04 | 1 | 6 | 216 | 22 | 242 | 2020 | 2021 | R16
169257207828 | 169437207828 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-10-21 | 2020-10-21 | 2020-10-21 | 2021-01-16 | 2021-01-19 | Overhead | R16 | 2021-01-16 | 1 |  | 63 | 2 | 65 | 2020 | 2021 | R16
168753224661 | 163091224661 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-24 | 2021-03-24 | 2021-03-24 | 2021-07-26 | 2022-10-18 | Overhead | R16 | 2021-07-26 | 1 |  | 89 | 322 | 410 | 2021 | 2022 | R16
165571220680 | 169139220680 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-25 | 2021-01-25 | 2021-02-16 | 2021-06-10 | 2021-09-28 | Overhead | R16 | 2021-06-10 | 1 | 17 | 83 | 79 | 177 | 2021 | 2021 | R16
163361203409 | 169873203409 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-10 | 2020-09-10 | 2020-09-10 | 2022-12-21 | 2023-06-07 | Overhead | R16 | 2022-12-21 | 1 |  | 595 | 121 | 715 | 2020 | 2023 | R16
161812212967 | 168907212967 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-05 | 2020-12-05 | 2020-12-05 | 2021-02-01 | 2021-02-02 | Overhead | R16 | 2021-02-01 | 0 |  | 41 | 2 | 42 | 2020 | 2021 | R16
167833159530 | 168302159530 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE FOR UPGRADE UD | Commercial | 2019-05-10 | 2019-05-21 | 2019-07-30 | 2019-08-08 | 2020-01-09 | Underground | R16 | 2019-08-08 | 8 | 51 | 8 | 111 | 175 | 2019 | 2020 | R16
169579229643 | 164070229643 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-28 | 2021-04-13 | 2021-05-05 | 2021-08-16 | 2021-10-25 | Underground | R16 | 2021-08-16 | 12 | 17 | 74 | 51 | 151 | 2021 | 2021 | R16
169355147173 | 164580147173 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-02-21 | 2019-02-26 | 2019-03-25 | 2020-01-17 | 2020-11-10 | Underground | R16 | 2020-01-17 | 4 | 20 | 215 | 213 | 449 | 2019 | 2020 | R16
168542232061 | 162333232061 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-03 | 2021-05-23 | 2021-05-23 | 2021-07-14 | 2021-08-13 | Overhead | R16 | 2021-07-14 | 15 |  | 38 | 23 | 75 | 2021 | 2021 | R16
163742311453 | 163013311453 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-27 | 2023-02-27 | 2023-03-03 |  | 2023-05-17 | Underground | R16 | 2023-03-07 | 1 | 5 | 3 | 52 | 58 | 2023 | 2023 | R16
168430145257 | 167086145257 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-07 | 2019-03-08 | 2019-03-08 | 2019-03-25 | 2019-03-28 | Underground | R16 | 2019-03-25 | 2 |  | 12 | 4 | 16 | 2019 | 2019 | R16
163412151103 | 166817151103 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-02 | 2019-05-02 | 2019-05-02 | 2019-06-05 | 2019-06-05 | Overhead | R16 | 2019-06-05 | 1 |  | 25 |  | 25 | 2019 | 2019 | R16
167177224324 | 162345224324 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-05-24 | 2021-05-25 | Overhead | R16 | 2021-05-24 | 1 |  | 46 | 2 | 47 | 2021 | 2021 | R16
163915314897 | 163290314897 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-28 | 2023-02-28 | 2023-04-06 |  | 2023-06-29 | Underground | R16 | 2023-06-23 | 1 | 28 | 57 | 5 | 88 | 2023 | 2023 | R16
162051154881 | 168202154881 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-05-09 | 2019-05-09 | 2019-06-10 | 2020-08-28 | 2021-03-11 | Underground | R16 | 2020-08-28 | 1 | 23 | 320 | 140 | 481 | 2019 | 2021 | R16
164018310615 | 162735310615 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-24 | 2023-02-24 | 2023-02-24 |  | 2023-05-18 | Overhead | R16 | 2023-03-22 | 1 |  | 19 | 42 | 60 | 2023 | 2023 | R16
160118149368 | 161066149368 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-01 | 2019-04-01 | 2019-04-16 | 2019-06-14 | 2019-06-17 | Underground | R16 | 2019-06-14 | 1 | 12 | 44 | 2 | 56 | 2019 | 2019 | R16
168614143622 | 163969143622 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-19 | 2019-02-19 | 2019-02-19 | 2019-04-05 | 2019-04-08 | Overhead | R16 | 2019-04-05 | 1 |  | 34 | 2 | 35 | 2019 | 2019 | R16
162444213001 | 163850213001 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-09 | 2020-11-25 | 2020-12-05 | 2021-03-05 | 2021-04-20 | Underground | R16 | 2021-03-05 | 13 | 8 | 65 | 33 | 117 | 2020 | 2021 | R16
167213217949 | 168701217949 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-21 | 2021-01-21 | 2021-01-21 | 2021-11-18 | 2022-01-11 | Overhead | R16 | 2021-11-18 | 1 |  | 216 | 39 | 254 | 2021 | 2022 | R16
162104231388 | 164694231388 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-11 | 2021-05-11 | 2021-05-18 | 2021-05-28 | 2021-08-13 | Underground | R16 | 2021-05-28 | 1 | 6 | 9 | 56 | 69 | 2021 | 2021 | R16
168319200021 | 162517200021 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-07 | 2020-08-07 | 2020-08-07 | 2020-08-11 | 2020-10-06 | Overhead | R16 | 2020-08-11 | 1 |  | 3 | 41 | 43 | 2020 | 2020 | R16
160834221444 | 161525221444 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-01 | 2021-02-04 | 2021-02-23 | 2021-04-03 | 2021-04-06 | Underground | R16 | 2021-04-03 | 4 | 14 | 29 | 2 | 47 | 2021 | 2021 | R16
168213141081 | 168188141081 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC DEVELOPMENT | Residential | 2019-01-22 | 2019-01-22 | 2019-01-23 | 2020-07-16 | 2019-11-21 | Underground | R16 | 2020-07-16 | 1 | 2 | 387 |  | 218 | 2019 | 2019 | R16
160628225532 | 166821225532 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-11-24 | 2020-11-24 | 2021-04-02 | 2022-03-14 | 2022-04-01 | Underground | R16 | 2022-03-14 | 1 | 94 | 247 | 15 | 354 | 2020 | 2022 | R16
168263198651 | 160297198651 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-07-28 | 2020-07-28 | 2020-07-28 | 2020-08-21 | 2021-07-02 | Overhead | R16 | 2020-08-21 | 1 |  | 19 | 226 | 244 | 2020 | 2021 | R16
162145239636 | 168728239636 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG R16 RESD AND NON RESD UD | Commercial | 2020-10-19 | 2021-06-07 | 2021-07-20 | 2022-09-01 | 2022-09-13 | Underground | R16 | 2022-09-01 | 166 | 32 | 293 | 9 | 497 | 2020 | 2022 | R16
162647264730 | 168674264730 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-04-16 | 2021-04-20 | 2022-01-13 | 2022-09-19 | 2022-10-07 | Overhead | R16 | 2022-09-19 | 3 | 193 | 178 | 15 | 386 | 2021 | 2022 | R16
166877224907 | 161298224907 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-17 | 2021-03-17 | 2021-03-26 | 2021-08-05 | 2021-09-01 | Underground | R16 | 2021-08-05 | 1 | 8 | 95 | 20 | 121 | 2021 | 2021 | R16
161780208941 | 161072208941 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-28 | 2020-10-28 | 2020-10-28 | 2020-10-28 | 2021-11-09 | Overhead | R16 | 2020-10-28 | 1 |  |  | 270 | 270 | 2020 | 2021 | R16
160786215688 | 161938215688 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-12-22 | 2020-12-29 | 2020-12-29 | 2021-06-04 | 2021-09-01 | Underground | R16 | 2021-06-04 | 6 |  | 114 | 64 | 182 | 2020 | 2021 | R16
166004215329 | 162964215329 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-12-22 | 2020-12-22 | 2020-12-22 | 2020-12-23 | 2021-04-29 | Underground | R16 | 2020-12-23 | 1 |  | 2 | 92 | 93 | 2020 | 2021 | R16
165608216134 | 164598216134 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-04 | 2021-01-04 | 2021-01-04 | 2021-01-05 | 2021-05-07 | Overhead | R16 | 2021-01-05 | 1 |  | 2 | 89 | 90 | 2021 | 2021 | R16
167907217574 | 165036217574 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-05 | 2021-01-05 | 2021-01-19 | 2021-02-10 | 2021-08-11 | Underground | R16 | 2021-02-10 | 1 | 11 | 17 | 131 | 157 | 2021 | 2021 | R16
169348230830 | 164634230830 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-11 | 2021-05-15 | 2021-05-15 | 2021-06-30 | 2021-06-30 | Underground | R16 | 2021-06-30 | 4 |  | 33 |  | 37 | 2021 | 2021 | R16
166679152741 | 169368152741 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-16 | 2019-05-16 | 2019-05-16 | 2019-06-10 | 2019-06-13 | Overhead | R16 | 2019-06-10 | 1 |  | 18 | 4 | 21 | 2019 | 2019 | R16
160707144810 | 166009144810 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-04 | 2019-03-04 | 2019-03-04 |  | 2019-03-29 | Underground | R16 |  | 1 |  |  |  | 20 | 2019 | 2019 | R16
163673227159 | 168671227159 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-16 | 2021-04-17 | 2021-04-17 | 2021-06-09 | 2021-08-16 | Overhead | R16 | 2021-06-09 | 1 |  | 38 | 49 | 87 | 2021 | 2021 | R16
164639219669 | 160626219669 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-13 | 2020-12-29 | 2021-02-04 | 2021-03-09 | 2021-08-11 | Overhead | R16 | 2021-03-09 | 12 | 28 | 24 | 112 | 173 | 2020 | 2021 | R16
164122198000 | 169208198000 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-07-21 | 2020-07-21 | 2020-07-21 | 2020-10-22 | 2021-11-10 | Overhead | R16 | 2020-10-22 | 1 |  | 68 | 275 | 342 | 2020 | 2021 | R16
165412309350 | 168012309350 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-02 | 2023-02-14 | 2023-02-14 |  | 2023-10-06 | Overhead | R16 | 2023-10-05 | 9 |  | 168 | 2 | 177 | 2023 | 2023 | R16
163387153899 | 161798153899 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-31 | 2019-05-31 | 2019-05-31 | 2019-11-21 | 2019-11-22 | Overhead | R16 | 2019-11-21 | 1 |  | 125 | 2 | 126 | 2019 | 2019 | R16
167234218670 | 167882218670 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-08-31 | 2020-08-31 | 2021-01-27 | 2022-01-07 | 2022-01-10 | Underground | R16 | 2022-01-07 | 1 | 108 | 248 | 2 | 356 | 2020 | 2022 | R16
165505311166 | 169634311166 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-09 | 2023-02-09 | 2023-03-02 |  | 2023-09-14 | Underground | R16 | 2023-05-24 | 1 | 16 | 60 | 82 | 156 | 2023 | 2023 | R16
165172316398 | 162135316398 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-07 | 2023-04-10 | 2023-04-20 |  | 2023-08-08 | Underground | R16 | 2023-04-24 | 2 | 9 | 3 | 77 | 88 | 2023 | 2023 | R16
165534312545 | 166717312545 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-15 | 2023-03-15 | 2023-03-15 |  | 2023-08-14 | Overhead | R16 | 2023-04-14 | 1 |  | 23 | 87 | 109 | 2023 | 2023 | R16
167822322159 | 160421322159 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-05-17 | 2023-06-09 | 2023-06-15 | 2023-07-28 | 2023-08-08 | Overhead | R16 | 2023-07-28 | 18 | 5 | 32 | 8 | 60 | 2023 | 2023 | R16
165571312901 | 164100312901 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-02 | 2023-03-02 | 2023-03-17 |  | 2023-09-28 | Underground | R16 | 2023-06-12 | 1 | 12 | 62 | 79 | 151 | 2023 | 2023 | R16
164073243705 | 168542243705 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-14 | 2021-08-14 | 2021-08-14 | 2022-01-06 | 2022-01-07 | Overhead | R16 | 2022-01-06 | 0 |  | 104 | 2 | 105 | 2021 | 2022 | R16
165252319489 | 168576319489 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-23 | 2023-05-18 | 2023-05-18 | 2023-07-27 | 2023-08-04 | Overhead | R16 | 2023-07-27 | 41 |  | 51 | 7 | 97 | 2023 | 2023 | R16
165596312843 | 166065312843 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-13 | 2023-03-17 | 2023-03-17 |  | 2023-06-08 | Underground | R16 | 2023-05-25 | 5 |  | 50 | 11 | 64 | 2023 | 2023 | R16
169100317528 | 160834317528 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-15 | 2023-05-01 | 2023-05-01 | 2023-08-23 | 2023-08-23 | Underground | R16 | 2023-08-23 | 54 |  | 83 |  | 136 | 2023 | 2023 | R16
160172318945 | 165826318945 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-25 | 2023-04-25 | 2023-05-12 | 2023-07-20 | 2023-08-23 | Underground | R16 | 2023-07-20 | 1 | 14 | 50 | 25 | 87 | 2023 | 2023 | R16
162643311345 | 164173311345 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2023-03-02 | 2023-03-02 | 2023-03-02 |  | 2023-07-28 | Overhead | R16 | 2023-03-28 | 1 |  | 19 | 89 | 107 | 2023 | 2023 | R16
160937243709 | 168680243709 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-14 | 2021-08-14 | 2021-08-14 | 2022-05-02 | 2022-07-25 | Overhead | R16 | 2022-05-02 | 0 |  | 186 | 61 | 246 | 2021 | 2022 | R16
161280325781 | 169309325781 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-05 | 2023-07-20 | 2023-07-20 | 2023-08-10 | 2023-09-21 | Overhead | R16 | 2023-08-10 | 12 |  | 16 | 31 | 57 | 2023 | 2023 | R16
165870314965 | 161850314965 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2023-04-06 | 2023-04-06 | 2023-04-06 |  | 2023-08-18 | Overhead | R16 | 2023-05-12 | 1 |  | 27 | 71 | 97 | 2023 | 2023 | R16
166296325815 | 160975325815 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-13 | 2023-07-21 | 2023-07-21 | 2023-07-25 | 2023-08-18 | Overhead | R16 | 2023-07-25 | 7 |  | 3 | 19 | 27 | 2023 | 2023 | R16
160222319081 | 167511319081 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-20 | 2023-03-20 | 2023-05-15 |  | 2023-06-14 | Underground | R16 | 2023-05-16 | 1 | 41 | 2 | 22 | 63 | 2023 | 2023 | R16
160496323017 | 163804323017 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-06 | 2023-06-06 | 2023-06-22 | 2023-09-07 | 2023-09-13 | Underground | R16 | 2023-09-07 | 1 | 13 | 56 | 5 | 72 | 2023 | 2023 | R16
166862324668 | 168791324668 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-30 | 2023-07-06 | 2023-07-11 | 2023-09-20 | 2023-09-29 | Overhead | R16 | 2023-09-20 | 5 | 4 | 52 | 8 | 66 | 2023 | 2023 | R16
162954284426 | 160845284426 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OD | Commercial | 2021-08-24 | 2021-08-24 | 2022-07-01 |  | 2023-01-27 | Overhead | R16 |  | 1 | 224 |  |  | 374 | 2021 | 2023 | R16
162825310775 | 160219310775 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-13 | 2023-02-13 | 2023-02-28 | 2023-05-18 | 2023-06-12 | Underground | R16 | 2023-05-18 | 1 | 12 | 58 | 18 | 86 | 2023 | 2023 | R16
166292312499 | 163735312499 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-01 | 2023-03-01 | 2023-03-15 |  | 2023-05-18 | Underground | R16 | 2023-03-20 | 1 | 11 | 4 | 44 | 57 | 2023 | 2023 | R16
167829306548 | 163429306548 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-12 | 2023-01-12 | 2023-01-30 | 2023-04-11 | 2023-05-18 | Underground | R16 | 2023-04-11 | 1 | 13 | 52 | 28 | 91 | 2023 | 2023 | R16
168966246127 | 162674246127 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-12-28 | 2021-12-29 | Underground | R16 | 2021-12-28 | 1 |  | 85 | 2 | 86 | 2021 | 2021 | R16
167992320312 | 161847320312 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-25 | 2023-05-25 | 2023-05-25 | 2023-07-05 | 2023-08-08 | Overhead | R16 | 2023-07-05 | 1 |  | 30 | 25 | 54 | 2023 | 2023 | R16
169055311440 | 160517311440 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-14 | 2023-02-14 | 2023-03-03 | 2023-09-08 | 2023-09-25 | Underground | R16 | 2023-09-08 | 1 | 14 | 136 | 12 | 160 | 2023 | 2023 | R16
166516318019 | 167032318019 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-17 | 2023-05-05 | 2023-05-05 | 2023-10-11 | 2023-10-13 | Underground | R16 | 2023-10-11 | 36 |  | 114 | 3 | 151 | 2023 | 2023 | R16
169790318403 | 163239318403 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-12 | 2023-05-08 | 2023-05-08 |  | 2023-06-26 | Underground | R16 | 2023-06-16 | 19 |  | 30 | 7 | 54 | 2023 | 2023 | R16
161574320996 | 163108320996 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-02 | 2023-06-02 | 2023-06-02 | 2023-06-28 | 2023-10-10 | Overhead | R16 | 2023-06-28 | 1 |  | 19 | 75 | 93 | 2023 | 2023 | R16
166522316795 | 164410316795 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-03 | 2023-03-03 | 2023-04-25 |  | 2023-07-10 | Underground | R16 | 2023-07-06 | 1 | 38 | 53 | 3 | 92 | 2023 | 2023 | R16
169177311577 | 164596311577 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-06 | 2023-03-06 | 2023-03-07 |  | 2023-07-31 | Overhead | R16 | 2023-03-30 | 1 | 2 | 18 | 88 | 106 | 2023 | 2023 | R16
161713327032 | 169291327032 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-05 | 2023-07-06 | 2023-08-01 | 2023-12-05 | 2023-12-15 | Underground | R16 | 2023-12-05 | 2 | 19 | 91 | 9 | 118 | 2023 | 2023 | R16
169662324979 | 165044324979 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-13 | 2023-06-13 | 2023-07-13 | 2023-07-26 | 2023-08-29 | Underground | R16 | 2023-07-26 | 1 | 23 | 10 | 25 | 56 | 2023 | 2023 | R16
166544313804 | 166075313804 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-13 | 2023-03-13 | 2023-03-27 |  | 2023-06-05 | Underground | R16 | 2023-04-05 | 1 | 11 | 8 | 44 | 61 | 2023 | 2023 | R16
160729320606 | 168200320606 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-05 | 2023-05-30 | 2023-05-30 | 2023-06-02 | 2023-06-05 | Overhead | R16 | 2023-06-02 | 18 |  | 4 | 2 | 22 | 2023 | 2023 | R16
160244306493 | 164185306493 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-17 | 2023-01-19 | 2023-01-30 | 2023-01-19 | 2023-06-16 | Overhead | R16 | 2023-01-19 | 3 | 8 |  | 107 | 109 | 2023 | 2023 | R16
167475314169 | 164701314169 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-06 |  | 2023-03-06 | 2023-07-27 | 2023-08-25 | Underground | R16 | 2023-07-27 |  |  | 104 | 22 | 125 | 2023 | 2023 | R16
167045306412 | 164143306412 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-17 | 2023-01-19 | 2023-01-30 | 2023-04-03 | 2023-04-06 | Overhead | R16 | 2023-04-03 | 3 | 8 | 46 | 4 | 58 | 2023 | 2023 | R16
160711319224 | 162412319224 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-23 | 2023-02-23 | 2023-05-15 | 2023-07-31 | 2023-08-14 | Overhead | R16 | 2023-07-31 | 1 | 58 | 56 | 11 | 123 | 2023 | 2023 | R16
162007319639 | 162855319639 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-11 | 2023-05-19 | 2023-05-19 | 2023-08-16 | 2023-10-23 | Overhead | R16 | 2023-08-16 | 29 |  | 64 | 49 | 140 | 2023 | 2023 | R16
168621311123 | 160515311123 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-14 | 2023-02-14 | 2023-03-01 | 2023-08-18 | 2023-09-12 | Underground | R16 | 2023-08-18 | 1 | 12 | 123 | 18 | 151 | 2023 | 2023 | R16
164103312582 | 166258312582 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-14 | 2023-03-14 | 2023-03-14 | 2023-04-14 | 2023-04-17 | Overhead | R16 | 2023-04-14 | 1 |  | 24 | 2 | 25 | 2023 | 2023 | R16
161883325448 | 160754325448 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-13 | 2023-07-18 | 2023-07-18 | 2023-08-01 | 2023-09-20 | Underground | R16 | 2023-08-01 | 4 |  | 11 | 37 | 50 | 2023 | 2023 | R16
167600245086 | 160972245086 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-24 | 2021-08-24 | 2021-08-24 | 2021-08-31 | 2021-11-09 | Overhead | R16 | 2021-08-31 | 1 |  | 6 | 51 | 56 | 2021 | 2021 | R16
166988313113 | 165095313113 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-08 | 2023-03-20 | 2023-03-20 |  | 2023-08-09 | Overhead | R16 | 2023-03-28 | 9 |  | 7 | 97 | 111 | 2023 | 2023 | R16
163817313252 | 165157313252 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-08 | 2023-03-08 | 2023-03-21 | 2023-08-16 | 2023-08-24 | Underground | R16 | 2023-08-16 | 1 | 10 | 107 | 7 | 122 | 2023 | 2023 | R16
163582308939 | 169616308939 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-09 | 2023-02-10 | 2023-02-10 | 2023-06-07 | 2023-06-08 | Overhead | R16 | 2023-06-07 | 2 |  | 84 | 2 | 86 | 2023 | 2023 | R16
160626245642 | 164315245642 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-28 | 2021-08-27 | 2021-08-27 | 2021-11-04 | 2021-12-02 | Overhead | R16 | 2021-11-04 | 23 |  | 50 | 21 | 92 | 2021 | 2021 | R16
167580308227 | 167637308227 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-01 | 2023-02-02 | 2023-02-02 |  | 2023-08-16 | Underground | R16 | 2023-05-04 | 2 |  | 66 | 75 | 141 | 2023 | 2023 | R16
165010310092 | 161591310092 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-20 | 2023-02-22 | 2023-02-22 | 2023-03-02 | 2023-04-18 | Overhead | R16 | 2023-03-02 | 3 |  | 7 | 34 | 42 | 2023 | 2023 | R16
168930321104 | 163199321104 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2023-06-02 | 2023-06-02 | 2023-06-02 |  | 2023-07-03 | Overhead | R16 |  | 1 |  |  |  | 22 | 2023 | 2023 | R16
166793318112 | 168191318112 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-05 | 2023-05-05 | 2023-05-05 | 2023-07-06 | 2023-08-02 | Overhead | R16 | 2023-07-06 | 1 |  | 45 | 20 | 64 | 2023 | 2023 | R16
161130323387 | 165441323387 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-21 | 2023-04-21 | 2023-06-26 | 2023-11-27 | 2023-12-19 | Underground | R16 | 2023-11-27 | 1 | 47 | 111 | 17 | 173 | 2023 | 2023 | R16
160438324752 | 166361324752 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-20 | 2023-06-20 | 2023-07-11 | 2023-08-08 | 2023-08-10 | Overhead | R16 | 2023-08-08 | 1 | 16 | 21 | 3 | 38 | 2023 | 2023 | R16
166105321586 | 169403321586 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-12-22 | 2023-01-31 | 2023-06-08 | 2023-06-13 | 2023-06-19 | Overhead | R16 | 2023-06-13 | 29 | 93 | 4 | 5 | 128 | 2022 | 2023 | R16
164303326171 | 164262326171 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-08 | 2023-06-08 | 2023-07-24 | 2023-07-26 | 2023-09-11 | Underground | R16 | 2023-07-26 | 1 | 33 | 3 | 34 | 68 | 2023 | 2023 | R16
169952326516 | 164844326516 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-12 | 2023-06-12 | 2023-07-27 | 2023-08-30 | 2023-12-11 | Overhead | R16 | 2023-08-30 | 1 | 34 | 25 | 74 | 131 | 2023 | 2023 | R16
168879316495 | 161312316495 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2023-04-04 | 2023-04-04 | 2023-04-20 | 2023-07-18 | 2023-07-28 | Underground | R16 | 2023-07-18 | 1 | 13 | 64 | 9 | 84 | 2023 | 2023 | R16
169124317148 | 166809317148 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-16 | 2023-03-16 | 2023-04-27 | 2023-05-10 | 2023-06-07 | Overhead | R16 | 2023-05-10 | 1 | 31 | 10 | 21 | 60 | 2023 | 2023 | R16
168923321662 | 164146321662 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-08 | 2023-06-08 | 2023-06-08 |  | 2023-07-15 | Overhead | R16 |  | 1 |  |  |  | 27 | 2023 | 2023 | R16
169037312391 | 166141312391 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-13 | 2023-03-13 | 2023-03-13 |  | 2023-08-14 | Overhead | R16 | 2023-03-20 | 1 |  | 6 | 106 | 111 | 2023 | 2023 | R16
167891322895 | 166806322895 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-22 | 2023-06-22 | 2023-06-22 | 2023-07-14 | 2023-07-17 | Overhead | R16 | 2023-07-14 | 1 |  | 17 | 2 | 18 | 2023 | 2023 | R16
164865315714 | 163497315714 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-04-13 | 2023-04-13 | 2023-04-13 | 2023-04-13 | 2023-07-31 | Overhead | R16 | 2023-04-13 | 1 |  |  | 78 | 78 | 2023 | 2023 | R16
163584312694 | 167028312694 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-05-09 | 2023-08-23 | Overhead | R16 | 2023-05-09 | 1 |  | 39 | 77 | 115 | 2023 | 2023 | R16
160274313126 | 163292313126 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-28 | 2023-03-01 | 2023-03-20 | 2023-07-06 | 2023-07-11 | Underground | R16 | 2023-07-06 | 2 | 14 | 79 | 4 | 96 | 2023 | 2023 | R16
160459323287 | 168447323287 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-23 | 2023-03-23 | 2023-06-26 | 2023-08-10 | 2023-08-10 | Underground | R16 | 2023-08-10 | 1 | 68 | 34 |  | 101 | 2023 | 2023 | R16
163324314924 | 164719314924 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-06 | 2023-03-24 | 2023-04-06 | 2023-09-12 | 2023-09-15 | Underground | R16 | 2023-09-12 | 15 | 10 | 114 | 4 | 140 | 2023 | 2023 | R16
162106242382 | 165733242382 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-03 | 2021-08-03 | 2021-08-05 | 2021-12-07 | 2022-01-20 | Underground | R16 | 2021-12-07 | 1 | 3 | 89 | 33 | 123 | 2021 | 2022 | R16
161671320259 | 161749320259 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-26 | 2023-05-26 | 2023-05-26 | 2023-06-09 | 2023-06-28 | Overhead | R16 | 2023-06-09 | 1 |  | 11 | 14 | 24 | 2023 | 2023 | R16
166991245042 | 168808245042 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-16 | 2021-08-16 | 2021-08-24 | 2021-11-17 | 2022-01-07 | Underground | R16 | 2021-11-17 | 1 | 7 | 62 | 38 | 105 | 2021 | 2022 | R16
168365324620 | 164504324620 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-09 | 2023-06-09 | 2023-07-09 | 2023-11-02 | 2023-12-18 | Overhead | R16 | 2023-11-02 | 1 | 21 | 84 | 33 | 137 | 2023 | 2023 | R16
163878246052 | 162544246052 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-31 | 2021-08-31 | 2021-08-31 | 2022-09-06 | 2022-09-30 | Overhead | R16 | 2022-09-06 | 1 |  | 266 | 19 | 284 | 2021 | 2022 | R16
167140315522 | 165143315522 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-07 | 2023-04-11 | 2023-04-11 | 2023-06-05 | 2023-06-14 | Overhead | R16 | 2023-06-05 | 26 |  | 40 | 8 | 72 | 2023 | 2023 | R16
163389314326 | 169163314326 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-27 | 2023-03-27 | 2023-03-31 |  | 2023-05-18 | Overhead | R16 | 2023-04-14 | 1 | 5 | 11 | 25 | 39 | 2023 | 2023 | R16
168221315816 | 165550315816 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-09 | 2023-03-09 | 2023-04-14 |  | 2023-07-26 | Underground | R16 | 2023-06-15 | 1 | 27 | 45 | 30 | 100 | 2023 | 2023 | R16
166073322311 | 164243322311 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-17 | 2023-06-16 | 2023-06-16 | 2023-08-15 | 2023-09-01 | Overhead | R16 | 2023-08-15 | 45 |  | 43 | 14 | 100 | 2023 | 2023 | R16
167729321373 | 166109321373 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-13 | 2023-06-06 | 2023-06-06 | 2023-08-04 | 2023-08-11 | Underground | R16 | 2023-08-04 | 62 |  | 44 | 6 | 110 | 2023 | 2023 | R16
168259311462 | 162276311462 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-23 | 2023-02-23 | 2023-03-04 |  | 2023-07-31 | Underground | R16 | 2023-03-10 | 1 | 7 | 5 | 102 | 113 | 2023 | 2023 | R16
167871320371 | 161944320371 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-26 | 2023-05-26 | 2023-05-26 | 2023-06-13 | 2023-08-24 | Overhead | R16 | 2023-06-13 | 1 |  | 13 | 53 | 65 | 2023 | 2023 | R16
166670306419 | 165020306419 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-19 | 2023-01-19 | 2023-01-30 | 2023-01-19 | 2023-04-27 | Overhead | R16 | 2023-01-19 | 1 | 8 |  | 71 | 71 | 2023 | 2023 | R16
163897244841 | 160650244841 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-23 | 2021-08-23 | 2021-08-23 | 2021-09-21 | 2021-10-28 | Overhead | R16 | 2021-09-21 | 1 |  | 22 | 28 | 49 | 2021 | 2021 | R16
167473306794 | 164617306794 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-18 | 2023-01-23 | 2023-01-30 | 2023-01-23 | 2023-09-20 | Overhead | R16 | 2023-01-23 | 4 | 6 |  | 173 | 176 | 2023 | 2023 | R16
169459316909 | 164363316909 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-18 | 2023-04-18 | 2023-04-25 | 2023-07-19 | 2023-08-14 | Underground | R16 | 2023-07-19 | 1 | 6 | 62 | 19 | 85 | 2023 | 2023 | R16
168416305477 | 161800305477 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-05 | 2023-01-06 | 2023-01-30 | 2023-07-28 | 2023-08-01 | Overhead | R16 | 2023-07-28 | 2 | 17 | 130 | 3 | 149 | 2023 | 2023 | R16
168496312604 | 166663312604 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-15 | 2023-03-15 | 2023-03-15 |  | 2023-05-18 | Overhead | R16 | 2023-03-27 | 1 |  | 9 | 39 | 47 | 2023 | 2023 | R16
166960245340 | 160355245340 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-20 |  | 2021-08-25 | 2021-10-07 | 2023-03-31 | Overhead | R16 | 2021-10-07 |  |  | 32 | 387 | 421 | 2021 | 2023 | R16
164447306839 | 167977306839 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-14 | 2022-12-14 | 2023-01-30 | 2023-01-23 | 2023-03-31 | Underground | R16 | 2023-01-23 | 1 | 34 |  | 50 | 78 | 2022 | 2023 | R16
163331305830 | 163515305830 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-13 | 2023-01-13 | 2023-01-25 | 2023-01-13 | 2023-08-14 | Overhead | R16 | 2023-01-13 | 1 | 9 |  | 152 | 152 | 2023 | 2023 | R16
168456249895 | 165189249895 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-13 | 2021-09-14 | 2021-09-29 | 2022-04-07 | 2022-04-08 | Underground | R16 | 2022-04-07 | 2 | 12 | 137 | 2 | 150 | 2021 | 2022 | R16
163147320717 | 161431320717 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-04 | 2023-04-04 | 2023-05-31 | 2023-07-31 | 2023-08-01 | Underground | R16 | 2023-07-31 | 1 | 42 | 44 | 2 | 86 | 2023 | 2023 | R16
168921313504 | 166079313504 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-13 | 2023-03-22 | 2023-03-23 |  | 2023-08-09 | Overhead | R16 | 2023-03-27 | 8 | 2 | 3 | 98 | 108 | 2023 | 2023 | R16
166860322171 | 165420322171 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-14 | 2023-06-14 | 2023-06-14 | 2023-07-17 | 2023-07-13 | Overhead | R16 | 2023-07-17 | 1 |  | 24 |  | 22 | 2023 | 2023 | R16
163952311505 | 161554311505 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-21 | 2023-02-21 | 2023-03-06 | 2023-05-09 | 2023-05-10 | Underground | R16 | 2023-05-09 | 1 | 10 | 47 | 2 | 57 | 2023 | 2023 | R16
169016310421 | 167009310421 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-30 | 2023-01-31 | 2023-02-23 | 2023-03-15 | 2023-06-12 | Overhead | R16 | 2023-03-15 | 2 | 18 | 15 | 64 | 96 | 2023 | 2023 | R16
165571306704 | 163450306704 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-12 | 2023-01-12 | 2023-01-30 | 2023-01-20 | 2023-05-02 | Underground | R16 | 2023-01-20 | 1 | 13 |  | 73 | 79 | 2023 | 2023 | R16
163614242141 | 165743242141 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-03 | 2021-08-03 | 2021-08-04 | 2021-10-05 | 2021-11-10 | Overhead | R16 | 2021-10-05 | 1 | 2 | 45 | 27 | 72 | 2021 | 2021 | R16
162427306375 | 164184306375 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-17 | 2023-01-18 | 2023-01-30 | 2023-05-17 | 2023-08-14 | Overhead | R16 | 2023-05-17 | 2 | 9 | 78 | 64 | 150 | 2023 | 2023 | R16
162577323329 | 167458323329 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-06-26 | 2023-06-26 | 2023-06-26 | 2023-07-26 | 2023-07-26 | Overhead | R16 | 2023-07-26 | 1 |  | 23 |  | 23 | 2023 | 2023 | R16
169354334111 | 161149334111 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-04 | 2023-04-04 | 2023-09-29 | 2023-12-07 | 2023-12-12 | Underground | R16 | 2023-12-07 | 1 | 129 | 50 | 4 | 181 | 2023 | 2023 | R16
164502325285 | 166124325285 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-19 | 2023-06-19 | 2023-07-17 | 2023-09-19 | 2023-09-20 | Underground | R16 | 2023-09-19 | 1 | 21 | 47 | 2 | 68 | 2023 | 2023 | R16
166576245650 | 169954245650 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-08-19 | 2021-08-27 | 2021-08-27 | 2022-07-29 | 2022-09-20 | Overhead | R16 | 2022-07-29 | 7 |  | 241 | 38 | 284 | 2021 | 2022 | R16
165345241743 | 164649241743 | AGRICULTURAL | OH R16 RES NON RES OS | Residential | 2021-07-29 | 2021-07-29 | 2021-08-02 | 2021-09-20 | 2021-10-06 | Overhead | R16 | 2021-09-20 | 1 | 3 | 36 | 13 | 50 | 2021 | 2021 | R16
166071326178 | 167407326178 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-02 | 2023-05-02 | 2023-07-25 | 2023-09-19 | 2023-10-23 | Underground | R16 | 2023-09-19 | 1 | 61 | 41 | 25 | 125 | 2023 | 2023 | R16
162002309112 | 169891309112 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2023-02-10 | 2023-02-10 | 2023-02-10 | 2023-05-24 | 2023-06-12 | Overhead | R16 | 2023-05-24 | 1 |  | 74 | 14 | 87 | 2023 | 2023 | R16
163797327739 | 169950327739 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-05-15 | 2023-08-01 | 2023-08-09 |  | 2023-10-16 | Underground | R16 | 2023-10-02 | 57 | 7 | 39 | 11 | 111 | 2023 | 2023 | R16
163111310857 | 161674310857 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-21 | 2023-02-28 | 2023-02-28 | 2023-08-28 | 2023-09-12 | Overhead | R16 | 2023-08-28 | 6 |  | 130 | 12 | 146 | 2023 | 2023 | R16
163982311830 | 165336311830 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-08 | 2023-03-08 | 2023-03-08 |  | 2023-05-17 | Overhead | R16 | 2023-03-13 | 1 |  | 4 | 48 | 51 | 2023 | 2023 | R16
169988325594 | 168338325594 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-29 | 2023-06-29 | 2023-07-19 | 2023-10-05 | 2023-12-19 | Overhead | R16 | 2023-10-05 | 1 | 15 | 57 | 54 | 124 | 2023 | 2023 | R16
169404323514 | 167895323514 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-28 | 2023-06-28 | 2023-06-28 | 2023-07-18 | 2023-07-18 | Overhead | R16 | 2023-07-18 | 1 |  | 15 |  | 15 | 2023 | 2023 | R16
168900247798 | 164995247798 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-13 | 2021-09-14 | 2021-09-14 | 2022-03-29 | 2022-03-30 | Underground | R16 | 2022-03-29 | 2 |  | 141 | 2 | 143 | 2021 | 2022 | R16
167450325461 | 160543325461 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-12 | 2023-07-18 | 2023-07-18 | 2023-07-20 | 2023-08-23 | Overhead | R16 | 2023-07-20 | 5 |  | 3 | 25 | 31 | 2023 | 2023 | R16
166286247953 | 163710247953 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-07 | 2021-09-07 | 2021-09-15 | 2022-02-18 | 2022-02-19 | Overhead | R16 | 2022-02-18 | 1 | 7 | 113 | 1 | 119 | 2021 | 2022 | R16
169814318326 | 163300318326 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-12 | 2023-05-08 | 2023-05-08 | 2023-09-19 | 2023-09-25 | Underground | R16 | 2023-09-19 | 19 |  | 97 | 5 | 119 | 2023 | 2023 | R16
160534315796 | 163896315796 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-15 | 2023-04-15 | 2023-04-15 |  | 2023-08-09 | Overhead | R16 | 2023-05-03 | 0 |  | 13 | 71 | 83 | 2023 | 2023 | R16
160300241321 | 164601241321 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-09-29 | 2021-11-09 | Overhead | R16 | 2021-09-29 | 1 |  | 45 | 30 | 74 | 2021 | 2021 | R16
162460314320 | 167632314320 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-20 | 2023-03-20 | 2023-03-30 |  | 2023-12-21 | Overhead | R16 | 2023-12-04 | 1 | 9 | 178 | 14 | 199 | 2023 | 2023 | R16
165467316584 | 160753316584 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-31 | 2023-04-21 | 2023-04-21 | 2023-07-21 | 2023-08-23 | Overhead | R16 | 2023-07-21 | 16 |  | 66 | 24 | 104 | 2023 | 2023 | R16
163211311268 | 164018311268 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-02 | 2023-03-02 | 2023-03-02 | 2023-08-14 | 2023-12-11 | Overhead | R16 | 2023-08-14 | 1 |  | 118 | 86 | 203 | 2023 | 2023 | R16
164933325756 | 169820325756 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-07 | 2023-07-21 | 2023-07-21 | 2023-09-12 | 2023-10-02 | Overhead | R16 | 2023-09-12 | 11 |  | 38 | 15 | 62 | 2023 | 2023 | R16
166465316940 | 168570316940 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-23 | 2023-03-23 | 2023-04-25 | 2023-08-30 | 2023-09-20 | Underground | R16 | 2023-08-30 | 1 | 24 | 92 | 16 | 130 | 2023 | 2023 | R16
160187310405 | 168301310405 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-03 | 2023-02-08 | 2023-02-23 | 2023-10-03 | 2023-11-02 | Underground | R16 | 2023-10-03 | 4 | 12 | 159 | 23 | 195 | 2023 | 2023 | R16
164341320758 | 160577320758 | CUSTOMER UPGRADE IN SERVICE | UG SVC CONVERSION | Residential | 2023-05-18 | 2023-05-18 | 2023-06-01 | 2023-07-21 | 2023-10-13 | Underground | R16 | 2023-07-21 | 1 | 11 | 37 | 61 | 107 | 2023 | 2023 | R16
160431319136 | 167629319136 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-20 | 2023-05-15 | 2023-05-15 | 2023-08-09 | 2023-09-15 | Overhead | R16 | 2023-08-09 | 41 |  | 63 | 28 | 130 | 2023 | 2023 | R16
163131314273 | 160744314273 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-03-31 | 2023-03-31 | 2023-03-31 | 2023-05-04 | 2023-05-05 | Overhead | R16 | 2023-05-04 | 1 |  | 25 | 2 | 26 | 2023 | 2023 | R16
161123324869 | 166463324869 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-20 | 2023-06-20 | 2023-07-13 | 2023-09-13 | 2023-11-03 | Underground | R16 | 2023-09-13 | 1 | 18 | 45 | 38 | 99 | 2023 | 2023 | R16
169821307803 | 167090307803 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-30 | 2023-01-31 | 2023-01-31 | 2023-04-03 | 2023-06-12 | Overhead | R16 | 2023-04-03 | 2 |  | 45 | 51 | 96 | 2023 | 2023 | R16
168814319338 | 164771319338 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-19 | 2023-04-19 | 2023-05-18 | 2023-07-18 | 2023-07-18 | Underground | R16 | 2023-07-18 | 1 | 22 | 44 |  | 65 | 2023 | 2023 | R16
160127320355 | 163445320355 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-13 | 2023-04-13 | 2023-05-26 | 2023-07-25 | 2023-11-01 | Overhead | R16 | 2023-07-25 | 1 | 32 | 43 | 72 | 145 | 2023 | 2023 | R16
165508259953 | 169320259953 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2021-08-17 | 2021-08-19 | 2021-12-06 | 2022-09-21 | 2022-10-03 | Underground | R16 | 2022-09-21 | 3 | 78 | 208 | 9 | 295 | 2021 | 2022 | R16
160250322009 | 161306322009 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2023-05-23 | 2023-05-23 | 2023-06-12 | 2023-10-12 | 2023-10-20 | Underground | R16 | 2023-10-12 | 1 | 15 | 89 | 7 | 109 | 2023 | 2023 | R16
168002326132 | 169635326132 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-07 | 2023-07-24 | 2023-07-24 | 2023-07-27 | 2023-08-29 | Overhead | R16 | 2023-07-27 | 12 |  | 4 | 24 | 38 | 2023 | 2023 | R16
168524307662 | 167013307662 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-30 | 2023-01-30 | 2023-01-30 | 2023-03-14 | 2023-03-28 | Overhead | R16 | 2023-03-14 | 1 |  | 32 | 11 | 42 | 2023 | 2023 | R16
169258316939 | 162228316939 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-07 | 2023-04-10 | 2023-04-27 | 2023-07-17 | 2023-09-19 | Underground | R16 | 2023-07-17 | 2 | 14 | 58 | 47 | 118 | 2023 | 2023 | R16
161784242700 | 166841242700 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-08 | 2021-08-08 | 2021-08-08 | 2021-11-10 | 2021-12-16 | Underground | R16 | 2021-11-10 | 0 |  | 68 | 27 | 94 | 2021 | 2021 | R16
168253308146 | 161040308146 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-04 | 2023-02-02 | 2023-02-02 | 2023-02-13 | 2023-02-21 | Overhead | R16 | 2023-02-13 | 22 |  | 8 | 7 | 35 | 2023 | 2023 | R16
167044244491 | 169985244491 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-19 | 2021-08-20 | 2021-08-20 | 2022-09-29 | 2023-03-30 | Overhead | R16 | 2022-09-29 | 2 |  | 290 | 131 | 421 | 2021 | 2023 | R16
167708319622 | 167409319622 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-02 | 2023-05-02 | 2023-05-18 | 2023-07-21 | 2023-08-07 | Overhead | R16 | 2023-07-21 | 1 | 13 | 47 | 12 | 70 | 2023 | 2023 | R16
162726242740 | 166611242740 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-08-06 | 2021-08-06 | 2021-08-09 | 2021-08-10 | 2021-12-09 | Underground | R16 | 2021-08-10 | 1 | 2 | 2 | 88 | 90 | 2021 | 2021 | R16
163451315918 | 160090315918 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-29 | 2023-04-14 | 2023-04-14 | 2023-08-01 | 2023-09-11 | Overhead | R16 | 2023-08-01 | 13 |  | 78 | 30 | 119 | 2023 | 2023 | R16
162301315202 | 160629315202 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-31 | 2023-03-31 | 2023-04-07 |  | 2023-08-14 | Overhead | R16 | 2023-04-26 | 1 | 6 | 14 | 79 | 97 | 2023 | 2023 | R16
167825251175 | 168843251175 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-16 | 2021-10-08 | 2021-10-08 | 2021-12-13 | 2022-03-10 | Overhead | R16 | 2021-12-13 | 40 |  | 47 | 64 | 149 | 2021 | 2022 | R16
167196244610 | 160411244610 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-10-07 | 2022-02-09 | Overhead | R16 | 2021-10-07 | 1 |  | 35 | 90 | 124 | 2021 | 2022 | R16
169014321208 | 165618321208 | RESIDENTIAL - SINGLE FAMILY ATTACHED | OH R16 RES NON RES OS | Residential | 2023-04-24 | 2023-06-05 | 2023-06-05 | 2023-07-26 | 2023-08-16 | Overhead | R16 | 2023-07-26 | 31 |  | 38 | 16 | 83 | 2023 | 2023 | R16
162775316219 | 168911316219 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-24 | 2023-03-24 | 2023-04-19 |  | 2023-08-09 | Overhead | R16 | 2023-04-20 | 1 | 19 | 2 | 80 | 99 | 2023 | 2023 | R16
167467245152 | 161361245152 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2022-08-15 | 2022-10-21 | Overhead | R16 | 2022-08-15 | 1 |  | 254 | 50 | 303 | 2021 | 2022 | R16
161313308858 | 168802308858 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-02-07 | 2023-02-09 | 2023-02-09 | 2023-04-03 | 2023-04-06 | Overhead | R16 | 2023-04-03 | 3 |  | 38 | 4 | 43 | 2023 | 2023 | R16
163822326153 | 165167326153 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2023-04-21 | 2023-04-21 | 2023-07-25 | 2023-11-23 | 2023-11-27 | Underground | R16 | 2023-11-23 | 1 | 68 | 88 | 3 | 157 | 2023 | 2023 | R16
161264247678 | 163637247678 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-07 | 2021-09-14 | 2021-09-14 | 2022-04-07 | 2022-05-03 | Overhead | R16 | 2022-04-07 | 6 |  | 148 | 19 | 171 | 2021 | 2022 | R16
162030316837 | 162842316837 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-11 | 2023-04-11 | 2023-04-24 |  | 2023-07-13 | Underground | R16 | 2023-07-13 | 1 | 10 | 59 |  | 68 | 2023 | 2023 | R16
167150306025 | 160256306025 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-30 | 2023-01-17 | 2023-01-25 | 2023-04-10 | 2023-04-12 | Underground | R16 | 2023-04-10 | 13 | 7 | 54 | 3 | 74 | 2022 | 2023 | R16
167879321370 | 163570321370 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-05 | 2023-06-05 | 2023-06-06 | 2023-07-28 | 2023-08-01 | Underground | R16 | 2023-07-28 | 1 | 2 | 39 | 3 | 42 | 2023 | 2023 | R16
162134316838 | 164312316838 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-18 | 2023-04-18 | 2023-04-24 |  | 2023-08-30 | Overhead | R16 | 2023-04-26 | 1 | 5 | 3 | 91 | 97 | 2023 | 2023 | R16
169352241971 | 165441241971 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-02 | 2021-08-04 | 2021-08-04 | 2021-11-19 | 2021-11-29 | Overhead | R16 | 2021-11-19 | 3 |  | 78 | 7 | 86 | 2021 | 2021 | R16
162231317636 | 164925317636 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2023-03-06 | 2023-03-06 | 2023-05-01 | 2023-07-18 | 2023-08-01 | Underground | R16 | 2023-07-18 | 1 | 41 | 57 | 11 | 107 | 2023 | 2023 | R16
163679304409 | 160382304409 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-30 | 2022-12-30 | 2023-01-30 | 2022-12-30 | 2023-06-19 | Overhead | R16 | 2022-12-30 | 1 | 22 |  | 122 | 122 | 2022 | 2023 | R16
162222308757 | 169091308757 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-08 | 2023-02-08 | 2023-02-08 | 2023-02-14 | 2023-04-08 | Overhead | R16 | 2023-02-14 | 1 |  | 5 | 39 | 43 | 2023 | 2023 | R16
167280312469 | 161110312469 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-16 | 2023-03-14 | 2023-03-14 | 2023-04-16 | 2023-05-03 | Overhead | R16 | 2023-04-16 | 19 |  | 24 | 13 | 55 | 2023 | 2023 | R16
166243317447 | 163914317447 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-02 | 2023-03-02 | 2023-05-01 | 2023-05-25 | 2023-05-30 | Overhead | R16 | 2023-05-25 | 1 | 43 | 19 | 4 | 64 | 2023 | 2023 | R16
165756305473 | 169108305473 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-20 | 2022-12-20 | 2023-01-30 | 2023-01-10 | 2023-04-27 | Underground | R16 | 2023-01-10 | 1 | 30 |  | 78 | 93 | 2022 | 2023 | R16
169182308184 | 167667308184 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-01 | 2023-02-01 | 2023-02-02 | 2023-05-16 | 2023-05-17 | Overhead | R16 | 2023-05-16 | 1 | 2 | 74 | 2 | 76 | 2023 | 2023 | R16
162658320777 | 162405320777 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-31 | 2023-05-31 | 2023-05-31 |  | 2023-08-04 | Overhead | R16 | 2023-07-26 | 1 |  | 41 | 8 | 48 | 2023 | 2023 | R16
164334269102 | 169848269102 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-18 | 2022-02-15 | 2022-02-15 | 2022-06-01 | 2022-07-25 | Overhead | R16 | 2022-06-01 | 130 |  | 77 | 39 | 244 | 2021 | 2022 | R16
164562247209 | 164318247209 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-09 | 2021-09-09 | 2021-09-09 | 2021-10-05 | 2021-11-05 | Overhead | R16 | 2021-10-05 | 1 |  | 19 | 24 | 42 | 2021 | 2021 | R16
164783328812 | 168882328812 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-10 | 2023-05-10 | 2023-08-18 | 2023-08-18 | 2023-09-12 | Overhead | R16 | 2023-08-18 | 1 | 73 |  | 18 | 90 | 2023 | 2023 | R16
165708323710 | 168483323710 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2023-06-29 | 2023-06-29 | 2023-06-29 | 2023-10-25 | 2023-11-01 | Overhead | R16 | 2023-10-25 | 1 |  | 85 | 6 | 90 | 2023 | 2023 | R16
162849316001 | 168941316001 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-24 | 2023-03-24 | 2023-04-16 |  | 2023-08-08 | Overhead | R16 | 2023-04-28 | 1 | 16 | 10 | 73 | 98 | 2023 | 2023 | R16
160525321361 | 160220321361 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-29 |  | 2023-03-29 | 2023-07-31 | 2023-08-25 | Underground | R16 | 2023-07-31 |  |  | 89 | 20 | 108 | 2023 | 2023 | R16
166742305652 | 163264305652 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-12 | 2023-01-12 | 2023-01-25 | 2023-03-01 | 2023-03-02 | Overhead | R16 | 2023-03-01 | 1 | 10 | 26 | 2 | 36 | 2023 | 2023 | R16
163843309485 | 160773309485 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-15 | 2023-02-15 | 2023-02-15 | 2023-02-16 | 2023-05-17 | Overhead | R16 | 2023-02-16 | 1 |  | 2 | 65 | 66 | 2023 | 2023 | R16
166277323820 | 168524323820 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-29 | 2023-06-29 | 2023-06-29 | 2023-07-14 | 2023-09-18 | Overhead | R16 | 2023-07-14 | 1 |  | 12 | 47 | 58 | 2023 | 2023 | R16
168654242293 | 165636242293 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-03 | 2021-08-05 | 2021-08-05 | 2021-09-30 | 2021-11-18 | Overhead | R16 | 2021-09-30 | 3 |  | 41 | 36 | 78 | 2021 | 2021 | R16
163926319457 | 160617319457 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-31 | 2023-04-13 |  | 2023-05-11 | 2023-07-18 | Overhead | R16 | 2023-05-11 | 10 |  |  | 49 | 78 | 2023 | 2023 | R16
166971318943 | 167972318943 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-02 | 2023-02-02 | 2023-05-12 | 2023-08-24 | 2023-09-05 | Underground | R16 | 2023-08-24 | 1 | 72 | 75 | 9 | 154 | 2023 | 2023 | R16
168709314606 | 160747314606 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-31 | 2023-04-03 | 2023-04-03 | 2023-06-16 | 2023-06-19 | Overhead | R16 | 2023-06-16 | 2 |  | 55 | 2 | 57 | 2023 | 2023 | R16
165943305801 | 163412305801 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-12 | 2023-01-12 | 2023-01-25 | 2023-04-04 | 2023-04-18 | Overhead | R16 | 2023-04-04 | 1 | 10 | 50 | 11 | 69 | 2023 | 2023 | R16
166360306205 | 164175306205 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-17 | 2023-01-17 | 2023-01-17 | 2023-01-19 | 2023-01-20 | Overhead | R16 | 2023-01-19 | 1 |  | 3 | 2 | 4 | 2023 | 2023 | R16
165678323975 | 168510323975 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-29 | 2023-07-05 | 2023-07-05 | 2023-10-31 | 2023-11-17 | Overhead | R16 | 2023-10-31 | 5 |  | 85 | 14 | 102 | 2023 | 2023 | R16
164283319545 | 165155319545 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-21 | 2023-04-21 | 2023-05-18 |  | 2023-09-05 | Underground | R16 | 2023-05-19 | 1 | 20 | 2 | 78 | 98 | 2023 | 2023 | R16
160772241480 | 165003241480 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-30 |  | 2021-07-30 | 2021-11-01 | 2021-12-02 | Overhead | R16 | 2021-11-01 |  |  | 67 | 24 | 90 | 2021 | 2021 | R16
168873255603 | 160663255603 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-23 | 2021-11-08 | 2021-11-08 | 2022-01-20 | 2022-02-28 | Overhead | R16 | 2022-01-20 | 56 |  | 54 | 28 | 136 | 2021 | 2022 | R16
166249323055 | 167131323055 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-23 | 2023-06-23 | 2023-06-23 | 2023-07-14 | 2023-08-28 | Underground | R16 | 2023-07-14 | 1 |  | 16 | 32 | 47 | 2023 | 2023 | R16
160768319676 | 160669319676 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2023-05-19 | 2023-05-19 | 2023-05-19 | 2023-06-26 | 2023-06-28 | Overhead | R16 | 2023-06-26 | 1 |  | 27 | 3 | 29 | 2023 | 2023 | R16
169843311535 | 165025311535 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-07 | 2023-03-07 | 2023-03-07 | 2023-03-19 | 2023-04-12 | Overhead | R16 | 2023-03-19 | 1 |  | 9 | 18 | 27 | 2023 | 2023 | R16
166821320677 | 162345320677 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-30 | 2023-05-30 | 2023-05-30 | 2023-07-14 | 2023-07-17 | Overhead | R16 | 2023-07-14 | 1 |  | 34 | 2 | 35 | 2023 | 2023 | R16
160990314296 | 160622314296 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-31 | 2023-03-31 | 2023-03-31 | 2023-04-18 | 2023-06-12 | Overhead | R16 | 2023-04-18 | 1 |  | 13 | 40 | 52 | 2023 | 2023 | R16
163440307103 | 164711307103 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2023-01-18 | 2023-01-18 | 2023-01-30 | 2023-10-16 | 2023-12-21 | Underground | R16 | 2023-10-16 | 1 | 9 | 186 | 49 | 242 | 2023 | 2023 | R16
163780262073 | 165536262073 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-09-15 | 2021-10-14 | 2021-12-20 | 2022-04-26 | 2022-05-10 | Underground | R16 | 2022-04-26 | 22 | 48 | 92 | 11 | 170 | 2021 | 2022 | R16
163193315403 | 162446315403 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-10 | 2023-04-10 | 2023-04-10 | 2023-07-21 | 2023-08-07 | Overhead | R16 | 2023-07-21 | 1 |  | 75 | 12 | 86 | 2023 | 2023 | R16
163856326177 | 163569326177 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-13 | 2023-04-13 | 2023-07-25 | 2023-12-16 | 2023-12-19 | Underground | R16 | 2023-12-16 | 1 | 74 | 104 | 2 | 179 | 2023 | 2023 | R16
160963318920 | 160794318920 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-15 | 2023-02-15 | 2023-05-11 | 2023-09-08 | 2023-09-13 | Underground | R16 | 2023-09-08 | 1 | 62 | 87 | 4 | 151 | 2023 | 2023 | R16
165291315611 | 160279315611 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-30 | 2023-03-30 | 2023-04-13 |  | 2023-05-18 | Underground | R16 | 2023-04-17 | 1 | 11 | 3 | 24 | 36 | 2023 | 2023 | R16
169560318513 | 168746318513 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-09 | 2023-05-09 | 2023-05-09 | 2023-08-14 | 2023-09-05 | Overhead | R16 | 2023-08-14 | 1 |  | 70 | 17 | 86 | 2023 | 2023 | R16
162823241124 | 164289241124 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-07-28 | 2021-07-28 | 2021-07-28 | 2021-08-04 | 2021-10-25 | Overhead | R16 | 2021-08-04 | 1 |  | 6 | 59 | 64 | 2021 | 2021 | R16
166879310606 | 162135310606 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-02-22 | 2023-02-24 | 2023-02-24 | 2023-06-10 | 2023-06-14 | Overhead | R16 | 2023-06-10 | 3 |  | 76 | 3 | 81 | 2023 | 2023 | R16
168389318549 | 166039318549 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-13 | 2023-05-09 | 2023-05-09 | 2023-08-03 | 2023-08-14 | Underground | R16 | 2023-08-03 | 42 |  | 63 | 8 | 111 | 2023 | 2023 | R16
161259320290 | 161713320290 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-25 | 2023-05-25 | 2023-05-25 | 2023-06-22 | 2023-08-03 | Overhead | R16 | 2023-06-22 | 1 |  | 21 | 31 | 51 | 2023 | 2023 | R16
163607320308 | 169964320308 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Commercial | 2023-05-16 | 2023-05-24 | 2023-05-25 | 2023-10-02 | 2023-10-24 | Underground | R16 | 2023-10-02 | 7 | 2 | 93 | 17 | 116 | 2023 | 2023 | R16
167077323824 | 167085323824 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-23 | 2023-06-23 | 2023-06-30 | 2023-08-21 | 2023-09-28 | Overhead | R16 | 2023-08-21 | 1 | 6 | 37 | 29 | 70 | 2023 | 2023 | R16
165022243995 | 169338243995 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-17 | 2021-08-17 | 2021-08-17 | 2021-09-01 | 2021-11-08 | Overhead | R16 | 2021-09-01 | 1 |  | 12 | 49 | 60 | 2021 | 2021 | R16
167898240985 | 163708240985 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-27 | 2021-07-27 | 2021-07-27 | 2021-09-09 | 2021-10-25 | Overhead | R16 | 2021-09-09 | 1 |  | 33 | 33 | 65 | 2021 | 2021 | R16
166223316091 | 160132316091 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-29 | 2023-03-30 | 2023-04-17 |  | 2023-06-29 | Underground | R16 | 2023-06-14 | 2 | 13 | 43 | 12 | 67 | 2023 | 2023 | R16
167936317172 | 166315317172 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-27 | 2023-04-27 | 2023-04-27 |  | 2023-06-29 | Overhead | R16 | 2023-06-20 | 1 |  | 39 | 8 | 46 | 2023 | 2023 | R16
160425322405 | 165072322405 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-13 | 2023-06-13 | 2023-06-16 | 2023-07-24 | 2023-09-05 | Underground | R16 | 2023-07-24 | 1 | 4 | 27 | 32 | 61 | 2023 | 2023 | R16
166090303793 | 168708303793 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-19 | 2022-12-19 | 2022-12-22 | 2023-01-19 | 2023-01-24 | Overhead | R16 | 2023-01-19 | 1 | 4 | 21 | 4 | 27 | 2022 | 2023 | R16
164695259192 | 169284259192 | NON-RESIDENTIAL - SMALL RETAIL | UG R16 RESD AND NON RESD UD | Commercial | 2021-08-17 | 2021-11-15 | 2021-11-30 | 2023-02-15 | 2023-03-13 | Underground | R16 | 2023-02-15 | 65 | 12 | 317 | 19 | 410 | 2021 | 2023 | R16
167533330170 | 167090330170 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-23 | 2023-06-23 | 2023-08-21 | 2023-08-22 | 2023-09-29 | Underground | R16 | 2023-08-22 | 1 | 42 | 2 | 29 | 71 | 2023 | 2023 | R16
166499319683 | 160618319683 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-19 | 2023-05-19 | 2023-05-19 |  | 2023-06-07 | Overhead | R16 | 2023-05-22 | 1 |  | 2 | 13 | 14 | 2023 | 2023 | R16
167685332635 | 161063332635 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-14 | 2023-09-14 | 2023-09-14 | 2023-10-05 | 2023-11-15 | Overhead | R16 | 2023-10-05 | 45 |  | 16 | 30 | 89 | 2023 | 2023 | R16
164646318060 | 167940318060 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-05-04 | 2023-05-04 | 2023-05-04 | 2023-11-27 | 2023-12-13 | Underground | R16 | 2023-11-27 | 1 |  | 148 | 13 | 160 | 2023 | 2023 | R16
160718334596 | 164837334596 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2023-04-20 | 2023-04-20 | 2023-10-04 | 2023-10-12 | 2023-11-14 | Overhead | R16 | 2023-10-12 | 1 | 120 | 7 | 24 | 149 | 2023 | 2023 | R16
169939324812 | 169425324812 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-06 | 2023-07-13 | 2023-07-13 | 2023-08-22 | 2023-10-18 | Overhead | R16 | 2023-08-22 | 6 |  | 29 | 42 | 75 | 2023 | 2023 | R16
160734313392 | 168442313392 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-23 | 2023-03-23 | 2023-03-23 | 2023-06-15 | 2023-06-29 | Overhead | R16 | 2023-06-15 | 1 |  | 61 | 11 | 71 | 2023 | 2023 | R16
163374319945 | 165563319945 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-09 | 2023-05-22 | 2023-05-22 | 2023-09-27 | 2023-10-06 | Underground | R16 | 2023-09-27 | 53 |  | 93 | 8 | 152 | 2023 | 2023 | R16
167185313187 | 167932313187 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-21 | 2023-03-21 | 2023-03-21 | 2023-03-31 | 2023-06-12 | Overhead | R16 | 2023-03-31 | 1 |  | 9 | 52 | 60 | 2023 | 2023 | R16
169093323477 | 161288323477 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-05 | 2023-06-28 | 2023-06-28 | 2023-07-18 | 2023-08-09 | Overhead | R16 | 2023-07-18 | 125 |  | 15 | 17 | 155 | 2023 | 2023 | R16
166930323005 | 166279323005 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-20 | 2023-06-22 | 2023-06-22 | 2023-06-29 | 2023-07-14 | Overhead | R16 | 2023-06-29 | 3 |  | 6 | 12 | 19 | 2023 | 2023 | R16
167743285305 | 164802285305 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-09-10 | 2022-04-11 | 2022-07-11 | 2023-03-20 | 2023-05-26 | Underground | R16 | 2023-03-20 | 152 | 66 | 181 | 50 | 446 | 2021 | 2023 | R16
165020319289 | 160205319289 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-16 | 2023-05-17 | 2023-05-17 | 2023-07-27 | 2023-08-01 | Overhead | R16 | 2023-07-27 | 2 |  | 52 | 4 | 56 | 2023 | 2023 | R16
168079326350 | 165691326350 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-04-24 | 2023-07-26 | 2023-07-26 | 2023-10-13 | 2023-10-16 | Overhead | R16 | 2023-10-13 | 68 |  | 58 | 2 | 126 | 2023 | 2023 | R16
165719310888 | 163135310888 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-27 | 2023-02-27 | 2023-02-28 | 2023-04-05 | 2023-04-21 | Overhead | R16 | 2023-04-05 | 1 | 2 | 27 | 13 | 40 | 2023 | 2023 | R16
166442245033 | 160708245033 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-23 | 2021-08-25 | 2021-08-25 | 2022-08-17 | 2022-09-15 | Overhead | R16 | 2022-08-17 | 3 |  | 256 | 22 | 279 | 2021 | 2022 | R16
162337303119 | 167881303119 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-13 | 2022-12-13 | 2022-12-21 | 2023-09-14 | 2023-09-22 | Overhead | R16 | 2023-09-14 | 1 | 7 | 192 | 7 | 204 | 2022 | 2023 | R16
167351320129 | 162800320129 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-11 | 2023-04-11 | 2023-05-24 |  | 2023-06-29 | Underground | R16 | 2023-05-31 | 1 | 32 | 6 | 22 | 58 | 2023 | 2023 | R16
166290243724 | 164341243724 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-07-28 | 2021-07-28 | 2021-08-13 | 2022-05-16 | 2022-06-20 | Underground | R16 | 2022-05-16 | 1 | 13 | 197 | 26 | 234 | 2021 | 2022 | R16
163354247230 | 169333247230 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-17 | 2021-09-10 | 2021-09-10 | 2022-03-04 | 2022-03-25 | Overhead | R16 | 2022-03-04 | 19 |  | 126 | 16 | 159 | 2021 | 2022 | R16
165646245253 | 169560245253 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-18 | 2021-08-18 | 2021-08-27 | 2021-12-28 | 2021-12-29 | Underground | R16 | 2021-12-28 | 1 | 8 | 88 | 2 | 96 | 2021 | 2021 | R16
165220303653 | 168951303653 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-20 | 2022-12-20 | 2022-12-22 | 2023-06-16 | 2023-06-23 | Overhead | R16 | 2023-06-16 | 1 | 3 | 127 | 6 | 134 | 2022 | 2023 | R16
168836327994 | 164044327994 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-07 | 2023-06-09 | 2023-08-11 | 2023-09-08 | 2023-11-01 | Underground | R16 | 2023-09-08 | 3 | 46 | 21 | 39 | 106 | 2023 | 2023 | R16
167923325293 | 161164325293 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-07-14 | 2023-07-14 | 2023-07-17 | 2023-09-27 | 2023-11-08 | Underground | R16 | 2023-09-27 | 1 | 2 | 53 | 31 | 84 | 2023 | 2023 | R16
162153322943 | 166774322943 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-21 | 2023-06-21 | 2023-06-21 | 2023-08-17 | 2023-09-21 | Overhead | R16 | 2023-08-17 | 1 |  | 42 | 26 | 67 | 2023 | 2023 | R16
163888314767 | 167529314767 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-20 | 2023-03-20 | 2023-04-04 | 2023-07-15 | 2023-07-18 | Overhead | R16 | 2023-07-15 | 1 | 12 | 74 | 2 | 87 | 2023 | 2023 | R16
162823325082 | 169190325082 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-11 | 2023-05-18 | 2023-07-13 | 2023-09-28 | 2023-10-05 | Underground | R16 | 2023-09-28 | 6 | 41 | 56 | 6 | 106 | 2023 | 2023 | R16
166086317105 | 165490317105 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-23 | 2023-04-25 | 2023-04-26 | 2023-08-24 | 2023-10-03 | Overhead | R16 | 2023-08-24 | 2 | 2 | 87 | 29 | 117 | 2023 | 2023 | R16
160907246492 | 163229246492 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2021-09-02 | 2021-09-02 | 2021-09-02 | 2022-07-03 | 2023-08-07 | Overhead | R16 | 2022-07-03 | 1 |  | 217 | 286 | 503 | 2021 | 2023 | R16
167320314304 | 169415314304 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2023-03-27 | 2023-03-29 | 2023-03-30 | 2023-05-02 | 2023-07-19 | Overhead | R16 | 2023-05-02 | 3 | 2 | 24 | 57 | 83 | 2023 | 2023 | R16
162436323512 | 169692323512 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-15 | 2023-05-15 | 2023-06-28 | 2023-07-12 | 2023-07-12 | Underground | R16 | 2023-07-12 | 1 | 33 | 11 |  | 43 | 2023 | 2023 | R16
167177323621 | 167499323621 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-27 | 2023-06-27 | 2023-06-28 | 2023-07-07 | 2023-08-09 | Overhead | R16 | 2023-07-07 | 1 | 2 | 8 | 24 | 32 | 2023 | 2023 | R16
168245306289 | 164390306289 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-18 | 2023-01-18 | 2023-01-18 | 2023-04-05 | 2023-04-06 | Overhead | R16 | 2023-04-05 | 1 |  | 56 | 2 | 57 | 2023 | 2023 | R16
169414315415 | 161729315415 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-05 | 2023-04-11 | 2023-04-11 | 2023-06-22 | 2023-06-23 | Overhead | R16 | 2023-06-22 | 5 |  | 53 | 2 | 58 | 2023 | 2023 | R16
169151317539 | 162444317539 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-02-23 | 2023-02-23 | 2023-05-01 | 2023-07-24 | 2023-07-31 | Underground | R16 | 2023-07-24 | 1 | 48 | 61 | 6 | 113 | 2023 | 2023 | R16
168909245013 | 160942245013 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-24 | 2021-08-24 | 2021-08-24 | 2022-04-07 | 2022-05-19 | Overhead | R16 | 2022-04-07 | 1 |  | 163 | 31 | 193 | 2021 | 2022 | R16
166756326946 | 167721326946 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-27 | 2023-06-27 | 2023-07-31 | 2023-07-31 | 2023-08-28 | Underground | R16 | 2023-07-31 | 1 | 25 |  | 21 | 45 | 2023 | 2023 | R16
166077315820 | 160800315820 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-03-31 | 2023-04-13 | 2023-04-13 | 2023-06-29 | 2023-08-17 | Overhead | R16 | 2023-06-29 | 10 |  | 56 | 36 | 100 | 2023 | 2023 | R16
163387320549 | 160450320549 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-02-14 | 2023-05-16 | 2023-05-30 | 2023-08-02 | 2023-08-16 | Underground | R16 | 2023-08-02 | 66 | 11 | 47 | 11 | 132 | 2023 | 2023 | R16
164354302971 | 167553302971 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-12 | 2022-12-12 | 2022-12-12 | 2022-12-14 | 2023-04-27 | Overhead | R16 | 2022-12-14 | 1 |  | 3 | 97 | 99 | 2022 | 2023 | R16
168938310622 | 162734310622 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-24 | 2023-02-24 | 2023-02-24 | 2023-05-14 | 2023-05-17 | Overhead | R16 | 2023-05-14 | 1 |  | 56 | 3 | 59 | 2023 | 2023 | R16
160764320713 | 160783320713 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-19 | 2023-05-31 | 2023-05-31 |  | 2023-06-14 | Overhead | R16 | 2023-06-01 | 9 |  | 2 | 10 | 19 | 2023 | 2023 | R16
161872241747 | 165377241747 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-02 | 2021-08-02 | 2021-08-02 |  | 2021-11-02 | Overhead | R16 |  | 1 |  |  |  | 67 | 2021 | 2021 | R16
162409336916 | 165012336916 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-06-13 | 2023-06-13 | 2023-10-25 | 2023-12-11 | 2023-12-13 | Underground | R16 | 2023-12-11 | 1 | 97 | 34 | 3 | 132 | 2023 | 2023 | R16
168935306107 | 162960306107 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-11 | 2023-01-11 | 2023-01-25 | 2023-03-20 | 2023-07-31 | Overhead | R16 | 2023-03-20 | 1 | 11 | 39 | 96 | 144 | 2023 | 2023 | R16
165796307112 | 165952307112 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-24 | 2023-01-25 | 2023-01-25 | 2023-03-14 | 2023-03-31 | Overhead | R16 | 2023-03-14 | 2 |  | 35 | 14 | 49 | 2023 | 2023 | R16
163290242739 | 165387242739 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-02 | 2021-08-02 | 2021-08-10 | 2021-08-31 | 2021-11-02 | Underground | R16 | 2021-08-31 | 1 | 7 | 16 | 46 | 67 | 2021 | 2021 | R16
166988244291 | 169244244291 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-17 | 2021-08-19 | 2021-08-19 | 2021-10-28 | 2021-11-18 | Overhead | R16 | 2021-10-28 | 3 |  | 51 | 16 | 68 | 2021 | 2021 | R16
166266305117 | 161893305117 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-05 | 2023-01-06 | 2023-01-30 | 2023-03-16 | 2023-03-25 | Underground | R16 | 2023-03-16 | 2 | 17 | 34 | 7 | 57 | 2023 | 2023 | R16
162634248373 | 168753248373 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2021-08-16 | 2021-08-16 | 2021-09-17 | 2022-02-11 | 2022-02-14 | Underground | R16 | 2022-02-11 | 1 | 25 | 106 | 2 | 131 | 2021 | 2022 | R16
167701246155 | 162872246155 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2022-02-08 | 2022-03-08 | Overhead | R16 | 2022-02-08 | 1 |  | 115 | 21 | 135 | 2021 | 2022 | R16
168282261416 | 164550261416 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-10 | 2021-09-13 | 2021-12-16 |  | 2022-03-31 | Underground | R16 |  | 2 | 69 |  |  | 145 | 2021 | 2022 | R16
168319317806 | 167446317806 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-03 | 2023-05-03 | 2023-05-03 | 2023-08-22 | 2023-10-02 | Overhead | R16 | 2023-08-22 | 1 |  | 80 | 30 | 109 | 2023 | 2023 | R16
168795326208 | 160005326208 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-07-10 | 2023-07-10 | 2023-07-24 | 2023-10-08 | 2023-10-16 | Underground | R16 | 2023-10-08 | 1 | 11 | 55 | 6 | 71 | 2023 | 2023 | R16
162215315618 | 162974315618 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-04-11 | 2023-04-11 | 2023-04-14 |  | 2023-06-21 | Underground | R16 | 2023-06-19 | 1 | 4 | 47 | 3 | 52 | 2023 | 2023 | R16
166973326749 | 164740326749 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-03-06 | 2023-03-06 | 2023-07-28 | 2023-12-05 | 2023-12-19 | Underground | R16 | 2023-12-05 | 1 | 105 | 93 | 11 | 207 | 2023 | 2023 | R16
167665320196 | 164787320196 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-04-20 | 2023-04-20 | 2023-05-25 | 2023-11-22 | 2023-11-29 | Underground | R16 | 2023-11-22 | 1 | 26 | 130 | 6 | 160 | 2023 | 2023 | R16
161429243663 | 166944243663 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-09 | 2021-08-13 | 2021-08-13 | 2021-09-21 | 2021-09-22 | Overhead | R16 | 2021-09-21 | 5 |  | 28 | 2 | 33 | 2021 | 2021 | R16
161682305189 | 161155305189 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-04 | 2023-01-06 | 2023-01-30 | 2023-01-06 | 2023-07-31 | Underground | R16 | 2023-01-06 | 3 | 17 |  | 147 | 149 | 2023 | 2023 | R16
169322248682 | 168413248682 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-13 | 2021-08-13 | 2021-09-20 | 2021-09-21 | 2021-11-13 | Underground | R16 | 2021-09-21 | 1 | 27 | 2 | 39 | 66 | 2021 | 2021 | R16
166697320152 | 161276320152 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-24 | 2023-05-24 | 2023-05-24 | 2023-07-17 | 2023-10-12 | Overhead | R16 | 2023-07-17 | 1 |  | 39 | 64 | 102 | 2023 | 2023 | R16
160922252057 | 164147252057 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-09 | 2021-09-09 | 2021-10-14 | 2022-03-17 | 2022-04-21 | Underground | R16 | 2022-03-17 | 1 | 26 | 111 | 26 | 161 | 2021 | 2022 | R16
167176320884 | 161236320884 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-23 | 2023-05-23 | 2023-06-01 | 2023-08-09 | 2023-08-30 | Overhead | R16 | 2023-08-09 | 1 | 8 | 50 | 16 | 72 | 2023 | 2023 | R16
166570321902 | 160658321902 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-01-03 | 2023-02-23 | 2023-06-12 | 2023-07-17 | 2023-07-20 | Overhead | R16 | 2023-07-17 | 38 | 78 | 26 | 4 | 143 | 2023 | 2023 | R16
169616241372 | 164858241372 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-30 | 2021-07-30 | 2021-07-30 | 2022-07-12 | 2022-08-23 | Overhead | R16 | 2022-07-12 | 1 |  | 248 | 31 | 278 | 2021 | 2022 | R16
169563246024 | 161295246024 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-26 | 2021-08-26 | 2021-08-31 | 2021-10-08 | 2021-10-11 | Underground | R16 | 2021-10-08 | 1 | 4 | 29 | 2 | 33 | 2021 | 2021 | R16
163576246138 | 169242246138 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2021-08-17 | 2021-08-18 | 2021-09-01 | 2022-06-28 | 2022-07-15 | Underground | R16 | 2022-06-28 | 2 | 11 | 215 | 14 | 239 | 2021 | 2022 | R16
161257319740 | 160677319740 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-19 | 2023-05-19 | 2023-05-19 | 2023-07-07 | 2023-09-14 | Overhead | R16 | 2023-07-07 | 1 |  | 36 | 50 | 85 | 2023 | 2023 | R16
160585252627 | 160689252627 | RESIDENTIAL - SINGLE FAMILY ATTACHED | ELEC OH MISC SVC OS | Residential | 2021-08-23 | 2021-08-23 | 2021-10-18 | 2021-10-18 | 2021-10-19 | Overhead | R16 | 2021-10-18 | 1 | 41 |  | 2 | 42 | 2021 | 2021 | R16
163745251123 | 165026251123 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-09-13 | 2021-09-13 | 2021-10-07 | 2021-11-08 | 2021-12-08 | Underground | R16 | 2021-11-08 | 1 | 19 | 23 | 23 | 63 | 2021 | 2021 | R16
169773307883 | 167045307883 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-01-30 | 2023-01-31 | 2023-01-31 | 2023-04-27 | 2023-10-17 | Overhead | R16 | 2023-04-27 | 2 |  | 63 | 124 | 187 | 2023 | 2023 | R16
161573320882 | 162656320882 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-07-19 | 2023-08-03 | Overhead | R16 | 2023-07-19 | 1 |  | 35 | 12 | 46 | 2023 | 2023 | R16
168798245087 | 161005245087 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-24 | 2021-08-24 | 2021-08-24 | 2021-08-31 | 2021-10-25 | Overhead | R16 | 2021-08-31 | 1 |  | 6 | 40 | 45 | 2021 | 2021 | R16
169929315283 | 161908315283 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-06 | 2023-04-10 | 2023-04-10 | 2023-07-27 | 2023-08-01 | Overhead | R16 | 2023-07-27 | 3 |  | 79 | 4 | 84 | 2023 | 2023 | R16
169848316263 | 164439316263 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2023-04-18 | 2023-04-18 | 2023-04-18 | 2023-04-24 | 2023-06-23 | Overhead | R16 | 2023-04-24 | 1 |  | 5 | 45 | 49 | 2023 | 2023 | R16
166593246802 | 163593246802 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-07 | 2021-09-07 | 2021-09-07 | 2022-07-14 | 2022-08-18 | Overhead | R16 | 2022-07-14 | 1 |  | 223 | 26 | 248 | 2021 | 2022 | R16
162954282270 | 163262282270 | SPECIFIC BUDGET PROJECTS | OH R16 RES NON RES OD | Commercial | 2021-09-03 | 2021-09-03 | 2022-06-10 |  | 2023-01-27 | Overhead | R16 |  | 1 | 201 |  |  | 366 | 2021 | 2023 | R16
169180308057 | 167036308057 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-30 | 2023-01-30 | 2023-02-02 | 2023-03-14 | 2023-06-12 | Underground | R16 | 2023-03-14 | 1 | 4 | 29 | 65 | 96 | 2023 | 2023 | R16
160289323853 | 165048323853 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-06-13 | 2023-06-13 | 2023-06-30 | 2023-08-21 | 2023-09-05 | Underground | R16 | 2023-08-21 | 1 | 14 | 37 | 12 | 61 | 2023 | 2023 | R16
165929317728 | 166245317728 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-04-27 | 2023-05-02 | 2023-05-02 | 2023-07-21 | 2023-08-07 | Overhead | R16 | 2023-07-21 | 4 |  | 59 | 12 | 73 | 2023 | 2023 | R16
167702247807 | 161544247807 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-26 | 2021-09-08 | 2021-09-14 | 2022-05-09 | 2022-06-09 | Overhead | R16 | 2022-05-09 | 10 | 5 | 170 | 24 | 206 | 2021 | 2022 | R16
167299328017 | 161106328017 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-14 | 2023-08-11 | 2023-08-11 | 2023-10-18 | 2023-10-30 | Overhead | R16 | 2023-10-18 | 21 |  | 49 | 9 | 77 | 2023 | 2023 | R16
166662306516 | 162413306516 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-10 | 2023-01-10 | 2023-01-30 | 2023-01-20 | 2023-05-18 | Underground | R16 | 2023-01-20 | 1 | 15 |  | 85 | 93 | 2023 | 2023 | R16
165529309046 | 162651309046 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-01-10 | 2023-01-13 | 2023-02-10 | 2023-05-13 | 2023-05-16 | Underground | R16 | 2023-05-13 | 4 | 21 | 66 | 2 | 91 | 2023 | 2023 | R16
169610310777 | 162473310777 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-02-23 | 2023-02-28 | 2023-02-28 | 2023-03-27 | 2023-04-03 | Overhead | R16 | 2023-03-27 | 4 |  | 20 | 6 | 28 | 2023 | 2023 | R16
161119241237 | 164719241237 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-08-30 | 2021-11-13 | Overhead | R16 | 2021-08-30 | 1 |  | 23 | 55 | 77 | 2021 | 2021 | R16
167884260087 | 160186260087 | NON-RESIDENTIAL - WAREHOUSE | UG R16 RESD AND NON RESD UD | Commercial | 2021-08-20 | 2021-08-20 | 2021-12-06 | 2022-03-28 | 2022-04-21 | Underground | R16 | 2022-03-28 | 1 | 77 | 81 | 19 | 175 | 2021 | 2022 | R16
169594246417 | 163264246417 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-09-03 | 2021-09-03 | 2021-09-03 | 2022-06-20 | 2022-06-20 | Overhead | R16 | 2022-06-20 | 1 |  | 207 |  | 207 | 2021 | 2022 | R16
164973323782 | 168405323782 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2023-06-29 | 2023-06-29 | 2023-06-29 | 2023-10-04 | 2023-10-17 | Underground | R16 | 2023-10-04 | 1 |  | 70 | 10 | 79 | 2023 | 2023 | R16
166799317514 | 166912317514 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-01 | 2023-05-01 | 2023-05-01 | 2023-06-13 | 2023-06-21 | Overhead | R16 | 2023-06-13 | 1 |  | 32 | 7 | 38 | 2023 | 2023 | R16
161890321274 | 161971321274 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-26 | 2023-06-05 | 2023-06-05 | 2023-07-28 | 2023-08-01 | Overhead | R16 | 2023-07-28 | 7 |  | 40 | 3 | 48 | 2023 | 2023 | R16
165949303842 | 168992303842 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-20 | 2022-12-20 | 2022-12-22 |  | 2023-03-25 | Overhead | R16 | 2023-02-27 | 1 | 3 | 48 | 20 | 69 | 2022 | 2023 | R16
163952245010 | 160755245010 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-24 | 2021-08-24 | 2021-08-24 | 2021-10-27 | 2021-12-02 | Overhead | R16 | 2021-10-27 | 1 |  | 47 | 27 | 73 | 2021 | 2021 | R16
168344328252 | 162253328252 | CUSTOMER UPGRADE IN SERVICE | OH R16 ELEC VEHICLE RES OS | Residential | 2023-05-30 | 2023-08-14 | 2023-08-14 | 2023-09-11 | 2023-09-13 | Overhead | R16 | 2023-09-11 | 55 |  | 21 | 3 | 77 | 2023 | 2023 | R16
162667321941 | 161065321941 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-22 | 2023-06-12 | 2023-06-12 | 2023-11-23 | 2023-11-28 | Overhead | R16 | 2023-11-23 | 16 |  | 119 | 4 | 137 | 2023 | 2023 | R16
168484328511 | 168990328511 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-10 | 2023-05-18 | 2023-08-16 | 2023-09-11 | 2023-09-15 | Overhead | R16 | 2023-09-11 | 7 | 65 | 19 | 5 | 93 | 2023 | 2023 | R16
164150308351 | 160383308351 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-30 | 2022-12-30 | 2023-02-03 |  | 2023-03-15 | Underground | R16 | 2023-03-03 | 1 | 26 | 21 | 9 | 54 | 2022 | 2023 | R16
166821280476 | 162755280476 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2021-09-01 | 2022-03-25 | 2022-05-24 |  | 2022-09-15 | Overhead | R16 |  | 148 | 43 |  |  | 272 | 2021 | 2022 | R16
162335303316 | 168188303316 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-12-15 | 2022-12-15 | 2022-12-21 |  | 2023-02-28 | Overhead | R16 | 2023-01-03 | 1 | 5 | 10 | 41 | 54 | 2022 | 2023 | R16
169253241764 | 165391241764 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-08-02 | 2021-08-02 | 2021-08-02 | 2021-09-14 | 2021-11-08 | Overhead | R16 | 2021-09-14 | 1 |  | 32 | 40 | 71 | 2021 | 2021 | R16
167756324243 | 169294324243 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-06 | 2023-07-06 | 2023-07-06 | 2023-07-06 | 2023-07-25 | Overhead | R16 | 2023-07-06 | 1 |  |  | 14 | 14 | 2023 | 2023 | R16
166870247210 | 162454247210 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-08-31 | 2021-08-31 | 2021-09-09 | 2021-11-18 | 2022-01-12 | Underground | R16 | 2021-11-18 | 1 | 8 | 51 | 40 | 97 | 2021 | 2022 | R16
165940322072 | 164075322072 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-06-07 | 2023-06-13 | 2023-06-13 | 2023-08-30 | 2023-08-31 | Overhead | R16 | 2023-08-30 | 5 |  | 57 | 2 | 62 | 2023 | 2023 | R16
162273314330 | 160606314330 | CUSTOMER UPGRADE IN SERVICE | UG SVC CONVERSION | Residential | 2023-03-31 | 2023-03-31 | 2023-03-31 | 2023-06-06 | 2023-06-15 | Underground | R16 | 2023-06-06 | 1 |  | 48 | 8 | 55 | 2023 | 2023 | R16
162553160602 | 163331160602 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2019-08-01 | 2019-08-05 | 2019-08-08 | 2019-09-01 | 2020-01-02 | Overhead | R16 | 2019-09-01 | 3 | 4 | 17 | 89 | 111 | 2019 | 2020 | R16
165296162861 | 168540162861 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-30 | 2019-08-30 | 2019-08-30 | 2019-09-23 | 2019-09-24 | Overhead | R16 | 2019-09-23 | 1 |  | 17 | 2 | 18 | 2019 | 2019 | R16
164830162374 | 167666162374 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-27 | 2019-08-27 | 2019-08-27 |  | 2021-11-05 | Underground | R16 | 2021-04-15 | 1 |  | 428 | 147 | 574 | 2019 | 2021 | R16
161251172063 | 162063172063 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-20 | 2019-09-20 | 2019-11-15 |  | 2020-06-09 | Underground | R16 | 2020-02-18 | 1 | 41 | 68 | 81 | 188 | 2019 | 2020 | R16
165177162831 | 166901162831 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-22 | 2019-08-22 | 2019-08-29 |  | 2019-09-25 | Underground | R16 | 2019-09-18 | 1 | 6 | 15 | 6 | 25 | 2019 | 2019 | R16
165184182961 | 165726182961 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-02 | 2019-12-02 | 2020-03-04 |  | 2020-07-02 | Underground | R16 | 2020-05-06 | 1 | 68 | 46 | 42 | 154 | 2019 | 2020 | R16
164040176765 | 168174176765 | NON-RESIDENTIAL - SMALL OFFICE | R16 RESD AND NON RESD US | Commercial | 2019-12-13 | 2019-12-13 | 2020-01-13 |  | 2020-07-08 | Underground | R16 |  | 1 | 22 |  |  | 149 | 2019 | 2020 | R16
166749167151 | 162184167151 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-09-20 | 2019-09-23 | 2019-10-08 | 2020-04-16 | 2020-04-24 | Underground | R16 | 2020-04-16 | 2 | 12 | 138 | 7 | 156 | 2019 | 2020 | R16
160494173979 | 160419173979 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-09-11 | 2019-09-11 | 2019-12-10 | 2019-12-30 | 2020-01-06 | Overhead | R16 | 2019-12-30 | 1 | 65 | 15 | 6 | 84 | 2019 | 2020 | R16
164147157016 | 164329157016 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-17 | 2019-06-17 | 2019-07-06 |  | 2019-11-15 | Underground | R16 | 2019-08-13 | 1 | 15 | 27 | 69 | 110 | 2019 | 2019 | R16
164876171475 | 160977171475 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-11-04 | 2019-11-04 | 2019-11-12 |  | 2020-06-09 | Underground | R16 |  | 1 | 7 |  |  | 157 | 2019 | 2020 | R16
163479184446 | 168295184446 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-12-13 | 2020-02-20 | 2020-03-17 |  | 2021-03-30 | Underground | R16 |  | 50 | 19 |  |  | 338 | 2019 | 2021 | R16
166490326900 | 160989326900 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2023-07-14 | 2023-07-14 | 2023-07-31 | 2023-09-20 | 2023-10-24 | Overhead | R16 | 2023-09-20 | 1 | 12 | 38 | 25 | 73 | 2023 | 2023 | R16
169467193823 | 164896193823 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH CP R16 WORK RELO TO UG | Commercial | 2019-10-05 | 2019-10-12 | 2020-06-10 | 2021-10-22 | 2022-01-25 | Overhead | R16 | 2021-10-22 | 5 | 173 | 358 | 68 | 602 | 2019 | 2022 | R16
160731165673 | 162848165673 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-25 | 2019-09-25 | 2019-09-25 |  | 2020-06-09 | Overhead | R16 | 2019-12-17 | 1 |  | 60 | 126 | 185 | 2019 | 2020 | R16
165552171654 | 162085171654 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-08 | 2019-11-08 | 2019-11-13 |  | 2020-12-17 | Underground | R16 |  | 1 | 4 |  |  | 290 | 2019 | 2020 | R16
166017164850 | 168249164850 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-30 | 2019-09-18 | 2019-09-18 | 2019-09-25 | 2019-11-27 | Overhead | R16 | 2019-09-25 | 14 |  | 6 | 46 | 64 | 2019 | 2019 | R16
168610156397 | 165308156397 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-20 | 2019-06-20 | 2019-06-26 |  | 2019-09-10 | Underground | R16 | 2019-09-03 | 1 | 5 | 50 | 6 | 59 | 2019 | 2019 | R16
164804175035 | 165799175035 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-04 | 2019-12-23 | 2019-12-23 | 2020-07-21 | 2020-10-06 | Overhead | R16 | 2020-07-21 | 14 |  | 152 | 56 | 220 | 2019 | 2020 | R16
162127173438 | 165718173438 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-03 | 2019-12-03 | 2019-12-03 | 2020-02-21 | 2020-06-09 | Overhead | R16 | 2020-02-21 | 1 |  | 59 | 78 | 136 | 2019 | 2020 | R16
160935169126 | 168053169126 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-21 | 2019-10-21 | 2019-10-21 |  | 2020-06-09 | Overhead | R16 | 2020-02-03 | 1 |  | 76 | 92 | 167 | 2019 | 2020 | R16
167502160086 | 163654160086 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-05 | 2019-08-05 | 2019-08-05 |  | 2019-09-03 | Overhead | R16 | 2019-08-08 | 1 |  | 4 | 19 | 22 | 2019 | 2019 | R16
168338172636 | 166765172636 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-14 | 2019-10-14 | 2019-11-22 |  | 2020-06-09 | Underground | R16 | 2020-02-18 | 1 | 30 | 63 | 81 | 172 | 2019 | 2020 | R16
169744156264 | 165766156264 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-24 | 2019-06-24 | 2019-06-24 | 2019-06-25 | 2019-08-26 | Overhead | R16 | 2019-06-25 | 1 |  | 2 | 45 | 46 | 2019 | 2019 | R16
168097160072 | 160056160072 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-15 | 2019-08-06 | 2019-08-06 |  | 2019-12-16 | Underground | R16 | 2019-12-05 | 17 |  | 88 | 8 | 111 | 2019 | 2019 | R16
165262175495 | 165463175495 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-27 | 2019-11-27 | 2020-01-02 | 2020-02-24 | 2020-06-09 | Underground | R16 | 2020-02-24 | 1 | 27 | 38 | 77 | 140 | 2019 | 2020 | R16
163097162532 | 167758162532 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-28 | 2019-08-28 | 2019-08-28 | 2019-11-27 | 2020-06-09 | Overhead | R16 | 2019-11-27 | 1 |  | 66 | 140 | 205 | 2019 | 2020 | R16
169331196455 | 160284196455 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-30 | 2019-10-30 | 2020-07-07 | 2020-11-19 | 2020-11-23 | Underground | R16 | 2020-11-19 | 1 | 180 | 98 | 3 | 279 | 2019 | 2020 | R16
164555156749 | 167625156749 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2020-03-30 | 2020-03-31 | Overhead | R16 | 2020-03-30 | 1 |  | 196 | 2 | 197 | 2019 | 2020 | R16
169670158968 | 161877158968 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-25 | 2019-07-25 | 2019-07-25 |  | 2019-09-12 | Underground | R16 | 2019-09-06 | 1 |  | 32 | 5 | 36 | 2019 | 2019 | R16
166381159089 | 166258159089 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-06-26 | 2019-06-27 | 2019-07-26 | 2020-03-19 | 2020-04-03 | Overhead | R16 | 2020-03-19 | 2 | 22 | 170 | 12 | 203 | 2019 | 2020 | R16
160548164345 | 167783164345 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-08-28 | 2019-08-28 | 2019-09-13 |  | 2022-08-29 | Underground | R16 |  | 1 | 13 |  |  | 784 | 2019 | 2022 | R16
168280169099 | 168520169099 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-22 | 2019-10-22 | 2019-10-22 |  | 2020-08-28 | Overhead | R16 | 2020-07-07 | 1 |  | 186 | 39 | 224 | 2019 | 2020 | R16
165000176406 | 168384176406 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-08-29 | 2019-08-29 | 2020-01-09 |  | 2021-04-21 | Underground | R16 |  | 1 | 96 |  |  | 430 | 2019 | 2021 | R16
166927174838 | 168371174838 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-29 | 2019-08-29 | 2019-12-19 |  | 2020-10-06 | Underground | R16 | 2020-08-14 | 1 | 81 | 172 | 38 | 289 | 2019 | 2020 | R16
167495157238 | 167197157238 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-01 | 2019-07-01 | 2019-07-08 | 2019-07-09 | 2019-07-09 | Overhead | R16 | 2019-07-09 | 1 | 6 | 2 |  | 7 | 2019 | 2019 | R16
163079161504 | 163671161504 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-08-05 | 2019-08-05 | 2019-08-19 |  | 2019-09-06 | Underground | R16 |  | 1 | 11 |  |  | 25 | 2019 | 2019 | R16
165501166656 | 164388166656 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-03 | 2019-10-03 | 2019-10-03 | 2019-10-11 | 2019-10-14 | Overhead | R16 | 2019-10-11 | 1 |  | 7 | 2 | 8 | 2019 | 2019 | R16
169127169139 | 168350169139 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-22 | 2019-10-22 | 2019-10-22 |  | 2019-12-30 | Overhead | R16 | 2019-12-27 | 1 |  | 49 | 2 | 50 | 2019 | 2019 | R16
160576166762 | 160746166762 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-12 | 2019-09-12 | 2019-10-03 |  | 2022-09-15 | Underground | R16 | 2022-09-14 | 1 | 16 | 770 | 2 | 786 | 2019 | 2022 | R16
166447156297 | 166129156297 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-26 | 2019-06-27 | 2019-06-27 | 2019-07-25 | 2019-08-26 | Overhead | R16 | 2019-07-25 | 2 |  | 21 | 23 | 44 | 2019 | 2019 | R16
160417169332 | 163804169332 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-01 | 2019-10-01 | 2019-10-24 |  | 2022-10-24 | Underground | R16 |  | 1 | 18 |  |  | 800 | 2019 | 2022 | R16
160880174604 | 160881174604 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-02 | 2019-11-02 | 2019-12-16 |  | 2020-06-09 | Underground | R16 | 2020-02-18 | 0 | 31 | 47 | 81 | 157 | 2019 | 2020 | R16
169839178781 | 163926178781 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-20 | 2019-11-20 | 2020-01-30 | 2020-03-13 | 2020-06-09 | Underground | R16 | 2020-03-13 | 1 | 52 | 32 | 63 | 145 | 2019 | 2020 | R16
162545158421 | 160870158421 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-18 | 2019-07-18 | 2019-07-19 | 2019-08-05 | 2019-08-05 | Overhead | R16 | 2019-08-05 | 1 | 2 | 12 |  | 13 | 2019 | 2019 | R16
163195168188 | 169630168188 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-06 | 2019-09-06 | 2019-10-14 | 2020-01-17 | 2020-04-27 | Underground | R16 | 2020-01-17 | 1 | 27 | 70 | 72 | 167 | 2019 | 2020 | R16
166537163418 | 169607163418 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-06 | 2019-09-06 | 2019-09-06 |  | 2019-11-15 | Overhead | R16 | 2019-11-08 | 1 |  | 46 | 6 | 51 | 2019 | 2019 | R16
160029171785 | 162996171785 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-13 | 2019-11-13 | 2019-11-13 |  | 2020-06-09 | Overhead | R16 | 2020-04-16 | 1 |  | 112 | 39 | 150 | 2019 | 2020 | R16
164358156601 | 166446156601 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-27 | 2019-06-27 | 2019-06-27 |  | 2019-10-14 | Overhead | R16 | 2019-10-03 | 1 |  | 71 | 8 | 78 | 2019 | 2019 | R16
161406176804 | 163124176804 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2019-11-14 | 2019-12-12 | 2020-01-13 |  | 2020-06-23 | Underground | R16 |  | 21 | 23 |  |  | 159 | 2019 | 2020 | R16
161958159041 | 162016159041 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-25 | 2019-07-25 | 2019-07-25 | 2019-07-29 | 2022-08-02 | Overhead | R16 | 2019-07-29 | 1 |  | 3 | 787 | 789 | 2019 | 2022 | R16
163746162445 | 167479162445 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-26 | 2019-08-26 | 2019-08-26 |  | 2019-10-30 | Overhead | R16 | 2019-10-23 | 1 |  | 43 | 6 | 48 | 2019 | 2019 | R16
164676176683 | 165693176683 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-02 | 2019-12-02 | 2020-01-13 |  | 2020-06-29 | Underground | R16 | 2020-04-24 | 1 | 31 | 75 | 47 | 151 | 2019 | 2020 | R16
163613156924 | 167605156924 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2019-07-16 | 2019-07-19 | Overhead | R16 | 2019-07-16 | 1 |  | 12 | 4 | 15 | 2019 | 2019 | R16
167464227954 | 164344227954 | Electric Vehicle | UG R16 RESD AND NON RESD UD | Commercial | 2019-11-20 | 2019-12-19 | 2021-04-22 | 2022-05-23 | 2022-06-13 | Underground | R16 | 2022-05-23 | 22 | 351 | 283 | 16 | 669 | 2019 | 2022 | R16
162076161558 | 166329161558 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-20 | 2019-08-20 | 2019-08-20 | 2019-11-02 | 2019-11-05 | Underground | R16 | 2019-11-02 | 1 |  | 54 | 2 | 56 | 2019 | 2019 | R16
162322164757 | 168536164757 | NON-RESIDENTIAL - LARGE RETAIL | R16 RESD AND NON RESD US | Commercial | 2019-08-30 | 2019-09-04 | 2019-09-18 | 2020-07-08 | 2020-10-21 | Underground | R16 | 2020-07-08 | 4 | 11 | 211 | 76 | 299 | 2019 | 2020 | R16
163567172649 | 164569172649 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-22 | 2019-11-22 | 2019-11-22 | 2020-10-31 | 2021-07-09 | Overhead | R16 | 2020-10-31 | 1 |  | 246 | 180 | 426 | 2019 | 2021 | R16
164609168946 | 168104168946 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-21 | 2019-10-21 | 2019-10-21 | 2020-01-10 | 2023-06-08 | Overhead | R16 | 2020-01-10 | 1 |  | 60 | 890 | 949 | 2019 | 2023 | R16
166058157121 | 166227157121 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-26 | 2019-06-26 | 2019-07-05 | 2020-05-18 | 2020-05-19 | Underground | R16 | 2020-05-18 | 1 | 8 | 227 | 2 | 235 | 2019 | 2020 | R16
161076161237 | 165777161237 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-15 | 2019-08-15 | 2019-08-15 |  | 2019-11-26 | Overhead | R16 | 2019-11-18 | 1 |  | 68 | 7 | 74 | 2019 | 2019 | R16
165339164575 | 169407164575 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-11 | 2019-07-17 | 2019-09-17 | 2020-03-09 | 2020-06-09 | Underground | R16 | 2020-03-09 | 5 | 45 | 125 | 67 | 239 | 2019 | 2020 | R16
169099160496 | 164446160496 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-08 | 2019-08-08 | 2019-08-08 | 2019-09-06 | 2021-12-16 | Overhead | R16 | 2019-09-06 | 1 |  | 22 | 595 | 616 | 2019 | 2021 | R16
162984177126 | 161211177126 | INDUSTRIAL | UG R16 RESD AND NON RESD UD | Commercial | 2019-09-16 | 2019-11-04 | 2020-01-16 | 2022-01-05 | 2022-01-24 | Underground | R16 | 2022-01-05 | 36 | 54 | 515 | 14 | 616 | 2019 | 2022 | R16
165676156437 | 166550156437 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-27 | 2019-06-27 | 2019-06-27 |  | 2019-08-28 | Overhead | R16 | 2019-08-23 | 1 |  | 42 | 4 | 45 | 2019 | 2019 | R16
165461158676 | 161547158676 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-23 | 2019-07-23 | 2019-07-23 |  | 2019-09-03 | Overhead | R16 | 2019-08-01 | 1 |  | 8 | 24 | 31 | 2019 | 2019 | R16
168323170200 | 160143170200 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-30 | 2019-10-30 | 2019-10-30 |  | 2021-11-10 | Overhead | R16 | 2020-01-27 | 1 |  | 64 | 468 | 531 | 2019 | 2021 | R16
166559161954 | 166529161954 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-08-21 | 2019-08-21 | 2019-08-23 |  | 2021-07-26 | Underground | R16 |  | 1 | 3 |  |  | 504 | 2019 | 2021 | R16
161981165442 | 161938165442 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC DEVELOPMENT | Residential Subdivision | 2019-09-20 | 2019-09-20 | 2019-09-23 | 2020-12-07 | 2019-11-08 | Underground | R16 | 2020-12-07 | 1 | 2 | 316 |  | 36 | 2019 | 2019 | R16
164093160958 | 165412160958 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-14 | 2019-08-14 | 2019-08-14 |  | 2023-06-09 | Overhead | R16 | 2019-08-21 | 1 |  | 6 | 993 | 998 | 2019 | 2023 | R16
168961182261 | 166596182261 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-10-12 | 2019-11-25 | 2020-02-27 |  | 2020-08-28 | Underground | R16 |  | 31 | 69 |  |  | 230 | 2019 | 2020 | R16
162695168349 | 167147168349 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-16 | 2019-10-16 | 2019-10-16 |  | 2019-11-21 | Overhead | R16 | 2019-11-13 | 1 |  | 21 | 7 | 27 | 2019 | 2019 | R16
162673160359 | 163465160359 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-06-12 | 2019-06-12 | 2019-08-08 | 2019-10-22 | 2020-05-05 | Underground | R16 | 2019-10-22 | 1 | 42 | 54 | 141 | 235 | 2019 | 2020 | R16
161320161394 | 165317161394 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-06-20 | 2019-06-25 | 2019-08-16 |  | 2019-09-03 | Overhead | R16 |  | 4 | 39 |  |  | 54 | 2019 | 2019 | R16
162541160709 | 163303160709 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-11 | 2019-06-11 | 2019-08-10 |  | 2022-07-22 | Underground | R16 | 2022-07-20 | 1 | 44 | 768 | 3 | 814 | 2019 | 2022 | R16
161825168282 | 166838168282 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-14 | 2019-10-14 | 2019-10-14 | 2019-11-05 | 2019-11-06 | Overhead | R16 | 2019-11-05 | 1 |  | 17 | 2 | 18 | 2019 | 2019 | R16
166860173877 | 166707173877 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-14 | 2019-10-14 | 2019-12-09 |  | 2022-12-15 | Underground | R16 | 2022-12-13 | 1 | 41 | 787 | 3 | 829 | 2019 | 2022 | R16
167037173943 | 164664173943 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-22 | 2019-11-22 | 2019-12-09 | 2020-05-05 | 2020-05-06 | Overhead | R16 | 2020-05-05 | 1 | 12 | 107 | 2 | 119 | 2019 | 2020 | R16
162918167305 | 164044167305 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-10-02 | 2019-10-07 | 2019-10-07 |  | 2021-08-23 | Underground | R16 | 2021-07-06 | 4 |  | 457 | 35 | 494 | 2019 | 2021 | R16
161504160515 | 164578160515 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-09 | 2019-08-09 | 2019-08-09 | 2019-11-13 | 2019-11-21 | Overhead | R16 | 2019-11-13 | 1 |  | 69 | 7 | 75 | 2019 | 2019 | R16
163175164909 | 169934164909 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-09 | 2019-09-09 | 2019-09-18 |  | 2019-10-28 | Underground | R16 | 2019-10-14 | 1 | 8 | 19 | 11 | 36 | 2019 | 2019 | R16
169001209604 | 160813209604 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-01 | 2019-11-01 | 2020-11-03 |  | 2023-06-07 | Underground | R16 |  | 1 | 263 |  |  | 939 | 2019 | 2023 | R16
167162158901 | 160445158901 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-17 | 2019-07-22 | 2019-07-24 |  | 2019-12-06 | Overhead | R16 |  | 4 | 3 |  |  | 103 | 2019 | 2019 | R16
167681161622 | 166162161622 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-19 | 2019-08-19 | 2019-08-19 |  | 2021-10-20 | Overhead | R16 | 2019-11-26 | 1 |  | 72 | 497 | 568 | 2019 | 2021 | R16
168020162758 | 168472162758 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-30 | 2019-08-30 | 2019-08-30 |  | 2021-05-20 | Overhead | R16 |  | 1 |  |  |  | 450 | 2019 | 2021 | R16
163890155677 | 163258155677 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-11 | 2019-06-11 | 2019-06-19 |  | 2019-07-18 | Underground | R16 | 2019-07-08 | 1 | 7 | 14 | 9 | 28 | 2019 | 2019 | R16
169309171648 | 162484171648 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-11 | 2019-11-11 | 2019-11-12 |  | 2020-06-09 | Overhead | R16 | 2020-01-15 | 1 | 2 | 47 | 105 | 152 | 2019 | 2020 | R16
164665157615 | 169395157615 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-11 | 2019-07-11 | 2019-07-11 |  | 2019-10-16 | Overhead | R16 | 2019-10-07 | 1 |  | 63 | 8 | 70 | 2019 | 2019 | R16
166678177814 | 167256177814 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-24 | 2019-08-24 | 2020-01-23 | 2020-05-20 | 2020-08-20 | Underground | R16 | 2020-05-20 | 0 | 109 | 85 | 67 | 259 | 2019 | 2020 | R16
166926164679 | 161358164679 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-17 | 2019-09-17 | 2019-09-17 |  | 2021-11-13 | Overhead | R16 | 2020-01-30 | 1 |  | 98 | 467 | 564 | 2019 | 2021 | R16
163084159627 | 162972159627 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-31 | 2019-07-31 | 2019-07-31 | 2019-08-28 | 2019-08-29 | Overhead | R16 | 2019-08-28 | 1 |  | 21 | 2 | 22 | 2019 | 2019 | R16
164779165440 | 162331165440 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-23 | 2019-09-23 | 2019-09-23 | 2019-10-04 | 2019-11-14 | Overhead | R16 | 2019-10-04 | 1 |  | 10 | 30 | 39 | 2019 | 2019 | R16
166572176407 | 165445176407 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-27 | 2019-11-27 | 2020-01-09 |  | 2022-10-19 | Underground | R16 |  | 1 | 32 |  |  | 756 | 2019 | 2022 | R16
165824219626 | 165825219626 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2019-12-03 | 2020-06-02 | 2021-02-04 | 2021-10-11 | 2021-10-27 | Underground | R16 | 2021-10-11 | 131 | 178 | 178 | 13 | 497 | 2019 | 2021 | R16
169161158453 | 160986158453 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-19 | 2019-07-19 | 2019-07-19 | 2019-07-19 | 2019-08-26 | Overhead | R16 | 2019-07-19 | 1 |  |  | 27 | 27 | 2019 | 2019 | R16
165250171479 | 167490171479 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-26 | 2019-09-06 | 2019-11-12 | 2021-06-02 | 2021-12-29 | Underground | R16 | 2021-06-02 | 10 | 48 | 407 | 151 | 613 | 2019 | 2021 | R16
163235161634 | 166029161634 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-16 | 2019-08-16 | 2019-08-20 |  | 2019-10-28 | Overhead | R16 | 2019-10-15 | 1 | 3 | 41 | 10 | 52 | 2019 | 2019 | R16
167964171735 | 168705171735 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-23 | 2019-10-23 | 2019-11-13 | 2020-07-08 | 2020-07-09 | Underground | R16 | 2020-07-08 | 1 | 16 | 171 | 2 | 187 | 2019 | 2020 | R16
162606173465 | 165794173465 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-03 | 2019-12-03 | 2019-12-03 | 2020-02-14 | 2020-06-17 | Underground | R16 | 2020-02-14 | 1 |  | 54 | 89 | 142 | 2019 | 2020 | R16
167947164346 | 160938164346 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-13 | 2019-09-13 | 2019-09-13 | 2019-11-01 | 2019-11-04 | Overhead | R16 | 2019-11-01 | 1 |  | 36 | 2 | 37 | 2019 | 2019 | R16
167165168595 | 163247168595 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-26 | 2019-10-08 | 2019-10-18 |  | 2021-11-10 | Overhead | R16 |  | 9 | 9 |  |  | 555 | 2019 | 2021 | R16
161490156723 | 165214156723 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-19 | 2019-07-01 | 2019-07-01 |  | 2019-12-09 | Overhead | R16 | 2019-08-23 | 9 |  | 40 | 77 | 124 | 2019 | 2019 | R16
168400155693 | 164975155693 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-18 | 2019-06-18 | 2019-06-18 | 2019-10-30 | 2021-12-16 | Overhead | R16 | 2019-10-30 | 1 |  | 97 | 557 | 653 | 2019 | 2021 | R16
161508167003 | 162401167003 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-07-29 | 2019-07-29 | 2019-10-04 | 2019-10-24 | 2019-10-25 | Underground | R16 | 2019-10-24 | 1 | 50 | 15 | 2 | 65 | 2019 | 2019 | R16
164492244596 | 161994244596 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2019-11-07 | 2021-08-16 | 2021-08-20 |  | 2022-08-03 | Underground | R16 |  | 463 | 5 |  |  | 715 | 2019 | 2022 | R16
166456183856 | 163653183856 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-18 | 2019-11-18 | 2020-03-12 | 2020-03-19 | 2020-04-03 | Overhead | R16 | 2020-03-19 | 1 | 84 | 6 | 12 | 100 | 2019 | 2020 | R16
160333202701 | 164987202701 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-11-25 | 2019-11-25 | 2020-09-03 |  | 2021-07-24 | Underground | R16 | 2020-11-09 | 1 | 204 | 48 | 185 | 435 | 2019 | 2021 | R16
161998165121 | 164275165121 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-07 | 2019-08-07 | 2019-09-19 | 2020-01-22 | 2020-09-15 | Underground | R16 | 2020-01-22 | 1 | 32 | 90 | 170 | 290 | 2019 | 2020 | R16
162230200014 | 162334200014 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH CP R16 WORK RELO TO UG | Commercial | 2019-09-23 | 2020-04-14 | 2020-08-07 | 2021-01-29 | 2022-04-01 | Overhead | R16 | 2021-01-29 | 147 | 84 | 126 | 306 | 660 | 2019 | 2022 | R16
167868165757 | 162907165757 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-25 | 2019-09-25 | 2019-09-25 |  | 2019-10-28 | Overhead | R16 | 2019-10-17 | 1 |  | 17 | 8 | 24 | 2019 | 2019 | R16
169735161122 | 162470161122 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-29 | 2019-08-13 | 2019-08-13 | 2020-01-14 | 2021-11-10 | Overhead | R16 | 2020-01-14 | 12 |  | 111 | 477 | 598 | 2019 | 2021 | R16
169114176725 | 163744176725 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-05 | 2019-08-05 | 2020-01-13 | 2020-02-11 | 2020-02-12 | Underground | R16 | 2020-02-11 | 1 | 116 | 22 | 2 | 138 | 2019 | 2020 | R16
161734169062 | 163638169062 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-05 | 2019-08-05 | 2019-10-21 |  | 2021-11-04 | Underground | R16 |  | 1 | 56 |  |  | 589 | 2019 | 2021 | R16
167870163880 | 167362163880 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-26 | 2019-08-26 | 2019-09-09 | 2020-02-25 | 2020-02-26 | Underground | R16 | 2020-02-25 | 1 | 11 | 122 | 2 | 133 | 2019 | 2020 | R16
166808173908 | 167088173908 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-10 | 2019-12-10 | 2019-12-10 |  | 2021-11-03 | Overhead | R16 | 2021-06-22 | 1 |  | 401 | 97 | 497 | 2019 | 2021 | R16
162656172282 | 165389172282 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-07 | 2019-10-07 | 2019-11-19 | 2021-04-14 | 2020-06-09 | Underground | R16 | 2021-04-14 | 1 | 32 | 367 |  | 177 | 2019 | 2020 | R16
163196158298 | 160991158298 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-19 | 2019-07-19 | 2019-07-19 |  | 2020-01-08 | Underground | R16 | 2020-01-02 | 1 |  | 120 | 5 | 124 | 2019 | 2020 | R16
160518160197 | 164061160197 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-06 | 2019-08-06 | 2019-08-07 |  | 2019-09-24 | Overhead | R16 | 2019-09-17 | 1 | 2 | 30 | 6 | 36 | 2019 | 2019 | R16
161201161164 | 165366161164 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-13 | 2019-08-13 | 2019-08-13 | 2020-03-06 | 2020-06-09 | Overhead | R16 | 2020-03-06 | 1 |  | 149 | 68 | 216 | 2019 | 2020 | R16
165065173235 | 165068173235 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-25 | 2019-11-25 | 2019-12-04 |  | 2020-06-09 | Underground | R16 | 2020-03-12 | 1 | 8 | 72 | 64 | 142 | 2019 | 2020 | R16
167230168487 | 167241168487 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2019-10-16 | 2019-10-16 | 2019-10-16 | 2021-08-30 | 2021-09-09 | Overhead | R16 | 2021-08-30 | 1 |  | 489 | 9 | 497 | 2019 | 2021 | R16
164687173593 | 166371173593 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-12-05 | 2019-12-05 | 2019-12-05 | 2020-01-16 | 2020-01-17 | Overhead | R16 | 2020-01-16 | 1 |  | 31 | 2 | 32 | 2019 | 2020 | R16
162612165244 | 165165165244 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-19 | 2019-06-19 | 2019-09-20 |  | 2020-01-02 | Underground | R16 | 2019-12-11 | 1 | 68 | 59 | 17 | 142 | 2019 | 2020 | R16
168131161218 | 165835161218 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-16 | 2019-08-16 | 2019-08-16 | 2019-11-08 | 2019-11-11 | Overhead | R16 | 2019-11-08 | 1 |  | 61 | 2 | 62 | 2019 | 2019 | R16
169554160299 | 161472160299 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-23 | 2019-07-26 | 2019-08-06 | 2019-09-09 | 2019-09-10 | Underground | R16 | 2019-09-09 | 4 | 8 | 25 | 2 | 36 | 2019 | 2019 | R16
166331178507 | 166077178507 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-06-25 | 2019-07-18 | 2020-01-29 | 2020-07-07 | 2020-11-04 | Underground | R16 | 2020-07-07 | 18 | 140 | 115 | 87 | 357 | 2019 | 2020 | R16
163987161316 | 165475161316 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-14 | 2019-08-16 | 2019-08-16 |  | 2020-06-09 | Overhead | R16 | 2020-02-10 | 3 |  | 127 | 87 | 215 | 2019 | 2020 | R16
162549180256 | 164329180256 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2019-10-03 | 2019-10-03 | 2020-02-13 | 2020-02-26 | 2020-02-26 | Underground | R16 | 2020-02-26 | 1 | 96 | 10 |  | 105 | 2019 | 2020 | R16
169426172807 | 161442172807 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-06 | 2019-11-25 | 2019-11-25 | 2020-02-24 | 2020-06-09 | Overhead | R16 | 2020-02-24 | 14 |  | 66 | 77 | 155 | 2019 | 2020 | R16
160785169167 | 168036169167 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-21 | 2019-10-21 | 2019-10-21 | 2021-11-01 | 2021-11-02 | Overhead | R16 | 2021-11-01 | 1 |  | 531 | 2 | 532 | 2019 | 2021 | R16
169615166801 | 164349166801 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-03 | 2019-10-03 | 2019-10-03 | 2020-03-06 | 2020-06-09 | Overhead | R16 | 2020-03-06 | 1 |  | 112 | 68 | 179 | 2019 | 2020 | R16
169834161125 | 162970161125 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-31 | 2019-08-13 | 2019-08-13 | 2019-10-21 | 2019-10-30 | Overhead | R16 | 2019-10-21 | 10 |  | 50 | 8 | 66 | 2019 | 2019 | R16
164368173096 | 165442173096 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-27 | 2019-11-27 | 2019-11-27 | 2019-12-27 | 2020-06-09 | Overhead | R16 | 2019-12-27 | 1 |  | 23 | 118 | 140 | 2019 | 2020 | R16
167178171044 | 168912171044 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-24 | 2019-10-24 | 2019-11-07 | 2020-01-02 | 2020-01-07 | Underground | R16 | 2020-01-02 | 1 | 11 | 41 | 4 | 54 | 2019 | 2020 | R16
161610173092 | 163494173092 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-16 | 2019-11-16 | 2019-11-27 | 2020-02-14 | 2020-06-09 | Underground | R16 | 2020-02-14 | 0 | 8 | 58 | 83 | 147 | 2019 | 2020 | R16
166008169846 | 162303169846 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-09-23 | 2019-09-23 | 2019-10-28 |  | 2020-06-09 | Underground | R16 | 2020-03-26 | 1 | 26 | 109 | 54 | 187 | 2019 | 2020 | R16
166748175387 | 167022175387 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-10 | 2019-12-10 | 2019-12-30 |  | 2020-10-06 | Underground | R16 | 2020-08-05 | 1 | 15 | 158 | 45 | 216 | 2019 | 2020 | R16
169563160102 | 167751160102 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-02 | 2019-07-02 | 2019-08-05 | 2019-09-18 | 2019-09-19 | Underground | R16 | 2019-09-18 | 1 | 25 | 33 | 2 | 58 | 2019 | 2019 | R16
168426161624 | 161621161624 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-07-23 | 2019-07-23 | 2019-08-19 |  | 2020-06-09 | Underground | R16 | 2020-02-19 | 1 | 20 | 133 | 80 | 231 | 2019 | 2020 | R16
166077158870 | 163711158870 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-13 | 2019-07-17 | 2019-07-25 |  | 2019-09-05 | Overhead | R16 |  | 25 | 7 |  |  | 61 | 2019 | 2019 | R16
163302165203 | 165492165203 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2019-08-14 | 2019-08-14 | 2019-09-19 |  | 2020-12-29 | Underground | R16 | 2020-09-24 | 1 | 27 | 266 | 69 | 360 | 2019 | 2020 | R16
163958174517 | 160966174517 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-04 | 2019-11-04 | 2019-12-17 | 2023-01-11 | 2022-09-24 | Underground | R16 | 2023-01-11 | 1 | 32 | 802 |  | 755 | 2019 | 2022 | R16
169118170937 | 161559170937 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-06 | 2019-11-06 | 2019-11-06 |  | 2022-05-17 | Overhead | R16 | 2020-02-20 | 1 |  | 77 | 584 | 660 | 2019 | 2022 | R16
165348157702 | 169512157702 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-11 | 2019-07-11 | 2019-07-11 |  | 2019-12-09 | Overhead | R16 | 2019-12-02 | 1 |  | 103 | 6 | 108 | 2019 | 2019 | R16
166712160557 | 161595160557 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-07-23 | 2019-08-09 | 2019-08-09 |  | 2021-08-16 | Underground | R16 | 2021-03-19 | 14 |  | 421 | 107 | 540 | 2019 | 2021 | R16
160555176724 | 163656176724 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-18 | 2019-11-18 | 2020-01-13 | 2020-10-03 | 2020-12-18 | Overhead | R16 | 2020-10-03 | 1 | 41 | 190 | 55 | 285 | 2019 | 2020 | R16
161039165907 | 160898165907 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2019-09-13 | 2019-09-13 | 2019-09-26 | 2019-10-05 | 2020-04-10 | Underground | R16 | 2019-10-05 | 1 | 10 | 7 | 135 | 151 | 2019 | 2020 | R16
166466157080 | 168014157080 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-03 | 2019-07-03 | 2019-07-03 |  | 2019-08-26 | Overhead | R16 | 2019-07-23 | 1 |  | 15 | 25 | 39 | 2019 | 2019 | R16
160736165957 | 162060165957 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-07-25 | 2019-07-25 | 2019-09-26 | 2020-12-17 | 2021-01-08 | Underground | R16 | 2020-12-17 | 1 | 46 | 321 | 17 | 382 | 2019 | 2021 | R16
162707174130 | 167287174130 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2019-12-11 | 2019-12-11 | 2019-12-11 |  | 2020-07-01 | Overhead | R16 | 2020-04-27 | 1 |  | 99 | 48 | 146 | 2019 | 2020 | R16
168621165154 | 162202165154 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-20 | 2019-09-20 | 2019-09-20 |  | 2019-12-06 | Overhead | R16 | 2019-10-15 | 1 |  | 18 | 39 | 56 | 2019 | 2019 | R16
165609176167 | 165854176167 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-09 | 2019-10-09 | 2020-01-07 | 2020-02-19 | 2020-02-19 | Underground | R16 | 2020-02-19 | 1 | 65 | 32 |  | 96 | 2019 | 2020 | R16
168654159354 | 162584159354 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-29 | 2019-07-29 | 2019-07-29 | 2019-08-31 | 2019-09-03 | Overhead | R16 | 2019-08-31 | 1 |  | 25 | 2 | 27 | 2019 | 2019 | R16
169286161727 | 166362161727 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-19 | 2019-08-19 | 2019-08-19 | 2019-11-11 | 2020-06-09 | Overhead | R16 | 2019-11-11 | 1 |  | 61 | 152 | 212 | 2019 | 2020 | R16
165915169363 | 166156169363 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-10 | 2019-10-10 | 2019-10-23 |  | 2019-12-18 | Underground | R16 | 2019-12-09 | 1 | 10 | 34 | 8 | 50 | 2019 | 2019 | R16
168864299908 | 166102299908 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-12-15 | 2022-11-09 | 2022-11-09 | 2023-07-20 | 2023-08-16 | Underground | R16 | 2023-07-20 | 236 |  | 182 | 20 | 436 | 2021 | 2023 | R16
163236161665 | 166145161665 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-08-19 | 2019-08-19 | 2019-08-19 |  | 2019-10-14 | Overhead | R16 | 2019-10-03 | 1 |  | 34 | 8 | 41 | 2019 | 2019 | R16
168683171918 | 169937171918 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-10-29 | 2019-10-29 | 2019-11-14 | 2019-11-15 | 2020-02-04 | Overhead | R16 | 2019-11-15 | 1 | 13 | 2 | 58 | 71 | 2019 | 2020 | R16
165139165959 | 163227165959 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-26 | 2019-09-26 | 2019-09-26 | 2019-12-18 | 2019-12-19 | Overhead | R16 | 2019-12-18 | 1 |  | 60 | 2 | 61 | 2019 | 2019 | R16
162257219436 | 163011219436 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-09-25 | 2019-09-26 | 2021-02-03 | 2021-03-23 | 2021-05-06 | Underground | R16 | 2021-03-23 | 2 | 355 | 35 | 33 | 422 | 2019 | 2021 | R16
165249201014 | 165527201014 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2019-10-08 | 2020-08-17 | 2020-08-19 |  | 2021-07-19 | Overhead | R16 |  | 225 | 3 |  |  | 465 | 2019 | 2021 | R16
166351165701 | 162762165701 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-09-24 | 2019-09-24 | 2019-09-24 |  | 2020-06-09 | Overhead | R16 | 2020-03-09 | 1 |  | 120 | 67 | 186 | 2019 | 2020 | R16
160583176888 | 165562176888 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-11-27 | 2019-12-12 | 2020-01-14 |  | 2021-04-14 | Overhead | R16 | 2020-12-14 | 12 | 24 | 240 | 88 | 361 | 2019 | 2021 | R16
161345159896 | 163556159896 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-02 | 2019-08-02 | 2019-08-02 | 2020-05-23 | 2020-05-26 | Overhead | R16 | 2020-05-23 | 1 |  | 211 | 2 | 213 | 2019 | 2020 | R16
162125168828 | 167852168828 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-19 | 2019-10-19 | 2019-10-19 |  | 2019-12-09 | Overhead | R16 | 2019-12-02 | 0 |  | 31 | 6 | 36 | 2019 | 2019 | R16
162711164283 | 160862164283 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-12 | 2019-09-12 | 2019-09-12 | 2019-10-08 | 2019-10-09 | Overhead | R16 | 2019-10-08 | 1 |  | 19 | 2 | 20 | 2019 | 2019 | R16
160338162088 | 167083162088 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-24 | 2019-08-24 | 2019-08-24 | 2019-11-13 | 2019-11-15 | Overhead | R16 | 2019-11-13 | 0 |  | 58 | 3 | 60 | 2019 | 2019 | R16
169765159722 | 161498159722 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-07-23 | 2019-07-23 | 2019-07-31 |  | 2020-10-06 | Underground | R16 | 2020-07-29 | 1 | 7 | 261 | 50 | 316 | 2019 | 2020 | R16
167183169796 | 161551169796 | NON-RESIDENTIAL - HEALTH CARE | R16 RESD AND NON RESD US | Commercial | 2019-07-23 | 2019-07-23 | 2019-10-28 | 2020-12-28 | 2021-04-09 | Underground | R16 | 2020-12-28 | 1 | 70 | 306 | 75 | 449 | 2019 | 2021 | R16
166734160217 | 161391160217 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-22 | 2019-07-24 | 2019-08-07 | 2019-11-17 | 2019-12-05 | Underground | R16 | 2019-11-17 | 3 | 11 | 73 | 14 | 99 | 2019 | 2019 | R16
163254155217 | 163668155217 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-13 | 2019-06-13 | 2019-06-13 |  | 2019-08-12 | Overhead | R16 | 2019-06-20 | 1 |  | 6 | 38 | 43 | 2019 | 2019 | R16
164978158155 | 165660158155 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-22 | 2019-06-22 | 2019-07-17 | 2019-08-09 | 2019-08-12 | Underground | R16 | 2019-08-09 | 0 | 18 | 18 | 2 | 36 | 2019 | 2019 | R16
163238163196 | 169178163196 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-05 | 2019-09-05 | 2019-09-05 |  | 2021-11-13 | Underground | R16 | 2020-01-06 | 1 |  | 88 | 485 | 572 | 2019 | 2021 | R16
164009169078 | 168284169078 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-22 | 2019-10-22 | 2019-10-22 | 2020-01-09 | 2021-11-10 | Overhead | R16 | 2020-01-09 | 1 |  | 58 | 480 | 537 | 2019 | 2021 | R16
161896159371 | 162593159371 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-07-29 | 2019-07-29 | 2019-07-29 |  | 2021-11-15 | Overhead | R16 | 2019-08-30 | 1 |  | 25 | 577 | 601 | 2019 | 2021 | R16
169243159367 | 162406159367 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-07-29 | 2019-07-29 | 2019-07-29 |  | 2020-06-09 | Overhead | R16 | 2020-03-06 | 1 |  | 160 | 68 | 227 | 2019 | 2020 | R16
166581166257 | 164035166257 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-01 | 2019-10-01 | 2019-10-01 | 2020-01-14 | 2021-11-10 | Overhead | R16 | 2020-01-14 | 1 |  | 76 | 477 | 552 | 2019 | 2021 | R16
163380173404 | 165608173404 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-12-02 | 2019-12-02 | 2019-12-02 |  | 2020-07-01 | Overhead | R16 | 2020-04-28 | 1 |  | 107 | 47 | 153 | 2019 | 2020 | R16
168595161833 | 166658161833 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-21 | 2019-08-21 | 2019-08-21 | 2019-09-06 | 2019-09-09 | Underground | R16 | 2019-09-06 | 1 |  | 13 | 2 | 14 | 2019 | 2019 | R16
167944160399 | 164319160399 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-07 | 2019-08-07 | 2019-08-07 | 2019-08-23 | 2019-08-26 | Overhead | R16 | 2019-08-23 | 1 |  | 13 | 2 | 14 | 2019 | 2019 | R16
161630171761 | 161971171761 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-11-07 | 2019-11-07 | 2019-11-13 |  | 2019-11-27 | Underground | R16 |  | 1 | 5 |  |  | 15 | 2019 | 2019 | R16
160631167299 | 165644167299 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-08 | 2019-10-08 | 2019-10-08 |  | 2021-11-10 | Overhead | R16 | 2019-12-19 | 1 |  | 53 | 495 | 547 | 2019 | 2021 | R16
160392169316 | 160405169316 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential Subdivision | 2019-09-11 | 2019-09-11 | 2019-10-24 |  | 2021-06-02 | Underground | R16 |  | 1 | 32 |  |  | 451 | 2019 | 2021 | R16
168017171320 | 168141171320 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-21 | 2019-10-21 | 2019-11-10 |  | 2022-04-22 | Underground | R16 | 2022-03-25 | 1 | 15 | 620 | 21 | 655 | 2019 | 2022 | R16
160658165123 | 167406165123 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-26 | 2019-08-26 | 2019-09-19 | 2019-12-19 | 2019-12-20 | Underground | R16 | 2019-12-19 | 1 | 19 | 66 | 2 | 85 | 2019 | 2019 | R16
168339161612 | 168571161612 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-07 | 2019-07-07 | 2019-08-19 | 2019-10-17 | 2021-10-20 | Underground | R16 | 2019-10-17 | 0 | 31 | 44 | 525 | 598 | 2019 | 2021 | R16
163328158962 | 164909158962 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-18 | 2019-06-18 | 2019-07-24 | 2019-09-07 | 2019-09-10 | Underground | R16 | 2019-09-07 | 1 | 27 | 33 | 2 | 61 | 2019 | 2019 | R16
162225155857 | 165389155857 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-20 | 2019-06-20 | 2019-06-20 | 2019-07-30 | 2019-09-03 | Overhead | R16 | 2019-07-30 | 1 |  | 29 | 26 | 54 | 2019 | 2019 | R16
167889171400 | 160657171400 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-11-01 | 2019-11-07 | 2019-11-11 |  | 2020-06-09 | Underground | R16 |  | 5 | 3 |  |  | 158 | 2019 | 2020 | R16
160571167425 | 162435167425 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-23 | 2019-09-23 | 2019-10-08 |  | 2020-12-15 | Underground | R16 | 2020-09-11 | 1 | 12 | 244 | 68 | 322 | 2019 | 2020 | R16
165818170327 | 160685170327 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-01 | 2019-11-01 | 2019-11-01 |  | 2020-06-09 | Overhead | R16 | 2019-12-19 | 1 |  | 35 | 124 | 158 | 2019 | 2020 | R16
166327166570 | 164148166570 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-02 | 2019-10-02 | 2019-10-02 | 2019-11-05 | 2019-11-06 | Overhead | R16 | 2019-11-05 | 1 |  | 25 | 2 | 26 | 2019 | 2019 | R16
166230156607 | 166488156607 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-08-28 | 2019-11-25 | Overhead | R16 | 2019-08-28 | 1 |  | 44 | 64 | 107 | 2019 | 2019 | R16
163385168552 | 167288168552 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-16 | 2019-10-16 | 2019-10-17 |  | 2020-06-09 | Overhead | R16 | 2019-12-20 | 1 | 2 | 47 | 123 | 170 | 2019 | 2020 | R16
168343165789 | 162771165789 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-24 | 2019-09-25 | 2019-09-25 |  | 2020-10-06 | Underground | R16 | 2020-06-26 | 2 |  | 198 | 73 | 271 | 2019 | 2020 | R16
166228169822 | 169516169822 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-28 | 2019-10-28 | 2019-10-28 |  | 2019-12-09 | Overhead | R16 | 2019-12-02 | 1 |  | 26 | 6 | 31 | 2019 | 2019 | R16
164121160153 | 160646160153 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-07-17 | 2019-07-17 | 2019-08-05 |  | 2019-08-28 | Overhead | R16 |  | 1 | 14 |  |  | 31 | 2019 | 2019 | R16
165553168429 | 167424168429 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-17 | 2019-10-17 | 2019-10-17 |  | 2019-12-09 | Overhead | R16 | 2019-12-02 | 1 |  | 33 | 6 | 38 | 2019 | 2019 | R16
163113170972 | 161741170972 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-07 | 2019-11-07 | 2019-11-07 | 2020-01-15 | 2020-01-16 | Overhead | R16 | 2020-01-15 | 1 |  | 50 | 2 | 51 | 2019 | 2020 | R16
164315256112 | 164449256112 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-11-21 | 2019-11-21 | 2021-11-11 | 2022-08-31 | 2022-10-03 | Underground | R16 | 2022-08-31 | 1 | 516 | 210 | 24 | 748 | 2019 | 2022 | R16
169544186244 | 169386186244 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-10-26 | 2019-10-26 | 2020-04-02 |  | 2021-04-20 | Underground | R16 |  | 0 | 114 |  |  | 387 | 2019 | 2021 | R16
167976170678 | 161630170678 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-17 | 2019-09-17 | 2019-11-05 | 2019-12-18 | 2019-12-19 | Underground | R16 | 2019-12-18 | 1 | 36 | 32 | 2 | 68 | 2019 | 2019 | R16
160206156981 | 167735156981 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-02 | 2019-07-02 | 2019-07-02 |  | 2021-11-13 | Underground | R16 | 2019-12-18 | 1 |  | 122 | 498 | 619 | 2019 | 2021 | R16
164462157554 | 169408157554 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2019-07-11 | 2019-07-11 | 2019-07-11 | 2019-08-29 | 2023-06-07 | Overhead | R16 | 2019-08-29 | 1 |  | 36 | 985 | 1020 | 2019 | 2023 | R16
169465169720 | 169411169720 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-25 | 2019-10-25 | 2019-10-25 |  | 2022-10-20 | Overhead | R16 |  | 1 |  |  |  | 780 | 2019 | 2022 | R16
163649156597 | 166685156597 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-06-28 | 2019-06-28 | 2019-06-28 |  | 2019-08-26 | Overhead | R16 | 2019-07-10 | 1 |  | 9 | 34 | 42 | 2019 | 2019 | R16
166652158809 | 166795158809 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-28 | 2019-07-19 | 2019-07-24 |  | 2019-10-14 | Overhead | R16 |  | 16 | 4 |  |  | 77 | 2019 | 2019 | R16
166556171205 | 162158171205 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-08 | 2019-11-08 | 2019-11-08 |  | 2020-01-09 | Overhead | R16 | 2019-12-30 | 1 |  | 37 | 9 | 45 | 2019 | 2020 | R16
164632196581 | 167850196581 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2019-10-18 | 2020-03-17 | 2020-07-06 |  | 2021-07-26 | Underground | R16 |  | 108 | 80 |  |  | 462 | 2019 | 2021 | R16
164542157544 | 169277157544 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-10 | 2019-07-10 | 2019-07-10 | 2023-04-10 | 2023-04-11 | Overhead | R16 | 2023-04-10 | 1 |  | 979 | 2 | 980 | 2019 | 2023 | R16
162214165795 | 168924165795 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-03 | 2019-09-03 | 2019-09-26 |  | 2019-10-28 | Underground | R16 | 2019-10-15 | 1 | 18 | 14 | 10 | 40 | 2019 | 2019 | R16
165432160081 | 163630160081 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-04 | 2019-08-04 | 2019-08-04 |  | 2019-08-28 | Overhead | R16 | 2019-08-23 | 0 |  | 15 | 4 | 18 | 2019 | 2019 | R16
168890156575 | 166585156575 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-27 | 2019-06-27 | 2019-06-28 | 2019-07-29 | 2020-09-23 | Overhead | R16 | 2019-07-29 | 1 | 2 | 22 | 303 | 325 | 2019 | 2020 | R16
160489168419 | 160762168419 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-12 | 2019-09-12 | 2019-10-17 |  | 2021-11-13 | Underground | R16 | 2019-12-16 | 1 | 26 | 43 | 500 | 567 | 2019 | 2021 | R16
164046164119 | 164186164119 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-06 | 2019-08-06 | 2019-09-12 |  | 2020-06-09 | Underground | R16 | 2020-02-25 | 1 | 28 | 119 | 76 | 221 | 2019 | 2020 | R16
164535173009 | 165434173009 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-27 | 2019-11-27 | 2019-11-27 |  | 2021-11-10 | Overhead | R16 | 2020-01-22 | 1 |  | 41 | 471 | 511 | 2019 | 2021 | R16
162270181451 | 164799181451 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-09 | 2019-08-19 | 2020-02-22 |  | 2020-06-29 | Underground | R16 | 2020-04-24 | 7 | 135 | 45 | 47 | 232 | 2019 | 2020 | R16
161944180301 | 166180180301 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-09 | 2019-10-09 | 2020-02-12 |  | 2020-10-06 | Underground | R16 | 2020-08-12 | 1 | 91 | 131 | 40 | 260 | 2019 | 2020 | R16
165124163508 | 169591163508 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-06 | 2019-09-06 | 2019-09-06 |  | 2019-10-28 | Overhead | R16 | 2019-10-15 | 1 |  | 28 | 10 | 37 | 2019 | 2019 | R16
164041190119 | 164176190119 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-07 | 2019-08-07 | 2020-05-06 | 2020-05-14 | 2021-07-11 | Overhead | R16 | 2020-05-14 | 1 | 196 | 7 | 302 | 503 | 2019 | 2021 | R16
165805204123 | 169962204123 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-09 | 2019-09-09 | 2020-09-16 |  | 2021-07-16 | Underground | R16 | 2020-11-17 | 1 | 268 | 45 | 174 | 485 | 2019 | 2021 | R16
167528158165 | 160499158165 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-17 | 2019-07-17 | 2019-07-17 |  | 2019-10-09 | Overhead | R16 | 2019-09-25 | 1 |  | 51 | 11 | 61 | 2019 | 2019 | R16
163473184283 | 163408184283 | NON-RESIDENTIAL - WAREHOUSE | UG R16 RESD AND NON RESD UD | Commercial | 2019-08-02 | 2019-08-02 | 2020-03-16 | 2021-02-11 | 2023-10-06 | Underground | R16 | 2021-02-11 | 1 | 162 | 239 | 692 | 1091 | 2019 | 2023 | R16
168413156246 | 165792156246 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-24 | 2019-06-24 | 2019-06-24 |  | 2019-08-26 | Overhead | R16 | 2019-07-22 | 1 |  | 21 | 26 | 46 | 2019 | 2019 | R16
161164165502 | 161234165502 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-09-16 | 2019-09-16 | 2019-09-23 |  | 2020-06-11 | Underground | R16 |  | 1 | 6 |  |  | 194 | 2019 | 2020 | R16
161511170878 | 163324170878 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-11 | 2019-09-16 | 2019-11-06 | 2020-05-18 | 2020-09-22 | Overhead | R16 | 2020-05-18 | 70 | 38 | 139 | 92 | 336 | 2019 | 2020 | R16
161871162667 | 167902162667 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-28 | 2019-08-28 | 2019-08-28 | 2019-08-29 | 2019-09-30 | Overhead | R16 | 2019-08-29 | 1 |  | 2 | 23 | 24 | 2019 | 2019 | R16
167154168695 | 167733168695 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-18 | 2019-10-18 | 2019-10-18 |  | 2020-06-24 | Overhead | R16 | 2020-04-21 | 1 |  | 133 | 47 | 179 | 2019 | 2020 | R16
168173185781 | 169187185781 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-25 | 2020-03-29 | 2020-03-29 | 2020-04-10 | 2020-06-24 | Overhead | R16 | 2020-04-10 | 111 |  | 10 | 54 | 174 | 2019 | 2020 | R16
161686166767 | 164309166767 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-03 | 2019-10-03 | 2019-10-03 |  | 2019-11-26 | Overhead | R16 | 2019-11-19 | 1 |  | 34 | 6 | 39 | 2019 | 2019 | R16
160620164758 | 161571164758 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-17 | 2019-09-17 | 2019-09-18 | 2019-11-19 | 2019-11-20 | Overhead | R16 | 2019-11-19 | 1 | 2 | 45 | 2 | 47 | 2019 | 2019 | R16
164591169366 | 166851169366 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-14 | 2019-10-23 | 2019-10-23 |  | 2021-11-13 | Underground | R16 | 2020-01-07 | 8 |  | 55 | 484 | 545 | 2019 | 2021 | R16
169261163364 | 169270163364 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-09-04 | 2019-09-04 | 2019-09-05 | 2020-08-13 | 2020-07-10 | Underground | R16 | 2020-08-13 | 1 | 2 | 246 |  | 223 | 2019 | 2020 | R16
163186181892 | 167910181892 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-11 | 2019-12-11 | 2020-02-26 | 2020-06-02 | 2020-06-02 | Underground | R16 | 2020-06-02 | 1 | 56 | 70 |  | 125 | 2019 | 2020 | R16
164832163423 | 169239163423 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-05 | 2019-09-05 | 2019-09-05 |  | 2019-10-28 | Underground | R16 | 2019-10-16 | 1 |  | 30 | 9 | 38 | 2019 | 2019 | R16
168086164350 | 168444164350 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-30 | 2019-08-30 | 2019-09-13 | 2020-06-05 | 2021-01-14 | Underground | R16 | 2020-06-05 | 1 | 11 | 191 | 160 | 360 | 2019 | 2021 | R16
161461174188 | 161821174188 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-19 | 2019-09-19 | 2019-12-12 | 2020-02-11 | 2020-02-11 | Underground | R16 | 2020-02-11 | 1 | 61 | 44 |  | 104 | 2019 | 2020 | R16
164986157059 | 168181157059 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-03 | 2019-07-03 | 2019-07-03 | 2019-09-18 | 2019-09-19 | Overhead | R16 | 2019-09-18 | 1 |  | 56 | 2 | 57 | 2019 | 2019 | R16
167486164085 | 160388164085 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-11 | 2019-09-11 | 2019-09-11 | 2020-03-03 | 2020-06-09 | Overhead | R16 | 2020-03-03 | 1 |  | 125 | 71 | 195 | 2019 | 2020 | R16
163346197971 | 163440197971 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-11-15 | 2020-06-29 | 2020-07-22 | 2022-02-08 | 2022-03-01 | Underground | R16 | 2022-02-08 | 162 | 18 | 405 | 16 | 598 | 2019 | 2022 | R16
165567207183 | 166435207183 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-06-27 | 2019-06-27 | 2020-10-13 | 2021-08-19 | 2021-09-13 | Underground | R16 | 2021-08-19 | 1 | 339 | 223 | 18 | 578 | 2019 | 2021 | R16
165783159309 | 162318159309 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-27 | 2019-07-27 | 2019-07-27 |  | 2019-08-28 | Overhead | R16 | 2019-08-20 | 0 |  | 17 | 7 | 23 | 2019 | 2019 | R16
163240169626 | 169323169626 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-25 | 2019-10-25 | 2019-10-25 |  | 2021-11-10 | Overhead | R16 | 2019-12-18 | 1 |  | 39 | 496 | 534 | 2019 | 2021 | R16
169409157137 | 168369157137 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-06 | 2019-07-06 | 2019-07-06 |  | 2019-11-15 | Overhead | R16 | 2019-08-09 | 0 |  | 25 | 71 | 95 | 2019 | 2019 | R16
169567157246 | 168426157246 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-06 | 2019-07-06 | 2019-07-06 | 2019-08-02 | 2019-08-02 | Overhead | R16 | 2019-08-02 | 0 |  | 20 |  | 20 | 2019 | 2019 | R16
166151185912 | 166787185912 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH CP R16 WORK RELO TO UG | Commercial | 2019-10-14 | 2019-12-06 | 2020-03-31 | 2020-05-26 | 2020-09-18 | Overhead | R16 | 2020-05-26 | 40 | 83 | 41 | 84 | 245 | 2019 | 2020 | R16
168420166343 | 163675166343 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-30 | 2019-09-30 | 2019-09-30 | 2019-12-10 | 2021-11-13 | Overhead | R16 | 2019-12-10 | 1 |  | 52 | 504 | 555 | 2019 | 2021 | R16
169525159353 | 162621159353 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-29 | 2019-07-29 | 2019-07-29 |  | 2019-09-03 | Overhead | R16 | 2019-07-30 | 1 |  | 2 | 26 | 27 | 2019 | 2019 | R16
161793158462 | 160982158462 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-19 | 2019-07-19 | 2019-07-19 | 2019-07-22 | 2019-12-06 | Overhead | R16 | 2019-07-22 | 1 |  | 2 | 100 | 101 | 2019 | 2019 | R16
167102163355 | 167782163355 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2019-08-27 | 2019-08-27 | 2019-09-04 |  | 2019-09-19 | Overhead | R16 |  | 1 | 7 |  |  | 18 | 2019 | 2019 | R16
165329157989 | 160103157989 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-16 | 2019-07-16 | 2019-07-16 | 2019-07-29 | 2019-09-03 | Overhead | R16 | 2019-07-29 | 1 |  | 10 | 27 | 36 | 2019 | 2019 | R16
167164165896 | 169933165896 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-09-09 | 2019-09-23 | 2019-09-26 |  | 2019-10-16 | Overhead | R16 |  | 11 | 4 |  |  | 28 | 2019 | 2019 | R16
166788169287 | 166835169287 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-14 | 2019-10-14 | 2019-10-22 | 2020-01-21 | 2020-01-22 | Underground | R16 | 2020-01-21 | 1 | 7 | 66 | 2 | 73 | 2019 | 2020 | R16
169184165133 | 161868165133 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-09-19 | 2019-09-19 | 2019-09-19 |  | 2019-11-26 | Underground | R16 | 2019-11-19 | 1 |  | 44 | 6 | 49 | 2019 | 2019 | R16
164388163084 | 168823163084 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-03 | 2019-09-03 | 2019-09-03 |  | 2019-10-14 | Overhead | R16 | 2019-10-03 | 1 |  | 23 | 8 | 30 | 2019 | 2019 | R16
165287173693 | 162149173693 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-08 | 2019-11-08 | 2019-12-06 |  | 2020-06-09 | Underground | R16 | 2020-02-14 | 1 | 21 | 51 | 83 | 153 | 2019 | 2020 | R16
169589191707 | 169754191707 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-10-28 | 2019-10-28 | 2020-05-20 | 2021-01-27 | 2021-04-23 | Underground | R16 | 2021-01-27 | 1 | 148 | 181 | 63 | 390 | 2019 | 2021 | R16
168574155300 | 163870155300 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-13 | 2019-06-13 | 2019-06-13 | 2019-07-19 | 2021-12-16 | Overhead | R16 | 2019-07-19 | 1 |  | 27 | 630 | 656 | 2019 | 2021 | R16
163915176856 | 164865176856 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-11-22 | 2019-12-16 | 2020-01-14 |  | 2020-06-09 | Overhead | R16 |  | 17 | 22 |  |  | 143 | 2019 | 2020 | R16
169498157631 | 169413157631 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-11 | 2019-07-11 | 2019-07-11 |  | 2019-10-09 | Overhead | R16 | 2019-09-26 | 1 |  | 56 | 10 | 65 | 2019 | 2019 | R16
160559161306 | 160943161306 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-18 | 2019-07-18 | 2019-08-16 | 2019-10-30 | 2019-11-05 | Underground | R16 | 2019-10-30 | 1 | 22 | 54 | 5 | 79 | 2019 | 2019 | R16
164098158904 | 160451158904 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-17 | 2019-07-17 | 2019-07-24 |  | 2019-10-30 | Underground | R16 | 2019-10-15 | 1 | 6 | 60 | 12 | 76 | 2019 | 2019 | R16
161649173078 | 165431173078 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-27 | 2019-11-27 | 2019-11-27 | 2020-02-21 | 2020-10-28 | Overhead | R16 | 2020-02-21 | 1 |  | 63 | 179 | 241 | 2019 | 2020 | R16
160353157917 | 167603157917 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-01 | 2019-07-01 | 2019-07-16 |  | 2022-05-17 | Underground | R16 | 2019-09-17 | 1 | 12 | 46 | 696 | 752 | 2019 | 2022 | R16
162912163145 | 167826163145 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-28 | 2019-08-28 | 2019-09-03 |  | 2020-07-01 | Overhead | R16 | 2020-04-29 | 1 | 5 | 172 | 46 | 221 | 2019 | 2020 | R16
168212170894 | 169222170894 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-24 | 2019-10-25 | 2019-11-06 | 2020-01-28 | 2020-01-29 | Underground | R16 | 2020-01-28 | 2 | 9 | 60 | 2 | 70 | 2019 | 2020 | R16
163327173539 | 166454173539 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-05 | 2019-12-05 | 2019-12-05 | 2020-01-06 | 2020-06-09 | Overhead | R16 | 2020-01-06 | 1 |  | 23 | 112 | 134 | 2019 | 2020 | R16
167882156241 | 165760156241 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-24 | 2019-06-24 | 2019-06-24 | 2019-07-17 | 2019-07-18 | Overhead | R16 | 2019-07-17 | 1 |  | 18 | 2 | 19 | 2019 | 2019 | R16
160342167648 | 166076167648 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-10-09 | 2019-10-10 | 2019-10-10 |  | 2019-12-04 | Overhead | R16 | 2019-11-25 | 2 |  | 33 | 8 | 41 | 2019 | 2019 | R16
168021156399 | 164547156399 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-17 | 2019-06-17 | 2019-06-26 |  | 2019-09-10 | Underground | R16 | 2019-09-10 | 1 | 8 | 55 |  | 62 | 2019 | 2019 | R16
160959201573 | 166819201573 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-10-14 | 2019-10-28 | 2020-08-24 | 2021-08-30 | 2021-09-28 | Underground | R16 | 2021-08-30 | 11 | 216 | 266 | 22 | 512 | 2019 | 2021 | R16
161942157632 | 169602157632 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-11 | 2019-07-11 | 2019-07-11 |  | 2019-09-03 | Overhead | R16 | 2019-07-31 | 1 |  | 15 | 25 | 39 | 2019 | 2019 | R16
163901165223 | 169803165223 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-07 | 2019-09-07 | 2019-09-20 | 2019-10-18 | 2019-10-21 | Underground | R16 | 2019-10-18 | 0 | 10 | 21 | 2 | 31 | 2019 | 2019 | R16
165314164668 | 161154164668 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-16 | 2019-09-16 | 2019-09-16 |  | 2019-10-28 | Overhead | R16 | 2019-10-15 | 1 |  | 22 | 10 | 31 | 2019 | 2019 | R16
162180171958 | 161152171958 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-16 | 2019-09-16 | 2019-11-18 |  | 2022-08-02 | Underground | R16 |  | 1 | 46 |  |  | 752 | 2019 | 2022 | R16
164919156831 | 167629156831 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-02 | 2019-07-02 | 2019-07-02 |  | 2019-08-26 | Overhead | R16 | 2019-07-24 | 1 |  | 17 | 24 | 40 | 2019 | 2019 | R16
168214175190 | 168657175190 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-23 | 2019-10-23 | 2019-12-27 | 2020-02-26 | 2020-02-27 | Underground | R16 | 2020-02-26 | 1 | 48 | 44 | 2 | 92 | 2019 | 2020 | R16
164366157072 | 168084157072 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-03 | 2019-07-03 | 2019-07-03 | 2019-08-26 | 2023-06-08 | Overhead | R16 | 2019-08-26 | 1 |  | 39 | 989 | 1027 | 2019 | 2023 | R16
161902178305 | 168509178305 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-12-16 | 2019-12-16 | 2020-01-28 |  | 2020-06-09 | Overhead | R16 |  | 1 | 32 |  |  | 127 | 2019 | 2020 | R16
162490168424 | 167341168424 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2019-10-16 | 2019-10-16 | 2019-10-16 |  | 2020-06-09 | Overhead | R16 | 2020-01-07 | 1 |  | 60 | 111 | 170 | 2019 | 2020 | R16
165893181752 | 166770181752 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-06 | 2019-12-06 | 2020-02-24 | 2020-07-14 | 2020-07-15 | Underground | R16 | 2020-07-14 | 1 | 57 | 102 | 2 | 159 | 2019 | 2020 | R16
163348161542 | 166150161542 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-18 | 2019-08-18 | 2019-08-18 | 2019-09-18 | 2019-09-19 | Overhead | R16 | 2019-09-18 | 0 |  | 23 | 2 | 24 | 2019 | 2019 | R16
162693163444 | 164656163444 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-09 | 2019-08-21 | 2019-09-05 | 2019-09-05 | 2019-11-13 | Underground | R16 | 2019-09-05 | 9 | 12 |  | 50 | 69 | 2019 | 2019 | R16
160699173094 | 162813173094 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-13 | 2019-11-27 | 2019-11-27 | 2020-03-13 | 2020-06-09 | Overhead | R16 | 2020-03-13 | 11 |  | 78 | 63 | 150 | 2019 | 2020 | R16
161605163273 | 169117163273 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-04 | 2019-09-04 | 2019-09-04 | 2019-09-30 | 2019-10-03 | Overhead | R16 | 2019-09-30 | 1 |  | 19 | 4 | 22 | 2019 | 2019 | R16
161957155324 | 163788155324 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-13 | 2019-06-14 | 2019-06-14 |  | 2019-08-12 | Overhead | R16 | 2019-06-21 | 2 |  | 6 | 37 | 43 | 2019 | 2019 | R16
167165161361 | 160396161361 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-17 | 2019-08-15 | 2019-08-16 |  | 2023-10-15 | Overhead | R16 |  | 22 | 2 |  |  | 1108 | 2019 | 2023 | R16
169015162348 | 163976162348 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-08-06 | 2019-08-26 | 2019-08-26 |  | 2020-07-08 | Overhead | R16 | 2020-05-15 | 15 |  | 190 | 39 | 242 | 2019 | 2020 | R16
163237173533 | 166206173533 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-04 | 2019-12-04 | 2019-12-04 |  | 2020-07-07 | Overhead | R16 | 2020-05-07 | 1 |  | 112 | 44 | 155 | 2019 | 2020 | R16
162801158558 | 164926158558 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-18 | 2019-06-18 | 2019-07-23 |  | 2019-10-28 | Underground | R16 | 2019-10-17 | 1 | 26 | 63 | 8 | 95 | 2019 | 2019 | R16
163101172473 | 164374172473 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-20 | 2019-11-20 | 2019-11-20 | 2019-12-04 | 2021-11-10 | Overhead | R16 | 2019-12-04 | 1 |  | 11 | 506 | 516 | 2019 | 2021 | R16
168170167198 | 168025167198 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-08-28 | 2019-08-28 | 2019-10-07 |  | 2022-06-01 | Underground | R16 |  | 1 | 29 |  |  | 721 | 2019 | 2022 | R16
165948204880 | 168808204880 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-09-03 | 2019-10-04 | 2020-09-23 | 2021-05-03 | 2021-06-28 | Underground | R16 | 2021-05-03 | 24 | 254 | 159 | 41 | 475 | 2019 | 2021 | R16
166554172110 | 163601172110 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-18 | 2019-11-18 | 2019-11-18 |  | 2020-01-09 | Overhead | R16 | 2019-12-30 | 1 |  | 31 | 9 | 39 | 2019 | 2020 | R16
161444192404 | 161175192404 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-16 | 2019-09-16 | 2020-05-27 |  | 2021-07-01 | Underground | R16 | 2020-08-05 | 1 | 183 | 51 | 237 | 469 | 2019 | 2021 | R16
164283167732 | 166480167732 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-11 | 2019-10-11 | 2019-10-11 |  | 2019-11-27 | Overhead | R16 | 2019-11-21 | 1 |  | 30 | 5 | 34 | 2019 | 2019 | R16
160375240922 | 166650240922 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-12-06 | 2020-09-30 | 2021-07-27 |  | 2023-10-16 | Underground | R16 |  | 214 | 215 |  |  | 1007 | 2019 | 2023 | R16
163854158451 | 167444158451 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-01 | 2019-07-01 | 2019-07-19 | 2019-12-16 | 2019-12-16 | Underground | R16 | 2019-12-16 | 1 | 15 | 107 |  | 121 | 2019 | 2019 | R16
167805170646 | 161122170646 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-04 | 2019-11-04 | 2019-11-04 |  | 2020-06-09 | Overhead | R16 | 2019-11-21 | 1 |  | 14 | 144 | 157 | 2019 | 2020 | R16
169003172081 | 160194172081 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2019-10-30 | 2019-10-31 | 2019-11-15 |  | 2020-07-10 | Underground | R16 |  | 2 | 12 |  |  | 183 | 2019 | 2020 | R16
162939172954 | 163952172954 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-06 | 2019-08-06 | 2019-11-26 | 2020-11-12 | 2020-11-13 | Underground | R16 | 2020-11-12 | 1 | 81 | 253 | 2 | 334 | 2019 | 2020 | R16
163165169281 | 168355169281 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-22 | 2019-10-22 | 2019-10-22 |  | 2019-12-03 | Overhead | R16 | 2019-11-25 | 1 |  | 25 | 7 | 31 | 2019 | 2019 | R16
168651173475 | 163121173475 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-25 | 2019-09-25 | 2019-12-04 | 2020-01-23 | 2020-01-24 | Underground | R16 | 2020-01-23 | 1 | 51 | 37 | 2 | 88 | 2019 | 2020 | R16
163968161288 | 165655161288 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-15 | 2019-08-15 | 2019-08-15 |  | 2021-04-21 | Overhead | R16 | 2021-01-20 | 1 |  | 375 | 66 | 440 | 2019 | 2021 | R16
167896160539 | 160904160539 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-18 | 2019-07-18 | 2019-08-08 | 2019-10-22 | 2019-10-23 | Underground | R16 | 2019-10-22 | 1 | 16 | 54 | 2 | 70 | 2019 | 2019 | R16
160679172517 | 164639172517 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-21 | 2019-11-21 | 2019-11-21 | 2020-11-09 | 2021-04-15 | Overhead | R16 | 2020-11-09 | 1 |  | 253 | 114 | 366 | 2019 | 2021 | R16
163419172263 | 163608172263 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-18 | 2019-11-19 | 2019-11-19 |  | 2020-06-09 | Overhead | R16 | 2020-01-27 | 2 |  | 50 | 97 | 147 | 2019 | 2020 | R16
160322165610 | 164346165610 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2019-06-17 | 2019-06-20 | 2019-09-24 |  | 2020-06-09 | Underground | R16 | 2020-03-27 | 4 | 69 | 134 | 53 | 257 | 2019 | 2020 | R16
161575158623 | 168148158623 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-03 | 2019-07-03 | 2019-07-22 |  | 2019-10-22 | Underground | R16 |  | 1 | 14 |  |  | 80 | 2019 | 2019 | R16
165259158920 | 161777158920 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-07-24 | 2019-07-24 | 2019-07-24 |  | 2019-09-03 | Underground | R16 | 2019-08-05 | 1 |  | 9 | 22 | 30 | 2019 | 2019 | R16
169678157820 | 169702157820 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-22 | 2019-09-03 | Underground | R16 | 2019-07-22 | 0 |  | 6 | 32 | 37 | 2019 | 2019 | R16
164277328681 | 160801328681 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-03-31 | 2023-03-31 | 2023-08-17 |  | 2023-10-24 | Underground | R16 | 2023-09-25 | 1 | 100 | 28 | 22 | 148 | 2023 | 2023 | R16
168976173458 | 165808173458 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-03 | 2019-12-03 | 2019-12-03 | 2020-01-24 | 2020-01-24 | Overhead | R16 | 2020-01-24 | 1 |  | 39 |  | 39 | 2019 | 2020 | R16
160899167239 | 166447167239 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-08-20 | 2019-08-21 | 2019-10-08 | 2019-12-03 | 2019-12-11 | Overhead | R16 | 2019-12-03 | 2 | 35 | 41 | 7 | 82 | 2019 | 2019 | R16
165728170573 | 161282170573 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-05 | 2019-11-05 | 2019-11-05 | 2019-12-26 | 2019-12-30 | Overhead | R16 | 2019-12-26 | 1 |  | 38 | 3 | 40 | 2019 | 2019 | R16
169648171071 | 168164171071 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-07-05 | 2019-07-05 | 2019-11-09 | 2020-03-05 | 2020-03-06 | Underground | R16 | 2020-03-05 | 1 | 91 | 84 | 2 | 176 | 2019 | 2020 | R16
165708216541 | 165051216541 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-05 | 2019-10-16 | 2021-01-07 | 2021-03-31 | 2021-06-02 | Underground | R16 | 2021-03-31 | 8 | 322 | 60 | 46 | 433 | 2019 | 2021 | R16
169171164158 | 162657164158 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2019-07-29 | 2019-09-05 | 2019-09-12 |  | 2021-11-10 | Overhead | R16 |  | 29 | 6 |  |  | 598 | 2019 | 2021 | R16
164155157097 | 164496157097 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-17 | 2019-06-17 | 2019-07-05 |  | 2019-09-03 | Underground | R16 | 2019-07-30 | 1 | 15 | 18 | 26 | 57 | 2019 | 2019 | R16
164032156348 | 165949156348 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-25 | 2019-06-25 | 2019-06-25 | 2019-12-19 | 2019-12-20 | Underground | R16 | 2019-12-19 | 1 |  | 128 | 2 | 129 | 2019 | 2019 | R16
161815200802 | 163243200802 | AGRICULTURAL | UG R16 RESD AND NON RESD UD | Residential | 2019-11-14 | 2020-05-29 | 2020-08-17 | 2020-09-25 | 2021-04-06 | Underground | R16 | 2020-09-25 | 142 | 57 | 30 | 138 | 364 | 2019 | 2021 | R16
160870165098 | 160882165098 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-09-12 | 2019-09-12 | 2019-09-20 |  | 2022-10-29 | Underground | R16 |  | 1 | 7 |  |  | 817 | 2019 | 2022 | R16
165988187094 | 166295187094 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-19 | 2019-08-20 | 2020-04-10 | 2020-08-06 | 2020-12-22 | Underground | R16 | 2020-08-06 | 2 | 169 | 85 | 99 | 352 | 2019 | 2020 | R16
169132165441 | 162111165441 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-20 | 2019-09-20 | 2019-09-23 |  | 2019-12-12 | Underground | R16 | 2019-12-03 | 1 | 2 | 52 | 8 | 60 | 2019 | 2019 | R16
166577163235 | 168169163235 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-29 | 2019-09-03 | 2019-09-03 |  | 2019-09-24 | Underground | R16 | 2019-09-16 | 4 |  | 10 | 7 | 19 | 2019 | 2019 | R16
163503162842 | 167246162842 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-08-23 | 2019-08-23 | 2019-08-30 | 2020-01-15 | 2020-01-15 | Overhead | R16 | 2020-01-15 | 1 | 6 | 99 |  | 104 | 2019 | 2020 | R16
163361162688 | 163560162688 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-02 | 2019-08-02 | 2019-08-30 |  | 2021-12-16 | Underground | R16 | 2019-11-11 | 1 | 21 | 52 | 549 | 620 | 2019 | 2021 | R16
161528160462 | 162392160462 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-29 | 2019-07-29 | 2019-08-07 | 2019-11-05 | 2019-10-25 | Overhead | R16 | 2019-11-05 | 1 | 8 | 65 |  | 65 | 2019 | 2019 | R16
160192157249 | 168441157249 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-07-06 | 2019-07-06 | 2019-07-06 |  | 2022-07-29 | Underground | R16 |  | 0 |  |  |  | 800 | 2019 | 2022 | R16
166516170022 | 169502170022 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-28 | 2019-10-28 | 2019-10-28 |  | 2020-01-03 | Underground | R16 | 2019-12-12 | 1 |  | 34 | 17 | 50 | 2019 | 2020 | R16
168836163405 | 167270163405 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-23 | 2019-08-26 | 2019-09-05 |  | 2020-06-09 | Underground | R16 | 2020-01-15 | 2 | 9 | 95 | 105 | 208 | 2019 | 2020 | R16
161499161578 | 166226161578 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-08-19 | 2019-08-19 | 2019-08-20 |  | 2019-09-19 | Overhead | R16 |  | 1 | 2 |  |  | 24 | 2019 | 2019 | R16
167595161271 | 164958161271 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-12 | 2019-08-15 | 2019-08-15 | 2019-10-21 | 2019-10-30 | Overhead | R16 | 2019-10-21 | 4 |  | 48 | 8 | 58 | 2019 | 2019 | R16
167960159246 | 160105159246 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-07-16 | 2019-07-16 | 2019-07-26 |  | 2020-07-09 | Underground | R16 | 2020-06-03 | 1 | 9 | 224 | 27 | 258 | 2019 | 2020 | R16
168030165047 | 169458165047 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-05 | 2019-09-05 | 2019-09-18 |  | 2021-12-08 | Underground | R16 | 2021-11-10 | 1 | 10 | 561 | 21 | 590 | 2019 | 2021 | R16
166432183868 | 160717183868 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-11 | 2019-09-11 | 2020-03-12 |  | 2022-10-18 | Underground | R16 |  | 1 | 132 |  |  | 810 | 2019 | 2022 | R16
162786168339 | 160117168339 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-10 | 2019-09-10 | 2019-10-17 | 2021-10-14 | 2021-10-15 | Underground | R16 | 2021-10-14 | 1 | 28 | 521 | 2 | 549 | 2019 | 2021 | R16
165033161001 | 164914161001 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-12 | 2019-08-12 | 2019-08-12 | 2019-09-19 | 2019-09-20 | Overhead | R16 | 2019-09-19 | 1 |  | 29 | 2 | 30 | 2019 | 2019 | R16
161716169381 | 168093169381 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 ELEC DEVELOPMENT | Residential | 2019-10-21 | 2019-10-23 | 2019-10-23 |  | 2021-02-20 | Underground | R16 |  | 3 |  |  |  | 350 | 2019 | 2021 | R16
164208170295 | 168296170295 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-22 | 2019-10-22 | 2019-10-31 |  | 2022-06-20 | Underground | R16 | 2022-05-24 | 1 | 8 | 669 | 20 | 695 | 2019 | 2022 | R16
169194165455 | 162452165455 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-09-23 | 2019-09-23 | 2019-09-23 |  | 2021-08-23 | Overhead | R16 | 2021-08-05 | 1 |  | 489 | 13 | 501 | 2019 | 2021 | R16
161528157907 | 169888157907 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-15 | 2019-07-15 | 2019-07-15 |  | 2019-08-26 | Overhead | R16 | 2019-07-17 | 1 |  | 3 | 29 | 31 | 2019 | 2019 | R16
167458161037 | 165004161037 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Commercial | 2019-08-12 | 2019-08-12 | 2019-08-13 |  | 2019-12-19 | Underground | R16 |  | 1 | 2 |  |  | 94 | 2019 | 2019 | R16
161949171841 | 162598171841 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2019-11-12 | 2019-11-12 | 2019-11-14 |  | 2020-06-09 | Underground | R16 | 2020-02-04 | 1 | 3 | 59 | 91 | 151 | 2019 | 2020 | R16
163663173202 | 165125173202 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-25 | 2019-11-25 | 2019-11-27 |  | 2020-06-09 | Overhead | R16 | 2020-01-13 | 1 | 3 | 34 | 107 | 142 | 2019 | 2020 | R16
166205175340 | 163430175340 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-15 | 2019-11-15 | 2019-12-30 | 2020-01-31 | 2020-02-03 | Underground | R16 | 2020-01-31 | 1 | 32 | 25 | 2 | 57 | 2019 | 2020 | R16
163535162722 | 166244162722 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-19 | 2019-08-19 | 2019-08-29 | 2020-01-22 | 2021-11-10 | Underground | R16 | 2020-01-22 | 1 | 9 | 105 | 471 | 583 | 2019 | 2021 | R16
164465172565 | 168928172565 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-09-03 | 2019-09-03 | 2019-11-21 |  | 2023-06-07 | Underground | R16 | 2020-01-29 | 1 | 58 | 50 | 876 | 982 | 2019 | 2023 | R16
160107159506 | 162616159506 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-29 | 2019-07-30 | 2019-07-30 |  | 2019-08-28 | Overhead | R16 | 2019-08-21 | 2 |  | 17 | 6 | 23 | 2019 | 2019 | R16
167038168054 | 164662168054 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-03 | 2019-10-03 | 2019-10-15 |  | 2019-11-21 | Overhead | R16 | 2019-11-21 | 1 | 9 | 28 |  | 36 | 2019 | 2019 | R16
160610176930 | 166113176930 | NON-RESIDENTIAL - HEALTH CARE | R16 RESD AND NON RESD US | Commercial | 2019-06-26 | 2019-06-26 | 2020-01-14 | 2020-07-08 | 2021-04-05 | Underground | R16 | 2020-07-08 | 1 | 145 | 127 | 194 | 464 | 2019 | 2021 | R16
161751169080 | 166684169080 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-10-12 | 2019-10-19 | 2019-10-21 |  | 2020-06-09 | Underground | R16 |  | 5 | 1 |  |  | 172 | 2019 | 2020 | R16
161314163227 | 162113163227 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-07-25 | 2019-07-25 | 2019-09-03 |  | 2021-11-05 | Underground | R16 | 2021-04-08 | 1 | 29 | 418 | 152 | 597 | 2019 | 2021 | R16
166623173909 | 167121173909 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-10 | 2019-12-10 | 2019-12-10 |  | 2021-11-10 | Overhead | R16 | 2020-01-15 | 1 |  | 27 | 476 | 502 | 2019 | 2021 | R16
164813170211 | 166316170211 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-11 | 2019-10-30 | 2019-10-30 | 2020-01-02 | 2021-11-13 | Overhead | R16 | 2020-01-02 | 14 |  | 47 | 487 | 546 | 2019 | 2021 | R16
166451202185 | 169197202185 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-04 | 2019-09-04 | 2020-08-28 |  | 2021-07-28 | Underground | R16 | 2021-01-15 | 1 | 258 | 101 | 139 | 496 | 2019 | 2021 | R16
163787181204 | 160118181204 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-10 | 2020-02-19 | 2020-02-19 | 2022-01-10 | 2022-03-02 | Underground | R16 | 2022-01-10 | 117 |  | 494 | 38 | 647 | 2019 | 2022 | R16
167420171040 | 168000171040 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-21 | 2019-11-07 | 2019-11-07 | 2020-01-14 | 2021-11-10 | Overhead | R16 | 2020-01-14 | 14 |  | 49 | 477 | 538 | 2019 | 2021 | R16
164149162446 | 167660162446 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-26 | 2019-08-26 | 2019-08-26 |  | 2019-09-16 | Overhead | R16 |  | 1 |  |  |  | 16 | 2019 | 2019 | R16
165742173579 | 164928173579 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2019-11-25 | 2019-11-25 | 2019-12-05 |  | 2022-08-29 | Overhead | R16 |  | 1 | 9 |  |  | 721 | 2019 | 2022 | R16
169344172578 | 164578172578 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-21 | 2019-11-21 | 2019-11-21 |  | 2020-06-09 | Overhead | R16 | 2020-02-11 | 1 |  | 59 | 86 | 144 | 2019 | 2020 | R16
160610155838 | 163468155838 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-12 | 2019-06-17 | 2019-06-20 |  | 2019-09-18 | Overhead | R16 | 2019-09-10 | 4 | 4 | 59 | 7 | 71 | 2019 | 2019 | R16
166285173166 | 166292173166 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-06-26 | 2019-06-26 | 2019-11-27 | 2020-10-12 | 2020-11-18 | Underground | R16 | 2020-10-12 | 1 | 111 | 229 | 28 | 366 | 2019 | 2020 | R16
167137170064 | 167428170064 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-17 | 2019-10-18 | 2019-10-29 |  | 2021-11-10 | Overhead | R16 | 2020-01-29 | 2 | 8 | 67 | 466 | 540 | 2019 | 2021 | R16
161393162342 | 167410162342 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-26 | 2019-08-26 | 2019-08-26 | 2019-09-26 | 2019-09-26 | Overhead | R16 | 2019-09-26 | 1 |  | 24 |  | 24 | 2019 | 2019 | R16
167512203534 | 162089203534 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-25 | 2020-05-28 | 2020-09-11 |  | 2021-07-26 | Overhead | R16 | 2020-11-02 | 221 | 77 | 37 | 191 | 523 | 2019 | 2021 | R16
165875170249 | 160816170249 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-09-12 | 2019-09-12 | 2019-10-30 | 2020-04-16 | 2020-09-18 | Overhead | R16 | 2020-04-16 | 1 | 35 | 122 | 112 | 267 | 2019 | 2020 | R16
163310178133 | 166364178133 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-04 | 2019-12-10 | 2020-01-28 | 2020-03-16 | 2020-03-17 | Underground | R16 | 2020-03-16 | 5 | 36 | 35 | 2 | 75 | 2019 | 2020 | R16
163118163872 | 169237163872 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-04 | 2019-09-04 | 2019-09-10 |  | 2019-10-28 | Underground | R16 | 2019-10-16 | 1 | 5 | 27 | 9 | 39 | 2019 | 2019 | R16
165109160558 | 164703160558 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-09 | 2019-08-09 | 2019-08-09 |  | 2019-12-06 | Overhead | R16 | 2019-09-09 | 1 |  | 22 | 65 | 86 | 2019 | 2019 | R16
167870166340 | 163581166340 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-30 | 2019-09-30 | 2019-09-30 | 2019-12-23 | 2020-06-09 | Overhead | R16 | 2019-12-23 | 1 |  | 61 | 122 | 182 | 2019 | 2020 | R16
168545166830 | 164614166830 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-03 | 2019-10-03 | 2019-10-03 | 2019-10-29 | 2019-10-30 | Overhead | R16 | 2019-10-29 | 1 |  | 19 | 2 | 20 | 2019 | 2019 | R16
160003167598 | 162537167598 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-24 | 2019-09-24 | 2019-10-10 |  | 2019-11-27 | Underground | R16 | 2019-11-21 | 1 | 13 | 31 | 5 | 47 | 2019 | 2019 | R16
163715176863 | 165037176863 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-25 | 2019-11-25 | 2020-01-13 | 2020-02-18 | 2021-11-10 | Underground | R16 | 2020-02-18 | 1 | 36 | 27 | 452 | 513 | 2019 | 2021 | R16
160065172917 | 162187172917 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-08 | 2019-11-26 | 2019-11-26 | 2020-02-06 | 2020-06-09 | Underground | R16 | 2020-02-06 | 13 |  | 53 | 89 | 153 | 2019 | 2020 | R16
167170157005 | 167780157005 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-02 | 2019-07-02 | 2019-07-02 |  | 2019-11-14 | Overhead | R16 | 2019-11-07 | 1 |  | 93 | 6 | 98 | 2019 | 2019 | R16
161403163700 | 169697163700 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-07 | 2019-09-07 | 2019-09-07 |  | 2019-10-16 | Overhead | R16 | 2019-10-10 | 0 |  | 24 | 5 | 28 | 2019 | 2019 | R16
160555167424 | 162305167424 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-23 | 2019-09-23 | 2019-10-08 |  | 2022-07-29 | Underground | R16 |  | 1 | 12 |  |  | 745 | 2019 | 2022 | R16
165372165104 | 161815165104 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-18 | 2019-09-18 | 2019-09-19 | 2019-11-25 | 2019-12-04 | Overhead | R16 | 2019-11-25 | 1 | 2 | 48 | 8 | 56 | 2019 | 2019 | R16
167861160155 | 163822160155 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-05 | 2019-08-05 | 2019-08-05 |  | 2021-11-03 | Overhead | R16 | 2019-10-02 | 1 |  | 43 | 546 | 588 | 2019 | 2021 | R16
164095161901 | 166768161901 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-21 | 2019-08-21 | 2019-08-21 | 2019-09-20 | 2019-09-24 | Overhead | R16 | 2019-09-20 | 1 |  | 23 | 3 | 25 | 2019 | 2019 | R16
163441163180 | 168780163180 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-01 | 2019-09-01 | 2019-09-03 | 2020-01-29 | 2020-01-30 | Overhead | R16 | 2020-01-29 | 0 | 2 | 107 | 2 | 109 | 2019 | 2020 | R16
166732182524 | 166561182524 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-10-11 | 2020-03-02 | 2020-03-02 | 2020-07-24 | 2020-07-28 | Overhead | R16 | 2020-07-24 | 102 |  | 105 | 3 | 208 | 2019 | 2020 | R16
162821169283 | 167578169283 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-17 | 2019-10-22 | 2019-10-22 | 2020-01-02 | 2021-11-13 | Overhead | R16 | 2020-01-02 | 4 |  | 53 | 487 | 542 | 2019 | 2021 | R16
169621180302 | 169529180302 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-28 | 2019-10-28 | 2020-02-12 |  | 2022-10-19 | Underground | R16 |  | 1 | 78 |  |  | 778 | 2019 | 2022 | R16
166648164641 | 161170164641 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-15 | 2019-09-15 | 2019-09-15 | 2019-11-15 | 2020-01-08 | Overhead | R16 | 2019-11-15 | 0 |  | 45 | 39 | 83 | 2019 | 2020 | R16
168138155712 | 164965155712 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-18 | 2019-06-18 | 2019-06-18 | 2019-07-17 | 2019-08-26 | Overhead | R16 | 2019-07-17 | 1 |  | 22 | 29 | 50 | 2019 | 2019 | R16
169128167594 | 166121167594 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-09 | 2019-10-09 | 2019-10-09 | 2020-04-06 | 2023-06-08 | Overhead | R16 | 2020-04-06 | 1 |  | 129 | 829 | 957 | 2019 | 2023 | R16
167321169647 | 169145169647 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-25 | 2019-10-25 | 2019-10-25 |  | 2019-12-19 | Overhead | R16 | 2019-12-10 | 1 |  | 33 | 8 | 40 | 2019 | 2019 | R16
166429163129 | 168818163129 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-03 | 2019-09-03 | 2019-09-03 |  | 2021-11-05 | Underground | R16 | 2021-05-03 | 1 |  | 435 | 135 | 569 | 2019 | 2021 | R16
168946156226 | 165419156226 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-20 | 2019-06-20 | 2019-06-24 |  | 2020-07-09 | Underground | R16 | 2020-06-05 | 1 | 3 | 250 | 25 | 276 | 2019 | 2020 | R16
162033155441 | 164374155441 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-17 | 2019-06-17 | 2019-06-17 | 2019-08-23 | 2019-09-03 | Overhead | R16 | 2019-08-23 | 1 |  | 50 | 8 | 57 | 2019 | 2019 | R16
165157165076 | 168852165076 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-08 | 2019-07-08 | 2019-09-19 | 2019-11-27 | 2019-12-12 | Underground | R16 | 2019-11-27 | 1 | 54 | 50 | 12 | 114 | 2019 | 2019 | R16
166137172214 | 166885172214 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-14 | 2019-10-14 | 2019-11-18 | 2019-12-10 | 2019-12-11 | Underground | R16 | 2019-12-10 | 1 | 26 | 17 | 2 | 43 | 2019 | 2019 | R16
164993162951 | 168131162951 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-28 | 2019-08-28 | 2019-08-30 | 2019-11-13 | 2019-11-15 | Underground | R16 | 2019-11-13 | 1 | 3 | 54 | 3 | 58 | 2019 | 2019 | R16
168931156229 | 165704156229 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-24 | 2019-06-24 | 2019-06-24 |  | 2021-02-17 | Underground | R16 | 2020-10-20 | 1 |  | 347 | 87 | 433 | 2019 | 2021 | R16
161157173098 | 165452173098 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-27 | 2019-11-27 | 2019-11-27 |  | 2020-06-09 | Overhead | R16 | 2020-01-21 | 1 |  | 40 | 101 | 140 | 2019 | 2020 | R16
164625174063 | 166974174063 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-10 | 2019-12-10 | 2019-12-10 | 2019-12-10 | 2020-06-09 | Overhead | R16 | 2019-12-10 | 1 |  |  | 131 | 131 | 2019 | 2020 | R16
163062166094 | 163633166094 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-05 | 2019-08-05 | 2019-09-27 |  | 2021-11-09 | Underground | R16 |  | 1 | 40 |  |  | 592 | 2019 | 2021 | R16
167539171909 | 162893171909 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-13 | 2019-11-13 | 2019-11-14 |  | 2020-01-08 | Overhead | R16 | 2019-12-31 | 1 | 2 | 34 | 7 | 41 | 2019 | 2020 | R16
161647167452 | 165866167452 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-09 | 2019-10-09 | 2019-10-09 |  | 2019-11-21 | Overhead | R16 | 2019-11-12 | 1 |  | 25 | 8 | 32 | 2019 | 2019 | R16
160572161599 | 163466161599 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-02 | 2019-08-02 | 2019-08-20 |  | 2019-11-21 | Underground | R16 | 2019-11-12 | 1 | 13 | 61 | 8 | 80 | 2019 | 2019 | R16
164883172902 | 169717172902 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-10-28 | 2019-11-12 | 2019-11-25 | 2019-11-26 | 2020-02-05 | Overhead | R16 | 2019-11-26 | 12 | 10 | 2 | 52 | 73 | 2019 | 2020 | R16
161230171769 | 162885171769 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-11-13 | 2019-11-13 | 2019-11-13 |  | 2021-11-09 | Underground | R16 | 2020-11-17 | 1 |  | 265 | 256 | 520 | 2019 | 2021 | R16
166856170626 | 161018170626 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-04 | 2019-11-04 | 2019-11-04 | 2020-09-24 | 2021-01-07 | Overhead | R16 | 2020-09-24 | 1 |  | 234 | 76 | 309 | 2019 | 2021 | R16
166968172940 | 165160172940 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-25 | 2019-11-25 | 2019-11-25 | 2020-02-05 | 2020-02-06 | Overhead | R16 | 2020-02-05 | 1 |  | 53 | 2 | 54 | 2019 | 2020 | R16
166273170781 | 166934170781 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-14 | 2019-10-14 | 2019-11-05 | 2022-12-21 | 2023-06-07 | Underground | R16 | 2022-12-21 | 1 | 17 | 817 | 121 | 953 | 2019 | 2023 | R16
162453156978 | 163269156978 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-11 | 2019-06-11 | 2019-07-03 |  | 2019-07-23 | Underground | R16 | 2019-07-15 | 1 | 17 | 9 | 7 | 31 | 2019 | 2019 | R16
163372170027 | 167395170027 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-01 | 2019-07-01 | 2019-10-28 | 2019-12-18 | 2019-12-19 | Underground | R16 | 2019-12-18 | 1 | 86 | 38 | 2 | 124 | 2019 | 2019 | R16
162546157768 | 169679157768 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-08-27 | 2019-08-28 | Underground | R16 | 2019-08-27 | 0 |  | 32 | 2 | 33 | 2019 | 2019 | R16
160788185644 | 162753185644 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-12 | 2019-11-12 | 2020-03-27 | 2020-05-04 | 2020-05-06 | Underground | R16 | 2020-05-04 | 1 | 99 | 27 | 3 | 127 | 2019 | 2020 | R16
166909158742 | 167460158742 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-01 | 2019-07-01 | 2019-07-23 | 2020-02-13 | 2020-02-14 | Underground | R16 | 2020-02-13 | 1 | 17 | 148 | 2 | 165 | 2019 | 2020 | R16
162572168601 | 164284168601 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-02 | 2019-10-02 | 2019-10-17 | 2020-02-12 | 2020-06-09 | Underground | R16 | 2020-02-12 | 1 | 12 | 85 | 85 | 180 | 2019 | 2020 | R16
164599164855 | 166482164855 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-20 | 2019-08-20 | 2019-09-18 |  | 2019-10-30 | Underground | R16 | 2019-10-21 | 1 | 22 | 24 | 8 | 52 | 2019 | 2019 | R16
165816179307 | 167014179307 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-15 | 2019-10-15 | 2020-02-04 | 2020-03-06 | 2020-03-09 | Underground | R16 | 2020-03-06 | 1 | 81 | 24 | 2 | 105 | 2019 | 2020 | R16
166599168587 | 160168168587 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-09 | 2019-09-13 | 2019-10-17 |  | 2021-11-13 | Overhead | R16 |  | 5 | 25 |  |  | 570 | 2019 | 2021 | R16
166776172834 | 166745172834 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-10-14 | 2019-10-14 | 2019-11-25 |  | 2022-10-20 | Underground | R16 |  | 1 | 31 |  |  | 789 | 2019 | 2022 | R16
167876169341 | 168555169341 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-23 | 2019-10-23 | 2019-10-23 | 2019-11-02 | 2019-11-05 | Overhead | R16 | 2019-11-02 | 1 |  | 8 | 2 | 10 | 2019 | 2019 | R16
162618157263 | 168502157263 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-07 | 2019-07-07 | 2019-07-07 |  | 2019-09-03 | Overhead | R16 | 2019-08-01 | 0 |  | 19 | 24 | 42 | 2019 | 2019 | R16
160536168768 | 163994168768 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-01 | 2019-10-01 | 2019-10-19 |  | 2021-10-25 | Underground | R16 | 2021-09-17 | 1 | 14 | 500 | 27 | 540 | 2019 | 2021 | R16
163080155943 | 165498155943 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-20 | 2019-06-20 | 2019-06-20 |  | 2019-09-03 | Overhead | R16 | 2019-07-29 | 1 |  | 28 | 27 | 54 | 2019 | 2019 | R16
166954163398 | 169594163398 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-09-06 | 2019-09-06 | 2019-09-06 | 2020-01-09 | 2021-11-10 | Overhead | R16 | 2020-01-09 | 1 |  | 90 | 480 | 569 | 2019 | 2021 | R16
169622159708 | 160388159708 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-07-17 | 2019-07-17 | 2019-08-01 | 2020-01-24 | 2020-01-28 | Underground | R16 | 2020-01-24 | 1 | 12 | 127 | 3 | 140 | 2019 | 2020 | R16
168273168965 | 160777168965 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-13 | 2019-09-13 | 2019-10-21 |  | 2020-06-09 | Underground | R16 | 2020-01-23 | 1 | 27 | 69 | 99 | 193 | 2019 | 2020 | R16
168951172712 | 161737172712 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-19 | 2019-09-19 | 2019-11-22 | 2020-01-14 | 2021-11-10 | Underground | R16 | 2020-01-14 | 1 | 47 | 38 | 477 | 560 | 2019 | 2021 | R16
164834173815 | 166527173815 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-12-06 | 2019-12-06 | 2019-12-09 | 2019-12-18 | 2019-12-19 | Underground | R16 | 2019-12-18 | 1 | 2 | 8 | 2 | 10 | 2019 | 2019 | R16
160056166601 | 160076166601 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-10 | 2019-09-10 | 2019-10-02 | 2019-10-30 | 2019-11-05 | Underground | R16 | 2019-10-30 | 1 | 17 | 21 | 5 | 41 | 2019 | 2019 | R16
161093320025 | 161251320025 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-23 | 2023-05-23 | 2023-05-23 | 2023-07-06 | 2023-09-13 | Overhead | R16 | 2023-07-06 | 1 |  | 33 | 50 | 82 | 2023 | 2023 | R16
160829164902 | 160887164902 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-18 | 2019-07-18 | 2019-09-17 | 2020-03-13 | 2020-07-07 | Underground | R16 | 2020-03-13 | 1 | 44 | 129 | 83 | 254 | 2019 | 2020 | R16
165982163792 | 161971163792 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2019-07-25 | 2019-07-25 | 2019-09-09 | 2020-05-14 | 2020-05-20 | Overhead | R16 | 2020-05-14 | 1 | 33 | 179 | 5 | 215 | 2019 | 2020 | R16
164897158737 | 160962158737 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-07-19 | 2019-07-19 | 2019-07-23 |  | 2021-11-13 | Overhead | R16 |  | 1 | 3 |  |  | 606 | 2019 | 2021 | R16
166354158373 | 166355158373 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-06-26 | 2019-06-26 | 2019-07-19 | 2020-03-19 | 2020-04-03 | Overhead | R16 | 2020-03-19 | 1 | 18 | 175 | 12 | 203 | 2019 | 2020 | R16
164297169871 | 169751169871 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-28 | 2019-10-28 | 2019-10-28 |  | 2020-06-09 | Overhead | R16 | 2020-04-07 | 1 |  | 117 | 46 | 162 | 2019 | 2020 | R16
160323165089 | 161860165089 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-19 | 2019-09-19 | 2019-09-19 |  | 2019-11-08 | Overhead | R16 | 2019-11-01 | 1 |  | 32 | 6 | 37 | 2019 | 2019 | R16
164184158006 | 160074158006 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-15 | 2019-07-16 | 2019-07-16 | 2019-08-20 | 2019-08-28 | Overhead | R16 | 2019-08-20 | 2 |  | 26 | 7 | 33 | 2019 | 2019 | R16
165874166107 | 169200166107 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-04 | 2019-09-04 | 2019-09-27 |  | 2020-06-09 | Underground | R16 | 2020-02-28 | 1 | 18 | 111 | 73 | 200 | 2019 | 2020 | R16
166624183509 | 168089183509 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-10-21 | 2020-02-05 | 2020-03-09 |  | 2021-10-25 | Underground | R16 |  | 78 | 24 |  |  | 526 | 2019 | 2021 | R16
161578160670 | 164834160670 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-09 | 2019-08-09 | 2019-08-09 | 2019-08-18 | 2019-08-22 | Overhead | R16 | 2019-08-18 | 1 |  | 6 | 4 | 10 | 2019 | 2019 | R16
165793169587 | 166296169587 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-10 | 2019-10-10 | 2019-10-25 |  | 2020-06-09 | Underground | R16 | 2020-03-04 | 1 | 12 | 94 | 70 | 174 | 2019 | 2020 | R16
162215156620 | 166447156620 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-06-27 | 2019-06-27 | 2019-06-27 |  | 2020-06-17 | Overhead | R16 | 2020-04-10 | 1 |  | 207 | 49 | 255 | 2019 | 2020 | R16
165489169835 | 160876169835 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-12 | 2019-09-12 | 2019-10-29 | 2019-12-04 | 2020-01-02 | Underground | R16 | 2019-12-04 | 1 | 34 | 27 | 22 | 81 | 2019 | 2020 | R16
164050174180 | 167673174180 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-12-11 | 2019-12-11 | 2019-12-11 |  | 2020-10-06 | Underground | R16 | 2020-07-21 | 1 |  | 160 | 56 | 215 | 2019 | 2020 | R16
167500168780 | 167726168780 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-18 | 2019-10-18 | 2019-10-18 |  | 2019-11-06 | Underground | R16 | 2019-10-28 | 1 |  | 7 | 8 | 14 | 2019 | 2019 | R16
163066163442 | 163523163442 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-02 | 2019-08-02 | 2019-09-05 |  | 2021-10-29 | Underground | R16 | 2019-12-11 | 1 | 25 | 70 | 493 | 586 | 2019 | 2021 | R16
163780160256 | 163842160256 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2019-08-05 | 2019-08-06 | 2019-08-06 |  | 2020-10-06 | Overhead | R16 | 2020-07-24 | 2 |  | 254 | 53 | 307 | 2019 | 2020 | R16
160267170936 | 161720170936 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-06 | 2019-11-06 | 2019-11-06 |  | 2021-11-10 | Overhead | R16 | 2019-12-18 | 1 |  | 31 | 496 | 526 | 2019 | 2021 | R16
161104167306 | 161623167306 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential Subdivision | 2019-07-24 | 2019-07-24 | 2019-10-07 | 2019-11-24 | 2020-04-01 | Underground | R16 | 2019-11-24 | 1 | 54 | 35 | 93 | 181 | 2019 | 2020 | R16
165715173382 | 166733173382 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-14 | 2019-10-14 | 2019-12-02 |  | 2020-06-24 | Underground | R16 | 2020-04-21 | 1 | 36 | 102 | 47 | 183 | 2019 | 2020 | R16
167105174675 | 166538174675 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-12-06 | 2019-12-06 | 2019-12-18 |  | 2020-06-09 | Overhead | R16 |  | 1 | 9 |  |  | 133 | 2019 | 2020 | R16
161669169913 | 169692169913 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-28 | 2019-10-28 | 2019-10-28 |  | 2019-11-08 | Overhead | R16 | 2019-10-30 | 1 |  | 3 | 8 | 10 | 2019 | 2019 | R16
160535156004 | 165571156004 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-21 | 2019-06-21 | 2019-06-21 |  | 2020-10-06 | Overhead | R16 | 2020-07-23 | 1 |  | 285 | 54 | 338 | 2019 | 2020 | R16
166101174265 | 166067174265 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-09 | 2019-10-09 | 2019-12-12 |  | 2021-10-27 | Underground | R16 | 2021-08-11 | 1 | 47 | 435 | 56 | 536 | 2019 | 2021 | R16
161061169184 | 168316169184 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-22 | 2019-10-22 | 2019-10-22 |  | 2020-06-09 | Overhead | R16 | 2020-01-14 | 1 |  | 61 | 106 | 166 | 2019 | 2020 | R16
162984177191 | 161212177191 | INDUSTRIAL | R16 RESD AND NON RESD US | Commercial | 2019-09-16 | 2020-01-06 | 2020-01-16 |  | 2022-08-03 | Underground | R16 |  | 81 | 9 |  |  | 753 | 2019 | 2022 | R16
162158157824 | 169744157824 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-12-06 | 2019-12-19 | Overhead | R16 | 2019-12-06 | 0 |  | 105 | 10 | 114 | 2019 | 2019 | R16
166811158258 | 160745158258 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-18 | 2019-07-18 | 2019-07-18 |  | 2019-12-06 | Overhead | R16 | 2019-08-09 | 1 |  | 17 | 86 | 102 | 2019 | 2019 | R16
162882171090 | 166949171090 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-15 | 2019-11-08 | 2019-11-08 | 2020-02-11 | 2020-06-09 | Overhead | R16 | 2020-02-11 | 19 |  | 68 | 86 | 171 | 2019 | 2020 | R16
161486168546 | 167398168546 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-17 | 2019-10-17 | 2019-10-17 |  | 2020-06-09 | Overhead | R16 | 2020-01-30 | 1 |  | 76 | 94 | 169 | 2019 | 2020 | R16
168811171222 | 162107171222 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-08 | 2019-11-08 | 2019-11-08 | 2020-01-05 | 2020-01-08 | Overhead | R16 | 2020-01-05 | 1 |  | 41 | 3 | 44 | 2019 | 2020 | R16
161803170810 | 164266170810 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-02 | 2019-10-02 | 2019-11-05 |  | 2020-08-28 | Underground | R16 | 2020-07-02 | 1 | 25 | 173 | 42 | 238 | 2019 | 2020 | R16
164767173517 | 164647173517 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-22 | 2019-11-22 | 2019-12-05 |  | 2020-06-09 | Underground | R16 | 2020-01-22 | 1 | 10 | 35 | 100 | 143 | 2019 | 2020 | R16
164996158661 | 168312158661 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-05 | 2019-07-08 | 2019-07-22 |  | 2019-08-23 | Overhead | R16 |  | 2 | 11 |  |  | 36 | 2019 | 2019 | R16
168134156454 | 166542156454 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-27 | 2019-06-27 | 2019-06-27 |  | 2019-09-12 | Overhead | R16 | 2019-09-06 | 1 |  | 52 | 5 | 56 | 2019 | 2019 | R16
163085219908 | 166549219908 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH CP R16 WORK RELO TO UG | Commercial | 2019-12-06 | 2020-02-27 | 2021-02-08 | 2021-03-18 | 2021-10-14 | Overhead | R16 | 2021-03-18 | 60 | 248 | 29 | 151 | 485 | 2019 | 2021 | R16
160548160939 | 165327160939 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-13 | 2019-08-13 | 2019-08-13 | 2019-09-13 | 2019-09-19 | Overhead | R16 | 2019-09-13 | 1 |  | 24 | 5 | 28 | 2019 | 2019 | R16
165488162527 | 167910162527 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-28 | 2019-08-28 | 2019-08-28 | 2020-02-12 | 2020-06-09 | Overhead | R16 | 2020-02-12 | 1 |  | 121 | 85 | 205 | 2019 | 2020 | R16
164770170216 | 160369170216 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-31 | 2019-10-31 | 2019-10-31 | 2020-02-21 | 2020-06-16 | Overhead | R16 | 2020-02-21 | 1 |  | 82 | 83 | 164 | 2019 | 2020 | R16
163068156228 | 165841156228 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-24 | 2019-06-24 | 2019-06-24 | 2019-07-25 | 2019-08-26 | Overhead | R16 | 2019-07-25 | 1 |  | 24 | 23 | 46 | 2019 | 2019 | R16
166079159589 | 161592159589 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-23 | 2019-07-26 | 2019-07-30 |  | 2019-08-28 | Overhead | R16 |  | 4 | 3 |  |  | 27 | 2019 | 2019 | R16
167550158170 | 160435158170 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-17 | 2019-07-17 | 2019-07-17 | 2019-10-01 | 2019-11-21 | Overhead | R16 | 2019-10-01 | 1 |  | 55 | 38 | 92 | 2019 | 2019 | R16
168334167587 | 165882167587 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-09 | 2019-10-09 | 2019-10-09 | 2020-09-11 | 2020-09-14 | Overhead | R16 | 2020-09-11 | 1 |  | 243 | 2 | 244 | 2019 | 2020 | R16
164595169964 | 167213169964 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-23 | 2019-08-26 | 2019-10-29 | 2019-12-02 | 2019-12-05 | Underground | R16 | 2019-12-02 | 2 | 47 | 25 | 4 | 75 | 2019 | 2019 | R16
161907172020 | 162374172020 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-23 | 2019-09-23 | 2019-11-15 |  | 2023-06-07 | Underground | R16 |  | 1 | 40 |  |  | 968 | 2019 | 2023 | R16
162545181418 | 164327181418 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-21 | 2020-01-16 | 2020-02-21 | 2020-06-09 | 2020-06-11 | Underground | R16 | 2020-06-09 | 41 | 27 | 78 | 3 | 146 | 2019 | 2020 | R16
167283172563 | 164053172563 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-20 | 2019-11-20 | 2019-11-21 |  | 2020-07-07 | Overhead | R16 | 2020-05-12 | 1 | 2 | 124 | 41 | 165 | 2019 | 2020 | R16
169257165984 | 167370165984 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-26 | 2019-08-26 | 2019-09-27 | 2019-11-22 | 2019-11-22 | Underground | R16 | 2019-11-22 | 1 | 25 | 41 |  | 65 | 2019 | 2019 | R16
162448162732 | 168659162732 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-30 | 2019-08-30 | 2019-08-30 | 2021-10-14 | 2021-10-14 | Overhead | R16 | 2021-10-14 | 1 |  | 555 |  | 555 | 2019 | 2021 | R16
160636172121 | 168886172121 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE FOR UPGRADE UD | Commercial | 2019-10-24 | 2019-10-24 | 2019-11-15 | 2020-06-25 | 2021-01-05 | Underground | R16 | 2020-06-25 | 1 | 17 | 160 | 139 | 314 | 2019 | 2021 | R16
162376165476 | 162527165476 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-23 | 2019-09-23 | 2019-09-23 |  | 2019-12-06 | Overhead | R16 | 2019-10-22 | 1 |  | 22 | 34 | 55 | 2019 | 2019 | R16
167164163462 | 167805163462 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-27 | 2019-08-30 | 2019-09-05 |  | 2019-09-19 | Overhead | R16 |  | 4 | 5 |  |  | 18 | 2019 | 2019 | R16
162375157019 | 168670157019 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-08 | 2019-07-08 | 2019-07-08 |  | 2019-09-03 | Overhead | R16 | 2019-08-02 | 1 |  | 20 | 23 | 42 | 2019 | 2019 | R16
161045171180 | 161572171180 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-06 | 2019-11-08 | 2019-11-08 |  | 2020-07-08 | Underground | R16 | 2020-04-17 | 3 |  | 116 | 59 | 176 | 2019 | 2020 | R16
162119179052 | 162137179052 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential Subdivision | 2019-09-20 | 2019-09-30 | 2020-02-03 |  | 2021-10-28 | Underground | R16 |  | 7 | 91 |  |  | 550 | 2019 | 2021 | R16
161050170778 | 161342170778 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-16 | 2019-09-16 | 2019-11-06 | 2020-01-29 | 2020-01-30 | Underground | R16 | 2020-01-29 | 1 | 38 | 61 | 2 | 99 | 2019 | 2020 | R16
163716176341 | 160864176341 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-02 | 2019-11-02 | 2020-01-08 |  | 2022-10-17 | Underground | R16 |  | 0 | 48 |  |  | 771 | 2019 | 2022 | R16
166604163887 | 161288163887 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-22 | 2019-07-29 | 2019-09-09 |  | 2019-10-30 | Underground | R16 | 2019-10-30 | 6 | 31 | 38 |  | 73 | 2019 | 2019 | R16
164761181405 | 164811181405 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-22 | 2019-11-22 | 2020-02-21 | 2021-01-14 | 2021-05-06 | Underground | R16 | 2021-01-14 | 1 | 66 | 235 | 81 | 380 | 2019 | 2021 | R16
167213163492 | 169690163492 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-09-06 | 2019-09-06 | 2019-09-06 | 2019-11-05 | 2019-11-05 | Overhead | R16 | 2019-11-05 | 1 |  | 43 |  | 43 | 2019 | 2019 | R16
169465183525 | 169011183525 | FOREIGN UTILITY | UG R16 RESD AND NON RESD UD | Commercial | 2019-09-03 | 2019-09-25 | 2020-03-09 | 2020-06-23 | 2021-02-05 | Underground | R16 | 2020-06-23 | 17 | 119 | 77 | 164 | 374 | 2019 | 2021 | R16
169424172622 | 161367172622 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-06 | 2019-11-21 | 2019-11-21 | 2020-01-03 | 2020-06-09 | Overhead | R16 | 2020-01-03 | 12 |  | 32 | 113 | 155 | 2019 | 2020 | R16
166283166480 | 163848166480 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-01 | 2019-10-01 | 2019-10-01 |  | 2021-11-13 | Overhead | R16 | 2020-03-12 | 1 |  | 118 | 437 | 554 | 2019 | 2021 | R16
164550172381 | 163735172381 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-11-19 | 2019-11-19 | 2019-11-19 | 2019-12-28 | 2019-12-31 | Overhead | R16 | 2019-12-28 | 1 |  | 29 | 2 | 31 | 2019 | 2019 | R16
168548162721 | 167931162721 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-08-28 | 2019-08-28 | 2019-08-29 | 2019-09-10 | 2019-09-13 | Overhead | R16 | 2019-09-10 | 1 | 2 | 9 | 4 | 13 | 2019 | 2019 | R16
160603172947 | 164303172947 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-20 | 2019-11-20 | 2019-11-26 |  | 2020-07-14 | Underground | R16 | 2020-06-16 | 1 | 5 | 146 | 21 | 170 | 2019 | 2020 | R16
169048173035 | 165331173035 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-26 | 2019-11-26 | 2019-11-26 | 2020-03-18 | 2020-06-09 | Overhead | R16 | 2020-03-18 | 1 |  | 82 | 60 | 141 | 2019 | 2020 | R16
163602163334 | 165731163334 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-24 | 2019-07-16 | 2019-09-05 |  | 2019-10-28 | Overhead | R16 | 2019-10-16 | 17 | 38 | 30 | 9 | 91 | 2019 | 2019 | R16
168184170551 | 161066170551 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-04 | 2019-11-04 | 2019-11-04 |  | 2020-06-09 | Overhead | R16 | 2020-03-05 | 1 |  | 89 | 69 | 157 | 2019 | 2020 | R16
162075161004 | 164986161004 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-12 | 2019-08-12 | 2019-08-12 |  | 2019-09-12 | Overhead | R16 | 2019-09-06 | 1 |  | 20 | 5 | 24 | 2019 | 2019 | R16
165593163741 | 169747163741 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-07 | 2019-09-07 | 2019-09-07 | 2019-11-19 | 2019-11-27 | Overhead | R16 | 2019-11-19 | 0 |  | 52 | 7 | 58 | 2019 | 2019 | R16
168952164746 | 161341164746 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-09-16 | 2019-09-16 | 2019-09-16 |  | 2019-10-04 | Overhead | R16 | 2019-09-19 | 1 |  | 4 | 12 | 15 | 2019 | 2019 | R16
165444161879 | 165467161879 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-15 | 2019-08-15 | 2019-08-21 |  | 2020-10-06 | Underground | R16 |  | 1 | 5 |  |  | 299 | 2019 | 2020 | R16
169334167861 | 166501167861 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-11 | 2019-10-11 | 2019-10-11 |  | 2022-10-19 | Overhead | R16 |  | 1 |  |  |  | 789 | 2019 | 2022 | R16
163504173860 | 166727173860 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-06 | 2019-12-06 | 2019-12-06 | 2020-02-28 | 2020-06-09 | Overhead | R16 | 2020-02-28 | 1 |  | 61 | 73 | 133 | 2019 | 2020 | R16
167505170006 | 169160170006 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-24 | 2019-10-24 | 2019-10-28 |  | 2019-12-17 | Underground | R16 | 2019-12-05 | 1 | 3 | 29 | 9 | 39 | 2019 | 2019 | R16
161443167455 | 165869167455 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-09 | 2019-10-09 | 2019-10-09 | 2020-03-06 | 2020-06-09 | Overhead | R16 | 2020-03-06 | 1 |  | 108 | 68 | 175 | 2019 | 2020 | R16
165386160082 | 163640160082 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-04 | 2019-08-04 | 2019-08-04 | 2019-10-17 | 2019-10-18 | Overhead | R16 | 2019-10-17 | 0 |  | 54 | 2 | 55 | 2019 | 2019 | R16
166882167084 | 163270167084 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-09-26 | 2019-09-27 | 2019-10-05 |  | 2020-06-09 | Underground | R16 |  | 2 | 6 |  |  | 184 | 2019 | 2020 | R16
167045168882 | 167894168882 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-19 | 2019-10-19 | 2019-10-19 |  | 2020-06-09 | Overhead | R16 | 2019-12-19 | 0 |  | 44 | 124 | 167 | 2019 | 2020 | R16
166945164213 | 168029164213 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-29 | 2019-08-29 | 2019-09-12 |  | 2019-10-28 | Underground | R16 | 2019-10-18 | 1 | 11 | 27 | 7 | 43 | 2019 | 2019 | R16
161261161142 | 165332161142 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-13 | 2019-08-13 | 2019-08-13 |  | 2021-07-26 | Overhead | R16 | 2020-10-30 | 1 |  | 319 | 192 | 510 | 2019 | 2021 | R16
161272164244 | 168944164244 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-03 | 2019-09-12 | 2019-09-12 | 2022-04-05 | 2022-09-12 | Overhead | R16 | 2022-04-05 | 8 |  | 669 | 115 | 790 | 2019 | 2022 | R16
169514172001 | 160042172001 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-09 | 2019-09-09 | 2019-11-15 |  | 2022-03-25 | Underground | R16 | 2022-03-25 | 1 | 50 | 616 |  | 665 | 2019 | 2022 | R16
164940161263 | 168407161263 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-08 | 2019-07-08 | 2019-08-14 | 2019-09-04 | 2019-09-05 | Underground | R16 | 2019-09-04 | 1 | 28 | 16 | 2 | 44 | 2019 | 2019 | R16
165808162719 | 166182162719 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-19 | 2019-08-28 | 2019-08-29 |  | 2019-10-16 | Overhead | R16 | 2019-10-16 | 8 | 2 | 35 |  | 43 | 2019 | 2019 | R16
163744166504 | 163756166504 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-09-30 | 2019-10-01 | 2019-10-01 |  | 2020-07-07 | Underground | R16 |  | 2 |  |  |  | 202 | 2019 | 2020 | R16
164103184596 | 168061184596 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-21 | 2019-10-21 | 2020-03-21 |  | 2021-05-07 | Underground | R16 | 2021-02-25 | 1 | 110 | 244 | 52 | 405 | 2019 | 2021 | R16
167877158843 | 167795158843 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-07-02 | 2019-07-02 | 2019-07-24 |  | 2020-07-13 | Underground | R16 |  | 1 | 17 |  |  | 270 | 2019 | 2020 | R16
165128165097 | 161930165097 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-19 | 2019-09-19 | 2019-09-19 |  | 2019-11-06 | Overhead | R16 | 2019-10-28 | 1 |  | 28 | 8 | 35 | 2019 | 2019 | R16
161413173602 | 165978173602 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-12-04 | 2019-12-04 | 2019-12-04 | 2021-02-18 | 2021-02-19 | Overhead | R16 | 2021-02-18 | 1 |  | 317 | 2 | 318 | 2019 | 2021 | R16
163387166542 | 163986166542 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-01 | 2019-10-01 | 2019-10-01 |  | 2020-07-14 | Underground | R16 | 2020-06-18 | 1 |  | 188 | 19 | 206 | 2019 | 2020 | R16
163232162703 | 168175162703 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-29 | 2019-08-29 | 2019-08-29 | 2019-10-01 | 2019-10-02 | Overhead | R16 | 2019-10-01 | 1 |  | 24 | 2 | 25 | 2019 | 2019 | R16
167489163534 | 169640163534 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-06 | 2019-09-06 | 2019-09-06 | 2019-12-03 | 2019-12-05 | Overhead | R16 | 2019-12-03 | 1 |  | 63 | 3 | 65 | 2019 | 2019 | R16
161642216682 | 163277216682 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-11-14 | 2019-11-18 | 2021-01-08 | 2021-08-12 | 2022-02-04 | Underground | R16 | 2021-08-12 | 3 | 300 | 155 | 127 | 582 | 2019 | 2022 | R16
164904169570 | 166750169570 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-14 | 2019-10-24 | 2019-10-24 | 2020-07-09 | 2020-10-06 | Overhead | R16 | 2020-07-09 | 9 |  | 186 | 64 | 257 | 2019 | 2020 | R16
169293181876 | 161469181876 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-06 | 2020-02-26 | 2020-02-26 | 2020-02-28 | 2020-07-02 | Overhead | R16 | 2020-02-28 | 81 |  | 3 | 90 | 172 | 2019 | 2020 | R16
162141172616 | 164608172616 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-22 | 2019-11-22 | 2019-11-22 | 2020-03-03 | 2020-06-09 | Overhead | R16 | 2020-03-03 | 1 |  | 73 | 71 | 143 | 2019 | 2020 | R16
161604162598 | 168215162598 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-29 | 2019-08-29 | 2019-08-29 |  | 2019-11-08 | Overhead | R16 | 2019-10-29 | 1 |  | 44 | 9 | 52 | 2019 | 2019 | R16
169748169900 | 169491169900 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-28 | 2019-10-28 | 2019-10-28 | 2020-01-31 | 2020-02-03 | Overhead | R16 | 2020-01-31 | 1 |  | 70 | 2 | 71 | 2019 | 2020 | R16
168787159586 | 162842159586 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-30 | 2019-07-30 | 2019-07-30 | 2020-01-23 | 2021-11-10 | Overhead | R16 | 2020-01-23 | 1 |  | 128 | 470 | 597 | 2019 | 2021 | R16
162069177306 | 163859177306 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-20 | 2019-11-20 | 2020-01-17 | 2020-03-06 | 2020-06-09 | Underground | R16 | 2020-03-06 | 1 | 43 | 36 | 68 | 145 | 2019 | 2020 | R16
160668175589 | 165423175589 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-07 | 2019-10-07 | 2020-01-02 |  | 2023-06-09 | Underground | R16 |  | 1 | 64 |  |  | 960 | 2019 | 2023 | R16
161492155142 | 163435155142 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-12 | 2019-06-12 | 2019-06-12 | 2019-07-30 | 2019-09-03 | Overhead | R16 | 2019-07-30 | 1 |  | 35 | 26 | 60 | 2019 | 2019 | R16
168340172133 | 162822172133 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-12 | 2019-11-12 | 2019-11-18 |  | 2020-07-09 | Overhead | R16 | 2020-05-28 | 1 | 5 | 139 | 31 | 173 | 2019 | 2020 | R16
166136168486 | 162729168486 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-25 | 2019-09-25 | 2019-10-16 | 2019-12-05 | 2019-12-06 | Overhead | R16 | 2019-12-05 | 1 | 16 | 37 | 2 | 53 | 2019 | 2019 | R16
160290175590 | 160572175590 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-31 | 2019-10-31 | 2020-01-02 |  | 2020-07-10 | Underground | R16 | 2020-06-10 | 1 | 46 | 115 | 23 | 182 | 2019 | 2020 | R16
168085168041 | 160080168041 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-09 | 2019-09-09 | 2019-10-13 |  | 2020-06-09 | Underground | R16 | 2020-04-06 | 1 | 25 | 126 | 47 | 197 | 2019 | 2020 | R16
160537301579 | 162380301579 | INDUSTRIAL | OH R16 RES NON RES OD | Commercial | 2022-01-18 | 2022-03-15 | 2022-11-29 | 2023-11-21 | 2023-12-20 | Overhead | R16 | 2023-11-21 | 41 | 186 | 256 | 22 | 502 | 2022 | 2023 | R16
160887155460 | 164353155460 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-17 | 2019-06-17 | 2019-06-17 | 2019-06-20 | 2019-07-01 | Overhead | R16 | 2019-06-20 | 1 |  | 4 | 8 | 11 | 2019 | 2019 | R16
165159159363 | 160824159363 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-18 | 2019-07-18 | 2019-07-29 |  | 2023-06-02 | Underground | R16 | 2019-10-22 | 1 | 8 | 62 | 944 | 1012 | 2019 | 2023 | R16
160111169339 | 160120169339 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-09 | 2019-09-09 | 2019-10-24 | 2020-10-02 | 2020-10-05 | Underground | R16 | 2020-10-02 | 1 | 34 | 247 | 2 | 281 | 2019 | 2020 | R16
168289163620 | 169693163620 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-06 | 2019-09-06 | 2019-09-06 |  | 2019-10-08 | Overhead | R16 | 2019-09-24 | 1 |  | 13 | 11 | 23 | 2019 | 2019 | R16
167466166223 | 168347166223 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-29 | 2019-08-29 | 2019-09-30 |  | 2019-11-13 | Underground | R16 | 2019-11-04 | 1 | 23 | 26 | 8 | 55 | 2019 | 2019 | R16
162500163967 | 163059163967 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-31 | 2019-07-31 | 2019-09-10 | 2019-10-22 | 2019-10-22 | Underground | R16 | 2019-10-22 | 1 | 30 | 31 |  | 60 | 2019 | 2019 | R16
167705164613 | 161363164613 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-16 | 2019-09-16 | 2019-09-16 |  | 2019-11-21 | Overhead | R16 | 2019-11-15 | 1 |  | 45 | 5 | 49 | 2019 | 2019 | R16
169254161742 | 166334161742 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-20 | 2019-08-20 | 2019-08-20 |  | 2021-12-16 | Overhead | R16 | 2019-09-04 | 1 |  | 12 | 597 | 608 | 2019 | 2021 | R16
162418186565 | 164329186565 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-21 | 2020-04-04 | 2020-04-06 | 2020-05-12 | 2021-04-29 | Overhead | R16 | 2020-05-12 | 97 | 1 | 27 | 253 | 376 | 2019 | 2021 | R16
163277159656 | 163074159656 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-31 | 2019-07-31 | 2019-07-31 | 2019-10-14 | 2019-12-30 | Overhead | R16 | 2019-10-14 | 1 |  | 54 | 56 | 109 | 2019 | 2019 | R16
168732327645 | 163069327645 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-26 | 2023-08-07 | 2023-08-07 | 2023-10-03 | 2023-10-17 | Overhead | R16 | 2023-10-03 | 9 |  | 42 | 11 | 60 | 2023 | 2023 | R16
165095188687 | 167005188687 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Commercial | 2019-12-10 | 2020-04-22 | 2020-04-22 | 2020-09-09 | 2021-03-19 | Underground | R16 | 2020-09-09 | 97 |  | 101 | 138 | 334 | 2019 | 2021 | R16
166711160100 | 163610160100 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-04 | 2019-08-04 | 2019-08-04 | 2019-08-21 | 2019-08-22 | Overhead | R16 | 2019-08-21 | 0 |  | 13 | 2 | 14 | 2019 | 2019 | R16
162426165601 | 161588165601 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-09-18 | 2019-09-18 | 2019-09-23 | 2019-09-24 | 2020-02-06 | Overhead | R16 | 2019-09-24 | 1 | 4 | 2 | 98 | 102 | 2019 | 2020 | R16
164202157068 | 167917157068 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-03 | 2019-07-03 | 2019-07-03 | 2019-08-26 | 2019-09-05 | Overhead | R16 | 2019-08-26 | 1 |  | 39 | 9 | 47 | 2019 | 2019 | R16
162335159550 | 169362159550 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-10 | 2019-07-11 | 2019-07-29 | 2019-11-25 | 2019-11-27 | Underground | R16 | 2019-11-25 | 2 | 13 | 86 | 3 | 101 | 2019 | 2019 | R16
167515164712 | 161425164712 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-17 | 2019-09-17 | 2019-09-17 | 2019-11-19 | 2019-12-03 | Overhead | R16 | 2019-11-19 | 1 |  | 46 | 11 | 56 | 2019 | 2019 | R16
165035165542 | 168103165542 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-28 | 2019-09-23 | 2019-09-23 |  | 2019-11-14 | Overhead | R16 | 2019-11-06 | 19 |  | 33 | 7 | 57 | 2019 | 2019 | R16
160823176404 | 160805176404 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-02 | 2019-11-02 | 2020-01-09 |  | 2022-08-23 | Underground | R16 |  | 0 | 49 |  |  | 732 | 2019 | 2022 | R16
161924164723 | 164459164723 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-08-08 | 2019-08-27 | 2019-09-16 |  | 2020-01-03 | Overhead | R16 |  | 14 | 15 |  |  | 107 | 2019 | 2020 | R16
162782157017 | 167960157017 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-07-02 | 2019-07-06 | 2019-07-06 |  | 2020-07-10 | Overhead | R16 | 2020-06-10 | 4 |  | 243 | 23 | 269 | 2019 | 2020 | R16
168782158970 | 161981158970 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-25 | 2019-07-25 | 2019-07-25 | 2019-09-09 | 2019-09-26 | Overhead | R16 | 2019-09-09 | 1 |  | 33 | 14 | 46 | 2019 | 2019 | R16
163056215562 | 166982215562 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-22 | 2019-09-25 | 2020-12-28 |  | 2023-10-06 | Underground | R16 |  | 25 | 329 |  |  | 1077 | 2019 | 2023 | R16
163541171907 | 163216171907 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-14 | 2019-11-14 | 2019-11-14 |  | 2021-11-13 | Overhead | R16 | 2020-02-20 | 1 |  | 71 | 452 | 522 | 2019 | 2021 | R16
160742167739 | 161626167739 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-17 | 2019-09-17 | 2019-10-11 |  | 2019-11-14 | Underground | R16 | 2019-11-06 | 1 | 19 | 19 | 7 | 43 | 2019 | 2019 | R16
162224160901 | 164940160901 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-12 | 2019-08-12 | 2019-08-12 |  | 2019-12-09 | Overhead | R16 | 2019-12-02 | 1 |  | 81 | 6 | 86 | 2019 | 2019 | R16
161980175614 | 163615175614 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-18 | 2019-11-18 | 2020-01-02 | 2020-04-29 | 2020-04-30 | Underground | R16 | 2020-04-29 | 1 | 34 | 85 | 2 | 119 | 2019 | 2020 | R16
164163170919 | 166537170919 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-08-20 | 2019-08-21 | 2019-11-07 | 2020-12-18 | 2022-01-24 | Underground | R16 | 2020-12-18 | 2 | 57 | 292 | 287 | 635 | 2019 | 2022 | R16
164749174087 | 167029174087 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-10 | 2019-12-10 | 2019-12-10 |  | 2020-06-09 | Overhead | R16 | 2020-02-26 | 1 |  | 57 | 75 | 131 | 2019 | 2020 | R16
162959170621 | 160449170621 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-31 | 2019-10-31 | 2019-11-04 | 2019-12-27 | 2019-12-30 | Overhead | R16 | 2019-12-27 | 1 | 3 | 40 | 2 | 43 | 2019 | 2019 | R16
163794156426 | 166198156426 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-26 | 2019-06-26 | 2019-06-26 |  | 2019-09-03 | Overhead | R16 | 2019-08-01 | 1 |  | 27 | 24 | 50 | 2019 | 2019 | R16
169760171116 | 162220171116 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-08 | 2019-11-08 | 2019-11-08 |  | 2020-01-08 | Overhead | R16 | 2020-01-02 | 1 |  | 40 | 5 | 44 | 2019 | 2020 | R16
162788158967 | 161922158967 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-25 | 2019-07-25 | 2019-07-25 |  | 2019-09-03 | Overhead | R16 | 2019-08-02 | 1 |  | 7 | 23 | 29 | 2019 | 2019 | R16
161963158409 | 160957158409 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-19 | 2019-07-19 | 2019-07-19 | 2019-07-30 | 2019-12-06 | Overhead | R16 | 2019-07-30 | 1 |  | 8 | 94 | 101 | 2019 | 2019 | R16
161506173717 | 162366173717 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-23 | 2019-09-23 | 2019-12-09 | 2020-01-08 | 2020-01-10 | Underground | R16 | 2020-01-08 | 1 | 56 | 23 | 3 | 80 | 2019 | 2020 | R16
166877166812 | 164281166812 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-02 | 2019-10-02 | 2019-10-04 |  | 2020-08-14 | Underground | R16 | 2020-06-22 | 1 | 3 | 187 | 40 | 228 | 2019 | 2020 | R16
166791164285 | 169024164285 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-04 | 2019-09-12 | 2019-09-12 |  | 2019-11-21 | Overhead | R16 | 2019-11-12 | 7 |  | 44 | 8 | 57 | 2019 | 2019 | R16
166918172340 | 166785172340 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-14 | 2019-10-14 | 2019-11-19 | 2020-02-23 | 2020-02-26 | Underground | R16 | 2020-02-23 | 1 | 27 | 69 | 3 | 98 | 2019 | 2020 | R16
166458180247 | 161625180247 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-17 | 2019-09-17 | 2020-02-12 | 2020-05-13 | 2020-05-14 | Underground | R16 | 2020-05-13 | 1 | 107 | 66 | 2 | 173 | 2019 | 2020 | R16
162475182219 | 165711182219 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-02 | 2019-12-02 | 2020-02-28 | 2020-04-22 | 2020-04-24 | Underground | R16 | 2020-04-22 | 1 | 65 | 39 | 3 | 105 | 2019 | 2020 | R16
160582181604 | 160583181604 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-09-11 | 2019-11-25 | 2020-02-24 |  | 2020-11-20 | Underground | R16 | 2020-03-24 | 54 | 66 | 22 | 174 | 313 | 2019 | 2020 | R16
169511173450 | 165785173450 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-03 | 2019-12-03 | 2019-12-03 |  | 2020-06-09 | Overhead | R16 | 2020-04-08 | 1 |  | 92 | 45 | 136 | 2019 | 2020 | R16
165107159756 | 165748159756 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-24 | 2019-06-24 | 2019-08-02 | 2020-05-12 | 2020-03-23 | Underground | R16 | 2020-05-12 | 1 | 30 | 203 |  | 196 | 2019 | 2020 | R16
162382193224 | 165522193224 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-11-27 | 2019-12-23 | 2020-06-04 |  | 2021-04-23 | Underground | R16 |  | 19 | 119 |  |  | 368 | 2019 | 2021 | R16
169491157082 | 164446157082 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-17 | 2019-06-17 | 2019-07-03 |  | 2019-10-11 | Underground | R16 | 2019-10-01 | 1 | 13 | 65 | 9 | 85 | 2019 | 2019 | R16
163287191380 | 163407191380 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Residential Subdivision | 2019-06-11 | 2019-06-12 | 2020-05-18 | 2020-08-19 | 2021-12-09 | Underground | R16 | 2020-08-19 | 2 | 244 | 68 | 342 | 653 | 2019 | 2021 | R16
165449195173 | 163217195173 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OD | Commercial | 2019-11-14 | 2020-04-02 | 2020-06-24 | 2021-02-10 | 2021-05-04 | Overhead | R16 | 2021-02-10 | 101 | 60 | 166 | 60 | 384 | 2019 | 2021 | R16
165860181017 | 168482181017 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-16 | 2019-12-16 | 2020-02-19 | 2020-04-14 | 2020-04-15 | Underground | R16 | 2020-04-14 | 1 | 48 | 40 | 2 | 88 | 2019 | 2020 | R16
169770168973 | 160337168973 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2019-09-11 | 2019-09-11 | 2019-10-21 |  | 2020-10-06 | Underground | R16 |  | 1 | 29 |  |  | 280 | 2019 | 2020 | R16
166383160223 | 163683160223 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-05 | 2019-08-05 | 2019-08-05 |  | 2021-12-16 | Overhead | R16 | 2019-09-04 | 1 |  | 23 | 597 | 619 | 2019 | 2021 | R16
160945165786 | 162924165786 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-25 | 2019-09-25 | 2019-09-25 |  | 2019-12-19 | Overhead | R16 | 2019-12-10 | 1 |  | 55 | 8 | 62 | 2019 | 2019 | R16
160200162341 | 163549162341 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-12 | 2019-06-17 | 2019-08-26 |  | 2019-10-11 | Underground | R16 | 2019-10-01 | 4 | 51 | 27 | 9 | 88 | 2019 | 2019 | R16
165698161658 | 166546161658 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-20 | 2019-08-21 | 2019-08-21 |  | 2019-10-16 | Overhead | R16 | 2019-10-08 | 2 |  | 35 | 7 | 42 | 2019 | 2019 | R16
167324323797 | 167747323797 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-06-27 | 2023-06-30 | 2023-06-30 | 2023-07-10 | 2023-07-28 | Overhead | R16 | 2023-07-10 | 4 |  | 7 | 15 | 24 | 2023 | 2023 | R16
168939168230 | 161210168230 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-16 | 2019-09-19 | 2019-10-15 | 2020-01-02 | 2021-11-13 | Underground | R16 | 2020-01-02 | 4 | 19 | 58 | 487 | 565 | 2019 | 2021 | R16
162872173675 | 162902173675 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-13 | 2019-11-13 | 2019-12-06 |  | 2020-06-09 | Underground | R16 | 2020-02-03 | 1 | 18 | 42 | 92 | 150 | 2019 | 2020 | R16
161852177143 | 162779177143 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-25 | 2019-10-17 | 2020-01-15 | 2020-01-19 | 2020-08-17 | Overhead | R16 | 2020-01-19 | 17 | 65 | 3 | 151 | 234 | 2019 | 2020 | R16
162336158163 | 160033158163 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-15 | 2019-07-15 | 2019-07-17 | 2019-09-09 | 2019-09-24 | Overhead | R16 | 2019-09-09 | 1 | 3 | 39 | 12 | 52 | 2019 | 2019 | R16
164057170073 | 169961170073 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-29 | 2019-10-29 | 2019-10-30 | 2020-01-21 | 2020-01-21 | Overhead | R16 | 2020-01-21 | 1 | 2 | 60 |  | 61 | 2019 | 2020 | R16
169479160296 | 161407160296 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-23 | 2019-07-26 | 2019-08-06 | 2019-08-21 | 2019-08-22 | Underground | R16 | 2019-08-21 | 4 | 8 | 12 | 2 | 23 | 2019 | 2019 | R16
167939156023 | 165428156023 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-21 | 2019-06-21 | 2019-06-21 |  | 2019-08-26 | Underground | R16 | 2019-07-26 | 1 |  | 26 | 22 | 47 | 2019 | 2019 | R16
164983166729 | 164502166729 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-03 | 2019-10-03 | 2019-10-03 | 2019-12-12 | 2019-12-13 | Overhead | R16 | 2019-12-12 | 1 |  | 51 | 2 | 52 | 2019 | 2019 | R16
168739325545 | 160090325545 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-10 | 2023-07-18 | 2023-07-18 | 2023-07-28 | 2023-08-16 | Overhead | R16 | 2023-07-28 | 7 |  | 9 | 14 | 28 | 2023 | 2023 | R16
164395163309 | 169032163309 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-04 | 2019-09-04 | 2019-09-04 | 2019-11-27 | 2019-12-12 | Underground | R16 | 2019-11-27 | 1 |  | 61 | 12 | 72 | 2019 | 2019 | R16
161354177078 | 166742177078 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-13 | 2019-10-13 | 2020-01-17 |  | 2020-07-09 | Underground | R16 | 2020-06-09 | 0 | 70 | 103 | 23 | 194 | 2019 | 2020 | R16
165195166355 | 163925166355 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-01 | 2019-10-01 | 2019-10-01 |  | 2019-10-30 | Overhead | R16 | 2019-10-21 | 1 |  | 15 | 8 | 22 | 2019 | 2019 | R16
164355163171 | 168892163171 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-03 | 2019-09-03 | 2019-09-03 |  | 2020-06-09 | Overhead | R16 | 2020-03-24 | 1 |  | 146 | 56 | 201 | 2019 | 2020 | R16
161061186043 | 163074186043 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-13 | 2019-11-15 | 2020-03-31 |  | 2020-08-20 | Underground | R16 | 2020-06-22 | 3 | 98 | 60 | 44 | 202 | 2019 | 2020 | R16
168997159616 | 163002159616 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-31 | 2019-07-31 | 2019-07-31 |  | 2019-10-28 | Overhead | R16 | 2019-10-18 | 1 |  | 58 | 7 | 64 | 2019 | 2019 | R16
165445164098 | 160794164098 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-12 | 2019-09-12 | 2019-09-12 |  | 2019-10-28 | Overhead | R16 | 2019-10-14 | 1 |  | 23 | 11 | 33 | 2019 | 2019 | R16
162885172895 | 165130172895 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2019-11-25 | 2019-11-25 | 2019-11-25 | 2020-05-13 | 2020-05-20 | Overhead | R16 | 2020-05-13 | 1 |  | 123 | 6 | 128 | 2019 | 2020 | R16
161913168280 | 166796168280 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-14 | 2019-10-14 | 2019-10-14 | 2019-12-26 | 2019-12-30 | Overhead | R16 | 2019-12-26 | 1 |  | 54 | 3 | 56 | 2019 | 2019 | R16
160824264322 | 163471264322 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-08-02 | 2020-01-27 | 2022-01-11 | 2022-05-11 | 2022-06-02 | Underground | R16 | 2022-05-11 | 127 | 512 | 87 | 17 | 740 | 2019 | 2022 | R16
160062165205 | 162110165205 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-20 | 2019-09-20 | 2019-09-20 |  | 2020-01-03 | Underground | R16 | 2019-12-12 | 1 |  | 60 | 17 | 76 | 2019 | 2020 | R16
166249170909 | 166920170909 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-14 | 2019-10-14 | 2019-11-06 | 2020-03-04 | 2020-03-06 | Underground | R16 | 2020-03-04 | 1 | 18 | 86 | 3 | 105 | 2019 | 2020 | R16
161508172291 | 163801172291 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-19 | 2019-11-20 | 2019-11-20 | 2020-02-18 | 2020-02-20 | Underground | R16 | 2020-02-18 | 2 |  | 65 | 3 | 68 | 2019 | 2020 | R16
165318171584 | 168380171584 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-22 | 2019-10-22 | 2019-11-12 | 2019-12-20 | 2020-06-09 | Underground | R16 | 2019-12-20 | 1 | 16 | 29 | 123 | 166 | 2019 | 2020 | R16
161406173114 | 164587173114 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-11-21 | 2019-11-21 | 2019-12-02 | 2019-12-03 | 2020-01-09 | Overhead | R16 | 2019-12-03 | 1 | 8 | 2 | 28 | 36 | 2019 | 2020 | R16
160075166393 | 161690166393 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-18 | 2019-09-18 | 2019-10-01 | 2019-10-02 | 2019-10-30 | Underground | R16 | 2019-10-02 | 1 | 10 | 2 | 21 | 31 | 2019 | 2019 | R16
161055165978 | 163392165978 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-27 | 2019-09-27 | 2019-09-27 |  | 2019-11-21 | Underground | R16 | 2019-11-13 | 1 |  | 34 | 7 | 40 | 2019 | 2019 | R16
167963162581 | 165082162581 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-12 | 2019-08-12 | 2019-08-27 |  | 2021-04-07 | Underground | R16 | 2020-12-01 | 1 | 12 | 331 | 92 | 433 | 2019 | 2021 | R16
165500167212 | 160411167212 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-11 | 2019-09-11 | 2019-10-08 | 2019-11-02 | 2019-11-05 | Underground | R16 | 2019-11-02 | 1 | 20 | 19 | 2 | 40 | 2019 | 2019 | R16
168024190709 | 166418190709 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-08-20 | 2020-02-19 | 2020-05-12 | 2021-05-12 | 2021-06-21 | Underground | R16 | 2021-05-12 | 132 | 60 | 262 | 29 | 480 | 2019 | 2021 | R16
163367161849 | 166641161849 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-21 | 2019-08-21 | 2019-08-21 |  | 2019-11-08 | Overhead | R16 | 2019-10-29 | 1 |  | 50 | 9 | 58 | 2019 | 2019 | R16
165454163276 | 169234163276 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-04 | 2019-09-04 | 2019-09-04 |  | 2021-10-25 | Underground | R16 | 2021-08-31 | 1 |  | 520 | 40 | 559 | 2019 | 2021 | R16
163883173750 | 166692173750 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-09 | 2019-12-09 | 2019-12-09 | 2019-12-09 | 2021-11-10 | Overhead | R16 | 2019-12-09 | 1 |  |  | 503 | 503 | 2019 | 2021 | R16
166001196777 | 164767196777 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-10-04 | 2019-10-04 | 2020-07-09 |  | 2021-07-02 | Underground | R16 | 2020-10-23 | 1 | 200 | 77 | 181 | 456 | 2019 | 2021 | R16
169495165449 | 168093165449 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-08-28 | 2019-08-28 | 2019-09-23 | 2022-04-29 | 2022-02-02 | Underground | R16 | 2022-04-29 | 1 | 19 | 680 |  | 636 | 2019 | 2022 | R16
161218173941 | 164565173941 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-21 | 2019-11-21 | 2019-12-09 |  | 2020-06-09 | Overhead | R16 | 2020-01-28 | 1 | 13 | 37 | 96 | 144 | 2019 | 2020 | R16
163092157378 | 166101157378 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-25 | 2019-06-25 | 2019-07-11 | 2020-02-11 | 2020-06-09 | Underground | R16 | 2020-02-11 | 1 | 13 | 154 | 86 | 251 | 2019 | 2020 | R16
165470160986 | 162772160986 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-30 | 2019-08-01 | 2019-08-12 |  | 2019-08-28 | Underground | R16 | 2019-08-21 | 3 | 8 | 8 | 6 | 22 | 2019 | 2019 | R16
168240163323 | 166045163323 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-08-17 | 2019-08-17 | 2019-09-04 | 2019-09-20 | 2020-02-05 | Underground | R16 | 2019-09-20 | 0 | 13 | 13 | 99 | 123 | 2019 | 2020 | R16
167679166338 | 163903166338 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-01 | 2019-10-01 | 2019-10-01 |  | 2019-11-08 | Overhead | R16 | 2019-11-01 | 1 |  | 24 | 6 | 29 | 2019 | 2019 | R16
160777169916 | 168121169916 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-10-21 | 2019-10-21 | 2019-10-29 |  | 2022-08-29 | Underground | R16 |  | 1 | 7 |  |  | 746 | 2019 | 2022 | R16
160036160743 | 167889160743 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-02 | 2019-07-02 | 2019-08-09 | 2019-09-13 | 2019-09-16 | Underground | R16 | 2019-09-13 | 1 | 29 | 26 | 2 | 55 | 2019 | 2019 | R16
162632177968 | 165912177968 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-03 | 2019-12-23 | 2020-01-24 | 2020-12-08 | 2021-03-27 | Underground | R16 | 2020-12-08 | 15 | 25 | 228 | 79 | 344 | 2019 | 2021 | R16
167780177402 | 161779177402 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-08 | 2019-11-08 | 2020-01-18 |  | 2022-10-19 | Underground | R16 |  | 1 | 51 |  |  | 769 | 2019 | 2022 | R16
162973177469 | 165676177469 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-03 | 2019-12-03 | 2020-01-21 |  | 2020-08-28 | Underground | R16 | 2020-07-07 | 1 | 36 | 121 | 39 | 194 | 2019 | 2020 | R16
168691162021 | 163091162021 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-07-31 | 2019-07-31 | 2019-08-22 |  | 2020-07-08 | Underground | R16 | 2020-05-26 | 1 | 17 | 199 | 32 | 246 | 2019 | 2020 | R16
167977167208 | 168419167208 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-29 | 2019-09-03 | 2019-10-07 | 2019-12-11 | 2019-12-12 | Underground | R16 | 2019-12-11 | 4 | 25 | 48 | 2 | 76 | 2019 | 2019 | R16
165449165549 | 169505165549 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Commercial | 2019-09-06 | 2019-09-06 | 2019-09-24 | 2019-09-26 | 2019-09-29 | Overhead | R16 | 2019-09-26 | 1 | 13 | 3 | 2 | 16 | 2019 | 2019 | R16
164344170407 | 160765170407 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-01 | 2019-11-01 | 2019-11-01 | 2020-01-28 | 2021-11-10 | Overhead | R16 | 2020-01-28 | 1 |  | 63 | 467 | 529 | 2019 | 2021 | R16
165394163158 | 165440163158 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-14 | 2019-08-14 | 2019-09-04 |  | 2022-08-02 | Underground | R16 |  | 1 | 16 |  |  | 775 | 2019 | 2022 | R16
167344156283 | 165885156283 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-06-25 | 2019-06-25 | 2019-06-25 |  | 2020-06-29 | Underground | R16 | 2020-04-24 | 1 |  | 219 | 47 | 265 | 2019 | 2020 | R16
168355163304 | 169061163304 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-03 | 2019-09-03 | 2019-09-03 | 2019-11-25 | 2022-07-19 | Overhead | R16 | 2019-11-25 | 1 |  | 60 | 692 | 751 | 2019 | 2022 | R16
164475169799 | 167856169799 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-07-02 | 2019-07-02 | 2019-10-28 | 2020-06-15 | 2020-08-28 | Underground | R16 | 2020-06-15 | 1 | 85 | 166 | 55 | 304 | 2019 | 2020 | R16
161046162747 | 163642162747 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-05 | 2019-08-29 | 2019-08-29 | 2019-09-09 | 2020-06-09 | Overhead | R16 | 2019-09-09 | 19 |  | 8 | 197 | 222 | 2019 | 2020 | R16
161531162659 | 161492162659 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2019-07-23 | 2019-07-23 | 2019-08-29 | 2020-05-21 | 2020-05-26 | Underground | R16 | 2020-05-21 | 1 | 28 | 191 | 4 | 221 | 2019 | 2020 | R16
169510176873 | 169905176873 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-09 | 2019-09-09 | 2020-01-14 | 2020-04-13 | 2020-04-14 | Underground | R16 | 2020-04-13 | 1 | 92 | 65 | 2 | 157 | 2019 | 2020 | R16
168250177746 | 168067177746 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-22 | 2019-10-22 | 2020-01-22 |  | 2022-11-04 | Underground | R16 | 2022-11-03 | 1 | 67 | 727 | 2 | 794 | 2019 | 2022 | R16
164686160338 | 166560160338 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-27 | 2019-06-27 | 2019-08-07 | 2019-12-19 | 2019-12-20 | Underground | R16 | 2019-12-19 | 1 | 30 | 97 | 2 | 127 | 2019 | 2019 | R16
167810175536 | 163599175536 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-18 | 2019-11-18 | 2020-01-02 |  | 2020-06-09 | Underground | R16 | 2020-01-14 | 1 | 34 | 9 | 106 | 147 | 2019 | 2020 | R16
165757158788 | 169694158788 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-12 | 2019-07-12 | 2019-07-23 |  | 2019-10-04 | Underground | R16 | 2019-09-23 | 1 | 8 | 45 | 10 | 61 | 2019 | 2019 | R16
169818162630 | 163007162630 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-01 | 2019-08-01 | 2019-08-28 |  | 2019-11-13 | Underground | R16 | 2019-11-05 | 1 | 20 | 50 | 7 | 75 | 2019 | 2019 | R16
164326175684 | 169135175684 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-25 | 2019-10-25 | 2020-01-03 |  | 2020-06-09 | Underground | R16 | 2020-02-05 | 1 | 51 | 24 | 90 | 163 | 2019 | 2020 | R16
164483171871 | 163175171871 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-11-14 | 2019-11-14 | 2019-11-14 | 2020-10-16 | 2021-02-16 | Underground | R16 | 2020-10-16 | 1 |  | 242 | 88 | 329 | 2019 | 2021 | R16
164964170218 | 169886170218 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-09 | 2019-09-09 | 2019-10-31 | 2019-11-22 | 2019-11-25 | Underground | R16 | 2019-11-22 | 1 | 39 | 17 | 2 | 56 | 2019 | 2019 | R16
166891175102 | 162884175102 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-13 | 2019-11-13 | 2019-12-20 |  | 2022-10-20 | Underground | R16 |  | 1 | 28 |  |  | 767 | 2019 | 2022 | R16
164966165799 | 163045165799 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-26 | 2019-09-26 | 2019-09-26 | 2019-10-28 | 2019-10-29 | Overhead | R16 | 2019-10-28 | 1 |  | 23 | 2 | 24 | 2019 | 2019 | R16
160519170837 | 163084170837 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-31 | 2019-07-31 | 2019-11-07 |  | 2020-01-08 | Underground | R16 | 2020-01-02 | 1 | 72 | 41 | 5 | 116 | 2019 | 2020 | R16
168674162245 | 163532162245 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-08-02 | 2019-08-26 | 2019-08-26 | 2019-10-23 | 2019-10-24 | Overhead | R16 | 2019-10-23 | 17 |  | 43 | 2 | 60 | 2019 | 2019 | R16
169050156001 | 165502156001 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-21 | 2019-06-21 | 2019-06-21 |  | 2020-06-09 | Underground | R16 | 2020-02-10 | 1 |  | 167 | 87 | 253 | 2019 | 2020 | R16
165528170612 | 161330170612 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-05 | 2019-11-05 | 2019-11-05 |  | 2021-11-10 | Overhead | R16 | 2019-12-19 | 1 |  | 33 | 495 | 527 | 2019 | 2021 | R16
169950157964 | 160049157964 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-15 | 2019-07-15 | 2019-07-15 | 2019-07-17 | 2019-07-17 | Overhead | R16 | 2019-07-17 | 1 |  | 3 |  | 3 | 2019 | 2019 | R16
160159170354 | 160213170354 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-10-30 | 2019-10-30 | 2019-10-31 | 2020-09-22 | 2020-09-29 | Overhead | R16 | 2020-09-22 | 1 | 2 | 234 | 6 | 240 | 2019 | 2020 | R16
163333168942 | 160967168942 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-13 | 2019-10-20 | 2019-10-20 | 2020-01-08 | 2020-01-08 | Overhead | R16 | 2020-01-08 | 26 |  | 58 |  | 84 | 2019 | 2020 | R16
160833168586 | 163301168586 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-26 | 2019-10-08 | 2019-10-17 |  | 2020-06-09 | Overhead | R16 |  | 9 | 8 |  |  | 184 | 2019 | 2020 | R16
161255168602 | 166935168602 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-14 | 2019-10-14 | 2019-10-17 |  | 2019-12-19 | Overhead | R16 | 2019-12-10 | 1 | 4 | 39 | 8 | 49 | 2019 | 2019 | R16
163645174191 | 167984174191 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-12 | 2019-12-12 | 2019-12-12 |  | 2020-07-09 | Overhead | R16 | 2020-06-01 | 1 |  | 123 | 29 | 151 | 2019 | 2020 | R16
168778231701 | 165082231701 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-06-19 | 2019-06-19 | 2021-05-20 | 2021-06-01 | 2021-06-09 | Underground | R16 | 2021-06-01 | 1 | 502 | 9 | 7 | 516 | 2019 | 2021 | R16
163029174792 | 165632174792 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-02 | 2019-12-02 | 2019-12-18 | 2021-06-01 | 2021-06-03 | Overhead | R16 | 2021-06-01 | 1 | 13 | 380 | 3 | 394 | 2019 | 2021 | R16
160405162313 | 167519162313 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-26 | 2019-08-26 | 2019-08-27 | 2019-09-26 | 2019-09-26 | Overhead | R16 | 2019-09-26 | 1 | 2 | 23 |  | 24 | 2019 | 2019 | R16
168580164921 | 161359164921 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-17 | 2019-09-17 | 2019-09-17 | 2019-12-10 | 2021-11-13 | Overhead | R16 | 2019-12-10 | 1 |  | 61 | 504 | 564 | 2019 | 2021 | R16
165381167085 | 162739167085 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential Subdivision | 2019-09-24 | 2019-09-24 | 2019-10-05 |  | 2022-08-29 | Overhead | R16 |  | 1 | 9 |  |  | 765 | 2019 | 2022 | R16
168780161025 | 165079161025 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-08-12 | 2019-08-12 | 2019-08-12 |  | 2020-08-28 | Overhead | R16 | 2020-06-30 | 1 |  | 232 | 44 | 275 | 2019 | 2020 | R16
164513165467 | 167082165467 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-08-23 | 2019-09-23 | 2019-09-23 |  | 2019-11-21 | Overhead | R16 | 2019-11-15 | 22 |  | 40 | 5 | 65 | 2019 | 2019 | R16
168773164186 | 160485164186 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-12 | 2019-09-12 | 2019-09-12 | 2019-09-30 | 2019-10-30 | Overhead | R16 | 2019-09-30 | 1 |  | 13 | 23 | 35 | 2019 | 2019 | R16
169146170066 | 163260170066 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-26 | 2019-09-26 | 2019-10-29 |  | 2020-01-02 | Underground | R16 | 2019-12-11 | 1 | 24 | 32 | 17 | 71 | 2019 | 2020 | R16
168326160706 | 168327160706 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-05 | 2019-07-05 | 2019-08-09 | 2023-01-11 | 2022-11-18 | Underground | R16 | 2023-01-11 | 1 | 26 | 894 |  | 881 | 2019 | 2022 | R16
167497160941 | 161387160941 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-07-23 | 2019-08-09 | 2019-08-12 |  | 2019-09-24 | Underground | R16 |  | 14 | 2 |  |  | 46 | 2019 | 2019 | R16
169616176066 | 161320176066 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-05 | 2020-01-06 | 2020-01-07 | 2020-02-05 | 2023-06-07 | Overhead | R16 | 2020-02-05 | 45 | 2 | 22 | 871 | 937 | 2019 | 2023 | R16
167042163832 | 160230163832 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-10 | 2019-09-10 | 2019-09-10 | 2019-11-15 | 2019-11-26 | Overhead | R16 | 2019-11-15 | 1 |  | 49 | 8 | 56 | 2019 | 2019 | R16
161290172811 | 165100172811 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-25 | 2019-11-25 | 2019-11-25 | 2020-04-27 | 2020-07-07 | Overhead | R16 | 2020-04-27 | 1 |  | 111 | 52 | 162 | 2019 | 2020 | R16
161335171031 | 161852171031 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-07 | 2019-11-07 | 2019-11-07 |  | 2021-11-10 | Overhead | R16 | 2020-01-16 | 1 |  | 51 | 475 | 525 | 2019 | 2021 | R16
168128165063 | 167994165063 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-28 | 2019-08-28 | 2019-09-18 | 2020-02-23 | 2020-03-02 | Underground | R16 | 2020-02-23 | 1 | 16 | 113 | 6 | 134 | 2019 | 2020 | R16
169502158972 | 168051158972 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential Subdivision | 2019-07-03 | 2019-07-03 | 2019-07-25 |  | 2021-11-12 | Underground | R16 | 2020-04-07 | 1 | 17 | 184 | 419 | 618 | 2019 | 2021 | R16
163276156472 | 166262156472 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-26 | 2019-06-26 | 2019-06-26 | 2019-08-12 | 2019-12-06 | Overhead | R16 | 2019-08-12 | 1 |  | 34 | 85 | 118 | 2019 | 2019 | R16
163329168738 | 167714168738 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-18 | 2019-10-18 | 2019-10-18 | 2020-03-03 | 2020-06-09 | Overhead | R16 | 2020-03-03 | 1 |  | 98 | 71 | 168 | 2019 | 2020 | R16
165342174584 | 166145174584 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-04 | 2019-12-16 | 2019-12-16 |  | 2020-09-16 | Overhead | R16 | 2020-07-08 | 9 |  | 148 | 51 | 206 | 2019 | 2020 | R16
160078159071 | 162295159071 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-27 | 2019-07-27 | 2019-07-27 |  | 2020-01-03 | Overhead | R16 | 2019-12-12 | 0 |  | 99 | 17 | 115 | 2019 | 2020 | R16
160419155623 | 164328155623 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-17 | 2019-06-17 | 2019-06-17 | 2019-07-20 | 2019-07-23 | Underground | R16 | 2019-07-20 | 1 |  | 25 | 2 | 27 | 2019 | 2019 | R16
160842173495 | 166207173495 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-04 | 2019-12-04 | 2019-12-04 | 2020-03-03 | 2020-06-09 | Overhead | R16 | 2020-03-03 | 1 |  | 65 | 71 | 135 | 2019 | 2020 | R16
160762176992 | 162804176992 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-12 | 2019-11-13 | 2020-01-14 | 2020-04-03 | 2020-04-20 | Underground | R16 | 2020-04-03 | 2 | 45 | 59 | 12 | 115 | 2019 | 2020 | R16
165190164717 | 169424164717 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-11 | 2019-07-11 | 2019-09-17 | 2019-12-18 | 2019-12-19 | Underground | R16 | 2019-12-18 | 1 | 49 | 67 | 2 | 116 | 2019 | 2019 | R16
168175159432 | 161535159432 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-23 | 2019-07-31 | 2019-07-31 |  | 2019-12-12 | Underground | R16 | 2019-12-03 | 7 |  | 90 | 8 | 103 | 2019 | 2019 | R16
160818160985 | 163890160985 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-05 | 2019-08-05 | 2019-08-12 |  | 2021-11-10 | Underground | R16 | 2021-10-14 | 1 | 6 | 569 | 20 | 593 | 2019 | 2021 | R16
169690163431 | 169544163431 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-05 | 2019-09-05 | 2019-09-05 | 2019-10-25 | 2019-10-31 | Overhead | R16 | 2019-10-25 | 1 |  | 37 | 5 | 41 | 2019 | 2019 | R16
165176161616 | 166208161616 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-08-19 | 2019-08-19 | 2019-08-19 |  | 2021-07-07 | Underground | R16 | 2020-07-15 | 1 |  | 238 | 256 | 493 | 2019 | 2021 | R16
165969170120 | 169874170120 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-29 | 2019-10-29 | 2019-10-29 | 2020-03-10 | 2020-03-11 | Overhead | R16 | 2020-03-10 | 1 |  | 96 | 2 | 97 | 2019 | 2020 | R16
164228176485 | 165021176485 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-10-05 | 2019-10-05 | 2020-01-09 |  | 2020-06-09 | Overhead | R16 |  | 0 | 69 |  |  | 177 | 2019 | 2020 | R16
167956168093 | 167033168093 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-15 | 2019-10-15 | 2019-10-15 |  | 2021-04-15 | Overhead | R16 | 2021-01-12 | 1 |  | 326 | 68 | 393 | 2019 | 2021 | R16
161094160106 | 163825160106 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-05 | 2019-08-05 | 2019-08-05 | 2019-09-05 | 2019-09-18 | Overhead | R16 | 2019-09-05 | 1 |  | 24 | 10 | 33 | 2019 | 2019 | R16
162485156871 | 166131156871 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-26 | 2019-06-26 | 2019-07-03 |  | 2019-12-06 | Underground | R16 | 2019-08-09 | 1 | 6 | 28 | 86 | 118 | 2019 | 2019 | R16
162017177160 | 167970177160 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-20 | 2019-10-20 | 2020-01-15 | 2020-09-24 | 2020-09-25 | Underground | R16 | 2020-09-24 | 0 | 63 | 182 | 2 | 245 | 2019 | 2020 | R16
165961172970 | 168098172970 | RESIDENTIAL - SUBSEQUENT WORK | UG R16 RESD AND NON RESD UD | Residential | 2019-08-29 | 2019-08-30 | 2019-11-26 | 2020-02-14 | 2020-06-18 | Underground | R16 | 2020-02-14 | 2 | 63 | 59 | 90 | 211 | 2019 | 2020 | R16
162257176394 | 162320176394 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-07-26 | 2019-07-30 | 2020-01-09 | 2021-01-13 | 2021-01-29 | Underground | R16 | 2021-01-13 | 3 | 118 | 265 | 13 | 396 | 2019 | 2021 | R16
163566161203 | 165557161203 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-14 | 2019-08-14 | 2019-08-14 |  | 2019-12-12 | Overhead | R16 | 2019-12-03 | 1 |  | 80 | 8 | 87 | 2019 | 2019 | R16
161287172303 | 163820172303 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-19 | 2019-11-19 | 2019-11-19 | 2020-02-11 | 2020-02-12 | Overhead | R16 | 2020-02-11 | 1 |  | 61 | 2 | 62 | 2019 | 2020 | R16
161247162501 | 167598162501 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-26 | 2019-08-26 | 2019-08-27 | 2019-08-28 | 2019-10-08 | Overhead | R16 | 2019-08-28 | 1 | 2 | 2 | 30 | 32 | 2019 | 2019 | R16
169346192580 | 167301192580 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-10-16 | 2019-12-19 | 2020-05-28 | 2020-07-23 | 2020-09-23 | Overhead | R16 | 2020-07-23 | 47 | 116 | 41 | 45 | 246 | 2019 | 2020 | R16
168089176450 | 168220176450 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-12-13 | 2019-12-13 | 2020-01-10 | 2020-10-21 | 2021-07-07 | Underground | R16 | 2020-10-21 | 1 | 21 | 204 | 186 | 409 | 2019 | 2021 | R16
160583162644 | 168039162644 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-08-28 | 2019-08-28 | 2019-08-28 |  | 2020-06-09 | Overhead | R16 | 2020-02-28 | 1 |  | 133 | 73 | 205 | 2019 | 2020 | R16
169759174096 | 161292174096 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-05 | 2019-11-06 | 2019-12-11 | 2020-02-12 | 2020-02-13 | Underground | R16 | 2020-02-12 | 2 | 26 | 46 | 2 | 73 | 2019 | 2020 | R16
168511166882 | 164352166882 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2019-10-02 | 2019-10-03 | 2019-10-04 | 2020-10-01 | 2021-01-02 | Overhead | R16 | 2020-10-01 | 2 | 2 | 260 | 67 | 328 | 2019 | 2021 | R16
166619164245 | 160753164245 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-12 | 2019-09-12 | 2019-09-12 | 2019-11-27 | 2019-12-16 | Overhead | R16 | 2019-11-27 | 1 |  | 55 | 14 | 68 | 2019 | 2019 | R16
169948208796 | 166413208796 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-10-11 | 2019-10-11 | 2020-10-29 | 2020-12-17 | 2021-02-04 | Underground | R16 | 2020-12-17 | 1 | 275 | 36 | 36 | 345 | 2019 | 2021 | R16
162871194646 | 168775194646 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-08 | 2019-07-08 | 2020-06-17 | 2020-11-20 | 2020-12-17 | Underground | R16 | 2020-11-20 | 1 | 248 | 113 | 20 | 379 | 2019 | 2020 | R16
167947162620 | 164926162620 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-12 | 2019-08-12 | 2019-08-27 | 2019-08-29 | 2019-11-08 | Underground | R16 | 2019-08-29 | 1 | 12 | 3 | 52 | 65 | 2019 | 2019 | R16
166025159895 | 163483159895 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-02 | 2019-08-02 | 2019-08-02 | 2019-09-04 | 2019-09-05 | Overhead | R16 | 2019-09-04 | 1 |  | 24 | 2 | 25 | 2019 | 2019 | R16
169234159321 | 162400159321 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-29 | 2019-07-29 | 2019-07-29 | 2019-08-05 | 2019-08-05 | Overhead | R16 | 2019-08-05 | 1 |  | 6 |  | 6 | 2019 | 2019 | R16
167041164922 | 161453164922 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-17 | 2019-09-17 | 2019-09-17 | 2019-09-20 | 2019-12-03 | Overhead | R16 | 2019-09-20 | 1 |  | 4 | 53 | 56 | 2019 | 2019 | R16
165521157613 | 169412157613 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-11 | 2019-07-11 | 2019-07-11 |  | 2019-10-16 | Overhead | R16 | 2019-10-07 | 1 |  | 63 | 8 | 70 | 2019 | 2019 | R16
168773197453 | 169685197453 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-07-12 | 2019-07-12 | 2020-07-15 |  | 2021-07-26 | Underground | R16 | 2020-10-30 | 1 | 264 | 78 | 192 | 532 | 2019 | 2021 | R16
160593224218 | 164930224218 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-10-04 | 2019-11-06 | 2021-03-22 |  | 2023-01-05 | Underground | R16 |  | 24 | 359 |  |  | 850 | 2019 | 2023 | R16
162622161028 | 165133161028 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-12 | 2019-08-12 | 2019-08-12 |  | 2020-06-09 | Overhead | R16 | 2020-04-08 | 1 |  | 173 | 45 | 217 | 2019 | 2020 | R16
165796178583 | 165840178583 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-09 | 2019-10-19 | 2020-01-29 | 2020-11-25 | 2021-02-27 | Underground | R16 | 2020-11-25 | 8 | 73 | 216 | 68 | 363 | 2019 | 2021 | R16
164830173138 | 162973173138 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE FOR UPGRADE UD | Commercial | 2019-07-31 | 2019-10-29 | 2019-12-02 | 2020-06-23 | 2020-11-19 | Underground | R16 | 2020-06-23 | 65 | 25 | 147 | 108 | 342 | 2019 | 2020 | R16
169918174036 | 165662174036 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-02 | 2019-12-02 | 2019-12-10 |  | 2020-06-09 | Overhead | R16 | 2020-02-25 | 1 | 7 | 56 | 76 | 137 | 2019 | 2020 | R16
160540170351 | 160498170351 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-31 | 2019-10-31 | 2019-10-31 | 2020-01-20 | 2020-02-24 | Overhead | R16 | 2020-01-20 | 1 |  | 58 | 26 | 83 | 2019 | 2020 | R16
161414170258 | 160650170258 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-31 | 2019-10-31 | 2019-10-31 | 2020-01-29 | 2020-01-30 | Overhead | R16 | 2020-01-29 | 1 |  | 65 | 2 | 66 | 2019 | 2020 | R16
160171168071 | 168033168071 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-07-03 | 2019-08-21 | 2019-10-14 |  | 2020-07-09 | Underground | R16 |  | 36 | 39 |  |  | 267 | 2019 | 2020 | R16
165417163375 | 169801163375 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-06 | 2019-09-06 | 2019-09-06 |  | 2019-12-06 | Overhead | R16 | 2019-10-22 | 1 |  | 33 | 34 | 66 | 2019 | 2019 | R16
162736180390 | 167161180390 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-10-15 | 2019-10-15 | 2020-02-13 |  | 2020-06-09 | Overhead | R16 | 2020-03-02 | 1 | 88 | 13 | 72 | 171 | 2019 | 2020 | R16
162171169274 | 168959169274 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-24 | 2019-10-24 | 2019-10-24 | 2020-02-12 | 2020-06-09 | Overhead | R16 | 2020-02-12 | 1 |  | 80 | 85 | 164 | 2019 | 2020 | R16
163173170450 | 163798170450 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-30 | 2019-09-30 | 2019-11-01 |  | 2021-11-10 | Underground | R16 | 2020-01-23 | 1 | 25 | 60 | 470 | 553 | 2019 | 2021 | R16
161579164879 | 161435164879 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2019-09-17 | 2019-09-17 | 2019-09-19 |  | 2019-10-28 | Overhead | R16 |  | 1 | 3 |  |  | 30 | 2019 | 2019 | R16
165562171337 | 167062171337 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-15 | 2019-10-15 | 2019-11-11 | 2019-12-19 | 2019-12-20 | Underground | R16 | 2019-12-19 | 1 | 20 | 29 | 2 | 49 | 2019 | 2019 | R16
160780164857 | 161586164857 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-18 | 2019-09-18 | 2019-09-18 | 2019-10-22 | 2019-10-23 | Overhead | R16 | 2019-10-22 | 1 |  | 25 | 2 | 26 | 2019 | 2019 | R16
164622160666 | 161929160666 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2019-07-25 | 2019-07-25 | 2019-08-09 |  | 2019-10-30 | Underground | R16 |  | 1 | 12 |  |  | 70 | 2019 | 2019 | R16
162236158502 | 160989158502 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-20 | 2019-07-20 | 2019-07-20 | 2019-09-03 | 2019-09-04 | Overhead | R16 | 2019-09-03 | 0 |  | 32 | 2 | 33 | 2019 | 2019 | R16
169423170717 | 161365170717 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-05 | 2019-11-05 | 2019-11-05 |  | 2022-10-21 | Underground | R16 | 2022-09-01 | 1 |  | 738 | 37 | 774 | 2019 | 2022 | R16
167347171359 | 162356171359 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-11 | 2019-11-11 | 2019-11-11 | 2020-01-16 | 2021-11-10 | Overhead | R16 | 2020-01-16 | 1 |  | 49 | 475 | 523 | 2019 | 2021 | R16
165589156028 | 165577156028 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-22 | 2019-06-22 | 2019-06-22 | 2019-07-05 | 2019-07-09 | Underground | R16 | 2019-07-05 | 0 |  | 10 | 3 | 12 | 2019 | 2019 | R16
164385164304 | 160825164304 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-13 | 2019-09-13 | 2019-09-13 | 2019-10-09 | 2019-10-10 | Overhead | R16 | 2019-10-09 | 1 |  | 19 | 2 | 20 | 2019 | 2019 | R16
166174171374 | 162462171374 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-11 | 2019-11-11 | 2019-11-11 | 2020-02-07 | 2020-02-10 | Overhead | R16 | 2020-02-07 | 1 |  | 65 | 2 | 66 | 2019 | 2020 | R16
164316170010 | 164396170010 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-03 | 2019-10-03 | 2019-10-28 | 2019-12-27 | 2019-12-30 | Underground | R16 | 2019-12-27 | 1 | 18 | 45 | 2 | 63 | 2019 | 2019 | R16
163460157597 | 169696157597 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-12 | 2019-07-12 | 2019-07-12 | 2019-08-01 | 2019-12-06 | Overhead | R16 | 2019-08-01 | 1 |  | 15 | 92 | 106 | 2019 | 2019 | R16
167850164163 | 160542164163 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-11 | 2019-09-11 | 2019-09-11 | 2019-10-15 | 2019-10-16 | Overhead | R16 | 2019-10-15 | 1 |  | 25 | 2 | 26 | 2019 | 2019 | R16
163131176256 | 165111176256 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-07 | 2019-10-07 | 2020-01-08 | 2020-01-28 | 2020-01-29 | Underground | R16 | 2020-01-28 | 1 | 68 | 15 | 2 | 83 | 2019 | 2020 | R16
166327183923 | 167119183923 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-11 | 2020-03-12 | 2020-03-12 | 2020-04-10 | 2020-05-26 | Overhead | R16 | 2020-04-10 | 67 |  | 22 | 33 | 120 | 2019 | 2020 | R16
162065169853 | 169259169853 | Fleet Chargers | R16 RESD AND NON RESD US | Commercial | 2019-09-04 | 2019-10-10 | 2019-10-28 |  | 2020-10-06 | Underground | R16 |  | 27 | 13 |  |  | 285 | 2019 | 2020 | R16
167786160487 | 161210160487 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-22 | 2019-07-22 | 2019-08-07 | 2019-11-04 | 2019-11-05 | Underground | R16 | 2019-11-04 | 1 | 13 | 64 | 2 | 77 | 2019 | 2019 | R16
169728166557 | 169899166557 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-09 | 2019-09-09 | 2019-10-03 |  | 2021-08-26 | Underground | R16 | 2021-06-07 | 1 | 19 | 438 | 59 | 514 | 2019 | 2021 | R16
167436164167 | 160852164167 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-09-12 | 2019-09-12 | 2019-09-12 |  | 2019-09-26 | Overhead | R16 | 2019-09-18 | 1 |  | 5 | 7 | 11 | 2019 | 2019 | R16
161511170879 | 163444170879 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-02 | 2019-10-07 | 2019-11-06 |  | 2022-08-29 | Overhead | R16 |  | 47 | 23 |  |  | 802 | 2019 | 2022 | R16
161904172619 | 164824172619 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-22 | 2019-11-22 | 2019-11-22 | 2020-03-24 | 2020-06-09 | Overhead | R16 | 2020-03-24 | 1 |  | 88 | 56 | 143 | 2019 | 2020 | R16
160349212377 | 167737212377 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-10-19 | 2019-10-19 | 2020-12-02 | 2023-09-28 | 2023-10-20 | Underground | R16 | 2023-09-28 | 0 | 293 | 737 | 17 | 1045 | 2019 | 2023 | R16
167129186184 | 166852186184 | NON-RESIDENTIAL - MISCELLANEOUS | UG ELEC MISC SVC US | Commercial | 2019-12-09 | 2019-12-09 | 2020-04-02 |  | 2021-01-21 | Underground | R16 |  | 1 | 84 |  |  | 294 | 2019 | 2021 | R16
166283171398 | 162482171398 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2019-11-11 | 2019-11-11 | 2019-11-11 | 2020-04-24 | 2020-07-02 | Overhead | R16 | 2020-04-24 | 1 |  | 120 | 50 | 169 | 2019 | 2020 | R16
161866166759 | 164364166759 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-02 | 2019-10-02 | 2019-10-02 |  | 2019-10-30 | Overhead | R16 | 2019-10-24 | 1 |  | 17 | 5 | 21 | 2019 | 2019 | R16
165718164002 | 169895164002 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-09 | 2019-09-09 | 2019-09-10 |  | 2019-11-08 | Underground | R16 | 2019-10-29 | 1 | 2 | 36 | 9 | 45 | 2019 | 2019 | R16
162240173651 | 165565173651 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-02 | 2019-12-02 | 2019-12-05 |  | 2021-11-10 | Underground | R16 | 2020-01-22 | 1 | 4 | 35 | 471 | 508 | 2019 | 2021 | R16
165598167737 | 166500167737 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-11 | 2019-10-11 | 2019-10-11 | 2019-11-04 | 2019-11-04 | Overhead | R16 | 2019-11-04 | 1 |  | 17 |  | 17 | 2019 | 2019 | R16
163175158977 | 166524158977 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-27 | 2019-06-27 | 2019-07-25 |  | 2019-11-14 | Overhead | R16 | 2019-11-07 | 1 | 21 | 76 | 6 | 101 | 2019 | 2019 | R16
169358156979 | 164176156979 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-15 | 2019-06-15 | 2019-07-03 | 2019-07-23 | 2019-07-26 | Underground | R16 | 2019-07-23 | 0 | 13 | 15 | 4 | 30 | 2019 | 2019 | R16
163529172975 | 165323172975 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-11-26 | 2019-11-26 | 2019-11-26 | 2020-03-02 | 2020-03-05 | Underground | R16 | 2020-03-02 | 1 |  | 70 | 4 | 73 | 2019 | 2020 | R16
166886173455 | 166809173455 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-14 | 2019-10-14 | 2019-12-03 |  | 2020-06-09 | Underground | R16 | 2019-12-19 | 1 | 37 | 13 | 124 | 172 | 2019 | 2020 | R16
163952169171 | 168143169171 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-21 | 2019-10-21 | 2019-10-21 | 2019-12-13 | 2019-12-17 | Overhead | R16 | 2019-12-13 | 1 |  | 40 | 3 | 42 | 2019 | 2019 | R16
166455164768 | 166562164768 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-08-20 | 2019-08-20 | 2019-09-16 | 2020-12-18 | 2021-04-21 | Underground | R16 | 2020-12-18 | 1 | 20 | 330 | 89 | 437 | 2019 | 2021 | R16
164643165462 | 162390165462 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-23 | 2019-09-23 | 2019-09-23 | 2019-10-23 | 2019-10-24 | Overhead | R16 | 2019-10-23 | 1 |  | 23 | 2 | 24 | 2019 | 2019 | R16
168115172345 | 163831172345 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-19 | 2019-11-19 | 2019-11-19 |  | 2021-11-10 | Overhead | R16 | 2020-01-29 | 1 |  | 52 | 466 | 517 | 2019 | 2021 | R16
162072170223 | 160158170223 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-30 | 2019-10-30 | 2019-10-30 | 2019-12-18 | 2019-12-19 | Overhead | R16 | 2019-12-18 | 1 |  | 36 | 2 | 37 | 2019 | 2019 | R16
163229156353 | 166214156353 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-26 | 2019-06-26 | 2019-06-26 |  | 2021-11-17 | Overhead | R16 | 2019-09-16 | 1 |  | 59 | 568 | 626 | 2019 | 2021 | R16
165050156572 | 165301156572 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-20 | 2019-06-20 | 2019-06-28 |  | 2019-08-26 | Underground | R16 | 2019-07-19 | 1 | 7 | 16 | 27 | 48 | 2019 | 2019 | R16
160661166231 | 163739166231 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-30 | 2019-09-30 | 2019-09-30 |  | 2019-10-30 | Overhead | R16 | 2019-10-23 | 1 |  | 18 | 6 | 23 | 2019 | 2019 | R16
161112156755 | 167760156755 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-02 | 2019-07-02 | 2019-07-02 | 2019-07-09 | 2019-07-24 | Overhead | R16 | 2019-07-09 | 1 |  | 6 | 12 | 17 | 2019 | 2019 | R16
163728167406 | 165591167406 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-08 | 2019-10-08 | 2019-10-08 |  | 2020-11-02 | Overhead | R16 | 2020-09-04 | 1 |  | 239 | 42 | 280 | 2019 | 2020 | R16
168029172510 | 161513172510 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-23 | 2019-07-23 | 2019-11-21 | 2020-02-10 | 2020-03-11 | Underground | R16 | 2020-02-10 | 1 | 88 | 58 | 23 | 167 | 2019 | 2020 | R16
169993167188 | 164060167188 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-01 | 2019-10-01 | 2019-10-07 |  | 2020-06-09 | Underground | R16 | 2020-03-06 | 1 | 5 | 110 | 68 | 181 | 2019 | 2020 | R16
164121174072 | 161662174072 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH CP R16 WORK RELO TO UG | Commercial | 2019-07-23 | 2019-07-23 | 2019-12-11 | 2020-01-25 | 2020-05-27 | Overhead | R16 | 2020-01-25 | 1 | 102 | 33 | 88 | 222 | 2019 | 2020 | R16
168932168108 | 166771168108 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-14 | 2019-10-14 | 2019-10-14 |  | 2020-06-09 | Overhead | R16 | 2020-03-25 | 1 |  | 118 | 55 | 172 | 2019 | 2020 | R16
167339165516 | 169880165516 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-09 | 2019-09-24 | 2019-09-24 | 2019-12-06 | 2019-12-17 | Overhead | R16 | 2019-12-06 | 12 |  | 54 | 8 | 72 | 2019 | 2019 | R16
166437159048 | 161029159048 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-19 | 2019-07-19 | 2019-07-25 | 2019-08-27 | 2019-09-04 | Underground | R16 | 2019-08-27 | 1 | 5 | 24 | 7 | 34 | 2019 | 2019 | R16
160260154915 | 163313154915 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-11 | 2019-06-11 | 2019-06-11 |  | 2019-08-26 | Overhead | R16 | 2019-07-19 | 1 |  | 29 | 27 | 55 | 2019 | 2019 | R16
162510169569 | 169200169569 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-24 | 2019-10-24 | 2019-10-24 | 2019-11-26 | 2022-10-20 | Overhead | R16 | 2019-11-26 | 1 |  | 24 | 758 | 781 | 2019 | 2022 | R16
161164166867 | 164270166867 | RESIDENTIAL - MULTI-FAMILY | R16 ELEC DEVELOPMENT | Residential Subdivision | 2019-10-02 | 2019-10-02 | 2019-10-04 |  | 2021-12-02 | Underground | R16 |  | 1 | 3 |  |  | 567 | 2019 | 2021 | R16
161326155566 | 164308155566 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-17 | 2019-06-17 | 2019-06-17 |  | 2019-10-16 | Overhead | R16 | 2019-10-08 | 1 |  | 82 | 7 | 88 | 2019 | 2019 | R16
169763176674 | 161113176674 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-11-04 | 2020-01-14 | 2020-01-14 |  | 2021-11-03 | Underground | R16 | 2021-06-23 | 52 |  | 377 | 96 | 523 | 2019 | 2021 | R16
164791163359 | 169313163359 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-05 | 2019-09-05 | 2019-09-05 |  | 2019-10-30 | Overhead | R16 | 2019-10-23 | 1 |  | 35 | 6 | 40 | 2019 | 2019 | R16
166219173998 | 167314173998 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-10 | 2019-12-10 | 2019-12-10 | 2020-01-07 | 2020-06-09 | Overhead | R16 | 2020-01-07 | 1 |  | 21 | 111 | 131 | 2019 | 2020 | R16
169770171606 | 162014171606 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-08 | 2019-11-12 | 2019-11-12 | 2020-01-29 | 2021-11-13 | Underground | R16 | 2020-01-29 | 3 |  | 57 | 468 | 526 | 2019 | 2021 | R16
164749172032 | 166953172032 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-14 | 2019-10-14 | 2019-11-18 | 2020-08-19 | 2020-12-18 | Underground | R16 | 2020-08-19 | 1 | 26 | 198 | 88 | 310 | 2019 | 2020 | R16
163892156423 | 166130156423 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-25 | 2019-06-25 | 2019-06-25 | 2019-08-12 | 2019-12-06 | Overhead | R16 | 2019-08-12 | 1 |  | 35 | 85 | 119 | 2019 | 2019 | R16
160110160120 | 163346160120 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-02 | 2019-08-02 | 2019-08-05 |  | 2019-10-16 | Underground | R16 | 2019-10-07 | 1 | 2 | 46 | 8 | 54 | 2019 | 2019 | R16
164883206944 | 166996206944 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2019-12-09 | 2020-02-24 | 2020-10-12 | 2021-06-16 | 2021-07-13 | Underground | R16 | 2021-06-16 | 56 | 166 | 178 | 20 | 417 | 2019 | 2021 | R16
169032164958 | 169464164958 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-05 | 2019-09-05 | 2019-09-20 | 2020-05-07 | 2020-05-08 | Underground | R16 | 2020-05-07 | 1 | 12 | 165 | 2 | 177 | 2019 | 2020 | R16
168715161607 | 169887161607 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-15 | 2019-07-15 | 2019-08-19 | 2019-09-25 | 2019-09-27 | Underground | R16 | 2019-09-25 | 1 | 26 | 28 | 3 | 55 | 2019 | 2019 | R16
165873170292 | 167116170292 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-16 | 2019-10-31 | 2019-10-31 | 2020-01-21 | 2021-11-10 | Overhead | R16 | 2020-01-21 | 12 |  | 59 | 472 | 541 | 2019 | 2021 | R16
163467172468 | 164088172468 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-20 | 2019-11-20 | 2019-11-20 | 2020-01-30 | 2020-02-03 | Overhead | R16 | 2020-01-30 | 1 |  | 52 | 3 | 54 | 2019 | 2020 | R16
160392171011 | 161733171011 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-11-07 | 2019-11-07 | 2019-11-07 |  | 2021-10-11 | Underground | R16 |  | 1 |  |  |  | 503 | 2019 | 2021 | R16
162062175465 | 168783175465 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2019-12-16 | 2019-12-16 | 2019-12-31 |  | 2020-08-28 | Underground | R16 | 2020-07-01 | 1 | 12 | 132 | 43 | 185 | 2019 | 2020 | R16
167634174019 | 167256174019 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-12-11 | 2019-12-11 | 2019-12-11 | 2019-12-24 | 2019-12-27 | Overhead | R16 | 2019-12-24 | 1 |  | 10 | 4 | 13 | 2019 | 2019 | R16
161967158192 | 160773158192 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-18 | 2019-07-18 | 2019-07-18 |  | 2019-11-08 | Overhead | R16 | 2019-11-01 | 1 |  | 77 | 6 | 82 | 2019 | 2019 | R16
169878185998 | 164289185998 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | UG R16 RESD AND NON RESD UD | Commercial | 2019-08-07 | 2020-01-24 | 2020-04-01 | 2020-10-29 | 2022-10-29 | Underground | R16 | 2020-10-29 | 123 | 49 | 152 | 522 | 843 | 2019 | 2022 | R16
168593170815 | 161306170815 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-06 | 2019-11-06 | 2019-11-06 | 2020-01-23 | 2021-11-10 | Overhead | R16 | 2020-01-23 | 1 |  | 57 | 470 | 526 | 2019 | 2021 | R16
165758164152 | 166266164152 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-19 | 2019-08-19 | 2019-09-12 | 2019-11-21 | 2019-11-22 | Underground | R16 | 2019-11-21 | 1 | 19 | 51 | 2 | 70 | 2019 | 2019 | R16
167064172577 | 164296172577 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-21 | 2019-11-21 | 2019-11-21 |  | 2022-07-19 | Overhead | R16 |  | 1 |  |  |  | 694 | 2019 | 2022 | R16
162229158365 | 160673158365 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-18 | 2019-07-18 | 2019-07-18 | 2019-10-01 | 2019-10-16 | Overhead | R16 | 2019-10-01 | 1 |  | 54 | 12 | 65 | 2019 | 2019 | R16
166447156493 | 166582156493 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-27 | 2019-06-27 | 2019-06-27 | 2019-08-22 | 2019-08-28 | Overhead | R16 | 2019-08-22 | 1 |  | 41 | 5 | 45 | 2019 | 2019 | R16
164354158581 | 161243158581 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-22 | 2019-07-22 | 2019-07-22 |  | 2019-10-28 | Underground | R16 | 2019-10-17 | 1 |  | 64 | 8 | 71 | 2019 | 2019 | R16
167097168609 | 167372168609 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-26 | 2019-08-27 | 2019-10-17 |  | 2020-06-09 | Overhead | R16 |  | 2 | 38 |  |  | 207 | 2019 | 2020 | R16
169342171023 | 168875171023 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | R16 RESD AND NON RESD US | Commercial | 2019-09-03 | 2019-10-22 | 2019-11-07 | 2020-06-09 | 2020-06-12 | Underground | R16 | 2020-06-09 | 36 | 13 | 154 | 4 | 204 | 2019 | 2020 | R16
162975175545 | 160997175545 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-11-04 | 2019-11-04 | 2019-12-31 | 2020-02-10 | 2020-11-10 | Underground | R16 | 2020-02-10 | 1 | 42 | 30 | 197 | 267 | 2019 | 2020 | R16
165295175475 | 167177175475 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-12-10 | 2019-12-13 | 2020-01-03 |  | 2020-06-23 | Overhead | R16 |  | 4 | 16 |  |  | 141 | 2019 | 2020 | R16
164836163949 | 160131163949 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-10 | 2019-09-10 | 2019-09-10 |  | 2019-11-13 | Overhead | R16 | 2019-11-13 | 1 |  | 47 |  | 47 | 2019 | 2019 | R16
165984161928 | 166483161928 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential Subdivision | 2019-06-27 | 2019-07-12 | 2019-08-22 |  | 2021-02-25 | Underground | R16 |  | 12 | 30 |  |  | 436 | 2019 | 2021 | R16
164921212839 | 165576212839 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-06-22 | 2019-06-22 | 2020-12-07 |  | 2021-04-21 | Underground | R16 |  | 0 | 381 |  |  | 478 | 2019 | 2021 | R16
163467155519 | 164871155519 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-18 | 2019-06-18 | 2019-06-18 | 2019-07-11 | 2019-07-12 | Overhead | R16 | 2019-07-11 | 1 |  | 18 | 2 | 19 | 2019 | 2019 | R16
160185173381 | 161141173381 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-16 | 2019-09-16 | 2019-12-02 |  | 2020-06-09 | Underground | R16 | 2020-01-07 | 1 | 56 | 27 | 111 | 192 | 2019 | 2020 | R16
165814158541 | 169143158541 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-10 | 2019-07-21 | 2019-07-21 |  | 2019-10-28 | Overhead | R16 | 2019-10-17 | 8 |  | 64 | 8 | 79 | 2019 | 2019 | R16
163809173434 | 164837173434 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-24 | 2019-12-03 | 2019-12-03 | 2020-03-06 | 2020-05-05 | Overhead | R16 | 2020-03-06 | 7 |  | 69 | 43 | 117 | 2019 | 2020 | R16
161212172288 | 163583172288 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-18 | 2019-11-18 | 2019-11-20 |  | 2021-11-13 | Underground | R16 | 2020-01-14 | 1 | 3 | 40 | 479 | 520 | 2019 | 2021 | R16
167419158542 | 161130158542 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-21 | 2019-07-21 | 2019-07-21 |  | 2019-10-11 | Overhead | R16 | 2019-10-01 | 0 |  | 52 | 9 | 60 | 2019 | 2019 | R16
161830172292 | 163496172292 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-18 | 2019-11-18 | 2019-11-20 |  | 2020-01-08 | Underground | R16 | 2020-01-03 | 1 | 3 | 33 | 4 | 38 | 2019 | 2020 | R16
165627159462 | 160624159462 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-17 | 2019-07-19 | 2019-07-29 |  | 2019-09-19 | Overhead | R16 |  | 3 | 7 |  |  | 47 | 2019 | 2019 | R16
162982168042 | 162947168042 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-25 | 2019-09-25 | 2019-10-13 |  | 2021-10-25 | Underground | R16 | 2021-09-17 | 1 | 13 | 505 | 27 | 544 | 2019 | 2021 | R16
167807171731 | 163071171731 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-13 | 2019-11-13 | 2019-11-13 |  | 2020-01-03 | Overhead | R16 | 2019-12-12 | 1 |  | 22 | 17 | 38 | 2019 | 2020 | R16
164058169883 | 165142169883 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-07 | 2019-10-07 | 2019-10-28 | 2020-01-15 | 2020-01-16 | Underground | R16 | 2020-01-15 | 1 | 16 | 58 | 2 | 74 | 2019 | 2020 | R16
161973162889 | 168604162889 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-30 | 2019-08-30 | 2019-08-30 | 2019-10-01 | 2019-10-02 | Overhead | R16 | 2019-10-01 | 1 |  | 23 | 2 | 24 | 2019 | 2019 | R16
167789162677 | 168247162677 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-29 | 2019-08-29 | 2019-08-29 |  | 2022-01-11 | Overhead | R16 | 2021-12-03 | 1 |  | 592 | 28 | 619 | 2019 | 2022 | R16
163963178545 | 164051178545 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-08-06 | 2019-08-06 | 2020-01-29 | 2020-07-29 | 2021-03-16 | Underground | R16 | 2020-07-29 | 1 | 127 | 131 | 165 | 421 | 2019 | 2021 | R16
164886163968 | 168772163968 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-08 | 2019-07-08 | 2019-09-10 | 2019-10-11 | 2019-10-16 | Overhead | R16 | 2019-10-11 | 1 | 47 | 24 | 4 | 73 | 2019 | 2019 | R16
162304158576 | 161169158576 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-22 | 2019-07-22 | 2019-07-22 | 2019-08-07 | 2019-08-09 | Overhead | R16 | 2019-08-07 | 1 |  | 13 | 3 | 15 | 2019 | 2019 | R16
161406182285 | 163125182285 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2019-11-14 | 2020-02-05 | 2020-02-28 |  | 2020-06-23 | Underground | R16 |  | 60 | 18 |  |  | 159 | 2019 | 2020 | R16
160812160613 | 164577160613 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-09 | 2019-08-09 | 2019-08-09 |  | 2019-11-08 | Underground | R16 | 2019-10-29 | 1 |  | 58 | 9 | 66 | 2019 | 2019 | R16
160007162120 | 167479162120 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-02 | 2019-07-02 | 2019-08-23 |  | 2022-08-02 | Underground | R16 |  | 1 | 39 |  |  | 806 | 2019 | 2022 | R16
160289157254 | 167663157254 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-01 | 2019-07-02 | 2019-07-08 |  | 2019-10-16 | Overhead | R16 | 2019-10-09 | 2 | 5 | 68 | 6 | 78 | 2019 | 2019 | R16
168251173088 | 168242173088 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-22 | 2019-10-22 | 2019-11-27 |  | 2021-04-14 | Underground | R16 | 2020-12-14 | 1 | 27 | 274 | 88 | 387 | 2019 | 2021 | R16
168766166714 | 160909166714 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-13 | 2019-09-30 | 2019-10-04 | 2019-12-10 | 2020-01-03 | Overhead | R16 | 2019-12-10 | 12 | 5 | 48 | 19 | 81 | 2019 | 2020 | R16
165331162534 | 167941162534 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-28 | 2019-08-28 | 2019-08-28 | 2020-04-10 | 2020-04-11 | Overhead | R16 | 2020-04-10 | 1 |  | 163 | 1 | 163 | 2019 | 2020 | R16
161176170389 | 160798170389 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-01 | 2019-11-01 | 2019-11-01 |  | 2022-10-20 | Overhead | R16 |  | 1 |  |  |  | 775 | 2019 | 2022 | R16
160539174882 | 161747174882 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-07 | 2019-11-07 | 2019-12-18 | 2020-02-25 | 2020-02-27 | Underground | R16 | 2020-02-25 | 1 | 30 | 50 | 3 | 81 | 2019 | 2020 | R16
162040161675 | 166253161675 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-19 | 2019-08-19 | 2019-08-20 |  | 2019-09-26 | Overhead | R16 | 2019-09-18 | 1 | 2 | 22 | 7 | 29 | 2019 | 2019 | R16
161808176993 | 163802176993 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-19 | 2019-11-27 | 2020-01-14 | 2020-03-24 | 2020-03-24 | Underground | R16 | 2020-03-24 | 7 | 35 | 51 |  | 91 | 2019 | 2020 | R16
166163170303 | 169634170303 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2019-10-28 | 2019-10-28 | 2019-10-31 |  | 2021-11-10 | Underground | R16 | 2020-01-17 | 1 | 4 | 57 | 474 | 533 | 2019 | 2021 | R16
161530161823 | 166394161823 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-20 | 2019-08-20 | 2019-08-20 |  | 2019-10-09 | Overhead | R16 | 2019-09-26 | 1 |  | 28 | 10 | 37 | 2019 | 2019 | R16
162323166536 | 169317166536 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-05 | 2019-09-05 | 2019-10-03 | 2020-07-13 | 2020-07-14 | Underground | R16 | 2020-07-13 | 1 | 21 | 203 | 2 | 224 | 2019 | 2020 | R16
169442166783 | 160124166783 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-10 | 2019-09-10 | 2019-10-03 | 2019-12-20 | 2019-12-18 | Underground | R16 | 2019-12-20 | 1 | 18 | 57 |  | 72 | 2019 | 2019 | R16
168047171507 | 169157171507 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-25 | 2019-11-12 | 2019-11-12 | 2020-03-24 | 2020-04-28 | Overhead | R16 | 2020-03-24 | 13 |  | 96 | 26 | 133 | 2019 | 2020 | R16
165966164770 | 166259164770 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-19 | 2019-08-19 | 2019-09-16 |  | 2019-10-16 | Underground | R16 | 2019-10-10 | 1 | 21 | 19 | 5 | 43 | 2019 | 2019 | R16
161316155640 | 164102155640 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-14 | 2019-06-14 | 2019-06-17 | 2019-07-23 | 2019-07-25 | Overhead | R16 | 2019-07-23 | 1 | 2 | 27 | 3 | 30 | 2019 | 2019 | R16
164025163349 | 164305163349 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-07 | 2019-08-07 | 2019-09-04 | 2019-10-25 | 2019-10-29 | Underground | R16 | 2019-10-25 | 1 | 21 | 38 | 3 | 60 | 2019 | 2019 | R16
167164159105 | 165058159105 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-18 | 2019-07-15 | 2019-07-26 |  | 2020-10-06 | Overhead | R16 |  | 20 | 10 |  |  | 341 | 2019 | 2020 | R16
162791162576 | 168134162576 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-28 | 2019-08-28 | 2019-08-28 | 2019-09-26 | 2019-09-26 | Overhead | R16 | 2019-09-26 | 1 |  | 22 |  | 22 | 2019 | 2019 | R16
164204159062 | 162062159062 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-25 | 2019-07-25 | 2019-07-25 |  | 2020-06-09 | Underground | R16 | 2020-03-17 | 1 |  | 169 | 61 | 229 | 2019 | 2020 | R16
169303163505 | 169388163505 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2019-09-05 | 2019-09-05 | 2019-09-06 |  | 2020-07-01 | Overhead | R16 | 2020-04-29 | 1 | 2 | 169 | 46 | 215 | 2019 | 2020 | R16
160465165954 | 162979165954 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-09-26 | 2019-09-26 | 2019-09-26 |  | 2019-10-30 | Overhead | R16 | 2019-10-25 | 1 |  | 22 | 4 | 25 | 2019 | 2019 | R16
169056197327 | 167477197327 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2019-08-26 | 2020-03-11 | 2020-07-14 | 2022-04-08 | 2023-01-31 | Underground | R16 | 2022-04-08 | 143 | 90 | 454 | 213 | 897 | 2019 | 2023 | R16
168490173655 | 166269173655 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-05 | 2019-12-05 | 2019-12-05 |  | 2020-12-29 | Overhead | R16 | 2020-09-28 | 1 |  | 213 | 67 | 279 | 2019 | 2020 | R16
163224179086 | 164829179086 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-22 | 2019-11-22 | 2020-02-03 | 2020-03-09 | 2020-03-25 | Underground | R16 | 2020-03-09 | 1 | 52 | 26 | 13 | 89 | 2019 | 2020 | R16
167916157447 | 166411157447 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-06-27 | 2019-06-27 | 2019-07-09 | 2019-08-09 | 2019-08-14 | Underground | R16 | 2019-08-09 | 1 | 9 | 24 | 4 | 35 | 2019 | 2019 | R16
163325158374 | 160976158374 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-19 | 2019-07-19 | 2019-07-19 |  | 2019-09-18 | Overhead | R16 | 2019-09-10 | 1 |  | 38 | 7 | 44 | 2019 | 2019 | R16
162257176395 | 162752176395 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-07-30 | 2019-07-30 | 2020-01-09 | 2021-05-27 | 2021-10-03 | Underground | R16 | 2021-05-27 | 1 | 118 | 361 | 92 | 569 | 2019 | 2021 | R16
169230165706 | 162631165706 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-24 | 2019-09-24 | 2019-09-25 |  | 2021-10-14 | Overhead | R16 | 2019-12-17 | 1 | 2 | 60 | 478 | 538 | 2019 | 2021 | R16
165653171104 | 166295171104 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-10 | 2019-10-10 | 2019-11-07 | 2020-02-05 | 2020-03-09 | Underground | R16 | 2020-02-05 | 1 | 21 | 65 | 24 | 108 | 2019 | 2020 | R16
163256156427 | 166217156427 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-26 | 2019-06-26 | 2019-06-26 | 2019-12-03 | 2020-01-02 | Overhead | R16 | 2019-12-03 | 1 |  | 115 | 23 | 137 | 2019 | 2020 | R16
169171159574 | 162610159574 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-29 | 2019-07-30 | 2019-07-30 |  | 2019-10-11 | Overhead | R16 | 2019-09-30 | 2 |  | 45 | 10 | 55 | 2019 | 2019 | R16
160889198454 | 163031198454 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Commercial | 2019-09-25 | 2019-09-25 | 2020-07-28 | 2020-09-08 | 2020-11-12 | Underground | R16 | 2020-09-08 | 1 | 220 | 31 | 48 | 297 | 2019 | 2020 | R16
162632167728 | 161691167728 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-07-24 | 2019-07-24 | 2019-10-10 |  | 2021-11-05 | Underground | R16 | 2021-11-05 | 1 | 57 | 542 |  | 598 | 2019 | 2021 | R16
165275165667 | 161311165667 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-09-17 | 2019-09-17 | 2019-09-24 |  | 2021-12-17 | Overhead | R16 | 2020-01-09 | 1 | 6 | 78 | 507 | 589 | 2019 | 2021 | R16
163862172238 | 163829172238 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-11-19 | 2019-11-19 | 2019-11-19 | 2019-12-27 | 2019-12-28 | Overhead | R16 | 2019-12-27 | 1 |  | 29 | 1 | 29 | 2019 | 2019 | R16
165205172916 | 165642172916 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-15 | 2019-08-15 | 2019-11-26 | 2020-01-29 | 2020-01-24 | Underground | R16 | 2020-01-29 | 1 | 74 | 47 |  | 117 | 2019 | 2020 | R16
161486167365 | 168732167365 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-03 | 2019-09-03 | 2019-10-08 |  | 2019-11-08 | Underground | R16 | 2019-10-31 | 1 | 26 | 18 | 7 | 49 | 2019 | 2019 | R16
160293161889 | 162614161889 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE FOR UPGRADE UD | Commercial | 2019-07-29 | 2019-08-07 | 2019-08-21 | 2019-10-31 | 2020-04-20 | Underground | R16 | 2019-10-31 | 8 | 11 | 52 | 123 | 191 | 2019 | 2020 | R16
168853164066 | 160269164066 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-11 | 2019-09-11 | 2019-09-11 |  | 2019-10-16 | Overhead | R16 | 2019-10-10 | 1 |  | 22 | 5 | 26 | 2019 | 2019 | R16
161305170114 | 162836170114 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-25 | 2019-09-25 | 2019-10-30 |  | 2020-07-08 | Underground | R16 | 2020-04-16 | 1 | 26 | 122 | 60 | 206 | 2019 | 2020 | R16
161698171161 | 167924171161 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-19 | 2019-10-19 | 2019-11-07 | 2020-06-24 | 2020-09-23 | Underground | R16 | 2020-06-24 | 0 | 14 | 165 | 66 | 243 | 2019 | 2020 | R16
169478171621 | 163707171621 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-05 | 2019-11-12 | 2019-11-12 | 2020-03-24 | 2020-06-09 | Overhead | R16 | 2020-03-24 | 72 |  | 96 | 56 | 222 | 2019 | 2020 | R16
164171164057 | 160649164057 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-09-12 | 2019-09-12 | 2019-09-12 |  | 2022-05-18 | Overhead | R16 | 2019-09-27 | 1 |  | 12 | 689 | 700 | 2019 | 2022 | R16
160363167087 | 167391167087 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-08-26 | 2019-08-26 | 2019-10-05 |  | 2020-07-08 | Underground | R16 |  | 1 | 30 |  |  | 228 | 2019 | 2020 | R16
163794172564 | 167034172564 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-15 | 2019-10-15 | 2019-11-21 | 2020-02-14 | 2020-06-09 | Underground | R16 | 2020-02-14 | 1 | 28 | 62 | 83 | 171 | 2019 | 2020 | R16
162706165225 | 162205165225 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-20 | 2019-09-20 | 2019-09-20 | 2019-11-29 | 2019-12-02 | Overhead | R16 | 2019-11-29 | 1 |  | 51 | 2 | 52 | 2019 | 2019 | R16
166332171356 | 162354171356 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-11 | 2019-11-11 | 2019-11-11 |  | 2022-08-02 | Overhead | R16 |  | 1 |  |  |  | 712 | 2019 | 2022 | R16
166679209098 | 168070209098 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2019-08-28 | 2020-10-31 | 2020-11-02 |  | 2022-03-08 | Overhead | R16 |  | 308 | 1 |  |  | 660 | 2019 | 2022 | R16
161176174607 | 162029174607 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-07-25 | 2019-07-25 | 2019-12-16 | 2020-05-28 | 2020-09-01 | Underground | R16 | 2020-05-28 | 1 | 103 | 119 | 69 | 289 | 2019 | 2020 | R16
167885166681 | 164315166681 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-10-02 | 2019-10-02 | 2019-10-02 |  | 2022-05-17 | Overhead | R16 | 2020-02-20 | 1 |  | 102 | 584 | 685 | 2019 | 2022 | R16
166338161741 | 166361161741 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-19 | 2022-12-20 | 2019-08-20 | 2019-10-09 | 2019-10-17 | Overhead | R16 | 2019-10-09 | 872 |  | 37 | 7 | 44 | 2019 | 2019 | R16
169727184618 | 161768184618 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-11-07 | 2020-02-13 | 2020-03-19 | 2021-02-05 | 2021-03-23 | Underground | R16 | 2021-02-05 | 71 | 26 | 232 | 33 | 359 | 2019 | 2021 | R16
162119179053 | 162138179053 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential Subdivision | 2019-09-20 | 2019-09-30 | 2020-02-03 |  | 2021-11-16 | Underground | R16 |  | 7 | 91 |  |  | 563 | 2019 | 2021 | R16
163737172402 | 167068172402 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-15 | 2019-10-15 | 2019-11-19 |  | 2020-07-14 | Underground | R16 | 2020-06-18 | 1 | 26 | 153 | 19 | 196 | 2019 | 2020 | R16
163640158679 | 169043158679 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-07-09 | 2019-07-09 | 2019-07-24 | 2022-12-13 | 2023-06-07 | Underground | R16 | 2022-12-13 | 1 | 12 | 885 | 127 | 1022 | 2019 | 2023 | R16
161874161223 | 165546161223 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-14 | 2019-08-14 | 2019-08-14 |  | 2020-10-06 | Underground | R16 | 2020-07-10 | 1 |  | 238 | 63 | 300 | 2019 | 2020 | R16
164100160501 | 164287160501 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-08-07 | 2019-08-07 | 2019-08-07 |  | 2019-12-09 | Overhead | R16 | 2019-08-23 | 1 |  | 13 | 77 | 89 | 2019 | 2019 | R16
162842166980 | 163058166980 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-31 | 2019-10-04 | 2019-10-04 |  | 2022-10-17 | Overhead | R16 |  | 48 |  |  |  | 839 | 2019 | 2022 | R16
169945179233 | 160138179233 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-10 | 2019-09-10 | 2020-02-03 | 2020-08-12 | 2020-10-06 | Underground | R16 | 2020-08-12 | 1 | 105 | 138 | 40 | 281 | 2019 | 2020 | R16
163041182051 | 163043182051 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-13 | 2019-11-13 | 2020-02-26 |  | 2020-07-09 | Underground | R16 | 2020-05-11 | 1 | 76 | 54 | 44 | 172 | 2019 | 2020 | R16
166557172308 | 160554172308 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-10-31 | 2019-11-08 | 2019-11-19 |  | 2019-12-17 | Overhead | R16 |  | 7 | 8 |  |  | 34 | 2019 | 2019 | R16
168847161291 | 165860161291 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-15 | 2019-08-15 | 2019-08-15 | 2019-09-17 | 2019-10-08 | Overhead | R16 | 2019-09-17 | 1 |  | 24 | 16 | 39 | 2019 | 2019 | R16
167765182697 | 160362182697 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-10-30 | 2019-10-30 | 2020-03-02 | 2020-04-21 | 2020-11-11 | Underground | R16 | 2020-04-21 | 1 | 89 | 37 | 147 | 271 | 2019 | 2020 | R16
161725159602 | 169530159602 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-11 | 2019-07-11 | 2019-07-30 |  | 2019-10-09 | Underground | R16 | 2019-09-25 | 1 | 14 | 42 | 11 | 65 | 2019 | 2019 | R16
160578160604 | 164544160604 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-08 | 2019-08-08 | 2019-08-08 |  | 2019-10-30 | Overhead | R16 | 2019-10-21 | 1 |  | 53 | 8 | 60 | 2019 | 2019 | R16
169489158664 | 167500158664 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-07-01 | 2019-07-01 | 2019-07-22 |  | 2019-11-15 | Overhead | R16 |  | 1 | 16 |  |  | 100 | 2019 | 2019 | R16
169545169721 | 169275169721 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-25 | 2019-10-25 | 2019-10-25 | 2019-12-16 | 2019-12-17 | Overhead | R16 | 2019-12-16 | 1 |  | 37 | 2 | 38 | 2019 | 2019 | R16
163806171692 | 164220171692 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-06 | 2019-08-06 | 2019-11-13 |  | 2021-11-13 | Underground | R16 | 2020-01-08 | 1 | 72 | 41 | 483 | 594 | 2019 | 2021 | R16
161466186547 | 165366186547 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-27 | 2019-11-27 | 2020-04-06 | 2020-07-20 | 2020-07-21 | Underground | R16 | 2020-07-20 | 1 | 94 | 76 | 2 | 170 | 2019 | 2020 | R16
168773171470 | 160748171470 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-01 | 2019-11-11 | 2019-11-11 | 2019-12-04 | 2020-04-29 | Overhead | R16 | 2019-12-04 | 7 |  | 18 | 106 | 129 | 2019 | 2020 | R16
165674167889 | 165811167889 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-10-09 | 2019-10-09 | 2019-10-12 | 2020-01-09 | 2020-01-14 | Overhead | R16 | 2020-01-09 | 1 | 3 | 64 | 4 | 70 | 2019 | 2020 | R16
163613156930 | 167584156930 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2019-07-19 | 2019-07-19 | Overhead | R16 | 2019-07-19 | 1 |  | 15 |  | 15 | 2019 | 2019 | R16
163929198813 | 165620198813 | NON-RESIDENTIAL - SCHOOLS / EDUCATIONAL | R16 RESD AND NON RESD US | Commercial | 2019-12-02 | 2019-12-02 | 2020-07-29 | 2022-05-06 | 2022-06-03 | Underground | R16 | 2022-05-06 | 1 | 173 | 463 | 21 | 655 | 2019 | 2022 | R16
167480164107 | 169928164107 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-09 | 2019-09-09 | 2019-09-11 |  | 2019-10-16 | Overhead | R16 | 2019-10-09 | 1 | 3 | 21 | 6 | 28 | 2019 | 2019 | R16
161476161462 | 163000161462 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-07-31 | 2019-08-16 | 2019-08-16 | 2020-03-13 | 2020-01-09 | Underground | R16 | 2020-03-13 | 13 |  | 151 |  | 117 | 2019 | 2020 | R16
162806155743 | 164999155743 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-18 | 2019-06-18 | 2019-06-18 | 2019-10-21 | 2019-10-30 | Overhead | R16 | 2019-10-21 | 1 |  | 90 | 8 | 97 | 2019 | 2019 | R16
160558166970 | 161827166970 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-19 | 2019-09-19 | 2019-10-05 | 2021-08-13 | 2021-09-03 | Underground | R16 | 2021-08-13 | 1 | 12 | 485 | 16 | 512 | 2019 | 2021 | R16
169661166448 | 163984166448 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-01 | 2019-10-01 | 2019-10-01 |  | 2019-12-30 | Overhead | R16 | 2019-12-27 | 1 |  | 64 | 2 | 65 | 2019 | 2019 | R16
166495164726 | 166995164726 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-22 | 2019-08-22 | 2019-09-16 |  | 2021-12-16 | Underground | R16 | 2020-01-30 | 1 | 18 | 99 | 491 | 606 | 2019 | 2021 | R16
168500170819 | 161521170819 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-06 | 2019-11-06 | 2019-11-06 | 2020-03-13 | 2020-06-09 | Overhead | R16 | 2020-03-13 | 1 |  | 93 | 63 | 155 | 2019 | 2020 | R16
167563157000 | 167806157000 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-02 | 2019-07-02 | 2019-07-02 | 2019-07-12 | 2019-07-15 | Overhead | R16 | 2019-07-12 | 1 |  | 9 | 2 | 10 | 2019 | 2019 | R16
163517162706 | 168178162706 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-29 | 2019-08-29 | 2019-08-29 |  | 2019-10-11 | Overhead | R16 | 2019-09-30 | 1 |  | 23 | 10 | 32 | 2019 | 2019 | R16
166753163956 | 167338163956 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-26 | 2019-08-26 | 2019-09-10 | 2019-12-20 | 2019-12-18 | Underground | R16 | 2019-12-20 | 1 | 12 | 74 |  | 83 | 2019 | 2019 | R16
161252157500 | 168886157500 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-09 | 2019-07-09 | 2019-07-09 | 2019-08-04 | 2019-12-06 | Overhead | R16 | 2019-08-04 | 1 |  | 19 | 90 | 109 | 2019 | 2019 | R16
167211174799 | 167530174799 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-17 | 2019-10-17 | 2019-12-18 | 2020-02-26 | 2020-02-27 | Underground | R16 | 2020-02-26 | 1 | 45 | 51 | 2 | 96 | 2019 | 2020 | R16
166670159222 | 169902159222 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-15 | 2019-07-15 | 2019-07-26 | 2019-10-07 | 2019-10-07 | Underground | R16 | 2019-10-07 | 1 | 10 | 52 |  | 61 | 2019 | 2019 | R16
169659163306 | 168888163306 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-03 | 2019-09-03 | 2019-09-03 | 2019-11-21 | 2019-11-22 | Overhead | R16 | 2019-11-21 | 1 |  | 58 | 2 | 59 | 2019 | 2019 | R16
160274169312 | 160265169312 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-10 | 2019-09-10 | 2019-10-24 | 2019-11-11 | 2019-11-21 | Underground | R16 | 2019-11-11 | 1 | 33 | 13 | 9 | 53 | 2019 | 2019 | R16
163955169849 | 169591169849 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-28 | 2019-10-28 | 2019-10-28 | 2020-02-13 | 2021-12-16 | Overhead | R16 | 2020-02-13 | 1 |  | 79 | 481 | 559 | 2019 | 2021 | R16
169544181240 | 168145181240 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-10-22 | 2019-12-27 | 2020-02-19 | 2023-06-23 | 2023-07-21 | Underground | R16 | 2023-06-23 | 49 | 39 | 873 | 21 | 979 | 2019 | 2023 | R16
163272167817 | 166245167817 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-10 | 2019-10-10 | 2019-10-11 |  | 2020-06-09 | Overhead | R16 | 2020-04-08 | 1 | 2 | 129 | 45 | 174 | 2019 | 2020 | R16
162784156384 | 166036156384 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-25 | 2019-06-25 | 2019-06-25 |  | 2019-09-03 | Overhead | R16 | 2019-08-01 | 1 |  | 28 | 24 | 51 | 2019 | 2019 | R16
167847159132 | 161334159132 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-22 | 2019-07-22 | 2019-07-27 |  | 2020-10-06 | Overhead | R16 | 2020-08-24 | 1 | 5 | 281 | 32 | 317 | 2019 | 2020 | R16
160503165761 | 160683165761 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2019-09-12 | 2019-09-13 | 2019-09-25 |  | 2019-12-04 | Underground | R16 |  | 2 | 9 |  |  | 60 | 2019 | 2019 | R16
167808174222 | 165435174222 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-27 | 2019-11-27 | 2019-12-12 |  | 2020-06-09 | Underground | R16 | 2020-02-06 | 1 | 12 | 41 | 89 | 140 | 2019 | 2020 | R16
167300170192 | 160294170192 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-30 | 2019-10-31 | 2019-10-31 |  | 2019-12-09 | Underground | R16 | 2019-12-02 | 2 |  | 23 | 6 | 29 | 2019 | 2019 | R16
160617171656 | 160680171656 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-31 | 2019-10-31 | 2019-11-13 |  | 2020-06-09 | Underground | R16 | 2020-02-11 | 1 | 10 | 65 | 86 | 159 | 2019 | 2020 | R16
160858160412 | 164173160412 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-07 | 2019-08-07 | 2019-08-07 |  | 2019-09-19 | Overhead | R16 | 2019-09-13 | 1 |  | 28 | 5 | 32 | 2019 | 2019 | R16
168463180999 | 168746180999 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2019-07-08 | 2019-07-08 | 2020-02-19 | 2021-06-16 | 2021-07-13 | Underground | R16 | 2021-06-16 | 1 | 163 | 346 | 20 | 527 | 2019 | 2021 | R16
160628166770 | 161060166770 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-13 | 2019-09-13 | 2019-10-03 |  | 2021-12-28 | Underground | R16 | 2021-10-14 | 1 | 15 | 531 | 54 | 598 | 2019 | 2021 | R16
163928220548 | 167640220548 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-17 | 2021-02-12 | 2021-02-12 | 2022-04-20 | 2022-05-16 | Underground | R16 | 2022-04-20 | 347 |  | 309 | 19 | 673 | 2019 | 2022 | R16
163026169018 | 168165169018 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-21 | 2019-10-21 | 2019-10-21 | 2019-11-25 | 2021-12-16 | Overhead | R16 | 2019-11-25 | 1 |  | 26 | 539 | 564 | 2019 | 2021 | R16
160199172889 | 162256172889 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-08 | 2019-11-25 | 2019-11-25 | 2020-03-13 | 2020-06-09 | Underground | R16 | 2020-03-13 | 12 |  | 80 | 63 | 153 | 2019 | 2020 | R16
166968319612 | 160654319612 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-05-19 | 2023-05-19 | 2023-05-19 | 2023-07-14 | 2023-08-09 | Overhead | R16 | 2023-07-14 | 1 |  | 41 | 19 | 59 | 2023 | 2023 | R16
163567167682 | 166118167682 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-10 | 2019-10-10 | 2019-10-10 |  | 2020-01-03 | Overhead | R16 | 2019-12-09 | 1 |  | 43 | 20 | 62 | 2019 | 2020 | R16
160401170205 | 166904170205 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-08-22 | 2019-09-13 | 2019-10-30 | 2020-06-01 | 2020-11-06 | Underground | R16 | 2020-06-01 | 17 | 34 | 154 | 115 | 317 | 2019 | 2020 | R16
160981169017 | 162057169017 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-20 | 2019-09-20 | 2019-10-21 |  | 2020-10-06 | Underground | R16 | 2020-08-27 | 1 | 22 | 224 | 29 | 273 | 2019 | 2020 | R16
164012162603 | 167803162603 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-27 | 2019-08-27 | 2019-08-27 | 2020-01-09 | 2021-11-10 | Underground | R16 | 2020-01-09 | 1 |  | 98 | 480 | 577 | 2019 | 2021 | R16
161298216879 | 161521216879 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-09-17 | 2019-09-17 | 2021-01-12 | 2021-03-11 | 2021-03-11 | Underground | R16 | 2021-03-11 | 1 | 346 | 43 |  | 388 | 2019 | 2021 | R16
161990172561 | 164451172561 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-21 | 2019-11-21 | 2019-11-21 | 2019-12-27 | 2020-07-01 | Overhead | R16 | 2019-12-27 | 1 |  | 27 | 134 | 160 | 2019 | 2020 | R16
168462218357 | 167845218357 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2019-12-11 | 2019-12-11 | 2021-01-26 | 2021-03-04 | 2021-11-29 | Underground | R16 | 2021-03-04 | 1 | 295 | 28 | 193 | 514 | 2019 | 2021 | R16
169466166441 | 161706166441 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-24 | 2019-07-24 | 2019-10-01 |  | 2019-11-27 | Underground | R16 | 2019-11-22 | 1 | 50 | 39 | 4 | 91 | 2019 | 2019 | R16
166732168266 | 166562168266 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-10-11 | 2019-10-14 | 2019-10-14 | 2019-11-14 | 2019-11-15 | Overhead | R16 | 2019-11-14 | 2 |  | 24 | 2 | 26 | 2019 | 2019 | R16
169514159002 | 161811159002 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-24 | 2019-07-24 | 2019-07-24 | 2019-11-12 | 2019-11-13 | Overhead | R16 | 2019-11-12 | 1 |  | 80 | 2 | 81 | 2019 | 2019 | R16
167514170917 | 169711170917 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-06 | 2019-09-06 | 2019-11-07 |  | 2019-12-09 | Overhead | R16 |  | 1 | 45 |  |  | 67 | 2019 | 2019 | R16
168008165750 | 168735165750 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-03 | 2019-09-03 | 2019-09-25 | 2020-10-12 | 2021-01-22 | Underground | R16 | 2020-10-12 | 1 | 17 | 274 | 75 | 364 | 2019 | 2021 | R16
168024171095 | 168976171095 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-24 | 2019-10-25 | 2019-11-08 |  | 2021-11-10 | Underground | R16 | 2020-01-30 | 2 | 11 | 60 | 465 | 535 | 2019 | 2021 | R16
166018158024 | 169989158024 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-16 | 2019-07-16 | 2019-07-16 | 2019-08-08 | 2019-12-06 | Overhead | R16 | 2019-08-08 | 1 |  | 18 | 87 | 104 | 2019 | 2019 | R16
163296160137 | 163648160137 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-05 | 2019-08-05 | 2019-08-05 |  | 2019-11-26 | Overhead | R16 | 2019-10-23 | 1 |  | 58 | 25 | 82 | 2019 | 2019 | R16
166895159712 | 167750159712 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-02 | 2019-07-02 | 2019-08-01 |  | 2019-11-15 | Underground | R16 | 2019-08-12 | 1 | 23 | 8 | 70 | 99 | 2019 | 2019 | R16
164469159587 | 168329159587 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-05 | 2019-07-05 | 2019-07-30 | 2020-07-15 | 2020-10-06 | Underground | R16 | 2020-07-15 | 1 | 18 | 252 | 60 | 328 | 2019 | 2020 | R16
160277169904 | 169524169904 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-28 | 2019-10-28 | 2019-10-28 |  | 2020-06-09 | Overhead | R16 | 2019-12-18 | 1 |  | 38 | 125 | 162 | 2019 | 2020 | R16
163526187516 | 168182187516 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-12-13 | 2020-03-10 | 2020-04-15 | 2020-06-12 | 2020-12-22 | Underground | R16 | 2020-06-12 | 63 | 27 | 43 | 138 | 268 | 2019 | 2020 | R16
168765172854 | 168575172854 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-10-23 | 2019-10-23 | 2019-11-26 | 2020-07-30 | 2020-07-31 | Underground | R16 | 2020-07-30 | 1 | 25 | 178 | 2 | 203 | 2019 | 2020 | R16
166882174504 | 168864174504 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-16 | 2019-12-16 | 2019-12-16 | 2019-12-28 | 2020-01-23 | Overhead | R16 | 2019-12-28 | 1 |  | 10 | 19 | 29 | 2019 | 2020 | R16
168059167155 | 161343167155 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-16 | 2019-09-16 | 2019-10-08 | 2020-06-25 | 2020-06-26 | Underground | R16 | 2020-06-25 | 1 | 17 | 188 | 2 | 205 | 2019 | 2020 | R16
160848173688 | 166553173688 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-06 | 2019-12-06 | 2019-12-06 |  | 2022-10-17 | Overhead | R16 |  | 1 |  |  |  | 747 | 2019 | 2022 | R16
167364170617 | 169407170617 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-25 | 2019-11-05 | 2019-11-05 | 2020-01-22 | 2021-11-10 | Overhead | R16 | 2020-01-22 | 8 |  | 57 | 471 | 534 | 2019 | 2021 | R16
163816161460 | 166016161460 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-16 | 2019-08-16 | 2019-08-16 |  | 2020-06-09 | Overhead | R16 | 2020-03-05 | 1 |  | 145 | 69 | 213 | 2019 | 2020 | R16
166001156585 | 164135156585 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-15 | 2019-06-15 | 2019-06-27 | 2019-10-07 | 2019-11-12 | Overhead | R16 | 2019-10-07 | 0 | 9 | 73 | 27 | 107 | 2019 | 2019 | R16
164864160982 | 164943160982 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-12 | 2019-08-12 | 2019-08-12 | 2020-08-13 | 2020-08-21 | Overhead | R16 | 2020-08-13 | 1 |  | 264 | 7 | 270 | 2019 | 2020 | R16
162944169239 | 163106169239 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-26 | 2019-09-26 | 2019-10-23 |  | 2021-11-10 | Underground | R16 | 2020-01-22 | 1 | 20 | 66 | 471 | 555 | 2019 | 2021 | R16
162765155901 | 163618155901 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-06-12 | 2019-06-12 | 2019-06-20 |  | 2019-12-30 | Underground | R16 | 2019-12-06 | 1 | 7 | 122 | 17 | 144 | 2019 | 2019 | R16
162011204368 | 162808204368 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-09-25 | 2019-09-25 | 2020-09-19 | 2021-04-14 | 2021-06-08 | Underground | R16 | 2021-04-14 | 1 | 258 | 148 | 40 | 445 | 2019 | 2021 | R16
165239183597 | 160055183597 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-10-30 | 2019-10-30 | 2020-03-10 |  | 2020-06-09 | Underground | R16 | 2020-04-07 | 1 | 95 | 21 | 46 | 160 | 2019 | 2020 | R16
162197296094 | 165570296094 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-10-05 | 2022-10-05 | 2022-10-05 |  | 2023-08-22 | Overhead | R16 | 2023-08-01 | 1 |  | 215 | 16 | 230 | 2022 | 2023 | R16
161857166678 | 164229166678 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-03 | 2019-10-03 | 2019-10-03 | 2019-11-20 | 2019-11-21 | Overhead | R16 | 2019-11-20 | 1 |  | 35 | 2 | 36 | 2019 | 2019 | R16
168897169199 | 168679169199 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-23 | 2019-10-23 | 2019-10-23 |  | 2020-06-09 | Overhead | R16 | 2020-03-20 | 1 |  | 108 | 58 | 165 | 2019 | 2020 | R16
166666178316 | 167316178316 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-24 | 2019-08-24 | 2020-01-28 |  | 2020-07-09 | Underground | R16 | 2020-05-27 | 0 | 112 | 87 | 32 | 229 | 2019 | 2020 | R16
163496156507 | 166358156507 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-26 | 2019-06-26 | 2019-06-27 |  | 2019-07-01 | Overhead | R16 |  | 1 | 2 |  |  | 4 | 2019 | 2019 | R16
161906169461 | 169030169461 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-24 | 2019-10-24 | 2019-10-24 |  | 2020-07-14 | Overhead | R16 | 2020-06-17 | 1 |  | 170 | 20 | 189 | 2019 | 2020 | R16
165445221840 | 165439221840 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Residential | 2019-06-21 | 2019-06-21 | 2021-02-26 | 2023-01-18 | 2022-07-25 | Underground | R16 | 2023-01-18 | 1 | 441 | 494 |  | 807 | 2019 | 2022 | R16
162763200553 | 167209200553 | RESIDENTIAL - SINGLE FAMILY ATTACHED | R16 RESD AND NON RESD US | Residential | 2019-12-11 | 2019-12-16 | 2020-08-14 |  | 2021-11-02 | Underground | R16 | 2021-06-15 | 4 | 175 | 218 | 101 | 495 | 2019 | 2021 | R16
169652169864 | 165290169864 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-08-13 | 2019-08-14 | 2019-10-28 | 2020-03-28 | 2020-11-11 | Overhead | R16 | 2020-03-28 | 2 | 54 | 110 | 163 | 327 | 2019 | 2020 | R16
161811175616 | 163618175616 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-18 | 2019-11-18 | 2020-01-02 | 2020-03-04 | 2020-03-06 | Underground | R16 | 2020-03-04 | 1 | 34 | 45 | 3 | 80 | 2019 | 2020 | R16
168853171986 | 162730171986 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-12 | 2019-11-15 | 2019-11-15 | 2020-01-09 | 2020-06-16 | Overhead | R16 | 2020-01-09 | 4 |  | 40 | 114 | 156 | 2019 | 2020 | R16
163205163485 | 169444163485 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-05 | 2019-09-05 | 2019-09-05 | 2019-09-20 | 2019-10-09 | Overhead | R16 | 2019-09-20 | 1 |  | 12 | 14 | 25 | 2019 | 2019 | R16
161584156970 | 168116156970 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-03 | 2019-07-03 | 2019-07-03 |  | 2019-09-03 | Overhead | R16 | 2019-07-30 | 1 |  | 20 | 26 | 45 | 2019 | 2019 | R16
167607164640 | 161160164640 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-15 | 2019-09-15 | 2019-09-15 | 2019-10-22 | 2019-10-23 | Overhead | R16 | 2019-10-22 | 0 |  | 27 | 2 | 28 | 2019 | 2019 | R16
168403159640 | 161203159640 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-22 | 2019-07-30 | 2019-07-30 | 2020-02-14 | 2020-06-09 | Overhead | R16 | 2020-02-14 | 7 |  | 144 | 83 | 232 | 2019 | 2020 | R16
169034160131 | 161774160131 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-24 | 2019-07-24 | 2019-08-05 |  | 2019-09-24 | Underground | R16 | 2019-09-16 | 1 | 9 | 31 | 7 | 45 | 2019 | 2019 | R16
167409169608 | 168529169608 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES UD | Residential | 2019-10-23 | 2019-10-23 | 2019-10-25 |  | 2021-11-13 | Underground | R16 | 2020-01-14 | 1 | 3 | 58 | 479 | 538 | 2019 | 2021 | R16
167520191675 | 164672191675 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-10-04 | 2019-10-04 | 2020-05-20 |  | 2020-07-10 | Underground | R16 | 2020-06-10 | 1 | 164 | 16 | 23 | 201 | 2019 | 2020 | R16
165539161314 | 165656161314 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-15 | 2019-08-15 | 2019-08-16 |  | 2019-09-20 | Overhead | R16 |  | 1 | 2 |  |  | 27 | 2019 | 2019 | R16
160187167824 | 161173167824 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-16 | 2019-09-16 | 2019-10-11 |  | 2019-11-21 | Underground | R16 | 2019-11-14 | 1 | 20 | 25 | 6 | 49 | 2019 | 2019 | R16
169010321645 | 168947321645 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2023-05-10 | 2023-05-10 | 2023-06-08 | 2023-06-15 | 2023-07-27 | Underground | R16 | 2023-06-15 | 1 | 22 | 6 | 31 | 57 | 2023 | 2023 | R16
165096170625 | 160956170625 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-04 | 2019-11-04 | 2019-11-04 |  | 2022-10-20 | Overhead | R16 |  | 1 |  |  |  | 774 | 2019 | 2022 | R16
166873158775 | 168869158775 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-09 | 2019-07-09 | 2019-07-25 |  | 2019-10-16 | Overhead | R16 |  | 1 | 13 |  |  | 72 | 2019 | 2019 | R16
160653164965 | 161399164965 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-09-18 | 2019-09-18 | 2019-09-18 | 2019-12-24 | 2019-12-27 | Overhead | R16 | 2019-12-24 | 1 |  | 70 | 4 | 73 | 2019 | 2019 | R16
162377162571 | 168126162571 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-28 | 2019-08-28 | 2019-08-28 | 2019-09-24 | 2019-09-25 | Overhead | R16 | 2019-09-24 | 1 |  | 20 | 2 | 21 | 2019 | 2019 | R16
165243178205 | 167896178205 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-10-19 | 2020-01-27 | 2020-01-27 |  | 2022-03-29 | Overhead | R16 | 2020-01-30 | 71 |  | 4 | 564 | 637 | 2019 | 2022 | R16
165569172431 | 166306172431 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-10 | 2019-10-10 | 2019-11-20 | 2020-01-29 | 2020-09-15 | Overhead | R16 | 2020-01-29 | 1 | 30 | 51 | 165 | 244 | 2019 | 2020 | R16
161642178909 | 163262178909 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-09-26 | 2019-09-26 | 2020-01-31 |  | 2022-10-20 | Underground | R16 |  | 1 | 92 |  |  | 801 | 2019 | 2022 | R16
166550175657 | 161566175657 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-18 | 2019-09-18 | 2020-01-03 |  | 2021-11-10 | Overhead | R16 |  | 1 | 78 |  |  | 561 | 2019 | 2021 | R16
166110170671 | 166924170671 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-14 | 2019-10-14 | 2019-11-04 | 2020-01-08 | 2020-06-09 | Underground | R16 | 2020-01-08 | 1 | 16 | 48 | 110 | 172 | 2019 | 2020 | R16
165095173612 | 165577173612 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential Subdivision | 2019-12-02 | 2019-12-03 | 2019-12-04 |  | 2021-11-13 | Underground | R16 |  | 2 | 2 |  |  | 510 | 2019 | 2021 | R16
166702165652 | 162707165652 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-24 | 2019-09-24 | 2019-09-24 |  | 2019-10-16 | Overhead | R16 | 2019-10-08 | 1 |  | 11 | 7 | 17 | 2019 | 2019 | R16
162784165206 | 169274165206 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-09-05 | 2019-09-05 | 2019-09-20 | 2020-02-12 | 2020-02-13 | Underground | R16 | 2020-02-12 | 1 | 12 | 104 | 2 | 116 | 2019 | 2020 | R16
168216163238 | 168981163238 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-09-03 | 2019-09-03 | 2019-09-03 |  | 2019-10-09 | Overhead | R16 | 2019-09-25 | 1 |  | 17 | 11 | 27 | 2019 | 2019 | R16
160860165969 | 165220165969 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-13 | 2019-08-13 | 2019-09-26 |  | 2022-08-02 | Underground | R16 |  | 1 | 33 |  |  | 776 | 2019 | 2022 | R16
163713168256 | 166916168256 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-15 | 2019-10-15 | 2019-10-15 | 2019-12-26 | 2020-01-08 | Overhead | R16 | 2019-12-26 | 1 |  | 53 | 10 | 62 | 2019 | 2020 | R16
163510170930 | 161083170930 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC DEVELOPMENT | Residential Subdivision | 2019-11-04 | 2019-11-05 | 2019-11-06 |  | 2021-04-22 | Underground | R16 |  | 2 | 2 |  |  | 384 | 2019 | 2021 | R16
161324173718 | 165161173718 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-07 | 2019-10-07 | 2019-12-09 | 2020-01-10 | 2020-01-13 | Underground | R16 | 2020-01-10 | 1 | 46 | 25 | 2 | 71 | 2019 | 2020 | R16
164540165074 | 162005165074 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-19 | 2019-09-19 | 2019-09-19 |  | 2019-11-06 | Overhead | R16 | 2019-10-28 | 1 |  | 28 | 8 | 35 | 2019 | 2019 | R16
166251160626 | 164546160626 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-08 | 2019-08-08 | 2019-08-08 | 2019-08-09 | 2019-09-10 | Overhead | R16 | 2019-08-09 | 1 |  | 2 | 23 | 24 | 2019 | 2019 | R16
164855157605 | 169366157605 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-11 | 2019-07-11 | 2019-07-11 | 2019-08-28 | 2019-11-25 | Overhead | R16 | 2019-08-28 | 1 |  | 35 | 64 | 98 | 2019 | 2019 | R16
168302165830 | 163057165830 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-26 | 2019-09-26 | 2019-09-26 | 2021-02-19 | 2021-02-22 | Overhead | R16 | 2021-02-19 | 1 |  | 367 | 2 | 368 | 2019 | 2021 | R16
167675171612 | 168373171612 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-29 | 2019-08-29 | 2019-11-13 | 2020-03-01 | 2020-03-05 | Underground | R16 | 2020-03-01 | 1 | 55 | 78 | 4 | 136 | 2019 | 2020 | R16
166347160957 | 165436160957 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-14 | 2019-08-14 | 2019-08-14 |  | 2023-06-08 | Overhead | R16 | 2019-10-03 | 1 |  | 37 | 961 | 997 | 2019 | 2023 | R16
169738175360 | 165447175360 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-12-01 | 2019-12-01 | 2019-12-30 |  | 2021-11-13 | Underground | R16 |  | 0 | 21 |  |  | 510 | 2019 | 2021 | R16
161132170040 | 169029170040 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-24 | 2019-10-24 | 2019-10-29 |  | 2020-07-09 | Overhead | R16 | 2020-06-03 | 1 | 4 | 157 | 27 | 186 | 2019 | 2020 | R16
160808166551 | 160943166551 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-13 | 2019-09-13 | 2019-10-03 | 2019-11-05 | 2019-11-06 | Underground | R16 | 2019-11-05 | 1 | 15 | 24 | 2 | 39 | 2019 | 2019 | R16
161236167615 | 166223167615 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-10 | 2019-10-10 | 2019-10-10 |  | 2019-11-06 | Overhead | R16 | 2019-10-28 | 1 |  | 13 | 8 | 20 | 2019 | 2019 | R16
167192237545 | 168858237545 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-09-03 | 2019-09-25 | 2021-07-01 | 2022-01-21 | 2022-02-09 | Underground | R16 | 2022-01-21 | 17 | 462 | 147 | 14 | 637 | 2019 | 2022 | R16
163164166540 | 163916166540 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-01 | 2019-10-01 | 2019-10-01 |  | 2019-12-04 | Underground | R16 | 2019-11-26 | 1 |  | 41 | 7 | 47 | 2019 | 2019 | R16
166139161710 | 161395161710 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-22 | 2019-07-23 | 2019-08-20 |  | 2020-06-09 | Underground | R16 | 2020-04-01 | 2 | 21 | 162 | 50 | 232 | 2019 | 2020 | R16
169341174385 | 168797174385 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-16 | 2019-12-16 | 2019-12-16 | 2020-02-03 | 2020-02-04 | Overhead | R16 | 2020-02-03 | 1 |  | 36 | 2 | 37 | 2019 | 2020 | R16
164967159692 | 165738159692 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-24 | 2019-06-24 | 2019-08-01 |  | 2019-10-14 | Underground | R16 | 2019-10-02 | 1 | 29 | 45 | 9 | 81 | 2019 | 2019 | R16
162674170956 | 161585170956 | NON-RESIDENTIAL - HEALTH CARE | R16 RESD AND NON RESD US | Commercial | 2019-09-18 | 2019-09-18 | 2019-11-06 | 2020-03-20 | 2020-04-27 | Underground | R16 | 2020-03-20 | 1 | 36 | 98 | 27 | 159 | 2019 | 2020 | R16
163640173716 | 166679173716 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-12-09 | 2019-12-09 | 2019-12-09 |  | 2020-10-06 | Overhead | R16 | 2020-08-18 | 1 |  | 182 | 36 | 217 | 2019 | 2020 | R16
169263160612 | 162872160612 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-30 | 2019-08-09 | 2019-08-09 |  | 2021-11-13 | Underground | R16 | 2019-12-13 | 9 |  | 91 | 501 | 599 | 2019 | 2021 | R16
169174170085 | 169869170085 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-29 | 2019-10-29 | 2019-10-29 |  | 2021-11-13 | Overhead | R16 | 2019-12-16 | 1 |  | 35 | 500 | 534 | 2019 | 2021 | R16
169506163261 | 168760163261 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-09-01 | 2019-09-01 | 2019-09-03 |  | 2019-09-19 | Overhead | R16 | 2019-09-13 | 0 | 2 | 9 | 5 | 14 | 2019 | 2019 | R16
168428167295 | 165571167295 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-08 | 2019-10-08 | 2019-10-08 |  | 2020-10-06 | Overhead | R16 | 2020-07-27 | 1 |  | 210 | 52 | 261 | 2019 | 2020 | R16
167349166548 | 161652166548 | SDG&E | UG ELEC MISC SVC US | Commercial | 2019-09-18 | 2019-09-18 | 2019-10-02 |  | 2023-11-24 | Underground | R16 |  | 1 | 11 |  |  | 1093 | 2019 | 2023 | R16
169602157565 | 166652157565 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-28 | 2019-06-28 | 2019-07-10 |  | 2020-07-14 | Underground | R16 | 2020-06-16 | 1 | 9 | 245 | 21 | 273 | 2019 | 2020 | R16
169915157422 | 168907157422 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-09 | 2019-07-09 | 2019-07-09 | 2019-08-22 | 2023-06-08 | Overhead | R16 | 2019-08-22 | 1 |  | 33 | 991 | 1023 | 2019 | 2023 | R16
161331167543 | 161332167543 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-07-22 | 2019-08-29 | 2019-10-09 | 2021-06-22 | 2021-06-25 | Underground | R16 | 2021-06-22 | 29 | 30 | 445 | 4 | 505 | 2019 | 2021 | R16
165774165026 | 169411165026 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-07-11 | 2019-07-11 | 2019-09-18 | 2020-01-10 | 2021-11-10 | Underground | R16 | 2020-01-10 | 1 | 50 | 83 | 479 | 610 | 2019 | 2021 | R16
164869163952 | 160094163952 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-10 | 2019-09-10 | 2019-09-10 | 2019-09-13 | 2019-11-08 | Overhead | R16 | 2019-09-13 | 1 |  | 4 | 41 | 44 | 2019 | 2019 | R16
160193172080 | 163367172080 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-15 | 2019-11-15 | 2019-11-15 |  | 2021-11-10 | Overhead | R16 | 2019-12-17 | 1 |  | 23 | 497 | 519 | 2019 | 2021 | R16
164386164725 | 161230164725 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-16 | 2019-09-16 | 2019-09-16 |  | 2019-10-28 | Overhead | R16 | 2019-10-14 | 1 |  | 21 | 11 | 31 | 2019 | 2019 | R16
168346162727 | 168501162727 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-30 | 2019-08-30 | 2019-08-30 | 2019-08-31 | 2019-09-03 | Underground | R16 | 2019-08-31 | 1 |  | 1 | 2 | 3 | 2019 | 2019 | R16
161406173115 | 164921173115 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential Subdivision | 2019-11-22 | 2019-11-26 | 2019-12-02 | 2019-12-03 | 2020-01-09 | Overhead | R16 | 2019-12-03 | 3 | 5 | 2 | 28 | 35 | 2019 | 2020 | R16
163336174709 | 165238174709 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-20 | 2019-08-15 | 2019-12-17 | 2020-02-11 | 2020-02-12 | Underground | R16 | 2020-02-11 | 41 | 89 | 41 | 2 | 170 | 2019 | 2020 | R16
161293160559 | 160965160559 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-19 | 2019-07-19 | 2019-08-09 |  | 2022-08-02 | Underground | R16 |  | 1 | 16 |  |  | 793 | 2019 | 2022 | R16
168323161580 | 168570161580 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-07 | 2019-07-07 | 2019-08-19 | 2019-09-19 | 2019-09-19 | Underground | R16 | 2019-09-19 | 0 | 31 | 24 |  | 54 | 2019 | 2019 | R16
163328168187 | 166726168187 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-14 | 2019-10-14 | 2019-10-14 | 2020-02-12 | 2020-06-09 | Overhead | R16 | 2020-02-12 | 1 |  | 88 | 85 | 172 | 2019 | 2020 | R16
164775169630 | 169415169630 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-25 | 2019-10-25 | 2019-10-25 | 2020-01-08 | 2021-12-16 | Overhead | R16 | 2020-01-08 | 1 |  | 54 | 507 | 560 | 2019 | 2021 | R16
166390157524 | 169150157524 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-09 | 2019-07-10 | 2019-07-10 |  | 2022-10-20 | Overhead | R16 |  | 2 |  |  |  | 858 | 2019 | 2022 | R16
163824290125 | 165235290125 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-22 | 2022-08-24 | 2022-08-24 | 2023-07-19 | 2023-07-28 | Overhead | R16 | 2023-07-19 | 3 |  | 236 | 8 | 245 | 2022 | 2023 | R16
164039181317 | 164177181317 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-07 | 2019-08-07 | 2020-02-21 |  | 2020-04-15 | Overhead | R16 |  | 1 | 143 |  |  | 181 | 2019 | 2020 | R16
163089170543 | 161002170543 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-04 | 2019-11-04 | 2019-11-04 | 2019-12-02 | 2019-12-03 | Overhead | R16 | 2019-12-02 | 1 |  | 21 | 2 | 22 | 2019 | 2019 | R16
164121167606 | 164759167606 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-04 | 2019-10-04 | 2019-10-10 |  | 2020-06-09 | Underground | R16 | 2020-06-08 | 1 | 5 | 173 | 2 | 178 | 2019 | 2020 | R16
165592170556 | 165871170556 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-09 | 2019-10-09 | 2019-11-05 | 2019-12-18 | 2019-12-26 | Underground | R16 | 2019-12-18 | 1 | 20 | 32 | 7 | 57 | 2019 | 2019 | R16
162391166771 | 164437166771 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-03 | 2019-10-03 | 2019-10-03 |  | 2019-10-30 | Overhead | R16 | 2019-10-24 | 1 |  | 16 | 5 | 20 | 2019 | 2019 | R16
169463161740 | 160818161740 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-18 | 2019-07-18 | 2019-08-20 | 2019-09-06 | 2021-12-16 | Underground | R16 | 2019-09-06 | 1 | 24 | 14 | 595 | 631 | 2019 | 2021 | R16
162106171855 | 165440171855 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-07 | 2019-10-07 | 2019-11-14 |  | 2020-07-01 | Underground | R16 | 2020-04-28 | 1 | 29 | 119 | 47 | 193 | 2019 | 2020 | R16
162533161652 | 166396161652 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-21 | 2019-08-21 | 2019-08-21 | 2021-03-17 | 2021-08-11 | Overhead | R16 | 2021-03-17 | 1 |  | 411 | 106 | 516 | 2019 | 2021 | R16
163272160481 | 164263160481 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-07 | 2019-08-07 | 2019-08-07 |  | 2019-11-15 | Overhead | R16 | 2019-11-08 | 1 |  | 68 | 6 | 73 | 2019 | 2019 | R16
161954158566 | 163205158566 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-11 | 2019-06-11 | 2019-07-22 |  | 2019-09-26 | Underground | R16 | 2019-09-19 | 1 | 30 | 44 | 6 | 78 | 2019 | 2019 | R16
163697173687 | 162793173687 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Commercial | 2019-07-30 | 2019-07-30 | 2019-12-06 | 2020-06-19 | 2020-08-31 | Underground | R16 | 2020-06-19 | 1 | 94 | 141 | 52 | 285 | 2019 | 2020 | R16
167689155247 | 163657155247 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-13 | 2019-06-13 | 2019-06-13 | 2020-06-10 | 2020-07-10 | Overhead | R16 | 2020-06-10 | 1 |  | 260 | 23 | 282 | 2019 | 2020 | R16
168083166966 | 160070166966 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-09 | 2019-09-09 | 2019-10-05 | 2020-05-07 | 2020-05-08 | Underground | R16 | 2020-05-07 | 1 | 20 | 154 | 2 | 175 | 2019 | 2020 | R16
167124171808 | 164641171808 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-10-03 | 2019-10-04 | 2019-11-13 |  | 2021-04-14 | Underground | R16 |  | 2 | 29 |  |  | 400 | 2019 | 2021 | R16
160406164021 | 162685164021 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-07-30 | 2019-07-31 | 2019-09-10 | 2023-01-11 | 2022-12-01 | Underground | R16 | 2023-01-11 | 2 | 30 | 872 |  | 873 | 2019 | 2022 | R16
160862161401 | 165931161401 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-16 | 2019-08-16 | 2019-08-16 | 2019-09-06 | 2019-09-09 | Overhead | R16 | 2019-09-06 | 1 |  | 16 | 2 | 17 | 2019 | 2019 | R16
160188158248 | 160648158248 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-18 | 2019-07-18 | 2019-07-18 | 2019-11-02 | 2019-12-05 | Overhead | R16 | 2019-11-02 | 1 |  | 77 | 24 | 101 | 2019 | 2019 | R16
162213162784 | 168355162784 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-30 | 2019-08-30 | 2019-08-30 |  | 2019-10-16 | Overhead | R16 | 2019-10-09 | 1 |  | 29 | 6 | 34 | 2019 | 2019 | R16
166933172863 | 164017172863 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-20 | 2019-11-20 | 2019-11-25 |  | 2020-06-09 | Underground | R16 | 2020-02-25 | 1 | 4 | 67 | 76 | 145 | 2019 | 2020 | R16
168049156170 | 165697156170 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-24 | 2019-06-24 | 2019-06-24 |  | 2019-09-03 | Overhead | R16 | 2019-07-30 | 1 |  | 27 | 26 | 52 | 2019 | 2019 | R16
163226157505 | 164809157505 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-19 | 2019-07-09 | 2019-07-09 | 2019-08-22 | 2019-08-28 | Overhead | R16 | 2019-08-22 | 15 |  | 33 | 5 | 51 | 2019 | 2019 | R16
163380168185 | 166734168185 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-14 | 2019-10-14 | 2019-10-14 | 2020-07-13 | 2020-10-06 | Overhead | R16 | 2020-07-13 | 1 |  | 196 | 62 | 257 | 2019 | 2020 | R16
160587171362 | 162226171362 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-08 | 2019-11-08 | 2019-11-11 |  | 2020-01-02 | Overhead | R16 | 2019-12-11 | 1 | 2 | 23 | 17 | 40 | 2019 | 2020 | R16
167463165522 | 168943165522 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-03 | 2019-09-03 | 2019-09-23 | 2020-10-08 | 2020-10-19 | Underground | R16 | 2020-10-08 | 1 | 15 | 274 | 8 | 295 | 2019 | 2020 | R16
165756169944 | 169518169944 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-28 | 2019-10-28 | 2019-10-28 | 2019-11-28 | 2021-12-16 | Overhead | R16 | 2019-11-28 | 1 |  | 24 | 536 | 559 | 2019 | 2021 | R16
166716156566 | 165511156566 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-06-21 | 2019-06-27 | 2019-06-27 |  | 2019-11-08 | Overhead | R16 | 2019-11-01 | 5 |  | 92 | 6 | 101 | 2019 | 2019 | R16
164506163108 | 168744163108 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-03 | 2019-09-03 | 2019-09-04 |  | 2019-10-09 | Overhead | R16 | 2019-09-25 | 1 | 2 | 16 | 11 | 27 | 2019 | 2019 | R16
168764163325 | 167220163325 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-23 | 2019-08-23 | 2019-09-04 | 2019-11-06 | 2019-11-07 | Overhead | R16 | 2019-11-06 | 1 | 9 | 46 | 2 | 55 | 2019 | 2019 | R16
168488170979 | 162059170979 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-08 | 2019-11-08 | 2019-11-08 |  | 2021-10-14 | Overhead | R16 | 2020-01-15 | 1 |  | 49 | 457 | 505 | 2019 | 2021 | R16
163753157653 | 169429157653 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-11 | 2019-07-11 | 2019-07-12 |  | 2019-09-03 | Overhead | R16 | 2019-08-26 | 1 | 2 | 32 | 7 | 39 | 2019 | 2019 | R16
163514181273 | 166786181273 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-09 | 2019-12-09 | 2020-02-21 | 2020-04-13 | 2020-04-14 | Underground | R16 | 2020-04-13 | 1 | 55 | 37 | 2 | 92 | 2019 | 2020 | R16
169258155723 | 164709155723 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-18 | 2019-06-18 | 2019-06-18 | 2019-07-01 | 2019-07-01 | Overhead | R16 | 2019-07-01 | 1 |  | 10 |  | 10 | 2019 | 2019 | R16
163592172843 | 165041172843 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-25 | 2019-11-25 | 2019-11-25 |  | 2020-06-09 | Underground | R16 | 2020-02-12 | 1 |  | 58 | 85 | 142 | 2019 | 2020 | R16
168143172012 | 168807172012 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-03 | 2019-09-03 | 2019-11-15 |  | 2020-06-09 | Underground | R16 | 2020-02-06 | 1 | 54 | 60 | 89 | 201 | 2019 | 2020 | R16
167530164086 | 160446164086 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-11 | 2019-09-11 | 2019-09-11 |  | 2019-11-21 | Overhead | R16 | 2019-11-15 | 1 |  | 48 | 5 | 52 | 2019 | 2019 | R16
167085175100 | 163123175100 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-14 | 2019-11-14 | 2019-12-20 | 2020-02-07 | 2020-03-24 | Underground | R16 | 2020-02-07 | 1 | 27 | 36 | 33 | 94 | 2019 | 2020 | R16
165243158380 | 160679158380 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-18 | 2019-07-18 | 2019-07-18 | 2019-07-31 | 2019-09-10 | Overhead | R16 | 2019-07-31 | 1 |  | 10 | 30 | 39 | 2019 | 2019 | R16
164747174310 | 167904174310 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-11 | 2019-12-12 | 2019-12-12 |  | 2021-11-05 | Underground | R16 | 2021-04-16 | 2 |  | 352 | 146 | 498 | 2019 | 2021 | R16
165188178486 | 160938178486 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-11-04 | 2019-11-04 | 2020-01-28 | 2022-05-23 | 2022-06-13 | Underground | R16 | 2022-05-23 | 1 | 62 | 605 | 16 | 681 | 2019 | 2022 | R16
162032158057 | 160340158057 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-16 | 2019-07-16 | 2019-07-16 | 2019-10-13 | 2019-10-16 | Overhead | R16 | 2019-10-13 | 1 |  | 64 | 3 | 67 | 2019 | 2019 | R16
169101162812 | 168634162812 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-30 | 2019-08-30 | 2019-08-30 |  | 2019-10-04 | Overhead | R16 | 2019-09-23 | 1 |  | 17 | 10 | 26 | 2019 | 2019 | R16
169423171401 | 162468171401 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-11-11 | 2019-11-11 | 2019-11-11 | 2020-09-18 | 2020-09-21 | Underground | R16 | 2020-09-18 | 1 |  | 225 | 2 | 226 | 2019 | 2020 | R16
164788173566 | 165678173566 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-12-03 | 2019-12-03 | 2019-12-04 |  | 2020-02-27 | Underground | R16 |  | 1 | 2 |  |  | 63 | 2019 | 2020 | R16
163014155968 | 165506155968 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-21 | 2019-06-21 | 2019-06-21 | 2019-08-20 | 2019-08-21 | Overhead | R16 | 2019-08-20 | 1 |  | 43 | 2 | 44 | 2019 | 2019 | R16
166661161957 | 160042161957 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-07-15 | 2019-07-17 | 2019-08-23 | 2019-11-20 | 2019-11-21 | Underground | R16 | 2019-11-20 | 3 | 28 | 64 | 2 | 94 | 2019 | 2019 | R16
160027176670 | 160090176670 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-09-09 | 2019-09-09 | 2020-01-14 |  | 2021-06-30 | Underground | R16 | 2020-10-22 | 1 | 92 | 203 | 180 | 473 | 2019 | 2021 | R16
166951163337 | 168844163337 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-03 | 2019-09-03 | 2019-09-05 |  | 2020-06-09 | Overhead | R16 | 2020-01-16 | 1 | 3 | 96 | 104 | 201 | 2019 | 2020 | R16
162615156383 | 165984156383 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-25 | 2019-06-25 | 2019-06-25 |  | 2019-09-04 | Overhead | R16 | 2019-08-28 | 1 |  | 47 | 6 | 52 | 2019 | 2019 | R16
163606156477 | 166375156477 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-26 | 2019-06-26 | 2019-06-26 | 2019-08-04 | 2019-12-06 | Overhead | R16 | 2019-08-04 | 1 |  | 28 | 90 | 118 | 2019 | 2019 | R16
163393167141 | 162892167141 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-25 | 2019-10-03 | 2019-10-07 |  | 2020-07-09 | Overhead | R16 |  | 7 | 3 |  |  | 207 | 2019 | 2020 | R16
160805165914 | 163264165914 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-27 | 2019-09-27 | 2019-09-27 |  | 2019-11-26 | Overhead | R16 | 2019-11-19 | 1 |  | 38 | 6 | 43 | 2019 | 2019 | R16
168003166387 | 168684166387 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-30 | 2019-08-30 | 2019-10-01 | 2020-05-21 | 2020-07-09 | Underground | R16 | 2020-05-21 | 1 | 23 | 168 | 36 | 225 | 2019 | 2020 | R16
164064156529 | 166484156529 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-06-27 | 2019-06-27 | 2019-06-27 | 2019-10-01 | 2019-10-14 | Overhead | R16 | 2019-10-01 | 1 |  | 69 | 10 | 78 | 2019 | 2019 | R16
164004162404 | 165545162404 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-14 | 2019-08-14 | 2019-08-26 | 2019-09-16 | 2019-09-19 | Underground | R16 | 2019-09-16 | 1 | 9 | 16 | 4 | 27 | 2019 | 2019 | R16
164530172512 | 164536172512 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-11-21 | 2019-11-21 | 2019-11-21 | 2019-11-26 | 2019-12-04 | Overhead | R16 | 2019-11-26 | 1 |  | 4 | 7 | 10 | 2019 | 2019 | R16
169007179864 | 169918179864 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-09 | 2019-09-09 | 2020-02-10 |  | 2020-04-01 | Underground | R16 |  | 1 | 111 |  |  | 148 | 2019 | 2020 | R16
165502222403 | 160840222403 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-09-12 | 2019-09-12 | 2021-03-03 |  | 2021-10-14 | Overhead | R16 | 2021-04-05 | 1 | 385 | 24 | 139 | 546 | 2019 | 2021 | R16
169943163176 | 169010163176 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-03 | 2019-09-03 | 2019-09-03 |  | 2019-11-14 | Overhead | R16 | 2019-11-06 | 1 |  | 47 | 7 | 53 | 2019 | 2019 | R16
162088160463 | 163098160463 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-01 | 2019-08-01 | 2019-08-07 | 2019-10-01 | 2019-10-02 | Underground | R16 | 2019-10-01 | 1 | 5 | 40 | 2 | 45 | 2019 | 2019 | R16
162539167827 | 166477167827 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-10-11 | 2019-10-11 | 2019-10-11 |  | 2020-06-09 | Overhead | R16 | 2020-03-30 | 1 |  | 122 | 52 | 173 | 2019 | 2020 | R16
161611156728 | 167399156728 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-01 | 2019-07-01 | 2019-07-01 |  | 2019-09-10 | Overhead | R16 | 2019-09-03 | 1 |  | 47 | 6 | 52 | 2019 | 2019 | R16
164488172641 | 166343172641 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-19 | 2019-08-19 | 2019-11-21 |  | 2021-04-21 | Underground | R16 | 2021-01-27 | 1 | 69 | 310 | 61 | 438 | 2019 | 2021 | R16
161088172405 | 164060172405 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-20 | 2019-11-20 | 2019-11-20 |  | 2021-11-13 | Overhead | R16 | 2020-01-06 | 1 |  | 34 | 485 | 518 | 2019 | 2021 | R16
164428335379 | 161147335379 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-07-22 | 2019-09-03 | 2023-10-12 | 2023-11-20 | 2023-11-30 | Underground | R16 | 2023-11-20 | 32 | 1073 | 28 | 9 | 1139 | 2019 | 2023 | R16
166641170274 | 169136170274 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-10-25 | 2019-10-25 | 2019-10-31 |  | 2021-11-10 | Overhead | R16 |  | 1 | 5 |  |  | 534 | 2019 | 2021 | R16
161853170977 | 162041170977 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-08 | 2019-11-08 | 2019-11-08 |  | 2021-11-10 | Underground | R16 | 2020-01-23 | 1 |  | 55 | 470 | 524 | 2019 | 2021 | R16
164980157518 | 169322157518 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-10 | 2019-07-10 | 2019-07-10 |  | 2023-06-05 | Overhead | R16 | 2019-08-30 | 1 |  | 38 | 982 | 1019 | 2019 | 2023 | R16
161442166711 | 163708166711 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-09-30 | 2019-09-30 | 2019-10-04 |  | 2021-11-10 | Overhead | R16 | 2019-12-17 | 1 | 5 | 53 | 497 | 553 | 2019 | 2021 | R16
167883175040 | 168119175040 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-13 | 2019-12-13 | 2019-12-20 | 2019-12-30 | 2021-11-01 | Underground | R16 | 2019-12-30 | 1 | 6 | 7 | 481 | 492 | 2019 | 2021 | R16
161583161295 | 165764161295 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-15 | 2019-08-15 | 2019-08-16 |  | 2019-11-14 | Overhead | R16 | 2019-11-06 | 1 | 2 | 59 | 7 | 66 | 2019 | 2019 | R16
161366169978 | 169384169978 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-26 | 2019-10-26 | 2019-10-30 |  | 2020-07-01 | Underground | R16 |  | 0 | 3 |  |  | 178 | 2019 | 2020 | R16
169576181007 | 166286181007 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-19 | 2019-08-19 | 2020-02-18 | 2020-04-29 | 2020-07-07 | Underground | R16 | 2020-04-29 | 1 | 132 | 52 | 50 | 232 | 2019 | 2020 | R16
164250171554 | 164231171554 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-02 | 2019-10-02 | 2019-11-13 |  | 2021-04-15 | Underground | R16 | 2020-12-21 | 1 | 31 | 289 | 84 | 402 | 2019 | 2021 | R16
166037156806 | 166252156806 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-06-26 | 2019-07-01 | 2019-07-01 |  | 2020-06-09 | Underground | R16 | 2020-04-03 | 4 |  | 200 | 48 | 250 | 2019 | 2020 | R16
162694162668 | 167995162668 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-28 | 2019-08-28 | 2019-08-28 | 2019-10-15 | 2019-10-16 | Overhead | R16 | 2019-10-15 | 1 |  | 35 | 2 | 36 | 2019 | 2019 | R16
161194178557 | 166509178557 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-12-05 | 2019-12-05 | 2020-01-30 |  | 2020-06-09 | Overhead | R16 | 2020-02-26 | 1 | 41 | 20 | 75 | 134 | 2019 | 2020 | R16
160324164483 | 168859164483 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-03 | 2019-09-03 | 2019-09-14 |  | 2020-06-09 | Underground | R16 | 2020-02-03 | 1 | 9 | 101 | 92 | 201 | 2019 | 2020 | R16
167084172461 | 163966172461 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-20 | 2019-11-20 | 2019-11-20 |  | 2020-06-09 | Overhead | R16 | 2020-01-14 | 1 |  | 40 | 106 | 145 | 2019 | 2020 | R16
161022171784 | 163068171784 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-13 | 2019-11-13 | 2019-11-13 |  | 2020-06-09 | Overhead | R16 | 2020-02-06 | 1 |  | 62 | 89 | 150 | 2019 | 2020 | R16
169725172250 | 163885172250 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-11-19 | 2019-11-19 | 2019-11-19 | 2019-11-26 | 2020-06-09 | Overhead | R16 | 2019-11-26 | 1 |  | 6 | 141 | 146 | 2019 | 2020 | R16
161479161638 | 163611161638 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-05 | 2019-08-20 | 2019-08-20 | 2019-12-10 | 2021-11-13 | Overhead | R16 | 2019-12-10 | 12 |  | 81 | 504 | 595 | 2019 | 2021 | R16
166887171357 | 168030171357 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-10-21 | 2019-10-22 | 2019-11-11 | 2020-04-24 | 2023-06-07 | Underground | R16 | 2020-04-24 | 2 | 15 | 120 | 814 | 948 | 2019 | 2023 | R16
163007186871 | 168996186871 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-10-24 | 2019-10-24 | 2020-04-09 |  | 2021-04-22 | Underground | R16 | 2021-01-29 | 1 | 121 | 212 | 60 | 391 | 2019 | 2021 | R16
163602163332 | 160365163332 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-16 | 2019-09-05 | 2019-09-05 |  | 2019-10-28 | Overhead | R16 | 2019-10-16 | 38 |  | 30 | 9 | 75 | 2019 | 2019 | R16
162069166446 | 168350166446 | NON-RESIDENTIAL - LARGE OFFICE | R16 RESD AND NON RESD US | Commercial | 2019-08-29 | 2019-08-29 | 2019-10-01 | 2023-05-01 | 2023-05-17 | Underground | R16 | 2023-05-01 | 1 | 24 | 935 | 13 | 970 | 2019 | 2023 | R16
166374160341 | 163730160341 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-08-05 | 2019-08-05 | 2019-08-06 | 2020-10-02 | 2021-02-10 | Underground | R16 | 2020-10-02 | 1 | 2 | 304 | 94 | 398 | 2019 | 2021 | R16
161630171434 | 161501171434 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-11-06 | 2019-11-06 | 2019-11-11 |  | 2020-01-03 | Underground | R16 |  | 1 | 4 |  |  | 43 | 2019 | 2020 | R16
163965172976 | 163896172976 | INDUSTRIAL | UG R16 RESD AND NON RESD UD | Commercial | 2019-08-06 | 2019-08-06 | 2019-11-26 | 2020-05-15 | 2021-07-11 | Underground | R16 | 2020-05-15 | 1 | 81 | 124 | 301 | 504 | 2019 | 2021 | R16
160504168555 | 163074168555 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-25 | 2019-10-16 | 2019-10-17 | 2019-12-26 | 2019-12-30 | Underground | R16 | 2019-12-26 | 16 | 2 | 51 | 3 | 69 | 2019 | 2019 | R16
168584215977 | 162204215977 | RESIDENTIAL - SINGLE FAMILY ATTACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-11-08 | 2020-12-21 | 2021-01-04 | 2021-04-14 | 2021-05-05 | Underground | R16 | 2021-04-14 | 292 | 11 | 73 | 16 | 389 | 2019 | 2021 | R16
163369157551 | 169236157551 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-07-11 | 2019-07-11 | 2019-07-11 |  | 2020-01-03 | Overhead | R16 | 2019-12-11 | 1 |  | 110 | 18 | 127 | 2019 | 2020 | R16
163040172505 | 169553172505 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Residential | 2019-07-11 | 2019-07-11 | 2019-11-21 |  | 2022-08-29 | Underground | R16 |  | 1 | 96 |  |  | 818 | 2019 | 2022 | R16
164566162329 | 165110162329 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-12 | 2019-08-12 | 2019-08-27 | 2019-11-06 | 2019-11-07 | Underground | R16 | 2019-11-06 | 1 | 12 | 52 | 2 | 64 | 2019 | 2019 | R16
166081172312 | 161021172312 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-13 | 2019-09-13 | 2019-11-19 |  | 2020-08-28 | Underground | R16 | 2020-07-07 | 1 | 48 | 166 | 39 | 251 | 2019 | 2020 | R16
164010159431 | 163544159431 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-12 | 2019-06-12 | 2019-07-31 | 2020-01-23 | 2020-01-24 | Underground | R16 | 2020-01-23 | 1 | 36 | 127 | 2 | 163 | 2019 | 2020 | R16
168177179722 | 168996179722 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-09-04 | 2019-09-04 | 2020-02-07 | 2020-06-05 | 2020-06-08 | Underground | R16 | 2020-06-05 | 1 | 113 | 86 | 2 | 199 | 2019 | 2020 | R16
168639176114 | 165659176114 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-08-15 | 2019-08-15 | 2020-01-08 |  | 2022-07-29 | Underground | R16 |  | 1 | 105 |  |  | 772 | 2019 | 2022 | R16
162406182365 | 164305182365 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-11-21 | 2019-11-22 | 2020-02-28 |  | 2020-07-02 | Overhead | R16 | 2020-05-04 | 2 | 71 | 47 | 44 | 161 | 2019 | 2020 | R16
165800163764 | 166230163764 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-08-19 | 2019-08-19 | 2019-09-09 |  | 2019-12-18 | Underground | R16 | 2019-12-09 | 1 | 16 | 66 | 8 | 88 | 2019 | 2019 | R16
167819160332 | 164151160332 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-08-06 | 2019-08-06 | 2019-08-06 |  | 2019-12-06 | Overhead | R16 | 2019-08-13 | 1 |  | 6 | 84 | 89 | 2019 | 2019 | R16
163255189183 | 163193189183 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-11-14 | 2019-11-14 | 2020-04-27 |  | 2021-11-11 | Underground | R16 |  | 1 | 118 |  |  | 521 | 2019 | 2021 | R16
169387159338 | 162512159338 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-07-29 | 2019-07-29 | 2019-07-30 |  | 2020-02-20 | Overhead | R16 |  | 1 | 2 |  |  | 149 | 2019 | 2020 | R16
165309174298 | 167063174298 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-08-23 | 2019-12-12 | 2019-12-12 | 2020-02-21 | 2020-06-09 | Overhead | R16 | 2020-02-21 | 80 |  | 52 | 78 | 208 | 2019 | 2020 | R16
161309176717 | 165614176717 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-12-02 | 2019-12-02 | 2020-01-14 |  | 2020-06-09 | Underground | R16 | 2020-03-13 | 1 | 32 | 44 | 63 | 137 | 2019 | 2020 | R16
164704341199 | 167821341199 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-11-29 | 2023-12-01 | 2023-12-01 | 2023-12-04 | 2023-12-12 | Overhead | R16 | 2023-12-04 | 3 |  | 2 | 7 | 10 | 2023 | 2023 | R16
160641340106 | 166004340106 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-11-17 | 2023-11-17 | 2023-11-17 | 2023-11-20 | 2023-12-15 | Overhead | R16 | 2023-11-20 | 1 |  | 2 | 20 | 21 | 2023 | 2023 | R16
168209341062 | 167644341062 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-11-29 | 2023-11-29 | 2023-11-29 | 2023-12-07 | 2023-12-12 | Overhead | R16 | 2023-12-07 | 1 |  | 7 | 4 | 10 | 2023 | 2023 | R16
163218341247 | 165349341247 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-11-14 | 2023-11-30 | 2023-11-30 | 2023-12-11 | 2023-12-26 | Overhead | R16 | 2023-12-11 | 13 |  | 8 | 12 | 31 | 2023 | 2023 | R16
169955339279 | 164370339279 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2023-11-07 | 2023-11-07 | 2023-11-10 | 2023-12-20 | 2023-12-20 | Underground | R16 | 2023-12-20 | 1 | 4 | 29 |  | 32 | 2023 | 2023 | R16
160080342568 | 160136342568 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-12-14 | 2023-12-14 | 2023-12-14 | 2023-12-15 | 2023-12-19 | Overhead | R16 | 2023-12-15 | 1 |  | 2 | 3 | 4 | 2023 | 2023 | R16
168875341893 | 168986341893 | NON-RESIDENTIAL - SMALL OFFICE | OH R16 RES NON RES OS | Commercial | 2023-12-07 | 2023-12-07 | 2023-12-07 | 2023-12-07 | 2023-12-08 | Overhead | R16 | 2023-12-07 | 1 |  |  | 2 | 2 | 2023 | 2023 | R16
167105338930 | 164052338930 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-11-06 | 2023-11-06 | 2023-11-08 | 2023-12-13 | 2023-12-15 | Overhead | R16 | 2023-12-13 | 1 | 3 | 26 | 3 | 30 | 2023 | 2023 | R16
166400143165 | 166407143165 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-09 | 2019-01-09 | 2019-02-14 |  | 2019-05-28 | Underground | R16 | 2019-04-24 | 1 | 27 | 50 | 25 | 100 | 2019 | 2019 | R16
169950242988 | 164683242988 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-12 | 2021-05-12 | 2021-08-10 |  | 2023-02-06 | Underground | R16 | 2021-10-13 | 1 | 65 | 47 | 344 | 454 | 2021 | 2023 | R16
161005214119 | 161323214119 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-16 | 2020-12-16 | 2020-12-16 | 2021-02-08 | 2022-10-21 | Overhead | R16 | 2021-02-08 | 1 |  | 39 | 445 | 483 | 2020 | 2022 | R16
164318140147 | 165610140147 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-07 | 2019-01-14 | 2019-01-14 |  | 2019-04-15 | Underground | R16 | 2019-03-27 | 6 |  | 53 | 14 | 71 | 2019 | 2019 | R16
169157232800 | 162835232800 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-04 | 2021-05-07 | 2021-05-27 | 2022-03-21 | 2022-03-24 | Underground | R16 | 2022-03-21 | 4 | 15 | 213 | 4 | 233 | 2021 | 2022 | R16
168337149555 | 169957149555 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-03-26 | 2019-03-26 | 2019-04-19 |  | 2019-08-26 | Underground | R16 | 2019-07-19 | 1 | 19 | 66 | 27 | 110 | 2019 | 2019 | R16
168063226953 | 169712226953 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-10 | 2021-03-17 | 2021-04-14 | 2021-07-06 | 2021-07-08 | Underground | R16 | 2021-07-06 | 6 | 21 | 60 | 3 | 87 | 2021 | 2021 | R16
169597148637 | 160445148637 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-28 | 2019-04-09 | 2019-04-09 | 2020-02-14 | 2020-06-09 | Overhead | R16 | 2020-02-14 | 9 |  | 224 | 83 | 314 | 2019 | 2020 | R16
168077204789 | 168179204789 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-09-02 | 2020-09-02 | 2020-09-24 |  | 2021-11-01 | Overhead | R16 | 2021-09-29 | 1 | 17 | 265 | 24 | 304 | 2020 | 2021 | R16
167946144324 | 162392144324 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-02-08 | 2019-02-08 | 2019-02-26 |  | 2019-05-20 | Underground | R16 | 2019-04-18 | 1 | 13 | 38 | 23 | 72 | 2019 | 2019 | R16
160294204937 | 160315204937 | RESIDENTIAL - MULTI-FAMILY | UG R16 RESD AND NON RESD UD | Residential | 2019-03-28 | 2020-05-05 | 2020-09-25 | 2021-08-23 | 2022-02-09 | Underground | R16 | 2021-08-23 | 289 | 104 | 237 | 123 | 750 | 2019 | 2022 | R16
161060157666 | 169313157666 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-01-28 | 2019-07-09 | 2019-07-12 |  | 2022-10-29 | Underground | R16 |  | 117 | 4 |  |  | 980 | 2019 | 2022 | R16
169762156344 | 167537156344 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-03-11 | 2019-05-07 | 2019-06-25 |  | 2019-09-19 | Underground | R16 | 2019-09-13 | 42 | 36 | 59 | 5 | 139 | 2019 | 2019 | R16
163125220634 | 164695220634 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-04-20 | 2021-04-21 | Overhead | R16 | 2021-04-20 | 1 |  | 46 | 2 | 47 | 2021 | 2021 | R16
164330145461 | 167126145461 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-03-08 | 2019-03-08 | 2019-03-08 | 2019-08-04 | 2019-09-06 | Overhead | R16 | 2019-08-04 | 1 |  | 106 | 25 | 131 | 2019 | 2019 | R16
160966146123 | 168126146123 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-14 | 2019-03-14 | 2019-03-14 | 2019-06-10 | 2019-11-18 | Overhead | R16 | 2019-06-10 | 1 |  | 63 | 116 | 178 | 2019 | 2019 | R16
162183209661 | 161243209661 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-29 | 2020-11-04 | 2020-11-04 | 2020-11-09 | 2021-11-09 | Overhead | R16 | 2020-11-09 | 5 |  | 4 | 262 | 269 | 2020 | 2021 | R16
169413222763 | 163106222763 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-09 | 2021-02-09 | 2021-03-05 | 2021-08-02 | 2021-11-01 | Underground | R16 | 2021-08-02 | 1 | 19 | 107 | 66 | 190 | 2021 | 2021 | R16
161120153424 | 160388153424 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-22 | 2019-05-22 | 2019-05-23 |  | 2019-08-26 | Overhead | R16 | 2019-07-31 | 1 | 2 | 50 | 19 | 69 | 2019 | 2019 | R16
168777153225 | 160475153225 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-05-23 | 2019-05-23 | 2019-05-23 |  | 2020-10-06 | Underground | R16 | 2020-08-07 | 1 |  | 317 | 43 | 359 | 2019 | 2020 | R16
161134208962 | 160997208962 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-28 | 2020-10-28 | 2020-10-28 | 2021-10-28 | 2021-10-29 | Overhead | R16 | 2021-10-28 | 1 |  | 262 | 2 | 263 | 2020 | 2021 | R16
163667213247 | 169512213247 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-08 | 2020-12-08 | 2020-12-08 |  | 2022-08-03 | Overhead | R16 |  | 1 |  |  |  | 432 | 2020 | 2022 | R16
168225228467 | 160551228467 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-26 | 2021-04-26 | 2021-04-26 |  | 2021-10-25 | Overhead | R16 | 2021-08-30 | 1 |  | 91 | 41 | 131 | 2021 | 2021 | R16
167471219064 | 160997219064 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-29 | 2021-01-29 | 2021-01-29 |  | 2021-12-17 | Overhead | R16 | 2021-11-17 | 1 |  | 209 | 23 | 231 | 2021 | 2021 | R16
162934144622 | 163131144622 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-02-12 | 2019-02-12 | 2019-02-28 |  | 2019-04-25 | Underground | R16 | 2019-03-21 | 1 | 13 | 16 | 26 | 53 | 2019 | 2019 | R16
163393205631 | 162399205631 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-22 | 2020-09-28 | 2020-09-29 |  | 2021-04-20 | Overhead | R16 |  | 5 | 2 |  |  | 151 | 2020 | 2021 | R16
167314158307 | 169033158307 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-03-20 | 2019-07-18 | 2019-07-18 |  | 2020-06-09 | Overhead | R16 | 2020-02-25 | 87 |  | 159 | 76 | 320 | 2019 | 2020 | R16
162091208120 | 165949208120 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-06 | 2020-10-07 | 2020-10-23 | 2022-01-05 | 2022-01-05 | Underground | R16 | 2022-01-05 | 2 | 13 | 314 |  | 327 | 2020 | 2022 | R16
166116223928 | 161185223928 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-17 | 2021-03-17 | 2021-03-17 | 2021-08-06 | 2022-10-20 | Overhead | R16 | 2021-08-06 | 1 |  | 103 | 315 | 417 | 2021 | 2022 | R16
168099139280 | 165194139280 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-04 | 2019-01-04 | 2019-01-04 |  | 2019-04-15 | Overhead | R16 | 2019-03-06 | 1 |  | 44 | 29 | 72 | 2019 | 2019 | R16
162540143022 | 169525143022 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-29 | 2019-01-29 | 2019-02-11 |  | 2019-05-16 | Underground | R16 | 2019-04-08 | 1 | 10 | 41 | 29 | 78 | 2019 | 2019 | R16
166048150008 | 162754150008 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-04-10 | 2019-04-19 | 2019-04-22 | 2021-03-03 | 2022-03-09 | Underground | R16 | 2021-03-03 | 8 | 2 | 488 | 266 | 761 | 2019 | 2022 | R16
169357157250 | 160787157250 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-24 | 2019-05-24 | 2019-07-06 | 2019-07-15 | 2019-08-26 | Underground | R16 | 2019-07-15 | 1 | 31 | 6 | 31 | 67 | 2019 | 2019 | R16
165834147738 | 165664147738 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-28 | 2019-03-29 | 2019-04-02 |  | 2019-05-28 | Overhead | R16 | 2019-04-25 | 22 | 3 | 18 | 24 | 64 | 2019 | 2019 | R16
162271182311 | 162512182311 | NON-RESIDENTIAL - SMALL RETAIL | UG R16 RESD AND NON RESD UD | Commercial | 2019-06-05 | 2019-06-10 | 2020-02-28 | 2021-06-28 | 2022-07-29 | Underground | R16 | 2021-06-28 | 4 | 190 | 347 | 285 | 823 | 2019 | 2022 | R16
168919212445 | 168006212445 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-02 | 2020-12-02 | 2020-12-02 | 2021-02-17 | 2021-05-07 | Overhead | R16 | 2021-02-17 | 1 |  | 56 | 58 | 113 | 2020 | 2021 | R16
163024145268 | 167122145268 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-07 | 2019-03-07 | 2019-03-07 |  | 2019-05-20 | Overhead | R16 | 2019-04-09 | 1 |  | 24 | 30 | 53 | 2019 | 2019 | R16
167730152985 | 169253152985 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-05-15 | 2019-05-16 | 2019-05-20 |  | 2019-08-12 | Overhead | R16 |  | 2 | 3 |  |  | 64 | 2019 | 2019 | R16
169779151822 | 163589151822 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-16 | 2019-04-16 | 2019-05-08 | 2019-05-20 | 2019-05-20 | Underground | R16 | 2019-05-20 | 1 | 17 | 9 |  | 25 | 2019 | 2019 | R16
168014159080 | 161407159080 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-05-30 | 2019-05-30 | 2019-07-25 |  | 2020-06-09 | Underground | R16 | 2019-12-19 | 1 | 41 | 106 | 124 | 269 | 2019 | 2020 | R16
161750228990 | 169291228990 | NON-RESIDENTIAL - SUBSEQUENT WORK | R16 RESD AND NON RESD US | Residential | 2021-03-09 | 2021-03-09 | 2021-05-01 |  | 2022-02-02 | Underground | R16 |  | 1 | 39 |  |  | 237 | 2021 | 2022 | R16
163448207000 | 167172207000 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-12 | 2020-10-12 | 2020-10-12 |  | 2021-11-08 | Overhead | R16 | 2021-05-18 | 1 |  | 157 | 125 | 281 | 2020 | 2021 | R16
168582212774 | 168751212774 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-04 | 2020-12-04 | 2020-12-04 |  | 2021-04-14 | Overhead | R16 | 2020-12-17 | 1 |  | 10 | 85 | 94 | 2020 | 2021 | R16
160215239976 | 164489239976 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-05 | 2021-01-05 | 2021-07-21 |  | 2022-03-03 | Underground | R16 | 2022-02-02 | 1 | 142 | 141 | 22 | 303 | 2021 | 2022 | R16
162739209247 | 161545209247 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-30 | 2020-10-30 | 2020-10-30 | 2021-01-11 | 2021-01-12 | Underground | R16 | 2021-01-11 | 1 |  | 52 | 2 | 53 | 2020 | 2021 | R16
168316219042 | 160905219042 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-29 | 2021-01-29 | 2021-01-29 | 2021-05-03 | 2021-11-05 | Overhead | R16 | 2021-05-03 | 1 |  | 67 | 135 | 201 | 2021 | 2021 | R16
165986242890 | 168641242890 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-04-16 | 2021-07-16 | 2021-08-10 |  | 2023-08-24 | Underground | R16 | 2023-08-03 | 66 | 18 | 518 | 16 | 615 | 2021 | 2023 | R16
161249247638 | 169868247638 | NON-RESIDENTIAL - SMALL RETAIL | R16 RESD AND NON RESD US | Commercial | 2020-10-22 | 2020-10-22 | 2021-09-13 |  | 2021-11-09 | Underground | R16 |  | 1 | 233 |  |  | 274 | 2020 | 2021 | R16
160796234125 | 162362234125 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-03 | 2021-05-28 | 2021-06-09 | 2021-07-16 | 2021-10-25 | Overhead | R16 | 2021-07-16 | 20 | 9 | 28 | 72 | 126 | 2021 | 2021 | R16
167324147982 | 160513147982 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-28 | 2019-03-28 | 2019-04-02 |  | 2019-06-03 | Underground | R16 | 2019-05-14 | 1 | 4 | 31 | 15 | 48 | 2019 | 2019 | R16
169174149429 | 163572149429 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-15 | 2019-04-17 | 2019-04-17 |  | 2019-06-03 | Overhead | R16 | 2019-05-13 | 3 |  | 19 | 16 | 36 | 2019 | 2019 | R16
162553200387 | 163386200387 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-12 | 2020-08-12 | 2020-08-12 |  | 2022-10-20 | Overhead | R16 |  | 1 |  |  |  | 572 | 2020 | 2022 | R16
165369141918 | 161011141918 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-02 | 2019-02-02 | 2019-02-02 |  | 2019-04-08 | Overhead | R16 | 2019-03-05 | 0 |  | 22 | 25 | 46 | 2019 | 2019 | R16
160337143146 | 160433143146 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-30 | 2019-01-30 | 2019-02-13 | 2019-06-12 | 2019-06-13 | Underground | R16 | 2019-06-12 | 1 | 11 | 86 | 2 | 97 | 2019 | 2019 | R16
168813218364 | 169747218364 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-09 | 2020-09-19 | 2021-01-25 | 2021-02-17 | 2021-04-15 | Underground | R16 | 2021-02-17 | 8 | 91 | 18 | 42 | 157 | 2020 | 2021 | R16
161432206496 | 166382206496 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-07 | 2020-10-07 | 2020-10-07 |  | 2021-11-09 | Overhead | R16 | 2020-11-16 | 1 |  | 29 | 257 | 285 | 2020 | 2021 | R16
161214219540 | 161447219540 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-02 | 2021-02-03 | 2021-02-03 | 2021-02-16 | 2021-05-06 | Overhead | R16 | 2021-02-16 | 2 |  | 10 | 58 | 68 | 2021 | 2021 | R16
166641151058 | 165900151058 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-01 | 2019-04-24 | 2019-05-03 |  | 2020-06-09 | Overhead | R16 |  | 39 | 8 |  |  | 333 | 2019 | 2020 | R16
160307203928 | 160829203928 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-15 | 2020-09-15 | 2020-09-15 |  | 2021-07-26 | Overhead | R16 | 2020-10-29 | 1 |  | 33 | 193 | 225 | 2020 | 2021 | R16
169039150444 | 162042150444 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-04-05 | 2019-04-05 | 2019-04-26 |  | 2020-06-09 | Overhead | R16 |  | 1 | 16 |  |  | 308 | 2019 | 2020 | R16
162045162782 | 162259162782 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-05 | 2019-06-05 | 2019-08-29 |  | 2019-09-18 | Underground | R16 | 2019-09-09 | 1 | 62 | 8 | 8 | 76 | 2019 | 2019 | R16
162893143703 | 164080143703 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-19 | 2019-02-19 | 2019-02-19 | 2019-12-10 | 2021-11-13 | Overhead | R16 | 2019-12-10 | 1 |  | 211 | 504 | 714 | 2019 | 2021 | R16
169405230135 | 164871230135 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-12 | 2021-05-12 | 2021-05-12 |  | 2021-09-01 | Overhead | R16 | 2021-08-09 | 1 |  | 64 | 18 | 81 | 2021 | 2021 | R16
161020219128 | 167884219128 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-18 | 2021-01-30 | 2021-01-30 | 2021-10-26 | 2021-12-01 | Overhead | R16 | 2021-10-26 | 10 |  | 192 | 27 | 228 | 2021 | 2021 | R16
166460225168 | 164591225168 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-03-30 | 2021-03-30 | 2021-03-30 | 2022-04-24 | 2022-04-27 | Overhead | R16 | 2022-04-24 | 1 |  | 279 | 3 | 282 | 2021 | 2022 | R16
164797212679 | 168469212679 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-04 | 2020-12-04 | 2020-12-04 | 2021-02-02 | 2021-06-03 | Overhead | R16 | 2021-02-02 | 1 |  | 43 | 88 | 130 | 2020 | 2021 | R16
168439150928 | 166342150928 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2019-04-30 | 2019-04-30 | 2019-04-30 | 2019-12-28 | 2019-12-31 | Overhead | R16 | 2019-12-28 | 1 |  | 174 | 2 | 176 | 2019 | 2019 | R16
163263152570 | 169505152570 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-16 | 2019-05-16 | 2019-05-16 |  | 2019-08-12 | Overhead | R16 | 2019-06-12 | 1 |  | 20 | 44 | 63 | 2019 | 2019 | R16
169041231298 | 168450231298 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2021-05-19 | 2021-05-19 | 2021-05-19 | 2022-09-15 | 2022-09-16 | Underground | R16 | 2022-09-15 | 1 |  | 347 | 2 | 348 | 2021 | 2022 | R16
166704220798 | 165250220798 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-18 | 2021-02-18 | 2021-02-18 | 2021-07-13 | 2021-07-14 | Overhead | R16 | 2021-07-13 | 1 |  | 104 | 2 | 105 | 2021 | 2021 | R16
160412201238 | 165834201238 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-08-21 | 2020-08-21 | 2020-08-21 | 2020-09-11 | 2022-01-03 | Overhead | R16 | 2020-09-11 | 1 |  | 16 | 342 | 357 | 2020 | 2022 | R16
164446145666 | 167456145666 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-11 | 2019-03-11 | 2019-03-11 |  | 2019-12-19 | Underground | R16 | 2019-08-12 | 1 |  | 111 | 94 | 204 | 2019 | 2019 | R16
165135206945 | 166639206945 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | R16 ELECTRIC RELOCATION US | Residential | 2020-10-08 | 2020-10-08 | 2020-10-12 |  | 2021-08-02 | Underground | R16 |  | 1 | 3 |  |  | 213 | 2020 | 2021 | R16
160992204089 | 166162204089 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-24 | 2020-08-24 | 2020-09-17 |  | 2021-06-03 | Underground | R16 | 2021-03-09 | 1 | 19 | 124 | 63 | 204 | 2020 | 2021 | R16
166512143167 | 163457143167 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-14 | 2019-02-14 | 2019-02-14 |  | 2020-06-09 | Overhead | R16 | 2020-01-15 | 1 |  | 240 | 105 | 344 | 2019 | 2020 | R16
163957143545 | 164100143545 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2019-02-19 | 2019-02-19 | 2019-02-19 | 2019-11-19 | 2020-04-13 | Underground | R16 | 2019-11-19 | 1 |  | 196 | 105 | 300 | 2019 | 2020 | R16
165238155192 | 167658155192 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-05-07 | 2019-05-07 | 2019-06-13 |  | 2023-06-08 | Underground | R16 | 2019-08-08 | 1 | 28 | 41 | 1001 | 1068 | 2019 | 2023 | R16
166687182870 | 166794182870 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-03-06 | 2019-03-06 | 2020-03-04 | 2020-05-19 | 2020-05-26 | Underground | R16 | 2020-05-19 | 1 | 261 | 55 | 6 | 320 | 2019 | 2020 | R16
161394140568 | 167689140568 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-01-17 | 2019-01-17 | 2019-01-17 | 2019-06-04 | 2019-06-05 | Underground | R16 | 2019-06-04 | 1 |  | 99 | 2 | 100 | 2019 | 2019 | R16
168718226261 | 162462226261 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-02-05 | 2021-02-05 | 2021-04-08 |  | 2021-11-13 | Underground | R16 | 2021-04-19 | 1 | 45 | 8 | 150 | 201 | 2021 | 2021 | R16
163429227640 | 167750227640 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2021-03-02 | 2021-04-14 | 2021-04-19 |  | 2021-11-03 | Overhead | R16 |  | 32 | 4 |  |  | 177 | 2021 | 2021 | R16
166172153409 | 160724153409 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-23 | 2019-05-24 | 2019-05-24 |  | 2023-06-08 | Overhead | R16 | 2019-07-10 | 2 |  | 34 | 1022 | 1056 | 2019 | 2023 | R16
167421217878 | 167030217878 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-14 | 2021-01-14 | 2021-01-22 | 2021-03-03 | 2021-08-16 | Overhead | R16 | 2021-03-03 | 1 | 7 | 29 | 119 | 153 | 2021 | 2021 | R16
168536154114 | 163278154114 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2019-02-13 | 2019-02-13 | 2019-06-04 | 2019-09-27 | 2021-09-23 | Underground | R16 | 2019-09-27 | 1 | 80 | 84 | 520 | 682 | 2019 | 2021 | R16
162212160573 | 168606160573 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-05-13 | 2019-05-13 | 2019-08-08 | 2020-05-28 | 2020-05-29 | Underground | R16 | 2020-05-28 | 1 | 64 | 211 | 2 | 275 | 2019 | 2020 | R16
165842205621 | 162573205621 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-09-22 | 2020-09-24 | 2020-09-28 |  | 2021-06-30 | Overhead | R16 |  | 3 | 3 |  |  | 202 | 2020 | 2021 | R16
165756225536 | 165335225536 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-02 | 2021-04-02 | 2021-04-02 | 2021-07-27 | 2021-08-23 | Overhead | R16 | 2021-07-27 | 1 |  | 83 | 20 | 102 | 2021 | 2021 | R16
160411172233 | 160796172233 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-24 | 2019-05-24 | 2019-11-19 | 2020-02-06 | 2020-06-09 | Underground | R16 | 2020-02-06 | 1 | 128 | 58 | 89 | 273 | 2019 | 2020 | R16
169646200308 | 163258200308 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-12 | 2020-08-12 | 2020-08-12 | 2020-08-13 | 2020-10-06 | Overhead | R16 | 2020-08-13 | 1 |  | 2 | 39 | 40 | 2020 | 2020 | R16
160386238114 | 160220238114 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-05-27 | 2021-05-27 | 2021-07-08 |  | 2023-10-16 | Underground | R16 |  | 1 | 31 |  |  | 623 | 2021 | 2023 | R16
162048149477 | 164175149477 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-04-18 | 2019-04-18 | 2019-04-18 |  | 2019-05-28 | Overhead | R16 | 2019-05-03 | 1 |  | 12 | 18 | 29 | 2019 | 2019 | R16
161251225578 | 165394225578 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-02 | 2021-04-05 | 2021-04-05 | 2021-05-11 | 2021-11-08 | Overhead | R16 | 2021-05-11 | 2 |  | 27 | 130 | 157 | 2021 | 2021 | R16
167828148935 | 163110148935 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-11 | 2019-04-12 | 2019-04-12 |  | 2021-11-05 | Underground | R16 | 2021-04-16 | 2 |  | 526 | 146 | 672 | 2019 | 2021 | R16
167167200851 | 164253200851 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-18 | 2020-08-18 | 2020-08-18 |  | 2022-08-03 | Overhead | R16 |  | 1 |  |  |  | 512 | 2020 | 2022 | R16
163129225301 | 164197225301 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-03-30 | 2021-03-30 | 2021-03-30 | 2021-03-30 | 2021-11-04 | Overhead | R16 | 2021-03-30 | 1 |  |  | 158 | 158 | 2021 | 2021 | R16
164678143216 | 166467143216 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-01-10 | 2019-01-10 | 2019-02-15 |  | 2019-10-30 | Underground | R16 | 2019-10-21 | 1 | 27 | 177 | 8 | 210 | 2019 | 2019 | R16
162572199939 | 162523199939 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-08-07 | 2020-08-07 | 2020-08-07 |  | 2020-12-17 | Overhead | R16 | 2020-09-17 | 1 |  | 30 | 66 | 95 | 2020 | 2020 | R16
169803225992 | 165077225992 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-01-05 | 2021-04-07 | 2021-04-07 |  | 2022-01-12 | Underground | R16 | 2021-12-03 | 67 |  | 173 | 29 | 267 | 2021 | 2022 | R16
161246200407 | 162431200407 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-08-06 | 2020-08-06 | 2020-08-12 |  | 2020-10-06 | Overhead | R16 |  | 1 | 5 |  |  | 44 | 2020 | 2020 | R16
160824157156 | 161358157156 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Residential | 2019-04-03 | 2019-04-03 | 2019-07-09 | 2022-05-11 | 2022-06-02 | Overhead | R16 | 2022-05-11 | 1 | 70 | 742 | 17 | 827 | 2019 | 2022 | R16
162436203864 | 169935203864 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-10 | 2020-09-10 | 2020-09-14 | 2020-10-21 | 2021-07-07 | Overhead | R16 | 2020-10-21 | 1 | 3 | 28 | 186 | 215 | 2020 | 2021 | R16
169187155485 | 163381155485 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-14 | 2019-04-14 | 2019-06-17 | 2019-08-10 | 2019-08-13 | Underground | R16 | 2019-08-10 | 0 | 46 | 40 | 2 | 87 | 2019 | 2019 | R16
160834230567 | 163730230567 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-06 | 2021-05-06 | 2021-05-13 | 2021-07-22 | 2021-07-27 | Overhead | R16 | 2021-07-22 | 1 | 6 | 51 | 4 | 59 | 2021 | 2021 | R16
165422147951 | 161275147951 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-02 | 2019-04-02 | 2019-04-03 |  | 2019-06-03 | Overhead | R16 | 2019-05-09 | 1 | 2 | 27 | 18 | 45 | 2019 | 2019 | R16
167656141130 | 168726141130 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-01-24 | 2019-01-24 | 2019-01-24 |  | 2019-08-12 | Overhead | R16 | 2019-06-18 | 1 |  | 104 | 40 | 143 | 2019 | 2019 | R16
169178207210 | 167906207210 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-14 | 2020-10-14 | 2020-10-14 | 2021-01-27 | 2021-04-23 | Overhead | R16 | 2021-01-27 | 1 |  | 76 | 63 | 138 | 2020 | 2021 | R16
166273178578 | 160393178578 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2019-05-22 | 2019-05-22 | 2020-01-29 |  | 2020-06-09 | Overhead | R16 | 2020-03-24 | 1 | 181 | 40 | 56 | 275 | 2019 | 2020 | R16
160501183637 | 169785183637 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-05-18 | 2019-05-18 | 2020-03-10 |  | 2020-10-06 | Underground | R16 |  | 0 | 212 |  |  | 362 | 2019 | 2020 | R16
168675225111 | 165257225111 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-02-18 | 2021-02-18 | 2021-03-29 |  | 2021-11-05 | Overhead | R16 | 2021-04-07 | 1 | 28 | 8 | 153 | 187 | 2021 | 2021 | R16
163277149606 | 161407149606 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-03 | 2019-04-03 | 2019-04-19 |  | 2019-08-12 | Underground | R16 | 2019-05-30 | 1 | 13 | 30 | 53 | 94 | 2019 | 2019 | R16
160057199291 | 161363199291 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-07-31 | 2020-07-31 | 2020-07-31 |  | 2020-10-06 | Overhead | R16 | 2020-08-07 | 1 |  | 6 | 43 | 48 | 2020 | 2020 | R16
164323146491 | 168696146491 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-18 | 2019-03-18 | 2019-03-19 |  | 2019-10-16 | Underground | R16 | 2019-10-07 | 1 | 2 | 145 | 8 | 153 | 2019 | 2019 | R16
163123221847 | 169740221847 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-26 | 2021-02-26 | 2021-02-26 | 2021-04-27 | 2021-11-03 | Overhead | R16 | 2021-04-27 | 24 |  | 43 | 137 | 202 | 2021 | 2021 | R16
167274262852 | 167351262852 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2020-11-28 | 2020-11-28 | 2021-12-29 |  | 2022-08-29 | Underground | R16 | 2022-08-26 | 0 | 283 | 173 | 2 | 456 | 2020 | 2022 | R16
161303232582 | 162794232582 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-05-04 | 2021-05-04 | 2021-05-27 |  | 2023-01-10 | Underground | R16 | 2022-11-10 | 1 | 18 | 381 | 44 | 441 | 2021 | 2023 | R16
169819149727 | 162957149727 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-04-11 | 2019-04-15 | 2019-04-19 |  | 2021-11-13 | Underground | R16 |  | 3 | 5 |  |  | 677 | 2019 | 2021 | R16
167714232063 | 160585232063 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-26 | 2021-05-23 | 2021-05-23 | 2021-06-11 | 2021-08-12 | Overhead | R16 | 2021-06-11 | 20 |  | 15 | 45 | 79 | 2021 | 2021 | R16
167617208972 | 167849208972 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-31 | 2020-08-31 | 2020-10-29 | 2022-01-06 | 2022-01-07 | Underground | R16 | 2022-01-06 | 1 | 44 | 311 | 2 | 355 | 2020 | 2022 | R16
160778207649 | 168654207649 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-19 | 2020-10-19 | 2020-10-19 |  | 2021-07-19 | Overhead | R16 | 2020-11-25 | 1 |  | 28 | 169 | 196 | 2020 | 2021 | R16
162707141713 | 169541141713 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-29 | 2019-01-29 | 2019-01-29 |  | 2019-03-11 | Overhead | R16 | 2019-02-19 | 1 |  | 16 | 15 | 30 | 2019 | 2019 | R16
169494222075 | 167553222075 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-01 | 2021-03-01 | 2021-03-01 | 2021-04-21 | 2021-04-22 | Overhead | R16 | 2021-04-21 | 1 |  | 38 | 2 | 39 | 2021 | 2021 | R16
163226205049 | 168237205049 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-09-02 | 2020-09-04 | 2020-09-25 |  | 2021-01-08 | Overhead | R16 |  | 3 | 16 |  |  | 93 | 2020 | 2021 | R16
164539143283 | 167886143283 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-01-17 | 2019-01-17 | 2019-02-14 |  | 2019-07-18 | Overhead | R16 | 2019-07-02 | 1 | 21 | 99 | 13 | 131 | 2019 | 2019 | R16
167306211147 | 165701211147 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-18 | 2020-11-18 | 2020-11-18 |  | 2021-04-29 | Overhead | R16 | 2021-02-11 | 1 |  | 62 | 56 | 117 | 2020 | 2021 | R16
162697206760 | 167061206760 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-09 | 2020-10-09 | 2020-10-09 |  | 2021-08-03 | Overhead | R16 | 2021-03-29 | 1 |  | 122 | 92 | 213 | 2020 | 2021 | R16
168463216493 | 165508216493 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-07 | 2021-01-07 | 2021-01-07 | 2021-03-26 | 2021-11-09 | Overhead | R16 | 2021-03-26 | 1 |  | 57 | 163 | 219 | 2021 | 2021 | R16
163234204489 | 163245204489 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-11 | 2020-08-11 | 2020-09-22 | 2020-10-06 | 2021-01-12 | Underground | R16 | 2020-10-06 | 1 | 31 | 11 | 71 | 111 | 2020 | 2021 | R16
163507227766 | 167890227766 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-02 | 2021-03-18 | 2021-04-20 |  | 2021-11-05 | Overhead | R16 | 2021-05-04 | 13 | 24 | 11 | 134 | 179 | 2021 | 2021 | R16
161126148123 | 169254148123 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-01-28 | 2019-01-28 | 2019-04-03 | 2019-11-14 | 2019-11-15 | Underground | R16 | 2019-11-14 | 1 | 48 | 162 | 2 | 210 | 2019 | 2019 | R16
161832211361 | 165918211361 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-19 | 2020-11-19 | 2020-11-19 |  | 2021-10-25 | Overhead | R16 | 2021-07-22 | 1 |  | 176 | 68 | 243 | 2020 | 2021 | R16
162283201988 | 167212201988 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-27 | 2020-08-27 | 2020-08-27 |  | 2021-04-07 | Underground | R16 | 2020-12-04 | 1 |  | 72 | 89 | 160 | 2020 | 2021 | R16
160935219686 | 162324219686 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-04 | 2021-02-04 | 2021-02-04 |  | 2021-11-04 | Overhead | R16 | 2021-06-24 | 1 |  | 101 | 96 | 196 | 2021 | 2021 | R16
164948146940 | 167795146940 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-03-12 | 2019-03-12 | 2019-03-22 |  | 2021-01-08 | Underground | R16 | 2020-10-05 | 1 | 9 | 402 | 70 | 479 | 2019 | 2021 | R16
161660230811 | 165845230811 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-04-06 | 2021-04-21 | 2021-05-14 | 2022-01-07 | 2022-02-07 | Underground | R16 | 2022-01-07 | 12 | 18 | 171 | 22 | 220 | 2021 | 2022 | R16
162797151857 | 168243151857 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-09 | 2019-05-09 | 2019-05-09 |  | 2019-08-12 | Overhead | R16 | 2019-06-04 | 1 |  | 19 | 50 | 68 | 2019 | 2019 | R16
169661219272 | 160545219272 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-26 | 2020-11-04 | 2021-02-02 | 2021-07-13 | 2021-07-13 | Underground | R16 | 2021-07-13 | 8 | 65 | 116 |  | 187 | 2020 | 2021 | R16
168217211576 | 164882211576 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-13 | 2020-11-17 | 2020-11-24 |  | 2021-11-08 | Overhead | R16 | 2021-04-21 | 3 | 6 | 107 | 144 | 257 | 2020 | 2021 | R16
165253248645 | 165396248645 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2021-02-19 | 2021-06-09 | 2021-09-20 | 2022-08-11 | 2022-10-04 | Underground | R16 | 2022-08-11 | 79 | 74 | 234 | 39 | 423 | 2021 | 2022 | R16
162154142172 | 161234142172 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-04 | 2019-02-04 | 2019-02-04 | 2019-07-11 | 2019-07-12 | Overhead | R16 | 2019-07-11 | 1 |  | 114 | 2 | 115 | 2019 | 2019 | R16
160327203497 | 160366203497 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-09-11 | 2020-09-11 | 2020-09-11 |  | 2021-01-20 | Overhead | R16 | 2020-10-08 | 1 |  | 20 | 75 | 94 | 2020 | 2021 | R16
162481152344 | 163361152344 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-04-13 | 2019-04-13 | 2019-05-14 |  | 2020-11-24 | Underground | R16 |  | 0 | 22 |  |  | 422 | 2019 | 2020 | R16
165266155861 | 161415155861 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-30 | 2019-05-30 | 2019-06-19 |  | 2019-09-12 | Underground | R16 | 2019-09-06 | 1 | 15 | 58 | 5 | 76 | 2019 | 2019 | R16
164704139522 | 165584139522 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-01-07 | 2019-01-07 | 2019-01-07 | 2019-04-05 | 2019-04-09 | Overhead | R16 | 2019-04-05 | 1 |  | 65 | 3 | 67 | 2019 | 2019 | R16
162954313981 | 165948313981 | SPECIFIC BUDGET PROJECTS | UG R16 RESD AND NON RESD UD | Commercial | 2020-11-19 | 2021-02-04 | 2023-03-28 |  | 2023-06-30 | Underground | R16 |  | 56 | 559 |  |  | 682 | 2020 | 2023 | R16
168242212363 | 167205212363 | REAR/CABLE POLE W/UG NON-RESIDENTIAL | OH CP R16 WORK RELO TO UG | Commercial | 2020-08-28 | 2020-08-31 | 2020-12-01 | 2021-01-11 | 2022-03-28 | Overhead | R16 | 2021-01-11 | 2 | 67 | 30 | 316 | 412 | 2020 | 2022 | R16
165194174116 | 168929174116 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-05-14 | 2019-05-14 | 2019-12-12 |  | 2020-07-08 | Underground | R16 |  | 1 | 153 |  |  | 302 | 2019 | 2020 | R16
168852243052 | 160796243052 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-16 | 2021-03-16 | 2021-08-11 | 2021-09-23 | 2021-10-28 | Underground | R16 | 2021-09-23 | 1 | 107 | 32 | 26 | 163 | 2021 | 2021 | R16
163090222419 | 169750222419 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-26 | 2021-03-05 | 2021-03-05 | 2021-10-20 | 2023-06-08 | Overhead | R16 | 2021-10-20 | 29 |  | 164 | 427 | 618 | 2021 | 2023 | R16
163348141726 | 160240141726 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-29 | 2019-01-29 | 2019-01-29 |  | 2019-04-01 | Overhead | R16 | 2019-02-28 | 1 |  | 23 | 23 | 45 | 2019 | 2019 | R16
161800220447 | 164004220447 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-12 | 2021-02-12 | 2021-02-12 | 2021-03-24 | 2021-11-05 | Overhead | R16 | 2021-03-24 | 1 |  | 29 | 163 | 191 | 2021 | 2021 | R16
168408281780 | 163903281780 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2020-12-29 | 2022-06-06 | 2022-06-06 | 2022-07-12 | 2022-08-18 | Overhead | R16 | 2022-07-12 | 375 |  | 27 | 28 | 428 | 2020 | 2022 | R16
161428151683 | 167780151683 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-07 | 2019-05-07 | 2019-05-07 |  | 2019-08-12 | Underground | R16 | 2019-06-04 | 1 |  | 21 | 50 | 70 | 2019 | 2019 | R16
165858160158 | 168614160158 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2019-05-13 | 2019-05-23 | 2019-08-05 |  | 2019-12-04 | Underground | R16 |  | 9 | 53 |  |  | 148 | 2019 | 2019 | R16
162963147488 | 167661147488 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2019-03-11 | 2019-03-28 | 2019-03-28 | 2020-07-15 | 2020-07-17 | Overhead | R16 | 2020-07-15 | 14 |  | 340 | 3 | 355 | 2019 | 2020 | R16
166955224032 | 161523224032 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-18 | 2021-03-18 | 2021-03-18 | 2021-05-17 | 2022-08-03 | Overhead | R16 | 2021-05-17 | 1 |  | 43 | 318 | 360 | 2021 | 2022 | R16
169158209945 | 164522209945 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-29 | 2020-09-29 | 2020-11-06 | 2020-11-10 | 2021-04-15 | Underground | R16 | 2020-11-10 | 1 | 29 | 3 | 113 | 143 | 2020 | 2021 | R16
168031227831 | 162576227831 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-22 | 2021-04-21 | 2021-04-21 | 2021-05-28 | 2021-11-04 | Overhead | R16 | 2021-05-28 | 23 |  | 28 | 115 | 164 | 2021 | 2021 | R16
162259139946 | 166645139946 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-10 | 2019-01-10 | 2019-01-11 |  | 2019-02-21 | Overhead | R16 | 2019-02-11 | 1 | 2 | 22 | 9 | 31 | 2019 | 2019 | R16
168773153342 | 160743153342 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-05-23 | 2019-05-23 | 2019-05-23 |  | 2019-07-08 | Overhead | R16 | 2019-07-01 | 1 |  | 28 | 6 | 33 | 2019 | 2019 | R16
161806153252 | 160833153252 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-05-24 | 2019-05-24 | 2019-05-24 |  | 2020-06-09 | Underground | R16 | 2020-04-03 | 1 |  | 226 | 48 | 273 | 2019 | 2020 | R16
163962205594 | 162154205594 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2020-09-21 | 2020-09-23 | 2020-09-29 | 2020-12-20 | 2021-01-07 | Underground | R16 | 2020-12-20 | 3 | 5 | 59 | 14 | 79 | 2020 | 2021 | R16
167200154484 | 161380154484 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2019-05-29 | 2019-05-30 | 2019-06-05 |  | 2019-12-19 | Overhead | R16 | 2019-08-08 | 2 | 5 | 47 | 96 | 147 | 2019 | 2019 | R16
163737218758 | 160611218758 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-28 | 2021-01-28 | 2021-01-28 |  | 2021-11-08 | Overhead | R16 | 2021-05-26 | 1 |  | 85 | 119 | 203 | 2021 | 2021 | R16
162184227024 | 166406227024 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-10-07 | 2020-10-07 | 2021-04-15 | 2022-02-01 | 2022-03-03 | Underground | R16 | 2022-02-01 | 1 | 137 | 209 | 23 | 367 | 2020 | 2022 | R16
164186231797 | 168799231797 | FOREIGN UTILITY | OH R16 RES NON RES OS | Commercial | 2021-05-21 | 2021-05-21 | 2021-05-21 |  | 2021-10-25 | Overhead | R16 | 2021-08-13 | 1 |  | 61 | 52 | 112 | 2021 | 2021 | R16
165629145773 | 165907145773 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-01 | 2019-03-07 | 2019-03-11 |  | 2019-06-03 | Overhead | R16 |  | 5 | 3 |  |  | 67 | 2019 | 2019 | R16
162047151928 | 168036151928 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Commercial | 2019-05-09 | 2019-05-09 | 2019-05-09 |  | 2019-10-16 | Overhead | R16 | 2019-10-07 | 1 |  | 108 | 8 | 115 | 2019 | 2019 | R16
168128163913 | 162457163913 | CUST REQUESTED UPGRADES & SERVICES UG | CUST UG UPGRADE SVC | Commercial | 2019-06-05 | 2019-06-05 | 2019-09-09 | 2020-04-07 | 2020-12-22 | Overhead | R16 | 2020-04-07 | 1 | 69 | 152 | 186 | 405 | 2019 | 2020 | R16
162990207381 | 160672207381 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-14 | 2020-09-14 | 2020-10-14 | 2020-12-17 | 2021-01-06 | Underground | R16 | 2020-12-17 | 1 | 23 | 47 | 15 | 83 | 2020 | 2021 | R16
168395153423 | 160521153423 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-22 | 2019-05-22 | 2019-05-23 |  | 2019-08-26 | Overhead | R16 | 2019-06-26 | 1 | 2 | 25 | 44 | 69 | 2019 | 2019 | R16
167459225959 | 167885225959 | NON-RESIDENTIAL - SMALL RETAIL | R16 RESD AND NON RESD US | Commercial | 2019-01-17 | 2019-01-17 | 2021-04-07 |  | 2021-11-10 | Underground | R16 |  | 1 | 580 |  |  | 735 | 2019 | 2021 | R16
162089210544 | 163685210544 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2020-11-09 | 2020-11-10 | 2020-11-12 |  | 2021-11-05 | Underground | R16 |  | 2 | 3 |  |  | 260 | 2020 | 2021 | R16
169271155138 | 160686155138 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-05-23 | 2019-05-23 | 2019-06-13 | 2019-07-08 | 2019-07-08 | Underground | R16 | 2019-07-08 | 1 | 16 | 18 |  | 33 | 2019 | 2019 | R16
168261152274 | 168890152274 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-14 | 2019-05-14 | 2019-05-14 |  | 2019-08-12 | Overhead | R16 | 2019-06-21 | 1 |  | 29 | 37 | 65 | 2019 | 2019 | R16
161057206307 | 165891206307 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-10-05 | 2020-10-05 | 2020-10-05 |  | 2021-07-24 | Overhead | R16 | 2020-11-06 | 1 |  | 25 | 186 | 210 | 2020 | 2021 | R16
160773144557 | 165820144557 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-03-01 | 2019-03-01 | 2019-03-01 | 2019-10-01 | 2019-10-02 | Underground | R16 | 2019-10-01 | 1 |  | 153 | 2 | 154 | 2019 | 2019 | R16
169154226729 | 167740226729 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-13 | 2021-04-13 | 2021-04-13 |  | 2021-08-23 | Overhead | R16 | 2021-07-12 | 1 |  | 65 | 31 | 95 | 2021 | 2021 | R16
163770207452 | 161814207452 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Commercial | 2020-08-03 | 2020-10-13 | 2020-10-16 |  | 2021-01-27 | Overhead | R16 |  | 52 | 4 |  |  | 128 | 2020 | 2021 | R16
165788207670 | 165494207670 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-08-21 | 2020-08-21 | 2020-10-20 |  | 2021-04-13 | Underground | R16 | 2020-12-08 | 1 | 43 | 36 | 91 | 168 | 2020 | 2021 | R16
160696218381 | 164826218381 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-01-05 | 2021-01-05 | 2021-01-25 | 2021-04-27 | 2022-07-22 | Underground | R16 | 2021-04-27 | 1 | 15 | 67 | 324 | 404 | 2021 | 2022 | R16
164945228842 | 168960228842 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-04-19 | 2021-04-29 | 2021-04-29 |  | 2021-11-04 | Overhead | R16 | 2021-06-24 | 9 |  | 41 | 96 | 144 | 2021 | 2021 | R16
164739148601 | 160755148601 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-03-29 | 2019-04-08 | 2019-04-08 |  | 2019-05-20 | Overhead | R16 | 2019-04-19 | 7 |  | 10 | 22 | 37 | 2019 | 2019 | R16
163330220535 | 164262220535 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-14 | 2021-02-14 | 2021-02-14 |  | 2021-11-13 | Overhead | R16 | 2021-04-19 | 0 |  | 46 | 150 | 195 | 2021 | 2021 | R16
168727244233 | 161193244233 | NON-RESIDENTIAL - SMALL RETAIL | R16 RESD AND NON RESD US | Commercial | 2021-03-17 | 2021-03-17 | 2021-08-18 | 2023-05-04 | 2023-07-18 | Underground | R16 | 2023-05-04 | 1 | 111 | 447 | 54 | 610 | 2021 | 2023 | R16
168979228626 | 161141228626 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-28 | 2021-04-28 | 2021-04-28 |  | 2021-08-18 | Overhead | R16 | 2021-06-16 | 1 |  | 36 | 46 | 81 | 2021 | 2021 | R16
163058147370 | 160450147370 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2019-03-28 | 2019-03-28 | 2019-03-28 |  | 2019-08-12 | Underground | R16 | 2019-06-12 | 1 |  | 55 | 44 | 98 | 2019 | 2019 | R16
162351224024 | 165988224024 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-23 | 2021-03-16 | 2021-03-17 |  | 2021-11-05 | Overhead | R16 | 2021-05-05 | 16 | 2 | 36 | 133 | 184 | 2021 | 2021 | R16
161561152486 | 167332152486 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-03-08 | 2019-03-08 | 2019-05-16 |  | 2020-07-09 | Underground | R16 | 2020-05-28 | 1 | 50 | 271 | 31 | 350 | 2019 | 2020 | R16
165835145606 | 167482145606 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2019-03-11 | 2019-03-11 | 2019-03-11 | 2019-05-06 | 2019-05-09 | Underground | R16 | 2019-05-06 | 1 |  | 41 | 4 | 44 | 2019 | 2019 | R16
160770219946 | 162839219946 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-08 | 2021-02-08 | 2021-02-08 | 2021-03-01 | 2021-06-02 | Overhead | R16 | 2021-03-01 | 1 |  | 16 | 68 | 83 | 2021 | 2021 | R16
168278148765 | 162624148765 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-09 | 2019-04-09 | 2019-04-09 |  | 2019-05-28 | Overhead | R16 | 2019-04-24 | 1 |  | 12 | 25 | 36 | 2019 | 2019 | R16
163777226382 | 166980226382 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-04-09 | 2021-04-09 | 2021-04-09 |  | 2021-11-08 | Overhead | R16 | 2021-04-22 | 1 |  | 10 | 143 | 152 | 2021 | 2021 | R16
167203314217 | 163128314217 | REAR/CABLE POLE W/ UG - RESIDENTIAL | OH CP R16 WORK RELO TO UG | Residential | 2020-09-24 | 2022-06-29 | 2023-03-30 | 2023-04-24 | 2023-06-12 | Overhead | R16 | 2023-04-24 | 460 | 197 | 18 | 36 | 708 | 2020 | 2023 | R16
167203314217 | 163128314217 | RESIDENTIAL - MULTI-FAMILY | OH R16 RES NON RES OS | Residential | 2020-09-24 | 2022-06-29 | 2023-03-30 | 2023-04-24 | 2023-06-12 | Overhead | R16 | 2023-04-24 | 460 | 197 | 18 | 36 | 708 | 2020 | 2023 | R16
164233153624 | 161067153624 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2019-05-28 | 2019-05-28 | 2019-05-28 | 2019-08-12 | 2019-12-06 | Overhead | R16 | 2019-08-12 | 1 |  | 55 | 85 | 139 | 2019 | 2019 | R16
163066139923 | 166613139923 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-01-10 | 2019-01-10 | 2019-01-10 |  | 2019-01-31 | Overhead | R16 | 2019-01-25 | 1 |  | 12 | 5 | 16 | 2019 | 2019 | R16
168605224333 | 162328224333 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2022-04-15 | 2022-09-02 | Overhead | R16 | 2022-04-15 | 1 |  | 280 | 101 | 380 | 2021 | 2022 | R16
162786217662 | 166457217662 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-01-13 | 2021-01-13 | 2021-01-19 |  | 2021-04-22 | Underground | R16 | 2021-01-28 | 1 | 5 | 8 | 61 | 72 | 2021 | 2021 | R16
162725207437 | 164281207437 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2020-09-28 | 2020-10-06 | 2020-10-17 | 2021-08-02 | 2021-08-26 | Underground | R16 | 2021-08-02 | 7 | 9 | 206 | 19 | 239 | 2020 | 2021 | R16
168311157730 | 166568157730 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2019-05-01 | 2019-06-06 | 2019-07-12 |  | 2021-10-25 | Underground | R16 |  | 27 | 27 |  |  | 649 | 2019 | 2021 | R16
168755239170 | 168627239170 | INDUSTRIAL | UG R16 RESD AND NON RESD UD | Commercial | 2020-10-19 | 2021-02-17 | 2021-07-15 | 2023-08-01 | 2023-08-16 | Underground | R16 | 2023-08-01 | 88 | 107 | 534 | 12 | 738 | 2020 | 2023 | R16
168751152639 | 166330152639 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2019-04-30 | 2019-04-30 | 2019-05-17 |  | 2021-04-14 | Underground | R16 |  | 1 | 14 |  |  | 512 | 2019 | 2021 | R16
166934222750 | 168696222750 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-16 | 2021-03-17 | Underground | R16 | 2021-03-16 | 1 |  | 8 | 2 | 9 | 2021 | 2021 | R16
164584148668 | 162400148668 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-08 | 2019-04-08 | 2019-04-08 | 2019-06-24 | 2023-06-08 | Overhead | R16 | 2019-06-24 | 1 |  | 56 | 1034 | 1089 | 2019 | 2023 | R16
160388237532 | 164617237532 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-11 | 2021-07-02 | 2021-07-02 | 2021-10-07 | 2021-11-10 | Overhead | R16 | 2021-10-07 | 39 |  | 70 | 25 | 132 | 2021 | 2021 | R16
163627230497 | 165156230497 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-13 | 2021-05-13 | 2021-05-13 | 2021-06-02 | 2021-08-11 | Overhead | R16 | 2021-06-02 | 1 |  | 15 | 51 | 65 | 2021 | 2021 | R16
160147252271 | 169700252271 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2021-04-21 | 2021-04-21 | 2021-10-15 | 2022-06-17 | 2022-06-27 | Underground | R16 | 2022-06-17 | 1 | 128 | 176 | 7 | 309 | 2021 | 2022 | R16
160553149939 | 165074149939 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-23 | 2019-04-23 | 2019-04-23 | 2019-05-23 | 2019-08-12 | Overhead | R16 | 2019-05-23 | 1 |  | 23 | 58 | 80 | 2019 | 2019 | R16
169375217757 | 168026217757 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-01-20 | 2021-01-20 | 2021-01-20 | 2021-01-21 | 2021-11-11 | Overhead | R16 | 2021-01-21 | 1 |  | 2 | 211 | 212 | 2021 | 2021 | R16
168799221516 | 166642221516 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-25 | 2021-02-25 | 2021-02-25 |  | 2021-08-23 | Overhead | R16 | 2021-07-12 | 1 |  | 98 | 31 | 128 | 2021 | 2021 | R16
164077144625 | 165660144625 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-28 | 2019-02-28 | 2019-02-28 |  | 2019-08-26 | Overhead | R16 | 2019-07-18 | 1 |  | 101 | 28 | 128 | 2019 | 2019 | R16
160985143042 | 161125143042 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-02-04 | 2019-02-04 | 2019-02-12 | 2020-06-01 | 2020-07-10 | Underground | R16 | 2020-06-01 | 1 | 7 | 340 | 30 | 375 | 2019 | 2020 | R16
166051224427 | 162582224427 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-05-10 | 2021-05-11 | Underground | R16 | 2021-05-10 | 1 |  | 36 | 2 | 37 | 2021 | 2021 | R16
163128230219 | 163195230219 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-05-05 | 2021-05-05 | 2021-05-11 | 2021-07-06 | 2023-10-16 | Overhead | R16 | 2021-07-06 | 1 | 5 | 41 | 595 | 639 | 2021 | 2023 | R16
161752226567 | 167261226567 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-28 | 2021-04-12 | 2021-04-12 | 2021-05-19 | 2021-08-31 | Overhead | R16 | 2021-05-19 | 31 |  | 28 | 75 | 132 | 2021 | 2021 | R16
167740211841 | 166903211841 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-24 | 2020-11-24 | 2020-11-24 |  | 2021-04-16 | Overhead | R16 | 2021-01-07 | 1 |  | 33 | 72 | 104 | 2020 | 2021 | R16
162968150343 | 163083150343 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-04-11 | 2019-04-11 | 2019-04-25 |  | 2019-07-11 | Underground | R16 | 2019-07-02 | 1 | 11 | 49 | 8 | 66 | 2019 | 2019 | R16
161488213859 | 167550213859 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2020-10-13 | 2020-10-30 | 2020-12-15 |  | 2021-04-15 | Overhead | R16 |  | 14 | 33 |  |  | 133 | 2020 | 2021 | R16
162862213305 | 169701213305 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-12-09 | 2020-12-09 | 2020-12-09 | 2021-08-05 | 2021-10-27 | Overhead | R16 | 2021-08-05 | 1 |  | 172 | 60 | 231 | 2020 | 2021 | R16
160062219819 | 162833219819 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-08 | 2021-02-08 | 2021-02-08 |  | 2021-08-12 | Overhead | R16 | 2021-03-30 | 1 |  | 37 | 98 | 134 | 2021 | 2021 | R16
162306156452 | 162455156452 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2019-06-05 | 2019-06-05 | 2019-06-27 | 2019-07-31 | 2019-08-01 | Underground | R16 | 2019-07-31 | 1 | 17 | 25 | 2 | 42 | 2019 | 2019 | R16
168891146711 | 169229146711 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2019-03-21 | 2019-03-21 | 2019-03-21 |  | 2022-02-09 | Underground | R16 | 2022-01-06 | 1 |  | 731 | 25 | 755 | 2019 | 2022 | R16
161629222021 | 167295222021 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-28 | 2021-02-28 | 2021-02-28 | 2021-06-22 | 2021-06-23 | Overhead | R16 | 2021-06-22 | 0 |  | 82 | 2 | 83 | 2021 | 2021 | R16
161589244502 | 169896244502 | CUSTOMER UPGRADE IN SERVICE | UG SVC CONVERSION | Residential | 2020-09-10 | 2021-04-01 | 2021-08-19 | 2021-12-09 | 2021-12-09 | Underground | R16 | 2021-12-09 | 146 | 101 | 81 |  | 326 | 2020 | 2021 | R16
163039221387 | 165960221387 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-02-23 | 2021-02-23 | 2021-02-23 |  | 2022-04-21 | Overhead | R16 | 2022-03-22 | 1 |  | 281 | 23 | 303 | 2021 | 2022 | R16
168005153190 | 163149153190 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2019-04-12 | 2019-04-26 | 2019-05-23 |  | 2019-12-19 | Underground | R16 |  | 11 | 20 |  |  | 180 | 2019 | 2019 | R16
160390149494 | 163757149494 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-04-16 | 2019-04-18 | 2019-04-18 | 2019-04-26 | 2019-05-22 | Overhead | R16 | 2019-04-26 | 3 |  | 7 | 19 | 27 | 2019 | 2019 | R16
164183225150 | 164290225150 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-03-29 | 2021-03-29 | 2021-03-29 | 2021-04-07 | 2021-11-11 | Underground | R16 | 2021-04-07 | 1 |  | 8 | 157 | 164 | 2021 | 2021 | R16
163859152268 | 168731152268 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-05-13 | 2019-05-13 | 2019-05-13 | 2019-07-29 | 2019-07-30 | Overhead | R16 | 2019-07-29 | 1 |  | 56 | 2 | 57 | 2019 | 2019 | R16
169321234958 | 160296234958 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-05-27 | 2021-05-27 | 2021-06-15 |  | 2021-11-08 | Underground | R16 | 2021-07-21 | 1 | 14 | 27 | 79 | 118 | 2021 | 2021 | R16
169631270538 | 167509270538 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2020-08-29 | 2022-02-25 | 2022-02-25 | 2022-04-20 | 2022-04-20 | Underground | R16 | 2022-04-20 | 390 |  | 39 |  | 428 | 2020 | 2022 | R16
161207142613 | 162368142613 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2019-02-08 | 2019-02-08 | 2019-02-08 |  | 2019-04-15 | Overhead | R16 | 2019-03-25 | 1 |  | 32 | 16 | 47 | 2019 | 2019 | R16
161088211219 | 165896211219 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-11-19 | 2020-11-19 | 2020-11-19 |  | 2021-04-22 | Overhead | R16 | 2021-02-01 | 1 |  | 53 | 59 | 111 | 2020 | 2021 | R16
165361287724 | 161136287724 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-03 | 2022-08-03 | 2022-08-03 |  | 2022-09-13 | Overhead | R16 | 2022-09-08 | 1 |  | 27 | 4 | 30 | 2022 | 2022 | R16
169646300011 | 160736300011 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-01 | 2022-11-09 | 2022-11-09 |  | 2023-07-26 | Overhead | R16 | 2023-04-06 | 7 |  | 107 | 80 | 192 | 2022 | 2023 | R16
169438303082 | 160409303082 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-31 | 2022-10-31 | 2022-12-21 |  | 2023-09-11 | Underground | R16 | 2023-01-25 | 1 | 38 | 26 | 164 | 226 | 2022 | 2023 | R16
165402331553 | 160909331553 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC DEVELOPMENT | Residential Subdivision | 2023-08-30 | 2023-08-31 | 2023-09-01 | 2023-12-26 | 2023-12-27 | Underground | R16 | 2023-12-26 | 2 | 2 | 83 | 2 | 86 | 2023 | 2023 | R16
160664332442 | 160472332442 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-28 | 2023-08-28 | 2023-09-12 | 2023-11-10 | 2023-12-05 | Overhead | R16 | 2023-11-10 | 1 | 12 | 44 | 18 | 72 | 2023 | 2023 | R16
161000304915 | 166310304915 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-12-05 | 2022-12-05 | 2023-01-30 | 2023-06-02 | 2023-06-05 | Underground | R16 | 2023-06-02 | 1 | 41 | 90 | 2 | 131 | 2022 | 2023 | R16
160220288661 | 162843288661 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-10 | 2022-08-11 | 2022-08-11 | 2023-01-18 | 2023-02-08 | Overhead | R16 | 2023-01-18 | 2 |  | 115 | 16 | 131 | 2022 | 2023 | R16
160102299944 | 169162299944 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2022-10-24 | 2022-10-24 | 2022-11-08 |  | 2023-07-31 | Underground | R16 |  | 1 | 12 |  |  | 201 | 2022 | 2023 | R16
164180296606 | 166373296606 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-10 | 2022-10-10 | 2022-10-10 | 2022-11-03 | 2023-02-03 | Overhead | R16 | 2022-11-03 | 1 |  | 19 | 67 | 85 | 2022 | 2023 | R16
164042332332 | 162979332332 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-09-12 | 2023-09-12 | 2023-09-12 | 2023-10-11 | 2023-12-11 | Overhead | R16 | 2023-10-11 | 1 |  | 22 | 44 | 65 | 2023 | 2023 | R16
169936294282 | 163703294282 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-15 | 2022-08-16 | 2022-09-19 |  | 2023-08-18 | Overhead | R16 |  | 2 | 25 |  |  | 265 | 2022 | 2023 | R16
163195296253 | 165607296253 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-10-05 | 2022-10-05 | 2022-10-07 |  | 2023-03-31 | Overhead | R16 | 2023-02-23 | 1 | 3 | 100 | 27 | 128 | 2022 | 2023 | R16
167342293850 | 166274293850 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-25 | 2022-08-29 | 2022-09-16 |  | 2023-02-03 | Underground | R16 | 2022-12-01 | 3 | 15 | 55 | 47 | 117 | 2022 | 2023 | R16
163968297603 | 168300297603 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-19 | 2022-10-19 | 2022-10-19 |  | 2023-02-27 | Overhead | R16 | 2023-01-03 | 1 |  | 55 | 40 | 94 | 2022 | 2023 | R16
169436312261 | 163862312261 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-17 | 2022-11-17 | 2023-03-13 |  | 2023-05-17 | Overhead | R16 | 2023-03-13 | 1 | 83 |  | 48 | 130 | 2022 | 2023 | R16
166967289018 | 164031289018 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-16 | 2022-08-16 | 2022-08-16 |  | 2022-10-05 | Overhead | R16 | 2022-10-04 | 1 |  | 36 | 2 | 37 | 2022 | 2022 | R16
160434289411 | 164512289411 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-08-17 | 2022-08-17 | 2022-08-17 |  | 2022-09-21 | Overhead | R16 | 2022-09-20 | 1 |  | 25 | 2 | 26 | 2022 | 2022 | R16
161212296327 | 165807296327 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-10-06 | 2022-10-07 | 2022-10-07 | 2023-05-03 | 2023-06-12 | Underground | R16 | 2023-05-03 | 2 |  | 149 | 29 | 178 | 2022 | 2023 | R16
163097295146 | 164205295146 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-09-28 | 2022-09-28 | 2022-09-28 | 2022-12-21 | 2023-01-04 | Overhead | R16 | 2022-12-21 | 1 |  | 61 | 11 | 71 | 2022 | 2023 | R16
168767288215 | 162255288215 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2022-08-08 | 2022-08-08 | 2022-08-08 | 2022-08-31 | 2022-08-31 | Overhead | R16 | 2022-08-31 | 1 |  | 18 |  | 18 | 2022 | 2022 | R16
163252295935 | 163737295935 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-09-27 | 2022-10-05 | 2022-10-05 |  | 2023-01-10 | Overhead | R16 | 2022-11-17 | 7 |  | 32 | 39 | 76 | 2022 | 2023 | R16
165937330282 | 161585330282 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2022-08-04 | 2022-08-04 | 2023-08-22 | 2023-12-03 | 2023-12-06 | Underground | R16 | 2023-12-03 | 1 | 274 | 74 | 3 | 350 | 2022 | 2023 | R16
167751287133 | 169873287133 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2022-07-28 | 2022-07-28 | 2022-07-28 | 2022-09-25 | 2022-09-28 | Overhead | R16 | 2022-09-25 | 1 |  | 42 | 3 | 45 | 2022 | 2022 | R16
162515326960 | 161582326960 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-07-18 | 2023-07-28 | 2023-07-31 | 2023-09-08 | 2023-09-25 | Overhead | R16 | 2023-09-08 | 9 | 2 | 30 | 12 | 50 | 2023 | 2023 | R16
164124302340 | 165629302340 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-10-06 | 2022-10-06 | 2022-12-05 | 2022-12-05 | 2023-07-13 | Overhead | R16 | 2022-12-05 | 1 | 43 |  | 159 | 201 | 2022 | 2023 | R16
168928331080 | 160132331080 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2023-08-24 |  | 2023-08-29 | 2023-10-12 | 2023-11-09 | Overhead | R16 | 2023-10-12 |  |  | 33 | 21 | 56 | 2023 | 2023 | R16
160828302569 | 165091302569 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2022-11-28 | 2022-12-06 | 2022-12-06 | 2023-04-28 | 2023-08-18 | Overhead | R16 | 2023-04-28 | 7 |  | 104 | 81 | 190 | 2022 | 2023 | R16
163303242785 | 169369242785 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-07 | 2021-07-08 | 2021-08-09 |  | 2021-10-26 | Underground | R16 | 2021-09-01 | 2 | 23 | 18 | 40 | 80 | 2021 | 2021 | R16
165015260167 | 161347260167 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-07-16 | 2021-08-02 | 2021-12-07 |  | 2023-04-27 | Underground | R16 | 2023-02-02 | 12 | 92 | 303 | 61 | 465 | 2021 | 2023 | R16
167121238168 | 169646238168 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-08 | 2021-07-08 | 2021-07-08 |  | 2021-10-27 | Overhead | R16 | 2021-08-11 | 1 |  | 25 | 56 | 80 | 2021 | 2021 | R16
163835240652 | 165522240652 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-06-18 | 2021-07-14 | 2021-07-27 |  | 2021-11-01 | Underground | R16 |  | 19 | 10 |  |  | 97 | 2021 | 2021 | R16
168455244299 | 162458244299 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-07-22 | 2021-08-03 | 2021-08-19 |  | 2021-11-10 | Overhead | R16 | 2021-10-15 | 9 | 13 | 42 | 19 | 80 | 2021 | 2021 | R16
161475234214 | 163265234214 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-06-09 | 2021-06-09 | 2021-06-09 |  | 2022-02-02 | Underground | R16 | 2021-12-15 | 1 |  | 136 | 36 | 171 | 2021 | 2022 | R16
167007239200 | 161268239200 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-15 | 2021-07-15 | 2021-07-15 | 2021-10-11 | 2021-10-12 | Overhead | R16 | 2021-10-11 | 1 |  | 63 | 2 | 64 | 2021 | 2021 | R16
163459269268 | 168248269268 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-02 | 2021-07-15 | 2022-02-16 |  | 2022-04-27 | Underground | R16 | 2022-03-31 | 10 | 155 | 32 | 20 | 214 | 2021 | 2022 | R16
162065243342 | 164799243342 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-15 | 2021-06-16 | 2021-08-12 | 2022-01-02 | 2022-01-05 | Underground | R16 | 2022-01-02 | 2 | 42 | 102 | 3 | 147 | 2021 | 2022 | R16
169020239936 | 162645239936 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-09-01 | 2021-10-25 | Overhead | R16 | 2021-09-01 | 1 |  | 31 | 39 | 69 | 2021 | 2021 | R16
161205271358 | 161948271358 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-06-04 | 2021-08-31 | 2022-03-03 | 2022-11-22 | 2022-12-30 | Underground | R16 | 2022-11-22 | 63 | 133 | 189 | 29 | 411 | 2021 | 2022 | R16
160510244499 | 162188244499 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-04 | 2021-06-04 | 2021-08-20 | 2022-09-28 | 2022-09-29 | Overhead | R16 | 2022-09-28 | 1 | 56 | 289 | 2 | 345 | 2021 | 2022 | R16
168798238166 | 169474238166 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-07-08 | 2021-07-08 | 2021-07-08 | 2021-10-14 | 2021-11-10 | Overhead | R16 | 2021-10-14 | 1 |  | 71 | 20 | 90 | 2021 | 2021 | R16
163069237036 | 167966237036 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-29 | 2021-06-30 | 2021-06-30 |  | 2021-10-28 | Overhead | R16 | 2021-07-29 | 2 |  | 22 | 66 | 88 | 2021 | 2021 | R16
160054236526 | 166636236526 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-23 | 2021-06-24 | 2021-06-24 | 2021-09-17 | 2021-10-25 | Overhead | R16 | 2021-09-17 | 2 |  | 62 | 27 | 89 | 2021 | 2021 | R16
161503237834 | 167928237834 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2021-06-30 | 2021-06-30 | 2021-07-06 | 2021-07-15 | 2022-01-07 | Overhead | R16 | 2021-07-15 | 1 | 5 | 8 | 127 | 138 | 2021 | 2022 | R16
166003260504 | 163040260504 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-22 | 2021-07-22 | 2021-12-09 |  | 2022-06-08 | Underground | R16 | 2022-05-06 | 1 | 101 | 107 | 24 | 230 | 2021 | 2022 | R16
165892236916 | 164427236916 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-14 | 2021-06-28 | 2021-06-28 | 2021-08-05 | 2021-10-27 | Overhead | R16 | 2021-08-05 | 11 |  | 29 | 60 | 98 | 2021 | 2021 | R16
164003235472 | 165527235472 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-18 | 2021-06-18 | 2021-06-18 | 2022-03-29 | 2022-06-20 | Overhead | R16 | 2022-03-29 | 1 |  | 203 | 60 | 262 | 2021 | 2022 | R16
167627248593 | 162549248593 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-21 | 2021-07-21 | 2021-09-21 | 2021-10-19 | 2021-11-13 | Underground | R16 | 2021-10-19 | 1 | 45 | 21 | 19 | 83 | 2021 | 2021 | R16
164544237240 | 166276237240 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-22 | 2021-06-29 | 2021-06-29 | 2021-07-27 | 2021-07-28 | Overhead | R16 | 2021-07-27 | 6 |  | 21 | 2 | 27 | 2021 | 2021 | R16
162468238738 | 160045238738 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2021-07-09 | 2021-07-13 | 2021-07-13 |  | 2022-02-25 | Underground | R16 |  | 3 |  |  |  | 166 | 2021 | 2022 | R16
164875244387 | 160744244387 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-13 | 2021-07-13 | 2021-08-19 | 2021-10-20 | 2021-10-20 | Underground | R16 | 2021-10-20 | 1 | 28 | 45 |  | 72 | 2021 | 2021 | R16
165873337771 | 160185337771 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-12 | 2021-07-23 | 2023-10-27 | 2023-11-20 | 2023-11-28 | Overhead | R16 | 2023-11-20 | 10 | 591 | 17 | 7 | 622 | 2021 | 2023 | R16
160554237205 | 163232237205 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-09 | 2021-06-09 | 2021-06-29 | 2022-02-07 | 2022-02-08 | Underground | R16 | 2022-02-07 | 1 | 15 | 160 | 2 | 175 | 2021 | 2022 | R16
168297233827 | 162525233827 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-07 | 2021-06-07 | 2021-06-07 |  | 2021-12-08 | Overhead | R16 | 2021-08-11 | 1 |  | 48 | 86 | 133 | 2021 | 2021 | R16
167858241460 | 161311241460 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-07-15 | 2021-07-22 | 2021-07-30 |  | 2021-10-25 | Underground | R16 | 2021-08-26 | 6 | 7 | 20 | 43 | 73 | 2021 | 2021 | R16
168544242375 | 163065242375 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-22 | 2021-08-07 | 2021-08-07 | 2022-09-15 | 2023-01-05 | Underground | R16 | 2022-09-15 | 12 |  | 289 | 81 | 381 | 2021 | 2023 | R16
165614239621 | 161860239621 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-19 | 2021-07-19 | 2021-07-19 | 2021-09-15 | 2021-11-08 | Overhead | R16 | 2021-09-15 | 1 |  | 43 | 39 | 81 | 2021 | 2021 | R16
162209236239 | 166640236239 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-23 | 2021-06-23 | 2021-06-23 |  | 2021-12-02 | Overhead | R16 | 2021-11-22 | 1 |  | 109 | 9 | 117 | 2021 | 2021 | R16
162813253086 | 166719253086 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-06-24 | 2021-07-29 | 2021-10-20 |  | 2022-06-24 | Underground | R16 |  | 26 | 60 |  |  | 262 | 2021 | 2022 | R16
164803240058 | 161654240058 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-17 | 2021-07-17 | 2021-07-22 | 2021-11-16 | 2021-12-21 | Underground | R16 | 2021-11-16 | 0 | 4 | 84 | 26 | 112 | 2021 | 2021 | R16
160684239878 | 160700239878 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-13 | 2021-07-13 | 2021-07-21 | 2021-08-28 | 2021-09-03 | Overhead | R16 | 2021-08-28 | 1 | 7 | 28 | 5 | 39 | 2021 | 2021 | R16
161085236274 | 166564236274 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-23 | 2021-06-23 | 2021-06-23 | 2021-08-16 | 2021-10-25 | Overhead | R16 | 2021-08-16 | 1 |  | 39 | 51 | 89 | 2021 | 2021 | R16
168372259310 | 161307259310 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-15 | 2021-07-15 | 2021-12-01 | 2022-01-19 | 2022-03-04 | Underground | R16 | 2022-01-19 | 1 | 100 | 36 | 33 | 167 | 2021 | 2022 | R16
168525235440 | 165423235440 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-17 | 2021-06-17 | 2021-06-17 |  | 2021-08-23 | Overhead | R16 | 2021-07-13 | 1 |  | 19 | 30 | 48 | 2021 | 2021 | R16
164801239201 | 161253239201 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-15 | 2021-07-15 | 2021-07-15 | 2021-10-13 | 2021-10-14 | Overhead | R16 | 2021-10-13 | 1 |  | 65 | 2 | 66 | 2021 | 2021 | R16
164630233386 | 161867233386 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-03 | 2021-06-03 | 2021-06-03 |  | 2021-10-25 | Overhead | R16 | 2021-09-16 | 1 |  | 76 | 28 | 103 | 2021 | 2021 | R16
169654277628 | 161453277628 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2021-06-02 | 2021-06-16 | 2022-04-29 |  | 2023-01-10 | Overhead | R16 |  | 11 | 228 |  |  | 420 | 2021 | 2023 | R16
164066243582 | 161351243582 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-15 | 2021-08-13 | 2021-08-13 |  | 2021-12-02 | Overhead | R16 | 2021-11-04 | 22 |  | 60 | 21 | 101 | 2021 | 2021 | R16
161668237277 | 164213237277 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-14 | 2021-07-01 | 2021-07-01 |  | 2022-06-01 | Overhead | R16 | 2022-05-03 | 14 |  | 219 | 22 | 253 | 2021 | 2022 | R16
168312234899 | 164239234899 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-14 | 2021-06-14 | 2021-06-14 |  | 2022-12-13 | Overhead | R16 | 2021-10-25 | 1 |  | 96 | 297 | 392 | 2021 | 2022 | R16
162369233600 | 162145233600 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-04 | 2021-06-04 | 2021-06-04 | 2021-09-01 | 2021-09-02 | Overhead | R16 | 2021-09-01 | 1 |  | 64 | 2 | 65 | 2021 | 2021 | R16
161728240288 | 162915240288 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-22 | 2021-07-22 | 2021-07-22 | 2021-09-15 | 2021-11-08 | Underground | R16 | 2021-09-15 | 1 |  | 40 | 39 | 78 | 2021 | 2021 | R16
165709282212 | 163057282212 | AGRICULTURAL | R16 RESD AND NON RESD US | Residential Subdivision | 2021-07-23 | 2021-08-19 | 2022-06-10 |  | 2023-01-05 | Underground | R16 |  | 20 | 212 |  |  | 380 | 2021 | 2023 | R16
160672234971 | 164220234971 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-08-04 | 2021-08-05 | Overhead | R16 | 2021-08-04 | 1 | 2 | 37 | 2 | 39 | 2021 | 2021 | R16
165981259738 | 163180259738 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2021-07-23 | 2021-09-10 | 2021-12-03 |  | 2022-09-14 | Underground | R16 | 2022-07-19 | 36 | 61 | 163 | 42 | 299 | 2021 | 2022 | R16
163098239181 | 168435239181 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-02 | 2021-07-15 | 2021-07-15 |  | 2021-11-18 | Overhead | R16 | 2021-10-26 | 10 |  | 74 | 18 | 100 | 2021 | 2021 | R16
166041242205 | 168055242205 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2021-06-30 | 2021-06-30 | 2021-08-05 | 2021-08-11 | 2021-09-13 | Underground | R16 | 2021-08-11 | 1 | 27 | 5 | 24 | 54 | 2021 | 2021 | R16
165667239182 | 161298239182 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-15 | 2021-07-15 | 2021-07-15 | 2021-08-24 | 2021-10-21 | Overhead | R16 | 2021-08-24 | 1 |  | 29 | 43 | 71 | 2021 | 2021 | R16
166965255753 | 168399255753 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-01 | 2021-11-10 | 2021-11-10 | 2022-02-16 | 2022-03-14 | Overhead | R16 | 2022-02-16 | 95 |  | 71 | 19 | 183 | 2021 | 2022 | R16
160872234170 | 163186234170 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-09 | 2021-06-09 | 2021-06-09 | 2021-07-15 | 2021-07-16 | Overhead | R16 | 2021-07-15 | 1 |  | 27 | 2 | 28 | 2021 | 2021 | R16
167064241948 | 169258241948 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-07 | 2021-07-08 | 2021-08-03 |  | 2021-10-25 | Overhead | R16 | 2021-09-08 | 2 | 19 | 27 | 34 | 79 | 2021 | 2021 | R16
166042233850 | 162523233850 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-07 | 2021-06-07 | 2021-06-07 |  | 2021-08-11 | Overhead | R16 | 2021-07-01 | 1 |  | 19 | 30 | 48 | 2021 | 2021 | R16
168130242771 | 168678242771 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-02 | 2021-07-02 | 2021-08-09 |  | 2021-10-25 | Overhead | R16 | 2021-08-25 | 1 | 27 | 13 | 44 | 82 | 2021 | 2021 | R16
160605235282 | 162174235282 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-04 | 2021-06-04 | 2021-06-16 |  | 2021-11-13 | Underground | R16 | 2021-07-28 | 1 | 9 | 31 | 78 | 116 | 2021 | 2021 | R16
165523250919 | 165877250919 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-21 | 2021-10-07 | 2021-10-07 | 2021-12-03 | 2022-01-18 | Overhead | R16 | 2021-12-03 | 79 |  | 42 | 33 | 152 | 2021 | 2022 | R16
161318239050 | 166641239050 | RESIDENTIAL - SINGLE FAMILY DETACHED | UG R16 RESD AND NON RESD UD | Residential | 2021-06-23 | 2021-06-23 | 2021-07-14 | 2021-09-03 | 2022-02-16 | Underground | R16 | 2021-09-03 | 1 | 16 | 38 | 119 | 171 | 2021 | 2022 | R16
163394236913 | 167164236913 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-25 | 2021-06-28 | 2021-06-28 | 2021-08-05 | 2021-09-01 | Overhead | R16 | 2021-08-05 | 2 |  | 29 | 20 | 49 | 2021 | 2021 | R16
163276244193 | 165890244193 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-21 | 2021-06-21 | 2021-08-18 |  | 2021-12-02 | Underground | R16 | 2021-11-10 | 1 | 43 | 61 | 17 | 119 | 2021 | 2021 | R16
163666236182 | 161672236182 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-03 | 2021-06-03 | 2021-06-22 |  | 2021-11-09 | Underground | R16 | 2021-09-30 | 1 | 14 | 73 | 29 | 114 | 2021 | 2021 | R16
167080233389 | 161893233389 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-03 | 2021-06-03 | 2021-06-03 |  | 2021-08-23 | Overhead | R16 | 2021-07-28 | 1 |  | 40 | 19 | 58 | 2021 | 2021 | R16
164333239583 | 161829239583 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-19 | 2021-07-19 | 2021-07-19 | 2021-08-16 | 2022-02-02 | Overhead | R16 | 2021-08-16 | 1 |  | 21 | 123 | 143 | 2021 | 2022 | R16
167707274401 | 160915274401 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Commercial | 2021-07-14 | 2022-02-04 | 2022-03-30 | 2022-06-13 | 2022-07-05 | Underground | R16 | 2022-06-13 | 148 | 39 | 54 | 17 | 255 | 2021 | 2022 | R16
164971241585 | 166717241585 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-23 | 2021-06-23 | 2021-07-30 |  | 2021-10-27 | Underground | R16 | 2021-09-07 | 1 | 28 | 28 | 37 | 91 | 2021 | 2021 | R16
164830240859 | 162456240859 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-07-21 | 2021-07-22 | 2021-07-27 | 2022-02-19 | 2022-08-29 | Underground | R16 | 2022-02-19 | 2 | 4 | 149 | 136 | 289 | 2021 | 2022 | R16
164522234140 | 162960234140 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-08 | 2021-06-08 | 2021-06-08 |  | 2021-08-23 | Overhead | R16 | 2021-07-28 | 1 |  | 37 | 19 | 55 | 2021 | 2021 | R16
160030240261 | 161507240261 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-17 | 2021-07-17 | 2021-07-22 | 2021-09-10 | 2021-10-25 | Underground | R16 | 2021-09-10 | 0 | 4 | 37 | 32 | 71 | 2021 | 2021 | R16
164534238374 | 167859238374 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-29 | 2021-06-29 | 2021-07-09 |  | 2022-02-28 | Overhead | R16 |  | 1 | 9 |  |  | 175 | 2021 | 2022 | R16
168344237977 | 169666237977 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-08 | 2021-07-08 | 2021-07-08 | 2021-10-25 | 2021-10-25 | Overhead | R16 | 2021-10-25 | 1 |  | 78 |  | 78 | 2021 | 2021 | R16
164543290379 | 162551290379 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-06-07 | 2021-06-09 | 2022-08-29 | 2023-01-05 | 2023-01-05 | Overhead | R16 | 2023-01-05 | 3 | 319 | 94 |  | 414 | 2021 | 2023 | R16
168741236449 | 164338236449 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-06-14 | 2021-06-15 | 2021-06-24 |  | 2021-08-12 | Overhead | R16 |  | 2 | 8 |  |  | 44 | 2021 | 2021 | R16
161144235098 | 165032235098 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2021-07-27 | 2021-08-23 | Underground | R16 | 2021-07-27 | 1 |  | 30 | 20 | 49 | 2021 | 2021 | R16
164403239841 | 162293239841 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2021-09-01 | 2021-10-26 | Overhead | R16 | 2021-09-01 | 1 |  | 32 | 40 | 71 | 2021 | 2021 | R16
166018237762 | 167720237762 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-28 | 2021-07-06 | 2021-07-06 |  | 2022-02-10 | Overhead | R16 | 2022-01-05 | 7 |  | 132 | 27 | 164 | 2021 | 2022 | R16
169594251239 | 162689251239 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-07 | 2021-10-08 | 2021-10-08 | 2021-11-24 | 2021-11-24 | Overhead | R16 | 2021-11-24 | 90 |  | 34 |  | 123 | 2021 | 2021 | R16
163347237860 | 168898237860 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-06 | 2021-07-06 | 2021-07-06 |  | 2021-08-23 | Overhead | R16 | 2021-07-28 | 1 |  | 17 | 19 | 35 | 2021 | 2021 | R16
164390243351 | 162009243351 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-20 | 2021-08-12 | 2021-08-12 |  | 2022-10-17 | Overhead | R16 |  | 18 |  |  |  | 325 | 2021 | 2022 | R16
162845237001 | 166586237001 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-06-23 | 2021-06-28 | 2021-06-28 |  | 2021-11-16 | Overhead | R16 | 2021-09-03 | 4 |  | 50 | 53 | 105 | 2021 | 2021 | R16
160335242388 | 160780242388 | NON-RESIDENTIAL - SMALL RETAIL | R16 RESD AND NON RESD US | Commercial | 2021-07-13 | 2021-07-14 | 2021-08-06 | 2021-11-30 | 2021-12-16 | Underground | R16 | 2021-11-30 | 2 | 18 | 83 | 13 | 113 | 2021 | 2021 | R16
163393236632 | 161818236632 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-06-03 | 2021-06-03 | 2021-06-25 |  | 2021-10-25 | Overhead | R16 |  | 1 | 17 |  |  | 103 | 2021 | 2021 | R16
160576242907 | 166209242907 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-22 | 2021-06-22 | 2021-08-10 |  | 2021-10-25 | Underground | R16 | 2021-09-09 | 1 | 36 | 23 | 33 | 90 | 2021 | 2021 | R16
169752236363 | 162151236363 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-04 | 2021-06-04 | 2021-06-23 | 2021-09-02 | 2021-10-25 | Underground | R16 | 2021-09-02 | 1 | 14 | 52 | 38 | 102 | 2021 | 2021 | R16
161572236638 | 167147236638 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-25 | 2021-06-25 | 2021-06-25 |  | 2021-10-25 | Overhead | R16 | 2021-09-02 | 1 |  | 50 | 38 | 87 | 2021 | 2021 | R16
163628235509 | 161540235509 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-02 | 2021-06-02 | 2021-06-18 |  | 2021-10-28 | Underground | R16 | 2021-07-29 | 1 | 13 | 30 | 66 | 107 | 2021 | 2021 | R16
167026233858 | 162618233858 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-07 | 2021-06-07 | 2021-06-07 |  | 2021-08-23 | Overhead | R16 | 2021-07-26 | 1 |  | 36 | 21 | 56 | 2021 | 2021 | R16
163202237650 | 168717237650 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-03 | 2021-07-03 | 2021-07-03 |  | 2022-06-06 | Overhead | R16 | 2022-05-11 | 0 |  | 223 | 19 | 241 | 2021 | 2022 | R16
163219236635 | 164316236635 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2021-06-14 | 2021-06-16 | 2021-06-25 | 2021-10-06 | 2021-10-26 | Underground | R16 | 2021-10-06 | 3 | 8 | 74 | 15 | 97 | 2021 | 2021 | R16
165160239682 | 161935239682 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-19 | 2021-07-19 | 2021-07-19 | 2021-08-27 | 2021-10-25 | Overhead | R16 | 2021-08-27 | 1 |  | 30 | 42 | 71 | 2021 | 2021 | R16
167904237436 | 167242237436 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-26 | 2021-07-03 | 2021-07-03 | 2021-11-30 | 2021-12-01 | Overhead | R16 | 2021-11-30 | 5 |  | 107 | 2 | 113 | 2021 | 2021 | R16
163714248772 | 165228248772 | NON-RESIDENTIAL - SUBSEQUENT WORK | OH R16 RES NON RES OD | Commercial | 2021-06-17 | 2021-06-17 | 2021-09-21 | 2021-09-28 | 2021-10-11 | Overhead | R16 | 2021-09-28 | 1 | 69 | 6 | 10 | 83 | 2021 | 2021 | R16
160132243989 | 165376243989 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-06-17 | 2021-06-17 | 2021-08-17 |  | 2021-11-09 | Underground | R16 | 2021-10-06 | 1 | 44 | 37 | 25 | 104 | 2021 | 2021 | R16
163187240080 | 162594240080 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-21 | 2021-07-21 | 2021-07-21 |  | 2021-10-25 | Overhead | R16 | 2021-09-15 | 1 |  | 41 | 29 | 69 | 2021 | 2021 | R16
166843239304 | 166827239304 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-06-24 | 2021-06-24 | 2021-07-16 | 2022-05-30 | 2022-12-20 | Underground | R16 | 2022-05-30 | 1 | 17 | 227 | 147 | 389 | 2021 | 2022 | R16
162675240843 | 163176240843 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-23 | 2021-07-26 | 2021-07-26 | 2021-09-08 | 2021-10-26 | Overhead | R16 | 2021-09-08 | 2 |  | 33 | 35 | 68 | 2021 | 2021 | R16
162864235056 | 164629235056 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-06-15 | 2021-06-15 | 2021-06-15 |  | 2021-08-23 | Underground | R16 | 2021-07-12 | 1 |  | 20 | 31 | 50 | 2021 | 2021 | R16
161846239929 | 162614239929 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-23 | 2021-07-28 | Overhead | R16 | 2021-07-23 | 1 |  | 3 | 4 | 6 | 2021 | 2021 | R16
162852248443 | 166710248443 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential | 2021-06-23 | 2021-07-07 | 2021-09-17 |  | 2022-04-25 | Underground | R16 |  | 11 | 53 |  |  | 219 | 2021 | 2022 | R16
169976237474 | 167730237474 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-28 | 2021-06-28 | 2021-06-28 | 2021-08-13 | 2021-10-25 | Underground | R16 | 2021-08-13 | 1 |  | 35 | 52 | 86 | 2021 | 2021 | R16
165911240245 | 167366240245 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-28 | 2021-07-24 | 2021-07-24 | 2022-01-20 | 2022-01-21 | Overhead | R16 | 2022-01-20 | 20 |  | 129 | 2 | 150 | 2021 | 2022 | R16
161922239497 | 162013239497 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-19 | 2021-07-19 | 2021-07-19 | 2022-01-27 | 2022-03-02 | Underground | R16 | 2022-01-27 | 1 |  | 139 | 25 | 163 | 2021 | 2022 | R16
160780240360 | 163224240360 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-09 | 2021-06-09 | 2021-07-23 | 2021-12-03 | 2022-10-17 | Underground | R16 | 2021-12-03 | 1 | 33 | 96 | 227 | 354 | 2021 | 2022 | R16
169276248235 | 168336248235 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-01 | 2021-07-01 | 2021-09-17 | 2023-03-26 | 2023-03-29 | Underground | R16 | 2023-03-26 | 1 | 57 | 396 | 3 | 455 | 2021 | 2023 | R16
162107237854 | 162216237854 | FOREIGN UTILITY | R16 RESD AND NON RESD US | Commercial | 2021-06-04 | 2021-06-04 | 2021-07-06 |  | 2023-08-23 | Underground | R16 |  | 1 | 23 |  |  | 579 | 2021 | 2023 | R16
163406251745 | 166833251745 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-06-24 | 2021-06-24 | 2021-10-12 | 2023-08-22 | 2023-08-25 | Underground | R16 | 2023-08-22 | 1 | 79 | 486 | 4 | 567 | 2021 | 2023 | R16
166648235413 | 165702235413 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-18 | 2021-06-18 | 2021-06-18 | 2021-07-28 | 2021-08-23 | Overhead | R16 | 2021-07-28 | 1 |  | 29 | 19 | 47 | 2021 | 2021 | R16
165291247943 | 166506247943 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-23 | 2021-09-14 | 2021-09-14 | 2021-09-28 | 2021-11-01 | Overhead | R16 | 2021-09-28 | 60 |  | 11 | 25 | 94 | 2021 | 2021 | R16
169634243353 | 163333243353 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-09 | 2021-08-12 | 2021-08-12 |  | 2021-12-17 | Overhead | R16 | 2021-11-19 | 47 |  | 72 | 21 | 138 | 2021 | 2021 | R16
165383233299 | 161568233299 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-03 | 2021-06-03 | 2021-06-03 |  | 2021-09-14 | Overhead | R16 | 2021-08-19 | 1 |  | 56 | 19 | 74 | 2021 | 2021 | R16
165925238048 | 167763238048 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-29 | 2021-06-29 | 2021-07-07 | 2021-11-04 | 2022-01-13 | Underground | R16 | 2021-11-04 | 1 | 7 | 87 | 51 | 143 | 2021 | 2022 | R16
160067240217 | 163218240217 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-07-23 | 2021-07-23 | 2021-07-23 |  | 2021-08-23 | Overhead | R16 | 2021-08-02 | 1 |  | 7 | 16 | 22 | 2021 | 2021 | R16
163696235306 | 164934235306 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-15 | 2021-06-15 | 2021-06-16 | 2021-08-02 | 2021-08-03 | Overhead | R16 | 2021-08-02 | 1 | 2 | 34 | 2 | 36 | 2021 | 2021 | R16
168954242203 | 161782242203 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-18 | 2021-08-05 | 2021-08-05 |  | 2022-02-07 | Overhead | R16 | 2022-01-11 | 14 |  | 114 | 20 | 146 | 2021 | 2022 | R16
160582235376 | 165509235376 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-18 | 2021-06-18 | 2021-06-18 | 2021-08-10 | 2021-09-10 | Overhead | R16 | 2021-08-10 | 1 |  | 38 | 24 | 61 | 2021 | 2021 | R16
162531242675 | 160863242675 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-14 | 2021-07-14 | 2021-08-09 | 2021-08-23 | 2022-01-13 | Underground | R16 | 2021-08-23 | 1 | 19 | 11 | 104 | 132 | 2021 | 2022 | R16
168167236944 | 167443236944 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-06-28 | 2021-06-28 | 2021-06-28 | 2021-09-02 | 2021-10-25 | Overhead | R16 | 2021-09-02 | 1 |  | 49 | 38 | 86 | 2021 | 2021 | R16
161442237981 | 168945237981 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-06 | 2021-07-06 | 2021-07-06 |  | 2021-08-23 | Overhead | R16 | 2021-07-15 | 1 |  | 8 | 28 | 35 | 2021 | 2021 | R16
163188240943 | 169353240943 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-07 | 2021-07-08 | 2021-07-27 |  | 2021-11-13 | Underground | R16 | 2021-10-19 | 2 | 14 | 61 | 19 | 93 | 2021 | 2021 | R16
162876244960 | 161640244960 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-16 | 2021-07-16 | 2021-08-23 | 2021-11-16 | 2021-12-17 | Overhead | R16 | 2021-11-16 | 1 | 27 | 62 | 24 | 111 | 2021 | 2021 | R16
162444245006 | 167799245006 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-30 | 2021-06-30 | 2021-08-24 |  | 2021-11-02 | Underground | R16 | 2021-10-06 | 1 | 40 | 32 | 20 | 90 | 2021 | 2021 | R16
163324251791 | 167463251791 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-28 | 2021-06-28 | 2021-10-12 |  | 2022-02-02 | Underground | R16 | 2021-12-16 | 1 | 77 | 48 | 35 | 158 | 2021 | 2022 | R16
164082269619 | 166602269619 | Affordable Housing | UG R16 RESD AND NON RESD UD | Commercial | 2021-06-23 | 2021-08-06 | 2022-02-18 | 2022-08-23 | 2022-10-04 | Underground | R16 | 2022-08-23 | 33 | 141 | 133 | 31 | 335 | 2021 | 2022 | R16
161132237649 | 162812237649 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-08 | 2021-06-08 | 2021-07-03 |  | 2021-11-02 | Underground | R16 | 2021-10-18 | 1 | 19 | 76 | 12 | 106 | 2021 | 2021 | R16
166179236327 | 166487236327 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Commercial | 2021-06-23 | 2021-06-23 | 2021-06-23 |  | 2021-08-12 | Overhead | R16 | 2021-07-09 | 1 |  | 13 | 25 | 37 | 2021 | 2021 | R16
167603234056 | 162974234056 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-09 | 2021-06-09 | 2021-06-09 | 2021-12-29 | 2022-02-10 | Overhead | R16 | 2021-12-29 | 1 |  | 146 | 32 | 177 | 2021 | 2022 | R16
168509237691 | 166177237691 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-06-22 | 2021-06-22 | 2021-07-02 | 2023-05-04 | 2023-08-18 | Overhead | R16 | 2023-05-04 | 1 | 9 | 480 | 77 | 564 | 2021 | 2023 | R16
163983239341 | 166274239341 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-22 | 2021-06-23 | 2021-07-16 |  | 2021-11-18 | Underground | R16 | 2021-10-25 | 2 | 18 | 72 | 19 | 108 | 2021 | 2021 | R16
163274302014 | 164428302014 | RESIDENTIAL - MOBILE HOME | OH R16 RES NON RES OS | Residential | 2021-06-15 | 2022-12-02 | 2022-12-02 | 2023-06-22 | 2023-06-30 | Overhead | R16 | 2023-06-22 | 384 |  | 145 | 7 | 534 | 2021 | 2023 | R16
162875255929 | 165881255929 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-21 | 2021-06-21 | 2021-11-10 | 2022-01-28 | 2022-03-08 | Underground | R16 | 2022-01-28 | 1 | 103 | 58 | 28 | 187 | 2021 | 2022 | R16
169306239754 | 164812239754 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-15 | 2021-06-15 | 2021-07-20 | 2021-09-01 | 2021-09-02 | Underground | R16 | 2021-09-01 | 1 | 26 | 32 | 2 | 58 | 2021 | 2021 | R16
165590235457 | 165544235457 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2021-06-18 | 2021-06-18 | 2021-06-18 | 2022-03-24 | 2021-12-21 | Underground | R16 | 2022-03-24 | 1 |  | 200 |  | 133 | 2021 | 2021 | R16
162848239421 | 161549239421 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-16 | 2021-07-16 | 2021-07-16 | 2021-12-09 | 2022-02-01 | Overhead | R16 | 2021-12-09 | 1 |  | 105 | 39 | 143 | 2021 | 2022 | R16
167466236000 | 165575236000 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2021-06-18 | 2021-06-18 | 2021-06-20 |  | 2022-10-21 | Underground | R16 |  | 1 | 1 |  |  | 351 | 2021 | 2022 | R16
168412310921 | 164226310921 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-06-13 | 2021-06-14 | 2023-02-28 |  | 2023-07-11 | Overhead | R16 |  | 1 | 447 |  |  | 542 | 2021 | 2023 | R16
169714233957 | 162860233957 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-08 | 2021-06-08 | 2021-06-08 |  | 2021-11-18 | Overhead | R16 | 2021-10-27 | 1 |  | 102 | 17 | 118 | 2021 | 2021 | R16
166301237883 | 168243237883 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-01 | 2021-07-06 | 2021-07-06 |  | 2021-10-26 | Overhead | R16 | 2021-09-01 | 4 |  | 42 | 40 | 84 | 2021 | 2021 | R16
165227233216 | 161652233216 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-02 | 2021-06-02 | 2021-06-02 |  | 2021-10-25 | Overhead | R16 | 2021-08-30 | 1 |  | 64 | 41 | 104 | 2021 | 2021 | R16
163204239588 | 161943239588 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-19 | 2021-07-19 | 2021-07-19 | 2021-10-07 | 2021-11-18 | Overhead | R16 | 2021-10-07 | 1 |  | 59 | 31 | 89 | 2021 | 2021 | R16
167833241947 | 169032241947 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-06 | 2021-07-09 | 2021-08-03 | 2021-09-14 | 2021-09-15 | Overhead | R16 | 2021-09-14 | 4 | 18 | 31 | 2 | 52 | 2021 | 2021 | R16
161760244118 | 164233244118 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-14 | 2021-06-30 | 2021-08-18 |  | 2021-12-29 | Underground | R16 | 2021-11-19 | 13 | 36 | 68 | 29 | 143 | 2021 | 2021 | R16
166211239059 | 169908239059 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-09 | 2021-07-15 | 2021-07-15 |  | 2023-08-14 | Overhead | R16 | 2023-04-04 | 5 |  | 449 | 95 | 547 | 2021 | 2023 | R16
162642243372 | 167524243372 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-28 | 2021-08-12 | 2021-08-12 | 2021-12-27 | 2022-01-24 | Overhead | R16 | 2021-12-27 | 34 |  | 98 | 21 | 151 | 2021 | 2022 | R16
166308247637 | 169685247637 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-09 | 2021-09-08 | 2021-09-13 | 2021-10-17 | 2021-11-18 | Underground | R16 | 2021-10-17 | 44 | 4 | 25 | 24 | 95 | 2021 | 2021 | R16
166490236294 | 166456236294 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-06-23 | 2021-06-23 | 2021-06-23 | 2021-06-23 | 2021-06-23 | Underground | R16 | 2021-06-23 | 1 |  |  |  | 1 | 2021 | 2021 | R16
160099245741 | 161551245741 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-06-02 | 2021-08-28 | 2021-08-28 |  | 2022-05-05 | Underground | R16 | 2022-04-13 | 63 |  | 163 | 17 | 242 | 2021 | 2022 | R16
169850236240 | 166197236240 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-22 | 2021-06-22 | 2021-06-22 | 2021-09-21 | 2023-06-08 | Overhead | R16 | 2021-09-21 | 1 |  | 66 | 448 | 513 | 2021 | 2023 | R16
163252247026 | 162067247026 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-06-04 | 2021-08-03 | 2021-09-08 | 2022-10-27 | 2023-06-08 | Underground | R16 | 2022-10-27 | 43 | 27 | 297 | 161 | 525 | 2021 | 2023 | R16
169386240043 | 162529240043 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-07-21 | 2021-07-21 | 2021-07-21 |  | 2021-10-27 | Overhead | R16 | 2021-08-12 | 1 |  | 17 | 55 | 71 | 2021 | 2021 | R16
165087238487 | 166831238487 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-24 | 2021-06-24 | 2021-07-12 | 2021-07-15 | 2021-10-25 | Underground | R16 | 2021-07-15 | 1 | 13 | 4 | 73 | 88 | 2021 | 2021 | R16
164920312413 | 169038312413 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-07-06 | 2021-07-06 | 2023-03-14 | 2023-07-10 | 2023-09-05 | Overhead | R16 | 2023-07-10 | 1 | 441 | 85 | 42 | 566 | 2021 | 2023 | R16
168211236344 | 164160236344 | RESIDENTIAL - MULTI-FAMILY | R16 RESD AND NON RESD US | Residential | 2021-06-13 | 2021-06-13 | 2021-06-23 | 2023-11-10 | 2023-11-10 | Underground | R16 | 2023-11-10 | 0 | 8 | 623 |  | 630 | 2021 | 2023 | R16
167431237206 | 167808237206 | RESIDENTIAL - SINGLE FAMILY DETACHED | OH R16 RES NON RES OS | Residential | 2021-06-29 | 2021-06-29 | 2021-06-29 |  | 2021-08-11 | Overhead | R16 | 2021-07-01 | 1 |  | 3 | 30 | 32 | 2021 | 2021 | R16
168341241853 | 162789241853 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-07-22 | 2021-07-22 | 2021-08-03 | 2021-09-02 | 2021-10-14 | Underground | R16 | 2021-09-02 | 1 | 9 | 23 | 31 | 61 | 2021 | 2021 | R16
163828274516 | 168620274516 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2021-07-02 | 2021-07-02 | 2022-04-01 | 2023-02-15 | 2022-06-13 | Underground | R16 | 2023-02-15 | 1 | 196 | 229 |  | 247 | 2021 | 2022 | R16
161045250946 | 163946250946 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2021-06-11 | 2021-07-09 | 2021-10-06 | 2022-06-06 | 2022-06-16 | Underground | R16 | 2022-06-06 | 21 | 64 | 174 | 9 | 265 | 2021 | 2022 | R16
169780233828 | 162596233828 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-07 | 2021-06-07 | 2021-06-07 | 2021-10-04 | 2021-10-04 | Overhead | R16 | 2021-10-04 | 1 |  | 86 |  | 86 | 2021 | 2021 | R16
165293240165 | 162997240165 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-22 | 2021-07-22 | 2021-07-22 | 2022-03-04 | 2022-10-17 | Overhead | R16 | 2022-03-04 | 1 |  | 162 | 162 | 323 | 2021 | 2022 | R16
164812235547 | 165143235547 | CUSTOMER RELATED RELOC/REARRANGEMENT/RFS | OH ELEC SVC RFS | Residential | 2021-06-17 | 2021-06-17 | 2021-06-18 |  | 2021-08-12 | Overhead | R16 |  | 1 | 2 |  |  | 41 | 2021 | 2021 | R16
169992259782 | 167193259782 | NON-RESIDENTIAL - MISCELLANEOUS | R16 RESD AND NON RESD US | Commercial | 2021-06-25 | 2021-11-23 | 2021-12-03 | 2023-06-08 | 2023-07-03 | Underground | R16 | 2023-06-08 | 108 | 9 | 395 | 18 | 527 | 2021 | 2023 | R16
163804238589 | 160289238589 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-12 | 2021-07-12 | 2021-07-12 | 2021-08-26 | 2021-10-25 | Overhead | R16 | 2021-08-26 | 1 |  | 34 | 43 | 76 | 2021 | 2021 | R16
163086236481 | 166077236481 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-22 | 2021-06-23 | 2021-06-23 | 2021-08-10 | 2021-11-16 | Overhead | R16 | 2021-08-10 | 2 |  | 35 | 71 | 106 | 2021 | 2021 | R16
165981259739 | 163181259739 | AGRICULTURAL | R16 RESD AND NON RESD US | Commercial | 2021-07-23 | 2021-10-12 | 2021-12-03 | 2023-01-05 | 2023-01-05 | Underground | R16 | 2023-01-05 | 58 | 39 | 285 |  | 380 | 2021 | 2023 | R16
163676238568 | 165308238568 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-06-17 | 2021-06-17 | 2021-07-12 | 2021-08-26 | 2021-08-27 | Underground | R16 | 2021-08-26 | 1 | 18 | 34 | 2 | 52 | 2021 | 2021 | R16
167320234503 | 163389234503 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-10 | 2021-06-10 | 2021-06-10 |  | 2021-10-25 | Overhead | R16 | 2021-08-31 | 1 |  | 59 | 40 | 98 | 2021 | 2021 | R16
163193234973 | 164192234973 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-13 | 2021-06-15 | 2021-06-15 |  | 2021-11-08 | Overhead | R16 | 2021-08-17 | 2 |  | 46 | 60 | 106 | 2021 | 2021 | R16
166152235183 | 164535235183 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Commercial | 2021-06-15 | 2021-06-15 | 2021-06-16 | 2021-06-18 | 2021-12-28 | Underground | R16 | 2021-06-18 | 1 | 2 | 3 | 138 | 141 | 2021 | 2021 | R16
162544239025 | 168583239025 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-02 | 2021-07-14 | 2021-07-14 |  | 2022-03-08 | Underground | R16 | 2022-01-19 | 9 |  | 136 | 35 | 178 | 2021 | 2022 | R16
161569238556 | 163299238556 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2021-06-09 | 2021-06-13 | 2021-07-13 | 2021-09-29 | 2021-10-19 | Underground | R16 | 2021-09-29 | 3 | 22 | 57 | 15 | 95 | 2021 | 2021 | R16
164864241905 | 160806241905 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-13 | 2021-07-13 | 2021-08-03 | 2021-10-12 | 2021-10-14 | Underground | R16 | 2021-10-12 | 1 | 16 | 51 | 3 | 68 | 2021 | 2021 | R16
169802235145 | 164978235145 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2021-07-27 | 2021-08-23 | Overhead | R16 | 2021-07-27 | 1 |  | 30 | 20 | 49 | 2021 | 2021 | R16
161138237763 | 167629237763 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-28 | 2021-07-06 | 2021-07-06 |  | 2021-10-25 | Overhead | R16 | 2021-08-31 | 7 |  | 41 | 40 | 86 | 2021 | 2021 | R16
165089236918 | 166883236918 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-25 | 2021-06-29 | 2021-06-29 | 2021-10-26 | 2021-12-01 | Overhead | R16 | 2021-10-26 | 3 |  | 86 | 27 | 114 | 2021 | 2021 | R16
165010238044 | 167762238044 | CUSTOMER UPGRADE IN SERVICE | UG R16 ELEC VEHICLE RES US | Residential | 2021-06-29 | 2021-06-29 | 2021-07-07 |  | 2021-10-28 | Underground | R16 | 2021-09-27 | 1 | 7 | 59 | 24 | 88 | 2021 | 2021 | R16
163188236912 | 167148236912 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-25 | 2021-06-28 | 2021-06-28 | 2021-08-05 | 2021-09-02 | Overhead | R16 | 2021-08-05 | 2 |  | 29 | 21 | 50 | 2021 | 2021 | R16
160528245721 | 164387245721 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-14 | 2021-06-14 | 2021-08-28 |  | 2021-10-25 | Underground | R16 | 2021-09-14 | 1 | 55 | 12 | 30 | 96 | 2021 | 2021 | R16
168075239134 | 161245239134 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-15 | 2021-07-15 | 2021-07-15 |  | 2021-09-10 | Overhead | R16 | 2021-08-17 | 1 |  | 24 | 19 | 42 | 2021 | 2021 | R16
165039239858 | 161770239858 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-18 | 2021-07-18 | 2021-07-21 |  | 2022-03-28 | Overhead | R16 |  | 0 | 3 |  |  | 181 | 2021 | 2022 | R16
161863237237 | 164747237237 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-15 | 2021-06-17 | 2021-06-30 |  | 2021-09-10 | Underground | R16 | 2021-08-16 | 3 | 10 | 34 | 20 | 64 | 2021 | 2021 | R16
167798241052 | 161611241052 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-16 | 2021-07-16 | 2021-07-28 | 2021-10-27 | 2021-11-10 | Underground | R16 | 2021-10-27 | 1 | 9 | 66 | 11 | 84 | 2021 | 2021 | R16
167161239490 | 162011239490 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-19 | 2021-07-19 | 2021-07-19 | 2021-10-07 | 2021-11-13 | Overhead | R16 | 2021-10-07 | 1 |  | 59 | 27 | 85 | 2021 | 2021 | R16
166314242257 | 162125242257 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-20 | 2021-08-04 | 2021-08-06 |  | 2021-10-25 | Underground | R16 | 2021-08-23 | 12 | 3 | 12 | 46 | 70 | 2021 | 2021 | R16
165085234361 | 163364234361 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-09 | 2021-06-09 | 2021-06-09 | 2021-10-05 | 2022-02-07 | Overhead | R16 | 2021-10-05 | 1 |  | 85 | 90 | 174 | 2021 | 2022 | R16
160564234111 | 163145234111 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-09 | 2021-06-09 | 2021-06-09 | 2021-06-14 | 2021-08-23 | Overhead | R16 | 2021-06-14 | 1 |  | 4 | 51 | 54 | 2021 | 2021 | R16
169656237799 | 163445237799 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-09 | 2021-06-25 | 2021-07-06 |  | 2021-09-10 | Underground | R16 | 2021-08-17 | 13 | 8 | 31 | 19 | 68 | 2021 | 2021 | R16
165150239844 | 162118239844 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2021-09-21 | 2021-10-28 | Overhead | R16 | 2021-09-21 | 1 |  | 46 | 28 | 73 | 2021 | 2021 | R16
165299238910 | 167941238910 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-29 | 2021-06-29 | 2021-07-14 | 2021-09-15 | 2021-09-17 | Underground | R16 | 2021-09-15 | 1 | 12 | 46 | 3 | 59 | 2021 | 2021 | R16
164345238532 | 160553238532 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-13 | 2021-07-13 | 2021-07-13 | 2021-08-19 | 2022-10-17 | Overhead | R16 | 2021-08-19 | 1 |  | 28 | 303 | 330 | 2021 | 2022 | R16
169674238152 | 168785238152 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2021-07-06 | 2021-07-06 | 2021-10-28 | 2021-12-02 | 2021-09-10 | Underground | R16 | 2021-12-02 | 1 | 83 | 26 |  | 49 | 2021 | 2021 | R16
164328238777 | 167106238777 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-25 | 2021-07-13 | 2021-07-13 |  | 2021-10-25 | Overhead | R16 | 2021-07-23 | 13 |  | 9 | 67 | 87 | 2021 | 2021 | R16
168572238097 | 162938238097 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-08 | 2021-07-08 | 2021-07-08 |  | 2022-02-09 | Underground | R16 | 2022-01-06 | 23 |  | 131 | 25 | 177 | 2021 | 2022 | R16
162109240345 | 167905240345 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-29 | 2021-07-23 | 2021-07-23 | 2021-09-10 | 2021-10-25 | Overhead | R16 | 2021-09-10 | 19 |  | 36 | 32 | 85 | 2021 | 2021 | R16
166319238385 | 169998238385 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-09 | 2021-07-09 | 2021-07-09 | 2021-12-29 | 2022-02-10 | Overhead | R16 | 2021-12-29 | 1 |  | 124 | 32 | 155 | 2021 | 2022 | R16
169375236013 | 162929236013 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-08 | 2021-06-22 | 2021-06-22 |  | 2021-11-18 | Overhead | R16 | 2021-10-27 | 11 |  | 92 | 17 | 118 | 2021 | 2021 | R16
160570236550 | 167027236550 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-25 | 2021-06-25 | 2021-06-25 |  | 2021-10-25 | Overhead | R16 | 2021-07-22 | 1 |  | 20 | 68 | 87 | 2021 | 2021 | R16
168776235305 | 165048235305 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2021-07-27 | 2021-08-23 | Overhead | R16 | 2021-07-27 | 1 |  | 30 | 20 | 49 | 2021 | 2021 | R16
169672242912 | 164513242912 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-06-14 | 2021-06-25 | 2021-08-10 | 2022-01-14 | 2022-03-08 | Underground | R16 | 2022-01-14 | 10 | 33 | 114 | 38 | 192 | 2021 | 2022 | R16
166205242921 | 166430242921 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-22 | 2021-06-22 | 2021-08-10 |  | 2021-11-09 | Overhead | R16 | 2021-10-11 | 1 | 36 | 45 | 22 | 101 | 2021 | 2021 | R16
162189243880 | 164860243880 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-06-15 | 2021-08-16 | 2021-08-16 |  | 2022-10-21 | Underground | R16 | 2022-08-23 | 45 |  | 267 | 44 | 354 | 2021 | 2022 | R16
167422240277 | 169989240277 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-09 | 2021-07-23 | 2021-07-23 |  | 2021-10-25 | Overhead | R16 | 2021-09-16 | 11 |  | 40 | 28 | 77 | 2021 | 2021 | R16
161726237111 | 162678237111 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-07 | 2021-06-29 | 2021-06-29 | 2021-06-30 | 2021-10-27 | Overhead | R16 | 2021-06-30 | 17 |  | 2 | 86 | 103 | 2021 | 2021 | R16
166702281758 | 166567281758 | NON-RESIDENTIAL - MISCELLANEOUS | UG R16 RESD AND NON RESD UD | Commercial | 2021-06-23 | 2021-06-23 | 2022-06-07 | 2022-09-12 | 2023-05-26 | Underground | R16 | 2022-09-12 | 1 | 250 | 70 | 185 | 503 | 2021 | 2023 | R16
164738239863 | 162331239863 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-20 | 2021-07-20 | 2021-07-20 | 2021-08-26 | 2021-10-25 | Overhead | R16 | 2021-08-26 | 1 |  | 28 | 43 | 70 | 2021 | 2021 | R16
160354237326 | 168064237326 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-30 | 2021-06-30 | 2021-06-30 | 2021-10-15 | 2021-10-18 | Overhead | R16 | 2021-10-15 | 1 |  | 78 | 2 | 79 | 2021 | 2021 | R16
164230237295 | 161504237295 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 RESD AND NON RESD US | Residential | 2021-06-02 | 2021-06-02 | 2021-07-01 |  | 2021-11-09 | Underground | R16 | 2021-10-05 | 1 | 22 | 69 | 26 | 115 | 2021 | 2021 | R16
162401243348 | 165393243348 | NON-RESIDENTIAL - MISCELLANEOUS | OH R16 RES NON RES OS | Commercial | 2021-06-17 | 2021-06-18 | 2021-08-12 | 2021-08-18 | 2021-09-13 | Overhead | R16 | 2021-08-18 | 2 | 40 | 5 | 19 | 63 | 2021 | 2021 | R16
161105237314 | 167870237314 | RESIDENTIAL - SINGLE FAMILY DETACHED | R16 ELEC SUBDIVISION | Residential Subdivision | 2021-06-29 | 2021-06-29 | 2021-07-01 |  | 2022-10-21 | Underground | R16 |  | 1 | 3 |  |  | 344 | 2021 | 2022 | R16
166710239543 | 161519239543 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-16 | 2021-07-19 | 2021-07-19 |  | 2021-10-28 | Overhead | R16 | 2021-09-27 | 2 |  | 51 | 24 | 75 | 2021 | 2021 | R16
164713237374 | 168337237374 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-07-28 | 2021-08-23 | Overhead | R16 | 2021-07-28 | 1 |  | 20 | 19 | 38 | 2021 | 2021 | R16
160799234231 | 163237234231 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-09 | 2021-06-09 | 2021-06-09 | 2021-06-11 | 2021-11-03 | Overhead | R16 | 2021-06-11 | 1 |  | 3 | 104 | 106 | 2021 | 2021 | R16
165898264892 | 160461264892 | CUSTOMER UPGRADE IN SERVICE | R16 REWIRE UPGRADE US | Residential | 2021-07-12 | 2021-07-12 | 2022-01-14 |  | 2022-03-08 | Underground | R16 | 2022-02-11 | 1 | 135 | 21 | 18 | 172 | 2021 | 2022 | R16
169599237279 | 164530237279 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2021-06-14 | 2021-07-01 | 2021-07-01 |  | 2022-03-11 | Overhead | R16 | 2022-02-15 | 14 |  | 164 | 19 | 195 | 2021 | 2022 | R16
168891198305 | 162098198305 | CUSTOMER UPGRADE IN SERVICE | OH REWIRE OS | Residential | 2020-04-16 | 2020-07-24 | 2020-07-24 |  | 2021-01-21 | Overhead | R16 | 2020-10-05 | 72 |  | 52 | 79 | 201 | 2020 | 2021 | R16